## A3- Land Parcel Status
A3- Land Parcel Status
SL No | District | Scheme Name | Scheme TSM Code | Scheme SM Code | Scheme Category | Scheme Coverage Type | Block | Village | Location | Purpose | Type | J.L. No. | Khatian No. | Plot No. | Area (in decimal) | Status | Remarks
1 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-II to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte..(TSM/009184,SM/10268) | TSM/009184 | SM/10268 | Augmentation | MVS | Chapra | Hatisala | AIRP | AIRP | Private | 1 | 8626 | 1156 | 41 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- 3913/PHE/1L-30/2022 Dated- 19/01/2023
2 | NADIA | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District(TSM/007073,SM/08127) | TSM/007073 | SM/08127 | Retrofitting | MVS | Karimpur-I | Madhugari | null | OHR | Vested | 108 | 9721 | 0 | 0 | Identified | null
3 | NADIA | HRIDAYPUR PIPED WATER SUPPLY SCHEME(TSM/012015,SM/12624) | TSM/012015 | SM/12624 | New | MVS | Chapra | Fulbari | 2nd Tube well Site | Pump House | Donated | 8 | 296 | 110 | 0 | Identified | null
4 | NADIA | Augmentation of ground water based Dhoradaha PWSS to accommodate FHTC in Karimpur-II Block with in Nadia District under Nadia Division,PHE Dte.(TSM/009587,SM/10083) | TSM/009587 | SM/10083 | Augmentation | MVS | Karimpur-II | Monoharpur | 3rd Tube Well | Pump House | Donated | 4 | 575 | 477 | 3 | Possessed | Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2023 and Registration done
5 | NADIA | HRIDAYPUR PIPED WATER SUPPLY SCHEME(TSM/012015,SM/12624) | TSM/012015 | SM/12624 | New | MVS | Chapra | Fulbari | Head Work Site | OHR | Vested | 8 | 1 | 159 | 0 | Possessed | mutation Done for 2nd tube well site & Proposal for IDT submitted to the ADM LR. Vide Memo No. 102/NACD-II,dated-15.12.2022
6 | NADIA | PANCHDARA ABHYNAGAR PIPED W/S SCHEME(TSM/008657,SM/10613) | TSM/008657 | SM/10613 | New | MVS | Tehatta-II | Panchdara Abhaynagar | HW Site | OHR | Donated | 20 | 9593 | 2618 | 0 | Possessed | null
7 | NADIA | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District(TSM/016126,SM/14063) | TSM/016126 | SM/14063 | New | MVS | Ranaghat-I | Gangni | 2nd Tube Well | Pump House | Donated | 1 | 0 | 33 | 3 | Possessed | Registration Done
8 | NADIA | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte.(TSM/011112,SM/11490) | TSM/011112 | SM/11490 | Augmentation | MVS | Chakdah | Kulia (P) (CT) | null | OHR | Vested | 83 | 6 | 0 | 12 | Identified | null
9 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR GEDE PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA(TSM/010321,SM/10573) | TSM/010321 | SM/10573 | Augmentation | SVS | Krishnaganj | Gede | OHR | OHR | Private | 51 | 3426 | 3582 | 18 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- PHE/242/1L-45/2022 Dated- 20/01/2023
10 | NADIA | HATKHOLA PIPED WATER SUPPLY SCHEME(TSM/008804,SM/10404) | TSM/008804 | SM/10404 | New | SVS | Chapra | Hatkhola | Head Work Site | OHR | Donated | 21 | 1040 | 1968 | 0 | Possessed | null
11 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016206,SM/15522) | TSM/016206 | SM/15522 | Augmentation | SVS | Santipur | Phulia (CT) | OHR | OHR | Vested | 54 | 1 | 326 | 19 | Possessed | Possetion Done
12 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011336,SM/11870) | TSM/011336 | SM/11870 | Augmentation | MVS | Kaliganj | Ashachia | OHR | OHR | Vested | 55 | 1 | 196 | 30 | Possessed | Sent to The Secretary Land Reforms Commission Vide Memo No- 4574/V/25-Land-DT/PWSS/2021 Dated-13/10/22 by ADM, (L & LR), Nadia Return back after Approval Vide Memo No- 1223-GE (M)/24012/2/2023 Dated- 30/03/2023 Letter for Hand Over Vide Memo No- 2099/V/25- Lands/ IDT/PWSS/2021 Dated- 26/04/2023
13 | NADIA | Dhopahat Piped Water Supply Scheme(TSM/008625,SM/09942) | TSM/008625 | SM/09942 | New | MVS | Tehatta-I | Dhopahat | HW Site | OHR | Vested | 28 | 1 | 0 | 1 | Possessed | null
14 | NADIA | RAJAPUR PIPED WATER SUPPLY SCHEME(TSM/011903,SM/11966) | TSM/011903 | SM/11966 | New | MVS | Tehatta-I | Jayrampur | HW Site | OHR | Donated | 64 | 287 | 750 | 0 | Identified | null
15 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte(TSM/010969,SM/11507) | TSM/010969 | SM/11507 | Augmentation | MVS | Krishnagar-I | Subarna Behar | OHR | OHR | Private | 54 | 18800 | 2585 | 13 | Identified | Cabinet Approval Made & DPR Prepared (Phase-II) Notification for Cabinet Approval Vide Memo No- PHE/341/1L-44/2022 Dated- 06/02/2023
16 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011479,SM/11742) | TSM/011479 | SM/11742 | Augmentation | MVS | Nakashipara | Teghari | Pump House | Pump House | Vested | 89 | 1 | 2506 | 9 | Possessed | Sent to LR department and returned back with a querry and Sent to B L & LRO Nakashipara for No- encumbrance Certificate Vide Memo No- 135/V/25-Land-DT/PWSS/2021 Dated- 3/1/23 Sent to LR department and returned back with a querry and Sent to B L & LRO Nakashipara for Vide Memo No- 135/V/25-Land-DT/PWSS/2021 Dated- 3/1/23
17 | NADIA | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte.(TSM/015030,SM/14243) | TSM/015030 | SM/14243 | New | MVS | Ranaghat-II | Debipur Chak | null | OHR | Private | 13 | 0 | 0 | 0 | Not Identified | null
18 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte(TSM/010969,SM/11507) | TSM/010969 | SM/11507 | Augmentation | MVS | Krishnagar-I | Subarna Behar | AIRP | AIRP | Private | 54 | 18792 | 2585 | 13 | Identified | Cabinet Approval Made & DPR Prepared (Phase-II) Notification for Cabinet Approval Vide Memo No- PHE/340/1L-49/2022 Dated- 06/02/2023
19 | NADIA | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME(TSM/014576,SM/12419) | TSM/014576 | SM/12419 | New | SVS | Krishnagar-I | Chakdignagar | 2nd Tube well Site | Pump House | Private | 118 | 0 | 0 | 0 | Possessed | null
20 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR TUNGI PWSS BLOCK: KRISHNAGANJ DISTRICT: NADIA(TSM/011231,SM/12363) | TSM/011231 | SM/12363 | Augmentation | MVS | Krishnaganj | Tungi | OHR | OHR | Private | 55 | 1297 | 357 | 33 | Identified | Cabinet Approval received vide memo no. PHE/1428/1L-24/2023 dt. 06/06/2023
21 | NADIA | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte.(TSM/015030,SM/14243) | TSM/015030 | SM/14243 | New | MVS | Ranaghat-II | Hijuli (CT) | null | OHR | Private | 155 | 450 | 20 | 34 | Identified | null
22 | NADIA | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI PWSS ZONE -IXB TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/011233,SM/11512) | TSM/011233 | SM/11512 | Augmentation | MVS | Karimpur-II | Dakshin Gopalpur | OHR | OHR | Donated | 32 | 671 | 495 | 29 | Possessed | 1) Registration Done 2) Mutation Done (New ROR No- 5606)
23 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011466,SM/12373) | TSM/011466 | SM/12373 | Augmentation | MVS | Nakashipara | Kshidirpur (CT) | OHR | OHR | Vested | 48 | 9582 | 1012 | 42 | Possessed | 1) Regulating Market (DM/ Nadia) 2) NOC Received from Seccretary, Nadia Zilla Regulated Market Committee Vide Memo No- 1104 Dated- 19/12/2022
24 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte.(TSM/009169,SM/09814) | TSM/009169 | SM/09814 | Augmentation | MVS | Karimpur-I | Mathurapur | null | OHR | Vested | 75 | 283 | 0 | 0 | Possessed | null
25 | NADIA | BINODNAGAR PIPED WATER SUPPLY SCHEME(TSM/011888,SM/11965) | TSM/011888 | SM/11965 | New | MVS | Tehatta-I | Binodnagar | 2nd TW Site | Pump House | Donated | 71 | 3311 | 282 | 0 | Identified | null
26 | NADIA | KHASPU PIPED WATER SUPPLY SCHEME(TSM/009215,SM/10402) | TSM/009215 | SM/10402 | New | MVS | Tehatta-I | Khaspu | HW Site | OHR | Vested | 33 | 1 | 1805 | 0 | Possessed | null
27 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011358,SM/11834) | TSM/011358 | SM/11834 | Augmentation | MVS | Kaliganj | Palasi | OHR | OHR | Vested | 4 | 4236 | 4236 | 25 | Possessed | null
28 | NADIA | PANINALA PIPED WATER SUPPLY SCHEME(TSM/008886,SM/10403) | TSM/008886 | SM/10403 | New | MVS | Krishnagar-I | Paninala | 2nd TW Site | Pump House | Donated | 43 | 950 | 389 | 0 | Identified | null
29 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017108,SM/18661) | TSM/017108 | SM/18661 | Augmentation | MVS | Chakdah | Silinda | null | OHR | Private | 167 | 1302 | 899 | 33 | Identified | null
30 | NADIA | KARUIGACHHI PIPED WATER SUPPLY SCHEME(TSM/009022,SM/10106) | TSM/009022 | SM/10106 | New | MVS | Chapra | Karuigachhi | 2nd Tube well Site | Pump House | Donated | 59 | 362 | 126 | 0 | Possessed | null
31 | NADIA | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/011238,SM/13039) | TSM/011238 | SM/13039 | Augmentation | MVS | Karimpur-II | Dogachhi | 2nd Tube Well | Pump House | Donated | 1 | 1475 | 3304 | 8 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2023 2) Registration Done Mutation Done
32 | NADIA | SANATANPUR PIPED WATER SUPPLY SCHEME(TSM/008959,SM/10409) | TSM/008959 | SM/10409 | New | MVS | Hanskhali | Sanatanur | H/W Site & 2nd tube well site | OHR | Donated | 24 | 995 | 658 | 0 | Identified | Registration Completed on 22.11.2022 for H/W Site & Registration Completed on 01.12.2022 for 2nd TW site
33 | NADIA | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010569,SM/11510) | TSM/010569 | SM/11510 | Augmentation | MVS | Hanskhali | Patuli (CT) | AIRP | AIRP | Vested | 43 | 2632 | 417 | 16 | Possessed | null
34 | NADIA | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010351,SM/10522) | TSM/010351 | SM/10522 | Augmentation | MVS | Karimpur-II | Chandpur | null | OHR | Vested | 52 | 1012 | 0 | 0 | Identified | null
35 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia(TSM/009818,SM/11918) | TSM/009818 | SM/11918 | Augmentation | MVS | Tehatta-II | Hanspukuria | HEAD WORK SITE | AIRP | Donated | 35 | 272 | 871 | 50 | Possessed | 1) Received from ADM (LR) Vide Memo No- 1943/V/25 Land/ DT/PWSS/2021 Dated- 02/06/2023. Regintration Done. 2) Registration Done 3) ROR Received
36 | NADIA | Surface Water Based Piped Water Supply Scheme Saguna Zone-VI (Part-I) for Arsenic Affected Areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE. Dte.(TSM/011112,SM/11490) | TSM/011112 | SM/11490 | Augmentation | MVS | Chakdah | Krishnapur | null | OHR | Vested | 81 | 200 | 0 | 12 | Identified | null
37 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-I to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte.(TSM/009177,SM/09811) | TSM/009177 | SM/09811 | Augmentation | MVS | Karimpur-I | Ber Ramchandrapur | null | OHR | Vested | 76 | 956 | 0 | 0 | Possessed | null
38 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011360,SM/11835) | TSM/011360 | SM/11835 | Augmentation | MVS | Kaliganj | Bharatpur | OHR | OHR | Vested | 30 | 1 | 367 | 30 | Possessed | Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 2083/V/25-Land-DT/PWSS/2021 Dated- 08/06/22 by ADM, (L & LR), Nadia vide Memo No- 2938/V/25-Land /DT/PWSS/2021 Dated- 21/07/2022
39 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011457,SM/11842) | TSM/011457 | SM/11842 | Augmentation | MVS | Nakashipara | Sonadanga | OHR | OHR | Donated | 23 | 441 | 633 | 29 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2024 2) Registration Done 3) Mutation Done
40 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016206,SM/15522) | TSM/016206 | SM/15522 | Augmentation | SVS | Santipur | Phulia (CT) | OHR | OHR | Vested | 54 | 1 | 329 | 8 | Possessed | Possetion Done
41 | NADIA | Detailed Project Report for Dakhin Bishnupur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/015021,SM/14242) | TSM/015021 | SM/14242 | New | MVS | Ranaghat-I | Dakshin Bishnupur | null | OHR | Vested | 123 | 1 | 330 | 33 | Identified | null
42 | NADIA | Detailed Project Report for Birnagar (Part) Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/015176,SM/14196) | TSM/015176 | SM/14196 | New | SVS | Ranaghat-I | Birnagar (P) | null | OHR | Private | 19 | 11853 | 46 | 23 | Identified | null
43 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Krishnaganj Majhdia to Accommodate FHTC in Krishnaganj Block of Nadia District under Nadia Division, PHE Dte.(TSM/009178,SM/09799) | TSM/009178 | SM/09799 | Augmentation | MVS | Krishnaganj | Krishna Ganj | 3rd Tube Well | Pump House | Donated | 39 | 2390 | 0 | 4 | Identified | Registration Done
44 | NADIA | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision)(TSM/005040,SM/16182) | TSM/005040 | SM/16182 | New | MVS | Nabadwip | Char Maijdia (CT) | 3rd Tube Well | Pump House | Private | 19 | 1455 | 32 | 5 | Identified | Sent for Cabinet Approval
45 | NADIA | BARUIHUDA PIPED WATER SUPPLY SCHEME(TSM/015027,SM/14423) | TSM/015027 | SM/14423 | New | SVS | Krishnagar-I | Baruihuda (CT) | 2nd Tube well Site | Pump House | Private | 91 | 12883 | 135 | 0 | Possessed | null
46 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011356,SM/11738) | TSM/011356 | SM/11738 | Augmentation | MVS | Kaliganj | Bathangachhi | OHR | OHR | Donated | 27 | 344 | 659 | 24 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2023 2) Registration Done 3) Mutation Done
47 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011298,SM/11550) | TSM/011298 | SM/11550 | Augmentation | MVS | Krishnagar-II | Khajuri | OHR | OHR | Private | 18 | 3208 | 142 | 30 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I)Notification for Cabinet Approval Vide Memo No- PHE/239/1L-31/2022 Dated- 20/01/2023
48 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte.(TSM/010078,SM/10598) | TSM/010078 | SM/10598 | Augmentation | MVS | Nabadwip | Gadkhali | OHR | OHR | Donated | 28 | 1257 | 1318 | 39 | Possessed | 1) Registration Done 2) Mutation Done
49 | NADIA | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District(TSM/007073,SM/08127) | TSM/007073 | SM/08127 | Retrofitting | MVS | Karimpur-I | Madhugari | null | OHR | Vested | 108 | 9721 | 0 | 0 | Identified | null
50 | NADIA | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/014920,SM/14234) | TSM/014920 | SM/14234 | New | SVS | Ranaghat-II | Raynagar | null | OHR | Private | 161 | 3851 | 467 | 66 | Identified | null
51 | NADIA | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) PHASE-II TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/011961,SM/11872) | TSM/011961 | SM/11872 | Augmentation | MVS | Karimpur-II | Hatishala | OHR | OHR | Donated | 58 | 391 | 561 | 26 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2941/V/25 Land/ DT/PWSS/2021 Dated- 21/07/2022 2) Registration Done 3) Mutation Done (New ROR No- 1085)
52 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016118,SM/18374) | TSM/016118 | SM/18374 | Augmentation | SVS | Santipur | Phulia (CT) | Pump House | Pump House | Vested | 54 | 1 | 1158 | 3 | Possessed | Sent to Joint Secretatary L & LR Dept by the ADM (L R) vide Memo No- 4989/V/25 Land/ DT/PWSS/2021 Dated- 16/11/2022 Letter for handing Over Viide Memo no- 928/V/25-LANDS/DT/PWSS/2021 Dated- 22/02/23 Possetion Done
53 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Chakdah | Madanpur (CT) | null | OHR | Private | 94 | 0 | 0 | 0 | Not Identified | null
54 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Uttar Brahma Pur | null | OHR | Private | 30 | 3102 | 1045 | 28 | Identified | null
55 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte.(TSM/009185,SM/10067) | TSM/009185 | SM/10067 | Augmentation | MVS | Chapra | Bangaljhi | 3rd Tube Well | Pump House | Vested | 33 | 1 | 1394 | 4 | Possessed | Sent to Principal Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 216/V/25-Land-DT/PWSS/2021 Dated- 27/01/22 by ADM, (L & LR), Nadia.Handmover of land initiated from ADM (LR) after getting approval vide Memo No- 2938/V/25-Land /DT/PWSS/2021 Dated- 21/07/2022
56 | NADIA | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BADKULLA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE.(TSM/019946,SM/15276) | TSM/019946 | SM/15276 | Augmentation | MVS | Hanskhali | Badkulla | OHR | OHR | Private | 44 | 5423 | 3136 | 33 | Identified | Sent for Cabinet Approval
57 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR BAGULA PWSS ZONE-I BLOCK: HANSKHALI DISTRICT: NADIA(TSM/011393,SM/11740) | TSM/011393 | SM/11740 | Augmentation | SVS | Hanskhali | Bagula | OHR | OHR | Vested | 69 | 1 | 1 | 10 | Possessed | null
58 | NADIA | AUGMENTATION OF GROUND WATER BASED KARIMPUR-JALANGI ZONE-VIII PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010317,SM/10473) | TSM/010317 | SM/10473 | Augmentation | MVS | Karimpur-II | Barbakpur | 3rd Tube Well | Pump House | Donated | 38 | 6265 | 2786 | 5 | Possessed | Registration Done
59 | NADIA | AUGMENTATION OF GROUND WATER BASED DOGACHI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/011238,SM/13039) | TSM/011238 | SM/13039 | Augmentation | MVS | Karimpur-II | Dogachhi | OHR | OHR | Donated | 1 | 3038 | 2656 | 25 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2023 2) Registration Done Mutation Done (New ROR No- 25738)
60 | NADIA | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte.(TSM/015030,SM/14243) | TSM/015030 | SM/14243 | New | MVS | Ranaghat-II | Hijuli (CT) | null | OHR | Private | 155 | 0 | 0 | 0 | Not Identified | null
61 | NADIA | Indrakpur Piped Water Supply Scheme.(TSM/005078,SM/13820) | TSM/005078 | SM/13820 | New | MVS | Nabadwip | Sankarpur | OHR | OHR | Donated | 2 | 1482 | 155 | 25 | Possessed | Registration Done
62 | NADIA | KHASPU PIPED WATER SUPPLY SCHEME(TSM/009215,SM/10402) | TSM/009215 | SM/10402 | New | MVS | Tehatta-I | Khaspu | 2nd TW Site | Pump House | Vested | 33 | 1 | 0 | 0 | Possessed | null
63 | NADIA | AUGMENTATION GROUND WATER BASED WATER SUPPLY OF BADKULLA PWSS ZONE 1 TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010567,SM/13791) | TSM/010567 | SM/13791 | Augmentation | MVS | Hanskhali | Badkulla | OHR | OHR | Donated | 44 | 5423 | 3136 | 33 | Possessed | null
64 | NADIA | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District(TSM/007109,SM/08050) | TSM/007109 | SM/08050 | Retrofitting | MVS | Krishnagar-I | Jahangirpur | null | OHR | Vested | 88 | 1614 | 0 | 0 | Identified | null
65 | NADIA | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District(TSM/016126,SM/14063) | TSM/016126 | SM/14063 | New | MVS | Ranaghat-I | Gangni | HEAD WORK SITE-III | OHR | Donated | 1 | 0 | 23 | 8 | Possessed | Registration Done
66 | NADIA | BARUIHUDA PIPED WATER SUPPLY SCHEME(TSM/015027,SM/14423) | TSM/015027 | SM/14423 | New | SVS | Krishnagar-I | Baruihuda (CT) | Head Work Site | OHR | Private | 91 | 144 | 1061 | 0 | Possessed | null
67 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme For CHAPRA BANGALJHI to Accommodate FHTC in Chapra Block of Nadia District under Nadia Division, PHE Dte.(TSM/009185,SM/10067) | TSM/009185 | SM/10067 | Augmentation | MVS | Chapra | Bangaljhi | 4th Tube Well | Pump House | Private | 33 | 6408 | 3015 | 4 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- 224/PHE/1L-27/2022 Dated- 19/01/2023
68 | NADIA | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District(TSM/016126,SM/14063) | TSM/016126 | SM/14063 | New | MVS | Ranaghat-I | Gangni | HEAD WORK SITE-II | OHR | Donated | 1 | 0 | 23 | 8 | Possessed | Registration Done
69 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016206,SM/15522) | TSM/016206 | SM/15522 | Augmentation | SVS | Santipur | Phulia (CT) | 2nd T/W | Pump House | Private | 54 | 742 | 233 | 3 | Identified | Cabinet Approval received vide memo no. PHE/2792/1L-23/2023 dt. 14/09/2023
70 | NADIA | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District(TSM/007109,SM/08050) | TSM/007109 | SM/08050 | Retrofitting | MVS | Krishnagar-I | Paschimbhatjangla | null | OHR | Vested | 90 | 3541 | 0 | 0 | Identified | null
71 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016119,SM/13878) | TSM/016119 | SM/13878 | Augmentation | SVS | Santipur | Phulia (CT) | OHR | Intake | Vested | 54 | 7152 | 0 | 16 | Identified | null
72 | NADIA | SIKRA PIPED WATER SUPPLY SCHEME(TSM/008800,SM/10410) | TSM/008800 | SM/10410 | New | MVS | Chapra | Dukria | Head Work Site | OHR | Donated | 22 | 132 | 1978 | 0 | Possessed | null
73 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for SUBARNABIHAR ZONE-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte(TSM/010969,SM/11507) | TSM/010969 | SM/11507 | Augmentation | MVS | Krishnagar-I | Subarna Behar | 2nd Tube Well | Pump House | Private | 54 | 272 | 2264 | 8 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- PHE/241/1L-42/2022 Dated- 20/01/2023
74 | NADIA | MADHUPUR PIPED WATER SUPPLY SCHEME(TSM/009069,SM/10103) | TSM/009069 | SM/10103 | New | MVS | Chapra | Fulkalmi | 2nd Tube well site | Pump House | Donated | 45 | 550 | 564 | 0 | Possessed | null
75 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/C (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011351,SM/11831) | TSM/011351 | SM/11831 | Augmentation | MVS | Kaliganj | Dakshin Hajrapota | OHR | OHR | Donated | 99 | 1251 | 2807 | 33 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2024 2) Registration Done 3) Mutation Done
76 | NADIA | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision)(TSM/005040,SM/16182) | TSM/005040 | SM/16182 | New | MVS | Nabadwip | Char Maijdia (CT) | 2nd Tube Well | Pump House | Private | 19 | 2009 | 209 | 5 | Identified | Cabinet Approval received vide memo no. PHE/2502/1L-38/2022 dt. 22/08/2023
77 | NADIA | KARUIGACHHI PIPED WATER SUPPLY SCHEME(TSM/009022,SM/10106) | TSM/009022 | SM/10106 | New | MVS | Chapra | Karuigachhi | Head Work Site | OHR | Donated | 59 | 518 | 351 | 0 | Possessed | null
78 | NADIA | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME(TSM/014576,SM/12419) | TSM/014576 | SM/12419 | New | SVS | Krishnagar-I | Chakdignagar | Head Work Site | OHR | Private | 118 | 369 | 31 | 0 | Possessed | null
79 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017108,SM/18661) | TSM/017108 | SM/18661 | Augmentation | MVS | Chakdah | Bagdob | null | OHR | Private | 148 | 150 | 149 | 41 | Identified | null
80 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017108,SM/18661) | TSM/017108 | SM/18661 | Augmentation | MVS | Chakdah | Khorgachhi | null | OHR | Private | 115 | 669 | 926 | 33 | Identified | null
81 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Chakdah | Narapati Para | null | OHR | Vested | 103 | 1 | 1053 | 33 | Identified | null
82 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017108,SM/18661) | TSM/017108 | SM/18661 | Augmentation | MVS | Chakdah | Kundulia | null | OHR | Private | 135 | 135 | 6154 | 28 | Identified | null
83 | NADIA | AUGMENTATION OF GROUND WATER BASED KARIMPURJALANGI PWSS ZONE-X(B) TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010318,SM/10737) | TSM/010318 | SM/10737 | Augmentation | MVS | Karimpur-II | Hatishala | OHR | OHR | Donated | 58 | 391 | 561 | 26 | Possessed | Registration & Mutation Done
84 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Par Majdia | null | OHR | Private | 17 | 443 | 351 | 24 | Identified | null
85 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Uttar Datta Para | null | OHR | Private | 25 | 242 | 975 | 33 | Identified | null
86 | NADIA | Anjangarh Pipe Water Supply Scheme in Ranaghat-I Block of Nadia District(TSM/016126,SM/14063) | TSM/016126 | SM/14063 | New | MVS | Ranaghat-I | Gangni | HEAD WORK SITE-I | OHR | Donated | 1 | 0 | 23 | 8 | Possessed | Registration Done
87 | NADIA | Augmentation of ground water based Andharkota PWSS to accommodate FHTC in Karimpur-I Block within Nadia District under Nadia Division(TSM/009580,SM/10075) | TSM/009580 | SM/10075 | Augmentation | MVS | Karimpur-I | Andhar Kotha | 3rd Tube Well | Pump House | Donated | 111 | 1645 | 6956 | 29 | Possessed | Registration Done
88 | NADIA | Augmentation of Ground Water Based MAHISBATHAN Piped Water Supply Scheme for Block: Karimpur-II, Dist: Nadia(TSM/009819,SM/10076) | TSM/009819 | SM/10076 | Augmentation | MVS | Karimpur-II | Mahish Bathan | OHR | OHR | Vested | 41 | 1 | 2483 | 28 | Possessed | 1) Sent to Principal Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 184/V/25-Land-DT/PWSS/2021 Dated- 10/01/23 by ADM (L & LR), Nadia.
89 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte.(TSM/009182,SM/10269) | TSM/009182 | SM/10269 | Augmentation | MVS | Tehatta-II | Dhwapara | 2nd Tube Well | Pump House | Vested | 7 | 1 | 1369 | 5 | Possessed | Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 946/V/25-Land-DT/PWSS/2021 Dated- 22/03/22 by ADM, (L & LR), Nadia.Handmover of land initiated from ADM (LR) after getting approval vide Memo No- 2938/V/25-Land /DT/PWSS/2021 Dated- 21/07/2022 2) Possetion Completed
90 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Mahisunra(Phase-II) to accommodate FHTC in Nabadwip block of Nadia District under Nadia Division, PHE Dte.(TSM/010078,SM/10598) | TSM/010078 | SM/10598 | Augmentation | MVS | Nabadwip | Mohisunra | 4th Tube Well | Pump House | Donated | 30 | 6408 | 83 | 4 | Possessed | 1) Registration Done 2) Mutation Done
91 | NADIA | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte.(TSM/007544,SM/08666) | TSM/007544 | SM/08666 | Retrofitting | MVS | Karimpur-II | Chandpur | null | OHR | Vested | 52 | 1012 | 0 | 0 | Identified | null
92 | NADIA | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/018089,SM/18257) | TSM/018089 | SM/18257 | New | MVS | Ranaghat-I | Par Niamatpur | Intake | Intake | Private | 136 | 1098 | 1024 | 116 | Identified | null
93 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE III/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011296,SM/11610) | TSM/011296 | SM/11610 | Augmentation | MVS | Krishnagar-II | Mayaral | OHR | OHR | Vested | 47 | 1 | 667 | 26 | Possessed | 1) Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 830/V/25-Land-DT/PWSS/2021 Dated- 14/03/22 by ADM, (L & LR), Nadia.Handmover of land initiated from ADM (LR) after getting approval vide Memo No- 2938/V/25-Land /DT/PWSS/2021 Dated- 21/07/2022 2) Posession Completed
94 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte.(TSM/009971,SM/10416) | TSM/009971 | SM/10416 | Augmentation | MVS | Tehatta-I | Gopalpur | OHR | OHR | Donated | 96 | 663 | 1027 | 2850 | Possessed | Registration complete
95 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte(TSM/009180,SM/10037) | TSM/009180 | SM/10037 | Augmentation | MVS | Chapra | Bara Andulia | 3rd Tube Well | Pump House | Private | 3 | 937 | 3698 | 5 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- 225/PHE/1L-23/2022 Dated- 19/01/2023
96 | NADIA | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010354,SM/10518) | TSM/010354 | SM/10518 | Augmentation | MVS | Karimpur-II | Dharar | null | OHR | Vested | 70 | 442 | 0 | 0 | Possessed | null
97 | NADIA | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. (TSM/020321,SM/17205) | TSM/020321 | SM/17205 | Augmentation | MVS | Karimpur-I | Madhugari | null | OHR | Vested | 108 | 9721 | 0 | 0 | Identified | null
98 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017108,SM/18661) | TSM/017108 | SM/18661 | Augmentation | MVS | Chakdah | Garuimari | null | OHR | Private | 188 | 282 | 780 | 20 | Identified | null
99 | NADIA | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II)(TSM/009578,SM/10084) | TSM/009578 | SM/10084 | Augmentation | MVS | Karimpur-I | Madhugari | null | OHR | Vested | 108 | 9721 | 0 | 0 | Identified | null
100 | NADIA | KANAINAGAR PIPED WATER SUPPLY SCHEME(TSM/008951,SM/10406) | TSM/008951 | SM/10406 | New | MVS | Tehatta-I | Shrirampur | 2nd TW Site | Pump House | Donated | 61 | 4998 | 1960 | 0 | Identified | null
101 | NADIA | Manik Nagar Piped W/S Scheme(TSM/008673,SM/10407) | TSM/008673 | SM/10407 | New | MVS | Santipur | Manik Nagar | Head Work Site | OHR | Donated | 1 | 765 | 91 | 0 | Identified | null
102 | NADIA | MRIGI PIPED WATER SUPPLY SCHEME(TSM/008996,SM/10408) | TSM/008996 | SM/10408 | New | SVS | Tehatta-I | Mrigi | 2nd TW Site | Pump House | Donated | 69 | 1314 | 2429 | 0 | Possessed | null
103 | NADIA | Raynagar Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/014920,SM/14234) | TSM/014920 | SM/14234 | New | SVS | Ranaghat-II | Raynagar | null | OHR | Private | 161 | 3851 | 467 | 66 | Identified | null
104 | NADIA | PANINALA PIPED WATER SUPPLY SCHEME(TSM/008886,SM/10403) | TSM/008886 | SM/10403 | New | MVS | Krishnagar-I | Paninala | H/W Site | OHR | Donated | 43 | 1378 | 332 | 1 | Identified | Mutation Done
105 | NADIA | AUGMENTATION OF GROUND WATER BASED BADKULLA PWSS ZONE-II TO ACCOMMODATE FHTC IN HANSKHALI BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010569,SM/11510) | TSM/010569 | SM/11510 | Augmentation | MVS | Hanskhali | Patuli (CT) | OHR | OHR | Vested | 43 | 2646 | 417 | 16 | Possessed
106 | NADIA | BINODNAGAR PIPED WATER SUPPLY SCHEME(TSM/011888,SM/11965) | TSM/011888 | SM/11965 | New | MVS | Tehatta-I | Binodnagar | HW Site | OHR | Donated | 71 | 3757 | 948 | 0 | Identified | null
107 | NADIA | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/011235,SM/11513) | TSM/011235 | SM/11513 | Augmentation | MVS | Karimpur-I | Sundalpur | Pump House | Pump House | Donated | 129 | 0 | 0 | 7 | Possessed | Registration Done
108 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BERRAMCHANDRA PUR Zone-II to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte.(TSM/009169,SM/09814) | TSM/009169 | SM/09814 | Augmentation | MVS | Karimpur-I | Mathurapur | null | OHR | Vested | 75 | 284 | 0 | 0 | Possessed | null
109 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Chakdah | Sikarpur | null | OHR | Vested | 41 | 268 | 33 | 33 | Identified | null
110 | NADIA | PROVIDING FHTC BY AUGMENTATION OF PALASHIPARA PWSS BLOCK: TEHATTA-II DISTRICT: NADIA(TSM/010319,SM/10691) | TSM/010319 | SM/10691 | Augmentation | MVS | Tehatta-II | Palashipara | 3rd Tube Well | Pump House | Vested | 42 | 1 | 401 | 3 | Possessed | Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 945/V/25-Land-DT/PWSS/2021 Dated- 22/03/22 by ADM, (L & LR), Nadia.Handmover of land initiated from ADM (LR) after getting approval vide Memo No- 2938/V/25-Land /DT/PWSS/2021 Dated- 21/07/2022 2) Possetion Completed
111 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for HANSPUKURIA Block: Tehatta-II, Dist: Nadia(TSM/009818,SM/11918) | TSM/009818 | SM/11918 | Augmentation | MVS | Tehatta-II | Hanspukuria | 2nd Tube Well | Pump House | Donated | 35 | 4516 | 1645 | 3 | Possessed | 1) Received from ADM (LR) Vide Memo No- 1943/V/25 Land/ DT/PWSS/2021 Dated- 02/06/2023. Registration done. 2) Registration Done 3) ROR Received
112 | NADIA | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-I) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010351,SM/10522) | TSM/010351 | SM/10522 | Augmentation | MVS | Karimpur-II | Chandpur | null | OHR | Vested | 52 | 1012 | 0 | 0 | Identified | null
113 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Purba Satbaria | null | OHR | Private | 34 | 3851 | 467 | 15 | Identified | null
114 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Sekandarpur | null | OHR | Private | 35 | 1004 | 3575 | 31 | Identified | null
115 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Hari Puknaria | null | OHR | Private | 75 | 200 | 284 | 21 | Identified | null
116 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Singa | null | OHR | Vested | 81 | 1 | 1441 | 28 | Identified | null
117 | NADIA | PANCHDARA ABHYNAGAR PIPED W/S SCHEME(TSM/008657,SM/10613) | TSM/008657 | SM/10613 | New | MVS | Tehatta-II | Panchdara Abhaynagar | 3rd TW Site | Pump House | Donated | 20 | 791 | 0 | 0 | Possessed | null
118 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011343,SM/11735) | TSM/011343 | SM/11735 | Augmentation | MVS | Kaliganj | Ghorai Khetra | OHR | OHR | Vested | 111 | 1 | 791 | 25 | Possessed | Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 2083/V/25-Land-DT/PWSS/2021 Dated- 08/06/22 by ADM, (L & LR), Nadia and Sent to LR department and returned back with a querry and Sent to B L & LRO Nakashipara for Pukur ParVide Memo No- 135/V/25-Land-DT/PWSS/2021 Dated- 27/12/22
119 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE V/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011353,SM/11736) | TSM/011353 | SM/11736 | Augmentation | MVS | Kaliganj | Debagram | OHR | OHR | Vested | 60 | 1 | 324 | 30 | Possessed | Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 2083/V/25-Land-DT/PWSS/2021 Dated- 08/06/22 by ADM, (L & LR), Nadia Sent to DM, Nadia from Land Dept Vide Memo No- 5184-GE(M)/24012/336/2022 Dated- 15/12/22
120 | NADIA | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/015322,SM/14244) | TSM/015322 | SM/14244 | New | SVS | Ranaghat-II | Nasra (CT) | null | OHR | Vested | 156 | 1 | 0 | 33 | Identified | null
121 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for TIORKHALI to Accommodate FHTC in NabadwipBlock of Nadia District under Nadia Division, P.H.E. Dte.(TSM/010296,SM/10728) | TSM/010296 | SM/10728 | Augmentation | MVS | Nabadwip | Tiorkhali | 3rd Tube Well | Pump House | Vested | 15 | 1 | 488 | 3 | Identified | 1) Sent to Principal Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 215/V/25-Land-DT/PWSS/2021 Dated- 27/01/22 by ADM (L & LR), Nadia. Handmover of land initiated from ADM (LR) after getting approval vide Memo No- 2938/V/25-Land /DT/PWSS/20 2) Possetion Completed
122 | NADIA | JITPUR PIPED WATER SUPPLY SCHEME(TSM/008994,SM/10405) | TSM/008994 | SM/10405 | New | MVS | Tehatta-I | Jitpur | HW Site | AIRP | Donated | 99 | 3252 | 1929 | 0 | Identified | null
123 | NADIA | KANAINAGAR PIPED WATER SUPPLY SCHEME(TSM/008951,SM/10406) | TSM/008951 | SM/10406 | New | MVS | Tehatta-I | Shrirampur | HW Site | OHR | Donated | 61 | 174 | 1316 | 0 | Identified | null
124 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011484,SM/12376) | TSM/011484 | SM/12376 | Augmentation | MVS | Nakashipara | Gachha | OHR | OHR | Donated | 100 | 100 | 4431 | 29 | Identified | Registration & Possetion Pending
125 | NADIA | Manik Nagar Piped W/S Scheme(TSM/008673,SM/10407) | TSM/008673 | SM/10407 | New | MVS | Santipur | Manik Nagar | 2nd Tube well Site | Pump House | Donated | 1 | 765 | 1053 | 0 | Identified | null
126 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Nathna Zone-II to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte.(TSM/009971,SM/10416) | TSM/009971 | SM/10416 | Augmentation | MVS | Tehatta-I | Gopalpur | 2nd Tube Well | Pump House | Donated | 96 | 3472 | 817 | 4 | Possessed | Registration complete
127 | NADIA | Gosaichar Char Piped Water Supply Scheme To Accommodate FHTC at Ranaghat-II Block under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/014935,SM/13758) | TSM/014935 | SM/13758 | New | SVS | Ranaghat-I | Gosair Char | null | OHR | Private | 189 | 865 | 115 | 23 | Identified | null
128 | NADIA | Gotpara Piped Water Supply Scheme(TSM/020436,SM/17685) | TSM/020436 | SM/17685 | New | MVS | Nakashipara | Gotpara | OHR | OHR | Donated | 58 | 2611 | 168 | 24 | Possessed | null
129 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for GOBRAPOTA to Accommodate FHTC in Krishnagar-I Block of Nadia District under Nadia Division, P.H.E. Dte(TSM/009814,SM/10417) | TSM/009814 | SM/10417 | Augmentation | MVS | Krishnagar-I | Gobrapota | OHR | OHR | Private | 106 | 797 | 76 | 42 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- PHE/243/1L-47/2022 Dated- 20/01/2023
130 | NADIA | Noachar Piped Water Supply Scheme(TSM/020435,SM/17686) | TSM/020435 | SM/17686 | New | SVS | Kaliganj | Noachar | OHR | OHR | Donated | 120 | 201 | 666 | 25 | Possessed | Registration Done
131 | NADIA | Dhopahat Piped Water Supply Scheme(TSM/008625,SM/09942) | TSM/008625 | SM/09942 | New | MVS | Tehatta-I | Kushtia | 2nd TW Site | Pump House | Vested | 34 | 776 | 2896 | 0 | Possessed | null
132 | NADIA | BHATGACHHI PIPED WATER SUPPLY SCHEME(TSM/009068,SM/10099) | TSM/009068 | SM/10099 | New | MVS | Chapra | Alfa | Head Work Site | OHR | Donated | 10 | 0 | 1713 | 0 | Possessed | null
133 | NADIA | Indrakpur Piped Water Supply Scheme.(TSM/005078,SM/13820) | TSM/005078 | SM/13820 | New | MVS | Nabadwip | Sankarpur | Pump House | OHR | Donated | 2 | 777 | 35 | 4 | Possessed | Registration Done
134 | NADIA | Providing FHTC by augmentation for Madhugari water supply scheme with in Karimpur-I Block in Nadia District under Nadia Division P.H.E. Dte. (Phase-II)(TSM/009578,SM/10084) | TSM/009578 | SM/10084 | Augmentation | MVS | Karimpur-I | Madhugari | null | OHR | Vested | 108 | 9721 | 0 | 0 | Identified | null
135 | NADIA | SIKRA PIPED WATER SUPPLY SCHEME(TSM/008800,SM/10410) | TSM/008800 | SM/10410 | New | MVS | Chapra | Sikra | 2nd Tube well Site | Pump House | Donated | 23 | 1332 | 2207 | 0 | Possessed | null
136 | NADIA | Providing Functional House Tap Connection from Teinpur Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte.(TSM/007544,SM/08666) | TSM/007544 | SM/08666 | Retrofitting | MVS | Karimpur-II | Chandpur | null | OHR | Vested | 52 | 1012 | 0 | 0 | Identified | null
137 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Dignagar Water Supply Scheme(TSM/008509,SM/10019) | TSM/008509 | SM/10019 | Augmentation | MVS | Krishnagar-I | Dignagar | 3rd Tube Well | Pump House | Donated | 83 | 99 | 943 | 4 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2022 2) Registration Done
138 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE II/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011447,SM/11838) | TSM/011447 | SM/11838 | Augmentation | MVS | Nakashipara | Mirjapur | OHR | OHR | Donated | 56 | 2000 | 446 | 25 | Possessed | 1) Registration Done 2) Mutation Done
139 | NADIA | AUGMENTATION OF GROUND WATER BASED KARIMPUR JALANGI ZONE-VI PWSS TO ACCOMMODATE FHTC IN KARIMPUR-I BLOCK IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/011235,SM/11513) | TSM/011235 | SM/11513 | Augmentation | MVS | Karimpur-I | Sundalpur | OHR | OHR | Donated | 129 | 3396 | 403 | 17 | Possessed | Registration Done
140 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA(TSM/011497,SM/11925) | TSM/011497 | SM/11925 | Augmentation | MVS | Santipur | Phulia (CT) | 2ND TW SITE | Pump House | Donated | 54 | 447 | 683 | 3 | Identified | null
141 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BARAIA to Accommodate FHTC in Tehatta-II block of Nadia District under Nadia Division, PHE Dte.(TSM/009182,SM/10269) | TSM/009182 | SM/10269 | Augmentation | MVS | Tehatta-II | Baraia | OHR | OHR | Donated | 8 | 55 | 2156 | 50 | Identified | Submitted to DL & LRO
142 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016206,SM/15522) | TSM/016206 | SM/15522 | Augmentation | SVS | Santipur | Phulia (CT) | OHR | OHR | Vested | 54 | 1 | 427 | 24 | Possessed | Possetion Done
143 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Narayanpur | null | OHR | Private | 10 | 2266 | 365 | 20 | Identified | null
144 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011358,SM/11834) | TSM/011358 | SM/11834 | Augmentation | MVS | Kaliganj | Bhurulia | OHR | OHR | Donated | 9 | 2355 | 517 | 24 | Possessed | 1) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2022 2) Registration Done 3) Mutation Done
145 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Singa | null | OHR | Vested | 81 | 6 | 254 | 24 | Identified | null
146 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BARUIPARA to Accommodate FHTC in Karimpur-I Block of Nadia District under Nadia Division, PHE Dte.(TSM/009057,SM/11815) | TSM/009057 | SM/11815 | Augmentation | MVS | Karimpur-I | Kechua Danga | 4th Tube Well | Pump House | Donated | 121 | 4220 | 4982 | 3 | Possessed | Registration Complete
147 | NADIA | Parbatipur Piped Water Supply Scheme at Ranaghat-I Block Under Nadia District Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/014928,SM/14422) | TSM/014928 | SM/14422 | New | MVS | Ranaghat-I | Gopalpur (CT) | null | OHR | Private | 147 | 7 | 14 | 44 | Identified | null
148 | NADIA | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting.(TSM/006452,SM/07490) | TSM/006452 | SM/07490 | Retrofitting | MVS | Krishnagar-I | Senpur | null | OHR | Vested | 119 | 3721 | 0 | 0 | Identified | null
149 | NADIA | HATKHOLA PIPED WATER SUPPLY SCHEME(TSM/008804,SM/10404) | TSM/008804 | SM/10404 | New | SVS | Chapra | Hatkhola | 2nd Tube well site | Pump House | Donated | 21 | 356 | 1928 | 0 | Possessed | null
150 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016118,SM/18374) | TSM/016118 | SM/18374 | Augmentation | SVS | Santipur | Phulia (CT) | Pump House | OHR | Vested | 54 | 1 | 1136 | 8 | Possessed | Sent to Joint Secretatary L & LR Dept by the ADM (L R) vide Memo No- 4989/V/25 Land/ DT/PWSS/2021 Dated- 16/11/2022 Sent to DM, Nadia from Land Dept Vide Memo No- 371-GE(M)/24012/494/2022 Dated- 30/01/23 Possetion Done
151 | NADIA | JITPUR PIPED WATER SUPPLY SCHEME(TSM/008994,SM/10405) | TSM/008994 | SM/10405 | New | MVS | Tehatta-I | Jitpur | 2nd TW Site | Pump House | Donated | 99 | 276 | 2044 | 0 | Identified | Registration Completed on 27.07..2022
152 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016118,SM/18374) | TSM/016118 | SM/18374 | Augmentation | SVS | Santipur | Phulia (CT) | Pump House | Pump House | Vested | 54 | 1 | 1206 | 3 | Possessed | Sent to Joint Secretatary L & LR Dept by the ADM (L R) vide Memo No- 4989/V/25 Land/ DT/PWSS/2021 Dated- 16/11/2022 Sent to DM, Nadia from Land Dept Vide Memo No- 371-GE(M)/24012/494/2022 Dated- 30/01/23 Possetion Done
153 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR TOPLA PWSS BLOCK: KARIMPUR - II DISTRICT: NADIA(TSM/011232,SM/11511) | TSM/011232 | SM/11511 | Augmentation | MVS | Karimpur-II | Topla | 3rd Tube Well | Pump House | Donated | 24 | 21477 | 1404 | 4 | Possessed | Registration Done
154 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VII/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011475,SM/12375) | TSM/011475 | SM/12375 | Augmentation | MVS | Nakashipara | Dhaparia | OHR | OHR | Vested | 83 | 1 | 567 | 20 | Possessed | Sent to Joint Secretatary L & LR Dept by the ADM (L R) vide Memo No- 4990/V/25 Land/ DT/PWSS/2021 Dated- 16/11/2022 Letter for handing over land Vide Memo No- 928/V/25-LANDS/DT/PWSS/2021 Dated- 22/02/23
155 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhimpur (Phase-II) to accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division, PHE Dte.(TSM/010074,SM/10726) | TSM/010074 | SM/10726 | Augmentation | MVS | Krishnagar-I | Bhimpur | OHR | OHR | Private | 910 | 4069 | 819 | 45 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- 43/PHE/1L-28/2022 Dated- 04/01/2023
156 | NADIA | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District.(TSM/009455,SM/11919) | TSM/009455 | SM/11919 | Augmentation | MVS | Tehatta-II | Palsunda | OHR | OHR | Donated | 14 | 1126 | 8409 | 46 | Possessed | 1) Registration Done 2) ROR Received
157 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016206,SM/15522) | TSM/016206 | SM/15522 | Augmentation | SVS | Santipur | Phulia (CT) | 3rd T/W | Pump House | Private | 54 | 1916 | 0 | 3 | Identified | Cabinet Approval received vide memo no. PHE/2197/1L-25/2023 dt. 02/08/2023
158 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BHALUKA to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte.(TSM/009168,SM/10068) | TSM/009168 | SM/10068 | Augmentation | MVS | Krishnagar-I | Bhaluka | 3rd Tube Well | Pump House | Donated | 68 | 7619 | 2784 | 4 | Possessed | 1) Registration Done 2) Mutation Done
159 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for Betai Zone-I to accommodate FHTC in Tehatta-I block of Nadia District under Nadia Division, PHE Dte.(TSM/009973,SM/10414) | TSM/009973 | SM/10414 | Augmentation | SVS | Tehatta-I | Betai | 3rd Tube Well, AIRP | AIRP | Donated | 89 | 11341 | 4875 | 17 | Possessed | Registration Done
160 | NADIA | RAJAPUR PIPED WATER SUPPLY SCHEME(TSM/011903,SM/11966) | TSM/011903 | SM/11966 | New | MVS | Tehatta-I | Jayrampur | 2nd TW Site | Pump House | Donated | 64 | 992 | 1394 | 0 | Identified | null
161 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR UDAYPUR PWSS BLOCK: SANTIPUR DISTRICT: NADIA(TSM/011497,SM/11925) | TSM/011497 | SM/11925 | Augmentation | MVS | Santipur | Phulia (CT) | OHR | OHR | Donated | 54 | 447 | 683 | 28 | Possessed | Registration Done
162 | NADIA | JAYRAMPUR PIPED WATER SUPPLY SCHEME(TSM/014577,SM/12423) | TSM/014577 | SM/12423 | New | SVS | Karimpur-I | Jayrampur | HW site & 2nd TW site | OHR | Donated | 98 | 530 | 993 | 0 | Identified | Registration Completed on 20.12.2022
163 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAKDAH (PART) AT CHAKDAH BLOCK UNDER NADIA DISTRICT UNDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017108,SM/18661) | TSM/017108 | SM/18661 | Augmentation | MVS | Chakdah | Srinagar | null | OHR | Private | 183 | 2974 | 1337 | 23 | Identified | null
164 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHISNENGRA Zone-II to Accommodate FHTC in Krishnagar-I block of Nadia District under Nadia Division PHE Dte.(TSM/009172,SM/09787) | TSM/009172 | SM/09787 | Augmentation | SVS | Krishnagar-I | Hijuli | OHR | OHR | Donated | 107 | 1008 | 518 | 11 | Identified | null
165 | NADIA | Detailed Project Report for Nasra Piped water Supply scheme at Ranaghat-II Block Under Nadia district Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/015322,SM/14244) | TSM/015322 | SM/14244 | New | SVS | Ranaghat-II | Nasra (CT) | null | OHR | Vested | 156 | 1 | 0 | 18 | Identified | null
166 | NADIA | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision)(TSM/005040,SM/16182) | TSM/005040 | SM/16182 | New | MVS | Nabadwip | Majdia | OHR | OHR | Private | 18 | 2301 | 222 | 42 | Identified | Cabinet Approval received vide memo no. PHE/1424/1L-34/2022 dt. 06/06/2023
167 | NADIA | BHATGACHHI PIPED WATER SUPPLY SCHEME(TSM/009068,SM/10099) | TSM/009068 | SM/10099 | New | MVS | Chapra | Alfa | 2nd Tube well Site | Pump House | Donated | 10 | 2052 | 1684 | 0 | Possessed | null
168 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VI/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011472,SM/12374) | TSM/011472 | SM/12374 | Augmentation | SVS | Nakashipara | Arbetai | OHR | OHR | Donated | 34 | 4255 | 1453 | 33 | Possessed | 1) Registration Done 2) Mutation Done
169 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IV/B (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011456,SM/11841) | TSM/011456 | SM/11841 | Augmentation | MVS | Nakashipara | Majhergram | OHR | OHR | Vested | 13 | 1205 | 1065 | 47 | Possessed | 1) Health (NOC Received Vide Memo No- BFW/432 Dated- 13/05/2022 2) Possetion Completed
170 | NADIA | Augmentation of ground water water based Palsonda PWSS to accommodate FHTC in Tehatta-II Block under Tehatta Sub-Division of Nadia Division in Nadia District.(TSM/009455,SM/11919) | TSM/009455 | SM/11919 | Augmentation | MVS | Tehatta-II | Palsunda | 2nd Tube Well | Pump House | Donated | 14 | 617 | 8407 | 4 | Possessed | 1) Registration Done, 2) ROR Received
171 | NADIA | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. (TSM/020321,SM/17205) | TSM/020321 | SM/17205 | Augmentation | MVS | Karimpur-I | Madhugari | null | OHR | Vested | 108 | 9721 | 0 | 0 | Identified | null
172 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE VIII/C (NORTHERN SECTOR PART-II) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011482,SM/11743) | TSM/011482 | SM/11743 | Augmentation | MVS | Nakashipara | Digha | OHR | OHR | Donated | 96 | 1091 | 201 | 25 | Possessed | i) Received from ADM (LR) Vide Memo No- 2267/V/25 Land/ DT/PWSS/2021 Dated- 16/06/2022 2) Possetion Done 3) Mutation Done
173 | NADIA | Augmentation of Ground Water Based Piped Water Supply Scheme for BARA ANDULIA ZONE-I to Accommodate FHTC in CHAPRA Block of Nadia District under Nadia Division, PHE Dte(TSM/009180,SM/10037) | TSM/009180 | SM/10037 | Augmentation | MVS | Chapra | Hatra | 4th Tube Well Site | Pump House | Private | 13 | 0 | 163 | 5 | Identified | Cabinet Approval received vide memo no. PHE/3328/1L-46/2022 dt. 01/11/2023
174 | NADIA | PANCHDARA ABHYNAGAR PIPED W/S SCHEME(TSM/008657,SM/10613) | TSM/008657 | SM/10613 | New | MVS | Tehatta-II | Panchdara Abhaynagar | 2nd TW Site | Pump House | Donated | 20 | 211 | 2559 | 0 | Possessed | null
175 | NADIA | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting.(TSM/006452,SM/07490) | TSM/006452 | SM/07490 | Retrofitting | MVS | Krishnagar-I | Senpur | null | OHR | Vested | 119 | 3721 | 0 | 0 | Identified | null
176 | NADIA | AUGMENTATION OF GROUND WATER BASED TEINPUR (ZONE-IV) PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KARIMPUR-II BLOCK WITH IN NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE(TSM/010354,SM/10518) | TSM/010354 | SM/10518 | Augmentation | MVS | Karimpur-II | Dharar | null | OHR | Vested | 70 | 729 | 0 | 0 | Possessed | null
177 | NADIA | MRIGI PIPED WATER SUPPLY SCHEME(TSM/008996,SM/10408) | TSM/008996 | SM/10408 | New | SVS | Tehatta-I | Mrigi | HW Site | AIRP | Donated | 69 | 3708 | 2789 | 0 | Possessed | null
178 | NADIA | Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block Under Nadia Arsenic Division-I, P.H.E. Dte.(TSM/018089,SM/18257) | TSM/018089 | SM/18257 | New | MVS | Ranaghat-II | Patuli | CWR | CWR | Private | 151 | 3851 | 467 | 108 | Identified | null
179 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-II) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016118,SM/18374) | TSM/016118 | SM/18374 | Augmentation | SVS | Santipur | Phulia (CT) | OHR | OHR | Vested | 54 | 1 | 1249 | 93 | Possessed | Sent to Joint Secretatary L & LR Dept by the ADM (L R) vide Memo No- 4989/V/25 Land/ DT/PWSS/2021 Dated- 16/11/2022Sent to DM, Nadia from Land Dept Vide Memo No- 371-GE(M)/24012/494/2022 Dated- 30/01/23 Possetion Done
180 | NADIA | SURUPPUR PIPED WATER SUPPLY SCHEME(TSM/008998,SM/10411) | TSM/008998 | SM/10411 | New | MVS | Tehatta-I | Tarangar | 2nd TW Site | Pump House | Donated | 50 | 987 | 610 | 0 | Possessed | null
181 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE IX/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011362,SM/11697) | TSM/011362 | SM/11697 | Augmentation | MVS | Kaliganj | Chhota Chandghar | OHR | OHR | Vested | 124 | 2157 | 2157 | 25 | Identified | null
182 | NADIA | SURUPPUR PIPED WATER SUPPLY SCHEME(TSM/008998,SM/10411) | TSM/008998 | SM/10411 | New | MVS | Tehatta-I | Suruppur | HW Site | AIRP | Donated | 51 | 0 | 188 | 0 | Possessed | null
183 | NADIA | MADHUPUR PIPED WATER SUPPLY SCHEME(TSM/009069,SM/10103) | TSM/009069 | SM/10103 | New | MVS | Chapra | Fulkalmi | Head Work Site | OHR | Donated | 45 | 0 | 550 | 0 | Possessed | null
184 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B (NORTHERN SECTOR PART-I) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011326,SM/11829) | TSM/011326 | SM/11829 | Augmentation | MVS | Kaliganj | Juranpur | OHR | OHR | Vested | 42 | 1 | 2225 | 28 | Possessed | Sent to The Secretary Land Reforms Commissioner (L & LR and RR & R Dept) Vide Memo No- 2083/V/25-Land-DT/PWSS/2021 Dated- 08/06/22 by ADM, (L & LR), Nadia Sent to DM, Nadia from Land Dept Vide Memo No- 5184-GE(M)/24012/336/2022 Dated- 15/12/22
185 | NADIA | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR HARINGHATA & CHAKDAH (PART) AT CHAKDAHA & HARINGHATA BLOCK UNDER NADIA DISTRICT UBDER NADIA ARSENIC DIVISION-I, P.H.E. DTE.(TSM/017098,SM/19042) | TSM/017098 | SM/19042 | Augmentation | MVS | Haringhata | Jhikra | null | OHR | Private | 88 | 0 | 0 | 33 | Not Identified | null
186 | NADIA | Detailed Project report of Hijuli Piped Water Supply Scheme at Ranaghat-II Block Under Nadia District Under Nadia Arseni Division-I, P.H.E. Dte.(TSM/015030,SM/14243) | TSM/015030 | SM/14243 | New | MVS | Ranaghat-II | Hijuli (CT) | null | OHR | Private | 155 | 0 | 0 | 0 | Not Identified | null
187 | NADIA | SURFACE WATER BASED W/S SCHEME FOR ARSENIC AFFECTED AREAS OF NADIA DISTRICT ZONE I/B(NORTHERN SECTOR PART-III) TO ACCOMMODATE FHTC UNDER NADIA DIVISION(TSM/011289,SM/11638) | TSM/011289 | SM/11638 | Augmentation | MVS | Krishnagar-II | Sadhanpara | OHR | OHR | Private | 3 | 1312 | 607 | 24 | Identified | Cabinet Approval Made & DPR Prepared (Phase-I) Notification for Cabinet Approval Vide Memo No- 223/PHE/1L-29/2022 Dated- 19/01/2023
188 | NADIA | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-III) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA(TSM/016119,SM/13878) | TSM/016119 | SM/13878 | Augmentation | SVS | Santipur | Phulia (CT) | AIRP | AIRP | Vested | 54 | 7205 | 0 | 17 | Identified | null