## A3- Land Parcel Status
A3- Land Parcel Status
SL No | District | Scheme Name | Scheme TSM Code | Scheme SM Code | Scheme Category | Scheme Coverage Type | Block | Village | Location | Purpose | Type | J.L. No. | Khatian No. | Plot No. | Area (in decimal) | Status | Remarks
1 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC(TSM/011198,SM/11762) | TSM/011198 | SM/11762 | Augmentation | MVS | Bagda | Uttar Panchpota | null | OHR | Donated | 78 | 2024 | 562 | 25 | Identified | LAND ACQUIRED
2 | NORTH 24 PARGANAS | Debitala Piped Water Supply Scheme(TSM/015448,SM/13523) | TSM/015448 | SM/13523 | New | SVS | Minakhan | Debitala | Debitala (HW site & Ph no- 1) | OHR | Private | 70 | 1245 | 693 | 32 | Possessed | Registration done
3 | NORTH 24 PARGANAS | Bargan Gopalpur Piped Water Supply Scheme(TSM/015449,SM/15902) | TSM/015449 | SM/15902 | New | MVS | Minakhan | Bargan Gopalpur | Margi | Pump House | Private | 71 | 779 | 102 | 33 | Possessed | Registration done
4 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Mohanpur(TSM/012029,SM/14151) | TSM/012029 | SM/14151 | Augmentation | SVS | Minakhan | Mohanpur | Barabari OHR & PH1 (MOHANPUR (Z-II) | OHR | Private | 139 | 2505 | 472 | 29 | Possessed | Registration done
5 | NORTH 24 PARGANAS | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC(TSM/015769,SM/14161) | TSM/015769 | SM/14161 | Augmentation | MVS | Barasat-I | Charkhara | null | Pump House | Private | 93 | 276 | 182 | 4 | Identified | Consent papers submitted.
6 | NORTH 24 PARGANAS | Kachurhula Zone-I Piped Water Supply Scheme(TSM/015511,SM/13522) | TSM/015511 | SM/13522 | New | SVS | Minakhan | Kachurhula | Atpukur HW site & Ph no- 1 | OHR | Private | 99 | 0 | 0 | 1 | Identified | Registration Not done
7 | NORTH 24 PARGANAS | Kaugachhi Zone-II Piped Water Supply Scheme(TSM/016488,SM/14500) | TSM/016488 | SM/14500 | New | SVS | Barrackpur-I | Kaugachhi (CT) | KOUGACHI | OHR | Vested | 0 | 1 | 657 | 33 | Identified | JOINT VERIFICATION WITH JOINT BL&LRO IS COMPLETE.
8 | NORTH 24 PARGANAS | Bachhra piped Water supply scheme(TSM/014837,SM/12712) | TSM/014837 | SM/12712 | New | MVS | Minakhan | Bachhra | Mohanpur HW site & Ph no- 1 | OHR | Private | 142 | 1111 | 62 | 30 | Possessed | Registration done
9 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015250,SM/13435) | TSM/015250 | SM/13435 | Augmentation | MVS | Deganga | Abjan Nagar | Abjan Nagar | OHR | Private | 107 | 0 | 0 | 28 | Identified | Cabinet approval received vide No.PHE/1429/1L-29/2023 Dt.06/06/2023
10 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC(TSM/010949,SM/12278) | TSM/010949 | SM/12278 | Augmentation | MVS | Hingalganj | Sahebkhali | Sahebkhali OHR | OHR | Private | 110 | 358 | 1059 | 36 | Identified | Registration done
11 | NORTH 24 PARGANAS | Bhandarkhali Piped Water Supply Scheme(TSM/015379,SM/15827) | TSM/015379 | SM/15827 | New | SVS | Hingalganj | Bhandarkhali | Dulduli | Pump House | Private | 92 | 0 | 63 | 5 | Identified | Registration Not done
12 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Hasnabad to accommodate FHTC(TSM/010922,SM/12124) | TSM/010922 | SM/12124 | Augmentation | MVS | Hasnabad | Angnara | HASNABAD OHR | OHR | Private | 53 | 0 | 0 | 1 | Identified | Registration Not done
13 | NORTH 24 PARGANAS | Atpukur Zone-I Piped Water Supply Scheme(TSM/015515,SM/15828) | TSM/015515 | SM/15828 | New | MVS | Minakhan | Atpukur | Atpukur | OHR | Private | 100 | 0 | 222 | 4 | Identified | Registration Not done
14 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chauberia to Accommodate FHTC(TSM/011106,SM/11592) | TSM/011106 | SM/11592 | Augmentation | SVS | Bongaon | Chauberia | CHOWBERIA | OHR | Private | 135 | 0 | 0 | 30 | Identified | e-filing done
15 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC(TSM/011110,SM/11594) | TSM/011110 | SM/11594 | Augmentation | MVS | Bongaon | Naraharipur | CHHAYGHARIA (ZONE-III) | OHR | Private | 110 | 0 | 0 | 8 | Identified | e-filing done
16 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kamlabas to accommodate FHTC(TSM/010859,SM/11602) | TSM/010859 | SM/11602 | Augmentation | MVS | Bagda | Kamlabas | null | Pump House | Donated | 4 | 1413 | 1219 | 2 | Identified | LAND ACQUIRED
17 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC(TSM/011275,SM/17679) | TSM/011275 | SM/17679 | Augmentation | SVS | Barasat-II | Deara (CT) | CHANDIGARH ROHANDA G.P. | Pump House | Private | 57 | 5945 | 1672 | 15 | Identified | selling consent letter from owner has been received, Mutation of land in progress
18 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/014881,SM/15819) | TSM/014881 | SM/15819 | Augmentation | MVS | Deganga | Raypur | Raypur | OHR | Vested | 50 | 0 | 0 | 33 | Identified | IDT in process.
19 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water supply Scheme for Gadpukuria Zone-II to Accommodate FHTC(TSM/011198,SM/11762) | TSM/011198 | SM/11762 | Augmentation | MVS | Bagda | Uttar Panchpota | null | Substation | Donated | 78 | 989 | 124 | 2 | Identified | LAND ACQUIRED
20 | NORTH 24 PARGANAS | Katakhali Piped Water Supply Scheme(TSM/015510,SM/15826) | TSM/015510 | SM/15826 | New | SVS | Hingalganj | Sandelerbil | Sandelerbill Pump house no-2 | Pump House | Private | 95 | 0 | 1868 | 5 | Identified | Registration Not done
21 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VII (Amulia) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015086,SM/18264) | TSM/015086 | SM/18264 | Augmentation | MVS | Deganga | Amulia | Amulia | OHR | Private | 58 | 0 | 0 | 29 | Identified | Land details are sent vide e-file No. DPHE-67/5/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Saptarshi Paul DS(SP)-SCHM(PHE)
22 | NORTH 24 PARGANAS | Katakhali Piped Water Supply Scheme(TSM/015510,SM/15826) | TSM/015510 | SM/15826 | New | SVS | Hasnabad | Barunhat | Pump house no-1 | Pump House | Private | 65 | 0 | 1986 | 5 | Identified | Registration Not done
23 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VI (Bashbaruni) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015249,SM/18265) | TSM/015249 | SM/18265 | Augmentation | MVS | Deganga | Bashbaruni | Bashbaruni | OHR | Private | 36 | 0 | 0 | 33 | Identified | Land details are sent vide e-file No. DPHE-67099/2/2023-EEN24WSDI SEC-DPHE.
24 | NORTH 24 PARGANAS | Ketarchak Piped Water Supply Scheme(TSM/015343,SM/15833) | TSM/015343 | SM/15833 | New | MVS | Hingalganj | Ketarchak | Dulduli Pump house no-3 | Pump House | Private | 104 | 803 | 259 | 4 | Possessed | Registration done
25 | NORTH 24 PARGANAS | Ketarchak Piped Water Supply Scheme(TSM/015343,SM/15833) | TSM/015343 | SM/15833 | New | MVS | Hingalganj | Ketarchak | Dulduli HW site & Ph no- 1 | OHR | Private | 104 | 782 | 98 | 33 | Possessed | Registration done
26 | NORTH 24 PARGANAS | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte.(TSM/017266,SM/14501) | TSM/017266 | SM/14501 | New | MVS | Barrackpur-I | Rahuta (P) | Rahuta (P) | Pump House | Vested | 22 | 271 | 0 | 3 | Identified | IDT in Process
27 | NORTH 24 PARGANAS | Sankardaha Piped water supply scheme(TSM/015446,SM/13518) | TSM/015446 | SM/13518 | New | MVS | Minakhan | Sankardaha | Sankardaha | Pump House | Private | 74 | 1488 | 223 | 5 | Possessed | Registration done
28 | NORTH 24 PARGANAS | Kharibaria Piped Water Supply Scheme.(TSM/015444,SM/13519) | TSM/015444 | SM/13519 | New | MVS | Minakhan | Kharibiaria | Dhuturdaha | Pump House | Private | 76 | 0 | 694 | 5 | Possessed | Registration done
29 | NORTH 24 PARGANAS | Debitala Piped Water Supply Scheme(TSM/015448,SM/13523) | TSM/015448 | SM/13523 | New | SVS | Minakhan | Debitala | Debitala | Pump House | Private | 70 | 929 | 504 | 4 | Possessed | Registration done
30 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Swethpur Zone-I to Accommodate FHTC.(TSM/011241,SM/18410) | TSM/011241 | SM/18410 | Augmentation | MVS | Deganga | Shwetpur | Swai Swetpur G.P. | Pump House | Private | 3 | 969 | 132 | 4 | Identified | e - filing done
31 | NORTH 24 PARGANAS | Khariat Abad Piped Water Supply Scheme(TSM/015513,SM/15829) | TSM/015513 | SM/15829 | New | MVS | Sandeshkhali-I | Khariat Abad | Boyermari-I HW site & Ph no- 1 | OHR | Private | 19 | 0 | 0 | 1 | Identified | Registration Not done
32 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Deara to accommodate FHTC(TSM/011275,SM/17679) | TSM/011275 | SM/17679 | Augmentation | SVS | Barasat-II | Deara (CT) | CHANDIGARH ROHANDA G.P. | OHR | Private | 57 | 2886 | 1672 | 15 | Identified | selling consent letter from owner has been received, Mutation of land in progress
33 | NORTH 24 PARGANAS | Kusangra Piped Water Supply Scheme(TSM/015447,SM/15832) | TSM/015447 | SM/15832 | New | MVS | Minakhan | Minakhan | Bamanpukur | Pump House | Private | 92 | 0 | 41 | 5 | Possessed | Registration done
34 | NORTH 24 PARGANAS | Niruli Abad Piped Water Supply Scheme.(TSM/014701,SM/12716) | TSM/014701 | SM/12716 | New | MVS | Minakhan | Niruli Abad | Niruli Abad | Pump House | Private | 145 | 3089 | 215 | 33 | Possessed | Registration done
35 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Durgapur Baylani Zone-I to accommodate FHTC(TSM/011157,SM/12275) | TSM/011157 | SM/12275 | Augmentation | MVS | Hingalganj | Bispur | Kathalberia OHR | OHR | Private | 82 | 219 | 54 | 33 | Identified | Registration done
36 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC(TSM/011166,SM/12276) | TSM/011166 | SM/12276 | Augmentation | MVS | Bagda | Amdob | Bansghata | OHR | Private | 105 | 0 | 0 | 4 | Identified | e-filing done.
37 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte.(TSM/010573,SM/10758) | TSM/010573 | SM/10758 | Augmentation | MVS | Bongaon | Khamarkalla | Khamarkalla | OHR | Private | 75 | 0 | 0 | 33 | Identified | Land details are sent vide e-file No. DPHE-67099/9/2023-EEN24WSDI SEC-DPHE. THE E-FILE IS PORESENTLY LYING WITH SWAPAN KUMAR BARAI SO(SKB)-ESTT(PHE)
38 | NORTH 24 PARGANAS | Dakshin Akhratala Piped Water Supply Scheme(TSM/015754,SM/18617) | TSM/015754 | SM/18617 | New | SVS | Sandeshkhali-I | Dashin Akhratala | Nazat-II Pump house no-4 | Pump House | Private | 23 | 0 | 30 | 5 | Possessed | Registration Not done
39 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC(TSM/011161,SM/12126) | TSM/011161 | SM/12126 | Augmentation | MVS | Hasnabad | Shulkuniabad | Bhabanipur PH NO-2 | Pump House | Private | 75 | 0 | 0 | 4 | Possessed | Registration done
40 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011863,SM/12372) | TSM/011863 | SM/12372 | Augmentation | MVS | Amdanga | Tapanpur | Tapanpur | OHR | Private | 56 | 0 | 0 | 29 | Identified | Cabinet approval received vide memo no - PHE/3655/1L-66/2023 dated 07-12-2023
41 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011948,SM/11864) | TSM/011948 | SM/11864 | Augmentation | MVS | Barasat-I | Malikapur | Malikapur | OHR | Private | 20 | 0 | 0 | 29 | Identified | Cabinet approval received vide No.PHE/1423/1L-26/2022 DT.06/06/2023
42 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC(TSM/011166,SM/12276) | TSM/011166 | SM/12276 | Augmentation | MVS | Bagda | Amdob | Bansghata | OHR | Private | 105 | 0 | 0 | 2 | Identified | e-filing done.
43 | NORTH 24 PARGANAS | TEGHARIA Piped Water Supply Scheme(TSM/016121,SM/16457) | TSM/016121 | SM/16457 | New | MVS | Barasat-II | Tegharia | null | OHR | Private | 145 | 278 | 398 | 28 | Identified | null
44 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-4 Piped Water Supply Scheme(TSM/015721,SM/15323) | TSM/015721 | SM/15323 | Augmentation | MVS | Deganga | Nandipara Kuchemora | Berachampa-I | OHR | Vested | 67 | 778 | 1390 | 31 | Identified | Memo issued to ADM (LR) for IDT
45 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XIV_A (Ruiya) and Zone-XIV_B (Dangadihila) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/014836,SM/15817) | TSM/014836 | SM/15817 | Augmentation | MVS | Barrackpur-II | Patulia (CT) | Patulia | OHR | Private | 0 | 0 | 0 | 34 | Not Identified | Land details are sent vide e-file No. DPHE-67099/4/2022-EEN24WSDI SEC-DPHE.
46 | NORTH 24 PARGANAS | Bamanpukuria Piped Water Supply Scheme.(TSM/014705,SM/13814) | TSM/014705 | SM/13814 | New | SVS | Minakhan | Bamanpukuria | Bamanpukur HW site & Ph no- 1 | OHR | Private | 90 | 0 | 0 | 1 | Identified | Registration Not done
47 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC.(TSM/011175,SM/12122) | TSM/011175 | SM/12122 | Augmentation | MVS | Hingalganj | Banstala | Rupamari PH 3 | Pump House | Private | 91 | 291 | 448 | 6 | Possessed | Registration done
48 | NORTH 24 PARGANAS | Matbari Abad Piped Water Supply Scheme(TSM/015514,SM/15825) | TSM/015514 | SM/15825 | New | SVS | Sandeshkhali-I | Matbari Abad | Boyermari-I HW site & Ph no- 1 | OHR | Private | 1 | 521 | 847 | 33 | Possessed | Registration done
49 | NORTH 24 PARGANAS | Bargan Gopalpur Piped Water Supply Scheme(TSM/015449,SM/15902) | TSM/015449 | SM/15902 | New | MVS | Minakhan | Bargan Gopalpur | Narabunia (HW Site & PH No.2) | OHR | Private | 71 | 584 | 90 | 3 | Possessed | Registration done
50 | NORTH 24 PARGANAS | Atpukur Zone-I Piped Water Supply Scheme(TSM/015515,SM/15828) | TSM/015515 | SM/15828 | New | MVS | Minakhan | Atpukur | Atpukur | Pump House | Private | 100 | 5875 | 4353 | 3 | Possessed | Registration done
51 | NORTH 24 PARGANAS | Atpukur Zone-I Piped Water Supply Scheme(TSM/015515,SM/15828) | TSM/015515 | SM/15828 | New | MVS | Minakhan | Atpukur | Dk sastitala | Pump House | Private | 100 | 1256 | 273 | 3 | Possessed | Registration done
52 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/013336,SM/18258) | TSM/013336 | SM/18258 | Augmentation | MVS | Barasat-I | Chhota Jagulia | Chhota Jagulia | OHR | Private | 115 | 0 | 0 | 21 | Identified | e-File sent vide No. DPHE-67099/21/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
53 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) for Mohanpur Water Supply Scheme in Barrackpore-II Block of North 24 Parganas District Under North 24 Pargans W/S Division-I, P.H.E. Dte.(TSM/010599,SM/10579) | TSM/010599 | SM/10579 | Augmentation | MVS | Barrackpur-II | Babanpur (P) | Babanpur | OHR | Vested | 1 | 0 | 0 | 36 | Identified | Already possession done.
54 | NORTH 24 PARGANAS | Sankardaha Piped water supply scheme(TSM/015446,SM/13518) | TSM/015446 | SM/13518 | New | MVS | Minakhan | Sankardaha | Sankardaha (HW site & Ph no- 1) | OHR | Private | 74 | 153 | 202 | 32 | Possessed | Registration done
55 | NORTH 24 PARGANAS | RAIGACHHI Piped Water Supply Scheme.(TSM/016043,SM/18599) | TSM/016043 | SM/18599 | New | SVS | Rajarhat | Raigachhi (CT) | null | OHR | Private | 0 | 0 | 0 | 0 | Not Identified | Land not Identified
56 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-III-B (KHILIKAPUR) in Barasat-I Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte.(TSM/013337,SM/13434) | TSM/013337 | SM/13434 | Augmentation | MVS | Barasat-I | Khilkapur | KHILKAPUR | OHR | Private | 4 | 0 | 0 | 27 | Identified | Cabinet approval received vide No.PHE/2211/1L-19/2023 Dt.03/08/2023
57 | NORTH 24 PARGANAS | Kachurhula Zone-II Piped Water Supply Scheme(TSM/015445,SM/13445) | TSM/015445 | SM/13445 | New | MVS | Minakhan | Kachurhula | Atpukur Pump house no-2 | Pump House | Private | 99 | 0 | 0 | 1 | Identified | Registration Not done
58 | NORTH 24 PARGANAS | Ground Water Based Piped Water Supply Scheme for augmentation of Auldanga Zone-II in Bagdah Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte. (TSM/010664,SM/10582) | TSM/010664 | SM/10582 | Augmentation | MVS | Bagda | Baikola | Baikola | OHR | Private | 18 | 0 | 0 | 32 | Identified | Cabinet approval received vide No.PHE/2180/1L-13/2023 Dt.01/08/2023
59 | NORTH 24 PARGANAS | Niruli Piped Water Supply Scheme(TSM/014715,SM/12714) | TSM/014715 | SM/12714 | New | MVS | Minakhan | Niruli | Chaital | Pump House | Private | 144 | 0 | 820 | 3 | Possessed | Registration done
60 | NORTH 24 PARGANAS | Garibpur Piped water supply scheme(TSM/016336,SM/13897) | TSM/016336 | SM/13897 | New | MVS | Bongaon | Garibpur | GARIBPUR | OHR | Private | 17 | 0 | 0 | 10 | Identified | e-filing done; sent back to concerned division for reverification purpose.
61 | NORTH 24 PARGANAS | JATRAGACHHI Piped Water Supply Scheme (TSM/016452,SM/16625) | TSM/016452 | SM/16625 | New | SVS | Rajarhat | Jatragachhi | null | OHR | Private | 24 | 2025 | 241 | 33 | Identified | null
62 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Malancha Zone-II to accommodate FHTC(TSM/010446,SM/10574) | TSM/010446 | SM/10574 | Augmentation | MVS | Minakhan | Chak Ahammadpur | MALANCHA PH NO-1 & HW | OHR | Private | 83 | 2722 | 514 | 33 | Possessed | Registration done
63 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC.(TSM/011175,SM/12122) | TSM/011175 | SM/12122 | Augmentation | MVS | Hingalganj | Banstala | Rupamari HW | OHR | Private | 91 | 219 | 54 | 33 | Possessed | Registration done
64 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC(TSM/011161,SM/12126) | TSM/011161 | SM/12126 | Augmentation | MVS | Hasnabad | Shulkuniabad | Bhabanipur OHR | OHR | Private | 75 | 0 | 0 | 17 | Identified | Registration Not done
65 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-B (Maricha) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011825,SM/12729) | TSM/011825 | SM/12729 | Augmentation | MVS | Amdanga | Maricha | Maricha | OHR | Vested | 5 | 0 | 0 | 28 | Identified | Already possessed.
66 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Kalitala and adjoining mouzas(TSM/012030,SM/14153) | TSM/012030 | SM/14153 | Augmentation | MVS | Hingalganj | Kalitala | KALITALA OHR | OHR | Private | 122 | 0 | 0 | 1 | Identified | IDT Proposal sent
67 | NORTH 24 PARGANAS | Providing FHTC by augmentation (Functional Household Tap Connection) of Ground Water Based Piped Water Supply Scheme for Barakpur Zone-II in Bongaon Block of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, PHE Dte.(TSM/011010,SM/11555) | TSM/011010 | SM/11555 | Augmentation | MVS | Bongaon | Satbaria | Satbaria | OHR | Private | 118 | 0 | 0 | 35 | Identified | Cabinet approval received vide No.PHE/2210/1L-18/2023 Dt.03/08/2023
68 | NORTH 24 PARGANAS | Balibhara Piped Water Supply Scheme(TSM/016295,SM/14498) | TSM/016295 | SM/14498 | New | SVS | Barrackpur-I | Balibhara (CT) | HEAD WORKS SITE | OHR | Private | 0 | 520 | 967 | 33 | Identified | Cabinet approval received vide No.PHE/2848/1L-09/2023 Dt.21/08/2023
69 | NORTH 24 PARGANAS | BARDASIA Piped Water Supply Scheme(TSM/016108,SM/16626) | TSM/016108 | SM/16626 | New | MVS | Barasat-II | Bardeshia | null | OHR | Private | 191 | 203 | 1116 | 25 | Identified | null
70 | NORTH 24 PARGANAS | Kaugachhi Zone-I Piped Water Supply Scheme(TSM/016327,SM/14499) | TSM/016327 | SM/14499 | New | SVS | Barrackpur-I | Kaugachhi (CT) | KOUGACHI | OHR | Private | 0 | 2115 | 0 | 27 | Identified | e-File done.
71 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Rupmari to Accommodate FHTC.(TSM/011175,SM/12122) | TSM/011175 | SM/12122 | Augmentation | MVS | Hingalganj | Banstala | Rupamari HW | OHR | Private | 91 | 631 | 91 | 35 | Possessed | Registration done
72 | NORTH 24 PARGANAS | Ghipukuria Piped Water Supply Scheme.(TSM/014711,SM/12718) | TSM/014711 | SM/12718 | New | MVS | Minakhan | Ghipukuria | Chaital HW site & Ph no- 1 | OHR | Private | 161 | 0 | 15 | 33 | Identified | Registration Not done
73 | NORTH 24 PARGANAS | Hatbhanga Piped Water Supply Scheme(TSM/015443,SM/13525) | TSM/015443 | SM/13525 | New | MVS | Minakhan | Hatbhanga | Bamanpukur HW site & Ph no- 1 | OHR | Private | 89 | 0 | 205 | 33 | Possessed | Registration done
74 | NORTH 24 PARGANAS | Matbari Abad Piped Water Supply Scheme(TSM/015514,SM/15825) | TSM/015514 | SM/15825 | New | SVS | Sandeshkhali-I | Matbari Abad | Boyermari-I Pump house no-2 | Pump House | Private | 1 | 3214 | 103 | 5 | Possessed | Registration done
75 | NORTH 24 PARGANAS | Augmentation of Bermajur Piped water supply scheme(TSM/018703,SM/14511) | TSM/018703 | SM/14511 | Augmentation | SVS | Sandeshkhali-II | Bermajur | BERMAJUR PH 2 | Pump House | Private | 16 | 6918 | 430 | 4 | Possessed | Registration done
76 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/013336,SM/18258) | TSM/013336 | SM/18258 | Augmentation | MVS | Barasat-I | Sikdespukhuria | Sikdesh Pukuria | OHR | Private | 95 | 0 | 0 | 10 | Identified | e-File sent vide No. DPHE-67099/21/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
77 | NORTH 24 PARGANAS | Petua Dhanihati Piped Water Supply Scheme(TSM/015512,SM/15830) | TSM/015512 | SM/15830 | New | MVS | Sandeshkhali-I | Matbari Abad | Petua Dhanihati HW site & Ph no- 1 | OHR | Private | 1 | 1060 | 527 | 31 | Identified | Registration done
78 | NORTH 24 PARGANAS | Augmentation of Bermajur Piped water supply scheme(TSM/018703,SM/14511) | TSM/018703 | SM/14511 | Augmentation | SVS | Sandeshkhali-II | Bermajur | BERMAJUR HW | OHR | Private | 16 | 1084 | 1637 | 18 | Possessed | Registration done
79 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Nurpur to accommodate FHTC.(TSM/011203,SM/11595) | TSM/011203 | SM/11595 | Augmentation | MVS | Minakhan | Bagchar | CHAMPALI OHR | OHR | Private | 152 | 420 | 40 | 29 | Possessed | Registration done
80 | NORTH 24 PARGANAS | Tapla Kusangra Piped Water Supply Scheme.(TSM/014693,SM/12720) | TSM/014693 | SM/12720 | New | MVS | Minakhan | Hatbhanga | Bamanpukur | Pump House | Private | 89 | 4351 | 1958 | 6 | Possessed | Registration done
81 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-I (Kamdebkati) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015463,SM/18259) | TSM/015463 | SM/18259 | Augmentation | MVS | Deganga | Kamdebkati | Kamdebkati | OHR | Private | 46 | 0 | 0 | 33 | Identified | Cabinet approval received vide memo no- PHE/3331/1L-55/2023 dated 01-11-2023
82 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC.(TSM/011206,SM/13313) | TSM/011206 | SM/13313 | Augmentation | MVS | Hasnabad | Haripur | HARIPUR PH NO-2 | Pump House | Private | 41 | 3637 | 1725 | 3 | Possessed | Registration done
83 | NORTH 24 PARGANAS | Mallik Gheri Piped Water Supply Scheme.(TSM/014697,SM/13813) | TSM/014697 | SM/13813 | New | MVS | Minakhan | Mallick Gheri | Mallick Gheri | Pump House | Private | 95 | 315 | 212 | 4 | Possessed | Registration done
84 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC.(TSM/011200,SM/11987) | TSM/011200 | SM/11987 | Augmentation | MVS | Hasnabad | Patlikhanpur | BARUNHAT PATLIKHANPUR (Z-I) BARUNHAT PATLIKHANPUR HW site | OHR | Private | 67 | 0 | 0 | 20 | Identified | Registration Not done
85 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Donnagar PWSS to Accommodate FHTC.(TSM/011254,SM/14127) | TSM/011254 | SM/14127 | Augmentation | MVS | Barasat-II | Banubankra (P) | null | OHR | Private | 47 | 0 | 0 | 33 | Identified | null
86 | NORTH 24 PARGANAS | Paschim Huda Piped water supply scheme(TSM/016341,SM/13895) | TSM/016341 | SM/13895 | New | MVS | Bongaon | Pashchim Huda | Paschim Huda | OHR | Private | 22 | 0 | 0 | 22 | Identified | e-filing done
87 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC(TSM/010932,SM/12123) | TSM/010932 | SM/12123 | Augmentation | MVS | Hasnabad | Sadigachhi (CT) | SADIGACHI Ph no-3 | Pump House | Private | 6 | 95 | 1507 | 3 | Possessed | Registration done
88 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC(TSM/011166,SM/12276) | TSM/011166 | SM/12276 | Augmentation | MVS | Bagda | Amdob | Bansghata | OHR | Private | 105 | 0 | 0 | 9 | Identified | e-filing done.
89 | NORTH 24 PARGANAS | SURFACE BASED PWSS FOR BARASAT-II BLOCK(TSM/018399,SM/19040) | TSM/018399 | SM/19040 | Augmentation | MVS | Barasat-II | Nababpur | null | CWR | Vested | 183 | 1 | 280 | 60 | Identified | null
90 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC(TSM/011177,SM/11699) | TSM/011177 | SM/11699 | Augmentation | SVS | Sandeshkhali-II | Sitalia | Dulduli Pump house no-2 | Pump House | Private | 41 | 3404 | 762 | 6 | Possessed | Registration done
91 | NORTH 24 PARGANAS | Niruli Abad Piped Water Supply Scheme.(TSM/014701,SM/12716) | TSM/014701 | SM/12716 | New | MVS | Minakhan | Niruli Abad | Niruli Abad (HW site & Ph no- 1) | OHR | Private | 145 | 3659 | 101 | 3 | Possessed | Registration done
92 | NORTH 24 PARGANAS | Pipuldaha Piped Water Supply Scheme.(TSM/014691,SM/12721) | TSM/014691 | SM/12721 | New | MVS | Minakhan | Pipuldaha | Bamanpukur HW site & Ph no- 1 | OHR | Private | 55 | 181 | 471 | 24 | Possessed | Registration done
93 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Kumarjole(TSM/009738,SM/10302) | TSM/009738 | SM/10302 | Augmentation | MVS | Minakhan | Kumarjol | Kumarjole OHR | OHR | Private | 77 | 3568 | 81 | 32 | Possessed | Registration done
94 | NORTH 24 PARGANAS | Uchildaha Piped water supply scheme(TSM/014828,SM/13815) | TSM/014828 | SM/13815 | New | SVS | Minakhan | Uchildaha | Uchildaha | Pump House | Private | 94 | 0 | 2229 | 3 | Possessed | Registration done
95 | NORTH 24 PARGANAS | Uchildaha Piped water supply scheme(TSM/014828,SM/13815) | TSM/014828 | SM/13815 | New | SVS | Minakhan | Uchildaha | Uchildaha | OHR | Private | 94 | 1135 | 1628 | 33 | Possessed | Registration done
96 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-I to Accommodate FHTC(TSM/011107,SM/11593) | TSM/011107 | SM/11593 | Augmentation | MVS | Bongaon | Chhaygharia | Chhaygharia (Zone-I) | OHR | Private | 115 | 0 | 0 | 25 | Identified | e-filing done
97 | NORTH 24 PARGANAS | Ground Water Based Piped Water Supply Scheme for augmentation of Paikpara Zone-II in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I, P.H.E. Dte.(TSM/010666,SM/10546) | TSM/010666 | SM/10546 | Augmentation | MVS | Bongaon | Bhashanpota | Bhashanpota | OHR | Private | 60 | 0 | 0 | 33 | Identified | Land details are sent vide e-file No. DPHE-67099/10/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Abhijit Bhattacharya SS(AB)(LR).
98 | NORTH 24 PARGANAS | GHUNI Piped Water Supply Scheme(TSM/016293,SM/18537) | TSM/016293 | SM/18537 | New | SVS | Rajarhat | Ghuni | null | OHR | Vested | 23 | 1 | 1354 | 21 | Identified | null
99 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XV (Chak Chandpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (TSM/014884,SM/15818) | TSM/014884 | SM/15818 | Augmentation | MVS | Deganga | Chak Chandpur | Chak Chandpur | OHR | Private | 89 | 66 | 101 | 33 | Identified | The e-file 67099/32/2023-EEN24WSDISEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
100 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC(TSM/011167,SM/11669) | TSM/011167 | SM/11669 | Augmentation | MVS | Minakhan | Chaital | Chaital | Pump House | Private | 163 | 0 | 1059 | 4 | Identified | Bilan
101 | NORTH 24 PARGANAS | Jhikra Piped Water Supply Scheme.(TSM/014699,SM/12719) | TSM/014699 | SM/12719 | New | MVS | Minakhan | Jhikra | Jhikra HW site & Ph no- 1 | OHR | Private | 61 | 2048 | 274 | 33 | Possessed | Registration done
102 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. (TSM/015472,SM/18262) | TSM/015472 | SM/18262 | Augmentation | MVS | Deganga | Chyangdana | Chyangdana | OHR | Private | 31 | 0 | 0 | 45 | Identified | Cabinet approval received vide No.PHE/2505/1L-45/2023 Dt.22/08/2023
103 | NORTH 24 PARGANAS | Bhandarkhali Piped Water Supply Scheme(TSM/015379,SM/15827) | TSM/015379 | SM/15827 | New | SVS | Hingalganj | Bhandarkhali | Dulduli | Pump House | Private | 92 | 0 | 112 | 5 | Identified | Registration Not done
104 | NORTH 24 PARGANAS | Ambaria Piped Water Supply Scheme(TSM/015378,SM/15831) | TSM/015378 | SM/15831 | New | MVS | Hingalganj | Ambaria | Sandelerbill HW site & Ph no- 1 | OHR | Private | 94 | 426 | 335 | 33 | Possessed | Registration done
105 | NORTH 24 PARGANAS | Niruli Piped Water Supply Scheme(TSM/014715,SM/12714) | TSM/014715 | SM/12714 | New | MVS | Minakhan | Niruli | Chaital | OHR | Private | 144 | 0 | 1029 | 32 | Possessed | Registration done
106 | NORTH 24 PARGANAS | Bhandarkhali Piped Water Supply Scheme(TSM/015379,SM/15827) | TSM/015379 | SM/15827 | New | SVS | Hingalganj | Bhandarkhali | Dulduli | Intake | Private | 92 | 0 | 1 | 33 | Identified | Registration Not done
107 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Maminpur to accommodate FHTC(TSM/011081,SM/11665) | TSM/011081 | SM/11665 | Augmentation | MVS | Basirhat-II | Sitalia | MOMINPUR W/S SCHEME | Pump House | Donated | 49 | 863 | 1230 | 1000 | Identified | land acquisition is in progress.
108 | NORTH 24 PARGANAS | Khariat Abad Piped Water Supply Scheme(TSM/015513,SM/15829) | TSM/015513 | SM/15829 | New | MVS | Sandeshkhali-I | Khariat Abad | Boyermari-I Pump house no-3 | Pump House | Private | 19 | 0 | 0 | 1 | Identified | Registration Not done
109 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Chaital to accommodate FHTC(TSM/011167,SM/11669) | TSM/011167 | SM/11669 | Augmentation | MVS | Minakhan | Chaital | CHAITAL HW site | OHR | Private | 163 | 8430 | 1347 | 17 | Identified | Registration done
110 | NORTH 24 PARGANAS | Petua Dhanihati Piped Water Supply Scheme(TSM/015512,SM/15830) | TSM/015512 | SM/15830 | New | MVS | Sandeshkhali-I | Matbari Abad | Boyermari-I Pump house no-2 | Pump House | Private | 1 | 0 | 0 | 1 | Identified | Registration Not done
111 | NORTH 24 PARGANAS | Kusangra Piped Water Supply Scheme(TSM/015447,SM/15832) | TSM/015447 | SM/15832 | New | MVS | Minakhan | Kushangra | Bamanpukur | Pump House | Private | 91 | 0 | 2058 | 5 | Possessed | Registration done
112 | NORTH 24 PARGANAS | Kusangra Piped Water Supply Scheme(TSM/015447,SM/15832) | TSM/015447 | SM/15832 | New | MVS | Minakhan | Kushangra | Bamanpukur HW site & Ph no- 1 | OHR | Private | 91 | 0 | 1598 | 33 | Possessed | Registration done
113 | NORTH 24 PARGANAS | Garibpur Piped water supply scheme(TSM/016336,SM/13897) | TSM/016336 | SM/13897 | New | MVS | Bongaon | Garibpur | GARIBPUR | OHR | Private | 17 | 0 | 0 | 10 | Identified | e-filing done;
114 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Mohanpur(TSM/012029,SM/14151) | TSM/012029 | SM/14151 | Augmentation | SVS | Minakhan | Mohanpur | Uttar Kalibari PH2 (MOHANPUR (Z-II) | Pump House | Private | 139 | 7505 | 1924 | 3 | Possessed | Registration done
115 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte.(TSM/010566,SM/10607) | TSM/010566 | SM/10607 | Augmentation | MVS | Bongaon | Hanidanga | Hanidanga | OHR | Private | 119 | 0 | 0 | 33 | Identified | Cabinet approval received vide memo no- PHE/3525/1L-16/2023 dated 23-11-2023
116 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bodai Zone-II to accommodate FHTC(TSM/011276,SM/14162) | TSM/011276 | SM/14162 | Augmentation | MVS | Amdanga | Amdanga | Amdanga G.P. | OHR | Vested | 48 | 621 | 2217 | 30 | Identified | Hospital Land. Memo issued to ADM(LR) for IDT
117 | NORTH 24 PARGANAS | TARULIA Piped Water Supply Scheme(TSM/016290,SM/18598) | TSM/016290 | SM/18598 | New | MVS | Rajarhat | Tarulia | null | OHR | Private | 21 | 649 | 70 | 15 | Identified | null
118 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Dakshin Bhebia Zone-I to accommodate FHTC(TSM/010932,SM/12123) | TSM/010932 | SM/12123 | Augmentation | MVS | Hasnabad | Dakshin Bhebia | SADIGACHI OHR | OHR | Private | 17 | 3529 | 19 | 28 | Possessed | Registration done
119 | NORTH 24 PARGANAS | Kachurhula Zone-II Piped Water Supply Scheme(TSM/015445,SM/13445) | TSM/015445 | SM/13445 | New | MVS | Minakhan | Kachurhula | Atpukur HW site & Ph no- 1 | OHR | Private | 99 | 0 | 0 | 1 | Identified | Registration Not done
120 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Matiagachha PWSS to Accommodate FHTC.(TSM/011247,SM/13446) | TSM/011247 | SM/13446 | Augmentation | SVS | Barasat-II | Matiagachha | Kirtipur-II G.P. | OHR | Private | 187 | 232 | 2217 | 30 | Identified | Land selling consent letter from owner has been received. Mutation of land in progress.
121 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XI (Jhikra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015092,SM/18261) | TSM/015092 | SM/18261 | Augmentation | MVS | Deganga | Jhikra | Jhikra | OHR | Vested | 101 | 0 | 0 | 45 | Identified | IDT in process.
122 | NORTH 24 PARGANAS | Ghipukuria Piped Water Supply Scheme.(TSM/014711,SM/12718) | TSM/014711 | SM/12718 | New | MVS | Minakhan | Ghipukuria | Chaital Pump house no-2 | Pump House | Private | 161 | 0 | 17 | 5 | Identified | Registration Not done
123 | NORTH 24 PARGANAS | KOLA Piped Water Supply Scheme(TSM/016122,SM/18591) | TSM/016122 | SM/18591 | New | MVS | Barasat-II | Kola | null | OHR | Private | 205 | 1 | 589 | 28 | Identified | null
124 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansghata to accommodate FHTC(TSM/011166,SM/12276) | TSM/011166 | SM/12276 | Augmentation | MVS | Bagda | Amdob | Bansghata | OHR | Private | 105 | 0 | 0 | 10 | Identified | e-filing done.
125 | NORTH 24 PARGANAS | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte.(TSM/011191,SM/11556) | TSM/011191 | SM/11556 | Augmentation | MVS | Barasat-I | Chaturia | CHATURIA | Pump House | Private | 34 | 0 | 0 | 5 | Identified | Cabinet approval received vide memo no- PHE/3222/1L-60/2023 dated 17-10-2023.
126 | NORTH 24 PARGANAS | Gar Shyamnagar Piped Water Supply Scheme(TSM/016489,SM/14504) | TSM/016489 | SM/14504 | New | SVS | Barrackpur-I | Garshyamnagar (CT) | Kougachi | OHR | Private | 0 | 0 | 0 | 33 | Identified | Land details are sent vide e-file No. DPHE-67099/5/2022-EEN24WSDI SEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
127 | NORTH 24 PARGANAS | Bachhra piped Water supply scheme(TSM/014837,SM/12712) | TSM/014837 | SM/12712 | New | MVS | Minakhan | Bachhra | Mohanpur | Pump House | Private | 142 | 394 | 348 | 3 | Possessed | Registration done
128 | NORTH 24 PARGANAS | Augmentation of Bermajur Piped water supply scheme(TSM/018703,SM/14511) | TSM/018703 | SM/14511 | Augmentation | SVS | Sandeshkhali-II | Bermajur | BERMAJUR PH 2 | Pump House | Private | 16 | 49 | 1638 | 12 | Possessed | Registration done
129 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-5 Piped Water Supply Scheme(TSM/015722,SM/13892) | TSM/015722 | SM/13892 | Augmentation | MVS | Deganga | Kaukepara | Berachampa-I G.P. | OHR | Private | 64 | 2023 | 3611 | 30 | Identified | Land selling consent letter from owner has been received. Mutation in progress.
130 | NORTH 24 PARGANAS | Garibpur Piped water supply scheme(TSM/016336,SM/13897) | TSM/016336 | SM/13897 | New | MVS | Bongaon | Garibpur | GARIBPUR | OHR | Private | 17 | 0 | 0 | 10 | Identified | e-filing done;
131 | NORTH 24 PARGANAS | Phulbari Abad Piped Water Supply Scheme.(TSM/014714,SM/12717) | TSM/014714 | SM/12717 | New | MVS | Minakhan | Bagchar Abad | Champali | Pump House | Private | 147 | 0 | 0 | 1 | Identified | Registration Not done
132 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Champali to accommodate FHTC(TSM/010452,SM/10584) | TSM/010452 | SM/10584 | Augmentation | MVS | Minakhan | Chanpali | CHAMPALI OHR | OHR | Private | 150 | 0 | 0 | 1 | Identified | Registration Not done
133 | NORTH 24 PARGANAS | Jhikra Piped Water Supply Scheme.(TSM/014699,SM/12719) | TSM/014699 | SM/12719 | New | MVS | Minakhan | Jhikra | Laugachi Abad Pump house no-2 | Pump House | Private | 61 | 888 | 448 | 3 | Possessed | Registration done
134 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Sahebkhali to accommodate FHTC(TSM/010949,SM/12278) | TSM/010949 | SM/12278 | Augmentation | MVS | Hingalganj | Sahebkhali | Natunhat HW SITE | OHR | Private | 110 | 0 | 0 | 1 | Identified | Registration Not done
135 | NORTH 24 PARGANAS | Uchildaha Piped water supply scheme(TSM/014828,SM/13815) | TSM/014828 | SM/13815 | New | SVS | Minakhan | Uchildaha | Uchildaha | Pump House | Private | 94 | 1523 | 2516 | 3 | Possessed | Registration done
136 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/013336,SM/18258) | TSM/013336 | SM/18258 | Augmentation | MVS | Barasat-I | Sikdespukhuria | Sikdesh Pukuria | OHR | Private | 95 | 0 | 0 | 9 | Identified | e-File sent vide No. DPHE-67099/21/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
137 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalupur to Accommodate FHTC(TSM/011108,SM/11631) | TSM/011108 | SM/11631 | Augmentation | MVS | Bongaon | Kalupur | KALUPUR | OHR | Private | 151 | 0 | 0 | 30 | Identified | ADM(LA), N24P
138 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bergum to accommodate FHTC(TSM/010006,SM/10514) | TSM/010006 | SM/10514 | Augmentation | MVS | Habra-I | Bergum | G.P. Bergum II | Pump House | Private | 139 | 0 | 3452 | 3 | Identified | e-filing done.
139 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IA-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011949,SM/12728) | TSM/011949 | SM/12728 | Augmentation | MVS | Barrackpur-II | Chak Kanthalia | Chak Kanthalia | OHR | Vested | 6 | 0 | 0 | 36 | Identified | Already possession done.
140 | NORTH 24 PARGANAS | Mallik Gheri Piped Water Supply Scheme.(TSM/014697,SM/13813) | TSM/014697 | SM/13813 | New | MVS | Minakhan | Muchikhola | Mallick Gheri | Pump House | Private | 96 | 0 | 202 | 4 | Possessed | Registration done
141 | NORTH 24 PARGANAS | Mallik Gheri Piped Water Supply Scheme.(TSM/014697,SM/13813) | TSM/014697 | SM/13813 | New | MVS | Minakhan | Mallick Gheri | Mallick Gheri (HW site & Ph no- 1) | OHR | Private | 95 | 4766 | 254 | 32 | Possessed | Registration done
142 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC(TSM/011169,SM/11535) | TSM/011169 | SM/11535 | Augmentation | MVS | Bongaon | Chhaygharia | Chhaygharia (Zone-II) | OHR | Private | 115 | 0 | 0 | 0 | Identified | e-filing
143 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-V/B (Gopalpur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011602,SM/12730) | TSM/011602 | SM/12730 | Augmentation | MVS | Barasat-I | Panchuria | null | OHR | Private | 129 | 970 | 690 | 34 | Identified | Land identified
144 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC.(TSM/011200,SM/11987) | TSM/011200 | SM/11987 | Augmentation | MVS | Hasnabad | Chanpatala | BARUNHAT PATLIKHANPUR Ph no-2 | Pump House | Private | 64 | 7905 | 1368 | 3 | Possessed | Registration done
145 | NORTH 24 PARGANAS | Atpukur Zone-II Piped Water Supply Scheme(TSM/015451,SM/13510) | TSM/015451 | SM/13510 | New | SVS | Minakhan | Atpukur | DK Sastitala (Pump house no-2) | Pump House | Private | 100 | 1256 | 815 | 3 | Possessed | Registration done
146 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-IV (Chakla) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/014883,SM/12383) | TSM/014883 | SM/12383 | Augmentation | MVS | Deganga | Chakla | Chakla | OHR | Vested | 52 | 0 | 0 | 24 | Identified | IDT in process.
147 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Barunhat Patlikhanpur to accommodate FHTC.(TSM/011200,SM/11987) | TSM/011200 | SM/11987 | Augmentation | MVS | Hasnabad | Barunhat | BARUNHAT PATLIKHANPUR Ph no-1 | Pump House | Private | 65 | 7850 | 2966 | 3 | Possessed | Registration done
148 | NORTH 24 PARGANAS | Kaugachhi Zone-III Piped Water Supply Scheme(TSM/016342,SM/14502) | TSM/016342 | SM/14502 | New | SVS | Barrackpur-I | Kaugachhi (CT) | NOAPARA | OHR | Private | 0 | 0 | 0 | 0 | Not Identified | null
149 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-C (Dariapur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011897,SM/12564) | TSM/011897 | SM/12564 | Augmentation | MVS | Amdanga | Dariapur | Dariapur | OHR | Private | 29 | 0 | 0 | 33 | Identified | Cabinet approval received vide No.PHE/1448/1L-27/2023 Dt. 07/06/2023
150 | NORTH 24 PARGANAS | Chutkia Radhanagar Piped Water Supply Scheme(TSM/015450,SM/13524) | TSM/015450 | SM/13524 | New | MVS | Minakhan | Chutkia Radhanagar | Sankardaha | Pump House | Private | 73 | 102 | 252 | 5 | Possessed | Registration done
151 | NORTH 24 PARGANAS | Chutkia Radhanagar Piped Water Supply Scheme(TSM/015450,SM/13524) | TSM/015450 | SM/13524 | New | MVS | Minakhan | Chutkia Radhanagar | Chutkia Radhanagar (HW site & Ph no- 1) | OHR | Private | 73 | 673 | 292 | 33 | Possessed | Registration done
152 | NORTH 24 PARGANAS | Dakshin Akhratala Piped Water Supply Scheme(TSM/015754,SM/18617) | TSM/015754 | SM/18617 | New | SVS | Sandeshkhali-I | Dashin Akhratala | Nazat-II Pump house no-2 | Pump House | Private | 23 | 0 | 225 | 5 | Possessed | Registration Not done
153 | NORTH 24 PARGANAS | Kachurhula Zone-I Piped Water Supply Scheme(TSM/015511,SM/13522) | TSM/015511 | SM/13522 | New | SVS | Minakhan | Kachurhula | Atpukur Pump house no-2 | Pump House | Private | 99 | 0 | 0 | 1 | Identified | Registration Not done
154 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011826,SM/11971) | TSM/011826 | SM/11971 | Augmentation | MVS | Amdanga | Pashardanga | Pashardanga | OHR | Private | 10 | 0 | 0 | 33 | Identified | Cabinet approval received vide No.PHE/2503/1L-52/2022 Dt.22/08/2023
155 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC.(TSM/011206,SM/13313) | TSM/011206 | SM/13313 | Augmentation | MVS | Hasnabad | Haripur | HARIPUR OHR & PH 1 | Pump House | Private | 41 | 2623 | 1745 | 30 | Possessed | Registration done
156 | NORTH 24 PARGANAS | SULANGGARI Piped Water Supply Scheme(TSM/016291,SM/14634) | TSM/016291 | SM/14634 | New | SVS | Rajarhat | Sulanggari | null | OHR | Private | 22 | 448 | 623 | 20 | Identified | null
157 | NORTH 24 PARGANAS | Kharibaria Piped Water Supply Scheme.(TSM/015444,SM/13519) | TSM/015444 | SM/13519 | New | MVS | Minakhan | Kharibiaria | Dhuturdaha | Pump House | Private | 76 | 0 | 614 | 33 | Possessed | Registration done
158 | NORTH 24 PARGANAS | Hatbhanga Piped Water Supply Scheme(TSM/015443,SM/13525) | TSM/015443 | SM/13525 | New | MVS | Minakhan | Hatbhanga | Bamanpukur | Pump House | Private | 89 | 4427 | 1523 | 3 | Possessed | Registration done
159 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-3 Piped Water Supply Scheme(TSM/015720,SM/13894) | TSM/015720 | SM/13894 | Augmentation | MVS | Deganga | Jadabpur Boalia | Berachampa -II G.P. | OHR | Vested | 70 | 1 | 1947 | 27 | Identified | Memo issued to ADM(LR) for IDT
160 | NORTH 24 PARGANAS | Augmentation of Ground water based Chandrapur Piped Water Supply scheme to Accommodate FHTC(TSM/015769,SM/14161) | TSM/015769 | SM/14161 | Augmentation | MVS | Barasat-I | Digha (CT) | GP KASHIMPUR | Pump House | Private | 94 | 86 | 674 | 4 | Identified | Consent papers submitted.
161 | NORTH 24 PARGANAS | Purana Bongaon Piped water supply scheme(TSM/016339,SM/13896) | TSM/016339 | SM/13896 | New | SVS | Bongaon | Purana Bangaon | PURATAN BONGAON | OHR | Private | 153 | 0 | 0 | 30 | Identified | e-filing done; returned back to concerned division for reverification purpose for Plot no - LR 1200
162 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC(TSM/011177,SM/11699) | TSM/011177 | SM/11699 | Augmentation | SVS | Sandeshkhali-II | Sitalia | Dulduli HW site & Ph no- 1 | OHR | Private | 41 | 730 | 105 | 33 | Possessed | Registration done
163 | NORTH 24 PARGANAS | Tapla Kusangra Piped Water Supply Scheme.(TSM/014693,SM/12720) | TSM/014693 | SM/12720 | New | MVS | Minakhan | Hatbhanga | Bamanpukur (HW site & Ph no- 1) | OHR | Private | 89 | 2471 | 209 | 24 | Possessed | Registration done
164 | NORTH 24 PARGANAS | Augmentation of Berachampa Zone-1 Piped Water Supply Scheme(TSM/015718,SM/14490) | TSM/015718 | SM/14490 | Augmentation | MVS | Deganga | Hosenpur | Deganga-I G.P. | OHR | Private | 28 | 13 | 287 | 30 | Possessed | e-filling under process.
165 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM) under command area of 'Surface water based water supply scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoning Moujas under North 24 Parganas District project' under Barasat Divisio, P.H.E. Dte. (AMDANGA BLOCK)(TSM/011507,SM/14542) | TSM/011507 | SM/14542 | Retrofitting | MVS | Amdanga | Amdanga | null | OHR | Vested | 48 | 622 | 2217 | 30 | Identified | null
166 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015251,SM/18260) | TSM/015251 | SM/18260 | Augmentation | MVS | Deganga | Kalijug Biswanathpur | Kalijug Biswanathpur | OHR | Private | 81 | 0 | 0 | 28 | Identified | Cabinet approval received vide No.PHE/2257/1L-40/2023 Dt.04/08/2023
167 | NORTH 24 PARGANAS | Augmentation of Bermajur Piped water supply scheme(TSM/018703,SM/14511) | TSM/018703 | SM/14511 | Augmentation | SVS | Sandeshkhali-II | Bermajur | BERMAJUR PH 3 | Pump House | Private | 16 | 4319 | 1199 | 4 | Possessed | Registration done
168 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-X (Basna Benapur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/015074,SM/18263) | TSM/015074 | SM/18263 | Augmentation | MVS | Deganga | Gobindapur | Basna Benapur | OHR | Private | 21 | 1869 | 638 | 34 | Identified | e-file no DPHE67099/33/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
169 | NORTH 24 PARGANAS | Augmentation of Ground water based Joypul Piped water supply scheme to accommodate FHTC(TSM/015764,SM/15324) | TSM/015764 | SM/15324 | Augmentation | SVS | Barasat-I | Joypul | joypul | OHR | Private | 126 | 312 | 4285 | 41 | Identified | cabinet approval yet to obtained.
170 | NORTH 24 PARGANAS | Katakhali Piped Water Supply Scheme(TSM/015510,SM/15826) | TSM/015510 | SM/15826 | New | SVS | Hingalganj | Sandelerbil | Sandelerbill Pump house no-3 | Pump House | Private | 95 | 0 | 586 | 5 | Possessed | Registration done
171 | NORTH 24 PARGANAS | Katakhali Piped Water Supply Scheme(TSM/015510,SM/15826) | TSM/015510 | SM/15826 | New | SVS | Hasnabad | Barunhat | Barunhat Rameswarpur HW site | OHR | Private | 65 | 0 | 157 | 33 | Possessed | Registration done
172 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC(TSM/011161,SM/12126) | TSM/011161 | SM/12126 | Augmentation | MVS | Hasnabad | Bedemari | Bhabanipur HW site | OHR | Private | 78 | 692 | 1948 | 16 | Possessed | Registration done
173 | NORTH 24 PARGANAS | Khariat Abad Piped Water Supply Scheme(TSM/015513,SM/15829) | TSM/015513 | SM/15829 | New | MVS | Sandeshkhali-I | Khariat Abad | Boyermari-I Pump house no-2 | Pump House | Private | 19 | 0 | 0 | 1 | Identified | Registration Not done
174 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte.(TSM/012003,SM/12625) | TSM/012003 | SM/12625 | Augmentation | MVS | Barasat-I | Sarbaria | Sarbaria | OHR | Vested | 112 | 0 | 0 | 30 | Identified | Already possession done.
175 | NORTH 24 PARGANAS | Ambaria Piped Water Supply Scheme(TSM/015378,SM/15831) | TSM/015378 | SM/15831 | New | MVS | Hingalganj | Ambaria | Amberia Pump house no-2 | Pump House | Private | 94 | 163 | 292 | 65 | Possessed | Registration done
176 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Mohanpur(TSM/012029,SM/14151) | TSM/012029 | SM/14151 | Augmentation | SVS | Minakhan | Mohanpur | MOHANPUR OHR | OHR | Private | 139 | 0 | 0 | 1 | Possessed | Registration Not done
177 | NORTH 24 PARGANAS | Ketarchak Piped Water Supply Scheme(TSM/015343,SM/15833) | TSM/015343 | SM/15833 | New | MVS | Hingalganj | Ketarchak | Dulduli Pump house no-2 | Pump House | Private | 104 | 757 | 277 | 5 | Possessed | Registration done
178 | NORTH 24 PARGANAS | Balibhara Piped Water Supply Scheme(TSM/016295,SM/14498) | TSM/016295 | SM/14498 | New | SVS | Barrackpur-I | Balibhara (CT) | 2nd TUBE WELL SITE | Pump House | Private | 0 | 320 | 1472 | 3 | Identified | Cabinet approval received vide No.PHE/1426/1L-12/2023 Dt.06/06/2023
179 | NORTH 24 PARGANAS | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar Noajispur, Bajitnagar, Mobarakpur & Bora Bisweswarpur mouzas (Part) within Sohai Swetpur Zone-I Piped Water Supply Scheme at Deganga Block under Barasat Division, P.H.E.Dte. (Phase-I)(TSM/007627,SM/08653) | TSM/007627 | SM/08653 | Retrofitting | MVS | Deganga | Shwetpur | null | Pump House | Private | 3 | 0 | 132 | 4 | Identified | e-filling under process.
180 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayagharia Zone- II to accommodate FHTC(TSM/011169,SM/11535) | TSM/011169 | SM/11535 | Augmentation | MVS | Bongaon | Chhaygharia | Chhaygharia (Zone-II) | OHR | Private | 115 | 0 | 0 | 29 | Identified | e-filing
181 | NORTH 24 PARGANAS | Dakshin Akhratala Piped Water Supply Scheme(TSM/015754,SM/18617) | TSM/015754 | SM/18617 | New | SVS | Sandeshkhali-I | Dashin Akhratala | Nazat-II Pump house no-3 | Pump House | Private | 23 | 0 | 33 | 5 | Possessed | Registration Not done
182 | NORTH 24 PARGANAS | Dakshin Akhratala Piped Water Supply Scheme(TSM/015754,SM/18617) | TSM/015754 | SM/18617 | New | SVS | Sandeshkhali-I | Dashin Akhratala | Nazat-II HW site & Ph no- 1 | OHR | Private | 23 | 0 | 692 | 33 | Identified | Registration Not done
183 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chandpur to accommodate FHTC.(TSM/011206,SM/13313) | TSM/011206 | SM/13313 | Augmentation | MVS | Hasnabad | Haripur | Chandpur OHR | OHR | Private | 41 | 1467 | 69 | 33 | Possessed | Registration done
184 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Talsa to accommodate(TSM/009762,SM/10693) | TSM/009762 | SM/10693 | Augmentation | MVS | Habra-II | Talsa | null | OHR | Private | 56 | 833 | 0 | 0 | Identified | Cabinet approval obtained
185 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC(TSM/010461,SM/10782) | TSM/010461 | SM/10782 | Augmentation | MVS | Habra-II | Balisha | G.P. Rajibpur-Bira | Pump House | Private | 102 | 0 | 1075 | 3 | Identified | e-filing done; document reverification needed
186 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Bhawanipur to accommodate FHTC(TSM/011161,SM/12126) | TSM/011161 | SM/12126 | Augmentation | MVS | Hasnabad | Shulkuniabad | Bhabanipur PH NO-1 | Pump House | Private | 75 | 0 | 0 | 4 | Possessed | Registration done
187 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-C (Murali) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/013336,SM/18258) | TSM/013336 | SM/18258 | Augmentation | MVS | Barasat-I | Sikdespukhuria | Sikdesh Pukuria | OHR | Private | 95 | 0 | 0 | 1 | Identified | e-File sent vide No. DPHE-67099/21/2023-EEN24WSDI SEC-DPHE. The e-file is presently lying with Swapan Kumar Barai SO(SKB)-ESTT(PHE)
188 | NORTH 24 PARGANAS | Augmentation of ground water based piped water supply scheme for Khulna Bhanderkhali Zone-II to accommodate FHTC(TSM/011177,SM/11699) | TSM/011177 | SM/11699 | Augmentation | SVS | Sandeshkhali-II | Sitalia | Bhanderkhali Pump house no-3 | Pump House | Private | 41 | 2615 | 331 | 5 | Possessed | Registration done
189 | NORTH 24 PARGANAS | Bamanpukuria Piped Water Supply Scheme.(TSM/014705,SM/13814) | TSM/014705 | SM/13814 | New | SVS | Minakhan | Bamanpukuria | Bamanpukur | Pump House | Private | 90 | 0 | 0 | 1 | Identified | Registration Not done
190 | NORTH 24 PARGANAS | Atpukur Zone-II Piped Water Supply Scheme(TSM/015451,SM/13510) | TSM/015451 | SM/13510 | New | SVS | Minakhan | Atpukur | Uttar Majherpara (HW site & Ph no- 1) | OHR | Private | 100 | 1393 | 842 | 33 | Possessed | Registration done
191 | NORTH 24 PARGANAS | Phulbari Abad Piped Water Supply Scheme.(TSM/014714,SM/12717) | TSM/014714 | SM/12717 | New | MVS | Minakhan | Bagchar Abad | Phulbari Abad (HW site & Ph no- 1) | OHR | Private | 147 | 339 | 103 | 30 | Possessed | Registration done
192 | NORTH 24 PARGANAS | Pipuldaha Piped Water Supply Scheme.(TSM/014691,SM/12721) | TSM/014691 | SM/12721 | New | MVS | Minakhan | Pipuldaha | Pipuldaha | Pump House | Private | 55 | 267 | 223 | 3 | Possessed | Registration done
193 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Chhayageria Zone-III to Accommodate FHTC(TSM/011110,SM/11594) | TSM/011110 | SM/11594 | Augmentation | MVS | Bongaon | Naraharipur | CHHAYGHARIA (ZONE-III) | OHR | Private | 110 | 0 | 0 | 0 | Identified | e-filing done
194 | NORTH 24 PARGANAS | Augmentation of Ground Water Based Piped Water Supply Scheme for Malancha Zone-I to accommodate FHTC.(TSM/011213,SM/11596) | TSM/011213 | SM/11596 | Augmentation | MVS | Minakhan | Baligari | MALANCHA 3rd TW | Pump House | Private | 85 | 4480 | 193 | 4 | Possessed | Registration done
195 | NORTH 24 PARGANAS | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII-B (Rautara) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte.(TSM/011891,SM/12565) | TSM/011891 | SM/12565 | Augmentation | MVS | Amdanga | Rautara | Rautara | OHR | Private | 39 | 0 | 0 | 40 | Identified | Cabinet approval received vide memo no- PHE/3531/1L-64/2023 dated 23-11-2023
196 | NORTH 24 PARGANAS | Augmentation of Ground water based piped water supply scheme for Bira Rajibpur to accommodate FHTC(TSM/010461,SM/10782) | TSM/010461 | SM/10782 | Augmentation | MVS | Habra-II | Tarulia | G.P. Rajibpur-Bira | Pump House | Private | 101 | 0 | 444 | 3 | Identified | e-filing done.