## A3- Land Parcel Status
A3- Land Parcel Status
SL No | District | Scheme Name | Scheme TSM Code | Scheme SM Code | Scheme Category | Scheme Coverage Type | Block | Village | Location | Purpose | Type | J.L. No. | Khatian No. | Plot No. | Area (in decimal) | Status | Remarks
1 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Purulia-II | Malthol | null | OHR | Vested | 101 | 101 | 2666 | 40 | Possessed | null
2 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Kudlung | null | OHR | Private | 196 | 376 | 2510 | 28 | Possessed | Proposal send for Cabinet Approval file no.DPHE/126/2023-PD(DPHE)-DPHE ( Computer No. 872040) dated 26/12/2023.
3 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Lipanya | null | OHR | Vested | 117 | 117 | 3951 | 33 | Identified | null
4 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Baragram | null | OHR | Vested | 68 | 120 | 29 | 21 | Possessed | null
5 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Palma | null | OHR | Vested | 131 | 131 | 4195 | 33 | Possessed | null
6 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Ranipur | null | OHR | Vested | 129 | 129 | 43 | 33 | Possessed | null
7 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Ichag | null | OHR | Vested | 55 | 55 | 3362 | 33 | Possessed | null
8 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Uhatu | null | OHR | Vested | 100 | 100 | 1413 | 33 | Possessed | null
9 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Rangametya | null | OHR | Vested | 100 | 100 | 1163 | 40 | Possessed | null
10 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Tetalda | null | OHR | Vested | 11 | 11 | 4713 | 33 | Possessed | null
11 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Bhatdi | null | OHR | Vested | 46 | 46 | 278 | 41 | Possessed | null
12 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Hatimara | null | OHR | Vested | 26 | 26 | 572 | 33 | Possessed | Part Vested
13 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Garyabhita | null | OHR | Vested | 28 | 28 | 381 | 33 | Possessed | null
14 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Ramkrishnapur alias Nutandi | null | OHR | Vested | 30 | 30 | 1710 | 17 | Possessed | null
15 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Palanja | null | OHR | Vested | 91 | 91 | 2880 | 25 | Identified | null
16 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Agharpur | null | OHR | Vested | 80 | 80 | 1912 | 33 | Identified | null
17 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Paschim Bero | null | OHR | Vested | 194 | 194 | 4930 | 40 | Possessed | null
18 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Bhanuridi | null | OHR | Vested | 108 | 108 | 1156 | 19 | Possessed | null
19 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Bhalu | null | OHR | Vested | 8 | 8 | 5 | 27 | Possessed | null
20 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Sanar | null | OHR | Vested | 91 | 91 | 1728 | 33 | Possessed | Part Vested
21 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Popo | null | OHR | Vested | 85 | 85 | 1531 | 26 | Possessed | null
22 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Nawagar | null | OHR | Vested | 263 | 263 | 263 | 33 | Possessed | null
23 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Garga | null | OHR | Vested | 22 | 22 | 292 | 33 | Possessed | null
24 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Susnidi | null | OHR | Vested | 70 | 70 | 199 | 33 | Possessed | null
25 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Dugdha | null | OHR | Vested | 20 | 20 | 1122 | 33 | Possessed | null
26 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Sindri | null | Pump House | Private | 193 | 2714 | 4269 | 63 | Possessed | Proposal send for Cabinet Approval file no.DPHE-17012/1/2023-SE(PMU-WBDWSIP) SEC-DPHE ( Computer No. 698911) dated 20/04/2023.
27 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-II | Belamu | null | OHR | Vested | 187 | 187 | 361 | 33 | Identified | null
28 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Chapaitanr | null | OHR | Vested | 88 | 88 | 545 | 33 | Identified | null
29 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Purulia-II | Loharsol | null | OHR | Vested | 60 | 60 | 731 | 40 | Possessed | null
30 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Tentulhiti | null | OHR | Vested | 56 | 56 | 3449 | 33 | Possessed | Part Vested
31 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Asurbandh | null | OHR | Vested | 61 | 61 | 2314 | 31 | Possessed | null
32 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Dhulabad | null | OHR | Vested | 86 | 86 | 1025 | 33 | Possessed | Part Vested
33 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Phusrabaid | null | OHR | Vested | 123 | 123 | 1079 | 33 | Possessed | null
34 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Ranipur | null | OHR | Vested | 129 | 129 | 45 | 34 | Possessed | null
35 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Matipur | null | OHR | Vested | 90 | 90 | 1904 | 17 | Possessed | null
36 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Dubrajpur | null | OHR | Vested | 68 | 68 | 369 | 33 | Possessed | null
37 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Salberya | null | OHR | Vested | 89 | 89 | 1397 | 33 | Possessed | null
38 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Senara | null | OHR | Vested | 185 | 185 | 5617 | 40 | Possessed | null
39 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Pabra | null | OHR | Vested | 57 | 57 | 314 | 41 | Possessed | null
40 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Rautara | null | OHR | Vested | 21 | 21 | 2679 | 33 | Possessed | Part Vested
41 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Ramkrishnapur alias Nutandi | null | OHR | Vested | 30 | 30 | 1245 | 33 | Possessed | Part Vested
42 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Sanar | null | OHR | Vested | 91 | 91 | 1658 | 33 | Possessed | Part Vested
43 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Metyala | null | OHR | Vested | 112 | 67 | 321 | 13 | Possessed | null
44 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Bansa | null | OHR | Vested | 35 | 35 | 973 | 33 | Possessed | null
45 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Shyamnagar Alias Jajodih | null | OHR | Vested | 84 | 84 | 32 | 33 | Possessed | null
46 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Baredi | null | OHR | Vested | 86 | 86 | 2221 | 33 | Possessed | null
47 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Latajharna | null | OHR | Vested | 134 | 134 | 51 | 30 | Possessed | null
48 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Madhuban | null | OHR | Vested | 123 | 123 | 338 | 30 | Possessed | null
49 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Malti | null | OHR | Vested | 78 | 78 | 520 | 33 | Possessed | null
50 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Kalimati | null | OHR | Vested | 32 | 32 | 1129 | 33 | Possessed | null
51 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Kukrudabar | null | OHR | Vested | 56 | 56 | 501 | 30 | Possessed | null
52 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Bhamragora | null | OHR | Vested | 95 | 95 | 1223 | 27 | Possessed | null
53 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | BAGHUBERA | null | Pump House | Vested | 111 | 1 | 1615 | 23 | Possessed | Letter sent to Additional District Magistrate(LR) for IDT vide memo no-699/W-09(M)/JICA/PMU/2013 dated 15-03-2023. work started. Letter send to LRC from ADM(LR) vide memo no-IV/34(124)/3020/R/DL&LRO/PRL/22 dated 04.09.2023
54 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Patkita | null | OHR | Vested | 90 | 90 | 159 | 35 | Possessed | null
55 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Moraidih | null | OHR | Vested | 88 | 88 | 270 | 33 | Possessed | null
56 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Dugdha | null | OHR | Vested | 20 | 20 | 1122 | 33 | Possessed | null
57 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Karru | null | OHR | Vested | 53 | 53 | 4193 | 33 | Possessed | null
58 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Maunia | null | OHR | Vested | 35 | 35 | 774 | 37 | Possessed | null
59 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Sarberia | null | OHR | Private | 206 | 921 | 352 | 27 | Possessed | Proposal send for Cabinet Approval file no.DPHE-17012/1/2023-SE(PMU-WBDWSIP) SEC-DPHE ( Computer No. 698911) dated 20/04/2023.
60 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-II | Urmad | null | OHR | Vested | 170 | 170 | 102 | 33 | Identified | null
61 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Tanasi | null | OHR | Vested | 90 | 90 | 1077 | 33 | Identified | null
62 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Singhagara | null | OHR | Vested | 45 | 45 | 627 | 33 | Identified | null
63 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Damru | null | OHR | Vested | 8 | 8 | 2023 | 33 | Possessed | null
64 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Keshargarh | null | OHR | Vested | 54 | 54 | 4114 | 17 | Possessed | null
65 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Chirugora | null | OHR | Vested | 25 | 25 | 973 | 30 | Possessed | null
66 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Lakshanpur | null | OHR | Vested | 40 | 40 | 1597 | 17 | Possessed | null
67 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Kesra | null | OHR | Vested | 34 | 34 | 1488 | 18 | Possessed | null
68 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Metyala | null | OHR | Vested | 112 | 112 | 2122 | 40 | Possessed | null
69 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Kana | null | OHR | Vested | 25 | 25 | 218 | 33 | Possessed | null
70 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Purulia-II | Mahudal Bazar | null | OHR | Vested | 84 | 84 | 3280 | 40 | Possessed | null
71 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Dhaska | null | OHR | Vested | 141 | 141 | 586 | 52 | Possessed | null
72 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Phusrabaid | null | OHR | Vested | 123 | 123 | 2570 | 40 | Possessed | null
73 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Sankupi | null | OHR | Vested | 127 | 127 | 3465 | 33 | Possessed | null
74 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Latar | null | OHR | Vested | 52 | 52 | 752 | 33 | Possessed | null
75 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Kushaldi | null | OHR | Vested | 47 | 47 | 2977 | 33 | Possessed | null
76 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Nowadih | null | OHR | Private | 163 | 92538 | 139 | 32 | Possessed | Proposal send for Cabinet Approval file no.DPHE-17012/1/2023-SE(PMU-WBDWSIP) SEC-DPHE ( Computer No. 698911) dated 20/04/2023.
77 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Raidih | null | OHR | Vested | 106 | 565 | 1669 | 25 | Possessed | Letter sent to Additional District Magistrate(LR) for IDT vide memo no-2488/W-09(M)/JICA/PMU/2013 dated 18-08-2023.
78 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Baratalpat | null | OHR | Vested | 39 | 39 | 976 | 25 | Possessed | null
79 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Kendapara | null | OHR | Vested | 31 | 31 | 1286 | 23 | Possessed | null
80 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Karma | null | OHR | Vested | 20 | 20 | 305 | 33 | Possessed | null
81 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Gunja | null | OHR | Vested | 81 | 81 | 2695 | 33 | Identified | null
82 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Mirmi | null | OHR | Vested | 4 | 4 | 210 | 33 | Possessed | null
83 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Rare Kacha | null | OHR | Vested | 7 | 7 | 572 | 33 | Possessed | null
84 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Burda | null | OHR | Vested | 68 | 68 | 5894 | 41 | Possessed | null
85 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Gorsika | null | OHR | Vested | 98 | 98 | 2412 | 33 | Possessed | null
86 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Metyala | null | OHR | Vested | 112 | 112 | 2123 | 40 | Possessed | null
87 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Metyala | null | OHR | Vested | 112 | 112 | 2121 | 40 | Possessed | null
88 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Shyamsundarpur | null | OHR | Vested | 102 | 102 | 1462 | 40 | Possessed | null
89 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Senara | null | OHR | Vested | 185 | 162 | 3358 | 40 | Possessed | null
90 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Hatimara | null | OHR | Vested | 26 | 26 | 1229 | 33 | Possessed | Part Vested
91 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Bhanuridi | null | OHR | Vested | 108 | 108 | 2136 | 33 | Possessed | null
92 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Lipanya | null | OHR | Vested | 117 | 117 | 5877 | 33 | Possessed | null
93 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Lipanya | null | OHR | Vested | 117 | 117 | 4163 | 19 | Possessed | null
94 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Dhulabad | null | OHR | Vested | 86 | 86 | 1281 | 33 | Possessed | Part Vested
95 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Palma | null | OHR | Vested | 131 | 131 | 4440 | 33 | Possessed | null
96 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Neturia | Nadiha | null | OHR | Vested | 81 | 81 | 2237 | 18 | Possessed | null
97 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Jiling | null | OHR | Private | 216 | 1566 | 2195 | 33 | Possessed | Proposal send for Cabinet Approval file no.DPHE-17012/1/2023-SE(PMU-WBDWSIP) SEC-DPHE ( Computer No. 698911) dated 20/04/2023.
98 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Gurda | null | OHR | Private | 150 | 64195 | 1198 | 29 | Possessed | Proposal send for Cabinet Approval file no.DPHE/126/2023-PD(DPHE)-DPHE ( Computer No. 872040) dated 26/12/2023.
99 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Gokulnagar | null | OHR | Vested | 103 | 1 | 430 | 30 | Possessed | Letter sent to Additional District Magistrate(LR) for IDT vide memo no-2424/W-09(M)/JICA/PMU/2013 dated 02-12-2022. Letter send to LRC from ADM(LR) vide memo no-IV/34(196)/2875/R/ADM & DL&LRO/PRL/22 dated22.08.2023
100 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Purulia-I | Dimdiha | null | OHR | Vested | 14 | 14 | 156 | 33 | Identified | null
101 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Chirkamu Alias Kirkamu | null | OHR | Vested | 14 | 14 | 1144 | 33 | Identified | null
102 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Parsia | null | OHR | Vested | 116 | 116 | 4170 | 17 | Possessed | null
103 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Nawadi | null | OHR | Vested | 96 | 96 | 670 | 17 | Possessed | null
104 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Baragram | null | OHR | Vested | 68 | 68 | 3358 | 17 | Possessed | null
105 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Sijumakhna | null | OHR | Vested | 49 | 49 | 216 | 17 | Possessed | null
106 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Haludbani | null | OHR | Vested | 2 | 2 | 753 | 30 | Possessed | null
107 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Baghaband | null | OHR | Vested | 86 | 86 | 696 | 33 | Possessed | null
108 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Balarampur | Genrua | null | OHR | Vested | 54 | 54 | 5138 | 33 | Possessed | null
109 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Purulia-II | Chargali | null | OHR | Vested | 73 | 73 | 477 | 40 | Possessed | null
110 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Sonahara | null | OHR | Vested | 78 | 78 | 100 | 50 | Possessed | null
111 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Asurbandh | null | OHR | Vested | 61 | 61 | 2207 | 33 | Possessed | null
112 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bagmundi | Sosokhas | null | OHR | Vested | 24 | 24 | 775 | 33 | Possessed | null
113 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Chitra | null | OHR | Vested | 49 | 49 | 2279 | 33 | Possessed | Part Vested
114 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Para | Ranipur | null | OHR | Vested | 129 | 129 | 47 | 31 | Possessed | null
115 | PURULIA | PURULIA WATER SUPPLY PROJECT SOUTHERN SECTOR (PHASE I)(TSM/011448,SM/18333) | TSM/011448 | SM/18333 | New | MVS | Bundwan | Panrra | null | OHR | Vested | 114 | 114 | 315 | 35 | Possessed | null
116 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Tulin | null | OHR | Vested | 42 | 42 | 207 | 33 | Possessed | null
117 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-I | Tulin | null | OHR | Vested | 42 | 42 | 210 | 33 | Possessed | null
118 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-II | Damrughutu | null | OHR | Vested | 199 | 199 | 1767 | 33 | Identified | null
119 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jhalda-II | Jabar | null | OHR | Vested | 176 | 176 | 721 | 33 | Identified | null
120 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Hoangda | null | OHR | Vested | 59 | 59 | 2216 | 33 | Identified | null
121 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Jaipur | Sidhi | null | OHR | Vested | 31 | 31 | 2612 | 33 | Identified | null
122 | PURULIA | Left out Mouzas of Barabazar pipe water supply scheme(TSM/011442,SM/18319) | TSM/011442 | SM/18319 | New | MVS | Barabazar | Narayanpur | null | OHR | Private | 128 | 1 | 648 | 35 | Possessed | Documents collection under progress.
123 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Kulgara | null | OHR | Vested | 42 | 42 | 3657 | 17 | Possessed | null
124 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Hura | Jabrra | null | OHR | Vested | 33 | 33 | 603 | 17 | Possessed | null
125 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Marbedya | null | OHR | Vested | 94 | 94 | 648 | 33 | Possessed | null
126 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Madhubanpur | null | OHR | Vested | 16 | 16 | 1040 | 33 | Possessed | null
127 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Santuri | Mohanpur | null | OHR | Vested | 27 | 27 | 811 | 33 | Possessed | null
128 | PURULIA | Surface water based piped water supply scheme for Purulia District (Northern sector) (Phase-I)(TSM/012586,SM/18528) | TSM/012586 | SM/18528 | New | MVS | Raghunathpur-I | Purbba Bero | null | OHR | Vested | 195 | 195 | 1839 | 40 | Possessed | null