## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 60 | ADITYA HAZRA | 75.75 | 0 | 93
2 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone-I (Part-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001346/2022-2023 | 10101/AD | 17/01/2023 | 300 | UCON | 328.79 | 0 | 30
3 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Purba Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000407/2020-2021 | 778/KSD | 14/10/2020 | 45 | M/S KHAJABABA ENTERPRISE | 4.77 | 4.53 | 0
4 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Paschim Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000419/2020-2021 | 796/KSD | 15/10/2020 | 45 | A.S.A.CONSTRUCTION AND CONSULTANT | 3.86 | 0 | 90
5 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Paschim Para (Part) of Shibpur W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000438/2020-2021 | 824/KSD | 16/10/2020 | 45 | M/S. MOYNA ENTERPRISE | 2.72 | 0 | 0
6 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC at Uttar Paschim Para (Part) of Shibpur W/S Scheme, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000439/2020-2021 | 825/KSD | 16/10/2020 | 45 | ANANDA MAITY | 2.97 | 2.93 | 0
7 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC at Madhya Para (Part) of Shibpur W/S Scheme, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000468/2020-2021 | 1046/KSD | 19/12/2020 | 20 | SUDIP KHANRA | 3.16 | 0 | 100
8 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Madhya Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000501/2020-2021 | 1074/KSD | 19/12/2020 | 20 | M/S. PARAMESWAR ENTERPRISE | 4.74 | 4.53 | 0
9 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000709/2023-2024 | 479/AD | 24/01/2024 | 0 | Resource Division | 12.17 | 0 | 0
10 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000702/2023-2024 | 472/AD | 24/01/2024 | 0 | Resource Division | 5.42 | 0 | 0
11 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-III including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000078/2020-2021 | 5443/AD | 24/02/2021 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 341.46 | 54.78 | 90
12 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipeline for balance portion providing remaining FHTC with allied works at Zone-III of Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000373/2022-2023 | 4345/AD | 25/08/2022 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 38.85 | 0 | 50
13 | Alipore Division | Diamond Harbour Sub-Division | Re-laying of distribution pipeline (damaged portion) near Dighirpar Bazar area (in between NP 2-3,NP 5-86,NP 3-186 of Falta (Zone-III) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000826/2022-2023 | 210/DHSD | 02/08/2022 | 45 | SRIJON ENTERPRISE | 4.56 | 0 | 0
14 | Alipore Division | Diamond Harbour Sub-Division | Inter connection between secondary grid and inlet of OHR and restoration of compound area at OHR site of Falta Zone-III for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000828/2022-2023 | 211/DHSD | 02/08/2022 | 45 | SRIJON ENTERPRISE | 2.82 | 0 | 0
15 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000021/2022-2023 | 1198/AD | 30/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
16 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000848/2023-2024 | 786/AD | 03/02/2024 | 0 | Resource Division | 10.26 | 0 | 0
17 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-V including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000020/2021-2022 | 340/AD | 12/05/2021 | 365 | CONCORD ENGINEERING | 309.32 | 65.27 | 90
18 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipeline due to changing of alignment drawing as per site condition and restoration of distribution pipeline (damaged portion) due to widening of Irrigation canal along with road restoration at Zone-V of Falta Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001113/2022-2023 | 8776/AD | 21/12/2022 | 30 | TIYASHA ENTERPRISE | 33.47 | 0 | 0
19 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000439/2023-2024 | 3621/AD | 30/10/2023 | 0 | Resource Division | 19.73 | 0 | 0
20 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -4 of Dakshin Redokhali Water Supply Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000057/2022-2023 | 793/AD | 12/05/2022 | 30 | BHATTACHARJEE AND CO. | 17.97 | 0 | 100
21 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000604/2020-2021 | 842/CSD | 12/10/2020 | 45 | ARANYA ENTERPRISE | 4.74 | 0 | 0
22 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000605/2020-2021 | 843/CSD | 12/10/2020 | 45 | TITHI ENTERPRISE | 4.74 | 0 | 0
23 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000606/2020-2021 | 844/CSD | 12/10/2020 | 45 | PROTIVA CONSTRUCTION | 4.74 | 0 | 100
24 | Alipore Division | Canning Sub-division | Relaying of pipeline due to construction of PMGSY road at Dakshin Redokhali W/S Scheme in connection with FHTC work, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (SM/07629) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001017/2023-2024 | 3302/AD | 07/10/2023 | 45 | SAHANA ENTERPRISE | 41.61 | 0 | 90
25 | Alipore Division | Canning Sub-division | Repairing of pipe line and also additional pipe line is required to connect the uncovered habitations at Mouza-Herobhanga, Garkhali, Uttar Rendokhali for FHTC work of Dakshin Rendokhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001062/2021-2022 | 5297/AD | 04/01/2022 | 60 | M/S CHANDIMATA CONSTRUCTION | 33.45 | 0 | 0
26 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001190/2020-2021 | 985/CSD | 13/11/2020 | 45 | GOUTAM HALDAR (I) | 4.65 | 4.64 | 100
27 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001193/2020-2021 | 986/CSD | 13/11/2020 | 45 | SWASTIK CONSTRUCTION | 4.73 | 0 | 0
28 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001382/2020-2021 | 983/CSD | 13/11/2020 | 45 | D.R.CONSTRUCTION | 4.71 | 4.7 | 100
29 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001383/2020-2021 | 984/CSD | 13/11/2020 | 45 | D.R.CONSTRUCTION | 4.62 | 0 | 100
30 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001385/2020-2021 | 987/CSD | 13/11/2020 | 45 | M/S P. B. CONSTRUCTION | 4.79 | 0 | 100
31 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001386/2020-2021 | 988/CSD | 13/11/2020 | 45 | NANDALAL DAS | 4.58 | 0 | 100
32 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001387/2020-2021 | 989/CSD | 13/11/2020 | 45 | P.P. CONCERN | 4.66 | 0 | 0
33 | Alipore Division | Canning Sub-division | roviding Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001389/2020-2021 | 990/CSD | 13/11/2020 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 4.7 | 4.68 | 100
34 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001390/2020-2021 | 991/CSD | 13/11/2020 | 45 | ARANYA ENTERPRISE | 4.78 | 0 | 100
35 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001391/2020-2021 | 992/CSD | 13/11/2020 | 45 | TITHI ENTERPRISE | 4.72 | 0 | 100
36 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001392/2020-2021 | 993/CSD | 13/11/2020 | 45 | TITHI ENTERPRISE | 4.78 | 0 | 0
37 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001406/2021-2022 | 813/CSD | 16/09/2021 | 45 | SHARANYA CONSTRUCTION | 4.78 | 0 | 0
38 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001427/2020-2021 | 994/CSD | 13/11/2020 | 45 | PROTIVA CONSTRUCTION | 4.7 | 0 | 100
39 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001428/2020-2021 | 961/CSD | 07/11/2020 | 45 | ARANYA ENTERPRISE | 4.71 | 0 | 100
40 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001433/2020-2021 | 962/CSD | 07/11/2020 | 45 | TITHI ENTERPRISE | 4.7 | 0 | 100
41 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Dakshin Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001435/2020-2021 | 963/CSD | 07/11/2020 | 45 | TITHI ENTERPRISE | 4.69 | 0 | 100
42 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001436/2020-2021 | 964/CSD | 07/11/2020 | 45 | PROTIVA CONSTRUCTION | 4.71 | 0 | 100
43 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001523/2020-2021 | 1191/CSD | 15/12/2020 | 45 | DIPTI ENTERPRISE | 4.74 | 0 | 0
44 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001525/2020-2021 | 1192/CSD | 15/12/2020 | 45 | DIPA CHHETRI | 4.71 | 0 | 95
45 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001527/2020-2021 | 1193/CSD | 15/12/2020 | 45 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.65 | 0 | 0
46 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001534/2020-2021 | 1194/CSD | 15/12/2020 | 45 | M/S KALPANA CONSTRUCTION | 4.6 | 0 | 0
47 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Hero Bhanga of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001536/2020-2021 | 1195/CSD | 15/12/2020 | 45 | R.G. ENTERPRISE (I) | 4.51 | 0 | 0
48 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Garkhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001537/2020-2021 | 1196/CSD | 15/12/2020 | 45 | ARANYA ENTERPRISE | 4.74 | 0 | 100
49 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001538/2020-2021 | 1197/CSD | 15/12/2020 | 45 | ARANYA ENTERPRISE | 4.79 | 0 | 100
50 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001539/2020-2021 | 1198/CSD | 15/12/2020 | 45 | PROTIVA CONSTRUCTION | 4.74 | 0 | 100
51 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001540/2020-2021 | 1199/CSD | 15/12/2020 | 45 | TITHI ENTERPRISE | 4.7 | 0 | 100
52 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001541/2020-2021 | 1200/CSD | 15/12/2020 | 45 | PROTIVA CONSTRUCTION | 4.66 | 0 | 100
53 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Uttar Redokhali of Dakshin Redokhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001542/2020-2021 | 1201/CSD | 15/12/2020 | 45 | PROTIVA CONSTRUCTION | 4.61 | 0 | 100
54 | Alipore Division | Canning Sub-division | Inter connection for TW No. -1 & 2 with reservoir at Dk. Redokhali W/S Scheme, Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001609/2020-2021 | 1341/CSD | 04/01/2021 | 30 | SUKANTA HALDER | 1.17 | 0 | 90
55 | Alipore Division | Canning Sub-division | Laying of additional pipe line and Protection of pipe line at Dakshin Redokhali W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002977/2024-2025 | 34./CSD | 09/01/2025 | 30 | BHATTACHARYA ENTERPRISE | 4.63 | 0 | 0
56 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000149/2023-2024 | 840/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
57 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Srinagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001551/2021-2022 | 6727/AD | 17/03/2022 | 15 | SUDIP PRADHAN | 11.34 | 0 | 90
58 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000831/2023-2024 | 676/AD | 30/01/2024 | 0 | Resource Division | 6.62 | 0 | 0
59 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000085/2020-2021 | 5308/AD | 18/02/2021 | 365 | NATURAL RESOURCES CONSORTIUM | 89.65 | 29.55 | 77
60 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Sardarpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000090/2022-2023 | 294/CSD | 20/05/2022 | 40 | NATURAL RESOURCES CONSORTIUM | 4.84 | 0 | 87
61 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Srinagar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001999/2022-2023 | 12813/AD | 16/03/2023 | 60 | SAHANA ENTERPRISE | 52.81 | 0 | 99
62 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VIII including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based Water Supply Scheme for Falta-Mathurapur" District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000009/2022-2023 | 139/AD | 07/04/2022 | 1080 | TANMAY ROY CHOWDHURY | 277.27 | 0 | 90
63 | Alipore Division | Diamond Harbour Sub-Division | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Gazipur, Tajpur, Sasan, Pikhira, Purba Gopalpur and Fatepur Village of Zone-VIII under Falta Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000584/2022-2023 | 5860/AD | 18/10/2022 | 45 | SUPRITI ENTERPRISE | 64.93 | 0 | 55
64 | Alipore Division | Diamond Harbour Sub-Division | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Rantan, Chaluary, Niogirhat, Durbarat, Kotaldanga, Benapukur, Shibpur, Ramrampur, Mayna and Kalaria Village of Zone-VIII under Falta Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000585/2022-2023 | 5861/AD | 18/10/2022 | 45 | SUPRITI ENTERPRISE | 63.77 | 0 | 45
65 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000122/2022-2023 | 12048/AD | 27/02/2023 | 0 | Resource Division | 2.61 | 0 | 0
66 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000435/2023-2024 | 3627/AD | 30/10/2023 | 0 | Resource Division | 6.16 | 0 | 0
67 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000437/2023-2024 | 3619/AD | 30/10/2023 | 0 | Resource Division | 33.88 | 0 | 0
68 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Haradhanpur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14159) (SM/09393) (SM/08793) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000450/2025-2026 | 3568/AD | 25/07/2025 | 45 | PALASH HALDAR | 8.12 | 0 | 0
69 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000697/2023-2024 | 467/AD | 24/01/2024 | 0 | Resource Division | 10.8 | 0 | 0
70 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Companirchar W/S Scheme (Phase-A), Haradhanpur W/S Scheme (Phase-A) & Krishnanagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 519/KSD, 24.8.21, T.No. 1784/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | VCH/002604/2021-2022 | BP-2021-22-507 | 22/03/2022 | 0 | LEMNISCATE | 3.53 | 0 | 0
71 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Kakdwip Akshaynagar W/S Scheme (Phase-A), Gobindarampur W/S Scheme (Phase-A), Kashinagar W/S Scheme (Phase-A) & Srikrishnanagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001008/2021-2022 | 514/KSD | 24/08/2021 | 10 | ROY CHOWDHURY ASSOCIATES | 4.7 | 0 | 100
72 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001015/2021-2022 | 533/KSD | 01/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 3.52 | 0 | 100
73 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001016/2021-2022 | 534/KSD | 01/09/2021 | 20 | M/S R.DUTTA & CO. | 3.89 | 0 | 100
74 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kakdwip Akshaynagar (Zone-III) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001017/2021-2022 | 535/KSD | 01/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 3.89 | 0 | 100
75 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001038/2021-2022 | 2269/AD | 06/09/2021 | 7 | M/S R.DUTTA & CO. | 2.64 | 0 | 100
76 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-II) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001039/2021-2022 | 2270/AD | 06/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.48 | 0 | 100
77 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kakdwip Akshaynagar (Zone-III) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001042/2021-2022 | 2273/AD | 06/09/2021 | 7 | M/S R.DUTTA & CO. | 2.76 | 0 | 100
78 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000087/2022-2023 | 5590/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
79 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000266/2023-2024 | 3065/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
80 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000379/2023-2024 | 3565/AD | 18/10/2023 | 0 | Resource Division | 5.95 | 0 | 0
81 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000596/2023-2024 | 95/AD | 03/01/2024 | 0 | Resource Division | 27.86 | 0 | 0
82 | Alipore Division | Raidighi Sub-Division | PERMANENT RESTORATION OF TRENCH CUTTING FOR LAYING WATER PIPELINE BY PHE DTE ALONG WITH THE ROAD (HARD CRIST & HARD SHOULDER) AT RIGHT SIDE BETWEEN CH. 0.200 KMP (BISHNUPUR PWD OFFICE) TO CH. 2.600 KMP (LALPUR) & CH. 4.200 KMP (JALGHATA) TO CH. 6.000 KMP (KATANDIGHI) OF PURBA BISHNUPUR-RAIDIGHI ROAD DURING CHEYEAR 2022-23 UNDER JOYNAGAR SUB-DIVISION, PW DTE. | Assistant Engineer, Raidighi sub division |  | BILL/02278/2023-2024 | BP-2023-24-825 | 18/12/2023 | 0 | PUBLIC WORKS DEPARTMENT | 135.47 | 0 | 0
83 | Alipore Division | Raidighi Sub-Division | Laying distribution system for providing FHTC at Zone - VIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000397/2024-2025 | 3160/AD | 30/07/2024 | 30 | KAMALA ENTERPRISE (I) | 20.49 | 0 | 0
84 | Alipore Division | Raidighi Sub-Division | Hydraulic testing and disinfection of laying distribution system including excavation of trial pit of piped water supply at Zone- VIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000995/2023-2024 | 292/RSD | 29/09/2023 | 60 | M/S. GANGA ENTERPRISE | 1.89 | 0 | 100
85 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000011/2022-2023 | 1172/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
86 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000023/2021-2022 | 5660/AD | 27/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
87 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000080/2022-2023 | 5551/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
88 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-D (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000155/2021-2022 | 408/KSD | 07/07/2021 | 15 | M/S KALIPADA JANA | 4.49 | 0 | 100
89 | Alipore Division | Kakdwip Sub-Division | Surging of 2 no. Big dia Tubewell under Debnibus Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000598/2022-2023 | 5923/AD | 19/10/2022 | 15 | S.K.GOLUI | 6.1 | 0 | 100
90 | Alipore Division | Kakdwip Sub-Division | Operation and maintenance of distribution system including rising main for Debnibus Piped Water Supply Scheme of Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [Period from 01.12.2021 to 30.11.2022] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000908/2021-2022 | 768/KSD | 29/11/2021 | 365 | ANANTA KUMAR GIRI | 4.75 | 0 | 100
91 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001031/2021-2022 | 541/KSD | 01/09/2021 | 20 | LEMNISCATE | 4.59 | 0 | 100
92 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block - Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001048/2021-2022 | 2287/AD | 07/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.34 | 0 | 100
93 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000287/2023-2024 | 3083/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
94 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000546/2023-2024 | 10/AD | 02/01/2024 | 0 | Resource Division | 17.88 | 0 | 0
95 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Sankarpur piped water supply scheme ( Mathurapur-I, Zone-XIV) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000571/2021-2022 | 3672/AD | 22/11/2021 | 365 | M/S B.M. CONSTRUCTION | 82 | 0 | 100
96 | Alipore Division |  | Parallel extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Birampur mouza (Node No. 176-177-178-179-180-181-182-184-185) of Sankarpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001586/2021-2022 | 770/RSD | 28/03/2022 | 60 | M/S B.M. CONSTRUCTION | 4.78 | 0 | 100
97 | Alipore Division |  | Extension of pipe line for providing FHTC at Zone-XIV of Mathurapur - I Block (Andharmanik & Sankarpur purba para) under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001767/2021-2022 | 625/RSD | 29/12/2021 | 15 | M/S M. ENTERPRISE | 4.75 | 0 | 100
98 | Alipore Division |  | Dismantling and road restoration in connection with Laying distrubution system of piped water supply at Zone - XIV (Mouza Birampur & Dakhin Janardanpur) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (PART - A) |  |  | ORD/001793/2022-2023 | 927/RSD | 10/03/2023 | 30 | M/S B.N.ENTERPRISE | 4.82 | 0 | 100
99 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 5658/AD | 27/01/2022 | 0 | Resource Division | 1.19 | 0 | 0
100 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000643/2023-2024 | 247/AD | 15/01/2024 | 0 | Resource Division | 12.06 | 0 | 0
101 | Alipore Division |  | Laying distribution system of piped water supply at Zone-IV of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000480/2021-2022 | 2438/AD | 16/09/2021 | 60 | M/S KALPANA CONSTRUCTION | 50.59 | 0 | 95
102 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Ranaghat piped water supply scheme ( Mathurapur-I, Zone-IV) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) |  |  | ORD/000570/2021-2022 | 3671/AD | 22/11/2021 | 365 | RANADHIR SINHA | 61.42 | 0 | 100
103 | Alipore Division |  | Parallel distribution pipeline to provide FHTC at Purba Ranaghata mouza under Zone-IV of Mathurapur-I block, under Surface water based water supply scheme Falta- Mathurapur of Raidighi Sub-Division under Alipore Division, PHE Dte. |  |  | ORD/001134/2022-2023 | 599/RSD | 23/12/2022 | 30 | SUPER CONSTRUCTION | 4.53 | 0 | 95
104 | Alipore Division |  | Estimate for parallel distribution line for providing FHTC at Purba Ranaghata W/S scheme of Mathurapur - I Block under ?Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas? under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001772/2021-2022 | 630/RSD | 29/12/2021 | 15 | M/S G.M. ASSOCIATES | 4.79 | 0 | 100
105 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000022/2021-2022 | 5659/AD | 27/01/2022 | 0 | Resource Division | 1 | 0 | 0
106 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000604/2023-2024 | 234/AD | 11/01/2024 | 0 | Resource Division | 9.69 | 0 | 0
107 | Alipore Division |  | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber under Krishnarampur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000219/2022-2023 | 3060/AD | 13/07/2022 | 30 | KAKALI ENTERPRISE | 8.06 | 0 | 100
108 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/05/2024 to 30/06/2024. |  |  | ORD/000498/2024-2025 | 559A/RSD | 28/04/2024 | 61 | HEMANTA MISTRY | 0.8 | 0 | 0
109 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/07/2024 to 31/08/2024. |  |  | ORD/000524/2024-2025 | 612/RSD | 28/06/2024 | 61 | HEMANTA MISTRY | 0.8 | 0 | 0
110 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/09/2024 to 31/10/2024. |  |  | ORD/000525/2024-2025 | 685/RSD | 29/08/2024 | 61 | HEMANTA MISTRY | 0.8 | 0 | 0
111 | Alipore Division |  | Laying distribution system of piped water supply at Zone- X of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000658/2024-2025 | 4204/AD | 23/10/2024 | 60 | R.S.CONSTRUCTION CO. | 38.62 | 0 | 0
112 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) |  |  | ORD/001199/2021-2022 | 5725/AD | 31/01/2022 | 365 | SUPRITI ENTERPRISE | 106.12 | 0 | 100
113 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.03.2023 to 30.04.2023 (Two) Months] |  |  | ORD/002426/2022-2023 | 901/RSD | 28/02/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
114 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/05/2023 to 30/06/2023 (Two) Months] |  |  | ORD/003171/2023-2024 | 48/RSD | 28/04/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
115 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/07/2023 to 31/08/2023 (Two) Months] |  |  | ORD/003172/2023-2024 | 117/RSD | 28/06/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
116 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/09/2023 to 31/10/2023 (Two) Months] |  |  | ORD/003173/2023-2024 | 255/RSD | 29/08/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
117 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/11/2023 to 31/12/2023 (Two) Months] |  |  | ORD/003174/2023-2024 | 335A/RSD | 30/10/2023 | 61 | SANKAR HALDER | 0.8 | 0 | 0
118 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/01/2024 to 29/02/2024 (Two) Months] |  |  | ORD/003175/2023-2024 | 419/RSD | 22/12/2023 | 62 | SANKAR HALDER | 0.8 | 0 | 0
119 | Alipore Division |  | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/03/2024 to 30/04/2024 (Two) Months] |  |  | ORD/003176/2023-2024 | 495A/RSD | 28/02/2024 | 60 | SANKAR HALDER | 0.8 | 0 | 0
120 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 5552/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
121 | Alipore Division |  | HIRE CHARGES BILL FOR VEHICLE NO. WB-19J-6364 |  |  | BILL/02359/2023-2024 | BP-2023-24-867 | 29/12/2023 | 0 | PINTU MONDAL | 1.08 | 0 | 0
122 | Alipore Division |  | HIRE CHARGES BILL OF VEHICLE NO WB-19G-0520 FOR THE MONTH FROM MAY'23 TO AUG'23 |  |  | BILL/02579/2023-2024 | BP-2023-24-698 | 18/11/2023 | 0 | AVIK HALDER | 1.54 | 0 | 0
123 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-I, Zone-XVI (Payla Bhagabanpur PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/001147/2021-2022 | 5535/AD | 20/01/2022 | 365 | FORTUNE ENGINEERING | 18.27 | 0 | 100
124 | Alipore Division |  | Hiring Charges of 1No Motor Cab (Diesel) for the Office fo Assistant Engineer. RWS, Alipore Sub-Division. P.H.E. Dte w.e.f. 01/03/2023 to 31/08/2023) |  |  | ORD/001717/2022-2023 | 757/RWS | 21/02/2023 | 181 | AVIK HALDER | 0.86 | 0 | 20
125 | Alipore Division |  | Remodeling of laying distribution system of piped water supply at Zone- XVI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/002229/2023-2024 | 921/AD | 08/02/2024 | 30 | KARMAKAR CONSTRUCTION | 17.1 | 0 | 90
126 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000020/2021-2022 | 5626/AD | 25/01/2022 | 0 | Resource Division | 1.39 | 0 | 0
127 | Alipore Division | Raidighi Sub-Division | Hydraulic testing and disinfection of laying distribution system including excavation of trial pit of piped water supply at Zone- XIV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000996/2023-2024 | 293/RSD | 29/09/2023 | 60 | M/S. GANGA ENTERPRISE | 2.44 | 0 | 100
128 | Alipore Division | Raidighi Sub-Division | Protection work for pipe lines at Radhakantapur Abad W/S Scheme (Node point 4-5, 3-4, 6-7, 150-151, 154-155, 73-74, 79-80), modified as Zone- XIV of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001906/2023-2024 | 435/RSD | 08/01/2024 | 60 | M/S. M.M. ENTERPRISE | 4.71 | 0 | 0
129 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10534 & SM/15506) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001930/2024-2025 | 109/AD | 08/01/2025 | 60 | A.K. INDUSTRIES | 179.67 | 0 | 0
130 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | RTOR000655/2023-2024 | 259/AD | 15/01/2024 | 0 | Resource Division | 10.9 | 0 | 0
131 | Alipore Division | Kakdwip Sub-Division | Retrofitting of Distribution System including Providing Functional Household Tap Connection (FHTC) to the households of Haripur Water Supply Scheme, Block ¿ Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001568/2021-2022 | 6830/AD | 23/03/2022 | 45 | BOSE & CO. | 115.98 | 0 | 80
132 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000795/2023-2024 | 640/AD | 30/01/2024 | 0 | Resource Division | 7.2 | 0 | 0
133 | Alipore Division | Canning Sub-division | Laying of Pipeline to connect the uncovered habitations of Atharabenki W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001577/2022-2023 | 11348/AD | 11/02/2023 | 90 | SAMSUL ENTERPRISE | 130.98 | 0 | 95
134 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 16 (sixteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Athara Beki Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001591/2021-2022 | 6962/AD | 29/03/2022 | 120 | SAMSUL ENTERPRISE | 253.28 | 0 | 94
135 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Atharabanki W/S Scheme for 365 Days during financial year 2020-2021 and 2021-2022 under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001765/2021-2022 | 710/CSD | 24/08/2021 | 365 | MAA LAXMI ENTERPRISE | 4.78 | 0 | 73
136 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000085/2022-2023 | 5548/AD | 29/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
137 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Debnibus, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000274/2023-2024 | 1424/AD | 13/07/2023 | 45 | K.P. CONSTRUCTION | 45.78 | 0 | 100
138 | Alipore Division | Kakdwip Sub-Division | Construction Platform with laying distribution system for providing FHTC, construction of Rising Main, Road Restoration for Augmentation of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000407/2024-2025 | 3190/AD | 31/07/2024 | 75 | K.P. CONSTRUCTION | 89.87 | 0 | 0
139 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of tubewell at 4th tubewell site of Namkhana W/S scheme under JJM, Block : Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000431/2022-2023 | 204/KSD | 01/06/2022 | 7 | SIMPLEX DRILLING CO. | 0.87 | 0 | 100
140 | Alipore Division | Kakdwip Sub-Division | Construction of brick platform, Road Restoration, for Augmentation of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-III) (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000460/2024-2025 | 3419/AD | 21/08/2024 | 45 | ANANTA KUMAR GIRI | 45.45 | 0 | 60
141 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DEBNIBAS PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000486/2022-2023 | 300/AD | 12/04/2022 | 45 | M/S R.DUTTA & CO. | 8.18 | 0 | 100
142 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. existing big dia Tubewell of Ramtanunagar, Block- Kakdwip and Debnibus W/S Scheme, Block- Namkhana for smooth water supply in existing FHTC under JJM under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000508/2024-2025 | 3608/AD | 06/09/2024 | 30 | S.K.GOLUI | 4.94 | 0 | 100
143 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Debnibus W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000538/2023-2024 | 356/KSD | 09/08/2023 | 20 | S.K.GOLUI | 2.74 | 0 | 100
144 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Debnibus Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000767/2022-2023 | 6497/AD | 11/11/2022 | 300 | K.P. CONSTRUCTION | 473.08 | 0 | 25
145 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Debnibus Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 600] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000773/2022-2023 | 6496/AD | 11/11/2022 | 990 | J.K. CONSTRUCTION | 118.07 | 0 | 70
146 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Debnibus W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001605/2021-2022 | 600/KSD | 27/09/2021 | 7 | LEMNISCATE | 4.38 | 0 | 100
147 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Debnibas PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002053/2022-2023 | 731/KSD | 14/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
148 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
149 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 1st Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002137/2024-2025 | 1977/KSD | 23/12/2024 | 20 | COPE ENTERPRISE | 1.79 | 0 | 0
150 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002138/2024-2025 | 1978/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.96 | 0 | 0
151 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 3rd Tube well site of Debnibus W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10092) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002139/2024-2025 | 1979/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.95 | 0 | 0
152 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000049/2022-2023 | 3903/AD | 12/08/2022 | 0 | Resource Division | 145.02 | 0 | 0
153 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000801/2023-2024 | 646/AD | 30/01/2024 | 0 | Resource Division | 29.38 | 0 | 0
154 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000974/2023-2024 | 1767/AD | 27/03/2024 | 0 | Resource Division | 1.3 | 0 | 0
155 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001144/2023-2024 | 556/DHSD | 31/10/2023 | 182 | SUMAN HALDER | 2.4 | 0 | 0
156 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000101/2022-2023 | 7497/AD | 26/11/2022 | 0 | Resource Division | 3.31 | 0 | 0
157 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000123/2022-2023 | 12049/AD | 27/02/2023 | 0 | Resource Division | 3.51 | 0 | 0
158 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000864/2023-2024 | 771/AD | 03/02/2024 | 0 | Resource Division | 16.91 | 0 | 0
159 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000932/2023-2024 | 1274/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
160 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the KALIKAMERYA having village with maximum 34 nos. households, Block - Diamond Harbour -II under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/001124/2022-2023 | 8768/AD | 21/12/2022 | 960 | S.S. ENTERPRISE (II) | 26.74 | 0 | 30
161 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | RTOR000885/2023-2024 | 759/AD | 03/02/2024 | 0 | Resource Division | 0.21 | 0 | 0
162 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kamalpur Rudranagar (Zone-II), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000347/2023-2024 | 1707/AD | 22/07/2023 | 45 | UNITED BUILDERS | 49.55 | 0 | 100
163 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000369/2022-2023 | 4120/AD | 18/08/2022 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 564.7 | 0 | 86
164 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kamalpur Rudranagar (Zone-I), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000407/2023-2024 | 1780/AD | 26/07/2023 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 47.04 | 0 | 100
165 | Alipore Division | Kakdwip Sub-Division | inking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Kamalpur Rudranagar W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000419/2023-2024 | 1908/AD | 01/08/2023 | 30 | FORTUNE ENGINEERING | 25.2 | 0 | 100
166 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KAMALPUR RUDRANAGAR) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000476/2022-2023 | 296/AD | 12/04/2022 | 45 | VOYAGER | 8.2 | 0 | 0
167 | Alipore Division | Kakdwip Sub-Division | Sanitary arrangement works and painting works for Pump House No. 4 of Kamalpur Rudranagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000493/2021-2022 | 564/KSD | 10/09/2021 | 45 | PRADIP KUMAR MONDAL | 1.29 | 0 | 100
168 | Alipore Division | Kakdwip Sub-Division | Surging of 1 no. Tubewell for augmentation of Kamalpur Rudranagar W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000540/2023-2024 | 358/KSD | 09/08/2023 | 62 | S.K.GOLUI | 1.77 | 0 | 100
169 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000289/2023-2024 | 3088/AD | 28/09/2023 | 0 | Resource Division | 20.14 | 0 | 0
170 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000325/2023-2024 | 3140/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
171 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000533/2023-2024 | 17/AD | 02/01/2024 | 0 | Resource Division | 20.14 | 0 | 0
172 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000116/2022-2023 | 1661/AD | 10/06/2022 | 120 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 267.47 | 0 | 71
173 | Alipore Division | Canning Sub-division | Sinking of 01 (one) no. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Tube Well No. - 3 at Deuli (Zone - I) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000474/2022-2023 | 5524/AD | 29/09/2022 | 30 | SIMPLEX DRILLING CO. | 18.76 | 0 | 0
174 | Alipore Division | Canning Sub-division | Laying of pipe line in place of existing damage line at Deuli Water Supply Scheme (Zone-I), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000589/2022-2023 | 5865/AD | 18/10/2022 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 97.22 | 0 | 100
175 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli Water Supply Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001341/2021-2022 | 6020/AD | 15/02/2022 | 365 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 228.74 | 0 | 0
176 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Deuli W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001566/2021-2022 | 6798/AD | 22/03/2022 | 120 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 278.33 | 0 | 72
177 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001655/2021-2022 | 614/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 100
178 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Deuli (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001657/2021-2022 | 615/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.46 | 0 | 100
179 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001658/2021-2022 | 616/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.85 | 0 | 100
180 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001659/2021-2022 | 617/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
181 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Deuli (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001661/2021-2022 | 618/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.54 | 0 | 100
182 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Deuli (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001662/2021-2022 | 619/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.64 | 0 | 100
183 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000062/2022-2023 | 3950/AD | 12/08/2022 | 0 | Resource Division | 11.97 | 0 | 0
184 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000073/2022-2023 | 4850/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
185 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
186 | Alipore Division | Canning Sub-division | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Kanthalberia, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000673/2023-2024 | 2700/AD | 07/09/2023 | 600 | GHOSH CONSTRUCTION (GOCHARAN) | 539.93 | 0 | 30
187 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Kanthalberia W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - IV) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000746/2024-2025 | 4413/AD | 05/11/2024 | 30 | G.B. CONSTRUCTION (TW) | 19.68 | 0 | 0
188 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. IV) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001225/2024-2025 | 5224/AD | 16/12/2024 | 45 | NEW DAWN POWER & CONSTRUCTION | 6.94 | 0 | 0
189 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Kanthalberia W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.E. Dte. (TW-1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001678/2023-2024 | 1353/CSD | 18/12/2023 | 45 | S.K.GOLUI | 3.72 | 0 | 100
190 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Bhajna PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/12732) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000190/2024-2025 | 2548/AD | 18/06/2024 | 60 | JAL PRAVAHIKA PVT. LTD. | 55.49 | 0 | 0
191 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Bhajna W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000341/2022-2023 | 6151/AD | 01/11/2022 | 45 | R.K. CONSTRUCTION | 36.69 | 0 | 50
192 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BHAJNA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000483/2022-2023 | 4192/AD | 22/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.3 | 0 | 100
193 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Bhajna W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000583/2023-2024 | 2340/AD | 18/08/2023 | 45 | JAL PRAVAHIKA PVT. LTD. | 42.49 | 0 | 0
194 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Bhajna Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000901/2022-2023 | 7275/AD | 24/11/2022 | 1083 | JAL PRAVAHIKA PVT. LTD. | 344.09 | 0 | 55
195 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bhajna W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000919/2023-2024 | 2972/AD | 26/09/2023 | 45 | M/S KHAJABABA ENTERPRISE | 28.21 | 0 | 100
196 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bhajna W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000920/2023-2024 | 2973/AD | 26/09/2023 | 45 | M/S. MAA MENAKA ENTERPRISE | 9.49 | 0 | 0
197 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bhajna PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002054/2022-2023 | 734/KSD | 16/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
198 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
199 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000084/2023-2024 | 530/AD | 12/05/2023 | 0 | Resource Division | 9 | 0 | 0
200 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000524/2023-2024 | 4933/AD | 22/12/2023 | 0 | Resource Division | 35.87 | 0 | 0
201 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000579/2023-2024 | 51/AD | 03/01/2024 | 0 | Resource Division | 1.56 | 0 | 0
202 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Thangara PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000051/2023-2024 | 37/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
203 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000333/2022-2023 | 4063/AD | 18/08/2022 | 30 | MUKHERJEE ENTERPRISE (II) | 17.79 | 0 | 95
204 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000334/2022-2023 | 4064/AD | 18/08/2022 | 30 | M/S. GANGA ENTERPRISE | 11.81 | 0 | 100
205 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Thangara W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000344/2022-2023 | 4071/AD | 18/08/2022 | 45 | AQUATECH ENGINEERS | 37.06 | 0 | 0
206 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary etc. at Thangara W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11850) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000464/2024-2025 | 3423/AD | 21/08/2024 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 21.44 | 0 | 0
207 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (THANGARA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000502/2022-2023 | 2495/AD | 27/06/2022 | 45 | LEMNISCATE | 3.94 | 0 | 100
208 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Thangara W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001155/2023-2024 | 3718/AD | 03/11/2023 | 30 | M/S. M.S. ENTERPRISE | 9.51 | 0 | 100
209 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Thangara Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001316/2022-2023 | 9881/AD | 10/01/2023 | 300 | PATHIK PABAN NANDI | 281.34 | 0 | 55
210 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Thangara W/S Scheme, Block: Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001480/2023-2024 | 4683/AD | 18/12/2023 | 275 | M/S IDEAL WORKS | 25.92 | 0 | 100
211 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
212 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000119/2023-2024 | 655/AD | 17/05/2023 | 0 | Resource Division | 5.66 | 0 | 0
213 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000441/2023-2024 | 4709/AD | 18/12/2023 | 0 | Resource Division | 42.17 | 0 | 0
214 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000808/2023-2024 | 653/AD | 30/01/2024 | 0 | Resource Division | 1.02 | 0 | 0
215 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000991/2023-2024 | 1784/AD | 27/03/2024 | 0 | Resource Division | 5.39 | 0 | 0
216 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Lakshmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11877) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000198/2024-2025 | 2581/AD | 19/06/2024 | 45 | SHIBU BISWAS | 38.17 | 0 | 0
217 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, construction of 01 no. Pump House Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Lakshmipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000360/2023-2024 | 1561/AD | 17/07/2023 | 90 | SHIBU BISWAS | 189.75 | 0 | 92
218 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Laxmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000362/2022-2023 | 4117/AD | 18/08/2022 | 30 | M/S NAIYA & MAITY | 18.12 | 0 | 100
219 | Alipore Division | Kakdwip Sub-Division | Construction of Platform and Road Restoration for Lakshmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (PART-II) (SM/11877) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000462/2024-2025 | 3421/AD | 21/08/2024 | 185 | ANANTA KUMAR GIRI | 67.99 | 0 | 20
220 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (for the period from 01.09.2022 to 28.02.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000469/2022-2023 | 316/HQ-I/AD | 29/08/2022 | 183 | FIROJA KHATUN | 2.4 | 0 | 38
221 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( LASKHMIPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000494/2022-2023 | 2493/AD | 27/06/2022 | 45 | LEMNISCATE | 5.79 | 0 | 100
222 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.09.2024 To 28.02.2025) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000648/2024-2025 | 3815/AD | 29/08/2024 | 183 | FIROJA KHATUN | 2.4 | 0 | 100
223 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.09.2023 to 29.02.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001043/2023-2024 | 155-/HQ-I/AD | 31/08/2023 | 182 | FIROJA KHATUN | 2.4 | 0 | 20
224 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Laxmipur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001159/2023-2024 | 3721/AD | 03/11/2023 | 30 | ANANDA CONSTRUCTION | 9.63 | 0 | 88
225 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including soil investigation including for Laxmipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11877) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001588/2024-2025 | 100/AD | 08/01/2025 | 270 | KALPANA TRADERS | 134.8 | 0 | 0
226 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Laskhmipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001724/2022-2023 | 11750/AD | 21/02/2023 | 30 | MODERN CONSTRUCTION (NEW) | 19.3 | 0 | 20
227 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (for the period from 01.03.2023 to 31.08.2023). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001836/2022-2023 | 551/HQ-I/AD | 27/02/2023 | 181 | FIROJA KHATUN | 2.4 | 0 | 40
228 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
229 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-I) under Alipore Division, PHE Dte. (From 01.03.2024 To 31.08.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002393/2023-2024 | 1195/AD | 28/02/2024 | 182 | FIROJA KHATUN | 2.4 | 0 | 100
230 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000444/2023-2024 | 4711/AD | 18/12/2023 | 0 | Resource Division | 25.6 | 0 | 0
231 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000586/2023-2024 | 85/AD | 03/01/2024 | 0 | Resource Division | 1.49 | 0 | 0
232 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000809/2023-2024 | 654/AD | 30/01/2024 | 0 | Resource Division | 13.01 | 0 | 0
233 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000993/2023-2024 | 1786/AD | 27/03/2024 | 0 | Resource Division | 36.04 | 0 | 0
234 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Moukhali-Kumarkhali (Part - VI) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000788/2022-2023 | 6643/AD | 14/11/2022 | 929 | MAITY SUPPLIERS | 47.01 | 0 | 80
235 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-VI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001902/2022-2023 | 5666/AD. | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.38 | 0 | 100
236 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000171/2023-2024 | 1124/AD | 22/06/2023 | 0 | Resource Division | 0.91 | 0 | 0
237 | Alipore Division | Canning Sub-division | Laying of pipeline and other allied work of Augmentation of Moukhali-Kumarkhali (Zone-II) RO Plant to Model School (English Medium), Canning-II Tambuldaha GP Office, Bakultala Jr. High Madrasha etc under Moukhali-Kumarkhali W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000220/2023-2024 | 1025/AD | 13/06/2023 | 30 | M/S. TAPAS MONDAL | 16.21 | 0 | 98
238 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - II) having village with maximum 124 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000785/2022-2023 | 6640/AD | 14/11/2022 | 60 | D.N. ENTERPRISE | 47.22 | 0 | 60
239 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001898/2022-2023 | 5662/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.39 | 0 | 0
240 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000167/2023-2024 | 1120/AD | 22/06/2023 | 0 | Resource Division | 0.76 | 0 | 0
241 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - IX) having village with maximum 173 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000793/2022-2023 | 6682/AD | 14/11/2022 | 60 | UCON | 53.36 | 0 | 35
242 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-IX) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001905/2022-2023 | 5669/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.43 | 0 | 0
243 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000174/2023-2024 | 1127/AD | 22/06/2023 | 0 | Resource Division | 1.07 | 0 | 0
244 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - XI) having village with maximum 272 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000795/2022-2023 | 6684/AD | 14/11/2022 | 780 | M/S. L.P. CONSTRUCTION | 59.22 | 0 | 65
245 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-XI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001908/2022-2023 | 5671/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.58 | 0 | 0
246 | Alipore Division | Canning Sub-division | Construction of Culvert for canal crossing in front of Khunkhali Part - II, Mini PWSS Scheme, under Canning Sub-Division of Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003333/2024-2025 | 1319/CSD | 22/11/2024 | 30 | M/S. R.M. CONSTRUCTION | 4.49 | 0 | 95
247 | Alipore Division | Canning Sub-division | Laying DI Pipe from Tubewell to Distribution for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Khunkhali (Part - I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003337/2024-2025 | 35./CSD | 09/01/2025 | 30 | M/S. M.M. ENTERPRISE | 4.64 | 0 | 95
248 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000176/2023-2024 | 1129/AD | 22/06/2023 | 0 | Resource Division | 1.68 | 0 | 0
249 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline under the Augmentation Scheme of Zone-XI at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/13909] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000010/2025-2026 | 1621/AD | 03/04/2025 | 150 | M/S. J.K. TRIPATHI & SONS | 120.58 | 0 | 10
250 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone No-XI of Kulpi Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000071/2025-2026 | 2260/AD | 14/05/2025 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 19.56 | 0 | 0
251 | Alipore Division | Diamond Harbour Sub-Division | Restoration of W.B.M damaged due to laying of pipes from Raghunathpur more to Rajarampur F.P School under Kulpi Zone X under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000349/2025-2026 | 3130/AD | 03/07/2025 | 30 | SAMIM AHMED | 11.64 | 0 | 100
252 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4113] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002066/2022-2023 | 12976/AD | 22/03/2023 | 900 | ABDUL HAI | 463.63 | 0 | 20
253 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-XI (Uttar Iswaripur, OHR Size-550) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002102/2022-2023 | 343/DHSD | 18/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
254 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000199/2023-2024 | 1624/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
255 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000214/2023-2024 | 2023/AD | 05/08/2023 | 0 | Resource Division | 14.51 | 0 | 0
256 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000365/2023-2024 | 3229/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
257 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000624/2023-2024 | 285/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
258 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000853/2023-2024 | 760/AD | 03/02/2024 | 0 | Resource Division | 16.1 | 0 | 0
259 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gangapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000122/2024-2025 | 2400/AD | 07/06/2024 | 270 | PRADIP KUMAR MONDAL | 11.8 | 0 | 95
260 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000207/2023-2024 | 790/AD | 24/05/2023 | 597 | M/S. S.S. ENTERPRISE | 49.26 | 0 | 100
261 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 242 | M/S. S.S. ENTERPRISE | 373.95 | 0 | 20
262 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANGAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001034/2022-2023 | 4153/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.9 | 0 | 100
263 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Gangapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002074/2023-2024 | 770(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
264 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
265 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gangapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002154/2023-2024 | 800/AD | 05/02/2024 | 60 | M/S.SREEJIT ENTERPRISE | 33.05 | 0 | 0
266 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000106/2023-2024 | 642/AD | 17/05/2023 | 0 | Resource Division | 7.31 | 0 | 0
267 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000500/2023-2024 | 4950/AD | 22/12/2023 | 0 | Resource Division | 21.84 | 0 | 0
268 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000749/2023-2024 | 584/AD | 29/01/2024 | 0 | Resource Division | 1.31 | 0 | 0
269 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000954/2023-2024 | 1688/AD | 22/03/2024 | 0 | Resource Division | 7.77 | 0 | 0
270 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Anduldaha Gopalpur having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001734/2022-2023 | 11764/AD | 21/02/2023 | 60 | M/S S.M. ENTERPRISE | 32.54 | 0 | 0
271 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000871/2023-2024 | 778/AD | 03/02/2024 | 0 | Resource Division | 0.65 | 0 | 0
272 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sudhanshupur piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1167] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000294/2023-2024 | 1504/AD | 15/07/2023 | 300 | SARDAR ENTERPRISE | 488.97 | 0 | 30
273 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sudhansupur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000490/2023-2024 | 1791/AD | 26/07/2023 | 30 | M/S MODINA ENTERPRISE | 15.27 | 0 | 0
274 | Alipore Division | Canning Sub-division | : Construction of boundary wall at Head Work site for Augmentation of Sudhansupur Piped Water Supply Scheme, Block- Gosaba under Canning Sub-Division of Alipore Division PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000734/2024-2025 | 4392/AD | 05/11/2024 | 30 | SARDAR ENTERPRISE | 29.93 | 0 | 0
275 | Alipore Division | Canning Sub-division | Survey, Design and DPR preparation for Augmentation of ground water based Sudhanshupur Water Supply Scheme to accommodate FHTC in Gosaba Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002065/2022-2023 | 1470/CSD | 28/03/2023 | 15 | TECH VISION | 3.84 | 0 | 95
276 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000042/2023-2024 | 249/AD | 24/04/2023 | 0 | Resource Division | 32.05 | 0 | 0
277 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000163/2023-2024 | 1056/AD | 15/06/2023 | 0 | Resource Division | 7.19 | 0 | 0
278 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipeline (left out portion) and protection works of pipeline as required in Part B and C of Zone-V under Kulpi Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000583/2022-2023 | 5859/AD | 18/10/2022 | 15 | MAA BHABANI CONSTRUCTION (DUM DUM) | 12.04 | 0 | 80
279 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-V at Kulpi block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 4527] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001395/2022-2023 | 10867/AD | 04/02/2023 | 90 | UCON | 340.41 | 0 | 0
280 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000192/2023-2024 | 1632/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
281 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000207/2023-2024 | 2027/AD | 05/08/2023 | 0 | Resource Division | 23.16 | 0 | 0
282 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000363/2023-2024 | 3227/AD | 04/10/2023 | 0 | Resource Division | 0.41 | 0 | 0
283 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000628/2023-2024 | 292/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
284 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000855/2023-2024 | 762/AD | 03/02/2024 | 0 | Resource Division | 3.25 | 0 | 0
285 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000935/2023-2024 | 1277/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
286 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - IV) having village with maximum 124 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000786/2022-2023 | 6641/AD | 14/11/2022 | 60 | CAMELIA CONSTRUCTION | 48.44 | 0 | 90
287 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001900/2022-2023 | 5664/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0
288 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000169/2023-2024 | 1122/AD | 22/06/2023 | 0 | Resource Division | 0.76 | 0 | 0
289 | Alipore Division | Baruipur Sub-Division | Road restoration for Chiner More to Haral Bani Scociation Bituminaous Via Punri Katpole to Bonabibi Tala | AE BSD,Assistant Engineer | Junior Engineer | BILL/01696/2024-2025 | BP-2024-25-785 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.12 | 0 | 0
290 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, fitting fixing supplying different dia. specials for Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000150/2024-2025 | 2488/AD | 14/06/2024 | 60 | UCON (II) | 31.23 | 0 | 0
291 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000425/2024-2025 | 3204/AD | 01/08/2024 | 30 | UCON | 5.36 | 0 | 0
292 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.06.2024 to 31.08.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000672/2024-2025 | 984/KSD | 27/05/2024 | 92 | NAMITA PRADHAN | 1.2 | 0 | 0
293 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000673/2024-2025 | 1252/KSD | 28/08/2024 | 91 | NAMITA PRADHAN | 1.2 | 0 | 0
294 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Dhablat (Zone- I & II)) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part - A) (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000761/2024-2025 | 4444/AD | 06/11/2024 | 60 | SUDIP PRADHAN | 25.81 | 0 | 100
295 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dhablat (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000972/2023-2024 | 321/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
296 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DHABLAT (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001058/2022-2023 | 4649/AD | 06/09/2022 | 45 | VOYAGER | 6.21 | 0 | 100
297 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001281/2022-2023 | 9594/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 90
298 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2022 to 30.11.2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001754/2022-2023 | 561/KSD | 02/12/2022 | 363 | NAMITA PRADHAN | 4.79 | 0 | 95
299 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001861/2022-2023 | 12414/AD | 09/03/2023 | 300 | UCON (II) | 221.19 | 0 | 72
300 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dhablat (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001985/2023-2024 | 504/AD | 25/01/2024 | 45 | SUDIP PRADHAN | 33.16 | 0 | 80
301 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dhablat (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001986/2023-2024 | 505/AD | 25/01/2024 | 30 | M/S. MOYNA ENTERPRISE | 11.53 | 0 | 100
302 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall, earth filling & approach road at 1st Tubewell site for Dhablat W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002118/2024-2025 | 1967/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.66 | 0 | 100
303 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall, earth filling, approach road at 2nd Tubewell site for Dhablat W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002119/2024-2025 | 1968/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.55 | 0 | 0
304 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dhablat Zone - I & II, Kamalpur Rudranagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002164/2023-2024 | 951/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
305 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC after completion of FHTC work for 01 Year for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002452/2023-2024 | 1310/AD | 04/03/2024 | 45 | SUDIP PRADHAN | 0 | 0 | 0
306 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dhablat (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 266] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002468/2023-2024 | 1361/AD | 06/03/2024 | 60 | UCON | 0 | 0 | 0
307 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002530/2023-2024 | 712/KSD | 30/11/2023 | 91 | NAMITA PRADHAN | 1.2 | 0 | 0
308 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.03.2024 to 31.05.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/003037/2023-2024 | 411/KSD | 27/02/2024 | 92 | NAMITA PRADHAN | 1.2 | 0 | 0
309 | Alipore Division | Kakdwip Sub-Division | Continuation order for Carriage of Chlorine from Ganeshpur store to different pump house of different PWSS of Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/003234/2023-2024 | 380/KSD | 21/02/2024 | 365 | SUDIP PRADHAN | 2.39 | 0 | 0
310 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000335/2023-2024 | 3150/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
311 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000512/2023-2024 | 4830/AD | 20/12/2023 | 0 | Resource Division | 23.39 | 0 | 0
312 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000532/2023-2024 | 16/AD | 02/01/2024 | 0 | Resource Division | 3.97 | 0 | 0
313 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000687/2023-2024 | 457/AD | 24/01/2024 | 0 | Resource Division | 5.88 | 0 | 0
314 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000971/2023-2024 | 1764/AD | 27/03/2024 | 0 | Resource Division | 1.41 | 0 | 0
315 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indraprastha W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000130/2024-2025 | 2406/AD | 07/06/2024 | 45 | M/S ASCON | 27.58 | 0 | 0
316 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc at Indraprastha PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13804) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000442/2024-2025 | 511/AD | 10/02/2025 | 60 | MAA LAXMI ENTERPRISE | 75.28 | 0 | 0
317 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000940/2023-2024 | 280(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
318 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRAPRASTHA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000980/2022-2023 | 3666/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3 | 0 | 100
319 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indraprastha W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000982/2023-2024 | 3001/AD | 26/09/2023 | 30 | SUJOY SADHUKHAN | 9.55 | 0 | 0
320 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Indraprastha Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 841] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001506/2022-2023 | 11024/AD | 08/02/2023 | 1057 | MAA LAXMI ENTERPRISE | 228.39 | 0 | 40
321 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
322 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000093/2023-2024 | 539/AD | 12/05/2023 | 0 | Resource Division | 4.62 | 0 | 0
323 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000511/2023-2024 | 4942/AD | 22/12/2023 | 0 | Resource Division | 23.91 | 0 | 0
324 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000747/2023-2024 | 582/AD | 29/01/2024 | 0 | Resource Division | 0.83 | 0 | 0
325 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Rajrajeshwarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13868) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000076/2025-2026 | 2307/AD | 16/05/2025 | 45 | B.K. ENTERPRISE. | 40.78 | 0 | 0
326 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Rajrajeshwarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000123/2024-2025 | 2401/AD | 07/06/2024 | 30 | SHIBSANKAR KAMILA | 9.6 | 0 | 0
327 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary etc at Rajrajeswarpur PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13868) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000236/2024-2025 | 2611/AD | 19/06/2024 | 579 | M/S ASCON | 15.81 | 0 | 80
328 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Raj Rajeshwarpur PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13868) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000396/2024-2025 | 4287/AD | 29/10/2024 | 60 | M/S B.M. CONSTRUCTION | 97.23 | 0 | 0
329 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rajrajeshwarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000932/2023-2024 | 276(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
330 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAJRAJESHWARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000988/2022-2023 | 4149/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.58 | 0 | 100
331 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Rajrajeshwarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001744/2022-2023 | 11559/AD | 17/02/2023 | 90 | M/S ASCON | 99.44 | 0 | 90
332 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Rajrajeshwarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 838] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002067/2022-2023 | 13006/AD | 23/03/2023 | 800 | M/S B.M. CONSTRUCTION | 263.39 | 0 | 30
333 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
334 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Rajrajeshwarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002158/2023-2024 | 803/AD | 05/02/2024 | 60 | M/S ASCON | 26.34 | 0 | 0
335 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000111/2023-2024 | 647/AD | 17/05/2023 | 0 | Resource Division | 4.6 | 0 | 0
336 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000483/2023-2024 | 4755/AD | 19/12/2023 | 0 | Resource Division | 12.71 | 0 | 0
337 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000576/2023-2024 | 60/AD | 03/01/2024 | 0 | Resource Division | 0.8 | 0 | 0
338 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000753/2023-2024 | 588/AD | 29/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
339 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000957/2023-2024 | 1691/AD | 22/03/2024 | 0 | Resource Division | 13.68 | 0 | 0
340 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Rajnagar (Phase-B) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 520] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000308/2023-2024 | 1511/AD | 15/07/2023 | 300 | UCON | 381.33 | 0 | 20
341 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Rajnagar W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000537/2023-2024 | 355/KSD | 09/08/2023 | 20 | S.K.GOLUI | 2.73 | 0 | 100
342 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAJNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001044/2022-2023 | 3675/AD | 01/08/2022 | 45 | M/S R.DUTTA & CO. | 3.66 | 0 | 100
343 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Rajnagar (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001776/2022-2023 | 12058/AD | 27/02/2023 | 30 | M/S MAITY CONSTRUCTION | 19.27 | 0 | 98
344 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Rajnagar W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002054/2023-2024 | 515/AD | 25/01/2024 | 349 | ROYAL CONSTRUCTION | 9.73 | 0 | 100
345 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
346 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000288/2023-2024 | 3084/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
347 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000493/2023-2024 | 4792/AD | 19/12/2023 | 0 | Resource Division | 30.64 | 0 | 0
348 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000545/2023-2024 | 29/AD | 02/01/2024 | 0 | Resource Division | 3.09 | 0 | 0
349 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000987/2023-2024 | 1780/AD | 27/03/2024 | 0 | Resource Division | 7.29 | 0 | 0
350 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-VI of Mathurapur - I Block in connection with remodeling of existing Batiswar water supply scheme under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000007/2022-2023 | 124/AD | 07/04/2022 | 30 | DEBARATI ENTERPRISE | 94.97 | 0 | 95
351 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
352 | Alipore Division | Raidighi Sub-Division | Miscellaneous work for smooth distribution system of piped water supply at Zone-VI of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000439/2022-2023 | 4353/AD | 25/08/2022 | 60 | DEBARATI ENTERPRISE | 49.88 | 0 | 99
353 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- VI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000880/2024-2025 | 4663/AD | 20/11/2024 | 90 | KARMAKAR CONSTRUCTION | 12.94 | 0 | 0
354 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Botiswar piped water supply Scheme at Zone- VI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001010/2023-2024 | 300/RSD | 29/09/2023 | 60 | DEBARATI ENTERPRISE | 3.86 | 0 | 100
355 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-I, Zone-VI (Batiswar PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001146/2021-2022 | 5534/AD | 20/01/2022 | 365 | DEBARATI ENTERPRISE | 80.58 | 0 | 75
356 | Alipore Division | Raidighi Sub-Division | Laying distribution DI pipeline and allied works to improve functionality Botiswar piped water supply Scheme at Zone- VI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001908/2023-2024 | 436/RSD | 08/01/2024 | 60 | DEBARATI ENTERPRISE | 2.99 | 0 | 100
357 | Alipore Division | Raidighi Sub-Division | Providing 100% Functional Household Tap Connection (FHTC) including Parallel pipeline and other allied works of piped water supply at Zone - VI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface Water Based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001911/2023-2024 | 141/AD | 05/01/2024 | 30 | DEBARATI ENTERPRISE | 12.41 | 0 | 100
358 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-VI, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001961/2022-2023 | 12715/AD | 14/03/2023 | 30 | DEBARATI ENTERPRISE | 37.98 | 0 | 100
359 | Alipore Division | Raidighi Sub-Division | Providing left-out Functional Household Tap Connection (FHTC) at Zone - VI (Mouza: Borasi, Raghabpur, Sadial, Sovanagar) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002269/2023-2024 | 476/RSD | 15/02/2024 | 30 | DEBARATI ENTERPRISE | 3.59 | 0 | 99
360 | Alipore Division | Raidighi Sub-Division | Providing left-out Functional Household Tap Connection (FHTC) at Zone - VI (Mouza : Sarberia, Uttar Joykrishnapur, Narayanpur, Batiswar) of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002270/2023-2024 | 477/RSD | 15/02/2024 | 30 | DEBARATI ENTERPRISE | 2.08 | 0 | 90
361 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000639/2023-2024 | 243/AD | 15/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
362 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-III of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001080/2023-2024 | 3539/AD | 17/10/2023 | 592 | TIYASHA ENTERPRISE | 96.43 | 0 | 35
363 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001689/2022-2023 | 11620/AD | 18/02/2023 | 45 | B. ENTERPRISE | 7.07 | 0 | 98
364 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Augmentation of Homrapolta W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001696/2022-2023 | 11627/AD | 18/02/2023 | 30 | TRIMURTI ENTERPRISE | 19.56 | 0 | 0
365 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Homrapolta Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002005/2022-2023 | 12819/AD | 16/03/2023 | 60 | TIYASHA ENTERPRISE | 58.34 | 0 | 51
366 | Alipore Division | Canning Sub-division | Relaying of damaged DI pipe at Homrapolta W/S Scheme due widening of PMGSY Road by Zilla Parishad under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002161/2020-2021 | 1593/CSD | 23/02/2021 | 30 | ARANYA ENTERPRISE | 3.54 | 0 | 99
367 | Alipore Division | Canning Sub-division | Renovation of Pump House no. - 2 of Homrapolta W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002453/2023-2024 | 1581/CSD | 22/02/2024 | 30 | SUKANTA HALDER | 3.27 | 0 | 95
368 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000017/2023-2024 | 222/AD | 21/04/2023 | 0 | Resource Division | 39.74 | 0 | 0
369 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000256/2023-2024 | 3048/AD | 28/09/2023 | 0 | Resource Division | 0.92 | 0 | 0
370 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution & FHTC for 1 year after completion of FHTC works for Narayanganj Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001424/2023-2024 | 4603/AD | 14/12/2023 | 90 | M/S P. B. CONSTRUCTION | 58.38 | 0 | 50
371 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Narayanganj W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001720/2022-2023 | 11746/AD | 21/02/2023 | 30 | ASMINA MOLLA | 19.26 | 0 | 100
372 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Narayanganj PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001805/2022-2023 | 3696/AD | 02/08/2022 | 45 | M/S R.DUTTA & CO. | 0.67 | 0 | 95
373 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Narayanganj W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002051/2023-2024 | 512/AD | 25/01/2024 | 30 | PALASH HALDAR | 9.71 | 0 | 98
374 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
375 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000485/2023-2024 | 4787/AD | 19/12/2023 | 0 | Resource Division | 1.18 | 0 | 0
376 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000553/2023-2024 | 41/AD | 03/01/2024 | 0 | Resource Division | 2.48 | 0 | 0
377 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000984/2023-2024 | 1777/AD | 27/03/2024 | 0 | Resource Division | 5.23 | 0 | 0
378 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation at Ramchandrapur W/S Scheme, Block - Kakdwip for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000164/2023-2024 | 608/AD | 15/05/2023 | 30 | KALACHAND DAS | 19.29 | 0 | 0
379 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ramchandrapur W/S Scheme, Block - Kakdwip for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15050) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000645/2024-2025 | 4141/AD | 05/10/2024 | 117 | S. CHAKRABORTY AND CO. | 20.41 | 0 | 100
380 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution and FHTC for 1 year after completion of FHTC works for Ramchandrapur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001426/2023-2024 | 4605/AD | 14/12/2023 | 654 | R.S.CONSTRUCTION CO. | 60.7 | 0 | 50
381 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
382 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000127/2023-2024 | 663/AD | 17/05/2023 | 0 | Resource Division | 1.21 | 0 | 0
383 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000458/2023-2024 | 4721/AD | 18/12/2023 | 0 | Resource Division | 1.42 | 0 | 0
384 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000817/2023-2024 | 662/AD | 30/01/2024 | 0 | Resource Division | 1.24 | 0 | 0
385 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II Zone-VI including Operation and Maintenance of scheme for 01 (one) year under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas Block Diamond Harbour-II, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000581/2021-2022 | 3646/AD | 22/11/2021 | 365 | ADITYA HAZRA | 83.79 | 0 | 100
386 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000031/2021-2022 | 4349/AD | 04/03/2022 | 0 | Resource Division | 19.81 | 0 | 0
387 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000099/2022-2023 | 7496/AD | 26/11/2022 | 0 | Resource Division | 2.28 | 0 | 0
388 | Alipore Division | Raidighi Sub-Division | Extension of distribution system (Node No. 85-AB) of Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000037/2022-2023 | 06/RSD | 04/04/2022 | 60 | R.G. ENTERPRISE (I) | 4.72 | 0 | 100
389 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-H) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000042/2022-2023 | 34/RSD | 19/04/2022 | 60 | B.S. CONSTRUCTION | 4.76 | 0 | 100
390 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 60 | SOURAV DEBNATH | 15.09 | 0 | 0
391 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (PART -A) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000114/2023-2024 | 483/AD | 10/05/2023 | 30 | SUTAPA ENTERPRISE | 16.05 | 0 | 98
392 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Ghatbakultala W/S Scheme (Zone-XIII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000434/2023-2024 | 1922/AD | 01/08/2023 | 30 | ALISHA ENTERPRISE | 19.83 | 0 | 100
393 | Alipore Division | Raidighi Sub-Division | Repairing of pump house no.2, including boundary wall and approach road and plinth protection at Ghatbakultala W/S Scheme, modified as Zone- XIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000608/2024-2025 | 748/RSD | 03/10/2024 | 60 | M/S. GANGA ENTERPRISE | 4.74 | 0 | 95
394 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001040/2024-2025 | 4958/AD | 04/12/2024 | 60 | SUKUMAR HALDAR | 31.88 | 0 | 0
395 | Alipore Division | Raidighi Sub-Division | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala (Node No. 13-12-10-8) under Ghatbakultala water supply scheme ( Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001547/2021-2022 | 713/RSD | 02/03/2022 | 60 | SHEKHAR CHAKRABORTY | 4.79 | 0 | 100
396 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001967/2022-2023 | 12721/AD | 14/03/2023 | 30 | THE TOWER CONSTRUCTION | 39.69 | 0 | 60
397 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Goalar Mal (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002365/2020-2021 | 737/RSD | 12/02/2021 | 60 | DIBYENDU BHATTACHARYA | 4.82 | 0 | 100
398 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000602/2023-2024 | 230/AD | 11/01/2024 | 0 | Resource Division | 2.56 | 0 | 0
399 | Alipore Division | Baruipur Sub-Division | Jagita Sarda House to Khalpar Bypass Via Roybahadur Via Projit Mondal To Nikfiil Ranjan Roy House Via Khardhya Math Via Bapi Naskar House | AE BSD,Assistant Engineer | Junior Engineer | BILL/01703/2024-2025 | BP-2024-25-788 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.16 | 0 | 0
400 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of different dia. M.S. distribution line for crossing of 10 nos. culvert with allied works at Lakshmipur village road, at Netra stations to Panchagram road and Netra stations to Usthi road under Augmentation scheme of Diamond Harbour-I Zone-II and Zone-VIII within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District - South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000097/2025-2026 | 2526/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 93.95 | 0 | 100
401 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VIII Lakshmipur at Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4527] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001015/2023-2024 | 1316/AD | 05/03/2024 | 600 | VISHAL CONSTRUCTION CO. | 858.06 | 0 | 45
402 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001025/2022-2023 | 304/DHSD | 23/09/2022 | 30 | GEO SOLUTION | 2.96 | 0 | 0
403 | Alipore Division | Diamond Harbour Sub-Division | Restoration of laying of distribution system damaged due to construction of PMGSY road at Lakshmipur PWSS in Zone-VIII of Diamond Harbour- I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001616/2022-2023 | 477/DHSD | 03/01/2023 | 21 | M/S B ENTERPRISE | 3.53 | 0 | 100
404 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 600 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-VIII at Lakshmipur of Diamond Harbour -I Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002406/2023-2024 | 1154/AD | 27/02/2024 | 90 | VISHAL CONSTRUCTION CO. | 49.71 | 0 | 80
405 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000129/2022-2023 | 26/AD | 05/04/2023 | 0 | Resource Division | 14.72 | 0 | 0
406 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000237/2023-2024 | 2198/AD | 10/08/2023 | 0 | Resource Division | 21.06 | 0 | 0
407 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000344/2023-2024 | 3208/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
408 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000608/2023-2024 | 270/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
409 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000888/2023-2024 | 742/AD | 03/02/2024 | 0 | Resource Division | 3.25 | 0 | 0
410 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000917/2023-2024 | 1259/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
411 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2024 to 31/10/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000006/2024-2025 | 48/DHSD | 30/04/2024 | 184 | GOPAL KUMAR JHA | 2.4 | 0 | 0
412 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/05/2024 to 31/10/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000007/2024-2025 | 49/DHSD | 30/04/2024 | 184 | SUMAN HALDER | 2.4 | 0 | 0
413 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipe line of different dia. M.S. and different dia. UPVC pipe line of damage portion due to road widening for 5 nos. culvert crossing with allied works at sonamukhi bridge near Parulia G.P, at Dostipur-Usthi road, at Hatuganje more to Netra stations road and OHR head work site to Hatuganje more road under Augmentation scheme of Diamond Harbour-I Zone-IV, Zone-X & Zone-III within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000098/2025-2026 | 2527/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 89.87 | 0 | 100
414 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/05/2025 to 31/10/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000209/2025-2026 | 74/DHSD | 29/04/2025 | 184 | SUMAN HALDER | 2.4 | 0 | 0
415 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Kuleswar under Zone- X of Diamond Harbour-I Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000506/2023-2024 | 1803/AD | 26/07/2023 | 30 | A.S.A.CONSTRUCTION AND CONSULTANT | 27.6 | 0 | 0
416 | Alipore Division | Diamond Harbour Sub-Division | Investigation of soil for the proposed 2(two) nos. R.C.C. Over Head Reservoir i.e. at Zone-X (Kuleswar OHR Size-600) and Zone-XI (Mongrajpur OHR Size-250) within Diamond Harbour-I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000509/2022-2023 | 5530/AD. | 29/09/2022 | 840 | NIRMAN (NEW) | 1.56 | 0 | 50
417 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- X at Kuleswar of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-4980]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000674/2023-2024 | 2701/AD | 07/09/2023 | 900 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 983.37 | 0 | 60
418 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-X at Diamond Harbour- I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000871/2024-2025 | 4655/AD | 20/11/2024 | 240 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 81.66 | 0 | 73
419 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2024 to 30/11/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000915/2024-2025 | 642/DHSD | 30/10/2024 | 30 | GOPAL KUMAR JHA | 0.4 | 0 | 0
420 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (Period from 01/11/2024 to 30/04/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001039/2024-2025 | 641/DHSD | 30/10/2024 | 181 | SUMAN HALDER | 2.4 | 0 | 0
421 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle for the use of JJM related works under the office of the Assistant Engineer, Diamond Harbour Sub-Division, under Alipore Division, P.H.E. Dte. (period from 01/10/2024 to 31/03/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001042/2024-2025 | 545/DHSD | 30/09/2024 | 182 | M.P. ENTERPRISE (II) | 2.4 | 0 | 0
422 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-X of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001053/2022-2023 | 306/DHSD | 23/09/2022 | 30 | MEASURE LAND | 2.96 | 0 | 0
423 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/12/2024 to 28/02/2025) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001563/2024-2025 | 700/DHSD | 29/11/2024 | 90 | AVIJIT SIL | 1.2 | 0 | 0
424 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-X (Kuleswar OHR Size-600) within Diamond Harbour-I Block under "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002090/2022-2023 | 324/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 0
425 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000127/2022-2023 | 28/AD | 05/04/2023 | 0 | Resource Division | 14.72 | 0 | 0
426 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000236/2023-2024 | 2197/AD | 10/08/2023 | 0 | Resource Division | 29.99 | 0 | 0
427 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000348/2023-2024 | 3212/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
428 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000894/2023-2024 | 748/AD | 03/02/2024 | 0 | Resource Division | 30.68 | 0 | 0
429 | Alipore Division | Canning Sub-division | Construction of 300 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sadhupur (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1161] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000023/2023-2024 | 150/AD | 18/04/2023 | 300 | TANMAY ROY CHOWDHURY | 412.42 | 0 | 30
430 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sadhupur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000098/2023-2024 | 454/AD | 08/05/2023 | 15 | MONDAL ENTERPRISE - 2 (SDK) | 16.47 | 0 | 0
431 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No - I for Gorund Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone - II) , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000386/2025-2026 | 3371/AD | 16/07/2025 | 30 | GANGA TUBEWELL AND HARDWARE | 11.16 | 0 | 0
432 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000387/2025-2026 | 3372/AD | 16/07/2025 | 30 | SOURAV DEBNATH | 10.36 | 0 | 0
433 | Alipore Division | Canning Sub-division | River crossing on the river bed and laying DI pipeline of Augmentation of Sadhupur W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001033/2024-2025 | 4943/AD | 03/12/2024 | 60 | SUBHO CONSTRUCTION | 78.35 | 0 | 0
434 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sadhupur (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001890/2022-2023 | 11551/AD | 17/02/2023 | 45 | M/S R.DUTTA & CO. | 6.86 | 0 | 100
435 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001957/2022-2023 | 12693/AD | 14/03/2023 | 45 | BAPAN HALDAR | 8.57 | 0 | 0
436 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001984/2022-2023 | 12645/AD | 13/03/2023 | 45 | RAJ & ENTERPRISE | 8.92 | 0 | 0
437 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000723/2023-2024 | 545/AD | 25/01/2024 | 0 | Resource Division | 111.13 | 0 | 0
438 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
439 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 903] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000026/2023-2024 | 149/AD | 17/04/2023 | 60 | M/S SUMAN SHIL | 227.54 | 0 | 62
440 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000149/2023-2024 | 694/AD | 18/05/2023 | 15 | BHOLANATH CONSTRUCTION | 13.87 | 0 | 0
441 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Sonakhali (Zone-I) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000290/2025-2026 | 693/CSD | 26/05/2025 | 30 | STARK ENTERPRISE | 2.43 | 0 | 0
442 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000312/2024-2025 | 2693/AD | 24/06/2024 | 45 | SAHANA ENTERPRISE | 7.01 | 0 | 0
443 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Sonakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000885/2024-2025 | 4714/AD | 21/11/2024 | 30 | RAJIB CONSTRUCTION | 19.98 | 0 | 0
444 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001851/2022-2023 | 11817/AD | 23/02/2023 | 45 | TECH VISION | 3.47 | 0 | 0
445 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001920/2022-2023 | 12464/AD | 10/03/2023 | 30 | SANDIP SARKAR | 19.56 | 0 | 0
446 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001985/2022-2023 | 12646/AD | 13/03/2023 | 45 | RAJ & ENTERPRISE | 7.1 | 0 | 0
447 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
448 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000035/2023-2024 | 240/AD | 24/04/2023 | 0 | Resource Division | 24.04 | 0 | 0
449 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000392/2023-2024 | 333/AD | 19/01/2024 | 0 | Resource Division | 5.56 | 0 | 0
450 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the DHURI, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000061/2023-2024 | 311/AD | 26/04/2023 | 810 | SAMSUL ENTERPRISE | 451.63 | 0 | 80
451 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Dhuri W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000774/2024-2025 | 4476/AD | 11/11/2024 | 45 | M/S P. B. CONSTRUCTION | 50.82 | 0 | 0
452 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Dhuri W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000775/2024-2025 | 4477/AD | 11/11/2024 | 30 | M/S ASHA ENGINEERING | 13.14 | 0 | 0
453 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dhuri W/S Scheme , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001818/2022-2023 | 12158/AD | 01/03/2023 | 45 | HI TECH ENTERPRISE | 7.35 | 0 | 0
454 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dhuri W/S Scheme , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001819/2022-2023 | 12159/AD | 01/03/2023 | 45 | HI TECH ENTERPRISE | 7.09 | 0 | 100
455 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Dhuri Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001917/2022-2023 | 11776/AD | 21/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.37 | 0 | 0
456 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
457 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000074/2023-2024 | 539/AD | 25/01/2024 | 0 | Resource Division | 49.66 | 0 | 0
458 | Alipore Division | Canning Sub-division | Construction of OHR (550 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Phul Malancha,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001088/2023-2024 | 3605/AD | 30/10/2023 | 300 | JIT CONSTRUCTION | 629.62 | 0 | 60
459 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000160/2023-2024 | 1052/AD | 15/06/2023 | 0 | Resource Division | 13.54 | 0 | 0
460 | Alipore Division | Baruipur Sub-Division | Road restoration of Debipur More to Sonagachi More. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01734/2024-2025 | BP-2024-25-798 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.46 | 0 | 0
461 | Alipore Division | Baruipur Sub-Division | Road restoration for Dakhshin Kalyanpur Panchanantala to Uttar Sashan Santali Sangha (Barikpara, Gazipara, Kalyanpur Uttar Railgate, Pashchim Madhabpur) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01730/2024-2025 | BP-2024-25-794 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.6 | 0 | 0
462 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) WB02435, L046-Mirpur on L045 to Ratanpur 2) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01669/2024-2025 | BP-2024-25-776 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.74 | 0 | 0
463 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
464 | Alipore Division | Canning Sub-division | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-VIII) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000033/2023-2024 | 127/AD | 13/04/2023 | 300 | M/S. SIKHA ENTERPRISE | 134.28 | 0 | 0
465 | Alipore Division | Canning Sub-division | Laying distribution system for Augmentation of Basanti W/S Scheme (Zone-VIII), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000054/2023-2024 | 146/AD | 17/04/2023 | 60 | M/S ROY TRADING CO. | 207.68 | 0 | 85
466 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti W/S Scheme (Zone-VIII), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1963] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000055/2023-2024 | 147/AD | 17/04/2023 | 60 | M/S ROY TRADING CO. | 111.41 | 0 | 55
467 | Alipore Division | Canning Sub-division | Laying of pipeline at different points of Basanti W/S Scheme (Zone-VIII),Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000091/2023-2024 | 447/AD | 08/05/2023 | 15 | MAA BHABANI CONSTRUCTION (DUM DUM) | 7.91 | 0 | 30
468 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VIII) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000094/2023-2024 | 450/AD | 08/05/2023 | 725 | MAA BHABANI CONSTRUCTION (DUM DUM) | 10.08 | 0 | 100
469 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-VIII), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001870/2022-2023 | 12462/AD | 10/03/2023 | 576 | SOMA ENTERPRISE | 58.79 | 0 | 100
470 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VIII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001938/2022-2023 | 11809/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.67 | 0 | 0
471 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001994/2022-2023 | 12685/AD | 14/03/2023 | 45 | PATRA CONSTRUCTION | 7.21 | 0 | 100
472 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001995/2022-2023 | 12686/AD | 14/03/2023 | 45 | PIU ENTERPRISE | 6.96 | 0 | 100
473 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VIII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001996/2022-2023 | 12694/AD | 14/03/2023 | 659 | S.MITRA & CO. | 6.96 | 0 | 100
474 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000028/2023-2024 | 233/AD | 24/04/2023 | 0 | Resource Division | 69.7 | 0 | 0
475 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000157/2023-2024 | 1043/AD | 15/06/2023 | 0 | Resource Division | 12.09 | 0 | 0
476 | Alipore Division | Kakdwip Sub-Division | Construction of 50 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Iswaripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000019/2023-2024 | 96/AD | 11/04/2023 | 1199 | RELIABLE CONSTRUCTIONS | 103.1 | 0 | 50
477 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002069/2022-2023 | 13219/AD | 31/03/2023 | 30 | JOY ENGINEERING & CONSTRUCTION | 14.48 | 0 | 70
478 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002070/2022-2023 | 13220/AD | 31/03/2023 | 30 | M/S BOSE & CO. | 12.98 | 0 | 100
479 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000129/2023-2024 | 665/AD | 17/05/2023 | 0 | Resource Division | 1.37 | 0 | 0
480 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000469/2023-2024 | 4776/AD | 19/12/2023 | 0 | Resource Division | 1.15 | 0 | 0
481 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000787/2023-2024 | 631/AD | 30/01/2024 | 0 | Resource Division | 0.91 | 0 | 0
482 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000068/2025-2026 | 2257/AD | 14/05/2025 | 45 | SAHANA ENTERPRISE | 15.98 | 0 | 0
483 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Netra Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000223/2023-2024 | 1028/AD | 13/06/2023 | 45 | SAHANA ENTERPRISE | 50.78 | 0 | 66
484 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Netra Water Supply Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House - III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000256/2022-2023 | 3490/AD | 26/07/2022 | 45 | R.G. ENTERPRISE (I) | 6.69 | 0 | 98
485 | Alipore Division | Canning Sub-division | Bamboo pilling and earth work in embankment for protection of boundary wall at head work site of Netra W/S Scheme, under Canning-II Block, South 24 Parganas District of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000326/2022-2023 | 267/CSD | 19/05/2022 | 30 | RSA ENTERPRISE | 4.71 | 0 | 98
486 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. V) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000483/2024-2025 | 3542/AD | 02/09/2024 | 45 | ZUBIN CONSTRUCTION | 7.07 | 0 | 0
487 | Alipore Division | Canning Sub-division | Laying additional pipeline at Augmentation of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E.Dte. (SM/09014 & SM/17225) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000762/2024-2025 | 4458/AD | 07/11/2024 | 60 | SAHANA ENTERPRISE | 97.21 | 0 | 98
488 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 2 Site for Augmentation of Netra W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001067/2024-2025 | 5004/AD | 05/12/2024 | 30 | B. ENTERPRISE | 15.68 | 0 | 0
489 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials of Augmentation of Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002491/2023-2024 | 1615/CSD | 29/02/2024 | 30 | SAHANA ENTERPRISE | 4.82 | 0 | 85
490 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000080/2023-2024 | 3054/AD | 28/09/2023 | 0 | Resource Division | 79.38 | 0 | 0
491 | Alipore Division | Diamond Harbour Sub-Division | Repairing and Renovation of existing 225 Cum. capacity Over Head Reservoir of Sirakole (Zone-I) Water Supply Scheme (Block - Mograhat-I) under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/002463/2023-2024 | 1545/AD | 15/03/2024 | 60 | BKB INFRA PROJECTS PRIVATE LIMITED | 35.5 | 0 | 100
492 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Surendraganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000208/2023-2024 | 791/AD | 24/05/2023 | 45 | M/S. BOSE CONCERN | 48.89 | 0 | 100
493 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (UTTAR SURENDRAGANJ PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000989/2022-2023 | 4150/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.42 | 0 | 100
494 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002169/2023-2024 | 810/AD | 05/02/2024 | 420 | R.S.CONSTRUCTION CO. | 33.1 | 0 | 100
495 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002281/2023-2024 | 917/AD | 08/02/2024 | 45 | M/S MODINA ENTERPRISE | 11.79 | 0 | 10
496 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000114/2023-2024 | 650/AD | 17/05/2023 | 0 | Resource Division | 6.62 | 0 | 0
497 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000300/2023-2024 | 3095/AD | 28/09/2023 | 0 | Resource Division | 19.51 | 0 | 0
498 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000574/2023-2024 | 72/AD | 03/01/2024 | 0 | Resource Division | 1.15 | 0 | 0
499 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000679/2023-2024 | 445/AD | 24/01/2024 | 0 | Resource Division | 1.43 | 0 | 0
500 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Baliara W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000117/2024-2025 | 2394/AD | 07/06/2024 | 45 | DEV AND COMPANY | 45.39 | 0 | 30
501 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Baliara PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18392) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000156/2024-2025 | 2507/AD | 15/06/2024 | 60 | PIJUSH KANTI TRIPATHI | 53.71 | 0 | 0
502 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Providing Functional Household Tap Connection (FHTC) to all households for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000344/2023-2024 | 1604/AD | 18/07/2023 | 90 | PIJUSH KANTI TRIPATHI | 110.16 | 0 | 50
503 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Baliara PWSS, Block-Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/18392) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000363/2024-2025 | 2912/AD | 10/07/2024 | 60 | AVIK ENTERPRISE | 115.68 | 0 | 0
504 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000366/2023-2024 | 1567/AD | 17/07/2023 | 838 | AVIK ENTERPRISE | 409.79 | 0 | 60
505 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site of Baliara W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18392) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000416/2024-2025 | 3067/AD | 25/07/2024 | 45 | AVIK ENTERPRISE | 44.14 | 0 | 0
506 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m.) for Baliara Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000580/2023-2024 | 2267/AD | 14/08/2023 | 657 | TANMAY ROY CHOWDHURY | 64.8 | 0 | 50
507 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kusumtala, Bagdanga, Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002138/2023-2024 | 939/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.54 | 0 | 100
508 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002602/2023-2024 | 227/KSD | 24/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
509 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000476/2023-2024 | 4781/AD | 19/12/2023 | 0 | Resource Division | 15.04 | 0 | 0
510 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000558/2023-2024 | 46/AD | 03/01/2024 | 0 | Resource Division | 16.9 | 0 | 0
511 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000980/2023-2024 | 1773/AD | 27/03/2024 | 0 | Resource Division | 1.17 | 0 | 0
512 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Chandranagar PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18394) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000157/2024-2025 | 2508/AD | 15/06/2024 | 75 | M/S. MIHIR KUMAR NASKAR | 89.74 | 0 | 0
513 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc at Dakshin Chandranagar PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18394) (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000366/2024-2025 | 2915/AD | 10/07/2024 | 60 | GARGO TRADERS | 98.12 | 0 | 0
514 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000369/2023-2024 | 1570/AD | 17/07/2023 | 624 | GARGO TRADERS | 473.26 | 0 | 50
515 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000391/2024-2025 | 3059/AD | 25/07/2024 | 30 | SK SAKIL AHAMED | 9.6 | 0 | 0
516 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Chandranagar W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18394) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000401/2024-2025 | 3184/AD | 31/07/2024 | 45 | RABIUL GAZI | 28.61 | 0 | 0
517 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000567/2023-2024 | 1807/AD | 26/07/2023 | 30 | FORTUNE ENGINEERING | 16.93 | 0 | 60
518 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000574/2023-2024 | 1828/AD | 27/07/2023 | 45 | MEGA SOLAR ENERGY | 36.66 | 0 | 100
519 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m.) for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000579/2023-2024 | 2266/AD | 14/08/2023 | 45 | B.S.ENTERPRISE (II) | 60.58 | 0 | 76
520 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Chandranagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =650] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001014/2023-2024 | 3205/AD | 04/10/2023 | 90 | M/S. MIHIR KUMAR NASKAR | 105.31 | 0 | 82
521 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell Site of Dakshin Chandranagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001835/2023-2024 | 123/AD | 05/01/2024 | 45 | SARADA CONSTRUCTION | 39.88 | 0 | 100
522 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
523 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000559/2023-2024 | 47/AD | 03/01/2024 | 0 | Resource Division | 11.33 | 0 | 0
524 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000789/2023-2024 | 633/AD | 30/01/2024 | 0 | Resource Division | 4.74 | 0 | 0
525 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000989/2023-2024 | 1782/AD | 27/03/2024 | 0 | Resource Division | 45.43 | 0 | 0
526 | Alipore Division | Kakdwip Sub-Division | Surging and repairing of 1no Tube well of Ramchandranagar Water Supply Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000599/2022-2023 | 5924/AD | 19/10/2022 | 15 | S.K.GOLUI | 3.76 | 0 | 100
527 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Ramchandranagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001144/2021-2022 | 5532/AD | 20/01/2022 | 365 | M/S B.N.ENTERPRISE | 54.95 | 0 | 100
528 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Suryanagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001567/2021-2022 | 6829/AD | 23/03/2022 | 45 | M/S B. ENTERPRISE | 113.06 | 0 | 94
529 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000017/2021-2022 | 5623/AD | 25/01/2022 | 0 | Resource Division | 4.51 | 0 | 0
530 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000802/2023-2024 | 647/AD | 30/01/2024 | 0 | Resource Division | 2.54 | 0 | 0
531 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Moukhali-Kumarkhali (Part - V) having village with maximum 247 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000787/2022-2023 | 6642/AD | 14/11/2022 | 810 | HARIDAS DUTTA | 56.64 | 0 | 92
532 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-V) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001901/2022-2023 | 5665/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.55 | 0 | 100
533 | Alipore Division | Canning Sub-division | Additional laying of pipeline & FHTC at Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - IV) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003329/2024-2025 | 944/CSD | 22/08/2024 | 30 | JOYJIT MUKHERJEE | 3.04 | 0 | 0
534 | Alipore Division | Canning Sub-division | Additional laying of pipeline & FHTC at Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - III) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003331/2024-2025 | 945/CSD | 22/08/2024 | 30 | S.S. ENTERPRISE (I) | 3.04 | 0 | 95
535 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000170/2023-2024 | 1123/AD | 22/06/2023 | 0 | Resource Division | 1.52 | 0 | 0
536 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Kakdwip Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 2582] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000194/2023-2024 | 2103/AD | 08/08/2023 | 90 | M/S. JHARNA ENTERPRISE | 259.33 | 0 | 40
537 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Kakdwip W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000302/2024-2025 | 2709/AD | 24/06/2024 | 60 | M/S. JHARNA ENTERPRISE | 163.39 | 0 | 0
538 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18682) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000415/2024-2025 | 3066/AD | 25/07/2024 | 45 | M/S. JHARNA ENTERPRISE | 28.68 | 0 | 0
539 | Alipore Division | Kakdwip Sub-Division | Sinking of 03 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Kakdwip W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000421/2023-2024 | 2152/AD | 09/08/2023 | 60 | IQBAL CONSTRUCTION | 57.38 | 0 | 66
540 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Kakdwip W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000443/2024-2025 | 3294/AD | 09/08/2024 | 30 | KHAN CONSTRUCTION (HASNABAD) | 9.31 | 0 | 0
541 | Alipore Division | Kakdwip Sub-Division | Construction of 600 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kakdwip Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 2500] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000545/2023-2024 | 2211/AD | 10/08/2023 | 900 | M/S. JHARNA ENTERPRISE | 369.23 | 0 | 70
542 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Kakdwip PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000643/2023-2024 | 2035/AD | 05/08/2023 | 45 | LEMNISCATE | 12.08 | 0 | 100
543 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001385/2023-2024 | 379/KSD | 17/08/2023 | 184 | ANAMIKA BERA | 2.4 | 0 | 100
544 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
545 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 600 cum. capacity OHR of Kakdwip PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002233/2023-2024 | 719/KSD | 01/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
546 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Kakdwip Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002286/2023-2024 | 1003/AD | 16/02/2024 | 90 | M/S. JHARNA ENTERPRISE | 128.24 | 0 | 60
547 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000454/2023-2024 | 4718/AD | 18/12/2023 | 0 | Resource Division | 40.56 | 0 | 0
548 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000590/2023-2024 | 89/AD | 03/01/2024 | 0 | Resource Division | 14.85 | 0 | 0
549 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000821/2023-2024 | 666/AD | 30/01/2024 | 0 | Resource Division | 15.91 | 0 | 0
550 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000908/2023-2024 | 896/AD | 07/02/2024 | 0 | Resource Division | 0.75 | 0 | 0
551 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Durgapur W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000222/2024-2025 | 2605/AD | 19/06/2024 | 225 | M/S KHAJABABA ENTERPRISE | 28.53 | 0 | 95
552 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Durgapur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000223/2024-2025 | 2606/AD | 19/06/2024 | 30 | NEPAL CHANDRA PRADHAN | 9.59 | 0 | 0
553 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Dakshin Durgapur W/S scheme, Block : Namkhan under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000389/2024-2025 | 3057/AD | 25/07/2024 | 30 | M/S BABUSONA ENTERPRISE | 9.58 | 0 | 0
554 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Dakshin Durgapur W/S scheme, Block : Namkhan under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000390/2024-2025 | 3058/AD | 25/07/2024 | 30 | SWASTIK CONSTRUCTION | 9.59 | 0 | 0
555 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000424/2024-2025 | 3202/AD | 01/08/2024 | 240 | H T R CONSTRUCTION | 47.47 | 0 | 30
556 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000573/2023-2024 | 2260/AD | 14/08/2023 | 45 | MEGA SOLAR ENERGY | 36.66 | 0 | 100
557 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000623/2023-2024 | 2432/AD | 22/08/2023 | 863 | H T R CONSTRUCTION | 614.68 | 0 | 75
558 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000699/2023-2024 | 2527/AD | 28/08/2023 | 30 | ABONTICA ENTERPRISE | 15.52 | 0 | 60
559 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000700/2023-2024 | 2528/AD | 28/08/2023 | 30 | SWASTIK CONSTRUCTION | 14.73 | 0 | 25
560 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000702/2023-2024 | 2529/AD | 28/08/2023 | 30 | UNIVERSAL CONSTRUCTION (ULUBERIA) | 13.71 | 0 | 30
561 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000705/2023-2024 | 2530/AD | 28/08/2023 | 30 | AROMA INC | 13.31 | 0 | 20
562 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-H) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000707/2023-2024 | 2531/AD | 28/08/2023 | 30 | SAB ENGINEERING WORKS | 13.11 | 0 | 20
563 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000708/2023-2024 | 2532/AD | 28/08/2023 | 30 | SUNIL ENTERPRISE | 8.16 | 0 | 90
564 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-J) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000711/2023-2024 | 2533/AD | 28/08/2023 | 30 | M/S SNEHALATA ENTERPRISE | 7.83 | 0 | 80
565 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Dakshin Durgapur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18684) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001044/2024-2025 | 4965/AD | 04/12/2024 | 300 | H T R CONSTRUCTION | 74.15 | 0 | 20
566 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 01 no. Pump House of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001450/2023-2024 | 4687/AD | 18/12/2023 | 120 | M/S. P. GIRI ENTERPRISE | 91.01 | 0 | 45
567 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 01 no. Pump House of Dakshin Durgapur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001451/2023-2024 | 4688/AD | 18/12/2023 | 120 | MOINAK POREL | 91.33 | 0 | 40
568 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 3rd and 4th Tubewell Site of Dakshin Durgapur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001837/2023-2024 | 125/AD | 05/01/2024 | 45 | MEHAI TECHNOLOGY LIMITED | 39.91 | 0 | 40
569 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
570 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 400 cum. capacity OHR of Dakshin Durgapur PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002217/2023-2024 | 874/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
571 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000475/2023-2024 | 4780/AD | 19/12/2023 | 0 | Resource Division | 26.31 | 0 | 0
572 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000793/2023-2024 | 638/AD | 30/01/2024 | 0 | Resource Division | 18.6 | 0 | 0
573 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000910/2023-2024 | 893/AD | 07/02/2024 | 0 | Resource Division | 10.67 | 0 | 0
574 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000979/2023-2024 | 1772/AD | 27/03/2024 | 0 | Resource Division | 14.69 | 0 | 0
575 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Bansra Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000125/2021-2022 | 1269/AD | 13/07/2021 | 365 | B. MOOKHERJEE | 326.08 | 0 | 80
576 | Alipore Division | Canning Sub-division | Laying of additional pipe line at Bansra (Zone - I & II) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001031/2024-2025 | 4941/AD | 03/12/2024 | 60 | M/S B.M. CONSTRUCTION | 52.15 | 0 | 0
577 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-II) Water Supply Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000111/2021-2022 | 1194/AD | 07/07/2021 | 45 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.47 | 0 | 51
578 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-F) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000406/2023-2024 | 1905/AD | 01/08/2023 | 45 | ASHIS ENTERPRISE | 20.52 | 0 | 93
579 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 365 | SUPER SKILL | 87.04 | 0 | 95
580 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
581 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary at 2nd Tubewell site of Shibkalinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07399) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002192/2024-2025 | 2073/KSD | 28/12/2024 | 20 | M/S IDEAL WORKS | 1.64 | 0 | 90
582 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000279/2023-2024 | 3078/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
583 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000835/2023-2024 | 680/AD | 30/01/2024 | 0 | Resource Division | 9.59 | 0 | 0
584 | Alipore Division |  | Laying pipe line to connect the uncovered habitation of Lot No.-126 W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/000270/2022-2023 | 262/CSD | 19/05/2022 | 30 | K.P. CONSTRUCTION | 4.8 | 0 | 99
585 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Lot No. - 126 Water Supply Scheme Block - Basanti, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year. |  |  | ORD/001375/2020-2021 | 5131/AD | 08/02/2021 | 365 | K.P. CONSTRUCTION | 189.54 | 142.23 | 100
586 | Alipore Division |  | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - B] |  |  | ORD/002016/2022-2023 | 12922/AD | 21/03/2023 | 60 | S.P. CONSTRUCTION (I) | 97.64 | 0 | 80
587 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Manasadwip Water Supply Scheme, Block - Sagar, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001257/2020-2021 | 2277/AD | 12/10/2020 | 365 | PIKASU BOSE | 128 | 100.03 | 100
588 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Gurudaspur Water Supply Scheme, Block - Patharpratima South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000499/2020-2021 | 5125/AD | 08/02/2021 | 365 | DHIRENDRA ENGINEERING & CONSTRUCTION | 92.45 | 24.95 | 44
589 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000772/2023-2024 | 606/AD | 29/01/2024 | 0 | Resource Division | 23.82 | 0 | 0
590 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [2340/AD, 21-22, T.No. 1603/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | VCH/002610/2021-2022 | BP-2021-22-513 | 23/03/2022 | 0 | LEMNISCATE | 2.67 | 0 | 0
591 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O NO. 548/KSD, 03.09.21, T.NO. 1783/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | VCH/002611/2021-2022 | BP-2021-22-514 | 23/03/2022 | 0 | M/S R.DUTTA & CO. | 4.26 | 0 | 0
592 | Alipore Division | Raidighi Sub-Division | Miscellaneous work for smooth distribution system of piped water supply at Zone-VI of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000439/2022-2023 | 4353/AD | 25/08/2022 | 60 | DEBARATI ENTERPRISE | 49.88 | 0 | 99
593 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000012/2022-2023 | 1170/AD | 27/05/2022 | 0 | Resource Division | 5.97 | 0 | 0
594 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000019/2021-2022 | 5625/AD | 25/01/2022 | 0 | Resource Division | 9.31 | 0 | 0
595 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000022/2022-2023 | 1678/AD | 13/06/2022 | 0 | Resource Division | 15.4 | 0 | 0
596 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000038/2022-2023 | 3585/AD | 29/07/2022 | 0 | Resource Division | 48.96 | 0 | 0
597 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-V (Raidighi PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001340/2021-2022 | 6034/AD | 16/02/2022 | 365 | TANMAY ROY CHOWDHURY | 171.21 | 0 | 85
598 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000025/2022-2023 | 1681/AD | 13/06/2022 | 0 | Resource Division | 15.4 | 0 | 0
599 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000096/2022-2023 | 6202/AD | 02/11/2022 | 0 | Resource Division | 76.28 | 0 | 0
600 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Narayangar Water Supply Scheme (Habitation- Narayangar, Sardarpara) Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) |  |  | ORD/000111/2022-2023 | 282/CSD | 19/05/2022 | 40 | BABA LOKENATH ENTERPRISE | 4.82 | 0 | 100
601 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Narayangar Water Supply Scheme (Habitation- Narayangar) Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) |  |  | ORD/000119/2022-2023 | 280/CSD | 19/05/2022 | 40 | M/S BOSE & CO. | 4.78 | 0 | 100
602 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Narayangar Water Supply Scheme (Habitation- Sardarpara) Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) |  |  | ORD/000120/2022-2023 | 281/CSD | 19/05/2022 | 40 | M/S BOSE & CO. | 4.81 | 0 | 100
603 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Narayangarh Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000563/2021-2022 | 3022/AD | 02/11/2021 | 365 | BOSE & CO. | 61.39 | 0 | 100
604 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
605 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kashinagar W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001026/2021-2022 | 540/KSD | 01/09/2021 | 20 | LEMNISCATE | 4.59 | 0 | 100
606 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kashinagar & Srikrishnanagar W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001045/2021-2022 | 2276/AD | 06/09/2021 | 7 | LEMNISCATE | 4.17 | 0 | 100
607 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000257/2023-2024 | 3062/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
608 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000843/2023-2024 | 689/AD | 30/01/2024 | 0 | Resource Division | 28.25 | 0 | 0
609 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 14 (fourteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Tilkumar Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001151/2021-2022 | 5302/AD | 04/01/2022 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 213.56 | 0 | 0
610 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000012/2021-2022 | 5618/AD | 25/01/2022 | 0 | Resource Division | 22.69 | 0 | 0
611 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000396/2023-2024 | 336/AD | 19/01/2024 | 0 | Resource Division | 36.35 | 0 | 0
612 | Alipore Division | Raidighi Sub-Division | Extension of distribution system (Node no. AB-CD) of Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000043/2022-2023 | 35/RSD | 19/04/2022 | 60 | R.G. ENTERPRISE (I) | 4.77 | 0 | 100
613 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system (Node No. 16-15-13-14, 16-17-18-19-20-21, 15-23-22-24) at Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000108/2022-2023 | 05/RSD | 04/04/2022 | 60 | KAKALI ENTERPRISE | 4.79 | 0 | 100
614 | Alipore Division | Raidighi Sub-Division | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 100
615 | Alipore Division | Raidighi Sub-Division | Bamboo pilling walling at Zone-X of Mathurapur - I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Node point -255 - 255A, 255-255E, 255-255D, 255-255C) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000267/2022-2023 | 103/RSD | 13/06/2022 | 60 | SUPRITI ENTERPRISE | 4.65 | 0 | 100
616 | Alipore Division | Raidighi Sub-Division | Construction of thrust block for D.I. pipe line at Zone - I, Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000426/2022-2023 | 282/RSD | 01/09/2022 | 60 | M/S KUNDU CONSTRUCTION | 0.81 | 0 | 100
617 | Alipore Division | Raidighi Sub-Division | Construction of 1500 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- I of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000576/2023-2024 | 2262/AD | 14/08/2023 | 600 | M/S. S.S. ENTERPRISE | 1185.63 | 0 | 10
618 | Alipore Division | Raidighi Sub-Division | Special repairing work of pipeline and allied works to mitigate water supply problem at Rajapur & adjacent area Uttar Durgapur water supply scheme ( Zone-I of Mathurapur-I Block) under Mega surface water based water supply scheme-Falta Mathurapur, Dist. ¿ South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000634/2022-2023 | 95/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 4.75 | 0 | 100
619 | Alipore Division | Raidighi Sub-Division | Dismantling and restoration of concrete village road for laying pipe line work at Zone-I (Nodal point 354-356-357-359-361-363-367) of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001133/2022-2023 | 598/RSD | 23/12/2022 | 30 | RAIS ALI MOLLA | 1.82 | 0 | 100
620 | Alipore Division | Raidighi Sub-Division | Construction of culvert at Zone-I of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega surface water based water supply scheme-Falta Mathurapur, Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001804/2022-2023 | 934/RSD | 10/03/2023 | 30 | SUKUMAR HALDAR | 1.07 | 0 | 99
621 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | RTOR000637/2023-2024 | 241/AD | 15/01/2024 | 0 | Resource Division | 52.95 | 0 | 0
622 | Alipore Division | Raidighi Sub-Division | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 100
623 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.05.2025 to 31.07.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000446/2025-2026 | 72/RSD | 30/04/2025 | 92 | DILIP DHALI | 1.2 | 0 | 0
624 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.05.2024 to 31.07.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000447/2025-2026 | 73/RSD | 30/04/2025 | 92 | SANKAR HALDER | 1.2 | 0 | 0
625 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for Office of the Assistant Engineer, Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/08/2022 to 31/07/2023. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/000850/2022-2023 | 227/RSD | 29/07/2022 | 365 | NITYANANDA MONDAL | 4.8 | 0 | 100
626 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/09/2022 to 31/10/2022. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001129/2022-2023 | 276/RSD | 31/08/2022 | 61 | BAPPA DAS | 0.8 | 0 | 100
627 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/11/2022 to 31/12/2022. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001130/2022-2023 | 384/RSD | 28/10/2022 | 61 | BAPPA DAS | 0.8 | 0 | 100
628 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works under Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/01/2023 to 28/02/2023. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/001143/2022-2023 | 679/RSD | 29/12/2022 | 2 | BAPPA DAS | 0.8 | 0 | 100
629 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.11.2024 to 31.01.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002375/2024-2025 | 768E/RSD | 30/10/2024 | 92 | DILIP DHALI | 1.2 | 0 | 10
630 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for Office of the Assistant Engineer, Raidighi Sub-Division P.H.E. Dte. w.e.f. 01/08/2023 to 31/07/2024. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002446/2023-2024 | 212/RSD | 28/07/2023 | 366 | NITYANANDA MONDAL | 4.8 | 0 | 0
631 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.11.2024 to 31.01.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002473/2024-2025 | 768D/RSD | 30/10/2024 | 92 | SANKAR HALDER | 1.2 | 0 | 100
632 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for official use of Assistant Engineer, Raidighi Sub-Division, PHE Dte. [For 01.02.2025 to 30.04.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002914/2024-2025 | 1032/RSD | 30/01/2025 | 90 | DILIP DHALI | 1.2 | 0 | 0
633 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01.02.2024 to 30.04.2025] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | ORD/002916/2024-2025 | 1033/RSD | 30/01/2025 | 90 | SANKAR HALDER | 1.2 | 0 | 0
634 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer 2, Raidghi Sub Division | RTOR000646/2023-2024 | 256/AD | 15/01/2024 | 0 | Resource Division | 47.12 | 0 | 0
635 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), Construction of boundary fencing, MS grilll type gate, land development, Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Baintala having village with maximum 66 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000953/2022-2023 | 7807/AD | 30/11/2022 | 60 | M/S SEKH ENTERPRISE | 34.11 | 0 | 25
636 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, &Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kuler Khonj having village with maximum 85 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000766/2022-2023 | 6495/AD | 11/11/2022 | 60 | SURYA ENTERPRISE | 33.84 | 0 | 88
637 | Alipore Division | Baruipur Sub-Division | Road Restoration of Madarat More Riksha Stand to Najirpur Auto Stand via Kobindapur More to Vurkul Khalpar | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01736/2024-2025 | BP-2024-25-800 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.82 | 0 | 0
638 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - VIII) having village with maximum 247 nos. households, Block - Canning -II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000792/2022-2023 | 6681/AD | 14/11/2022 | 90 | R.S.CONSTRUCTION CO. | 52.9 | 0 | 75
639 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-VIII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001904/2022-2023 | 5668/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.53 | 0 | 0
640 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000173/2023-2024 | 1126/AD | 22/06/2023 | 0 | Resource Division | 1.52 | 0 | 0
641 | Alipore Division | Canning Sub-division | Improvement & Retrofitting of UPVC pipe line (balance part) in distribution system due to damage of pipe line by widening of road by South 24 Pgs. Zilla Parishad at Improvement & Retrofitting of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000814/2022-2023 | 6809/AD | 16/11/2022 | 30 | TANMAY ROY CHOWDHURY | 60.33 | 0 | 100
642 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-III of Homrapolta W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001080/2023-2024 | 3539/AD | 17/10/2023 | 592 | TIYASHA ENTERPRISE | 96.43 | 0 | 35
643 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Improvement & Retrofitting of Homrapolta and its adjoining Mouza W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001382/2022-2023 | 1065/CSD | 15/12/2022 | 40 | S.P. CONSTRUCTION (I) | 0.96 | 0 | 90
644 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Homrapolta Water Supply Scheme Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001458/2021-2022 | 6071/AD | 17/02/2022 | 365 | M/S. BLUE BELL ENTERPRISE | 169.37 | 0 | 75
645 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Homrapalta Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001676/2021-2022 | 643/CSD | 11/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.42 | 0 | 100
646 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Homrapalta Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001677/2021-2022 | 644/CSD | 11/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.1 | 0 | 100
647 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000063/2022-2023 | 3951/AD | 12/08/2022 | 0 | Resource Division | 0.86 | 0 | 0
648 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Chhoto Banashyamnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000205/2023-2024 | 788/AD | 24/05/2023 | 566 | M/S. S.S. ENTERPRISE | 49.26 | 0 | 100
649 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 242 | M/S. S.S. ENTERPRISE | 373.95 | 0 | 20
650 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.07.2024 to 30.09.2024 - 3 months] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000534/2024-2025 | 2523/AD | 18/06/2024 | 92 | PARBATI MONDAL | 1.2 | 0 | 100
651 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (CHHOTO BANASHYAM NAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001039/2022-2023 | 4154/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.31 | 0 | 100
652 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Chhoto Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001200/2023-2024 | 4077/AD | 23/11/2023 | 45 | SK SAKIL AHAMED | 33.2 | 0 | 0
653 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Chhoto Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001201/2023-2024 | 4078/AD | 23/11/2023 | 454 | B. ENTERPRISE | 11.59 | 0 | 98
654 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 100 cum. capacity OHR of Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002069/2023-2024 | 765(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
655 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
656 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000115/2023-2024 | 651/AD | 17/05/2023 | 0 | Resource Division | 9.93 | 0 | 0
657 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000471/2023-2024 | 4759/AD | 19/12/2023 | 0 | Resource Division | 53.56 | 0 | 0
658 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000575/2023-2024 | 73/AD | 03/01/2024 | 0 | Resource Division | 1.72 | 0 | 0
659 | Alipore Division | Canning Sub-division | Construction of OHR (100 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the JELEPARA, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000060/2023-2024 | 310/AD | 26/04/2023 | 300 | ADITYA HAZRA | 244.02 | 0 | 60
660 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Jelepara W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000216/2023-2024 | 956/AD | 06/06/2023 | 269 | INDIA CONSTRUCTION | 43.94 | 0 | 100
661 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based at Jelepara Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000736/2024-2025 | 4394/AD | 05/11/2024 | 30 | SARDAR ENTERPRISE | 14.29 | 0 | 0
662 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Jelepara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001579/2022-2023 | 10683/AD | 01/02/2023 | 45 | SARDAR ENTERPRISE | 8.87 | 0 | 100
663 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Jelepara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001820/2022-2023 | 12335/AD | 06/03/2023 | 45 | SARDAR ENTERPRISE | 8.59 | 0 | 100
664 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Jelepara New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001884/2022-2023 | 7597/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 3.32 | 0 | 95
665 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000041/2023-2024 | 248/AD | 24/04/2023 | 0 | Resource Division | 40.56 | 0 | 0
666 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000162/2023-2024 | 1058/AD | 15/06/2023 | 0 | Resource Division | 4.64 | 0 | 0
667 | Alipore Division | Canning Sub-division | Construction of 150 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Pipes W/S Scheme for Biprodaspur Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1466] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000041/2023-2024 | 176/AD | 19/04/2023 | 300 | I.S. ENTERPRISE | 423.65 | 0 | 25
668 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Bipradaspur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000296/2024-2025 | 2666/AD | 21/06/2024 | 45 | REZU CONSTRUCTION | 8.92 | 0 | 100
669 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bipradaspur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000297/2024-2025 | 2667/AD | 21/06/2024 | 45 | REZU CONSTRUCTION | 8.61 | 0 | 0
670 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Biprodaspur W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000384/2023-2024 | 1518/AD | 15/07/2023 | 45 | PURKAIT CONSTRUCTION | 43.92 | 0 | 0
671 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Bipradaspur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000545/2024-2025 | 3716/AD | 12/09/2024 | 60 | I.S. ENTERPRISE | 76.62 | 0 | 0
672 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Biprodaspur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001355/2023-2024 | 4427/AD | 06/12/2023 | 665 | BANGA NIRMAN | 11.91 | 0 | 80
673 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Biprodaspur New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001882/2022-2023 | 7524/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 4.94 | 0 | 99
674 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000043/2023-2024 | 250/AD | 24/04/2023 | 0 | Resource Division | 45.11 | 0 | 0
675 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000164/2023-2024 | 1048/AD | 15/06/2023 | 0 | Resource Division | 9.03 | 0 | 0
676 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Ganeshnagar Zone-I W/S Scheme, Block - Namkhan for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000165/2024-2025 | 2516/AD | 15/06/2024 | 244 | M/S NAIYA & MAITY | 20.36 | 0 | 100
677 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ganeshnagar (Zone-I) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1092] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000311/2023-2024 | 1517/AD | 15/07/2023 | 300 | SUJAN KUMAR MISTRY | 242.27 | 0 | 30
678 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ganeshnagar Zone - I W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000316/2023-2024 | 191/KSD | 21/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
679 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at 2nd Tubewell Site of Ganeshnagar Zone - I W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000317/2023-2024 | 193/KSD | 21/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
680 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ganeshnagar Zone-I W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000413/2024-2025 | 3064/AD | 25/07/2024 | 45 | LUCKY CONSTRUCTION (HASNABAD) | 28.53 | 0 | 0
681 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ganeshnagar (Zone-I) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000422/2023-2024 | 1910/AD | 01/08/2023 | 30 | MERAJUL ALAM | 19.95 | 0 | 0
682 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ganeshnagar Zone-I W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13842) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000592/2024-2025 | 4057/AD | 01/10/2024 | 30 | AZAD RAHAMAN LASKAR | 8.68 | 0 | 0
683 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANESHNAGAR (ZONE-I) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001043/2022-2023 | 4156/AD | 19/08/2022 | 45 | M/S R.DUTTA & CO. | 3.02 | 0 | 100
684 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ganeshnagar (Zone-I) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001303/2022-2023 | 9885/AD | 10/01/2023 | 45 | MERAJUL ALAM | 38.59 | 0 | 0
685 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
686 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000131/2023-2024 | 667/AD | 17/05/2023 | 0 | Resource Division | 6.31 | 0 | 0
687 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000477/2023-2024 | 4782/AD | 19/12/2023 | 0 | Resource Division | 14.38 | 0 | 0
688 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000784/2023-2024 | 628/AD | 30/01/2024 | 0 | Resource Division | 0.62 | 0 | 0
689 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Durga Gobindapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000942/2023-2024 | 281(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
690 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Durga Gobindapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000943/2023-2024 | 281(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
691 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DURGA GOBINDOPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000982/2022-2023 | 3668/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.16 | 0 | 100
692 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Durga Gobindapur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000983/2023-2024 | 3002/AD | 26/09/2023 | 30 | BOWEX ENTERPRISE | 9.44 | 0 | 0
693 | Alipore Division | Kakdwip Sub-Division | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Durga Gobindapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13803) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001046/2024-2025 | 4967/AD | 04/12/2024 | 45 | M/S NAIYA & MAITY | 40.6 | 0 | 100
694 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Durga Gobindapur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001413/2023-2024 | 4466/AD | 08/12/2023 | 45 | SWATHI ENTERPRISE | 27.53 | 0 | 0
695 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Durga Gobindapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 350] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001829/2022-2023 | 12098/AD | 28/02/2023 | 1200 | RELIABLE CONSTRUCTIONS | 171.03 | 0 | 33
696 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Durga Gobindapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1176] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001830/2022-2023 | 12099/AD | 28/02/2023 | 899 | RELIABLE CONSTRUCTIONS | 162.3 | 0 | 48
697 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
698 | Alipore Division | Kakdwip Sub-Division | Laying 125 mm dia. UPVC pipe line for providing FHTC at Durga Gobindapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub Division of Alipore Division, P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002570/2023-2024 | 513/KSD | 15/03/2024 | 20 | SOHINI ENTERPRISE | 1.99 | 0 | 100
699 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000094/2023-2024 | 540/AD | 12/05/2023 | 0 | Resource Division | 8.38 | 0 | 0
700 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000313/2023-2024 | 3122/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
701 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000510/2023-2024 | 4943/AD | 22/12/2023 | 0 | Resource Division | 34.01 | 0 | 0
702 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000746/2023-2024 | 581/AD | 29/01/2024 | 0 | Resource Division | 1.5 | 0 | 0
703 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Ramanandapur having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001127/2022-2023 | 8771/AD | 21/12/2022 | 60 | JOY GURU TRADING | 32.55 | 0 | 0
704 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000874/2023-2024 | 781/AD | 03/02/2024 | 0 | Resource Division | 0.65 | 0 | 0
705 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Padmapukhuria having village with maximum 90 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001125/2022-2023 | 8769/AD | 21/12/2022 | 60 | ARBINA ENTERPRISE | 32.04 | 0 | 0
706 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000872/2023-2024 | 779/AD | 03/02/2024 | 0 | Resource Division | 0.59 | 0 | 0
707 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | RTOR000896/2023-2024 | 750/AD | 03/02/2024 | 0 | Resource Division | 0.53 | 0 | 0
708 | Alipore Division | Kakdwip Sub-Division | Laying PVC and UPVC pipe line for providing FHTC at Gobindapur Abad Water Supply Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000225/2022-2023 | 3066/AD | 13/07/2022 | 30 | M/S A.K. GHATAK | 10.71 | 0 | 100
709 | Alipore Division | Kakdwip Sub-Division | Supply, Delivery & Laying of Specials Required for Laying Rising Main & Inter - Connection Line between Tubewells in Gobindapur Abad Water Supply Scheme at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000350/2022-2023 | 335/KSD | 01/08/2022 | 20 | TANMAY ROY CHOWDHURY | 4.41 | 0 | 100
710 | Alipore Division | Kakdwip Sub-Division | Construction of deep foundation with earth work protection in connection with construction of boundary wall at 2nd Tubewell Site of Gobindapur Abad W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000354/2022-2023 | 339/KSD | 01/08/2022 | 20 | MOUMITA ENTERPRISE | 4.75 | 0 | 100
711 | Alipore Division | Kakdwip Sub-Division | Trial Run of distribution system including rising main for Gobindapur Abad Piped Water Supply Scheme under JJM of Pathar Pratima Block under Kakdwip Sub Division of Alipore Division, PHE Dte. [for 3 month] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000427/2022-2023 | 130/KSD | 20/04/2022 | 91 | TANMAY ROY CHOWDHURY | 1.45 | 0 | 92
712 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary etc for Retrofitting of Gobindapur Abad W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09006) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000441/2024-2025 | 3076/AD | 25/07/2024 | 615 | M/S B. ENTERPRISE | 90.93 | 0 | 80
713 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gobindapur Abad W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09006)(2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000451/2024-2025 | 3360/AD | 14/08/2024 | 30 | S. CHAKRABORTY AND CO. | 25.94 | 0 | 0
714 | Alipore Division | Kakdwip Sub-Division | Surging of 1 no. Tubewell for retrofitting of Gobindapur Abad W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000530/2023-2024 | 354/KSD | 09/08/2023 | 562 | S.K.GOLUI | 2.17 | 0 | 100
715 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
716 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000088/2022-2023 | 5595/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
717 | Alipore Division | Canning Sub-division | nking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Tambuldaha (Part - I) having village with maximum 143 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000658/2022-2023 | 6164/AD | 01/11/2022 | 60 | S.C. ENTERPRISE (I) | 56.82 | 0 | 95
718 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Tambuldaha (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001913/2022-2023 | 5153/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.46 | 0 | 0
719 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS at Dhaspara (Zone-I and II) (SM/15221), Ghoramara (SM/14988) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000020/2025-2026 | 2006/AD | 28/04/2025 | 30 | ROY CHOWDHURY ASSOCIATES | 7.24 | 0 | 100
720 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different household for Ghoramara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14988) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000143/2024-2025 | 2481/AD | 14/06/2024 | 292 | M/S. JHARNA ENTERPRISE | 71.83 | 0 | 100
721 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Ghoramara W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001000/2023-2024 | 507/KSD | 03/10/2023 | 7 | M/S. JHARNA ENTERPRISE | 3.87 | 0 | 100
722 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households and Construction of Pump House (5.40m. x 3.60m) including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1291] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001174/2023-2024 | 1037/AD | 13/06/2023 | 45 | M/S. JHARNA ENTERPRISE | 39.71 | 0 | 100
723 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001531/2022-2023 | 11021/AD | 08/02/2023 | 45 | HARIDAS DUTTA | 47.07 | 0 | 92
724 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households and Construction of Pump House (5.40m. x 3.60m) including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ghoramara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1291] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001745/2022-2023 | 11554/AD | 17/02/2023 | 685 | M/S. JHARNA ENTERPRISE | 197.94 | 0 | 100
725 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Shibpur Zone - I & II, Ghoramara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002175/2023-2024 | 954/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.61 | 0 | 100
726 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ghoramara W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002180/2023-2024 | 816/AD | 05/02/2024 | 363 | TAPAS KUMAR PRADHAN | 11.71 | 0 | 100
727 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ghoramara W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002428/2023-2024 | 1458/AD | 11/03/2024 | 295 | ADRIJA ENTERPRISE | 31.62 | 0 | 100
728 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000527/2023-2024 | 12/AD | 02/01/2024 | 0 | Resource Division | 7.67 | 0 | 0
729 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000973/2023-2024 | 1766/AD | 27/03/2024 | 0 | Resource Division | 30.41 | 0 | 0
730 | Alipore Division | Diamond Harbour Sub-Division | Trial Run of existing distribution system (CI/DI/UPVC/HDPE) and other allied works for Falta Zone-IX under Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000823/2024-2025 | 4505/AD | 11/11/2024 | 90 | SRIJON ENTERPRISE | 28.97 | 0 | 0
731 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IX at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001379/2024-2025 | 5524/AD | 28/12/2024 | 90 | SRIJON ENTERPRISE | 36.85 | 0 | 0
732 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IX of Falta block | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001392/2022-2023 | 10864/AD | 04/02/2023 | 810 | SRIJON ENTERPRISE | 340.8 | 0 | 85
733 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-IX at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001408/2024-2025 | 5534/AD | 30/12/2024 | 60 | SRIJON ENTERPRISE | 14.92 | 0 | 0
734 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000434/2023-2024 | 3617/AD | 30/10/2023 | 0 | Resource Division | 3.08 | 0 | 0
735 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000618/2023-2024 | 279/AD | 15/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
736 | Alipore Division | Diamond Harbour Sub-Division | Restoration and Relaying of pipe line (damaged portion) by MS pipe in distribution system (Node Point- 3 to 5, 9 to 12, 12 to 13, 13 to 23) at Falta Zone-III within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000081/2025-2026 | 2422/AD | 23/05/2025 | 30 | SRIJON ENTERPRISE | 6.15 | 0 | 0
737 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-II at Falta block for providing balance pipe lying works, House Hold Tap connection, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000822/2024-2025 | 780/AD | 25/02/2025 | 225 | M/S PARAMESWAR CHOWDHURY | 80.38 | 0 | 75
738 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIA at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001375/2024-2025 | 5520/AD | 28/12/2024 | 45 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 35.51 | 0 | 0
739 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-III of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001537/2023-2024 | 438/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
740 | Alipore Division | Diamond Harbour Sub-Division | Construction of platform of size 600mm x 600mm (inner dimension) for the existing FHTC along with road restoration at Zone-III of Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001923/2022-2023 | 12712/AD | 14/03/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 138.23 | 0 | 70
741 | Alipore Division | Diamond Harbour Sub-Division | Additional laying distribution system at Gazipur and Shibanipur Mouza for covering the command area of Falta Zone-III due to avoiding NH crossings of pipelines under Falta Zone-VII for providing 100% FHTC within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001974/2022-2023 | 12593/AD | 13/03/2023 | 646 | JOY GURU TRADING | 28.35 | 0 | 100
742 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000360/2023-2024 | 3224/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
743 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000849/2023-2024 | 787/AD | 03/02/2024 | 0 | Resource Division | 12.32 | 0 | 0
744 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000926/2023-2024 | 1268/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
745 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000041/2025-2026 | 2031/AD | 29/04/2025 | 60 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 82 | 0 | 0
746 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VI of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001051/2022-2023 | 301/DHSD | 15/09/2022 | 30 | MEASURE LAND | 2.83 | 0 | 0
747 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000345/2023-2024 | 3209/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
748 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000893/2023-2024 | 747/AD | 03/02/2024 | 0 | Resource Division | 20.38 | 0 | 0
749 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000915/2023-2024 | 1257/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
750 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Gopalkata W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000124/2023-2024 | 570/AD | 12/05/2023 | 15 | M/S MANGALCHANDI CONSTRUCTION | 7.59 | 0 | 0
751 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000215/2023-2024 | 955/AD | 06/06/2023 | 57 | SALMAN CONSTRUCTION | 43.94 | 0 | 100
752 | Alipore Division | Canning Sub-division | Construction of 100 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Gopalkata piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 888] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000295/2023-2024 | 3732/AD | 03/11/2023 | 300 | CHAKRABORTTI ENTERPRISE | 258.61 | 0 | 55
753 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Sitefor Ground water Based at Gopalkata Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000737/2024-2025 | 4395/AD | 05/11/2024 | 45 | SUBHO CONSTRUCTION | 32.48 | 0 | 0
754 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No- 2 for Ground water Based at Gopalkata Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000738/2024-2025 | 4407/AD | 05/11/2024 | 30 | M/S. BISWAS CONSTRUCTION(I) | 19.52 | 0 | 0
755 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gopalkata New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001883/2022-2023 | 7596/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 3.28 | 0 | 95
756 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002045/2022-2023 | 13045/AD | 24/03/2023 | 45 | BINAPANI ENTERPRISE | 8.92 | 0 | 0
757 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Gopalkata W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002046/2022-2023 | 13046/AD | 24/03/2023 | 708 | BINAPANI ENTERPRISE | 8.61 | 0 | 100
758 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000062/2023-2024 | 382/AD | 02/05/2023 | 0 | Resource Division | 11.74 | 0 | 0
759 | Alipore Division | Kakdwip Sub-Division | Fuel charges bill for M.V Sidheswari for the month of Dec'22 to March'23. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/03229/2023-2024 | BP-2023-24-1215 | 20/03/2024 | 0 | RAJKUMAR MANNA | 13.72 | 0 | 0
760 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Piprakhali PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11846) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000189/2024-2025 | 924/AD | 05/03/2025 | 60 | M/S PARAMESWAR CHOWDHURY | 55.38 | 0 | 0
761 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Buraburirtat PWSS, Mouza - Sitarampur, Burabuirtat, Gobardhanpur; Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13801) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000342/2024-2025 | 2754/AD | 27/06/2024 | 90 | GROWING CONCERN | 99.12 | 0 | 0
762 | Alipore Division | Kakdwip Sub-Division | Laying pipe line for Buraburir Tat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000617/2023-2024 | 2315/AD | 17/08/2023 | 60 | GROWING CONCERN | 131.1 | 0 | 10
763 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying D.I. Pipe Line including design & drawing of foundation after soil investigation for Buraburirtat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13801) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000644/2024-2025 | 4147/AD | 05/10/2024 | 270 | GROWING CONCERN | 147.24 | 0 | 18
764 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2024 to 31.01.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000664/2024-2025 | 1176/KSD | 26/07/2024 | 184 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
765 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2024 to 31.01.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000671/2024-2025 | 1177/KSD | 26/07/2024 | 184 | PIKASU BOSE | 2.4 | 0 | 0
766 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Buraburirtat W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000721/2023-2024 | 2538/AD | 28/08/2023 | 30 | ANANTA KUMAR GIRI | 5.32 | 0 | 100
767 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BURABURIR TAT PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001035/2022-2023 | 3665/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.89 | 0 | 100
768 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001042/2023-2024 | 325/KSD | 31/07/2023 | 184 | BADSHA ALOM | 2.4 | 0 | 30
769 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001044/2023-2024 | 326/KSD | 31/07/2023 | 184 | PIKASU BOSE | 2.4 | 0 | 100
770 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Buraburir Tat W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001061/2023-2024 | 3379/AD | 11/10/2023 | 45 | SUDIP PRADHAN | 33.31 | 0 | 0
771 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Buraburir Tat W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001062/2023-2024 | 3380/AD | 11/10/2023 | 30 | M/S BHUNIA ENTERPRISE | 11.77 | 0 | 0
772 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Pathar Pratima Block under Kakdwip Sub - Division of Alipore Division, PHE Dte. for the period from 03.12.2022 to 30.11.2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001085/2022-2023 | 563/KSD | 02/12/2022 | 363 | RUPAK DAS MAHAPATRA | 4.8 | 0 | 20
773 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001090/2022-2023 | 321/KSD | 26/07/2022 | 184 | PIKASU BOSE | 2.4 | 0 | 95
774 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001091/2022-2023 | 322/KSD | 26/07/2022 | 184 | BADSHA ALOM | 2.4 | 0 | 0
775 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2022 to 30.11.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001092/2022-2023 | 537/KSD | 23/11/2022 | 365 | RAJKUMAR MANNA | 4.36 | 0 | 20
776 | Alipore Division | Kakdwip Sub-Division | Laboratory Maintenance of Kakdwip Sub - District Water Testing Laboratory under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte.(Period from 08.09.2022 to 07.09.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001093/2022-2023 | 399/KSD | 05/09/2022 | 365 | ANANTA KUMAR GIRI | 0.69 | 0 | 100
777 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Buraburir Tat W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001280/2022-2023 | 9592/AD | 03/01/2023 | 45 | M/S. BOSE CONCERN | 48.69 | 0 | 100
778 | Alipore Division | Kakdwip Sub-Division | Laying Rising Main and construction of 02 nos. Pump House for providing FHTC for Buraburir Tat Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001423/2023-2024 | 4602/AD | 14/12/2023 | 422 | BISWAJIT SAMANTA | 21.27 | 0 | 100
779 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS of Buraburir Tat W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001995/2023-2024 | 468/KSD | 22/09/2023 | 30 | M/S R.DUTTA & CO. | 4.34 | 0 | 100
780 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
781 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Pathar Pratima Block under Kakdwip Sub - Division of Alipore Division, PHE Dte. for the period from 01.12.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002531/2023-2024 | 711/KSD | 30/11/2023 | 91 | RUPAK DAS MAHAPATRA | 1.2 | 0 | 0
782 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002532/2023-2024 | 260/KSD | 31/01/2024 | 182 | PIKASU BOSE | 2.4 | 0 | 0
783 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Ramdebpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14984) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002590/2024-2025 | 922/AD | 05/03/2025 | 60 | CHANDAN ROY | 60.06 | 0 | 0
784 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2025 to 31.07.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002898/2024-2025 | 204/KSD | 24/01/2025 | 181 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
785 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2023 to 31.01.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002948/2023-2024 | 325(A)/KSD | 31/07/2023 | 184 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
786 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2025 to 31.07.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002958/2024-2025 | 227/KSD | 28/01/2025 | 181 | PIKASU BOSE | 2.4 | 0 | 0
787 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/003030/2023-2024 | 259(A)/KSD | 31/01/2024 | 184 | M/S KHAJABABA ENTERPRISE | 2.4 | 0 | 0
788 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000301/2023-2024 | 3096/AD | 28/09/2023 | 0 | Resource Division | 20.07 | 0 | 0
789 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000678/2023-2024 | 444/AD | 24/01/2024 | 0 | Resource Division | 6.75 | 0 | 0
790 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000769/2023-2024 | 603/AD | 29/01/2024 | 0 | Resource Division | 9.54 | 0 | 0
791 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ganeshnagar Zone - II W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000318/2023-2024 | 195/KSD | 22/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
792 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at 2nd Tubewell Site of Ganeshnagar Zone - II W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000319/2023-2024 | 198/KSD | 23/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 100
793 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ganeshnagar Zone-II W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13973) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000414/2024-2025 | 3065/AD | 25/07/2024 | 45 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 28.86 | 0 | 0
794 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ganeshnagar (Zone-II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000423/2023-2024 | 1911/AD | 01/08/2023 | 30 | IQBAL CONSTRUCTION | 19.77 | 0 | 92
795 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ganeshnagar Zone-II W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13973) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000843/2024-2025 | 4578/AD | 15/11/2024 | 30 | M/S DEB ENTERPRISE | 8.56 | 0 | 0
796 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ganeshnagar (Zone-II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001304/2022-2023 | 9886/AD | 10/01/2023 | 45 | IQBAL CONSTRUCTION | 38.59 | 0 | 0
797 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANESHNAGAR (ZONE-II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001341/2022-2023 | 3799/AD | 05/08/2022 | 45 | M/S R.DUTTA & CO. | 3.69 | 0 | 100
798 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ganeshnagar (Zone-II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1366] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001546/2022-2023 | 11020/AD | 08/02/2023 | 300 | SUJATA CONSTRUCTION | 313.36 | 0 | 48
799 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Ganeshnagar Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002077/2023-2024 | 774(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
800 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
801 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000478/2023-2024 | 4782/AD | 19/12/2023 | 0 | Resource Division | 22.81 | 0 | 0
802 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000557/2023-2024 | 45/AD | 03/01/2024 | 0 | Resource Division | 8.11 | 0 | 0
803 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000981/2023-2024 | 1774/AD | 27/03/2024 | 0 | Resource Division | 1.41 | 0 | 0
804 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-B) [No. of FHTC = 450] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000307/2023-2024 | 1510/AD | 15/07/2023 | 90 | M/S ANUBHAB CONSTRUCTION | 117.97 | 0 | 86
805 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Budhakhali Zone-2 PWSS, Block -Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14123) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000307/2024-2025 | 2681/AD | 24/06/2024 | 285 | ASHOKA ENTERPRISE | 156 | 0 | 80
806 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-A) [No. of FHTC = 150] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000310/2023-2024 | 1513/AD | 15/07/2023 | 90 | SUNNY ELECTRIC CO. | 124.9 | 0 | 60
807 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000403/2023-2024 | 1902/AD | 01/08/2023 | 45 | M/S. SONAMONI ENTERPRISE | 11.48 | 0 | 71
808 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000404/2023-2024 | 1903/AD | 01/08/2023 | 45 | S.MITRA & CO. | 11.16 | 0 | 0
809 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000405/2023-2024 | 1904/AD | 01/08/2023 | 45 | M/S BABUSONA ENTERPRISE | 14.66 | 0 | 100
810 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Budhakhali Zone-II (Part- II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001772/2022-2023 | 12045/AD | 27/02/2023 | 45 | M/S MAITY CONSTRUCTION | 38.49 | 0 | 60
811 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Budhakhali [Zone-II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001811/2022-2023 | 06/AD | 01/04/2022 | 45 | M/S R.DUTTA & CO. | 7.3 | 0 | 95
812 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone - II (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) [No. of FHTC = 645] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001827/2022-2023 | 12100/AD | 28/02/2023 | 763 | ASHOKA ENTERPRISE | 334.36 | 0 | 94
813 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Budhakhali Zone - II (Part - I & II) W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002052/2023-2024 | 513/AD | 25/01/2024 | 45 | BARUN KANTI PAUL | 27.79 | 0 | 100
814 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Budhakhali Zone - II (Part - I & II) W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002053/2023-2024 | 514/AD | 25/01/2024 | 310 | R G ENTERPRISE (III) | 9.49 | 0 | 100
815 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Budhakhali Zone-II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002065/2023-2024 | 759/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
816 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
817 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Budhakhali Zone-II Part W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14123) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002186/2024-2025 | 2067/KSD | 28/12/2024 | 20 | IMAGINEER VENTURES | 2.43 | 0 | 0
818 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-II (Part - I and II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002289/2023-2024 | 1027/AD | 19/02/2024 | 45 | M/S. BRINDABAN DAS & SONS | 27.81 | 0 | 51
819 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000489/2023-2024 | 4788/AD | 19/12/2023 | 0 | Resource Division | 22.85 | 0 | 0
820 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000551/2023-2024 | 34/AD | 02/01/2024 | 0 | Resource Division | 9.29 | 0 | 0
821 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile cap for OHR etc. at Indranarayanpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13827) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000195/2024-2025 | 4553/AD | 13/11/2024 | 75 | M/S R.K.ENTERPRISE (SALBAGAN) | 86.17 | 0 | 0
822 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Indranarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000380/2023-2024 | 1773/AD | 26/07/2023 | 45 | SAHANA CO.OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 18.85 | 0 | 30
823 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRANARAYANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000987/2022-2023 | 3673/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.65 | 0 | 100
824 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Indranarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001479/2022-2023 | 10987/AD | 07/02/2023 | 300 | M/S R.K.ENTERPRISE (SALBAGAN) | 285.27 | 0 | 40
825 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indranarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002046/2023-2024 | 528/AD | 25/01/2024 | 45 | SAHANA CO.OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 25.76 | 0 | 0
826 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indranarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002047/2023-2024 | 529/AD | 25/01/2024 | 30 | DEVAM ENTERPRISE | 9.58 | 0 | 0
827 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
828 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000104/2023-2024 | 640/AD | 17/05/2023 | 0 | Resource Division | 6.59 | 0 | 0
829 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000307/2023-2024 | 3102/AD | 28/09/2023 | 0 | Resource Division | 23.04 | 0 | 0
830 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000748/2023-2024 | 583/AD | 29/01/2024 | 0 | Resource Division | 2.74 | 0 | 0
831 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000943/2023-2024 | 1677/AD | 22/03/2024 | 0 | Resource Division | 11.9 | 0 | 0
832 | Alipore Division | Canning Sub-division | Restoration of Kolkata Basanti Road from 59.00 km to 68.00km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01322/2024-2025 | BP-2024-25-626 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 38.98 | 0 | 0
833 | Alipore Division | Canning Sub-division | Laying damaged pipeline (balance portion) under Atharabeki Water Supply Scheme, due to widening and strengthening of Basanti-Kolkata Road within Dhuri Bus Stop and Fakirtakia, Block-Canning - II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000113/2021-2022 | 1196/AD | 07/07/2021 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 48.88 | 0 | 95
834 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1700 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Atharabeki Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000262/2023-2024 | 1450/AD | 13/07/2023 | 90 | SAMSUL ENTERPRISE | 105.53 | 0 | 0
835 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Atharabeki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001322/2022-2023 | 9784/AD | 07/01/2023 | 45 | KALPANA BUILDERS (II) | 39.97 | 0 | 100
836 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Atharabeki W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001667/2022-2023 | 11479/AD | 15/02/2023 | 30 | SATYAM CONSTRUCTION | 19.55 | 0 | 100
837 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabeki W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001685/2022-2023 | 11492/AD | 15/02/2023 | 315 | RAHUL ENTERPRISE | 7.05 | 0 | 100
838 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000004/2023-2024 | 119/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
839 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000139/2023-2024 | 856/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
840 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000733/2023-2024 | 557/AD | 25/01/2024 | 0 | Resource Division | 73.82 | 0 | 0
841 | Alipore Division | Canning Sub-division | Restoration of Jhorer more to Khuribhanga pumping station Road under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01324/2024-2025 | BP-2024-25-621 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 20.08 | 0 | 0
842 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (449 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Maukhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000222/2023-2024 | 1027/AD | 13/06/2023 | 45 | JAMIRUL CONSTRUCTION | 57.91 | 0 | 50
843 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitation at Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001025/2024-2025 | 4935/AD | 03/12/2024 | 30 | KALIDAS ENTERPRISE | 17.41 | 0 | 0
844 | Alipore Division | Canning Sub-division | Additional work of construction of concrete road from main road to reservoir site of Moukhali W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001581/2020-2021 | 981/CSD | 09/11/2020 | 20 | RIVER BENZ CONSTRUCTION | 1.93 | 0 | 90
845 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001691/2022-2023 | 11622/AD | 18/02/2023 | 45 | SRI DURGA ENTERPRISE | 7.05 | 0 | 100
846 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Moukhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 6) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001692/2022-2023 | 11623/AD | 18/02/2023 | 45 | SRI DURGA ENTERPRISE | 7.05 | 0 | 100
847 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V & VI of Augmentation of Moukhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001694/2022-2023 | 11625/AD | 18/02/2023 | 45 | M/S MARIYA ENTERPRISES | 39.17 | 0 | 100
848 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Moukhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002059/2023-2024 | 1305/AD | 04/03/2024 | 30 | GANGA TUBEWELL AND HARDWARE | 2.82 | 0 | 0
849 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 6 at Ground Water Based Augmentation Piped Water Supply Scheme of Moukhali W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002488/2024-2025 | 770/AD | 25/02/2025 | 30 | SMART SOLUTION | 6.99 | 0 | 0
850 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000072/2023-2024 | 550/AD | 25/01/2024 | 0 | Resource Division | 79.87 | 0 | 0
851 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials from Head work site to PH-III for Zone-I & Head work site to PH-III for Zone-II of Deuli (Zone - I & II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000291/2023-2024 | 1435/AD | 13/07/2023 | 90 | UNIVERSAL CORPORATION | 236.64 | 0 | 100
852 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1600 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Deuli (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000324/2023-2024 | 1550/AD | 17/07/2023 | 90 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 105.02 | 0 | 0
853 | Alipore Division | Canning Sub-division | Laying of pipe line in place of existing damage line at Deuli W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000338/2023-2024 | 1555/AD | 17/07/2023 | 90 | SOMA CONSTRUCTION | 106.44 | 0 | 0
854 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Deuli (Zone - I) W/S Scheme under JJM, Block - Canning-II under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000414/2023-2024 | 773/CSD | 02/08/2023 | 40 | S.K.GOLUI | 2.3 | 0 | 99
855 | Alipore Division | Canning Sub-division | Laying damage pipe line from Akkashia Madrasa to H/O Chandika Show at Deuli W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001644/2021-2022 | 1512/CSD | 15/02/2022 | 20 | M/S. TAPAS MONDAL | 4.81 | 0 | 0
856 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 for each zone of Augmentation of Deuli (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001669/2022-2023 | 11480/AD | 15/02/2023 | 585 | ELECTROMECH | 39.19 | 0 | 100
857 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Augmentation of Deuli (Zone - II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001672/2022-2023 | 11483/AD | 15/02/2023 | 1053 | B.K. ENTERPRISE. | 19.99 | 0 | 0
858 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli W/S Scheme (Zone - II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001688/2022-2023 | 11495/AD | 15/02/2023 | 680 | ARFIN CONSTRUCTION | 7.09 | 0 | 100
859 | Alipore Division | Canning Sub-division | Laying damage rising main from Panchayat More to PH-II and other distribution lines at Deuli W/S Scheme (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002162/2020-2021 | 1594/CSD | 23/02/2021 | 30 | M/S. TAPAS MONDAL | 3.85 | 0 | 0
860 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000019/2023-2024 | 225/AD | 22/04/2023 | 0 | Resource Division | 117.02 | 0 | 0
861 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000259/2023-2024 | 3049/AD | 28/09/2023 | 0 | Resource Division | 0.78 | 0 | 0
862 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing ) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Chimta (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1117] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000032/2023-2024 | 125/AD | 13/04/2023 | 600 | KHAN ENTERPRISE | 314.86 | 0 | 65
863 | Alipore Division | Canning Sub-division | Laying of pipeline to connect the uncovered habitation at Chimta (Zone-I and II) W/S Scheme, Block - Gosaba, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000280/2024-2025 | 2495/AD | 15/06/2024 | 105 | SWASTIK CONSTRUCTION | 33.27 | 0 | 70
864 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Chimta (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1117] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000296/2023-2024 | 1506/AD | 15/07/2023 | 300 | MAA SANTOSHI ENTERPRISE | 314.54 | 0 | 39
865 | Alipore Division | Canning Sub-division | Additional work of inter connection & rising main with supply of specials of Augmentation of Chimta (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000480/2024-2025 | 943/CSD | 22/08/2024 | 30 | CHANDRA ENTERPRISE | 3.28 | 0 | 90
866 | Alipore Division | Canning Sub-division | Inter c connection and rising main with supply of specials of Augmentation of Chimta (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000733/2023-2024 | 2894/AD | 19/09/2023 | 15 | GANGA TUBEWELL AND HARDWARE | 9.27 | 0 | 0
867 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No-2 for Ground water Based at Chimta (Zone-I & II)Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000741/2024-2025 | 4398/AD | 05/11/2024 | 30 | MAA SANTOSHI ENTERPRISE | 15.13 | 0 | 0
868 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001116/2022-2023 | 11940/AD | 24/02/2023 | 45 | AQUATECH ENGINEERS | 44.82 | 0 | 98
869 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001117/2022-2023 | 11941/AD | 24/02/2023 | 45 | AQUATECH ENGINEER | 44.84 | 0 | 30
870 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Chimta (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001353/2023-2024 | 4425/AD | 06/12/2023 | 270 | CHANDRA ENTERPRISE | 7.12 | 0 | 100
871 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001739/2022-2023 | 11752/AD | 21/02/2023 | 619 | SOHAM ENTERPRISE | 8.92 | 0 | 100
872 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001740/2022-2023 | 11767/AD | 21/02/2023 | 45 | SOHAM ENTERPRISE | 8.61 | 0 | 0
873 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001741/2022-2023 | 11768/AD | 21/02/2023 | 45 | SOHAM ENTERPRISE | 8.92 | 0 | 0
874 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chimta W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001742/2022-2023 | 11772/AD | 21/02/2023 | 45 | SOHAM ENTERPRISE | 8.61 | 0 | 0
875 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Chimta (Zone - I & II)New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001887/2022-2023 | 11549/AD | 17/02/2023 | 45 | M/S R.DUTTA & CO. | 7.4 | 0 | 0
876 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000060/2023-2024 | 380/AD | 02/05/2023 | 0 | Resource Division | 45.96 | 0 | 0
877 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000195/2023-2024 | 877/AD | 29/05/2023 | 673 | SUPRITI ENTERPRISE | 1165.66 | 0 | 52
878 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-III at Kulpi block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000913/2024-2025 | 4757/AD | 25/11/2024 | 60 | SUPRITI ENTERPRISE | 82.23 | 0 | 0
879 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-III of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001017/2022-2023 | 289/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.45 | 0 | 0
880 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Ramnagar under Zone- III of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002007/2022-2023 | 12913/AD | 21/03/2023 | 30 | S.S.TRADERS | 25.04 | 0 | 90
881 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for fundation for the proposed R.C.C. Over Head Reservoir at Zone-III (Ramnagar, OHR Size-700 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002095/2022-2023 | 330/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
882 | Alipore Division | Diamond Harbour Sub-Division | Laying of pipeline as per revised laying distribution system due to shifting of OHR site under the Augmentation Scheme of Kulpi Zone-III for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002115/2023-2024 | 829/AD | 05/02/2024 | 420 | SUPRITI ENTERPRISE | 85.58 | 0 | 75
883 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000145/2022-2023 | 12/AD | 05/04/2023 | 0 | Resource Division | 23.55 | 0 | 0
884 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000190/2023-2024 | 1630/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
885 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000205/2023-2024 | 2024/AD | 05/08/2023 | 0 | Resource Division | 9.17 | 0 | 0
886 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000630/2023-2024 | 289/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
887 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000857/2023-2024 | 764/AD | 03/02/2024 | 0 | Resource Division | 5.84 | 0 | 0
888 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000933/2023-2024 | 1275/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
889 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
890 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply and allied works at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000116/2023-2024 | 485/AD | 10/05/2023 | 30 | KAMALA ENTERPRISE (I) | 8.57 | 0 | 80
891 | Alipore Division | Raidighi Sub-Division | Restoration of distribution system of piped water supply (N.P. 121-122,109-121, 110-109, 229-232, 228-229, 130-129) at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000265/2022-2023 | 101/RSD | 13/06/2022 | 60 | UNITED BUILDERS | 4.77 | 0 | 100
892 | Alipore Division | Raidighi Sub-Division | Restoration of distribution system of piped water supply (N.P. 113-114, 128-126, 129-128, 130-129,131-130) at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000266/2022-2023 | 102/RSD | 13/06/2022 | 60 | NITYANANDA MONDAL | 4.2 | 0 | 100
893 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000875/2024-2025 | 4659/AD | 20/11/2024 | 120 | MONCON INDIA | 27.43 | 0 | 95
894 | Alipore Division | Raidighi Sub-Division | Construction of approach road for Pump House No. 2 at Nandakumarpur Zone - III W/S Scheme, modified as Zone ¿ XII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001139/2023-2024 | 289/RSD | 29/09/2023 | 60 | MAA KALI ENTERPRISE | 4.29 | 0 | 90
895 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Nandakumarpur Zone - III W/S Scheme, modified as Zone- XII of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001301/2024-2025 | 5375/AD | 23/12/2024 | 30 | M/S R.K.ENTERPRISE | 4.77 | 0 | 0
896 | Alipore Division | Raidighi Sub-Division | Providing FHTC at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001968/2022-2023 | 12722/AD | 14/03/2023 | 45 | R CONSTRUCTION | 87.48 | 0 | 40
897 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000651/2023-2024 | 254/AD | 15/01/2024 | 0 | Resource Division | 5.33 | 0 | 0
898 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- V of Mathurapur-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 4138 ] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000087/2023-2024 | 498/AD | 11/05/2023 | 963 | JAL PRAVAHIKA PVT. LTD. | 569.23 | 0 | 41
899 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 60 | SOURAV DEBNATH | 15.09 | 0 | 0
900 | Alipore Division | Raidighi Sub-Division | Laying of additional Pipe Line at Zone - V of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000876/2024-2025 | 4660/AD | 20/11/2024 | 90 | HARIDAS DUTTA | 16.64 | 0 | 2
901 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000244/2023-2024 | 2914/AD | 20/09/2023 | 0 | Resource Division | 13.83 | 0 | 0
902 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000645/2023-2024 | 249/AD | 15/01/2024 | 0 | Resource Division | 8.36 | 0 | 0
903 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap connection (FHTC) to all the households in Zone-VII of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000072/2022-2023 | 1036/AD | 23/05/2022 | 30 | S.S. ENTERPRISE (II) | 31.2 | 0 | 95
904 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Mathurapur W/S Scheme (Zone-VII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000432/2023-2024 | 1920/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 0
905 | Alipore Division | Raidighi Sub-Division | Construction of steel structure for canal crossing of HDPE pipe (LDS) at at Zone-VII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001137/2022-2023 | 602/RSD | 23/12/2022 | 30 | M/S B ENTERPRISE | 0.98 | 0 | 0
906 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-VII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001726/2020-2021 | 5315/AD | 18/02/2021 | 120 | S.S. ENTERPRISE (II) | 88.26 | 0 | 100
907 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-VII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001960/2022-2023 | 12714/AD | 14/03/2023 | 45 | MONDAL ENTERPRISE - 2 (SDK) | 55.92 | 0 | 75
908 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 7 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000022/2025-2026 | 2008/AD | 28/04/2025 | 30 | RAHIMA ENTERPRISE | 11.92 | 0 | 0
909 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 6 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000023/2025-2026 | 2009/AD | 28/04/2025 | 30 | RAHIMA ENTERPRISE | 11.49 | 0 | 0
910 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-V, VI & VII of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000242/2023-2024 | 1394/AD | 12/07/2023 | 30 | ISHAN CONSTRUCTION | 54.94 | 0 | 0
911 | Alipore Division | Canning Sub-division | Protection of pipe line and other allied works at Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000752/2024-2025 | 4426/AD | 05/11/2024 | 60 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 93.79 | 0 | 0
912 | Alipore Division | Canning Sub-division | Protection of pipe line and other allied works at Augmentation of Bijoynagar W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001060/2024-2025 | 1288/CSD | 20/11/2024 | 30 | A.P. CONSTRUCTION | 4.55 | 0 | 0
913 | Alipore Division | Canning Sub-division | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Augmentation of Bijoynagar piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/15499) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001099/2024-2025 | 5030/AD | 06/12/2024 | 270 | UNITED BUILDERS | 195.23 | 0 | 0
914 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 5 for Ground Water Based at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001241/2024-2025 | 5222/AD | 16/12/2024 | 30 | MAA SANTOSHI ENTERPRISE | 15.05 | 0 | 0
915 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 6) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001699/2022-2023 | 11663/AD | 20/02/2023 | 45 | ESSCON | 8.61 | 0 | 100
916 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bijoynagar W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001715/2022-2023 | 11679/AD | 20/02/2023 | 712 | JYOTI ENTERPRISES | 8.4 | 0 | 100
917 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000114/2022-2023 | 383/AD | 02/05/2023 | 0 | Resource Division | 99.35 | 0 | 0
918 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 60 | M/S B. ENTERPRISE | 27.24 | 0 | 0
919 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-III, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC = 807 Nos.) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000117/2023-2024 | 486/AD | 10/05/2023 | 45 | M/S B.M. CONSTRUCTION | 96.3 | 0 | 95
920 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system and Rising Main system of piped water supply at Zone - III (Koutala PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000277/2024-2025 | 2473/AD | 14/06/2024 | 20 | NITYANANDA MONDAL | 7.42 | 0 | 90
921 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- III of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000659/2024-2025 | 4205/AD | 23/10/2024 | 90 | NITYANANDA MONDAL | 27.44 | 0 | 0
922 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 2 & 3 and approach road and plinth protection at Koutala W/S Scheme, modified as Zone- III of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000990/2023-2024 | 286/RSD | 29/09/2023 | 60 | L.N. ENTERPRISE | 3.48 | 0 | 100
923 | Alipore Division | Raidighi Sub-Division | Repairing of boundary wall at Koutala W/S Scheme, modified as Zone- III of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000991/2023-2024 | 287/RSD | 29/09/2023 | 60 | M/S R.K.ENTERPRISE | 4.76 | 0 | 100
924 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - III of Mathurapur - II Block (Koutala PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001969/2022-2023 | 12723/AD | 14/03/2023 | 30 | NITYANANDA MONDAL | 17.09 | 0 | 95
925 | Alipore Division | Raidighi Sub-Division | Construction of 450 cum. Capacity 20mtr. staging height RCC Over Head Reservoir at as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Mathurapur-II block (zone-III) for Mega surface water based water supply Scheme for Falta Mathurapur, South 24 Parganas under AD PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002154/2019-2020 | 7936/AD | 11/03/2020 | 1826 | PIKASU BOSE | 23.76 | 0 | 100
926 | Alipore Division | Raidighi Sub-Division | Laying distribution system of damaged pipe line of Koutala piped water supply scheme at Zone- III of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002375/2023-2024 | 1215/AD | 29/02/2024 | 45 | KALIDAS ENTERPRISE | 13.5 | 0 | 100
927 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000648/2023-2024 | 251/AD | 15/01/2024 | 0 | Resource Division | 4.97 | 0 | 0
928 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017459) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000018/2023-2024 | 90/AD | 11/04/2023 | 90 | SHEKHAR CHAKRABORTY | 131.1 | 0 | 100
929 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000027/2025-2026 | 2013/AD | 28/04/2025 | 135 | SAHANA ENTERPRISE | 26.16 | 0 | 0
930 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kalaria Zone- IIB W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000129/2023-2024 | 489/AD | 10/05/2023 | 30 | ASHIS ENTERPRISE | 17.98 | 0 | 25
931 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2098] (TSM/017459) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000353/2023-2024 | 1662/AD | 20/07/2023 | 720 | SAHANA ENTERPRISE | 105.65 | 0 | 90
932 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000465/2023-2024 | 1927/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.09 | 0 | 90
933 | Alipore Division | Canning Sub-division | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IIB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000484/2024-2025 | 3543/AD | 02/09/2024 | 45 | SUPRITI ENTERPRISE | 19.63 | 0 | 0
934 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001084/2023-2024 | 3543/AD | 17/10/2023 | 405 | M/S. ASIRUDDIN SEKH ENTERPRISE | 7.28 | 0 | 100
935 | Alipore Division | Canning Sub-division | Sinking of 02 (two) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kalaria (Zone-IIB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001867/2022-2023 | 12456/AD | 10/03/2023 | 45 | B.K. ENTERPRISE. | 40.76 | 0 | 95
936 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IIB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001950/2022-2023 | 11811/AD | 22/02/2023 | 45 | SIRCON ENGINEERING SERVICES | 5.79 | 0 | 95
937 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
938 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000067/2023-2024 | 270/AD | 24/04/2023 | 0 | Resource Division | 34.64 | 0 | 0
939 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1296] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000031/2023-2024 | 124/AD | 13/04/2023 | 400 | M N J ENTERPRISES | 492.25 | 0 | 35
940 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001929/2022-2023 | 11802/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 4.43 | 0 | 95
941 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001983/2022-2023 | 12644/AD | 13/03/2023 | 45 | M/S MA KALI ELECTRIC LIGHT CORPORATION. | 8.83 | 0 | 0
942 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002011/2022-2023 | 12917/AD | 21/03/2023 | 772 | MISTRY CONSTRUCTION | 8.61 | 0 | 100
943 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002032/2022-2023 | 13028/AD | 24/03/2023 | 45 | NILAVA GHOSHAL | 43.98 | 0 | 100
944 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Purba Radhnagar (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002350/2023-2024 | 1165/AD | 27/02/2024 | 340 | A.K. ENTERPRISE | 6.98 | 0 | 90
945 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000046/2023-2024 | 253/AD | 23/04/2023 | 0 | Resource Division | 17.55 | 0 | 0
946 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000316/2024-2025 | 2697/AD | 24/06/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.08 | 0 | 0
947 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000317/2024-2025 | 2698/AD | 24/06/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.08 | 0 | 0
948 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
949 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VI) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000728/2023-2024 | 2889/AD | 19/09/2023 | 15 | A.K. ENTERPRISE (II) | 11.16 | 0 | 0
950 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - II) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000784/2024-2025 | 4485/AD | 11/11/2024 | 231 | SNEHA CONSTRUCTION | 19.59 | 0 | 98
951 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Basanti W/S Scheme (Zone-VI), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000786/2024-2025 | 4486/AD | 11/11/2024 | 30 | SNEHA CONSTRUCTION | 19.59 | 0 | 0
952 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
953 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VI) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001936/2022-2023 | 11807/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.26 | 0 | 0
954 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VI) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001993/2022-2023 | 12684/AD | 14/03/2023 | 45 | NATH CONSTRUCTION | 7.08 | 0 | 1
955 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000026/2023-2024 | 232/AD | 24/04/2023 | 0 | Resource Division | 63.43 | 0 | 0
956 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000155/2023-2024 | 1044/AD | 15/06/2023 | 0 | Resource Division | 7.03 | 0 | 0
957 | Alipore Division | Canning Sub-division | Restoration of Basanti Goran Bose Ganga Mela block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01326/2024-2025 | BP-2024-25-624 | 30/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 99.74 | 0 | 0
958 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -2 of Basanti Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000054/2022-2023 | 790/AD | 12/05/2022 | 30 | G.B. CONSTRUCTION (TW) | 17.99 | 0 | 0
959 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000109/2023-2024 | 507/AD | 11/05/2023 | 15 | SUPER CONSTRUCTION | 6.22 | 0 | 95
960 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
961 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
962 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-II) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001868/2022-2023 | 12521/AD | 10/03/2023 | 45 | SNEHA CONSTRUCTION | 39.8 | 0 | 81
963 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001933/2022-2023 | 11805/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.2 | 0 | 99
964 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001988/2022-2023 | 12679/AD | 14/03/2023 | 706 | M/S KALIPADA JANA | 7.29 | 0 | 98
965 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-II) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001989/2022-2023 | 12680/AD | 14/03/2023 | 45 | M/S ANNAPURNA ENTERPRISE | 7.03 | 0 | 0
966 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000022/2023-2024 | 228/AD | 24/04/2023 | 0 | Resource Division | 14.27 | 0 | 0
967 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000151/2023-2024 | 1046AD | 15/06/2023 | 0 | Resource Division | 9.38 | 0 | 0
968 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000251/2023-2024 | 3043/AD | 28/09/2023 | 0 | Resource Division | 62.96 | 0 | 0
969 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
970 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bhubannagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000959/2023-2024 | 2991/AD | 26/09/2023 | 45 | M/S SABITRI ENTERPRISE | 27.77 | 0 | 0
971 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bhubannagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000960/2023-2024 | 2992/AD | 26/09/2023 | 30 | M/S. PARAMESWAR ENTERPRISE | 9.54 | 0 | 0
972 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Bhubannagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001832/2022-2023 | 12182/AD | 01/03/2023 | 45 | SUNDARBAN SPARK TRADERS | 38.5 | 0 | 50
973 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
974 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Bhubannagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002165/2022-2023 | 8338/AD | 12/12/2022 | 45 | LEMNISCATE | 6.05 | 0 | 100
975 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000126/2023-2024 | 662/AD | 17/05/2023 | 0 | Resource Division | 13.7 | 0 | 0
976 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000457/2023-2024 | 4720/AD | 18/12/2023 | 0 | Resource Division | 33.36 | 0 | 0
977 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000820/2023-2024 | 665/AD | 30/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
978 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000995/2023-2024 | 1788/AD | 27/03/2024 | 0 | Resource Division | 6.44 | 0 | 0
979 | Alipore Division | Baruipur Sub-Division | Road restoration for Canning mam to Padma Stopaj Via Kailasbabur Abad Khal Par | AE BSD,Assistant Engineer | Junior Engineer | BILL/01675/2024-2025 | BP-2024-25-780 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.72 | 0 | 0
980 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000166/2023-2024 | 2264/AD | 14/08/2023 | 45 | SARADA CONSTRUCTION | 61.08 | 0 | 60
981 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Shibnagar Abad W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000230/2024-2025 | 2560/AD | 18/06/2024 | 30 | SUKUMAR HALDAR | 9.6 | 0 | 0
982 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000231/2024-2025 | 2542/AD | 18/06/2024 | 45 | M/S SAKTI GIRI ENTERPRISE | 5.62 | 0 | 0
983 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded GravelFilter for Shibnagar Abad W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18129)(2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000450/2024-2025 | 3359/AD | 14/08/2024 | 113 | SARADA CONSTRUCTION | 20.39 | 0 | 100
984 | Alipore Division | Kakdwip Sub-Division | Construction of Platform and Road Restoration for Shibnagar Abad W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/18129) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000459/2024-2025 | 3418/AD | 21/08/2024 | 30 | SARADA CONSTRUCTION | 18.15 | 0 | 0
985 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001143/2023-2024 | 3671/AD | 01/11/2023 | 700 | PRINCE INDUSTRIES (INDIA) | 381.91 | 0 | 75
986 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002050/2023-2024 | 511/AD | 25/01/2024 | 30 | SRI DURGA ENTERPRISE | 9.58 | 0 | 0
987 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002080/2022-2023 | 13255/AD | 31/03/2023 | 45 | AQUATECH ENGINEERS | 36.97 | 0 | 40
988 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002129/2023-2024 | 819/AD | 05/02/2024 | 631 | S.M. ENTERPRISE | 30.06 | 0 | 80
989 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
990 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Shibnagar Abad W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002277/2023-2024 | 914/AD | 08/02/2024 | 45 | CAMELIA CONSTRUCTION | 26.92 | 0 | 0
991 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Shibnagar Abad Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002573/2023-2024 | 516/KSD | 15/03/2024 | 20 | M/S SANKARI ENTERPRISE (II) | 3.82 | 0 | 0
992 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibnagar Abad PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002619/2023-2024 | 956/KSD | 19/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
993 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000472/2023-2024 | 4778/AD | 19/12/2023 | 0 | Resource Division | 36.29 | 0 | 0
994 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000562/2023-2024 | 50/AD | 03/01/2024 | 0 | Resource Division | 8.93 | 0 | 0
995 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000788/2023-2024 | 632/AD | 30/01/2024 | 0 | Resource Division | 0.43 | 0 | 0
996 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000977/2023-2024 | 1770/AD | 27/03/2024 | 0 | Resource Division | 3.32 | 0 | 0
997 | Alipore Division | Canning Sub-division | Inter connection of Tubewell-1 & Tubewell-2 and laying of pipe line from Chatrakhali PWD Road to Spandan Sishu Academy at Chatrakhali W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000277/2022-2023 | 270/CSD | 19/05/2022 | 30 | M/S. MIHIR KUMAR NASKAR | 1.43 | 0 | 98
998 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Chatrakhali, Zone-II W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000277/2025-2026 | 682/CSD | 26/05/2025 | 30 | SUDIP DEBNATH | 2.4 | 0 | 0
999 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000354/2023-2024 | 1663/AD | 20/07/2023 | 90 | RIVER BENZ CONSTRUCTION | 249.56 | 0 | 0
1000 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000371/2023-2024 | 1572/AD | 17/07/2023 | 733 | SUPRITI ENTERPRISE | 308.46 | 0 | 22
1001 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Chatrakhali (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000374/2023-2024 | 1573/AD | 17/07/2023 | 15 | BHOLANATH CONSTRUCTION | 13.56 | 0 | 0
1002 | Alipore Division | Canning Sub-division | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Chatrakhali (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000387/2023-2024 | 1576/AD | 17/07/2023 | 90 | ANWAR SHAIKH | 77.59 | 0 | 0
1003 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Chatrakhali (Zone-II) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000388/2023-2024 | 1577/AD | 17/07/2023 | 30 | MAA SARADA ENTERPRISE | 19.57 | 0 | 0
1004 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Chatrakhali (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000391/2023-2024 | 1777/AD | 26/07/2023 | 15 | M/S BABUSONA ENTERPRISE | 13.7 | 0 | 0
1005 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000469/2023-2024 | 1781/AD | 26/07/2023 | 45 | M/S. TAPAS MONDAL | 7.37 | 0 | 0
1006 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000470/2023-2024 | 1782/AD | 26/07/2023 | 45 | SUJIT KUMAR GHOSH | 7.11 | 0 | 0
1007 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000471/2023-2024 | 1783/AD | 26/07/2023 | 45 | M/S. TAPAS MONDAL | 7.11 | 0 | 0
1008 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-IV] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000472/2023-2024 | 1784/AD | 26/07/2023 | 45 | SUJIT KUMAR GHOSH | 7.11 | 0 | 0
1009 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-II) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000473/2023-2024 | 1785/AD | 26/07/2023 | 45 | SUSHANTA MANDAL | 7.11 | 0 | 0
1010 | Alipore Division | Canning Sub-division | onstruction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000474/2023-2024 | 1786/AD | 26/07/2023 | 45 | SABITA INFRASTRUCTURE | 7.11 | 0 | 0
1011 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000475/2023-2024 | 1787/AD | 26/07/2023 | 45 | JAGANNATH CONSTRUCTION | 7.11 | 0 | 0
1012 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Chatrakhali (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000614/2023-2024 | 1832/AD | 27/07/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 15.03 | 0 | 98
1013 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water basedAugmentation Piped Water Supply Scheme for the CHATRAKHALI (ZONE-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000755/2024-2025 | 4439/AD | 06/11/2024 | 270 | SUPRITI ENTERPRISE | 309.22 | 0 | 30
1014 | Alipore Division | Canning Sub-division | Sinking of 1 Nos. 200mm x 100mm dia. 420 mtr. deep Tubewell (Replacement) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Chatrakhali Water Supply Scheme Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000934/2020-2021 | 4862/AD | 28/01/2021 | 45 | AQUATECH ENGINEERS | 16.7 | 0 | 99
1015 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chatrakhali W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001147/2023-2024 | 3692/AD | 02/11/2023 | 45 | I.B. ENTERPRISE | 7.36 | 0 | 0
1016 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of the Augmentation Ground Water Based at Chatrakhali (Zone-I, II & III) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (Zone-I, TW No. 1 replacement Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002379/2023-2024 | 1203/AD | 29/02/2024 | 399 | BHATTACHARJEE & CO. | 19.68 | 0 | 99
1017 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
1018 | Alipore Division | Canning Sub-division | Supply and delivery of UPVC pipe (CD) for Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Augmentation Ground Water Based at Chatrakhali (Zone - I, II & III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Zone - I,Tubewell No. - 1, Replacement Tubewell) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/003677/2024-2025 | 258/CSD | 04/03/2025 | 2 | BHATTACHARJEE & CO. | 1.58 | 0 | 95
1019 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000032/2023-2024 | 237/AD | 24/04/2023 | 0 | Resource Division | 157.26 | 0 | 0
1020 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000387/2023-2024 | 328/AD | 19/01/2024 | 0 | Resource Division | 41.73 | 0 | 0
1021 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000073/2023-2024 | 54/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1022 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gurudaspur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/10486) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000232/2024-2025 | 2607/AD | 19/06/2024 | 60 | UNITED BUILDERS | 87.78 | 0 | 0
1023 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Gurudaspur W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000275/2023-2024 | 1425/AD | 13/07/2023 | 45 | UNITED BUILDERS | 31.2 | 0 | 100
1024 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GURUDASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000441/2022-2023 | 292/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.41 | 0 | 100
1025 | Alipore Division | Kakdwip Sub-Division | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 8.23 | 0 | 100
1026 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Gurudaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000900/2022-2023 | 7274/AD | 24/11/2022 | 300 | UNITED BUILDERS | 411.28 | 0 | 80
1027 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gurudaspur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001614/2021-2022 | 613/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 1.92 | 0 | 100
1028 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS of Gurudaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001996/2023-2024 | 469/KSD | 22/09/2023 | 30 | ROY CHOWDHURY ASSOCIATES | 3.53 | 0 | 100
1029 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
1030 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.07.2024 to 08.10.2024). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002171/2024-2025 | 2889/AD | 08/07/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
1031 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 09.10.2024 to 07.01.2025). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002173/2024-2025 | 4157/AD | 05/10/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
1032 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 3nos Pump House site of Gurudaspur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10486) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002181/2024-2025 | 2064/KSD | 28/12/2024 | 20 | KANIKA CONSTRUCTION | 3.94 | 0 | 0
1033 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000053/2022-2023 | 3918/AD | 12/08/2022 | 0 | Resource Division | 47.6 | 0 | 0
1034 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000311/2023-2024 | 3120/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1035 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000570/2023-2024 | 77/AD | 03/01/2024 | 0 | Resource Division | 5.22 | 0 | 0
1036 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000739/2023-2024 | 574/AD | 29/01/2024 | 0 | Resource Division | 14.83 | 0 | 0
1037 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with soil investigation, Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. for Augmentation of Kusumtala Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/12731) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000304/2024-2025 | 2687/AD | 24/06/2024 | 600 | L.N. ENTERPRISE | 279.17 | 0 | 70
1038 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Kusumtala W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/12731) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000417/2024-2025 | 3068/AD | 25/07/2024 | 30 | M/S. PAPIYA ENTERPRISE | 10.67 | 0 | 0
1039 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KUSUMTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000488/2022-2023 | 4191/AD | 22/08/2022 | 45 | M/S R.DUTTA & CO. | 5.21 | 0 | 100
1040 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kusumtala Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 350] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000547/2022-2023 | 5723/AD | 13/10/2022 | 901 | M/S B. ENTERPRISE | 250.59 | 0 | 100
1041 | Alipore Division | Kakdwip Sub-Division | Surging and repairing of 1st Tube well of Kusumtala Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000597/2022-2023 | 5922/AD | 19/10/2022 | 15 | S.K.GOLUI | 5.1 | 0 | 100
1042 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Kusumtala W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000922/2023-2024 | 2975/AD | 26/09/2023 | 30 | S. CHAKRABORTY AND CO. | 22.7 | 0 | 0
1043 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kusumtala, Bagdanga, Baliara PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002138/2023-2024 | 939/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.54 | 0 | 100
1044 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000291/2023-2024 | 3086/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1045 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000494/2023-2024 | 4793/AD | 19/12/2023 | 0 | Resource Division | 25.9 | 0 | 0
1046 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000544/2023-2024 | 28/AD | 02/01/2024 | 0 | Resource Division | 2.08 | 0 | 0
1047 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000783/2023-2024 | 627/AD | 30/01/2024 | 0 | Resource Division | 0.75 | 0 | 0
1048 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000988/2023-2024 | 1781/AD | 27/03/2024 | 0 | Resource Division | 14.03 | 0 | 0
1049 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000149/2025-2026 | 2671/AD | 09/06/2025 | 45 | FREEDOM CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 7.06 | 0 | 0
1050 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal after dismantling of dilapidated R.C.C. Elevated Reservoir of Capcaity 50000 Gallon at Narayanpur W/S Scheme, Block - Namkhana, South 24 Parganas under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000150/2025-2026 | 2672/AD | 09/06/2025 | 400 | SUPREME NIRMAN UDYOG | 131.79 | 0 | 0
1051 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Narayanpur W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000218/2024-2025 | 2601/AD | 19/06/2024 | 30 | CHANDRA ENTERPRISE | 9.59 | 0 | 0
1052 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanpur Zone II W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000330/2024-2025 | 2733/AD | 25/06/2024 | 60 | M/S B. ENTERPRISE | 117.78 | 0 | 0
1053 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanpur Zone I W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000403/2024-2025 | 3186/AD | 31/07/2024 | 60 | C L B SYNDICATE | 58.37 | 0 | 0
1054 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001030/2021-2022 | 544/KSD | 01/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.57 | 0 | 98
1055 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 Nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 2647] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001142/2023-2024 | 3655/AD | 31/10/2023 | 883 | M/S B. ENTERPRISE | 470.08 | 0 | 92
1056 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NARAYANPUR )) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001364/2023-2024 | 3437/AD | 12/10/2023 | 45 | M/S R.DUTTA & CO. | 15.05 | 0 | 100
1057 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001419/2023-2024 | 1575/AD | 16/03/2024 | 334 | SAFTI PRIVATE LIMITED | 18.21 | 0 | 0
1058 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001420/2023-2024 | 1576/AD | 16/03/2024 | 334 | SAFTI PRIVATE LIMITED | 13.36 | 0 | 0
1059 | Alipore Division | Kakdwip Sub-Division | Laying distribution system along with Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main & FHTC for 01 year after completion of FHTC work for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001452/2023-2024 | 4690/AD | 18/12/2023 | 90 | M/S SWAPAN KUMAR PRADHAN | 79.34 | 0 | 50
1060 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Narayanpur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001453/2023-2024 | 1190/AD | 28/02/2024 | 379 | SAFTI PRIVATE LIMITED | 31.47 | 0 | 0
1061 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001610/2021-2022 | 608/KSD | 27/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 4.57 | 0 | 0
1062 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Narayanpur W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001619/2021-2022 | 622/KSD | 05/10/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.31 | 0 | 0
1063 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
1064 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at 2nd Tubewell site of Zone-I of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002215/2024-2025 | 2110/KSD | 30/12/2024 | 15 | AZAD RAHAMAN LASKAR | 2.58 | 0 | 0
1065 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at 3rd Tubewell site of Zone-I of Narayanpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18984) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002216/2024-2025 | 2111/KSD | 30/12/2024 | 15 | AZAD RAHAMAN LASKAR | 2.32 | 0 | 0
1066 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Iswaripur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18128) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002525/2024-2025 | 810/AD | 27/02/2025 | 30 | SIMPLEX DRILLING CO. | 20.37 | 0 | 0
1067 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Narayanganj W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15046) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002589/2024-2025 | 921/AD | 05/03/2025 | 30 | M/S P. B. CONSTRUCTION | 7.18 | 0 | 0
1068 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Narayanpur PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/002617/2023-2024 | 894/KSD | 18/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1069 | Alipore Division | Kakdwip Sub-Division | Continuation order for Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/003232/2023-2024 | 370/KSD | 19/02/2024 | 274 | BIMALENDU GIRI | 0.61 | 0 | 0
1070 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000004/2024-2025 | 5157/AD | 12/12/2024 | 0 | Resource Division | 123.2 | 0 | 0
1071 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000492/2023-2024 | 4791/AD | 19/12/2023 | 0 | Resource Division | 28.85 | 0 | 0
1072 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000547/2023-2024 | 30/AD | 02/01/2024 | 0 | Resource Division | 22.85 | 0 | 0
1073 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000792/2023-2024 | 637/AD | 30/01/2024 | 0 | Resource Division | 24.89 | 0 | 0
1074 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Gangadharpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18697) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000359/2024-2025 | 2872/AD | 08/07/2024 | 75 | SUPER SKILL | 178.53 | 0 | 0
1075 | Alipore Division | Kakdwip Sub-Division | Construction of 700 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000532/2023-2024 | 3740/AD | 03/11/2023 | 693 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 489.98 | 0 | 20
1076 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000533/2023-2024 | 2146/AD | 09/08/2023 | 601 | SUPER SKILL | 312.7 | 0 | 30
1077 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation at Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000556/2023-2024 | 2238/AD | 11/08/2023 | 493 | S.M. ENTERPRISE | 18.81 | 0 | 100
1078 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000577/2023-2024 | 2263/AD | 14/08/2023 | 30 | M/S. SIKHA ENTERPRISE | 30.66 | 0 | 0
1079 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Gangadharpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000641/2023-2024 | 2033/AD | 05/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 8.84 | 0 | 100
1080 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 700 cum. capacity OHR of Dakshin Gangadharpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002071/2023-2024 | 767(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1081 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1082 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000304/2023-2024 | 3099/AD | 28/09/2023 | 0 | Resource Division | 133.07 | 0 | 0
1083 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000308/2023-2024 | 3117/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1084 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000526/2023-2024 | 4986/AD | 26/12/2023 | 0 | Resource Division | 16.64 | 0 | 0
1085 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000568/2023-2024 | 79/AD | 03/01/2024 | 0 | Resource Division | 5.35 | 0 | 0
1086 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000767/2023-2024 | 601/AD | 29/01/2024 | 0 | Resource Division | 5.56 | 0 | 0
1087 | Alipore Division |  | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Kusumtala Water Supply Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000466/2021-2022 | 2414/AD | 15/09/2021 | 45 | PIJUSH KANTI TRIPATHI | 13.41 | 0 | 100
1088 | Alipore Division |  | Surging and repairing of 1st Tube well of Kusumtala Water Supply Scheme under JJM, Block - Namkhana under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. |  |  | ORD/000597/2022-2023 | 5922/AD | 19/10/2022 | 15 | S.K.GOLUI | 5.1 | 0 | 100
1089 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households and operation & maintenance for 1(One) year and repairing of distribution main of Kusumtala Water Supply Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001373/2020-2021 | 5129/AD | 08/02/2021 | 365 | PIJUSH KANTI TRIPATHI | 73.47 | 35.34 | 100
1090 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Tambuldaha (Part - II) having village with maximum 143 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000659/2022-2023 | 6165/AD | 01/11/2022 | 60 | G. S. CONSTRUCTION & CO. | 47.99 | 0 | 51
1091 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Tambuldaha (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001914/2022-2023 | 5154/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0
1092 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-II) Water Supply Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000111/2021-2022 | 1194/AD | 07/07/2021 | 45 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.47 | 0 | 51
1093 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000281/2023-2024 | 3080/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1094 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000794/2023-2024 | 639/AD | 30/01/2024 | 0 | Resource Division | 9.86 | 0 | 0
1095 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Mahishmari Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001243/2020-2021 | 2274/AD | 12/10/2020 | 365 | M. MUKHERJEE | 106.14 | 80.41 | 95
1096 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part B) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000015/2022-2023 | 332/AD | 18/04/2022 | 365 | M/S. ROY CHOWDHURY & CO. | 110.99 | 0 | 68
1097 | Alipore Division | Canning Sub-division | Relaying and repairing of pipeline Daria Water Supply Scheme near PH - 1, 2 and 3 Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000112/2021-2022 | 1195/AD | 07/07/2021 | 45 | DEBARATI ENTERPRISE | 35.86 | 0 | 100
1098 | Alipore Division | Canning Sub-division | Repairing and extension of pipeline for FHTC work for Daria Waster Supply Scheme, Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000197/2022-2023 | 2642/AD | 29/06/2022 | 30 | A.K. SIKDAR | 16.14 | 0 | 100
1099 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. [Part - A] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001136/2021-2022 | 5542/AD | 20/01/2022 | 365 | A.K. SIKDAR | 47.45 | 0 | 100
1100 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000014/2021-2022 | 5620/AD | 25/01/2022 | 0 | Resource Division | 5.4 | 0 | 0
1101 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000017/2022-2023 | 1174/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
1102 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000497/2020-2021 | 5312/AD | 18/02/2021 | 365 | MONDAL PRECISION PRIVATE LIMITED | 105.31 | 0 | 90
1103 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Srinagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001551/2021-2022 | 6727/AD | 17/03/2022 | 15 | SUDIP PRADHAN | 11.34 | 0 | 90
1104 | Alipore Division | Kakdwip Sub-Division | Laying D.I. Pipe Line for Rising Main and inter connection in between Tubewell No. 1 & Tubewell No. 2 for Srinagar W/S Scheme under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001935/2020-2021 | 1348/KSD | 23/02/2021 | 10 | SARADA CONSTRUCTION | 4.77 | 0 | 80
1105 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Banibadabelekhali Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000087/2020-2021 | 5123/AD | 08/02/2021 | 365 | DIVINE | 162.5 | 105.59 | 92
1106 | Alipore Division | Canning Sub-division | Construction of concrete road (balanced portion) in OHR premises of Pump House no. - 1 of Banibadabelekhali W/S Scheme, Block - Canning I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000370/2025-2026 | 671/CSD | 26/05/2025 | 30 | A.N.S. ENTERPRISE | 1.71 | 0 | 0
1107 | Alipore Division | Kakdwip Sub-Division | Hire Charges Vehicle bill (June '22 to Oct'22) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/03273/2023-2024 |  | 20/03/2024 | 0 | RAJKUMAR MANNA | 6.29 | 0 | 0
1108 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of June'22 to August'22 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | BILL/03275/2023-2024 | BP-2023-24-1259 | 26/03/2024 | 0 | RAJKUMAR MANNA | 1.1 | 0 | 0
1109 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Taktipur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11876) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000412/2024-2025 | 3063/AD | 25/07/2024 | 45 | RAJ ENTERPRISE | 38.71 | 0 | 0
1110 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Taktipur Zone- II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11876) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000466/2024-2025 | 3461/AD | 23/08/2024 | 45 | GHOSH CONSTRUCTION | 18.54 | 0 | 0
1111 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 29.09.2022 to 30.11.2022 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000776/2022-2023 | 266/HQ-II/AD | 28/09/2022 | 63 | PRIYANKI SADHUKHAN | 0.8 | 0 | 85
1112 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001870/2020-2021 | 1301/KSD | 23/02/2021 | 10 | M/S THREE STAR & CON. | 4.39 | 0 | 93
1113 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Madhya Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001874/2020-2021 | 1303/KSD | 23/02/2021 | 10 | M/S. MAA MENAKA ENTERPRISE | 4.38 | 0 | 93
1114 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001889/2020-2021 | 1311/KSD | 23/02/2021 | 10 | M/S THREE STAR & CON. | 4.38 | 0 | 92
1115 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001907/2020-2021 | 1322/KSD | 23/02/2021 | 10 | M/S. MA LAXMI ENTERPRISE | 4.38 | 0 | 93
1116 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Naskarchak for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001919/2020-2021 | 1329/KSD | 23/02/2021 | 10 | MOUMITA ENTERPRISE | 4.39 | 0 | 93
1117 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Janarchak for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001921/2020-2021 | 1331/KSD | 23/02/2021 | 10 | MOUMITA ENTERPRISE | 4.39 | 0 | 93
1118 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001925/2020-2021 | 1337/KSD | 23/02/2021 | 10 | SUFIA ENTERPRISE | 4.39 | 0 | 93
1119 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001927/2020-2021 | 1339/KSD | 23/02/2021 | 10 | M/S. MA LAXMI ENTERPRISE | 4.39 | 0 | 93
1120 | Alipore Division | Kakdwip Sub-Division | Laying UPVC Pipe Line for Providing House Connection to the Households of Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001929/2020-2021 | 1342/KSD | 23/02/2021 | 15 | SARADA CONSTRUCTION | 3.07 | 0 | 100
1121 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001931/2020-2021 | 1344/KSD | 23/02/2021 | 10 | SUFIA ENTERPRISE | 4.38 | 0 | 86
1122 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Madhya Para and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001933/2020-2021 | 1346/KSD | 23/02/2021 | 10 | M/S. MAA MENAKA ENTERPRISE | 4.39 | 0 | 91
1123 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Narayanpur and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001970/2020-2021 | 1335/KSD | 23/02/2021 | 10 | M/S MAA BASANTI ENTERPRISE | 4.38 | 0 | 93
1124 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Narayanpur and Taktipur (Part) for Taktipur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Phase-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001972/2020-2021 | 1341/KSD | 23/02/2021 | 10 | M/S MAA BASANTI ENTERPRISE | 4.38 | 0 | 92
1125 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000824/2023-2024 | 669/AD | 30/01/2024 | 0 | Resource Division | 8.82 | 0 | 0
1126 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Maukhali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000070/2021-2022 | 867/AD | 21/06/2021 | 365 | TANMAY ROY CHOWDHURY | 203.52 | 59.8 | 44
1127 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Puinjali Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000089/2020-2021 | 5124/AD | 08/02/2021 | 365 | RAMEN GHOSH | 87.24 | 0 | 82
1128 | Alipore Division | Canning Sub-division | Laying of pipeline of uncovered FHTC work area of Puinjali Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001179/2022-2023 | 8775/AD | 21/12/2022 | 30 | RAMEN GHOSH | 18.23 | 0 | 80
1129 | Alipore Division | Canning Sub-division | Providing support service for detail surveying, cross checking of available LOP with making permission drawing for other department by using Survey Instruments at Kolkata-Basanti Road (SH 3A, from chainage 71.000 to 86.790), Basanti-Godkhali Road (SH 3A, from chainage 0.000 to 9.894) and Bharatgar Bazar to Ganga Mela Road (from chainage 5.800 to 11.900) like Remotely Piloted Aircraft System / DGPS / Total Station etc. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000272/2022-2023 | 265/CSD | 19/05/2022 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 1.82 | 0 | 98
1130 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Bharatgarh W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000749/2024-2025 | 4421/AD | 05/11/2024 | 30 | RAKTIM ENTERPRISE | 27.39 | 0 | 0
1131 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Bharatgarh W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000750/2024-2025 | 4422/AD | 05/11/2024 | 30 | RAKTIM ENTERPRISE | 12.56 | 0 | 0
1132 | Alipore Division | Canning Sub-division | Laying High Density Poly-ethylene Pipe in connection with functional house hold tap connection (FHTC) in Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001735/2020-2021 | 1438/CSD | 25/01/2021 | 30 | SRIJON ENTERPRISE | 4.8 | 0 | 100
1133 | Alipore Division | Canning Sub-division | Laying High Density Poly-ethylene Pipe in connection with functional house hold tap connection (FHTC) in Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001736/2020-2021 | 1439/CSD | 25/01/2021 | 30 | SRIJON ENTERPRISE | 4.69 | 0 | 98
1134 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials at TW No. 1 & 5 of Bharatgarh W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/003338/2024-2025 | 36./CSD | 09/01/2025 | 30 | RAKTIM ENTERPRISE | 2.04 | 0 | 0
1135 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000400/2023-2024 | 358/AD | 19/01/2024 | 0 | Resource Division | 3.39 | 0 | 0
1136 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Jyotishpur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001302/2020-2021 | 2101/AD | 01/10/2020 | 365 | M/S. JAYDEEP DASGUPTA | 108.5 | 66.19 | 100
1137 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2021 to 30.11.2022) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/01169/2022-2023 | BP-2023-24-18 | 18/04/2023 | 0 | RAJKUMAR MANNA | 6.51 | 0 | 0
1138 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division under Alipore Division, P.H.E. Dte. in connection with execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas (Period from 01.12.2021 to 30.11.2022) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/01170/2022-2023 | BP-2023-24-31 | 28/04/2023 | 0 | RAJKUMAR MANNA | 6.06 | 0 | 0
1139 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub Division of Alipore Division, PHE Dte. (01.06.2022 to 31.08.2022) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | BILL/03520/2023-2024 | BP-2023-24-1074 | 24/02/2024 | 0 | RAJKUMAR MANNA | 6.51 | 0 | 0
1140 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Bishnupur Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000002/2022-2023 | 28/AD | 04/04/2022 | 45 | M. MUKHERJEE | 114.37 | 0 | 98
1141 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Land Development, Boundary Wall Repair and Painting and Approach Road at 1st Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000338/2025-2026 | 3044/AD | 30/06/2025 | 45 | PALASH HALDAR | 5.71 | 0 | 0
1142 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Land Development, Boundary Wall Painting and Repair and Approach Road at 2nd Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000449/2025-2026 | 3567/AD | 25/07/2025 | 45 | SWAPAN GUCHHAIT | 3.89 | 0 | 0
1143 | Alipore Division | Kakdwip Sub-Division | Surging of 3 nos. Tubewell for Augmentation of Bishnupur- 1 no., Mahishamari- 1 no., Kamalpur Rudranagar- 1 no. W/S Scheme under JJM, Block - Sagar under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000506/2024-2025 | 3607/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 5.34 | 0 | 100
1144 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000382/2023-2024 | 3568/AD | 18/10/2023 | 0 | Resource Division | 10.38 | 0 | 0
1145 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000694/2023-2024 | 464/AD | 24/01/2024 | 0 | Resource Division | 10.19 | 0 | 0
1146 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works along the East side of Main Road for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part - S) (SM/11747) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000759/2024-2025 | 4442/AD | 06/11/2024 | 30 | M/S. MANDAL ENTERPRISE | 9.79 | 0 | 100
1147 | Alipore Division | Kakdwip Sub-Division | HIRING OF AN INSPECTION VEHICLE (DIESEL OPERATED WITH LUXURY PERMIT) FOR USE OF ASSISTANT ENGINEER (HQ-II), ALIPORE DIVISION, PHE DTE. (FOR THE PERIOD FROM 01.09.2024 TO 28.02.2025) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000864/2024-2025 | 3534/HQ-II/AD | 30/08/2024 | 182 | BINDU PRASAD DEVI | 2.4 | 0 | 55
1148 | Alipore Division | Kakdwip Sub-Division | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.03.2024 to 30.06.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/003075/2023-2024 | 1142/AD | 27/02/2024 | 121 | M/S P. B. CONSTRUCTION | 1.6 | 0 | 0
1149 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000074/2022-2023 | 4849/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
1150 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000378/2023-2024 | 3517/AD | 16/10/2023 | 0 | Resource Division | 14.31 | 0 | 0
1151 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- XVII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000132/2023-2024 | 674/AD | 17/05/2023 | 813 | BALAJI UDDYOG | 553.99 | 0 | 60
1152 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000636/2023-2024 | 240/AD | 15/01/2024 | 0 | Resource Division | 12.62 | 0 | 0
1153 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001057/2021-2022 | 2345/AD | 09/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.42 | 0 | 100
1154 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001083/2021-2022 | 574/KSD | 10/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.6 | 0 | 100
1155 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & boundary wall at 3rd Tubewell site for Mandirtala (PH-3, Kuntala) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08805) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001292/2024-2025 | 1925/KSD | 20/12/2024 | 25 | IMAGINEER VENTURES | 3.29 | 0 | 100
1156 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Mandirtala W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001618/2021-2022 | 618/KSD | 27/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.32 | 0 | 100
1157 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000706/2023-2024 | 476/AD | 24/01/2024 | 0 | Resource Division | 21.22 | 0 | 0
1158 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households for 43 (forty three) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sibnagar W/S Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000015/2021-2022 | 3164/AD | 09/11/2021 | 365 | M/S. SAMADDAR CONSTRUCTION | 84.8 | 0 | 80
1159 | Alipore Division | Kakdwip Sub-Division | Surging of 01 no. Big dia Tubewell of Sibnagar W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000231/2023-2024 | 157/KSD | 01/06/2023 | 20 | S.K.GOLUI | 1.37 | 0 | 95
1160 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
1161 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000840/2023-2024 | 688/AD | 30/01/2024 | 0 | Resource Division | 11.37 | 0 | 0
1162 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000323/2022-2023 | 3870/AD | 08/08/2022 | 30 | M/S PIR BABA ENTERPRISE | 5.96 | 0 | 50
1163 | Alipore Division | Kakdwip Sub-Division | Retrofitting of Distribution System including Providing Functional Household Tap Connection (FHTC) to the households of Gangadharpur Water Supply Scheme , Block ¿ Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte.(Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001145/2021-2022 | 5533/AD | 20/01/2022 | 365 | JAI BHARAT COMMERCIAL CORPORATION | 51.59 | 0 | 58
1164 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000018/2021-2022 | 5624/AD | 25/01/2022 | 0 | Resource Division | 4.4 | 0 | 0
1165 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000273/2023-2024 | 3072/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1166 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000803/2023-2024 | 648/AD | 30/01/2024 | 0 | Resource Division | 3.79 | 0 | 0
1167 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap Connection (FHTC) to all the households in Zone-XII of Mathurapur-I Block including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based water supply scheme for Falta-Mathurapur, District-South 24-Parganas" under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2022-2023 | 1660/AD | 10/06/2022 | 120 | M/S. SUMAN ENTERPRISE | 236.89 | 0 | 95
1168 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000037/2022-2023 | 3584/AD | 29/07/2022 | 0 | Resource Division | 37.95 | 0 | 0
1169 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing for Retrofitting of Bhangankhali W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000817/2022-2023 | 6812/AD | 16/11/2022 | 30 | BANGA NIRMAN | 7.18 | 0 | 0
1170 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Retrofitting of Bhangankhali W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000854/2022-2023 | 6993/AD | 19/11/2022 | 30 | M/S SEKH ENTERPRISE | 19.48 | 0 | 0
1171 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Bhangan Khali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001836/2021-2022 | 658/CSD | 12/08/2021 | 15 | HORIZEN | 2.81 | 0 | 100
1172 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Bhangan Khali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001837/2021-2022 | 659/CSD | 12/08/2021 | 15 | HORIZEN | 3.33 | 0 | 100
1173 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000389/2023-2024 | 330/AD | 19/01/2024 | 0 | Resource Division | 13.96 | 0 | 0
1174 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and allied works for Haripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000126/2022-2023 | 2029/AD | 21/06/2022 | 30 | M/S BOSE & CO. | 18.21 | 0 | 0
1175 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and allied works for Haripur Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000127/2022-2023 | 2030/AD | 21/06/2022 | 30 | M/S BOSE & CO. | 16.85 | 0 | 0
1176 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 4 nos Pump House site of Haripur (Zone-I) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18698) (SM/09075) (SM/09076) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000378/2025-2026 | 3253/AD | 09/07/2025 | 45 | SAMANTA AND COMPANY | 4.35 | 0 | 0
1177 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000076/2022-2023 | 5145/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
1178 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000290/2023-2024 | 3085/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1179 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of habitation - Das Para and Majher Para at Companirchar Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001137/2021-2022 | 5529/AD | 20/01/2022 | 365 | SANKAR HALDER | 28.77 | 0 | 96
1180 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of habitation ¿ Companir Char and Uttar Para at Companir Char Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001140/2021-2022 | 5530/AD | 20/01/2022 | 365 | SWAPAN KUMAR PRADHAN | 36.94 | 0 | 94
1181 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000015/2022-2023 | 1171/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
1182 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000025/2021-2022 | 5762/AD | 02/02/2022 | 0 | Resource Division | 206.4 | 0 | 0
1183 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000700/2023-2024 | 470/AD | 24/01/2024 | 0 | Resource Division | 9.29 | 0 | 0
1184 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Damkal mouza (JL No. 133) in Mathurapur-II, Zone-IX under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000347/2022-2023 | 4074/AD | 18/08/2022 | 60 | M/S B.M. CONSTRUCTION | 62.36 | 0 | 90
1185 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Purba Sridharpur mouza (JL No. 131) and Nagendrapur Mouza (JL No. 132)in Mathurapur-II, Zone-IX under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000348/2022-2023 | 4075/AD | 18/08/2022 | 60 | JAL PRAVAHIKA PVT. LTD. | 84.29 | 0 | 99
1186 | Alipore Division | Raidighi Sub-Division | Land development of OHR site at Zone - IX, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001802/2022-2023 | 932/RSD | 10/03/2023 | 30 | G.B. CONSTRUCTION & CO. | 2.27 | 0 | 10
1187 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000036/2022-2023 | 3583/AD | 29/07/2022 | 0 | Resource Division | 73 | 0 | 0
1188 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000647/2023-2024 | 250/AD | 15/01/2024 | 0 | Resource Division | 21.81 | 0 | 0
1189 | Alipore Division | Raidighi Sub-Division | Repairing of pump house ? 1 & 3 and approach road and plinth protection at Uttar Kashinagar W/S Scheme, modified as Zone- I of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000993/2023-2024 | 290/RSD | 29/09/2023 | 60 | M/S. BISWAS CONSTRUCTION (II) | 3.95 | 0 | 100
1190 | Alipore Division | Raidighi Sub-Division | Repairing of boundary wall at Head work site of Uttar Kashinagar W/S Scheme, modified as Zone- I of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000994/2023-2024 | 291/RSD | 29/09/2023 | 60 | SANKAR HALDER | 4.77 | 0 | 100
1191 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-I (Uttar Kashinagar PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001455/2021-2022 | 6070/AD | 17/02/2022 | 365 | SPA ENTERPRISE | 117 | 0 | 70
1192 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000041/2022-2023 | 3582/AD | 29/07/2022 | 0 | Resource Division | 16.52 | 0 | 0
1193 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000078/2022-2023 | 5550/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
1194 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Dakshin Shibganj W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000230/2023-2024 | 156/KSD | 01/06/2023 | 25 | S.K.GOLUI | 3.36 | 0 | 99
1195 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Dakshin Shibganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/10482) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000380/2024-2025 | 3056/AD | 25/07/2024 | 60 | TRIPTI ENTERPRISE | 171.55 | 0 | 0
1196 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Shibganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/10482) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000418/2024-2025 | 3069/AD | 25/07/2024 | 45 | M/S B. ENTERPRISE | 28.74 | 0 | 60
1197 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Shibganj PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000457/2022-2023 | 298/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.29 | 0 | 0
1198 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000789/2023-2024 | 2785/AD | 12/09/2023 | 300 | TRIPTI ENTERPRISE | 191.9 | 0 | 30
1199 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1200 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002185/2022-2023 | 691/KSD | 23/02/2023 | 365 | M/S B. ENTERPRISE | 1.05 | 0 | 100
1201 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002607/2023-2024 | 293/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1202 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000052/2022-2023 | 3913/AD | 12/08/2022 | 0 | Resource Division | 72.71 | 0 | 0
1203 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000310/2023-2024 | 3119/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1204 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000774/2023-2024 | 608/AD | 29/01/2024 | 0 | Resource Division | 11.08 | 0 | 0
1205 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ganeshpur Kalinagar Zone - I PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000046/2023-2024 | 31/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
1206 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ganeshpur Kalinagar Zone - II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000047/2023-2024 | 32/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
1207 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter for Augmentation of Ganeshpur Kalinagar (Zone-I and II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000119/2024-2025 | 2396AD | 07/06/2024 | 45 | FORTUNE ENGINEERING | 39.72 | 0 | 0
1208 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia and others for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000129/2021-2022 | 384/KSD | 07/07/2021 | 15 | KHOKAN MONDAL | 4.39 | 0 | 100
1209 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000132/2021-2022 | 387/KSD | 07/07/2021 | 15 | M/S. MANIMALA ENTERPRISE | 4.78 | 0 | 100
1210 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000137/2021-2022 | 392/KSD | 07/07/2021 | 15 | UNIQUE CONSTRUCTION (II) | 4.39 | 0 | 100
1211 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia and others for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000138/2021-2022 | 393/KSD | 07/07/2021 | 15 | KHOKAN MONDAL | 4.39 | 0 | 100
1212 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000150/2021-2022 | 402/KSD | 07/07/2021 | 15 | M/S. MANIMALA ENTERPRISE | 4.78 | 0 | 100
1213 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000152/2021-2022 | 404/KSD | 07/07/2021 | 15 | M/S. MANIMALA ENTERPRISE | 4.77 | 0 | 100
1214 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Rathtala, Bangheri and others (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000153/2021-2022 | 406/KSD | 07/07/2021 | 15 | TAPAN DAS | 4.77 | 0 | 95
1215 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000164/2024-2025 | 2515/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
1216 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. At Head Work Site for Augmentation of Ganeshpur Kalinagar Zone-I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000202/2024-2025 | 2585/AD | 19/06/2024 | 227 | SOHINI ENTERPRISE | 5.6 | 0 | 0
1217 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000203/2024-2025 | 2586/AD | 19/06/2024 | 45 | GARGO TRADERS | 46.46 | 0 | 0
1218 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Ganeshpur Kalinagar Zone-II W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000233/2023-2024 | 162/KSD | 01/06/2023 | 20 | S.K.GOLUI | 2.74 | 0 | 95
1219 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Ganeshpur Kalinagar (Zone-I), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000271/2023-2024 | 1421/AD | 13/07/2023 | 45 | ASHIT BARAN BOSE | 61.55 | 0 | 100
1220 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Ganeshpur Kalinagar (Zone-II), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000272/2023-2024 | 1422/AD | 13/07/2023 | 45 | GARGO TRADERS | 65.44 | 0 | 100
1221 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Ganeshpur Kalinagar Zone- I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (SM/10336) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000335/2024-2025 | 2750/AD | 27/06/2024 | 60 | SUDIP PRADHAN | 111.95 | 0 | 0
1222 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000382/2023-2024 | 1775/AD | 26/07/2023 | 45 | SWASTIK CONSTRUCTION | 14.02 | 0 | 100
1223 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000420/2022-2023 | 4346/AD | 25/08/2022 | 60 | G.M. ENTERPRISE | 41.23 | 0 | 20
1224 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000424/2022-2023 | 4347/AD | 25/08/2022 | 30 | ASHIS ENTERPRISE | 16.81 | 0 | 90
1225 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000433/2022-2023 | 4348/AD | 25/08/2022 | 30 | UNIQUE CONSTRUCTION (II) | 16.37 | 0 | 75
1226 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( GANESHPUR KALINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000490/2022-2023 | 303/AD | 12/04/2022 | 45 | LEMNISCATE | 12.79 | 0 | 100
1227 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000554/2022-2023 | 5728/AD | 13/10/2022 | 880 | GARGO TRADERS | 320.99 | 0 | 40
1228 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Ganeshpur Kalinagar Zone-I W/S Scheme under JJM under Kakdwip Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000635/2023-2024 | 2463/AD | 24/08/2023 | 45 | M/S. BRINDABAN DAS & SONS | 8.5 | 0 | 0
1229 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000669/2022-2023 | 6154/AD. | 01/11/2022 | 90 | S.S. ENTERPRISE (I) | 134.59 | 0 | 80
1230 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Kalinagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000670/2022-2023 | 6155/AD. | 01/11/2022 | 1105 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 168.21 | 0 | 50
1231 | Alipore Division | Kakdwip Sub-Division | Road Restoration for Laying distribution system of Augmentation of Ganeshpur Kalinagar Water Supply Scheme for providing FHTC, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000986/2023-2024 | 3005/AD | 26/09/2023 | 906 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 76.51 | 0 | 100
1232 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-I) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001018/2021-2022 | 536/KSD | 01/09/2021 | 20 | LEMNISCATE | 2.82 | 0 | 100
1233 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001023/2021-2022 | 537/KSD | 01/11/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.6 | 0 | 100
1234 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur Kalinagar (Zone-I) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001040/2021-2022 | 2271/AD | 06/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 2.58 | 0 | 0
1235 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001041/2021-2022 | 2272/AD | 06/09/2021 | 7 | LEMNISCATE | 4.45 | 0 | 0
1236 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Kalinagar (Zone-II) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001616/2021-2022 | 615/KSD | 27/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 2.62 | 0 | 100
1237 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gangasagar Zone - I & Gangasagar Zone - II W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001617/2021-2022 | 616/KSD | 27/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 1.27 | 0 | 100
1238 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001733/2021-2022 | 1006/KSD | 21/02/2022 | 365 | SARADA CONSTRUCTION | 1.46 | 0 | 80
1239 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001782/2020-2021 | 1227/KSD | 23/02/2021 | 10 | M/S. MANIMALA ENTERPRISE | 4.26 | 0 | 100
1240 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001854/2020-2021 | 1285/KSD | 23/02/2021 | 10 | M/S. MANIMALA ENTERPRISE | 4.38 | 0 | 100
1241 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001891/2020-2021 | 1313/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.7 | 0 | 100
1242 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-VI) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001893/2020-2021 | 1315/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 2.91 | 0 | 100
1243 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001896/2020-2021 | 1318/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.74 | 0 | 100
1244 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-IV) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001905/2020-2021 | 1321/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.3 | 0 | 100
1245 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-V) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001914/2020-2021 | 1324/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.61 | 0 | 100
1246 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001916/2020-2021 | 1326/KSD | 23/02/2021 | 10 | FIDERE MARINE SERVICES PVT. LTD. | 4.74 | 0 | 100
1247 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
1248 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002187/2022-2023 | 689/KSD | 23/02/2023 | 365 | SARADA CONSTRUCTION | 1.54 | 0 | 100
1249 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2024 to 31.05.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002536/2023-2024 | 408/KSD | 27/02/2024 | 92 | ANAMIKA BERA | 1.2 | 0 | 0
1250 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000055/2022-2023 | 3905/AD | 12/08/2022 | 0 | Resource Division | 147.3 | 0 | 0
1251 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000090/2022-2023 | 5594/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
1252 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR001001/2023-2024 | 1800/AD | 27/03/2024 | 0 | Resource Division | 18.82 | 0 | 0
1253 | Alipore Division | Baruipur Sub-Division | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01707/2024-2025 | BP-2024-25-792 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0
1254 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kumarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000069/2023-2024 | 50/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1255 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kumarpur, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000283/2023-2024 | 1708/AD | 22/07/2023 | 45 | S & P ENTERPRISE | 34.38 | 0 | 100
1256 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000301/2022-2023 | 3837/AD | 08/08/2022 | 1271 | M/S CHANDIMATA CONSTRUCTION | 60.21 | 0 | 40
1257 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000302/2022-2023 | 3838/AD | 08/08/2022 | 1241 | M/S CHANDIMATA CONSTRUCTION | 12.99 | 0 | 0
1258 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000303/2022-2023 | 3839/AD | 08/08/2022 | 1211 | M/S CHANDIMATA CONSTRUCTION | 7.93 | 0 | 0
1259 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KUMARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000462/2022-2023 | 1707/AD | 14/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.46 | 0 | 100
1260 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Kumarpur Water Supply Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11746) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000469/2024-2025 | 3464/AD | 23/08/2024 | 45 | PRONICON INDIA | 55.66 | 0 | 0
1261 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kumarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000975/2023-2024 | 2994/AD | 06/10/2023 | 45 | M/S KRISHNA MONDAL | 27.73 | 0 | 70
1262 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Kumarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000976/2023-2024 | 2995/AD | 06/10/2023 | 30 | M/S S.DAS ENTERPRISE | 9.65 | 0 | 0
1263 | Alipore Division | Kakdwip Sub-Division | Continuation Work Order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site for Kumarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001150/2024-2025 | 4506/AD | 11/11/2024 | 60 | MEHAI TECHNOLOGY LIMITED | 19.96 | 0 | 100
1264 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Kumarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001315/2022-2023 | 9880/AD | 10/01/2023 | 870 | S & P ENTERPRISE | 427.97 | 0 | 50
1265 | Alipore Division | Kakdwip Sub-Division | Hiring of 01 No. Diesel Car / Luxury Taxi for supervision of different works at Gangasagar Point in connection with Gangasagar Mela 2022 under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2021 to 31.03.2022. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001348/2021-2022 | 661/KSD | 23/11/2021 | 120 | SUDIP PRADHAN | 1.6 | 0 | 100
1266 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2022 to 31.07.2022. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001678/2021-2022 | 934/KSD | 31/01/2022 | 181 | BADSHA ALOM | 2.39 | 0 | 100
1267 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1268 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000067/2022-2023 | 3955/AD | 12/08/2022 | 0 | Resource Division | 13.09 | 0 | 0
1269 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000305/2023-2024 | 3100/AD | 28/09/2023 | 0 | Resource Division | 16.22 | 0 | 0
1270 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000583/2023-2024 | 57/AD | 03/01/2024 | 0 | Resource Division | 8.75 | 0 | 0
1271 | Alipore Division | Baruipur Sub-Division | 1) L027-Sagarsangha Math on T03 to Dudhnai(WB/02/480) 2) Construction of Road from Fultala Chow More to Block-A, B.C,D to Ramkrisna Polly to Mohamonilala Greater Kolkata Enginnering College to Ramnagar Bazar via Dhapdhopi road Shakharipukur under Baruipur Block. | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01677/2024-2025 | BP-2024-25-782 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.88 | 0 | 0
1272 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000870/2023-2024 | 777/AD | 03/02/2024 | 0 | Resource Division | 0.55 | 0 | 0
1273 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Digambarpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13764) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000191/2024-2025 | 2550/AD | 18/06/2024 | 75 | MS FIROJA ENTERPRISE | 71.1 | 0 | 0
1274 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Digambarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000378/2023-2024 | 1771/AD | 26/07/2023 | 60 | SWASTIK ENTERPRISE (NEW) | 9.06 | 0 | 60
1275 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Digambarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000961/2023-2024 | 284(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1276 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DIGAMBERPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000977/2022-2023 | 3662/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.72 | 0 | 100
1277 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Digambarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000980/2023-2024 | 2999/AD | 26/09/2023 | 45 | PRADIP KUMAR MONDAL | 27.46 | 0 | 0
1278 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Digambarpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000981/2023-2024 | 3000/AD | 06/11/2023 | 30 | M/S MAA KALI ENTERPRISE | 9 | 0 | 0
1279 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Digambarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13764) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001045/2024-2025 | 4966/AD | 04/12/2024 | 91 | AQUATECH ENGINEERS | 40.73 | 0 | 50
1280 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Digambarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001495/2022-2023 | 10988/AD | 07/02/2023 | 300 | MUNNA AGROTECH ENTERPRISE | 297.15 | 0 | 30
1281 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Digambarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 700 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002062/2022-2023 | 13004/AD | 23/03/2023 | 90 | S.P. CONSTRUCTION (I) | 100.07 | 0 | 86
1282 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
1283 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000092/2023-2024 | 538/AD | 12/05/2023 | 0 | Resource Division | 11.15 | 0 | 0
1284 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000517/2023-2024 | 4941/AD | 22/12/2023 | 0 | Resource Division | 28.75 | 0 | 0
1285 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000950/2023-2024 | 1684/AD | 22/03/2024 | 0 | Resource Division | 1.85 | 0 | 0
1286 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Ramganga Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000017/2022-2023 | 3836/AD | 08/08/2022 | 30 | ABONTICA ENTERPRISE | 5.15 | 0 | 100
1287 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Ramganga Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000026/2022-2023 | 2926/AD | 07/07/2022 | 30 | AQUATECH ENGINEER | 18.32 | 0 | 98
1288 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 3nos Pump House site of Ramganga Water Supply Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11281) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000132/2025-2026 | 2630/AD | 05/06/2025 | 45 | AZAD RAHAMAN LASKAR | 5.99 | 0 | 0
1289 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Ramganga PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11281) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000186/2024-2025 | 2546/AD | 18/06/2024 | 244 | M/S. S.S. ENTERPRISE | 87.68 | 0 | 80
1290 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Ramganga PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000461/2022-2023 | 295/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.33 | 0 | 100
1291 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ramganga Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000505/2022-2023 | 5091/AD | 20/09/2022 | 902 | M/S. S.S. ENTERPRISE | 494.53 | 0 | 55
1292 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramganga Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/000858/2022-2023 | 6941/AD | 18/11/2022 | 120 | RAMEN GHOSH | 219.32 | 0 | 60
1293 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ramganga W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001077/2021-2022 | 547/KSD | 03/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.6 | 0 | 100
1294 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramganga W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001202/2023-2024 | 4079/AD | 23/11/2023 | 486 | G.M. ENTERPRISE | 9.55 | 0 | 90
1295 | Alipore Division | Kakdwip Sub-Division | Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.01.2024 to 09.04.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/001870/2023-2024 | 199/AD | 09/01/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
1296 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
1297 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Motor Launch for Kakdwip Sub-Division under Alipore Division, P.H.E.D. for execution and maintenance of different piped water supply schemes at different Island in the district of South 24 Parganas. (Period from 10.04.2024 to 09.07.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | ORD/002155/2024-2025 | 1966/AD | 05/04/2024 | 91 | RAJKUMAR MANNA | 8.97 | 0 | 0
1298 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000047/2022-2023 | 3910/AD | 12/08/2022 | 0 | Resource Division | 36.27 | 0 | 0
1299 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000309/2023-2024 | 3118/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1300 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000771/2023-2024 | 605/AD | 29/01/2024 | 0 | Resource Division | 21.26 | 0 | 0
1301 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_blk_pathar, Kakdwip Sub Division | RTOR000941/2023-2024 | 1675/AD | 22/03/2024 | 0 | Resource Division | 19.24 | 0 | 0
1302 | Alipore Division | Diamond Harbour Sub-Division | Repairing and Renovation of existing 100 Cum. capacity Over Head Reservoir of Zone-IV, Diamond Harbour -II Block (At Sarisha Ramkrishna Mission) Water Supply Scheme under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000131/2023-2024 | 490/AD | 10/05/2023 | 60 | NIVA CONSTRUCTION | 20.82 | 0 | 100
1303 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
1304 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000142/2022-2023 | 15/AD | 05/04/2023 | 0 | Resource Division | 15.11 | 0 | 0
1305 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000182/2023-2024 | 1273/AD | 05/07/2023 | 0 | Resource Division | 15.11 | 0 | 0
1306 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000353/2023-2024 | 3217/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
1307 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution system at Zone-V of Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000003/2021-2022 | 341/AD | 12/05/2021 | 180 | M/S. S.S. ENTERPRISE | 189.98 | 0 | 0
1308 | Alipore Division | Diamond Harbour Sub-Division | Interconnection of tubewell, and erection of RBT fencing at Pump House No.-2 of Khandalia W/S Scheme, Block: Diamond Harbour-II under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000822/2022-2023 | 206/DHSD | 02/08/2022 | 45 | S.S. ENTERPRISE (II) | 2.66 | 0 | 100
1309 | Alipore Division | Diamond Harbour Sub-Division | Construction of Boundary wall,approach road and renovation of Pump House as per departmental design and drawing at Pump House No. 2 of Khandalia W/S Scheme under Diamond Harbour Sub-Division of Alipore Division, P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001520/2020-2021 | 336/DHSD | 06/01/2021 | 30 | M/S. SUMAN ENTERPRISE | 4.81 | 0 | 100
1310 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000355/2023-2024 | 3219/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
1311 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Dakshin Madhusudanpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13977) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000447/2024-2025 | 3324/AD | 12/08/2024 | 60 | MONDAL CONSTRUCTION NEW | 102.17 | 0 | 0
1312 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Madhusudanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000965/2023-2024 | 288(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1313 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Madhusudanpur W/S scheme, Block- Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001057/2023-2024 | 3376/AD | 11/10/2023 | 45 | M/S ANNAPURNA ENTERPRISE | 27.54 | 0 | 0
1314 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Madhusudanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001058/2023-2024 | 3377/AD | 11/10/2023 | 30 | M/S BABUSONA ENTERPRISE | 9.48 | 0 | 0
1315 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN MADHUSUDANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001328/2022-2023 | 3312/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.9 | 0 | 100
1316 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Madhusudanpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001721/2022-2023 | 11747/AD | 21/02/2023 | 45 | MODERN CONSTRUCTION (NEW) | 38.58 | 0 | 80
1317 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Madhusudanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC=1664] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001757/2022-2023 | 11556/AD | 17/02/2023 | 1257 | MONDAL CONSTRUCTION NEW | 299.31 | 0 | 35
1318 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1319 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000105/2023-2024 | 641/AD | 17/05/2023 | 0 | Resource Division | 9.14 | 0 | 0
1320 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000502/2023-2024 | 4959/AD | 22/12/2023 | 0 | Resource Division | 17.94 | 0 | 0
1321 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000759/2023-2024 | 594/AD | 29/01/2024 | 0 | Resource Division | 1.64 | 0 | 0
1322 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000953/2023-2024 | 1687/AD | 22/03/2024 | 0 | Resource Division | 9.35 | 0 | 0
1323 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000253/2023-2024 | 1396/AD | 12/07/2023 | 570 | RAKTIM ENTERPRISE | 8.88 | 0 | 100
1324 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000254/2023-2024 | 1397/AD | 12/07/2023 | 539 | RAKTIM ENTERPRISE | 8.57 | 0 | 100
1325 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Kamarpara piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1443] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000293/2023-2024 | 1503/AD | 15/07/2023 | 1005 | PROJECT INDIA | 354.06 | 0 | 85
1326 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kamarpara W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000386/2023-2024 | 1575/AD | 17/07/2023 | 55 | GIASHUDDIN CONSTRUCTION | 43.94 | 0 | 100
1327 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Sitef or Ground water Based at Kamarpara Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000388/2025-2026 | 3373/AD | 16/07/2025 | 45 | SWASTIK CONSTRUCTION | 32.27 | 0 | 0
1328 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kamarpara W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000732/2023-2024 | 2893/AD | 19/09/2023 | 15 | M/S. MIHIR KUMAR NASKAR | 13.26 | 0 | 0
1329 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No-2 at Kamarpara Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000735/2024-2025 | 4393/AD | 05/11/2024 | 30 | SUKUMAR HALDAR | 14.97 | 0 | 0
1330 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kamarpara New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001886/2022-2023 | 7599/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 4.49 | 0 | 95
1331 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000044/2023-2024 | 251/AD | 24/04/2023 | 0 | Resource Division | 50.79 | 0 | 0
1332 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000165/2023-2024 | 1047/AD | 15/06/2023 | 0 | Resource Division | 8.89 | 0 | 0
1333 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Rakhalpur W/S scheme, Block - Patharpratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000155/2023-2024 | 677/AD | 17/05/2023 | 30 | JOY ENGINEERING & CONSTRUCTION | 11.79 | 0 | 0
1334 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Rakhalpur W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000156/2023-2024 | 678/AD | 17/05/2023 | 1005 | M/S G.M. ASSOCIATES | 34.25 | 0 | 81
1335 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Rakhalpur (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14987) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000343/2024-2025 | 2755/AD | 27/06/2024 | 75 | BIMALENDU GIRI | 167.27 | 0 | 0
1336 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rakhalpur (Zone-I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000967/2023-2024 | 305/KSD | 20/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1337 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Rakhalpur (Zone-I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000968/2023-2024 | 306/KSD | 20/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1338 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Rakhalpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001794/2022-2023 | 3959/AD | 12/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.06 | 0 | 95
1339 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Rakhalpur W/S Scheme, Block - Pathar PRatima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone- I and II) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001961/2023-2024 | 396/AD | 22/01/2024 | 45 | AQUATECH ENGINEERS | 49.26 | 0 | 50
1340 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Rakhalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002058/2022-2023 | 13000/AD | 23/03/2023 | 740 | GROWING CONCERN | 253.61 | 0 | 5
1341 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Rakhalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002059/2022-2023 | 13001/AD | 23/03/2023 | 740 | GROWING CONCERN | 251.42 | 0 | 5
1342 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sridharnagar Zone - I & II, Rakhalpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002106/2023-2024 | 928/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1343 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000318/2023-2024 | 3127/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1344 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000442/2023-2024 | 4767/AD | 19/12/2023 | 0 | Resource Division | 40.95 | 0 | 0
1345 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000563/2023-2024 | 84/AD | 03/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
1346 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000763/2023-2024 | 597/AD | 29/01/2024 | 0 | Resource Division | 3.79 | 0 | 0
1347 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000964/2023-2024 | 1698/AD | 22/03/2024 | 0 | Resource Division | 11.49 | 0 | 0
1348 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (INDRAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001038/2022-2023 | 3672/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.37 | 0 | 100
1349 | Alipore Division | Kakdwip Sub-Division | Sinking of 03 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st, 2nd and 3rd Tubewell Site of Indrapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001270/2022-2023 | 9582/AD | 03/01/2023 | 60 | M/S. BOSE CONCERN | 73.43 | 0 | 100
1350 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002041/2023-2024 | 523/AD | 25/01/2024 | 374 | SK SAKIL AHAMED | 33.48 | 0 | 100
1351 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002042/2023-2024 | 524/AD | 25/01/2024 | 30 | M/S. ASIRUDDIN SEKH ENTERPRISE | 11.8 | 0 | 0
1352 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Indrapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002043/2023-2024 | 525/AD | 25/01/2024 | 30 | SIMRAN ENTERPRISE | 11.82 | 0 | 100
1353 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 200 cum. capacity OHR of Indrapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002064/2023-2024 | 758/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1354 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1355 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000102/2023-2024 | 548/AD | 12/05/2023 | 0 | Resource Division | 10.34 | 0 | 0
1356 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000298/2023-2024 | 3093/AD | 28/09/2023 | 0 | Resource Division | 24.37 | 0 | 0
1357 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000744/2023-2024 | 579/AD | 29/01/2024 | 0 | Resource Division | 1.85 | 0 | 0
1358 | Alipore Division | Canning Sub-division | Earth working embankment at Head work site of Srinagar Water Supply Scheme, Block-canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000003/2022-2023 | 120/AD | 07/04/2022 | 7 | SWASTIK CONSTRUCTION | 8.31 | 0 | 97
1359 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. Store Room (multipurpose) (4.88m x 3.66m) at head work site of Srinagar Water Supply Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000062/2022-2023 | 843/AD | 13/05/2022 | 30 | BHUNIA BUILDERS | 5.95 | 0 | 80
1360 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000085/2020-2021 | 5308/AD | 18/02/2021 | 365 | NATURAL RESOURCES CONSORTIUM | 89.65 | 0 | 77
1361 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Banamalipur Khanpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000089/2022-2023 | 293/CSD | 20/05/2022 | 40 | NATURAL RESOURCES CONSORTIUM | 4.83 | 0 | 87
1362 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Srinagar Water Supply Scheme (Habitation- Mollapara, Sekhpara & Majherpara), Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000112/2022-2023 | 295/CSD | 20/05/2022 | 40 | RAJLAKSHMI ENTERPRISE | 4.81 | 0 | 77
1363 | Alipore Division | Canning Sub-division | Laying of DI pipe to connect OHR with rising main and distribution system at Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000994/2021-2022 | 989/CSD | 26/10/2021 | 30 | K.P. CONSTRUCTION | 4.21 | 0 | 90
1364 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Srinagar W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001671/2022-2023 | 11482/AD | 15/02/2023 | 30 | TRIMURTI ENTERPRISE | 19.58 | 0 | 98
1365 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Srinagar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001690/2022-2023 | 11261/AD | 18/02/2023 | 581 | RAHUL ENTERPRISE | 7.05 | 0 | 99
1366 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Srinagar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001999/2022-2023 | 12813/AD | 16/03/2023 | 60 | SAHANA ENTERPRISE | 52.81 | 0 | 99
1367 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000016/2023-2024 | 221/AD | 21/04/2023 | 0 | Resource Division | 64.05 | 0 | 0
1368 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000501/2024-2025 | 3604/AD | 06/09/2024 | 360 | SARADA CONSTRUCTION | 80.76 | 0 | 55
1369 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Amarabati W/S Scheme, Namkhana Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000588/2023-2024 | 2345/AD | 18/08/2023 | 45 | SARADA CONSTRUCTION | 42.65 | 0 | 98
1370 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000938/2023-2024 | 278(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1371 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Amrabati PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001784/2022-2023 | 3693/AD | 02/08/2022 | 45 | M/S R.DUTTA & CO. | 9.01 | 0 | 95
1372 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 100] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002075/2022-2023 | 12945/AD | 21/03/2023 | 300 | SARADA CONSTRUCTION | 169.37 | 0 | 28
1373 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002076/2022-2023 | 12946/AD | 21/03/2023 | 90 | SARADA CONSTRUCTION | 151.76 | 0 | 77
1374 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Amarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002077/2022-2023 | 12947/AD | 21/03/2023 | 90 | SARADA CONSTRUCTION | 169.36 | 0 | 24
1375 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 1st Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002125/2024-2025 | 1972/KSD | 23/12/2024 | 20 | IMAGINEER VENTURES | 1.88 | 0 | 0
1376 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002126/2024-2025 | 1973/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.87 | 0 | 0
1377 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
1378 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 3rd Tube well site of Amarabati W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14156) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002133/2024-2025 | 1974/KSD | 23/12/2024 | 20 | FORTUNE ENGINEERING | 1.33 | 0 | 0
1379 | Alipore Division | Kakdwip Sub-Division | Road restoration and other allied works for laying pipe line to providing Functional Household Tap Connection (FHTC) to all households for Aamarabati Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002565/2023-2024 | 510/KSD | 15/03/2024 | 5 | SARADA CONSTRUCTION | 3.63 | 0 | 90
1380 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000484/2023-2024 | 4786/AD | 19/12/2023 | 0 | Resource Division | 64.94 | 0 | 0
1381 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000554/2023-2024 | 42/AD | 03/01/2024 | 0 | Resource Division | 16.45 | 0 | 0
1382 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000983/2023-2024 | 1776/AD | 27/03/2024 | 0 | Resource Division | 4.9 | 0 | 0
1383 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- XI of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000025/2023-2024 | 105/AD | 13/04/2023 | 913 | SUJATA CONSTRUCTION | 319.09 | 0 | 85
1384 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000877/2024-2025 | 4661/AD | 20/11/2024 | 45 | L.N. ENTERPRISE | 17.1 | 0 | 0
1385 | Alipore Division | Raidighi Sub-Division | Extension of Pipeline at Gabbati of under Ghoradal Water supply Scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001034/2021-2022 | 538/RSD | 30/11/2021 | 60 | UNITED BUILDERS | 4.65 | 0 | 100
1386 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000606/2023-2024 | 236/AD | 11/01/2024 | 0 | Resource Division | 6.75 | 0 | 0
1387 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
1388 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- XVII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000132/2023-2024 | 674/AD | 17/05/2023 | 813 | BALAJI UDDYOG | 553.99 | 0 | 60
1389 | Alipore Division | Raidighi Sub-Division | Laying distribution system and other allied works for piped water supply at Zone - XVII of Mathurapur- I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09396 and SM/15467) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000533/2024-2025 | 3639/AD | 09/09/2024 | 315 | BALAJI UDDYOG | 37 | 0 | 10
1390 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XVII of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000883/2024-2025 | 4665/AD | 20/11/2024 | 60 | SUPRITI ENTERPRISE | 45.45 | 0 | 0
1391 | Alipore Division | Raidighi Sub-Division | Construction of 1 no. Pump House of size 4.80 Mtr. X 3.66 Mtr. (as per Dept. drawing) at Zone - XVII Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000884/2024-2025 | 4666/AD | 20/11/2024 | 45 | S.S. CONSTRUCTION (NAMKHANA) | 13.11 | 0 | 0
1392 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Raghudevpur W/S Scheme (Zone-XVII, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001256/2023-2024 | 4181/AD | 28/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.84 | 0 | 99
1393 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000601/2023-2024 | 229/AD | 11/01/2024 | 0 | Resource Division | 5.78 | 0 | 0
1394 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zones ( Zone-II, V, XIII), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000109/2025-2026 | 2575/AD | 03/06/2025 | 60 | SOURAV DEBNATH | 15.09 | 0 | 0
1395 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- II of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000120/2023-2024 | 591/AD | 15/05/2023 | 90 | DIPTI ENTERPRISE | 140.01 | 0 | 40
1396 | Alipore Division | Raidighi Sub-Division | Filling in foundation of Overhead Reservoir (Mathurapur - I, Zone -II ) by silver sand filling for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur, South 24 Paraganas under Raidighi Sub - Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000241/2022-2023 | 74/RSD | 18/05/2022 | 60 | G.B. CONSTRUCTION & CO. | 2.79 | 0 | 0
1397 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Debipur piped water supply scheme ( Mathurapur-I, Zone-II) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001197/2021-2022 | 5724/AD | 31/01/2022 | 365 | M/S. JHARNA ENTERPRISE | 101.84 | 0 | 85
1398 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-II of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001339/2021-2022 | 6033/AD | 16/02/2022 | 90 | DIPTI ENTERPRISE | 123.9 | 0 | 95
1399 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - II of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001963/2022-2023 | 12717/AD | 14/03/2023 | 30 | MONCON INDIA | 10.98 | 0 | 95
1400 | Alipore Division | Raidighi Sub-Division | Construction of 500 cum capacity 20 M. staging height RCC Over Head Water Reservoir as per departmental drawing & specification incl. RCC Bored Pile & Pile Cap upto pedestal at Mathurapur - I Block (Zn. - II) for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur South 24 Pgs. under Raidighi Sub Divn. of Alipore Division, PHE dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002025/2019-2020 | 7721/AD | 26/02/2020 | 1827 | G.B. CONSTRUCTION & CO. | 64.12 | 0 | 75
1401 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000632/2023-2024 | 268/AD | 15/01/2024 | 0 | Resource Division | 6.71 | 0 | 0
1402 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall (length - 40 m.) and concrete block pavement at proposed OHR site and Land development at Mouza-Kamarpole under Zone- VII of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000072/2025-2026 | 2261/AD | 14/05/2025 | 30 | M/S B ENTERPRISE | 9.12 | 0 | 0
1403 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VII at Diamond Harbour- II block for providing House Hold Tap connection, under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001998/2024-2025 | 317/AD | 27/01/2025 | 30 | YAMUNA CONSTRUCTION | 12.73 | 0 | 0
1404 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VII at Diamond Harbour- II block for providing balance pipe lying works, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002246/2024-2025 | 544/AD | 12/02/2025 | 60 | S.M. ENTERPRISE | 56.88 | 0 | 0
1405 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000612/2023-2024 | 274/AD | 15/01/2024 | 0 | Resource Division | 5.85 | 0 | 0
1406 | Alipore Division | Baruipur Sub-Division | Road restoration of WB024 17, L053 Gudamer Hat to Singher Dari Hugh School | AE BSD,Assistant Engineer | Junior Engineer | BILL/01781/2024-2025 | BP-2024-25-806 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 9.76 | 0 | 0
1407 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 1 no. deep Tube well (300mm x 200mm dia. & 360 mtr. deep) with allied works under Zone-VII (Sarisha Ramkrishna Mission water supply scheme ) of Diamond Harbour-II Block of Diamond Harbour Sub-Division under Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000213/2023-2024 | 953/AD | 06/06/2023 | 45 | CIVIL CRAFT | 28.55 | 0 | 70
1408 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-VII at Kamarpole of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-950] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000305/2023-2024 | 1508/AD | 15/07/2023 | 1197 | JYOTY SOLAR POWER | 423.33 | 0 | 15
1409 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000141/2022-2023 | 16/AD | 05/04/2023 | 0 | Resource Division | 32.1 | 0 | 0
1410 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000183/2023-2024 | 1274/AD | 05/07/2023 | 0 | Resource Division | 32.1 | 0 | 0
1411 | Alipore Division | Canning Sub-division | Laying distribution system of Nagartala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000117/2022-2023 | 1662/AD | 10/06/2022 | 120 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 369.02 | 0 | 20
1412 | Alipore Division | Canning Sub-division | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New & Replacement) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Nagartala (Zone - I &II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001661/2022-2023 | 11474/AD | 15/02/2023 | 90 | MERAJUL ALAM | 78.41 | 0 | 35
1413 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001676/2022-2023 | 11485/AD | 15/02/2023 | 45 | SAHANA ENTERPRISE | 7.07 | 0 | 100
1414 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001677/2022-2023 | 11486/AD | 15/02/2023 | 45 | SAHANA ENTERPRISE | 7.06 | 0 | 100
1415 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001679/2022-2023 | 11488/AD | 15/02/2023 | 777 | PAL AGENCY | 7.1 | 0 | 98
1416 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000007/2023-2024 | 115/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
1417 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000135/2023-2024 | 842/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
1418 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000255/2023-2024 | 3047/AD | 28/09/2023 | 0 | Resource Division | 232.42 | 0 | 0
1419 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(B) at Kulpi block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-5259]. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000012/2023-2024 | 03/AD | 04/04/2023 | 1080 | S.MISRA INFRADEV PVT. LTD. | 1217.22 | 0 | 60
1420 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from Distribution System under Zone - VIIIB & Zone-X at Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - X/B) [No. of FHTC = 9578] | Assistant Engineer, Diamond Harbour sub division |  | ORD/000342/2023-2024 | 1560/AD | 17/07/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 512.43 | 0 | 0
1421 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII(B) of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001021/2022-2023 | 294/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.59 | 0 | 100
1422 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline under the Augmentation Scheme of Zone-VIIIB at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/15320] | Assistant Engineer, Diamond Harbour sub division |  | ORD/001048/2024-2025 | 4992/AD | 05/12/2024 | 420 | SHYAM DEVELOPER | 113.34 | 0 | 0
1423 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at porposed OHR site at Mouza - Laxmipur under Zone- VIIIB of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001370/2024-2025 | 5499/AD | 27/12/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 22.15 | 0 | 0
1424 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VIII(B) (Lakshmipur, OHR Size-600 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/002100/2022-2023 | 339/DHSD | 17/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
1425 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone No-VIIIB of Kulpi Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/002150/2024-2025 | 409/AD | 31/01/2025 | 30 | S.MISRA INFRADEV PVT. LTD. | 21.56 | 0 | 0
1426 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000146/2022-2023 | 11/AD | 05/04/2023 | 0 | Resource Division | 38.18 | 0 | 0
1427 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000196/2023-2024 | 1629/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
1428 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000211/2023-2024 | 2020/AD | 05/08/2023 | 0 | Resource Division | 12.51 | 0 | 0
1429 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000623/2023-2024 | 284/AD | 15/01/2024 | 0 | Resource Division | 24.64 | 0 | 0
1430 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000856/2023-2024 | 763/AD | 03/02/2024 | 0 | Resource Division | 7.76 | 0 | 0
1431 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000939/2023-2024 | 1281/AD | 02/03/2024 | 0 | Resource Division | 1.24 | 0 | 0
1432 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
1433 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- IX of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000123/2023-2024 | 602/AD | 15/05/2023 | 90 | M/S B.M. CONSTRUCTION | 111.14 | 0 | 80
1434 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Uttar Laxminarayanpur W/S Scheme (Zone-IX, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000433/2023-2024 | 1921/AD | 01/08/2023 | 30 | ALISHA ENTERPRISE | 19.83 | 0 | 100
1435 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- IX of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000657/2024-2025 | 4203/AD | 23/10/2024 | 60 | TANMAY ROY CHOWDHURY | 34.45 | 0 | 0
1436 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Uttar Laxminarayanpur W/S Scheme, modified as Zone- IX of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001302/2024-2025 | 5376/AD | 23/12/2024 | 30 | M/S IDEAL WORKS | 4.76 | 0 | 90
1437 | Alipore Division | Raidighi Sub-Division | Construction of approach road for Over Head Reservoir site at Zone IX of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/003645/2024-2025 | 1016/RSD | 24/01/2025 | 60 | R. ENTERPRISE (II) | 4.3 | 0 | 100
1438 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000603/2023-2024 | 232/AD | 11/01/2024 | 0 | Resource Division | 4.38 | 0 | 0
1439 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-V of Uttar Angadberia W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000243/2023-2024 | 1395/AD | 12/07/2023 | 45 | S.P. CONSTRUCTION (I) | 89.25 | 0 | 0
1440 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (200 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Uttar Angadberia Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001030/2023-2024 | 3314/AD | 07/10/2023 | 45 | SWASTIK ENTERPRISE | 36.08 | 0 | 65
1441 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Uttar Angadberia W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001817/2022-2023 | 12157/AD | 01/03/2023 | 45 | THE TOWER CONSTRUCTION | 7.09 | 0 | 0
1442 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Uttar Angadberia Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001948/2022-2023 | 11507/AD | 15/02/2023 | 45 | M/S. MIHIR KUMAR NASKAR | 1.52 | 0 | 95
1443 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000070/2023-2024 | 3040/AD | 28/09/2023 | 0 | Resource Division | 57.93 | 0 | 0
1444 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000728/2023-2024 | 551/AD | 25/01/2024 | 0 | Resource Division | 59.7 | 0 | 0
1445 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000704/2023-2024 | 474/AD | 24/01/2024 | 0 | Resource Division | 5.48 | 0 | 0
1446 | Alipore Division | Canning Sub-division | Construction of 100 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Harishpur (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 921] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000038/2023-2024 | 173/AD | 19/04/2023 | 804 | SARDAR ENTERPRISE | 354.02 | 0 | 56
1447 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 2 of Augmentation of Harishpur W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000187/2025-2026 | 555/CSD | 02/05/2025 | 30 | SANGJOG | 3.1 | 0 | 0
1448 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work for Augmentation of Harishpur (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000732/2024-2025 | 4390/AD | 05/11/2024 | 45 | SARDAR ENTERPRISE | 33.94 | 0 | 0
1449 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Harishpur (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001853/2022-2023 | 11819/AD | 23/02/2023 | 45 | TECH VISION | 3.68 | 0 | 0
1450 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Harishpur (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002017/2022-2023 | 12923/AD | 21/03/2023 | 560 | M/S. TRIPATHI & CO. | 31.2 | 0 | 95
1451 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 1 of Augmentation of Harishpur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002507/2023-2024 | 1602/CSD | 28/02/2024 | 30 | NASKAR ENTERPRISE | 3.59 | 0 | 100
1452 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 3 of Augmentation of Harishpur W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002508/2023-2024 | 1603/CSD | 28/02/2024 | 30 | KIRON CONSTRUCTION | 2.63 | 0 | 100
1453 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000057/2023-2024 | 264/AD | 24/04/2023 | 0 | Resource Division | 45.85 | 0 | 0
1454 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000419/2023-2024 | 374/AD | 19/01/2024 | 0 | Resource Division | 5.67 | 0 | 0
1455 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-II) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1076] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000039/2023-2024 | 1289/AD | 06/07/2023 | 665 | PATHIK PABAN NANDI | 429.73 | 0 | 56
1456 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000235/2023-2024 | 1388/AD | 12/07/2023 | 386 | S.S.COMSULTANCY & CONSTRUCTION | 21.99 | 0 | 90
1457 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001849/2022-2023 | 11815/AD | 23/02/2023 | 45 | TECH VISION | 3.89 | 0 | 0
1458 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001979/2022-2023 | 12640/AD | 13/03/2023 | 45 | R.G. ENTERPRISE (I) | 8.59 | 0 | 100
1459 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002009/2022-2023 | 12915/AD | 21/03/2023 | 45 | MONDAL CONSTRUCTION (SANDESHKHALI) | 8.92 | 0 | 98
1460 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002036/2022-2023 | 13032/AD | 24/03/2023 | 45 | TAPAN DAS (NEW) | 43.96 | 0 | 25
1461 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000052/2023-2024 | 259/AD | 24/04/2023 | 0 | Resource Division | 42.97 | 0 | 0
1462 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000414/2023-2024 | 370/AD | 19/01/2024 | 0 | Resource Division | 6.62 | 0 | 0
1463 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000035/2023-2024 | 170/AD | 19/04/2023 | 90 | S.R. ENTERPRISE | 104.91 | 0 | 98
1464 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1140] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000036/2023-2024 | 171/AD | 19/04/2023 | 741 | K.B. ENTERPRISE | 113.44 | 0 | 90
1465 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Debnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16027) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000155/2024-2025 | 2506/AD | 15/06/2024 | 518 | M/S DEBABRATA DAS | 91.21 | 0 | 25
1466 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000365/2023-2024 | 1566/AD | 17/07/2023 | 899 | M/S DEBABRATA DAS | 298.39 | 0 | 80
1467 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investigation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Debnagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). [No. of FHTC = 700] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001349/2023-2024 | 4127/AD | 24/11/2023 | 312 | M/S DEBABRATA DAS | 10.02 | 0 | 100
1468 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Debnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001833/2022-2023 | 12183/AD | 01/03/2023 | 45 | GOLDEN GROUPS | 38.57 | 0 | 80
1469 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
1470 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme (Debnagar) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002161/2022-2023 | 8334/AD | 12/12/2022 | 45 | M/S R.DUTTA & CO. | 5.66 | 0 | 100
1471 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Debnagar PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002218/2023-2024 | 875/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1472 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Debnagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002278/2023-2024 | 915/AD | 08/02/2024 | 358 | P & S ASSOCIATES | 9.6 | 0 | 100
1473 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000482/2023-2024 | 4784/AD | 19/12/2023 | 0 | Resource Division | 27.67 | 0 | 0
1474 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000555/2023-2024 | 43/AD | 03/01/2024 | 0 | Resource Division | 15.09 | 0 | 0
1475 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000906/2023-2024 | 894/AD | 07/02/2024 | 0 | Resource Division | 12.81 | 0 | 0
1476 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000982/2023-2024 | 1775/AD | 27/03/2024 | 0 | Resource Division | 3.32 | 0 | 0
1477 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -3 of Sonakhali Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000056/2022-2023 | 792/AD | 12/05/2022 | 30 | G.B. CONSTRUCTION (TW) | 17.99 | 0 | 94
1478 | Alipore Division | Canning Sub-division | Surging of 03 nos. Big dia Tubewell of Sonakhali (Zone-II) (TW-2) and Harbhangi (TW-3 & 4) W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000241/2025-2026 | 680/CSD | 26/05/2025 | 30 | FORTUNE ENGINEERING | 4.3 | 0 | 0
1479 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1220] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000256/2023-2024 | 1444/AD | 13/07/2023 | 60 | RIVER BENZ CONSTRUCTION | 265.52 | 0 | 81
1480 | Alipore Division | Canning Sub-division | onstruction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000313/2024-2025 | 2694/AD | 24/06/2024 | 45 | SAHANA ENTERPRISE | 7.08 | 0 | 0
1481 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Sonakhali (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000487/2024-2025 | 3546/AD | 02/09/2024 | 122 | MONDAL ENTERPRISE (MURSHIDABAD) | 43.98 | 0 | 95
1482 | Alipore Division | Canning Sub-division | Inter connection in between the replacement tubewell towards distribution system for Sonakhali W/S Scheme (Zone-II), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-2) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001255/2023-2024 | 1203/CSD | 10/11/2023 | 30 | C.S. CONSTRUCTION | 1.01 | 0 | 0
1483 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001852/2022-2023 | 11818/AD | 23/02/2023 | 45 | TECH VISION | 4.56 | 0 | 0
1484 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
1485 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000036/2023-2024 | 241/AD | 24/04/2023 | 0 | Resource Division | 85.44 | 0 | 0
1486 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000393/2023-2024 | 334/AD | 19/01/2024 | 0 | Resource Division | 7.52 | 0 | 0
1487 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
1488 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Mrinalnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000131/2024-2025 | 2407/AD | 07/06/2024 | 30 | M/S DHIRENDRA ENTERPRISE | 9.53 | 0 | 0
1489 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
1490 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Mrinalnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000956/2023-2024 | 2988/AD | 26/09/2023 | 45 | ANANTA KUMAR GIRI | 27.69 | 0 | 0
1491 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Mrinalnagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/16292) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001364/2024-2025 | 5485/AD | 27/12/2024 | 230 | S. CHAKRABORTY AND CO. | 40.78 | 0 | 100
1492 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Mrinalnagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002072/2023-2024 | 768(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1493 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
1494 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Mrinalnagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002164/2022-2023 | 8337/AD | 12/12/2022 | 45 | LEMNISCATE | 6.95 | 0 | 100
1495 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000125/2023-2024 | 660/AD | 17/05/2023 | 0 | Resource Division | 15.22 | 0 | 0
1496 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000452/2023-2024 | 4717/AD | 18/12/2023 | 0 | Resource Division | 31.65 | 0 | 0
1497 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000819/2023-2024 | 664/AD | 30/01/2024 | 0 | Resource Division | 2.73 | 0 | 0
1498 | Alipore Division | Baruipur Sub-Division | Road restoration of 1) Conslrucfion Of Biluminous Road From Mirpur School To Matarmaa Veri 2) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01706/2024-2025 | BP-2024-25-791 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 4.04 | 0 | 0
1499 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramnagar Abad W/S Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000120/2024-2025 | 2398/AD | 07/06/2024 | 208 | S. CHAKRABORTY AND CO. | 39.9 | 0 | 100
1500 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000134/2023-2024 | 606/AD | 15/05/2023 | 60 | SIMPLEX DRILLING CO. | 36.27 | 0 | 0
1501 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Ramnagarabad and Dakshin Durgapur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16759 and 16758) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000329/2024-2025 | 2732/AD | 25/06/2024 | 494 | M/S B. ENTERPRISE | 318.12 | 0 | 25
1502 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. (1 no.) and 300 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 450] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000765/2023-2024 | 2911/AD | 20/09/2023 | 300 | M/S B. ENTERPRISE | 547.29 | 0 | 25
1503 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing at 2nd Tubewell Site of Ramnagar Abad Water Supply Scheme, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001164/2023-2024 | 3726/AD | 03/11/2023 | 60 | SUDIP PRADHAN | 5.14 | 0 | 0
1504 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1192] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001214/2023-2024 | 3818/AD | 07/11/2023 | 90 | M/S B. ENTERPRISE | 377.97 | 0 | 30
1505 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
1506 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramnagar Abad W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002162/2023-2024 | 806/AD | 05/02/2024 | 60 | M/S B. ENTERPRISE | 27.51 | 0 | 100
1507 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramnagar Abad W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002163/2023-2024 | 807/AD | 05/02/2024 | 30 | M/S. BABA KAPIL MUNI ENTERPRISE | 9.36 | 0 | 0
1508 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramnagar Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002624/2023-2024 | 881/KSD | 15/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1509 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000112/2023-2024 | 648/AD | 17/05/2023 | 0 | Resource Division | 10.14 | 0 | 0
1510 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000480/2023-2024 | 4757/AD | 19/12/2023 | 0 | Resource Division | 42.86 | 0 | 0
1511 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000765/2023-2024 | 599/AD | 29/01/2024 | 0 | Resource Division | 1.82 | 0 | 0
1512 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Ramnagar Bazar to Sakhartpur Battafa, Bangal para under ramnagar-2 gp 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01697/2024-2025 | BP-2024-25-786 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.64 | 0 | 0
1513 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000106/2023-2024 | 1545/AD | 17/07/2023 | 15 | GANGA TUBEWELL AND HARDWARE | 10.68 | 0 | 0
1514 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000107/2023-2024 | 1546/AD | 17/07/2023 | 15 | M/S. MIHIR KUMAR NASKAR | 15.23 | 0 | 0
1515 | Alipore Division | Canning Sub-division | Laying of Distribution Systemof Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000312/2023-2024 | 1514/AD | 15/07/2023 | 90 | M/S ROY TRADING CO. | 183.15 | 0 | 60
1516 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2147] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000313/2023-2024 | 1515/AD | 15/07/2023 | 90 | M/S ROY TRADING CO. | 139.14 | 0 | 0
1517 | Alipore Division | Canning Sub-division | Laying of Distribution Systemof Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte.(TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000361/2023-2024 | 1562/AD | 17/07/2023 | 546 | M N J ENTERPRISES | 174.43 | 0 | 90
1518 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1909] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000362/2023-2024 | 1563/AD | 17/07/2023 | 90 | M/S GIRIDHARI ENTERPRISE | 125.9 | 0 | 0
1519 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Matherdighi (Zone-III), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 715] (TSM/016448) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000368/2023-2024 | 1569/AD | 17/07/2023 | 763 | S.R.ENTERPRISE | 146.5 | 0 | 50
1520 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-III), Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000392/2023-2024 | 1778/AD | 26/07/2023 | 60 | CIVIL CRAFT | 59.88 | 0 | 100
1521 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-I), Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000550/2023-2024 | 2082/AD | 07/08/2023 | 60 | BHATTACHARJEE & CO. | 60.27 | 0 | 66
1522 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Matherdighi W/S Scheme (Zone-II), Block - Canning-II under Canning Sub Division of Alipore Division, P | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000551/2023-2024 | 2083/AD | 07/08/2023 | 165 | G.B. CONSTRUCTION (TW) | 60.27 | 0 | 65
1523 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Matherdighi (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000612/2023-2024 | 1831/AD | 27/07/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 12.1 | 0 | 98
1524 | Alipore Division | Canning Sub-division | Laying of Pipeline and other allied works of AUGMENTATION OF GROUND WATER BASED MATHER DIGHI (ZONE-I,II and III) PIPED WATER SUPPLY SCHEME , Block ¿ Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Matherdighi, Zone-III) SM/18280 | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001018/2023-2024 | 3303/AD | 07/10/2023 | 30 | M/S. LOKNATH CONSTRUCTION | 6.24 | 0 | 100
1525 | Alipore Division | Canning Sub-division | Laying of washout pipe line with other allied works at Matherdighi RO Plant (Zone -A) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001051/2024-2025 | 1269/CSD | 18/11/2024 | 30 | SUKANTA HALDER | 4.17 | 0 | 100
1526 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Matherdighi (Zone-III) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001354/2023-2024 | 4426/AD | 06/12/2023 | 406 | AHANA ENTERPRISE | 8.02 | 0 | 90
1527 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
1528 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002506/2023-2024 | 1561/AD | 16/03/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.25 | 0 | 0
1529 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002510/2023-2024 | 1562/AD | 16/03/2024 | 45 | MOSTAFIZUR HAQUE GAINE | 7.25 | 0 | 0
1530 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - I) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002515/2023-2024 | 1563/AD | 16/03/2024 | 45 | M/S GIRIDHARI ENTERPRISE | 7.5 | 0 | 0
1531 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - II)(2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002517/2023-2024 | 1564/AD | 16/03/2024 | 260 | M/S GIRIDHARI ENTERPRISE | 7.26 | 0 | 100
1532 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II & III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-III, Pump House No. - III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002519/2023-2024 | 1565/AD | 16/03/2024 | 322 | RIDIP ENTERPRISE | 7.26 | 0 | 100
1533 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II, III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I, Pump House No. - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002566/2024-2025 | 893/AD | 04/03/2025 | 45 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0
1534 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Matherdighi W/S Scheme (Zone-I, II, III), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002569/2024-2025 | 894/AD | 04/03/2025 | 45 | KIRON CONSTRUCTION | 7.05 | 0 | 0
1535 | Alipore Division | Diamond Harbour Sub-Division | Road restoration at an urgent basis at Koutala, Dari Koutala, Shimulberia, Lakshminarayanpur, Kushberia, Kishorepur, Krishnarampur, Nakali, under Dhola G.P under the Augmentation Scheme of Kulpi Zone-VII under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000017/2025-2026 | 1928/AD | 23/04/2025 | 45 | SRINAGAR COOPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED | 9.01 | 0 | 90
1536 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VII at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-5851]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000340/2023-2024 | 1557/AD | 17/07/2023 | 624 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1417.15 | 0 | 20
1537 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001019/2022-2023 | 292/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.52 | 0 | 99
1538 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-VII under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001368/2024-2025 | 5497/AD | 27/12/2024 | 60 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 92.22 | 0 | 0
1539 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VII (Simulberia, OHR Size-900 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002101/2022-2023 | 340/DHSD | 17/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
1540 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000008/2024-2025 | 5160/AD | 12/12/2024 | 0 | Resource Division | 61.6 | 0 | 0
1541 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000194/2023-2024 | 1628/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
1542 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000209/2023-2024 | 2017/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
1543 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000368/2023-2024 | 3232/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
1544 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000668/2023-2024 | 421/AD | 22/01/2024 | 0 | Resource Division | 39 | 0 | 0
1545 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000866/2023-2024 | 773/AD | 03/02/2024 | 0 | Resource Division | 36.04 | 0 | 0
1546 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000937/2023-2024 | 1279/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
1547 | Alipore Division |  | Road restoration for L036- Gabbria on T01 to Purba paschima para (WB02 403) |  |  | BILL/01735/2024-2025 | BP-2024-25-799 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.64 | 0 | 0
1548 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kabasenre having village with maximum 62 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001737/2022-2023 | 11766/AD | 21/02/2023 | 60 | MUNNA AGROTECH ENTERPRISE | 30.53 | 0 | 0
1549 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000868/2023-2024 | 775/AD | 03/02/2024 | 0 | Resource Division | 0.47 | 0 | 0
1550 | Alipore Division | Raidighi Sub-Division | Construction of 150 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, boundary wall and other allied works at Zone- XV of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10532 & SM/18872) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000432/2024-2025 | 3275/AD | 07/08/2024 | 300 | PINKI CONSTRUCTION | 129.16 | 0 | 0
1551 | Alipore Division | Raidighi Sub-Division | Construction of approach road for Over Head Reservoir site at Zone ¿ XV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000873/2024-2025 | 4657/AD | 20/11/2024 | 45 | L.N. ENTERPRISE | 12.97 | 0 | 100
1552 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000874/2024-2025 | 4658/AD | 20/11/2024 | 60 | M/S. JHARNA ENTERPRISE | 29.11 | 0 | 0
1553 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
1554 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Uttar Kashiabad PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000912/2023-2024 | 270(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1555 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( UTTAR KASHIABAD PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001050/2022-2023 | 3677/AD | 01/08/2022 | 45 | LEMNISCATE | 4.84 | 0 | 100
1556 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Kashiabad W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001161/2023-2024 | 3723/AD | 03/11/2023 | 45 | M/S MALI ENTERPRISE | 27.74 | 0 | 60
1557 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Kashiabad W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001162/2023-2024 | 3724/AD | 03/11/2023 | 30 | KHATEJA CONSTRUCTION | 9.5 | 0 | 0
1558 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Kashiabad W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001311/2022-2023 | 9894/AD | 10/01/2023 | 45 | BENGAL ENTERPRISE | 38.58 | 0 | 0
1559 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
1560 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000121/2023-2024 | 658/AD | 17/05/2023 | 0 | Resource Division | 8.96 | 0 | 0
1561 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000450/2023-2024 | 4715/AD | 18/12/2023 | 0 | Resource Division | 38.71 | 0 | 0
1562 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000814/2023-2024 | 659/AD | 30/01/2024 | 0 | Resource Division | 1.61 | 0 | 0
1563 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Kashinagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18873) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000215/2024-2025 | 2598/AD | 19/06/2024 | 45 | M/S AINUR ENTERPRISE | 9.73 | 0 | 0
1564 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter at 3rd Tubewell Site of Kashinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000322/2024-2025 | 2397/AD | 07/06/2024 | 30 | S. CHAKRABORTY AND CO. | 19.95 | 0 | 100
1565 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
1566 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( KASINAGAR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001363/2023-2024 | 3259/AD | 05/10/2023 | 45 | LEMNISCATE | 5.75 | 0 | 100
1567 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Kashinagar Water Supply Scheme (Augmentation), Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001410/2023-2024 | 4596/AD | 14/12/2023 | 30 | AQUATECH ENGINEERS | 18.31 | 0 | 0
1568 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
1569 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000999/2023-2024 | 1792/AD | 27/03/2024 | 0 | Resource Division | 33.67 | 0 | 0
1570 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Gangasagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (Part-B) (SM/18983) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000423/2024-2025 | 4440/AD | 06/11/2024 | 182 | PIKASU BOSE | 126.64 | 0 | 100
1571 | Alipore Division | Kakdwip Sub-Division | Supply and installation on hire basis Printed Flex Banner for Creating Public Awareness on JJM for different area of Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18983) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001334/2024-2025 | 5423/AD | 24/12/2024 | 30 | SHOUMMODIP AND CO. | 11.44 | 0 | 100
1572 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GANGASAGAR (ZONE - I & II) PWSS (PHASE - B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001362/2023-2024 | 3436/AD | 12/10/2023 | 45 | VOYAGER | 7.61 | 0 | 100
1573 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bishnupur Zone - I & II, Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002150/2023-2024 | 947/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1574 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main and FHTC for 1 year after completion of FHTC works for Augmentation of Gangasagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002231/2023-2024 | 904/AD | 08/02/2024 | 783 | ANUP PAUL | 390.45 | 0 | 30
1575 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002622/2023-2024 | 865(A)/KSD | 13/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
1576 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000716/2023-2024 | 486/AD | 24/01/2024 | 0 | Resource Division | 13.4 | 0 | 0
1577 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000903/2023-2024 | 889/AD | 07/02/2024 | 0 | Resource Division | 67.34 | 0 | 0
1578 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000968/2023-2024 | 1760/AD | 27/03/2024 | 0 | Resource Division | 29.12 | 0 | 0
1579 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Dharmatala Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000082/2020-2021 | 5305/AD | 18/02/2021 | 365 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 257.73 | 47.48 | 78
1580 | Alipore Division | Canning Sub-division | Laying pipe line at Badhukulla of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000300/2023-2024 | 187/CSD | 23/05/2023 | 30 | GOUTAM HALDAR (I) | 0.95 | 0 | 100
1581 | Alipore Division | Canning Sub-division | Laying pipe line Badhukulla and Naliakhali of Dharmatala Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000588/2022-2023 | 5864/AD | 18/10/2022 | 15 | SAB ENGINEERING WORKS | 9.27 | 0 | 100
1582 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations at Mouza-Amtala Bhadri, Dakshin Kalikatala, Herobhanga and Basur Chak of Dharmatala Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001063/2021-2022 | 5298/AD | 04/01/2022 | 60 | SAHANA ENTERPRISE | 28.74 | 0 | 100
1583 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001348/2022-2023 | 10215/AD | 19/01/2023 | 60 | B.K. ENTERPRISE. | 59.91 | 0 | 90
1584 | Alipore Division | Canning Sub-division | Laying rising main from tubewell no. 4 at Dharmatala W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001407/2023-2024 | 1146/CSD | 01/11/2023 | 30 | GOUTAM HALDAR (I) | 1.92 | 0 | 100
1585 | Alipore Division | Baruipur Sub-Division | Road restoration for Shikharbali-I GP lo Dakshin Kalyanpur | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01778/2024-2025 | BP-2024-25-803 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.31 | 0 | 0
1586 | Alipore Division | Diamond Harbour Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 360 mtr. deep Tubewell by Direct Rotary method for improvement of water supply at Pump House No. 01 of Birendra Bagaria W/S Scheme Block - Kulpi under Diamond Harbour Sub-Division in the District of South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000473/2022-2023 | 5525/AD | 29/09/2022 | 30 | SIMPLEX DRILLING CO. | 24.61 | 0 | 100
1587 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of Laying of distribution system at Zone-X of Kulpi Block for providing 100% FHTC under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - A) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000479/2023-2024 | 1992/AD | 04/08/2023 | 697 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 1049.75 | 0 | 20
1588 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-X of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001023/2022-2023 | 296/DHSD | 15/09/2022 | 30 | CHAYANIKA ENGINEERING CONSULTANCY | 4.14 | 0 | 98
1589 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000213/2023-2024 | 2022/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
1590 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000626/2023-2024 | 287/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
1591 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000665/2023-2024 | 325/AD | 19/01/2024 | 0 | Resource Division | 535.64 | 0 | 0
1592 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000860/2023-2024 | 767/AD | 03/02/2024 | 0 | Resource Division | 49.76 | 0 | 0
1593 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 60 | ADITYA HAZRA | 75.75 | 0 | 93
1594 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Budhakhali Zone - I (Part - I & II) W/S Scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) (2nd Call) (SM/14041) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000499/2024-2025 | 3602/AD | 06/09/2024 | 45 | M/S MALI ENTERPRISE | 27.79 | 0 | 50
1595 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Budhakhali Zone-1 PWSS, Block -Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14041) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000500/2024-2025 | 3603/AD | 06/09/2024 | 75 | UCON (II) | 92.85 | 0 | 0
1596 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Budhakhali Zone-I Part-II W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000593/2023-2024 | 2350/AD | 18/08/2023 | 45 | UCON | 36.01 | 0 | 0
1597 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Budhakhali Zone-I (Part-II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000939/2023-2024 | 279(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1598 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001096/2022-2023 | 8431/AD | 15/12/2022 | 365 | M/S. J.K. TRIPATHI & SONS | 89.96 | 0 | 91
1599 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001097/2022-2023 | 8432/AD | 15/12/2022 | 60 | B.N.C. CONSTRUCTION | 85.86 | 0 | 90
1600 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001098/2022-2023 | 8433/AD | 15/12/2022 | 60 | M/S. UMA CONSTRUCTION | 88.4 | 0 | 100
1601 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001099/2022-2023 | 8434/AD | 15/12/2022 | 610 | GIRI ENTERPRISE | 88.01 | 0 | 95
1602 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001100/2022-2023 | 8435/AD | 15/12/2022 | 30 | DIPANKAR DUTTA | 20.66 | 0 | 60
1603 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Budhakhali Zone-I (Part- II) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001101/2022-2023 | 8436/AD | 15/12/2022 | 45 | SARADA CONSTRUCTION | 36.64 | 0 | 0
1604 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Budhakhali Zone-I (Part-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001346/2022-2023 | 10101/AD | 17/01/2023 | 300 | UCON | 328.79 | 0 | 30
1605 | Alipore Division | Kakdwip Sub-Division | Sinking of 1 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using PVC Pipe and Pre-packed Resin Bonded Gravel at 2nd Tubewell Site of Budhakhali Zone-I Water Supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001580/2021-2022 | 6960/AD | 29/03/2022 | 30 | SIMPLEX DRILLING CO. | 18.06 | 0 | 100
1606 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Budhakhali [Zone-I] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001810/2022-2023 | 05/AD | 01/04/2022 | 45 | M/S R.DUTTA & CO. | 7.34 | 0 | 95
1607 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (BUDAKHALI ZONE- I PWSS) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [Phase-I]. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001897/2021-2022 | 6921/AD | 28/03/2022 | 45 | M/S R.DUTTA & CO. | 7.34 | 0 | 0
1608 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
1609 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 1st Tubewell site for Budhakhali Zone 1 Part 1 W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14041) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002184/2024-2025 | 2065/KSD | 28/12/2024 | 20 | HARAKRISHNA KAMILA | 2.56 | 0 | 100
1610 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Budhakhali Zone - I (Part-1) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14041) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002185/2024-2025 | 2066/KSD | 28/12/2024 | 20 | IMAGINEER VENTURES | 2.44 | 0 | 0
1611 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000488/2023-2024 | 4785/AD | 19/12/2023 | 0 | Resource Division | 34.44 | 0 | 0
1612 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000552/2023-2024 | 40/AD | 03/01/2024 | 0 | Resource Division | 5.64 | 0 | 0
1613 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000785/2023-2024 | 629/AD | 30/01/2024 | 0 | Resource Division | 1.36 | 0 | 0
1614 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000907/2023-2024 | 895/AD | 07/02/2024 | 0 | Resource Division | 1.57 | 0 | 0
1615 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Paschim Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000124/2024-2025 | 2402/AD | 07/06/2024 | 272 | GRAVITA ENTERPRISE | 11.58 | 0 | 100
1616 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PASCHIM SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000979/2022-2023 | 3664/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.97 | 0 | 0
1617 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Paschim Sripatinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001278/2022-2023 | 9590/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
1618 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation Water Supply Scheme (PASCHIM SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001325/2022-2023 | 3308/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.97 | 0 | 100
1619 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Paschim Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002038/2023-2024 | 520/AD | 25/01/2024 | 585 | S.S.CONSULTANCY & CONSTRUCTION | 32.87 | 0 | 40
1620 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000098/2023-2024 | 544/AD | 12/05/2023 | 0 | Resource Division | 10.76 | 0 | 0
1621 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000303/2023-2024 | 3098/AD | 28/09/2023 | 0 | Resource Division | 18.47 | 0 | 0
1622 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000676/2023-2024 | 442/AD | 24/01/2024 | 0 | Resource Division | 1.72 | 0 | 0
1623 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000743/2023-2024 | 578/AD | 29/01/2024 | 0 | Resource Division | 1.93 | 0 | 0
1624 | Alipore Division | Diamond Harbour Sub-Division | Repairing of boundary wall at Pump House No-2 under Kulpi PWSS under Zone- IV of Kulpi Block for "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000325/2025-2026 | 267/DHSD | 16/06/2025 | 45 | M/S B ENTERPRISE | 4.6 | 0 | 0
1625 | Alipore Division | Diamond Harbour Sub-Division | Repairing of Pump House no-2 under Zone-IV of Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000328/2025-2026 | 268/DHSD | 16/06/2025 | 45 | S.S. ENTERPRISE (II) | 1.11 | 0 | 0
1626 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IV of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001045/2022-2023 | 290/DHSD | 15/09/2022 | 30 | MEASURE LAND | 3.66 | 0 | 98
1627 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-7293]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001136/2023-2024 | 3653/AD | 31/10/2023 | 500 | SAFECO ENTERPRISES | 1446.19 | 0 | 65
1628 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-IV (Sitarampur, OHR Size-1000 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002097/2022-2023 | 332/DHSD | 10/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
1629 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000206/2023-2024 | 2024/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
1630 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000622/2023-2024 | 283/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
1631 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000669/2023-2024 | 422/AD | 22/01/2024 | 0 | Resource Division | 222.03 | 0 | 0
1632 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000858/2023-2024 | 765/AD | 03/02/2024 | 0 | Resource Division | 35.68 | 0 | 0
1633 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000934/2023-2024 | 1276/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
1634 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-III including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Diamond Harbour-II under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000075/2020-2021 | 5352/AD | 19/02/2021 | 365 | SUPRITI ENTERPRISE | 404.97 | 212.18 | 99
1635 | Alipore Division | Diamond Harbour Sub-Division | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Gondia Raghunathpur village due to Swajal Gram activities under Zone-III of Diamond Harbour-II within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000581/2022-2023 | 5857/AD | 18/10/2022 | 30 | SRIJON ENTERPRISE | 38.07 | 0 | 100
1636 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for 4(four) months (period from 01/01/2022 to 30/04/2022) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001207/2021-2022 | 404/DHSD | 28/12/2021 | 121 | SUMAN HALDER | 1.6 | 0 | 0
1637 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-IIIA at Diamond Harbour- II block for providing House Hold Tap connection, under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001403/2024-2025 | 5527/AD | 28/12/2024 | 45 | DURGA ENTERPRISE | 19.3 | 0 | 0
1638 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-II (Akrapanji, OHR Size-1250) within Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002092/2022-2023 | 326/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
1639 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000003/2021-2022 | 2022/AD | 01/09/2021 | 0 | Resource Division | 4.07 | 0 | 0
1640 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000121/2022-2023 | 12051/AD | 27/02/2023 | 0 | Resource Division | 4.82 | 0 | 0
1641 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000881/2023-2024 | 755/AD | 03/02/2024 | 0 | Resource Division | 28.59 | 0 | 0
1642 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000920/2023-2024 | 1262/AD | 02/03/2024 | 0 | Resource Division | 0.93 | 0 | 0
1643 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 365 | BALAJEE ENTERPRISE. | 337.44 | 119.83 | 100
1644 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 365 | M/S. S.S. ENTERPRISE | 440.86 | 152.32 | 100
1645 | Alipore Division | Diamond Harbour Sub-Division | Laying distribution pipe line damaged due to widening and strengthening of Falta PWD main road at Falta Zone-I for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001192/2021-2022 | 5709/AD.. | 31/01/2022 | 60 | S.P. CONSTRUCTION (V) | 50.97 | 0 | 0
1646 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gosta Para (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001765/2020-2021 | 1224/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 4.25 | 0
1647 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kali Mandir Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001779/2020-2021 | 1226/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 4.25 | 0
1648 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Phase-I), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001787/2020-2021 | 1232/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 4.27 | 0
1649 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Part) & Bamankhali (Part) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001794/2020-2021 | 1239/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.66 | 4.6 | 0
1650 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 2 no. Block, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001804/2020-2021 | 1243/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 4.28 | 0
1651 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001809/2020-2021 | 1247/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.69 | 0
1652 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001810/2020-2021 | 1249/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.75 | 0
1653 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-I) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001812/2020-2021 | 1251/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.71 | 0
1654 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Surendranagar (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001824/2020-2021 | 1258/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 4.24 | 0
1655 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001825/2020-2021 | 1259/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.74 | 0
1656 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001831/2020-2021 | 1262/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.63 | 0
1657 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paschim Surendranagar (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001832/2020-2021 | 1263/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 4.24 | 0
1658 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-II) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001834/2020-2021 | 1265/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.72 | 0
1659 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purba Para, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001852/2020-2021 | 1283/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 4.27 | 0
1660 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001862/2020-2021 | 1293/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.74 | 0
1661 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001866/2020-2021 | 1297/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.73 | 0
1662 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mandirtala (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001872/2020-2021 | 1302/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.75 | 0
1663 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001886/2020-2021 | 1308/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.5 | 3.39 | 0
1664 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Chakfuldubi (Phase-V) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001888/2020-2021 | 1310/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 2.85 | 0
1665 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-IV) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001890/2020-2021 | 1312/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 4.74 | 0
1666 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bamankhali (Phase-III) for Mandirtala W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001892/2020-2021 | 1314/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.72 | 0
1667 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 1 no. Block, for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001926/2020-2021 | 1338/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 4.28 | 0
1668 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000020/2022-2023 | 1197/AD | 30/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
1669 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/13876) (SM/07403) (SM/07405) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001332/2024-2025 | 5416/AD | 24/12/2024 | 480 | MONDAL ENTERPRISE (MURSHIDABAD) | 44 | 0 | 51
1670 | Alipore Division |  | HIRING OF AN Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer, DIAMOND HARBOUR SUB-DIVISION under Alipore Division, PHE Dte. (From 01.11.23 to 30.04.2023) |  |  | BILL/03385/2023-2024 | BP-2023-24-954 | 25/01/2024 | 0 | GOPAL KUMAR JHA | 0.7 | 0 | 0
1671 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-II including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000068/2021-2022 | 343/AD | 12/05/2021 | 365 | B. MOOKHERJEE | 310.16 | 0 | 100
1672 | Alipore Division |  | Balance works under the Augmentation scheme of Zone-II at Falta block for providing balance pipe lying works, House Hold Tap connection, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000822/2024-2025 | 780/AD | 25/02/2025 | 225 | M/S PARAMESWAR CHOWDHURY | 80.38 | 0 | 75
1673 | Alipore Division |  | Relaying of distribution pipeline (damaged portion by open cut method) & road restoration near NP 92 & NP 77 at Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000833/2022-2023 | 213/DHSD | 02/08/2022 | 45 | B. MOOKHERJEE | 3.61 | 0 | 0
1674 | Alipore Division |  | Relaying of distribution pipeline (damaged portion due to widening of road) in between NP 2 to NP 377 at Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000834/2022-2023 | 214/DHSD | 02/08/2022 | 45 | PEECON | 3.26 | 0 | 0
1675 | Alipore Division |  | Laying of parallel distribution pipeline along opposite flank of Falta main road at Zone-II of Falta Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/001652/2021-2022 | 454/DHSD | 15/03/2022 | 15 | B. MOOKHERJEE | 4.8 | 0 | 100
1676 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000100/2022-2023 | 7494/AD | 26/11/2022 | 0 | Resource Division | 2.69 | 0 | 0
1677 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000431/2023-2024 | 3626/AD | 30/10/2023 | 0 | Resource Division | 6.16 | 0 | 0
1678 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000846/2023-2024 | 784/AD | 03/02/2024 | 0 | Resource Division | 2.03 | 0 | 0
1679 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001421/2023-2024 | 4601/AD | 14/12/2023 | 472 | MAA BHABANI CONSTRUCTION (DUM DUM) | 47.31 | 0 | 70
1680 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000832/2023-2024 | 677/AD | 30/01/2024 | 0 | Resource Division | 5.35 | 0 | 0
1681 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Master Para (Part) & Mali Para of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000403/2020-2021 | 774/KSD | 14/10/2020 | 45 | M/S. SIKHA ENTERPRISE | 4.77 | 4.68 | 0
1682 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Mahendraganj (Part) & Ghol Para of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000404/2020-2021 | 775/KSD | 14/10/2020 | 45 | M/S. BABA KAPIL MUNI ENTERPRISE | 4.74 | 4.69 | 0
1683 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dhaspara (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000405/2020-2021 | 776/KSD | 14/10/2020 | 45 | AVIJIT MAITY | 2.97 | 2.53 | 0
1684 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Panchayet Bazar Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000417/2020-2021 | 794/KSD | 15/10/2020 | 45 | M/S BHUNIA ENTERPRISE | 4.06 | 0 | 99
1685 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Das Para, Muntan Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000433/2020-2021 | 819/KSD | 16/10/2020 | 45 | SUMAN INDUSTRIES PVT. LTD. | 4.35 | 0 | 90
1686 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 256 to 257 (Part), 253 to 264, 264 to 265, 265 to 267, 211 to 223, 221 to 222, 41 to 42 (Part) & 42 to 43 (Part) of Dhaspara W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000436/2020-2021 | 822/KSD | 16/10/2020 | 45 | G.M. ENTERPRISE | 4.78 | 0 | 100
1687 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Purba Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000466/2020-2021 | 1044/KSD | 19/12/2020 | 20 | M/S. JOYGURU ENTERPRISE | 3.52 | 3.45 | 0
1688 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Paschim Para (Part) of Dhaspara W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000536/2020-2021 | 793/KSD | 15/10/2020 | 45 | SAB ENGINEERING WORKS | 3.83 | 0 | 0
1689 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000703/2023-2024 | 473/AD | 24/01/2024 | 0 | Resource Division | 12.79 | 0 | 0
1690 | Alipore Division | Kakdwip Sub-Division | Laying of rising main & distribution main and retrofitting of FHTC under JJM for Shibpur Water Supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000199/2022-2023 | 2685/AD | 30/06/2022 | 30 | BIMALENDU GIRI | 19.72 | 0 | 100
1691 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dk. Madhya Shibpur and adjoining areas of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000215/2020-2021 | 650/KSD | 19/08/2020 | 15 | ANANTA KUMAR GIRI | 4.68 | 4.67 | 0
1692 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Shibpur Para (Part) of Shibpur W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000420/2020-2021 | 797/KSD | 15/10/2020 | 45 | SUMAN INDUSTRIES PVT. LTD. | 4.09 | 0 | 100
1693 | Alipore Division | Kakdwip Sub-Division | Restoration of Remaining Functional Household Tap Connection (FHTC) to the households of Habitation: Dk. Madhya Shibpur, Dk Paschim Shibpur and Uttar Purba Shibpur of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000458/2020-2021 | 846/KSD | 16/10/2020 | 45 | GROWING CONCERN | 4.37 | 4.37 | 0
1694 | Alipore Division | Kakdwip Sub-Division | Restoration of Remaining Functional Household Tap Connection (FHTC) to the households of Habitation: Freserganj Dk Shibpur, Shibpur Uttar Majherpara and Uttar Paschim Shibpur of Shibpur W/S Scheme, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000459/2020-2021 | 848/KSD | 16/10/2020 | 45 | ASHIS ENTERPRISE | 4.56 | 4.56 | 0
1695 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000477/2020-2021 | 1055/KSD | 19/12/2020 | 25 | ANANTA KUMAR GIRI | 4.45 | 4.37 | 0
1696 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000482/2020-2021 | 1060/KSD | 19/12/2020 | 25 | ASHIS ENTERPRISE | 4.72 | 0 | 96
1697 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Shibpur piped water supply Scheme, Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000488/2020-2021 | 1065/KSD | 19/12/2020 | 25 | GROWING CONCERN | 4.31 | 4.09 | 0
1698 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC to all households for Augmentation of Sibpur (Zone-I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000987/2023-2024 | 3006/AD | 26/09/2023 | 30 | PALCON | 11.99 | 0 | 100
1699 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000797/2023-2024 | 642/AD | 30/01/2024 | 0 | Resource Division | 8.54 | 0 | 0
1700 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000428/2024-2025 | 3258/AD | 06/08/2024 | 360 | M. MUKHERJEE | 150.27 | 0 | 0
1701 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line by replacing the damaged pipe line of different dia. for providing FHTC at Mahishamari Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000470/2021-2022 | 2418/AD | 15/09/2021 | 45 | M. MUKHERJEE | 14.85 | 0 | 100
1702 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Mahishmari Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001243/2020-2021 | 2274/AD | 12/10/2020 | 365 | M. MUKHERJEE | 106.14 | 6.97 | 95
1703 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000712/2023-2024 | 482/AD | 24/01/2024 | 0 | Resource Division | 6.62 | 0 | 0
1704 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households at Ananda Abad Water Supply Scheme (Habitation- Ananda Abad), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) |  |  | ORD/000079/2022-2023 | 275/CSD | 19/05/2022 | 40 | M/S. MANABESH ROY | 4.81 | 0 | 100
1705 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Ananda Abad Water Supply Scheme Block - Basanti, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year |  |  | ORD/001379/2020-2021 | 5370/AD | 19/02/2021 | 365 | M/S. MANABESH ROY | 61.07 | 17.46 | 100
1706 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Singheswar Water Supply Scheme Block - Canning - II, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001381/2020-2021 | 5371/AD | 19/02/2021 | 365 | M/S. SARADA UDYOG | 68.19 | 42.99 | 96
1707 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (410 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Singheswar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002312/2023-2024 | 1065/AD | 21/02/2024 | 282 | RAKTIM ENTERPRISE | 35.55 | 0 | 93
1708 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Uttar Angadberia Water Supply Scheme, Block - Canning-I, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000084/2020-2021 | 5307/AD | 18/02/2021 | 365 | M/S ROY TRADING CO. | 107.85 | 20.48 | 84
1709 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Makhaltala Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000088/2020-2021 | 5310/AD | 18/02/2021 | 365 | M/S. SUMAN ENTERPRISE | 121.24 | 0 | 100
1710 | Alipore Division | Raidighi Sub-Division | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghoradal Uttar (Dakshinpara) and Fhatki Paschimpara under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000039/2022-2023 | 08/RSD | 04/04/2022 | 60 | M/S R.K.ENTERPRISE | 4.77 | 0 | 100
1711 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Gabbati (Part-B) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000270/2021-2022 | 380/RSD | 13/08/2021 | 60 | M/S R.K.ENTERPRISE | 4.82 | 4.57 | 100
1712 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Killa Dakshin (Part-1) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000291/2020-2021 | 376/RSD | 15/10/2020 | 30 | L.N. ENTERPRISE | 4.76 | 4.76 | 0
1713 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Killa Uttar (Part-1) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000292/2020-2021 | 377/RSD | 15/10/2020 | 30 | L.N. ENTERPRISE | 4.76 | 4.76 | 0
1714 | Alipore Division | Raidighi Sub-Division | Laying distribution system and other allied works for piped water supply at Zone - XI of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/07751 and SM/15466) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000532/2024-2025 | 3638/AD | 09/09/2024 | 90 | SUJATA CONSTRUCTION | 26.06 | 0 | 0
1715 | Alipore Division | Raidighi Sub-Division | Extension of Pipeline in connection with Functional Household Tap Connection (FHTC) from SI of schools to Dhopapara (node no. 167-172-176) at Ghoradal mouza under Ghoradal Water supply Scheme of Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001156/2021-2022 | 570/RSD | 15/12/2021 | 60 | M/S R.K.ENTERPRISE | 4.68 | 0 | 100
1716 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Ghoradal at Habitation-Gabbati in Ghoradal piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001183/2021-2022 | 536/RSD | 30/11/2021 | 60 | M/S. JHARNA ENTERPRISE | 4.76 | 0 | 100
1717 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza- Istaranpur at Habitation-Gabbati in Ghoradal piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001184/2021-2022 | 537/RSD | 30/11/2021 | 60 | M/S R.K.ENTERPRISE | 4.8 | 0 | 100
1718 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Gabbati (Part-A) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001214/2020-2021 | 561/RSD | 30/12/2020 | 60 | L.N. ENTERPRISE | 4.82 | 4.55 | 0
1719 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Ghoradal (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001228/2020-2021 | 563/RSD | 30/12/2020 | 60 | L.N. ENTERPRISE | 4.82 | 4.54 | 0
1720 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Killa Dakshin (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001231/2020-2021 | 565/RSD | 30/12/2020 | 60 | M/S R.K.ENTERPRISE | 4.82 | 4.55 | 0
1721 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghoradal at Habitation - Killa Uttar (Part-2) in Ghoradal Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001235/2020-2021 | 567/RSD | 30/12/2020 | 60 | M/S R.K.ENTERPRISE | 4.82 | 4.54 | 0
1722 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Istaranpur at Habitation-Ulubati Istaranpur in Ghoradal piped water supply scheme, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001485/2021-2022 | 710/RSD | 02/03/2022 | 60 | L.N. ENTERPRISE | 4.22 | 0 | 100
1723 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Mouza-Istaranpur at Habitation-Ulubati Istaranpur in Ghoradal piped water supply scheme, District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001545/2021-2022 | 710/RSD | 02/03/2022 | 60 | L.N. ENTERPRISE | 4.22 | 0 | 100
1724 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000633/2023-2024 | 237/AD | 15/01/2024 | 0 | Resource Division | 11.25 | 0 | 0
1725 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works and Construction of 01 no. Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000626/2022-2023 | 5979/AD | 20/10/2022 | 90 | M/S. JAYDEEP DASGUPTA | 129.4 | 0 | 100
1726 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001731/2020-2021 | 1213/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.65 | 0 | 94
1727 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bark Para & Maity Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001742/2020-2021 | 1215/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.71 | 0 | 94
1728 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001758/2020-2021 | 1217/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 3.66 | 98
1729 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sumanta Para & Kaylapara (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001761/2020-2021 | 1220/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.82 | 3.76 | 99
1730 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakhin Para (Phase-I) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001763/2020-2021 | 1222/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.1 | 0 | 94
1731 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para (Part) & Purb Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001790/2020-2021 | 1235/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.5 | 0 | 94
1732 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - A) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001813/2020-2021 | 1252/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.62 | 94
1733 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - B) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001837/2020-2021 | 1268/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 4.65 | 97
1734 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Maity Para (Part) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001840/2020-2021 | 1271/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.93 | 3.84 | 94
1735 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001842/2020-2021 | 1273/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.77 | 0 | 94
1736 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001845/2020-2021 | 1276/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 0 | 99
1737 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakhin Para (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001848/2020-2021 | 1279/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.11 | 0 | 94
1738 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-II) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001856/2020-2021 | 1287/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.65 | 0 | 94
1739 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sk. More for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001894/2020-2021 | 1316/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.6 | 0 | 94
1740 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Purb Para for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001908/2020-2021 | 1323/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 4.77 | 0 | 94
1741 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kaylapara (Part - C) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001915/2020-2021 | 1325/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.78 | 4.66 | 94
1742 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mondal Para (Phase-III) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001918/2020-2021 | 1328/KSD | 23/02/2021 | 10 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 3.76 | 0 | 94
1743 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mrityunjoy Nagar (Phase-III) for Mrityunjoynagar W/S Scheme, Block - Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001923/2020-2021 | 1334/KSD | 23/02/2021 | 10 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 3.65 | 0 | 94
1744 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000715/2023-2024 | 485/AD | 24/01/2024 | 0 | Resource Division | 8.73 | 0 | 0
1745 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Uttar Lakshminarayanpur Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001310/2020-2021 | 2221/AD | 08/10/2020 | 1825 | M/S B.M. CONSTRUCTION | 106 | 0 | 90
1746 | Alipore Division | Raidighi Sub-Division | Extension of pipeline to provide Functional Household Tap Connection (FHTC) (in between NP- 148-149-150, ext from 150,144-147,152-153-154, ext from 154-156,ext of 15-16, ext from 144-147,136-138,3-4-6,113-114-115,154-156-157, ext 36-37,ext from34-35,34-36,34-32-33,ext from 35) under Uttar Laxminarayanpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001546/2021-2022 | 712/RSD | 02/03/2022 | 60 | M/S B.M. CONSTRUCTION | 4.7 | 0 | 100
1747 | Alipore Division | Raidighi Sub-Division | Additional work (horizontal boring, village road crossing etc.) in connection with Functional Household Tap Connection (FHTCs) at Uttar Laxminarayanpur water supply scheme (Zone-IX of Mathurapur - I Block) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001548/2021-2022 | 714/RSD | 02/03/2022 | 60 | M/S B.M. CONSTRUCTION | 4 | 0 | 100
1748 | Alipore Division | Raidighi Sub-Division | Extension of pipeline to provide Functional Household Tap Connection (FHTC) (in between NP-44-45, 43-40, 35-36, ext from 57, 63-65, 64-63, 60-61, 45-53, ext from 50-52, 46-47, 45-53, 60-61, 52-53, etc) under Uttar Laxminarayanpur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001769/2021-2022 | 627/RSD | 29/12/2021 | 15 | M/S B.M. CONSTRUCTION | 4.28 | 0 | 100
1749 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000642/2023-2024 | 246/AD | 15/01/2024 | 0 | Resource Division | 12.88 | 0 | 0
1750 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the all habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Nebutala Water Supply Scheme, Block ¿ Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000572/2021-2022 | 3673/AD | 22/11/2021 | 365 | SHEKHAR CHAKRABORTY | 53.74 | 0 | 70
1751 | Alipore Division | Kakdwip Sub-Division | Supply and delivery of 6/10 mm NB Gun-metal Ferrule for Providing Functional Household Tap Connection (FHTC) to the households of Nebutala W/S Scheme under JJM Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001751/2021-2022 | 238/KSD/Camp/G.S.Mela 22 | 31/01/2022 | 7 | SHEKHAR CHAKRABORTY | 4.09 | 0 | 100
1752 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000013/2022-2023 | 1168/AD | 27/05/2022 | 0 | Resource Division | 5.97 | 0 | 0
1753 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000823/2023-2024 | 668/AD | 30/01/2024 | 0 | Resource Division | 3.01 | 0 | 0
1754 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000710/2023-2024 | 480/AD | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
1755 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part - F) (SM/13569) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000495/2024-2025 | 3571/AD | 04/09/2024 | 90 | GROWING CONCERN | 100.89 | 0 | 100
1756 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000330/2023-2024 | 3145/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1757 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000380/2023-2024 | 3566/AD | 18/10/2023 | 0 | Resource Division | 18.23 | 0 | 0
1758 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000696/2023-2024 | 466/AD | 24/01/2024 | 0 | Resource Division | 7.9 | 0 | 0
1759 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000015/2021-2022 | 5621/AD | 25/01/2022 | 0 | Resource Division | 5.39 | 0 | 0
1760 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000681/2023-2024 | 451/AD | 24/01/2024 | 0 | Resource Division | 3.25 | 0 | 0
1761 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Netra Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000012/2021-2022 | 3020/AD | 02/11/2021 | 365 | JAYANTA KUMAR DEY | 80.16 | 0 | 40
1762 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Netra W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000068/2025-2026 | 2257/AD | 14/05/2025 | 45 | SAHANA ENTERPRISE | 15.98 | 0 | 0
1763 | Alipore Division | Canning Sub-division | Laying additional pipeline at Augmentation of Netra W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E.Dte. (SM/09014 & SM/17225) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000762/2024-2025 | 4458/AD | 07/11/2024 | 60 | SAHANA ENTERPRISE | 97.21 | 0 | 98
1764 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Improvement & Retrofitting of Netra W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001383/2022-2023 | 1066/CSD | 15/12/2022 | 40 | A.P. CONSTRUCTION | 0.96 | 0 | 95
1765 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000822/2023-2024 | 667/AD | 30/01/2024 | 0 | Resource Division | 5.05 | 0 | 0
1766 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 01 (one) no. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Gangacheri Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000010/2021-2022 | 1343/AD | 19/07/2021 | 365 | S.S. ENTERPRISE (II) | 37.06 | 0 | 95
1767 | Alipore Division | Canning Sub-division | Relaying of damage pipeline due to uncovered FHTC work at Amlamethi Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000527/2022-2023 | 5513/AD | 29/09/2022 | 30 | BIMALENDU GIRI | 59.66 | 0 | 0
1768 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Amlamethi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000642/2021-2022 | 3696/AD | 22/11/2021 | 365 | GROWING CONCERN | 205.06 | 0 | 80
1769 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000071/2022-2023 | 5146/AD | 21/09/2022 | 0 | Resource Division | 30.75 | 0 | 0
1770 | Alipore Division | Canning Sub-division | LAUNCH HIRE CHARGES FOR OCT'22 TO DEC'22 UNDER CANNING SUB-DIVISION, PHE DTE. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | BILL/00680/2024-2025 | BP-2024-25-224 | 20/06/2024 | 0 | RAJKUMAR MANNA | 1.1 | 0 | 0
1771 | Alipore Division | Canning Sub-division | HIRE bill for month of JULY-SEP23 | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | BILL/03541/2023-2024 | BP-2023-24-1272 | 27/03/2024 | 0 | RAJKUMAR MANNA | 8.08 | 0 | 0
1772 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-IV of Bayarsing Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000198/2022-2023 | 2643/AD | 29/06/2022 | 30 | SUDIP PRADHAN | 35.96 | 0 | 0
1773 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bayarsing Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000206/2021-2022 | 1423/AD | 27/07/2021 | 1619 | M/S. SAMADDAR CONSTRUCTION | 152.62 | 0 | 83
1774 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Retrofitting of Narayantala W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000816/2022-2023 | 6811/AD | 16/11/2022 | 892 | HARIDAS DUTTA | 19.49 | 0 | 100
1775 | Alipore Division | Canning Sub-division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 23.12.2022 to 30.06.2023 | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001753/2022-2023 | 460/HQ-II/AD | 22/12/2022 | 182 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 100
1776 | Alipore Division | Canning Sub-division | Survey, Design and DPR preparation for Augmentation of ground water based Narayantala Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001844/2021-2022 | 687/CSD | 19/08/2021 | 15 | HORIZEN | 4.12 | 0 | 100
1777 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000390/2023-2024 | 331/AD | 19/01/2024 | 0 | Resource Division | 6.13 | 0 | 0
1778 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing for Retrofitting of Phulmalancha W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000819/2022-2023 | 6814/AD | 16/11/2022 | 30 | BANGA NIRMAN | 7.18 | 0 | 0
1779 | Alipore Division | Canning Sub-division | Construction of OHR (550 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Phul Malancha,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001088/2023-2024 | 3605/AD | 30/10/2023 | 300 | JIT CONSTRUCTION | 629.62 | 0 | 60
1780 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Phulmalancha Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001845/2021-2022 | 691/CSD | 19/08/2021 | 15 | HORIZEN | 3.15 | 0 | 100
1781 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Phulmalancha Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001846/2021-2022 | 692/CSD | 19/08/2021 | 15 | HORIZEN | 3.26 | 0 | 100
1782 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000047/2022-2023 | 600/AD | 28/04/2022 | 1320 | M/S. S.S. ENTERPRISE | 537.16 | 0 | 73
1783 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (2500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalikatala (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub- Division of Alipore Division, P.H.E.Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000322/2023-2024 | 1548/AD | 17/07/2023 | 863 | M/S. S.S. ENTERPRISE | 177.08 | 0 | 30
1784 | Alipore Division | Canning Sub-division | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Kalikatala (Zone - I & II) of Canning-II Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone-II) (SM/10051) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000695/2024-2025 | 4307/AD | 29/10/2024 | 270 | AMWOODO ECO PRODUCTS PRIVATE LIMITED | 159.68 | 0 | 0
1785 | Alipore Division | Canning Sub-division | Laying distribution system including Providing Functional Household Tap Connection (FHTC) of Kalikatala W/S Scheme (Zone-I) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001541/2021-2022 | 6708/AD | 16/03/2022 | 120 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 341.37 | 0 | 86
1786 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001663/2021-2022 | 620/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
1787 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001665/2021-2022 | 621/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.2 | 0 | 100
1788 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001666/2021-2022 | 622/CSD | 06/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 1.57 | 0 | 100
1789 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001667/2021-2022 | 632/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.92 | 0 | 100
1790 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Kalikatala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001668/2021-2022 | 633/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 0 | 100
1791 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Kalikatala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001669/2021-2022 | 634/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.35 | 0 | 100
1792 | Alipore Division | Canning Sub-division | Additional pipeline for FHTC work of Kalikatala W/S Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001972/2022-2023 | 12591/AD | 13/03/2023 | 45 | M/S. S.S. ENTERPRISE | 90.52 | 0 | 100
1793 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000064/2022-2023 | 3952/AD | 12/08/2022 | 0 | Resource Division | 180.31 | 0 | 0
1794 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000084/2022-2023 | 5547/AD | 29/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
1795 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VIII including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based Water Supply Scheme for Falta-Mathurapur" District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. |  |  | ORD/000009/2022-2023 | 139/AD | 07/04/2022 | 1080 | TANMAY ROY CHOWDHURY | 277.27 | 0 | 90
1796 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 365 | BALAJEE ENTERPRISE. | 337.44 | 0 | 100
1797 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) |  |  | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 365 | M/S. S.S. ENTERPRISE | 440.86 | 0 | 100
1798 | Alipore Division |  | Additional balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe laying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) |  |  | ORD/000389/2025-2026 | 3374/AD | 16/07/2025 | 45 | THE TOWER CONSTRUCTION | 40.87 | 0 | 0
1799 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) in Baidyakhali, Abad Simulgaunge, Pakurtala, Ahamedpur Mouza of Falta Zone-VI under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas Block Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000529/2022-2023 | 5514/AD | 29/09/2022 | 30 | TIYASHA ENTERPRISE | 31.57 | 0 | 50
1800 | Alipore Division |  | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Asta, Chaka,Guthari,Mahadebpur & Padmapur villages due to Swajal Gram activities under Zone-VI of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. |  |  | ORD/000579/2022-2023 | 5855/AD | 18/10/2022 | 15 | BALAJEE ENTERPRISE. | 7.2 | 0 | 100
1801 | Alipore Division |  | Laying of distribution pipeline (leftout portion) over Kantakhali Lock gate and restoration of village concrete road damaged during FHTC work at Zone-VI of Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. |  |  | ORD/000664/2022-2023 | 6169/AD | 01/11/2022 | 10 | BALAJEE ENTERPRISE. | 3.98 | 0 | 100
1802 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 4346/AD | 04/03/2022 | 0 | Resource Division | 38.31 | 0 | 0
1803 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000433/2023-2024 | 3616/AD | 30/10/2023 | 0 | Resource Division | 14.78 | 0 | 0
1804 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000125/2022-2023 | 2028/AD | 21/06/2022 | 30 | M/S. GIRI ENTERPRISE | 12.18 | 0 | 20
1805 | Alipore Division | Kakdwip Sub-Division | Road restoration, Y junction and other allied laying works for providing Functional Household Tap Connection (FHTC) for Kachuberia W/S, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000135/2024-2025 | 2472/AD | 14/06/2024 | 30 | SOMBHUNATH BHATTACHARJEE | 6.12 | 0 | 100
1806 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 400] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000406/2022-2023 | 4660/AD | 07/09/2022 | 90 | SOMBHUNATH BHATTACHARJEE | 111.8 | 0 | 100
1807 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KACHUBERIA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000478/2022-2023 | 297/AD | 12/04/2022 | 45 | VOYAGER | 9.73 | 0 | 0
1808 | Alipore Division | Kakdwip Sub-Division | Surging of 1 no. Tubewell for augmentation of Kachuberia W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000539/2023-2024 | 357/KSD | 09/08/2023 | 20 | S.K.GOLUI | 1.77 | 0 | 100
1809 | Alipore Division | Kakdwip Sub-Division | Construction of 700 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Kachuberia Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001484/2022-2023 | 10710/AD | 02/02/2023 | 790 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 992.52 | 0 | 65
1810 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002055/2022-2023 | 735/KSD | 16/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1811 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
1812 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002184/2022-2023 | 692/KSD | 23/02/2023 | 365 | SUDIP PRADHAN | 2.39 | 0 | 100
1813 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000057/2022-2023 | 3906/AD | 12/08/2022 | 0 | Resource Division | 117.89 | 0 | 0
1814 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000282/2023-2024 | 3057/AD | 28/09/2023 | 0 | Resource Division | 20.5 | 0 | 0
1815 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000320/2023-2024 | 3135/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
1816 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000537/2023-2024 | 21/AD | 02/01/2024 | 0 | Resource Division | 15.6 | 0 | 0
1817 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000898/2023-2024 | 884/AD | 07/02/2024 | 0 | Resource Division | 11.9 | 0 | 0
1818 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000295/2022-2023 | 5706/AD | 13/10/2022 | 45 | SIMPLEX DRILLING CO. | 45.85 | 0 | 0
1819 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Nagendraganj Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000319/2022-2023 | 5704/AD. | 13/10/2022 | 45 | MOUMITA ENTERPRISE | 56.41 | 0 | 0
1820 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamber, fitting fixing supplying different dia specials etc. for Augmentation of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-D) (SM/12626) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000333/2024-2025 | 2741/AD | 26/06/2024 | 45 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 181.12 | 0 | 0
1821 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NAGANDRAGANJ (ZONE - I & II)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000481/2022-2023 | 4190/AD | 22/08/2022 | 45 | VOYAGER | 8.65 | 0 | 100
1822 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 02 nos. Pump House, Functional Household Tap Connection (FHTC) to all households for Augmentation of Nagendraganj Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000540/2022-2023 | 5705/AD.. | 13/10/2022 | 852 | M/S. DAS BUILDERS | 50.5 | 0 | 70
1823 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Nagendraganj W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000592/2023-2024 | 2349/AD | 18/08/2023 | 45 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 52.27 | 0 | 0
1824 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Nagendraganj Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000782/2022-2023 | 6536/AD | 11/11/2022 | 990 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 546.08 | 0 | 20
1825 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Nagendraganj (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000971/2023-2024 | 320/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1826 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Nagendraganj W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001003/2023-2024 | 508/KSD | 03/10/2023 | 20 | S.K.GOLUI | 3.54 | 0 | 0
1827 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/12626) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2024-2025 | 1982/KSD | 23/12/2024 | 20 | M/S MODINA ENTERPRISE | 3.14 | 0 | 0
1828 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Zone-I of Nagendraganj W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/12626) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002143/2024-2025 | 1983/KSD | 23/12/2024 | 20 | M/S. SONAMONI ENTERPRISE | 2.03 | 0 | 90
1829 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Haradhanpur Zone - I & II, Nagendraganj Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002156/2023-2024 | 949/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1830 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Nagendraganj (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002420/2023-2024 | 1347/AD | 06/03/2024 | 45 | M/S KHAJABABA ENTERPRISE | 32.97 | 0 | 90
1831 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Nagendraganj (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002421/2023-2024 | 1348/AD | 06/03/2024 | 389 | RAJLAKSHMI ENTERPRISE | 10.93 | 0 | 100
1832 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000505/2023-2024 | 4828/AD | 20/12/2023 | 0 | Resource Division | 25.17 | 0 | 0
1833 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000718/2023-2024 | 488/AD | 24/01/2024 | 0 | Resource Division | 11.95 | 0 | 0
1834 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000966/2023-2024 | 1759/AD | 27/03/2024 | 0 | Resource Division | 31.52 | 0 | 0
1835 | Alipore Division | Baruipur Sub-Division | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01670/2024-2025 | BP-2024-25-777 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
1836 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the HAZRABAND having village with maximum 123 nos. households, Block - Diamond Harbour -I under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -II,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 2 DHSD | ORD/001123/2022-2023 | 8767/AD | 21/12/2022 | 60 | MAMONI ENTERPRISE | 33.66 | 0 | 0
1837 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 300 Mtr. Depth Rig bored Tube wells, Construction of Switch Room (3750 X 3750), boundary fencing, MS grill type gate,, Pipe connections, Laying of delivery main & Laying of Distribution System, Providing Functional Household Tap Connection, Supplying and installation PVC storage tank etc. of Ground Water Based Mini Piped Water Supply Scheme for the Par Kalugachi having village with maximum 82 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000749/2022-2023 | 6410/AD | 10/11/2022 | 60 | GANGA TUBEWELL AND HARDWARE | 34.64 | 0 | 86
1838 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Battali W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000125/2023-2024 | 571/AD | 15/05/2023 | 870 | ARFIN CONSTRUCTION | 11.53 | 0 | 80
1839 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Battali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000214/2023-2024 | 954/AD | 06/06/2023 | 65 | SALMAN CONSTRUCTION | 43.94 | 0 | 100
1840 | Alipore Division | Canning Sub-division | Construction of OHR (150 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the BATTALI, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC= 1300] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000544/2023-2024 | 2210/AD | 10/08/2023 | 300 | FIDERE MARINE SERVICES PVT. LTD. | 358.79 | 0 | 34
1841 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground water Based at Battali Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000739/2024-2025 | 4396/AD | 05/11/2024 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 33.7 | 0 | 0
1842 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No-2 for Ground water Based at Battali Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000740/2024-2025 | 4397/AD | 05/11/2024 | 30 | SUBHO CONSTRUCTION | 14.36 | 0 | 0
1843 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Battali W/S Scheme , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001401/2022-2023 | 10926/AD | 06/02/2023 | 634 | ARBINA ENTERPRISE | 8.88 | 0 | 100
1844 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Battali W/S Scheme , Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001402/2022-2023 | 10927/AD | 06/02/2023 | 45 | ARBINA ENTERPRISE | 8.57 | 0 | 0
1845 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Battali New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001881/2022-2023 | 7523/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 4.32 | 0 | 99
1846 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000048/2023-2024 | 255/AD | 24/04/2023 | 0 | Resource Division | 39.04 | 0 | 0
1847 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000409/2023-2024 | 363/AD | 19/01/2024 | 0 | Resource Division | 8.01 | 0 | 0
1848 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Bhairabitala having village with maximum 100 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte, | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001121/2022-2023 | 8765/AD | 21/12/2022 | 60 | A.M. ENTERPRISE | 32.19 | 0 | 0
1849 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000873/2023-2024 | 780/AD | 03/02/2024 | 0 | Resource Division | 0.66 | 0 | 0
1850 | Alipore Division | Canning Sub-division | Extension of pipe line for covered the uncovered FHTC area at Luxbagan Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000081/2022-2023 | 1130/AD | 26/05/2022 | 30 | MAA LAXMI ENTERPRISE | 18.44 | 0 | 100
1851 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sridharnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000157/2023-2024 | 679/AD | 17/05/2023 | 30 | M/S S.DAS ENTERPRISE | 11.79 | 0 | 0
1852 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Sridharnagar (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14986) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000362/2024-2025 | 2891/AD | 09/07/2024 | 90 | TANMAY ROY CHOWDHURY | 261.1 | 0 | 30
1853 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Sridharnagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000918/2023-2024 | 2971/AD | 26/09/2023 | 45 | ARBINA ENTERPRISE | 34.35 | 0 | 0
1854 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Sridharnagar PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001792/2022-2023 | 3958/AD | 12/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.64 | 0 | 95
1855 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sridharnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001963/2023-2024 | 397AD | 22/01/2024 | 45 | AQUATECH ENGINEERS | 49.26 | 0 | 100
1856 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sridharnagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002026/2022-2023 | 12993/AD | 23/03/2023 | 300 | TANMAY ROY CHOWDHURY | 296.12 | 0 | 30
1857 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sridharnagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 100 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002027/2022-2023 | 12994/AD | 23/03/2023 | 300 | TANMAY ROY CHOWDHURY | 290.89 | 0 | 30
1858 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sridharnagar Zone - I & II, Rakhalpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002106/2023-2024 | 928/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
1859 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sridharnagar Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002604/2023-2024 | 290/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1860 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sridharnagar (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002609/2023-2024 | 304/KSD | 08/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1861 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000446/2023-2024 | 4766/AD | 19/12/2023 | 0 | Resource Division | 38.86 | 0 | 0
1862 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000564/2023-2024 | 83/AD | 03/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
1863 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000762/2023-2024 | 596/AD | 29/01/2024 | 0 | Resource Division | 6.76 | 0 | 0
1864 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000963/2023-2024 | 1697/AD | 22/03/2024 | 0 | Resource Division | 11.88 | 0 | 0
1865 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Madhabnagar Zone-II W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000154/2023-2024 | 676/AD | 17/05/2023 | 30 | DEY ENTERPRISE (III) | 9.62 | 0 | 100
1866 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Madhabnagar Zone-II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000204/2023-2024 | 742/AD | 23/05/2023 | 635 | REALIENCE CONSTRUCTION | 507.58 | 0 | 40
1867 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhabnagar Zone-II W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000917/2023-2024 | 2970/AD | 26/09/2023 | 45 | AALOKRENU | 27.45 | 0 | 100
1868 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Madhabnagar Zone - II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001403/2022-2023 | 10333/AD | 25/01/2023 | 795 | A.K. SIKDAR | 61.73 | 0 | 75
1869 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar, Zone -II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001404/2022-2023 | 10334/AD | 25/01/2023 | 30 | A.S.A.CONSTRUCTION AND CONSULTANT | 16.68 | 0 | 0
1870 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar Zone -II Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =820] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001756/2022-2023 | 11756/AD | 21/02/2023 | 851 | DIPAK ROY | 156.91 | 0 | 70
1871 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhabnagar (Zone-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001781/2022-2023 | 11758/AD | 21/02/2023 | 45 | S. CHAKRABORTY AND CO. | 36.7 | 0 | 90
1872 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1873 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Madhabnagar (Zone-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002295/2023-2024 | 216/AD | 11/01/2024 | 30 | S. CHAKRABORTY AND CO. | 20.41 | 0 | 100
1874 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Indraprastha W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13804) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002528/2024-2025 | 813/AD | 27/02/2025 | 45 | CHANDA ENTERPRISE (KOLKATA) | 40.78 | 0 | 0
1875 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Madhabnagar Zone-II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002605/2023-2024 | 291/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1876 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000088/2023-2024 | 534AD | 12/05/2023 | 0 | Resource Division | 14.88 | 0 | 0
1877 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000521/2023-2024 | 4937/AD | 22/12/2023 | 0 | Resource Division | 22.61 | 0 | 0
1878 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000581/2023-2024 | 56/AD | 03/01/2024 | 0 | Resource Division | 2.57 | 0 | 0
1879 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000946/2023-2024 | 1680/AD | 22/03/2024 | 0 | Resource Division | 28.55 | 0 | 0
1880 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-I including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000076/2020-2021 | 5353/AD | 19/02/2021 | 365 | M/S. S.S. ENTERPRISE | 440.86 | 0 | 100
1881 | Alipore Division | Diamond Harbour Sub-Division | Laying of parallel distribution pipeline along Falta main road at Falta Zone-I under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001193/2021-2022 | 5710/AD. | 31/01/2022 | 60 | M/S. S.S. ENTERPRISE | 42.99 | 0 | 90
1882 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Basulat under Zone-I of Falta Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002022/2022-2023 | 12926/AD | 21/03/2023 | 690 | M/S. S.S. ENTERPRISE | 27.99 | 0 | 80
1883 | Alipore Division | Diamond Harbour Sub-Division | Augmentation in distribution system due to improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-I of Falta Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002023/2022-2023 | 12927/AD | 21/03/2023 | 660 | THE TOWER CONSTRUCTION | 30.5 | 0 | 50
1884 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000083/2023-2024 | 405/AD | 03/05/2023 | 0 | Resource Division | 29.8 | 0 | 0
1885 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000185/2023-2024 | 1276/AD | 05/07/2023 | 0 | Resource Division | 29.8 | 0 | 0
1886 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000225/2023-2024 | 2188/AD | 10/08/2023 | 0 | Resource Division | 1.38 | 0 | 0
1887 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000361/2023-2024 | 3225/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
1888 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Chandakhali to Dhapdhapi More 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01666/2024-2025 | BP-2024-25-773 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.74 | 0 | 0
1889 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA SRIPATINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000984/2022-2023 | 3669/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.43 | 0 | 100
1890 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002036/2023-2024 | 518/AD | 25/01/2024 | 45 | KALPANA TRADERS | 33.32 | 0 | 100
1891 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Sripatinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002037/2023-2024 | 519/AD | 25/01/2024 | 332 | B.P.R. CONSTRUCTION | 11.6 | 0 | 100
1892 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 150 cum. capacity OHR of Purba Sripatinagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002067/2023-2024 | 763(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1893 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
1894 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Sripatinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002392/2023-2024 | 1231/AD | 29/02/2024 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
1895 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000097/2023-2024 | 543/AD | 12/05/2023 | 0 | Resource Division | 8.12 | 0 | 0
1896 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000302/2023-2024 | 3097/AD | 28/09/2023 | 0 | Resource Division | 27.56 | 0 | 0
1897 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000677/2023-2024 | 443/AD | 24/01/2024 | 0 | Resource Division | 0.57 | 0 | 0
1898 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Amtali (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000099/2023-2024 | 468/AD | 08/05/2023 | 15 | KUNDU CONSTRUCTION CO. | 17.56 | 0 | 70
1899 | Alipore Division | Canning Sub-division | Construction of 100 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Piped W/S Scheme for Amtali (Zone-I) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 799] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000168/2023-2024 | 936/AD | 31/05/2023 | 900 | MAA LAXMI ENTERPRISE | 285.43 | 0 | 70
1900 | Alipore Division | Canning Sub-division | Construction of 150 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Piped W/S Scheme for Amtali (Zone-II) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1198] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000260/2023-2024 | 1448/AD | 13/07/2023 | 600 | ADARSH ENTERPRISES | 335.67 | 0 | 80
1901 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Amtali W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001114/2022-2023 | 12059/AD | 27/02/2023 | 30 | M/S SEKH ENTERPRISE | 21.98 | 0 | 0
1902 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Amtali W/S Scheme (Zone - II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001115/2022-2023 | 12060/AD | 27/02/2023 | 30 | M/S SEKH ENTERPRISE | 21.98 | 0 | 0
1903 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Amtali (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001240/2024-2025 | 5221/AD | 16/12/2024 | 45 | ADARSH ENTERPRISES | 36.01 | 0 | 0
1904 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Amtali (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001242/2024-2025 | 5223/AD | 16/12/2024 | 45 | MAA SANTOSHI ENTERPRISE | 31.9 | 0 | 0
1905 | Alipore Division | Canning Sub-division | Laying additional pipeline at Augmentation of Amtali (Zone-II) W/S Scheme, Block - Gosaba, under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001244/2024-2025 | 5242/AD | 17/12/2024 | 240 | NOVELTY CONSTRUCTION | 46.47 | 0 | 45
1906 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Amtali W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001399/2022-2023 | 10924/AD | 06/02/2023 | 45 | A 8 T CONSTRUCTION | 8.59 | 0 | 0
1907 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Amtali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001400/2022-2023 | 10925/AD | 06/02/2023 | 45 | A 8 T CONSTRUCTION | 8.59 | 0 | 0
1908 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Amtali (Zone-I & II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001891/2022-2023 | 12290/AD | 03/01/2023 | 45 | M/S R.DUTTA & CO. | 7.33 | 0 | 100
1909 | Alipore Division | Canning Sub-division | Relaying of HDPE pipe from H/O Dr. Amulya Mondal to Samshanghat at Amtali W/S Scheme (Zone-E), Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002158/2020-2021 | 1590/CSD | 23/02/2021 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 4.17 | 0 | 90
1910 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 3 of Augmentation of Amtali W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002546/2023-2024 | 1601/CSD | 28/02/2024 | 30 | DIPA ENTERPRISE | 1.84 | 0 | 100
1911 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000054/2023-2024 | 261/AD | 24/04/2023 | 0 | Resource Division | 110.06 | 0 | 0
1912 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Paschim Surendranagar Zone-I W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000166/2024-2025 | 2517/AD | 15/06/2024 | 30 | MUNNA AGROTECH ENTERPRISE | 20.39 | 0 | 100
1913 | Alipore Division | Kakdwip Sub-Division | Construction of 2 nos. 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone-I (Part - I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- I & II) [No. of FHTC = 160] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000348/2023-2024 | 1658/AD | 20/07/2023 | 300 | BHUWALKA DEVELOPMENTS PVT LTD. | 541.96 | 0 | 50
1914 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Augmentation of Paschim Surendranagar Zone I Part I & II W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000440/2024-2025 | 3075/AD | 25/07/2024 | 60 | CHHETRI ENTERPRISES | 74.62 | 0 | 0
1915 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Paschim Surendranagar Zone-I W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000522/2023-2024 | 350/KSD | 09/08/2023 | 558 | S.K.GOLUI | 2.73 | 0 | 100
1916 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-I (Part - I, II & III) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000927/2023-2024 | 273(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1917 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001203/2023-2024 | 4080/AD | 23/11/2023 | 45 | REZU CONSTRUCTION | 27.88 | 0 | 60
1918 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001204/2023-2024 | 4081/AD | 23/11/2023 | 495 | B.B. CONSTRUCTION | 9.38 | 0 | 100
1919 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001205/2023-2024 | 4082/AD | 23/11/2023 | 45 | BANGA NIRMAN | 27.91 | 0 | 0
1920 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-I (Part- I, II and III) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001206/2023-2024 | 4083/AD | 23/11/2023 | 30 | M/S A.K. ENTERPRISE | 9.7 | 0 | 50
1921 | Alipore Division | Kakdwip Sub-Division | Sinking of 04 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Paschim Surendranagar (Zone-I) (Part-I, II & III) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001275/2022-2023 | 9587/AD | 03/01/2023 | 90 | MUNNA AGROTECH ENTERPRISE | 77.16 | 0 | 100
1922 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Paschim Surendranagar (Zone-I) [Part-I, II & III] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001791/2022-2023 | 3186/AD | 15/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 9.15 | 0 | 95
1923 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone-I (Part - I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part- III) [No. of FHTC = 286] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002028/2022-2023 | 12995/AD | 23/03/2023 | 858 | DEEPAK ENTERPRISE | 248.99 | 0 | 40
1924 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 1st Tubewell site for Paschim Surendranagar Zone-I (Part-II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14124) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002096/2024-2025 | 1929/KSD | 20/12/2024 | 25 | AJMIR ENTERPRISE | 4.08 | 0 | 0
1925 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
1926 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone - I (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002603/2023-2024 | 273/KSD | 02/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1927 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-I (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002608/2023-2024 | 294/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
1928 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000456/2023-2024 | 4763/AD | 19/12/2023 | 0 | Resource Division | 84.68 | 0 | 0
1929 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000567/2023-2024 | 80/AD | 03/01/2024 | 0 | Resource Division | 2.65 | 0 | 0
1930 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000760/2023-2024 | 595/AD | 29/01/2024 | 0 | Resource Division | 3.71 | 0 | 0
1931 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000960/2023-2024 | 1694/AD | 22/03/2024 | 0 | Resource Division | 3.69 | 0 | 0
1932 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including providing of Functional Household Tap Connection (FHTC) with allied works in Zone-VIII of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 5302] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000372/2023-2024 | 1767/AD | 27/07/2023 | 720 | SPA ENTERPRISE | 1008.05 | 0 | 55
1933 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII of Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001026/2022-2023 | 308/DHSD | 23/09/2022 | 30 | GEO SOLUTION | 3.17 | 0 | 0
1934 | Alipore Division | Diamond Harbour Sub-Division | Additional balance Laying Distribution works under the Augmentation scheme of Zone-I at Diamond Harbour- II block for providing balance pipe lying works, including pipe carrying structure, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002491/2024-2025 | 782/AD | 25/02/2025 | 60 | K.P. CONSTRUCTION | 83.24 | 0 | 0
1935 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
1936 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000140/2022-2023 | 17/AD | 05/04/2023 | 0 | Resource Division | 34.48 | 0 | 0
1937 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000224/2023-2024 | 2207/AD | 10/08/2023 | 0 | Resource Division | 27.63 | 0 | 0
1938 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000429/2023-2024 | 3615/AD | 30/10/2023 | 0 | Resource Division | 0.92 | 0 | 0
1939 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000615/2023-2024 | 276/AD | 15/01/2024 | 0 | Resource Division | 31.72 | 0 | 0
1940 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000738/2023-2024 | 568/AD | 27/01/2024 | 0 | Resource Division | 9.72 | 0 | 0
1941 | Alipore Division | Canning Sub-division | Restoration of Kanthalberia Chunakhali Road block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01325/2024-2025 | BP-2024-25-625 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 60.02 | 0 | 0
1942 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali (Zone - I & II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000336/2023-2024 | 1553/AD | 17/07/2023 | 90 | TIYASHA ENTERPRISE | 140.12 | 0 | 80
1943 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials for each zone of Chunakhali (Zone - I & II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000339/2023-2024 | 3739/AD | 03/11/2023 | 725 | BUILDERS | 67.39 | 0 | 40
1944 | Alipore Division | Canning Sub-division | Protection of pipe line and inter connection in-between existing rising main and TW No. - 3 at Chunakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000995/2021-2022 | 990/CSD | 26/10/2021 | 30 | MODERN CONSTRUCTION | 3.14 | 0 | 54
1945 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using UPVC pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Chunakhali Water Supply Scheme (Zone-II) Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001575/2021-2022 | 6956/AD | 30/03/2022 | 30 | AQUATECH ENGINEER | 17.84 | 0 | 54
1946 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Chunakhali (Zone - I & II) W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.E. Dte. (Zon-II, TW-3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001682/2023-2024 | 1359/CSD | 19/12/2023 | 45 | S.K.GOLUI | 3.89 | 0 | 100
1947 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chunakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001709/2022-2023 | 11673/AD | 20/02/2023 | 45 | A.K. ENTERPRISE | 7.07 | 0 | 0
1948 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Chunakhali W/S Scheme (Zone-II), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001710/2022-2023 | 11674/AD | 20/02/2023 | 45 | A.K. ENTERPRISE | 7.07 | 0 | 0
1949 | Alipore Division | Canning Sub-division | Surging of 03 (three) nos. 250mm x 150mm. dia. 360 mtr. Deep Tubewell at Chunakhali W/S Scheme (Zone-II) TW-1, 2 & 3 under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001746/2020-2021 | 1448/CSD | 27/01/2021 | 15 | AQUATECH ENGINEER | 2.01 | 0 | 54
1950 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. Switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Chunakhali W/S Scheme, Block : Basanti under Canning Sub-Division of Alipore Division, PHE Dte.[Pump House-3] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/003185/2020-2021 | 322/AD | 08/06/2020 | 0 | M/S. MIHIR KUMAR NASKAR | 5.08 | 0 | 0
1951 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000113/2022-2023 | 245/AD | 24/04/2023 | 0 | Resource Division | 159.84 | 0 | 0
1952 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000398/2023-2024 | 356/AD | 19/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
1953 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000337/2023-2024 | 1939/AD | 02/08/2023 | 90 | KIRON CONSTRUCTION | 126.68 | 0 | 0
1954 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-V of Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000735/2023-2024 | 2896/AD | 19/09/2023 | 15 | SUPER CONSTRUCTION | 37.51 | 0 | 0
1955 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Budhkhali W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - VI) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000782/2024-2025 | 4483/AD | 11/11/2024 | 30 | B.K. ENTERPRISE. | 19.35 | 0 | 0
1956 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Budhkhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001666/2022-2023 | 11478/AD | 15/02/2023 | 30 | M.R.ENTERPRISE (II) | 19.52 | 0 | 0
1957 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Budhkhali W/S Scheme under JJM, Block - Canning - I under Canning Sub-Division under Alipore Division P.H.E. Dte. (TW-2) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001680/2023-2024 | 1357/CSD | 19/12/2023 | 30 | S.K.GOLUI | 2.85 | 0 | 100
1958 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001704/2022-2023 | 11668/AD | 20/02/2023 | 45 | BABAMONI CONSTRUCTION | 7.09 | 0 | 0
1959 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Budhkhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (TW No. 2 alternative Tubewell) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002377/2023-2024 | 1201/AD | 29/02/2024 | 30 | BHATTACHARJEE & CO. | 19.52 | 0 | 100
1960 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials at Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002551/2024-2025 | 1414/CSD | 10/12/2024 | 25 | ASHIS ENTERPRISE | 0.49 | 0 | 100
1961 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000071/2023-2024 | 272/AD | 24/04/2023 | 0 | Resource Division | 88.67 | 0 | 0
1962 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Adhia (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 955] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000029/2023-2024 | 157/AD | 18/04/2023 | 660 | M/S. MIHIR KUMAR NASKAR | 129.78 | 0 | 45
1963 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Adhia W/S Scheme (Part-B), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001764/2022-2023 | 12037/AD | 27/02/2023 | 675 | KRISHNA CONSTRUCTION | 7.06 | 0 | 100
1964 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Adhia (Part B) (Kakradaha) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001839/2022-2023 | 10938/AD | 06/03/2023 | 45 | TECH VISION | 3.88 | 0 | 0
1965 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
1966 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000726/2023-2024 | 548/AD | 25/01/2024 | 0 | Resource Division | 1.76 | 0 | 0
1967 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap Connection (FHTC) to all the households in Zone-XII of Mathurapur-I Block including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water based water supply scheme for Falta-Mathurapur, District-South 24-Parganas" under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2022-2023 | 1660/AD | 10/06/2022 | 120 | M/S. SUMAN ENTERPRISE | 236.89 | 0 | 95
1968 | Alipore Division | Raidighi Sub-Division | Laying of Rising Main (From 2nd Tube Well to Over Head Reservoir) and construction of valve chamber of piped water supply at Zone - XII of Mathurapur - I Block (Abad Bhagabanpur PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000248/2023-2024 | 185/RSD | 14/07/2023 | 30 | SUKUMAR HALDAR | 3.78 | 0 | 100
1969 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 1 and approach road and plinth protection including boundary wall at Abad Bhagabanpur W/S Scheme, modified as Zone- XII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001007/2023-2024 | 298/RSD | 29/09/2023 | 60 | M/S. GANGA ENTERPRISE | 4.08 | 0 | 100
1970 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Ramchandrapur) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001175/2023-2024 | 354/RSD | 21/11/2023 | 60 | S.S. ENTERPRISE (II) | 4.02 | 0 | 100
1971 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Satpukur, Rajarampur, Chakbhagabanpur, Nandapur) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001176/2023-2024 | 355/RSD | 21/11/2023 | 60 | M/S. SUMAN ENTERPRISE | 4.68 | 0 | 100
1972 | Alipore Division | Raidighi Sub-Division | Extension of pipelines to provide FHTC of Abad Bhagabanpur (Mouza - Gadberia) piped water supply Scheme at Zone- XII of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001177/2023-2024 | 356/RSD | 21/11/2023 | 60 | M/S B ENTERPRISE | 4.7 | 0 | 100
1973 | Alipore Division | Raidighi Sub-Division | Repair and renovation work for 250 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir at Abad Bhagabanpur W/S Scheme, modified as Zone- XII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001913/2023-2024 | 143/AD | 05/01/2024 | 45 | MAHALAXMI CONSTRUCTION | 16.13 | 0 | 98
1974 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XII, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001959/2022-2023 | 12713/AD | 14/03/2023 | 45 | ADITYA HAZRA | 83.94 | 0 | 65
1975 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000635/2023-2024 | 239/AD | 15/01/2024 | 0 | Resource Division | 4.07 | 0 | 0
1976 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- VIII of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000044/2023-2024 | 179/AD | 19/04/2023 | 60 | G.B. CONSTRUCTION & CO. | 100.29 | 0 | 25
1977 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Jatardeul Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000511/2020-2021 | 5196/AD | 12/02/2021 | 365 | G.B. CONSTRUCTION & CO. | 125.27 | 0 | 98
1978 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- VIII of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001043/2024-2025 | 4960/AD | 04/12/2024 | 60 | TIYASHA ENTERPRISE | 28.21 | 0 | 0
1979 | Alipore Division | Raidighi Sub-Division | Restoration of Pipeline (N.P. 70-71, 80-81) at Purba Jatardeul mouza under Purba Jatardeul Water supply Scheme of Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001770/2021-2022 | 628/RSD | 29/12/2021 | 15 | NITYANANDA MONDAL | 2 | 0 | 0
1980 | Alipore Division | Raidighi Sub-Division | Rejuvenation of distribution pipe line and other allied works to Providing Functional Household Tap Connection (FHTC) at Zone- VIII of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002274/2023-2024 | 481/RSD | 15/02/2024 | 60 | M/S KALPANA CONSTRUCTION | 2.4 | 0 | 98
1981 | Alipore Division | Raidighi Sub-Division | Rejuvenation of Functional Household Tap Connection (FHTC) at Zone - VIII (Purba Jatardule) of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002275/2023-2024 | 482/RSD | 15/02/2024 | 121 | G.B. CONSTRUCTION & CO. | 4.78 | 0 | 98
1982 | Alipore Division | Raidighi Sub-Division | Rejuvenation of Functional Household Tap Connection (FHTC) at Zone - VIII (Paschim Jatardule) of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002276/2023-2024 | 483/RSD | 15/02/2024 | 60 | G.B. CONSTRUCTION & CO. | 4.78 | 0 | 0
1983 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000661/2023-2024 | 265/AD | 15/01/2024 | 0 | Resource Division | 5.21 | 0 | 0
1984 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials from Head work site to PH-IV for Zone-I & Head work site to PH-IV for Zone-II of Bansra (Zone-I & II) W/S Scheme,Block-Canning-I under Canning Sub-Division of Alipore Division,PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000263/2023-2024 | 1451/AD | 13/07/2023 | 538 | M.N. ENTERPRISE | 139.79 | 0 | 95
1985 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bansra W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001705/2022-2023 | 11669/AD | 20/02/2023 | 45 | SAHANA ENTERPRISE | 7.06 | 0 | 0
1986 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bansra W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001706/2022-2023 | 11670/AD | 20/02/2023 | 45 | SAHANA ENTERPRISE | 7.05 | 0 | 0
1987 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 300mm x 200mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Bansra (Zone - I & II) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001812/2022-2023 | 12152/AD | 01/03/2023 | 45 | M.R.ENTERPRISE (II) | 49.69 | 0 | 0
1988 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (2000 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Bansra (Zone - I and II) Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001997/2022-2023 | 12811/AD | 16/03/2023 | 933 | RAMEN GHOSH | 95.95 | 0 | 70
1989 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000077/2023-2024 | 377/AD | 02/05/2023 | 0 | Resource Division | 151.98 | 0 | 0
1990 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000724/2023-2024 | 546/AD | 25/01/2024 | 0 | Resource Division | 65.17 | 0 | 0
1991 | Alipore Division | Canning Sub-division | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0
1992 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000110/2023-2024 | 508/AD | 11/05/2023 | 661 | SUPER CONSTRUCTION | 5.77 | 0 | 96
1993 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti (Zone-III and VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1767] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000257/2023-2024 | 1445/AD | 13/07/2023 | 60 | M/S SWAPAN KUMAR PRADHAN | 103.39 | 0 | 35
1994 | Alipore Division | Canning Sub-division | Laying distribution system for Augmentation of Basanti (Zone - III) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000258/2023-2024 | 1446/AD | 13/07/2023 | 60 | M/S SWAPAN KUMAR PRADHAN | 106.47 | 0 | 90
1995 | Alipore Division | Canning Sub-division | Construction of 200 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-III) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000396/2023-2024 | 1496/AD | 14/07/2023 | 300 | SUMAN MONDAL | 101.59 | 0 | 36
1996 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000494/2023-2024 | 1795/AD | 26/07/2023 | 45 | B.S.ENTERPRISE | 7.35 | 0 | 98
1997 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000495/2023-2024 | 1796/AD | 26/07/2023 | 45 | B.S.ENTERPRISE | 7.09 | 0 | 98
1998 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001790/2022-2023 | 12129/AD | 01/03/2023 | 45 | BHATTACHARJEE & CO. | 39.86 | 0 | 95
1999 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001894/2022-2023 | 11553/AD | 17/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 3 | 0 | 100
2000 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000023/2023-2024 | 229/AD | 24/04/2023 | 0 | Resource Division | 14.27 | 0 | 0
2001 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000152/2023-2024 | 1045/AD | 15/06/2023 | 0 | Resource Division | 5.03 | 0 | 0
2002 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
2003 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000731/2023-2024 | 2892/AD | 19/09/2023 | 15 | SURYA ENTERPRISE | 9.53 | 0 | 97
2004 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
2005 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-IV) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001869/2022-2023 | 12522/AD | 10/03/2023 | 60 | G.B. CONSTRUCTION (TW) | 59.73 | 0 | 100
2006 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001934/2022-2023 | 11806/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.33 | 0 | 99
2007 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001990/2022-2023 | 12681/AD | 14/03/2023 | 45 | GOUTAM HALDAR (I) | 7.36 | 0 | 98
2008 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001991/2022-2023 | 12682/AD | 14/03/2023 | 45 | GOUTAM HALDAR (I) | 7.11 | 0 | 99
2009 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001992/2022-2023 | 12683/AD | 14/03/2023 | 90 | NATH CONSTRUCTION | 7.08 | 0 | 98
2010 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000024/2023-2024 | 230/AD | 24/04/2023 | 0 | Resource Division | 32.96 | 0 | 0
2011 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000153/2023-2024 | 1057/AD | 15/06/2023 | 0 | Resource Division | 9.36 | 0 | 0
2012 | Alipore Division | Baruipur Sub-Division | Road restoration of WB02526, L022- Dhosa to Dhosa Chandaneswar irrigation road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01780/2024-2025 | BP-2024-25-805 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 8.36 | 0 | 0
2013 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Durgapur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000024/2022-2023 | 13065/AD | 24/03/2023 | 691 | AQUATECH ENGINEERS | 36.6 | 0 | 100
2014 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Ramnagarabad and Dakshin Durgapur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/16759 and 16758) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000329/2024-2025 | 2732/AD | 25/06/2024 | 494 | M/S B. ENTERPRISE | 318.12 | 0 | 25
2015 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. (1 no.) and 300 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 450] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000765/2023-2024 | 2911/AD | 20/09/2023 | 300 | M/S B. ENTERPRISE | 547.29 | 0 | 25
2016 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dakshin Durgapur and Ramnagar Abad Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1192] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001214/2023-2024 | 3818/AD | 07/11/2023 | 90 | M/S B. ENTERPRISE | 377.97 | 0 | 30
2017 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Digambarpur, Indranarayanpur, Dakshin Durgapur, Ramnagar Abad, Gurudaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002102/2023-2024 | 926/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.79 | 0 | 100
2018 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Durgapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002159/2023-2024 | 804/AD | 05/02/2024 | 60 | M/S. SIKHA ENTERPRISE | 27.47 | 0 | 0
2019 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Durgapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002160/2023-2024 | 805/AD | 05/02/2024 | 30 | SANKAR HALDER | 9.55 | 0 | 0
2020 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Durgapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002623/2023-2024 | 880/KSD | 15/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
2021 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000481/2023-2024 | 4756/AD | 19/12/2023 | 0 | Resource Division | 46.54 | 0 | 0
2022 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000560/2023-2024 | 48/AD | 03/01/2024 | 0 | Resource Division | 14.52 | 0 | 0
2023 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Harekrishnapur W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000238/2023-2024 | 1390/AD | 12/07/2023 | 15 | SUPER CONSTRUCTION | 23.7 | 0 | 80
2024 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000286/2023-2024 | 1539/AD | 17/07/2023 | 45 | RINAS INFRASTRUCTURE | 7.08 | 0 | 0
2025 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000288/2023-2024 | 1540/AD | 17/07/2023 | 45 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0
2026 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Harekrishnapur W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-IV] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000290/2023-2024 | 1541/AD | 17/07/2023 | 45 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0
2027 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Harekrishnapur, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2343] | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000315/2023-2024 | 1516/AD | 15/07/2023 | 90 | M/S SHIBAM ENTERPRISE | 405.58 | 0 | 40
2028 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Harekrishnapur Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002447/2023-2024 | 1513/AD | 13/03/2024 | 45 | M/S APEX ENGINEERING | 7.15 | 0 | 100
2029 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
2030 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000003/2023-2024 | 120/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
2031 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000031/2023-2024 | 235/AD | 24/04/2023 | 0 | Resource Division | 109.7 | 0 | 0
2032 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000140/2023-2024 | 852/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
2033 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kumirmari (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000239/2023-2024 | 1391/AD | 12/07/2023 | 15 | SWASTIK CONSTRUCTION | 29.2 | 0 | 0
2034 | Alipore Division | Canning Sub-division | Construction of OHR (400 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KUMIRMARI (ZONE-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000309/2023-2024 | 3737/AD | 03/11/2023 | 515 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 780.29 | 0 | 64
2035 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kumirmari W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000560/2023-2024 | 1804/AD | 26/07/2023 | 45 | GANGA TUBEWELL AND HARDWARE | 8.57 | 0 | 0
2036 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kumirmari (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000608/2023-2024 | 1830/AD | 27/07/2023 | 45 | TECH VISION | 8.1 | 0 | 98
2037 | Alipore Division | Canning Sub-division | Name of Work : Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumirmari (Zone - I) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000644/2023-2024 | 1833/AD | 27/07/2023 | 30 | M/S SEKH ENTERPRISE | 21.99 | 0 | 0
2038 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Kumirmari (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000693/2024-2025 | 4298/AD | 29/10/2024 | 60 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 97.98 | 0 | 0
2039 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 2 of Augmentation of Kumirmari W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001677/2023-2024 | 1349/CSD | 18/12/2023 | 30 | SHRESTHA | 2.33 | 0 | 100
2040 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000055/2023-2024 | 262/AD | 24/04/2023 | 0 | Resource Division | 45.19 | 0 | 0
2041 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000417/2023-2024 | 372/AD | 19/01/2024 | 0 | Resource Division | 18.25 | 0 | 0
2042 | Alipore Division | Canning Sub-division | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Kaparpuri & Adjoining Mouzas (Jalghata), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000336/2024-2025 | 2770/AD | 28/06/2024 | 90 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 126.53 | 0 | 0
2043 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Kaparpuri & Adjoining Mouzas (Jalghata) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000346/2024-2025 | 2787/AD | 01/07/2024 | 241 | AQUATECH ENGINEER | 34.45 | 0 | 100
2044 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for the Augmentation of Kaparpuri & Adjoining Mouzas (Jalghata) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ Pump House No. - I] | Assistant Engineer, Canning sub division |  | ORD/002390/2023-2024 | 1213/AD | 29/02/2024 | 407 | J H L CONSTRUCTION | 6.9 | 0 | 100
2045 | Alipore Division | Diamond Harbour Sub-Division | Construction of Boundary Wall at proposed OHR site of Moukhali Water Supply Scheme (Block: Budge Budge-I) under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000516/2022-2023 | 5537/AD | 29/09/2022 | 45 | M/S. S.S. ENTERPRISE | 16.2 | 0 | 98
2046 | Alipore Division | Diamond Harbour Sub-Division | Construction of Chlorination Room at proposed OHR Site of Moukhali W/S Scheme, Block: Budge Budge-I under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000520/2022-2023 | 5507/AD | 29/09/2022 | 45 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 5.46 | 0 | 10
2047 | Alipore Division | Diamond Harbour Sub-Division | Construction of 350 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap within Moukhali W/S Scheme of Budge Budge - I Block under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. (SM/18867) | Assistant Engineer, Diamond Harbour sub division |  | ORD/000604/2024-2025 | 4098/AD | 03/10/2024 | 540 | M.M. ENTERPRISE | 144.41 | 0 | 10
2048 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000252/2023-2024 | 3044/AD | 28/09/2023 | 0 | Resource Division | 77.51 | 0 | 0
2049 | Alipore Division | Raidighi Sub-Division | Providing FHTC at Zone- VI of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC =4922 nos) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000121/2023-2024 | 592/AD | 15/05/2023 | 90 | M/S. JHARNA ENTERPRISE | 272.12 | 0 | 0
2050 | Alipore Division | Raidighi Sub-Division | Construction of 900 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing & specification including R.C.C. Bored Pile & Pile Cap upto pedestal and laying distribution system of piped water supply at Mathurapur - II Block (Zone-VI) for " MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, SOUTH 24 PARGANAS" under Raidighi Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000601/2021-2022 | 3459/AD | 18/11/2021 | 1460 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 501.72 | 0 | 20
2051 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000243/2023-2024 | 2915/AD | 20/09/2023 | 0 | Resource Division | 336.38 | 0 | 0
2052 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000650/2023-2024 | 253/AD | 15/01/2024 | 0 | Resource Division | 9.1 | 0 | 0
2053 | Alipore Division | Raidighi Sub-Division | Construction of 700 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- VII, Mathurapur-II Block (Part-A) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000481/2023-2024 | 1994/AD | 04/08/2023 | 606 | MATRI ENTERPRISE | 1265.16 | 0 | 30
2054 | Alipore Division | Raidighi Sub-Division | Construction of 700 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- VII, Mathurapur-II Block (Part-B) for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000670/2023-2024 | 1709/AD | 22/07/2023 | 600 | M/S GHOSH & CO. | 1194.19 | 0 | 30
2055 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 700 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone-VIIA, Mathurapur- II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001049/2023-2024 | 338/RSD | 30/10/2023 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2056 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000247/2023-2024 | 3104/AD | 28/09/2023 | 0 | Resource Division | 342.8 | 0 | 0
2057 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Srinarayanpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13570) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000344/2024-2025 | 2756/AD | 27/06/2024 | 60 | BIMALENDU GIRI | 116.4 | 0 | 0
2058 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Srinarayanpur (Part-I) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000547/2024-2025 | 3776/AD | 18/09/2024 | 60 | MOSTAFIZUR HAQUE GAINE | 73.31 | 0 | 0
2059 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Srinarayanpur (Part-I) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000636/2023-2024 | 2464/AD | 24/08/2023 | 60 | ISHAN CONSTRUCTION | 35.53 | 0 | 100
2060 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Srinarayanpur (Part-III) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000637/2023-2024 | 2465/AD | 24/08/2023 | 90 | CHANCHAL ENTERPRISE & CO. | 78.12 | 0 | 40
2061 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinarayanpur (Part-I) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000779/2022-2023 | 6650/AD | 14/11/2022 | 45 | M/S. DATTA ENTERPRISE | 36.67 | 0 | 100
2062 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinarayanpur (Part-III) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000780/2022-2023 | 6651/AD | 14/11/2022 | 45 | MONDAL & CO. | 36.67 | 0 | 100
2063 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinarayanpur (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000944/2023-2024 | 282(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2064 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinarayanpur (Part - I, II & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000966/2023-2024 | 289(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2065 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme [SRINARAYANPUR (PART I,II & III PWSS)] including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001041/2022-2023 | 32/AD | 04/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 11.81 | 0 | 100
2066 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinarayanpur (Paer-I, II, II) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001063/2023-2024 | 3381/AD | 11/10/2023 | 45 | M/S SUNITY ENTERPRISE | 27.67 | 0 | 100
2067 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Srinarayanpur (Paer-I, II, II) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001064/2023-2024 | 3382/AD | 11/10/2023 | 30 | M/S MODINA ENTERPRISE | 9.49 | 0 | 100
2068 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Srinarayanpur (Part-I, II, III) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001065/2023-2024 | 3383/AD | 11/10/2023 | 659 | M/S. SONAMONI ENTERPRISE | 9.53 | 0 | 100
2069 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinarayanpur (Part-I, II, III) W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001213/2023-2024 | 3870/AD | 09/11/2023 | 45 | KIRAN ENTERPRISES | 27.71 | 0 | 50
2070 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001317/2022-2023 | 9882/AD | 10/01/2023 | 300 | MAHMOOD ASSOCIATES PVT LTD | 326.43 | 0 | 25
2071 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 02 nos. pump house, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001318/2022-2023 | 9883/AD | 10/01/2023 | 300 | KAMIRUL SK AND CO. | 309.53 | 0 | 30
2072 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 02 nos. pump house, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinarayanpur (Part I, II & III) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001746/2022-2023 | 11555/AD | 17/02/2023 | 300 | SUPRITI ENTERPRISE | 309.39 | 0 | 30
2073 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
2074 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Srinarayanpur (Part - I, II & III) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-III) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002234/2023-2024 | 720/KSD | 01/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
2075 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000316/2023-2024 | 3125/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2076 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000461/2023-2024 | 4762/AD | 19/12/2023 | 0 | Resource Division | 58.24 | 0 | 0
2077 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000572/2023-2024 | 75/AD | 03/01/2024 | 0 | Resource Division | 3.98 | 0 | 0
2078 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000742/2023-2024 | 577/AD | 29/01/2024 | 0 | Resource Division | 2.84 | 0 | 0
2079 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000959/2023-2024 | 1693/AD | 22/03/2024 | 0 | Resource Division | 29.77 | 0 | 0
2080 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haripur (Zone-I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000531/2023-2024 | 2144/AD | 09/08/2023 | 875 | MALLICK ENTERPRISE | 286.52 | 0 | 80
2081 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 (two) Nos. 250mm x 150mm dia. 390 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JJM of Haripur (Zone-II) W/S Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000575/2023-2024 | 2261/AD | 14/08/2023 | 45 | AQUATECH ENGINEERS | 39.53 | 0 | 100
2082 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Haripur (Zone - I & II)) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000642/2023-2024 | 2034/AD | 05/08/2023 | 45 | M/S R.DUTTA & CO. | 7.87 | 0 | 100
2083 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC (Retrofitting) of Haripur (Zone- I and II) W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub Division of Alipore Division, PHED. (Zone-II) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002125/2023-2024 | 817/AD | 05/02/2024 | 45 | ASHIS ENTERPRISE | 40.55 | 0 | 50
2084 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC of Haripur (Zone- I and II) W/S Scheme under JJM, Block - Namkhana under Kakdwip Sub Division of Alipore Division, PHED. (Zone-II) (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002127/2023-2024 | 818/AD | 05/02/2024 | 45 | JOY GURU TRADING | 43.99 | 0 | 0
2085 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dakshin Chandranagar, Haripur Zone - I & II, Amarabati PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002131/2023-2024 | 937/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
2086 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Haripur (Zone - I and II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/18698) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002133/2023-2024 | 821/AD | 05/02/2024 | 30 | MEGA SOLAR ENERGY | 19.93 | 0 | 100
2087 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Haripur (Zone - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002232/2023-2024 | 718/KSD | 01/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
2088 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000490/2023-2024 | 4789/AD | 19/12/2023 | 0 | Resource Division | 29.51 | 0 | 0
2089 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000550/2023-2024 | 33/AD | 02/01/2024 | 0 | Resource Division | 2.97 | 0 | 0
2090 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000791/2023-2024 | 636/AD | 30/01/2024 | 0 | Resource Division | 4.68 | 0 | 0
2091 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Kshetra Mohanpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (SM/18673) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000398/2024-2025 | 3181/AD | 31/07/2024 | 60 | CHAKRABORTTI ENTERPRISE | 54.18 | 0 | 0
2092 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) [No. of FHTC = 350] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000534/2023-2024 | 2147/AD | 09/08/2023 | 895 | RELIABLE CONSTRUCTIONS | 169.85 | 0 | 20
2093 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) (Part-B) [No. of FHTC = 800] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000535/2023-2024 | 2148/AD | 09/08/2023 | 797 | RELIABLE CONSTRUCTIONS | 169.24 | 0 | 55
2094 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-B) [No. of FHTC = 455] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000536/2023-2024 | 3738/AD | 03/11/2023 | 537 | CHAKRABORTTI ENTERPRISE | 128.72 | 0 | 50
2095 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kshetra Mohanpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 350] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000542/2023-2024 | 3729/AD | 03/11/2023 | 880 | CHAKRABORTTI ENTERPRISE | 168.05 | 0 | 20
2096 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kshetra Mohanpur (Zone-I & II)W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000554/2023-2024 | 2236/AD | 11/08/2023 | 45 | GOLDEN GROUPS | 49.2 | 0 | 90
2097 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kshetra Mohanpur (Zone - I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000555/2023-2024 | 2237/AD | 11/08/2023 | 407 | GOLDEN GROUPS | 49.2 | 0 | 100
2098 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Kshetra mohanpur (Zone - I & II)PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000639/2023-2024 | 2032/AD | 05/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 8.71 | 0 | 100
2099 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kshetramohanpur Zone - I & II, Brojoballavpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002112/2023-2024 | 932/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
2100 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kshetra Mohanpur (Zone - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-I) (SM/18673) | Assistant Engineer, Kakdwip Sub Division |  | ORD/003207/2023-2024 | 160/KSD | 05/01/2024 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
2101 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000109/2023-2024 | 645/AD | 17/05/2023 | 0 | Resource Division | 10.74 | 0 | 0
2102 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000487/2023-2024 | 4753/AD | 19/12/2023 | 0 | Resource Division | 52.84 | 0 | 0
2103 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000766/2023-2024 | 600/AD | 29/01/2024 | 0 | Resource Division | 4.05 | 0 | 0
2104 | Alipore Division | Diamond Harbour Sub-Division | Laying of pipeline as per revised laying distribution system due to shifting of OHR site under the Augmentation Scheme of Kulpi Zone-VI for providing 100% FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18554] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000446/2024-2025 | 3323/AD | 12/08/2024 | 90 | MAHMOOD ASSOCIATES PVT LTD | 150.13 | 0 | 30
2105 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VI at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-7276] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000477/2023-2024 | 2485/AD | 25/08/2023 | 676 | MAHMOOD ASSOCIATES PVT LTD | 1473.09 | 0 | 16
2106 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Gobindapur under Zone- VI of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000505/2023-2024 | 1802/AD | 26/07/2023 | 30 | S.S.TRADERS | 24.17 | 0 | 75
2107 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VI of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001018/2022-2023 | 291/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 3.6 | 0 | 98
2108 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at Pump House no 1 under Dhola PWSS under Zone- VI of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001371/2024-2025 | 5500/AD | 27/12/2024 | 45 | M/S SEIKH ENTERPRISE | 25.16 | 0 | 0
2109 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline under the Augmentation Scheme of Zone-VI at Kulpi Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18554] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001606/2024-2025 | 125/AD | 09/01/2025 | 75 | PINKI CONSTRUCTION | 132.51 | 0 | 0
2110 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VI (Gobindapur, OHR Size-1000 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002098/2022-2023 | 334/DHSD | 14/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2111 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system by 150 mm dia. HDPE pipe from Pump House No- 1 to Beluni more of Dhola PWSS under Zone-VI of Kulpi Block within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002113/2023-2024 | 825/AD | 05/02/2024 | 364 | M/S.SREEJIT ENTERPRISE | 24.24 | 0 | 100
2112 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000005/2024-2025 | 5159/AD | 12/12/2024 | 0 | Resource Division | 61.6 | 0 | 0
2113 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000208/2023-2024 | 2018/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
2114 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000631/2023-2024 | 290/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
2115 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000861/2023-2024 | 768/AD | 03/02/2024 | 0 | Resource Division | 35.58 | 0 | 0
2116 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000936/2023-2024 | 1278/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2117 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including Construction of 1 no. 250cum capcity OHR and 01 no 400 cum capacity OHR to extend the benefit 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Mangarajpur & Zone-V at Atkrishnarampur of Diamond harbour - I block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000487/2023-2024 | 4927/AD | 22/12/2023 | 831 | PRASUN ENTERPRISE | 972.76 | 0 | 10
2118 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-V of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001049/2022-2023 | 300/DHSD | 15/09/2022 | 30 | MEASURE LAND | 2.83 | 0 | 0
2119 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-V (Atkrishnarampur, OHR Size-400 ) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002089/2022-2023 | 323/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2120 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000130/2022-2023 | 30/AD | 05/04/2023 | 0 | Resource Division | 8.21 | 0 | 0
2121 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000234/2023-2024 | 2195/AD | 10/08/2023 | 0 | Resource Division | 4.64 | 0 | 0
2122 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000343/2023-2024 | 3207/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2123 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000607/2023-2024 | 269/AD | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
2124 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000667/2023-2024 | 420/AD | 22/01/2024 | 0 | Resource Division | 8.26 | 0 | 0
2125 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000887/2023-2024 | 741/AD | 03/02/2024 | 0 | Resource Division | 1.59 | 0 | 0
2126 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000914/2023-2024 | 1256/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2127 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for providing FHTC damaged due to upgradation of Road for Chandipur Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001484/2021-2022 | 6394/AD | 02/03/2022 | 30 | M/S RAKESH ENTERPRISE | 37.72 | 0 | 93
2128 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000833/2023-2024 | 678/AD | 30/01/2024 | 0 | Resource Division | 5.35 | 0 | 0
2129 | Alipore Division |  | Extension distribution system (at Node no. 11) in Zone-X of Mathurapur - II Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000245/2022-2023 | 78/RSD | 18/05/2022 | 60 | BANGA NIRMAN | 4.81 | 0 | 0
2130 | Alipore Division |  | Day to day annual operation and maintenance of Over Head Reservoir, rising main & Distribution System (CI/DI/AC/UPVC of pipeline) of Nandakumarpur (Zone - I) W/S Scheme under Raidighi Sub-Division of Alipore Division P.H.E. Dte. [From 15.12.2021 to 14.12.2022] |  |  | ORD/001187/2021-2022 | 557/RSD | 14/12/2021 | 365 | M/S A.R. CONSTRUCTION | 4.47 | 0 | 100
2131 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Bhuiner Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001234/2020-2021 | 566/RSD | 30/12/2020 | 60 | M/S B.M. CONSTRUCTION | 4.47 | 4.47 | 0
2132 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Janar Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001236/2020-2021 | 568/RSD | 30/12/2020 | 60 | M/S B.M. CONSTRUCTION | 4.48 | 4.47 | 0
2133 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Manager Gheri (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001237/2020-2021 | 569/RSD | 30/12/2020 | 60 | M/S. M.M. ENTERPRISE | 4.51 | 4.51 | 0
2134 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Kailaspur at Habitation - Manger Gheri Purba (Part-A) in Nandakumarpur - II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001238/2020-2021 | 570/RSD | 30/12/2020 | 60 | M/S. M.M. ENTERPRISE | 4.47 | 4.3 | 0
2135 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-I) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001333/2020-2021 | 2222/AD | 08/10/2020 | 365 | SUKALPA NIRMAN | 70.74 | 0 | 100
2136 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 365 | UNITED BUILDERS | 108.61 | 18.44 | 100
2137 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj Majhi para, Mondal para of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000398/2020-2021 | 771/KSD | 14/10/2020 | 45 | BHUNIA BUILDERS | 2.92 | 0 | 0
2138 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj (part), Debimathurapur (part) and Barui Para of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000399/2020-2021 | 772/KSD | 14/10/2020 | 45 | M/S MODINA ENTERPRISE | 4.79 | 4.77 | 0
2139 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj(part), Jana Para, Khan Para and Gobindapur(Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000402/2020-2021 | 773/KSD | 14/10/2020 | 45 | KHOKAN MONDAL | 4.78 | 4.74 | 0
2140 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj Patra Para & Debimathurapur (Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000414/2020-2021 | 790/KSD | 15/10/2020 | 45 | M/S KALIPADA JANA | 3.18 | 2.95 | 0
2141 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Nagendraganj (Part) & Gobindapur (Part) of Nagendraganj W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000415/2020-2021 | 791/KSD | 15/10/2020 | 45 | JOY ENGINEERING & CONSTRUCTION | 3.74 | 0 | 80
2142 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Chokirdar Para & Bar Para of Nagendraganj W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000416/2020-2021 | 792/KSD | 15/10/2020 | 45 | M/S. BRINDABAN DAS & SONS | 3.34 | 0 | 95
2143 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 245 to 246, 245 to 250, 254 to 255 & 255 to 256 of Nagendraganj W/S Scheme under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000431/2020-2021 | 817/KSD | 16/10/2020 | 45 | M/S MODINA ENTERPRISE | 4.59 | 0 | 80
2144 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 256 to 258, 258 to 259, 259 to 260 260 to 261, 261 to 262, 262 to 263 & 263 to 264 of Nagendraganj W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000432/2020-2021 | 818/KSD | 16/10/2020 | 45 | SUDIP PRADHAN | 3.42 | 0 | 100
2145 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC Pipe Line for Retrofitting of FHTC from Node Point 11 to 104, 20 to 21, 21 to 23 & 20 to 42 of Nagendraganj W/S Scheme under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000470/2020-2021 | 1048/KSD | 19/12/2020 | 20 | M/S. JOYGURU ENTERPRISE | 4.45 | 0 | 100
2146 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000332/2023-2024 | 3147/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2147 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000701/2023-2024 | 471/AD | 24/01/2024 | 0 | Resource Division | 5.71 | 0 | 0
2148 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Nagendraganj W/S Scheme (Phase-A), Dhaspara W/S Scheme (Phase-A), Shibpur W/S Scheme (Phase-A) & Bishnupur W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 518/KSD, 24.08.21, T.No. 1792/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | VCH/002607/2021-2022 | BP-2021-22-510 | 22/03/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 4.7 | 0 | 0
2149 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Chaplarkhop Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000512/2020-2021 | 5127/AD | 08/02/2021 | 365 | M/S. DAS BUILDERS | 53.21 | 0 | 96
2150 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-D) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000558/2021-2022 | 492/RSD | 04/10/2021 | 60 | M/S R.K.ENTERPRISE | 4.8 | 0 | 100
2151 | Alipore Division | Raidighi Sub-Division | Remodeling of pipeline at (Node point - 21-23,23-25,25-26,26-28,28-156,156-158,26-27,28-29,156-157,158-159,30-31,160-161,162-163,63-64) of Chaplarkhop W/S Scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001035/2021-2022 | 539/RSD | 30/11/2021 | 60 | SWASTIK ENTERPRISE (NEW) | 4.8 | 0 | 100
2152 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Jogendra Nagar at Habitation - Jogendra Nagara (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001229/2020-2021 | 564/RSD | 30/12/2020 | 60 | SANKAR HALDER | 4.82 | 0 | 100
2153 | Alipore Division | Raidighi Sub-Division | Inter connection between OHR and Distrubtion system with supply of Specials, Laying HDPE pipe, Restoration at Zone - XIII water supply scheme of Mathurapur - II Block (Chaplarkhop PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002230/2023-2024 | 922/AD | 08/02/2024 | 30 | SUKUMAR HALDAR | 7.81 | 0 | 0
2154 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-C) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002363/2020-2021 | 735/RSD | 12/02/2021 | 60 | SWASTIK ENTERPRISE (NEW) | 4.82 | 0 | 100
2155 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Jogendra Nagar at Habitation - Jogendra Nagara (Part-B) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002364/2020-2021 | 736/RSD | 12/02/2021 | 60 | M.S. ENTERPRISE | 4.82 | 0 | 100
2156 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000658/2023-2024 | 262/AD | 15/01/2024 | 0 | Resource Division | 5.36 | 0 | 0
2157 | Alipore Division |  | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to the households under Banshtala Baragheri mouza (JL No. 114) & partly Ghatbakultala mouza (JL No. 116) in Mathurapur-I block, Zone-XIII under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/000391/2022-2023 | 4484/AD | 31/08/2022 | 30 | M/S. L.P. CONSTRUCTION | 28.94 | 0 | 100
2158 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-D) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/000558/2021-2022 | 492/RSD | 04/10/2021 | 60 | M/S R.K.ENTERPRISE | 4.8 | 0 | 100
2159 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-E) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block- Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte |  |  | ORD/000607/2021-2022 | 528/RSD | 18/11/2021 | 60 | L.N. ENTERPRISE | 4.77 | 0 | 100
2160 | Alipore Division |  | Restoration of distribution system of Ghatbakultala W/S scheme (near Ashokenagar-Jgendranagar) at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000635/2022-2023 | 96/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 4.76 | 0 | 100
2161 | Alipore Division |  | Restoration of distribution system near node no. 139 of Zone-XIII Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000636/2022-2023 | 97/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 4.75 | 0 | 100
2162 | Alipore Division |  | Restoration of distribution system near jogendranagar more to provide FHTC at Ghatbakultala W/S scheme at Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000637/2022-2023 | 98/RSD | 07/06/2022 | 30 | R.G. ENTERPRISE (I) | 3.42 | 0 | 100
2163 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-F) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/001155/2021-2022 | 569/RSD | 15/12/2021 | 60 | S.P. CONSTRUCTION (II) | 4.77 | 0 | 100
2164 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-A) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/001307/2020-2021 | 562/RSD | 30/12/2020 | 60 | M/S KALPANA CONSTRUCTION | 4.82 | 0 | 100
2165 | Alipore Division |  | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala (Node No. 27-25-22-16-15-13) under Ghatbakultala water supply scheme ( Zone-XIII of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001582/2021-2022 | 711/RSD | 02/03/2022 | 60 | N.B.N CONSTRUCTION | 4.76 | 0 | 100
2166 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Ghatbakultala at Habitation-Ghatbakultala (Part-G) in Ghatbakultala piped water supply scheme , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/001590/2021-2022 | 774/RSD | 28/03/2022 | 60 | M/S KALIPADA JANA | 4.75 | 0 | 100
2167 | Alipore Division |  | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Ghatbakultala water supply scheme (Zone-XIII of Mathurapur-I block for Mega Surface water based water supply scheme for Falta- Mathurapur, District South 24 parganas) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001768/2021-2022 | 626/RSD | 29/12/2021 | 15 | L.N. ENTERPRISE | 4.47 | 0 | 100
2168 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to households of Mouza - Ghatbakultala at Habitation - Ghat Bakul Tala (Part-B) in Ghatbakultala Water Supply Scheme, Block - Mathurapur-I, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/002357/2020-2021 | 734/RSD | 12/02/2021 | 60 | M/S. BISWAS CONSTRUCTION (II) | 4.82 | 0 | 100
2169 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 5661/AD | 27/01/2022 | 0 | Resource Division | 0.7 | 0 | 0
2170 | Alipore Division | Kakdwip Sub-Division | LAUNCH HIRE CHARGES FOR MAR'22 TO MAY'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/00681/2024-2025 | BP-2024-25-225 | 20/06/2024 | 0 | RAJKUMAR MANNA | 1.1 | 0 | 0
2171 | Alipore Division | Kakdwip Sub-Division | LAUNCH HIRE CHARGES FOR NOV'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/00683/2024-2025 | BP-2024-25-228 | 20/06/2024 | 0 | RAJKUMAR MANNA | 0.36 | 0 | 0
2172 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001188/2023-2024 | 555/DHSD | 31/10/2023 | 182 | GOPAL KUMAR JHA | 2.4 | 0 | 100
2173 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Koaberia Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001371/2020-2021 | 5128/AD | 08/02/2021 | 365 | M. CHAKRABORTY | 56.38 | 0 | 92
2174 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2175 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House and boundary wall at 1st Tubewell site for Koaberia W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07579) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002158/2024-2025 | 1986/KSD | 23/12/2024 | 25 | IMAGINEER VENTURES | 2.26 | 0 | 0
2176 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000276/2023-2024 | 3075/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2177 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000838/2023-2024 | 683/AD | 30/01/2024 | 0 | Resource Division | 6.6 | 0 | 0
2178 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 300] [SM/11847] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002288/2023-2024 | 1004/AD | 16/02/2024 | 240 | M/S. JHARNA ENTERPRISE | 172.02 | 0 | 10
2179 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000527/2023-2024 | 2142/AD | 09/08/2023 | 630 | PUTUL RANI MAITY | 217.06 | 0 | 97
2180 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Kalaria Water Supply Scheme Block - Canning - I, South 24 Parganas District under Canning Sub Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of Scheme for 01 (one) year | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001378/2020-2021 | 5132/AD | 08/02/2021 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS | 153.65 | 51.27 | 100
2181 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation and laying extension pipe line for providing FHTC for Srikrishnanagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000595/2022-2023 | 5920/AD | 19/10/2022 | 30 | L.N. ENTERPRISE | 15.68 | 0 | 95
2182 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Srikrishnanagar W/S Scheme, Block Kakdwip and Dakshin Shibganj W/S Scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001087/2021-2022 | 578/KSD | 10/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.24 | 0 | 100
2183 | Alipore Division | Kakdwip Sub-Division | Connection of Tubewell with distribution line of Head Work Site of Srikrishnanagar W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001173/2021-2022 | 761/KSD | 29/11/2021 | 20 | MANDAL ENTERPRISE (JOYNAGAR) | 0.44 | 0 | 95
2184 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000829/2023-2024 | 674/AD | 30/01/2024 | 0 | Resource Division | 7.15 | 0 | 0
2185 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Budhkhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000337/2023-2024 | 1939/AD | 02/08/2023 | 90 | KIRON CONSTRUCTION | 126.68 | 0 | 0
2186 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000611/2020-2021 | 850/CSD | 12/10/2020 | 45 | DIPA CHHETRI | 4.74 | 4.74 | 0
2187 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000614/2020-2021 | 853/CSD | 12/10/2020 | 45 | SUKANTA HALDER | 4.74 | 0 | 0
2188 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000616/2020-2021 | 855/CSD | 12/10/2020 | 45 | MODERN CONSTRUCTION | 4.74 | 0 | 0
2189 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000617/2020-2021 | 860/CSD | 12/10/2020 | 45 | C.S. CONSTRUCTION | 4.73 | 0 | 95
2190 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000618/2020-2021 | 861/CSD | 12/10/2020 | 45 | SARKAR CONSTRUCTION | 4.75 | 4.72 | 0
2191 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000619/2020-2021 | 862/CSD | 12/10/2020 | 45 | ARFIN CONSTRUCTION | 4.75 | 0 | 100
2192 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000620/2020-2021 | 863/CSD | 12/10/2020 | 45 | KUNDU CONSTRUCTION CO. | 4.74 | 4.72 | 0
2193 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000621/2020-2021 | 864/CSD | 12/10/2020 | 45 | GANGA TUBEWELL AND HARDWARE | 4.74 | 0 | 100
2194 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000622/2020-2021 | 865/CSD | 12/10/2020 | 45 | M/S. M.K. NASKAR & CONSTRUCTION | 4.73 | 0 | 100
2195 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000623/2020-2021 | 866/CSD | 12/10/2020 | 45 | M/S. MANABESH ROY | 4.74 | 4.74 | 0
2196 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000624/2020-2021 | 867/CSD | 12/10/2020 | 45 | ASHIS ENTERPRISE | 4.72 | 0 | 100
2197 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000625/2020-2021 | 868/CSD | 12/10/2020 | 45 | DEY ENTERPRISE (III) | 4.74 | 0 | 100
2198 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Kripa Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000630/2020-2021 | 869/CSD | 12/10/2020 | 45 | SAHANA ENTERPRISE | 4.74 | 0 | 100
2199 | Alipore Division | Canning Sub-division | Laying pipe line for FHTC work at Budhkhali W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000996/2021-2022 | 991/CSD | 26/10/2021 | 30 | MODERN CONSTRUCTION | 3.74 | 0 | 100
2200 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001455/2020-2021 | 1003/CSD | 13/11/2020 | 45 | MONCON INDIA | 4.7 | 4.7 | 100
2201 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001456/2020-2021 | 1005/CSD | 13/11/2020 | 45 | MODERN CONSTRUCTION | 4.74 | 0 | 100
2202 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001457/2020-2021 | 1006/CSD | 13/11/2020 | 45 | SOURAV NASKAR | 4.79 | 0 | 100
2203 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001466/2020-2021 | 1018/CSD | 23/11/2020 | 45 | SUKANTA HALDER | 4.71 | 0 | 100
2204 | Alipore Division | Canning Sub-division | Extension of pipeline for FHTC work of Budhkhali Piped Water Supply Scheme Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001468/2021-2022 | 1490/CSD | 09/02/2022 | 20 | MITRA ASSOCIATE | 4.6 | 0 | 100
2205 | Alipore Division | Canning Sub-division | Repairing & relaying of damaged pipeline for FHTC work of Budhkhali Piped Water Supply Scheme Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001469/2021-2022 | 1491/CSD | 09/02/2022 | 20 | ASHIS ENTERPRISE | 4.56 | 0 | 100
2206 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001470/2020-2021 | 1019/CSD | 23/11/2020 | 45 | A.S.A.CONSTRUCTION AND CONSULTANT | 4.77 | 0 | 100
2207 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001471/2020-2021 | 1020/CSD | 23/11/2020 | 45 | RAKTIM ENTERPRISE | 4.69 | 0 | 100
2208 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001472/2020-2021 | 1021/CSD | 23/11/2020 | 45 | M/S TAMAL CHAKRABORTY | 4.72 | 0 | 0
2209 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - X) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001473/2020-2021 | 1022/CSD | 23/11/2020 | 45 | M/S. PROMILA CONSTRUCTION | 4.62 | 0 | 0
2210 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001474/2020-2021 | 1023/CSD | 23/11/2020 | 45 | R.G. ENTERPRISE (I) | 4.78 | 0 | 0
2211 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001475/2020-2021 | 1029/CSD | 24/11/2020 | 45 | BANERJEE ENTERPRISE | 4.73 | 0 | 0
2212 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Gola Bari of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001476/2020-2021 | 1030/CSD | 24/11/2020 | 45 | MODERN CONSTRUCTION | 4.7 | 0 | 100
2213 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001477/2020-2021 | 1031/CSD | 24/11/2020 | 45 | GANGA TUBEWELL AND HARDWARE | 4.79 | 0 | 100
2214 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001478/2020-2021 | 1032/CSD | 24/11/2020 | 45 | ASHIS ENTERPRISE | 4.72 | 0 | 100
2215 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001479/2020-2021 | 1033/CSD | 24/11/2020 | 45 | GANGA TUBEWELL AND HARDWARE | 4.69 | 0 | 100
2216 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Modhu Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001480/2020-2021 | 1034/CSD | 24/11/2020 | 45 | S.C. ENTERPRISE (I) | 4.66 | 0 | 100
2217 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001506/2020-2021 | 1004/CSD | 13/11/2020 | 45 | M/S KRISHNA MONDAL | 4.75 | 4.74 | 100
2218 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001556/2020-2021 | 1211/CSD | 15/12/2020 | 45 | M/S M3 SOLUTION | 4.7 | 4.69 | 100
2219 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001557/2020-2021 | 1212/CSD | 15/12/2020 | 45 | M/S. MANABESH ROY | 4.65 | 0 | 100
2220 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XVI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001558/2020-2021 | 1214/CSD | 15/12/2020 | 45 | D.R.CONSTRUCTION | 4.6 | 0 | 100
2221 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XVII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001747/2020-2021 | 1450/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.61 | 0 | 100
2222 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XVIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001748/2020-2021 | 1451/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.69 | 0 | 100
2223 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XIX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001751/2020-2021 | 1452/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.57 | 0 | 100
2224 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - XX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001754/2020-2021 | 1453/CSD | 27/01/2021 | 45 | KIRON CONSTRUCTION | 4.65 | 0 | 100
2225 | Alipore Division | Canning Sub-division | Laying of pipeline for providing house connection from H/O Rajkumar Sardar to H/O Bhagyadhar Sardar of Pakhirali habitation under Budhkhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002028/2020-2021 | 1517/CSD | 10/02/2021 | 30 | MONCON INDIA | 0.43 | 0.42 | 0
2226 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Budh Khali of Budh Khali Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002039/2020-2021 | 1210/CSD | 15/12/2020 | 45 | M/S ARIYAN ENTERPRISE | 4.72 | 0 | 100
2227 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sitarampur Water Supply Scheme including one year Operation & Maintenance and repairing of distribution system, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000033/2022-2023 | 675/AD | 05/05/2022 | 120 | GROWING CONCERN | 150.83 | 0 | 80
2228 | Alipore Division | Kakdwip Sub-Division | Supply, Delivery & Laying of Specials Required for Laying Rising Main and Inter-Connection Line between Tubewells and other allied works for providing FHTC under JJM at Sitarampur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000224/2022-2023 | 3065/AD | 13/07/2022 | 30 | ANANTA KUMAR GIRI | 7.64 | 0 | 100
2229 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000781/2023-2024 | 615/AD | 29/01/2024 | 0 | Resource Division | 12.81 | 0 | 0
2230 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000825/2023-2024 | 670/AD | 30/01/2024 | 0 | Resource Division | 12.64 | 0 | 0
2231 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001025/2021-2022 | 539/KSD | 01/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.58 | 0 | 100
2232 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001044/2021-2022 | 2275/AD | 06/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 3.04 | 0 | 100
2233 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gobindarampur W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001609/2021-2022 | 607/KSD | 27/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 4.02 | 0 | 100
2234 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000268/2023-2024 | 3067/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2235 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000830/2023-2024 | 675/AD | 30/01/2024 | 0 | Resource Division | 18.1 | 0 | 0
2236 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Jameson Island & Kali Mandir Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001729/2020-2021 | 1211/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
2237 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Hari Mandir Para (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001741/2020-2021 | 1214/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
2238 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kamar Para (Part) & Library Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001762/2020-2021 | 1221/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
2239 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mollar Chak & Shivnagar for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001792/2020-2021 | 1237/KSD | 23/02/2021 | 10 | M/S MODINA ENTERPRISE | 4.55 | 0 | 84
2240 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001808/2020-2021 | 1246/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.76 | 0 | 96
2241 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahis Gheri, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001835/2020-2021 | 1266/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 80
2242 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Library Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001839/2020-2021 | 1270/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
2243 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gosta Para (Phase-II), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001843/2020-2021 | 1274/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
2244 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001846/2020-2021 | 1277/KSD | 23/02/2021 | 10 | KHOKAN MONDAL | 4.74 | 0 | 100
2245 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Khorimutha for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001849/2020-2021 | 1280/KSD | 23/02/2021 | 10 | M/S MODINA ENTERPRISE | 4.1 | 0 | 91
2246 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-B | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001853/2020-2021 | 1284/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.46 | 0 | 87
2247 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttar Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001860/2020-2021 | 1291/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
2248 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Sitala Mandir Para, for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001863/2020-2021 | 1294/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
2249 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Para (Part) & Gosta Para (Part), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001897/2020-2021 | 1319/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.24 | 0 | 0
2250 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000775/2023-2024 | 609/AD | 29/01/2024 | 0 | Resource Division | 14.15 | 0 | 0
2251 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dutta Babur Abad Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000272/2021-2022 | 1719/AD | 17/08/2021 | 1825 | M/S. ROY CHOWDHURY & CO. | 120.85 | 0 | 80
2252 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000143/2023-2024 | 854/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
2253 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 06 (six) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001465/2021-2022 | 6259/AD | 24/02/2022 | 420 | SAJAL KUMAR DAS | 105.31 | 0 | 95
2254 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dwariknagar W/S Scheme, Block - Namkhana for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000345/2022-2023 | 4072/AD | 18/08/2022 | 30 | FORTUNE ENGINEERING | 18.33 | 0 | 100
2255 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, construction of 01 no. 5.40m. x 3.60m Pump House, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000438/2022-2023 | 4352/AD | 25/08/2022 | 60 | M/S KRISHNA MONDAL | 87.53 | 0 | 70
2256 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DWARIKNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000485/2022-2023 | 2492/AD | 27/06/2022 | 45 | M/S R.DUTTA & CO. | 4.61 | 0 | 100
2257 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Namkhana Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001102/2022-2023 | 8485/AD | 16/12/2022 | 837 | BALAJEE ENTERPRISE. | 691.56 | 0 | 100
2258 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Dwariknagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001479/2023-2024 | 4689/AD | 18/12/2023 | 411 | M/S. DAS BUILDERS | 9.51 | 0 | 100
2259 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work and 2nd Tubewell Site of Dwariknagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001836/2023-2024 | 124/AD | 05/01/2024 | 45 | M/S NAIYA & MAITY | 39.81 | 0 | 50
2260 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001841/2023-2024 | 129/AD | 05/01/2024 | 45 | M/S KRISHNA MONDAL | 40.83 | 0 | 60
2261 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
2262 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Dwariknagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 300] [SM/11847] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002288/2023-2024 | 1004/AD | 16/02/2024 | 240 | M/S. JHARNA ENTERPRISE | 172.02 | 0 | 10
2263 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000292/2023-2024 | 3060/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2264 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000491/2023-2024 | 4790/AD | 19/12/2023 | 0 | Resource Division | 7.83 | 0 | 0
2265 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000549/2023-2024 | 32/AD | 02/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
2266 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000782/2023-2024 | 626/AD | 30/01/2024 | 0 | Resource Division | 2.74 | 0 | 0
2267 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000985/2023-2024 | 1778/AD | 27/03/2024 | 0 | Resource Division | 2.09 | 0 | 0
2268 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2022 to 30/04/2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000216/2022-2023 | 45/DHSD | 29/04/2022 | 1 | GOPAL KUMAR JHA | 4.8 | 0 | 71
2269 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Gangadharpur (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000294/2022-2023 | 3831/AD | 08/08/2022 | 45 | M/S AHAMED CONSTRUCTION | 36.53 | 0 | 100
2270 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 2 nos. Pump House for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000321/2022-2023 | 3868/AD | 08/08/2022 | 30 | SANKAR HALDER | 59.33 | 0 | 85
2271 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000322/2022-2023 | 3869/AD | 08/08/2022 | 30 | MS S.M. ENTERPRISE | 14.79 | 0 | 100
2272 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( GANGADHARPUR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000492/2022-2023 | 1750/AD | 15/06/2022 | 45 | LEMNISCATE | 6.22 | 0 | 100
2273 | Alipore Division | Kakdwip Sub-Division | Construction of 2 nos. 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Gangadharpur (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 600] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000543/2023-2024 | 2209/AD | 10/08/2023 | 875 | M/S PIONEER CONSTRUCTION | 450.22 | 0 | 60
2274 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gangadharpur (Zone - I &II) PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11805) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000573/2024-2025 | 4027/AD | 30/09/2024 | 458 | M/S PIONEER CONSTRUCTION | 154.01 | 0 | 20
2275 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Gangadharpur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11805) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001330/2024-2025 | 5414/AD | 24/12/2024 | 45 | L G CONSTRUCTION | 39.76 | 0 | 0
2276 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
2277 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002599/2023-2024 | 177/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2278 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002600/2023-2024 | 178/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2279 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur (Zone - I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002615/2023-2024 | 733/KSD | 05/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
2280 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gangadharpur (Zone - I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002616/2023-2024 | 864(A)/KSD | 13/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
2281 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000089/2022-2023 | 5596/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
2282 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000459/2023-2024 | 4722/AD | 18/12/2023 | 0 | Resource Division | 33.17 | 0 | 0
2283 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000996/2023-2024 | 1789/AD | 27/03/2024 | 0 | Resource Division | 30.96 | 0 | 0
2284 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000862/2023-2024 | 769/AD | 03/02/2024 | 0 | Resource Division | 20.59 | 0 | 0
2285 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000931/2023-2024 | 1273/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2286 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Companir Char Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11748) (SM/09077) (SM/08802) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000021/2025-2026 | 2007/AD | 28/04/2025 | 45 | PALASH HALDAR | 8.27 | 0 | 0
2287 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Companir Char PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000076/2023-2024 | 60/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2288 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Companirchar W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000280/2023-2024 | 1430/AD | 13/07/2023 | 45 | TANMAY ROY CHOWDHURY | 88.41 | 0 | 50
2289 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Companirchar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000296/2022-2023 | 3832/AD | 08/08/2022 | 30 | SIMPLEX DRILLING CO. | 22.93 | 0 | 100
2290 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companir char Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000306/2022-2023 | 3842/AD | 08/08/2022 | 30 | DIPA CHHETRI | 11.78 | 0 | 100
2291 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000307/2022-2023 | 3855/AD | 08/08/2022 | 15 | GHOSH CONSTRUCTION | 8.03 | 0 | 100
2292 | Alipore Division | Kakdwip Sub-Division | Relaying UPVC pipe line from Nodal Point 18 to 20, 13 to 48, 13 to 64 of Companirchar W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000390/2020-2021 | 952/KSD | 03/11/2020 | 30 | SK ENTERPRISE | 4.42 | 0 | 100
2293 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000446/2022-2023 | 4645/AD | 06/09/2022 | 120 | RELIABLE CONSTRUCTION | 149.69 | 0 | 100
2294 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (COMPANIR CHAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000480/2022-2023 | 1710/AD | 14/06/2022 | 45 | VOYAGER | 6.12 | 0 | 100
2295 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 1 no. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Companirchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000671/2022-2023 | 6156/AD | 01/11/2022 | 902 | TANMAY ROY CHOWDHURY | 344.09 | 0 | 95
2296 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Companir Char W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000717/2023-2024 | 2535/AD | 28/08/2023 | 30 | TANMAY ROY CHOWDHURY | 9.03 | 0 | 100
2297 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for 4(four) months (period from 01/01/2022 to 30/04/2022) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001206/2021-2022 | 403/DHSD | 28/12/2021 | 4 | MADHUSUDAN MAITY | 1.6 | 0 | 55
2298 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
2299 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Companir char W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002179/2023-2024 | 815/AD | 05/02/2024 | 30 | M/S. MANDAL ENTERPRISE | 11.65 | 0 | 0
2300 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000095/2022-2023 | 5597/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
2301 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000285/2023-2024 | 3087/AD | 28/09/2023 | 0 | Resource Division | 56.81 | 0 | 0
2302 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000333/2023-2024 | 3148/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2303 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000901/2023-2024 | 887/AD | 07/02/2024 | 0 | Resource Division | 3.44 | 0 | 0
2304 | Alipore Division | Canning Sub-division | Surging of 1no. Big dia Tubewell of Narayantala W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-2) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000415/2023-2024 | 774/CSD | 02/08/2023 | 35 | S.K.GOLUI | 2.17 | 0 | 99
2305 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations and pipe protection work at Narayantala W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001029/2024-2025 | 4939/AD | 03/12/2024 | 60 | DIPTI ENTERPRISE | 56.82 | 0 | 0
2306 | Alipore Division | Canning Sub-division | Restoration of pipe line damaged due to flood like situation occurred by breaking of rivers embankment at Choradakatia under Narayantala W/S Scheme of Basanti Block under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001351/2020-2021 | 1259/CSD | 21/12/2020 | 30 | SURYA ENTERPRISE | 4.8 | 0 | 100
2307 | Alipore Division | Canning Sub-division | Construction of OHR (200 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Narayantala,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001641/2022-2023 | 11378/AD | 13/02/2023 | 1200 | DIPTI ENTERPRISE | 319 | 0 | 48
2308 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000073/2023-2024 | 538/AD | 25/01/2024 | 0 | Resource Division | 40.34 | 0 | 0
2309 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bamanagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000049/2023-2024 | 34/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2310 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile & pile cap upto pedestal at Bamanagar, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000269/2023-2024 | 1419/AD | 13/07/2023 | 446 | GARGO TRADERS | 43.4 | 0 | 70
2311 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000338/2022-2023 | 5707/AD. | 13/10/2022 | 30 | R CONSTRUCTION | 13.63 | 0 | 70
2312 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Bamanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000471/2022-2023 | 5202/AD | 22/09/2022 | 45 | AQUATECH ENGINEER | 37.06 | 0 | 100
2313 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( BAMANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000495/2022-2023 | 4193/AD | 22/08/2022 | 45 | LEMNISCATE | 5.14 | 0 | 100
2314 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000541/2022-2023 | 5708/AD. | 13/10/2022 | 30 | SUMAN ENTERPRISE | 11.89 | 0 | 60
2315 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000552/2022-2023 | 5726/AD | 13/10/2022 | 901 | GARGO TRADERS | 434.79 | 0 | 80
2316 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Bamanagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000575/2022-2023 | 5713/AD | 13/10/2022 | 21 | M/S SAKTI GIRI ENTERPRISE | 9.89 | 0 | 100
2317 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Bamanagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001156/2023-2024 | 3719/AD | 03/11/2023 | 45 | G.M. ENTERPRISE | 27.73 | 0 | 70
2318 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Bamanagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001157/2023-2024 | 3720/AD | 03/11/2023 | 30 | SUKUMAR HALDAR | 9.57 | 0 | 100
2319 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
2320 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000120/2023-2024 | 656/AD | 17/05/2023 | 0 | Resource Division | 11.61 | 0 | 0
2321 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000443/2023-2024 | 4710/AD | 18/12/2023 | 0 | Resource Division | 9.1 | 0 | 0
2322 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000811/2023-2024 | 656/AD | 30/01/2024 | 0 | Resource Division | 2.08 | 0 | 0
2323 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000992/2023-2024 | 1785/AD | 27/03/2024 | 0 | Resource Division | 32.17 | 0 | 0
2324 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Bijoyrampur having village with maximum 97 nos. households, Block - Diamond Harbour -I under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001718/2022-2023 | 11628/AD | 18/02/2023 | 60 | DEV AND COMPANY | 32.52 | 0 | 0
2325 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000867/2023-2024 | 774/AD | 03/02/2024 | 0 | Resource Division | 0.6 | 0 | 0
2326 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Harendragnagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000048/2023-2024 | 33/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2327 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile andile cap upto pedestal at Harendranagar, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000277/2023-2024 | 1427/AD | 13/07/2023 | 45 | SUPRITI ENTERPRISE | 32 | 0 | 0
2328 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000335/2022-2023 | 4065/AD | 18/08/2022 | 30 | M/S MODINA ENTERPRISE | 19.21 | 0 | 40
2329 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000336/2022-2023 | 4066/AD | 18/08/2022 | 867 | M/S. PARAMESWAR ENTERPRISE | 12.68 | 0 | 100
2330 | Alipore Division | Kakdwip Sub-Division | Laying distribution systemfor Providing Functional Household Tap Connection (FHTC) to all households for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000337/2022-2023 | 4067/AD | 18/08/2022 | 21 | M/S. MOYNA ENTERPRISE | 7.49 | 0 | 100
2331 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Harendranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000343/2022-2023 | 4070/AD | 18/08/2022 | 45 | AQUATECH ENGINEER | 37.06 | 0 | 0
2332 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (HARENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000501/2022-2023 | 2494/AD | 27/06/2022 | 45 | LEMNISCATE | 4.71 | 0 | 100
2333 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Harendranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000783/2022-2023 | 6537/AD | 11/11/2022 | 300 | SUPRITI ENTERPRISE | 371.44 | 0 | 20
2334 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harendranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000945/2023-2024 | 2978/AD | 26/09/2023 | 45 | C L B SYNDICATE | 27.65 | 0 | 0
2335 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harendranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000947/2023-2024 | 2979/AD | 26/09/2023 | 30 | DEBIKA CONSTRUCTION | 9.52 | 0 | 0
2336 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Harendranagar W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001008/2023-2024 | 512/KSD | 03/10/2023 | 7 | S.K.GOLUI | 2.72 | 0 | 100
2337 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.08.2021 to 31.01.2022 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001331/2021-2022 | 456/KSD | 29/07/2021 | 184 | PIKASU BOSE | 2.4 | 0 | 100
2338 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2022 to 31.07.2022 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001679/2021-2022 | 935/KSD | 31/01/2022 | 181 | PIKASU BOSE | 2.4 | 0 | 100
2339 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2340 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000118/2023-2024 | 654/AD | 17/05/2023 | 0 | Resource Division | 7.62 | 0 | 0
2341 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000440/2023-2024 | 4708/AD | 18/12/2023 | 0 | Resource Division | 12.49 | 0 | 0
2342 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000807/2023-2024 | 652/AD | 30/01/2024 | 0 | Resource Division | 1.37 | 0 | 0
2343 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000990/2023-2024 | 1783/AD | 27/03/2024 | 0 | Resource Division | 27 | 0 | 0
2344 | Alipore Division | Baruipur Sub-Division | Road restoration of L030-Belegachhi Buks Stand on T01 to Sardarpara(WB/02/416) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01729/2024-2025 | BP-2024-25-793 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.35 | 0 | 0
2345 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - X) having village with maximum 198 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000794/2022-2023 | 6683/AD | 14/11/2022 | 805 | M/S. L.P. CONSTRUCTION | 55.83 | 0 | 95
2346 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-X) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001906/2022-2023 | 5670/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.55 | 0 | 0
2347 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000175/2023-2024 | 1128/AD | 22/06/2023 | 0 | Resource Division | 1.22 | 0 | 0
2348 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - IV) having village with maximum 70 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000791/2022-2023 | 6679/AD | 14/11/2022 | 958 | SNEHA CONSTRUCTION | 38.95 | 0 | 80
2349 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001896/2022-2023 | 5660/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.32 | 0 | 0
2350 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000181/2023-2024 | 1134/AD | 22/06/2023 | 0 | Resource Division | 0.43 | 0 | 0
2351 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% FHTC household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IV of Diamond Harbour-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 1450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000341/2023-2024 | 3601/AD | 25/10/2023 | 609 | CREATION CONSTRUCTION | 403.02 | 0 | 37
2352 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR with allide works at Zone - IV Diamond Harbour - II Block for Providing 100% FHTC within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Zone - IIIB, Part - A). | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000367/2023-2024 | 1568/AD | 17/07/2023 | 300 | M/S J.T. CONSTRUCTION | 253.06 | 0 | 0
2353 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall (length - 25 m.) at proposed OHR site and Land development at Mouza - Sarisha under Zone- IV of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000792/2024-2025 | 4497/AD | 11/11/2024 | 30 | SK SAKIL AHAMED | 7.52 | 0 | 0
2354 | Alipore Division | Diamond Harbour Sub-Division | Augmentation in distribution system due to improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-IV of Diamond Harbour - II Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002024/2022-2023 | 12928/AD | 21/03/2023 | 30 | MAHALAXMI CONSTRUCTION | 30.28 | 0 | 90
2355 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
2356 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000354/2023-2024 | 3218/AD | 04/10/2023 | 0 | Resource Division | 0.31 | 0 | 0
2357 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000882/2023-2024 | 756/AD | 03/02/2024 | 0 | Resource Division | 16.32 | 0 | 0
2358 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
2359 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 200mm x 100mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Ramgopalpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13976) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000596/2024-2025 | 4062/AD | 01/10/2024 | 30 | S.K.GOLUI | 15.8 | 0 | 100
2360 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramgopalpur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000952/2023-2024 | 2984/AD | 29/09/2023 | 45 | TIYASHA ENTERPRISE | 27.65 | 0 | 0
2361 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramgopalpur W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000953/2023-2024 | 2985/AD | 26/09/2023 | 30 | BHABASANKAR NAYAK | 9.52 | 0 | 0
2362 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Ramgopalpur W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001006/2023-2024 | 511/KSD | 03/10/2023 | 7 | S.K.GOLUI | 2.73 | 0 | 100
2363 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramgopalpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001312/2022-2023 | 9895/AD | 10/01/2023 | 45 | KHAIRUL BASAR | 38.55 | 0 | 15
2364 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAMGOPALPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001343/2022-2023 | 3801/AD | 05/08/2022 | 45 | LEMNISCATE | 4.32 | 0 | 100
2365 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2366 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000122/2023-2024 | 657/AD | 17/05/2023 | 0 | Resource Division | 9.53 | 0 | 0
2367 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000448/2023-2024 | 4714/AD | 18/12/2023 | 0 | Resource Division | 26.47 | 0 | 0
2368 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000815/2023-2024 | 660/AD | 30/01/2024 | 0 | Resource Division | 1.71 | 0 | 0
2369 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-II of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 2180] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000264/2023-2024 | 3668/AD | 31/10/2023 | 720 | PARAMESWAR CHOWDHURY | 271.31 | 0 | 95
2370 | Alipore Division | Diamond Harbour Sub-Division | Construction of community tank in different Primary and High Schools under Zone-II of Falta Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000825/2022-2023 | 209/DHSD | 02/08/2022 | 45 | B. MOOKHERJEE | 4.22 | 0 | 0
2371 | Alipore Division | Diamond Harbour Sub-Division | Restoration and laying of parallel line by UPVC pipes in distribution system at Falta Zone-II for providing 100% FHTC within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Node Point- 223 to 224,305 to 299,249 to 290, 248 to 314, 314 to 335, 290 to 305, 305 to 312, 312 to 337, 337 to 339, 339 to 343, 343 to 345, 345 to 350) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001151/2023-2024 | 3197/AD | 04/10/2023 | 45 | ADITYA HAZRA | 54.35 | 0 | 100
2372 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-II of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001536/2023-2024 | 437/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
2373 | Alipore Division | Diamond Harbour Sub-Division | Extension of distribution pipeline at Chandpala Anantharampur & Brihaspatipur Mouza under Zone-II of Falta Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001653/2021-2022 | 458/DHSD | 15/03/2022 | 15 | PEECON | 3.72 | 0 | 100
2374 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000438/2023-2024 | 3623/AD | 30/10/2023 | 0 | Resource Division | 12.32 | 0 | 0
2375 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000847/2023-2024 | 785/AD | 03/02/2024 | 0 | Resource Division | 1.11 | 0 | 0
2376 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gayadham PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11744) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000187/2024-2025 | 923/AD | 05/03/2025 | 60 | M/S B. ENTERPRISE | 53.26 | 0 | 0
2377 | Alipore Division | Kakdwip Sub-Division | Construction of concrete Y junction for laying pipe line to provide FHTC at Rakhaskhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13802) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000194/2024-2025 | 2554/AD | 18/06/2024 | 45 | M/S B. ENTERPRISE | 37.27 | 0 | 10
2378 | Alipore Division | Kakdwip Sub-Division | Laying D.I. Pipe for providing FHTC, Road Restoration and Y junction for Rakhaskhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. ( (SM/13802) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000502/2024-2025 | 3605/AD | 06/09/2024 | 148 | M/S PARAMESWAR CHOWDHURY | 13.82 | 0 | 100
2379 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAKHASKHALI PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001037/2022-2023 | 3671/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.52 | 0 | 100
2380 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Rakhaskhali W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001055/2023-2024 | 3374/AD | 11/10/2023 | 45 | KHOKAN MONDAL | 33.28 | 0 | 100
2381 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Rakhaskhali W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001056/2023-2024 | 3375/AD | 11/10/2023 | 30 | M/S. SONAMONI ENTERPRISE | 11.75 | 0 | 100
2382 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Rakhaskhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001273/2022-2023 | 9585/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
2383 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Rakhaskhali Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1018] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002061/2022-2023 | 13003/AD | 23/03/2023 | 741 | M/S B. ENTERPRISE | 259.34 | 0 | 100
2384 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Buraburir Tat, Sitarampur, Rakhaskhali, Gobindapur Abad PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002111/2023-2024 | 931/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
2385 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000101/2023-2024 | 547/AD | 12/05/2023 | 0 | Resource Division | 9.16 | 0 | 0
2386 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000506/2023-2024 | 4946/AD | 22/12/2023 | 0 | Resource Division | 24.05 | 0 | 0
2387 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. At 3rd Tubewell Site for Augmentation of Ganeshpur Kalinagar Zone-I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/10336) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000011/2025-2026 | 1702/AD | 08/04/2025 | 45 | PRANABANANDA CONSTRUCTION | 5.43 | 0 | 0
2388 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Chandipur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13812) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000217/2024-2025 | 2600/AD | 19/06/2024 | 30 | LASKAR ENTERPRISE | 9.1 | 0 | 100
2389 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000398/2023-2024 | 1873/AD | 01/08/2023 | 45 | M/S SUNITY ENTERPRISE | 11.53 | 0 | 70
2390 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000399/2023-2024 | 1874/AD | 01/08/2023 | 45 | C.S. CONSTRUCTION | 11.18 | 0 | 100
2391 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000400/2023-2024 | 1899/AD | 01/08/2023 | 45 | M/S. BRINDABAN DAS & SONS | 10.77 | 0 | 70
2392 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000401/2023-2024 | 1900/AD | 01/08/2023 | 609 | DEV AND COMPANY | 9.51 | 0 | 40
2393 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Chandipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13812) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000662/2024-2025 | 4211/AD | 23/10/2024 | 218 | SARADA CONSTRUCTION | 92.01 | 0 | 61
2394 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-E) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001031/2023-2024 | 3315/AD | 07/10/2023 | 45 | SARKAR ENTERPRISE | 10 | 0 | 60
2395 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Part-G) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001032/2023-2024 | 3316/AD | 07/10/2023 | 45 | JHARNA ENTERPRISE | 30.86 | 0 | 80
2396 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (CHANDIPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001055/2022-2023 | 4145/AD | 19/08/2022 | 45 | LEMNISCATE | 4.22 | 0 | 100
2397 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Chandipur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001421/2023-2024 | 4601/AD | 14/12/2023 | 472 | MAA BHABANI CONSTRUCTION (DUM DUM) | 47.31 | 0 | 70
2398 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Chandipur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001774/2022-2023 | 12047/AD | 27/02/2023 | 30 | M/S MAITY CONSTRUCTION | 19.26 | 0 | 100
2399 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
2400 | Alipore Division | Kakdwip Sub-Division | Inter connection between two nos. Tubewell for Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002548/2024-2025 | 817/AD | 27/02/2025 | 45 | PAUL CONSTRUCTION | 13.31 | 0 | 0
2401 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ganeshpur Kalinagar (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/10336) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002555/2024-2025 | 819/AD | 27/02/2025 | 45 | M/S. GANGA ENTERPRISE | 9.54 | 0 | 0
2402 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000271/2023-2024 | 3070/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2403 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000466/2023-2024 | 4726/AD | 18/12/2023 | 0 | Resource Division | 38.66 | 0 | 0
2404 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000595/2023-2024 | 94/AD | 03/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
2405 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000813/2023-2024 | 658/AD | 30/01/2024 | 0 | Resource Division | 9.62 | 0 | 0
2406 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR001000/2023-2024 | 1799/AD | 27/03/2024 | 0 | Resource Division | 25.73 | 0 | 0
2407 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Char Baidyarabad W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000855/2022-2023 | 6994/AD | 19/11/2022 | 30 | PAPPU ENTERPRISE | 19.48 | 0 | 95
2408 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Char Baidyarabad Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001838/2021-2022 | 660/CSD | 12/08/2021 | 15 | HORIZEN | 3.92 | 0 | 100
2409 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Char Baidyarabad Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001839/2021-2022 | 670/CSD | 17/08/2021 | 15 | HORIZEN | 3.04 | 0 | 100
2410 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000388/2023-2024 | 329/AD | 19/01/2024 | 0 | Resource Division | 12.11 | 0 | 0
2411 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Satyadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000638/2023-2024 | 2466/AD | 24/08/2023 | 90 | PIKASU BOSE | 52.93 | 0 | 100
2412 | Alipore Division | Kakdwip Sub-Division | Construction of Approach Road with Box Culvert and Allied works at Satyadaspur Water Supply OHR Site, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13965) (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000902/2024-2025 | 4751/AD | 23/11/2024 | 182 | PIKASU BOSE | 27.02 | 0 | 100
2413 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Satyadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000934/2023-2024 | 277(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2414 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Satyadaspur W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000998/2023-2024 | 505/KSD | 03/10/2023 | 7 | FORTUNE ENGINEERING | 3.37 | 0 | 100
2415 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001184/2023-2024 | 3945/AD | 17/11/2023 | 20 | SARADA CONSTRUCTION | 24.59 | 0 | 0
2416 | Alipore Division | Kakdwip Sub-Division | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001276/2022-2023 | 9588/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
2417 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation Water Supply Scheme (SATYADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001326/2022-2023 | 3309/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.98 | 0 | 100
2418 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 450 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Satyadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001979/2023-2024 | 438/AD | 24/01/2024 | 30 | SARADA CONSTRUCTION | 30.53 | 0 | 100
2419 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Satyadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002040/2023-2024 | 522/AD | 25/01/2024 | 45 | A.R.CONSTRUCTION | 33.21 | 0 | 0
2420 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
2421 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Satyadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002152/2023-2024 | 799/AD | 05/02/2024 | 391 | NARAYAN ENTERPRISE | 11.58 | 0 | 100
2422 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000100/2023-2024 | 546/AD | 12/05/2023 | 0 | Resource Division | 8.14 | 0 | 0
2423 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000296/2023-2024 | 3091/AD | 28/09/2023 | 0 | Resource Division | 23.44 | 0 | 0
2424 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000757/2023-2024 | 592/AD | 29/01/2024 | 0 | Resource Division | 2.59 | 0 | 0
2425 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - II) having village with maximum 70 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000790/2022-2023 | 6645/AD | 14/11/2022 | 90 | M/S. R.M. CONSTRUCTION | 42.42 | 0 | 80
2426 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001911/2022-2023 | 5151/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.35 | 0 | 0
2427 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000179/2023-2024 | 1132/AD | 22/06/2023 | 0 | Resource Division | 0.43 | 0 | 0
2428 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution system at Zone-VI of Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000564/2021-2022 | 2702/AD | 01/10/2021 | 180 | MALAY KANTI DEY | 125.75 | 0 | 47
2429 | Alipore Division | Diamond Harbour Sub-Division | Functional Household Tap Connection (FHTC) for balance portion in Diamond Harbour-II Zone-VI (Khordanahala) for providing 100% coverage for Swajal Gram activity under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas, Block Falta, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000750/2022-2023 | 6181/AD | 01/11/2022 | 30 | ADITYA HAZRA | 46.66 | 0 | 96
2430 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-V of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. (Phase-II) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001393/2022-2023 | 10865/AD | 04/02/2023 | 90 | TIRUPATI ENTERPRISES | 298.7 | 0 | 85
2431 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000883/2023-2024 | 757/AD | 03/02/2024 | 0 | Resource Division | 11.24 | 0 | 0
2432 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000923/2023-2024 | 1265/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2433 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system with allied works to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III B (Dostipur) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-2330]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000306/2023-2024 | 1509/AD | 15/07/2023 | 720 | M/S A.K. GHATAK | 455.49 | 0 | 70
2434 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone- III(B) (Dostipur) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001000/2022-2023 | 288/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 2.83 | 0 | 0
2435 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-IIIB at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002393/2024-2025 | 638/AD | 18/02/2025 | 30 | K.P. CONSTRUCTION | 7.98 | 0 | 0
2436 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIB at Falta block for providing balance pipe lying works, road restoration works etc.under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002472/2024-2025 | 720/AD | 21/02/2025 | 30 | M/S A.K. GHATAK | 20.23 | 0 | 0
2437 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000137/2022-2023 | 20/AD | 05/04/2023 | 0 | Resource Division | 12.74 | 0 | 0
2438 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000184/2023-2024 | 1278/AD | 05/07/2023 | 0 | Resource Division | 12.74 | 0 | 0
2439 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000428/2023-2024 | 3622/AD | 30/10/2023 | 0 | Resource Division | 14.35 | 0 | 0
2440 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000621/2023-2024 | 282/AD | 15/01/2024 | 0 | Resource Division | 0.79 | 0 | 0
2441 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VI at Boria of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-2939] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000090/2023-2024 | 501/AD | 11/05/2023 | 874 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 634.45 | 0 | 70
2442 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- II block for providing balance pipe lying works, road restoration works etc. under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000333/2025-2026 | 270/DHSD | 16/06/2025 | 45 | M/S ROY CONSTRUCTION | 3.39 | 0 | 0
2443 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for fundation of different capacities for the proposed R.C.C. Over Head Reservoir at Diamond Harbour-I Block, (Zone-VI, OHR Size-600 Cum., Mouza - Boria) and (Zone-VIII, OHR Size-600 Cum. Mouza - Paschim Gansingber) under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000361/2022-2023 | 197/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 100
2444 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000134/2022-2023 | 31/AD | 05/04/2023 | 0 | Resource Division | 7.86 | 0 | 0
2445 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000229/2023-2024 | 2201/AD | 10/08/2023 | 0 | Resource Division | 10.69 | 0 | 0
2446 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000351/2023-2024 | 3215/AD | 04/10/2023 | 0 | Resource Division | 0.41 | 0 | 0
2447 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000424/2023-2024 | 3625/AD | 30/10/2023 | 0 | Resource Division | 15.4 | 0 | 0
2448 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000610/2023-2024 | 272/AD | 15/01/2024 | 0 | Resource Division | 3.08 | 0 | 0
2449 | Alipore Division | Baruipur Sub-Division | Road restoration for Chiner More to Haral Bani Scociation Bituminaous Via Punri Katpole to Bonabibi Tala. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01695/2024-2025 | BP-2024-25-784 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.12 | 0 | 0
2450 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including Construction of 1 no. 250cum capcity OHR and 01 no 400 cum capacity OHR to extend the benefit 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XI at Mangarajpur & Zone-V at Atkrishnarampur of Diamond harbour - I block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000487/2023-2024 | 4927/AD | 22/12/2023 | 831 | PRASUN ENTERPRISE | 972.76 | 0 | 10
2451 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XI of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001054/2022-2023 | 307/DHSD | 23/09/2022 | 30 | MEASURE LAND | 2.62 | 0 | 0
2452 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-XI (Mongrajpur OHR Size-250) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002091/2022-2023 | 325/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2453 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000126/2022-2023 | 29/AD | 05/04/2023 | 0 | Resource Division | 8.2 | 0 | 0
2454 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000239/2023-2024 | 2200/AD | 10/08/2023 | 0 | Resource Division | 8.21 | 0 | 0
2455 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000349/2023-2024 | 3213/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2456 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000895/2023-2024 | 749/AD | 03/02/2024 | 0 | Resource Division | 10.37 | 0 | 0
2457 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - I) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000655/2022-2023 | 6677/AD | 14/11/2022 | 60 | M/S P. B. CONSTRUCTION | 49.13 | 0 | 88
2458 | Alipore Division | Canning Sub-division | Laying of pipe line at Moukhali High School and Moukhali Jr. High School (Girls) from Moukhali-Kumarkhali (Zone-I) R.O. Plant at Moukhali-Kumarkhali W/S Scheme (Zone-I), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000865/2022-2023 | 840/CSD | 12/08/2022 | 30 | SUJIT KUMAR GHOSH | 3.43 | 0 | 0
2459 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Moukhali-Kumarkhali (Zone - I to VI), under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001380/2022-2023 | 1062/CSD | 14/12/2022 | 40 | M/S. M.K. NASKAR & CONSTRUCTION | 0.96 | 0 | 0
2460 | Alipore Division | Canning Sub-division | Surging of 02 (two) nos. 250mm x 150mm. dia. 360 mtr. Deep Tubewell at Moukhali-Kumarkhali W/S Scheme (Zone-I, TW-1) & (Zone-II, TW-1) under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001637/2023-2024 | 1048/CSD | 04/10/2023 | 30 | ASHIM SHIL | 0.91 | 0 | 100
2461 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001897/2022-2023 | 5661/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.4 | 0 | 0
2462 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000166/2023-2024 | 1119/AD | 22/06/2023 | 0 | Resource Division | 0.91 | 0 | 0
2463 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - VII) having village with maximum 345 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000600/2022-2023 | 6680/AD | 14/11/2022 | 60 | SEKH CONSTRUCTION | 65.01 | 0 | 80
2464 | Alipore Division | Canning Sub-division | 03 (three) nos. 40 mm dia. 375 mtr. deep Trial Bore by water jet method for Augmentation of Ground Water Based Mini Piped Water Supply Scheme for Moukhali-Kumarkhali (Zone - VII to XII), under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001381/2022-2023 | 1063/CSD | 14/12/2022 | 40 | M/S. MIHIR KUMAR NASKAR | 0.96 | 0 | 0
2465 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-VII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001903/2022-2023 | 5667/AD. | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.61 | 0 | 0
2466 | Alipore Division | Canning Sub-division | Additional laying of pipe line at Augmentation of Moukhali-Kumarkhali W/S Scheme (Part-VII), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002110/2023-2024 | 1219/CSD | 21/11/2023 | 30 | S. DAS ENTERPRISE | 4.51 | 0 | 100
2467 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000172/2023-2024 | 1125/AD | 22/06/2023 | 0 | Resource Division | 2.13 | 0 | 0
2468 | Alipore Division | Diamond Harbour Sub-Division | Inter connection due to increase of additional length from existing Tubewells to OHR site for improvement of water within Zone No-I of Falta Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000814/2024-2025 | 4500/AD | 11/11/2024 | 180 | THE TOWER CONSTRUCTION | 11.52 | 0 | 100
2469 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-I of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001535/2023-2024 | 436/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
2470 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-I of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 3450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001942/2022-2023 | 12790/AD | 16/03/2023 | 726 | M/S. S.S. ENTERPRISE | 502.63 | 0 | 62
2471 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000436/2023-2024 | 3618/AD | 30/10/2023 | 0 | Resource Division | 12.32 | 0 | 0
2472 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000619/2023-2024 | 280/AD | 15/01/2024 | 0 | Resource Division | 8.93 | 0 | 0
2473 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000735/2023-2024 | 569/AD | 27/01/2024 | 0 | Resource Division | 38.84 | 0 | 0
2474 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000925/2023-2024 | 1267/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
2475 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different household for Augmentation of Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000151/2024-2025 | 2489/AD | 14/06/2024 | 420 | J.K. CONSTRUCTION | 45.71 | 0 | 0
2476 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Radhakrishnapur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000400/2024-2025 | 3183/AD | 31/07/2024 | 30 | SOMNATH ENTERPRISE | 11.72 | 0 | 0
2477 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000553/2024-2025 | 3782/AD | 18/09/2024 | 360 | J.K. CONSTRUCTION | 73.8 | 0 | 0
2478 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (RADHAKRISHNAPUR) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001340/2022-2023 | 3802/AD | 05/08/2022 | 45 | VOYAGER | 5.03 | 0 | 100
2479 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001476/2023-2024 | 4685/AD | 18/12/2023 | 30 | SARADA CONSTRUCTION | 25.38 | 0 | 100
2480 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Radhakrishnapur Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001578/2021-2022 | 6958/AD | 29/03/2022 | 30 | SIMPLEX DRILLING CO. | 23.04 | 0 | 100
2481 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Radhakrishnapur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 300 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002030/2022-2023 | 12997/AD | 23/03/2023 | 990 | M. MUKHERJEE | 274.08 | 0 | 60
2482 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
2483 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with approach road at 1st Tubewell site of Radhakrishnapur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13972) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002187/2024-2025 | 2068/KSD | 28/12/2024 | 20 | PIJUSH KANTI TRIPATHI | 4.14 | 0 | 0
2484 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000340/2023-2024 | 3155/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2485 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000514/2023-2024 | 4832/AD | 20/12/2023 | 0 | Resource Division | 24.77 | 0 | 0
2486 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000530/2023-2024 | 13/AD | 02/01/2024 | 0 | Resource Division | 1.78 | 0 | 0
2487 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000688/2023-2024 | 458/AD | 24/01/2024 | 0 | Resource Division | 3.12 | 0 | 0
2488 | Alipore Division | Baruipur Sub-Division | Road restoration for Ramnagar Bazar to Matiar Dhali House. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01694/2024-2025 | BP-2024-25-783 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.08 | 0 | 0
2489 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Paschim Surendranagar Zone-II (Part - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (Part-B) [No. of FHTC = 90] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000618/2023-2024 | 2316/AD | 17/08/2023 | 60 | L.N. ENTERPRISE | 99.93 | 0 | 100
2490 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-II (Part - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000929/2023-2024 | 274(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2491 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Paschim Surendranagar Zone-II (Part - I & II) PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000931/2023-2024 | 275(I)/KSD | 13/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2492 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PASCHIM SURENDRANAGAR (ZONE-II) (PART I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001042/2022-2023 | 3674/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.18 | 0 | 100
2493 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Paschim Surendranagar Zone-II (Part- I and II) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001207/2023-2024 | 4084/AD | 23/11/2023 | 405 | M/S KRISHNA MONDAL | 27.88 | 0 | 70
2494 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Paschim Surendranagar Zone-II (Part- I and II) W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001208/2023-2024 | 4085/AD | 23/11/2023 | 30 | RAJDEEP ENTERPRISE | 9.74 | 0 | 0
2495 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Paschim Surendranagar (Zone-II) (Part-I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001271/2022-2023 | 9583/AD | 03/01/2023 | 45 | PRITI ENTERPRISE | 38.53 | 0 | 100
2496 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 1st Tubewell site for Paschim Surendranagar Zone-II (Part-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13873) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001297/2024-2025 | 1931/KSD | 20/12/2024 | 25 | G.G. PROJECT | 4.33 | 0 | 0
2497 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 2nd Tubewell site for Paschim Surendranagar Zone-II (Part-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13873) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001298/2024-2025 | 1932/KSD | 20/12/2024 | 25 | MANAS INFRA PROJECTS | 4.16 | 0 | 100
2498 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone - II (Part - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) [No. of FHTC = 200 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002060/2022-2023 | 13002/AD | 23/03/2023 | 300 | M/S BOSE & CO. | 280.07 | 0 | 78
2499 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
2500 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Paschim Surendranagar Zone - II (Part - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (Part-A) [No. of FHTC = 50] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003301/2024-2025 | 1993/AD | 09/04/2024 | 60 | L.N. ENTERPRISE | 28.14 | 0 | 0
2501 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000315/2023-2024 | 3124/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2502 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000453/2023-2024 | 4764/AD | 19/12/2023 | 0 | Resource Division | 49.96 | 0 | 0
2503 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000566/2023-2024 | 81/AD | 03/01/2024 | 0 | Resource Division | 1.78 | 0 | 0
2504 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000756/2023-2024 | 591/AD | 29/01/2024 | 0 | Resource Division | 2.67 | 0 | 0
2505 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000905/2023-2024 | 891/AD | 07/02/2024 | 0 | Resource Division | 0.75 | 0 | 0
2506 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000961/2023-2024 | 1695/AD | 22/03/2024 | 0 | Resource Division | 21.64 | 0 | 0
2507 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different household for Augmentation of Shibpur (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000147/2024-2025 | 2485/AD | 14/06/2024 | 75 | PALCON | 51.57 | 0 | 0
2508 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, fitting fixing supplying different dia. specials for Augmentation of Shibpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000148/2024-2025 | 2486/AD | 14/06/2024 | 75 | UCON (II) | 51.21 | 0 | 0
2509 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Shibpur (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000554/2024-2025 | 3783/AD | 18/09/2024 | 423 | PALCON | 42.85 | 0 | 60
2510 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibpur (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000970/2023-2024 | 319/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2511 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for Providing FHTC to all households for Augmentation of Sibpur (Zone-I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000987/2023-2024 | 3006/AD | 26/09/2023 | 30 | PALCON | 11.99 | 0 | 100
2512 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SHIBPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001059/2022-2023 | 3678/AD | 01/08/2022 | 45 | VOYAGER | 6.57 | 0 | 100
2513 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sibpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001279/2022-2023 | 9591/AD | 03/01/2023 | 45 | SARADA CONSTRUCTION | 49.18 | 0 | 100
2514 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works for Augmentation of Shibpur (Zone- I & II)) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part - B) (SM/13788) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001333/2024-2025 | 5417/AD | 24/12/2024 | 480 | NOVELTY CONSTRUCTION | 58.45 | 0 | 70
2515 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 608] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001859/2022-2023 | 12412/AD | 09/03/2023 | 90 | PALCON | 128.51 | 0 | 100
2516 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sibpur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002139/2023-2024 | 798/AD | 05/02/2024 | 30 | M/S BHAGABATI ENTERPRISE | 11.46 | 0 | 0
2517 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Shibpur Zone - I & II, Ghoramara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002175/2023-2024 | 954/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.61 | 0 | 100
2518 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 200 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 2 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 608] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002466/2023-2024 | 1360/AD | 06/03/2024 | 60 | UCON | 0 | 0 | 0
2519 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000336/2023-2024 | 3151/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2520 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000513/2023-2024 | 4831/AD | 20/12/2023 | 0 | Resource Division | 24.78 | 0 | 0
2521 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000531/2023-2024 | 14/AD | 02/01/2024 | 0 | Resource Division | 7.22 | 0 | 0
2522 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000685/2023-2024 | 455/AD | 24/01/2024 | 0 | Resource Division | 4.25 | 0 | 0
2523 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS at Manasadwip (Zone-I and II) (SM/13117) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000019/2025-2026 | 2005/AD | 28/04/2025 | 30 | LEMNISCATE | 7.21 | 0 | 100
2524 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Manasadwip Zone-I & Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000079/2023-2024 | 63/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2525 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform, Valve Chamber etc. at different household for Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000136/2024-2025 | 2474/AD | 14/06/2024 | 60 | SWAPAN KUMAR PRADHAN | 67.89 | 0 | 0
2526 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Manasadwip (Zone-I and II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000137/2024-2025 | 2475/AD | 14/06/2024 | 45 | SIMPLEX DRILLING CO. | 49.93 | 0 | 50
2527 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Augmentation of Manasadwip (Zone I & II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000139/2024-2025 | 2477/AD | 14/06/2024 | 30 | M/S. PARAMESWAR ENTERPRISE | 11.66 | 0 | 0
2528 | Alipore Division | Kakdwip Sub-Division | Laying UPVC pipe line between Nodal Point 226 to 227 and 227 to 229 of Manasadwip Water supply scheme under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000444/2020-2021 | 830/KSD | 16/10/2020 | 45 | PIKASU BOSE | 3.55 | 0 | 5
2529 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Manasadwip Zone-II W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000591/2023-2024 | 2348/AD | 18/08/2023 | 45 | BENGAL BUILDERS | 49.7 | 0 | 100
2530 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001422/2022-2023 | 10980/AD | 07/02/2023 | 30 | ANANDA MAITY | 12.91 | 0 | 100
2531 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001461/2023-2024 | 4692/AD | 18/12/2023 | 45 | M/S KHAJABABA ENTERPRISE | 29.61 | 0 | 100
2532 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001462/2023-2024 | 4693/AD | 18/12/2023 | 45 | DIPA CHHETRI | 24.81 | 0 | 100
2533 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001463/2023-2024 | 4694/AD | 18/12/2023 | 30 | P.N. ENTERPRISE | 6.42 | 0 | 100
2534 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-H) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001464/2023-2024 | 4695/AD | 18/12/2023 | 30 | KAMALA ENTERPRISE (I) | 5.78 | 0 | 100
2535 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001465/2023-2024 | 4696/AD | 18/12/2023 | 30 | S.B. ENTERPRISE | 5.65 | 0 | 100
2536 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-J) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001466/2023-2024 | 4697/AD | 18/12/2023 | 30 | SRI DURGA ENTERPRISE | 5.48 | 0 | 100
2537 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-T) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001467/2023-2024 | 4698/AD | 18/12/2023 | 30 | AVIJIT MAITY | 9.41 | 0 | 100
2538 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-U) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001469/2023-2024 | 4699/AD | 18/12/2023 | 30 | M/S BIJALI ENTERPRISE | 15.38 | 0 | 0
2539 | Alipore Division | Kakdwip Sub-Division | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001544/2022-2023 | 10981/AD | 07/02/2023 | 30 | M/S MAA BASANTI ENTERPRISE | 9.62 | 0 | 100
2540 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Manasadwip (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001545/2022-2023 | 10982/AD | 07/02/2023 | 45 | SIMPLEX DRILLING CO. | 45.85 | 0 | 100
2541 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001689/2023-2024 | 5115/AD | 29/12/2023 | 60 | SHYAM DEVELOPER | 44.93 | 0 | 80
2542 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001690/2023-2024 | 5116/AD | 29/12/2023 | 427 | PALCON | 46.25 | 0 | 100
2543 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-K) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001692/2023-2024 | 5117/AD | 29/12/2023 | 30 | MONDAL ENTERPRISE (JOYNAGAR) | 9.39 | 0 | 100
2544 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-M) (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001783/2023-2024 | 920/KSD | 19/12/2023 | 30 | M/S B.S. ENTERPRISE | 4.64 | 0 | 100
2545 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001824/2022-2023 | 12120/AD | 01/03/2023 | 912 | BENGAL BUILDERS | 449.37 | 0 | 34
2546 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Manasadwip [Zone-I & II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001916/2021-2022 | 6554/AD | 10/03/2022 | 45 | VOYAGER | 9.82 | 0 | 95
2547 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Manasadwip (Zone I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001984/2023-2024 | 503/AD | 25/01/2024 | 432 | M/S. PRADHAN ENTERPRISE | 11.64 | 0 | 100
2548 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dhaspara Zone - I & II, Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002161/2023-2024 | 950/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
2549 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with construction of approach road at Head work site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002188/2024-2025 | 2069/KSD | 28/12/2024 | 20 | P.N. ENTERPRISE | 4.15 | 0 | 0
2550 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with approach road at 2nd Tubewell site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002189/2024-2025 | 2070/KSD | 28/12/2024 | 20 | SWAPAN KUMAR PRADHAN | 2.89 | 0 | 0
2551 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall with approach road at 3rd Tubewell site of Zone-I of Manasadwip W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14518) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002190/2024-2025 | 2071/KSD | 28/12/2024 | 20 | P.N. ENTERPRISE | 4.21 | 0 | 0
2552 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-L) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002430/2023-2024 | 365/KSD | 19/02/2024 | 30 | M/S DHIRENDRA ENTERPRISE | 4.8 | 0 | 100
2553 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-O) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002431/2023-2024 | 366/KSD | 19/02/2024 | 30 | M/S S.M. CONSTRUCTION | 4.49 | 0 | 100
2554 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-Q) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002432/2023-2024 | 367/KSD | 19/02/2024 | 30 | M/S. MA BHABANI CONSTRUCTION | 3.81 | 0 | 100
2555 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-R) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002433/2023-2024 | 368/KSD | 19/02/2024 | 30 | S. DAS ENTERPRISE | 3.2 | 0 | 100
2556 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-S) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002434/2023-2024 | 369/KSD | 19/02/2024 | 30 | M/S MA KALI ELECTRIC LIGHT CORPORATION. | 3.01 | 0 | 100
2557 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of Diesel Car / Luxury Taxi for supervision of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2024 to 31.07.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002533/2023-2024 | 259/KSD | 31/01/2024 | 182 | BADSHA ALOM | 2.4 | 0 | 10
2558 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of 2 nos. big dia. tubewell at 1st & 2nd Tubewell Site for Augmentation of Manasadwip Zone-II W/S scheme under JJM, Block : Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002571/2023-2024 | 514/KSD | 15/03/2024 | 5 | M/S KHAJABABA ENTERPRISE | 2.96 | 0 | 100
2559 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002626/2023-2024 | 887/KSD | 16/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
2560 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000326/2023-2024 | 3141/AD | 29/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
2561 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000503/2023-2024 | 4827/AD | 20/12/2023 | 0 | Resource Division | 36.98 | 0 | 0
2562 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000540/2023-2024 | 24/AD | 02/01/2024 | 0 | Resource Division | 2.08 | 0 | 0
2563 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000690/2023-2024 | 460/AD | 24/01/2024 | 0 | Resource Division | 10.56 | 0 | 0
2564 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000902/2023-2024 | 888/AD | 07/02/2024 | 0 | Resource Division | 25 | 0 | 0
2565 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Lot No.-126 (Zone-I) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000311/2024-2025 | 2692/AD | 24/06/2024 | 30 | SURYA ENTERPRISE | 8.72 | 0 | 0
2566 | Alipore Division | Canning Sub-division | Construction of Toilet including Sanitary arrangement as per departmental drawing at the site for Augmentation of Lot No. 126 (Zone - I & II) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001070/2024-2025 | 1305/CSD | 22/11/2024 | 60 | A.P. CONSTRUCTION | 2.09 | 0 | 0
2567 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Lot-126 (Zone-I & II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001946/2022-2023 | 10894/AD | 04/02/2023 | 45 | GANGA TUBEWELL AND HARDWARE | 2.6 | 0 | 95
2568 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - A] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002015/2022-2023 | 12921/AD | 21/03/2023 | 30 | JYOTI ENTERPRISES | 14.41 | 0 | 100
2569 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at Augmentation of Lot No. 126 W/S Scheme (Zone-I and II), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Part - B] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002016/2022-2023 | 12922/AD | 21/03/2023 | 60 | S.P. CONSTRUCTION (I) | 97.64 | 0 | 80
2570 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Lot 126 (Zone - I & II) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002382/2024-2025 | 619/AD | 17/02/2025 | 30 | SURYA ENTERPRISE | 12.58 | 0 | 0
2571 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Lot 126 (Zone - I & II) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002383/2024-2025 | 620/AD | 17/02/2025 | 30 | SURYA ENTERPRISE | 11.46 | 0 | 0
2572 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000039/2023-2024 | 244/AD | 24/04/2023 | 0 | Resource Division | 84.63 | 0 | 0
2573 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000397/2023-2024 | 355/AD | 19/01/2024 | 0 | Resource Division | 4.31 | 0 | 0
2574 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-IV for each zone of Kalikatala (Zone - I and II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000236/2023-2024 | 1324/AD | 07/07/2023 | 60 | JAYANTA KUMAR DEY | 64.08 | 0 | 100
2575 | Alipore Division | Canning Sub-division | Surging of 03 no. Big dia Tubewell of Ramchadrakhali (Zone-II) (TW-3) and Kalikatala (Zone-II) (TW-1 & 3) W/S Scheme under JJM, Block - Basanti & Canning-II, under Canning Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000242/2025-2026 | 681/CSD | 26/05/2025 | 30 | FORTUNE ENGINEERING | 4.3 | 0 | 0
2576 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalikatala W/S Scheme (Zone - I), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001686/2022-2023 | 11493/AD | 15/02/2023 | 45 | KUNDU CONSTRUCTION CO. | 7.1 | 0 | 100
2577 | Alipore Division | Canning Sub-division | : Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalikatala W/S Scheme (Zone - II), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001687/2022-2023 | 11494/AD | 15/02/2023 | 45 | ARFIN CONSTRUCTION | 7.09 | 0 | 100
2578 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Kalikatala (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001695/2022-2023 | 11626/AD | 18/02/2023 | 45 | ELECTROMECH | 39.19 | 0 | 100
2579 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000002/2023-2024 | 117/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
2580 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000014/2023-2024 | 219/AD | 21/04/2023 | 0 | Resource Division | 159.84 | 0 | 0
2581 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000137/2023-2024 | 841/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
2582 | Alipore Division | Raidighi Sub-Division | Dismantling and restoration of concrete village road for laying pipe line and Constriction of an steel structure for khal crossing at Zone-X of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000218/2022-2023 | 3059/AD | 13/07/2022 | 30 | DIPTI ENTERPRISE | 9 | 0 | 100
2583 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- X of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000658/2024-2025 | 4204/AD | 23/10/2024 | 60 | R.S.CONSTRUCTION CO. | 38.62 | 0 | 0
2584 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Krishnarampur piped water supply scheme ( Mathurapur-I, Zone-X) including Operation & Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001199/2021-2022 | 5725/AD | 31/01/2022 | 365 | SUPRITI ENTERPRISE | 106.12 | 0 | 100
2585 | Alipore Division | Raidighi Sub-Division | Repairing of pump house-1 including boundary wall and approach road and plinth protection at Krishnarampur W/S Scheme, modified as Zone- X of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001903/2023-2024 | 434/RSD | 08/01/2024 | 60 | SUKUMAR HALDAR | 4.81 | 0 | 100
2586 | Alipore Division | Raidighi Sub-Division | Providing FHTC including parallel distribution pipeline at Zone- X of Mathurapur -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001966/2022-2023 | 12720/AD | 14/03/2023 | 45 | R.S.CONSTRUCTION CO. | 77.04 | 0 | 60
2587 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000641/2023-2024 | 245/AD | 15/01/2024 | 0 | Resource Division | 5.01 | 0 | 0
2588 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 m3 capacity OHR at Zone - III of Diamond Harbour - II Block to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIA) [No. of FHTC = 2400] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000364/2023-2024 | 1565/AD | 17/07/2023 | 904 | M/S. PROMILA CONSTRUCTION | 433.39 | 0 | 25
2589 | Alipore Division | Diamond Harbour Sub-Division | Road restoration work due to laying of 315 mm dia. distribution line and 315 mm dia. secondary grid from Kalitola more to Khordho FP School Zone No-III (B) of Diamond Harbour - II Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000870/2024-2025 | 4654/AD | 20/11/2024 | 45 | M/S SUBIR GHOSH | 12.61 | 0 | 100
2590 | Alipore Division | Diamond Harbour Sub-Division | Inter connection between secondary grid to distribution system to facilitate direct supply of water under Zone-III (B) of Diamond Harbour-II block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour Sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000872/2024-2025 | 4656/AD | 20/11/2024 | 30 | S.S. ENTERPRISE (II) | 6.58 | 0 | 0
2591 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIA at Diamond Harbour- II block for providing balance pipe lying works, road restoration works for new laid pipe etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001373/2024-2025 | 5518/AD | 28/12/2024 | 30 | NAZRUL ENTERPRISE | 11.28 | 0 | 0
2592 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-IIIB at Diamond Harbour- II block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001374/2024-2025 | 5519/AD | 28/12/2024 | 221 | M/S SUBIR GHOSH | 30.79 | 0 | 35
2593 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-IIIA of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001524/2023-2024 | 434/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
2594 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-III (Bhaduria, OHR Size-1500 ) within Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002093/2022-2023 | 327/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
2595 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IIIA at Bhadura of Diamond Harbour -II Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002405/2023-2024 | 1153/AD | 27/02/2024 | 60 | M/S. PROMILA CONSTRUCTION | 39.73 | 0 | 0
2596 | Alipore Division | Diamond Harbour Sub-Division | Inter connection of M.S. distribution pipeline and allied works related to Gap Closing at Bhadura Bridge in Diamond Harbour -II Zone - III under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/003146/2020-2021 | 252/DHSD | 25/11/2020 | 30 | SUPER SKILL | 4.71 | 0 | 95
2597 | Alipore Division | Diamond Harbour Sub-Division | Inter connection of M.S. distribution pipeline and allied works related to Gap Closing at Panarpole Bridge in Diamond Harbour -II Zone - III under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/003147/2020-2021 | 255/DHSD | 25/11/2020 | 20 | SUPER SKILL | 3.18 | 0 | 95
2598 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000220/2023-2024 | 2203/AD | 10/08/2023 | 0 | Resource Division | 19.99 | 0 | 0
2599 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000356/2023-2024 | 3220/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2600 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000427/2023-2024 | 3610/AD | 30/10/2023 | 0 | Resource Division | 1.23 | 0 | 0
2601 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000611/2023-2024 | 273/AD | 15/01/2024 | 0 | Resource Division | 16.32 | 0 | 0
2602 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000878/2023-2024 | 752/AD | 03/02/2024 | 0 | Resource Division | 2.46 | 0 | 0
2603 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIA) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000025/2025-2026 | 2011/AD | 28/04/2025 | 30 | HALDER & CO. | 8.53 | 0 | 0
2604 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 4 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIA) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000026/2025-2026 | 2012/AD | 28/04/2025 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.84 | 0 | 0
2605 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIA), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-I) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000255/2023-2024 | 1398/AD | 12/07/2023 | 45 | M/S. MA BHABANI CONSTRUCTION | 7.25 | 0 | 100
2606 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2430] (TSM/017473) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000356/2023-2024 | 1686/AD | 21/07/2023 | 810 | NEW STAR CONSTRUCTION | 132.25 | 0 | 25
2607 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IIA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017473) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000357/2023-2024 | 1687/AD | 21/07/2023 | 540 | NEW STAR CONSTRUCTION | 137.02 | 0 | 96
2608 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IIA), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001510/2023-2024 | 4748/AD | 19/12/2023 | 405 | MALANCHA CONSTRUCTION | 7.06 | 0 | 100
2609 | Alipore Division | Canning Sub-division | Sinking of 02 (two) Nos. of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using UPVC pipe (CD) and UPVC Deep well screen (RDS) pipe with ribs pipe at Tube Well No. - 3 of Augmentation of Kalaria (Zone-IIA) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001673/2022-2023 | 11484/AD | 15/02/2023 | 45 | B.K. ENTERPRISE. | 40.73 | 0 | 100
2610 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IIA) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001949/2022-2023 | 10893/AD | 04/02/2023 | 45 | SIRCON ENGINEERING SERVICES | 6.76 | 0 | 90
2611 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000066/2023-2024 | 269/AD | 24/04/2023 | 0 | Resource Division | 64.87 | 0 | 0
2612 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for Dharmatala (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1544] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000028/2023-2024 | 156/AD | 18/04/2023 | 836 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 244.1 | 0 | 20
2613 | Alipore Division | Canning Sub-division | Laying of pipeline within some uncovered habitation for Functional Household Tap Connection at Augmentation of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000218/2023-2024 | 1023/AD | 13/06/2023 | 630 | GOUTAM HALDAR (I) | 12.65 | 0 | 100
2614 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Dharmatala W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001348/2022-2023 | 10215/AD | 19/01/2023 | 60 | B.K. ENTERPRISE. | 59.91 | 0 | 90
2615 | Alipore Division | Canning Sub-division | Construction of Boundary Wall and Renovation of Pump House No. 4 at Dharmatala W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001406/2023-2024 | 1145/CSD | 01/11/2023 | 30 | GOUTAM HALDAR (I) | 3.8 | 0 | 100
2616 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001582/2022-2023 | 10781/AD | 03/02/2023 | 45 | MAA SOLAR ENTERPRISE | 7.02 | 0 | 100
2617 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001583/2022-2023 | 10782/AD | 03/02/2023 | 45 | MAA SOLAR ENTERPRISE | 7.02 | 0 | 100
2618 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Dharmatala (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001822/2022-2023 | 12337/AD | 06/03/2023 | 45 | M/S ARIYAN ENTERPRISE | 7.35 | 0 | 100
2619 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Dharmatala (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001840/2022-2023 | 10939/AD | 06/02/2023 | 45 | TECH VISION | 4.2 | 0 | 0
2620 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
2621 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000068/2023-2024 | 271/AD | 24/04/2023 | 0 | Resource Division | 16.49 | 0 | 0
2622 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Garan Bose Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001301/2020-2021 | 2275/AD | 12/10/2020 | 365 | M/S. BLUE BELL ENTERPRISE | 136.08 | 0 | 63
2623 | Alipore Division | Canning Sub-division | inking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Goran Bose W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001670/2022-2023 | 11481/AD | 15/02/2023 | 45 | RAHAMAN ENTERPRISE | 39.19 | 0 | 0
2624 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001712/2022-2023 | 11676/AD | 20/02/2023 | 45 | BABAMONI CONSTRUCTION | 7.1 | 0 | 0
2625 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (620 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Goranbose Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002003/2022-2023 | 12817/AD | 16/03/2023 | 45 | MS SINHA ROY & CO | 49.13 | 0 | 40
2626 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002043/2022-2023 | 13043/AD | 24/03/2023 | 45 | SUNNY CONSTRUCTION | 42.98 | 0 | 40
2627 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000040/2023-2024 | 246/AD | 24/04/2023 | 0 | Resource Division | 81.96 | 0 | 0
2628 | Alipore Division | Diamond Harbour Sub-Division | Construction of Pump House at CWR (200 Cumec) within Padmapur Mouza of Zone-VI under Falta Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000096/2025-2026 | 2525/AD | 30/05/2025 | 30 | K.P. CONSTRUCTION | 5.74 | 0 | 0
2629 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe laying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000389/2025-2026 | 3374/AD | 16/07/2025 | 45 | THE TOWER CONSTRUCTION | 40.87 | 0 | 0
2630 | Alipore Division | Diamond Harbour Sub-Division | Construction of 1 no. CWR (200 Cum) at Padmapur Mouza due to improvement of water supply at 5 nos. Mouza i.e. Baidyakhadi, Pakurtala, Padmapur, Abad simulguange and Ahamedpur of Mallickpur G.P. Within Falta Zone-VI Of Falta Block under Diamond Harbour Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001401/2024-2025 | 5525/AD | 28/12/2024 | 450 | M/S B.N.ENTERPRISES | 66.07 | 0 | 0
2631 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VI at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001406/2024-2025 | 5551/AD | 30/12/2024 | 45 | SAFTI PRIVATE LIMITED | 35.97 | 0 | 0
2632 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-VI of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 1200] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001456/2023-2024 | 2158/AD | 09/08/2023 | 90 | MANAS CHATTERJEE | 224.55 | 0 | 75
2633 | Alipore Division | Diamond Harbour Sub-Division | Re-layig of damaged distribution pipeline along Falta-Nainan main road due to laying of primary grid pipeline at Falta Zone-VI under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003151/2020-2021 | 263/DHSD | 26/11/2020 | 30 | CONCORD PROJECTS PRIVATE LIMITED | 4.76 | 0 | 100
2634 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000359/2023-2024 | 3223/AD | 04/10/2023 | 0 | Resource Division | 0.31 | 0 | 0
2635 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000851/2023-2024 | 789/AD | 03/02/2024 | 0 | Resource Division | 14.78 | 0 | 0
2636 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 3 of Augmentation of Gosaba W/S Scheme (Zone-I), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000183/2025-2026 | 546/CSD | 30/04/2025 | 30 | M/S JBL CONSTRUCTION | 2.27 | 0 | 0
2637 | Alipore Division | Canning Sub-division | Laying of additional pipe line at Augmentation of Gosaba W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000309/2024-2025 | 2690/AD | 24/06/2024 | 480 | B.S. CONSTRUCTION | 56.54 | 0 | 30
2638 | Alipore Division | Canning Sub-division | Construction of OHR (250 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000484/2023-2024 | 1997/AD | 04/08/2023 | 390 | DIVINE | 617.63 | 0 | 65
2639 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Gosaba (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001230/2024-2025 | 5211/AD | 16/12/2024 | 45 | SARADA CONSTRUCTION | 32.99 | 0 | 0
2640 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001888/2022-2023 | 10940/AD | 06/02/2023 | 45 | M/S R.DUTTA & CO. | 6.94 | 0 | 0
2641 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000010/2023-2024 | 112/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
2642 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000132/2023-2024 | 843/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
2643 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000406/2023-2024 | 360/AD | 19/01/2024 | 0 | Resource Division | 15.52 | 0 | 0
2644 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000720/2023-2024 | 542/AD | 25/01/2024 | 0 | Resource Division | 161.43 | 0 | 0
2645 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 1 of Phulmalancha W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000279/2025-2026 | 684/CSD | 26/05/2025 | 30 | BANERJEE ENTERPRISE | 2.44 | 0 | 0
2646 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Phulmalancha W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000280/2025-2026 | 685/CSD | 26/05/2025 | 30 | BANERJEE ENTERPRISE | 2.45 | 0 | 0
2647 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000030/2023-2024 | 378/AD | 02/05/2023 | 0 | Resource Division | 35.29 | 0 | 0
2648 | Alipore Division | Canning Sub-division | Sinking of 300mm x 200mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 of Adhia Water Supply Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000059/2022-2023 | 795/AD | 12/05/2022 | 30 | AQUATECH ENGINEERS | 24.68 | 0 | 62
2649 | Alipore Division | Canning Sub-division | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Adhia piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. [SM/07596 & SM/15477] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000690/2024-2025 | 4271/AD | 28/10/2024 | 270 | MAMON ENTERPRISE AND CONSTRUCTION | 128.22 | 0 | 0
2650 | Alipore Division | Canning Sub-division | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001185/2023-2024 | 877/CSD | 31/08/2023 | 182 | SAILEN CHANDRA DAS | 0.86 | 0 | 100
2651 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Adhia W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001347/2022-2023 | 10943/AD | 06/02/2023 | 30 | SNEHA CONSTRUCTION | 19.49 | 0 | 0
2652 | Alipore Division | Canning Sub-division | Bypass arrangement on risingmain, installation of air valve, restoration of damage road & other works at Adhia W/S Scheme,Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001574/2020-2021 | 1062/CSD | 27/11/2020 | 30 | SUKANTA HALDER | 1.48 | 0 | 96
2653 | Alipore Division | Canning Sub-division | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.03.2023 to 31.08.2023 | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002172/2022-2023 | 1370/CSD | 27/02/2023 | 184 | SAILEN CHANDRA DAS | 0.86 | 0 | 0
2654 | Alipore Division | Canning Sub-division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002175/2022-2023 | 1354/CSD | 20/02/2023 | 365 | SWAPAN KUMAR MANDAL | 4.8 | 0 | 12
2655 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000118/2022-2023 | 3045/AD | 28/09/2023 | 0 | Resource Division | 51.93 | 0 | 0
2656 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000725/2023-2024 | 547/AD | 25/01/2024 | 0 | Resource Division | 55.77 | 0 | 0
2657 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Chharanekhali & Uttar Sonakhali), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000088/2022-2023 | 279/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.76 | 0 | 85
2658 | Alipore Division | Canning Sub-division | Construction of Sluice Valve Chamber and protection of pipe line work at Augmentation of Harbhangi W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000361/2024-2025 | 731/CSD | 28/06/2024 | 30 | A.M. ENTERPRISE | 1.47 | 0 | 99
2659 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (620 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Harbhangi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002004/2022-2023 | 12818/AD | 16/03/2023 | 45 | RAKTIM ENTERPRISE | 45.51 | 0 | 75
2660 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Harbhangi W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002044/2022-2023 | 13044/AD | 24/03/2023 | 45 | A.S.A.CONSTRUCTION AND CONSULTANT | 23.84 | 0 | 0
2661 | Alipore Division | Canning Sub-division | Surging of 03 nos. Big dia Tubewell of Harbhangi W/S Scheme under JJM, Block - Basanti under Canning Sub-Division under Alipore Division P.H.Engg. Dte. (TW-1, 2 & 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002976/2024-2025 | 32./CSD | 09/01/2025 | 30 | FORTUNE ENGINEERING | 4.3 | 0 | 0
2662 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000115/2022-2023 | 247/AD | 24/04/2023 | 0 | Resource Division | 195.03 | 0 | 0
2663 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000144/2023-2024 | 848/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
2664 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000100/2023-2024 | 503/AD | 11/05/2023 | 15 | S.P. CONSTRUCTION (I) | 18.49 | 0 | 0
2665 | Alipore Division | Canning Sub-division | Construction of 200 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-I) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1893] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001071/2023-2024 | 3508/AD | 16/10/2023 | 300 | PATHIK PABAN NANDI | 512.98 | 0 | 60
2666 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001847/2022-2023 | 11814/AD | 23/02/2023 | 45 | TECH VISION | 3.82 | 0 | 0
2667 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001975/2022-2023 | 12638/AD | 13/03/2023 | 45 | M/S. BISWAS CONSTRUCTION(I) | 8.91 | 0 | 100
2668 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001978/2022-2023 | 12639/AD | 13/03/2023 | 507 | M/S. BISWAS CONSTRUCTION(I) | 8.6 | 0 | 100
2669 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002008/2022-2023 | 12914/AD | 21/03/2023 | 499 | MONDAL CONSTRUCTION (SANDESHKHALI) | 8.61 | 0 | 100
2670 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002035/2022-2023 | 13031/AD | 24/03/2023 | 120 | SADIKUL ISLAM | 65.92 | 0 | 90
2671 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000051/2023-2024 | 258/AD | 24/04/2023 | 0 | Resource Division | 44.96 | 0 | 0
2672 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000413/2023-2024 | 369/AD | 19/01/2024 | 0 | Resource Division | 11.66 | 0 | 0
2673 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) L027-Sagarsangha Math on T03 to Dudhnai(WB/02/480) 2) Construction of Road from Fultala Chow More to Block-A, B.C,D to Ramkrisna Polly to Mohamonilala Greater Kolkata Enginnering College to Ramnagar Bazar via Dhapdhopi road Shakharipukur under Baruipur Block. | AE BSD,Assistant Engineer | Junior Engineer | BILL/01676/2024-2025 | BP-2024-25-781 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.78 | 0 | 0
2674 | Alipore Division | Baruipur Sub-Division | Road restoration 1) Chandakhali to Dhapdhapi More 2) Ramnagar Bazar to Matiar Dhali House 3) Doctor More to Madanpur Ashok Sangha CIub 4) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01667/2024-2025 | BP-2024-25-774 | 23/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 7.11 | 0 | 0
2675 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1416] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000292/2023-2024 | 1502/AD | 15/07/2023 | 600 | JYOTY SOLAR POWER | 498.31 | 0 | 22
2676 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001928/2022-2023 | 11801/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 3.75 | 0 | 95
2677 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001981/2022-2023 | 12642/AD | 13/03/2023 | 45 | SRI DURGA ENTERPRISE | 8.88 | 0 | 0
2678 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001982/2022-2023 | 12643/AD | 13/03/2023 | 45 | SRI DURGA ENTERPRISE | 8.57 | 0 | 0
2679 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002037/2022-2023 | 13033/AD | 24/03/2023 | 45 | MD JIYAUL HOQUE | 43.95 | 0 | 100
2680 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000045/2023-2024 | 252/AD | 24/04/2023 | 0 | Resource Division | 20.97 | 0 | 0
2681 | Alipore Division | Canning Sub-division | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Sabek Mahisahara and Adjoining Mouzas (Chunpuri), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000279/2024-2025 | 2494/AD | 14/06/2024 | 353 | TARUN KUMAR LAHA | 48.15 | 0 | 15
2682 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for the Augmentation of Sabek Mahisahara & Adjoining Mouzas (Chunpuri) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ Pump House No. - I] (3rd Call) | Assistant Engineer, Canning sub division |  | ORD/000538/2024-2025 | 3709/AD | 12/09/2024 | 45 | NIJAMUDDIN ENTERPRISE | 6.97 | 0 | 0
2683 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 300 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for the Augmentation of Kaorakhali & Adjoining Mouzas (Bakultala) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000345/2024-2025 | 2786/AD | 01/07/2024 | 194 | AQUATECH ENGINEERS | 34.47 | 0 | 98
2684 | Alipore Division | Canning Sub-division | Laying distribution system with supply of specials for Augmentation of Ground Water Based Piped Water Supply Scheme for Kaorakhali & Adjoining Mouzas (Bakultala), Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000372/2024-2025 | 2967/AD | 15/07/2024 | 290 | CREATIVE | 137.23 | 0 | 60
2685 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 02 (two) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Parbatipur Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000013/2021-2022 | 3021/AD | 02/11/2021 | 365 | M/S A.K. GHATAK | 83.3 | 0 | 99
2686 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Parbatipur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ III) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000416/2023-2024 | 775/CSD | 02/08/2023 | 30 | JOY MAA TARA ENTERPRISE | 4.57 | 0 | 0
2687 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Parbatipur Water Supply Scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001466/2022-2023 | 1285/CSD | 31/01/2023 | 30 | M.P. ENTERPRISE | 4.81 | 0 | 99
2688 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - III) having village with maximum 105 nos. households, Block - Canning -II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000661/2022-2023 | 6166/AD | 01/11/2022 | 105 | SWASTIK CONSTRUCTION | 37.67 | 0 | 79
2689 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001912/2022-2023 | 5152/AD | 21/09/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.31 | 0 | 0
2690 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000180/2023-2024 | 1133/AD | 22/06/2023 | 0 | Resource Division | 0.65 | 0 | 0
2691 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Piprakhali PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000070/2023-2024 | 51/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2692 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Piprakhali PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11846) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000189/2024-2025 | 924/AD | 05/03/2025 | 60 | M/S PARAMESWAR CHOWDHURY | 55.38 | 0 | 0
2693 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Piprakhali W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000270/2023-2024 | 1420/AD | 13/07/2023 | 45 | M/S PARAMESWAR CHOWDHURY | 39.73 | 0 | 100
2694 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Piprakhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000342/2022-2023 | 4069/AD | 18/08/2022 | 45 | M. R. ENTERPRISE (I) | 36.69 | 0 | 50
2695 | Alipore Division | Kakdwip Sub-Division | Laying of 63 mm dia. UPVC pipe line for providing FHTC to the household under JJM at Piprakhali W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000425/2023-2024 | 1913/AD | 01/08/2023 | 20 | BABUN ENTERPRISE | 4.86 | 0 | 100
2696 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PIPRAKHALI PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000468/2022-2023 | 2491/AD | 27/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.04 | 0 | 100
2697 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Piprakhali Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000679/2022-2023 | 5978/AD | 20/10/2022 | 300 | PARAMESWAR CHOWDHURY | 223.76 | 0 | 52
2698 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Piprakhali W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000979/2023-2024 | 2998/AD | 26/09/2023 | 30 | M/S M.B.ENTERPRISE | 9.02 | 0 | 0
2699 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Piprakhali W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11846) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001047/2024-2025 | 4968/AD | 04/12/2024 | 30 | SIMPLEX DRILLING CO. | 20.37 | 0 | 0
2700 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Piprakhali W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001054/2023-2024 | 3373/AD | 11/10/2023 | 45 | M/S. TRIPATHI & CO. | 26.76 | 0 | 0
2701 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
2702 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000091/2023-2024 | 537/AD | 12/05/2023 | 0 | Resource Division | 3.86 | 0 | 0
2703 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000518/2023-2024 | 4940/AD | 22/12/2023 | 0 | Resource Division | 9.94 | 0 | 0
2704 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000585/2023-2024 | 59/AD | 03/01/2024 | 0 | Resource Division | 0.67 | 0 | 0
2705 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000949/2023-2024 | 1683/AD | 22/03/2024 | 0 | Resource Division | 23.18 | 0 | 0
2706 | Alipore Division | Baruipur Sub-Division | Road restoration of L023- Shyamnagar F.P. School to Purba Gobindapur PWD Road | AE BSD,Assistant Engineer | Junior Engineer | BILL/01783/2024-2025 | BP-2024-25-808 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 14.73 | 0 | 0
2707 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 219.10 mm dia. (OD) M.S. distribution line for crossing of Karanjali Canal at Karanjali bridge (Node point 249 to 253) for Providing distribution network under the Augmentation scheme of Kulpi Zone-IX within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District-South-24 Parganas under Diamond Harbour Sub- Division, of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000069/2025-2026 | 2258/AD | 14/05/2025 | 30 | SRIJON ENTERPRISE | 39.56 | 0 | 0
2708 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 600 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IX at Krishnachandrapur of Kulpi Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000331/2024-2025 | 2748/AD | 26/06/2024 | 90 | M/S GHOSH & CO. | 60.27 | 0 | 60
2709 | Alipore Division | Diamond Harbour Sub-Division | Restoration of W.B.M damaged due to laying of pipes from Raghunathpur more to Rajarampur F.P School under Kulpi Zone X under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000349/2025-2026 | 3130/AD | 03/07/2025 | 30 | SAMIM AHMED | 11.64 | 0 | 100
2710 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for fundation of different capacities for the proposed R.C.C. Over Head Reservoir at (Zone IX, OHR Size-450 Cum. Mouza - Karanjali ) of Kulpi Block and at Moukhali W/S Scheme (OHR Size-350 Cum., Mouza - Moukhali) of Budge Budge-I Block under "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas" under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000365/2022-2023 | 198/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 30
2711 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IX at Kulpi block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000561/2023-2024 | 3736/AD | 03/11/2023 | 879 | M/S GHOSH & CO. | 905.65 | 0 | 100
2712 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IX of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001022/2022-2023 | 295/DHSD | 15/09/2022 | 30 | CHAYANIKA ENGINEERING CONSULTANCY | 3.59 | 0 | 98
2713 | Alipore Division | Diamond Harbour Sub-Division | Repairing of boundary wall at Pump House No-2 under Karanjali PWSS under Zone- IX of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001369/2024-2025 | 5498/AD | 27/12/2024 | 30 | SANKAR HALDER | 5.36 | 0 | 100
2714 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone No-X of Kulpi Block under Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002490/2024-2025 | 781/AD | 25/02/2025 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 21.59 | 0 | 0
2715 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000212/2023-2024 | 2021/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
2716 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000364/2023-2024 | 3228/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
2717 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000629/2023-2024 | 291/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
2718 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000671/2023-2024 | 424/AD | 22/01/2024 | 0 | Resource Division | 24.29 | 0 | 0
2719 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000897/2023-2024 | 791/AD | 03/02/2024 | 0 | Resource Division | 11.21 | 0 | 0
2720 | Alipore Division | Kakdwip Sub-Division | Relaying and repairing of pipe line for FHTC work of Budhkhali, Madhukhali, Golabari Mouza at Budhkhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000029/2022-2023 | 515/AD | 26/04/2022 | 30 | MS SINHA ROY & CO | 38.8 | 0 | 100
2721 | Alipore Division | Kakdwip Sub-Division | Relaying of damaged distribution System by new for Providing Functional Household Tap Connection (FHTC) to the remaining households in connection with Jal Swapna for Budhakhali (Zone-I) W/S Scheme Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000109/2021-2022 | 1193/AD | 07/07/2021 | 60 | ADITYA HAZRA | 75.75 | 0 | 93
2722 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Budhakhali Zone-I (Part - I & II) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001098/2022-2023 | 8433/AD | 15/12/2022 | 60 | M/S. UMA CONSTRUCTION | 88.4 | 0 | 100
2723 | Alipore Division | Kakdwip Sub-Division | Construction of Rising Main, Platform, Road Restoration and Y junction for Augmentation of Rajnagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13875) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000406/2024-2025 | 3189/AD | 31/07/2024 | 60 | UCON (II) | 45.01 | 0 | 0
2724 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the remaining households of Habitation: Pulaha and Pulastha of Rajnagar W/S Scheme, Block - Namkhana, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000453/2020-2021 | 841/KSD | 16/10/2020 | 45 | ASHIS ENTERPRISE | 4.67 | 3.43 | 0
2725 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the remaining households of Habitation: Angira and Atri of Rajnagar W/S Scheme, Block - Namkhana, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte.(Part-1) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000461/2020-2021 | 851/KSD | 16/10/2020 | 45 | ASHIS ENTERPRISE | 4.69 | 3.75 | 0
2726 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000799/2023-2024 | 644/AD | 30/01/2024 | 0 | Resource Division | 7.78 | 0 | 0
2727 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Majherpara, Laskarpara and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000209/2020-2021 | 644/KSD | 19/08/2020 | 15 | SARADA CONSTRUCTION | 4.48 | 0 | 95
2728 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Paschimpara, Panupara and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000210/2020-2021 | 645/KSD | 19/08/2020 | 15 | G.M. ENTERPRISE | 4.48 | 0 | 0
2729 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Ramtanupara, Tulsitala and others of Ramtanunagar W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000211/2020-2021 | 646/KSD | 19/08/2020 | 15 | PIJUSH KANTI TRIPATHI | 4.48 | 0 | 0
2730 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Ramtanupara and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000448/2020-2021 | 834/KSD | 16/10/2020 | 45 | FORTUNE ENGINEERING | 4.45 | 0 | 96
2731 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Madhya Para and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000452/2020-2021 | 838/KSD | 16/10/2020 | 45 | FORTUNE ENGINEERING | 3.59 | 0 | 97
2732 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation - Muslim Para and others of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000454/2020-2021 | 842/KSD | 16/10/2020 | 45 | SARADA CONSTRUCTION | 3.7 | 0 | 96
2733 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. existing big dia Tubewell of Ramtanunagar, Block- Kakdwip and Debnibus W/S Scheme, Block- Namkhana for smooth water supply in existing FHTC under JJM under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000508/2024-2025 | 3608/AD | 06/09/2024 | 30 | S.K.GOLUI | 4.94 | 0 | 100
2734 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.07.2024 to 30.09.2024 - 3 months] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000534/2024-2025 | 2523/AD | 18/06/2024 | 92 | PARBATI MONDAL | 1.2 | 0 | 100
2735 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line for FHTC work of Ramtanunagar W/S Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000902/2021-2022 | 762/KSD | 29/11/2021 | 30 | SARADA CONSTRUCTION | 4.58 | 0 | 100
2736 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Govt. Officials under Alipore Division, PHE Dte. for the period from 01.07.2024 to 30.06.2025 [Actually work order valid for the period from 01.10.2024 to 31.12.2024 - 3 months] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/000985/2024-2025 | 4002/AD | 28/09/2024 | 91 | PARBATI MONDAL | 1.2 | 0 | 75
2737 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for official use of the Assistant Engineer, Kakdwip Sub Division, P.H.E. Dte. for the period from 01.02.2023 to 31.07.2023 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/002176/2022-2023 | 652/KSD | 31/01/2023 | 181 | PIKASU BOSE | 2.39 | 0 | 90
2738 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000827/2023-2024 | 672/AD | 30/01/2024 | 0 | Resource Division | 7.13 | 0 | 0
2739 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Uttar Durgapur and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000204/2020-2021 | 641/KSD | 19/08/2020 | 15 | AVIRUP CONSTRUCTION | 4.48 | 3.11 | 0
2740 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000206/2020-2021 | 642/KSD | 19/08/2020 | 15 | MAA LAXMI ENTERPRISE | 4.48 | 0 | 90
2741 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Durgapur and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000208/2020-2021 | 643/KSD | 19/08/2020 | 15 | M/S B. ENTERPRISE | 4.48 | 0 | 90
2742 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No.- 184 and others of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000447/2020-2021 | 833/KSD | 16/10/2020 | 45 | MAA LAXMI ENTERPRISE | 3.26 | 0 | 90
2743 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No. -180 of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000449/2020-2021 | 835/KSD | 16/10/2020 | 45 | M/S B. ENTERPRISE | 4.51 | 4.46 | 0
2744 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No.- 185 and others of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000450/2020-2021 | 836/KSD | 16/10/2020 | 45 | MAA LAXMI ENTERPRISE | 4.01 | 0 | 90
2745 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households at Booth No. -180 of Hesamabad W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000455/2020-2021 | 843/KSD | 16/10/2020 | 45 | M/S B. ENTERPRISE | 4.56 | 4.52 | 0
2746 | Alipore Division | Kakdwip Sub-Division | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 8.23 | 0 | 100
2747 | Alipore Division | Kakdwip Sub-Division | Surging and repairing of 2no Tube well of Hesamabad Water Supply Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000596/2022-2023 | 5921/AD | 19/10/2022 | 15 | S.K.GOLUI | 7.37 | 0 | 100
2748 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2749 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, boundary wall and approach road at 2nd Tubewell site for Hesamabad W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07576) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002159/2024-2025 | 1989/KSD | 23/12/2024 | 25 | IMAGINEER VENTURES | 2.06 | 0 | 0
2750 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002501/2020-2021 | 611/KSD | 12/08/2020 | 15 | MAA LAXMI ENTERPRISE | 4.47 | 0 | 90
2751 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation: Hesamabad and others of Hesamabad W/S Scheme, Block - Kakdwip, under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. (PART-III) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002502/2020-2021 | 627/KSD | 13/08/2020 | 15 | MAA LAXMI ENTERPRISE | 4.48 | 0 | 90
2752 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000280/2023-2024 | 3079/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2753 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000839/2023-2024 | 684/AD | 30/01/2024 | 0 | Resource Division | 6.8 | 0 | 0
2754 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Hesamabad W/S Scheme (Phase-A), Chandipur W/S Scheme (Phase-A), Gangadharpur W/S Scheme (Phase-A) & Nebutala W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 512/AD, 24.08.21, T.No. 1761/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | VCH/002606/2021-2022 | BP-2021-22-509 | 22/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 4.71 | 0 | 0
2755 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Dwariknagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001369/2020-2021 | 5367/AD | 19/02/2021 | 365 | M/S. PROMILA CONSTRUCTION | 98.02 | 0 | 75
2756 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000796/2023-2024 | 641/AD | 30/01/2024 | 0 | Resource Division | 5.4 | 0 | 0
2757 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 350 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. -4 of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000475/2022-2023 | 5526/AD | 29/09/2022 | 30 | SIMPLEX DRILLING CO. | 18.32 | 0 | 0
2758 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000607/2020-2021 | 846/CSD | 12/10/2020 | 45 | SUSHANTA MANDAL | 4.73 | 4.73 | 0
2759 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000608/2020-2021 | 848/CSD | 12/10/2020 | 45 | SUKANTA HALDER | 4.74 | 4.72 | 0
2760 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000631/2020-2021 | 845/CSD | 12/10/2020 | 45 | PRASANTA MONDAL | 4.74 | 0 | 100
2761 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000650/2020-2021 | 847/CSD | 12/10/2020 | 45 | KAMALA ENTERPRISE (I) | 4.72 | 4.71 | 0
2762 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 09 (nine) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chunakhali Water Supply Scheme (Zone-I) including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000848/2021-2022 | 3198/AD | 11/11/2021 | 365 | UNITED BUILDERS | 99.47 | 0 | 63
2763 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001429/2020-2021 | 995/CSD | 13/11/2020 | 45 | L.N. ENTERPRISE | 4.6 | 4.59 | 100
2764 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001430/2020-2021 | 996/CSD | 13/11/2020 | 45 | L.N. ENTERPRISE | 4.64 | 4.62 | 100
2765 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001440/2020-2021 | 965/CSD | 07/11/2020 | 45 | M/S R.K.ENTERPRISE | 4.62 | 4.6 | 100
2766 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001441/2020-2021 | 966/CSD | 07/11/2020 | 45 | L.N. ENTERPRISE | 4.7 | 4.68 | 100
2767 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001443/2020-2021 | 997/CSD | 13/11/2020 | 45 | SUSHANTA MANDAL | 4.71 | 0 | 0
2768 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001444/2020-2021 | 1007/CSD | 13/11/2020 | 45 | L.N. ENTERPRISE | 4.67 | 4.65 | 100
2769 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001445/2020-2021 | 998/CSD | 13/11/2020 | 45 | M/S M.G.CONSTRUCTION | 4.72 | 4.71 | 100
2770 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001446/2020-2021 | 999/CSD | 13/11/2020 | 45 | SUSHANTA MANDAL | 4.79 | 4.78 | 100
2771 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001447/2020-2021 | 1008/CSD | 13/11/2020 | 45 | SUSHANTA MANDAL | 4.63 | 4.62 | 100
2772 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001448/2020-2021 | 1000/CSD | 13/11/2020 | 45 | SUKANTA HALDER | 4.75 | 4.74 | 100
2773 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001449/2020-2021 | 1009/CSD | 13/11/2020 | 45 | SUKANTA HALDER | 4.69 | 0 | 0
2774 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001450/2020-2021 | 1010/CSD | 13/11/2020 | 45 | SURYA ENTERPRISE | 4.74 | 4.41 | 100
2775 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IV) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001452/2020-2021 | 1001/CSD | 13/11/2020 | 45 | M/S M.G.CONSTRUCTION | 4.72 | 4.71 | 100
2776 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001453/2020-2021 | 1002/CSD | 13/11/2020 | 45 | C.S. CONSTRUCTION | 4.79 | 4.79 | 100
2777 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001454/2020-2021 | 1011/CSD | 13/11/2020 | 45 | NAZRUL ENTERPRISE | 4.72 | 0 | 0
2778 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001458/2020-2021 | 1012/CSD | 13/11/2020 | 45 | JAGANNATH ENTERPRISE | 4.77 | 0 | 100
2779 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001543/2020-2021 | 1202/CSD | 15/12/2020 | 45 | SUKANTA HALDER | 4.78 | 0 | 0
2780 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Baria of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ IX) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001544/2020-2021 | 1203/CSD | 15/12/2020 | 45 | SUSHANTA MANDAL | 4.73 | 0 | 0
2781 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Bugulakhali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001549/2020-2021 | 1204/CSD | 15/12/2020 | 45 | SARKAR ENTERPRISE | 4.78 | 4.76 | 100
2782 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ V) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001550/2020-2021 | 1205/CSD | 15/12/2020 | 45 | SUKANTA HALDER | 4.78 | 4.76 | 100
2783 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Purba Bayar Sing of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001551/2020-2021 | 1206/CSD | 15/12/2020 | 45 | C.S. CONSTRUCTION | 4.75 | 4.74 | 100
2784 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VI) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001552/2020-2021 | 1207/CSD | 15/12/2020 | 45 | MODERN CONSTRUCTION | 4.73 | 4.71 | 100
2785 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001553/2020-2021 | 1208/CSD | 15/12/2020 | 45 | KUNDU CONSTRUCTION CO. | 4.7 | 0 | 0
2786 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Sachea Khali of Chunakhali Water Supply Scheme (Zone-II), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase ¿ VIII) | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001555/2020-2021 | 1209/CSD | 15/12/2020 | 45 | HALDER & CO. | 4.65 | 0 | 0
2787 | Alipore Division | Canning Sub-division | Relaying and repairing of damaged pipeline for FHTC at Chunakhali W/S Scheme at Khanka Sarif More to Sachiakhali FP School of Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001619/2020-2021 | 1345/CSD | 04/01/2021 | 30 | MODERN CONSTRUCTION | 4.82 | 0 | 100
2788 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme at Laskarpara to PWD Road and H/O Ganesh Sardar to H/O Dinanath Sardar of Purba Bayar Sing Mouza and Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001632/2020-2021 | 1348/CSD | 06/01/2021 | 30 | MODERN CONSTRUCTION | 4.68 | 0 | 100
2789 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme Chunakhali Primary School to H/O Shyamal Das and H/O Prasanta Das to Chowmatha at Buglakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001633/2020-2021 | 1349/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.73 | 0 | 100
2790 | Alipore Division | Canning Sub-division | Repairing damaged pipeline for FHTC at Chunakhali W/S Scheme at Buglakhali Mouza, Purba Bayar Sing Mouza, Sachiakhali Mouza and Baria Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001637/2020-2021 | 1350/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.74 | 0 | 100
2791 | Alipore Division | Canning Sub-division | Construction of 400 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing )with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Adhia piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. [SM/07596 & SM/15477] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000690/2024-2025 | 4271/AD | 28/10/2024 | 270 | MAMON ENTERPRISE AND CONSTRUCTION | 128.22 | 0 | 0
2792 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Adhia Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001306/2020-2021 | 2223/AD | 08/10/2020 | 365 | M/S. MIHIR KUMAR NASKAR | 85.78 | 27.8 | 75
2793 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Bhaleya Water Supply Scheme, Block - Canning-I, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001217/2020-2021 | 1619/AD | 28/08/2020 | 365 | PUTUL RANI MAITY | 86.44 | 35.93 | 92
2794 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dakshin Para (Part) of Khasramkarchar W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000406/2020-2021 | 777/KSD | 14/10/2020 | 45 | M/S. M.S. ENTERPRISE | 4.78 | 4.44 | 0
2795 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Khasramkarchar (Part) of Khasramkarchar W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000418/2020-2021 | 795/KSD | 15/10/2020 | 45 | M/S BABUSONA ENTERPRISE | 4.79 | 4.46 | 0
2796 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Khas Ramkarchar (Phase-B) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000418/2023-2024 | 1907/AD | 01/08/2023 | 30 | FORTUNE ENGINEERING | 25.22 | 0 | 100
2797 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Muslim Para (Part) of Khasramkarchar W/S Scheme, Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000437/2020-2021 | 823/KSD | 16/10/2020 | 45 | M/S. PAPIYA ENTERPRISE | 3.93 | 3.56 | 0
2798 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Khas Ramkarchar W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000526/2023-2024 | 352/KSD | 09/08/2023 | 470 | S.K.GOLUI | 3.55 | 0 | 100
2799 | Alipore Division | Kakdwip Sub-Division | Construction of approach road, earth work and other allied work of Khas Ramkarchar Water supply scheme, Block-Sagar under Kakdwip Sub division of Alipore Division, P.H.E Dte. (SM/18871) (SM/07756) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002275/2024-2025 | 580/AD | 13/02/2025 | 30 | M/S RELIABLE ENTERPRISE | 12.55 | 0 | 0
2800 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000334/2023-2024 | 3149/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2801 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000713/2023-2024 | 483/AD | 24/01/2024 | 0 | Resource Division | 8.91 | 0 | 0
2802 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Srikrishnanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/09435) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000206/2024-2025 | 2589/AD | 19/06/2024 | 45 | SARADA CONSTRUCTION | 34.89 | 0 | 0
2803 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Srikrishnanagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000400/2020-2021 | 3855/AD | 03/12/2020 | 365 | L.N. ENTERPRISE | 27.43 | 0 | 100
2804 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SRIKRISHNANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000498/2022-2023 | 314/AD | 13/04/2022 | 45 | LEMNISCATE | 1.79 | 0 | 0
2805 | Alipore Division | Kakdwip Sub-Division | Laying distribution system along with rising main for Augmentation of Srikrishnanagar Water Supply Scheme, Block - Kakdwip under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001483/2021-2022 | 6393/AD | 02/03/2022 | 60 | SARADA CONSTRUCTION | 71.83 | 0 | 98
2806 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2807 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000056/2022-2023 | 3915/AD | 12/08/2022 | 0 | Resource Division | 9.19 | 0 | 0
2808 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000267/2023-2024 | 3065/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2809 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000673/2023-2024 | 439/AD | 24/01/2024 | 0 | Resource Division | 2.22 | 0 | 0
2810 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000828/2023-2024 | 673/AD | 30/01/2024 | 0 | Resource Division | 4.19 | 0 | 0
2811 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Haradhanpur Water Supply scheme, Block - Sagar, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001142/2021-2022 | 5531/AD | 20/01/2022 | 365 | UNIVERSAL CORPORATION | 68.89 | 0 | 97
2812 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.02.2023 to 31.07.2023. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/002177/2022-2023 | 653/KSD | 31/01/2023 | 181 | BADSHA ALOM | 2.39 | 0 | 70
2813 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000014/2022-2023 | 1169/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
2814 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000016/2021-2022 | 5622/AD | 25/01/2022 | 0 | Resource Division | 6.19 | 0 | 0
2815 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000682/2023-2024 | 452/AD | 24/01/2024 | 0 | Resource Division | 3.06 | 0 | 0
2816 | Alipore Division | Raidighi Sub-Division | Remodeling of Distribution System of Krishnachandrapur PWS Scheme as Zone-III of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000034/2022-2023 | 597/AD | 28/04/2022 | 30 | M/S B.M. CONSTRUCTION | 95.84 | 0 | 50
2817 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - III (Krishnachandrapur PWSS) Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000611/2023-2024 | 242/RSD | 22/08/2023 | 30 | M/S. M.M. ENTERPRISE | 4.49 | 0 | 98
2818 | Alipore Division | Raidighi Sub-Division | Extension of pipeline in connection with Functional Household Tap Connection (FHTC) at Dakatmari area under Krishnachandrapur water supply scheme under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001589/2021-2022 | 773/RSD | 28/03/2022 | 60 | M/S M. ENTERPRISE | 4.79 | 0 | 98
2819 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000024/2022-2023 | 1680/AD | 13/06/2022 | 0 | Resource Division | 15.38 | 0 | 0
2820 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000034/2021-2022 | 6489/AD | 08/03/2022 | 0 | Resource Division | 32.96 | 0 | 0
2821 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000034/2022-2023 | 3586/AD | 29/07/2022 | 0 | Resource Division | 56.23 | 0 | 0
2822 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 60 | M/S B. ENTERPRISE | 27.24 | 0 | 0
2823 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- II, Mathurapur-II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000345/2023-2024 | 3372/AD | 11/10/2023 | 630 | M/S. TAPAS MONDAL | 114.8 | 0 | 20
2824 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 1 and approach road and plinth protection including boundary wall at Khari (Zone-I) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000997/2023-2024 | 294/RSD | 29/09/2023 | 60 | TIYASHA ENTERPRISE | 2.99 | 0 | 100
2825 | Alipore Division | Raidighi Sub-Division | Repairing of pump house ¿ 2 and approach road and plinth protection including boundary wall at Khari (Zone-I) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001001/2023-2024 | 295/RSD | 29/09/2023 | 60 | JOY MAA TARA ENTERPRISE | 3.14 | 0 | 100
2826 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 3 and approach road and plinth protection including boundary wall at Khari (Zone-II) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001002/2023-2024 | 296/RSD | 29/09/2023 | 60 | SUKUMAR HALDAR | 3.11 | 0 | 100
2827 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 2 and approach road and plinth protection at Khari (Zone-II) W/S Scheme, modified as Zone- II of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001004/2023-2024 | 297/RSD | 29/09/2023 | 60 | SUKUMAR HALDAR | 2.26 | 0 | 100
2828 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - I of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001912/2023-2024 | 1434/AD | 09/03/2024 | 30 | NITYANANDA MONDAL | 14.82 | 0 | 95
2829 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- I of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002254/2024-2025 | 556/AD | 12/02/2025 | 120 | M/S BANERJEE ENGINEERING SYSTEM | 27.31 | 0 | 0
2830 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000075/2022-2023 | 5148/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
2831 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I). | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000409/2024-2025 | 3203/AD | 01/08/2024 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 27.65 | 0 | 0
2832 | Alipore Division | Kakdwip Sub-Division | Surging of 3 nos. Tubewell for Augmentation of Bishnupur- 1 no., Mahishamari- 1 no., Kamalpur Rudranagar- 1 no. W/S Scheme under JJM, Block - Sagar under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000506/2024-2025 | 3607/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 5.34 | 0 | 100
2833 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works and other allied works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (SM/10151) (SM/08795) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000550/2024-2025 | 3779/AD | 18/09/2024 | 179 | NITYANANDA MONDAL | 60.65 | 0 | 100
2834 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Naraharipur W/S Scheme (Phase-A), Purusottampur W/S Scheme (Phase-A), Kamalpur Rudranagar W/S Scheme (Phase-A) & Khasramkar Char W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001011/2021-2022 | 517/KSD | 24/08/2021 | 10 | M/S R.DUTTA & CO. | 4.7 | 0 | 100
2835 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kamalpur Rudranagar W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001059/2021-2022 | 2347/AD | 09/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.09 | 0 | 100
2836 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kamalpur Rudranagar W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001086/2021-2022 | 577/KSD | 10/09/2021 | 20 | M/S R.DUTTA & CO. | 4.23 | 0 | 100
2837 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kamalpur Rudranagar W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001615/2021-2022 | 614/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 2.96 | 0 | 100
2838 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000707/2023-2024 | 477/AD | 24/01/2024 | 0 | Resource Division | 17.19 | 0 | 0
2839 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Gangasagar W/S Scheme (Phase-A), Kachuberia W/S Scheme (Phase-A), Khansaheber Abad W/S Scheme (Phase-A) & Mandirlata W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001010/2021-2022 | 516/KSD | 24/08/2021 | 10 | INDRANIL DUTTA & ASSOCIATES | 4.7 | 0 | 100
2840 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Khansaheber Abad & Naraharipur W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001056/2021-2022 | 2344/AD | 09/09/2021 | 7 | LEMNISCATE | 4.48 | 0 | 100
2841 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Khan Saheber Abad W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001082/2021-2022 | 573/KSD | 10/09/2021 | 20 | M/S R.DUTTA & CO. | 3.88 | 0 | 100
2842 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000 ] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001085/2023-2024 | 3499/AD | 16/10/2023 | 90 | S.P. CONSTRUCTION (V) | 110.29 | 0 | 78
2843 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000321/2023-2024 | 3136/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2844 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000536/2023-2024 | 20/AD | 02/01/2024 | 0 | Resource Division | 11.16 | 0 | 0
2845 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 03 (three) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Dhuri Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000009/2021-2022 | 3019/AD | 02/11/2021 | 365 | SOMBHUNATH BHATTACHARJEE | 92.97 | 0 | 0
2846 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000161/2023-2024 | 1051/AD | 15/06/2023 | 0 | Resource Division | 17.89 | 0 | 0
2847 | Alipore Division | Canning Sub-division | Laying of pipe line and FHTC work at Hiranmoypur W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000327/2024-2025 | 2731/AD | 25/06/2024 | 371 | R.S.CONSTRUCTION CO. | 197.64 | 0 | 25
2848 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 07 (seven) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Hiranmoypur Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000562/2021-2022 | 3698AD | 22/11/2021 | 365 | G.B. CONSTRUCTION & CO. | 187.36 | 0 | 83
2849 | Alipore Division | Canning Sub-division | Laying of additional pipe line to cover the FHTC work and other allied works for Retrofitting of Taldi (Zone - I and II) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000602/2023-2024 | 2351/AD | 18/08/2023 | 45 | SUPRITI ENTERPRISE | 53.79 | 0 | 100
2850 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 20 (twenty) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Taldi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000849/2021-2022 | 4430/AD | 06/12/2021 | 365 | SUPRITI ENTERPRISE | 277.8 | 0 | 32
2851 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | RTOR000011/2021-2022 | 5617/AD | 25/01/2022 | 0 | Resource Division | 29.69 | 0 | 0
2852 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 15 (fifteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Sambhunagar Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000590/2021-2022 | 2984/AD | 29/10/2021 | 365 | M/S. S.S. ENTERPRISE | 160.98 | 0 | 81
2853 | Alipore Division | Canning Sub-division | Hiring Motor launch for Canning Sub Division under Alipore Division, PHE Dte. in connection with execution & maintenance of different piped water supply schemes at different island in the district of South 24 parganas.(Period 01/01/2022 to 30/06/2022) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001462/2021-2022 | 1289/CSD | 17/12/2021 | 181 | RAJKUMAR MANNA | 2.16 | 0 | 0
2854 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Devis Abad Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000644/2021-2022 | 3697/AD | 22/11/2021 | 365 | SPA ENTERPRISE | 172.91 | 0 | 48
2855 | Alipore Division | Canning Sub-division | Inter connection and rising main works of Retrofitting of Devis Abad W/S Scheme, Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/09011) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001024/2023-2024 | 3399/AD | 11/10/2023 | 45 | SPA ENTERPRISE | 26.17 | 0 | 75
2856 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 12 (twelve) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001571/2021-2022 | 6834/AD | 23/03/2022 | 365 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 110.82 | 0 | 86
2857 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/13117) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000383/2024-2025 | 3079/AD | 25/07/2024 | 30 | RANJIT CONSTRUCTION | 11.67 | 0 | 0
2858 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th Tubewell site for Bishnupur (Zone- I and II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000384/2024-2025 | 3080/AD | 25/07/2024 | 45 | M/S AINUR ENTERPRISE | 7.18 | 0 | 0
2859 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Land Development, Boundary Wall Painting and Repair and Approach Road at 2nd Tubewell site for Bishnupur (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13117) (SM/09358) (SM/08800) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000449/2025-2026 | 3567/AD | 25/07/2025 | 45 | SWAPAN GUCHHAIT | 3.89 | 0 | 0
2860 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000693/2023-2024 | 463/AD | 24/01/2024 | 0 | Resource Division | 16.99 | 0 | 0
2861 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 4th Tubewell site of Namkhana Water Supply Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000020/2022-2023 | 214/AD | 11/04/2022 | 30 | M/S DAS ENTERPRISE | 5.16 | 0 | 0
2862 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Namkhana PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000059/2023-2024 | 43/KSD | 27/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2863 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 4th Tubewell site of Namkhana Water Supply Scheme (Augmentation), Block - Namkhana under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000064/2022-2023 | 958/AD | 20/05/2022 | 30 | SIMPLEX DRILLING CO. | 18.26 | 0 | 100
2864 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Namkhana W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000282/2023-2024 | 1432/AD | 13/07/2023 | 45 | BALAJEE ENTERPRISE. | 53.48 | 0 | 95
2865 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NAMKHANA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000487/2022-2023 | 301/AD | 12/04/2022 | 45 | M/S R.DUTTA & CO. | 5.91 | 0 | 100
2866 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Namkhana W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001029/2021-2022 | 543/KSD | 01/09/2021 | 20 | M/S R.DUTTA & CO. | 4.59 | 0 | 100
2867 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Namkhana Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001102/2022-2023 | 8485/AD | 16/12/2022 | 837 | BALAJEE ENTERPRISE. | 691.56 | 0 | 100
2868 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Namkhana W/S Scheme & it's adjacent areas, Block Namkhana under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001613/2021-2022 | 612/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 2.33 | 0 | 100
2869 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
2870 | Alipore Division | Kakdwip Sub-Division | Carriage of Chlorine from Ganeshpur store to different Pump house of different PWSS of Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (For one year) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002186/2022-2023 | 690/KSD | 23/02/2023 | 365 | BIMALENDU GIRI | 0.81 | 0 | 100
2871 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000043/2022-2023 | 3907/AD | 12/08/2022 | 0 | Resource Division | 32.17 | 0 | 0
2872 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000286/2023-2024 | 3082/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2873 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000548/2023-2024 | 31/AD | 02/01/2024 | 0 | Resource Division | 18.71 | 0 | 0
2874 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000909/2023-2024 | 892/AD | 07/02/2024 | 0 | Resource Division | 1.52 | 0 | 0
2875 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000975/2023-2024 | 1768/AD | 27/03/2024 | 0 | Resource Division | 1.92 | 0 | 0
2876 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Iswaripur W/S Scheme for 365 Days during financial year 2020-2021 and 2021-2022 under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000529/2020-2021 | 586/CSD | 27/08/2020 | 365 | SUKANTA HALDER | 2.26 | 0 | 100
2877 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 08 (eight) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Iswaripur Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001190/2021-2022 | 5708/AD | 31/01/2022 | 365 | ASHIT BARAN BOSE | 84.89 | 0 | 100
2878 | Alipore Division | Canning Sub-division | Laying pipeline for dispose of waste water from IEP at Head Work Site of Iswaripur W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001973/2022-2023 | 12592/AD | 13/03/2023 | 15 | BHUNIA BUILDERS | 5.97 | 0 | 100
2879 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000018/2022-2023 | 1175/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
2880 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000077/2023-2024 | 61/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2881 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Mandirtala (Zone-I & II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000278/2023-2024 | 1428/AD | 13/07/2023 | 630 | SUPRITI ENTERPRISE | 80.97 | 0 | 86
2882 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MANDIRTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000477/2022-2023 | 31/AD | 04/04/2022 | 45 | VOYAGER | 7.71 | 0 | 0
2883 | Alipore Division | Kakdwip Sub-Division | Surging of 01 no. Tubewell for augmentation of Mandirtala W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000524/2023-2024 | 351/KSD | 09/08/2023 | 20 | S.K.GOLUI | 1.77 | 0 | 100
2884 | Alipore Division | Kakdwip Sub-Division | Construction of 600 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Mandirtala Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000781/2022-2023 | 6535/AD | 11/11/2022 | 300 | SUPRITI ENTERPRISE | 821.1 | 0 | 78
2885 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000050/2022-2023 | 3902/AD | 12/08/2022 | 0 | Resource Division | 148.87 | 0 | 0
2886 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000094/2022-2023 | 5588/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
2887 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000283/2023-2024 | 3058/AD | 28/09/2023 | 0 | Resource Division | 110.39 | 0 | 0
2888 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000323/2023-2024 | 3138/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2889 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000683/2023-2024 | 453/AD | 24/01/2024 | 0 | Resource Division | 1.44 | 0 | 0
2890 | Alipore Division | Raidighi Sub-Division | Remodeling of distribution system for providing Functional Household Tap connection (FHTC) to all the households related works in Zone-III of Mathurapur - II Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000071/2022-2023 | 1035/AD | 23/05/2022 | 1363 | UNITED BUILDERS | 45.42 | 0 | 75
2891 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-III (Kautala PWSS) including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001451/2021-2022 | 6068/AD | 17/02/2022 | 1505 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 107.95 | 0 | 60
2892 | Alipore Division | Raidighi Sub-Division | Laying distribution system of damaged pipe line of Koutala piped water supply scheme at Zone- III of Mathurapur -II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002375/2023-2024 | 1215/AD | 29/02/2024 | 45 | KALIDAS ENTERPRISE | 13.5 | 0 | 100
2893 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000023/2022-2023 | 1679/AD | 13/06/2022 | 0 | Resource Division | 15.4 | 0 | 0
2894 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000040/2022-2023 | 3581/AD | 29/07/2022 | 0 | Resource Division | 31.31 | 0 | 0
2895 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000077/2022-2023 | 5144/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
2896 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000079/2022-2023 | 5554/AD | 29/09/2022 | 0 | Resource Division | 8.15 | 0 | 0
2897 | Alipore Division | Kakdwip Sub-Division | Construction of 1 (one) no. Pump House (5.40m x 3.60m) including sanitary arrangement as per departmental drawing for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Herambagopalpur Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000018/2022-2023 | 213/AD | 11/04/2022 | 30 | M/S BABUSONA ENTERPRISE | 5.15 | 0 | 100
2898 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for implementing of JAL SWAPNA (JJM) at 3rd Tubewell site of Herambagopalpur Water Supply Scheme (Augmentation), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000027/2022-2023 | 411/AD | 20/04/2022 | 30 | AQUATECH ENGINEER | 18.32 | 0 | 100
2899 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Herambagopalpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000066/2023-2024 | 47/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2900 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Herambagopalpur W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000276/2023-2024 | 1426/AD | 13/07/2023 | 597 | GARGO TRADERS | 42.5 | 0 | 70
2901 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Herambogopalpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000458/2022-2023 | 293/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.27 | 0 | 100
2902 | Alipore Division | Kakdwip Sub-Division | Surging of 6 nos. Tubewell for Augmentation of Hesamabad- 2 nos., Block- Kakdwip, Herambagopalpur- 2 nos., Gurdaspur- 2 nos. W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000503/2024-2025 | 3606/AD | 06/09/2024 | 30 | COPE ENTERPRISE | 8.23 | 0 | 100
2903 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Herambagopalpur W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000504/2023-2024 | 349/KSD | 09/08/2023 | 20 | S.K.GOLUI | 2.73 | 0 | 100
2904 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Herambagopalpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000551/2022-2023 | 5725/AD. | 13/10/2022 | 901 | GARGO TRADERS | 706.06 | 0 | 36
2905 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Herambagopalpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001076/2021-2022 | 546/KSD | 03/09/2021 | 20 | LEMNISCATE | 4.6 | 0 | 100
2906 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001080/2021-2022 | 558/KSD | 08/09/2021 | 20 | LEMNISCATE | 4.24 | 0 | 100
2907 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Herambagopalpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001606/2021-2022 | 604/KSD | 27/09/2021 | 7 | LEMNISCATE | 1.56 | 0 | 100
2908 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000044/2022-2023 | 3908/AD | 12/08/2022 | 0 | Resource Division | 19.42 | 0 | 0
2909 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000312/2023-2024 | 3121/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2910 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000571/2023-2024 | 76/AD | 03/01/2024 | 0 | Resource Division | 21.58 | 0 | 0
2911 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000940/2023-2024 | 1674/AD | 22/03/2024 | 0 | Resource Division | 7.49 | 0 | 0
2912 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Kumarkhali, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2968] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000148/2023-2024 | 741/AD | 22/05/2023 | 875 | G.B. CONSTRUCTION & CO. | 553.93 | 0 | 83
2913 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kumarkhali Water Supply Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000263/2022-2023 | 3496/AD | 26/07/2022 | 45 | A 8 T CONSTRUCTION | 6.77 | 0 | 98
2914 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumarkhali W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001120/2022-2023 | 8847/AD | 22/12/2022 | 30 | G.B. CONSTRUCTION (TW) | 19.51 | 0 | 0
2915 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Kumarkhali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001842/2021-2022 | 681/CSD | 18/08/2021 | 15 | HORIZEN | 3.66 | 0 | 100
2916 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Kumarkhali Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001843/2021-2022 | 682/CSD | 18/08/2021 | 15 | HORIZEN | 2.89 | 0 | 100
2917 | Alipore Division | Canning Sub-division | Additional laying of pipe line at Kumarkhali W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002182/2023-2024 | 833/AD | 05/02/2024 | 90 | ISHAN CONSTRUCTION | 87.63 | 0 | 90
2918 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
2919 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000046/2022-2023 | 3909/AD | 12/08/2022 | 0 | Resource Division | 110.14 | 0 | 0
2920 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000159/2023-2024 | 1054/AD | 15/06/2023 | 0 | Resource Division | 18.28 | 0 | 0
2921 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kakdwip & Akshaynagar Zone-II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000050/2023-2024 | 36/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2922 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC and Construction of Platform to all households for Augmentation of Kakdwip Akshaynagar Zone-II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000200/2024-2025 | 2583/AD | 19/06/2024 | 316 | SWASTIK ENTERPRISE (NEW) | 10.04 | 0 | 100
2923 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for augmentation of Kakdwip Akshaynagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000201/2024-2025 | 2584/AD | 19/06/2024 | 230 | M/S B.N.ENTERPRISES | 37.98 | 0 | 100
2924 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Kakdwip Akshaynagar Zone-I W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000234/2023-2024 | 164/KSD | 02/06/2023 | 20 | S.K.GOLUI | 2.84 | 0 | 95
2925 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Kakdwip Akshaynagar (Zone-II), South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000273/2023-2024 | 1423/AD | 13/07/2023 | 45 | M/S. JHARNA ENTERPRISE | 41.66 | 0 | 100
2926 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, fitting fixing supplying specials, etc. for Augmentation of Kakdwip Akshaynagar (Zone- I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-II) (Part-A) (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000303/2024-2025 | 2710/AD | 24/06/2024 | 60 | M/S. JHARNA ENTERPRISE | 144.99 | 0 | 0
2927 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal after dismantling of dilapidated R.C.C. Elevated Reservoir of Capcaity 700 CuM at Kakdwip Akshaynagar Zone I, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000495/2025-2026 | 4426/AD | 09/09/2025 | 400 | SARADA CONSTRUCTION | 148.07 | 0 | 0
2928 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KAKDWIP & AKSHOYNAGAR PWSS ) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000497/2022-2023 | 313/AD | 13/04/2022 | 45 | LEMNISCATE | 12.61 | 0 | 0
2929 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000503/2022-2023 | 4930/AD | 15/09/2022 | 1229 | M/S. JHARNA ENTERPRISE | 280.09 | 0 | 90
2930 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kakdwip Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-A) [No. of FHTC = 1782] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000545/2022-2023 | 5721/AD | 13/10/2022 | 1021 | L.N. ENTERPRISE | 215 | 0 | 98
2931 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 1100] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000628/2022-2023 | 5980/AD | 20/10/2022 | 819 | M/S B.N.ENTERPRISE | 134.44 | 0 | 100
2932 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.06.2024 to 31.08.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000665/2024-2025 | 981/KSD | 27/05/2024 | 92 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
2933 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000666/2024-2025 | 1254/KSD | 28/08/2024 | 91 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
2934 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip & Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-C) [No. of FHTC = 1220] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000768/2022-2023 | 6498/AD | 11/11/2022 | 90 | A.K. SIKDAR | 109.54 | 0 | 80
2935 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.0225. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000778/2025-2026 | 968/KSD | 25/11/2025 | 92 | NAMITA PRADHAN | 1.21 | 0 | 0
2936 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Kakdwip Akshaynagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub -Division of Alipore Division, P.H.E. Dte. (Zone - I) (Part-B) [ No. of FHTC = 800] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001110/2022-2023 | 8486/AD | 16/12/2022 | 1001 | M/S KALPANA CONSTRUCTION | 109.65 | 0 | 90
2937 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrinalnagar, Koaberia, Hesamabad, Kakdwip, Kakdwip & Akshaynagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002144/2023-2024 | 944/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2938 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House with construction of approach road at 1st Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002204/2024-2025 | 2106/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.2 | 0 | 0
2939 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House with construction of approach road at 2nd Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002211/2024-2025 | 2107/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.16 | 0 | 0
2940 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and boundary wall with construction of approach road at 4th Tubewell site of Zone-I of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002212/2024-2025 | 2108/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.09 | 0 | 0
2941 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and boundary wall with construction of approach road at 1st Tubewell site of Zone-II of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002213/2024-2025 | 2109/KSD | 30/12/2024 | 15 | IMAGINEER VENTURES | 3.18 | 0 | 0
2942 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and boundary wall at 2nd Tubewell site of Zone-II of Kakdwip Akshaynagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09998) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002214/2024-2025 | 258/KSD | 31/01/2025 | 15 | M/S S.M. CONSTRUCTION | 2.98 | 0 | 100
2943 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 no. 100mm x 50mm dia. having 4 nos. Strainer upto 360 mtr (Average) depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying PVC Pipe for providing FHTC at Augmentation of Kakdwip Akshaynagar Zone-II W/S Scheme for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002566/2023-2024 | 511/KSD | 15/03/2024 | 10 | M/S. R.M. CONSTRUCTION | 2.81 | 0 | 0
2944 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2023 to 29.02.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002841/2023-2024 | 380/KSD | 17/08/2023 | 184 | ANANTA KUMAR GIRI | 2.4 | 0 | 0
2945 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2024 to 31.05.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002843/2023-2024 | 409/KSD | 27/02/2024 | 92 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
2946 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002846/2024-2025 | 1655/KSD | 26/11/2024 | 90 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
2947 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Sagar Block under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002891/2024-2025 | 1665/KSD | 27/11/2024 | 90 | NAMITA PRADHAN | 1.2 | 0 | 0
2948 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003034/2024-2025 | 349/KSD | 27/02/2025 | 92 | ANANTA KUMAR GIRI | 1.2 | 0 | 0
2949 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.0225. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003682/2024-2025 | 353/KSD | 27/02/2025 | 92 | NAMITA PRADHAN | 1.21 | 0 | 0
2950 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000264/2023-2024 | 3064/AD | 28/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
2951 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000467/2023-2024 | 4727/AD | 18/12/2023 | 0 | Resource Division | 95.8 | 0 | 0
2952 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000836/2023-2024 | 681/AD | 30/01/2024 | 0 | Resource Division | 58.18 | 0 | 0
2953 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000130/2021-2022 | 385/KSD | 07/07/2021 | 15 | UNIQUE CONSTRUCTION (II) | 4.39 | 0 | 0
2954 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar, Dakshin and others (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000133/2021-2022 | 388/KSD | 07/07/2021 | 15 | UNIQUE CONSTRUCTION (II) | 4.39 | 0 | 0
2955 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Ganeshpur Left Out W/S Scheme, Block - Kakdwip under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000163/2024-2025 | 2514/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
2956 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Augmentation of Ganeshpur Left Out W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000204/2024-2025 | 2587/AD | 19/06/2024 | 45 | R. UNIQUE CONSTRUCTION | 9.7 | 0 | 0
2957 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 5th tubewell Site for Augmentation of Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/09922) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000205/2024-2025 | 2588/AD | 19/06/2024 | 45 | R. UNIQUE CONSTRUCTION | 5.6 | 0 | 0
2958 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000301/2023-2024 | 1493/AD | 14/07/2023 | 300 | SPA ENTERPRISE | 592.38 | 0 | 20
2959 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( Ganeshpur (Left out Areas) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000489/2022-2023 | 302/AD | 12/04/2022 | 45 | LEMNISCATE | 8.66 | 0 | 0
2960 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 01 no. Pump House for Ganeshpur Left Out Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000856/2022-2023 | 6939/AD | 18/11/2022 | 929 | M/S PRADIP KUMAR PAL | 104.35 | 0 | 100
2961 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Left Out W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001024/2021-2022 | 538/KSD | 01/09/2021 | 20 | M/S R.DUTTA & CO. | 4.59 | 0 | 100
2962 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Ganeshpur (Left Out) W/S Scheme & it's adjacent areas, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001043/2021-2022 | 2274/AD | 06/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.25 | 0 | 100
2963 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Ganeshpur Left Out W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001612/2021-2022 | 611/KSD | 27/09/2021 | 7 | M/S R.DUTTA & CO. | 1.55 | 0 | 100
2964 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001798/2020-2021 | 1240/KSD | 23/02/2021 | 10 | UNIQUE CONSTRUCTION (II) | 4.7 | 0 | 0
2965 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia Uttar Dakshin (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001807/2020-2021 | 1245/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.79 | 0 | 0
2966 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Krishnanagar (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001811/2020-2021 | 1250/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.79 | 0 | 0
2967 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Krishnanagar (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001838/2020-2021 | 1269/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.78 | 0 | 0
2968 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Pukurberia Uttar Dakshin (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001841/2020-2021 | 1272/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.74 | 0 | 0
2969 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gheri Uttar (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001844/2020-2021 | 1275/KSD | 23/02/2021 | 10 | UNIQUE CONSTRUCTION (II) | 4.38 | 0 | 0
2970 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-II) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001851/2020-2021 | 1282/KSD | 23/02/2021 | 10 | FIDERE MARINE SERVICES PVT. LTD. | 4.6 | 0 | 0
2971 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-I) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001858/2020-2021 | 1248/KSD | 23/02/2021 | 10 | FIDERE MARINE SERVICES PVT. LTD. | 4.7 | 0 | 0
2972 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gobindapur (Phase-V) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001895/2020-2021 | 1317/KSD | 23/02/2021 | 10 | M/S. SUNITY ENTERPRISE | 4.74 | 0 | 0
2973 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
2974 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000054/2022-2023 | 3904/AD | 12/08/2022 | 0 | Resource Division | 348.05 | 0 | 0
2975 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000092/2022-2023 | 5589/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
2976 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000258/2023-2024 | 3063/AD | 28/09/2023 | 0 | Resource Division | 1.2 | 0 | 0
2977 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000674/2023-2024 | 440/AD | 24/01/2024 | 0 | Resource Division | 4.29 | 0 | 0
2978 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000804/2023-2024 | 649/AD | 30/01/2024 | 0 | Resource Division | 10.22 | 0 | 0
2979 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Nebutala W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11750) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000167/2024-2025 | 2518/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.41 | 0 | 0
2980 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Nebutala W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11750) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000216/2024-2025 | 2599/AD | 19/06/2024 | 30 | SWATHI ENTERPRISE | 9.69 | 0 | 0
2981 | Alipore Division | Kakdwip Sub-Division | Surging of 02 nos. Big dia Tubewell of Nebutala W/S Scheme under JJM, Block - Kakdwip under Kakdwip Sub-Division under Alipore Division P.H.Engg. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000232/2023-2024 | 161/KSD | 01/06/2023 | 20 | S.K.GOLUI | 2.74 | 0 | 100
2982 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Nebutala, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000268/2023-2024 | 1418/AD | 13/07/2023 | 927 | M/S B.N.ENTERPRISE | 37.36 | 0 | 50
2983 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Nebutala Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000325/2022-2023 | 3872/AD | 08/08/2022 | 30 | M/S M3 SOLUTION | 8.76 | 0 | 100
2984 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 1 no. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Nebutala Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000360/2022-2023 | 3892/AD | 10/08/2022 | 1504 | M/S B.N.ENTERPRISE | 239.96 | 0 | 60
2985 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Nebutala W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-C) (SM/11750) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000392/2024-2025 | 3093/AD | 25/07/2024 | 60 | M/S B.N.ENTERPRISES | 58.8 | 0 | 0
2986 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( NEBUTALA PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000499/2022-2023 | 1751/AD | 15/06/2022 | 45 | LEMNISCATE | 3.76 | 0 | 100
2987 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002052/2022-2023 | 730/KSD | 14/03/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
2988 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
2989 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002597/2023-2024 | 176/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
2990 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000061/2022-2023 | 3947/AD | 12/08/2022 | 0 | Resource Division | 43.58 | 0 | 0
2991 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000269/2023-2024 | 3068/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
2992 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000592/2023-2024 | 91/AD | 03/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
2993 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000805/2023-2024 | 650/AD | 30/01/2024 | 0 | Resource Division | 3.96 | 0 | 0
2994 | Alipore Division | Baruipur Sub-Division | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01674/2024-2025 | BP-2024-25-779 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
2995 | Alipore Division | Baruipur Sub-Division | Road restoration for Shikharbali-I GP lo Dakshin Kalyanpur | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01777/2024-2025 | BP-2024-25-802 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.31 | 0 | 0
2996 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Kashinagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000266/2023-2024 | 1454/AD | 13/07/2023 | 600 | MITHU BUILDERS | 308.59 | 0 | 60
2997 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Kashinagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000377/2023-2024 | 1770/AD | 26/07/2023 | 60 | B.S. CONSTRUCTION | 62.86 | 0 | 44
2998 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. of Dakshin Kashinagar W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13763) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000512/2024-2025 | 3611/AD | 06/09/2024 | 329 | M/S B. ENTERPRISE | 59.35 | 0 | 60
2999 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN KASHINAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000978/2022-2023 | 3663/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.2 | 0 | 100
3000 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Kashinagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13763) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001367/2024-2025 | 5496/AD | 27/12/2024 | 210 | CHANDA ENTERPRISE (KOLKATA) | 40.78 | 0 | 100
3001 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Kashinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002034/2023-2024 | 516/AD | 25/01/2024 | 45 | M/S S.DAS ENTERPRISE | 25.46 | 0 | 0
3002 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Kashinagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002035/2023-2024 | 517/AD | 25/01/2024 | 360 | SUJOY SADHUKHAN | 9.58 | 0 | 100
3003 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Purba Surendranagar, Dakshin Kashinagar, Herambagopalpur, Achintyanagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002105/2023-2024 | 927/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
3004 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000096/2023-2024 | 542/AD | 12/05/2023 | 0 | Resource Division | 9.14 | 0 | 0
3005 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000508/2023-2024 | 4945/AD | 22/12/2023 | 0 | Resource Division | 24.05 | 0 | 0
3006 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000952/2023-2024 | 1686/AD | 22/03/2024 | 0 | Resource Division | 0.57 | 0 | 0
3007 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road at OHR Site for Augmentation of Kachuberia W/S Scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000471/2024-2025 | 3457/AD | 23/08/2024 | 45 | M/S SOURAV MAHAPATRA | 32.06 | 0 | 0
3008 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001055/2021-2022 | 2343/AD | 09/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 3.8 | 0 | 100
3009 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001081/2021-2022 | 572/KSD | 10/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.6 | 0 | 100
3010 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Kachuberia W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/001611/2021-2022 | 610KSD | 27/09/2021 | 7 | ROY CHOWDHURY ASSOCIATES | 2.26 | 0 | 100
3011 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000705/2023-2024 | 475/AD | 24/01/2024 | 0 | Resource Division | 24.87 | 0 | 0
3012 | Alipore Division | Canning Sub-division | Additional laying of pipeline and FHTC work at Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - XII) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000563/2024-2025 | 3894/AD | 24/09/2024 | 219 | SUJOY SADHUKHAN | 5.87 | 0 | 65
3013 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for Maukhali-Kumarkhali (Part - XII) having village with maximum 297 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000796/2022-2023 | 6685/AD | 14/11/2022 | 60 | FIDERE MARINE SERVICES PVT. LTD. | 71.35 | 0 | 77
3014 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-XII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001909/2022-2023 | 5672/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.64 | 0 | 0
3015 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000177/2023-2024 | 1130/AD | 22/06/2023 | 0 | Resource Division | 1.83 | 0 | 0
3016 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Khunkhali (Part - I) having village with maximum 105 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000789/2022-2023 | 6644/AD | 14/11/2022 | 120 | M/S M. ENTERPRISE | 45.15 | 0 | 89
3017 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khunkhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001895/2022-2023 | 5659/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.37 | 0 | 0
3018 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000178/2023-2024 | 1131/AD | 22/06/2023 | 0 | Resource Division | 0.65 | 0 | 0
3019 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for Bibir Abad, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1703] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000122/2023-2024 | 158/AD | 18/04/2023 | 895 | NAUTAN DAS AND CO | 300.96 | 0 | 70
3020 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for head work Site for Ground Water Based of Bibir Abad Piped Water Supply Scheme, Block - Canning- II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001065/2024-2025 | 5002/AD | 05/12/2024 | 45 | DEVAM ENTERPRISE | 32.5 | 0 | 0
3021 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 3 Site for Ground Water Based of Bibir Abad Piped Water Supply Scheme, Block - Canning- II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001066/2024-2025 | 5003/AD | 05/12/2024 | 30 | SUBHO CONSTRUCTION | 10.4 | 0 | 0
3022 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001766/2022-2023 | 12039/AD | 27/02/2023 | 45 | GIRI ENTERPRISE (NEW) | 7.33 | 0 | 98
3023 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001767/2022-2023 | 12040/AD | 27/02/2023 | 45 | KRISHNA CONSTRUCTION | 7.07 | 0 | 98
3024 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001821/2022-2023 | 12336/AD | 06/03/2023 | 105 | M/S ARIYAN ENTERPRISE | 7.1 | 0 | 98
3025 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Bibir Abad New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001892/2022-2023 | 8036/AD | 02/12/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.72 | 0 | 0
3026 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Bibir Abad W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002021/2022-2023 | 12104/AD | 28/02/2023 | 60 | SNEHA CONSTRUCTION | 59.76 | 0 | 98
3027 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
3028 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000012/2023-2024 | 217/AD | 21/04/2023 | 0 | Resource Division | 103.46 | 0 | 0
3029 | Alipore Division | Canning Sub-division | Construction of OHR (200 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KAMAKHYAPUR, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000062/2023-2024 | 312/AD | 26/04/2023 | 300 | SAMSUL ENTERPRISE | 432.74 | 0 | 30
3030 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Kamakhyapur Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000120/2025-2026 | 2583/AD | 03/06/2025 | 45 | JHARNA CONSTRUCTION | 37.41 | 0 | 0
3031 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (3rd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000217/2023-2024 | 957/AD | 30/05/2023 | 65 | INDIA CONSTRUCTION | 43.94 | 0 | 100
3032 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Kamakhyapur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000542/2024-2025 | 3713/AD | 12/09/2024 | 60 | SAMSUL ENTERPRISE | 60.04 | 0 | 0
3033 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kamakhyapur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001083/2023-2024 | 3542/AD | 17/10/2023 | 746 | GHOSH CONSTRUCTION | 11 | 0 | 80
3034 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001762/2022-2023 | 11944/AD | 24/02/2023 | 708 | BANGA NIRMAN | 8.61 | 0 | 100
3035 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kamakshyapur New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001885/2022-2023 | 7598/AD | 28/11/2022 | 45 | M/S R.DUTTA & CO. | 5.39 | 0 | 95
3036 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kamakhyapur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002111/2022-2023 | 12877/AD | 17/03/2023 | 656 | JOY GURU BUILDERS | 8.92 | 0 | 100
3037 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000061/2023-2024 | 381/AD | 02/05/2023 | 0 | Resource Division | 30.19 | 0 | 0
3038 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Srinagar (Zone - I & II) W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000212/2024-2025 | 2595/AD | 19/06/2024 | 45 | KHOKAN MONDAL | 28.76 | 0 | 0
3039 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Sri Nagar PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13811) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000378/2024-2025 | 3044/AD | 24/07/2024 | 60 | MAA LAXMI ENTERPRISE | 120.33 | 0 | 0
3040 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Srinagar Zone - I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000426/2023-2024 | 1914/AD | 01/08/2023 | 30 | HYDROTECH ASSOCIATES | 12.04 | 0 | 90
3041 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Srinagar Zone - I & II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000427/2023-2024 | 1915/AD | 01/08/2023 | 30 | M/S.SREEJIT ENTERPRISE | 11.8 | 0 | 60
3042 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Srinagar Water Supply Scheme, Block - Kakdwip South 24 Pgs. District under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000497/2020-2021 | 5312/AD | 18/02/2021 | 365 | MONDAL PRECISION PRIVATE LIMITED | 105.31 | 0 | 90
3043 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Srinagar (Zone-I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000909/2023-2024 | 268(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3044 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SRINAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001061/2022-2023 | 4650/AD | 06/09/2022 | 45 | LEMNISCATE | 6.13 | 0 | 100
3045 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Srinagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001775/2022-2023 | 12057/AD | 27/02/2023 | 45 | M/S MAITY CONSTRUCTION | 38.52 | 0 | 100
3046 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Augmentation of Srinagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 70] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001865/2022-2023 | 12418/AD | 09/03/2023 | 1029 | MAA LAXMI ENTERPRISE | 276.43 | 0 | 90
3047 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Srinagar (Zone - I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) [No. of FHTC = 70] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002031/2022-2023 | 12998/AD | 23/03/2023 | 830 | PREMANANDA ROY BISWAS | 179.16 | 0 | 100
3048 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
3049 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & Boundary Wall at 1st Tubewell site for Srinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13811) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002156/2024-2025 | 1984/KSD | 23/12/2024 | 25 | LASKAR ENTERPRISE | 2 | 0 | 100
3050 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & boundary wall at 2nd Tubewell site for Srinagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13811) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002157/2024-2025 | 1985/KSD | 23/12/2024 | 25 | M/S IDEAL WORKS | 2 | 0 | 0
3051 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 no. 100mm x 50mm dia. having 4 nos. Strainer upto 360 mtr (Average) depth fitted with India Mark-II DWP Hand Pump Tubewell with supplying PVC Pipe for providing FHTC at Augmentation of Srinagar Zone-I & II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub - Division of Alipore Division, P.H.E.D. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002568/2023-2024 | 512/KSD | 15/03/2024 | 10 | MAA LAXMI ENTERPRISE | 2.8 | 0 | 0
3052 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000274/2023-2024 | 3073/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3053 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000465/2023-2024 | 4725/AD | 18/12/2023 | 0 | Resource Division | 24.69 | 0 | 0
3054 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000594/2023-2024 | 93/AD | 03/01/2024 | 0 | Resource Division | 0.83 | 0 | 0
3055 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000812/2023-2024 | 657/AD | 30/01/2024 | 0 | Resource Division | 12.8 | 0 | 0
3056 | Alipore Division | Diamond Harbour Sub-Division | Bamboo pilling work due to protection of distribution pipe line in between Node Points 16-17, 25-26, 32-33, 33-34, 35-36, 60-62, 62-63, 94-96 & 98-99 for laying distribution of piped water supply at Zone - III (Part-A) of Diamond Harbour -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, Ditrict South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000823/2022-2023 | 207/DHSD | 02/08/2022 | 45 | BANERJEE ENTERPRISE | 4.37 | 0 | 98
3057 | Alipore Division | Diamond Harbour Sub-Division | Bamboo pilling work due to protection of distribution pipe line in between Node Points 7-8, 8-9, 9-6, 10-12, 9-14, 14-15, 64-66 & 76-78 for laying distribution of piped water supply at Zone - III (Part-A) of Diamond Harbour -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, Ditrict South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000824/2022-2023 | 208/DHSD | 02/08/2022 | 45 | G.M. ENTERPRISE | 4.38 | 0 | 98
3058 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-III at Diamond Harbour- I block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14823] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001102/2024-2025 | 5031/AD | 06/12/2024 | 180 | JAL PRAVAHIKA PVT. LTD. | 100.79 | 0 | 0
3059 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying of distribution system in the left out areas of Part-C at ZONE-III of Diamond Harbour-I Block for providing 100% FHTC under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001153/2023-2024 | 3199/AD | 04/10/2023 | 630 | S.C. ENTERPRISE (I) | 84.6 | 0 | 65
3060 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-III at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 6507] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001743/2022-2023 | 11710/AD | 21/02/2023 | 1080 | JAL PRAVAHIKA PVT. LTD. | 477.57 | 0 | 60
3061 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000131/2022-2023 | 25/AD | 05/04/2023 | 0 | Resource Division | 25.43 | 0 | 0
3062 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000215/2023-2024 | 1985/AD | 04/08/2023 | 0 | Resource Division | 20.98 | 0 | 0
3063 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000232/2023-2024 | 2193/AD | 10/08/2023 | 0 | Resource Division | 33.01 | 0 | 0
3064 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000350/2023-2024 | 3214/AD | 04/10/2023 | 0 | Resource Division | 0.31 | 0 | 0
3065 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000423/2023-2024 | 3613/AD | 30/10/2023 | 0 | Resource Division | 18.48 | 0 | 0
3066 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000609/2023-2024 | 271/AD | 15/01/2024 | 0 | Resource Division | 21.56 | 0 | 0
3067 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000912/2023-2024 | 1254/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3068 | Alipore Division | Diamond Harbour Sub-Division | Augmentation in distribution system due to improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-IX of Falta Block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000665/2023-2024 | 2599/AD | 31/08/2023 | 757 | BANGA NIRMAN | 30.51 | 0 | 0
3069 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-1) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003148/2020-2021 | 256/DHSD | 25/11/2020 | 45 | ASMIT ENTERPRISE | 4.66 | 0 | 100
3070 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-2) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003149/2020-2021 | 261/DHSD | 26/11/2020 | 45 | SRIJON ENTERPRISE | 4.05 | 0 | 100
3071 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-3) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003150/2020-2021 | 262/DHSD | 26/11/2020 | 45 | SUJOY SADHUKHAN | 4.42 | 0 | 100
3072 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000082/2023-2024 | 406/AD | 03/05/2023 | 0 | Resource Division | 34.5 | 0 | 0
3073 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000186/2023-2024 | 1275/AD | 05/07/2023 | 0 | Resource Division | 29.8 | 0 | 0
3074 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000228/2023-2024 | 2190/AD | 10/08/2023 | 0 | Resource Division | 13.78 | 0 | 0
3075 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000358/2023-2024 | 3222/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
3076 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000736/2023-2024 | 570/AD | 27/01/2024 | 0 | Resource Division | 12.95 | 0 | 0
3077 | Alipore Division | Diamond Harbour Sub-Division | Preparation of re-design, drawing for fundation considering pile cap for group piles of different capacities for the proposed R.C.C. Over Head Reservoir at (Zone-II, OHR Size-600 Cum. Mouza - Paschim Gopal Nagar) of Kulpi Block and (Zone-VIII, OHR Size-1000 Cum. Mouza - Baneshwarpur) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000367/2022-2023 | 201/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 100
3078 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-II at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-3856] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001922/2022-2023 | 12711/AD | 14/03/2023 | 300 | M/S R.K.ENTERPRISE (SALBAGAN) | 463.56 | 0 | 25
3079 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000189/2023-2024 | 1631/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
3080 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000204/2023-2024 | 2025/AD | 05/08/2023 | 0 | Resource Division | 22.17 | 0 | 0
3081 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000366/2023-2024 | 3230/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
3082 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000865/2023-2024 | 772/AD | 03/02/2024 | 0 | Resource Division | 23.75 | 0 | 0
3083 | Alipore Division | Baruipur Sub-Division | Road restoration for Chandakhali to Dhapdhapi More. | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01664/2024-2025 | BP-2024-25-771 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.41 | 0 | 0
3084 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Lakhinarayanpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000209/2023-2024 | 860/AD | 27/05/2023 | 557 | DEVAM ENTERPRISE | 38.28 | 0 | 100
3085 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Dakshin Lakhinarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000383/2023-2024 | 1776/AD | 26/07/2023 | 600 | AQUATECH ENGINEERS | 89.3 | 0 | 68
3086 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Dakshin Lakhinarayanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 600] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000619/2023-2024 | 3730/AD | 03/11/2023 | 591 | SYN DEVELOPERS PVT. LTD. | 250.67 | 0 | 30
3087 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (DAKSHIN LAKHINARAYANPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000986/2022-2023 | 4148/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.24 | 0 | 100
3088 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Laksinarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002044/2023-2024 | 526/AD | 25/01/2024 | 598 | SARADA CONSTRUCTION | 27.89 | 0 | 100
3089 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Laksinarayanpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002045/2023-2024 | 527/AD | 25/01/2024 | 551 | GHOSH CONSTRUCTION | 9.6 | 0 | 0
3090 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
3091 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Lakhinarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002620/2023-2024 | 731(A)/KSD | 05/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
3092 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000103/2023-2024 | 549/AD | 12/05/2023 | 0 | Resource Division | 8.49 | 0 | 0
3093 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000504/2023-2024 | 4947/AD | 22/12/2023 | 0 | Resource Division | 38.43 | 0 | 0
3094 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000754/2023-2024 | 589/AD | 29/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
3095 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Krishnadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13871) (Part-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000196/2024-2025 | 2579/AD | 19/06/2024 | 45 | M/S SHIBAM ENTERPRISE | 39.24 | 0 | 0
3096 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Krishnadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000375/2023-2024 | 1769/AD | 26/07/2023 | 60 | TANMAY ROY CHOWDHURY | 55.24 | 0 | 59
3097 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000985/2022-2023 | 4147/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.15 | 0 | 0
3098 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Krishnadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001306/2022-2023 | 9889/AD | 10/01/2023 | 45 | PURE RENOVATION GROUP | 49.2 | 0 | 0
3099 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNADASPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001327/2022-2023 | 3310/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.5 | 0 | 100
3100 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Krishnadaspur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001825/2022-2023 | 12121/AD | 01/03/2023 | 300 | SHRAYA ROADSLINE | 278.36 | 0 | 10
3101 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Krishnadaspur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002039/2023-2024 | 521/AD | 25/01/2024 | 30 | KUNDU CONSTRUCTION CO. | 11.87 | 0 | 100
3102 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 100 cum. capacity OHR of Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002070/2023-2024 | 766(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3103 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3104 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe and Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Krishnadaspur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002135/2023-2024 | 822/AD | 05/02/2024 | 45 | SARADA CONSTRUCTION | 50.9 | 0 | 50
3105 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (SM/13871) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/003200/2023-2024 | 958/KSD | 19/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
3106 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000099/2023-2024 | 545/AD | 12/05/2023 | 0 | Resource Division | 5.14 | 0 | 0
3107 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000297/2023-2024 | 3092/AD | 28/09/2023 | 0 | Resource Division | 24.65 | 0 | 0
3108 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000755/2023-2024 | 590/AD | 29/01/2024 | 0 | Resource Division | 0.92 | 0 | 0
3109 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000904/2023-2024 | 890/AD | 07/02/2024 | 0 | Resource Division | 1.38 | 0 | 0
3110 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhabnagar Zone-I W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000153/2023-2024 | 639/AD | 17/05/2023 | 45 | M/S PAUL & CO. | 28.77 | 0 | 0
3111 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gopalnagar Uttar PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13870) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000233/2024-2025 | 822/AD | 27/02/2025 | 45 | RELIABLE CONSTRUCTIONS | 64.65 | 0 | 0
3112 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of foundation after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Madhabnagar (Zone-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000767/2023-2024 | 2929/AD | 21/09/2023 | 300 | VISHAL CONSTRUCTION CO. | 590.16 | 0 | 45
3113 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar, Zone -I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001779/2022-2023 | 11503/AD | 15/02/2023 | 958 | JOY GURU TRADING | 15.14 | 0 | 60
3114 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhabnagar (Zone-I) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001780/2022-2023 | 11757/AD | 21/02/2023 | 45 | S. CHAKRABORTY AND CO. | 36.7 | 0 | 50
3115 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Madhabnagar Zone - I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001782/2022-2023 | 11924/AD | 24/02/2023 | 982 | M/S. JHARNA ENTERPRISE | 62.67 | 0 | 30
3116 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Madhabnagar Zone -I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =820] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001826/2022-2023 | 12122/AD | 01/03/2023 | 120 | KALPANA BUILDERS (I) | 149.55 | 0 | 0
3117 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Paschim Surendranagar Zone-I (Part - I, II & III), Madhabnagar Zone - I, Madhabnagar Zone - II, Dakshin Shibganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002098/2023-2024 | 924/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3118 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Madhabnagar Zone-I PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002606/2023-2024 | 292/KSD | 07/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3119 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Madhavnagar Zone-1 PWSS, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/15525) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002852/2024-2025 | 1152/AD | 18/03/2025 | 60 | VISHAL CONSTRUCTION CO. | 110.85 | 0 | 0
3120 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000087/2023-2024 | 533/AD | 12/05/2023 | 0 | Resource Division | 17.51 | 0 | 0
3121 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000522/2023-2024 | 4936/AD | 22/12/2023 | 0 | Resource Division | 28.55 | 0 | 0
3122 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000580/2023-2024 | 55/AD | 03/01/2024 | 0 | Resource Division | 0.18 | 0 | 0
3123 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000945/2023-2024 | 1679/AD | 22/03/2024 | 0 | Resource Division | 27 | 0 | 0
3124 | Alipore Division | Canning Sub-division | Construction of OHR (350 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KUMIRMARI (ZONE-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000252/2023-2024 | 1434/AD | 13/07/2023 | 597 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 697.57 | 0 | 65
3125 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kumirmari (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001082/2023-2024 | 3541/AD | 17/10/2023 | 30 | SWASTIK CONSTRUCTION | 44.74 | 0 | 0
3126 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Kumirmari Zone-II Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001228/2024-2025 | 5209/AD | 16/12/2024 | 45 | SUDIP PRADHAN | 32.94 | 0 | 0
3127 | Alipore Division | Canning Sub-division | inking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kumirmari (Zone - II) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001321/2022-2023 | 11951/AD | 24/02/2023 | 30 | M/S SEKH ENTERPRISE | 21.99 | 0 | 0
3128 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 1 of Augmentation of Kumirmari W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001404/2023-2024 | 1140/CSD | 31/10/2023 | 30 | NASKAR ENTERPRISE | 2.15 | 0 | 100
3129 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 2 of Augmentation of Kumirmari W/S Scheme (Zone-II), under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001405/2023-2024 | 1144/CSD | 01/11/2023 | 30 | HALDER & CO. | 2.01 | 0 | 100
3130 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kumirmari W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001768/2022-2023 | 12041/AD | 27/02/2023 | 45 | M/S. MIHIR KUMAR NASKAR | 8.56 | 0 | 0
3131 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kumirmari (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001844/2022-2023 | 11541/AD | 16/02/2023 | 45 | TECH VISION | 7.44 | 0 | 0
3132 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000056/2023-2024 | 263/AD | 24/04/2023 | 0 | Resource Division | 105.54 | 0 | 0
3133 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000418/2023-2024 | 373/AD | 19/01/2024 | 0 | Resource Division | 14.93 | 0 | 0
3134 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
3135 | Alipore Division | Raidighi Sub-Division | Contruction of 400 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Construction of Boundary wall, Providing FHTC including distribution system and other allied works at Zone- VIII of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/000631/2023-2024 | 3731/AD | 03/11/2023 | 960 | MONDAL CONSTRUCTION NEW | 366.12 | 0 | 5
3136 | Alipore Division | Raidighi Sub-Division | Protection work at the Head work site of Mirjapur W/S Scheme, modified as Zone- VIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001178/2023-2024 | 357/RSD | 21/11/2023 | 60 | M/S. GANGA ENTERPRISE | 2.94 | 0 | 100
3137 | Alipore Division | Raidighi Sub-Division | Construction of approach road at the Head work site of Mirjapur W/S Scheme, modified as Zone- VIII of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division |  | ORD/001179/2023-2024 | 358/RSD | 21/11/2023 | 60 | M/S M.B.ENTERPRISE | 3.29 | 0 | 0
3138 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division |  | RTOR000248/2023-2024 | 3105/AD | 28/09/2023 | 0 | Resource Division | 13.4 | 0 | 0
3139 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1400 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daria Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000335/2023-2024 | 1552/AD | 17/07/2023 | 180 | M/S. ROY CHOWDHURY & CO. | 156.75 | 0 | 45
3140 | Alipore Division | Canning Sub-division | Relaying and repairing of pipeline Daria W/S Scheme (NP-11-12,12-14,14-18), Block-Canning -I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001565/2020-2021 | 972/CSD | 09/11/2020 | 30 | GANGA TUBEWELL AND HARDWARE | 4.82 | 0 | 0
3141 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Daria W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001693/2022-2023 | 11624/AD | 18/02/2023 | 787 | THE TOWER CONSTRUCTION | 7.09 | 0 | 100
3142 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 5 of Augmentation of Daria W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001769/2022-2023 | 12042/AD | 27/02/2023 | 30 | ZINARUL ISLAM | 19.6 | 0 | 100
3143 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000116/2022-2023 | 3041/AD | 28/09/2023 | 0 | Resource Division | 85.12 | 0 | 0
3144 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000730/2023-2024 | 553/AD | 25/01/2024 | 0 | Resource Division | 87.75 | 0 | 0
3145 | Alipore Division | Diamond Harbour Sub-Division | Trial Run of existing distribution system (CI/DI/UPVC/HDPE) for Falta Zone-V under Mega Surface Water Based Water Supply Scheme of Falta-Mathurapur, South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000818/2024-2025 | 4502/AD | 11/11/2024 | 30 | K.P. CONSTRUCTION | 7.55 | 0 | 0
3146 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001376/2024-2025 | 5521/AD | 28/12/2024 | 360 | MAA BHABANI CONSTRUCTION (DUM DUM) | 49.28 | 0 | 90
3147 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-V of Falta block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 1500] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001391/2022-2023 | 10863/AD | 04/02/2023 | 785 | CONCORD ENGINEERING | 230.24 | 0 | 55
3148 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-V of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001540/2023-2024 | 439/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 0
3149 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002256/2024-2025 | 568/AD | 12/02/2025 | 180 | SAB ENGINEERING WORKS | 29.99 | 0 | 0
3150 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional UPVC pipe line for balance portion in the distribution system for Providing balance FHTC to cover 100% household under the Augmentation Scheme of Falta Zone-V within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002403/2023-2024 | 1152/AD | 27/02/2024 | 300 | S.M. ENTERPRISE | 29.8 | 0 | 90
3151 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000850/2023-2024 | 788/AD | 03/02/2024 | 0 | Resource Division | 13.43 | 0 | 0
3152 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000928/2023-2024 | 1270/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3153 | Alipore Division | Raidighi Sub-Division | Construction of 350 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- XIV of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (No. of FHTC - 100] | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000064/2023-2024 | 344/AD | 28/04/2023 | 975 | A.G.ENTERPRISE | 206.07 | 0 | 50
3154 | Alipore Division | Raidighi Sub-Division | Extension of distibution line (between node no. 3 & 30) for providing FHTC at Sankarpur PWSS of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000246/2022-2023 | 79/RSD | 18/05/2022 | 60 | RSA ENTERPRISE | 4.72 | 0 | 100
3155 | Alipore Division | Raidighi Sub-Division | Parallel distribution line for providing FHTC (Birampur, Dakshin Janardanpur & Andrarmanik) at Zone-XIV of Mathurapur - I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000268/2022-2023 | 104/RSD | 13/06/2022 | 60 | AROMA INC | 4.71 | 0 | 100
3156 | Alipore Division | Raidighi Sub-Division | Protection work to protect Laying distribution system of piped water supply at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/15058) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000656/2024-2025 | 4202/AD | 23/10/2024 | 30 | A.G.ENTERPRISE | 7.76 | 0 | 0
3157 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000881/2024-2025 | 4664/AD | 20/11/2024 | 90 | KARMAKAR CONSTRUCTION | 15.16 | 0 | 0
3158 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-XIV of Mathurapur - I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000901/2021-2022 | 4943/AD | 16/12/2021 | 90 | M/S B.N.ENTERPRISE | 83.01 | 0 | 100
3159 | Alipore Division | Raidighi Sub-Division | Interconnection between tubewells and Rising Main system of piped water supply at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001965/2022-2023 | 12719/AD | 14/03/2023 | 30 | KARMAKAR CONSTRUCTION | 6.77 | 0 | 98
3160 | Alipore Division | Raidighi Sub-Division | Protection work to protect Rising Main system and other ancillary work at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002271/2023-2024 | 478/RSD | 15/02/2024 | 30 | KARMAKAR CONSTRUCTION | 1.18 | 0 | 98
3161 | Alipore Division | Raidighi Sub-Division | Laying distrubution system (Node point 111-123-110) for providing FHTC at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002272/2023-2024 | 479/RSD | 15/02/2024 | 60 | M/S. M.M. ENTERPRISE | 4.82 | 0 | 100
3162 | Alipore Division | Raidighi Sub-Division | Laying parallel distrubution system for providing FHTC at Zone - XIV of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002273/2023-2024 | 480/RSD | 15/02/2024 | 60 | M/S. M.M. ENTERPRISE | 4.64 | 0 | 100
3163 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000600/2023-2024 | 228/AD | 11/01/2024 | 0 | Resource Division | 6.24 | 0 | 0
3164 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Haradhanpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000072/2023-2024 | 53/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3165 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for Augmentation of Haradhanpur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (for Zone-I) (SM/14159) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000145/2024-2025 | 2483/AD | 14/06/2024 | 75 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 65.9 | 0 | 0
3166 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) (SM/14159) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000555/2024-2025 | 3784/AD | 18/09/2024 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 12.13 | 0 | 0
3167 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Haradhanpur (Zone-II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000585/2023-2024 | 2342/AD | 18/08/2023 | 45 | UNIQUE AGENCY (PARTNER) | 39.91 | 0 | 100
3168 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Haradhanpur (Zone-II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000713/2023-2024 | 2534/AD | 28/08/2023 | 30 | UNIQUE AGENCY (PARTNER) | 5.05 | 0 | 100
3169 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Haradhanpur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001324/2022-2023 | 9246/AD | 29/12/2022 | 45 | SIMPLEX DRILLING CO. | 45.85 | 0 | 100
3170 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site for Haradhanpur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001477/2023-2024 | 4686/AD | 18/12/2023 | 30 | SIMPLEX DRILLING CO. | 24.97 | 0 | 100
3171 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Haradhanpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001786/2022-2023 | 3185/AD | 15/07/2022 | 45 | VOYAGER | 7.42 | 0 | 95
3172 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 480] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001858/2022-2023 | 12411/AD | 09/03/2023 | 90 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 265.34 | 0 | 90
3173 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Haradhanpur Zone - I & II, Nagendraganj Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002156/2023-2024 | 949/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
3174 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Haradhanpur (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002178/2023-2024 | 814/AD | 05/02/2024 | 30 | M/S. NIRODAMAYEE ENTERPRISE | 11.83 | 0 | 0
3175 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Haradhanpur (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002282/2023-2024 | 918/AD | 08/02/2024 | 60 | KHOKAN MONDAL | 33.69 | 0 | 100
3176 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Haradhanpur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 480] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002464/2023-2024 | 1341/AD | 05/03/2024 | 60 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 0 | 0 | 0
3177 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000293/2023-2024 | 3089/AD | 28/09/2023 | 0 | Resource Division | 1.15 | 0 | 0
3178 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000329/2023-2024 | 3144/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3179 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000499/2023-2024 | 4825/AD | 20/12/2023 | 0 | Resource Division | 16.05 | 0 | 0
3180 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000541/2023-2024 | 25/AD | 02/01/2024 | 0 | Resource Division | 5.7 | 0 | 0
3181 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000689/2023-2024 | 459/AD | 24/01/2024 | 0 | Resource Division | 8.24 | 0 | 0
3182 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
3183 | Alipore Division | Raidighi Sub-Division | Providing FHTC including laying distribution system and other allied works at Zone- XI of Mathurapur -II Block for ''Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000088/2023-2024 | 499/AD | 11/05/2023 | 813 | M/S B.N.ENTERPRISE | 131.92 | 0 | 60
3184 | Alipore Division | Raidighi Sub-Division | Dismantling and restoration of concrete village road for laying pipe line work at Zone-XI of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000222/2022-2023 | 3063/AD | 13/07/2022 | 30 | M/S B.N.ENTERPRISE | 6.13 | 0 | 100
3185 | Alipore Division | Raidighi Sub-Division | Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000359/2020-2021 | 426/RSD | 23/11/2020 | 60 | TIYASHA ENTERPRISE | 4.82 | 0 | 100
3186 | Alipore Division | Raidighi Sub-Division | Functional Household Tap Connection (FHTC) to the households at Marayari Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part- II) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000580/2020-2021 | 506/RSD | 24/12/2020 | 60 | TIYASHA ENTERPRISE | 4.82 | 0 | 100
3187 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XI of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000660/2024-2025 | 4206/AD | 23/10/2024 | 240 | M/S B.N.ENTERPRISES | 38.78 | 0 | 75
3188 | Alipore Division | Raidighi Sub-Division | Laying of distribution pipeline of Zone- XI at Mathurapur - II Block under MEGA SURFACE WATER BASED WATER SUPPLY SCHEME, FALTA-MATHURAPUR, South 24 Parganas by remodeling the existing Nandakumarpur Zone-II water supply scheme under Raidighi Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001727/2020-2021 | 5316/AD | 18/02/2021 | 120 | M/S B.N.ENTERPRISE | 73.83 | 0 | 100
3189 | Alipore Division | Raidighi Sub-Division | Special repairing work of pipeline under Nandakumarpur Zone -II of Nandakumarpur W/S Scheme, Mathurapur -II Block under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002182/2020-2021 | 709/RSD | 08/02/2021 | 60 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.04 | 0 | 100
3190 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000654/2023-2024 | 258/AD | 15/01/2024 | 0 | Resource Division | 5.13 | 0 | 0
3191 | Alipore Division | Raidighi Sub-Division | Providing FHTC including parallel pipeline at Zone- XVI of Mathurapur -I Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000057/2023-2024 | 194/AD | 19/04/2023 | 30 | B.S. CONSTRUCTION | 15.85 | 0 | 25
3192 | Alipore Division | Raidighi Sub-Division | Surging of Deep Tubewell at different W/S Scheme under Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001233/2022-2023 | 756/RSD | 30/12/2022 | 30 | SIMPLEX DRILLING CO. | 4.72 | 0 | 100
3193 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Payla Bhagabanpur W/S Scheme, modified as Zone- XVI of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001299/2024-2025 | 5373/AD | 23/12/2024 | 30 | SANKAR HALDER | 4.8 | 0 | 100
3194 | Alipore Division | Raidighi Sub-Division | Remodeling of laying distribution system of piped water supply at Zone- XVI of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002229/2023-2024 | 921/AD | 08/02/2024 | 30 | KARMAKAR CONSTRUCTION | 17.1 | 0 | 90
3195 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000644/2023-2024 | 248/AD | 15/01/2024 | 0 | Resource Division | 0.63 | 0 | 0
3196 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
3197 | Alipore Division | Raidighi Sub-Division | Construction of 300 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- XIV of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000346/2023-2024 | 1606/AD | 18/07/2023 | 923 | A.K. INDUSTRIES | 308.36 | 0 | 20
3198 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000245/2023-2024 | 3066/AD | 28/09/2023 | 0 | Resource Division | 39.42 | 0 | 0
3199 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
3200 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- X of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000355/2023-2024 | 3733/AD | 03/11/2023 | 722 | M/S ASCON | 111.11 | 0 | 50
3201 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 1 and 2, including boundary wall and approach road and plinth protection at Nandakumarpur Zone - I W/S Scheme, modified as Zone- X of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001300/2024-2025 | 5374/AD | 23/12/2024 | 30 | MONDAL ENTERPRISE (JOYNAGAR) | 4.85 | 0 | 0
3202 | Alipore Division | Raidighi Sub-Division | Horizontal boring and allied works for laying of distribution system of piped water supply at Zone-X of Mathurapur-II Block for ?Mega Surface water based water supply scheme for Falta- Mathurapur, District South 24 parganas? under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001771/2021-2022 | 629/RSD | 29/12/2021 | 15 | M/S B.M. CONSTRUCTION | 3 | 0 | 100
3203 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000656/2023-2024 | 260/AD | 15/01/2024 | 0 | Resource Division | 3.84 | 0 | 0
3204 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Khagra, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 542] (TSM/017752) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000119/2023-2024 | 555/AD | 12/05/2023 | 90 | MAJUMDER ENTERPRISE | 208.66 | 0 | 86
3205 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. 360Mtr. Depth Rig bored Tube wells for the Khagra Mini Piped Water Supply Scheme, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001807/2022-2023 | 12131/AD | 01/03/2023 | 814 | B.K. ENTERPRISE. | 15.65 | 0 | 95
3206 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Khagra New Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001893/2022-2023 | 11552/AD | 17/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 1.59 | 0 | 0
3207 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000734/2023-2024 | 558/AD | 25/01/2024 | 0 | Resource Division | 1.18 | 0 | 0
3208 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 24 (twenty four) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Chhota Molla Khali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Gosaba South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000552/2021-2022 | 2619/AD | 28/09/2021 | 1281 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 445.83 | 0 | 50
3209 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Choto Mollakhali Water Supply Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000940/2021-2022 | 4946/AD | 17/12/2021 | 60 | R.G. ENTERPRISE (I) | 7.66 | 0 | 100
3210 | Alipore Division | Canning Sub-division | Construction of 300 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Pathankhali (Zone- II) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1153] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000040/2023-2024 | 175/AD | 19/04/2023 | 300 | SAMSUL ENTERPRISE | 483.35 | 0 | 60
3211 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000137/2023-2024 | 692/AD | 18/05/2023 | 15 | HI TECH ENTERPRISE | 10.48 | 0 | 0
3212 | Alipore Division | Canning Sub-division | Sinking of 02 (Two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Pathankhali (Zone - II) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000141/2023-2024 | 277/AD | 24/04/2023 | 45 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 43.98 | 0 | 0
3213 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work for Augmentation of Pathakhali (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000731/2024-2025 | 4389/AD | 05/11/2024 | 45 | SAMSUL ENTERPRISE | 44.02 | 0 | 0
3214 | Alipore Division | Canning Sub-division | Development of tube well no-1 at Pathankhali W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000859/2022-2023 | 288/CSD | 19/05/2022 | 40 | S.P. CONSTRUCTION (I) | 0.67 | 0 | 100
3215 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep replacement tubewell by Direct Rotary Rig Method using UPVC pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4, Chandipur of Pathankhali Water Supply Scheme Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001574/2021-2022 | 6955/AD | 29/03/2022 | 30 | AQUATECH ENGINEER | 20.64 | 0 | 0
3216 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001927/2022-2023 | 11800/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 5.74 | 0 | 95
3217 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001952/2022-2023 | 12688/AD | 14/03/2023 | 45 | RAJLAKSHMI ENTERPRISE | 8.92 | 0 | 0
3218 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001953/2022-2023 | 12689/AD | 14/03/2023 | 45 | PODDER ENTERPRISE | 8.61 | 0 | 0
3219 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Pathankhali (Zone-III) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002200/2024-2025 | 471/AD | 06/02/2025 | 60 | MOUSUMI ENTERPRISE | 29.17 | 0 | 0
3220 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000011/2023-2024 | 118/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
3221 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000050/2023-2024 | 257/AD | 24/04/2023 | 0 | Resource Division | 48.14 | 0 | 0
3222 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000138/2023-2024 | 857/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
3223 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000411/2023-2024 | 367/AD | 19/01/2024 | 0 | Resource Division | 7.1 | 0 | 0
3224 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Purba Radhanagar (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000096/2023-2024 | 452/AD | 08/05/2023 | 15 | M/S ARIYAN ENTERPRISE | 13.19 | 0 | 0
3225 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Purba Radhanagar (Zone-III) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 1382] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000133/2023-2024 | 757/AD | 23/05/2023 | 710 | M N J ENTERPRISES | 519.69 | 0 | 45
3226 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000139/2023-2024 | 199/AD | 19/04/2023 | 60 | M/S ABDUL BARIK | 65.94 | 0 | 0
3227 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Purba Radhanagar (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001930/2022-2023 | 11803/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 4.65 | 0 | 95
3228 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002012/2022-2023 | 12918/AD | 21/03/2023 | 45 | M/S JAHANGIR SARDAR | 8.92 | 0 | 0
3229 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002013/2022-2023 | 12919/AD | 21/03/2023 | 45 | M/S JAHANGIR SARDAR | 8.61 | 0 | 0
3230 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Purba Radhanagar W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002038/2022-2023 | 13034/AD | 24/03/2023 | 45 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 0
3231 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000047/2023-2024 | 254/AD | 24/04/2023 | 0 | Resource Division | 60.78 | 0 | 0
3232 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
3233 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Site of Manmathanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000163/2023-2024 | 279/AD | 24/04/2023 | 45 | GOLDEN GROUPS | 38.55 | 0 | 0
3234 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections pile and pile cap for OHR etc at Kasinagar, Mrinalnagar, Manmathapur PWSS, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18873,16292,16291) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000364/2024-2025 | 2913/AD | 10/07/2024 | 120 | GARGO TRADERS | 471.61 | 0 | 0
3235 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Manmathanagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000954/2023-2024 | 2986/AD | 26/09/2023 | 45 | M/S.SREEJIT ENTERPRISE | 27.52 | 0 | 0
3236 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Manmathanagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000955/2023-2024 | 2987/AD | 26/09/2023 | 30 | M/S. S.B. MANDAL & SONS | 9.58 | 0 | 0
3237 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Site of Manmathanagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001834/2022-2023 | 12184/AD | 01/03/2023 | 706 | GOLDEN GROUPS | 38.55 | 0 | 100
3238 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002073/2023-2024 | 769(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3239 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
3240 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Manmathanagar PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002163/2022-2023 | 8336/AD | 12/12/2022 | 45 | LEMNISCATE | 6.91 | 0 | 100
3241 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000123/2023-2024 | 659/AD | 17/05/2023 | 0 | Resource Division | 15.46 | 0 | 0
3242 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000451/2023-2024 | 4716/AD | 18/12/2023 | 0 | Resource Division | 32.08 | 0 | 0
3243 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000818/2023-2024 | 663/AD | 30/01/2024 | 0 | Resource Division | 2.77 | 0 | 0
3244 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) WB02328, L043-Sankarpur II GP Office Ie Rajgara School via Gocharan Road 2) Debipur More to Sonagachi More | AE BSD,Assistant Engineer | Junior Engineer | BILL/01733/2024-2025 | BP-2024-25-797 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.96 | 0 | 0
3245 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
3246 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000102/2023-2024 | 505/AD | 11/05/2023 | 15 | SURYA ENTERPRISE | 7.71 | 0 | 0
3247 | Alipore Division | Canning Sub-division | Laying Distribution system for Augmentation of Basanti W/S Scheme (Zone - VII), Block - Basanti under Canning Sub - Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000127/2023-2024 | 145/AD | 17/04/2023 | 849 | ARISTOCON ENGINEERS'CO-OP. SOCIETY LTD. | 161.26 | 0 | 95
3248 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti (Zone-III and VII) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1767] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000257/2023-2024 | 1445/AD | 13/07/2023 | 60 | M/S SWAPAN KUMAR PRADHAN | 103.39 | 0 | 35
3249 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VII), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000496/2023-2024 | 1797/AD | 26/07/2023 | 45 | MONDAL ENTERPRISE (SALTLAKE) | 7.35 | 0 | 0
3250 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-VII) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000498/2023-2024 | 1798/AD | 26/07/2023 | 618 | B.S.ENTERPRISE | 7.09 | 0 | 100
3251 | Alipore Division | Canning Sub-division | Construction of 250 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for augmentation of Basanti (Zone-VII) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000625/2023-2024 | 4327/AD | 01/12/2023 | 300 | R.S.CONSTRUCTION CO. | 105.35 | 0 | 0
3252 | Alipore Division | Canning Sub-division | Sinking of 02 (two) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-VII), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001919/2022-2023 | 12461/AD | 10/03/2023 | 45 | SANDIP SARKAR | 39.12 | 0 | 0
3253 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-VII) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001937/2022-2023 | 11808/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 0
3254 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000027/2023-2024 | 232/AD | 24/04/2023 | 0 | Resource Division | 36.13 | 0 | 0
3255 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000156/2023-2024 | 1049/AD | 15/06/2023 | 0 | Resource Division | 5.86 | 0 | 0
3256 | Alipore Division | Baruipur Sub-Division | Road restoration of Jagita Sarda House to Khalpar Bypass Via Roybahadur Via Projit Mondal To Nikfiil Ranjan Roy House Via Khardhya Math Via Bapi Naskar House | AE BSD,Assistant Engineer | Junior Engineer | BILL/01702/2024-2025 | BP-2024-25-787 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.16 | 0 | 0
3257 | Alipore Division | Diamond Harbour Sub-Division | Sinking of Rig bored 300mm x 200mm dia. & 360 mtr. deep Tubewell by Direct Rotary method for improvement of water supply at Pump House No. 01 of Fatepur W/S Scheme Block - Falta under Diamond Harbour Sub-Division in the District of South 24 Parganas under Alipore Division, PHE Dte. (zone-vii) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000472/2022-2023 | 5523/AD | 29/09/2022 | 30 | D.N. ENTERPRISE | 24.51 | 0 | 100
3258 | Alipore Division | Diamond Harbour Sub-Division | Surging of Tube Well No. 01 of Fatepur Water Supply Scheme and Tube Well No. 01 of Birendra Bagaria Water Supply Scheme under Diamond Harbour Sub-Division, of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000959/2021-2022 | 300/DHSD | 08/10/2021 | 10 | SIMPLEX DRILLING CO. | 0.63 | 0 | 100
3259 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VII at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001377/2024-2025 | 5522/AD | 28/12/2024 | 30 | SUPRITI ENTERPRISE | 22.69 | 0 | 0
3260 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-VI of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001542/2023-2024 | 440/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 0
3261 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-VIIIA of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001544/2023-2024 | 441/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
3262 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-VIIIB of Falta Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001547/2023-2024 | 442/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
3263 | Alipore Division | Diamond Harbour Sub-Division | Extension of distribution pipeline from Shop of Mondal Carry bag & Plastic Wholesaler to House of Binniyani Purkait near Sherpur Bazar area of Sirakol Zone-II W/S Scheme of Mograhat-I Block and installation of different dia Sluice valves at various points of existing distribution pipeline of Fatepur W/S Scheme of Falta Block under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001615/2022-2023 | 478/DHSD | 03/01/2023 | 10 | CHANDRA ENTERPRISE | 4.47 | 0 | 0
3264 | Alipore Division | Diamond Harbour Sub-Division | Surging of Tube Well No. 01 of Fatepur Water Supply Scheme, Block : Falta under Diamond Harbour Sub-Division, of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001749/2022-2023 | 269/DHSD | 02/09/2022 | 15 | SIMPLEX DRILLING CO. | 0.67 | 0 | 95
3265 | Alipore Division | Diamond Harbour Sub-Division | Laying of UPVC pipe line for balance portion in the distribution system for Providing balance FHTC to cover 100 percent household under Falta Zone-VII within Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002114/2023-2024 | 828/AD | 05/02/2024 | 90 | SUPRITI ENTERPRISE | 31.02 | 0 | 100
3266 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VII at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002395/2024-2025 | 639/AD | 18/02/2025 | 30 | MAA BHABANI CONSTRUCTION (DUM DUM) | 13.33 | 0 | 0
3267 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000617/2023-2024 | 278/AD | 15/01/2024 | 0 | Resource Division | 15.14 | 0 | 0
3268 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000929/2023-2024 | 1271/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3269 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
3270 | Alipore Division | Canning Sub-division | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0
3271 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 2 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (for Zone-II) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000034/2025-2026 | 2020/AD | 28/04/2025 | 30 | SAHANA ENTERPRISE | 14.69 | 0 | 0
3272 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000103/2023-2024 | 1542/AD | 17/07/2023 | 15 | DIPTI ENTERPRISE | 8.34 | 0 | 0
3273 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Tilkumar (Zone-II) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000104/2023-2024 | 1543/AD | 17/07/2023 | 15 | DIPTI ENTERPRISE | 8.77 | 0 | 0
3274 | Alipore Division | Canning Sub-division | Laying Distribution System for Augmentation of Tilkumar W/S Scheme (Zone-I, Zone-II and Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000483/2023-2024 | 1996/AD | 04/08/2023 | 608 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 556.14 | 0 | 70
3275 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 3 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000772/2024-2025 | 4474/AD | 11/11/2024 | 30 | B.S.ENTERPRISE | 16.16 | 0 | 0
3276 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for head work Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-II] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000773/2024-2025 | 4475/AD | 11/11/2024 | 45 | SUDIP PRADHAN | 42.27 | 0 | 0
3277 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 2 Site for Augmentation of Tilkumar (Zone-I, II & III) W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [for Zone-III] | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001306/2024-2025 | 5380/AD | 23/12/2024 | 30 | AAHAN CONSTRUCTION | 11.98 | 0 | 0
3278 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation and Retrofitting of Tilkumar PWSS, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II, Pump House No. - III) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001907/2023-2024 | 221/AD | 11/01/2024 | 45 | M/S ASHA ENGINEERING | 6.65 | 0 | 98
3279 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Tilkumar (Zone-I, II & III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002448/2023-2024 | 1514/AD | 15/03/2024 | 45 | M/S APEX ENGINEERING | 22.4 | 0 | 100
3280 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
3281 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Char Baidyarabad W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/000229/2023-2024 | 1386/AD | 12/07/2023 | 508 | R CONSTRUCTION | 35.33 | 0 | 86
3282 | Alipore Division | Canning Sub-division | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Char Baidyarabad, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000486/2023-2024 | 1999/AD | 04/08/2023 | 900 | SAMSUL ENTERPRISE | 651.91 | 0 | 71
3283 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for Retrofitting of Char Baidyarabad W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/000489/2023-2024 | 1789/AD | 26/07/2023 | 30 | NATURAL RESOURCES CONSORTIUM | 7.17 | 0 | 98
3284 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Char Baidyarabad W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000855/2022-2023 | 6994/AD | 19/11/2022 | 30 | PAPPU ENTERPRISE | 19.48 | 0 | 95
3285 | Alipore Division | Canning Sub-division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 06 (six) months from the issuance of work order. | Assistant Engineer, Canning sub division |  | ORD/002429/2023-2024 | 1553/CSD | 19/02/2024 | 182 | SWAPAN KUMAR MANDAL | 2.4 | 0 | 70
3286 | Alipore Division | Canning Sub-division | Laying of additional pipe line to connect the uncovered habitation at Augmentation of Char Baidyarabad, Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. [SM/18391] | Assistant Engineer, Canning sub division |  | ORD/002489/2024-2025 | 771/AD | 25/02/2025 | 60 | M/S. UMA CONSTRUCTION | 128.86 | 0 | 0
3287 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000033/2023-2024 | 238/AD | 24/04/2023 | 0 | Resource Division | 73.69 | 0 | 0
3288 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone- I W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part- B) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000207/2024-2025 | 2590/AD | 19/06/2024 | 248 | ANANTA KUMAR GIRI | 25.16 | 0 | 30
3289 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone - II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000208/2024-2025 | 2591/AD | 19/06/2024 | 557 | SARADA CONSTRUCTION | 52.8 | 0 | 30
3290 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone - II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000209/2024-2025 | 2592/AD | 19/06/2024 | 45 | MAA BHABANI CONSTRUCTION (DUM DUM) | 42.65 | 0 | 0
3291 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Suryanagar (Zone - I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000213/2024-2025 | 2596/AD | 19/06/2024 | 45 | M/S. SUNITY ENTERPRISE | 28.44 | 0 | 0
3292 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Suryanagar (Zone - I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (Zone-II) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000214/2024-2025 | 2597/AD | 19/06/2024 | 30 | JOY ENGINEERING & CONSTRUCTION | 9.66 | 0 | 0
3293 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Suryanagar (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000470/2022-2023 | 5089/AD | 20/09/2022 | 45 | NIRMAN CONSTRUCTION | 36.67 | 0 | 100
3294 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( SURYANAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000496/2022-2023 | 4189/AD | 22/08/2022 | 45 | LEMNISCATE | 9.6 | 0 | 100
3295 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Suryanagar Zone- I W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/12572) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000496/2024-2025 | 3580/AD | 05/09/2024 | 239 | M/S RAJKUMAR KHAN | 82.06 | 0 | 40
3296 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000570/2022-2023 | 5710/AD | 13/10/2022 | 60 | R.S.CONSTRUCTION CO. | 63.91 | 0 | 0
3297 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000571/2022-2023 | .5711/AD | 13/10/2022 | 30 | TOJO ENTERPRISE | 10.65 | 0 | 95
3298 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000572/2022-2023 | 5712/AD | 13/10/2022 | 21 | THE TOWER CONSTRUCTION | 7.9 | 0 | 100
3299 | Alipore Division | Kakdwip Sub-Division | aying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000576/2022-2023 | 5714/AD | 13/10/2022 | 30 | M/S. L.P. CONSTRUCTION | 16.87 | 0 | 80
3300 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000577/2022-2023 | 5715/AD | 13/10/2022 | 60 | SARADA CONSTRUCTION | 89.01 | 0 | 60
3301 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000578/2022-2023 | 5716/AD | 13/10/2022 | 30 | M/S BANERJEE ENGINEERING SYSTEM | 16.66 | 0 | 100
3302 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 600 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Suryanagar Zone - I & II W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000590/2023-2024 | 2347/AD | 18/08/2023 | 45 | KAMIRUL SK AND CO. | 60.02 | 0 | 100
3303 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.06.2024 to 31.08.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000669/2024-2025 | 983/KSD | 27/05/2024 | 92 | ANAMIKA BERA | 1.2 | 0 | 0
3304 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.09.2024 to 30.11.2024. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000670/2024-2025 | 1256/KSD | 28/08/2024 | 91 | ANAMIKA BERA | 1.2 | 0 | 0
3305 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Suryanagar (Zone-I & II) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000908/2023-2024 | 267(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3306 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 100] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000913/2022-2023 | 7412/AD | 25/11/2022 | 90 | M/S RAJKUMAR KHAN | 119.67 | 0 | 80
3307 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. 550 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Suryanagar (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001319/2022-2023 | 9884/AD | 10/01/2023 | 1233 | KAMIRUL SK AND CO. | 319.24 | 0 | 40
3308 | Alipore Division | Kakdwip Sub-Division | Support services for preparation of documentation in relating to submission to other Department i.e. PWD (NH) for approval of laying rising main and distribution main along / across NH 117 from Nischintapur to Bakkhali for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001997/2023-2024 | 470/KSD | 22/09/2023 | 30 | ROY CHOWDHURY ASSOCIATES | 3.14 | 0 | 100
3309 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
3310 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.12.2024 to 28.02.2025. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002847/2024-2025 | 1656/KSD | 26/11/2024 | 90 | ANAMIKA BERA | 1.2 | 0 | 0
3311 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Kakdwip, Namkhana, Sagar and Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, PHE Dte. for the period from 01.03.2025 to 31.05.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/003035/2024-2025 | 352/KSD | 27/02/2025 | 92 | ANAMIKA BERA | 1.2 | 0 | 0
3312 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000272/2023-2024 | 3071/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3313 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000460/2023-2024 | 4723/AD | 18/12/2023 | 0 | Resource Division | 30.66 | 0 | 0
3314 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000591/2023-2024 | 90/AD | 03/01/2024 | 0 | Resource Division | 5.94 | 0 | 0
3315 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000810/2023-2024 | 655/AD | 30/01/2024 | 0 | Resource Division | 17.57 | 0 | 0
3316 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000997/2023-2024 | 1790/AD | 27/03/2024 | 0 | Resource Division | 25.73 | 0 | 0
3317 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Khan Saheber Abad W/S Scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18874) (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000073/2025-2026 | 2262/AD | 14/05/2025 | 45 | M/S. GIRI ENTERPRISE | 28.4 | 0 | 0
3318 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC, for Augmentation of Khan Saheber Abad W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000463/2024-2025 | 3422/AD | 21/08/2024 | 298 | M/S. DAS BUILDERS | 39.16 | 0 | 62
3319 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd Tubewell site for Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000591/2024-2025 | 4056/AD | 01/10/2024 | 45 | M/S. GIRI ENTERPRISE | 7.08 | 0 | 0
3320 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000935/2023-2024 | 3264/AD | 06/10/2023 | 30 | SUDIP PRADHAN | 17.3 | 0 | 80
3321 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000937/2023-2024 | 3265/AD | 06/10/2023 | 30 | SUDIP PRADHAN | 16.16 | 0 | 80
3322 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000 ] | Assistant Engineer, Kakdwip Sub Division |  | ORD/001085/2023-2024 | 3499/AD | 16/10/2023 | 90 | S.P. CONSTRUCTION (V) | 110.29 | 0 | 78
3323 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001086/2023-2024 | 3500/AD | 16/10/2023 | 300 | NIRMAL UDYOG | 174.3 | 0 | 50
3324 | Alipore Division | Kakdwip Sub-Division | Laying distribution system including Functional Household Tap Connection (FHTC) to all households for Augmentation of Khan Saheber Abad Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division |  | ORD/001137/2023-2024 | 3606/AD | 30/10/2023 | 30 | G.M. ENTERPRISE | 15.07 | 0 | 80
3325 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KHAN SAHEBER ABAD PWSS (PHASE-B) ) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001361/2023-2024 | 3258/AD | 05/10/2023 | 45 | VOYAGER | 3.74 | 0 | 100
3326 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & Boundary Wall at 1st Tubewell site for Khan Saheber Abad W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002120/2024-2025 | 1969/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.27 | 0 | 100
3327 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House & Boundary Wall at 2nd Tubewell site for Khan Saheber Abad W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18874) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002121/2024-2025 | 1970/KSD | 23/12/2024 | 20 | KHOKAN MONDAL | 2.26 | 0 | 100
3328 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3329 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th Tubewell site for Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/002537/2024-2025 | 815/AD | 27/02/2025 | 45 | M/S. M.S. ENTERPRISE | 7.1 | 0 | 0
3330 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Khansaheber Abad PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002614/2023-2024 | 379/KSD | 21/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3331 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Khan Saheber Abad PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002621/2023-2024 | 732/KSD | 05/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 0
3332 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000967/2023-2024 | 1761/AD | 27/03/2024 | 0 | Resource Division | 28.28 | 0 | 0
3333 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Laying distribution system for providing FHTC, construction of Valve Chamber etc. for Augmentation of Purusottampur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/18875) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000354/2024-2025 | 2799/AD | 02/07/2024 | 45 | A.G.ENTERPRISE | 0 | 0 | 0
3334 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURUSOTTAMPUR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001358/2023-2024 | 3255/AD | 05/10/2023 | 45 | VOYAGER | 5.51 | 0 | 100
3335 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Purusottampur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001428/2023-2024 | 4611/AD | 14/12/2023 | 300 | SPA ENTERPRISE | 641.07 | 0 | 50
3336 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Chemaguri, Purusottampur, Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002177/2023-2024 | 955/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.61 | 0 | 100
3337 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000970/2023-2024 | 1763/AD | 27/03/2024 | 0 | Resource Division | 108.57 | 0 | 0
3338 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Naraharipur W/S Scheme, Block - Sagar under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000159/2024-2025 | 2510/AD | 15/06/2024 | 190 | SIMPLEX DRILLING CO. | 51.43 | 0 | 100
3339 | Alipore Division | Kakdwip Sub-Division | Construction, Placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. at Naraharipur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000182/2024-2025 | 2541/AD | 18/06/2024 | 75 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 78.34 | 0 | 0
3340 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd Tubewell site for Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000386/2024-2025 | 3082/AD | 25/07/2024 | 45 | ARUSHI CONSTRUCTION | 7.18 | 0 | 0
3341 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Naraharipur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000387/2024-2025 | 3083/AD | 25/07/2024 | 45 | SWAPAN KUMAR PRADHAN | 34.22 | 0 | 0
3342 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 4th Tubewell Site for Augmentation of Naraharipur W/S scheme, Block : Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18876) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000388/2024-2025 | 3084/AD | 25/07/2024 | 30 | M/S. DAS BUILDERS | 11.75 | 0 | 0
3343 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001171/2023-2024 | 3815/AD | 07/11/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 668.32 | 0 | 40
3344 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (NARAHARIPUR PWSS (PHASE-B)) including Functional Household Tap Connection (FHTC) or implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/001359/2023-2024 | 3256/AD | 05/10/2023 | 45 | VOYAGER | 6.35 | 0 | 100
3345 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3346 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Naraharipur PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002610/2023-2024 | 377/KSD | 21/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3347 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000969/2023-2024 | 1762/AD | 27/03/2024 | 0 | Resource Division | 43.44 | 0 | 0
3348 | Alipore Division | Raidighi Sub-Division | Soil-Investigation work for the proposed 1500 Cum. Capacity Over Head Reservoir for Zone I, Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Maga surface water based W/S Scheme for Falta - Mathurapur Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000133/2025-2026 | 179/RSD | 05/06/2025 | 15 | BOSE ENGINEERS | 0.96 | 0 | 100
3349 | Alipore Division | Raidighi Sub-Division | Supply of Specials, laying DI pipeline including restoration of road in connection with piped water supply at Zone-I Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000281/2024-2025 | 2629/AD | 20/06/2024 | 90 | M/S B. ENTERPRISE | 127.22 | 0 | 95
3350 | Alipore Division | Raidighi Sub-Division | Restoration of road in connection with piped water supply at Zone-I Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/10218 & SM/18378) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000444/2024-2025 | 3325/AD | 12/08/2024 | 270 | M/S B. ENTERPRISE | 119.73 | 0 | 95
3351 | Alipore Division | Raidighi Sub-Division | Construction of 1500 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- I of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000576/2023-2024 | 2262/AD | 14/08/2023 | 600 | M/S. S.S. ENTERPRISE | 1185.63 | 0 | 10
3352 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 2) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Tentulberia W/S Scheme (Zone-I, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001258/2023-2024 | 4183/AD | 28/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.84 | 0 | 95
3353 | Alipore Division | Raidighi Sub-Division | Supplying, fabrication & insertion of 600 mm dia. (ID) 10mm thick MS casing pipe line 75 mtr. in length by HORIZONTAL DIRECTION DRILLING (HDD) technique underneath the Railway Track in between Node Point No. 442 to 443 of LDS under Zone ¿ I, Mathurapur ¿ I Block. The said location is in between Mathurapur and Madhabpur railway Station (Between mast no. 56/4, 56/6 and 56/5, 56/7 of Baruipur ¿ Lakshikantapur Section of Eastern Railway and comes with Gunjipur mouza as per permission of Railway Authority, for laying of 355.6 (OD) mm dia., 8 mm thick MS Water Supply Pipe 90 mtr. in length through the casing pipe for Augmentation of Laying Distribution System to extend the benefit of 100% households in Zone-I at Mathurapur ¿ I Block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District- South 24 Parganas under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002290/2023-2024 | 1026/AD | 19/02/2024 | 300 | TELETONE INDIA PVT. LTD. | 60.47 | 0 | 0
3354 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/05/2024 to 30/06/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002722/2024-2025 | 141/RSD | 29/04/2024 | 61 | SANKAR HALDER | 0.8 | 0 | 0
3355 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/07/2024 to 31/08/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002723/2024-2025 | 613/RSD | 29/06/2024 | 61 | SANKAR HALDER | 0.8 | 0 | 0
3356 | Alipore Division | Raidighi Sub-Division | Hiring of Diesel Maxi Cab for inspection and monitoring of JJM works on temporary basis under Raidighi Sub-Division P.H.E. Dte. [For 01/09/2024 to 31/10/2024 (Two) Months] | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002724/2024-2025 | 689C/RSD | 29/08/2024 | 61 | SANKAR HALDER | 0.8 | 0 | 0
3357 | Alipore Division | Raidighi Sub-Division | Restoration of concrete village road for LDS work at Zone-I (Node point Y-Z) of Mathurapur-I Block under 'Mega surface water based water supply scheme-Falta Mathurapur, Dist. ¿ South 24 Parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/003184/2020-2021 | 357/RSD | 13/10/2020 | 30 | M/S. GANGA ENTERPRISE | 4.8 | 0 | 100
3358 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000598/2023-2024 | 233/AD | 11/01/2024 | 0 | Resource Division | 13 | 0 | 0
3359 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000844/2023-2024 | 707/AD | 31/01/2024 | 0 | Resource Division | 137.95 | 0 | 0
3360 | Alipore Division | Kakdwip Sub-Division | Release of fund to PWD towards road restoration work. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | BILL/00939/2024-2025 | BP-2024-25-438 | 09/08/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 31.01 | 0 | 0
3361 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, Pile and Pile Cap for OHR etc at Hardwood Point PWSS, Block -Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14157) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000334/2024-2025 | 2739/AD | 26/06/2024 | 60 | M/S SAMADDAR CONSTRUCTION | 138.26 | 0 | 0
3362 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000399/2024-2025 | 3182/AD | 31/07/2024 | 30 | M/S D.D. INFRASTRUCTURE | 9.03 | 0 | 0
3363 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Harwood Point W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000957/2023-2024 | 2989/AD | 26/09/2023 | 45 | M/S SAMADDAR CONSTRUCTION | 27.68 | 0 | 100
3364 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Harwood Point W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/000958/2023-2024 | 2990/AD | 26/09/2023 | 30 | FORTUNE ENGINEERING | 9.53 | 0 | 0
3365 | Alipore Division | Kakdwip Sub-Division | Continuation Work Order for Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001152/2024-2025 | 2863/AD | 06/07/2024 | 25 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
3366 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Hardwood Point PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001783/2022-2023 | 3692/AD | 02/08/2022 | 45 | LEMNISCATE | 8.62 | 0 | 95
3367 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Hardwood Point Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 2040] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/001864/2022-2023 | 12417/AD | 09/03/2023 | 1135 | M/S SAMADDAR CONSTRUCTION | 167.97 | 0 | 50
3368 | Alipore Division | Kakdwip Sub-Division | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Hardwood Point Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1500 ] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002029/2022-2023 | 12996/AD | 23/03/2023 | 1200 | M/S SAMADDAR CONSTRUCTION | 366.95 | 0 | 50
3369 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 450 cum. capacity OHR of Hardwood Point PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002066/2023-2024 | 761(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3370 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Hardwood Point, Ganeshpur Kalinagar Zone - I & II, Kashinagar, Srinagar Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/002145/2023-2024 | 945/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
3371 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Harwood Point W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14157) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | ORD/003052/2024-2025 | 4087/AD | 03/10/2024 | 150 | GARAI INFRA PROJECT | 19.96 | 0 | 100
3372 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000124/2023-2024 | 661/AD | 17/05/2023 | 0 | Resource Division | 19.45 | 0 | 0
3373 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000455/2023-2024 | 4719/AD | 18/12/2023 | 0 | Resource Division | 89.99 | 0 | 0
3374 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000816/2023-2024 | 661/AD | 30/01/2024 | 0 | Resource Division | 3.49 | 0 | 0
3375 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division | RTOR000994/2023-2024 | 1787/AD | 27/03/2024 | 0 | Resource Division | 6.44 | 0 | 0
3376 | Alipore Division | Canning Sub-division | Laying additional pipe line to connect the uncovered habitation for Augmentation of Kalaria (Zone-IB) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000488/2024-2025 | 3547/AD | 02/09/2024 | 45 | SUPRITI ENTERPRISE | 34.28 | 0 | 0
3377 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Kalaria (Zone- IB) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000492/2023-2024 | 1792/AD | 26/07/2023 | 540 | S.B. ENTERPRISE | 8.75 | 0 | 100
3378 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer, Canning sub division |  | ORD/000520/2023-2024 | 2075/AD | 07/08/2023 | 45 | S.M. ENTERPRISE | 7.33 | 0 | 100
3379 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer, Canning sub division |  | ORD/000521/2023-2024 | 2076/AD | 07/08/2023 | 45 | ASHIS ENTERPRISE | 7.06 | 0 | 100
3380 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kalaria W/S Scheme (Zone-IB), Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House-III) | Assistant Engineer, Canning sub division |  | ORD/000523/2023-2024 | 2077/AD | 07/08/2023 | 45 | ASHIS ENTERPRISE | 7.05 | 0 | 100
3381 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IB), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1422] (TSM/017465) | Assistant Engineer, Canning sub division |  | ORD/000525/2023-2024 | 2141/AD | 09/08/2023 | 630 | SUPRITI ENTERPRISE | 270.46 | 0 | 85
3382 | Alipore Division | Canning Sub-division | Laying of Distribution System of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (TSM/017465) | Assistant Engineer, Canning sub division |  | ORD/000527/2023-2024 | 2142/AD | 09/08/2023 | 630 | PUTUL RANI MAITY | 217.06 | 0 | 97
3383 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) of Ground Water Based Augmentation Piped Water Supply Scheme for Kalaria (Zone-IA), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 2133] (TSM/017465) | Assistant Engineer, Canning sub division |  | ORD/000528/2023-2024 | 2143/AD | 09/08/2023 | 540 | PUTUL RANI MAITY | 127.34 | 0 | 70
3384 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kalaria (Zone-IB) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000558/2023-2024 | 2245/AD | 11/08/2023 | 60 | B.K. ENTERPRISE. | 60 | 0 | 98
3385 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Kalaria (Zone-IA & IB) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000616/2023-2024 | 2271/AD | 14/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.51 | 0 | 98
3386 | Alipore Division | Canning Sub-division | Construction of street stand post and valve chamber, damaged due to widening of road from Piali Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/001029/2022-2023 | 866/CSD | 26/08/2022 | 675 | ASHIS ENTERPRISE | 2.53 | 0 | 100
3387 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
3388 | Alipore Division | Canning Sub-division | Hiring of Diesel Car / Luxury Taxi for official use of Assistant Engineer, Canning Sub-Division, PHE Dte. for the period from 01.03.2024 to 15.03.2024 | Assistant Engineer, Canning sub division |  | ORD/003235/2023-2024 | 1568/CSD | 21/02/2024 | 15 | SAILEN CHANDRA DAS | 0.07 | 0 | 0
3389 | Alipore Division | Canning Sub-division | Hiring of 1 (One) No. Diesel Car / Luxury Taxi for supervision of different works Under JJM at Canning Sub-Division of Alipore Division, PHE Dte. for 1 (one) Year from the issuance of work order. (Perid from 16.03.2025 to 14.03.2026) | Assistant Engineer, Canning sub division |  | ORD/003373/2024-2025 | 309/CSD | 13/03/2025 | 365 | SAILEN CHANDRA DAS | 4.8 | 0 | 0
3390 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000065/2023-2024 | 268/AD | 24/04/2023 | 0 | Resource Division | 42.51 | 0 | 0
3391 | Alipore Division |  | Road restoration of 070- Atghora on L068 To Tagarberia(WB/02/320) |  |  | BILL/01779/2024-2025 | BP-2024-25-804 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.75 | 0 | 0
3392 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Ramtanunagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000291/2022-2023 | 3828/AD | 08/08/2022 | 30 | DEVDAS SHAW | 18.26 | 0 | 100
3393 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramtanunagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000324/2022-2023 | 3871/AD | 08/08/2022 | 30 | R.K. CONSTRUCTION | 11.92 | 0 | 45
3394 | Alipore Division | Kakdwip Sub-Division | Construction of Platform, Rising Main and Road Restoration for Augmentation of Ramtanunagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11751) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000472/2024-2025 | 3458/AD | 23/08/2024 | 75 | SARADA CONSTRUCTION | 86.58 | 0 | 100
3395 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (RAMTANUNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000500/2022-2023 | 1978/AD | 20/06/2022 | 45 | LEMNISCATE | 3.3 | 0 | 100
3396 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Construction of Pump House, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Ramtanunagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC =200] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000550/2022-2023 | 5724/AD | 13/10/2022 | 120 | SARADA CONSTRUCTION | 168.05 | 0 | 80
3397 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramtanunagar W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001163/2023-2024 | 3725/AD | 03/11/2023 | 30 | S.R. CONSTRUCTION | 9.57 | 0 | 80
3398 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at Head Work Site of Ramtanunagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11751) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002132/2023-2024 | 820/AD | 05/02/2024 | 30 | S. CHAKRABORTY AND CO. | 19.96 | 0 | 98
3399 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
3400 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000060/2022-2023 | 3949/AD | 12/08/2022 | 0 | Resource Division | 28.82 | 0 | 0
3401 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000277/2023-2024 | 3076/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3402 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000593/2023-2024 | 92/AD | 03/01/2024 | 0 | Resource Division | 1.19 | 0 | 0
3403 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000806/2023-2024 | 651/AD | 30/01/2024 | 0 | Resource Division | 3.42 | 0 | 0
3404 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 365 | SUPER SKILL | 87.04 | 50.54 | 95
3405 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division | RTOR000834/2023-2024 | 679/AD | 30/01/2024 | 0 | Resource Division | 10.93 | 0 | 0
3406 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Basantapur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000408/2020-2021 | 779/KSD | 14/10/2020 | 45 | M/S. SONAMONI ENTERPRISE | 4.78 | 4.65 | 0
3407 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Dhablat (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000409/2020-2021 | 780/KSD | 14/10/2020 | 45 | M/S. SUNITY ENTERPRISE | 4.71 | 4.53 | 0
3408 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Lalpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000421/2020-2021 | 798/KSD | 15/10/2020 | 45 | DIPA CHHETRI | 3.11 | 3.02 | 0
3409 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Golakpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000422/2020-2021 | 799/KSD | 15/10/2020 | 45 | JAGANNATH ENTERPRISE | 3.35 | 0 | 98
3410 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Prasadpur (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000440/2020-2021 | 826/KSD | 16/10/2020 | 45 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 3.41 | 0 | 100
3411 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Laxmibazar area (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000441/2020-2021 | 827/KSD | 16/10/2020 | 45 | M/S SNEHALATA ENTERPRISE | 3.64 | 0 | 100
3412 | Alipore Division | Kakdwip Sub-Division | Restoration of Functional Household Tap Connection (FHTC) to the households of Habitation: Bamoner More area (Part) of Dhablat W/S Scheme (Phase-I), Block -Sagar under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000472/2020-2021 | 1050/KSD | 19/12/2020 | 20 | M/S SAKTI GIRI ENTERPRISE | 3.97 | 0 | 93
3413 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works Augmentation of Dhablat (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) (SM/13876) (SM/07403) (SM/07405) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001332/2024-2025 | 5416/AD | 24/12/2024 | 480 | MONDAL ENTERPRISE (MURSHIDABAD) | 44 | 0 | 51
3414 | Alipore Division | Kakdwip Sub-Division | Laying Rising Main 150 mm dia. D.I. (K9) pipe and inter connection between 1 & 2 for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001930/2020-2021 | 1343/KSD | 23/02/2021 | 10 | UNITED BUILDERS | 3.32 | 0 | 90
3415 | Alipore Division | Kakdwip Sub-Division | Supply of CIDF Sluice Valves and 150 mm dia. CIDF Pipes and Specials for laying rising main for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001932/2020-2021 | 1345/KSD | 23/02/2021 | 10 | NITYANANDA MONDAL | 3.68 | 0 | 90
3416 | Alipore Division | Kakdwip Sub-Division | Supply of 250 mm dia. CIDF pipe and sSpecials for laying rising main for Dhablat W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001934/2020-2021 | 1347/KSD | 23/02/2021 | 10 | UNITED BUILDERS | 4.71 | 0 | 90
3417 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000708/2023-2024 | 478/AD | 24/01/2024 | 0 | Resource Division | 9.46 | 0 | 0
3418 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Nagartala Water Supply Scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000066/2021-2022 | 708/AD | 10/06/2021 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 223.57 | 0 | 70
3419 | Alipore Division | Canning Sub-division | Laying distribution system of Nagartala Water Supply Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000587/2022-2023 | 5863/AD | 18/10/2022 | 30 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 45.64 | 0 | 0
3420 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Nagartala (Zone-II) W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [365 Days] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002229/2020-2021 | 2030/CSD | 24/03/2021 | 365 | MODERN CONSTRUCTION | 2.77 | 0 | 100
3421 | Alipore Division | Canning Sub-division | Day to day annual operation, repair & maintenance of CI/DI/AC/UPVC Rising Main & Distribution System for different zones at Nagartala W/S Scheme (Zone-II) under Canning Sub Division of Alipore Division, PHE Dte. [From 01.01.2021 to 23.03.2021] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002421/2020-2021 | 1291/CSD | 30/12/2020 | 82 | MODERN CONSTRUCTION | 1.84 | 0 | 100
3422 | Alipore Division | Canning Sub-division | Construction of day to day annual Operation, repair & Maintenance of CI/DI/AC/UPVC Riising main & distribution system for different zones at Nagartala (zone-II) W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte.. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/003183/2020-2021 | 501/CSD | 05/08/2020 | 0 | MODERN CONSTRUCTION | 1.29 | 0 | 100
3423 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Suryanagar Water Supply scheme, Block - Kakdwip, South 24 Parganas District under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001567/2021-2022 | 6829/AD | 23/03/2022 | 45 | M/S B. ENTERPRISE | 113.06 | 0 | 94
3424 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000842/2023-2024 | 690/AD | 30/01/2024 | 0 | Resource Division | 24.01 | 0 | 0
3425 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Ramchandranagar W/S Scheme (Phase-A), Srinagar W/S Scheme (Phase-A), Suryanagar W/S Scheme (Phase-A) & Taktipur W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. [W/O No. 515/KSD, 24.08.21, T.No. 1801/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | VCH/002605/2021-2022 | BP-2021-22-508 | 22/03/2022 | 0 | LEMNISCATE | 4.7 | 0 | 0
3426 | Alipore Division | Kakdwip Sub-Division | Providing Valves for maintaining proper pressure head at dam area in Dakshin Shibganj W/S Scheme, Block - Pathar Pratima in connection with Retrofitting of Distribution System for Providing Functional Household Tap Connection (FHTC) under Jal Swapna under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000395/2020-2021 | 957/KSD | 03/11/2020 | 30 | M/S B. ENTERPRISE | 4.18 | 4.17 | 0
3427 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Shibganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/10482) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000418/2024-2025 | 3069/AD | 25/07/2024 | 45 | M/S B. ENTERPRISE | 28.74 | 0 | 60
3428 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (22-23, 21-25, 19-30, 8-9), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000480/2020-2021 | 1058/KSD | 19/12/2020 | 25 | M/S B. ENTERPRISE | 4.78 | 4.77 | 0
3429 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (16-17, 11-12, 5-6, 2-3), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000485/2020-2021 | 1062/KSD | 19/12/2020 | 25 | M/S B. ENTERPRISE | 4.75 | 4.74 | 0
3430 | Alipore Division | Kakdwip Sub-Division | Laying PUVC pipe line for providing Functional Household Tap Connection for Dakshin Shibganj piped water supply Scheme From Node Point - (30-31, 16-17, 3-3A, 27-28), Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/000504/2020-2021 | 1076/KSD | 19/12/2020 | 25 | M/S B. ENTERPRISE | 4.79 | 4.78 | 0
3431 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Dakshin Shibganj & Laxmijanardanpur W/S Scheme & it's adjacent areas, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001049/2021-2022 | 2332/AD | 09/09/2021 | 7 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
3432 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Dakshin Sibnagar Water Supply Scheme, Block - Kakdwip, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001207/2020-2021 | 2103/AD | 01/10/2020 | 365 | M/S B. ENTERPRISE | 64.82 | 0 | 95
3433 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House with approach road at 1st Tubewell site for Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07749) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001287/2024-2025 | 1920/KSD | 20/12/2024 | 25 | AZAD RAHAMAN LASKAR | 2.3 | 0 | 0
3434 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary Wall with approach road at 2nd Tubewell site for Dakshin Shibganj Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/07749) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001288/2024-2025 | 1921/KSD | 20/12/2024 | 25 | AZAD RAHAMAN LASKAR | 3.92 | 0 | 0
3435 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gangadharpur for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001785/2020-2021 | 1230/KSD | 23/02/2021 | 10 | SRI DURGA ENTERPRISE | 4.39 | 0 | 95
3436 | Alipore Division | Kakdwip Sub-Division | Laying UPVC pipe line for maintaining Functional Household Tap Connection at Pathar Pratima Bazar Area for Dakshin Shibganj piped water supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001789/2020-2021 | 1234/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.42 | 4.4 | 100
3437 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000773/2023-2024 | 607/AD | 29/01/2024 | 0 | Resource Division | 7.26 | 0 | 0
3438 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000311/2020-2021 | 328/A/RSD | 30/09/2020 | 15 | TIYASHA ENTERPRISE | 4.73 | 0 | 100
3439 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Purba Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000312/2020-2021 | 329/A/RSD | 30/09/2020 | 15 | M/S. JHARNA ENTERPRISE | 4.73 | 4.62 | 0
3440 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Marayari Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/000324/2020-2021 | 382/RSD | 16/10/2020 | 30 | TIYASHA ENTERPRISE | 4.73 | 0 | 100
3441 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Purba Boler Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/000326/2020-2021 | 383/RSD | 16/10/2020 | 30 | TIYASHA ENTERPRISE | 4.74 | 0 | 100
3442 | Alipore Division |  | Providing 110 nos Functional Household Tap Connection (FHTC) to the households at Uttar Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000348/2020-2021 | 391/RSD | 27/10/2020 | 30 | M/S. JHARNA ENTERPRISE | 4.74 | 4.63 | 0
3443 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Janar Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) |  |  | ORD/000359/2020-2021 | 426/RSD | 23/11/2020 | 60 | TIYASHA ENTERPRISE | 4.82 | 0 | 100
3444 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Purba Goler Gheri, Mouza-Jagannath Chak in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part -II) |  |  | ORD/000360/2020-2021 | 427/RSD | 23/11/2020 | 60 | M/S. JHARNA ENTERPRISE | 4.64 | 4.6 | 0
3445 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Manager Gheri, Mouza-Kailashpur in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/000361/2020-2021 | 428/RSD | 23/11/2020 | 60 | M/S. JHARNA ENTERPRISE | 4.82 | 4.8 | 0
3446 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Janar Gheri & Sarda Gheri, Mouza-Kailashpur in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. |  |  | ORD/000362/2020-2021 | 429/RSD | 23/11/2020 | 60 | M/S. R.M. CONSTRUCTION | 4.82 | 4.8 | 0
3447 | Alipore Division |  | Functional Household Tap Connection (FHTC) to the households at Purba Boler Gheri, Mouza-Mahabatnagar in Nandakumarpur Zone-II Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E.Dte. (Part-II) |  |  | ORD/000579/2020-2021 | 505/RSD | 24/12/2020 | 60 | A.P.C.ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.39 | 0 | 100
3448 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Kailashpur (Part-B) in Nandakumarpur Zone II piped water supply scheme, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001185/2021-2022 | 541/RSD | 30/11/2021 | 60 | M/S. L.P. CONSTRUCTION | 4.79 | 0 | 100
3449 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households of Mouza-Kailashpur (Part-A) in Nandakumarpur Zone II piped water supply scheme, District South 24 Parganas, Block - Mathurapur-II under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. |  |  | ORD/001205/2021-2022 | 523/RSD | 18/11/2021 | 60 | M/S. L.P. CONSTRUCTION | 4.79 | 0 | 100
3450 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000652/2023-2024 | 255/AD | 15/01/2024 | 0 | Resource Division | 11.25 | 0 | 0
3451 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamder etc. for Chemaguri W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/07757) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000339/2024-2025 | 2771/AD | 28/06/2024 | 224 | M. MUKHERJEE | 118.51 | 0 | 2
3452 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Chemaguri, Purusottampur, Mandirtala PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/002177/2023-2024 | 955/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.61 | 0 | 100
3453 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000341/2023-2024 | 3156/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3454 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000714/2023-2024 | 484/AD | 24/01/2024 | 0 | Resource Division | 8.91 | 0 | 0
3455 | Alipore Division |  | Laying 63 mm dia. (OD) UPVC Pipe Line to cover house holds situated at Bahirplot far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000144/2021-2022 | 399/KSD | 07/07/2021 | 25 | M/S. P. GIRI ENTERPRISE | 4.77 | 0 | 100
3456 | Alipore Division |  | Laying 25 mm dia. & 15 mm dia. PVC Pipe Line to cover house holds situated at Radhakrishnapur and Bahirplot area which are far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000146/2021-2022 | 401/KSD | 07/07/2021 | 15 | M/S. P. GIRI ENTERPRISE | 4.77 | 0 | 100
3457 | Alipore Division |  | Laying 90 mm dia. (OD) UPVC Pipe Line to cover house holds situated far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000151/2021-2022 | 403/KSD | 07/07/2021 | 25 | M/S. P. GIRI ENTERPRISE | 4.78 | 0 | 100
3458 | Alipore Division |  | Laying 63 mm dia. (OD) UPVC Pipe Line to cover house holds situated at Radhakrishnapur far away from habitations of Radhakrishnapur W/S Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000154/2021-2022 | 407/KSD | 07/07/2021 | 25 | M/S. P. GIRI ENTERPRISE | 4.79 | 0 | 100
3459 | Alipore Division |  | Laying Rising Main and inter connection of Tubewell and Supply and delivery of DI / CI specials for the same works for implementation of JJM of Radhakrishnapur Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division PHE Dte. |  |  | ORD/000353/2022-2023 | 338/KSD | 01/08/2022 | 20 | M/S BABUSONA ENTERPRISE | 2.47 | 0 | 100
3460 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Radhakrishnapur Water Supply Scheme, Block - Sagar, South 24 Parganas District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001277/2020-2021 | 2003/AD | 26/09/2020 | 365 | M/S. P. GIRI ENTERPRISE | 59.38 | 47.56 | 100
3461 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000711/2023-2024 | 481/AD | 24/01/2024 | 0 | Resource Division | 6.08 | 0 | 0
3462 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of APR-NOV23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/00437/2024-2025 |  | 28/05/2024 | 0 | RAJKUMAR MANNA | 18.72 | 0 | 0
3463 | Alipore Division | Kakdwip Sub-Division | LAUNCH HIRE CHARGES FOR SEPT'22-OCT'22 UNDER KAKDWIP SUB-DIVISION, PHE DTE-FUEL | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/00682/2024-2025 | BP-2024-25-227 | 20/06/2024 | 0 | RAJKUMAR MANNA | 0.73 | 0 | 0
3464 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of APR-NOV23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/03542/2023-2024 | BP-2023-24-1273 | 27/03/2024 | 0 | RAJKUMAR MANNA | 18.72 | 0 | 0
3465 | Alipore Division | Kakdwip Sub-Division | HIRE bill for month of APR-NOV23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | BILL/03543/2023-2024 | BP-2023-24-1274 | 27/03/2024 | 0 | RAJKUMAR MANNA | 1.46 | 0 | 0
3466 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Dakshin Gangadharpur Water Supply scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000005/2022-2023 | 122/AD | 07/04/2022 | 15 | FIDERE MARINE SERVICES PVT. LTD. | 12.98 | 0 | 100
3467 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Part-II) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000006/2022-2023 | 123/AD | 07/04/2022 | 15 | FIDERE MARINE SERVICES PVT. LTD. | 12.99 | 0 | 80
3468 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000019/2020-2021 | 2342/AD | 14/10/2020 | 60 | M/S. MA BHABANI CONSTRUCTION | 10.26 | 0 | 100
3469 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Abad Gangadharpur (Part) and Bahirchak (Part) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000139/2021-2022 | 394/KSD | 07/07/2021 | 15 | M/S BHAGABATI ENTERPRISE | 4.48 | 0 | 100
3470 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000162/2021-2022 | 405/KSD | 07/07/2021 | 15 | M/S PIRBABA ENTERPRISE | 4.79 | 0 | 97
3471 | Alipore Division | Kakdwip Sub-Division | Laying of UPVC pipe line by replacing the damaged pipe line of different dia. for providing FHTC at Dakshin Gangadharpur Water Supply Scheme, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000469/2021-2022 | 2417/AD | 15/09/2021 | 60 | L.N. ENTERPRISE | 37.12 | 0 | 100
3472 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001784/2020-2021 | 1229/KSD | 23/02/2021 | 10 | M/S JANA CONSTRUCTION | 4.39 | 4.38 | 100
3473 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Gangadharpur for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001785/2020-2021 | 1230/KSD | 23/02/2021 | 10 | SRI DURGA ENTERPRISE | 4.39 | 3.81 | 95
3474 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Taltukuri for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001786/2020-2021 | 1231/KSD | 23/02/2021 | 10 | KHATEJA CONSTRUCTION | 4.39 | 3.82 | 88
3475 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dhutkhali for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001788/2020-2021 | 1233/KSD | 23/02/2021 | 10 | GROWING CONCERN | 4.4 | 4.39 | 100
3476 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Kasarir Chak for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001793/2020-2021 | 1238/KSD | 23/02/2021 | 10 | M/S. NIRMAL KUMAR MONDAL | 4.61 | 4.26 | 93
3477 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001799/2020-2021 | 1241/KSD | 23/02/2021 | 10 | M/S. J.K. TRIPATHI & SONS | 4.74 | 4.69 | 99
3478 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001800/2020-2021 | 1242/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.74 | 4.73 | 100
3479 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001806/2020-2021 | 1244/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.74 | 4.73 | 100
3480 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bahirchak (Phase-I) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001814/2020-2021 | 1253/KSD | 23/02/2021 | 10 | L.N. ENTERPRISE | 3.95 | 3.95 | 100
3481 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001823/2020-2021 | 1257/KSD | 23/02/2021 | 10 | M/S. J.K. TRIPATHI & SONS | 4.61 | 0 | 93
3482 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001826/2020-2021 | 1260/KSD | 23/02/2021 | 10 | M/S JANA CONSTRUCTION | 3.51 | 3.5 | 100
3483 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001830/2020-2021 | 1261/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.6 | 4.53 | 0
3484 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001833/2020-2021 | 1264/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.61 | 0 | 98
3485 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bahirchak (Phase-II) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001836/2020-2021 | 1267/KSD | 23/02/2021 | 10 | L.N. ENTERPRISE | 2.63 | 2.46 | 94
3486 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001861/2020-2021 | 1292/KSD | 23/02/2021 | 10 | KRISHNA CONSTRUCTION | 4.74 | 4.47 | 95
3487 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Matilal (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001864/2020-2021 | 1295/KSD | 23/02/2021 | 10 | M/S JANA CONSTRUCTION | 2.19 | 0 | 96
3488 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Uttraabad Manasatala (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001865/2020-2021 | 1296/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 4.39 | 4.38 | 100
3489 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001867/2020-2021 | 1298/KSD | 23/02/2021 | 10 | TIYASHA ENTERPRISE | 3.29 | 0 | 80
3490 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-V) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001869/2020-2021 | 1300/KSD | 23/02/2021 | 10 | MITRA CONSTRUCTION | 3.07 | 2.97 | 97
3491 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Paik Para (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001875/2020-2021 | 1304/KSD | 23/02/2021 | 10 | MITRA CONSTRUCTION | 3.51 | 3.41 | 98
3492 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-III) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001877/2020-2021 | 1305/KSD | 23/02/2021 | 10 | ANANTA KUMAR GIRI | 4.39 | 4.31 | 99
3493 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Durganagar (Phase-IV) for Dakshin Gangadharpur W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001885/2020-2021 | 1307/KSD | 23/02/2021 | 10 | GROWING CONCERN | 3.07 | 3.07 | 100
3494 | Alipore Division | Kakdwip Sub-Division | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.01.2024 to 30.06.2024. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002122/2023-2024 | 5112/AD | 29/12/2023 | 183 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 100
3495 | Alipore Division | Kakdwip Sub-Division | Continuation order for the work of Laying distribution system along the East side of Main Road for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-N) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000422/2024-2025 | 3206/AD | 01/08/2024 | 30 | KHOKAN MONDAL | 14.43 | 0 | 100
3496 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for additional works along the East side of Main Road for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part - Q) (SM/11747) (SM/09395) (SM/08803) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000551/2024-2025 | 3780/AD | 18/09/2024 | 30 | KHOKAN MONDAL | 12.86 | 0 | 100
3497 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000698/2023-2024 | 468/AD | 24/01/2024 | 0 | Resource Division | 10 | 0 | 0
3498 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Gangasagar Zone - I & Gangasagar Zone - II W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001028/2021-2022 | 542/KSD | 01/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.57 | 0 | 100
3499 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000324/2023-2024 | 3139/AD | 29/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
3500 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000538/2023-2024 | 22/AD | 02/01/2024 | 0 | Resource Division | 18.95 | 0 | 0
3501 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000717/2023-2024 | 487/AD | 24/01/2024 | 0 | Resource Division | 12.34 | 0 | 0
3502 | Alipore Division | Kakdwip Sub-Division | Preparation of Design and DPR including estimate for retrofitting for Providing FHTC at Purusottampur W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001058/2021-2022 | 2346/AD | 09/09/2021 | 7 | M/S R.DUTTA & CO. | 2.12 | 0 | 100
3503 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Purusottampur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001085/2021-2022 | 576/KSD | 10/09/2021 | 20 | ROY CHOWDHURY ASSOCIATES | 4.59 | 0 | 100
3504 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Purusottampur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001428/2023-2024 | 4611/AD | 14/12/2023 | 300 | SPA ENTERPRISE | 641.07 | 0 | 50
3505 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000322/2023-2024 | 3137/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3506 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000534/2023-2024 | 18/AD | 02/01/2024 | 0 | Resource Division | 12.38 | 0 | 0
3507 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Naraharipur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001084/2021-2022 | 575/KSD | 01/09/2021 | 20 | LEMNISCATE | 4.24 | 0 | 100
3508 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Naraharipur Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001171/2023-2024 | 3815/AD | 07/11/2023 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 668.32 | 0 | 40
3509 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Naraharipur W/S Scheme & it's adjacent areas, Block Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001608/2021-2022 | 606/KSD | 27/09/2021 | 7 | LEMNISCATE | 1.55 | 0 | 100
3510 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000327/2023-2024 | 3142/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3511 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000535/2023-2024 | 19/AD | 02/01/2024 | 0 | Resource Division | 16.67 | 0 | 0
3512 | Alipore Division | Diamond Harbour Sub-Division | Laying distribution system in left out portion for 100% coverage of Functional Household Tap Connection (FHTC) at Kandalia, Sundarika, Parashurampur and Gopalpur villages due to Swajal Gram activities under Zone-V of Diamond Harbour-II within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000580/2022-2023 | 5856/AD | 18/10/2022 | 30 | M/S SAMADDAR CONSTRUCTION | 91.55 | 0 | 60
3513 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II Zone-V including Operation and Maintenance of scheme for 01 (one) year under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas Block Diamond Harbour-II, under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001337/2021-2022 | 6018/AD | 15/02/2022 | 365 | M/S A.K. GHATAK | 185.19 | 0 | 100
3514 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000069/2022-2023 | 4969/AD | 16/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
3515 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000097/2022-2023 | 7495/AD | 26/11/2022 | 0 | Resource Division | 3.52 | 0 | 0
3516 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Dakshin Gopalnagar 3 No. for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001744/2020-2021 | 1216/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.19 | 0 | 0
3517 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Hari Mandir Para (Phase-I), for Paschim Surendranagar Zone - I W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001759/2020-2021 | 1218/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.25 | 0 | 0
3518 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-A | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001796/2020-2021 | 1236/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.5 | 0 | 97
3519 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Part) & Purba Para (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001850/2020-2021 | 1281/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 0 | 0
3520 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-B | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001853/2020-2021 | 1284/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.46 | 0 | 87
3521 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Mahendranagar (Paschim) (Phase-II), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001855/2020-2021 | 1286/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
3522 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 1 no. Block (Part) & 2 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001857/2020-2021 | 1288/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
3523 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 4 no. Block (Part) & 5 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001887/2020-2021 | 1309/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
3524 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- Bangheri (Phase-III) for Ganeshpur W/S Scheme, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001917/2020-2021 | 1327/KSD | 23/02/2021 | 10 | TAPAN DAS | 4.39 | 0 | 100
3525 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Village :- Debnibus & Bijoybati of Debnibus W/S Scheme, Block -Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. Part-C | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001920/2020-2021 | 1330/KSD | 23/02/2021 | 10 | SUMAN ENTERPRISE | 4.49 | 0 | 96
3526 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 5 no. Block (Part) & Dakshin Gopalnagar 3 no. (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001922/2020-2021 | 1333/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.27 | 0 | 0
3527 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Habitation :- 2 no. Block (Part) & 4 no. Block (Part), for Paschim Surendranagar Zone - II W/S Scheme, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | ORD/001924/2020-2021 | 1336/KSD | 23/02/2021 | 10 | M/S B. ENTERPRISE | 4.28 | 0 | 0
3528 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_2, Kakdwip Sub Division | RTOR000776/2023-2024 | 610/AD | 29/01/2024 | 0 | Resource Division | 9.27 | 0 | 0
3529 | Alipore Division | Canning Sub-division | Inter connection and rising main for Tubewell No. 1, 2, 3 and 4 with supply of specials at Ramchandrakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000250/2023-2024 | 1393/AD | 12/07/2023 | 15 | ARBINA ENTERPRISE | 16.29 | 0 | 100
3530 | Alipore Division | Canning Sub-division | Laying Distribution system for Ramchandrakhali W/S Scheme (Zone-I), Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000665/2022-2023 | 6170/AD | 01/11/2022 | 840 | M/S R.K.ENTERPRISE (SALBAGAN) | 227.75 | 0 | 100
3531 | Alipore Division | Canning Sub-division | Relaying and repairing of pipe line for FHTC work at node point no. 124-122-121-120-33-34-36-89-88-87-85-38-40-50-51-52-55-56 of Chunakhali Water Supply Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000031/2022-2023 | 517/AD | 26/04/2022 | 30 | R.S.CONSTRUCTION CO. | 45.81 | 0 | 100
3532 | Alipore Division | Canning Sub-division | Relaying and repairing of damaged pipeline for FHTC at Chunakhali W/S Scheme at Khanka Sarif More to Sachiakhali FP School of Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001619/2020-2021 | 1345/CSD | 04/01/2021 | 30 | MODERN CONSTRUCTION | 4.82 | 0 | 100
3533 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme at Laskarpara to PWD Road and H/O Ganesh Sardar to H/O Dinanath Sardar of Purba Bayar Sing Mouza and Sachiakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001632/2020-2021 | 1348/CSD | 06/01/2021 | 30 | MODERN CONSTRUCTION | 4.68 | 0 | 100
3534 | Alipore Division | Canning Sub-division | Relaying damaged pipeline for FHTC at Chunakhali W/S Scheme Chunakhali Primary School to H/O Shyamal Das and H/O Prasanta Das to Chowmatha at Buglakhali Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001633/2020-2021 | 1349/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.73 | 0 | 100
3535 | Alipore Division | Canning Sub-division | Repairing damaged pipeline for FHTC at Chunakhali W/S Scheme at Buglakhali Mouza, Purba Bayar Sing Mouza, Sachiakhali Mouza and Baria Mouza, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001637/2020-2021 | 1350/CSD | 06/01/2021 | 30 | SUKANTA HALDER | 4.74 | 0 | 100
3536 | Alipore Division | Canning Sub-division | Continuation order for the work of Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Chunakhali (Zone - I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002438/2024-2025 | 623/AD | 17/02/2025 | 121 | AQUATECH ENGINEER | 19.6 | 0 | 100
3537 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- XV of Mathurapur -I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000111/2023-2024 | 37/AD | 05/04/2023 | 60 | M/S. JHARNA ENTERPRISE | 93.18 | 0 | 80
3538 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XV, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 718 Nos.) [Part - B] | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000112/2023-2024 | 38/AD | 05/04/2023 | 45 | BANERJEE ENTERPRISE | 44.3 | 0 | 10
3539 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | RTOR000242/2023-2024 | 2913/AD | 20/09/2023 | 0 | Resource Division | 1.38 | 0 | 0
3540 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | RTOR000638/2023-2024 | 242/AD | 15/01/2024 | 0 | Resource Division | 4.42 | 0 | 0
3541 | Alipore Division | Raidighi Sub-Division | Supply and delivery different dia of C.I.D.F. Sluice valve for different zone of Mathurapur I and II Block of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) of Raidighi Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000113/2023-2024 | 198/AD | 19/04/2023 | 15 | SSPR VALVE MANUFACTURING PVT. LTD | 22.66 | 0 | 100
3542 | Alipore Division | Raidighi Sub-Division | Providing FHTC at Zone- VI of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (New FHTC =4922 nos) | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000121/2023-2024 | 592/AD | 15/05/2023 | 90 | M/S. JHARNA ENTERPRISE | 272.12 | 0 | 0
3543 | Alipore Division | Raidighi Sub-Division | Land Development at head work site of Zone-VI, Mathurapur-II block under 'Mega surface water based water supply scheme-Falta Mathurapur under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/000440/2022-2023 | 4354/AD | 25/08/2022 | 30 | TARUN KUMAR BHATTACHARYA, PROP.- AVINABA BHATTACHARYA | 23.26 | 0 | 75
3544 | Alipore Division | Raidighi Sub-Division | Construction of service road for head work site of Zone-VI, Mathurapur-II block under Mega surface water based water supply scheme-FaltaMathurapur under Raidighi Sub-Division of AliporeDivision,P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | ORD/001136/2022-2023 | 601/RSD | 23/12/2022 | 30 | M/S M.B.ENTERPRISE | 4.7 | 0 | 20
3545 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Raidighi sub division | Junior Engineer,Junior Engineer1, Raidghi Sub Division | RTOR000039/2022-2023 | 3587/AD | 29/07/2022 | 0 | Resource Division | 700.28 | 0 | 0
3546 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 10 (ten) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Daharani Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001464/2021-2022 | 6258/AD | 24/02/2022 | 365 | A.G.ENTERPRISE | 145.57 | 0 | 95
3547 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000016/2022-2023 | 1173/AD | 27/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
3548 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000083/2022-2023 | 5549/AD | 29/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
3549 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Madarat More Riksha Stand to Najirpur Auto Stand via Kobindapur More to Vurkul Khalpar 2) L070- Atghora on L068 To Tagarberia(WB/02/320) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01776/2024-2025 | BP-2024-25-801 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 6.57 | 0 | 0
3550 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Meherpur W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000158/2023-2024 | 680/AD | 17/05/2023 | 1050 | M/S B. ENTERPRISE | 28.72 | 0 | 60
3551 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Meherpur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11745) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000188/2024-2025 | 2549/AD | 18/06/2024 | 60 | TANMAY ROY CHOWDHURY | 65.22 | 0 | 0
3552 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Meherpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000298/2023-2024 | 1492/AD | 14/07/2023 | 300 | TANMAY ROY CHOWDHURY | 311.15 | 0 | 30
3553 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Meherpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000299/2022-2023 | 3835/AD | 08/08/2022 | 45 | M/S. L.P. CONSTRUCTION | 37.08 | 0 | 100
3554 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Meherpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000305/2022-2023 | 3841/AD | 08/08/2022 | 30 | KUNDU CONSTRUCTION CO. | 9.96 | 0 | 50
3555 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MEHERPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000467/2022-2023 | 1708/AD | 14/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.77 | 0 | 100
3556 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Meherpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000921/2023-2024 | 2974/AD | 26/09/2023 | 45 | RAMKRISHNA ENTERPRISE | 9.54 | 0 | 0
3557 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Meherpur, Srinarayanpur (Part - I, II & II), Rajrajeswarpur, Ramganga PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002090/2023-2024 | 922/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.95 | 0 | 100
3558 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000065/2022-2023 | 3953/AD | 12/08/2022 | 0 | Resource Division | 13.52 | 0 | 0
3559 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000578/2023-2024 | 52/AD | 03/01/2024 | 0 | Resource Division | 6.41 | 0 | 0
3560 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000942/2023-2024 | 1676/AD | 22/03/2024 | 0 | Resource Division | 14.42 | 0 | 0
3561 | Alipore Division | Kakdwip Sub-Division | VEHICLE BILL FOR ASSISTANT ENGINEER HQ-II | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | BILL/00787/2022-2023 | BP-2022-23-981 | 21/03/2023 | 0 | DEEPAK KUMAR PRASAD | 0.38 | 0 | 0
3562 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Krishnanagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000144/2023-2024 | 143/KSD | 30/05/2023 | 10 | M/S. P. GIRI ENTERPRISE | 3.38 | 0 | 100
3563 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC, for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-P) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000169/2024-2025 | 2528/AD | 18/06/2024 | 30 | M/S. P. GIRI ENTERPRISE | 7.62 | 0 | 100
3564 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Krishnanagar for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000170/2024-2025 | 2529/AD | 18/06/2024 | 30 | ANANDA MAITY | 7.98 | 0 | 0
3565 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Paschim Gharai Para for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000171/2024-2025 | 2530/AD | 18/06/2024 | 30 | M/S SNEHALATA ENTERPRISE | 7.66 | 0 | 0
3566 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Gholapara South for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000172/2024-2025 | 2531/AD | 18/06/2024 | 30 | M/S. JOYGURU ENTERPRISE | 5.66 | 0 | 0
3567 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household in habitation - Gholapara for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000173/2024-2025 | 2532/AD | 18/06/2024 | 30 | M/S. MOYNA ENTERPRISE | 7.06 | 0 | 0
3568 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000174/2024-2025 | 2533/AD | 18/06/2024 | 30 | M/S B.S. ENTERPRISE | 5.73 | 0 | 0
3569 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000175/2024-2025 | 2534/AD | 18/06/2024 | 30 | PRADIP KUMAR MONDAL | 5.62 | 0 | 0
3570 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000177/2024-2025 | 2536/AD | 18/06/2024 | 30 | M/S MODINA ENTERPRISE | 5.52 | 0 | 0
3571 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000178/2024-2025 | 2537/AD | 18/06/2024 | 30 | M/S. JOYGURU ENTERPRISE | 5.43 | 0 | 0
3572 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000179/2024-2025 | 2538/AD | 18/06/2024 | 30 | M/S. BABA KAPIL MUNI ENTERPRISE | 7.01 | 0 | 0
3573 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household for augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) (SM/11747) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000180/2024-2025 | 2539/AD | 18/06/2024 | 30 | M/S PIR BABA ENTERPRISE | 5 | 0 | 0
3574 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Krishnanagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000297/2022-2023 | 3833/AD | 08/08/2022 | 30 | SIMPLEX DRILLING CO. | 22.93 | 0 | 99
3575 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 01 No. Pump House for Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000308/2022-2023 | 3856/AD | 08/08/2022 | 45 | MODERN CONSTRUCTION | 59.61 | 0 | 100
3576 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000309/2022-2023 | 3857/AD | 08/08/2022 | 30 | A. K. INDUSTRIES | 13.48 | 0 | 100
3577 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000310/2022-2023 | 3858/AD | 08/08/2022 | 30 | A. K. INDUSTRIES | 13.15 | 0 | 100
3578 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000311/2022-2023 | 3859/AD | 08/08/2022 | 30 | JOY GURU TRADING | 13.82 | 0 | 100
3579 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-G) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000312/2022-2023 | 3860/AD | 08/08/2022 | 30 | SARKAR ENTERPRISE | 11.97 | 0 | 100
3580 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-H) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000313/2022-2023 | 3861/AD | 08/08/2022 | 30 | DEY ENTERPRISE (III) | 11.47 | 0 | 100
3581 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000314/2022-2023 | 3862/AD | 08/08/2022 | 15 | SRI DURGA ENTERPRISE | 7.2 | 0 | 100
3582 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-J) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000315/2022-2023 | 3863/AD | 08/08/2022 | 15 | NARAYAN ENTERPRISE | 6.95 | 0 | 100
3583 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-K) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000316/2022-2023 | 3864/AD | 08/08/2022 | 30 | SWASTIK ENTERPRISE (NEW) | 6.95 | 0 | 100
3584 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-L) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000317/2022-2023 | 3865/AD | 08/08/2022 | 30 | M/S SNEHALATA ENTERPRISE | 5.57 | 0 | 100
3585 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-M) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000318/2022-2023 | 3866/AD | 08/08/2022 | 30 | M/S AMULLYA SARASWATI ENTERPRISE & CO. | 5.11 | 0 | 100
3586 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =510] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000407/2022-2023 | 4661/AD | 07/09/2022 | 120 | UNIVERSAL CORPORATION | 148.05 | 0 | 75
3587 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC =510] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000409/2022-2023 | 4678/AD | 07/09/2022 | 120 | M/S. P. GIRI ENTERPRISE | 151.6 | 0 | 100
3588 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (for the period from 01.09.2022 to 28.02.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000465/2022-2023 | 200/HQ-I/AD | 29/08/2022 | 6 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 60
3589 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KRISHNANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000479/2022-2023 | 1709/AD | 14/06/2022 | 45 | VOYAGER | 5.47 | 0 | 100
3590 | Alipore Division | Kakdwip Sub-Division | Inter connection between tubewell no. 1 and 2 to distribution system of Krishnanagar Water Supply Scheme, Block - Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001148/2021-2022 | 5536/AD | 20/01/2022 | 15 | JHARNA ENTERPRISE | 6.17 | 0 | 100
3591 | Alipore Division | Kakdwip Sub-Division | Laying distribution system along the East side of Main Road for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Krishnanagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-N) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001840/2023-2024 | 128/AD | 05/01/2024 | 54 | KHOKAN MONDAL | 29.23 | 0 | 100
3592 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3593 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Krishnanagar W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002419/2023-2024 | 1346/AD | 06/03/2024 | 30 | M/S. NAYAK CONSTRUCTION | 11.59 | 0 | 50
3594 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000093/2022-2023 | 5591/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
3595 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000331/2023-2024 | 3146/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3596 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000501/2023-2024 | 4826/AD | 20/12/2023 | 0 | Resource Division | 58.78 | 0 | 0
3597 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Ramchandranagar W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000132/2024-2025 | 2408/AD | 07/06/2024 | 30 | SUKUMAR HALDAR | 9.51 | 0 | 0
3598 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. for Augmentation of Ramchandranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11749) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000306/2024-2025 | 2680/AD | 24/06/2024 | 361 | AKKRITI CONSTRUCTION | 82.24 | 0 | 0
3599 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Construction of 1 no. Pump House for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000320/2022-2023 | 3867/AD | 08/08/2022 | 45 | S.S. ENTERPRISE (I) | 60.13 | 0 | 0
3600 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Ramchandranagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000389/2022-2023 | 4483/AD | 31/08/2022 | 30 | M/S BHAGABATI ENTERPRISE | 11.83 | 0 | 100
3601 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( RAMCHANDRANAGAR, PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000491/2022-2023 | 1749/AD | 15/06/2022 | 45 | LEMNISCATE | 5.29 | 0 | 100
3602 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Ramchandranagar W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11749) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000560/2024-2025 | 3812/AD | 19/09/2024 | 30 | S. CHAKRABORTY AND CO. | 20.39 | 0 | 0
3603 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gobindapur, Ramchandrapur, Ramchandranagar, Srikrishnanagar, Sibnagar, Manmathapur (Manmathanagar) PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002143/2023-2024 | 943/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
3604 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Ramchandranagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002601/2023-2024 | 179/KSD | 09/01/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3605 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000058/2022-2023 | 3917/AD | 12/08/2022 | 0 | Resource Division | 43.94 | 0 | 0
3606 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000275/2023-2024 | 3074/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3607 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000675/2023-2024 | 441/AD | 24/01/2024 | 0 | Resource Division | 7.18 | 0 | 0
3608 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000826/2023-2024 | 671/AD | 30/01/2024 | 0 | Resource Division | 13.45 | 0 | 0
3609 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000071/2023-2024 | 52/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3610 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Roypur PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11213)(Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000185/2024-2025 | 2545/AD | 18/06/2024 | 501 | M/S. TAPAS MONDAL | 61.79 | 0 | 0
3611 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000434/2022-2023 | 4349/AD | 25/08/2022 | 30 | M/S KHAJABABA ENTERPRISE | 21.58 | 0 | 60
3612 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000435/2022-2023 | 4350/AD | 25/08/2022 | 30 | M/S. TRIPATHI & CO. | 31.6 | 0 | 70
3613 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-F) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000436/2022-2023 | 4351/AD | 25/08/2022 | 30 | KHATEJA CONSTRUCTION | 9.07 | 0 | 0
3614 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dakshin Raypur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000459/2022-2023 | 294/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.88 | 0 | 100
3615 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 800] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000546/2022-2023 | 5722/AD | 13/10/2022 | 90 | S.P. CONSTRUCTION (I) | 99.45 | 0 | 84
3616 | Alipore Division | Kakdwip Sub-Division | Construction of 450 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000555/2022-2023 | 5729/AD | 13/10/2022 | 1080 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 497.15 | 0 | 20
3617 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 450 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Dakshin Roypur W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000582/2023-2024 | 2339/AD | 18/08/2023 | 45 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 57.53 | 0 | 0
3618 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 530] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000857/2022-2023 | 6940/AD | 18/11/2022 | 806 | M/S. TAPAS MONDAL | 104.45 | 0 | 92
3619 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dakshin Roypur W/S scheme, Block- Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001067/2023-2024 | 3385/AD | 11/10/2023 | 45 | SARADA CONSTRUCTION | 27.64 | 0 | 100
3620 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dakshin Roypur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001068/2023-2024 | 3387/AD | 11/10/2023 | 30 | ANANDA MAITY | 9.55 | 0 | 100
3621 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Dakshin Roypur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001079/2021-2022 | 557/KSD | 08/09/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.58 | 0 | 100
3622 | Alipore Division | Kakdwip Sub-Division | Construction of 02 nos. Pump House of size 5.40 mtr. x 3.60 mtr. as per departmental drawing and design for Augmentation of Dakshin Roypur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001417/2023-2024 | 4597/AD | 14/12/2023 | 60 | FORTUNE ENGINEERING | 11.18 | 0 | 100
3623 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Dakshin Raypur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001725/2022-2023 | 11751/AD | 21/02/2023 | 45 | NATIONAL ENTERPRISE | 38.58 | 0 | 100
3624 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3625 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall, approach road at 2nos Pump House site of Dakshin Roypur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11213) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002182/2024-2025 | 176/KSD | 11/01/2025 | 20 | KRISHNA CONSTRUCTION | 3.06 | 0 | 0
3626 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000449/2023-2024 | 4765/AD | 19/12/2023 | 0 | Resource Division | 78.58 | 0 | 0
3627 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000565/2023-2024 | 82/AD | 03/01/2024 | 0 | Resource Division | 21.5 | 0 | 0
3628 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000740/2023-2024 | 575/AD | 29/01/2024 | 0 | Resource Division | 8.29 | 0 | 0
3629 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000962/2023-2024 | 1696/AD | 22/03/2024 | 0 | Resource Division | 28.27 | 0 | 0
3630 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Uttar Damodarpur having village with maximum 114 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001128/2022-2023 | 8772/AD | 21/12/2022 | 60 | MD. NAZRUL ISLAM GAZI | 32.85 | 0 | 0
3631 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000876/2023-2024 | 783/AD | 03/02/2024 | 0 | Resource Division | 0.7 | 0 | 0
3632 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Alipore RWS Sub-Division, Alipore Division, P.H.E. Dte. for (WB-19G-0520) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | BILL/03557/2023-2024 | BP-2023-24-1264 | 27/03/2024 | 0 | AVIK HALDER | 1.87 | 0 | 0
3633 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Ramratanpur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000146/2023-2024 | 145/KSD | 30/05/2023 | 20 | MANDAL ENTERPRISE (JOYNAGAR) | 4.63 | 0 | 89
3634 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households of different habitation for Ramratanpur Water Supply Scheme, Block - Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000593/2022-2023 | 5918/AD | 19/10/2022 | 15 | HARIDAS DUTTA | 3.64 | 0 | 90
3635 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Ramratanpur Water Supply Scheme, Block - Kakdwip, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001294/2020-2021 | 2276/AD | 12/10/2020 | 365 | SARADA CONSTRUCTION | 59.73 | 48.32 | 95
3636 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Ramratanpur, Suryanagar Zone - I & II, Ganeshpur Left Out area PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002147/2023-2024 | 946/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
3637 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000278/2023-2024 | 3077/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3638 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000837/2023-2024 | 682/AD | 30/01/2024 | 0 | Resource Division | 6.26 | 0 | 0
3639 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Ramratanpur W/S Scheme (Phase-A), Koaberia W/S Scheme (Phase-A), Ramtanunagar W/S Scheme (Phase-A) & Shibkalinagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block Kakdwip under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte.[W/O NO. 513/AD, 20.08.21, T.NO. 1755/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | VCH/002608/2021-2022 | BP-2021-22-511 | 22/03/2022 | 0 | M/S R.DUTTA & CO. | 4.7 | 0 | 0
3640 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Mrityunjounagar W/S Scheme, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000145/2023-2024 | 144/KSD | 30/05/2023 | 10 | M/S. JAYDEEP DASGUPTA | 2.16 | 0 | 100
3641 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Mrityunjoynagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000276/2022-2023 | 3688/AD | 02/08/2022 | 30 | SIMPLEX DRILLING CO. | 22.95 | 0 | 100
3642 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MRITYUNJAYNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000482/2022-2023 | 1976/AD | 20/06/2022 | 45 | VOYAGER | 4.86 | 0 | 100
3643 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works and Construction of 01 no. Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000626/2022-2023 | 5979/AD | 20/10/2022 | 90 | M/S. JAYDEEP DASGUPTA | 129.4 | 0 | 100
3644 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001140/2022-2023 | 9079/AD | 27/12/2022 | 90 | M/S RAKESH ENTERPRISE | 129.2 | 0 | 100
3645 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Boundary Wall Painting, Repair and OHR Cat Ladder at 1st Tubewell site for Mritunjaynagar W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11698) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002161/2024-2025 | 171/KSD | 11/01/2025 | 142 | M/S THREE STAR & CO. | 3.82 | 0 | 100
3646 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mrityunjoynagar, Radhakrishnapur, Companirchar, Kachuberia PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002168/2023-2024 | 952/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3647 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Mrityunjaynagar W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002284/2023-2024 | 920/AD | 08/02/2024 | 30 | NEPAL CHANDRA PRADHAN | 11.88 | 0 | 100
3648 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works and Construction Pump House for Augmentation of Mrityunjoynagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A). | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002299/2023-2024 | 898/AD | 07/02/2024 | 45 | M/S. JAYDEEP DASGUPTA | 40.43 | 0 | 100
3649 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000045/2022-2023 | 3911/AD | 12/08/2022 | 0 | Resource Division | 59.91 | 0 | 0
3650 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000091/2022-2023 | 5592/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
3651 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000339/2023-2024 | 3154/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3652 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000900/2023-2024 | 886/AD | 07/02/2024 | 0 | Resource Division | 28.17 | 0 | 0
3653 | Alipore Division | Baruipur Sub-Division | Road restoration Construction of road mom Kanlokhal Bazar lo Begampur Colony Ghalonika Bridge | AE BSD,Assistant Engineer | JE-1,Junior Engineer | BILL/01705/2024-2025 | BP-2024-25-790 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.5 | 0 | 0
3654 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell,construction of boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Kamarchak having village with maximum 91 nos. households, Block - Diamond Harbour -I under Diamond Harbour Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001736/2022-2023 | 11765/AD | 21/02/2023 | 60 | BARI ENTERPRISE | 32.29 | 0 | 0
3655 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000869/2023-2024 | 776/AD | 03/02/2024 | 0 | Resource Division | 0.56 | 0 | 0
3656 | Alipore Division | Diamond Harbour Sub-Division | Repairing of Pump House no-1 under Zone-XIII of Kulpi Block under "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000330/2025-2026 | 269/DHSD | 16/06/2025 | 45 | M.P. ENTERPRISE (II) | 1.2 | 0 | 0
3657 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system with allied works to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-XIII at Kulpi block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 3170] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000373/2023-2024 | 1768/AD | 26/07/2023 | 615 | K.P. CONSTRUCTION | 634.65 | 0 | 60
3658 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XIII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001046/2022-2023 | 298/DHSD | 15/09/2022 | 30 | RAMKRISHNA CHAKRABORTY | 3.03 | 0 | 100
3659 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000144/2022-2023 | 14/AD | 05/04/2023 | 0 | Resource Division | 52.38 | 0 | 0
3660 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000201/2023-2024 | 1623/AD | 19/07/2023 | 0 | Resource Division | 15.54 | 0 | 0
3661 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000217/2023-2024 | 2028/AD | 05/08/2023 | 0 | Resource Division | 2.69 | 0 | 0
3662 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000426/2023-2024 | 3614/AD | 30/10/2023 | 0 | Resource Division | 19.53 | 0 | 0
3663 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-XII under Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001018/2024-2025 | 4929/AD | 03/12/2024 | 60 | M/S. JHARNA ENTERPRISE | 77.72 | 0 | 0
3664 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-XII of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001024/2022-2023 | 297/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 2.96 | 0 | 0
3665 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000125/2022-2023 | 12800/AD | 16/03/2023 | 0 | Resource Division | 19.82 | 0 | 0
3666 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000143/2022-2023 | 13/AD | 05/04/2023 | 0 | Resource Division | 21 | 0 | 0
3667 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000627/2023-2024 | 288/AD | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
3668 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000854/2023-2024 | 761/AD | 03/02/2024 | 0 | Resource Division | 3.97 | 0 | 0
3669 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Sibnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000126/2024-2025 | 2404/AD | 07/06/2024 | 30 | P & S ASSOCIATES | 11.73 | 0 | 0
3670 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Sibnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000206/2023-2024 | 789/AD | 24/05/2023 | 469 | M/S. BOSE CONCERN | 48.91 | 0 | 50
3671 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 1 no. 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal & Laying distribution system for providing FHTC, Platform, Road Restoration and Y junction for Augmentation of Chhoto Banashyamnagar, Sibnagar, Gangapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-B) (SM/13835, SM/13844, SM/13843) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000338/2024-2025 | 2752/AD | 27/06/2024 | 242 | M/S. S.S. ENTERPRISE | 373.95 | 0 | 20
3672 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Sibnagar W/S Scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (3rd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000593/2024-2025 | 4058/AD | 01/10/2024 | 45 | M/S SOURAV MAHAPATRA | 32.15 | 0 | 0
3673 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 2nd Tubewell Site of Sibnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/000831/2025-2026 | 2082/AD | 30/04/2025 | 30 | SARADA CONSTRUCTION | 26.06 | 0 | 0
3674 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SIBNAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001040/2022-2023 | 4155/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.14 | 0 | 100
3675 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 200 cum. capacity OHR of Sibnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/002068/2023-2024 | 764(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3676 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
3677 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000116/2023-2024 | 652/AD | 17/05/2023 | 0 | Resource Division | 10.98 | 0 | 0
3678 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000464/2023-2024 | 4760/AD | 19/12/2023 | 0 | Resource Division | 16.8 | 0 | 0
3679 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000750/2023-2024 | 585/AD | 29/01/2024 | 0 | Resource Division | 1.97 | 0 | 0
3680 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Kedarpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13845) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000456/2024-2025 | 3414/AD | 21/08/2024 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 46.54 | 0 | 0
3681 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (KEDARPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000990/2022-2023 | 4151/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.59 | 0 | 100
3682 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Kedarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001059/2023-2024 | 3378/AD | 11/10/2023 | 45 | DEBASIS JANA | 27.6 | 0 | 0
3683 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Kedarpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001310/2022-2023 | 9893/AD | 09/01/2023 | 45 | MANDAL CONSTRUCTION | 38.6 | 0 | 90
3684 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Kedarpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 972] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001879/2022-2023 | 12422/AD | 09/03/2023 | 300 | FIDERE MARINE SERVICES PVT. LTD. | 284.95 | 0 | 25
3685 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3686 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Kedarpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002155/2023-2024 | 801/AD | 05/02/2024 | 45 | M/S SNEHALATA ENTERPRISE | 11.73 | 0 | 100
3687 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Kedarpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/003144/2023-2024 | 382/KSD | 20/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3688 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000107/2023-2024 | 643/AD | 17/05/2023 | 0 | Resource Division | 5.34 | 0 | 0
3689 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000496/2023-2024 | 4961/AD | 22/12/2023 | 0 | Resource Division | 33.79 | 0 | 0
3690 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000751/2023-2024 | 586/AD | 29/01/2024 | 0 | Resource Division | 0.96 | 0 | 0
3691 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000955/2023-2024 | 1689/AD | 22/03/2024 | 0 | Resource Division | 0.47 | 0 | 0
3692 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st Tubewell Site of Gobindapur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001160/2023-2024 | 3722/AD | 03/11/2023 | 30 | NEPAL CHANDRA PRADHAN | 9.43 | 0 | 100
3693 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gobindapur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001314/2022-2023 | 9897/AD | 10/01/2023 | 30 | M/S NAIYA & MAITY | 19.06 | 0 | 100
3694 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GOBINDPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001342/2022-2023 | 3800/AD | 05/08/2022 | 45 | LEMNISCATE | 0.6 | 0 | 100
3695 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, construction of 01 no. pump house size 5.40mtr. x 3.60 mtr., Functional Household Tap Connection (FHTC) to all households including O & M of Laying distribution & FHTC for 1 year after completion of FHTC works for Gobindapur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | ORD/001425/2023-2024 | 4604/AD | 14/12/2023 | 90 | M/S. LOKNATH CONSTRUCTION | 62.37 | 0 | 0
3696 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Junior Engineer 4, Raidghi Sub Division,Juniour Engineer_2, Kakdwip Sub Division | RTOR000589/2023-2024 | 88/AD | 03/01/2024 | 0 | Resource Division | 1.57 | 0 | 0
3697 | Alipore Division | South 24 Pgs. W/S Division - I | Road restoration of Harishankarpur Bharat Ghosh more to Dakshin Mukundapur Under Magrahal II PS | AE RWS, Alipore Division,Assistant Engineer | JE RWS, HQ,Junior Engineer | BILL/01668/2024-2025 | BP-2024-25-775 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.36 | 0 | 0
3698 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Ramdebpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 766] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000265/2023-2024 | 3828/AD | 07/11/2023 | 300 | CHANDAN ROY | 172.49 | 0 | 0
3699 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Ramdebpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001060/2023-2024 | 3386/AD | 11/10/2023 | 45 | DEB ASSOCIATE | 27.5 | 0 | 0
3700 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Ramdebpur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001212/2023-2024 | 3869/AD | 09/11/2023 | 30 | SOMNATH ENTERPRISE | 9.47 | 0 | 70
3701 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Ramdebpur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001722/2022-2023 | 11748/AD | 21/02/2023 | 45 | MODERN CONSTRUCTION (NEW) | 38.59 | 0 | 100
3702 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Ramdebpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Patharpratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001788/2022-2023 | 3694/AD | 02/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 2.63 | 0 | 95
3703 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhajna, Dakshin Madhusudanpur, Ramdebpur, Dakshin Gangadharpur, Gayadham, Indraprastha PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002089/2023-2024 | 921/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3704 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Ramdebpur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14984) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002590/2024-2025 | 922/AD | 05/03/2025 | 60 | CHANDAN ROY | 60.06 | 0 | 0
3705 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000117/2023-2024 | 653/AD | 17/05/2023 | 0 | Resource Division | 4.21 | 0 | 0
3706 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000462/2023-2024 | 4761/AD | 19/12/2023 | 0 | Resource Division | 20.06 | 0 | 0
3707 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000573/2023-2024 | 74/AD | 03/01/2024 | 0 | Resource Division | 0.73 | 0 | 0
3708 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000958/2023-2024 | 1692/AD | 22/03/2024 | 0 | Resource Division | 7.32 | 0 | 0
3709 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of "Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas", under Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. (period from 01/05/2023 to 31/10/2023) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000081/2023-2024 | 27/DHSD | 25/04/2023 | 184 | SUMAN HALDER | 2.4 | 0 | 0
3710 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution pipe line of different dia. M.S. and different dia. UPVC pipe line of damage portion due to road widening for 5 nos. culvert crossing with allied works at sonamukhi bridge near Parulia G.P, at Dostipur-Usthi road, at Hatuganje more to Netra stations road and OHR head work site to Hatuganje more road under Augmentation scheme of Diamond Harbour-I Zone-IV, Zone-X & Zone-III within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000098/2025-2026 | 2527/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 89.87 | 0 | 100
3711 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle for the use of JJM related works under the office of the Assistant Engineer, Diamond Harbour Sub-Division, under Alipore Division, P.H.E. Dte. (period from 01/10/2023 to 30/09/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001268/2023-2024 | 449/DHSD | 29/09/2023 | 366 | M.P. ENTERPRISE (II) | 4.8 | 0 | 0
3712 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 2510] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001397/2022-2023 | 10869/AD | 04/02/2023 | 900 | PROJECT & MAINTENANCE | 197.45 | 0 | 80
3713 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000133/2022-2023 | 23/AD | 05/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
3714 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000233/2023-2024 | 2194/AD | 10/08/2023 | 0 | Resource Division | 15.42 | 0 | 0
3715 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000347/2023-2024 | 3211/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
3716 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000892/2023-2024 | 746/AD | 03/02/2024 | 0 | Resource Division | 15.46 | 0 | 0
3717 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000913/2023-2024 | 1255/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3718 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-I at Diamond Harbour-I block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14476] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000983/2024-2025 | 4854/AD | 29/11/2024 | 180 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 118.31 | 0 | 40
3719 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-I at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 3240] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001396/2022-2023 | 10868/AD | 04/02/2023 | 900 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 252.48 | 0 | 70
3720 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000230/2023-2024 | 2191/AD | 10/08/2023 | 0 | Resource Division | 19.34 | 0 | 0
3721 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000352/2023-2024 | 3216/AD | 04/10/2023 | 0 | Resource Division | 0.52 | 0 | 0
3722 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000889/2023-2024 | 743/AD | 03/02/2024 | 0 | Resource Division | 19.34 | 0 | 0
3723 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bishnupur Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000074/2023-2024 | 58/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3724 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Bishnupur Zone-I PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000075/2023-2024 | 59/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3725 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform etc. at different households for Augmentation of Bishnupur W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone- I & II) (SM/13117) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000337/2024-2025 | 2751/AD | 27/06/2024 | 45 | M/S. S.S. ENTERPRISE | 109.19 | 0 | 100
3726 | Alipore Division | Kakdwip Sub-Division | Surging of 2 nos. Tubewell for augmentation of Bishnupur W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000541/2023-2024 | 359/KSD | 09/08/2023 | 565 | S.K.GOLUI | 3.55 | 0 | 100
3727 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 2 nos. 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Bishnupur (Zone-I & II) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000621/2023-2024 | 2431/AD | 22/08/2023 | 60 | M/S. S.S. ENTERPRISE | 119.53 | 0 | 50
3728 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000769/2022-2023 | 6524/AD | 11/11/2022 | 90 | M/S. SARADA UDYOG | 104.36 | 0 | 100
3729 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Bishnupur (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000770/2022-2023 | 6525/AD | 11/11/2022 | 45 | SIMPLEX DRILLING CO. | 45.84 | 0 | 100
3730 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000771/2022-2023 | 6526/AD | 11/11/2022 | 30 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 13.02 | 0 | 100
3731 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Bishnupur (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000772/2022-2023 | 6527/AD | 11/11/2022 | 30 | M/S. PAPIYA ENTERPRISE | 6.89 | 0 | 98
3732 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BISHNUPUR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001056/2022-2023 | 4647/AD | 06/09/2022 | 45 | VOYAGER | 11.73 | 0 | 100
3733 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Bishnupur (Zone-I and II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001418/2023-2024 | 4598/AD | 14/12/2023 | 30 | M/S. S.S. ENTERPRISE | 12.53 | 0 | 100
3734 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bishnupur Zone - I & II, Gangasagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002150/2023-2024 | 947/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
3735 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002173/2023-2024 | 811/AD | 05/02/2024 | 45 | M/S SUNITY ENTERPRISE | 33.71 | 0 | 100
3736 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Bishnupur (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002174/2023-2024 | 812/AD | 05/02/2024 | 30 | M/S SWAPAN KUMAR PRADHAN | 11.77 | 0 | 100
3737 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000328/2023-2024 | 3143/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
3738 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000497/2023-2024 | 4823/AD | 20/12/2023 | 0 | Resource Division | 83.64 | 0 | 0
3739 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000543/2023-2024 | 27/AD | 02/01/2024 | 0 | Resource Division | 6.09 | 0 | 0
3740 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000684/2023-2024 | 454/AD | 24/01/2024 | 0 | Resource Division | 10.97 | 0 | 0
3741 | Alipore Division | Canning Sub-division | Sinking of 150 X 100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, Construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Maukhali-Kumarkhali (Part - III) having village with maximum 148 nos. households, Block - Canning -II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000657/2022-2023 | 6678/AD | 14/11/2022 | 85 | S.S. ENTERPRISE (I) | 43.3 | 0 | 84
3742 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Maukhali-Kumarkhali (Part-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001899/2022-2023 | 5663/AD | 10/11/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 0.37 | 0 | 0
3743 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000168/2023-2024 | 1121/AD | 22/06/2023 | 0 | Resource Division | 0.91 | 0 | 0
3744 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Surendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13799) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000168/2024-2025 | 2519/AD | 15/06/2024 | 45 | SIMPLEX DRILLING CO. | 40.38 | 0 | 0
3745 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Purba Surendranagar W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13799) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000454/2024-2025 | 3412/AD | 21/08/2024 | 60 | FIDERE MARINE SERVICES PVT. LTD. | 65.8 | 0 | 0
3746 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA SURENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000983/2022-2023 | 3667/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.53 | 0 | 100
3747 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Surendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000984/2023-2024 | 3003/AD | 26/09/2023 | 45 | M/S MA BILASINI CONSTRUCTION | 27.16 | 0 | 0
3748 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Surendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000985/2023-2024 | 3004/AD | 26/09/2023 | 30 | NARAYAN ENTERPRISE | 9.49 | 0 | 65
3749 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Purba Surendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001876/2022-2023 | 12419/AD | 09/03/2023 | 90 | M/S. SARADA UDYOG | 129.3 | 0 | 55
3750 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Purba Surendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 910] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001878/2022-2023 | 12421/AD | 09/03/2023 | 300 | FIDERE MARINE SERVICES PVT. LTD. | 251 | 0 | 40
3751 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Purba Surendranagar, Dakshin Kashinagar, Herambagopalpur, Achintyanagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002105/2023-2024 | 927/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
3752 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000095/2023-2024 | 541/AD | 12/05/2023 | 0 | Resource Division | 9.94 | 0 | 0
3753 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000509/2023-2024 | 4944/AD | 22/12/2023 | 0 | Resource Division | 44.12 | 0 | 0
3754 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000745/2023-2024 | 580/AD | 29/01/2024 | 0 | Resource Division | 1.79 | 0 | 0
3755 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000951/2023-2024 | 1685/AD | 22/03/2024 | 0 | Resource Division | 0.57 | 0 | 0
3756 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Dakshin Surendraganj PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13974) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000184/2024-2025 | 2544/AD | 18/06/2024 | 75 | GROWING CONCERN | 91.83 | 0 | 100
3757 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dakshin Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000962/2023-2024 | 285(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3758 | Alipore Division | Kakdwip Sub-Division | Continuation work order for Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Dakshin Surendraganj W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001087/2023-2024 | 3554/AD | 17/10/2023 | 30 | SARADA CONSTRUCTION | 49.21 | 0 | 100
3759 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme [DAKSHIN SURENDRAGANJ PWSS] including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001329/2022-2023 | 3311/AD | 20/07/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.53 | 0 | 100
3760 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Dakshin Surendraganj W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001843/2023-2024 | 131/AD | 05/01/2024 | 60 | BIMALENDU GIRI | 36.15 | 0 | 100
3761 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Satyadaspur, Indrapur, Dakshin Surendraganj, Uttar Surendraganj PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002109/2023-2024 | 930/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
3762 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002165/2023-2024 | 808/AD | 05/02/2024 | 391 | TANMAY ROY CHOWDHURY | 33.34 | 0 | 100
3763 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Surendraganj W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002166/2023-2024 | 809/AD | 05/02/2024 | 360 | TIYASHA ENTERPRISE | 11.73 | 0 | 100
3764 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000113/2023-2024 | 649/AD | 17/05/2023 | 0 | Resource Division | 8.43 | 0 | 0
3765 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000299/2023-2024 | 3094/AD | 28/09/2023 | 0 | Resource Division | 18.61 | 0 | 0
3766 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000473/2023-2024 | 4758/AD | 19/12/2023 | 0 | Resource Division | 21.21 | 0 | 0
3767 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000680/2023-2024 | 446/AD | 24/01/2024 | 0 | Resource Division | 5.13 | 0 | 0
3768 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000758/2023-2024 | 593/AD | 29/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
3769 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Purba Dwarokapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000381/2023-2024 | 1774/AD | 26/07/2023 | 706 | SUPRITI ENTERPRISE | 54.89 | 0 | 50
3770 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Purba Dwarokapur W/S Scheme, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13867) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000455/2024-2025 | 3413/AD | 21/08/2024 | 60 | S.S. ENTERPRISE (II) | 65.96 | 0 | 0
3771 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Purba Dwarokapur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000964/2023-2024 | 287(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3772 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (PURBA DWAROKAPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001032/2022-2023 | 4152/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.96 | 0 | 100
3773 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Purba Dwarokapur W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001723/2022-2023 | 11749/AD | 21/02/2023 | 45 | NATIONAL ENTERPRISE | 38.58 | 0 | 100
3774 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Purba Dwarokapur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 900] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001787/2022-2023 | 11558/AD | 17/02/2023 | 1049 | M/S. SUMAN ENTERPRISE | 272.92 | 0 | 60
3775 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
3776 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Purba Dwarokapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002157/2023-2024 | 802/AD | 05/02/2024 | 606 | S.S. ENTERPRISE (II) | 27.9 | 0 | 0
3777 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Purba Dwarokapur W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002280/2023-2024 | 916/AD | 08/02/2024 | 263 | M/S RADHAKRISHNA CONSTRUCTION | 9.71 | 0 | 96
3778 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000108/2023-2024 | 644/AD | 17/05/2023 | 0 | Resource Division | 6.7 | 0 | 0
3779 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000495/2023-2024 | 4962/AD | 22/12/2023 | 0 | Resource Division | 20.42 | 0 | 0
3780 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000752/2023-2024 | 587/AD | 29/01/2024 | 0 | Resource Division | 1.2 | 0 | 0
3781 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000956/2023-2024 | 1690/AD | 22/03/2024 | 0 | Resource Division | 0.47 | 0 | 0
3782 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gopalnagar Uttar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000159/2023-2024 | 681/AD | 17/05/2023 | 45 | ARBINA ENTERPRISE | 28.27 | 0 | 0
3783 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gopalnagar Uttar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000160/2023-2024 | 682/AD | 17/05/2023 | 30 | CHATTERJEE ENTERPRISES | 9.65 | 0 | 100
3784 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia. depth up to 450 mtr. for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Gopalnagar Uttar W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000314/2023-2024 | 190/KSD | 21/06/2023 | 7 | FORTUNE ENGINEERING | 2.73 | 0 | 99
3785 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000379/2023-2024 | 1772/AD | 26/07/2023 | 70 | MOUMITA ENTERPRISE | 39.62 | 0 | 100
3786 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Gopalnagar Uttar W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000586/2023-2024 | 2343/AD | 18/08/2023 | 587 | RELIABLE CONSTRUCTIONS | 34.49 | 0 | 50
3787 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials of Gopalnagar Uttar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000719/2023-2024 | 2536/AD | 28/08/2023 | 60 | RELIABLE CONSTRUCTIONS | 5.5 | 0 | 100
3788 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gopalnagar Uttar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000910/2023-2024 | 269(I)/KSD | 10/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3789 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GOPALNAGAR UTTAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000981/2022-2023 | 4146/AD | 19/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.4 | 0 | 100
3790 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 Nos. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site of Gopalnagar Uttar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001269/2023-2024 | 4214/AD | 29/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.3 | 0 | 100
3791 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Gopalnagar Uttar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001308/2022-2023 | 9891/AD | 10/01/2023 | 45 | MANDAL CONSTRUCTION | 38.6 | 0 | 100
3792 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Gopalnagar Uttar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 350] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001507/2022-2023 | 11025/AD | 08/02/2023 | 902 | RELIABLE CONSTRUCTIONS | 174.79 | 0 | 50
3793 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Gopalnagar Uttar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 950] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001541/2022-2023 | 11026/AD | 08/02/2023 | 1059 | RELIABLE CONSTRUCTIONS | 174.69 | 0 | 82
3794 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
3795 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000085/2023-2024 | 531/AD | 12/05/2023 | 0 | Resource Division | 8.79 | 0 | 0
3796 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000525/2023-2024 | 4934/AD | 22/12/2023 | 0 | Resource Division | 18.65 | 0 | 0
3797 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000582/2023-2024 | 54/AD | 03/01/2024 | 0 | Resource Division | 1.52 | 0 | 0
3798 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Upendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000121/2024-2025 | 2399/AD | 07/06/2024 | 45 | SARADA CONSTRUCTION | 50.92 | 0 | 100
3799 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Upendranagar PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/13828) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000663/2024-2025 | 4212/AD | 23/10/2024 | 60 | SARADA CONSTRUCTION | 135.89 | 0 | 0
3800 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Upendranagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000963/2023-2024 | 286(I)/KSD | 18/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3801 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Upendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000977/2023-2024 | 2996/AD | 26/09/2023 | 45 | DEBASIS JANA | 33.33 | 0 | 0
3802 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Upendranagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000978/2023-2024 | 2997/AD | 26/09/2023 | 30 | M/S KHAJABABA ENTERPRISE | 11.7 | 0 | 0
3803 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (UPENDRANAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001036/2022-2023 | 3670/AD | 01/08/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.24 | 0 | 100
3804 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 150] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001505/2022-2023 | 10991/AD | 07/02/2023 | 810 | SARADA CONSTRUCTION | 174.6 | 0 | 80
3805 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households including construction of 02 nos, Pump House for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 500] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001542/2022-2023 | 11027/AD | 08/02/2023 | 90 | SARADA CONSTRUCTION | 173.65 | 0 | 25
3806 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Upendranagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC = 1084] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002063/2022-2023 | 13005/AD | 23/03/2023 | 90 | SARADA CONSTRUCTION | 163.54 | 0 | 50
3807 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Upendranagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002083/2022-2023 | 13256/AD | 31/03/2023 | 45 | PRADIP KUMAR JATI | 46.55 | 0 | 0
3808 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Upendranagar, Purba Sripatinagar, Paschim Sripatinagar, Krishnadaspur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002108/2023-2024 | 929/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
3809 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000090/2023-2024 | 536/AD | 12/05/2023 | 0 | Resource Division | 9.53 | 0 | 0
3810 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000519/2023-2024 | 4939/AD | 22/12/2023 | 0 | Resource Division | 19.36 | 0 | 0
3811 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000584/2023-2024 | 58/AD | 03/01/2024 | 0 | Resource Division | 1.65 | 0 | 0
3812 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000948/2023-2024 | 1682/AD | 22/03/2024 | 0 | Resource Division | 1.98 | 0 | 0
3813 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gopalnagar Uttar Zone-I W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000151/2023-2024 | 637/AD | 17/05/2023 | 45 | MOUMITA ENTERPRISE | 28.64 | 0 | 0
3814 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gopalnagar Uttar Zone-I W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000152/2023-2024 | 638/AD | 17/05/2023 | 30 | JOY GURU BUILDERS | 9.59 | 0 | 0
3815 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Gopalnagar Uttar Zone I W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000192/2024-2025 | 2552/AD | 18/06/2024 | 45 | MANASH GHOSH | 50.94 | 0 | 0
3816 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc for Gopalnagar Uttar Zone I W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/15524) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000375/2024-2025 | 3001/AD | 19/07/2024 | 75 | MANASH GHOSH | 240.67 | 0 | 0
3817 | Alipore Division | Kakdwip Sub-Division | Construction of 2 nos. Pump House for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000420/2024-2025 | 3071/AD | 25/07/2024 | 45 | MONDAL ENTERPRISE (NEW) | 11.18 | 0 | 0
3818 | Alipore Division | Kakdwip Sub-Division | Trial bore (1 no.) of 100mm dia depth up to 450 mtr for Sinking of 250mm x 150mm dia. deep Tubewell by D.R. Rig method at Head Work Site of Gopalnagar Uttar Zone-I W/S Scheme under JJM, Block - Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001005/2023-2024 | 509/KSD | 03/10/2023 | 7 | S.K.GOLUI | 2.73 | 0 | 0
3819 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001777/2022-2023 | 11501/AD | 15/02/2023 | 895 | M/S ACME ENTERPRISE | 11.94 | 0 | 50
3820 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar, Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001778/2022-2023 | 11502/AD | 15/02/2023 | 50 | M/S MODINA ENTERPRISE | 16.93 | 0 | 100
3821 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002057/2022-2023 | 12651/AD | 13/03/2023 | 300 | MANASH GHOSH | 466.39 | 0 | 50
3822 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Gopalnagar Uttar Zone-I PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002075/2023-2024 | 772(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
3823 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Gopalnagar Uttar Zone-I Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =325] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002078/2022-2023 | 13127/AD | 27/03/2023 | 905 | M/S CHANDIMATA CONSTRUCTION | 105.76 | 0 | 60
3824 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Gopalnagar Uttar, Durga Gobindapur, Paschim Surendranagar Zone-II (Part - I & II), Gopalnagar Uttar Zone-I, Dakshin Laxminarayanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002091/2023-2024 | 923/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
3825 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st tubewell site of Gopalnagar Uttar (Zone-I) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15524) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/003646/2024-2025 | 3155/AD | 29/07/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 0
3826 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000086/2023-2024 | 532/AD | 12/05/2023 | 0 | Resource Division | 11.73 | 0 | 0
3827 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000523/2023-2024 | 4935/AD | 22/12/2023 | 0 | Resource Division | 25.44 | 0 | 0
3828 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000764/2023-2024 | 598/AD | 29/01/2024 | 0 | Resource Division | 6.31 | 0 | 0
3829 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000944/2023-2024 | 1678/AD | 22/03/2024 | 0 | Resource Division | 31.52 | 0 | 0
3830 | Alipore Division | Raidighi Sub-Division | Payment against "Restoration of Purba Bishnupur Raidighi Road (MDR) 11Km-15.5Km), under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Raidighi Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 264(W)/618G, Dt. 19.02.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | BILL/01576/2024-2025 | BP-2024-25-889 | 19/11/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 71.65 | 0 | 0
3831 | Alipore Division | Raidighi Sub-Division | Remodeling of Distribution System of Krishnachandrapur PWS Scheme as Zone-III of Mathurapur - I Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000034/2022-2023 | 597/AD | 28/04/2022 | 30 | M/S B.M. CONSTRUCTION | 95.84 | 0 | 50
3832 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-III, VI, XVII, IV,VII, VIII, IX, X), Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000110/2025-2026 | 2576/AD | 03/06/2025 | 60 | M/S B. ENTERPRISE | 43.57 | 0 | 0
3833 | Alipore Division | Raidighi Sub-Division | Laying distribution system and other allied works of piped water supply at Zone - III of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000115/2023-2024 | 484/AD | 10/05/2023 | 45 | M/S B.M. CONSTRUCTION | 95.36 | 0 | 40
3834 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Zone-III, Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 255 Nos.) [Part - D] | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000118/2023-2024 | 487/AD | 10/05/2023 | 315 | TIYASHA ENTERPRISE | 70.74 | 0 | 98
3835 | Alipore Division | Raidighi Sub-Division | Construction of 550 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- III of Mathurapur -I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000343/2023-2024 | 1455/AD | 13/07/2023 | 300 | M/S SUMAN SHIL | 205.1 | 0 | 0
3836 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- III of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000879/2024-2025 | 4662/AD | 20/11/2024 | 45 | M/S B.M. CONSTRUCTION | 25.39 | 0 | 0
3837 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - III of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001964/2022-2023 | 12718/AD | 14/03/2023 | 30 | M/S B.M. CONSTRUCTION | 30.56 | 0 | 50
3838 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000006/2024-2025 | 5161/AD | 12/12/2024 | 0 | Resource Division | 30.8 | 0 | 0
3839 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000634/2023-2024 | 238/AD | 15/01/2024 | 0 | Resource Division | 7.85 | 0 | 0
3840 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using UPVC pipe (CD) and UPVC Deep well screen (RDS) pipe with ribs pipe at Tube Well No. - 3 of Augmentation of Singheswar W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001815/2022-2023 | 12155/AD | 01/03/2023 | 45 | SNEHA CONSTRUCTION | 19.9 | 0 | 0
3841 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Singheswar W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 3) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001816/2022-2023 | 12156/AD | 01/03/2023 | 45 | GHOSH CONSTRUCTION | 7.09 | 0 | 96
3842 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (410 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Singheswar Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002312/2023-2024 | 1065/AD | 21/02/2024 | 282 | RAKTIM ENTERPRISE | 35.55 | 0 | 93
3843 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000020/2023-2024 | 226/AD | 24/04/2023 | 0 | Resource Division | 23.13 | 0 | 0
3844 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VI at Diamond Harbour- II block for House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002389/2024-2025 | 636/AD | 18/02/2025 | 30 | K.P. CONSTRUCTION | 12.8 | 0 | 0
3845 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000884/2023-2024 | 758/AD | 03/02/2024 | 0 | Resource Division | 4.74 | 0 | 0
3846 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000924/2023-2024 | 1266/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
3847 | Alipore Division | Sub-Division - II under South 24pgs W/s Division - I | Road restoration of Kesili to Ghola more Under Magrahat I | AE SWSD-II | JE4 | BILL/01704/2024-2025 | BP-2024-25-789 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 2.37 | 0 | 0
3848 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for retrofitting of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000815/2022-2023 | 6810/AD | 16/11/2022 | 30 | HARIDAS DUTTA | 19.49 | 0 | 95
3849 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site for Retrofitting of Kanthalberia W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000818/2022-2023 | 6813/AD | 16/11/2022 | 30 | M/S BHUNIA ENTERPRISE | 7.18 | 0 | 0
3850 | Alipore Division | Canning Sub-division | Survey work for Augmentation of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-I | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001840/2021-2022 | 679CSD | 18/08/2021 | 15 | HORIZEN | 1.99 | 0 | 100
3851 | Alipore Division | Canning Sub-division | Design and DPR preparation for Augmentation of ground water based Kanthalberia Water Supply Scheme to accommodate FHTC in Basanti Block of South 24 Parganas District under Alipore Division, PHE Dte. Part-II | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001841/2021-2022 | 680/CSD | 18/08/2021 | 15 | HORIZEN | 3.19 | 0 | 100
3852 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000037/2021-2022 | 7033/AD | 31/03/2022 | 0 | Resource Division | 194.4 | 0 | 0
3853 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000391/2023-2024 | 332/AD | 19/01/2024 | 0 | Resource Division | 13.21 | 0 | 0
3854 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1000 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-I at Paschim Gobindapur of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8053]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000017/2023-2024 | 58/AD | 10/04/2023 | 900 | K.P. CONSTRUCTION | 866.96 | 0 | 84
3855 | Alipore Division | Diamond Harbour Sub-Division | Construction of Platform of size 600mm x 600mm (inner dimension) for the FHTC along with road restoration at Zone-I & Zone-III of Diamond Harbour-II Block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part-III A / B) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000042/2023-2024 | 177/AD | 19/04/2023 | 90 | PRONICON INDIA | 164.18 | 0 | 50
3856 | Alipore Division | Diamond Harbour Sub-Division | Preparation of re-design, drawing for fundation considering pile cap for group piles for the proposed R.C.C. Over Head Reservoir at (Zone-I, OHR Size-1000 Cum., Mouza - Paschim Gobindapur) and (Zone-VII, OHR Size-600 Cum., Mouza - Kamarpole) of Diamond Harbour-II Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000366/2022-2023 | 199/DHSD | 27/07/2022 | 7 | ASTER CONSULTANCY | 1 | 0 | 100
3857 | Alipore Division | Diamond Harbour Sub-Division | Restoration by concreting of village road due to laying of pipeline within Zone-I under Diamond Harbour-II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001180/2022-2023 | 11617/AD | 17/02/2023 | 570 | K.P. CONSTRUCTION | 87.56 | 0 | 90
3858 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000138/2022-2023 | 19/AD | 05/04/2023 | 0 | Resource Division | 96.26 | 0 | 0
3859 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000218/2023-2024 | 2102/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
3860 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000357/2023-2024 | 3221/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
3861 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000613/2023-2024 | 275/AD | 15/01/2024 | 0 | Resource Division | 49.28 | 0 | 0
3862 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000879/2023-2024 | 753/AD | 03/02/2024 | 0 | Resource Division | 0.33 | 0 | 0
3863 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Kalugachi W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. V) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000286/2024-2025 | 2657/AD | 21/06/2024 | 45 | RABIUL GAZI | 7.07 | 0 | 0
3864 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Kalugachi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000334/2023-2024 | 1551/AD | 17/07/2023 | 805 | M/S. MIHIR KUMAR NASKAR | 122.86 | 0 | 0
3865 | Alipore Division | Canning Sub-division | Additional work inter connection & distribution at Kalugachi W/S Scheme, Block- Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000350/2024-2025 | 722/CSD | 27/06/2024 | 30 | P.S. CONSTRUCTION | 2.26 | 0 | 0
3866 | Alipore Division | Canning Sub-division | Additional work for laying distribution in connection with FHTC work at AUGMENTATION AND RETROFITTING OF KALUGACHHI W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (SM/15478) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001016/2023-2024 | 3301/AD | 07/10/2023 | 30 | STAR ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 10.97 | 0 | 90
3867 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Kaluagachi W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001683/2022-2023 | 11490/AD | 15/02/2023 | 45 | R CONSTRUCTION | 7.11 | 0 | 0
3868 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 for each zone of Augmentation of Kalugachi W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001770/2022-2023 | 12043/AD | 27/02/2023 | 30 | ZINARUL ISLAM | 19.59 | 0 | 0
3869 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000005/2023-2024 | 116/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
3870 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000136/2023-2024 | 850/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
3871 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000262/2023-2024 | 3052/AD | 28/09/2023 | 0 | Resource Division | 85.12 | 0 | 0
3872 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-I of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000014/2022-2023 | 211/AD | 11/04/2022 | 1335 | NITYANANDA MONDAL | 173.32 | 0 | 97
3873 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system, making structure for canal crossing and other allied works at Zone- I of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000063/2023-2024 | 343/AD | 28/04/2023 | 90 | SPA ENTERPRISE | 137.27 | 0 | 50
3874 | Alipore Division | Raidighi Sub-Division | Construction of 500 cum. Capacity 20mtr. staging height RCC Over Head Reservoir at as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Mathurapur-II block (zone-I) for Mega surface water based water supply Scheme in 24 pgs (south) under Raidighi Sub Division of AD PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002155/2019-2020 | 7935/AD | 11/03/2020 | 2191 | MANGES INDUSTRIAL CORPORATION | 116.83 | 0 | 80
3875 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000653/2023-2024 | 257/AD | 15/01/2024 | 0 | Resource Division | 5.3 | 0 | 0
3876 | Alipore Division | Canning Sub-division | Interconnection & rising main with supply of specials from Head work site to PH-IV & Head work site to PH-V of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000321/2023-2024 | 1547/AD | 17/07/2023 | 709 | SANKAR MONDAL | 132.1 | 0 | 100
3877 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations at Mouza-Baluijhaka and Bhaleya of Bhaleya Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001065/2021-2022 | 5300/AD | 04/01/2022 | 60 | M/S CHANDIMATA CONSTRUCTION | 33.22 | 0 | 98
3878 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001707/2022-2023 | 11671/AD | 20/02/2023 | 45 | BARUN KANTI PAUL | 7.09 | 0 | 0
3879 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bhaleya W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001708/2022-2023 | 11672/AD | 20/02/2023 | 45 | R.G. ENTERPRISE (I) | 7.07 | 0 | 0
3880 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Bhaleya W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001813/2022-2023 | 12153/AD | 01/03/2023 | 45 | M.R.ENTERPRISE (II) | 39.03 | 0 | 0
3881 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Bhaleya Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001944/2022-2023 | 11504/AD | 15/02/2023 | 45 | M/S. M.K. NASKAR & CONSTRUCTION | 2.6 | 0 | 95
3882 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitation (Mondal Para) at Bhaleya Mouza of Bhaleya W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002314/2020-2021 | 1520/CSD | 10/02/2021 | 30 | ADITYA SARDAR | 4.83 | 0 | 83
3883 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000249/2023-2024 | 3039/AD | 28/09/2023 | 0 | Resource Division | 81.05 | 0 | 0
3884 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000727/2023-2024 | 549/AD | 25/01/2024 | 0 | Resource Division | 111.53 | 0 | 0
3885 | Alipore Division | Raidighi Sub-Division | Providing FHTC and other allied works at Zone- V of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000065/2023-2024 | 195/AD | 19/04/2023 | 90 | G.B. CONSTRUCTION & CO. | 196.43 | 0 | 62
3886 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 3) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Raidighi W/S Scheme (Zone-V, Mathurapur-II Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000430/2023-2024 | 1918/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 99
3887 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-V of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001249/2021-2022 | 5822/AD | 07/02/2022 | 60 | G.B. CONSTRUCTION & CO. | 252.1 | 0 | 80
3888 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000649/2023-2024 | 252/AD | 15/01/2024 | 0 | Resource Division | 9.17 | 0 | 0
3889 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sadhupur (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000097/2023-2024 | 453/AD | 08/05/2023 | 15 | UNIVERSAL CONSTRUCTION | 19.52 | 0 | 0
3890 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based Piped Water Supply Scheme for Augmentation of Sadhupur (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000123/2025-2026 | 2586/AD | 03/06/2025 | 30 | KHAN CONSTRUCTION (BASANTI) | 10.27 | 0 | 0
3891 | Alipore Division | Canning Sub-division | Construction of 500 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height, Laying Distribution System, Providing Functional Household Tap Connection etc. for augmentation of Sadhupur (Zone-I) piped water supply scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. [No. of FHTC = 2159] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001195/2023-2024 | 4045/AD | 22/11/2023 | 300 | SUPRITI ENTERPRISE | 648.45 | 0 | 30
3892 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sadhupur (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001931/2022-2023 | 11804/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 6.53 | 0 | 95
3893 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001956/2022-2023 | 12692/AD | 14/03/2023 | 659 | BAPAN HALDAR | 8.88 | 0 | 100
3894 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sadhupur W/S Scheme (Zone - I), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002033/2022-2023 | 13029/AD | 24/03/2023 | 60 | GIASHUDDIN CONSTRUCTION | 65.85 | 0 | 100
3895 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002039/2022-2023 | 13035/AD | 24/03/2023 | 680 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 100
3896 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sadhupur W/S Scheme (Zone-I), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002040/2022-2023 | 13036/AD | 24/03/2023 | 680 | MAA SOLAR ENTERPRISE | 8.61 | 0 | 100
3897 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000059/2023-2024 | 379/AD | 02/05/2023 | 0 | Resource Division | 67.54 | 0 | 0
3898 | Alipore Division | Baruipur Sub-Division | Road restoration for L048-Jauhia lo Patpukur. | AE BSD |  | BILL/01732/2024-2025 | BP-2024-25-796 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 3.48 | 0 | 0
3899 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Satjelia (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000101/2023-2024 | 504/AD | 11/05/2023 | 782 | M/S. BISWAS CONSTRUCTION(I) | 23.87 | 0 | 80
3900 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Satjelia W/S Scheme (Zone - III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000140/2023-2024 | 276/AD | 24/04/2023 | 75 | GOLDEN ENTERPRISE | 43.97 | 0 | 100
3901 | Alipore Division | Canning Sub-division | Construction of 200 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation Piped W/S Scheme for Satjelia (Zone-III) Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1271] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000261/2023-2024 | 1449/AD | 13/07/2023 | 689 | SUBHO CONSTRUCTION | 389.99 | 0 | 71
3902 | Alipore Division | Canning Sub-division | Laying additional pipeline and other allied works at Augmentation of Satjelia (Zone - III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000310/2024-2025 | 2691/AD | 24/06/2024 | 434 | R.S.CONSTRUCTION CO. | 65.49 | 0 | 40
3903 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Satjelia (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001850/2022-2023 | 11816/AD | 23/02/2023 | 45 | TECH VISION | 4.2 | 0 | 0
3904 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001980/2022-2023 | 12641/AD | 13/03/2023 | 45 | R.G. ENTERPRISE (I) | 8.9 | 0 | 0
3905 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Satjelia W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002010/2022-2023 | 12916/AD | 21/03/2023 | 499 | MISTRY CONSTRUCTION | 8.61 | 0 | 100
3906 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000053/2023-2024 | 260/AD | 24/04/2023 | 0 | Resource Division | 50.2 | 0 | 0
3907 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000415/2023-2024 | 371/AD | 19/01/2024 | 0 | Resource Division | 7.83 | 0 | 0
3908 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of Basanti (Zone-IX) piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000053/2023-2024 | 144/AD | 13/04/2023 | 300 | RIVER BENZ CONSTRUCTION | 141.92 | 0 | 0
3909 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) of Augmentation of Basanti W/S Scheme (Zone-IX), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1593] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000056/2023-2024 | 148/AD | 17/04/2023 | 670 | M.T.C. CONSTRUCTION | 91.45 | 0 | 30
3910 | Alipore Division | Canning Sub-division | Laying distribution system for Augmentation of Basanti W/S Scheme (Zone-IX), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018392] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000167/2023-2024 | 978/AD | 08/06/2023 | 600 | RIVER BENZ CONSTRUCTION | 146.19 | 0 | 100
3911 | Alipore Division | Canning Sub-division | Construction of Toilet including Sanitary arrangement at the site for Augmentation of Basanti (Zone - IX) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House - 3 (Old)] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000457/2025-2026 | 816/CSD | 17/06/2025 | 30 | M/S NABIBAR BUILDERS | 1.91 | 0 | 0
3912 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000499/2023-2024 | 1799/AD | 26/07/2023 | 45 | PAL ENTERPRISE | 7.35 | 0 | 0
3913 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000500/2023-2024 | 1800/AD | 26/07/2023 | 45 | STRINGS ENGINEERING PVT. LTD. | 7.1 | 0 | 0
3914 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-IX) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000501/2023-2024 | 1801/AD | 26/07/2023 | 45 | SAMIR GIRI | 7.09 | 0 | 100
3915 | Alipore Division | Canning Sub-division | Construction of Toilet including Sanitary arrangement at the site for Augmentation of Basanti (Zone - IX) W/S Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House - 1 (Old)] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000727/2025-2026 | 815/CSD | 17/06/2025 | 30 | ASIK CONSTRUCTION | 1.91 | 0 | 0
3916 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-IX) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000729/2023-2024 | 2890/AD | 19/09/2023 | 15 | SURYA ENTERPRISE | 10.48 | 0 | 90
3917 | Alipore Division | Canning Sub-division | Laying additional pipe line with other allied works at Basanti (Zone-IX) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000829/2024-2025 | 4535/AD | 13/11/2024 | 60 | S.S. CONSTRUCTION | 38.57 | 0 | 0
3918 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. 3 for Augmentation of Basanti (Zone-IX) Piped Water Supply Scheme, Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001226/2024-2025 | 5225/AD | 16/12/2024 | 376 | NEW DAWN POWER & CONSTRUCTION | 13.34 | 0 | 80
3919 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001871/2022-2023 | 12463/AD | 10/03/2023 | 517 | SOMA ENTERPRISE | 58.76 | 0 | 100
3920 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-IX) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001939/2022-2023 | 11810/AD | 22/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 5.49 | 0 | 0
3921 | Alipore Division | Canning Sub-division | Laying of additional pipe line for Augmentation of Basanti W/S Scheme (Zone-IX), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002181/2023-2024 | 832/AD | 05/02/2024 | 30 | NAZRUL ENTERPRISE | 8.2 | 0 | 100
3922 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000029/2023-2024 | 234/AD | 24/04/2023 | 0 | Resource Division | 74.55 | 0 | 0
3923 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000158/2023-2024 | 1055/AD | 15/06/2023 | 0 | Resource Division | 9.81 | 0 | 0
3924 | Alipore Division |  | Bill for way leave/ track crossing proposal with application ID : ER-SHAH-2023-WL-79 in IR/RBCS |  |  | BILL/00436/2024-2025 | BP-2024-25-163 | 04/06/2024 | 0 | EASTERN RAILWAY (SEALDAH DIVISION) | 5.77 | 0 | 0
3925 | Alipore Division |  | DISMANTLING AND RESTORATION OF CONCRETE VILLAGE ROAD FOR LDS WORK AT ZONE-I OF MATHURAPUR-I BLOCK FOR MEGA SURFACE WATER BASED WATER SUPPLY SCHEME FOR FALTA MATHURAPUR UNDER RAIDIGHI SUB DIVISION OF ALIPORE DIVISION, PHE Dte. |  |  | BILL/00985/2024-2025 | BP-2024-25-472 | 17/08/2024 | 0 | M/S RAJU CONSTRUCTION | 1.47 | 0 | 0
3926 | Alipore Division |  | Laying distribution system of piped water supply and allied works at Zone- XII of Mathurapur -II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000116/2023-2024 | 485/AD | 10/05/2023 | 30 | KAMALA ENTERPRISE (I) | 8.57 | 0 | 80
3927 | Alipore Division |  | Extension of pipeline to provide Functional Household Tap Connection (FHTC) and construction of sluice valve chamber at Nandakumarpur Zone - III (Zone-XII of Mathurapur - II Block) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. |  |  | ORD/000220/2022-2023 | 3061/AD | 13/07/2022 | 30 | UNITED BUILDERS | 13.1 | 0 | 100
3928 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 365 | UNITED BUILDERS | 108.61 | 0 | 100
3929 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 5553/AD | 29/09/2022 | 0 | Resource Division | 4.08 | 0 | 0
3930 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 6th tubewell Site for Achintyanagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08632) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000234/2024-2025 | 2609/AD | 19/06/2024 | 266 | M/S A.M. ENTERPRISE | 5.62 | 0 | 100
3931 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 6th Tubewell Site for Achintyanagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/08632) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000235/2024-2025 | 2610/AD | 19/06/2024 | 266 | M/S A.M. ENTERPRISE | 9.72 | 0 | 100
3932 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Achintyanagar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000999/2023-2024 | 506/KSD | 03/10/2023 | 7 | M/S B. ENTERPRISE | 3.74 | 0 | 100
3933 | Alipore Division | Kakdwip Sub-Division | : Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 5th Tubewell Site for Achintyanagar W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/08632) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/001331/2024-2025 | 5415/AD | 24/12/2024 | 189 | AVIJIT ENTERPRISE (64) | 7.93 | 0 | 100
3934 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Purba Surendranagar, Dakshin Kashinagar, Herambagopalpur, Achintyanagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/002105/2023-2024 | 927/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.63 | 0 | 100
3935 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000381/2023-2024 | 3567/AD | 18/10/2023 | 0 | Resource Division | 44.3 | 0 | 0
3936 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000779/2023-2024 | 613/AD | 29/01/2024 | 0 | Resource Division | 8.33 | 0 | 0
3937 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Madhusudanpur Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1927] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000143/2023-2024 | 756/AD | 23/05/2023 | 601 | PAUL CONSTRUCTION | 389.27 | 0 | 30
3938 | Alipore Division | Kakdwip Sub-Division | Construction of Platform and other allied works of pipe line protection at Madhusudanpur W/S Scheme for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000199/2024-2025 | 2582/AD | 19/06/2024 | 45 | PAUL CONSTRUCTION | 39.88 | 0 | 20
3939 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000424/2023-2024 | 1912/AD | 01/08/2023 | 45 | G.B. CONSTRUCTION (TW) | 38.38 | 0 | 90
3940 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Madhusudanpur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000948/2023-2024 | 2980/AD | 26/09/2023 | 45 | SARADA CONSTRUCTION | 27.73 | 0 | 0
3941 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Madhusudanpur W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000949/2023-2024 | 2981/AD | 26/09/2023 | 30 | M/S NAIYA & MAITY | 9.6 | 0 | 0
3942 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Bhubannagar, Gobindarampur, Laxmipur, Madhusudanpur, Ramtanunagar, Shibkalinagar PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002142/2023-2024 | 942/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
3943 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme Madhusudanpur PWSS including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002162/2022-2023 | 8335/AD | 12/12/2022 | 45 | LEMNISCATE | 4.16 | 0 | 100
3944 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 350 cum. capacity OHR of Madhusudanpur PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002216/2023-2024 | 873/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
3945 | Alipore Division | Kakdwip Sub-Division | Inter connection between two nos. Tubewell for Madhusudanpur W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18126) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002548/2024-2025 | 817/AD | 27/02/2025 | 45 | PAUL CONSTRUCTION | 13.31 | 0 | 0
3946 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000445/2023-2024 | 4712/AD | 18/12/2023 | 0 | Resource Division | 19.93 | 0 | 0
3947 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000587/2023-2024 | 86/AD | 03/01/2024 | 0 | Resource Division | 11.45 | 0 | 0
3948 | Alipore Division | Canning Sub-division | Construction of 200 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Harishpur (Zone-II) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1474] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000259/2023-2024 | 1447/AD | 13/07/2023 | 300 | SAMSUL ENTERPRISE | 489.25 | 0 | 60
3949 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Augmentation of Harishpur (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000733/2024-2025 | 4391/AD | 05/11/2024 | 45 | SAMSUL ENTERPRISE | 45.41 | 0 | 0
3950 | Alipore Division | Canning Sub-division | Laying of additional pipe line and other allied works at Harishpur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001227/2024-2025 | 5230/AD | 16/12/2024 | 271 | P.S. CONSTRUCTION | 84.35 | 0 | 0
3951 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Harishpur (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002018/2022-2023 | 12924/AD | 21/03/2023 | 986 | MOUMITA ENTERPRISE | 42.77 | 0 | 40
3952 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Harishpur (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/002112/2022-2023 | 12878/AD | 17/03/2023 | 45 | TECH VISION | 5.24 | 0 | 95
3953 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000058/2023-2024 | 265/AD | 24/04/2023 | 0 | Resource Division | 46.64 | 0 | 0
3954 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000420/2023-2024 | 375/AD | 19/01/2024 | 0 | Resource Division | 9.08 | 0 | 0
3955 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone - l) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000094/2025-2026 | 2523/AD | 30/05/2025 | 45 | SURYA ENTERPRISE | 19.5 | 0 | 0
3956 | Alipore Division | Canning Sub-division | Construction of OHR (350 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the PATHANKHALI (ZONE-I), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000485/2023-2024 | 1998/AD | 04/08/2023 | 300 | M/S SHIBAM ENTERPRISE | 711.48 | 0 | 25
3957 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-I) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000491/2023-2024 | 1931/AD | 01/08/2023 | 45 | NATURAL RESOURCES CONSORTIUM | 51.2 | 0 | 0
3958 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000607/2023-2024 | 1829/AD | 27/07/2023 | 45 | TECH VISION | 7.45 | 0 | 99
3959 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House no.1 for Augmentation of Pathakhali (Zone-I) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000730/2024-2025 | 4388/AD | 05/11/2024 | 30 | KANAN CONSTRUCTION | 28.81 | 0 | 0
3960 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep (Replacement) Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Augmentation of Pathankhali (Zone - I) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - 4) (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000743/2024-2025 | 4417/AD | 05/11/2024 | 30 | MOSTAFIZUR HAQUE GAINE | 22.43 | 0 | 25
3961 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Ground Water Based at Bipradaspur Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002495/2024-2025 | 788/AD | 25/02/2025 | 30 | REZU CONSTRUCTION | 12.42 | 0 | 0
3962 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000049/2023-2024 | 256/AD | 24/04/2023 | 0 | Resource Division | 124.68 | 0 | 0
3963 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000410/2023-2024 | 364/AD | 19/01/2024 | 0 | Resource Division | 14.32 | 0 | 0
3964 | Alipore Division | Canning Sub-division | Laying damaged pipe line due to widening of road by South 24 Parganas Zilla Parishad from Piali Railway Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000280/2022-2023 | 273/CSD | 19/05/2022 | 30 | ASHIS ENTERPRISE | 4.18 | 0 | 100
3965 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000683/2024-2025 | 4288/AD | 29/10/2024 | 180 | SAHANA ENTERPRISE | 4.83 | 0 | 0
3966 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000684/2024-2025 | 4289/AD | 29/10/2024 | 30 | ASHIS ENTERPRISE | 10.8 | 0 | 0
3967 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 3 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000685/2024-2025 | 4290/AD | 29/10/2024 | 30 | SAHANA ENTERPRISE | 8.33 | 0 | 68
3968 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Piped Water Supply Scheme of Kalaria (Zone - IIB) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000686/2024-2025 | 4291/AD | 29/10/2024 | 30 | HARIDAS DUTTA | 8.59 | 0 | 0
3969 | Alipore Division | Canning Sub-division | Land development work at Over Head Reservoir site (balance portion) of Kalaria W/S Scheme (Zone-I), under Canning-I Block, south 24 parganas District of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000867/2022-2023 | 844/CSD | 16/08/2022 | 25 | ASHIS ENTERPRISE | 3.54 | 0 | 100
3970 | Alipore Division | Canning Sub-division | Supply and delivery of DI fittings and construction of Sluice Valve Chamber for the proposed DI line from Piali Railway Station to Nawbhasan More at Kalaria W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000999/2022-2023 | 849/CSD | 18/08/2022 | 30 | ASHIS ENTERPRISE | 4.76 | 0 | 100
3971 | Alipore Division | Canning Sub-division | Land development work at Over Head Reservoir site of Kalaria W/S Scheme (Zone-I), under Canning-I Block, south 24 parganas Distric of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/001643/2021-2022 | 1511/CSD | 15/02/2022 | 15 | ASHIS ENTERPRISE | 1.98 | 0 | 100
3972 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000002/2024-2025 | 4550/AD | 13/11/2024 | 0 | Resource Division | 61.6 | 0 | 0
3973 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000003/2024-2025 | 5158/AD | 12/12/2024 | 0 | Resource Division | 123.2 | 0 | 0
3974 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer, Canning sub division |  | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
3975 | Alipore Division | Canning Sub-division | Construction of OHR (500 cum.), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Augmentation Piped Water Supply Scheme for the Bhangankhali,Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division |  | ORD/000352/2023-2024 | 1661/AD | 20/07/2023 | 300 | SPA ENTERPRISE | 636.93 | 0 | 5
3976 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Bhangankhali W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division |  | ORD/000493/2023-2024 | 1793/AD | 26/07/2023 | 60 | M/S KRISHNA MONDAL | 88.05 | 0 | 0
3977 | Alipore Division | Canning Sub-division | Renovation of Pump House No. 3 and its boundary wall of Bhangankhali W/S Scheme, under Basanti Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division |  | ORD/002514/2023-2024 | 1605/CSD | 28/02/2024 | 30 | DIPA CHHETRI | 2.03 | 0 | 95
3978 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division |  | RTOR000034/2023-2024 | 239/AD | 24/04/2023 | 0 | Resource Division | 142.93 | 0 | 0
3979 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-I, II, III, IV, V), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000043/2025-2026 | 2071/AD | 30/04/2025 | 60 | M/S B. ENTERPRISE | 27.24 | 0 | 0
3980 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 1250 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone - IV, Mathurapur - II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000276/2024-2025 | 593/RSD | 10/06/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 90
3981 | Alipore Division | Raidighi Sub-Division | Laying of additional D.I. (K7) pipes in connection with revised design of laying distribution alongwith supply, delivery and fitting & fixing at site of different dia specials at Zone - IV (Gilarchat PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000326/2024-2025 | 2729/AD | 25/06/2024 | 360 | NITYANANDA MONDAL | 149.16 | 0 | 10
3982 | Alipore Division | Raidighi Sub-Division | Contruction of 1250 cum capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system and other allied works at Zone- IV of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000482/2023-2024 | 1995/AD | 04/08/2023 | 300 | SPA ENTERPRISE | 818.91 | 0 | 0
3983 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 1250 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone IV, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Maga surface water based W/S Scheme for Falta - Mathurapur Dist. South 24 Parganas under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000491/2024-2025 | 629/RSD | 11/07/2024 | 15 | SPA ENTERPRISE | 0.48 | 0 | 100
3984 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-IV of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09401 & SM/18380) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000790/2024-2025 | 4489/AD | 11/11/2024 | 120 | NITYANANDA MONDAL | 115.08 | 0 | 0
3985 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone- IV of Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001041/2024-2025 | 4959/AD | 04/12/2024 | 60 | S.M. ENTERPRISE | 40.33 | 0 | 0
3986 | Alipore Division | Raidighi Sub-Division | Construction of boundary wall at Zone - IV, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (SM/09401 and SM/18380) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001303/2024-2025 | 5377/AD | 23/12/2024 | 30 | BAPAN HALDAR | 6.52 | 0 | 0
3987 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000663/2023-2024 | 267/AD | 15/01/2024 | 0 | Resource Division | 11.41 | 0 | 0
3988 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000845/2023-2024 | 706/AD | 31/01/2024 | 0 | Resource Division | 264.14 | 0 | 0
3989 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Pump House No. 1) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Purba Ranaghat W/S Scheme (Zone-IV, Mathurapur-I Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000429/2023-2024 | 1917/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 95
3990 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-IV, Mathurapur-I in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000557/2023-2024 | 2239/AD | 11/08/2023 | 45 | ISHAN CONSTRUCTION | 59.38 | 0 | 70
3991 | Alipore Division | Raidighi Sub-Division | Repairing of pump house - 2, including plinth protection and boundary wall at Purba Ranaghata W/S Scheme, modified as Zone- IV of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/001180/2023-2024 | 359/RSD | 21/11/2023 | 60 | MAA TARA ENTERPRISE | 2.96 | 0 | 100
3992 | Alipore Division | Raidighi Sub-Division | Providing 100% Functional Household Tap Connection (FHTC) including Parallel pipeline and other allied works of piped water supply at Zone - IV of Mathurapur-I Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002183/2023-2024 | 834/AD | 05/02/2024 | 60 | M/S. L.P. CONSTRUCTION | 53.03 | 0 | 99
3993 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000640/2023-2024 | 244/AD | 15/01/2024 | 0 | Resource Division | 4.88 | 0 | 0
3994 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Shibpur (Part-B) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000058/2023-2024 | 41/KSD | 27/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
3995 | Alipore Division | Kakdwip Sub-Division | Construction of Platform, rising main and Road Restoration for Augmentation of Shibpur (Phase-B) W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-II) (SM/11875) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000461/2024-2025 | 3420/AD | 21/08/2024 | 226 | BIMALENDU GIRI | 58.17 | 0 | 30
3996 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SHIBPUR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000484/2022-2023 | 1748/AD | 15/06/2022 | 45 | M/S R.DUTTA & CO. | 4.54 | 0 | 100
3997 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Sibpur W/S Scheme, South 24 Parganas, Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000589/2023-2024 | 2346/AD | 18/08/2023 | 502 | R.P. ENTERPRISE | 45.18 | 0 | 100
3998 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Shibpur W/S Scheme, Block - Namkhana, for implementing of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11875) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000605/2024-2025 | 4092/AD | 03/10/2024 | 30 | MEHAI TECHNOLOGY LIMITED | 20.27 | 0 | 100
3999 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.06.2024 to 31.08.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000667/2024-2025 | 982/KSD | 27/05/2024 | 92 | SARADA CONSTRUCTION | 1.2 | 0 | 0
4000 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.09.2024 to 30.11.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000668/2024-2025 | 1255/KSD | 28/08/2024 | 91 | SARADA CONSTRUCTION | 1.2 | 0 | 0
4001 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Sibpur (Phase-B) Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 250] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001785/2022-2023 | 11557/AD | 17/02/2023 | 300 | R.P. ENTERPRISE | 176.39 | 0 | 0
4002 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS of Shibpur W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001994/2023-2024 | 467/KSD | 22/09/2023 | 30 | INDRANIL DUTTA & ASSOCIATES | 3.81 | 0 | 100
4003 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Debnibus, Shibpur, Budhakhali Zone-II (Part- I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2023-2024 | 938/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.63 | 0 | 100
4004 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site for Augmentation of Sibpur W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002279/2023-2024 | 969/AD | 12/02/2024 | 30 | M/S ASHA ENGINEERING | 9.66 | 0 | 0
4005 | Alipore Division | Kakdwip Sub-Division | Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2022 to 30.11.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002423/2022-2023 | 562/KSD | 02/12/2022 | 363 | SARADA CONSTRUCTION | 4.8 | 0 | 0
4006 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2024 to 28.02.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002923/2024-2025 | 1654/KSD | 26/11/2024 | 90 | SARADA CONSTRUCTION | 1.2 | 0 | 0
4007 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2025 to 31.05.2025 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/003006/2024-2025 | 350/KSD | 27/02/2025 | 92 | SARADA CONSTRUCTION | 1.2 | 0 | 0
4008 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.12.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/003031/2023-2024 | 713/KSD | 30/11/2023 | 91 | SARADA CONSTRUCTION | 1.2 | 0 | 0
4009 | Alipore Division | Kakdwip Sub-Division | Continuation order for Hiring of 1 (one) No. Diesel Car / Luxury Taxi for supervision of different works under JJM at Kakdwip and Namkhana Block under Kakdwip Sub Division of Alipore Division, PHE Dte. period from 01.03.2024 to 31.05.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/003032/2023-2024 | 410/KSD | 27/02/2024 | 92 | SARADA CONSTRUCTION | 1.2 | 0 | 0
4010 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000284/2023-2024 | 3081/AD | 28/09/2023 | 0 | Resource Division | 0.6 | 0 | 0
4011 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000798/2023-2024 | 643/AD | 30/01/2024 | 0 | Resource Division | 3.38 | 0 | 0
4012 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000986/2023-2024 | 1779/AD | 27/03/2024 | 0 | Resource Division | 37.58 | 0 | 0
4013 | Alipore Division | Kakdwip Sub-Division | Construction of 400 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Kamalpur Rudranagar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/000369/2022-2023 | 4120/AD | 18/08/2022 | 300 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 564.7 | 0 | 86
4014 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households along with construction of 01 no. Pump House including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Khas Ramkarchar Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 100] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001165/2023-2024 | 3744/AD | 03/11/2023 | 90 | DEBARATI ENTERPRISE | 213.65 | 0 | 100
4015 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation (KHAS RAMKARCHAR (Phase - B)) water supply scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001360/2023-2024 | 3257/AD | 05/10/2023 | 45 | VOYAGER | 5.58 | 0 | 100
4016 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Augmentation of Khas Ramkarchar (Zone- I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (Part-A) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001838/2023-2024 | 126/AD | 05/01/2024 | 45 | M/S. GIRI ENTERPRISE | 23.17 | 0 | 60
4017 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC to all households for Augmentation of Khas Ramkarchar (Zone- I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/001839/2023-2024 | 127/AD | 05/01/2024 | 45 | M/S. TRIPATHI & CO. | 21.4 | 0 | 60
4018 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Krishnanagar, Khansaheber Abad, Naraharipur, Khas Ramkarchar PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | ORD/002171/2023-2024 | 953/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.81 | 0 | 100
4019 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000516/2023-2024 | 4834/AD | 20/12/2023 | 0 | Resource Division | 41.76 | 0 | 0
4020 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000528/2023-2024 | 15/AD | 02/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
4021 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Kakdwip Sub Division | RTOR000692/2023-2024 | 462/AD | 24/01/2024 | 0 | Resource Division | 9.25 | 0 | 0
4022 | Alipore Division | Canning Sub-division | Laying distribution system of Nagartala W/S Scheme (Zone-II) Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000010/2022-2023 | 65/AD | 06/04/2022 | 120 | DIVINE | 245.35 | 0 | 100
4023 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 4 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000304/2025-2026 | 2957/AD | 25/06/2025 | 30 | M/S KHAJABABA ENTERPRISE | 10.73 | 0 | 0
4024 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 4 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-I) (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000305/2025-2026 | 2958/AD | 25/06/2025 | 30 | SUNIL ENTERPRISE | 8.93 | 0 | 0
4025 | Alipore Division | Canning Sub-division | Inter connection & rising main with supply of specials from Head work site to PH - 3, 4 & 5 of Nagartala (Zone I & II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. [Nagartala - Z-II] (SM/09935) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000694/2024-2025 | 4295/AD | 29/10/2024 | 180 | RAKHI CONSTRUCTION | 61.46 | 0 | 98
4026 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no. 3 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001054/2024-2025 | 4995/AD | 05/12/2024 | 120 | KUNDU CONSTRUCTION CO. | 11.11 | 0 | 98
4027 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well no 5 Site for Augmentation of Nagartala (Zone-I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (at Zone-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001056/2024-2025 | 4996/AD | 05/12/2024 | 30 | MAA SOLAR ENTERPRISE | 10.73 | 0 | 0
4028 | Alipore Division | Canning Sub-division | Laying of DI Pipeline form OHR to Distribution line of Augmentation Nagartala (Zone- I & II) W/S Scheme, Block-Canning - II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001267/2023-2024 | 1212/CSD | 17/11/2023 | 30 | SUKANTA HALDER | 2.44 | 0 | 98
4029 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001670/2021-2022 | 635/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.78 | 0 | 100
4030 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-I) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001671/2021-2022 | 636/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.28 | 0 | 100
4031 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-I) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001672/2021-2022 | 637/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 3.43 | 0 | 100
4032 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-A] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001673/2021-2022 | 638/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 4.64 | 0 | 100
4033 | Alipore Division | Canning Sub-division | Preparation of Design & DPR including Estimate for Retrofitting for Providing FHTC at Ground Water Based Nagartala (Zone-II) Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001674/2021-2022 | 639/CSD | 10/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 2.67 | 0 | 100
4034 | Alipore Division | Canning Sub-division | Route Survey for Providing FHTC at Ground Water Based Nagartala (Zone-II) [Part-B] Water Supply Scheme, Block : Canning - II, District- South 24 Pgs. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001675/2021-2022 | 642/CSD | 11/08/2021 | 15 | INDRANIL DUTTA & ASSOCIATES | 1.35 | 0 | 100
4035 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Nagartala (Zone - II) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001678/2022-2023 | 11487/AD | 15/02/2023 | 45 | PAL AGENCY | 7.1 | 0 | 98
4036 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000068/2022-2023 | 3948/AD | 12/08/2022 | 0 | Resource Division | 16.35 | 0 | 0
4037 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1500 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8848] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000478/2023-2024 | 1991/AD | 04/08/2023 | 882 | M/S. S.S. ENTERPRISE | 2077.27 | 0 | 30
4038 | Alipore Division | Diamond Harbour Sub-Division | Improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-VIII(A) of Kulpi Block under Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000666/2023-2024 | 2600/AD | 31/08/2023 | 15 | GLOBUS CONSULTANCEY | 9.43 | 0 | 0
4039 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-VIII(A) of Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001020/2022-2023 | 293/DHSD | 15/09/2022 | 30 | GEO SOLUTION | 4.41 | 0 | 99
4040 | Alipore Division | Diamond Harbour Sub-Division | Special repairing and restoration of distribution system at different places (Rangafala, Patra para etc.) of Arunnagar Belpukuria PWSS under zone-VIIIA at Kulpi Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001152/2023-2024 | 3198/AD | 04/10/2023 | 30 | M/S. SUMAN ENTERPRISE | 26.48 | 0 | 0
4041 | Alipore Division | Diamond Harbour Sub-Division | Land Developement and other allied works within the head works site under Zone No-VIIIA of Kulpi Block under "Mega Surface Water Based Water Supply Scheme , Dist. South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18552] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001397/2024-2025 | 5543/AD | 30/12/2024 | 45 | M/S. S.S. ENTERPRISE | 100.84 | 0 | 30
4042 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of pipeline under the Augmentation Scheme of Kulpi Zone-VIIIA for providing 100% FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/18552] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/001456/2024-2025 | 14/AD | 03/01/2025 | 60 | SUBHO CONSTRUCTION | 361.14 | 0 | 0
4043 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-VIII(A) (Arunnagar, OHR Size-1500 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002099/2022-2023 | 338/DHSD | 17/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
4044 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000210/2023-2024 | 2019/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
4045 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000369/2023-2024 | 3233/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4046 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000625/2023-2024 | 286/AD | 15/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
4047 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000672/2023-2024 | 425/AD | 22/01/2024 | 0 | Resource Division | 244.27 | 0 | 0
4048 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000859/2023-2024 | 766/AD | 03/02/2024 | 0 | Resource Division | 45.26 | 0 | 0
4049 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000938/2023-2024 | 1280/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4050 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Taktipur Zone - I & II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000045/2023-2024 | 30/KSD | 24/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
4051 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connection etc. for Augmentation of Taktipur Zone- II W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/11876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000211/2024-2025 | 2594/AD | 19/06/2024 | 45 | M/S B.M. CONSTRUCTION | 37.59 | 0 | 0
4052 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Taktipur Abad Zone-I W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000279/2023-2024 | 1429/AD | 13/07/2023 | 45 | MAJUMDER ENTERPRISE | 44.25 | 0 | 100
4053 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Taktipur Abad (Zone-I & II) W/S Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000363/2022-2023 | 4118/AD | 18/08/2022 | 45 | SARADA CONSTRUCTION | 36.64 | 0 | 100
4054 | Alipore Division | Kakdwip Sub-Division | Continuation work order for the work of Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.07.2024 to 31.12.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000374/2024-2025 | 2793/AD | 01/07/2024 | 184 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 100
4055 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 22.07.2022 to 21.01.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000377/2022-2023 | 130/HQ-II/AD | 20/07/2022 | 6 | BISWADIP SIKDAR | 2.4 | 0 | 50
4056 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.07.2023 to 31.12.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000397/2023-2024 | 102/HQ-II/AD | 28/06/2023 | 183 | M/S P. B. CONSTRUCTION | 2.4 | 0 | 30
4057 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 1st and 2nd Tubewell Site for Augmentation of Taktipur (Zone-I & II) W/S scheme, Block : Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/11876) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000412/2024-2025 | 3063/AD | 25/07/2024 | 45 | RAJ ENTERPRISE | 38.71 | 0 | 0
4058 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( TAKTIPUR ABAD (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000493/2022-2023 | 1977/AD | 20/06/2022 | 45 | LEMNISCATE | 6 | 0 | 100
4059 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Taktipur Abad (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000504/2022-2023 | 5090/AD | 20/09/2022 | 300 | MAJUMDER ENTERPRISE | 260.4 | 0 | 100
4060 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 2 Nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Taktipur Abad (Zone-I & II) Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000553/2022-2023 | 5727/AD | 13/10/2022 | 820 | M/S B.M. CONSTRUCTION | 211.19 | 0 | 85
4061 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Taktipur Abad Zone-II Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/000634/2023-2024 | 2462/AD | 24/08/2023 | 45 | M/S M. ENTERPRISE | 11.72 | 0 | 60
4062 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Executive Engineer, Alipore Division, PHE Dte. for the period from 01.12.2022 to 15.12.2022 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001062/2022-2023 | 384/HQ-II/AD | 29/11/2022 | 15 | PRIYANKI SADHUKHAN | 0.2 | 0 | 85
4063 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Taktipur Zone-II W/S Scheme, South 24 Parganas, Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/001842/2023-2024 | 130/AD | 05/01/2024 | 60 | M/S B.M. CONSTRUCTION | 38.33 | 0 | 100
4064 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Taktipur Abad Zone - I & II, Chandipur, Bamanagar, Gangadharpur Zone - I &II PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | ORD/002141/2023-2024 | 941/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 100
4065 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000086/2022-2023 | 5593/AD | 29/09/2022 | 0 | Resource Division | 14.31 | 0 | 0
4066 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000270/2023-2024 | 3069 | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4067 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000463/2023-2024 | 4724/AD | 18/12/2023 | 0 | Resource Division | 27.96 | 0 | 0
4068 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_4, Kakdwip Sub Division,Juniour Engineer_4, Raidighi Sub Division | RTOR000998/2023-2024 | 1791/AD | 27/03/2024 | 0 | Resource Division | 15.78 | 0 | 0
4069 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households of Rakhalpur Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001595/2020-2021 | 5454/AD | 24/02/2021 | 365 | GROWING CONCERN | 100.46 | 74.33 | 95
4070 | Alipore Division |  | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile & pile cap for OHR etc at Rakhalpur (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14987) |  |  | ORD/000343/2024-2025 | 2755/AD | 27/06/2024 | 75 | BIMALENDU GIRI | 167.27 | 0 | 0
4071 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households of Rakhalpur Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001595/2020-2021 | 5454/AD | 24/02/2021 | 365 | GROWING CONCERN | 100.46 | 0 | 95
4072 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000778/2023-2024 | 612/AD | 29/01/2024 | 0 | Resource Division | 8.18 | 0 | 0
4073 | Alipore Division | Diamond Harbour Sub-Division | HIRING VEHICLE BILL FOR MONTH OF DECEMBER '22 TO FEBRUARY'23 | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01275/2022-2023 | BP-2022-23-1055 | 31/03/2023 | 0 | GOPAL KUMAR JHA | 1.18 | 0 | 0
4074 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-IX including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000081/2020-2021 | 5444/AD | 24/02/2021 | 365 | GHOSH ENTERPRISE | 228.22 | 119.51 | 100
4075 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/11/2023 to 30/04/2024) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001188/2023-2024 | 555/DHSD | 31/10/2023 | 182 | GOPAL KUMAR JHA | 2.4 | 0 | 100
4076 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-1) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003148/2020-2021 | 256/DHSD | 25/11/2020 | 45 | ASMIT ENTERPRISE | 4.66 | 0 | 100
4077 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-2) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003149/2020-2021 | 261/DHSD | 26/11/2020 | 45 | SRIJON ENTERPRISE | 4.05 | 0 | 100
4078 | Alipore Division | Diamond Harbour Sub-Division | Dismantling and restoration of existing village concrete road for retrofitting of distribution pipeline of Falta Zone-IX under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Part-3) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/003150/2020-2021 | 262/DHSD | 26/11/2020 | 45 | SUJOY SADHUKHAN | 4.42 | 0 | 100
4079 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000852/2023-2024 | 790/AD | 03/02/2024 | 0 | Resource Division | 3.84 | 0 | 0
4080 | Alipore Division | Canning Sub-division | Trial run of CI/DI/AC/UPVC Rising Main & Distribution System at Lahiripur W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [60 Days] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000001/2022-2023 | 01/CSD | 01/04/2022 | 60 | GANGA TUBEWELL AND HARDWARE | 1.27 | 0 | 95
4081 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) at Lahiripur W/S Scheme (uncovered area), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000219/2023-2024 | 1024/AD | 13/06/2023 | 45 | SUPRITI ENTERPRISE | 59.73 | 0 | 99
4082 | Alipore Division | Canning Sub-division | Relaying of pipe line at node point 194-200, 217-209, 207-208 etc. at Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000289/2022-2023 | 299/CSD | 23/05/2022 | 30 | S.P. CONSTRUCTION (I) | 3.61 | 0 | 90
4083 | Alipore Division | Canning Sub-division | DI Pipeline protection of Lahiripur W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001635/2021-2022 | 1503/CSD | 15/02/2022 | 20 | GANGA TUBEWELL AND HARDWARE | 1.83 | 0 | 98
4084 | Alipore Division | Canning Sub-division | Extension of pipe line for FHTC work at Santigachhi of Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001645/2021-2022 | 1513/CSD | 15/02/2022 | 20 | C.S. CONSTRUCTION | 2.33 | 0 | 100
4085 | Alipore Division | Canning Sub-division | Relaying pipe line for uncovered FHTC work at Lahiripur W/S Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001646/2021-2022 | 1514/CSD | 15/02/2022 | 30 | S.P. CONSTRUCTION (I) | 3.24 | 0 | 95
4086 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Bidhan Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001665/2020-2021 | 1367/CSD | 08/01/2021 | 45 | SURYA ENTERPRISE | 3.6 | 0 | 95
4087 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001666/2020-2021 | 1368/CSD | 08/01/2021 | 45 | GANGA TUBEWELL AND HARDWARE | 4.29 | 0 | 95
4088 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Uttar Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001668/2020-2021 | 1370/CSD | 08/01/2021 | 45 | FIDERE MARINE SERVICES PVT. LTD. | 3.29 | 0 | 95
4089 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Ch Uttar Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001671/2020-2021 | 1371/CSD | 08/01/2021 | 45 | S.C. ENTERPRISE (I) | 3.28 | 0 | 95
4090 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001672/2020-2021 | 1372/CSD | 08/01/2021 | 45 | SURYA ENTERPRISE | 4.66 | 0 | 95
4091 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001673/2020-2021 | 1373/CSD | 08/01/2021 | 45 | A.P. CONSTRUCTION | 4.71 | 0 | 95
4092 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Chargheri Dakhin Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001674/2020-2021 | 1374/CSD | 08/01/2021 | 45 | SURYA ENTERPRISE | 4.74 | 0 | 95
4093 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001675/2020-2021 | 1375/CSD | 08/01/2021 | 45 | ADITYA ENTERPRISE | 2.71 | 0 | 95
4094 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Purba Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001676/2020-2021 | 1377/CSD | 08/01/2021 | 45 | S.P. CONSTRUCTION (I) | 3.25 | 0 | 95
4095 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Purba Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001678/2020-2021 | 1378/CSD | 08/01/2021 | 45 | C.S. CONSTRUCTION | 2.4 | 0 | 95
4096 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001682/2020-2021 | 1379/CSD | 08/01/2021 | 45 | GANGA TUBEWELL AND HARDWARE | 4.47 | 0 | 95
4097 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001683/2020-2021 | 1380/CSD | 08/01/2021 | 45 | M. CHAKRABORTY | 4.47 | 0 | 95
4098 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001684/2020-2021 | 1381/CSD | 08/01/2021 | 45 | MODERN CONSTRUCTION | 4.47 | 0 | 95
4099 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Lahiripur of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001685/2020-2021 | 1382/CSD | 08/01/2021 | 45 | SUKANTA HALDER | 4.42 | 0 | 95
4100 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001686/2020-2021 | 1383/CSD | 08/01/2021 | 45 | KAYAL ENTERPRISE | 3.47 | 0 | 95
4101 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001687/2020-2021 | 1384/CSD | 08/01/2021 | 45 | S.P. CONSTRUCTION (I) | 3.48 | 0 | 95
4102 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Paschim Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001688/2020-2021 | 1387/CSD | 18/01/2021 | 45 | A.P. CONSTRUCTION | 3.41 | 0 | 95
4103 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001689/2020-2021 | 1388/CSD | 18/01/2021 | 45 | M. CHAKRABORTY | 4.01 | 0 | 95
4104 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001690/2020-2021 | 1389/CSD | 18/01/2021 | 45 | SHREEMAA ENTERPRISE | 4 | 0 | 95
4105 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001691/2020-2021 | 1390/CSD | 18/01/2021 | 45 | S.P. CONSTRUCTION (I) | 3.99 | 0 | 95
4106 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Santigachi of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001692/2020-2021 | 1391/CSD | 18/01/2021 | 45 | BENGAL BUILDERS | 3.98 | 0 | 95
4107 | Alipore Division | Canning Sub-division | Trial run of CI/DI/AC/UPVC Rising Main & Distribution System at Lahiripur W/S Scheme under Canning Sub Division of Alipore Division, PHE Dte. [60 Days] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001768/2020-2021 | 1455/CSD | 27/01/2021 | 60 | GANGA TUBEWELL AND HARDWARE | 1.27 | 0 | 98
4108 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at L Pur Majher Para of Lahiripur W/S Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, PHE Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/002040/2020-2021 | 1376/CSD | 08/01/2021 | 45 | SANTANU GHOSH | 2.94 | 0 | 95
4109 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Srinarayanpur Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/001349/2020-2021 | 5199/AD | 12/02/2021 | 365 | M/S. JHARNA ENTERPRISE | 155.66 | 83.82 | 97
4110 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000770/2023-2024 | 604/AD | 29/01/2024 | 0 | Resource Division | 18.94 | 0 | 0
4111 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Manasadwip Water Supply Scheme, Block - Sagar, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. |  |  | ORD/001257/2020-2021 | 2277/AD | 12/10/2020 | 365 | PIKASU BOSE | 128 | 2.21 | 100
4112 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to the households of Shibkalinagar Water Supply Scheme including one year Operation & Maintenance and repairing of distribution main, Block - Kakdwip under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. |  |  | ORD/001374/2020-2021 | 5130/AD | 08/02/2021 | 365 | SUPER SKILL | 87.04 | 0 | 95
4113 | Alipore Division |  | Laying distribution system and retrofitting of Functional Household Tap Connection (FHTC) to all households for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) |  |  | ORD/001422/2022-2023 | 10980/AD | 07/02/2023 | 30 | ANANDA MAITY | 12.91 | 0 | 100
4114 | Alipore Division |  | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Manasadwip (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) |  |  | ORD/001824/2022-2023 | 12120/AD | 01/03/2023 | 912 | BENGAL BUILDERS | 449.37 | 0 | 34
4115 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000699/2023-2024 | 469/AD | 24/01/2024 | 0 | Resource Division | 4.8 | 0 | 0
4116 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Narayanpur Water Supply Scheme, Block - Canning-II, South 24 Parganas District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000086/2020-2021 | 5309/AD | 18/02/2021 | 1627 | AVIK ENTERPRISE | 118.2 | 26.57 | 90
4117 | Alipore Division | Raidighi Sub-Division | Laying distribution line and construction of masonry valve chamber and others miscellaneous work for providing FHTC at Zone-VIII of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000346/2022-2023 | 4073/AD | 18/08/2022 | 30 | L.N. ENTERPRISE | 14.68 | 0 | 90
4118 | Alipore Division | Raidighi Sub-Division | Horizontally boring for providing FHTC at Zone-VIII of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000425/2022-2023 | 281/RSD | 01/09/2022 | 60 | L.N. ENTERPRISE | 0.84 | 0 | 100
4119 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Purba Jatardeul Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000511/2020-2021 | 5196/AD | 12/02/2021 | 365 | G.B. CONSTRUCTION & CO. | 125.27 | 47.88 | 98
4120 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Nandakumarpur (Zone-III) Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001336/2020-2021 | 2220/AD | 08/10/2020 | 365 | UNITED BUILDERS | 108.61 | 13.65 | 100
4121 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000070/2022-2023 | 5147/AD | 21/09/2022 | 0 | Resource Division | 18.45 | 0 | 0
4122 | Alipore Division | Raidighi Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur-II, Zone-IV (Gilarchat PWSS) including Operation & Maintenance of scheme for 1 (one) year under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District-South 24-Parganas, Block-Mathurapur-II under Raidighi Sub-Division of Alipore Division, PHE Dte. (Phase-I). | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000013/2022-2023 | 205/AD | 11/04/2022 | 1027 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 251.07 | 0 | 50
4123 | Alipore Division | Raidighi Sub-Division | Laying distribution system of piped water supply at Zone-IV of Mathurapur - II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000016/2022-2023 | 212/AD | 11/04/2022 | 1246 | UNITED BUILDERS | 337.79 | 0 | 70
4124 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000659/2023-2024 | 263/AD | 15/01/2024 | 0 | Resource Division | 33.26 | 0 | 0
4125 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 2nd Tubewell site for Sumatinagar (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13569) (SM/09394) (SM/08792) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000347/2025-2026 | 3103/AD | 02/07/2025 | 45 | M/S. MA BHABANI CONSTRUCTION | 5.58 | 0 | 0
4126 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000778/2022-2023 | 6649/AD | 14/11/2022 | 30 | MONCON INDIA | 10.01 | 0 | 100
4127 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =835] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | ORD/000813/2022-2023 | 6754/AD | 15/11/2022 | 120 | UCON | 140.93 | 0 | 100
4128 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | RTOR000695/2023-2024 | 465/AD | 24/01/2024 | 0 | Resource Division | 11.27 | 0 | 0
4129 | Alipore Division | Kakdwip Sub-Division | Preparation of DPR including estimate for Providing FHTC at Manasadwip W/S Scheme (Phase-A) & Sumatinagar W/S Scheme (Phase-A) W/S Scheme & it's adjacent areas, Block - Sagar under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte.[ W/O NO 520/AD, 24.08.21, T.NO. 1791/AD, 21-22] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_5, Kakdwip Sub Division | VCH/002609/2021-2022 | BP-2021-22-512 | 22/03/2022 | 0 | INDRANIL DUTTA & ASSOCIATES | 2.35 | 0 | 0
4130 | Alipore Division | Kakdwip Sub-Division | HIRE bill for month of MAY-JUL23 | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | BILL/03539/2023-2024 | BP-2023-24-1270 | 27/03/2024 | 0 | RAJKUMAR MANNA | 4.56 | 0 | 0
4131 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Achintyanagar W/S Scheme, Block - Pathar Pratima under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/08628) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000162/2024-2025 | 2513/AD | 15/06/2024 | 30 | SHREE J M CONSTRUCTION | 20.39 | 0 | 100
4132 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households of Achintyanagar Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Pathar Pratima under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000271/2021-2022 | 1718/AD | 17/08/2021 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 251.54 | 0 | 70
4133 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of tubewell at 4th Tubewell Site of Achintyanagar W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000430/2022-2023 | 203/KSD | 01/06/2022 | 7 | M/S B. ENTERPRISE | 0.61 | 0 | 100
4134 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Achintyanagar W/S Scheme under JJM, Block- Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | ORD/000999/2023-2024 | 506/KSD | 03/10/2023 | 7 | M/S B. ENTERPRISE | 3.74 | 0 | 100
4135 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000317/2023-2024 | 3126/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4136 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_4, Raidighi Sub Division,Juniour Engineer_5, Kakdwip Sub Division | RTOR000780/2023-2024 | 614/AD | 29/01/2024 | 0 | Resource Division | 12.28 | 0 | 0
4137 | Alipore Division | Kakdwip Sub-Division | Providing Functional Household Tap Connection (FHTC) to the households for 12 (twelve) nos. habitation of all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Bagdanga Water Supply Scheme including one year Operation and Maintenance and repairing of distribution main, Block - Namkhana under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000014/2021-2022 | 3163/AD | 09/11/2021 | 365 | MAHAVIR PUMPS MANUFACTURING PVT. LTD | 90.17 | 0 | 26
4138 | Alipore Division | Kakdwip Sub-Division | Relaying of DI pipeline with ancillary pipeline protection work for crossing over pond (9 nos.) at Bagbagan of Gosaba W/S Scheme (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000287/2023-2024 | 184/CSD | 22/05/2023 | 30 | SUSHANTA MANDAL | 4.74 | 0 | 99
4139 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000294/2023-2024 | 3061/AD | 28/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4140 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000800/2023-2024 | 645/AD | 30/01/2024 | 0 | Resource Division | 10 | 0 | 0
4141 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Tetultala), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - I) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000085/2022-2023 | 277/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.77 | 0 | 85
4142 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Narayantala, Naliakhali & Tetultala), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - II) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000086/2022-2023 | 278/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.79 | 0 | 85
4143 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to the households at Harbhangi Water Supply Scheme (Habitation- Chharanekhali & Uttar Sonakhali), Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Phase - III) | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000088/2022-2023 | 279/CSD | 19/05/2022 | 40 | PROJECT & MAINTENANCE | 4.76 | 0 | 85
4144 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for 19 (nineteen) nos. habitation in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Harbhangi Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Basanti, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000207/2021-2022 | 1424/AD | 27/07/2021 | 365 | PROJECT & MAINTENANCE | 129.74 | 0 | 97
4145 | Alipore Division | Diamond Harbour Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated) for the use of Assistant Engineer, Diamond Harbour Sub-Division, of Alipore Division, P.H.E. Dte. for (period from 01/05/2023 to 31/10/2023) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000080/2023-2024 | 23/DHSD | 25/04/2023 | 184 | GOPAL KUMAR JHA | 2.4 | 0 | 50
4146 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-VII at Kamarpole of Diamond Harbour- II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-950] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000305/2023-2024 | 1508/AD | 15/07/2023 | 1197 | JYOTY SOLAR POWER | 423.33 | 0 | 15
4147 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-VII including Operation and Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001150/2021-2022 | 5301/AD | 04/01/2022 | 1547 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 137.23 | 0 | 25
4148 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000013/2021-2022 | 5619/AD | 25/01/2022 | 0 | Resource Division | 17.45 | 0 | 0
4149 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000614/2023-2024 | 293/AD | 15/01/2024 | 0 | Resource Division | 12.32 | 0 | 0
4150 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% FHTC household by providing Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-IV of Diamond Harbour-II block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 1450] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000341/2023-2024 | 3601/AD | 25/10/2023 | 609 | CREATION CONSTRUCTION | 403.02 | 0 | 37
4151 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Diamond Harbour-II, Zone-IV including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001325/2021-2022 | 5934/AD | 11/02/2022 | 365 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 366.63 | 0 | 0
4152 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-II (Netra, OHR Size-900) within Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002369/2022-2023 | 322/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
4153 | Alipore Division | Diamond Harbour Sub-Division | Interconnection from secondary grid to OHR and laying in the left-out portion of distribution system of different dia. DI pipes i.e. 200mm, 300mm, 450mm along with 63mm to 280mm UPVC pipes with allied road restoration work under augmentation scheme of Zone-IV of Diamond Harbour-II Block under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [SM/09508, SM/13912, SM/13914] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002529/2024-2025 | 814/AD | 27/02/2025 | 360 | K.P. CONSTRUCTION | 146.09 | 0 | 52
4154 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000120/2022-2023 | 12050/AD | 27/02/2023 | 0 | Resource Division | 3.51 | 0 | 0
4155 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000877/2023-2024 | 751/AD | 03/02/2024 | 0 | Resource Division | 17.38 | 0 | 0
4156 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000922/2023-2024 | 1264/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4157 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the PH No.1, zone II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00006/2022-2023 | BP-2022-23-503 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 6.59 | 0 | 0
4158 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the P/H No. 1, zone-II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00007/2022-2023 | BP-2022-23-504 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 3.41 | 0 | 0
4159 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the PH No.1, zone II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00039/2022-2023 | BP-2022-23-503 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 0.38 | 0 | 0
4160 | Alipore Division | Canning Sub-division | Submission of power supply quotation for the P/H No. 1, zone-II of Jibantala W/S Scheme under SMD | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | BILL/00040/2022-2023 | BP-2022-23-504 | 12/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 0.38 | 0 | 0
4161 | Alipore Division | Canning Sub-division | Inter connection from TW No. -1, 2 and 3 to distribution line and supply materials at Jibantala Water Supply Scheme (Zone-I), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/000073/2022-2023 | 1037/AD | 23/05/2022 | 30 | KAMALA ENTERPRISE (I) | 7.68 | 0 | 95
4162 | Alipore Division | Canning Sub-division | Laying of additional pipeline with other allied works at Jibantala (Zone-I & II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/001030/2024-2025 | 4940/AD | 03/12/2024 | 45 | M/S. JHARNA ENTERPRISE | 20.96 | 0 | 0
4163 | Alipore Division | Canning Sub-division | Laying of additional pipe line to cover the FHTC work and other allied works for Jibantala (Zone - II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002056/2023-2024 | 572/AD | 29/01/2024 | 425 | VISHAL CONSTRUCTION CO. | 93.43 | 0 | 90
4164 | Alipore Division | Canning Sub-division | Laying of additional pipe line to cover the FHTC work and other allied works for Jibantala (Zone - I) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002057/2023-2024 | 573/AD | 29/01/2024 | 180 | ANKUSH CONSTRUCTION AND CO. | 26.61 | 0 | 70
4165 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 2 for Jibantala (Zone - II) Water Supply Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | ORD/002131/2024-2025 | 390/AD | 30/01/2025 | 30 | KUNDU CONSTRUCTION CO. | 14.2 | 0 | 0
4166 | Alipore Division | Canning Sub-division | Submission of power supply connection for Jibantala W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | VCH/001719/2022-2023 | BP-2022-23-432 | 17/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 5.53 | 0 | 0
4167 | Alipore Division | Canning Sub-division | Submission of power supply connection for Jibantala W/S Scheme under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 4 CSD | VCH/001720/2022-2023 | BP-2022-23-431 | 17/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED. | 3.58 | 0 | 0
4168 | Alipore Division | Diamond Harbour Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VI including Operation & Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000065/2021-2022 | 342/AD | 12/05/2021 | 365 | BALAJEE ENTERPRISE. | 337.44 | 0 | 100
4169 | Alipore Division | Diamond Harbour Sub-Division | Shifting of distribution pipeline due to road widening programme by PWD at Sherpur Sirakole connector and Sherpur Bazar area of existing water supply scheme of Magrahat-I Block and inter connection between 03(three) nos. existing tube well of Fatepur W/S Scheme to the OHR of Falta Zone-VII for providing FHTC under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000444/2022-2023 | 4958/AD | 16/09/2022 | 30 | SUPRITI ENTERPRISE | 20.53 | 0 | 100
4170 | Alipore Division | Diamond Harbour Sub-Division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households in Falta, Zone-VII including Operation and Maintenance of scheme for 1 (one) year under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas, Block - Falta under Diamond Harbour Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001327/2021-2022 | 5935/AD | 11/02/2022 | 365 | SUPRITI ENTERPRISE | 279.46 | 0 | 95
4171 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000019/2022-2023 | 1196/AD | 30/05/2022 | 0 | Resource Division | 3.98 | 0 | 0
4172 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000030/2021-2022 | 4348/AD | 04/03/2022 | 0 | Resource Division | 26.84 | 0 | 0
4173 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000032/2021-2022 | 4347/AD | 04/03/2022 | 0 | Resource Division | 8.65 | 0 | 0
4174 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000033/2021-2022 | 4345/AD | 04/03/2022 | 0 | Resource Division | 14.64 | 0 | 0
4175 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000072/2022-2023 | 4851/AD | 21/09/2022 | 0 | Resource Division | 24.6 | 0 | 0
4176 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000098/2022-2023 | 7493/AD | 26/11/2022 | 0 | Resource Division | 2.69 | 0 | 0
4177 | Alipore Division |  | Providing Functional Household Tap Connection (FHTC) to all the households in Mathurapur piped water supply scheme ( Mathurapur-I, Zone-VII) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (Phase-I) |  |  | ORD/000569/2021-2022 | 3670/AD | 22/11/2021 | 365 | M/S. J.K. TRIPATHI & SONS | 80.12 | 0 | 100
4178 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 6636/AD | 15/03/2022 | 0 | Resource Division | 326.7 | 0 | 0
4179 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000605/2023-2024 | 235/AD | 11/01/2024 | 0 | Resource Division | 11.33 | 0 | 0
4180 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- V of Mathurapur-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 4138 ] | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/000087/2023-2024 | 498/AD | 11/05/2023 | 963 | JAL PRAVAHIKA PVT. LTD. | 569.23 | 0 | 41
4181 | Alipore Division | Raidighi Sub-Division | Construction of 700M3 capacity 20m straging height R.C.C OHR as per departmental design drawing & specification including R.C.C. bored pile & pile cap upto pedestal at Mathurapur-I block zone- v Site for Mega surface water based water supply scheme for Falta Mathurapur project under Raidighi Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002152/2019-2020 | 7722/AD | 26/02/2020 | 90 | JAL PRAVAHIKA PVT. LTD. | 128.67 | 0 | 80
4182 | Alipore Division | Raidighi Sub-Division | Protection of pipeline at Zone -V Mathurapur -I block under Raidighi Sub Division of Alipore Division, PHE Dte. (Tender no.- Not found) | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | ORD/002164/2019-2020 | 681/RSD | 03/01/2020 | 0 | M/S MAA ENTERPRISE | 4.63 | 0 | 100
4183 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer1, Raidghi Sub Division | RTOR000599/2023-2024 | 231/AD | 11/01/2024 | 0 | Resource Division | 24.54 | 0 | 0
4184 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Laxmi Janardanpur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000068/2023-2024 | 49/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4185 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of tubewell at 3rd tubewell site of Laxmi Janardanpur W/S scheme under JJM, Block : Pathar Pratima under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000432/2022-2023 | 205/KSD | 01/06/2022 | 7 | AQUATECH ENGINEER | 0.89 | 0 | 100
4186 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Lakshmi Janardhanpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000464/2022-2023 | 299/AD | 12/04/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 4.77 | 0 | 100
4187 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Laxmi Janardanpur W/S Scheme, South 24 Parganas, Patharpratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000584/2023-2024 | 2438/AD | 22/08/2023 | 45 | DEEPAK ENTERPRISE | 31.6 | 0 | 100
4188 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001080/2021-2022 | 558/KSD | 08/09/2021 | 20 | LEMNISCATE | 4.24 | 0 | 100
4189 | Alipore Division | Kakdwip Sub-Division | Hiring of Diesel Car / Luxury Taxi for supervision of works of different works of Sagar Island under Kakdwip Sub Division of Alipore Division, P.H.E. Dte. for the period from 01.08.2022 to 31.01.2023. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001091/2022-2023 | 322/KSD | 26/07/2022 | 184 | BADSHA ALOM | 2.4 | 0 | 0
4190 | Alipore Division | Kakdwip Sub-Division | Route Survey for Providing FHTC at Laxmi Janardanpur W/S Scheme & it's adjacent areas, Block Pathar Pratima under Kakdwip Sub - Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001607/2021-2022 | 605/KSD | 27/09/2021 | 7 | LEMNISCATE | 1.55 | 0 | 100
4191 | Alipore Division | Kakdwip Sub-Division | Construction of 200 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Augmentation of Laxmi Janardanpur Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001649/2022-2023 | 11316/AD | 10/02/2023 | 1076 | DEEPAK ENTERPRISE | 603.25 | 0 | 45
4192 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kumarpur, Kedarpur, Purba Dwarokapur, Laxmi Janardanpur, Piprakhali, Dakshin Roypur PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002099/2023-2024 | 925/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 100
4193 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000048/2022-2023 | 3901/AD | 12/08/2022 | 0 | Resource Division | 10.09 | 0 | 0
4194 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000306/2023-2024 | 3101/AD | 28/09/2023 | 0 | Resource Division | 12.99 | 0 | 0
4195 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000314/2023-2024 | 3123/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4196 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000569/2023-2024 | 78/AD | 03/01/2024 | 0 | Resource Division | 14.52 | 0 | 0
4197 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 6 at Bijoynagar Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000023/2025-2026 | 2009/AD | 28/04/2025 | 30 | RAHIMA ENTERPRISE | 11.49 | 0 | 0
4198 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households in Bijoynagar Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000083/2020-2021 | 5306/AD | 18/02/2021 | 365 | SPA ENTERPRISE | 281.51 | 0 | 85
4199 | Alipore Division | Canning Sub-division | Additional laying of pipe line at Bijoynagar Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000084/2022-2023 | 1131/AD | 26/05/2022 | 30 | M/S. BISWAS CONSTRUCTION(I) | 18.18 | 0 | 91
4200 | Alipore Division | Canning Sub-division | Relaying and extension of pipeline due to FHTC work at Bijoynagar Water Supply Scheme Block- Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001064/2021-2022 | 5299/AD | 04/01/2022 | 60 | ANUP PAUL | 28.3 | 0 | 100
4201 | Alipore Division | Canning Sub-division | Laying of pipeline of uncovered FHTC work area of Bijoynagar Water Supply Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001178/2022-2023 | 8773/AD | 21/12/2022 | 30 | MONDAL ENTERPRISE - 2 (SDK) | 21.86 | 0 | 0
4202 | Alipore Division | Canning Sub-division | Providing Functional Household Tap Connection (FHTC) to all the households of Bijoynagar Water Supply Scheme, Block - Gosaba, South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001770/2020-2021 | 1456/CSD | 27/01/2021 | 45 | SUSHANTA MANDAL | 1.26 | 1.25 | 0
4203 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Gayadham W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000161/2023-2024 | 683/AD | 17/05/2023 | 686 | M/S B. ENTERPRISE | 28.69 | 0 | 100
4204 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Gayadham W/S scheme, Block : Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E.Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000162/2023-2024 | 684/AD | 17/05/2023 | 30 | M/S. JOYGURU ENTERPRISE | 9.56 | 0 | 0
4205 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc at Gayadham PWSS, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11744) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000187/2024-2025 | 923/AD | 05/03/2025 | 60 | M/S B. ENTERPRISE | 53.26 | 0 | 0
4206 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with 2 nos. Pump House and Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Gayadham Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000193/2023-2024 | 945/AD | 05/06/2023 | 667 | M/S B. ENTERPRISE | 297.45 | 0 | 86
4207 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing Functional Household Tap Connection (FHTC) to all households for Gayadham Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000304/2022-2023 | 3840/AD | 08/08/2022 | 15 | M/S. MANDAL ENTERPRISE | 7.72 | 0 | 0
4208 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gayadham W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000399/2022-2023 | 4529/AD | 01/09/2022 | 45 | MAMONI ENTERPRISE | 36.34 | 0 | 0
4209 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (GAYADHAM PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000466/2022-2023 | 1689/AD | 13/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 3.77 | 0 | 100
4210 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Gayadham W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/11744) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000558/2024-2025 | 3786/AD | 19/09/2024 | 80 | SARADA CONSTRUCTION | 40.8 | 0 | 100
4211 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Gayadham PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/003145/2023-2024 | 383/KSD | 22/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4212 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000066/2022-2023 | 3954/AD | 12/08/2022 | 0 | Resource Division | 37.1 | 0 | 0
4213 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000295/2023-2024 | 3090/AD | 28/09/2023 | 0 | Resource Division | 31.28 | 0 | 0
4214 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000577/2023-2024 | 53/AD | 03/01/2024 | 0 | Resource Division | 6.39 | 0 | 0
4215 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 997] (TSM/014717) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000020/2023-2024 | 91/AD | 11/04/2023 | 708 | MODERN CONSTRUCTION | 164.78 | 0 | 100
4216 | Alipore Division | Canning Sub-division | Laying damaged pipe line from PH-1 to Sadanandar More and Hatberia More to House of Chandika Show at Deuli Water Supply Scheme (Zone-II), Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000105/2021-2022 | 1189/AD | 07/07/2021 | 45 | M/S S AND P CONSTRUCTION | 38.01 | 0 | 100
4217 | Alipore Division | Canning Sub-division | Laying pipe line for uncovered habitation of Ground Water Based Augmentation Piped Water Supply Scheme for Deuli and Adjoining Mouzas (Kaluakhali, Mukhajyapara), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000543/2024-2025 | 3714/AD | 12/09/2024 | 30 | AHANA ENTERPRISE | 8.09 | 0 | 0
4218 | Alipore Division | Canning Sub-division | Bamboo pile walling for protection of pipe line for Ground Water Based of Augmentation Piped Water Supply Scheme for Deuli & Adjoining Mouzas (Kaluakhali, Mukhajyapara), Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000751/2024-2025 | 4425/AD | 05/11/2024 | 180 | AHANA ENTERPRISE | 30.06 | 0 | 100
4219 | Alipore Division | Canning Sub-division | Laying pipeline at Head Work Site for washed of OHR and parallel line of Augmentation of Deuli (Zone - I) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001027/2023-2024 | 1338/AD | 05/03/2024 | 40 | NARAYAN ENTERPRISE | 5.91 | 0 | 100
4220 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001119/2022-2023 | 8848/AD | 22/12/2022 | 45 | BHATTACHARJEE & CO. | 39.02 | 0 | 0
4221 | Alipore Division | Canning Sub-division | Road restoration work for the road damage due to laying of pipe line on Augmentation & Retrofitting of Deuli (Zone-I & II) PWSS, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [ at Deuli (Zone-I) ] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001632/2023-2024 | 1139/CSD | 31/10/2023 | 30 | SUKANTA HALDER | 3.06 | 0 | 100
4222 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001760/2022-2023 | 11942/AD | 24/02/2023 | 45 | M/S SEIKH ENTERPRISE | 7.34 | 0 | 95
4223 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Deuli & Adjoining Mouzas (Kaluakhali & Mukhajyapara) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001761/2022-2023 | 11943/AD | 24/02/2023 | 45 | M/S SEIKH ENTERPRISE | 7.08 | 0 | 85
4224 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Deuli & adjoining Mouzas (Kaluakhali & Mukhajyapara Mouza) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001943/2022-2023 | 5608/AD | 29/09/2022 | 45 | M/S APEX ENGINEERING | 2.61 | 0 | 80
4225 | Alipore Division | Canning Sub-division | Renovation of Pump House no. - 1 of Augmentation of Deuli (Zone - I & II) W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-I) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002458/2023-2024 | 1588/CSD | 23/02/2024 | 30 | SUKANTA HALDER | 1.59 | 0 | 100
4226 | Alipore Division | Canning Sub-division | Renovation of Pump House no. - 2 of Augmentation of Deuli (Zone - I & II) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002501/2023-2024 | 1598/CSD | 28/02/2024 | 30 | NAZRUL ENTERPRISE | 2 | 0 | 100
4227 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Chandakhali to Dhapdhapi More 2) Construction of road from T03 SurJapur Hat to Ramnagar to petrol pump on Pultala Champahali Road of PMGSY-III under Baruipur Block.(WB 02 573) | AE BSD,Assistant Engineer | JE-2,Junior Engineer | BILL/01665/2024-2025 | BP-2024-25-772 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 1.74 | 0 | 0
4228 | Alipore Division | Kakdwip Sub-Division | Vehicle bill for month of December'22 to January'2023 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | BILL/00461/2022-2023 | BP-2022-23-791 | 22/02/2023 | 0 | DEEPAK KUMAR PRASAD | 0.79 | 0 | 0
4229 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000067/2023-2024 | 48/KSD | 28/04/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 0
4230 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000127/2024-2025 | 2405/AD | 07/06/2024 | 30 | SANJIVINI ENTERPRISE | 11.78 | 0 | 0
4231 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (BANASHYAM NAGAR PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000463/2022-2023 | 2490/AD | 27/06/2022 | 45 | INDRANIL DUTTA & ASSOCIATES | 6.47 | 0 | 100
4232 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Banashyamnagar W/S Scheme, South 24 Parganas, Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000587/2023-2024 | 2344/AD | 18/08/2023 | 45 | UNIQUE AGENCY (PARTNER) | 58.37 | 0 | 90
4233 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Banashyam Nagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000668/2022-2023 | 6153/AD. | 01/11/2022 | 1157 | UNIQUE AGENCY | 333.06 | 0 | 50
4234 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction of 02 nos. Pump House for Banashyam Nagar Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC = 1000] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000784/2022-2023 | 6538/AD | 11/11/2022 | 120 | M/S A.K. GHATAK | 273.49 | 0 | 55
4235 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (From 01.09.2023 to 29.02.2024 | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000887/2023-2024 | 165/HQ-II/AD | 24/08/2023 | 184 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 45
4236 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Banashyamnagar W/S scheme, Block - Pathar Pratima under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000974/2023-2024 | 2993/AD | 06/10/2023 | 45 | M/S RAKESH ENTERPRISE | 33.2 | 0 | 0
4237 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site of Banashyamnagar W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/11848) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001366/2024-2025 | 5495/AD | 27/12/2024 | 131 | SARADA CONSTRUCTION | 52.11 | 0 | 100
4238 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (for the period from 01.03.2023 to 31.08.2023) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001828/2022-2023 | 520/HQ-II/AD | 27/02/2023 | 181 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 100
4239 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Banashyamnagar, Shibnagar, Gangapur, Chhoto Banashyamnagar PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002117/2023-2024 | 933/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.81 | 0 | 100
4240 | Alipore Division | Kakdwip Sub-Division | Hiring of an Inspection Vehicle (Diesel Operated with Luxury Permit) for use of the Assistant Engineer (HQ-II) under Alipore Division, PHE Dte. (From 01.03.2024 to 31.08.2024) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002317/2023-2024 | 1103/AD | 23/02/2024 | 182 | DEEPAK KUMAR PRASAD | 2.4 | 0 | 100
4241 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000089/2023-2024 | 535/AD | 12/05/2023 | 0 | Resource Division | 10.85 | 0 | 0
4242 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000520/2023-2024 | 4938/AD | 22/12/2023 | 0 | Resource Division | 16.27 | 0 | 0
4243 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000741/2023-2024 | 576/AD | 29/01/2024 | 0 | Resource Division | 1.94 | 0 | 0
4244 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000947/2023-2024 | 1681/AD | 22/03/2024 | 0 | Resource Division | 23.18 | 0 | 0
4245 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Sumatinagar Zone-II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000078/2023-2024 | 62/KSD | 02/05/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4246 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000152/2024-2025 | 2490/AD | 14/06/2024 | 75 | COPE ENTERPRISE | 57.99 | 0 | 100
4247 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000153/2024-2025 | 2491/AD | 14/06/2024 | 30 | ANANTA KUMAR GIRI | 26.9 | 0 | 100
4248 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household etc. for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000154/2024-2025 | 2492/AD | 14/06/2024 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 6.12 | 0 | 0
4249 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 250 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing and specification including R.C.C. Bored pile and pile cap upto pedestal at Sumatinagar (Zone-I & II), South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000281/2023-2024 | 1431/AD | 13/07/2023 | 45 | GROWING CONCERN | 41.85 | 0 | 100
4250 | Alipore Division | Kakdwip Sub-Division | Repairing of 1 no. Pump House, Earth Filling, Boundary Wall Painting and Repair, Approach Road at 1st Tubewell site for Sumatinagar (Zone-I) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/13569) (SM/09394) (SM/08792) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000339/2025-2026 | 3045/AD | 30/06/2025 | 45 | PALASH HALDAR | 7.87 | 0 | 0
4251 | Alipore Division | Kakdwip Sub-Division | Sinking of 01 No. 250mm x 150mm dia. 360 mtr. deep Tubewell Replacement Tubewell (damaged due to natural calamities) by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st Tubewell Site for Augmentation of Sumatinagar (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000420/2023-2024 | 1909/AD | 01/08/2023 | 30 | SARADA CONSTRUCTION | 24.12 | 0 | 100
4252 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Sumatinagar (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part - F) (SM/13569) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000495/2024-2025 | 3571/AD | 04/09/2024 | 90 | GROWING CONCERN | 100.89 | 0 | 100
4253 | Alipore Division | Kakdwip Sub-Division | Supplying, fitting, fixing and delivery of different dia. specials for Augmentation of Sumatinagar (Zone-I and II) W/S Scheme under JJM, Block- Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000720/2023-2024 | 2537/AD | 28/08/2023 | 30 | ANANTA KUMAR GIRI | 8.71 | 0 | 100
4254 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Sumatinagar (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000774/2022-2023 | 6646/AD | 14/11/2022 | 45 | SARADA CONSTRUCTION | 45.89 | 0 | 100
4255 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000775/2022-2023 | 6647/AD | 14/11/2022 | 30 | FIDERE MARINE SERVICES PVT. LTD. | 12.01 | 0 | 100
4256 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000777/2022-2023 | 6648/AD | 14/11/2022 | 45 | RANJIT CONSTRUCTION | 7.99 | 0 | 100
4257 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Augmentation of Sumatinagar (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) [No. of FHTC =835] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000813/2022-2023 | 6754/AD | 15/11/2022 | 120 | UCON | 140.93 | 0 | 100
4258 | Alipore Division | Kakdwip Sub-Division | Development of Land for sinking of 02 nos. tubewell for Sumatinagar Zone - II W/S scheme under JJM, Block : Sagar under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/000989/2023-2024 | 504/KSD | 03/10/2023 | 7 | SARADA CONSTRUCTION | 2.57 | 0 | 100
4259 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (SUMATINAGAR (ZONE - I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/001057/2022-2023 | 4648/AD | 06/09/2022 | 45 | VOYAGER | 8.14 | 0 | 100
4260 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mahishamari Zone - I & II, Sumatinagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002153/2023-2024 | 948/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
4261 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Sumatinagar (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002176/2023-2024 | 813/AD | 05/02/2024 | 45 | M/S. MA BHABANI CONSTRUCTION | 11.71 | 0 | 100
4262 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Sumatinagar (Zone-I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | ORD/002467/2023-2024 | 1571/AD | 16/03/2024 | 382 | BIMALENDU GIRI | 33.73 | 0 | 68
4263 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000498/2023-2024 | 4824/AD | 20/12/2023 | 0 | Resource Division | 34.63 | 0 | 0
4264 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000542/2023-2024 | 26/AD | 02/01/2024 | 0 | Resource Division | 10.31 | 0 | 0
4265 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_5, Kakdwip Sub Division | RTOR000965/2023-2024 | 1758/AD | 27/03/2024 | 0 | Resource Division | 28.55 | 0 | 0
4266 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system at Zone-II & Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIB / C) [No. of FHTC = 2650] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000043/2023-2024 | 178/AD | 19/04/2023 | 694 | SUNNY ELECTRIC CO. | 146 | 0 | 20
4267 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system at Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - III B) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000363/2023-2024 | 1564/AD | 17/07/2023 | 90 | M/S SUBIR GHOSH | 524.53 | 0 | 84
4268 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-IIIB of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001530/2023-2024 | 435/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
4269 | Alipore Division | Diamond Harbour Sub-Division | Additional bored cast in situ R.C.C pile due to revised drawing for the construction of 1000 m3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir within Zone-IIIA at Bhadura of Diamond Harbour -II Block for the Mega Surface Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002405/2023-2024 | 1153/AD | 27/02/2024 | 60 | M/S. PROMILA CONSTRUCTION | 39.73 | 0 | 0
4270 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000921/2023-2024 | 1263/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4271 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-II of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/001047/2022-2023 | 299/DHSD | 15/09/2022 | 30 | RAMKRISHNA CHAKRABORTY | 3.24 | 0 | 100
4272 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000342/2023-2024 | 3206/AD | 04/10/2023 | 0 | Resource Division | 0.41 | 0 | 0
4273 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000890/2023-2024 | 744/AD | 03/02/2024 | 0 | Resource Division | 35.24 | 0 | 0
4274 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division |  | RTOR000911/2023-2024 | 1253 | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4275 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 5 at Ground Water Based Augmentation Piped Water Supply Scheme of Atharabeki W/S Scheme Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000028/2025-2026 | 2014/AD | 28/04/2025 | 30 | HIMALAYAN PROPERTY DEALERS AND PROMOTERS PVT LTD | 14.17 | 0 | 0
4276 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection of Ground Water Based Augmentation Piped Water Supply Scheme for Atharabeki (Part - B), Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000030/2023-2024 | 169/AD | 19/04/2023 | 60 | SAMSUL ENTERPRISE | 120.51 | 0 | 95
4277 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Atharabeki (Part-B) W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000092/2023-2024 | 448/AD | 08/05/2023 | 829 | ASHIS ENTERPRISE | 13.07 | 0 | 65
4278 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabenki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001763/2022-2023 | 11945/AD | 24/02/2023 | 675 | BANGA NIRMAN | 7.36 | 0 | 100
4279 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Atharabeki (Part-B) W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001765/2022-2023 | 12038/AD | 27/02/2023 | 675 | BANGA NIRMAN | 7.1 | 0 | 100
4280 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Athara Beki (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-II Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001838/2022-2023 | 10937/AD | 06/02/2023 | 45 | TECH VISION | 2.82 | 0 | 0
4281 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
4282 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000013/2023-2024 | 218/AD | 21/04/2023 | 0 | Resource Division | 15.7 | 0 | 0
4283 | Alipore Division | Diamond Harbour Sub-Division | Payment for "Restoration of Fatepur Falta Road (MDR) near Panchloki to Basulat Battala, damaged caused due to laying of water pipelines by PHED under Diamond Harbour Sub Division in the District of South 24 Pgs" - Vide memo no. 1347(W)/681G, dated 02.11.2023 of Superintending Engineer, Southern Circle, P.W.Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01188/2024-2025 | BP-2024-25-558 | 11/09/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DEPTT. | 0.94 | 0 | 0
4284 | Alipore Division | Diamond Harbour Sub-Division | Payment for "Restoration of Fatepur Falta Road (MDR) (various chainage 465.5 mtr. , damaged caused due to laying of water pipelines by PHED under Diamond Harbour Sub Division in the District of South 24 Pgs" - Vide memo no. 1347(W)/681G, dated 02.11.2023 of Superintending Engineer, Southern Circle, P.W.Dte., | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01189/2024-2025 | BP-2024-25-559 | 11/09/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DEPTT. | 28 | 0 | 0
4285 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system to extend the benefit of 100% household by proving Functional Household Tap Connection (FHTC) for leftout areas and construction of platform for existing FHTC with allied works in Zone-VIII of Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No of FHTC-700]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000013/2023-2024 | 04/AD | 04/04/2023 | 90 | TANMAY ROY CHOWDHURY | 169.17 | 0 | 80
4286 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 400 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000021/2023-2024 | 92/AD | 11/04/2023 | 300 | BIDYUT UDYOG | 196.04 | 0 | 1
4287 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 600 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(B) at Falta block within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000304/2023-2024 | 1507/AD | 15/07/2023 | 900 | SUBRATA GHOSH | 285.95 | 0 | 40
4288 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- VII at Falta block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte.(Phase-II). [No of FHTC-1300]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002051/2022-2023 | 12973/AD | 22/03/2023 | 90 | SUPRITI ENTERPRISE | 106.69 | 0 | 70
4289 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000135/2022-2023 | 22/AD | 05/04/2023 | 0 | Resource Division | 101.08 | 0 | 0
4290 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000187/2023-2024 | 1277/AD | 05/07/2023 | 0 | Resource Division | 101.08 | 0 | 0
4291 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 400 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VIII(A) at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000021/2023-2024 | 92/AD | 11/04/2023 | 300 | BIDYUT UDYOG | 196.04 | 0 | 1
4292 | Alipore Division | Diamond Harbour Sub-Division | Land Development and beautification within the head works site under Zone-VIIIB at Falta block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000070/2025-2026 | 2259/AD | 14/05/2025 | 180 | SUBRATA GHOSH | 19.47 | 0 | 0
4293 | Alipore Division | Diamond Harbour Sub-Division | Construction of approach WBM Road for Falta Zone-VIIIB OHR site within Mega Surface water-based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001022/2024-2025 | 4933/AD | 03/12/2024 | 360 | SUBRATA GHOSH | 14.19 | 0 | 0
4294 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VIII at Falta block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001378/2024-2025 | 5523/AD | 28/12/2024 | 405 | MONDAL ENTERPRISE (MURSHIDABAD) | 44.51 | 0 | 75
4295 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-VIII at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001407/2024-2025 | 5552/AD | 30/12/2024 | 45 | TANMAY ROY CHOWDHURY | 31.11 | 0 | 0
4296 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000241/2023-2024 | 2780/AD | 12/09/2023 | 0 | Resource Division | 15.19 | 0 | 0
4297 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000620/2023-2024 | 281/AD | 15/01/2024 | 0 | Resource Division | 9.06 | 0 | 0
4298 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000930/2023-2024 | 1272/AD | 02/03/2024 | 0 | Resource Division | 1.24 | 0 | 0
4299 | Alipore Division | Diamond Harbour Sub-Division | Additional balance works under the Augmentation scheme of Zone-VII at Diamond Harbour-I block for providing balance pipe lying works, road restoration works etc. under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000080/2025-2026 | 2421/AD | 23/05/2025 | 60 | AVIK ENTERPRISE | 87.23 | 0 | 0
4300 | Alipore Division | Diamond Harbour Sub-Division | Construction of Car parking shed by Galvanised corrugated iron sheet at office premiese under Zone VII of Diamond Harbour-I Block for "Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas"under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001123/2023-2024 | 518/DHSD | 13/10/2023 | 30 | M/S B ENTERPRISE | 4.8 | 0 | 100
4301 | Alipore Division | Diamond Harbour Sub-Division | R.C.C Roof construction over existing Laboratory building of Office of the Assistant Engineer, Diamond Harbour Sub Division, PHE Dte. under Zone VII of Diamond Harbour-I Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001146/2023-2024 | 524/DHSD | 13/10/2023 | 30 | SAMIM AHMED | 4.81 | 0 | 100
4302 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 01(One) no.100mm x 50mm dia. having 5 nos. Strainer upto 300 mtr (Average) depth at office of the Assistant Engineer, Diamond Harbour Sub-Division under Zone-VII of Diamond Harbour-I Block under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001158/2023-2024 | 527/DHSD | 13/10/2023 | 7 | M/S B ENTERPRISE | 2.51 | 0 | 0
4303 | Alipore Division | Diamond Harbour Sub-Division | Augmentation for Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-VII at Diamond Harbour- I block under " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No. of FHTC = 5140] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001398/2022-2023 | 10870/AD | 04/02/2023 | 990 | AVIK ENTERPRISE | 383.98 | 0 | 95
4304 | Alipore Division | Diamond Harbour Sub-Division | Improvement of water as an interim measure by interconnection from Tubewells to OHR within Zone No-VII of Diamond Harbour-I Block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002025/2022-2023 | 12929/AD | 21/03/2023 | 15 | AVIK ENTERPRISE | 10.47 | 0 | 90
4305 | Alipore Division | Diamond Harbour Sub-Division | Additional laying of UPVC pipe line for balance portion in the distribution system for coverage 100% FHTC in Zone-VII at Diamond Harbour- I block under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002116/2023-2024 | 830/AD | 05/02/2024 | 45 | AVIK ENTERPRISE | 23.85 | 0 | 100
4306 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000001/2023-2024 | 33/AD | 05/04/2023 | 0 | Resource Division | 2.3 | 0 | 0
4307 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000132/2022-2023 | 24/AD | 05/04/2023 | 0 | Resource Division | 16.27 | 0 | 0
4308 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000235/2023-2024 | 2196/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
4309 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000240/2023-2024 | 2653/AD | 04/09/2023 | 0 | Resource Division | 30.8 | 0 | 0
4310 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000425/2023-2024 | 3611/AD | 30/10/2023 | 0 | Resource Division | 15.4 | 0 | 0
4311 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000916/2023-2024 | 1258/AD | 02/03/2024 | 0 | Resource Division | 0.93 | 0 | 0
4312 | Alipore Division | Diamond Harbour Sub-Division | Payment against "Restoration of Fatepur Falta Road (MDR) 0.3Km-0.6Km, 9.539Km- 10.05, 13.728Km-14.098Km, 14.098Km-14.418Km, 12.683Km-13.728Km & 9nos points: 5.9-6.1Km) under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Diamond Harbour Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 1118(W)/618G, Dt. 01.08.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | BILL/01575/2024-2025 | BP-2024-25-890 | 19/11/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 85.83 | 0 | 0
4313 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1250 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-IV at Falta block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8074]. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000350/2023-2024 | 1660/AD | 20/07/2023 | 438 | S.MISRA INFRADEV PVT. LTD. | 1874.49 | 0 | 87
4314 | Alipore Division | Diamond Harbour Sub-Division | Investigation of soil for the proposed 1(one) no. R.C.C. Over Head Reservoir i.e. at Zone-IV (OHR Size-1250) of Falta Block under Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000515/2022-2023 | 5536/AD. | 21/09/2022 | 10 | RAJIB KUMAR CHAKRABORTY | 0.82 | 0 | 0
4315 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 323.9 mm dia. (OD) M.S. and 100 mm dia. GI Distribution line for crossing of Bhatheria Canal at Gangadharpur mouza (Node point 297 to 299) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District. South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000529/2024-2025 | 3646/AD | 09/09/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 38.41 | 0 | 100
4316 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 100 mm dia. GI Distribution line for crossing of Canal at Kantafuli mouza (Node point 103 to 110) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000530/2024-2025 | 3647/AD | 09/09/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 20.24 | 0 | 100
4317 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of 273 mm dia (OD) MS Distribution line for crossing of Canal at Dholtikari mouza (Node point 10 to 11 ) for Providing 100% FHTC under the Augmentation scheme of Falta Zone-IV within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District.- South-24 Pgns. under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. (SM/ 14680) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000531/2024-2025 | 3648/AD | 09/09/2024 | 45 | S.MISRA INFRADEV PVT. LTD. | 23.17 | 0 | 100
4318 | Alipore Division | Diamond Harbour Sub-Division | Land Development and ICBP within the head works site under Zone-IV at Falta block under Mega Surface Water Based Water Supply Scheme, Dist. South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/000815/2024-2025 | 4501/AD | 11/11/2024 | 60 | S.MISRA INFRADEV PVT. LTD. | 25.1 | 0 | 100
4319 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IV of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001001/2022-2023 | 284/DHSD | 13/09/2022 | 30 | GEO SOLUTION | 3.72 | 0 | 0
4320 | Alipore Division | Diamond Harbour Sub-Division | Laying of additional pipeline, road restoration works etc. under the Augmentation scheme of Zone-IV at Falta block for providing 100% FHTC under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [SM/14680] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/001305/2024-2025 | 5379/AD | 23/12/2024 | 75 | S.MISRA INFRADEV PVT. LTD. | 152.39 | 0 | 0
4321 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-IV (OHR Size-1250) of Falta Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002103/2022-2023 | 344/DHSD | 18/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 100
4322 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-V at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002256/2024-2025 | 568/AD | 12/02/2025 | 180 | SAB ENGINEERING WORKS | 29.99 | 0 | 0
4323 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-I at Falta block for providing balance pipe lying works, House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | ORD/002390/2024-2025 | 637/AD | 18/02/2025 | 45 | M/S. S.S. ENTERPRISE | 23.13 | 0 | 0
4324 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000136/2022-2023 | 21/AD | 05/04/2023 | 0 | Resource Division | 393.9 | 0 | 0
4325 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000226/2023-2024 | 2189/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
4326 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000362/2023-2024 | 3226/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4327 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000430/2023-2024 | 3624/AD | 30/10/2023 | 0 | Resource Division | 36.96 | 0 | 0
4328 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000616/2023-2024 | 277/AD | 15/01/2024 | 0 | Resource Division | 12.78 | 0 | 0
4329 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 1 DHSD | RTOR000927/2023-2024 | 1269/AD | 02/03/2024 | 0 | Resource Division | 2.48 | 0 | 0
4330 | Alipore Division | Canning Sub-division | Restoration of Thunkati Canning Road South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | BILL/01323/2024-2025 | BP-2024-25-622 | 27/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 8.73 | 0 | 0
4331 | Alipore Division | Canning Sub-division | Laying distribution system for piped Water Supply Scheme for Augmentation of Canning PWSS Zone-I Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000066/2022-2023 | 5806/AD | 17/10/2022 | 1016 | MAA LAXMI ENTERPRISE | 195.19 | 0 | 70
4332 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000207/2022-2023 | 2994/AD | 11/07/2022 | 30 | SWASTIK CONSTRUCTION | 7 | 0 | 98
4333 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000208/2022-2023 | 2995/AD | 11/07/2022 | 30 | SWASTIK CONSTRUCTION | 6.78 | 0 | 98
4334 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-I), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000209/2022-2023 | 2996/AD | 11/07/2022 | 30 | SWASTIK CONSTRUCTION | 6.78 | 0 | 98
4335 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000210/2022-2023 | 2997/AD | 11/07/2022 | 30 | M/S P. B. CONSTRUCTION | 6.98 | 0 | 0
4336 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000211/2022-2023 | 2998/AD | 11/07/2022 | 30 | M/S P. B. CONSTRUCTION | 6.76 | 0 | 0
4337 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. - I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000212/2022-2023 | 2999/AD | 11/07/2022 | 30 | SUKALPA NIRMAN | 6.99 | 0 | 95
4338 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000213/2022-2023 | 3000/AD | 11/07/2022 | 30 | SUKALPA NIRMAN | 6.77 | 0 | 0
4339 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Canning W/S Scheme (Zone-III), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000214/2022-2023 | 3001/AD | 11/07/2022 | 30 | M/S. ASIRUDDIN SEKH ENTERPRISE | 6.73 | 0 | 0
4340 | Alipore Division | Canning Sub-division | Additional Laying of pipe line to connect the balance area of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I, under Canning Sub-Division of Alipore Division, P.H.E.Dte. (Zone-III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000278/2024-2025 | 2832/AD | 04/07/2024 | 270 | K.P. CONSTRUCTION | 75.69 | 0 | 80
4341 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitation and protection work at Augmentation of Canning (Zone- I, II & III) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000355/2024-2025 | 2827/AD | 04/07/2024 | 450 | AVIK ENTERPRISE | 141.64 | 0 | 45
4342 | Alipore Division | Canning Sub-division | Laying pipe line, construction of sluice valve chamber and other works at Canning W/S Scheme (Zone - I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000413/2023-2024 | 772/CSD | 02/08/2023 | 30 | JHARNA ENTERPRISE | 2.23 | 0 | 98
4343 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for head work Site for Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000444/2025-2026 | 3566/AD | 25/07/2025 | 45 | M.P. ENTERPRISE (II) | 29.51 | 0 | 0
4344 | Alipore Division | Canning Sub-division | Dismantling work of Plain Cement Concrete Road and restoration work (Canning Station areas) for laying distribution work of Augmentation of Canning Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-III) ( SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000546/2024-2025 | 3717/AD | 12/09/2024 | 270 | M.P. ENTERPRISE (II) | 41.04 | 0 | 98
4345 | Alipore Division | Canning Sub-division | Laying distribution system for piped Water Supply Scheme for Augumentation of Canning PWSS Zone-II Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000556/2022-2023 | 5807/AD | 17/10/2022 | 840 | AVIK ENTERPRISE | 232.69 | 0 | 80
4346 | Alipore Division | Canning Sub-division | Laying distribution system for piped Water Supply Scheme for Augumentation of Canning PWSS Zone-III Block Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000557/2022-2023 | 5808/AD | 17/10/2022 | 120 | K.P. CONSTRUCTION | 268.06 | 0 | 94
4347 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - I, Part -C) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000560/2022-2023 | 5811/AD | 17/10/2022 | 365 | MAA LAXMI ENTERPRISE | 56.93 | 0 | 0
4348 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - A) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000562/2022-2023 | 5812/AD | 17/10/2022 | 365 | AVIK ENTERPRISE | 59.17 | 0 | 0
4349 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - B) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000563/2022-2023 | 5813/AD | 17/10/2022 | 1095 | AVIK ENTERPRISE | 55.75 | 0 | 0
4350 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II, Part - C) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000564/2022-2023 | 5814/AD | 17/10/2022 | 1095 | AVIK ENTERPRISE | 49.11 | 0 | 96
4351 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - III, Part - A) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000565/2022-2023 | 5815/AD | 17/10/2022 | 365 | K.P. CONSTRUCTION | 83.63 | 0 | 0
4352 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone ¿ III, Part ¿ B) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000573/2022-2023 | 5816/AD | 17/10/2022 | 896 | K.P. CONSTRUCTION | 50.57 | 0 | 85
4353 | Alipore Division | Canning Sub-division | Retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households for all the households in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Canning Augmentation Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone ¿ III, Part ¿ C) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000574/2022-2023 | 5817/AD | 17/10/2022 | 365 | K.P. CONSTRUCTION | 61.49 | 0 | 98
4354 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 3 at Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000687/2024-2025 | 4292/AD | 29/10/2024 | 30 | M/S M.G.CONSTRUCTION | 8.94 | 0 | 0
4355 | Alipore Division | Canning Sub-division | Construction of 700 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - I) [SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000841/2024-2025 | 4576/AD | 15/11/2024 | 270 | JYOTY SOLAR POWER | 220.03 | 0 | 0
4356 | Alipore Division | Canning Sub-division | Construction of 900 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - III) [SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000842/2024-2025 | 4577/AD | 15/11/2024 | 270 | K.P. CONSTRUCTION | 288.41 | 0 | 0
4357 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-II) (SM/13116 ) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/000988/2023-2024 | 3300/AD | 07/10/2023 | 30 | MMS CONSTRUCTIONS PVT. LTD. | 14.05 | 0 | 100
4358 | Alipore Division | Canning Sub-division | Dismantling work of Plain Cement Concrete Road and restoration work up to laying distribution work for Canning (Zone-I, II & III) W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001019/2023-2024 | 3304/AD | 07/10/2023 | 105 | MAA LAXMI ENTERPRISE | 38.83 | 0 | 95
4359 | Alipore Division | Canning Sub-division | Dismantling of existing concrete road and restoration the same (Bahirsona and Kumarsha Chak Part) after laying pipe line at Augmentation of Canning Water Supply Scheme (Zone- I, II & III), Block- Canning- I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone-II) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001020/2023-2024 | 3305/AD | 07/10/2023 | 540 | AVIK ENTERPRISE | 34.3 | 0 | 0
4360 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-I) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001022/2023-2024 | 3307/AD | 07/10/2023 | 455 | SARKAR ENTERPRISE | 15.95 | 0 | 98
4361 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Canning W/S Scheme (Zone-I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) (SM/13116) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001023/2023-2024 | 3308/AD | 07/10/2023 | 511 | K.P. CONSTRUCTION | 17.47 | 0 | 95
4362 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for T/W No - 3 Site for Augmentation of Canning W/S Scheme (Zone-I, II & III), Block - Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (at Zone-III) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001059/2024-2025 | 4999/AD | 05/12/2024 | 30 | JOYDEB MANNA | 6.11 | 0 | 0
4363 | Alipore Division | Canning Sub-division | Earth work in filling between proposed Head Work Site and PWD Road at Canning W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001379/2022-2023 | 1061/CSD | 14/12/2022 | 20 | SNEHA CONSTRUCTION | 0.56 | 0 | 100
4364 | Alipore Division | Canning Sub-division | Laying pipe line, construction of sluice valve chamber and other works at Canning W/S Scheme (Zone - I, II & III), Block- Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001408/2023-2024 | 1147/CSD | 01/11/2023 | 30 | JHARNA ENTERPRISE | 2.84 | 0 | 100
4365 | Alipore Division | Canning Sub-division | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - II), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001436/2021-2022 | 6245/AD | 23/02/2022 | 60 | SNEHA CONSTRUCTION | 63.19 | 0 | 70
4366 | Alipore Division | Canning Sub-division | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - III), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001440/2021-2022 | 6246/AD | 23/02/2022 | 60 | BHATTACHARJEE AND CO. | 63.16 | 0 | 66
4367 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing on Augmentation of Canning PWSS (Zone-I, II, and III) , Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Canning (Zone-II), Pump House No. - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/001909/2023-2024 | 222/AD | 11/01/2024 | 270 | M/S. BABA KAPIL MUNI ENTERPRISE | 6.54 | 0 | 100
4368 | Alipore Division | Canning Sub-division | Sinking of 3 (three) Nos. 300mm x 200mm dia. 360 mtr. deep Tubewell by D.R. Rig method using PVC Pipe & Pre-packed Resin Bonded Gravel at 3 different Tubewell Sites for Augmentation of Canning Water Supply Scheme (Zone - I), Block - Canning - I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002413/2022-2023 | 5673/AD | 11/10/2022 | 60 | AQUATECH ENGINEERS | 71.43 | 0 | 90
4369 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) W/S Scheme Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (Zone - II) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002493/2024-2025 | 785/AD | 25/02/2025 | 30 | AVIJIT CONSTRUCTION | 8 | 0 | 0
4370 | Alipore Division | Canning Sub-division | Construction of 700 m³ capacity R.C.C OHR (based on Departmental Design & Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Ground Water Based Augmentation Piped Water Supply Scheme of Canning (Zone-I, II & III) of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (Zone - II) [SM/13116] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | ORD/002853/2024-2025 | 1153/AD | 18/03/2025 | 270 | RIVER BENZ CONSTRUCTION | 220.05 | 0 | 0
4371 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer | RTOR000731/2023-2024 | 554/AD | 25/01/2024 | 0 | Resource Division | 226.04 | 0 | 0
4372 | Alipore Division | Diamond Harbour Sub-Division | Sinking of 150 X100 mm dia. X 360 Mtr. Depth Rig bored Tube wells, Ground Water Recharge Structure of Tubewell, construction of Switch Room (3750 x 2550), Construction of soak pit, pavement, boundary fencing, MS gate, land development, approach road, Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water Based Mini Piped Water Supply Scheme for the Chak Ruplaskar having village with maximum 77 nos. households, Block - Kulpi under Diamond Harbour Sub Division of Alipore Division, PHE Dte. | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | ORD/001122/2022-2023 | 8766/AD | 21/12/2022 | 60 | SUSHANTA MANDAL | 31.08 | 0 | 0
4373 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Diamond Harbour sub division | Junior Engineer,Junior Engineer 4 DHSD | RTOR000875/2023-2024 | 782/AD | 03/02/2024 | 0 | Resource Division | 0.49 | 0 | 0
4374 | Alipore Division | Diamond Harbour Sub-Division | Estimate for Re-construction of Boundary wall (Part of North face, length = 27.00 mtr) as per departmental design and drawing at Masat Head Work Site of Diamond Harbour Sub-Division under Alipore Division, P.H.E Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000835/2022-2023 | 215/DHSD | 12/08/2022 | 45 | M/S M.B.ENTERPRISE | 3.59 | 0 | 0
4375 | Alipore Division | Diamond Harbour Sub-Division | Support service for detail surveying, cross checking of available LOP with making permission drawings for other department by using Survey Instruments like Remotly Piloted Aircraft System/ DGPS / Total Station etc. and detailed design of pipeline by using Watergems Software on the basis of the population density within the Zone-IX of Diamond Harbour-I Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001052/2022-2023 | 305/DHSD | 23/09/2022 | 30 | MEASURE LAND | 2.69 | 0 | 0
4376 | Alipore Division | Diamond Harbour Sub-Division | Renovation and reconstruction of existing staff room for the purpose of additional store room at Masat HWS in Zone-IX of Diamond Harbour-I Block for the project of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001181/2022-2023 | 8777/AD | 21/12/2022 | 120 | S.S. ENTERPRISE (II) | 13.97 | 0 | 100
4377 | Alipore Division | Diamond Harbour Sub-Division | Renovation of boundary wall including fencing work with R.B.T (Reinforced Barbed Tape) Concertina fencing at Masat HWS in Zone-IX of Diamond Harbour-I Block for the project of Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001182/2022-2023 | 8778/AD | 21/12/2022 | 30 | M/S S.DAS ENTERPRISE | 8.31 | 0 | 100
4378 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including providing (2184 nos) of Functional Household Tap Connection (FHTC) with allied works in Zone-IX of Diamond Harbour-I block within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur under Diamond Harbour sub- Division of Alipore Division P.H.E Dte. [No. of FHTC = 2184] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/001394/2022-2023 | 10866/AD | 04/02/2023 | 900 | BALAJI UDDYOG | 341.01 | 0 | 60
4379 | Alipore Division | Diamond Harbour Sub-Division | Repairing and Renovation of existing 272 Cum. capacity Over Head Reservoir of Zone-IX, Diamond Harbour-I Block (At Masat Water Supply Scheme), Block - Diamond Harbour - I under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (3rd Call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/002460/2023-2024 | 1559/AD | 16/03/2024 | 300 | SHARADIYA ENTERPRISE | 32.74 | 0 | 100
4380 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000124/2022-2023 | 12799/AD | 16/03/2023 | 0 | Resource Division | 19.82 | 0 | 0
4381 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000128/2022-2023 | 27/AD | 05/04/2023 | 0 | Resource Division | 9.31 | 0 | 0
4382 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000346/2023-2024 | 3210/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4383 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000422/2023-2024 | 3612/AD | 30/10/2023 | 0 | Resource Division | 12.32 | 0 | 0
4384 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000886/2023-2024 | 740/AD | 03/02/2024 | 0 | Resource Division | 1.13 | 0 | 0
4385 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000918/2023-2024 | 1260/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4386 | Alipore Division | Kakdwip Sub-Division | Construction of 300 cum. (2 nos.), 250 cum. (1 no.), 200 cum. (02 nos.) and 150 cum. (1 no.) Over Head Reservoir (OHR), (20 mtr. Staging Height) along with 12 nos. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investagation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Kashiabad, Dakshin Kashiabad, Manmathapur, Ramgopalpur, Mrinalnagar and Bhubannagar Water Supply Scheme, Block - Kakdwip for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No of FHTC= 12945] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000052/2023-2024 | 122/AD | 13/04/2023 | 719 | GARGO TRADERS | 2798.35 | 0 | 64
4387 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Dakshin Kasiabad W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000950/2023-2024 | 2982/AD | 26/09/2023 | 45 | M/S. RABIN CON | 27.5 | 0 | 0
4388 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Dakshin Kasiabad W/S scheme, Block - Kakdwip under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/000951/2023-2024 | 2983/AD | 26/09/2023 | 30 | M/S. PAPIYA ENTERPRISE | 9.47 | 0 | 0
4389 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme ( DAKSHIN KASIABAD PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/001048/2022-2023 | 3676/AD | 01/08/2022 | 45 | LEMNISCATE | 3.86 | 0 | 100
4390 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Harendranagar, Ramgopalpur, Uttar Kashiabad, Dakshin Kashiabad, Thangara, Nebutala PWSS under JJM at Kakdwip Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | ORD/002140/2023-2024 | 940/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.94 | 0 | 100
4391 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000447/2023-2024 | 4713/AD | 18/12/2023 | 0 | Resource Division | 14.1 | 0 | 0
4392 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_3, Kakdwip Sub Division | RTOR000588/2023-2024 | 87/AD | 03/01/2024 | 0 | Resource Division | 9.3 | 0 | 0
4393 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system at Zone-II & Zone-III of Diamond Harbour-II Block for providing 100% FHTC at leftout areas within "Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (Part - IIIB / C) [No. of FHTC = 2650] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000043/2023-2024 | 178/AD | 19/04/2023 | 694 | SUNNY ELECTRIC CO. | 146 | 0 | 20
4394 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 1250 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system with allied works in Zone-II of Diamond Harbour-II block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-8312] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000086/2023-2024 | 197/AD | 19/04/2023 | 1019 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 1011.34 | 0 | 25
4395 | Alipore Division | Diamond Harbour Sub-Division | Restoration on bituminous road (PWD), protection work due to pipe laying (225 mm. to 350 mm. dia.) and supply of D.I specials within Zone-II under Diamond Harbour-II Block for MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, DISTRICT SOUTH 24 PARGANAS under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000445/2022-2023 | 5527/AD | 29/09/2022 | 645 | GHOSH ENTERPRISE (II) | 22.78 | 0 | 100
4396 | Alipore Division | Diamond Harbour Sub-Division | Restoration by concreting of village road due to laying of pipeline dia. varies from 90 mm. to 350 mm. within Zone-II under Diamond Harbour-II Block for MEGA SURFACE WATER BASED WATER SUPPLY SCHEME OF FALTA-MATHURAPUR, SOUTH 24 PARGANAS under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000447/2022-2023 | 5528/AD | 29/09/2022 | 840 | GHOSH ENTERPRISE (II) | 94 | 0 | 100
4397 | Alipore Division | Diamond Harbour Sub-Division | Restoration of road and drain of damaged portion due to laying distribution and rising main pipeline from Raichoak more to Singhalganj F.P School under Zone- I of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000528/2024-2025 | 3645/AD | 09/09/2024 | 60 | K.P. CONSTRUCTION | 66.42 | 0 | 100
4398 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall (length - 145 m.) at proposed OHR site at Mouza - Akrapunji under Zone-II of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/000869/2024-2025 | 4653/AD | 20/11/2024 | 60 | MOUSUMI ENTERPRISE | 26.73 | 0 | 0
4399 | Alipore Division | Diamond Harbour Sub-Division | Laying of distribution system at Zone-II of Diamond Harbour-II Block for Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001459/2021-2022 | 6072/AD | 17/02/2022 | 1194 | SAMIRON GHOSH | 479.57 | 0 | 100
4400 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-I of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001517/2023-2024 | 432/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
4401 | Alipore Division | Diamond Harbour Sub-Division | Support service for Detail Design & Drawing of pipe line by using Watergems Software on the basis of the population density within the ZONE-II of Diamond Harbour-II Block under " Megha Surface water based W/S scheme for Falta-Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/001521/2023-2024 | 433/DHSD | 22/09/2023 | 14 | GEO SOLUTION | 0.84 | 0 | 100
4402 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-II at Diamond Harbour- II block for providing House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002151/2024-2025 | 410/AD | 31/01/2025 | 30 | M/S. S.S. ENTERPRISE | 16.15 | 0 | 0
4403 | Alipore Division | Diamond Harbour Sub-Division | Laying of different dia pipes(DI pipe- 350mm to 400mm, UPVC- 90mm to 225mm) for the balance portion in the distribution system under Diamond Harbour II Block along with the Restoration of subsequent Bitumenous road and concrete road under the jurisdiction of PWD and Diamond Harbour II Panchayat Samiti / Block with the supply of DI specials and allied works of totaling 9453 mtr. under the Augmentation scheme of Diamond Harbour Zone-II within ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division of PHE Dte.(Under Jal Jeevan Mission) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002315/2023-2024 | 1092/AD | 22/02/2024 | 720 | SAMIRON GHOSH | 264.14 | 0 | 85
4404 | Alipore Division | Diamond Harbour Sub-Division | Balance works under the Augmentation scheme of Zone-I at Diamond Harbour- II block for providing House Hold Tap connection under Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | ORD/002492/2024-2025 | 783/AD | 25/02/2025 | 45 | K.P. CONSTRUCTION | 23.55 | 0 | 0
4405 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000139/2022-2023 | 18/AD | 05/04/2023 | 0 | Resource Division | 757.19 | 0 | 0
4406 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000219/2023-2024 | 2202/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
4407 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000737/2023-2024 | 567/ad | 27/01/2024 | 0 | Resource Division | 245.4 | 0 | 0
4408 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000880/2023-2024 | 754/AD | 03/02/2024 | 0 | Resource Division | 51.2 | 0 | 0
4409 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 3 DHSD | RTOR000919/2023-2024 | 1261/AD | 02/03/2024 | 0 | Resource Division | 0.62 | 0 | 0
4410 | Alipore Division | Canning Sub-division | Construction of boundary wall and Land development for Tube Well No. 4 Site at Narayanpur W/S Scheme, Block - Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000311/2025-2026 | 2964/AD | 25/06/2025 | 30 | CHATTERJEE CONSTRUCTION | 19.11 | 0 | 0
4411 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials at PH-IV of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000734/2023-2024 | 2895/AD | 19/09/2023 | 45 | DIPTI ENTERPRISE | 70.53 | 0 | 60
4412 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 of Augmentation of Narayanpur W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001663/2022-2023 | 11475/AD | 15/02/2023 | 30 | SARFARAZ CONSTRUCTION | 19.59 | 0 | 90
4413 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Narayanpur W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001682/2022-2023 | 11489/AD | 15/02/2023 | 45 | R CONSTRUCTION | 7.11 | 0 | 98
4414 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000006/2023-2024 | 121/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
4415 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000015/2023-2024 | 220/AD | 21/04/2023 | 0 | Resource Division | 61.12 | 0 | 0
4416 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000141/2023-2024 | 853/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4417 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
4418 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-V) W/S Scheme , Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000093/2023-2024 | 449/AD | 03/05/2023 | 593 | HI TECH ENTERPRISE | 9.12 | 0 | 90
4419 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
4420 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Augmentation of Basanti (Zone-I, II, IV, V & VI) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (SM/15053, SM/15959, SM/15975, SM/15052 & SM/15976) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001223/2024-2025 | 5181/AD | 13/12/2024 | 60 | ARNAB ENTERPRISE (HABRA) | 113.4 | 0 | 99
4421 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001703/2022-2023 | 11667/AD | 20/02/2023 | 45 | SARKAR CONSTRUCTION | 7.36 | 0 | 99
4422 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-V) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001726/2022-2023 | 11763/AD | 21/02/2023 | 80 | B.K. ENTERPRISE. | 60 | 0 | 97
4423 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-V) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001916/2022-2023 | 10942/AD | 06/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.26 | 0 | 99
4424 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002047/2022-2023 | 13047/AD | 24/03/2023 | 45 | JAGANNATH CONSTRUCTION | 7.11 | 0 | 98
4425 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-V) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002048/2022-2023 | 13048/AD | 24/03/2023 | 45 | SABITA INFRASTRUCTURE | 7.11 | 0 | 98
4426 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000025/2023-2024 | 231/AD | 24/04/2023 | 0 | Resource Division | 24.45 | 0 | 0
4427 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000154/2023-2024 | 1050/AD | 15/06/2023 | 0 | Resource Division | 13.83 | 0 | 0
4428 | Alipore Division | Canning Sub-division | Restoration of Basanti Goran Bose Ganga Mela block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01326/2024-2025 | BP-2024-25-624 | 30/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 99.74 | 0 | 0
4429 | Alipore Division | Canning Sub-division | Restoration ofChurchgate Chandur More Road block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01327/2024-2025 | BP-2024-25-623 | 30/09/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 5.53 | 0 | 0
4430 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Basanti (Zone-I) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000108/2023-2024 | 506/AD | 11/05/2023 | 15 | A.P. CONSTRUCTION | 13.02 | 0 | 0
4431 | Alipore Division | Canning Sub-division | Construction of OHR, Laying of Distribution System, Providing Functional Household Tap Connection of Augmentation Piped Water Supply Scheme for Basanti (Zone-I, II, IV, V & VI), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No of FHTC=9052] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000349/2023-2024 | 1659/AD | 20/07/2023 | 900 | M/S PATH MAKERS | 2061.38 | 0 | 78
4432 | Alipore Division | Canning Sub-division | Supply of water through pipe line connection at BL & LRO Basanti office from existing pipe line of Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001196/2020-2021 | 1180/CSD | 15/12/2020 | 7 | A.P. CONSTRUCTION | 0.65 | 0 | 0
4433 | Alipore Division | Canning Sub-division | Inter connection in between the replacement tubewell towards distribution system for Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. (TW-1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001261/2023-2024 | 1205/CSD | 10/11/2023 | 30 | SUSHANTA MANDAL | 1.06 | 0 | 95
4434 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Basanti (Zone-I) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001349/2022-2023 | 10216/AD | 19/01/2023 | 81 | SNEHA CONSTRUCTION | 58.47 | 0 | 66
4435 | Alipore Division | Canning Sub-division | Pipe line connection from Petrol Pump of Rambabu to basanti Chowmatha TV Relay Centre at Basanti W/S Scheme (Zone-I), Block - Basanti, under Canning Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001397/2023-2024 | 1129/CSD | 30/10/2023 | 30 | KAYAL ENTERPRISE | 1.62 | 0 | 100
4436 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001700/2022-2023 | 11664/AD | 20/02/2023 | 45 | LASKAR CONSTRUCTION | 7.24 | 0 | 98
4437 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001701/2022-2023 | 11665/AD | 20/02/2023 | 650 | SUJOY SADHUKHAN | 7.08 | 0 | 98
4438 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Basanti W/S Scheme (Zone-I) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001702/2022-2023 | 11666/AD | 20/02/2023 | 45 | SARKAR CONSTRUCTION | 7.11 | 0 | 0
4439 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Basanti (Zone-I) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001915/2022-2023 | 10941/AD | 06/02/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 7.25 | 0 | 99
4440 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000021/2023-2024 | 227/AD | 24/04/2023 | 0 | Resource Division | 110.78 | 0 | 0
4441 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000150/2023-2024 | 1053/AD | 15/06/2023 | 0 | Resource Division | 16.16 | 0 | 0
4442 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000250/2023-2024 | 3042/AD | 28/09/2023 | 0 | Resource Division | 94.19 | 0 | 0
4443 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Nadabhanga W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000133/2024-2025 | 2470/AD | 14/06/2024 | 45 | M/S MAITY CONSTRUCTION | 27.83 | 0 | 0
4444 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC Platform at every individual beneficiary, pump connections etc. for Nadabangha W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/14158) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000404/2024-2025 | 3187/AD | 31/07/2024 | 75 | UCON (II) | 95.23 | 0 | 0
4445 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Nadabangha W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001305/2022-2023 | 9888/AD | 10/01/2023 | 45 | MONDAL ENTERPRISE (MURSHIDABAD) | 38.59 | 0 | 0
4446 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Nadabhanga PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001798/2022-2023 | 3695/AD | 02/08/2022 | 45 | M/S R.DUTTA & CO. | 7.26 | 0 | 95
4447 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Nadabangha Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 2365] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002081/2022-2023 | 12546/AD | 10/03/2023 | 934 | UCON | 385.79 | 0 | 50
4448 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
4449 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 250 cum. capacity OHR of Nadabhanga PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002215/2023-2024 | 872/KSD | 14/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
4450 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000479/2023-2024 | 4783/AD | 19/12/2023 | 0 | Resource Division | 16.42 | 0 | 0
4451 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000556/2023-2024 | 44/AD | 03/01/2024 | 0 | Resource Division | 14.05 | 0 | 0
4452 | Alipore Division | Kakdwip Sub-Division | Providing support services for data mapping of available data within command area for preparation of GMIS at Dhaspara (Zone-I and II) (SM/15221), Ghoramara (SM/14988) W/S Scheme, Block - Sagar of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000020/2025-2026 | 2006/AD | 28/04/2025 | 30 | ROY CHOWDHURY ASSOCIATES | 7.24 | 0 | 100
4453 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Dhaspara W/S Scheme, Sagar Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000183/2024-2025 | 2543/AD | 18/06/2024 | 45 | MANASH GHOSH | 43.99 | 0 | 0
4454 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the construction of 300 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal at Dhaspara W/S Scheme, Sagar Block, Dist. - South 24 Parganas, under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (for Zone-II) (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/000193/2024-2025 | 2553/AD | 18/06/2024 | 45 | MANASH GHOSH | 48.99 | 0 | 0
4455 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different household, Construction of Sluice Valve Chamber, fitting fixing supplying different dia specials etc. for Augmentation of Dhaspara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-C) (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001103/2024-2025 | 5034/AD | 06/12/2024 | 60 | MANASH GHOSH | 206.17 | 0 | 0
4456 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Dhaspara [Zone-I & II] PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/001917/2021-2022 | 6555/AD | 10/03/2022 | 45 | VOYAGER | 8.94 | 0 | 95
4457 | Alipore Division | Kakdwip Sub-Division | Construction of 2 Nos. 300 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for Augmentation of Dhaspara Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002041/2022-2023 | 12999/AD | 23/03/2023 | 300 | MANASH GHOSH | 656.29 | 0 | 20
4458 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st & 2nd Tubewell Site for Augmentation of Dhaspara W/S Scheme (Zone-I & II), Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002056/2022-2023 | 13064/AD | 24/03/2023 | 45 | AQUATECH ENGINEERS | 47.54 | 0 | 0
4459 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of 300 cum. capacity OHR of Dhaspara PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002076/2023-2024 | 773(A)/KSD | 08/12/2023 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4460 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at Head work site of Zone-I of Dhaspara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002135/2024-2025 | 1975/KSD | 23/12/2024 | 20 | M/S MODINA ENTERPRISE | 2.72 | 0 | 0
4461 | Alipore Division | Kakdwip Sub-Division | Repairing of Pump House and Boundary wall at 2nd Tube well site of Zone-I of Dhaspara W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/15221) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002136/2024-2025 | 1976/KSD | 23/12/2024 | 20 | M/S MODINA ENTERPRISE | 2.59 | 0 | 0
4462 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Dhaspara Zone - I & II, Manasadwip Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002161/2023-2024 | 950/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
4463 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Dhaspara (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002283/2023-2024 | 919/AD | 08/02/2024 | 45 | BHUNIA BUILDERS | 33.71 | 0 | 80
4464 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Dhaspara (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002285/2023-2024 | 970/AD | 12/02/2024 | 30 | JAYANTA KUMAR DEY | 11.81 | 0 | 97
4465 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Dhaspara (Zone - I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | ORD/002611/2023-2024 | 378/KSD | 21/02/2024 | 5 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4466 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000337/2023-2024 | 3152/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4467 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000507/2023-2024 | 4829/AD | 20/12/2023 | 0 | Resource Division | 39.83 | 0 | 0
4468 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000539/2023-2024 | 23/AD | 02/01/2024 | 0 | Resource Division | 0.59 | 0 | 0
4469 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_1, Kakdwip Sub Division | RTOR000691/2023-2024 | 461/AD | 24/01/2024 | 0 | Resource Division | 12.17 | 0 | 0
4470 | Alipore Division | Raidighi Sub-Division | Providing FHTC including distribution system and other allied works at Zone- IX of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000085/2023-2024 | 213/AD | 20/04/2023 | 810 | JAL PRAVAHIKA PVT. LTD. | 144.19 | 0 | 30
4471 | Alipore Division | Raidighi Sub-Division | Inter connection between tubewells and Rising Main system of piped water supply at Zone - IX of Mathurapur - II Block for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. (2nd Call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000228/2023-2024 | 1385/AD | 12/07/2023 | 30 | R.P. ENTERPRISE (DAKSHINESWAR) | 13.91 | 0 | 100
4472 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - IX (Nagendrapur PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000610/2023-2024 | 241/RSD | 22/08/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 4.04 | 0 | 100
4473 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with Interconnection of Tube Well at Zone - IX (Nagendrapur PWSS) Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000613/2023-2024 | 243/RSD | 22/08/2023 | 30 | JAL PRAVAHIKA PVT. LTD. | 2.34 | 0 | 100
4474 | Alipore Division | Raidighi Sub-Division | EARNEST MONEY DEDUCTION. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002114/2019-2020 | 7761/AD | 27/02/2020 | 1827 | G.B. CONSTRUCTION & CO. | 23.06 | 0 | 5
4475 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000662/2023-2024 | 266/AD | 15/01/2024 | 0 | Resource Division | 8.13 | 0 | 0
4476 | Alipore Division | Raidighi Sub-Division | Interconnection with OHR, Rising main and distribution system for different Zone ( Zone-X, XI, XII, XIII, XIV), Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000085/2025-2026 | 2396/AD | 22/05/2025 | 60 | L.N. ENTERPRISE | 27.53 | 0 | 0
4477 | Alipore Division | Raidighi Sub-Division | Sinking of 01 (one) No. 250mm x 150mm dia. 360 mtr. deep Replacement Tubewell (Head Work Site) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter for Augmentation of Chaplarkhop W/S Scheme (Zone-XIII, Mathurapur-II Block) in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000431/2023-2024 | 1919/AD | 01/08/2023 | 30 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 19.83 | 0 | 100
4478 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Chaplarkhop Water Supply Scheme, Block - Mathurapur-II, South 24 Pgs. District under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. including Operation & Maintenance of scheme for 1 (one) year. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000512/2020-2021 | 5127/AD | 08/02/2021 | 365 | M/S. DAS BUILDERS | 53.21 | 0 | 96
4479 | Alipore Division | Raidighi Sub-Division | Extention of pipeline for Providing Functional Household Tap Connection (FHTC) and allied works at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000609/2024-2025 | 749/RSD | 03/10/2024 | 60 | P.L.CONSTRUCTION | 3.03 | 0 | 100
4480 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under "Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur", District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (New FHTC = 83 Nos.) | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000610/2024-2025 | 750/RSD | 03/10/2024 | 60 | P.L.CONSTRUCTION | 4.2 | 0 | 100
4481 | Alipore Division | Raidighi Sub-Division | Repairing of pump house 2 and approach road and plinth protection including boundary wall at Chaplarkhop W/S Scheme, modified as Zone- XIII of Mathurapur-II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001711/2023-2024 | 301/RSD | 29/09/2023 | 60 | HALDER ENTERPRISE (I) | 2.86 | 0 | 90
4482 | Alipore Division | Raidighi Sub-Division | Construction of boundary wall at Zone - XIII, Mathurapur - II Block in connection with Jal Jeevan Mission (JJM) for Mega Surface Water Based water supply scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001866/2023-2024 | 140/AD | 05/01/2024 | 30 | SUKUMAR HALDAR | 8.63 | 0 | 100
4483 | Alipore Division | Raidighi Sub-Division | Augmentation and retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to all the households at Zone-XIII, Mathurapur-II in connection with Jal Jeevan Mission (JJM) under Mega Surface Water Based Water Supply Scheme for Falta-Mathurapur, District South 24 Parganas under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001962/2022-2023 | 12716/AD | 14/03/2023 | 30 | P.L.CONSTRUCTION | 25.31 | 0 | 100
4484 | Alipore Division | Raidighi Sub-Division | Inter connection between OHR and Distrubtion system with supply of Specials, Laying HDPE pipe, Restoration at Zone - XIII water supply scheme of Mathurapur - II Block (Chaplarkhop PWSS) in connection with Jal Jeevan Mission (JJM) for Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/002230/2023-2024 | 922/AD | 08/02/2024 | 30 | SUKUMAR HALDAR | 7.81 | 0 | 0
4485 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000660/2023-2024 | 264/AD | 15/01/2024 | 0 | Resource Division | 1.69 | 0 | 0
4486 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (1500 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) and Jal Swapna for Mallik Kati Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-II South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/000323/2023-2024 | 1549/AD | 17/07/2023 | 90 | SAJAL KUMAR DAS | 131.07 | 0 | 20
4487 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 3 & 4 of Augmentation of Mallik Kati W/S Scheme, Block - Canning-II under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001665/2022-2023 | 11477/AD | 15/02/2023 | 807 | SATYAM CONSTRUCTION | 39.13 | 0 | 50
4488 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/001684/2022-2023 | 11491/AD | 15/02/2023 | 45 | M/S M.B.ENTERPRISE | 7.07 | 0 | 0
4489 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-III and Head work site to PH-IV of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002002/2022-2023 | 12816/AD | 16/03/2023 | 60 | MA KALI CONSTRUCTION | 67.36 | 0 | 50
4490 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Mallik Kati W/S Scheme, Block-Canning-II under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 3) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | ORD/002049/2022-2023 | 13049/AD | 24/03/2023 | 659 | BINAPANI ENTERPRISE | 7.1 | 0 | 100
4491 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000009/2023-2024 | 113/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
4492 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000018/2023-2024 | 223/AD | 21/04/2023 | 0 | Resource Division | 174.21 | 0 | 0
4493 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 4 CSD | RTOR000133/2023-2024 | 855/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4494 | Alipore Division | Canning Sub-division | Construction of 250 m³ capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Laying distribution system & Providing FHTC etc of Ground Water Based Augmentation of Pathankhali (Zone- III) piped water supply scheme of Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. [No. of FHTC = 1032] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000037/2023-2024 | 172/AD | 19/04/2023 | 743 | SAMSUL ENTERPRISE | 453.31 | 0 | 56
4495 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Pathankhali (Zone-III) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000138/2023-2024 | 838/AD | 26/05/2023 | 15 | M/S P. B. CONSTRUCTION | 7.5 | 0 | 0
4496 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Pathankhali (Zone - III) W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000142/2023-2024 | 278/AD | 24/04/2023 | 45 | MONDAL CONSTRUCTION (MADHYAMGRAM) | 43.98 | 0 | 0
4497 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Pathankhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001889/2022-2023 | 11550/AD | 17/02/2023 | 45 | M/S R.DUTTA & CO. | 4.29 | 0 | 99
4498 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001954/2022-2023 | 12690/AD | 14/03/2023 | 45 | PODDER ENTERPRISE | 8.92 | 0 | 0
4499 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Pathankhali W/S Scheme (Zone-III), Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001955/2022-2023 | 12691/AD | 14/03/2023 | 45 | RIYAZ ENTERPRISE | 8.6 | 0 | 0
4500 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000412/2023-2024 | 368/AD | 19/01/2024 | 0 | Resource Division | 6.36 | 0 | 0
4501 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000719/2023-2024 | 540/AD | 25/01/2024 | 0 | Resource Division | 22.19 | 0 | 0
4502 | Alipore Division | Baruipur Sub-Division | Road restoration for L03 1-Ramdhari Bazar on T01 to Harimul(WB/02/321) | AE BSD,Assistant Engineer | Junior Engineer | BILL/01671/2024-2025 | BP-2024-25-778 | 23/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 0.54 | 0 | 0
4503 | Alipore Division | Canning Sub-division | Payment for "Restoration of P.C Sen road Raibaghini to Golabari Kheyaghat(WB/02/ 564) damaged caused due to laying of water pipelines by PHED. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01192/2024-2025 | BP-2024-25-556 | 11/09/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 21 | 0 | 0
4504 | Alipore Division | Canning Sub-division | Laying of pipe line due to widening of roads from P.C. Sen Road (Raibaghini) to Golabari Kheyaghat at Banibadabelekhali Water Supply Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000030/2022-2023 | 516/AD | 25/04/2022 | 30 | M.T.C. CONSTRUCTION | 46.43 | 0 | 0
4505 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (755 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) of Augmentation of Banibadabelekhali Water Supply Scheme including one year Operation & Maintenance of scheme, Block - Canning-I South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000221/2023-2024 | 1026/AD | 13/06/2023 | 765 | M.T.C. CONSTRUCTION | 58.43 | 0 | 35
4506 | Alipore Division | Canning Sub-division | Rising main with OHR to distribution system at Banibadabelekhali W/S Scheme (Zone-II), Block-Canning-I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/000271/2022-2023 | 263/CSD | 19/05/2022 | 30 | R.P. ENTERPRISE | 1.88 | 0 | 87
4507 | Alipore Division | Canning Sub-division | Laying pipe line to connect the uncovered habitations at Banibadabelekhali Water Supply Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001061/2021-2022 | 5296/AD | 04/01/2022 | 60 | S.S. ENTERPRISE (I) | 63.28 | 0 | 81
4508 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - V of Augmentation of Banibadabelekhali W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001808/2022-2023 | 12132/AD | 01/03/2023 | 30 | KUNTAL CHOWDHURY | 19.59 | 0 | 0
4509 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Banibadabelekhali Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001945/2022-2023 | 11505/AD | 15/02/2023 | 45 | M/S. MIHIR KUMAR NASKAR | 1.75 | 0 | 95
4510 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Banibadabelekhali W/S Scheme, Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. (PH No. - 5) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002050/2022-2023 | 13050/AD | 24/03/2023 | 45 | BINAPANI ENTERPRISE | 7.09 | 0 | 0
4511 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000119/2022-2023 | 3046/AD | 28/09/2023 | 0 | Resource Division | 46.38 | 0 | 0
4512 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000729/2023-2024 | 552/AD | 25/01/2024 | 0 | Resource Division | 59.7 | 0 | 0
4513 | Alipore Division | Canning Sub-division | Payment for "Restoration of L066-Sibganj To Nol Garanbose Kheyaghat Via Maheshpur H S nd Bharatgarh Market(WB/02/318), damaged caused due to laying of water pipelines by PHED. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01191/2024-2025 | BP-2024-25-557 | 11/09/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 25.5 | 0 | 0
4514 | Alipore Division | Canning Sub-division | Restoration of Basanti Herobhanga Road from 0.00 kmp to 19.95km. block Basanti under South 24 Pags. Highway Division damaged caused due to laying of water pipe lines by PHED under Canning Sub Division of Alipore Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | BILL/01321/2024-2025 | BP-2024-25-683 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 107.4 | 0 | 0
4515 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Bharatgarh W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001193/2023-2024 | 3998/AD | 21/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 19.99 | 0 | 100
4516 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001713/2022-2023 | 11677/AD | 20/02/2023 | 810 | R.G. ENTERPRISE (I) | 7.1 | 0 | 100
4517 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 5) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001714/2022-2023 | 11678/AD | 20/02/2023 | 45 | JYOTI ENTERPRISES | 6.93 | 0 | 100
4518 | Alipore Division | Canning Sub-division | Sinking of 02 (two) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell (New) by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Tube Well No. - 4 & 5 of Augmentation of Bharatgarh W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001814/2022-2023 | 12154/AD | 01/03/2023 | 45 | B.K. ENTERPRISE. | 39.96 | 0 | 100
4519 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Bharatgarh Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001947/2022-2023 | 11506/AD | 15/02/2023 | 45 | GANGA TUBEWELL AND HARDWARE | 2.07 | 0 | 95
4520 | Alipore Division | Canning Sub-division | Additional work for retrofitting of distribution system for Providing Functional Household Tap Connection (FHTC) to additional households (550 nos.) in excess of IMIS in connection with Jal Jeevan Mission (JJM) for Bharatgarh Water Supply Scheme including one year Operation and Maintenance of scheme, Block - Basanti South 24 Pgs. District under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/001998/2022-2023 | 12812/AD | 16/03/2023 | 855 | M/S. MIHIR KUMAR NASKAR | 46.27 | 0 | 30
4521 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials from Head work site to PH-IV and Head work site to PH-V of Bharatgarh W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | ORD/002001/2022-2023 | 12815/AD | 16/03/2023 | 45 | SUNNY CONSTRUCTION | 46.05 | 0 | 0
4522 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer,1 CSD | RTOR000117/2022-2023 | 3056/AD | 28/09/2023 | 0 | Resource Division | 97.75 | 0 | 0
4523 | Alipore Division | Canning Sub-division | RESTORATION OF KOLKATA BASANTI ROAD FROM 68.00 TO 96.255 KM BLOCK CANNING I UNDER SOUTH 24 PARGANAS HIGHWAY DIVISION, DAMAGED CAUSED DUE TO LAYING OF WATER PIPE LINE BY PHED UNDER CSD | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | BILL/01320/2024-2025 | BP-2024-25-684 | 04/10/2024 | 0 | EXECUTIVE ENGNEER, 24 PGS. HIGHWAY DIVN, P.W.(ROADS) DEPTT. | 416.07 | 0 | 0
4524 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000150/2023-2024 | 695/AD | 18/05/2023 | 15 | KHOKAN MONDAL | 15.59 | 0 | 0
4525 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 2 of Sonakhali (Zone-IV) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000284/2025-2026 | 689/CSD | 26/05/2025 | 30 | KIRON CONSTRUCTION | 3.42 | 0 | 0
4526 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-IV), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000315/2024-2025 | 2696/AD | 24/06/2024 | 45 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0
4527 | Alipore Division | Canning Sub-division | Additional laying of pipeline at Sonakhali (Zone-IV) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000486/2024-2025 | 3545/AD | 02/09/2024 | 105 | RIVER BENZ CONSTRUCTION | 25.36 | 0 | 75
4528 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Sonakhali W/S Scheme (Zone-IV), Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. (Tube well no. - III) (2nd Call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000745/2024-2025 | 4412/AD | 05/11/2024 | 30 | TRIMURTI ENTERPRISE | 19.95 | 0 | 0
4529 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - IV) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001795/2022-2023 | 12130/AD | 01/03/2023 | 30 | SAMIR GIRI | 19.56 | 0 | 0
4530 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-IV) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001842/2022-2023 | 11540/AD | 16/02/2023 | 45 | TECH VISION | 3.08 | 0 | 0
4531 | Alipore Division | Canning Sub-division | onstruction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-IV) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001986/2022-2023 | 12647/AD | 13/03/2023 | 45 | RINAS INFRASTRUCTURE | 7.08 | 0 | 0
4532 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
4533 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000038/2023-2024 | 242/AD | 24/04/2023 | 0 | Resource Division | 38.11 | 0 | 0
4534 | Alipore Division | Canning Sub-division | Construction of OHR (150 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-III), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018434] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/000034/2023-2024 | 275/AD | 24/04/2023 | 300 | I.S. ENTERPRISE | 325.97 | 0 | 35
4535 | Alipore Division | Canning Sub-division | Sinking of 01 (one) no. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-III), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - 1) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001194/2023-2024 | 3999/AD | 21/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 22.45 | 0 | 0
4536 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | ORD/001926/2022-2023 | 11799/AD | 22/02/2023 | 45 | M/S R.DUTTA & CO. | 3.18 | 0 | 0
4537 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000408/2023-2024 | 362/AD | 19/01/2024 | 0 | Resource Division | 7.37 | 0 | 0
4538 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 3 CSD | RTOR000722/2023-2024 | 544/AD | 25/01/2024 | 0 | Resource Division | 40.24 | 0 | 0
4539 | Alipore Division | Baruipur Sub-Division | Road restoration for 1) Dakhshin Kalyanpur Panchanantala to Uttar Sashan Santali Sangha (Barikpara, Gazipara, Kalyanpur Uttar Railgate, Pashchim Madhabpur) 2) Repairing of Road from Sikharbali- I GP to Dakshin Kalyanpur at Sikhardali-1 GP under Baruipur PS | AE BSD,Assistant Engineer | Junior Engineer | BILL/01731/2024-2025 | BP-2024-25-795 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 5.86 | 0 | 0
4540 | Alipore Division | Canning Sub-division | Laying of Distribution System, Providing Functional Household Tap Connection (FHTC) etc. of Ground Water Based Augmentation Piped Water Supply Scheme for Narayangar (Part-B), Block-Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1542] (TSM/018335) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000083/2023-2024 | 196/AD | 19/04/2023 | 90 | EQUIPMENTS & SPARES AGENCIES | 255.63 | 0 | 85
4541 | Alipore Division | Canning Sub-division | Sinking of 03 (three) Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub Division of Alipore Division, PHE Dte. (2nd call) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000135/2023-2024 | 690/AD | 18/05/2023 | 60 | SNEHA CONSTRUCTION | 58.66 | 0 | 95
4542 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (5.4m x 3.6m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-I] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000466/2023-2024 | 1928/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.35 | 0 | 98
4543 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-II] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000467/2023-2024 | 1929/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.09 | 0 | 98
4544 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Narayangar (Part-B) W/S Scheme, Block - Canning-I under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House-III] | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000468/2023-2024 | 1930/AD | 01/08/2023 | 45 | A.R.CONSTRUCTION | 7.09 | 0 | 98
4545 | Alipore Division | Canning Sub-division | Construction of 350 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including Geo- Technical investigation, foundation, pipeline connection and cost of pipes, specials etc. for Augmentation of Narayangarh piped water supply scheme of Canning-I Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/15961) | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/000569/2024-2025 | 3979/AD | 27/09/2024 | 540 | GHOSH ENTERPRISE (II) | 138.78 | 0 | 25
4546 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Narayangar (Part-B) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Canning-I Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/001846/2022-2023 | 11813/AD | 23/02/2023 | 45 | TECH VISION | 4.6 | 0 | 0
4547 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Narayangar (Part-B) W/S Scheme, Block-Canning- I under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002019/2022-2023 | 12925/AD | 16/03/2023 | 45 | SWASTIK CONSTRUCTION | 22.8 | 0 | 81
4548 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
4549 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000008/2023-2024 | 114/AD | 13/04/2023 | 0 | Resource Division | 0.34 | 0 | 0
4550 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000064/2023-2024 | 267/AD | 24/04/2023 | 0 | Resource Division | 27.5 | 0 | 0
4551 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer ,Assistant Engineer, Canning sub division | Junior Engineer,Junior Engineer, 2 CSD | RTOR000134/2023-2024 | 849/AD | 27/05/2023 | 0 | Resource Division | 1.72 | 0 | 0
4552 | Alipore Division | Kakdwip Sub-Division | Construction of 60 cum. Over Head Reservoir (OHR), (15 mtr. Staging Height) along with Laying distribution system, Rising Main, construction of 1 no. 5.40m x 3.60m. Pump House, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Durganagar Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000022/2023-2024 | 97/AD | 11/04/2023 | 1199 | ADITYA HAZRA | 108.12 | 0 | 30
4553 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Durganagar W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002048/2023-2024 | 509/AD | 25/01/2024 | 406 | SUGANDHIT SUNDARBAN ENTERPRISE PVT. LTD. | 27.8 | 0 | 80
4554 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002071/2022-2023 | 13221/AD | 31/03/2023 | 30 | G.M. ENTERPRISE | 15.94 | 0 | 100
4555 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002072/2022-2023 | 13222/AD | 31/03/2023 | 30 | KHOKAN MONDAL | 15.16 | 0 | 100
4556 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002073/2022-2023 | 13223/AD | 31/03/2023 | 30 | BHUNIA BUILDERS | 7.25 | 0 | 82
4557 | Alipore Division | Kakdwip Sub-Division | Laying distribution system providing FHTC for Durganagar W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-E) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002074/2022-2023 | 13224/AD | 31/03/2023 | 30 | BHOLANATH CONSTRUCTION | 8.23 | 0 | 50
4558 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Durganagar, Iswaripur, Ganeshnagar Zone-I, Ganeshnagar Zone-II, Narayanpur Zone- I & II PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002118/2023-2024 | 934/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.94 | 0 | 90
4559 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000128/2023-2024 | 664/AD | 17/05/2023 | 0 | Resource Division | 1.65 | 0 | 0
4560 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000468/2023-2024 | 4775/AD | 19/12/2023 | 0 | Resource Division | 0.71 | 0 | 0
4561 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000786/2023-2024 | 630/AD | 30/01/2024 | 0 | Resource Division | 1.16 | 0 | 0
4562 | Alipore Division | Raidighi Sub-Division | Supply and delivery at site of different dia. Specials in connection with laying distribution system of piped water supply at Zone - II (Debipur PWSS) Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/000609/2023-2024 | 240/RSD | 22/08/2023 | 30 | DIPTI ENTERPRISE | 0.96 | 0 | 99
4563 | Alipore Division | Raidighi Sub-Division | Parallel distribution pipeline to provide FHTC at Debipur moza under Zone-II of Mathurapur-I block, under Surface water based water supply scheme Falta- Mathurapur of Raidighi Sub-Division under Alipore Division, PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001135/2022-2023 | 600/RSD | 23/12/2022 | 30 | SANKAR HALDER | 4.76 | 0 | 99
4564 | Alipore Division | Raidighi Sub-Division | Providing Functional Household Tap Connection (FHTC) to all the households in Debipur piped water supply scheme ( Mathurapur-I, Zone-II) including Operation and Maintenance of scheme for 1 (one) year , District South 24 Parganas, Block - Mathurapur-I under Raidighi Sub-Division of Alipore Division, P.H.E.Dte. (Phase-I) (2nd call) | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001197/2021-2022 | 5724/AD | 31/01/2022 | 365 | M/S. JHARNA ENTERPRISE | 101.84 | 0 | 85
4565 | Alipore Division | Raidighi Sub-Division | Protection and other ancillary work (Node No. 2-30, 28-26, 25-23, 21-22, 17-19) for laying distribution system and providing FHTC at Zone - II Block of Mathurapur - I Block in connection with Jal Jeevan Mission (JJM) under under Mega surface water based water supply scheme-Falta Mathurapur under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/001799/2022-2023 | 930/RSD | 10/03/2023 | 30 | DIPTI ENTERPRISE | 4.27 | 0 | 99
4566 | Alipore Division | Raidighi Sub-Division | Construction of 500 cum capacity 20 M. staging height RCC Over Head Water Reservoir as per departmental drawing & specification incl. RCC Bored Pile & Pile Cap upto pedestal at Mathurapur - I Block (Zn. - II) for Mega Surface Water Based Water Supply Scheme of Falta - Mathurapur South 24 Pgs. under Raidighi Sub Divn. of Alipore Division, PHE dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | ORD/002025/2019-2020 | 7721/AD | 26/02/2020 | 1827 | G.B. CONSTRUCTION & CO. | 64.12 | 0 | 75
4567 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000033/2022-2023 | 3450/AD | 25/07/2022 | 0 | Resource Division | 45.51 | 0 | 0
4568 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 3, Raidghi Sub Division | RTOR000035/2022-2023 | 3588/AD | 29/07/2022 | 0 | Resource Division | 3.28 | 0 | 0
4569 | Alipore Division | Baruipur Sub-Division | Road restoration of Nolgora to Sonartikari | AE BSD |  | BILL/01782/2024-2025 | BP-2024-25-807 | 25/10/2024 | 0 | W.B.S.R.D.A., SOUTH TWENTY FOUR PARGANAS DIVISION | 14.42 | 0 | 0
4570 | Alipore Division | Canning Sub-division | Renovation and retrofitting of Pump House No. 1 of Augmentation of Kachukhali W/S Scheme, under Gosaba Block of Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000189/2025-2026 | 629/CSD | 21/05/2025 | 30 | HALDER & CO. | 2.93 | 0 | 100
4571 | Alipore Division | Canning Sub-division | Laying additional pipeline and other allied works at Augmentation of Kachukhali W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000282/2024-2025 | 2639/AD | 20/06/2024 | 315 | MS SINHA ROY & CO | 39.38 | 0 | 80
4572 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000385/2023-2024 | 1574/AD | 17/07/2023 | 30 | MAA SANTOSHI ENTERPRISE | 21.96 | 0 | 0
4573 | Alipore Division | Canning Sub-division | Construction of OHR (200 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the KACHUKHALI, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000630/2023-2024 | 2434/AD | 22/08/2023 | 300 | UNITED BUILDERS | 588.5 | 0 | 70
4574 | Alipore Division | Canning Sub-division | Sinking of 200mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter at Augmentation of Kachukhali W/S Scheme, Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. - II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001190/2023-2024 | 3995/AD | 21/11/2023 | 30 | MEHAI TECHNOLOGY LIMITED | 20.46 | 0 | 0
4575 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 for Ground Water Based at Kachukhali Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001237/2024-2025 | 5218/AD | 16/12/2024 | 30 | UNITED BUILDERS | 6.91 | 0 | 0
4576 | Alipore Division | Canning Sub-division | Construction of boundary wall at Head Work Site for Ground Water Based at Kachukhali Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001238/2024-2025 | 5219/AD | 16/12/2024 | 40 | NITYANANDA MONDAL | 32.8 | 0 | 0
4577 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000063/2023-2024 | 541/AD | 25/01/2024 | 0 | Resource Division | 26.47 | 0 | 0
4578 | Alipore Division | Diamond Harbour Sub-Division | Payment against "Restoration of Hatuganj Basuldanga Road (MDR) 0Km-12.2Km), under Diamond Harbour Highway Division, PWD damaged caused due to laying of water pipe lines by PHED under Raidighi Sub Division, PHE Dte. in the district of South 24 Pgs" vide Memo no. 264(W)/618G, Dt. 19.02.2024 of SE, Southern highway Circle P.W.(Roads) Dte. & 9nos | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | BILL/01577/2024-2025 | BP-2024-25-891 | 19/11/2024 | 0 | EXECUTIVE ENGNEER, DIAMOND HARBOUR DIVN, P.W.(ROADS) DTE. | 54.41 | 0 | 0
4579 | Alipore Division | Diamond Harbour Sub-Division | Erection of 20 nos scheme information display board at different headwork site of falta,Diamond Harbour I ,Diamond Harbour II and Kulpi Block under Diamond Harbour Sub Division of Alipore Division PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000065/2025-2026 | 35/DHSD | 08/04/2025 | 7 | SADHURHAT CO OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 3.75 | 0 | 100
4580 | Alipore Division | Diamond Harbour Sub-Division | Construction of pipe carrying structure with laying of different dia. M.S. distribution line for crossing of 10 nos. culvert with allied works at Lakshmipur village road, at Netra stations to Panchagram road and Netra stations to Usthi road under Augmentation scheme of Diamond Harbour-I Zone-II and Zone-VIII within Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur District - South-24 Parganas under Diamond Harbour Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000097/2025-2026 | 2526/AD | 30/05/2025 | 60 | SRIJON ENTERPRISE | 93.95 | 0 | 100
4581 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Netra under Zone- II of Diamond Harbour-I Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. (2nd call) | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000130/2023-2024 | 1790/AD | 26/07/2023 | 30 | MAYA CONSTRUCTION | 25.02 | 0 | 0
4582 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 cum capacity of OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone- II at Netra of Diamond Harbour- I block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC=6323] . | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | ORD/000740/2023-2024 | 2908/AD | 20/09/2023 | 622 | TARUN ENTERPRISE | 1223.41 | 0 | 55
4583 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000231/2023-2024 | 2192/AD | 10/08/2023 | 0 | Resource Division | 37.76 | 0 | 0
4584 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000666/2023-2024 | 419/AD | 22/01/2024 | 0 | Resource Division | 315.41 | 0 | 0
4585 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 2 DHSD | RTOR000891/2023-2024 | 745/AD | 03/02/2024 | 0 | Resource Division | 38.95 | 0 | 0
4586 | Alipore Division | Diamond Harbour Sub-Division | Construction of Chlorination Room at OHR Site of Jamalpur Water Supply Scheme, Block: Budge Budge-I under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000060/2022-2023 | 841/AD | 13/05/2022 | 30 | BANGA NIRMAN | 5.15 | 0 | 98
4587 | Alipore Division | Diamond Harbour Sub-Division | Construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per departmental design, drawing and specification including R.C.C. Bored Pile & Pile Cap upto pedestal at JAMALPUR Water Supply Scheme, Block - Budge-Budge-I under Diamond Harbour Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000069/2021-2022 | 834/AD | 18/06/2021 | 365 | M/S. S.S. ENTERPRISE | 63.1 | 0 | 5
4588 | Alipore Division | Diamond Harbour Sub-Division | Development and strengthening of earthen approach road from Jamalpur Health Centre to proposed OHR site of Jamalpur W/S Scheme and allied works in Budge Budge-I Block under Diamond Harbour Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Diamond Harbour sub division |  | ORD/000215/2022-2023 | 3002/AD | 11/07/2022 | 15 | M/S. S.S. ENTERPRISE | 10.89 | 0 | 95
4589 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 at Ground Water Based Augmentation Piped Water Supply Scheme of Goranbose W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000747/2024-2025 | 4419/AD | 05/11/2024 | 30 | S.S. CONSTRUCTION | 29.61 | 0 | 0
4590 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 at Ground Water Based Augmentation Piped Water Supply Scheme of Goranbose W/S Scheme Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/000748/2024-2025 | 4420/AD | 05/11/2024 | 30 | MODERN CONSTRUCTION | 20.83 | 0 | 0
4591 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Augmentation of Goranbose W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. (PH - 4) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/001711/2022-2023 | 11675/AD | 20/02/2023 | 720 | A 8 T CONSTRUCTION | 7.09 | 0 | 100
4592 | Alipore Division | Canning Sub-division | Construction of 600 m³ capacity R.C.C OHR (based on Departmental Design &. Drawing) with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. of Goranbose piped water supply scheme of Basanti Block under Canning Sub- Division of Alipore Division, PHE Dte. (SM/05716) | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | ORD/002095/2024-2025 | 351/AD | 28/01/2025 | 300 | MS SINHA ROY & CO | 181.43 | 0 | 0
4593 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer,1 CSD | RTOR000399/2023-2024 | 357/AD | 19/01/2024 | 0 | Resource Division | 3.82 | 0 | 0
4594 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Patibania W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000161/2024-2025 | 2512/AD | 15/06/2024 | 270 | DEV AND COMPANY | 40.82 | 0 | 50
4595 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Patibania W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000219/2024-2025 | 2602/AD | 19/06/2024 | 45 | M/S MALI ENTERPRISE | 28.95 | 0 | 0
4596 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Patibania W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000220/2024-2025 | 2603/AD | 19/06/2024 | 30 | KRISHNA CONSTRUCTION | 9.56 | 0 | 0
4597 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Patibania W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000226/2024-2025 | 2525/AD | 18/06/2024 | 30 | RIYANA ENTERPRISE | 9.66 | 0 | 0
4598 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th tubewell Site for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000227/2024-2025 | 2557/AD | 18/06/2024 | 45 | M/S MALI ENTERPRISE | 5.62 | 0 | 0
4599 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. for Patibania W/S Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. [Part-I] (SM/18395) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000340/2024-2025 | 2772/AD | 28/06/2024 | 60 | PROJECT INDIA | 99.02 | 0 | 0
4600 | Alipore Division | Kakdwip Sub-Division | Construction of 350 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) including design & drawing of pile foundation & pile cap after soil investigation along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including O & M for 1 year after completion of FHTC works for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000359/2023-2024 | 1558/AD | 17/07/2023 | 838 | SYN DEVELOPERS PVT. LTD. | 437.8 | 0 | 15
4601 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Patibania W/S scheme, Block - Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18395) (2nd Call) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000510/2024-2025 | 4570/AD | 14/11/2024 | 30 | AZAD RAHAMAN LASKAR | 8.9 | 0 | 0
4602 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000566/2023-2024 | 1806/AD | 26/07/2023 | 30 | ABONTICA ENTERPRISE | 17.93 | 0 | 0
4603 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000572/2023-2024 | 1809/AD | 26/07/2023 | 45 | AQUATECH ENGINEER | 36.71 | 0 | 80
4604 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Patibania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000578/2023-2024 | 2265/AD | 14/08/2023 | 45 | SUPRITI ENTERPRISE | 63.53 | 0 | 20
4605 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Patabania Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) [No. of FHTC =950] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000716/2023-2024 | 2661/AD | 04/09/2023 | 120 | PROJECT INDIA | 161.87 | 0 | 40
4606 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Nadabhanga, Patibania, Dakshin Durgapur, Rajnagar, Budhakhali Zone - I (Part - I & II) PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002128/2023-2024 | 935/KSD | 19/12/2023 | 5 | M/S B. ENTERPRISE | 0.95 | 0 | 90
4607 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Patibania PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002625/2023-2024 | 882/KSD | 15/12/2023 | 10 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
4608 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000130/2023-2024 | 666/AD | 17/05/2023 | 0 | Resource Division | 15.23 | 0 | 0
4609 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000470/2023-2024 | 4777/AD | 19/12/2023 | 0 | Resource Division | 29.79 | 0 | 0
4610 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000841/2023-2024 | 634/AD | 30/01/2024 | 0 | Resource Division | 7.87 | 0 | 0
4611 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000976/2023-2024 | 1769/AD | 27/03/2024 | 0 | Resource Division | 28.97 | 0 | 0
4612 | Alipore Division | Raidighi Sub-Division | Construction of 900 M3 capacity 20 M. staging height R.C.C. Over Head Water Reservoir, Providing FHTC including distribution system, boundary wall and other allied works at Zone- II of Mathurapur -II Block for ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ in connection with Jal Jeevan Mission (JJM) under Raidighi Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/000480/2023-2024 | 3670/AD | 01/11/2023 | 900 | M/S GHOSH & CO. | 1045.49 | 0 | 28
4613 | Alipore Division | Raidighi Sub-Division | Preparation of Design (Pile with Pile Cap), Drawing for foundation of 900 m3 capacity Over Head Reservoir as per latest requisite I.S. Codes at Zone-II, Mathurapur- II Block under JJM as per direction and satisfaction of the Engineer In-Charge under Raidighi Sub-Division of Alipore Division PHE Dte. | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | ORD/001712/2023-2024 | 421/RSD | 02/01/2024 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4614 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000007/2024-2025 | 5162/AD | 12/12/2024 | 0 | Resource Division | 30.8 | 0 | 0
4615 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000246/2023-2024 | 3103/AD | 28/09/2023 | 0 | Resource Division | 43.57 | 0 | 0
4616 | Alipore Division | Raidighi Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Raidighi sub division | Junior Engineer 2, Raidghi Sub Division | RTOR000657/2023-2024 | 261/AD | 15/01/2024 | 0 | Resource Division | 8.95 | 0 | 0
4617 | Alipore Division |  | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections, pile and pile cap for OHR etc. at Sridharnagar (Zone-I & II) PWSS, Block - Patharpratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/14986) |  |  | ORD/000362/2024-2025 | 2891/AD | 09/07/2024 | 90 | TANMAY ROY CHOWDHURY | 261.1 | 0 | 30
4618 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000319/2023-2024 | 3128/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4619 | Alipore Division |  | Material Requisition To Resource Division |  |  | RTOR000777/2023-2024 | 611/AD | 29/01/2024 | 0 | Resource Division | 9.2 | 0 | 0
4620 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Brojaballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-B) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000376/2023-2024 | 3501/AD | 16/10/2023 | 60 | PIJUSH KANTI TRIPATHI | 77.26 | 0 | 20
4621 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connection etc. at Brojaballavpur (Zone-I &II) W/S Scheme, Block -Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-I) (SM/18718) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000435/2024-2025 | 3074/AD | 25/07/2024 | 546 | SHYAM DEVELOPER | 60.73 | 0 | 0
4622 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Brojaballavpur (Zone-I & II)W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000552/2023-2024 | 2234/AD | 11/08/2023 | 45 | KANAN CONSTRUCTION | 49.16 | 0 | 90
4623 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Brojaballavpur (Zone - I & II) W/S Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) | Assistant Engineer, Kakdwip Sub Division |  | ORD/000553/2023-2024 | 2235/AD | 11/08/2023 | 45 | KANAN CONSTRUCTION | 49.14 | 0 | 90
4624 | Alipore Division | Kakdwip Sub-Division | Construction of 100 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Brojoballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) (Part-A) [No. of FHTC = 500] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000564/2023-2024 | 2256/AD | 14/08/2023 | 1171 | M/S B.N.ENTERPRISE | 249.59 | 0 | 35
4625 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Brojaballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-B) [No. of FHTC = 1145] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000565/2023-2024 | 2257/AD | 14/08/2023 | 748 | TANMAY ROY CHOWDHURY | 217.83 | 0 | 20
4626 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (Brojaballavpur PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division |  | ORD/000640/2023-2024 | 2272/AD | 14/08/2023 | 45 | INDRANIL DUTTA & ASSOCIATES | 9.35 | 0 | 100
4627 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of foundation after soil investagation including O & M of Laying distribution, Rising Main & FHTC for 1 year after completion of FHTC works for Brojoballavpur (Zone - I & II) Water Supply Scheme, Block - Pathar Pratima for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) (Part-A) [No. of FHTC = 400] | Assistant Engineer, Kakdwip Sub Division |  | ORD/000790/2023-2024 | 3734/AD | 03/11/2023 | 901 | M/S B.N.ENTERPRISES | 266.67 | 0 | 41
4628 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Kshetramohanpur Zone - I & II, Brojoballavpur Zone - I & II PWSS under JJM at Pathar Pratima Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division |  | ORD/002112/2023-2024 | 932/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
4629 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000110/2023-2024 | 646/AD | 17/05/2023 | 0 | Resource Division | 14.14 | 0 | 0
4630 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000486/2023-2024 | 4754/AD | 19/12/2023 | 0 | Resource Division | 43.79 | 0 | 0
4631 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division |  | RTOR000768/2023-2024 | 602/AD | 29/01/2024 | 0 | Resource Division | 2.54 | 0 | 0
4632 | Alipore Division | Kakdwip Sub-Division | Construction of Household Tap Platform at different households, fitting fixing supplying of different dia. specials for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000146/2024-2025 | 2484/AD | 14/06/2024 | 450 | M. MUKHERJEE | 73.02 | 0 | 0
4633 | Alipore Division | Kakdwip Sub-Division | Laying distribution system for providing FHTC for Augmentation of Mahishamari (Zone - I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (Part-A) (SM/13872) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000428/2024-2025 | 3258/AD | 06/08/2024 | 360 | M. MUKHERJEE | 150.27 | 0 | 0
4634 | Alipore Division | Kakdwip Sub-Division | Surging of 01 No. Tubewell for augmentation of Mahishamari (Zone - I & II) W/S Scheme under JJM, Block - Sagar under Kakdwip Sub - Division under Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000529/2023-2024 | 353/KSD | 09/08/2023 | 25 | S.K.GOLUI | 2.18 | 0 | 100
4635 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mahishmari (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000969/2023-2024 | 307/KSD | 20/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4636 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Mahishmari (Zone-I & II) PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. (Zone-II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/000973/2023-2024 | 322/KSD | 27/07/2023 | 4 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.49 | 0 | 100
4637 | Alipore Division | Kakdwip Sub-Division | Conducting route survey, design distribution network and preparation & submission of DPR for each of different new water supply scheme / each Augmentation water supply scheme (MAHISMARI(ZONE- I & II) PWSS) including Functional Household Tap Connection (FHTC) for implementation of JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001060/2022-2023 | 4651/AD | 06/09/2022 | 45 | VOYAGER | 6.89 | 0 | 100
4638 | Alipore Division | Kakdwip Sub-Division | inking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Augmentation of Mahishamari (Zone-I & II) W/S Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001277/2022-2023 | 9589/AD | 03/01/2023 | 698 | SARADA CONSTRUCTION | 49.18 | 0 | 50
4639 | Alipore Division | Kakdwip Sub-Division | Allied works for pile and pile cap portion regarding the Construction of 150 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) as per departmental design, drawing & specification including R.C.C. Bored pile & pile cap upto pedestal for Augmentation of Mahishamari (Zone-I) W/S Scheme, South 24 Parganas, Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001474/2023-2024 | 4684/AD | 18/12/2023 | 30 | M. MUKHERJEE | 39.65 | 0 | 100
4640 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Mahishamari (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-II) [No. of FHTC = 80] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001862/2022-2023 | 12415/AD | 09/03/2023 | 1050 | M. MUKHERJEE | 252.54 | 0 | 88
4641 | Alipore Division | Kakdwip Sub-Division | Construction of 150 cum. Over Head Reservoir (OHR) (20 mtr. Staging Height) along with 1 no. Pump House, Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Augmentation of Mahishamari (Zone-I & II) Water Supply Scheme, Block - Sagar for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Zone-I) [No. of FHTC = 80] | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001863/2022-2023 | 12416/AD | 09/03/2023 | 1052 | M. MUKHERJEE | 234.69 | 0 | 70
4642 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site for Augmentation of Mahishamari (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - II) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001988/2023-2024 | 507/AD | 25/01/2024 | 45 | M/S SWAPAN KUMAR PRADHAN | 33.09 | 0 | 0
4643 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site for Augmentation of Mahishamari (Zone - I and II) W/S scheme, Block - Sagar under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (For Zone - I) | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/001989/2023-2024 | 508/AD | 25/01/2024 | 30 | ANANDA MAITY | 11.74 | 0 | 100
4644 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Mahishamari Zone - I & II, Sumatinagar Zone - I & II PWSS under JJM at Sagar Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | ORD/002153/2023-2024 | 948/KSD | 19/12/2023 | 5 | BIMALENDU GIRI | 0.81 | 0 | 100
4645 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000338/2023-2024 | 3153/AD | 29/09/2023 | 0 | Resource Division | 0.3 | 0 | 0
4646 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000515/2023-2024 | 4833/AD | 20/12/2023 | 0 | Resource Division | 56.08 | 0 | 0
4647 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000529/2023-2024 | 11/AD | 02/01/2024 | 0 | Resource Division | 0.95 | 0 | 0
4648 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000686/2023-2024 | 456/AD | 24/01/2024 | 0 | Resource Division | 5.38 | 0 | 0
4649 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer -I,Assistant Engineer, Kakdwip Sub Division | Junior Engineer,Juniour Engineer_2, Kakdwip Sub Division | RTOR000972/2023-2024 | 1765/AD | 27/03/2024 | 0 | Resource Division | 8.34 | 0 | 0
4650 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 9 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000024/2025-2026 | 2010/AD | 28/04/2025 | 30 | SUBHASISH SAU | 12.97 | 0 | 0
4651 | Alipore Division | Canning Sub-division | Laying pipe line from C.W.R. - 2 to O.H.R. point of Augmentation of Ground Water Based at Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000092/2025-2026 | 2521/AD | 30/05/2025 | 45 | S.P. CONSTRUCTION (I) | 25.17 | 0 | 0
4652 | Alipore Division | Canning Sub-division | Construction of 02 (two) nos. 100 Cum. Clear Water Reservoir (CWR) at Gosaba (Zone-II) Water Supply Scheme of Gosaba Block under Canning Sub- Division of Alipore Division, PHE Dte. (2nd Call) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000299/2024-2025 | 2679AD | 24/06/2024 | 311 | SWASTIK CONSTRUCTION | 67.49 | 0 | 40
4653 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No. I) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000507/2023-2024 | 2062/AD | 07/08/2023 | 544 | S.B. ENTERPRISE | 8.64 | 0 | 100
4654 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-II) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000508/2023-2024 | 2063/AD | 07/08/2023 | 45 | S.B. ENTERPRISE | 8.64 | 0 | 0
4655 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Agumentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.III) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000509/2023-2024 | 2064/AD | 07/08/2023 | 45 | M/S. GANGA ENTERPRISE | 8.64 | 0 | 0
4656 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-IV) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000510/2023-2024 | 2065/AD | 07/08/2023 | 45 | M/S. GANGA ENTERPRISE | 8.63 | 0 | 0
4657 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-V) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000511/2023-2024 | 2066/AD | 07/08/2023 | 360 | JYOTI ENTERPRISES | 8.64 | 0 | 100
4658 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-VI) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000512/2023-2024 | 2067/AD | 07/08/2023 | 360 | JYOTI ENTERPRISES | 8.64 | 0 | 100
4659 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.VII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000513/2023-2024 | 2068/AD | 07/08/2023 | 513 | SUPER CONSTRUCTION | 8.59 | 0 | 100
4660 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Agumentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No.VIII] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000514/2023-2024 | 2069/AD | 07/08/2023 | 45 | SUPER CONSTRUCTION | 8.59 | 0 | 0
4661 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-IX) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000515/2023-2024 | 2070/AD | 07/08/2023 | 45 | A.M.ENTERPRISE (I) | 8.64 | 0 | 0
4662 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-X) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000516/2023-2024 | 2071/AD | 07/08/2023 | 452 | A.M.ENTERPRISE (I) | 8.64 | 0 | 100
4663 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-XI) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000517/2023-2024 | 2072/AD | 07/08/2023 | 45 | B.S.ENTERPRISE | 8.62 | 0 | 100
4664 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.XII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000518/2023-2024 | 2073/AD | 07/08/2023 | 45 | RAJLAKSHMI ENTERPRISE | 8.64 | 0 | 0
4665 | Alipore Division | Canning Sub-division | Construction of 01 (one) nos. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site Augmentation of Gosaba (Zone-II) W/S Scheme, Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. (Pump House No.-XIII) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000519/2023-2024 | 2074/AD | 07/08/2023 | 45 | KAMALA ENTERPRISE (I) | 8.64 | 0 | 0
4666 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 1, 2, 3) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000546/2023-2024 | 2078/AD | 07/08/2023 | 60 | DOLY CONSTRUCTION | 67.35 | 0 | 0
4667 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 4, 5, 6) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000547/2023-2024 | 2079/AD | 07/08/2023 | 937 | SUNDARBAN CONSTRUCTION | 67.23 | 0 | 90
4668 | Alipore Division | Canning Sub-division | Sinking of 03 (three) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 7, 8, 9) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000548/2023-2024 | 2080/AD | 07/08/2023 | 756 | SUNDARBAN CONSTRUCTION | 67.23 | 0 | 100
4669 | Alipore Division | Canning Sub-division | Sinking of 04 (four) nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub Division of Alipore Division, PHE Dte. (Tubewell No. 10, 11, 12, 13) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000549/2023-2024 | 2081/AD | 07/08/2023 | 90 | SETABUR RAHAMAN | 89.78 | 0 | 0
4670 | Alipore Division | Canning Sub-division | Construction of OHR (250 Cum), Construction of OHR (600 Cum), Laying of Distribution System, Providing Functional Household Tap Connection etc. of Ground Water based Augmentation Piped Water Supply Scheme for the Gosaba (Zone-II), Block-Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. [TSM/018435] | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000563/2023-2024 | 2255/AD | 14/08/2023 | 745 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT. LTD.) | 2050.6 | 0 | 25
4671 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Gosaba (Zone-II) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Gosaba Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000615/2023-2024 | 2270/AD | 14/08/2023 | 45 | M/S R.DUTTA & CO. | 35.42 | 0 | 98
4672 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 2 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000676/2024-2025 | 4249/AD | 26/10/2024 | 30 | S.B. ENTERPRISE | 14.29 | 0 | 0
4673 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 1 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000677/2024-2025 | 4250/AD | 26/10/2024 | 30 | NEPAL CHANDRA PRADHAN | 11.97 | 0 | 0
4674 | Alipore Division | Canning Sub-division | Construction of boundary wall at CWR for Augmentation of Ground water Based at Gosaba (Zone- II)Piped Water Supply Scheme Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000742/2024-2025 | 4399/AD | 05/11/2024 | 45 | SWASTIK CONSTRUCTION | 37.17 | 0 | 0
4675 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 12 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000767/2024-2025 | 4468/AD | 11/11/2024 | 30 | A 8 T CONSTRUCTION | 13.68 | 0 | 0
4676 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 11 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000768/2024-2025 | 4469/AD | 11/11/2024 | 30 | BANGA NIRMAN | 13.35 | 0 | 0
4677 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 10 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000769/2024-2025 | 4470/AD | 11/11/2024 | 30 | BANGA NIRMAN | 13.35 | 0 | 0
4678 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 7 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000770/2024-2025 | 4471/AD | 11/11/2024 | 30 | SUBHO CONSTRUCTION | 14.16 | 0 | 0
4679 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 5 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/000771/2024-2025 | 4472/AD | 11/11/2024 | 30 | CHATTERJEE ENTERPRISES | 13.85 | 0 | 0
4680 | Alipore Division | Canning Sub-division | Laying pipe line at the Augmentation of Gosaba W/S Scheme (Zone-II), Block - Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001032/2024-2025 | 4942/AD | 03/12/2024 | 90 | SURYA ENTERPRISE | 27.22 | 0 | 100
4681 | Alipore Division | Canning Sub-division | Survey, Soil Investigation/Geo-technical survey, preparation of design and drawing, making service corridor for installation of 315 mm (Nominal OD) HDPE Pipe by HDD method under the river bed of Durga Doani River at Gosaba Island for Gosaba Zone -II WS Scheme. The works include transportation of machineries and mobilization, supply of 315 mm (Nominal OD) HDPE pipe (PE80, PN10) including laying / installation, pressure testing of laid pipe, hire charges of all machine and tools, expenses of consumables (Bentonite /Polymer, Diesel, hydraulic machine, water etc.) including transportation all type of man power, HDD operation cost, Electric / Lighting arrangement at site, insurance for staff, labour, materials and machine including GST @18%, cess @1% and riverine @22.50% and all other charges including site clearance. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001033/2023-2024 | 3188/AD | 03/10/2023 | 75 | ATINDRA CONSTRUCTION PRIVATE LIMITED | 449.89 | 0 | 100
4682 | Alipore Division | Canning Sub-division | Construction of boundary wall at Pump House No. - 8 for Augmentation of Ground Water Based Gosaba (Zone-II) Piped Water Supply Scheme, Block - Gosaba under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001243/2024-2025 | 5241/AD | 17/12/2024 | 30 | ASHIS ENTERPRISE | 14.16 | 0 | 0
4683 | Alipore Division | Canning Sub-division | Hiring Motor launch for Canning Sub Division under Alipore Division,PHE Dte. in connection with execution and maintenance of different piped water supply schemes at different island in the district of South 24 Parganas. (for 365 days) | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001336/2024-2025 | 5442/AD | 26/12/2024 | 365 | RAJKUMAR MANNA | 40.7 | 0 | 0
4684 | Alipore Division | Canning Sub-division | Laying DI pipe line and other allied works at Kalir Khal of Pond Based Surface Water Supply Scheme of Block- Gosaba under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | ORD/001929/2023-2024 | 1173/CSD | 06/11/2023 | 10 | MOHANA ENTERPRISES | 0.97 | 0 | 100
4685 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000407/2023-2024 | 361/AD | 19/01/2024 | 0 | Resource Division | 60.32 | 0 | 0
4686 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 3 CSD | RTOR000721/2023-2024 | 543/AD | 25/01/2024 | 0 | Resource Division | 1057.58 | 0 | 0
4687 | Alipore Division | Canning Sub-division | Repairing & renovation of Pump House no. - 1 of Sonakhali (Zone-III) W/S Scheme Block - Basanti under Canning Sub- Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000287/2025-2026 | 690/CSD | 26/05/2025 | 30 | ARANYA ENTERPRISE | 2.92 | 0 | 0
4688 | Alipore Division | Canning Sub-division | Construction of 1 (one) no. switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-III), Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [Pump House No. III] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000314/2024-2025 | 2695/AD | 24/06/2024 | 45 | GANGA TUBEWELL AND HARDWARE | 7.05 | 0 | 0
4689 | Alipore Division | Canning Sub-division | Construction of switch room cum chlorine room (4.88m x 3.66m) including Sanitary arrangement as per departmental drawing at the site of Sonakhali W/S Scheme (Zone-III) , Block - Basanti under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000502/2023-2024 | 2060/AD | 07/08/2023 | 45 | MAA SOLAR ENTERPRISE | 7.11 | 0 | 0
4690 | Alipore Division | Canning Sub-division | Sinking of 250mm x 150mm dia. 360 mtr. deep Tubewell by Direct Rotary Rig Method using P.V.C pipe and pre-packed Resin Bonded Gravel Filter of Sonakhali (Zone - III) W/S Scheme, Block - Basanti under Canning Sub Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000559/2023-2024 | 2246/AD | 11/08/2023 | 30 | SAMIR GIRI | 19.56 | 0 | 0
4691 | Alipore Division | Canning Sub-division | Conducting route survey, design distribution network and preparation & submission of DPR for Sonakhali (Zone-III) Augmentation Water Supply Scheme including Functional Household Tap Connection (FHTC) for implementation of JJM at Basanti Block under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000606/2023-2024 | 2269/AD | 14/08/2023 | 45 | TECH VISION | 6.39 | 0 | 99
4692 | Alipore Division | Canning Sub-division | Laying Distribution System, Providing Functional Household Tap Connection for Ground Water Based Augmentation Piped Water Supply Scheme for the Sonakhali (Zone-III), Block-Basanti under Canning Sub-Division of Alipore Division, PHE Dte. [No. of FHTC = 1981] | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/000632/2023-2024 | 2156/AD | 09/08/2023 | 90 | M/S SHIBAM ENTERPRISE | 450.06 | 0 | 65
4693 | Alipore Division | Canning Sub-division | Inter connection and rising main with supply of specials of Augmentation of Sonakhali (Zone-III) W/S Scheme, Block-Basanti under Canning Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/001081/2023-2024 | 3540/AD | 17/10/2023 | 15 | ARBINA ENTERPRISE | 27.69 | 0 | 0
4694 | Alipore Division | Canning Sub-division | Construction of 23 Nos. different capacity R.C.C OHR (based on Departmental Design & Drawing ) with 20 mtr. staging height including Geo-Technical investigation, foundation, pipeline connection and cost of pipes , specials etc. for augmentation of different piped water supply scheme of Canning-I, Canning-II & Basanti Block under Canning Sub-Division of Alipore Division, PHE Dte. | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | ORD/002461/2023-2024 | 1512/AD | 13/03/2024 | 600 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LTD | 2624.49 | 0 | 30
4695 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000037/2023-2024 | 243/AD | 24/04/2023 | 0 | Resource Division | 82.44 | 0 | 0
4696 | Alipore Division | Canning Sub-division | Material Requisition To Resource Division | Assistant Engineer, Canning sub division | Junior Engineer, 2 CSD | RTOR000394/2023-2024 | 335/AD | 19/01/2024 | 0 | Resource Division | 12.2 | 0 | 0
4697 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter for Uttar Chandanpiri W/S Scheme, Block - Namkhana under JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000160/2024-2025 | 2511/AD | 15/06/2024 | 45 | DEV AND COMPANY | 40.82 | 0 | 0
4698 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development and Plinth Protection and Approach Road for Pump House at Head Work Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000221/2024-2025 | 2604/AD | 19/06/2024 | 45 | MODERN CONSTRUCTION | 28.84 | 0 | 0
4699 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 3rd Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000228/2024-2025 | 2558/AD | 18/06/2024 | 30 | M/S R.K.ENTERPRISE | 9.66 | 0 | 0
4700 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 4th Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000229/2024-2025 | 2559/AD | 18/06/2024 | 30 | PRADIP KUMAR MONDAL | 9.65 | 0 | 0
4701 | Alipore Division | Kakdwip Sub-Division | Construction, placing and fixing of FHTC platform at every individual beneficiary, pump connections etc. at Uttar Chandanpiri PWSS, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E.D. (SM/18683) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000357/2024-2025 | 2841/AD | 05/07/2024 | 635 | SOMA CONSTRUCTION | 117.46 | 0 | 50
4702 | Alipore Division | Kakdwip Sub-Division | Construction of 1 nos. Pump House of size 5.40 mtr. x 3.60 mtr. at 3rd tubewell Site for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) (2nd call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000467/2024-2025 | 3462/AD | 23/08/2024 | 45 | M/S R.K.ENTERPRISE | 5.62 | 0 | 0
4703 | Alipore Division | Kakdwip Sub-Division | Construction of 1 no. Pump House of size 5.40 mtr. x 3.60 mtr. at 4th tubewell Site for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (SM/18683) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000468/2024-2025 | 3463/AD | 23/08/2024 | 45 | M/S. TARA MAA CONSTRUCTION | 5.6 | 0 | 0
4704 | Alipore Division | Kakdwip Sub-Division | Construction of boundary wall along with Land Development, Plinth Protection and Approach Road for Pump House at 2nd Tubewell Site of Uttar Chandanpiri W/S scheme, Block : Namkhana under JJM of Kakdwip Sub-Division under Alipore Division, P.H.E. Dte. (SM/18683) (2nd Call) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000509/2024-2025 | 3609/AD | 06/09/2024 | 30 | KAMALA ENTERPRISE | 9.61 | 0 | 0
4705 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-C) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000568/2023-2024 | 2258/AD | 14/08/2023 | 60 | M/S ARPAN ENTERPRISE | 16.9 | 0 | 70
4706 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-D) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000569/2023-2024 | 2084/AD | 07/08/2023 | 30 | AROMA INC | 12.09 | 0 | 50
4707 | Alipore Division | Kakdwip Sub-Division | Sinking of 02 Nos. 250mm x 150mm dia. 360 mtr. deep Tubewell by D.R. Rig method using UPVC Pipe & Pre-packed Resin Bonded Gravel Filter at 1st and 2nd Tubewell Site of Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000571/2023-2024 | 2259/AD | 14/08/2023 | 45 | AQUATECH ENGINEERS | 36.71 | 0 | 50
4708 | Alipore Division | Kakdwip Sub-Division | Laying distribution system, Functional Household Tap Connection (FHTC) to all households and Construction 02 nos. Pump House (5.40m. x 3.60m) for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-B) | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000581/2023-2024 | 2268/AD | 14/08/2023 | 45 | NATURAL RESOURCES CONSORTIUM | 60.84 | 0 | 0
4709 | Alipore Division | Kakdwip Sub-Division | Construction of 250 cum. Over Head Reservoir (OHR), (20 mtr. Staging Height) along with Laying distribution system, Rising Main, Functional Household Tap Connection (FHTC) to all households including design & drawing of pile foundation & pile cap after soil investigation including O & M of distribution system, rising main, FHTC for 1 year after completion of FHTC works for Uttar Chandanpiri Water Supply Scheme, Block - Namkhana for implementation of JJM under Kakdwip Sub-Division of Alipore Division, P.H.E. Dte. (Part-A) [No. of FHTC = 1577] | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/000633/2023-2024 | 2451/AD | 23/08/2023 | 952 | SOMA CONSTRUCTION | 486 | 0 | 60
4710 | Alipore Division | Kakdwip Sub-Division | Making and fixing of permanent display board at headwork site of Sibnagar Abad, Debnagar, Narayanganj, Dwariknagar, Namkhana, Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E.D. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002130/2023-2024 | 936/KSD | 19/12/2023 | 5 | ANANTA KUMAR GIRI | 0.94 | 0 | 100
4711 | Alipore Division | Kakdwip Sub-Division | Preparation of design (Pile and Pile Cap) drawing for foundation of different capacity OHR of Uttar Chandanpiri PWSS under JJM at Namkhana Block under Kakdwip Sub-Division of Alipore Division P.H.E. Dte. | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | ORD/002618/2023-2024 | 895/KSD | 18/12/2023 | 5 | CONSTEEL CONSULTANCY & SERVICES | 0.48 | 0 | 100
4712 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000474/2023-2024 | 4779/AD | 19/12/2023 | 0 | Resource Division | 16.05 | 0 | 0
4713 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000561/2023-2024 | 49/AD | 03/01/2024 | 0 | Resource Division | 13.23 | 0 | 0
4714 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000790/2023-2024 | 635/AD | 30/01/2024 | 0 | Resource Division | 0.5 | 0 | 0
4715 | Alipore Division | Kakdwip Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Kakdwip Sub Division | Juniour Engineer_3, Kakdwip Sub Division | RTOR000978/2023-2024 | 1771/AD | 27/03/2024 | 0 | Resource Division | 38.31 | 0 | 0
4716 | Alipore Division | Diamond Harbour Sub-Division | Construction of boundary wall at proposed OHR site at Mouza - Karimnagar under Zone- I of Kulpi Block for Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000503/2023-2024 | 2061/AD | 07/08/2023 | 30 | ESSCON | 25.16 | 0 | 0
4717 | Alipore Division | Diamond Harbour Sub-Division | Augmentation of laying distribution system including construction of 900 m3 capacity OHR to extend the benefit of 100% household by Providing Functional Household Tap Connection (FHTC) from distribution system in Zone-I at Kulpi block within " Mega Surface Water Based Water Supply Scheme for Falta- Mathurapur, District South 24 Parganas" under Diamond Harbour Sub-Division of Alipore Division of PHE Dte. [No of FHTC-6682] | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/000562/2023-2024 | 2254/AD | 14/08/2023 | 300 | DIVINE | 712.58 | 0 | 0
4718 | Alipore Division | Diamond Harbour Sub-Division | Preparation of design, drawing for foundation for the proposed R.C.C. Over Head Reservoir at Zone-I (Karimnagar, OHR Size-900 ) within Kulpi Block under ¿Mega Surface water based water supply scheme for Falta-Mathurapur, District South 24 parganas¿ under Diamond Harbour Sub-Division of Alipore Division, P.H.E. Dte. | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | ORD/002094/2022-2023 | 329/DHSD | 07/11/2022 | 7 | ASTER CONSULTANCY | 0.5 | 0 | 0
4719 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000203/2023-2024 | 2026/AD | 05/08/2023 | 0 | Resource Division | 25.17 | 0 | 0
4720 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000367/2023-2024 | 3231/AD | 04/10/2023 | 0 | Resource Division | 0.21 | 0 | 0
4721 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000670/2023-2024 | 423/AD | 22/01/2024 | 0 | Resource Division | 19.18 | 0 | 0
4722 | Alipore Division | Diamond Harbour Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Diamond Harbour sub division | Junior Engineer 4 DHSD | RTOR000863/2023-2024 | 770/AD | 03/02/2024 | 0 | Resource Division | 41.16 | 0 | 0
Total | [10 empty] | 314904.06 | 2565.42