## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2022-2023 | 2864/BD | 21/09/2022 | 0 | Resource Division | 2.16 | 0 | 0
2 | Barasat Division | Bangaon Sub-Division | providing of Functional House hold Tap connection (FHTC) in connection with JJM under command area of Malidah Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002299/2020-2021 | 276/BD. | 05/02/2021 | 7 | ORIENT CONSTRUCTION. | 11 | 11 | 1
3 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000051/2022-2023 | 2858/BD | 21/09/2022 | 0 | Resource Division | 1.85 | 0 | 0
4 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for KULIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001993/2021-2022 | 374/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.77 | 2.77 | 1
5 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in Bankra mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj Water Supply Scheme (Zone-II), at Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2022-2023 | 1295/ BD | 05/04/2022 | 60 | MONDAL PRECISION PVT.LTD | 112.27 | 0 | 1
6 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of DI rising main at near PH No- 3 (Old LS) within Hingalganj w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000247/2022-2023 | 1156/HSD | 12/07/2022 | 10 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 2.53 | 2.53 | 1
7 | Barasat Division | Hasnabad Sub-Division | Work Order for " Providing Functional Household Tap Connection (FHTC) in Sandlerbil Mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj W/S/Scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, P.H.E.Dte." | Assistant Engineer | Junior Engineer | ORD/000257/2020-2021 | 49/BD | 13/01/2021 | 90 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 155.31 | 29.14 | 1
8 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration by laying of 140/110/90/75 mm dia. HDPE distribution pipe line from Bankra Bazar to Rupamari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000398/2022-2023 | 1337/HSD | 02/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.29 | 4.29 | 1
9 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration by laying of 200/180/160 mm dia. HDPE distribution pipe line from Kathabari more to Rupamari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 1341/HSD | 02/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.66 | 4.66 | 1
10 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to widening of PWD road from Bankra Bazar to Rupamari more in connection with retrofitting of Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000428/2022-2023 | 1356/HSD | 03/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 2.9 | 2.9 | 1
11 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line for damage portion at different places due widening of PWD road of Hingalganj w/s Scheme (Zone-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000432/2022-2023 | 1358/HSD | 03/08/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.9 | 4.9 | 1
12 | Barasat Division | Hasnabad Sub-Division | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the different mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000667/2022-2023 | 2922/BD | 26/09/2022 | 30 | M/S RAJPATH CONSTRUCTION. | 11.95 | 11.94 | 1
13 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of 150mm dia. DI rising main from near Kathabari more to CWR i/c CWR connection within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000758/2022-2023 | 620/HSD | 07/04/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 3.28 | 3.28 | 1
14 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000804/2021-2022 | 1858/HSD. | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 2.96 | 2.96 | 1
15 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2022-2023 | 622/HSD | 07/04/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 2.34 | 2.34 | 1
16 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in khosbas, Singherkati mouza & Kanaknagar Mouza for Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001149/2021-2022 | 237/BD | 25/01/2022 | 30 | M/S PROGATI ENTERPRISE. | 31.04 | 31.03 | 1
17 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at OHR site & CWR site (PH No.-3) within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001436/2021-2022 | 527/BD | 23/02/2022 | 30 | ABDUL HAMID GAZI. | 22.43 | 20.86 | 1
18 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places for Rejuvenation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001666/2021-2022 | 420/HSD | 04/03/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.82 | 0 | 1
19 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of different dia. UPVC pipe line by UC Bullah pile at different places in Paschim Sandelerbill Uttarpara within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002069/2021-2022 | 1470/BD. | 13/08/2021 | 15 | M/S B.K.ENTERPRISE. | 15.23 | 2.57 | 1
20 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at different places in Sandelerbill mouza within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/002093/2021-2022 | 1463/BD. | 13/08/2021 | 15 | M/S PROGATI ENTERPRISE. | 15.81 | 2.48 | 1
21 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Bankra & Bankra Dobar mouza within Hingalganj W/S/Scheme(Z-II). Hingalganj Block under Hasnabad Sub-Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/002125/2021-2022 | 1464/BD. | 13/08/2021 | 30 | MONDAL & CO. (BASIRHAT). | 31.68 | 5.28 | 1
22 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in Bankra mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj Water Supply Scheme (Zone-II), at Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002126/2021-2022 | 1295/BD. | 26/07/2021 | 60 | MONDAL PRECISION PVT.LTD | 115.98 | 100.18 | 1
23 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Bankra Dobar mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002215/2020-2021 | 491/BD. | 26/02/2021 | 30 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 3.45 | 3.45 | 1
24 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Bermajur w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002571/2021-2022 | 417/HSD | 04/03/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.87 | 0 | 1
25 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002572/2021-2022 | 406/HSD | 04/03/2022 | 10 | S.K.ENTERPRISE. | 3.98 | 3.97 | 1
26 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of 160 mm dia. HDPE pipe line from PH No- 4 to near Kathabari more due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002875/2021-2022 | 583/HSD | 28/03/2022 | 15 | SARKAR ENTERPRISE | 4.94 | 4.94 | 1
27 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of different dia. UPVC pipe line at different places in Bankra & Bankra Dobar Mouza due to widening & strengthing of PWD road for damage portion within Hingalganj W/S Scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002885/2021-2022 | 594/HSD | 29/03/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.49 | 4.49 | 1
28 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2022-2023 | 1438/BD | 23/05/2022 | 0 | Resource Division | 9.71 | 0 | 0
29 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2021-2022 | 941/BD | 28/03/2022 | 0 | Resource Division | 150.53 | 0 | 0
30 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000031/2021-2022 | 961/BD | 29/03/2022 | 0 | Resource Division | 115.45 | 0 | 0
31 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000090/2023-2024 | 1815/BD | 19/06/2023 | 0 | Resource Division | 18.48 | 0 | 0
32 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of CHIKANPARA Water Supply Scheme at GAIGHATA Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001157/2021-2022 | 259/BD | 28/01/2022 | 90 | SUPER SKILL. | 195.19 | 194.56 | 1
33 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chikanpara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001351/2021-2022 | 147/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.37 | 4.37 | 1
34 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000103/2022-2023 | 3658/BD | 13/12/2022 | 0 | Resource Division | 15.09 | 0 | 0
35 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Akipur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000569/2021-2022 | 1956/BD | 08/10/2021 | 30 | BANERJEE CONSTRUCTION. | 58.26 | 53.25 | 1
36 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Pifa Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001140/2021-2022 | 221/BD | 24/01/2022 | 45 | M/S ANUBHAB CONSTRUCTION. | 68.51 | 67.86 | 1
37 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for PIFA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001934/2021-2022 | 190/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.65 | 1
38 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000072/2022-2023 | 2985/BD | 29/09/2022 | 0 | Resource Division | 7.39 | 0 | 0
39 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000636/2023-2024 | 619/BON | 08/08/2023 | 20 | MA CONSTRUCTION. | 3.98 | 3.95 | 100
40 | Barasat Division | Bangaon Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gangrapota Water Supply Scheme at Bongaon Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000643/2021-2022 | 2175/BD | 18/11/2021 | 90 | AMIT KUMAR BOSE. | 167.22 | 159.23 | 1
41 | Barasat Division | Bangaon Sub-Division | Construction of Boundary wall at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000643/2023-2024 | 614/Bon | 08/08/2023 | 21 | A.D.ENTERPRISE. | 3.66 | 0 | 0
42 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & DPR Preparation for Kamarpur & Adj. Mouzas W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000935/2021-2022 | 558/HAB | 20/12/2021 | 10 | UMWELT ENGINEER PVT.LTD. | 3.42 | 3.41 | 1
43 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & DPR Preparation for Gangrapota Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001117/2021-2022 | 611/Bon | 31/12/2021 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.12 | 4.1 | 1
44 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2021-2022 | 2238/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0
45 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work in different places of Jhupkhali Mouza in connection with retrofitting of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000034/2023-2024 | 1324/BD | 28/04/2023 | 30 | RADIANT | 112.53 | 112.39 | 0
46 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2022-2023 | 1617/BD | 07/06/2022 | 90 | RADIANT | 124.77 | 123.97 | 0
47 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Dhulia Jhupkhali FP School, Dhulia Jhupkhali Jr. High School & Jhupkhali FP School within the command area of Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000866/2023-2024 | 1052/HSD | 31/08/2023 | 7 | M/S RAJPATH CONSTRUCTION. | 0.53 | 0.53 | 100
48 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile in Laukhali and Jhupkhali w/s scheme, Sandeshkhali-I & II block respectively under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000879/2023-2024 | 2681/BD | 04/09/2023 | 30 | SURYA ENTERPRISE. | 67.91 | 0 | 99
49 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Jhupkhali mouza due to erosion of soil for heavy rain fall during monsoon season within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000976/2023-2024 | 1064/HSD | 31/08/2023 | 10 | JESMINE ENTERPRISE. | 0.98 | 0 | 100
50 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001271/2024-2025 | 355/BD | 31/01/2025 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 27.86 | 0 | 0
51 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (TW No-1) within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001304/2023-2024 | 4377/BD | 10/11/2023 | 90 | JESMINE ENTERPRISE. | 21.09 | 0 | 100
52 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Jhupkhali water supply scheme in order to provide Har Ghar Jal Certification, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001721/2023-2024 | 371/BD | 06/02/2024 | 208 | ROHAN MONDAL. | 39.12 | 0 | 100
53 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Laukhali W/s scheme Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2022-2023 | 1569/BD | 01/06/2022 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 250.04 | 186.86 | 100
54 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 100 cum/hr Iron Removal Plant with blower room & other allied works within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000192/2025-2026 | 2024/BD | 18/06/2025 | 150 | FIDERE MARINE SERVICES PVT. LTD. | 38.3 | 0 | 0
55 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 100/150 mm dia DI pipeline at different places within Laukhali Patharghata w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000238/2022-2023 | 1147/HSD | 12/07/2022 | 15 | PRITAM MUKHOPADHYAY. | 4.06 | 3.97 | 0
56 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places of Laukhali Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000260/2022-2023 | 1169/HSD | 12/07/2022 | 15 | M/S S.S.ENTERPRISE. (SOUTH) | 4.81 | 4.8 | 1
57 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order forProtection of newly laid UPVC pipe line by bamboo pilling at different places at Agarhati mouza in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2022-2023 | 1334/HSD | 02/08/2022 | 10 | K.T.ENGINEERING & CO. | 4.47 | 4.46 | 1
58 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places at Laukhali Patharghata mouza in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000396/2022-2023 | 1335/HSD | 02/08/2022 | 10 | NIKHIL SAMADDAR | 4.5 | 4.48 | 1
59 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling near Baba Loknath Mandir, N/H/O Kalu Singh, Subrata Mondal at Rajbari Sundariakhali and other different places at Laukhali village in connection with retrofitting of Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000397/2022-2023 | 1336/HSD | 02/08/2022 | 10 | NIKHIL SAMADDAR | 4.52 | 4.51 | 1
60 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site (Ph No-1) within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001319/2023-2024 | 4433/BD | 10/11/2023 | 90 | MATRI ENTERPRISE | 16.97 | 0 | 100
61 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 700 cum capacity 20mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Laukhali water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001544/2021-2022 | 536/BD | 23/02/2022 | 365 | M/S S.S.ENTERPRISE. (SOUTH) | 452.05 | 156.2 | 100
62 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent casing of UPVC pipe line at different locations over Khal, channel, culverts, roads within Laukhali W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002798/2021-2022 | 358/HSD | 23/02/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.39 | 4.49 | 1
63 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional emergent resting of 100/150 mm dia DI pipeline by concrete block at different places within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002799/2021-2022 | 359/HSD | 23/02/2022 | 15 | MD.SALIM GAZI. | 4.19 | 4.15 | 1
64 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional emergent resting of 200/250/300 mm dia DI pipeline by concrete block at different places within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002800/2021-2022 | 360/HSD | 23/02/2022 | 15 | SARKAR ENTERPRISE | 4.31 | 4.26 | 1
65 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Agarhati Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002801/2021-2022 | 361/HSD | 23/02/2022 | 15 | MD.SALIM GAZI. | 4.76 | 4.76 | 1
66 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Agarhati Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002802/2021-2022 | 362/HSD | 23/02/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.76 | 4.76 | 1
67 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Patharghata Laukhali Mouza within Laukhali w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002803/2021-2022 | 363/HSD | 23/02/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.76 | 4.76 | 1
68 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000157/2022-2023 | 156/BD | 18/01/2023 | 0 | Resource Division | 35.12 | 0 | 0
69 | Barasat Division | Hasnabad Sub-Division | Enhancement of GST for the work providing FHTC for Augmentation of Kalinagar (Zone-II) W/S Scheme | Assistant Engineer | Junior Engineer | BILL/00275/2024-2025 | BP-2024-25-78 | 10/07/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 6.76 | 0 | 0
70 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work for newly laid UPVC pipe line at different places of Gajalia, Putimari & Ghatihara Mouza in connection with retrofitting of Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000041/2023-2024 | 1359/BD | 04/05/2023 | 30 | UMWELT ENGINEER PVT.LTD. | 138.59 | 138.51 | 59
71 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan mission (JJM and Jal Swapna) within command area of Kalinagar (Zone-II) W/S Scheme, Sandeshkhali-I Block, Dist. - North 24 Parganas under Hasnabad Sub-Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2022-2023 | 1506/BD | 26/05/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 208.93 | 199.91 | 47
72 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Ghatihara mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000871/2023-2024 | 1057/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.98 | 0.98 | 100
73 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Putimari mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000872/2023-2024 | 1058/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0.94 | 100
74 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Gazalia mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000873/2023-2024 | 1059/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.95 | 0.95 | 100
75 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site (PH No-1) within Kalinagar w/s scheme (Z-II), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001333/2023-2024 | 4436/BD | 10/11/2023 | 90 | M/S SANJAY ADHIKARI | 16.63 | 0 | 81
76 | Barasat Division | Hasnabad Sub-Division | Acceptance Cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Kalinagar (Z-II) Water Supply Scheme in order to provide Har Ghar Jal Certification, Sandeshkhalli -I Block under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001727/2023-2024 | 427/BD | 09/02/2024 | 300 | ABDUL ALIM MONDAL. | 55.66 | 0 | 90
77 | Barasat Division | Habra Sub-Division | Construction of Service Road (35 Mtr. Length X 2 Mtr. Width) for Pump House No:1 of Talsa Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000344/2024-2025 | 698/HAB | 26/07/2024 | 10 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 2.14 | 0 | 100
78 | Barasat Division | Habra Sub-Division | Construction of Service Road (20 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Talsa Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000345/2024-2025 | 701/HAB | 29/07/2024 | 10 | DEBANJAN GHOSH. | 1.22 | 0 | 100
79 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Talsa Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 2312/BD | 03/08/2022 | 90 | DEBAPRASAD MONDAL. | 295.79 | 194.52 | 100
80 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Talsa W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000894/2024-2025 | 926/HAB | 05/11/2024 | 20 | JP CONSTRUCTION & SUPPLIERS. | 2.66 | 0 | 0
81 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Talsa W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000899/2024-2025 | 931/HAB | 05/11/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.6 | 0 | 0
82 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Talsa water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000973/2023-2024 | 2781/BD | 11/09/2023 | 60 | M/S K.P.PAL. | 28.99 | 0 | 100
83 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. - 1 & 2 of Talsa W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002986/2021-2022 | 498/HAB | 02/12/2021 | 30 | TALUKDER & CO. | 2.16 | 0 | 1
84 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000043/2022-2023 | 2516/BD | 25/08/2022 | 0 | Resource Division | 7.71 | 0 | 0
85 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000128/2022-2023 | 3791/BD | 22/12/2022 | 0 | Resource Division | 10.96 | 0 | 0
86 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chandpara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000831/2022-2023 | 3629/BD | 12/12/2022 | 1170 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 525.18 | 334.56 | 92
87 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chandpara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/000885/2023-2024 | 2699/BD | 04/09/2023 | 30 | NADIA TUBEWELLS | 16.16 | 0 | 100
88 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chandpara Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001114/2023-2024 | 2937/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 0 | 100
89 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation & repairing of Boundary wall at Head work site for Augmentation of Chandpara water Supply scheme, Gaighata Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001479/2023-2024 | 4412/BD | 10/11/2023 | 60 | BHABANI ENTERPRISE. | 13.44 | 0 | 100
90 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at 3rd Tube Well site and Construction of Approach Road at 3rd Tube Well site and Head work site under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001555/2023-2024 | 41/BD | 04/01/2024 | 23 | ROY ENGINEERS. | 7.4 | 0 | 100
91 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001566/2023-2024 | 63/BD | 05/01/2024 | 390 | SAMBHU RAY CHOWDHURY. | 6.02 | 0 | 100
92 | Barasat Division | Bangaon Sub-Division | Formal work order for Dismantling and Cement Concreting of existing Cement Concrete Road for laying rest part of UPVC pipes within command area and Drum Sheet Walling for supporting other UPVC Pipes along the NH 35 for Augmentation work at Chandpara W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002017/2023-2024 | 808/BD | 12/03/2024 | 720 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 112.22 | 0 | 60
93 | Barasat Division | Bangaon Sub-Division | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Chandpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002275/2023-2024 | 841/Bon | 01/11/2023 | 23 | M/S SAYAN ENTERPRISE. | 4.59 | 0 | 0
94 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chandpara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002860/2021-2022 | 144/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 0 | 1
95 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chandapara Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002898/2021-2022 | 143/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 4.04 | 1
96 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chandpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002928/2021-2022 | 537/Bon | 03/11/2021 | 21 | SAMBHU RAY CHOWDHURY. | 2.52 | 2.47 | 1
97 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Chandpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002936/2021-2022 | 634/BON | 31/12/2021 | 21 | SAMBHU RAY CHOWDHURY. | 1.26 | 1.14 | 1
98 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2022-2023 | 1360/BD | 13/05/2022 | 0 | Resource Division | 11.96 | 0 | 0
99 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000100/2022-2023 | 3657/BD | 13/12/2022 | 0 | Resource Division | 31.17 | 0 | 0
100 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Special Repair & Maintenance work inconnection with augmentation work at Ichhapur W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2024-2025 | 2596/BD | 06/09/2024 | 12 | ROY ENGINEERS. | 13.24 | 0 | 100
101 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Ichhapur Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction and also to convert the mouzas into Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2025-2026 | 1905/BD | 05/06/2025 | 120 | ROY ENGINEERS. | 16.43 | 0 | 0
102 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Ichhapur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2025-2026 | 1770/BD | 29/05/2025 | 240 | SONALI CONSTRUCTION | 21.51 | 0 | 0
103 | Barasat Division | Bangaon Sub-Division | Construction of Latrine at 2nd Pump House site and Renovation of PH No - 1 & 2 for Ichhapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000611/2025-2026 | 653/Bon | 22/05/2025 | 45 | ROY ENGINEERS. | 3.3 | 0 | 0
104 | Barasat Division | Bangaon Sub-Division | Additional laying of UPVC pipe to connect every house hold connection with Augmentation work at Ichhapur W/S Scheme under Gaighata block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000641/2024-2025 | 1322/Bon | 12/11/2024 | 100 | UPWARDS ENGINEERING PRIVATE LIMITED. | 4.97 | 0 | 100
105 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ichhapur water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000799/2023-2024 | 2698/BD | 04/09/2023 | 30 | NADIA TUBEWELLS | 16.16 | 0 | 100
106 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Ichhapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000867/2022-2023 | 3768/BD | 20/12/2022 | 90 | BALAJI UDDYOG | 468.29 | 433.93 | 100
107 | Barasat Division | Bangaon Sub-Division | Laying of badly damaged distribution pipe line and others allied works for making Panchayet Drain at Ichhapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001182/2023-2024 | 329/Bon | 03/05/2023 | 12 | ROY ENGINEERS. | 0.51 | 0 | 100
108 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Laying of badly damaged UPVC Distribution Pipe Lines due to laying of Secondary Rising Main of Habra-Gaighata Project from Amkola More to Kulipara More along with Road Restoration and other allied works at ICCHAPUR Water Supply Scheme within the jurisdiction of Bongaon SubDivision, under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001576/2023-2024 | 85/BD | 08/01/2024 | 30 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 19.15 | 0 | 100
109 | Barasat Division | Bangaon Sub-Division | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Ichhapur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002350/2023-2024 | 978/Bon | 27/12/2023 | 30 | SAMBHU RAY CHOWDHURY. | 3.63 | 0 | 0
110 | Barasat Division | Bangaon Sub-Division | Work order for repairing & renovation of Pump House and allied works of Ichhapur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002941/2021-2022 | 540/ BON | 03/11/2021 | 21 | ROY ENGINEERS. | 2.52 | 2.48 | 1
111 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2022-2023 | 1363/BD | 13/05/2022 | 0 | Resource Division | 10.74 | 0 | 0
112 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Champali w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000371/2022-2023 | 2436/BD | 22/08/2022 | 30 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 19.15 | 100
113 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Champali water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000518/2022-2023 | 2400/BD | 17/08/2022 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 129.78 | 128.23 | 1
114 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Champali water supply scheme, Minakhan Block under hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001247/2023-2024 | 4179/BD | 30/10/2023 | 365 | M/S BISWAS BROTHERS. | 114.29 | 0 | 0
115 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Champali w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001370/2024-2025 | 237/HSD | 30/01/2025 | 10 | SARKAR ENTERPRISE | 0.81 | 0 | 100
116 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation for Champali water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001907/2023-2024 | 279/HSD | 06/03/2024 | 10 | SARKAR ENTERPRISE | 0.6 | 0 | 100
117 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2022-2023 | 2474/BD | 24/08/2022 | 0 | Resource Division | 2.46 | 0 | 0
118 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection for Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2025-2026 | 1604/BD | 19/05/2025 | 30 | M/S SAIN ENTERPRISE. | 10.62 | 0 | 0
119 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Fakirtakia water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2023-2024 | 1722/BD | 08/06/2023 | 365 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 153.55 | 0 | 72
120 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Bitpole in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000249/2023-2024 | 775/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.94 | 0.94 | 100
121 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Chotto Ajgora in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000257/2023-2024 | 783/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.94 | 0.94 | 29
122 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near PH No- 1 in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000263/2023-2024 | 789/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.98 | 0.98 | 31
123 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at near Baro Ajgora in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 778/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.89 | 0.89 | 29
124 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Fakiratakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000358/2022-2023 | 2236/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.41 | 15.19 | 1
125 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Fakirtakia water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000596/2022-2023 | 2674/BD | 08/09/2022 | 90 | PROJECT INDIA | 228.86 | 223.88 | 1
126 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Fakitakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001292/2023-2024 | 1414/HSD | 06/11/2023 | 7 | BADAL GHOSH. | 0.79 | 0 | 100
127 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Repairing of existing FHTC & other allied works in connection with Augmentation of Fakirtakia w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001403/2024-2025 | 390/BD | 05/02/2025 | 60 | SARKAR ENTERPRISE & CO. | 29.16 | 0 | 100
128 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Fakirtakia water supply scheme in order to provide Har Ghar Jal Certification, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001722/2023-2024 | 372/BD | 06/02/2024 | 329 | SARKAR ENTERPRISE & CO. | 47.73 | 0 | 100
129 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation for Fakirtakia water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001830/2023-2024 | 257/HSD | 06/03/2024 | 10 | BADAL GHOSH. | 0.59 | 0 | 100
130 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000047/2022-2023 | 2578/BD | 31/08/2022 | 0 | Resource Division | 6.15 | 0 | 0
131 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000173/2022-2023 | 520/BD | 20/02/2023 | 0 | Resource Division | 14.66 | 0 | 0
132 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Patua Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000787/2022-2023 | 3549/BD | 06/12/2022 | 1054 | SUBHASH BOSE. | 326.66 | 0 | 27
133 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Patua Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002755/2021-2022 | 444/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 4.16 | 1
134 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000180/2022-2023 | 601/BD | 23/02/2023 | 0 | Resource Division | 6.94 | 0 | 0
135 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000201/2022-2023 | 859/BD | 20/03/2023 | 0 | Resource Division | 48.85 | 0 | 0
136 | Barasat Division | Hasnabad Sub-Division | Acceptance Cum Work Order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2023-2024 | 1096/BD | 06/04/2023 | 30 | MONDAL & CO. (BASIRHAT). | 62.05 | 47.57 | 0
137 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000067/2025-2026 | 1753/BD | 28/05/2025 | 60 | MONDAL & CO. (BASIRHAT). | 251.97 | 0 | 0
138 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Durgamandop Mouza within Durgamandop w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000313/2024-2025 | 888/HSD | 07/08/2024 | 10 | SARKAR ENTERPRISE & CO. | 0.94 | 0 | 100
139 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 2401/BD | 17/08/2022 | 90 | MONDAL & CO. (BASIRHAT). | 287.51 | 266.78 | 1
140 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000843/2023-2024 | 2652/BD | 01/09/2023 | 30 | MONDAL & CO. (BASIRHAT). | 56.83 | 56.73 | 84
141 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000857/2023-2024 | 1043/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100
142 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000858/2023-2024 | 1044/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.93 | 0.93 | 100
143 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Dk Durgamandop FP School, DTD Sahid Smriti Bidyalaya & Durgamandop Sardar para High School within the command area of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000867/2023-2024 | 1053/HSD | 31/08/2023 | 7 | M/S RAJPATH CONSTRUCTION. | 0.69 | 0 | 0
144 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Durgamandop water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001252/2023-2024 | 4182/BD | 30/10/2023 | 732 | DEBASIS SAMADDAR | 150.76 | 0 | 60
145 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001293/2023-2024 | 1415/HSD | 06/11/2023 | 7 | SARKAR ENTERPRISE | 0.83 | 0 | 100
146 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places at Ghat para in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001426/2024-2025 | 307/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE & CO. | 0.98 | 0 | 100
147 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001440/2024-2025 | 110/BD | 09/01/2025 | 75 | MD.SALIM GAZI. | 11.68 | 0 | 0
148 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Bairagi para at Durgamandop mouza in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001461/2024-2025 | 338/HSD | 06/02/2025 | 10 | RATAN SARKAR. | 0.96 | 0 | 100
149 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Durgamandop water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001852/2023-2024 | 276/HSD | 06/03/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0 | 83
150 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2022-2023 | 2471/BD | 24/08/2022 | 0 | Resource Division | 7.56 | 0 | 0
151 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Dakshin Debipur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000748/2022-2023 | 3373/BD | 18/11/2022 | 90 | CHANCHAL ENTERPRISE & CO. | 212.57 | 212.53 | 85
152 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing new FHTC (Functional Household Tap Connection) by Augmentation and relaying of rising main, distribution UPVC pipe line and repairing of existing FHTC connection which damaged due to construction of drain by local Panchayet from Pump house I to Pump house II of Dakshin Debipur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000800/2024-2025 | 3294/BD | 26/11/2024 | 210 | ROHAN MONDAL. | 57.65 | 0 | 80
153 | Barasat Division | Basirhat Sub-Division | Construction of pathway & Land development at H/W site of Dakshin Debipur Water Supply Scheme under Basirhat-Il Block under Basirhat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001929/2021-2022 | 380/BHTSD | 17/03/2022 | 20 | M/S MITRA CONSTRUCTION. | 3.27 | 3.17 | 1
154 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DAKSHIN DEBIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002794/2021-2022 | 312/ BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 2.87 | 1
155 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000031/2022-2023 | 2306/BD | 03/08/2022 | 0 | Resource Division | 2.3 | 0 | 0
156 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000146/2022-2023 | 3815/BD | 23/12/2022 | 0 | Resource Division | 2.38 | 0 | 0
157 | Barasat Division | Basirhat Sub-Division | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Sangrampur WS Scheme | Assistant Engineer | Junior Engineer | BILL/00831/2024-2025 | BP-02024-25-262 | 12/09/2024 | 0 | H.I.ENTERPRISE. | 34.82 | 0 | 0
158 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution system pipeline and Providing FHTC (Functional Household Tap Connection)for augmentation of Sangrampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000681/2022-2023 | 3196/BD | 01/11/2022 | 90 | H.I.ENTERPRISE. | 654.07 | 596.93 | 83
159 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Construction of Boundary Wall at the Head Work site of Sangrampur Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001037/2024-2025 | 59/BD | 07/01/2025 | 210 | IKBAL HOSSAIN | 18.27 | 0 | 40
160 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for construction of CWR at Sangrampur W/S scheme under Basirhat Sub-Division, P.H.E. Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001165/2021-2022 | 333/BD | 02/02/2022 | 45 | MD AMIRUL MOLLA. | 5.2 | 4.49 | 1
161 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Sangrampur Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. 2nd Call. | Assistant Engineer | Junior Engineer | ORD/001212/2024-2025 | 195/BD | 16/01/2025 | 30 | JESMINE ENTERPRISE. | 21.72 | 0 | 0
162 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SANGRAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002895/2021-2022 | 195/BHT SD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
163 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2023-2024 | 1101/BD | 06/04/2023 | 0 | Resource Division | 92.65 | 0 | 0
164 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000072/2023-2024 | 1659/BD | 05/06/2023 | 0 | Resource Division | 10.04 | 0 | 0
165 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000136/2022-2023 | 3811/BD | 23/12/2022 | 0 | Resource Division | 83.52 | 0 | 0
166 | Barasat Division | Basirhat Sub-Division | Special repairing of rising mains pipe lines at Mathurapur water supply scheme under Basirhat Sub-Division under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000259/2024-2025 | 1030/BHTSD | 28/06/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0
167 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Mathurapur Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000783/2022-2023 | 3490/BD | 02/12/2022 | 90 | M/S DATTA ENTERPRISE. | 325.16 | 247.03 | 76
168 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000156/2023-2024 | 4419/BD | 10/11/2023 | 0 | Resource Division | 9.24 | 0 | 0
169 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000159/2022-2023 | 496/BD | 17/02/2023 | 0 | Resource Division | 29.48 | 0 | 0
170 | Barasat Division | Basirhat Sub-Division | Relaying of 75mm dia UPVC Parallel line for repairing of FHTC connections which damaged due to construction of drain from local Panchayet at SriKrishnapur Mouza (Node no. 300 to 307 to 314 to 320) of Raghunathpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000257/2024-2025 | 1028/BHTSD | 28/06/2024 | 7 | M/S MAA TARA ENTERPRISE | 0.73 | 0 | 100
171 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raghunathpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000746/2022-2023 | 3344/BD | 16/11/2022 | 90 | UTPAL CONSTRUCTION & CO. | 180.46 | 155.48 | 88
172 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000158/2022-2023 | 493/BD | 17/02/2023 | 0 | Resource Division | 10.73 | 0 | 0
173 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Debhog Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000704/2024-2025 | 3254/BD | 25/11/2024 | 30 | ROHAN MONDAL. | 21.41 | 0 | 0
174 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC Distribution system pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Debhog water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2022-2023 | 518/BD | 20/02/2023 | 773 | UTPAL CONSTRUCTION & CO. | 301.59 | 202.41 | 80
175 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2023-2024 | 1250/BD | 25/04/2023 | 0 | Resource Division | 17.73 | 0 | 0
176 | Barasat Division | Habra Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XII) under Habra-Gaighata surface based PWSS of Habra-I Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001159/2023-2024 | 2957/BD | 29/09/2023 | 810 | AMAL DUTTA ROY | 1929.73 | 0 | 22
177 | Barasat Division | Bangaon Sub-Division | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2022 to 31/01/2023). | Assistant Engineer | Junior Engineer | ORD/001396/2021-2022 | 45/Bon | 31/01/2022 | 1 | ROY ENGINEERS. | 1.73 | 1.68 | 1
178 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Sankardaha W/S scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2023-2024 | 1699/BD | 08/06/2023 | 732 | M/S DATTA ENTERPRISE. | 405.52 | 130.24 | 100
179 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion at different places in connection with retrofitting of Khas Sankardaha & Sankardaha Abad within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000553/2024-2025 | 995/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.93 | 0 | 100
180 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Strengthing of Brick pavement road for movement of rig machineries for sinking of big dia Tube well at PH No-2 within Sankardaha w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000887/2023-2024 | 1129/HSD | 05/09/2023 | 7 | RUDRA DAS. | 3.55 | 0 | 100
181 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Strengthing of existing concrete & Brick pavement road for movement of rig machineries for sinking of big dia Tube well at PH No-1 within Sankardaha w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000906/2023-2024 | 2717/BD | 05/09/2023 | 7 | ARBINA ENTERPRISE. | 5.56 | 0 | 100
182 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Sankardaha water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001471/2024-2025 | 345/HSD | 06/02/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 100
183 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (SANKARDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002732/2021-2022 | 308/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 0
184 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (SANKARDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002733/2021-2022 | 309/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.06 | 2.06 | 0
185 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000215/2022-2023 | 884/BD | 22/03/2023 | 0 | Resource Division | 17.11 | 0 | 0
186 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Laying Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC at Zonal Head Work Site Zone-VI within the jurisdiction of (Zone-VI) under Habra-Gaighata surface based PWSS of Deganga Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001178/2023-2024 | 3008/BD | 05/10/2023 | 90 | PATHIK PABAN NANDI | 697.92 | 0 | 0
187 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000118/2023-2024 | 4025/BD | 12/10/2023 | 0 | Resource Division | 78.14 | 0 | 0
188 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Phulbari Abad w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000117/2023-2024 | 1691/BD | 07/06/2023 | 366 | M/S B.K.ENTERPRISE. | 252.21 | 0 | 80
189 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PHULBARI ABAD Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002730/2021-2022 | 306/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 1
190 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000218/2022-2023 | 886/BD | 22/03/2023 | 0 | Resource Division | 11.94 | 0 | 0
191 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 300 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Matiagachha water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2023-2024 | 1715/BD | 08/06/2023 | 366 | MITRA CONSTRUCTION. | 378.68 | 0 | 39
192 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Matiagachha Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-20 | Assistant Engineer | Junior Engineer | ORD/000313/2022-2023 | 567/BSD | 29/06/2022 | 30 | RADIANT | 3.27 | 0 | 100
193 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Boundary Wall at Matiagacha Water Supply Scheme under Barasat-II Block, under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000568/2024-2025 | 3080/BD | 29/10/2024 | 30 | SANTU GHOSH. | 25.1 | 0 | 0
194 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Additional Laying of UPVC pipe line and allied work in connection with Augmentation Matiagachha Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001050/2024-2025 | 57/BD | 07/01/2025 | 30 | MITRA CONSTRUCTION | 37.61 | 0 | 0
195 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Matiagacha Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2023-2024 | 2942/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 0 | 100
196 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Renovation of Iron Elimination Plant at Matiagachha Water Supply Scheme within Barasat-II Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001157/2024-2025 | 98/BD | 09/01/2025 | 40 | AMIT KUMAR BOSE. | 9.19 | 0 | 0
197 | Barasat Division | Barasat Sadar Sub-Division | Construction of Pump House with latrine at Matiagachha water Supply Scheme under Barasat-II Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001384/2024-2025 | 1022/BSD | 03/01/2025 | 40 | BUSTER CONSTRUCTION | 4.87 | 0 | 0
198 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001783/2023-2024 | 627/BD | 28/02/2024 | 45 | R.K.MANDAL & CO. | 23.11 | 0 | 100
199 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Repair & Renovation work at Different site in connection with Augmentation of Matiagacha Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002047/2024-2025 | 930/BD | 24/03/2025 | 45 | AREOCON. | 9.03 | 0 | 100
200 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Matiagachha Water Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002951/2021-2022 | 833/BSD | 16/12/2021 | 30 | M.ENTERPRISE. | 1.85 | 0 | 1
201 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (P.H. No-II) and allied works at Matiagachha Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002956/2021-2022 | 837/BSD | 20/12/2021 | 30 | K.D ENTERPRISE. | 1.25 | 0 | 100
202 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000050/2023-2024 | 1285/BD | 25/04/2023 | 0 | Resource Division | 46.16 | 0 | 0
203 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000073/2023-2024 | 1673/BD | 06/06/2023 | 0 | Resource Division | 46.16 | 0 | 0
204 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000078/2023-2024 | 1676/BD | 06/06/2023 | 0 | Resource Division | 11.83 | 0 | 0
205 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000129/2023-2024 | 4375/BD | 10/11/2023 | 0 | Resource Division | 12.98 | 0 | 0
206 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 150 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2023-2024 | 1205/BD | 20/04/2023 | 30 | ABDUL ALIM MONDAL. | 25.87 | 11.93 | 63
207 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Padmapukuria water supply scheme (Zone - I), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2023-2024 | 1723/BD | 08/06/2023 | 725 | MONDAL & CO. (BASIRHAT). | 152.66 | 0 | 99
208 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Murshid Molla in connection with Augmentation of Padmapukuria w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000178/2024-2025 | 2097/BD | 26/07/2024 | 151 | JESMINE ENTERPRISE. | 7.53 | 0 | 100
209 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Reservoir as per Deptt. design, drawing and specification including bored pile with pile cap for Augmentaion of Padmapukuria water supply scheme (Zone - II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 1739/BD | 08/06/2023 | 724 | M/S B.K.ENTERPRISE. | 121.96 | 0 | 100
210 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Rahaman Molla, Motaleb Molla at Maliari Sekh para & Other places for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2022-2023 | 1196/HSD | 13/07/2022 | 10 | M/S ATRI BISWAS | 2.05 | 2.05 | 1
211 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Padmapukuria W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000579/2024-2025 | 1141/HSD | 24/09/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.87 | 0 | 100
212 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Padmapukuria W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000581/2024-2025 | 1143/HSD | 24/09/2024 | 10 | M/S R.B.S.ENTERPRISE. | 0.87 | 0 | 100
213 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Padmapukuria water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000928/2022-2023 | 127/BD | 16/01/2023 | 90 | MONDAL & CO. (BASIRHAT). | 416.99 | 369.68 | 1
214 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Padmapukuria water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001008/2022-2023 | 171/BD | 19/01/2023 | 90 | M/S B.K.ENTERPRISE. | 446.28 | 282.82 | 75
215 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Padmapukuria mouza in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001326/2024-2025 | 170/HSD | 27/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 100
216 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001363/2024-2025 | 409/BD | 06/02/2025 | 300 | M/S RAJPATH CONSTRUCTION. | 51.15 | 0 | 96
217 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at N/H/O Hasmat Molla at Maliari for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001391/2023-2024 | 1495/HSD | 01/12/2023 | 15 | GAZI ENTERPRISE | 4.03 | 0 | 70
218 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Padmapukuria w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001394/2024-2025 | 260/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.95 | 0 | 100
219 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at Maliari Masjid pond for Augmentation of Padmapukuria w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001400/2023-2024 | 1494/HSD | 01/12/2023 | 15 | BABUSONA CONSTRUCTION. | 4.41 | 0 | 68
220 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with column structure at OHR site, PH No-2 & 3 in connection with augmentation of Padmapukuria w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002261/2024-2025 | 1030/BD | 28/03/2025 | 90 | JESMINE ENTERPRISE. | 28.96 | 0 | 0
221 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with column structure at OHR site in connection with augmentation of Padmapukuria w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002262/2024-2025 | 1029/BD | 28/03/2025 | 90 | M/S B.K.ENTERPRISE. | 18.14 | 0 | 0
222 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000176/2022-2023 | 518/BD | 20/02/2023 | 0 | Resource Division | 124.37 | 0 | 0
223 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000263/2022-2023 | 913/BD | 22/03/2023 | 0 | Resource Division | 48.74 | 0 | 0
224 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2023-2024 | 1203/BD | 20/04/2023 | 30 | ANJALI ENTERPRISE. | 21.52 | 18.03 | 0
225 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Pressure sand filter of capacity 120 cum/hr at Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000190/2025-2026 | 2023/BD | 18/06/2025 | 150 | FIDERE MARINE SERVICES PVT. LTD. | 38.29 | 0 | 0
226 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 2 & 3(at defunct T/W site) with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Hingalganj W/S(old) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000527/2022-2023 | 2242/BD | 22/08/2022 | 30 | ACME CONSTRUCTION | 44.4 | 0 | 55
227 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000536/2024-2025 | 2902/BD | 03/10/2024 | 60 | ANJALI ENTERPRISE. | 51.76 | 0 | 0
228 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000548/2024-2025 | 3025/BD | 22/10/2024 | 90 | M/S ANUBHAB CONSTRUCTION. | 15.83 | 0 | 0
229 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000732/2023-2024 | 2480/BD | 18/08/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 51.64 | 0 | 100
230 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000733/2023-2024 | 2482/BD | 18/08/2023 | 30 | MONDAL & CO. (BASIRHAT). | 51.6 | 0 | 100
231 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - I Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000771/2022-2023 | 635/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 0
232 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Ajay Manna & Bijon Manna at Mamudpur in connection with Augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000994/2024-2025 | 3498/BD | 11/12/2024 | 30 | NURJAHAN ENTERPRISE. | 7.55 | 0 | 0
233 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001157/2022-2023 | 697/BD | 03/03/2023 | 90 | M/S PROGATI ENTERPRISE. | 296.42 | 251.35 | 53
234 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line and other allied works in connection with retrofitting work at different places in connection with augmentation of Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001457/2024-2025 | 94/BD | 08/01/2025 | 14 | MONDAL & CO. (BASIRHAT). | 13.34 | 0 | 100
235 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hingalganj mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001800/2023-2024 | 219/HSD | 29/02/2024 | 10 | MONDAL & CO. (BASIRHAT). | 0.97 | 0 | 100
236 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Mamudpur mouza within Hingalganj w/s scheme(Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001801/2023-2024 | 220/HSD | 29/02/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.94 | 0 | 100
237 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000250/2022-2023 | 929/BD | 22/03/2023 | 0 | Resource Division | 50.77 | 0 | 0
238 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXIII) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001163/2023-2024 | 2956/BD | 29/09/2023 | 900 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 2089.66 | 0 | 20
239 | Barasat Division | Hasnabad Sub-Division | Formal work order for Withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Bangali para, near cyclone centre, Sahaji para, shayam molla para, Barik para, Ghorami para etc of Jhupkhali and Nazat BDO office, Metekhali, Parsemari & other tail end areas of Boyermari Abad to improve functionality under Khariat Abad w/s scheme under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000065/2025-2026 | 1749/BD | 28/05/2025 | 120 | CHANCHAL ENTERPRISE & CO. | 177.38 | 0 | 0
240 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Khariat Abad W/S Scheme, Sandeshkhali block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001202/2023-2024 | 4027/BD | 12/10/2023 | 730 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 618.97 | 0 | 50
241 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002741/2021-2022 | 337/HSD | 21/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 4.83 | 1
242 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002742/2021-2022 | 338/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
243 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIAT ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/002743/2021-2022 | 347/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.72 | 1.72 | 1
244 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000233/2022-2023 | 870/BD | 22/03/2023 | 0 | Resource Division | 51.83 | 0 | 0
245 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 No. 400.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe and strainers at T/W site-1 for Ketarchak w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000061/2025-2026 | 844/HSD | 19/05/2025 | 10 | M/S GHOSH CONSTRUCTION. | 3.39 | 0 | 0
246 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) & PH No-1 (Size-3.60x3.00 mtr.) for Kalitala w/s scheme (Z-I), Hingalganj Block under Ketarchak Piped Water Supply Scheme within Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2024-2025 | 2959/BD | 04/10/2024 | 60 | MD.SALIM GAZI. | 21.3 | 0 | 0
247 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Ketarchak water supply scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000724/2023-2024 | 2615/BD | 29/08/2023 | 366 | MONDAL PRECISION PVT.LTD | 507.61 | 0 | 30
248 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No- 1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Ketarchak w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001501/2024-2025 | 634/BD | 28/02/2025 | 60 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.48 | 0 | 0
249 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KETARCHAK Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002695/2021-2022 | 237/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 1
250 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KETARCHAK Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002696/2021-2022 | 238/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
251 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000229/2022-2023 | 878/BD | 22/03/2023 | 0 | Resource Division | 42.93 | 0 | 0
252 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Sohai Swetpur Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000678/2022-2023 | 455/BSD | 20/05/2022 | 30 | RADIANT | 3.38 | 0 | 100
253 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Swetpur (Zone-II) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2023-2024 | 2594/BD | 28/08/2023 | 731 | SINGHA ROY & CO. | 523.5 | 0 | 8
254 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Swetpur-II Water Supply Scheme under JJM programme in Deganga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001017/2024-2025 | 524/BD | 17/02/2025 | 90 | A.P POWER & CONCRETE | 192.44 | 0 | 0
255 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001842/2023-2024 | 1117./1/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0 | 100
256 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000109/2023-2024 | 3091/BD | 10/10/2023 | 0 | Resource Division | 11.72 | 0 | 0
257 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000128/2023-2024 | 4369/BD | 10/11/2023 | 0 | Resource Division | 1.35 | 0 | 0
258 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Paschim Madhyampur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001237/2022-2023 | 1040/BD | 31/03/2023 | 702 | UTPAL CONSTRUCTION & CO. | 487.91 | 296.62 | 68
259 | Barasat Division | Basirhat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-I Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | Assistant Engineer | Junior Engineer | ORD/001477/2024-2025 | 148/BHTSD | 29/01/2025 | 20 | M.R.CONSTRUCTION. | 0.88 | 0 | 90
260 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for PASCHIM MADHYAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002792/2021-2022 | 197/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 3.95 | 1
261 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000147/2023-2024 | 4426/BD | 10/11/2023 | 0 | Resource Division | 13.34 | 0 | 0
262 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000192/2022-2023 | 611/BD | 23/02/2023 | 0 | Resource Division | 10.1 | 0 | 0
263 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000198/2022-2023 | 853/BD | 20/03/2023 | 0 | Resource Division | 51.49 | 0 | 0
264 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for augmentation of Ghatpatila (Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000036/2023-2024 | 1354/BD | 04/05/2023 | 630 | PATHIK PABAN NANDI | 403.71 | 195.93 | 95
265 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ghatpatila (Zone-II) water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000767/2023-2024 | 2688/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 0 | 100
266 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe line under Augmentation work at Ghatpatila (Zone - II) W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001051/2024-2025 | 3736/BD | 27/12/2024 | 180 | PATHIK PABAN NANDI | 120.24 | 0 | 80
267 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Ghatpatila (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001457/2023-2024 | 4409/BD | 10/11/2023 | 60 | ROY CHOWDHURY CONSTRUCTION. | 15.27 | 0 | 100
268 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Ghatpatila (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001488/2023-2024 | 4463/BD | 21/11/2023 | 414 | ROY ENGINEERS. | 9.57 | 0 | 0
269 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002779/2021-2022 | 131/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.89 | 3.89 | 1
270 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000093/2023-2024 | 1861/BD | 23/06/2023 | 0 | Resource Division | 15.65 | 0 | 0
271 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000156/2022-2023 | 1257/BD | 25/04/2023 | 0 | Resource Division | 64.8 | 0 | 0
272 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000340/2021-2022 | 1672/BD | 08/09/2021 | 45 | MONDAL & CO. (BASIRHAT). | 84.12 | 82.46 | 1
273 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC in Noorpur/Bokchara mouza within Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000701/2021-2022 | 1989/HSD | 02/12/2021 | 7 | MONDAL & CO. (BASIRHAT). | 1.63 | 1.63 | 1
274 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000080/2023-2024 | 1809/BD | 19/06/2023 | 0 | Resource Division | 14.78 | 0 | 0
275 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Chandipur water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer |  | ORD/000597/2023-2024 | 2418/BD | 11/08/2023 | 684 | H.I.ENTERPRISE. | 813.8 | 312.87 | 85
276 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001985/2021-2022 | 357/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100
277 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for CHANDIPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001986/2021-2022 | 358/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.31 | 0.28 | 100
278 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000024/2023-2024 | 1251/BD | 25/04/2023 | 0 | Resource Division | 139.05 | 0 | 0
279 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000049/2022-2023 | 2861/BD | 21/09/2022 | 0 | Resource Division | 0 | 0 | 0
280 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sand filling at ditch area for construction of temporary approach road for movement of winch machine and other allied machineries at OHR site within Malancha W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2025-2026 | 936/HSD | 29/05/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.96 | 0 | 0
281 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Mouli mouza within Malancha w/s scheme (Z-II), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000151/2025-2026 | 999/HSD | 04/06/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.96 | 0 | 0
282 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Malancha w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000362/2022-2023 | 2240/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.4 | 35.8 | 1
283 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Malancha water supply scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2022-2023 | 2449/BD | 23/08/2022 | 90 | MONDAL & CO. (BASIRHAT). | 297.24 | 283.96 | 1
284 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Malancha w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000847/2023-2024 | 2655/BD | 01/09/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 50.24 | 37.76 | 37
285 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001066/2023-2024 | 2863/BD | 20/09/2023 | 365 | M/S B.K.ENTERPRISE. | 152.47 | 0 | 75
286 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Withdrawing and relaying of different dia. UPVC pipe line at Mouli mouza in connection with augmentation of Malancha W/S scheme (Z-II), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001401/2024-2025 | 389/BD | 05/02/2025 | 60 | JESMINE ENTERPRISE. | 11.03 | 0 | 100
287 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2022-2023 | 2577/BD | 31/08/2022 | 0 | Resource Division | 21.53 | 0 | 0
288 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000086/2022-2023 | 3363/BD | 17/11/2022 | 0 | Resource Division | 3.53 | 0 | 0
289 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000262/2022-2023 | 915/BD | 22/03/2023 | 0 | Resource Division | 22.12 | 0 | 0
290 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kamlabas Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001336/2021-2022 | 135/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.26 | 3.26 | 1
291 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | Assistant Engineer | Junior Engineer | ORD/000008/2022-2023 | 1174/BD | 19/04/2022 | 90 | SUPRITI ENTERPRISE. | 392.59 | 260.82 | 1
292 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Krishnachandrapur W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000041/2025-2026 | 1542/BD | 15/05/2025 | 120 | B.S.ENTERPRISE. (BASIRHAT) | 51.11 | 0 | 0
293 | Barasat Division | Bangaon Sub-Division | Construction of 3.60 mtr. X 3.00mtr. size Guard room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Krishnachandrapur w/s scheme, Bongaon block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000617/2025-2026 | 678/Bon | 27/05/2025 | 45 | M/S S.HAQUE & CO. | 4.46 | 0 | 0
294 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Krishnacandrapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000640/2023-2024 | 623/Bon | 08/08/2023 | 25 | ROY CHOWDHURY CONSTRUCTION. | 4.73 | 0 | 100
295 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repair and renovation works of R.C.C. Elevated Reservoir of 456 cum for Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001013/2022-2023 | 189/BD | 20/01/2023 | 30 | TRISHA ENTERPRISE & CO. | 19.03 | 18.97 | 100
296 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Krishnachandrapur Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001154/2023-2024 | 2945/BD | 27/09/2023 | 60 | JOY GURU ENTERPRISE | 32.24 | 0 | 100
297 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Krishnachandrapur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001739/2023-2024 | 535/BD | 21/02/2024 | 45 | ANKUSH CONSTRUCTION & CO. | 17.78 | 0 | 100
298 | Barasat Division | Bangaon Sub-Division | Formal Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household and laying of UPVC Dedicated Main Pipe Line towards different mouza for better supply of drinking water along with pipe protection and Road Restoration work under Augmentation work at Krishnachandrapur W/S Scheme at Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002022/2023-2024 | 887/BD | 14/03/2024 | 711 | SAHA CONSTRUCTION & CO | 108.9 | 0 | 90
299 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Krishnachandrapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002952/2021-2022 | 636/BON | 31/12/2021 | 21 | ACHINTA KUMAR HALDER. | 1.26 | 1.14 | 1
300 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2022-2023 | 1362/BD | 13/05/2022 | 0 | Resource Division | 20.47 | 0 | 0
301 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2022-2023 | 1674/BD | 13/06/2022 | 0 | Resource Division | 20.09 | 0 | 0
302 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Dholkhali & Tongtala mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 1670/BD | 08/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 49.88 | 17.52 | 1
303 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000706/2021-2022 | 1994/HSD | 02/12/2021 | 7 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 2 | 2 | 1
304 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Bouthakurani Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001030/2021-2022 | 18/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.9 | 4.9 | 1
305 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001035/2021-2022 | 22/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.9 | 4.9 | 1
306 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001111/2021-2022 | 14/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 1
307 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bouthakurani w/s scheme (Zone-I to III), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001667/2021-2022 | 421/HSD | 04/03/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.73 | 4.78 | 1
308 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bouthakurani w/s scheme (Zone-IV to V), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001668/2021-2022 | 422/HSD | 04/03/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.73 | 4.73 | 1
309 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bouthakurani w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001748/2021-2022 | 464/HSD | 10/03/2022 | 10 | R.K.MANDAL AND CO. | 3.39 | 3.39 | 1
310 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001750/2021-2022 | 465/HSD | 10/03/2022 | 10 | R.K.MANDAL AND CO. | 4.85 | 4.85 | 1
311 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000086/2023-2024 | 1818/BD | 19/06/2023 | 0 | Resource Division | 16.39 | 0 | 0
312 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Sinking of 1 no. 300 mm. x 200 mm. dia. 214 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Ward No.- 6 under Ashokenagar-Kalyangar Municipality within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002671/2021-2022 | 2452/BD | 17/12/2021 | 30 | NADIA TUBEWELLS | 2.89 | 2.89 | 1
313 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Deora W/S Scheme in Swarupnagar Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002023/2021-2022 | 126/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.23 | 3.19 | 1
314 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAGDAH Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/002056/2021-2022 | 990/BD. | 27/05/2021 | 45 | UMWELT ENGINEER PVT.LTD. | 89.35 | 11.75 | 1
315 | Barasat Division | Bangaon Sub-Division | - Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Bongaon Sub-Division P.H.E. Dte. (Period from 01.02.2021 to 31.01.2022.) | Assistant Engineer | Junior Engineer | ORD/002217/2020-2021 | 77/Bon | 29/01/2021 | 365 | ROY ENGINEERS. | 1.73 | 0 | 1
316 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Khulna Bhandarkhali (Zone-I) Water Supply scheme Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000482/2021-2022 | 1740/BD | 14/09/2021 | 45 | M/S B.K.ENTERPRISE. | 76.95 | 76.79 | 1
317 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Khulna Bhanderkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001719/2021-2022 | 1981/HSD | 02/12/2021 | 10 | M/S NIRMAN CONSTRUCTION. | 3.54 | 3.54 | 1
318 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dobila Piped Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000567/2021-2022 | 1954/BD | 08/10/2021 | 15 | M/S SUKANTA ENTERPRISE. | 14.73 | 13.84 | 1
319 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002025/2021-2022 | 128/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 0 | 1
320 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000056/2022-2023 | 2863/BD | 21/09/2022 | 0 | Resource Division | 3.08 | 0 | 0
321 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Joypur Gopmahal Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000563/2021-2022 | 1951/BD | 08/10/2021 | 15 | SHIBU BISWAS. | 21.73 | 20.05 | 1
322 | Barasat Division | Basirhat Sub-Division | Sinking of 300 Mtr.Deep 100X40 mm dia Trial- cum-production Tube-Well fitting with PVC Pipes and strainer with Indian Mark-II at Joypur Gopmahal of Basirhat-II Block under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002657/2021-2022 | 1111/ BHT SD | 27/08/2021 | 20 | M/S MAA TARA ENTERPRISE | 2.34 | 1.95 | 1
323 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Dhopaberia Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000337/2021-2022 | 1652/BD | 07/09/2021 | 30 | UTPAL CONSTRUCTION & CO. | 53.77 | 52.68 | 1
324 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DHOPABERIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001959/2021-2022 | 310/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.6 | 3.6 | 1
325 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2021-2022 | 2242/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0
326 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Mirzanagar Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000335/2021-2022 | 1656/BD | 07/09/2021 | 45 | CHANCHAL ENTERPRISE & CO. | 85.87 | 83.5 | 1
327 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for MIRZANAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001956/2021-2022 | 307/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.78 | 3.69 | 1
328 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Sohai Swetpur Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002944/2021-2022 | 818/BSD | 10/12/2021 | 30 | BHABANI ENTERPRISE. | 1.84 | 1.75 | 0
329 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Kachua Swarupnagar Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000333/2021-2022 | 1654/BD | 07/09/2021 | 45 | UTPAL CONSTRUCTION & CO. | 86.71 | 85.64 | 1
330 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for KACHUA SWARUPNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001957/2021-2022 | 308/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.29 | 4.07 | 1
331 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-I) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001317/2021-2022 | 123/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 0 | 1
332 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-II) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001318/2021-2022 | 124/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 0 | 1
333 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-III) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001320/2021-2022 | 125/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.42 | 0 | 1
334 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chowberia Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001322/2021-2022 | 127/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 0 | 1
335 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001328/2021-2022 | 129/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 0 | 1
336 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001330/2021-2022 | 131/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.89 | 0 | 1
337 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kola Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001337/2021-2022 | 136/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.64 | 0 | 1
338 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001339/2021-2022 | 138/Bon | 18/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.05 | 0 | 1
339 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Malidah Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001343/2021-2022 | 140/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 0 | 1
340 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for PASCHIM MADHYAMPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001941/2021-2022 | 197/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 0 | 1
341 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GACHHARATI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001943/2021-2022 | 199/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.69 | 0 | 1
342 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for NALKORA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001946/2021-2022 | 202/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.79 | 0 | 1
343 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR DHOKRA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001949/2021-2022 | 205/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 0 | 1
344 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-I Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001950/2021-2022 | 206/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.15 | 0 | 1
345 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAJENDRAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001960/2021-2022 | 311/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.19 | 0 | 1
346 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DAKSHIN DEBIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001961/2021-2022 | 312/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 0 | 1
347 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SRINAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001968/2021-2022 | 342/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.1 | 0 | 1
348 | Barasat Division | Basirhat Sub-Division | Additional survey work for DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001996/2021-2022 | 377/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.66 | 0 | 1
349 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Kapileswarpur Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/002034/2021-2022 | 940/BD | 28/03/2022 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 164.9 | 108.96 | 1
350 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002679/2021-2022 | 208/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.72 | 0 | 1
351 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Bansghata Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002680/2021-2022 | 142/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 0 | 1
352 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2022-2023 | 2866/BD | 21/09/2022 | 0 | Resource Division | 0.1 | 0 | 0
353 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.08.2022 to 31.07.2023 = 365 days. | Assistant Engineer | Junior Engineer | ORD/000224/2022-2023 | 1118/HSD | 08/07/2022 | 1 | RANJIT KUMAR MANDAL. | 3.23 | 11.93 | 100
354 | Barasat Division | Habra Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Janaphul Water Supply Scheme at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000753/2021-2022 | 2389/BD | 09/12/2021 | 45 | ORIENT CONSTRUCTION. | 72.42 | 67.56 | 1
355 | Barasat Division | Habra Sub-Division | Acceptance cum Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B. | Assistant Engineer | Junior Engineer | ORD/001180/2023-2024 | 253/BKP | 31/07/2023 | 184 | GOPAL SINGHA. | 0.87 | 0 | 40
356 | Barasat Division | Basirhat Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area under Magurali Water Supply Scheme at Baduria Block, District- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000823/2021-2022 | 2439/BD | 13/12/2021 | 90 | UTPAL CONSTRUCTION & CO. | 232.79 | 205.13 | 1
357 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for MAGURALI Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001978/2021-2022 | 350/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 1
358 | Barasat Division | Basirhat Sub-Division | Formal Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Itinda Panitar Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000912/2021-2022 | 2622/BD | 27/12/2021 | 90 | SUBHASH BOSE. | 171.59 | 164.59 | 1
359 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for ITINDA PANITOR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001933/2021-2022 | 189/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
360 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000177/2022-2023 | 598/BD | 23/02/2023 | 0 | Resource Division | 22.18 | 0 | 0
361 | Barasat Division | Basirhat Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Arsula Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000817/2021-2022 | 2437/BD | 13/12/2021 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 194.62 | 160.59 | 1
362 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for ARSULA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001987/2021-2022 | 359/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.34 | 3.34 | 1
363 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000067/2022-2023 | 2340/BD | 26/09/2022 | 0 | Resource Division | 18.3 | 0 | 0
364 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - II) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000044/2023-2024 | 1406/BD | 08/05/2023 | 30 | ARUN TRADERS | 14.49 | 0 | 100
365 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 2 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2024-2025 | 2410/BD | 22/08/2024 | 35 | M/S MITRA CONSTRUCTION | 5.71 | 0 | 0
366 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 3 of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000356/2024-2025 | 2409/BD | 22/08/2024 | 45 | JOY ENTERPRISE | 6.1 | 0 | 100
367 | Barasat Division | Habra Sub-Division | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000534/2022-2023 | 2448/BD | 23/08/2022 | 900 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 526.45 | 381.78 | 1
368 | Barasat Division | Habra Sub-Division | construction of the Service Road 35.00 Mtr. Length and 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing in Head Work Site of Maslandapur- II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000603/2024-2025 | 916/HAB | 30/10/2024 | 10 | M/S GUHA CONSTRUCTION. | 2.26 | 0 | 0
369 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of boundary wall for raising height, drain and repairing of existing boundary wall for the Head Work site of Maslandapur II Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000702/2024-2025 | 3160/BD | 14/11/2024 | 40 | S.G. ENTERPRISE | 5.12 | 0 | 100
370 | Barasat Division | Habra Sub-Division | Improvement of Iron Elimination Plant at Maslandapur Zone II WS Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001406/2023-2024 | 671/HAB | 30/10/2023 | 30 | S.G. ENTERPRISE | 4.47 | 0 | 100
371 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Maslandapur(Zone - II) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001533/2023-2024 | 07/BD | 02/01/2024 | 30 | M/S B.K.ENTERPRISE. | 19.45 | 0 | 100
372 | Barasat Division | Habra Sub-Division | Construction of Service Road (10 Mtr. Length & 2 Mtr. Wide while 1.00 Mtr existing Road ) for Pump House No:2 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001886/2023-2024 | 134/HAB | 05/02/2024 | 15 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 0.75 | 0 | 100
373 | Barasat Division | Habra Sub-Division | Construction of Service Road (10 Mtr. Length & 2 Mtr. Width) for Pump House No:3 of Maslandapur II Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001887/2023-2024 | 135/HAB | 05/02/2024 | 15 | JOY ENTERPRISE | 0.6 | 0 | 100
374 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. - 1 & 2 of Maslandapur W/S scheme (Zone - II) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002977/2021-2022 | 490/HAB | 30/11/2021 | 30 | ANJALI CONSTRUCTION. | 2.18 | 2.17 | 1
375 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2022-2023 | 2515/BD | 25/08/2022 | 0 | Resource Division | 22.72 | 0 | 0
376 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000057/2023-2024 | 1558/BD | 23/05/2023 | 0 | Resource Division | 1.85 | 0 | 0
377 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000124/2022-2023 | 3790/BD | 22/12/2022 | 0 | Resource Division | 34.22 | 0 | 0
378 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with retrofitting of Kanmari w/s scheme (Zone-I), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000971/2022-2023 | 99/BD | 11/01/2023 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 282.73 | 277.6 | 1
379 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Kanmari mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000998/2023-2024 | 1082/HSD | 31/08/2023 | 10 | SARKAR ENTERPRISE | 0.93 | 0 | 100
380 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Nalkora mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001000/2023-2024 | 1083/HSD | 31/08/2023 | 10 | SARKAR ENTERPRISE | 0.92 | 0 | 100
381 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Kanmari water supply scheme (Zone-I), Sandeshkhali-I Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001248/2023-2024 | 4180/BD | 30/10/2023 | 365 | TRISHA ENTERPRISE & CO. | 113.9 | 0 | 70
382 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at PH No-1 & 2 within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001334/2023-2024 | 4406/BD | 10/11/2023 | 90 | NIKHIL SAMADDAR | 26.72 | 0 | 70
383 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000026/2022-2023 | 1828/BD | 29/06/2022 | 0 | Resource Division | 195.63 | 0 | 0
384 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work in different places of Bhangatushkhali Mouza in connection with retrofitting of Bhangatushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 1697/BD | 08/06/2023 | 30 | AMAL DUTTA ROY | 167.81 | 90.35 | 100
385 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Bhangatushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000164/2022-2023 | 1668/BD | 13/06/2022 | 90 | S. GHOSH & ASSOCIATES PVT. LTD. | 168.43 | 167.55 | 1
386 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Bhangatushkhali W/s Scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000793/2024-2025 | 3311/BD | 27/11/2024 | 30 | SUBHAJIT SAHA | 31.69 | 0 | 0
387 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection within Bhangatushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001419/2024-2025 | 143/BD | 13/01/2025 | 75 | PRITAM MUKHOPADHYAY. | 8.88 | 0 | 0
388 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Bhanga Tushkhali mouza within Bhanga Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002837/2021-2022 | 536/HSD | 16/03/2022 | 15 | MD.SALIM GAZI. | 4.75 | 4.68 | 1
389 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of Boundary Wall (90 m Length) for Pump House no 1 of Talsa & Adj Mouzas water Supply Scheme in connection with Augmentation work under JJM project with in the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2024-2025 | 2583/BD | 05/09/2024 | 45 | BRIGHT STAR CO-OP LABOUR CONTRACTOR & CONSTRUCTION SOCIETY LTD. | 14.76 | 0 | 0
390 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Talsa & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000414/2022-2023 | 2313/BD | 03/08/2022 | 90 | M/S B.K.ENTERPRISE. | 230.62 | 154.79 | 1
391 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of Boundary Wall for Pump House No - 2 of Talsa & Adj Mouzas water Supply Scheme in connection with Augmentation work under JJM project with in the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000588/2024-2025 | 3065/BD | 25/10/2024 | 40 | PUSPA CONSTRUCTION. | 5.62 | 0 | 0
392 | Barasat Division | Habra Sub-Division | Construction of Service Road 40 Mtr. Length X 2 Mtr. Width for Pump House No 1 of Talsa and Adj Mouzas Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2024-2025 | 920/HAB | 30/10/2024 | 10 | TALUKDER & CO. | 2.44 | 0 | 0
393 | Barasat Division | Habra Sub-Division | Special repair and renovation of pump house and other Allied Works for Pump House No - 2 of Talsa and Adj Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000900/2024-2025 | 932/HAB | 05/11/2024 | 20 | M/S SANKAR ENTERPRISE. | 2.58 | 0 | 0
394 | Barasat Division | Habra Sub-Division | Special repair and renovation of pump house and other Allied Works of Pump House No - 1 under Talsa and Adj Mouzas WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000904/2024-2025 | 936/HAB | 06/11/2024 | 20 | TALUKDER & CO. | 2.66 | 0 | 0
395 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Talsa & Adj Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000975/2023-2024 | 2779/BD | 11/09/2023 | 60 | M/S SUKANTA ENTERPRISE. | 39.1 | 0 | 100
396 | Barasat Division | Habra Sub-Division | Improvement of Iron Elimination Plant at Talsa & Adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001423/2023-2024 | 672/HAB | 30/10/2023 | 30 | M/S SANKAR ENTERPRISE. | 3.29 | 0 | 100
397 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of Service Road(10 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Talsa & Adj Mouzas Water Supply Scheme in connection with Augmentation work undeer JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001900/2023-2024 | 172/HAB | 19/02/2024 | 15 | M/S LATIKA CONSTRUCTION. | 0.61 | 0 | 0
398 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. ¿ 1 & 2 of Talsa& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under BarasatDivision, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002985/2021-2022 | 515/HAB | 10/12/2021 | 30 | DAS & CO. | 1.55 | 1.51 | 1
399 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000129/2022-2023 | 3792/BD | 22/12/2022 | 0 | Resource Division | 14.47 | 0 | 0
400 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001340/2021-2022 | 139/Bon | 18/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 3.86 | 3.86 | 1
401 | Barasat Division | Habra Sub-Division | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis ( from 01-01-2022 to 30-06-2022) for the Office use of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002639/2021-2022 | 2688/ BD | 31/12/2021 | 181 | DIPANKAR NASKAR. | 0.86 | 0 | 1
402 | Barasat Division | Hasnabad Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03462/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 31.71 | 0 | 0
403 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baro Bankra water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 1720/BD | 08/06/2023 | 642 | MADE & TRADE CO. | 433.09 | 114.11 | 58
404 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for special repair renovation of existing structures like Pump house, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Akhipur, Baro Bankra, Bithari Z-I, Bithari Z-II water supply scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000265/2025-2026 | 2381/BD | 10/07/2025 | 150 | JP CONSTRUCTION & SUPPLIERS. | 81.91 | 0 | 0
405 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at pump house 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Boro Bankra Water Supply Scheme in Swarupnagar Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000773/2024-2025 | 3265/BD | 25/11/2024 | 120 | JOY GURU ENTERPRISE | 21.74 | 0 | 100
406 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2023-2024 | 1271/BD | 25/04/2023 | 0 | Resource Division | 149.36 | 0 | 0
407 | Barasat Division | Basirhat Sub-Division | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Jafarpur WS Scheme | Assistant Engineer | Junior Engineer | BILL/00833/2024-2025 | BP-2024-25-262 | 12/09/2024 | 0 | H.I.ENTERPRISE. | 23.64 | 0 | 0
408 | Barasat Division | Basirhat Sub-Division | Repairing of damaged concrete road due to laying of Pipe Line in various place of zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. [SM/11585] | Assistant Engineer | Junior Engineer | ORD/000061/2024-2025 | 916/BHTSD | 24/05/2024 | 7 | RAKESH ENTERPRISE. | 0.96 | 0 | 100
409 | Barasat Division | Basirhat Sub-Division | Relaying of 90mm, 110mm dia UPVC pipe line and repairing of FHTC connection which damaged due to construction of drain from local Panchayet at Node no. 103 to 137 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000249/2024-2025 | 1022/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.89 | 0 | 100
410 | Barasat Division | Basirhat Sub-Division | Relaying of 90mm, 110mm, 125mm, 160mm dia UPVC pipe line which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 429/465 & 543 to 563 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000250/2024-2025 | 1023/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.99 | 0 | 100
411 | Barasat Division | Basirhat Sub-Division | Relaying of 75mm, 90mm, 110mm, 160mm dia UPVC pipe line which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 402 to 190 to 57 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000251/2024-2025 | 1024/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.99 | 0 | 100
412 | Barasat Division | Basirhat Sub-Division | Relaying of 160mm dia UPVC pipe line and repairing of FHTC connection which damaged due to strengthening and culvert construction in Gopalpur Haroa road by PWD (Roads) Department at Node no. 190 to 57 of Zafarpur pwss under Basirhat Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000252/2024-2025 | 1025/BHTSD | 28/06/2024 | 7 | RAKESH ENTERPRISE. | 0.96 | 0 | 100
413 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Jafarpur Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000770/2024-2025 | 3256/BD | 25/11/2024 | 90 | GHOSH CONSTRUCTION. | 21.75 | 0 | 0
414 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Jafarpur water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000865/2022-2023 | 3763/BD | 20/12/2022 | 90 | H.I.ENTERPRISE. | 438.55 | 438.38 | 82
415 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000171/2022-2023 | 489/BD | 17/02/2023 | 0 | Resource Division | 28.3 | 0 | 0
416 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bajitpur Zone-I B water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000004/2023-2024 | 1124/BD | 11/04/2023 | 90 | SHIBU BISWAS. | 209.36 | 115.02 | 82
417 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of (Bajitpur Zone-I A) water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000133/2023-2024 | 1709/BD | 08/06/2023 | 630 | UTPAL CONSTRUCTION & CO. | 356.76 | 0 | 42
418 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Bajitpur Zone-IB water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000987/2023-2024 | 2802/BD | 12/09/2023 | 30 | DHELA BABA ENTERPRISE | 21.53 | 0 | 0
419 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2023-2024 | 1242/BD | 25/04/2023 | 0 | Resource Division | 95.52 | 0 | 0
420 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000060/2023-2024 | 1625/BD | 01/06/2023 | 0 | Resource Division | 9.22 | 0 | 0
421 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Gokulpur water supply scheme in Swarupnagar block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001245/2022-2023 | 1039/BD | 31/03/2023 | 730 | UTPAL CONSTRUCTION & CO. | 411.53 | 200.14 | 70
422 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Gokulpur Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002757/2021-2022 | 448/ BHTSD | 23/03/2022 | 150 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.32 | 4.32 | 1
423 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2023-2024 | 1243/BD | 25/04/2023 | 0 | Resource Division | 15.85 | 0 | 0
424 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000191/2022-2023 | 605/BD | 23/02/2023 | 0 | Resource Division | 20.7 | 0 | 0
425 | Barasat Division | Barasat Sadar Sub-Division | Repair and Renovation Work of Pump House at 2nd Tubewell site and allied works at Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000464/2024-2025 | 582/BSD | 10/09/2024 | 82 | M/S S.HAQUE & CO. | 2.55 | 0 | 100
426 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (3rd Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000470/2024-2025 | 585/BSD | 10/09/2024 | 20 | MANGES INDUSTRIAL CORPORATION. | 2.82 | 0 | 100
427 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Nebadhui Duttapukur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000680/2022-2023 | 457/BSD | 20/05/2022 | 30 | RADIANT | 3.7 | 0 | 100
428 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Nebhadui Duttapukur Z-II Water Supply Scheme under JJM programme in Barasat-I block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001018/2024-2025 | 3737/BD | 27/12/2024 | 90 | M/S B.K.ENTERPRISE. | 100.4 | 0 | 0
429 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Nebadhui Duttapukur Zone-II PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/001103/2024-2025 | 1005/BSD | 02/01/2025 | 20 | ROMI TREDERS. | 3.89 | 0 | 0
430 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 550 cum capacity 20Mtr. Height R.C.C. Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Nebadhui Duttapukur Zone-II Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001201/2023-2024 | 4122/BD | 17/10/2023 | 623 | M/S B.K.ENTERPRISE. | 598.56 | 0 | 35
431 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000031/2023-2024 | 1281/BD | 25/04/2023 | 0 | Resource Division | 86.51 | 0 | 0
432 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000116/2023-2024 | 4021/BD | 12/10/2023 | 0 | Resource Division | 24.5 | 0 | 0
433 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials and Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Atpukur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 1550/BD | 22/05/2023 | 669 | SARKAR ENTERPRISE & CO. | 210.66 | 136.99 | 95
434 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 Nos. 300.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Atpukur w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2023-2024 | 1132/HSD | 05/09/2023 | 30 | SARKAR ENTERPRISE & CO. | 2.63 | 0 | 100
435 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Atpukur water supply scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001466/2024-2025 | 341/HSD | 06/02/2025 | 10 | RATAN SARKAR. | 0.72 | 0 | 100
436 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-A). | Assistant Engineer | Junior Engineer | ORD/001908/2023-2024 | 280/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.87 | 0 | 100
437 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-B). | Assistant Engineer | Junior Engineer | ORD/001909/2023-2024 | 281/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.88 | 0 | 100
438 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-D). | Assistant Engineer | Junior Engineer | ORD/001912/2023-2024 | 284/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
439 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-E). | Assistant Engineer | Junior Engineer | ORD/001914/2023-2024 | 286/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
440 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-H). | Assistant Engineer | Junior Engineer | ORD/001918/2023-2024 | 290/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.87 | 0 | 100
441 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-J). | Assistant Engineer | Junior Engineer | ORD/001920/2023-2024 | 292/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
442 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-C). | Assistant Engineer | Junior Engineer | ORD/001936/2023-2024 | 260/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
443 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002699/2021-2022 | 241/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.63 | 4.63 | 1
444 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000223/2022-2023 | 874/BD | 22/03/2023 | 0 | Resource Division | 15.62 | 0 | 0
445 | Barasat Division | Habra Sub-Division | Formal work order for Construction of 2 nos. (1250 CuM & 600 CuM) capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-X and XI Head work sites including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001211/2023-2024 | 4072/BD | 16/10/2023 | 1095 | GARGO TRADERS | 3804.4 | 0 | 44
446 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXVI) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001165/2023-2024 | 2955/BD | 29/09/2023 | 900 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 1603.84 | 0 | 75
447 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Niruli Abad w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 1692/BD | 07/06/2023 | 1092 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 188.07 | 0 | 58
448 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (NIRULI ABAD Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002729/2021-2022 | 292/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.68 | 3.68 | 1
449 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000207/2022-2023 | 889/BD | 22/03/2023 | 0 | Resource Division | 12.1 | 0 | 0
450 | Barasat Division | Bangaon Sub-Division | Formal work order for Construction of 1150 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at (Zone- XXV) i.e. Jhikra & Laying of Distribution System, Providing FHTC, Construction Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XXV) under Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project¿ under Barasat Division, P.H.E. Dte. Gaighata Block, PART-G. | Assistant Engineer | Junior Engineer | ORD/001215/2023-2024 | 4081/BD | 16/10/2023 | 747 | GBC INFRASTRUCTURE PRIVATE LIMITED | 1699.27 | 0 | 45
451 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia DI-UPVC rising/distribution pipe line by UC bullah/bamboo pile for Kachurhula Zone-II w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 1610/BD | 19/05/2025 | 30 | SARKAR ENTERPRISE & CO. | 15.55 | 0 | 0
452 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Kachurhula w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000093/2023-2024 | 1524/BD | 19/05/2023 | 958 | ROY CHOWDHURY CONSTRUCTION. | 147.05 | 79.51 | 96
453 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002718/2021-2022 | 281/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.09 | 3.09 | 1
454 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-II Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002994/2021-2022 | 281/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.09 | 0 | 1
455 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000209/2022-2023 | 885/BD | 22/03/2023 | 0 | Resource Division | 14.83 | 0 | 0
456 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Bamangachi PWSS (1st Tubewell - Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000427/2024-2025 | 559/BSD | 09/09/2024 | 20 | SANTU GHOSH. | 4.87 | 0 | 100
457 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Bamangachi PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000428/2024-2025 | 560/BSD | 09/09/2024 | 20 | TALUKDER & CO. | 4.64 | 0 | 100
458 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Bamangachhi Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-02 | Assistant Engineer | Junior Engineer | ORD/000604/2022-2023 | 657/BSD | 18/08/2022 | 30 | RADIANT | 3 | 0 | 100
459 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Bamangachhi water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2023-2024 | 2650/BD | 01/09/2023 | 366 | S.S.ENTERPRISE. (BAMANGACHI) | 538.69 | 0 | 100
460 | Barasat Division | Barasat Sadar Sub-Division | Renovation of Iron Elimination Plant at Bamangachhi Water Supply Scheme at Pump House - I (46m3/hr.) within Barasat-I Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001381/2024-2025 | 852/BSD | 28/11/2024 | 30 | MANGES INDUSTRIAL CORPORATION. | 4.35 | 0 | 100
461 | Barasat Division | Barasat Sadar Sub-Division | Renovation of Iron Elimination Plant at Bamangachhi Water Supply Scheme at Pump House - IV (46m3/hr.) within Barasat-I Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001382/2024-2025 | 853/BSD | 28/11/2024 | 30 | MANGES INDUSTRIAL CORPORATION. | 4.35 | 0 | 0
462 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. big dia. 210 mtr deep Tubewell by D.R. Rig method having 250 mm dia 42.0 mtr. long PVC housing pipe & 150 mm dia 30.0 mtr. long filter for Augmentation Bamangachhi Water Supply Scheme (2nd T/W Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001771/2023-2024 | 588/BD | 23/02/2024 | 30 | SUBHAJIT SAHA | 11.22 | 0 | 100
463 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000032/2023-2024 | 1287/BD | 25/04/2023 | 0 | Resource Division | 73.47 | 0 | 0
464 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000110/2023-2024 | 3092/BD | 10/10/2023 | 0 | Resource Division | 12.26 | 0 | 0
465 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000124/2023-2024 | 4368/BD | 10/11/2023 | 0 | Resource Division | 21.03 | 0 | 0
466 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House at PH No- 2 for Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000292/2023-2024 | 796/HSD | 13/07/2023 | 7 | SAGAR DAS. | 0.62 | 0 | 100
467 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Rajbari Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2022-2023 | 633/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.72 | 3.72 | 1
468 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump house and Dismantling, Re-construction of boundary wall and approach road for movement of rig & other machineries for sinking of big dia. TW at PH no- 1 in connection with Augmentation of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000907/2023-2024 | 2718/BD | 05/09/2023 | 21 | M/S ANUBHAB CONSTRUCTION. | 5.06 | 0 | 100
469 | Barasat Division | Hasnabad Sub-Division | Formal work order for for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajbari water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2022-2023 | 829/BD | 15/03/2023 | 90 | M/S DATTA ENTERPRISE. | 279.81 | 159.23 | 100
470 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional household tap connection at Rajbari Purbapara SSK & Paschim Laukhali Sobahan Molla Smriti FP School, within the command area of Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001918/2024-2025 | 545/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.5 | 0 | 0
471 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000243/2022-2023 | 940/BD | 22/03/2023 | 0 | Resource Division | 25.03 | 0 | 0
472 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Electrocoagulation Based Package Surface Water based Water Supply Scheme (Solar Power) in Minakhan Block, North 24 Parganas District of Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001064/2022-2023 | 407/BD | 09/02/2023 | 30 | CARBON SERVICES INDIA | 45.12 | 35.83 | 0
473 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 200 cum capacity CWR , pipe connection and cost of pipes, specials for Augmentation of Sandeshkhali water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000027/2025-2026 | 1499/BD | 13/05/2025 | 180 | SUFIA ENTERPRISE | 53.52 | 0 | 0
474 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line & providing Functional Household Tap Connection with other allied works for Augmentation of Sandeshkhali water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2023-2024 | 1300/BD | 26/04/2023 | 901 | KINGS & CO. | 356.31 | 0 | 45
475 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks ( Sandeshkhali- I & II ) in North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 755/HSD | 19/07/2024 | 10 | IMAGIN | 0.98 | 0 | 100
476 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000729/2023-2024 | 2478/BD | 18/08/2023 | 540 | M/S SUKANTA ENTERPRISE. | 31.71 | 0 | 100
477 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Radharani High School at Sandeshkhali in connection with augmentation of Sandeshkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000868/2023-2024 | 1054/HSD | 31/08/2023 | 7 | M/S RAJPATH CONSTRUCTION. | 0.9 | 0 | 0
478 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Dhamakhali mouza with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001026/2024-2025 | 3583/BD | 18/12/2024 | 30 | TITUMIR INTERNATIONAL | 25.86 | 0 | 0
479 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001295/2024-2025 | 865/BD | 19/03/2025 | 360 | M/S K.B.ENTERPRISE. | 102.2 | 0 | 30
480 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection at Dhamakhali mouza within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001417/2024-2025 | 864/BD | 19/03/2025 | 225 | RUDRA DAS. | 10.58 | 0 | 90
481 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection at Rampur & Jhupkhali adjoining mouza within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001418/2024-2025 | 863/BD | 19/03/2025 | 75 | ABUL KALAM GAZI | 10.6 | 0 | 100
482 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002429/2023-2024 | 33/HSD | 09/01/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 100
483 | Barasat Division | Hasnabad Sub-Division | Work order for Supply of one motor launch on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.11.23 to 31.03.24 = 152 days. | Assistant Engineer | Junior Engineer | ORD/002444/2023-2024 | 1362/HSD | 31/10/2023 | 152 | SUSMITA MANDAL. | 2.26 | 0 | 10
484 | Barasat Division | Hasnabad Sub-Division | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.23 to 31.10.23 = 61 days. | Assistant Engineer | Junior Engineer | ORD/002445/2023-2024 | 1030/HSD | 29/08/2023 | 61 | SUSMITA MANDAL. | 0.91 | 0 | 5
485 | Barasat Division | Hasnabad Sub-Division | Work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.11.23 to 30.04.24 | Assistant Engineer | Junior Engineer | ORD/002446/2023-2024 | 1396/HSD | 31/10/2023 | 182 | RANJIT KUMAR MANDAL | 1.61 | 0 | 5
486 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002449/2023-2024 | 34/HSD | 09/01/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.92 | 0 | 100
487 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000121/2023-2024 | 4174/BD | 30/10/2023 | 0 | Resource Division | 10.35 | 0 | 0
488 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000248/2022-2023 | 937/BD | 22/03/2023 | 0 | Resource Division | 50.86 | 0 | 0
489 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. Sl. No.-02 | Assistant Engineer | Junior Engineer | ORD/000288/2022-2023 | 549/BSD | 29/06/2022 | 30 | RADIANT | 3.41 | 0 | 100
490 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-II Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2024-2025 | 2229/BD | 07/08/2024 | 450 | CHANDA CONSTRUCTION. | 433.82 | 0 | 25
491 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for construction of 750 cum capacity 20 mtr. height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentaion of Bodai (Zone-II) water supply scheme under Barsasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000763/2023-2024 | 2617/BD | 29/08/2023 | 366 | SUPRITI ENTERPRISE. | 874.9 | 0 | 20
492 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Bodai Zone-II PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/001099/2024-2025 | 1002/BSD | 02/01/2025 | 20 | M/S DAS & CO. | 3.93 | 0 | 0
493 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Bodai Zone-II PWSS (1st Tubewell - Boundary Wall). | Assistant Engineer | Junior Engineer | ORD/001101/2024-2025 | 1003/BSD | 02/01/2025 | 20 | K.D ENTERPRISE. | 2.36 | 0 | 0
494 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-C | Assistant Engineer | Junior Engineer | ORD/001839/2023-2024 | 1116A/BSD | 09/02/2024 | 4 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
495 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000028/2023-2024 | 1266/BD | 25/04/2023 | 0 | Resource Division | 158.32 | 0 | 0
496 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000112/2023-2024 | 3095/BD | 10/10/2023 | 0 | Resource Division | 21.72 | 0 | 0
497 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Sultanpur Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000768/2022-2023 | 632/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3 | 3 | 1
498 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road with cement concrete at PH No.-1 within Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2023-2024 | 1130/HSD | 05/09/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 1.83 | 0 | 100
499 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sultanpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001158/2022-2023 | 698/BD | 03/03/2023 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 239.69 | 210.08 | 92
500 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of UPVC distribution pipe line & Providing FHTC for the leftout portion in connection with Augmentation of Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001395/2024-2025 | 261/HSD | 30/01/2025 | 10 | M/S TAMAL CHAKRABORTY. | 0.97 | 0 | 100
501 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001980/2023-2024 | 917/BD | 15/03/2024 | 45 | M/S B.K.ENTERPRISE. | 50.73 | 0 | 100
502 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. X 200mm.dia. 190.00mtr. deep tubewell by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long filter for Augumentation of Berachampa Zone-IV Water Supply Scheme at OHR Site under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000280/2024-2025 | 2193/BD | 05/08/2024 | 30 | ANJALI ENTERPRISE. | 13.3 | 0 | 100
503 | Barasat Division | Barasat Sadar Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-IV under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000610/2022-2023 | 671/BSD | 29/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.95 | 3.95 | 1
504 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Boundary Wall at Nandipara Kuchemora Under Berachampa Zone-IV Water Supply Scheme under Deganga Block, under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000992/2024-2025 | 3476/BD | 10/12/2024 | 30 | JP CONSTRUCTION & SUPPLIERS. | 32.77 | 0 | 0
505 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 700 cum capacity 20mtr staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Berachampa Zone-IV Water Supply scheme under Barasat Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001204/2023-2024 | 4018/BD | 12/10/2023 | 730 | A.P POWER & CONCRETE | 877.47 | 0 | 30
506 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different villages of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-F | Assistant Engineer | Junior Engineer | ORD/001849/2023-2024 | 1120./1/BSD | 09/02/2024 | 4 | S.M.TRADERS. | 0.87 | 0 | 100
507 | Barasat Division | Barasat Sadar Sub-Division | Construction of Pump House with latrine at Berachampa Zone-IV water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002153/2023-2024 | 1244/BSD | 15/03/2024 | 31 | M/S S.HAQUE & CO. | 4.88 | 0 | 100
508 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000043/2023-2024 | 1278/BD | 25/04/2023 | 0 | Resource Division | 197.95 | 0 | 0
509 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000106/2023-2024 | 3086/BD | 10/10/2023 | 0 | Resource Division | 28.89 | 0 | 0
510 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000133/2023-2024 | 4371/BD | 10/11/2023 | 0 | Resource Division | 94.42 | 0 | 0
511 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Pump House with latrine at Joypul water Supply Scheme under Barasat-I Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2024-2025 | 1922/BD | 09/07/2024 | 184 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 5.09 | 0 | 100
512 | Barasat Division | Barasat Sadar Sub-Division | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.05.2023 to 31.08.2023) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 382/BST | 27/04/2023 | 123 | DEBAPRASAD MONDAL. | 0.58 | 0 | 0
513 | Barasat Division | Barasat Sadar Sub-Division | Continuation work order for Hiring 1(One) No. Diesel Luxury Car on Daily basis for 6 (six) months for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred and seventy five only) per day excluding fuel. (Period from 01/09/2024 to 28/02/2024) | Assistant Engineer | Junior Engineer | ORD/000377/2024-2025 | 504/BSD | 29/08/2024 | 183 | ANJALI ENTERPRISE. | 0.86 | 0 | 0
514 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Joypul PWSS (1st Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000436/2024-2025 | 567/BSD | 09/09/2024 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.12 | 0 | 100
515 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Joypul PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000437/2024-2025 | 568/BSD | 09/09/2024 | 20 | NEW MA TARA ENTERPRISE. | 2.95 | 0 | 100
516 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Joypul PWSS (2nd Tubewell - Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000451/2024-2025 | 573/BSD | 10/09/2024 | 82 | SANTU GHOSH. | 3.09 | 0 | 100
517 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Joypul Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | Assistant Engineer | Junior Engineer | ORD/000603/2022-2023 | 656/BSD | 18/08/2022 | 30 | RADIANT | 3.73 | 0 | 100
518 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 550cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and laying of Rising main & distribution pipe line by DI & UPVC and Providing FHTC for Augmentation of Joypul water supply Scheme under Barasat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000754/2023-2024 | 2549/BD | 23/08/2023 | 1096 | MONDAL ENTERPRISE. (BARASAT) | 650.34 | 0 | 60
519 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2023 to 29.02.2024) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001183/2023-2024 | 783/BST | 29/08/2023 | 182 | DEBAPRASAD MONDAL. | 0.86 | 0 | 0
520 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for six months w.e.f. 08.09.2023) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001405/2023-2024 | 663/BSD | 07/09/2023 | 182 | ANJALI ENTERPRISE. | 0.86 | 0 | 2
521 | Barasat Division | Barasat Sadar Sub-Division | Continuation work order for Hiring 1(One) No. Diesel Luxury Car on Daily basis for 6 (six) months for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred and seventy five only) per day excluding fuel. (Period from 01/03/2025 to 31/08/2025) | Assistant Engineer | Junior Engineer | ORD/001553/2024-2025 | 1194/BSD | 24/02/2025 | 184 | ANJALI ENTERPRISE. | 0.87 | 0 | 0
522 | Barasat Division | Barasat Sadar Sub-Division | Laying of partly damaged UPVC pipe line at Nabajibonpally under Joypul Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001854/2023-2024 | 1133/BSD | 12/02/2024 | 7 | TALUKDER & CO. | 0.87 | 0 | 100
523 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(One) No. Diesel Luxury Car on Daily basis for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. (For the Period from 08/03/2024 to 31/08/2024) | Assistant Engineer | Junior Engineer | ORD/002032/2023-2024 | 1215/BSD | 07/03/2024 | 176 | ANJALI ENTERPRISE. | 0.84 | 0 | 0
524 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000034/2023-2024 | 1289/BD | 25/04/2023 | 0 | Resource Division | 76.38 | 0 | 0
525 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000114/2023-2024 | 4023/BD | 12/10/2023 | 0 | Resource Division | 25.78 | 0 | 0
526 | Barasat Division | Habra Sub-Division | Formal work order for Construction of 2 nos. (1250 CuM & 600 CuM) capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-X and XI Head work sites including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001211/2023-2024 | 4072/BD | 16/10/2023 | 1095 | GARGO TRADERS | 3804.4 | 0 | 44
527 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, leftout work of 500 cum reservoir in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad Block, Construction of Protection wall for protection of UPVC distribution pipe line, Construction of approach road Zone-5 of Surfaced based w/s scheme Hasnabad, Protection works in different location of Amberia and Ghuni mouza, 2 nos. pump connection at PH No.-1 & 2 with CWR in connection within Amberia water supply scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2025-2026 | 1748/BD | 28/05/2025 | 60 | M/S DATTA ENTERPRISE. | 102.67 | 0 | 80
528 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR, pipe connection and cost of pipes specials for Amberia W/S Scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2023-2024 | 1737/BD | 08/06/2023 | 731 | MONDAL & CO. (BASIRHAT). | 411.21 | 241.49 | 96
529 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (AMBARIA Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002691/2021-2022 | 233/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
530 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (AMBARIA Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002692/2021-2022 | 234/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.29 | 4.29 | 1
531 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000230/2022-2023 | 881/BD | 22/03/2023 | 0 | Resource Division | 24.21 | 0 | 0
532 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum Work Order for Hiring of 1(one) number vehicle of category Motor Cab/Maruti Omni(standard)(Non Air-conditioned) with Diesel/LPG/CNG Engine)[not more than 5 (five) years old] including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700120, district- North 24Pgns, W.B. | Assistant Engineer | Junior Engineer | ORD/000344/2021-2022 | 432/BKP | 27/07/2021 | 12 | GOPAL SINGHA. | 1.49 | 0.65 | 1
533 | Barasat Division | Barasat Sadar Sub-Division | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(period from 01.08.2024 to 31.01.2025) | Assistant Engineer | Junior Engineer | ORD/000412/2024-2025 | 461/BKP | 12/07/2024 | 184 | GOPAL SINGHA. | 0.87 | 0 | 0
534 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum Work Order for Hiring of 1(one) number vehicle of category Motor Cab/Maruti Omni(standard)(Non Air-conditioned) with Diesel/LPG/CNG Engine)[not more than 5 (five) years old] including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, district- North 24Pgns, W.B. | Assistant Engineer | Junior Engineer | ORD/000594/2022-2023 | 158/BKP | 29/07/2022 | 365 | GOPAL SINGHA. | 1.73 | 3.93 | 1
535 | Barasat Division | Barasat Sadar Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dangatangatangi, Bodai, Sonadanga, Kamdebpur, Mirhati, Mathura, Durlavpur & Belu mouzas (Part) within Bodai Zone-I Water Supply Scheme at Amdanga Block under Barasat Division, PHE Dte. Part-A Phase-I | Assistant Engineer | Junior Engineer | ORD/000630/2021-2022 | 2145/BD | 12/11/2021 | 90 | UMWELT ENGINEER PVT.LTD. | 222.53 | 201.49 | 1
536 | Barasat Division | Barasat Sadar Sub-Division | Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(period from 01.10.2024 to 31.03.2025) | Assistant Engineer | Junior Engineer | ORD/000851/2024-2025 | 528/BKP | 30/09/2024 | 182 | GOPAL SINGHA. | 0.86 | 0 | 0
537 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for six months from w.e.f. 01.12.2022) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001123/2022-2023 | 804/BSD | 30/11/2022 | 182 | MADHAB CHANDRA DAS | 0.86 | 0.26 | 1
538 | Barasat Division | Barasat Sadar Sub-Division | Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer,Habra Sub-Division, P.H.E. Dte. (For the period from: 01.12.2021 to 30.11.2022) | Assistant Engineer | Junior Engineer | ORD/001160/2021-2022 | 488/HAB | 30/11/2021 | 1 | M/S LATIKA CONSTRUCTION. | 1.73 | 3.52 | 1
539 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(From 01.10.2023 to 31.03.2024) | Assistant Engineer | Junior Engineer | ORD/001235/2023-2024 | 333/BKP | 29/09/2023 | 182 | GOPAL SINGHA. | 0.87 | 0 | 80
540 | Barasat Division | Barasat Sadar Sub-Division | Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, P.H.E. Dte. (For the period from : 01.12.2022 to 30.11.2023) | Assistant Engineer | Junior Engineer | ORD/001346/2022-2023 | 660/HAB | 30/11/2022 | 365 | M/S LATIKA CONSTRUCTION. | 1.73 | 3.59 | 40
541 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Bodai Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. Sl. No.-1 | Assistant Engineer | Junior Engineer | ORD/001542/2021-2022 | 805/BSD | 06/12/2021 | 30 | PURBA SERVICES | 1.84 | 1.75 | 0
542 | Barasat Division | Barasat Sadar Sub-Division | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(Period from 01.02. 2024 to 31.07.2024) | Assistant Engineer | Junior Engineer | ORD/001946/2023-2024 | 43/BKP | 22/01/2024 | 182 | GOPAL SINGHA. | 0.86 | 0 | 100
543 | Barasat Division | Barasat Sadar Sub-Division | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub- Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B. | Assistant Engineer | Junior Engineer | ORD/002038/2023-2024 | 107/BKP | 06/03/2024 | 184 | GOPAL SINGHA. | 0.87 | 0 | 100
544 | Barasat Division | Barasat Sadar Sub-Division | Continuation Work Order for Hiring of 1(one) number vehicle of Category Motor Cab/Maruti Omni(standard)(Non Air-Conditioned)/LPG/CNG Engine including Driver for performing the inspection works and official duties for the office of the Assistant Engineer, Barrackpore Sub-Division, P.H.E. Dte. at Barrackpore, Kolkata-700122, District- North 24Pgns, W.B.(period from 01.02.2025 to 31.07.2025) | Assistant Engineer | Junior Engineer | ORD/002178/2024-2025 | 21/BKP | 30/01/2025 | 181 | GOPAL SINGHA. | 0.86 | 0 | 0
545 | Barasat Division | Barasat Sadar Sub-Division | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-04-2022 to 30-09-2022) for the Office of the Executive Engineer, Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002600/2021-2022 | 962/BD | 29/03/2022 | 6 | MADHAB CHANDRA DAS | 0.9 | 1.32 | 1
546 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-II & III) and allied works at Bodai Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002948/2021-2022 | 809/BSD | 08/12/2021 | 30 | MONDAL ENTERPRISE. (BARASAT) | 2.52 | 2.33 | 0
547 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-IV & V) and allied works at Bodai Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002950/2021-2022 | 810/BSD | 09/12/2021 | 30 | SUN ENTERPRISE. | 2.52 | 2.32 | 0
548 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 12 months from 01.03.2022 to 28.02.2023 w.e.f. 01.12.2022) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/003025/2021-2022 | 193/BSD | 25/02/2022 | 365 | MADHAB CHANDRA DAS | 1.25 | 0.76 | 0
549 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2021-2022 | 2240/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0
550 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing FHTC including laying of Pipe Line, Renovation of Filter Media, Repairing of Wooden Jetty and Electro Mechanical Work for Augmentation at Tyantra Neora pond based water supply scheme in Basirhat - II Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000233/2023-2024 | 1738/BD | 08/06/2023 | 90 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 88.36 | 0 | 30
551 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for TYANTRA NEORA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001948/2021-2022 | 204/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.94 | 2.51 | 0
552 | Barasat Division | Bangaon Sub-Division | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-II) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000083/2025-2026 | 538/Bon | 23/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0
553 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Chhaighoria (Zone-II) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000095/2023-2024 | 1545/BD | 19/05/2023 | 30 | NEW MA TARA ENTERPRISE. | 15.85 | 0 | 100
554 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhaygharia (Zone-II) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000348/2024-2025 | 2357/BD | 20/08/2024 | 405 | B.S.ENTERPRISE. (BASIRHAT) | 45.95 | 0 | 15
555 | Barasat Division | Bangaon Sub-Division | Laying of badly damaged distribution pipe line and others allied for widening Panchayet Road from Chhaygharia Ajay Mondal's House to Khedapara F.P School to Trimonipara at Chhaygharia (Zone-II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000626/2022-2023 | 411/Bon | 23/08/2022 | 15 | PRABIR KUMAR MONDAL. | 4.55 | 3.39 | 1
556 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia(Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000822/2022-2023 | 3601/BD | 09/12/2022 | 90 | M/S B.N ENTERPRISE | 152.03 | 151.24 | 100
557 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation within command area for Augmentation of Chhaygharia Zone-II Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000899/2023-2024 | 2797/BD | 12/09/2023 | 730 | JOY HIND TUBEWELLS. | 91.85 | 0 | 60
558 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-II) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001552/2023-2024 | 38/BD | 04/01/2024 | 23 | M/S SANJAY ADHIKARI | 12 | 0 | 100
559 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-II) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002771/2021-2022 | 124/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 1
560 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Chhayagharia Zone- II water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002957/2021-2022 | 534/BON | 03/11/2021 | 21 | PRABIR KUMAR MONDAL. | 2.52 | 2.49 | 1
561 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000092/2022-2023 | 3661/BD | 13/12/2022 | 0 | Resource Division | 8.27 | 0 | 0
562 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000106/2022-2023 | 3696/BD | 14/12/2022 | 0 | Resource Division | 51.36 | 0 | 0
563 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Chandpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000007/2023-2024 | 1150/BD | 13/04/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 318.37 | 0 | 36
564 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, leftout work of 500 cum reservoir in connection with Augmentation of Chandpur w/s scheme (Z-II), Hasnabad Block, Construction of Protection wall for protection of UPVC distribution pipe line, Construction of approach road Zone-5 of Surfaced based w/s scheme Hasnabad, Protection works in different location of Amberia and Ghuni mouza, 2 nos. pump connection at PH No.-1 & 2 with CWR in connection within Amberia water supply scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000066/2025-2026 | 1748/BD | 28/05/2025 | 60 | M/S DATTA ENTERPRISE. | 102.67 | 0 | 80
565 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2023-2024 | 1429/BD | 11/05/2023 | 60 | PRITAM MUKHOPADHYAY. | 17.32 | 0 | 85
566 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap in connection with Augmentation of Chandpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 2329/BD | 16/08/2024 | 365 | GOPINATH ENTERPRISES | 100.59 | 0 | 0
567 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000545/2024-2025 | 2973/BD | 04/10/2024 | 180 | SONALI CONSTRUCTION | 10.52 | 0 | 100
568 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Chandpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001066/2022-2023 | 402/BD | 09/02/2023 | 90 | MONDAL & CO. (BASIRHAT). | 318.72 | 250.15 | 60
569 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 500 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap in connection with Augmentation of Chandpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001096/2023-2024 | 2866/BD | 20/09/2023 | 365 | MONDAL & CO. (BASIRHAT). | 202.58 | 0 | 75
570 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Chandpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001180/2022-2023 | 793/BD | 13/03/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 42.88 | 0 | 100
571 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Chandpur water supply scheme (Z-II) , Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001301/2024-2025 | 147/HSD | 27/01/2025 | 10 | ANKUSH CONSTRUCTION & CO. | 0.84 | 0 | 100
572 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Chandpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001664/2023-2024 | 294/BD | 30/01/2024 | 45 | M/S K.P.PAL. | 51.76 | 0 | 100
573 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000164/2023-2024 | 4511/BD | 28/11/2023 | 0 | Resource Division | 26.12 | 0 | 0
574 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000237/2022-2023 | 928/BD | 22/03/2023 | 0 | Resource Division | 55.9 | 0 | 0
575 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03466/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 13.3 | 0 | 0
576 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03469/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 8.79 | 0 | 0
577 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Gobindapur W/S Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000040/2025-2026 | 1697/BD | 23/05/2025 | 120 | M/S B.K.ENTERPRISE. | 20.9 | 0 | 0
578 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road and plinth protection of Pump House at Head Work site of Gobindapur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000073/2025-2026 | 1769/BD | 29/05/2025 | 120 | RAKESH ENTERPRISE. | 24.5 | 0 | 0
579 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Gobindapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2022-2023 | 3488/BD | 02/12/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 341.88 | 0 | 99
580 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001007/2022-2023 | 170/BD | 19/01/2023 | 858 | KINGS & CO. | 437.87 | 0 | 66
581 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Construction of Boundary Wall at the site of Pump House -III of Gobindapur Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001039/2024-2025 | 58/BD | 07/01/2025 | 120 | IKBAL HOSSAIN | 14.35 | 0 | 60
582 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gabindapur Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001166/2023-2024 | 2921/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 0 | 29
583 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002517/2021-2022 | 443 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 1
584 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2023-2024 | 1244/BD | 25/04/2023 | 0 | Resource Division | 158.92 | 0 | 0
585 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000065/2023-2024 | 1628/BD | 01/06/2023 | 0 | Resource Division | 9.42 | 0 | 0
586 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000112/2022-2023 | 3699/BD | 14/12/2022 | 0 | Resource Division | 26.46 | 0 | 0
587 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000188/2022-2023 | 600/BD | 23/02/2023 | 0 | Resource Division | 9.36 | 0 | 0
588 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Diara Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001344/2021-2022 | 141/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.08 | 4.07 | 1
589 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Diara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002910/2021-2022 | 516/Bon | 27/10/2021 | 21 | ROY ENGINEERS. | 2.52 | 2.47 | 0
590 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001118/2021-2022 | 612/Bon | 31/12/2021 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.09 | 4.07 | 1
591 | Barasat Division | Basirhat Sub-Division | Formal work order for "Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Malatipur & Chaita (Part) Mouzas under Sadiknagar Zone - II Water Supply Scheme at Basirhat - II Block Under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001760/2020-2021 | 495/BD. | 26/02/2021 | 90 | ORIENT CONSTRUCTION. | 97.09 | 56.62 | 1
592 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-II Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001951/2021-2022 | 207/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.51 | 3.5 | 1
593 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Khulna Bhandarkhali Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002035/2021-2022 | 2177/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.92 | 3.93 | 1
594 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000076/2022-2023 | 2988/BD | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0
595 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Korakati Water Supply scheme Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000483/2021-2022 | 1741/BD | 14/09/2021 | 45 | R.K.MANDAL AND CO. | 76.55 | 76.55 | 1
596 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Dakshin Bhebia Zone-II Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001002/2021-2022 | 2182/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.99 | 1.99 | 1
597 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places of Bashberia within Baunia Abad w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000069/2022-2023 | 785/HSD | 13/05/2022 | 10 | M/S DATTA ENTERPRISE. | 4.85 | 4.83 | 1
598 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chandpur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000981/2021-2022 | 2166/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.5 | 4.46 | 1
599 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in Baunia Abad mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001068/2021-2022 | 93/BD | 17/01/2022 | 45 | M/S PROGATI ENTERPRISE. | 77.75 | 77.77 | 1
600 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Anchor block for resting of different dia DI Rising/Distribution main for low areas at different places for Rejuvenation of Baunia Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001662/2021-2022 | 416/HSD | 04/03/2022 | 15 | M/S DATTA ENTERPRISE. | 4.04 | 4.04 | 1
601 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Anchor block for resting of different dia DI Rising/Distribution main for low areas at different places for Rejuvenation of Baunia Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/002119/2021-2022 | 415/HSD | 04/03/2022 | 15 | M/S PROGATI ENTERPRISE. | 4.71 | 4.71 | 1
602 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000082/2023-2024 | 1811/BD | 19/06/2023 | 0 | Resource Division | 3.15 | 0 | 0
603 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Boyermari Abad Water Supply scheme Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000477/2021-2022 | 1738/BD | 14/09/2021 | 45 | DEBAPRASAD MONDAL. | 81.09 | 78.93 | 1
604 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000083/2023-2024 | 1812/BD | 19/06/2023 | 0 | Resource Division | 16.51 | 0 | 0
605 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area under Patua Water Supply Scheme at SWARUPNAGAR Block, Dist.- North 24 Parganas under Barasat Division. PHE. Dte. (PHASE-I) | Assistant Engineer | Junior Engineer | ORD/000007/2022-2023 | 1177/BD | 19/04/2022 | 90 | KINGS & CO. | 193.55 | 172.97 | 1
606 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000064/2022-2023 | 2342/BD | 26/09/2022 | 0 | Resource Division | 24.12 | 0 | 0
607 | Barasat Division | Basirhat Sub-Division | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-07-2022 to 31-12-2022). | Assistant Engineer | Junior Engineer | ORD/000193/2022-2023 | 1819/BD | 27/06/2022 | 184 | DIPANKAR NASKAR. | 0.87 | 1.77 | 1
608 | Barasat Division | Basirhat Sub-Division | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2022 to 31.12.2022) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000598/2022-2023 | 641/BST | 31/08/2022 | 122 | DEBAPRASAD MONDAL. | 0.58 | 0.93 | 1
609 | Barasat Division | Basirhat Sub-Division | Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.09.2021 to 31.08.2022) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000601/2021-2022 | 447/BST | 25/08/2021 | 365 | DEBAPRASAD MONDAL. | 1.72 | 1.31 | 1
610 | Barasat Division | Basirhat Sub-Division | Continuation work order for Hiring 1(one) no. Diesel Luxary Car on daily basis (for 01.01.2023 to 30.04.2023) for office use of the Assistant Engineer, R.W.S Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001138/2022-2023 | 883/BST | 28/12/2022 | 120 | DEBAPRASAD MONDAL. | 0.57 | 0.95 | 1
611 | Barasat Division | Basirhat Sub-Division | Formal work order for for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Banglani Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001139/2021-2022 | 217/BD | 24/01/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 221.85 | 168.02 | 1
612 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2022-2023 | 2338/BD | 26/09/2022 | 0 | Resource Division | 61.5 | 0 | 0
613 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Mathurapur Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000334/2021-2022 | 1655/BD | 07/09/2021 | 45 | CHANCHAL ENTERPRISE & CO. | 85.87 | 83.61 | 1
614 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for MATHURAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001967/2021-2022 | 341/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 3.5 | 1
615 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Durgapur Baylani Zone I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000961/2021-2022 | 2158/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.18 | 4.13 | 1
616 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe line and necessary fittings within Gabberia Water Supply Scheme at Sandeshkhali-II Block under Hsnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/001851/2020-2021 | 435/BD. | 22/02/2021 | 30 | DEBAPRASAD MONDAL. | 77.8 | 32.86 | 1
617 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000087/2023-2024 | 1819/BD | 19/06/2023 | 0 | Resource Division | 21.78 | 0 | 0
618 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area under BAJITPUR ZONE-I Water Supply Scheme at Baduria Block, District- North 24 Parganas under Barasat Division,PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001082/2021-2022 | 141/BD | 18/01/2022 | 90 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 266.04 | 179.15 | 1
619 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BAJITPUR ZONE 1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001981/2021-2022 | 353/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 1
620 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for BAJITPUR ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001982/2021-2022 | 354/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0.61 | 1
621 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dhanyakuria water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001256/2021-2022 | 404/BD | 10/02/2022 | 45 | UTPAL CONSTRUCTION & CO. | 82.7 | 73.58 | 1
622 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DHANYAKURIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001973/2021-2022 | 346/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.79 | 4.79 | 1
623 | Barasat Division | Basirhat Sub-Division | Additional Route Survey work for DPR Preparation for DHANYAKURIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001975/2021-2022 | 347/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.25 | 1.25 | 1
624 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2022-2023 | 2989/BD | 29/09/2022 | 0 | Resource Division | 7.39 | 0 | 0
625 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for additional Construction of 2 nos. switch room cum chlorine room (5.40x3.60) for augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 1633/BD | 20/05/2025 | 60 | JAGANNATH CONSTRUCTION. | 18.2 | 0 | 0
626 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 1201/BD | 20/04/2023 | 30 | M/S NIRMAN CONSTRUCTION. | 62.06 | 0 | 56
627 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Baunia Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000141/2023-2024 | 1724/BD | 08/06/2023 | 662 | DEBAPRASAD MONDAL. | 187.27 | 0 | 100
628 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Baunia Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2721/BD | 14/09/2022 | 90 | KINGS & CO. | 452.15 | 350.04 | 1
629 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000797/2024-2025 | 3303/BD | 27/11/2024 | 150 | JOY GURU ENTERPRISE | 63.39 | 0 | 0
630 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Baunia Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001361/2024-2025 | 350/BD | 31/01/2025 | 90 | M/S DATTA ENTERPRISE. | 223.88 | 0 | 0
631 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connectin with Augmentation of Baunia Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001916/2023-2024 | 288/HSD | 06/03/2024 | 10 | DEBAPRASAD MONDAL. | 0.84 | 0 | 100
632 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000245/2022-2023 | 939/BD | 22/03/2023 | 0 | Resource Division | 9.92 | 0 | 0
633 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Jeliakhali Purba Khanda W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 1605/BD | 07/06/2022 | 90 | SUBHASH BOSE. | 126.81 | 120.92 | 1
634 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work in different places of Jeliakhali Mouza in connection with retrofitting of Jeliakhali Purba Khanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 1496/BD | 17/05/2023 | 30 | SUBHASH BOSE. | 137.02 | 0 | 100
635 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000796/2024-2025 | 3314/BD | 27/11/2024 | 30 | JOY GURU ENTERPRISE | 31.69 | 0 | 0
636 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with brick masonry structure at Head Work site within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001311/2023-2024 | 4382/BD | 10/11/2023 | 90 | MD.SALIM GAZI. | 28.33 | 0 | 68
637 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC pipe line at different places at Jeliakhali Purba mouza within Jeliakhali Purbakhanda w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002835/2021-2022 | 533/HSD | 15/03/2022 | 15 | PRITAM MUKHOPADHYAY. | 4.77 | 4.71 | 1
638 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Tushkhali W/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000087/2022-2023 | 1604/BD | 07/06/2022 | 90 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 183.73 | 164.74 | 0
639 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2024-2025 | 3334/BD | 28/11/2024 | 30 | UTPAL CONSTRUCTION & CO. | 31.69 | 0 | 0
640 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter at Joygopalpur tail end within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000863/2024-2025 | 3378/BD | 02/12/2024 | 30 | CHANCHAL ENTERPRISE & CO. | 31.47 | 0 | 0
641 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001272/2024-2025 | 259/BD | 22/01/2025 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 34.32 | 0 | 0
642 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work order for Construction of boundary wall with RCC column structure at Head Work site within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001307/2023-2024 | 4379/BD | 10/11/2023 | 90 | R. B. ENTERPRISE | 21.29 | 0 | 100
643 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Tushkhali water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001404/2024-2025 | 391/BD | 05/02/2025 | 60 | ANKUSH CONSTRUCTION & CO. | 36.68 | 0 | 100
644 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection at Joygopalpur tail end within Tushkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001704/2024-2025 | 951/BD | 25/03/2025 | 75 | SABIR ALI GAZI | 8.92 | 0 | 0
645 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing and renovation works for 225 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir for Augmentation of Kurulia (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000454/2024-2025 | 3039/BD | 22/10/2024 | 135 | GHOSH CONSTRUCTION. | 13.22 | 0 | 100
646 | Barasat Division | Bangaon Sub-Division | Construction of Latrine at Head Work site and Renovation of PH No - 1 & 2 and allied works for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2025-2026 | 662/Bon | 23/05/2025 | 45 | M/S SAYAN ENTERPRISE. | 3.51 | 0 | 0
647 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000637/2023-2024 | 620/Bon | 08/08/2023 | 15 | ONKAR ENTERPRISE. | 2.4 | 0 | 100
648 | Barasat Division | Bangaon Sub-Division | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000642/2023-2024 | 612/Bon | 08/08/2023 | 21 | ROY CHOWDHURY CONSTRUCTION. | 2.76 | 2.72 | 100
649 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Kurulia (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000777/2022-2023 | 1243/BD | 26/04/2022 | 90 | M/S NANDY ENTERPRISE | 470.6 | 231.12 | 100
650 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Kurulia (Zone-I) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000817/2022-2023 | 3589/BD | 08/12/2022 | 15 | M/S SUKANTA ENTERPRISE. | 15.04 | 14.07 | 0
651 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KURULIA (Zone-II) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/002293/2020-2021 | 490/BD. | 26/02/2021 | 45 | ORIENT CONSTRUCTION. | 67.42 | 0 | 1
652 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kurulia (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002784/2021-2022 | 138/BON | 18/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.05 | 4.03 | 1
653 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2022-2023 | 1366/BD | 13/05/2022 | 0 | Resource Division | 8.83 | 0 | 0
654 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000019/2022-2023 | 1671/BD | 13/06/2022 | 0 | Resource Division | 8.71 | 0 | 0
655 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Bagdah Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000001/2022-2023 | 1002/BD | 04/04/2022 | 1440 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 450.95 | 259.19 | 80
656 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Bagdah PWSS (341 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2024-2025 | 687/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.74 | 0 | 100
657 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Bagdah W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000046/2025-2026 | 1544/BD | 15/05/2025 | 120 | N.H. ENTERPRISE | 40.13 | 0 | 0
658 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Bagdah Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000641/2023-2024 | 624/Bon | 08/08/2023 | 15 | TAPAN GHOSH. | 2.39 | 2.38 | 100
659 | Barasat Division | Bangaon Sub-Division | Construction and Repairing works of damaged part of Boundary wall, Main Gate, Drain, Valve Chamber and allied works due to DI Pipe stacking and shifting at Bagdah High School play ground for Bongaon-Bagdah surface water based PWSS within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000886/2024-2025 | 1393/Bon | 27/11/2024 | 25 | VAI ENTERPRISE. | 4.73 | 0 | 0
660 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Bagdah Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001153/2023-2024 | 2927/BD | 26/09/2023 | 30 | DHELA BABA ENTERPRISE | 16.1 | 0 | 100
661 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Bagdah Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001600/2024-2025 | 705/BD | 06/03/2025 | 60 | TAPAN GHOSH. | 11.39 | 0 | 0
662 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000008/2022-2023 | 1361/BD | 13/05/2022 | 0 | Resource Division | 23.36 | 0 | 0
663 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2022-2023 | 1670/BD | 13/06/2022 | 0 | Resource Division | 21.96 | 0 | 0
664 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Dakshin Chatra Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 1210/BD | 20/04/2023 | 951 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 971.71 | 268.64 | 38
665 | Barasat Division | Basirhat Sub-Division | Supply of Sluice valve (200 mm) including construction of Sluice valve chamber for Augmentation of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000075/2024-2025 | 928/BHTSD | 24/05/2024 | 7 | ROHAN MONDAL. | 0.97 | 0 | 100
666 | Barasat Division | Basirhat Sub-Division | Laying of HDPE pipe line and Repairing of DI pipelines including supply of Sluice valve (200 mm) for interconnection of AIRP under Augmentation work of Dakshin Chatra Zone-I Water Supply Scheme under Basirhat Sub Division , P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000079/2024-2025 | 929/BHTSD | 24/05/2024 | 7 | S.R.M. ENTERPRISE. | 1 | 0 | 100
667 | Barasat Division | Basirhat Sub-Division | Hiring Diesel Luxury Car on daily basis (for 06 months from 01.01.2023 to 30.06.2023) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001343/2022-2023 | 1420 /BHTSD | 30/12/2022 | 181 | OM ENTERPRISE | 0.86 | 2.33 | 100
668 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001979/2021-2022 | 351/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 1
669 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for DAKSHIN CHATRA ZONE -1 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001980/2021-2022 | 352/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.38 | 1.36 | 1
670 | Barasat Division | Basirhat Sub-Division | Continuation Work for Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024 for Six Month) | Assistant Engineer | Junior Engineer | ORD/002197/2023-2024 | 1290/BHTSD | 29/12/2023 | 182 | DEB KUMAR DAS. | 0.86 | 0 | 100
671 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2023-2024 | 1254/BD | 25/04/2023 | 0 | Resource Division | 260.28 | 0 | 0
672 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000063/2023-2024 | 1632/BD | 01/06/2023 | 0 | Resource Division | 48.44 | 0 | 0
673 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03465/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 49.56 | 0 | 0
674 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03468/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 32.73 | 0 | 0
675 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection) for Augmentation of Nalabara Zone-II Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2023-2024 | 1125/BD | 11/04/2023 | 811 | H.I.ENTERPRISE. | 634.74 | 412.38 | 60
676 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI / UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) by Augmentation of Nalabara (Zone-I) Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000776/2023-2024 | 2713/BD | 05/09/2023 | 546 | GARGO TRADERS | 559.43 | 0 | 72
677 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Nalabara Zone-II water supply scheme in Swarupnagar Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000980/2023-2024 | 2800/BD | 12/09/2023 | 30 | DHELA BABA ENTERPRISE | 21.53 | 0 | 0
678 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Balance Work of Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Nalabara Z-II water Supply Scheme within Swarupnagar Block under Basirhat Sub Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001537/2024-2025 | 399/BD | 05/02/2025 | 360 | H.I.ENTERPRISE. | 75.98 | 0 | 65
679 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Nalabara Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002751/2021-2022 | 454/ BHTSD | 23/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 1
680 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Nalabara Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002752/2021-2022 | 455/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.61 | 1
681 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2023-2024 | 1260/BD | 25/04/2023 | 0 | Resource Division | 381.58 | 0 | 0
682 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000067/2023-2024 | 1629/BD | 01/06/2023 | 0 | Resource Division | 71.08 | 0 | 0
683 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2025-2026 | 2474/BD | 17/07/2025 | 150 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0
684 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Paikardanga water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001010/2022-2023 | 173/BD | 19/01/2023 | 984 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 707.21 | 262.57 | 38
685 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat I Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001036/2024-2025 | 3626/BD | 20/12/2024 | 180 | NISHITH BANERJEE | 45.36 | 0 | 100
686 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for PAIKARDANGA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001938/2021-2022 | 194/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
687 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000190/2022-2023 | 602/BD | 23/02/2023 | 0 | Resource Division | 31.31 | 0 | 0
688 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000196/2022-2023 | 854/BD | 20/03/2023 | 0 | Resource Division | 377.63 | 0 | 0
689 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion with protection work in connection with Augmentation of Durgapur Baylani water supply scheme (Z-I & II), Hingalganj Block of Hasnabad Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000100/2024-2025 | 2401/BD | 22/08/2024 | 360 | M/S S.C. CIVIL ENTERPRISES | 116 | 0 | 0
690 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Land development at OHR site in connection with augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000255/2025-2026 | 2334/BD | 07/07/2025 | 60 | BABUSONA CONSTRUCTION. | 7.13 | 0 | 0
691 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte.Part-C | Assistant Engineer | Junior Engineer | ORD/001467/2024-2025 | 342/HSD | 06/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.85 | 0 | 100
692 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 140 mm(Near Asharia Paschim) ,180 mm(Near OHR) dia UPVC distribution pipe line in connection with Augmentation of Durgapur Baylani water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001534/2024-2025 | 389/HSD | 10/02/2025 | 10 | M/S K.B.ENTERPRISE. | 0.86 | 0 | 100
693 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000249/2022-2023 | 933/BD | 22/03/2023 | 0 | Resource Division | 120.6 | 0 | 0
694 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work for newly laid UPVC pipe line at different places of Dhuchnikhali Mouza, Korakati Mouza, & Monipur Mouza in connection with retrofitting of Joygopalpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000042/2023-2024 | 1360/BD | 04/05/2023 | 30 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 117.2 | 0 | 0
695 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Joygopalpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2022-2023 | 1746/BD | 20/06/2022 | 90 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 278.19 | 213.07 | 1
696 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work for newly laid UPVC pipe line at different places of Sukhdoani Mouza in connection with retrofitting of Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2023-2024 | 1165/BD | 13/04/2023 | 30 | SUPRITI ENTERPRISE. | 68.84 | 68.78 | 0
697 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Sukhdaoni w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000153/2022-2023 | 1660/BD | 10/06/2022 | 90 | SUPRITI ENTERPRISE. | 113.4 | 102.01 | 1
698 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Sukhdoani Mouza within Sukhdoani w/s scheme , Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 885/HSD | 07/08/2024 | 10 | NEW LIFE CONSTRUCTION. | 0.96 | 0 | 100
699 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis (for 6 months from 01.10.2022 to 31.03.2023) for the office use of the Executive Engineer, Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000805/2022-2023 | 2826/BD | 29/09/2022 | 181 | MADHAB CHANDRA DAS | 0.89 | 1.56 | 0
700 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Sukhdoani (SPL) FP School, Dk. Sukhdoani FP School & Sukhdoani Dwarikanath FP School within the command area of Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000870/2023-2024 | 1056/HSD | 31/08/2023 | 7 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.6 | 0.6 | 100
701 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (Ph No-1) within Sukhdoani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001309/2023-2024 | 4381/BD | 10/11/2023 | 90 | ABDUL ALIM MONDAL. | 24.32 | 0 | 100
702 | Barasat Division | Bangaon Sub-Division | Emergency laying of wash out pipe line and others allied works from Kola Pump House No-I to nearest Baor at Adibasi Para at Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 383/Bon | 05/08/2022 | 12 | ACHINTA KUMAR HALDER. | 1.1 | 1.08 | 1
703 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kola Water Supply Scheme, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001029/2022-2023 | 264/BD | 01/02/2023 | 90 | MONDAL PRECISION PVT.LTD | 330.92 | 272.35 | 100
704 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kola Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001115/2023-2024 | 2938/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 0 | 100
705 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation of 34 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Kola water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001541/2023-2024 | 12/BD | 02/01/2024 | 60 | PUSPA ENTERPRISE. | 38.78 | 0 | 100
706 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001758/2023-2024 | 524/BD | 20/02/2024 | 30 | DEL DELTA CONSTRUCTION | 13.55 | 0 | 85
707 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Boundary wall at 2nd T/W site and Construction of Approach Road at Head work site and 2nd T/W site under Augmentation of Kola Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001773/2023-2024 | 624/BD | 28/02/2024 | 360 | ONKAR ENTERPRISE. | 11.17 | 0 | 100
708 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kola Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002786/2021-2022 | 136/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.64 | 3.62 | 1
709 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002907/2021-2022 | 527/Bon | 01/11/2021 | 21 | ACHINTA KUMAR HALDER. | 2.52 | 2.47 | 1
710 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000108/2022-2023 | 3694/BD | 14/12/2022 | 0 | Resource Division | 26.68 | 0 | 0
711 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000121/2022-2023 | 3713/BD | 15/12/2022 | 0 | Resource Division | 11.89 | 0 | 0
712 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Restoration of damaged pipe line due to Construction of Pucca Drain by laying of UPVC pipe at different places under Chhaigharia Gram Panchayet, Bongaon Block of Chhaigharia (Zone - III) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 2053/BD | 20/06/2025 | 90 | VAI ENTERPRISE. | 23.12 | 0 | 0
713 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order Providing Functional Household Tap Connection (FHTC) to the uncovered household at Jayantipur mouza including laying of UPVC pipe and allied works under Augmentation work at Chhaigharia (Zone-III) W/S Scheme under Chhaigharia G.P., Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000021/2025-2026 | 1649/BD | 21/05/2025 | 90 | SUJAN KUMAR MISTRY | 25.23 | 0 | 0
714 | Barasat Division | Bangaon Sub-Division | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-III) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000084/2025-2026 | 539/Bon | 23/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0
715 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Chhaighoria (Zone-III) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 1546/BD | 22/05/2023 | 30 | NEW MA TARA ENTERPRISE. | 15.81 | 0 | 100
716 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhaygharia (Zone-III) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000349/2024-2025 | 2419/BD | 23/08/2024 | 60 | ONKAR ENTERPRISE. | 42.48 | 0 | 0
717 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia (Zone-III) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000784/2022-2023 | 3491/BD | 02/12/2022 | 90 | M/S PROGATI ENTERPRISE. | 296.33 | 296.19 | 100
718 | Barasat Division | Bangaon Sub-Division | Laying of UPVC pipe line at different damaged portions under Augmentation work at Chhaygharia (Zone-III) W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000883/2024-2025 | 1384/Bon | 26/11/2024 | 86 | JOY GURU ENTERPRISE | 4.96 | 0 | 100
719 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-III) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001745/2023-2024 | 561/BD | 22/02/2024 | 45 | ROY ENGINEERS. | 10.23 | 0 | 100
720 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-III) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002787/2021-2022 | 125/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.42 | 3.4 | 1
721 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chhaygharia (Zone-III) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002927/2021-2022 | 535/Bon | 03/11/2021 | 21 | VAI ENTERPIRSE. | 2.52 | 2.47 | 1
722 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000093/2022-2023 | 3653/BD | 13/12/2022 | 0 | Resource Division | 15.03 | 0 | 0
723 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000110/2022-2023 | 3695/BD | 14/12/2022 | 0 | Resource Division | 110.28 | 0 | 0
724 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Malancha water supply scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 1189/BD | 19/04/2023 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 417.27 | 371.04 | 88
725 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 1606/BD | 19/05/2025 | 30 | M/S RAJPATH CONSTRUCTION. | 5.91 | 0 | 0
726 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Salauddin Molla in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000036/2025-2026 | 1528/BD | 14/05/2025 | 21 | MD.SALIM GAZI. | 10.2 | 0 | 0
727 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000408/2024-2025 | 2865/BD | 30/09/2024 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 151.25 | 0 | 100
728 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Ph No- 2 within Malancha W/S scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000551/2024-2025 | 993/HSD | 29/08/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.87 | 0 | 100
729 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000740/2023-2024 | 2493/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 43.9 | 0 | 80
730 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at Joygram Molla para N/H/O Emdadul Haque in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000983/2024-2025 | 3461/BD | 09/12/2024 | 30 | M/S ANUBHAB CONSTRUCTION. | 8.77 | 0 | 0
731 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Malancha water supply scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001099/2023-2024 | 2886/BD | 20/09/2023 | 365 | S.S.ENTERPRISE. (BAMANGACHI) | 152.49 | 0 | 100
732 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001177/2022-2023 | 790/BD | 13/03/2023 | 30 | ABDUL ALIM MONDAL. | 21.44 | 17.49 | 100
733 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 200 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001601/2023-2024 | 30/HSD | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0 | 80
734 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 150 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001602/2023-2024 | 31/HSD | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.94 | 0 | 82
735 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001604/2023-2024 | 32-HSD.. | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0 | 0
736 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 100 mm dia DI pipeline by concrete block at different places in connection with Augmentation of Malancha w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001856/2023-2024 | 32/HSD | 09/01/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.91 | 0 | 62
737 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000261/2022-2023 | 922/BD | 22/03/2023 | 0 | Resource Division | 22.12 | 0 | 0
738 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2023-2024 | 1208/BD | 20/04/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 21.47 | 17.1 | 91
739 | Barasat Division | Hasnabad Sub-Division | Formal work order for the work of Laying of Di/UPVC distribution pipe line, construction of 500cum capacity 20mtr staging height R.C.C over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap Connection in connection with Augmentation of Durgapur Baylani Water Supply Scheme(Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000682/2023-2024 | 2458/BD | 17/08/2023 | 1096 | APURBA MANDAL | 844.5 | 208.82 | 71
740 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000738/2023-2024 | 2492/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 21.95 | 0 | 66
741 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Durgapur Baylani Z-I w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001377/2024-2025 | 244/HSD | 30/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.63 | 0 | 100
742 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Itinda Panitor water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001119/2022-2023 | 429/BD | 13/02/2023 | 959 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 662.31 | 182.01 | 24
743 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2024-2025 | 3479/BD | 10/12/2024 | 0 | Resource Division | 77.88 | 0 | 0
744 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000153/2023-2024 | 4414/BD | 10/11/2023 | 0 | Resource Division | 18.48 | 0 | 0
745 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000197/2022-2023 | 857/BD | 20/03/2023 | 0 | Resource Division | 190.23 | 0 | 0
746 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2025-2026 | 2474/BD | 17/07/2025 | 150 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0
747 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Joypur Gopmahal water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000812/2022-2023 | 3585/BD | 08/12/2022 | 744 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 37.54 | 18.81 | 100
748 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Joypur Gopmahal Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001024/2022-2023 | 206/BD | 24/01/2023 | 30 | MONDAL & CO. (BASIRHAT). | 39.55 | 38.28 | 100
749 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000168/2022-2023 | 483/BD | 17/02/2023 | 0 | Resource Division | 0.55 | 0 | 0
750 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for special repair and renovation of existing structure like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Dobila, Eojnogar, Gobindapur Dhokra, Goknasree Gobindapur, Gotra, Sankchura and Mominpur Water Supply Scheme of different block within Basirhat Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000287/2025-2026 | 2464/BD | 16/07/2025 | 150 | M/S TARAFDAR CONSTRUCTION | 81.09 | 0 | 0
751 | Barasat Division | Basirhat Sub-Division | Formal work order for laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Goknashri Gobindapur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001187/2022-2023 | 1042/BD | 31/03/2023 | 739 | UTPAL CONSTRUCTION & CO. | 383.12 | 246.03 | 64
752 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOKNASREE GOBINDAPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001937/2021-2022 | 193/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.63 | 1
753 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Goknasree Gobindapur W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity- 60.00 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002029/2023-2024 | 923/BD | 15/03/2024 | 60 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 33.01 | 0 | 50
754 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000004/2023-2024 | 1245/BD | 25/04/2023 | 0 | Resource Division | 5.09 | 0 | 0
755 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000151/2023-2024 | 4412/BD | 10/11/2023 | 0 | Resource Division | 16.02 | 0 | 0
756 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03470/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 39.73 | 0 | 0
757 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Zone-I water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 1357/BD | 04/05/2023 | 785 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 723.95 | 96.44 | 48
758 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for special repair renovation of existing structures like Pump house, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Akhipur, Baro Bankra, Bithari Z-I, Bithari Z-II water supply scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000265/2025-2026 | 2381/BD | 10/07/2025 | 150 | JP CONSTRUCTION & SUPPLIERS. | 81.91 | 0 | 0
759 | Barasat Division | Basirhat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Swarupnagar Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - A) | Assistant Engineer | Junior Engineer | ORD/001491/2024-2025 | 152/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 90
760 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for BITHARI ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002507/2021-2022 | 451 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.22 | 0 | 1
761 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Bithari Zone-I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002963/2021-2022 | 450/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 1
762 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Bithari Zone-I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002964/2021-2022 | 451/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.22 | 1.22 | 0
763 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2023-2024 | 1241/BD | 25/04/2023 | 0 | Resource Division | 145.39 | 0 | 0
764 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000066/2023-2024 | 1631/BD | 01/06/2023 | 0 | Resource Division | 43.69 | 0 | 0
765 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Kulia water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000813/2022-2023 | 3586/BD | 08/12/2022 | 30 | PREMANANDA ROY BISWAS. | 73.89 | 72.44 | 100
766 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000161/2022-2023 | 494/BD | 17/02/2023 | 0 | Resource Division | 2.75 | 0 | 0
767 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Taranipur Zone-I Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000235/2023-2024 | 1734/BD | 08/06/2023 | 630 | DIVINE | 307.75 | 160.1 | 75
768 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Taranipur Zone I Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002758/2021-2022 | 446/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 3.69 | 1
769 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000046/2023-2024 | 1272/BD | 25/04/2023 | 0 | Resource Division | 5.86 | 0 | 0
770 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000027/2023-2024 | 1218/BD | 20/04/2023 | 30 | ANJALI ENTERPRISE. | 25.41 | 17.83 | 0
771 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 1219/BD | 20/04/2023 | 30 | ANJALI ENTERPRISE. | 12.7 | 9.5 | 0
772 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Barunhat Patlikhanpur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2023-2024 | 1428/BD | 11/05/2023 | 60 | JESMINE ENTERPRISE. | 17.34 | 17.15 | 100
773 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the left out portion in connection with Augmentation of Baruhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block of Hasnabad Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000097/2024-2025 | 1735/BD | 27/06/2024 | 90 | MONDAL & CO. (BASIRHAT). | 107.74 | 0 | 70
774 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of pump house with boundary wall & other allied works at PH No.-1 of Barunhat Patlikhanpur w/s scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000303/2023-2024 | 2117/BD | 19/07/2023 | 21 | M/S K.B.ENTERPRISE. | 7.39 | 0 | 100
775 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of new stand post for Barunhat patlikhanpur w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000308/2023-2024 | 829/HSD | 14/07/2023 | 10 | PRASANTA MITRA. | 2.89 | 0 | 100
776 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 500cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply Scheme(Z-I), Hasnabad Block under Hasnabad Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000751/2023-2024 | 2611/BD | 29/08/2023 | 365 | MONDAL & CO. (BASIRHAT). | 203.7 | 0 | 100
777 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000946/2022-2023 | 87/BD | 11/01/2023 | 90 | R.K.MANDAL & CO. | 317.9 | 262.6 | 80
778 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 350 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Barunhat Patlikhanpur water supply scheme (Z-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001097/2023-2024 | 2867/BD | 20/09/2023 | 528 | R.K.MANDAL & CO. | 152.42 | 0 | 100
779 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Barunhat Patlikhanpur water supply scheme (Z-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001150/2022-2023 | 699/BD | 03/03/2023 | 90 | MONDAL & CO. (BASIRHAT). | 417.62 | 406.32 | 48
780 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at OHR site in connection with augmentation io Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001452/2024-2025 | 326/HSD | 04/02/2025 | 10 | MONDAL & CO. (BASIRHAT). | 0.98 | 0 | 0
781 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Barunhat Patlikhanpur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001859/2023-2024 | 38/HSD | 09/01/2024 | 10 | SHYAM SUNDAR DAS. | 0.93 | 0 | 100
782 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000234/2022-2023 | 935/BD | 22/03/2023 | 0 | Resource Division | 80.45 | 0 | 0
783 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Sonepur water Supply Scheme within Swarupnagar Block under Basirhat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2024-2025 | 782/BD | 12/03/2025 | 300 | PREMANANDA ROY BISWAS. | 4.64 | 0 | 0
784 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Sonpur water supply scheme in Swarupnagar block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000750/2022-2023 | 3401/BD | 21/11/2022 | 90 | M/S ANUBHAB CONSTRUCTION. | 133.98 | 114.81 | 95
785 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Sonepur W/S Scheme including increasing the height of back wash water tank at Swarupnagara Block under Basirhat Sub Division, PHE Dte. Capacity-10.00Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002033/2023-2024 | 924/BD | 15/03/2024 | 360 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 23.32 | 0 | 75
786 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SONPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002497/2021-2022 | 458 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.87 | 2.87 | 1
787 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000148/2022-2023 | 3809/BD | 23/12/2022 | 0 | Resource Division | 0.41 | 0 | 0
788 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000152/2023-2024 | 4413/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0
789 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Sitalia Khaitala SSK, ICDS Centre no-77, Dakshin Sitalia FP School, South Hatgacha Jr. Basic School and Hatgacha Goramari FP Schoolwithin the command area of Khulna Bhanderkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000148/2025-2026 | 997/HSD | 04/06/2025 | 10 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.96 | 0 | 0
790 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at pond site for damaged portion & repairing of existing boundary wall at CWR site within Khulna Bhanderkhali w/s scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000298/2023-2024 | 2113/BD | 19/07/2023 | 21 | ANKUSH CONSTRUCTION & CO. | 6.14 | 6.14 | 55
791 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Khulna Bhanderkhali (Zone-II) under Surface Based Water Supply Scheme Hasnabad under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000321/2024-2025 | 2261/BD | 12/08/2024 | 365 | B.S.ENTERPRISE. (BASIRHAT) | 115.79 | 0 | 0
792 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Khulna Bhanderkhali W/S scheme (Zone-II), Sandeshkhali-II Block within Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000663/2022-2023 | 2722/BD | 14/09/2022 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 345.34 | 320.2 | 1
793 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000737/2023-2024 | 2491/BD | 18/08/2023 | 30 | M/S PROGATI ENTERPRISE. | 26.89 | 20.57 | 100
794 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Khulna Bhandarkhali Zone-II w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000848/2023-2024 | 2656/BD | 01/09/2023 | 30 | M/S DATTA ENTERPRISE. | 58.87 | 39.74 | 85
795 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001172/2022-2023 | 785/BD | 13/03/2023 | 30 | M/S NIRMAN CONSTRUCTION. | 47.08 | 36.84 | 100
796 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-3 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001296/2023-2024 | 1418/HSD | 06/11/2023 | 7 | DEB PRASAD GHOSH. | 0.93 | 0 | 100
797 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001297/2023-2024 | 1419/HSD | 06/11/2023 | 7 | DEB PRASAD GHOSH. | 0.96 | 0 | 100
798 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House at PH No- 1, 2 & 3 in connection with augmentation of Khulna Bhandarkhali w/s scheme (Zone-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001711/2024-2025 | 895/BD | 20/03/2025 | 75 | GAZI ENTERPRISE | 5.52 | 0 | 0
799 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000090/2022-2023 | 3421/BD | 23/11/2022 | 0 | Resource Division | 62.56 | 0 | 0
800 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000255/2022-2023 | 941/BD | 22/03/2023 | 0 | Resource Division | 9.14 | 0 | 0
801 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials and Laying of DI rising main, DI/UPVC distribution pipe line, providing Functional Household Tap Connection in connection with Augmentation of Chaimalpur water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000025/2023-2024 | 1221/BD | 20/04/2023 | 366 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 215.47 | 181.6 | 65
802 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 180 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300 mm dia 48 mtr. long housing pipe & 200 mm dia 30 mtr. long filter for Augmentation of Chaimalpur w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000744/2023-2024 | 2496/BD | 21/08/2023 | 30 | ANJALI ENTERPRISE. | 26.02 | 0 | 69
803 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in Nandanpur mouza within Chaimalpur w/s scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001372/2024-2025 | 239/HSD | 30/01/2025 | 10 | ABDUL HAMID GAZI. | 0.89 | 0 | 100
804 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000236/2022-2023 | 926/BD | 22/03/2023 | 0 | Resource Division | 4.71 | 0 | 0
805 | Barasat Division | Hasnabad Sub-Division | Enhancement of GST for the work providing FHTC for augmentation of Khulna Bhanderkhali (Zone-I) | Assistant Engineer | Junior Engineer | BILL/00273/2024-2025 | BP-2024-25-78 | 10/07/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 25.4 | 0 | 0
806 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-1 in connection with Augmentation of Khulna Bhandarkhali w/s scheme (Z-I), Sandeshkhali -II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000272/2023-2024 | 799/HSD | 13/07/2023 | 10 | JESMINE ENTERPRISE. | 0.9 | 0 | 100
807 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road with cement concrete at Pump house No-1 within Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000274/2023-2024 | 801/HSD | 13/07/2023 | 7 | JESMINE ENTERPRISE. | 0.57 | 0 | 100
808 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Khulna Bhanderkhali W/S scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2022-2023 | 3182/BD | 01/11/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 497.55 | 300.12 | 100
809 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000736/2023-2024 | 2490/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 26.91 | 0 | 100
810 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 450 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Khulna Bhanderkhali water supply scheme (Zone - I), Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000753/2023-2024 | 2610/BD | 29/08/2023 | 1095 | M/S PROGATI ENTERPRISE. | 194.78 | 0 | 0
811 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House at PH No- 1, 2 & 3 for Khulna Bhandarkhali w/s scheme (Zone-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000908/2023-2024 | 2719/BD | 05/09/2023 | 21 | LAHIRI CONSTRUCTION. | 6.11 | 0 | 80
812 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001173/2022-2023 | 786/BD | 13/03/2023 | 30 | MONDAL & CO. (BASIRHAT). | 47.09 | 37.47 | 0
813 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001295/2023-2024 | 1417/HSD | 06/11/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 0.98 | 0 | 100
814 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Khulna Bhanderkhali w/s scheme (Z-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001402/2024-2025 | 392/BD | 05/02/2025 | 60 | ANKUSH CONSTRUCTION & CO. | 12.47 | 0 | 100
815 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household tap connection at Sitalia FP School, South Hatgacha Jr. High School, Dakshin Hatgacha Adibasi SSK and Uttar Hatgacha SSK within the command area of Khulna Bhanderkhaliw/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001909/2024-2025 | 543/HSD | 10/03/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.83 | 0 | 0
816 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-3 in connection with Augmentation for Khulna Bhanderkhali water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001913/2023-2024 | 285/HSD | 06/03/2024 | 10 | DEB PRASAD GHOSH. | 0.67 | 0 | 100
817 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-3 in connection with Augmentation of Khulna Bhandarkhali w/s scheme (Z-I), Sandeshkhali -II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002346/2023-2024 | 800/HSD | 24/05/2023 | 10 | JESMINE ENTERPRISE. | 0.84 | 0 | 100
818 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000256/2022-2023 | 923/BD | 22/03/2023 | 0 | Resource Division | 94.23 | 0 | 0
819 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR, pipe connection and cost of pipes specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at P.H. No.-1 (Size - 5.40 x 3.60 mtr.) & P.H. No-2 (Size - 3.60 x 3.00 mtr.) for Hatbhanga W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000140/2023-2024 | 1714/BD | 08/06/2023 | 366 | POWER TOOLS & ENGINEERING | 268.27 | 0 | 65
820 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (HATBHANGA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002713/2021-2022 | 276/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
821 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (HATBHANGA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002714/2021-2022 | 277/HSD | 09/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 0.8 | 0.8 | 1
822 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000225/2022-2023 | 880/BD | 22/03/2023 | 0 | Resource Division | 16.26 | 0 | 0
823 | Barasat Division | Habra Sub-Division | Formal work order for Laying Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC at Zonal Head work site - XVII i.e. Betpuli within the jurisdiction of (Zone-XVII) under Habra-Gaighata surface based PWSS of Habra-I Block PART-F under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001179/2023-2024 | 3020/BD | 05/10/2023 | 810 | BALAJI UDDYOG | 991.27 | 0 | 65
824 | Barasat Division | Habra Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XIII) under Habra-Gaighata surface based PWSS of Habra-I Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001160/2023-2024 | 2958/BD | 29/09/2023 | 810 | M/S S.S.ENTERPRISE. (SOUTH) | 2094.04 | 0 | 65
825 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Donnagar Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000092/2023-2024 | 1531/BD | 19/05/2023 | 681 | M/S S. & P CONSTRUCTION | 147.04 | 15.87 | 20
826 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Donnagar Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-15 | Assistant Engineer | Junior Engineer | ORD/000308/2022-2023 | 562/BSD | 29/06/2022 | 30 | RADIANT | 2.6 | 0 | 100
827 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 250mm. X 150mm.dia. 300.00mtr. deep tubewell by direct rotary rig method, having 250mm.dia. 30.0mtr. long PVC housing pipe & 150mm.dia. 30.0mtr. long pre-packed resin bonded filter at Head Work Site of Donnagar Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000830/2022-2023 | 523/BD | 20/02/2023 | 15 | M/S SUKANTA ENTERPRISE. | 14.69 | 0 | 32
828 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000035/2023-2024 | 1274/BD | 25/04/2023 | 0 | Resource Division | 23.58 | 0 | 0
829 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000077/2023-2024 | 1675/BD | 06/06/2023 | 0 | Resource Division | 7.07 | 0 | 0
830 | Barasat Division | Bangaon Sub-Division | Formal work order for Construction of 350 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Purana Bongaon Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme). | Assistant Engineer | Junior Engineer | ORD/000246/2023-2024 | 2033/BD | 13/07/2023 | 366 | M/S B.K.ENTERPRISE. | 431.33 | 0 | 55
831 | Barasat Division | Bangaon Sub-Division | Survey, Design, Drawing & DPR preparation for new PWSS at Puratan Bongaon water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E.Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000848/2022-2023 | 344/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
832 | Barasat Division | Bangaon Sub-Division | Survey, Design, Drawing & DPR preparation for new PWSS at Puratan Bongaon water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E.Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000849/2022-2023 | 345/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.16 | 2.16 | 1
833 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Purana Bongaon Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001017/2023-2024 | 2834/BD | 15/09/2023 | 510 | NADIA TUBEWELLS | 21.56 | 0 | 100
834 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road and Land development at Head Work site of Purana Bongaon Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. 2nd Call. | Assistant Engineer | Junior Engineer | ORD/001250/2024-2025 | 228/BD | 20/01/2025 | 300 | SARKAR ENTERPRISE & CO. | 33.13 | 0 | 50
835 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000097/2023-2024 | 1863/BD | 23/06/2023 | 0 | Resource Division | 14.21 | 0 | 0
836 | Barasat Division | Bangaon Sub-Division | Formal Work order for Construction of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Garibpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme) | Assistant Engineer | Junior Engineer | ORD/000248/2023-2024 | 2057/BD | 14/07/2023 | 731 | AMIT KUMAR BOSE. | 223.93 | 75.26 | 54
837 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road and Land development at Head Work site of Garibpur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000572/2024-2025 | 3157/BD | 14/11/2024 | 30 | AMIT KUMAR BOSE. | 34.19 | 0 | 0
838 | Barasat Division | Bangaon Sub-Division | Survey, Design, Drawing & DPR preparation for new PWSS at Garibpur water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000852/2022-2023 | 348/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.45 | 4.45 | 1
839 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Garibpur Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001015/2023-2024 | 2832/BD | 15/09/2023 | 30 | NADIA TUBEWELLS | 21.56 | 0 | 100
840 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Garibpur w/s scheme Bongaon Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002173/2023-2024 | 607/BD | 23/02/2024 | 307 | TAPAN GHOSH. | 5.61 | 0 | 100
841 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000096/2023-2024 | 1866/BD | 23/06/2023 | 0 | Resource Division | 4.65 | 0 | 0
842 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXIV) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001172/2023-2024 | 2959/BD | 29/09/2023 | 720 | M/S S.S.ENTERPRISE. (SOUTH) | 1776.28 | 0 | 33
843 | Barasat Division | Barrackpore Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000100/2023-2024 | 1995/BD | 10/07/2023 | 0 | Resource Division | 126.15 | 0 | 0
844 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2, 3 & 4 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr.staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Katakhali water supply scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 1729/BD | 08/06/2023 | 1028 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 389.24 | 104.48 | 100
845 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of DI Rising main & UPVC distribution pipe line, protection works & other allied works within Katakhali w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000407/2024-2025 | 2738/BD | 20/09/2024 | 240 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 211.44 | 0 | 75
846 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1,2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Katakhali w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000862/2024-2025 | 3371/BD | 02/12/2024 | 90 | SHIBU BISWAS. | 77.65 | 0 | 100
847 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with column structure at PH No-- 2, 3 & 4 within Katakhali w/s scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002258/2024-2025 | 1028/BD | 28/03/2025 | 90 | R B ENTERPRISE | 25.44 | 0 | 0
848 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KATAKHALI Water Supply Scheme) in HASNABAD BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002689/2021-2022 | 231/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
849 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KATAKHALI Water Supply Scheme) in HASNABAD BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002690/2021-2022 | 232/HSD | 02/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.01 | 4.01 | 1
850 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000228/2022-2023 | 871/BD | 22/03/2023 | 0 | Resource Division | 249.11 | 0 | 0
851 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Kusangra W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000898/2023-2024 | 2703/BD | 04/09/2023 | 1096 | M/S PROGATI ENTERPRISE. | 439.52 | 0 | 20
852 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No- 1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kusangra w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001502/2024-2025 | 632/BD | 28/02/2025 | 60 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.49 | 0 | 0
853 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Over Head Reservoir site (HW site) for Kusangra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001811/2023-2024 | 676/BD | 01/03/2024 | 280 | M/S GHOSH CONSTRUCTION. | 8.58 | 0 | 90
854 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002721/2021-2022 | 284/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 0
855 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002722/2021-2022 | 287/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.44 | 3.44 | 0
856 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2024-2025 | 3477/BD | 10/12/2024 | 0 | Resource Division | 25.32 | 0 | 0
857 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000208/2022-2023 | 893/BD | 22/03/2023 | 0 | Resource Division | 45.01 | 0 | 0
858 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2025-2026 | 1385/BD | 30/04/2025 | 60 | UPWARDS ENGINEERING PRIVATE LIMITED. | 11.42 | 0 | 0
859 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Additional laying of UPVC pipe line under Augmentation of Koniara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000467/2025-2026 | 2860/BD | 14/08/2025 | 45 | HAQUE ENTERPRISE | 6.12 | 0 | 0
860 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000768/2023-2024 | 2689/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 0 | 100
861 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kaniara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2023-2024 | 2687/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 0 | 100
862 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kaniara Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 3764/BD | 20/12/2022 | 90 | SUPER SKILL. | 341.46 | 281.22 | 100
863 | Barasat Division | Bangaon Sub-Division | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.09.22 to 28.02.23=181 days. | Assistant Engineer | Junior Engineer | ORD/000949/2022-2023 | 1484/HSD | 29/08/2022 | 183 | SUSMITA MANDAL. | 2.7 | 9.29 | 100
864 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Koniara Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001338/2021-2022 | 137/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 1
865 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation of 32 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Koniara water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001543/2023-2024 | 14/BD | 02/01/2024 | 60 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 36.22 | 0 | 100
866 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Koniara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002969/2021-2022 | 552/ BON | 03/11/2021 | 21 | K. ENTERPRISE | 2.52 | 2.49 | 1
867 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000099/2022-2023 | 3656/BD | 13/12/2022 | 0 | Resource Division | 12.62 | 0 | 0
868 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000107/2022-2023 | 3693/BD | 14/12/2022 | 0 | Resource Division | 30.39 | 0 | 0
869 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 Nos. 330.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Sahebkhali w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2024-2025 | 629/HSD | 12/06/2024 | 10 | DEB PRASAD GHOSH. | 3.5 | 0 | 0
870 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Sahebkhali water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000031/2023-2024 | 1304/BD | 26/04/2023 | 777 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 554.49 | 222.57 | 90
871 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional laying of UPVC distribution pipe line including protection work for DI pipe at N/H/O Provas Halder towards Suvomay Mondal house & other allied work for UPVC pipe laying at different places in connection with Augmentation of Sahebkhali w/s scheme (Z-I), Hingalganj block within Hasnabad Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000069/2025-2026 | 1797/BD | 30/05/2025 | 60 | SAHA CONSTRUCTION & CO | 139.89 | 0 | 0
872 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No -I with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000534/2024-2025 | 2900/BD | 03/10/2024 | 30 | SUBHAJIT SAHA | 31.68 | 0 | 0
873 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Sahebkhali water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000938/2022-2023 | 88/BD | 11/01/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 354.45 | 260.86 | 1
874 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 250 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Sahebkhali water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001228/2023-2024 | 4110/BD | 17/10/2023 | 791 | ROY CHOWDHURY CONSTRUCTION. | 140.37 | 0 | 75
875 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Sahebkhali water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001266/2023-2024 | 4200/BD | 31/10/2023 | 365 | M/S RAJPATH CONSTRUCTION. | 150.42 | 0 | 0
876 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) for Augmentation of Sahebkhali w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001293/2024-2025 | 301/BD | 28/01/2025 | 75 | M/S S.HAQUE & CO. | 12.36 | 0 | 0
877 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001683/2023-2024 | 526/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 61.24 | 0 | 100
878 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3, 4 & 5 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Sahebkhali w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001932/2023-2024 | 915/BD | 15/03/2024 | 60 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 94.87 | 0 | 100
879 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000120/2023-2024 | 4175/BD | 30/10/2023 | 0 | Resource Division | 18.56 | 0 | 0
880 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000258/2022-2023 | 920/BD | 22/03/2023 | 0 | Resource Division | 137.48 | 0 | 0
881 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road with cement concrete at PH No.-3 within Joygopalpur w/s scheme, Sandehkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2022-2023 | 792/HSD | 13/05/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.8 | 0 | 1
882 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Connection of OHR from rising main and other allied works at Head Work site within Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000243/2022-2023 | 1152/HSD | 12/07/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 4.11 | 4.1 | 1
883 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional works for approach road with cement concrete and other allied works at Head Work site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000244/2022-2023 | 1153/HSD | 12/07/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 1.55 | 1.55 | 1
884 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Laxmikanta Singh within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2022-2023 | 1243/HSD | 20/07/2022 | 15 | M/S ANUBHAB CONSTRUCTION. | 0.56 | 0.57 | 1
885 | Barasat Division | Hasnabad Sub-Division | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Bermajur mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000665/2022-2023 | 2920/BD | 26/09/2022 | 30 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 24.18 | 24.16 | 1
886 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of existing concrete road for damaged portion due to movement of heavy vehicles during construction of OHR at Bermajur H.W. site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000704/2021-2022 | 1992/HSD | 02/12/2021 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.4 | 4.39 | 1
887 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of existing concrete road for damaged portion due to movement of heavy vehicles during construction of OHR at Bermajur H.W. site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000705/2021-2022 | 1993/HSD | 02/12/2021 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.78 | 4.78 | 1
888 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent supply, fitting & fixing of Main gate and other allied works at OHR site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000756/2022-2023 | 617/HSD | 07/04/2022 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.6 | 0.6 | 1
889 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000920/2021-2022 | 1861/HSD. | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 2.37 | 0 | 1
890 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000921/2021-2022 | 1861/HSD.. | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 2.37 | 2.37 | 0
891 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Malancha Zone I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000955/2021-2022 | 2151/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.43 | 4.4 | 1
892 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Malancha Zone II Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000956/2021-2022 | 2152/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.77 | 3.75 | 1
893 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Bhabanipur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000960/2021-2022 | 2156/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 1
894 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kalitala Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000999/2021-2022 | 2179/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.93 | 3.93 | 1
895 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at different places for protection of different dia UPVC distribution pipe line within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001526/2021-2022 | 1865/HSD | 17/11/2021 | 15 | M/S NIRMAN CONSTRUCTION. | 4.79 | 4.77 | 1
896 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001759/2021-2022 | 470/HSD | 10/03/2022 | 10 | ARBINA ENTERPRISE. | 3.89 | 3.88 | 1
897 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Bermajur Taltala Para, Molla para, Hatkhola Para, Dangal para, Kalyani para, Kachari para & Pol para within Bermajur W/S/Scheme Sandeshkhali-II Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002121/2021-2022 | 1465/BD. | 13/08/2021 | 30 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 32.29 | 6.09 | 1
898 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Bermajur w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002573/2021-2022 | 417/HSD | 04/03/2022 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.87 | 3.89 | 1
899 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.07.2021 to 30.06.2022 = 365 days | Assistant Engineer | Junior Engineer | ORD/002867/2021-2022 | 1112/HSD | 29/06/2021 | 365 | RANJIT KUMAR MANDAL. | 3.15 | 1.05 | 1
900 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000091/2023-2024 | 1820/BD | 19/06/2023 | 0 | Resource Division | 20.33 | 0 | 0
901 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000194/2022-2023 | 677/BD | 01/03/2023 | 0 | Resource Division | 61.6 | 0 | 0
902 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Akipur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001248/2021-2022 | 402/BD | 10/02/2022 | 30 | SARKAR ENTERPRISE & CO. | 51.46 | 46.89 | 1
903 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for AKIPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001953/2021-2022 | 304/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.02 | 2.95 | 1
904 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000074/2022-2023 | 2987/BD | 29/09/2022 | 0 | Resource Division | 0.01 | 0 | 0
905 | Barasat Division | Basirhat Sub-Division | Repairing & renovation of Pump House No. - 1 & 2 of Deora W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000366/2022-2023 | 389/HAB | 21/07/2022 | 30 | M/S SAMIT CHANDRA DEY. | 2.09 | 2.06 | 0
906 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000065/2022-2023 | 2341/BD | 26/09/2022 | 0 | Resource Division | 2.93 | 0 | 0
907 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000178/2022-2023 | 603/BD | 23/02/2023 | 0 | Resource Division | 38.14 | 0 | 0
908 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001026/2021-2022 | 14/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 0 | 1
909 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001028/2021-2022 | 16/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 1
910 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Bouthakurani Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001032/2021-2022 | 20/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 1
911 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001037/2021-2022 | 24/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 1
912 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/001040/2021-2022 | 26/HSD | 04/01/2022 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.79 | 4.76 | 1
913 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000085/2023-2024 | 1813/BD | 19/06/2023 | 0 | Resource Division | 2.59 | 0 | 0
914 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Dakshin Bagundi piped Water Supply Scheme at Basirhat -I Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000568/2021-2022 | 1955/BD | 08/10/2021 | 15 | DEY & CO. | 16.5 | 14.77 | 1
915 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Kulia Piped water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000566/2021-2022 | 1953/BD | 08/10/2021 | 15 | B.S.ENTERPRISE. (BASIRHAT) | 21.69 | 21.27 | 1
916 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALSA Water Supply Scheme at Habra - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001120/2021-2022 | 181/BD | 20/01/2022 | 45 | CHANDA CONSTRUCTION. | 71.19 | 69.88 | 1
917 | Barasat Division | Basirhat Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Bajitur Zone-II Water Supply Scheme at Baduria Block, Dist- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/000670/2021-2022 | 2269/BD/BD | 26/11/2021 | 90 | ORIENT CONSTRUCTION. | 128.44 | 114.35 | 1
918 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BAJITPUR ZONE -2 Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001983/2021-2022 | 355/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 3.72 | 1
919 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Raghunathpur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000342/2021-2022 | 1673/BD | 08/09/2021 | 30 | SHIBU BISWAS. | 48.8 | 48.11 | 1
920 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAGHUNATHPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001971/2021-2022 | 345/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.11 | 3.1 | 1
921 | Barasat Division | Habra Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHOSDELPUR & ITS ADJ. MOUZAS Water Supply Scheme at Habra - II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000915/2021-2022 | 2624/BD | 27/12/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PVT.LTD. | 114.14 | 87.23 | 1
922 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Murarisha Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000957/2021-2022 | 2153/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.05 | 4.05 | 1
923 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001326/2021-2022 | 128/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.55 | 4.55 | 1
924 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Dakshin Bhebia Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002036/2021-2022 | 2183/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.49 | 4.49 | 1
925 | Barasat Division | Basirhat Sub-Division | Day to Day repair Operation & maintenance of CI/DI/HDPE/UPVC/AC/GI Rising main & Distribution system for Bansghata water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001229/2021-2022 | 622/Bon | 31/12/2021 | 1 | KAMAL HALDAR. | 1.39 | 0 | 1
926 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Bansjhari Mallikpur Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase -I). | Assistant Engineer | Junior Engineer | ORD/001242/2021-2022 | 400/BD | 10/02/2022 | 30 | SUDHAMAY MAJUMDAR. | 50.02 | 21.5 | 1
927 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BANSJHARI MALLIKPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001942/2021-2022 | 198/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.29 | 3.27 | 1
928 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000101/2022-2023 | 3660/BD | 13/12/2022 | 0 | Resource Division | 3.12 | 0 | 0
929 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Champali w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000339/2021-2022 | 1671/BD | 08/09/2021 | 45 | M/S NIRMAN CONSTRUCTION. | 77.7 | 76.48 | 1
930 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line in Champali mouza within Champali w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000699/2021-2022 | 1987/HSD | 02/12/2021 | 7 | S.K.ENTERPRISE. | 2.44 | 2.44 | 1
931 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid DI/UPVC pipe line by UC bullah pile at different places in Champali mouza within Champali w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000703/2021-2022 | 1991/HSD | 02/12/2021 | 10 | M/S NIRMAN CONSTRUCTION. | 4.38 | 4.38 | 1
932 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000081/2023-2024 | 1810/BD | 19/06/2023 | 0 | Resource Division | 13.49 | 0 | 0
933 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000083/2022-2023 | 1539/BD | 30/05/2022 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 158.7 | 155.05 | 1
934 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work for newly laid UPVC pipe line at different places of Rampur & Dhamakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 1670/BD | 06/06/2023 | 30 | S.S.ENTERPRISE. (BAMANGACHI) | 115.27 | 115.23 | 60
935 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Moilobi Para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000380/2022-2023 | 1318/HSD | 02/08/2022 | 10 | R.K.MANDAL & CO. | 4.81 | 4.76 | 1
936 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Gayen para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000381/2022-2023 | 1319/HSD | 02/08/2022 | 10 | SARKAR ENTERPRISE & CO. | 3.98 | 3.97 | 1
937 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur Hat khola para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 1320/HSD | 02/08/2022 | 10 | BARNALI DUTTA | 3.91 | 3.88 | 1
938 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Kachari para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000383/2022-2023 | 1321/HSD | 02/09/2022 | 10 | ABDUL HAMID GAZI. | 4.05 | 4.04 | 1
939 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line from Molla store to Abu baktar shop at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000391/2022-2023 | 1330/HSD | 02/08/2022 | 10 | S.S.ENTERPRISE. (BAMANGACHI) | 2.6 | 2.59 | 1
940 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line From Abu Baktar to Toto stand at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000393/2022-2023 | 1332/HSD | 02/08/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 3.98 | 3.95 | 1
941 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line From Khaja baba Fish arot to Mamoni Builder's at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000399/2022-2023 | 1338/HSD | 02/08/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.17 | 4.11 | 1
942 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia HDPE/UPVC distribution pipe line From Mamoni Builder's to Molla store at Rampur Bazaar in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2022-2023 | 1339/HSD | 02/08/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 2.97 | 2.91 | 1
943 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur Haldar para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000415/2022-2023 | 1347/HSD | 03/08/2022 | 10 | R.K.MANDAL & CO. | 4.88 | 4.85 | 1
944 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur notun para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000416/2022-2023 | 1348/HSD | 03/08/2022 | 10 | SARKAR ENTERPRISE & CO. | 4.17 | 4.16 | 1
945 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Rampur Adibasi para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000417/2022-2023 | 1349/HSD | 03/08/2022 | 10 | R.K.MANDAL & CO. | 4.76 | 4.73 | 1
946 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Refuge para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000420/2022-2023 | 1352/HSD | 03/08/2022 | 10 | R.K.MANDAL & CO. | 4.33 | 4.29 | 1
947 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Arsad Miya Bazaar in Dhamakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000421/2022-2023 | 1353/HSD | 03/08/2022 | 10 | SARKAR ENTERPRISE & CO. | 4.73 | 4.56 | 1
948 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Paschim Dhamakhali pramanik para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000433/2022-2023 | 1359/HSD | 03/08/2022 | 10 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 4.02 | 4.01 | 1
949 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Purba dhamakhali pramanik para in Dhamakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000434/2022-2023 | 1360/HSD | 03/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.81 | 4.76 | 1
950 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of samanta Para in Rampur Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad SubDivision P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000446/2022-2023 | 1317/HSD | 02/08/2022 | 10 | MUKHERJEE CONSTRUCTION | 4.85 | 4.85 | 1
951 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Ghoja para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000466/2022-2023 | 1391/HSD | 08/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.26 | 4.21 | 1
952 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of Mistiri para in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000467/2022-2023 | 1392/HSD | 08/08/2022 | 10 | M/S R.B.S.ENTERPRISE. | 4.13 | 4.12 | 1
953 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid UPVC pipe line at different places of 50 Bigha More in Damakhali Mouza in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2022-2023 | 1394/HSD | 08/08/2022 | 10 | M/S B.K.ENTERPRISE. | 4.09 | 4.08 | 1
954 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Rampur mouza due to erosion of soil for heavy rain fall during monsoon season within Rampur w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000996/2023-2024 | 1080/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.99 | 0 | 100
955 | Barasat Division | Hasnabad Sub-Division | Continuation order for Hiring of one no. DIESEL MOTOR CAB (BS-IV) on daily hire basis for use of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.10.21 to 30.09.22. | Assistant Engineer | Junior Engineer | ORD/001081/2021-2022 | 1617/HSD | 29/09/2021 | 365 | SUSMITA MANDAL. | 1.72 | 3.75 | 1
956 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at Pump House No.-2 within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001144/2022-2023 | 771/HSD | 13/05/2022 | 21 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.77 | 4.17 | 1
957 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at Pump House No.-2 within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001145/2022-2023 | 772/HSD | 13/05/2022 | 21 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 1.75 | 1.7 | 1
958 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work (Ph No-1) site within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001349/2023-2024 | 4438/BD | 10/11/2023 | 90 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 22.05 | 0 | 100
959 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road & other allied works at Head Work site (PH No.-1) within Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001427/2021-2022 | 526/BD | 23/02/2022 | 990 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 31.47 | 13.57 | 100
960 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid Distribution main 300 mm dia DI Pipe with UC bullah pile from HW site to PWD Road within Rampur w/s scheme,Sandeskhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002826/2021-2022 | 510/HSD | 15/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 2.25 | 2.01 | 1
961 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of distribution main by concrete block for low areas from Pole para to Rampur bazaar in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002827/2021-2022 | 511/HSD | 15/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.09 | 4.03 | 1
962 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 100/150 mm dia DI distribution main by concrete block for low areas of Rampur w/s scheme in connection with retrofitting, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002828/2021-2022 | 512/HSD | 15/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 3.05 | 2.94 | 1
963 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of distribution main by concrete block for low areas at Halder Ghery to Pole para in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002852/2021-2022 | 568/HSD | 22/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 3.97 | 3.92 | 1
964 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Emergent resting of distribution main by concrete block for low areas at Halder Ghery to Pole para in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002853/2021-2022 | 569/HSD | 22/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 4.24 | 4.19 | 1
965 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of distribution main by concrete block for low areas at PWD road to Rampur Burning ghat in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002854/2021-2022 | 570/HSD | 22/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.02 | 2.38 | 1
966 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 200mm dia DI distribution main by concrete block for low areas in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002855/2021-2022 | 571/HSD | 22/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.5 | 3.63 | 0
967 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 250mm dia DI distribution main by concrete block for low areas in connection with retrofitting of Rampur w/s scheme , Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002856/2021-2022 | 572/HSD | 22/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 4.12 | 3.28 | 0
968 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid 125 mm dia HDPE distribution pipe line from Arsad Miya Bazar to Dhamakhali Busstand in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002870/2021-2022 | 578/HSD | 28/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.73 | 3.59 | 1
969 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Haldar para,Haldar gheri more & pole para in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002874/2021-2022 | 582/HSD | 28/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.17 | 4.11 | 1
970 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Molla para,Colony para,Samanta Para & Bagdi para connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002877/2021-2022 | 586/HSD | 28/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.06 | 3.97 | 1
971 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Akunji para,Naskar para,Gajen para & 50 Bigha more in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002881/2021-2022 | 590/HSD | 29/03/2022 | 15 | S.S.ENTERPRISE. (BAMANGACHI) | 4.75 | 4.6 | 1
972 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia UPVC distribution pipe line at different places of Bagdipara to rampur bazar road,rampur ferry ghat to anganwadi centre & 972 bus stand in connection with retrofitting of Rampur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002889/2021-2022 | 598/HSD | 31/03/2022 | 15 | NEW MANGES INDUSTRIAL CORPORATION | 1.39 | 1.31 | 1
973 | Barasat Division | Habra Sub-Division | Construction of Service Road (55 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000342/2024-2025 | 693/HAB | 25/07/2024 | 10 | G.P.ENTERPRISE. | 1.22 | 0 | 0
974 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system for Augmentation of Kamarpur & Adj. Mouzas water supply scheme within jurisdiction of Habra Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000523/2022-2023 | 2445/BD | 23/08/2022 | 90 | CHANDA CONSTRUCTION. | 212.3 | 172.88 | 100
975 | Barasat Division | Habra Sub-Division | Special repair and renovation of pump house and other Allied Works for Pump House No - 1 of Kamarpur WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2024-2025 | 922/HAB | 30/10/2024 | 20 | M/S LATIKA CONSTRUCTION. | 2.66 | 0 | 0
976 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Kamarpur W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000895/2024-2025 | 927/HAB | 05/11/2024 | 20 | M/S LATIKA CONSTRUCTION. | 2.6 | 0 | 100
977 | Barasat Division | Habra Sub-Division | Construction of Service Road 55 Mtr. Length X 2 Mtr. Width for Pump House No1 of kamarpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000901/2024-2025 | 934/HAB | 06/11/2024 | 10 | M/S LATIKA CONSTRUCTION. | 3.35 | 0 | 0
978 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Kamarpur & Adjoining Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000912/2023-2024 | 2776/BD | 11/09/2023 | 60 | ANJALI ENTERPRISE. | 28.99 | 0 | 65
979 | Barasat Division | Habra Sub-Division | Improvement of Iron Elimination Plant at Kamarpur & adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001460/2023-2024 | 689/HAB | 01/11/2023 | 30 | M/S LATIKA CONSTRUCTION. | 2.97 | 0 | 100
980 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. ? 1 & 2 of Kamarpur& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002984/2021-2022 | 512/HAB | 10/12/2021 | 30 | M/S LATIKA CONSTRUCTION. | 1.4 | 1.32 | 1
981 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2022-2023 | 2517/BD | 25/08/2022 | 0 | Resource Division | 6.75 | 0 | 0
982 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000132/2022-2023 | 3800/BD | 22/12/2022 | 0 | Resource Division | 4.41 | 0 | 0
983 | Barasat Division | Habra Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Sadpur Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000110/2023-2024 | 1669/BD | 06/06/2023 | 90 | B.M.ENTERPRISE. | 105.99 | 0 | 80
984 | Barasat Division | Habra Sub-Division | Repairing of Boundary Wall for Pump House No - 1 of Sadpur water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000199/2024-2025 | 691/HAB | 24/07/2024 | 35 | JOY ENTERPRISE | 4 | 0 | 100
985 | Barasat Division | Habra Sub-Division | Construction of Service Road 50 Mtr. Length and 2 Mtr. Width for Pump House No1 of Sadpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000600/2024-2025 | 783/HAB | 20/08/2024 | 10 | JOY ENTERPRISE | 2.95 | 0 | 100
986 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 for Augmentation of Sadpur water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000959/2023-2024 | 2772/BD | 11/09/2023 | 674 | NADIA TUBEWELLS | 14.48 | 0 | 100
987 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other allied Works for Pump House No - 1 of Sadpur W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001888/2023-2024 | 136/HAB | 05/02/2024 | 15 | JOY ENTERPRISE | 0.45 | 0 | 100
988 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. - 1 of Sadpur W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002979/2021-2022 | 500/HAB | 02/12/2021 | 30 | M/S SUKANTA ENTERPRISE. | 0.74 | 0.7 | 1
989 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 1560/BD | 23/05/2023 | 0 | Resource Division | 1.23 | 0 | 0
990 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000135/2022-2023 | 3795/BD | 22/12/2022 | 0 | Resource Division | 0.87 | 0 | 0
991 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at East & West side for damaged portion at PH No.-4 for Rejuvenation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000527/2020-2021 | 393/HSD | 11/02/2021 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.87 | 1.8 | 0
992 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) for Hingalganj Mouza within Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000539/2021-2022 | 1644/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 2.59 | 2.58 | 0
993 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) for Mamudpur Mouza within Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000540/2021-2022 | 1645/HSD | 05/10/2021 | 15 | TRISHA ENTERPRISE & CO. | 2.54 | 2.53 | 0
994 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for OHR connection with distribution main including Laying of balance laying work of rising main and distribution pipe line within Hingalganj water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2021-2022 | 1646/HSD | 05/10/2021 | 15 | ANKUSH CONSTRUCTION & CO. | 4.51 | 4.48 | 0
995 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Land development at Pump House No.-1 (New site) within Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000542/2021-2022 | 1647/HSD | 05/10/2021 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.14 | 1.14 | 0
996 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Pump House No-2 to Pump House No.-1 (New site) within Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000543/2021-2022 | 1648/HSD | 05/10/2021 | 10 | R.K.MANDAL AND CO. | 1.2 | 1.18 | 0
997 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Paitkelpota & Paitkelpota Abad mouza including laying of UPVC/PVC pipe & supply of necessary fittings Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000544/2021-2022 | 1649/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 1.9 | 1.9 | 0
998 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Joykrisnapur mouza including laying of UPVC/PVC pipe & supply of necessary fittings Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2021-2022 | 1652/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 3.04 | 3.04 | 0
999 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of pipeline by withdrawn & relaying of different dia. UPVC pipe line for extra widening of PWD road from Ghoshpara More to Sri Chaitanya Math within Hingalganj W/S Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000548/2021-2022 | 1653/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 4.61 | 4.6 | 0
1000 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of pipeline by withdrawn & relaying of different dia. UPVC pipe line for extra widening of PWD road from Sri Chaitanya Math to Pather Dabi More within Hingalganj W/S Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2021-2022 | 1654/HSD | 05/10/2021 | 15 | MONDAL & CO. (BASIRHAT). | 4.6 | 4.59 | 0
1001 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Bouthakurani water supply scheme (For Bouthakurani & Tongtala Mouza) at Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2021-2022 | 1655/HSD | 05/10/2021 | 15 | M/S B.K.ENTERPRISE. | 4.35 | 4.35 | 0
1002 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Emergent restoration of concrete road for damage portion at different places due to newly laid HDPE/DI pipeline within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000553/2021-2022 | 1658/HSD | 05/10/2021 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 2.86 | 2.86 | 0
1003 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/HDPE/UPVC) of Hasnabad w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000554/2021-2022 | 1659/HSD | 05/10/2021 | 21 | MONDAL & CO. (BASIRHAT). | 4.4 | 4.4 | 0
1004 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional land development at tube well site-3 (CWR site) within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000555/2021-2022 | 1660/HSD | 05/10/2021 | 10 | TRISHA ENTERPRISE & CO. | 0.92 | 0.92 | 0
1005 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Khosbas & Singerkati mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000556/2021-2022 | 1661/HSD | 05/10/2021 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.2 | 1.2 | 0
1006 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of different dia. Sluice Valve & construction of different dia. Sluice Valve chamber at different places within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000558/2021-2022 | 1663/HSD | 05/10/2021 | 10 | MONDAL & CO. (BASIRHAT). | 4.88 | 4.88 | 0
1007 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Radhanagar mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Chotto Sehara w/s scheme Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000560/2021-2022 | 1665/HSD | 05/10/2021 | 10 | TRISHA ENTERPRISE & CO. | 3.56 | 3.56 | 0
1008 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House No.-3 for Rejuvenation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000647/2020-2021 | 385/HSD | 11/02/2021 | 15 | M/S LALTI ENTERPRISE | 1.31 | 1.28 | 0
1009 | Barasat Division | Basirhat Sub-Division | Special Repairing of DI pipe, Supply of Sluice valve & construction of Sluice valve chamber for Augmentation of Dhanyakuria Water Supply Scheme in Basirhat-II block of North 24 Parganas district under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2024-2025 | 935/BHTSD | 24/05/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.88 | 0 | 0
1010 | Barasat Division | Basirhat Sub-Division | Special Repairing of existing HDPE & UPVC pipelines for Augmentation of Dhanyakuria Water Supply Scheme in Basirhat-II block of North 24 Parganas district under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000081/2024-2025 | 936/BHTSD | 24/05/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 0.98 | 0 | 0
1011 | Barasat Division | Basirhat Sub-Division | Hiring of Diesel Luxury Car is essential for proper supervision of huge number of ground water based Augmentation Scheme at different blocks under Basirhat Sub-Division P.H.E. Dte. (Period 01.07.2024 to 31.12.2024 for Six Month), Sl.No. - 01 | Assistant Engineer | Junior Engineer | ORD/000157/2024-2025 | 1017/BHTSD | 28/06/2024 | 184 | OM ENTERPRISE | 0.87 | 0 | 0
1012 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Dhanyakuria water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000745/2022-2023 | 3343/BD | 16/11/2022 | 991 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 888.3 | 175.53 | 36
1013 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Eucalyptus Bullah Pilling for Emergency protection Work of Pipe line at different places for Augmentation of Dhanyakuria Water Supply Scheme of Basirhat Sub Division under Barasat Division P.H.E. | Assistant Engineer | Junior Engineer | ORD/001561/2024-2025 | 542/BD | 19/02/2025 | 30 | SAMIR KUMAR DEY. | 52.24 | 0 | 0
1014 | Barasat Division | Basirhat Sub-Division | Hiring additional Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.07.2023 to 31.12.2023) | Assistant Engineer | Junior Engineer | ORD/002104/2023-2024 | 605/BHTSD | 28/06/2023 | 184 | OM ENTERPRISE | 0.87 | 0 | 0
1015 | Barasat Division | Basirhat Sub-Division | Continuation Work for Hiring additional Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period: 01.01.2024 to 30.06.2024) | Assistant Engineer | Junior Engineer | ORD/002419/2023-2024 | 1291/BHTSD | 29/12/2023 | 183 | OM ENTERPRISE | 0.86 | 0 | 0
1016 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2024-2025 | 3480/BD | 10/12/2024 | 0 | Resource Division | 99.05 | 0 | 0
1017 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000145/2023-2024 | 4410/BD | 10/11/2023 | 0 | Resource Division | 12.32 | 0 | 0
1018 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000172/2022-2023 | 491/BD | 17/02/2023 | 0 | Resource Division | 184.92 | 0 | 0
1019 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000186/2022-2023 | 608/BD | 23/02/2023 | 0 | Resource Division | 40.91 | 0 | 0
1020 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Magurali water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000744/2022-2023 | 3342/BD | 16/11/2022 | 984 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 567.42 | 396.63 | 71
1021 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000136/2023-2024 | 4408/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0
1022 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000147/2022-2023 | 3816/BD | 23/12/2022 | 0 | Resource Division | 119.56 | 0 | 0
1023 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000179/2022-2023 | 610/BD | 23/02/2023 | 0 | Resource Division | 10.1 | 0 | 0
1024 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for special repair and renovation of existing structures like Pump House, boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Champapukur, Chandipur, Dakhin Debipur, Dhopaberia, Srinagar and Sangrampur Water Supply Scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2025-2026 | 2424/BD | 14/07/2025 | 150 | DAS ENTERPRISE | 82.86 | 0 | 0
1025 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 1 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Champapukuria Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2024-2025 | 3261/BD | 25/11/2024 | 30 | NEW MA TARA ENTERPRISE. | 21.59 | 0 | 0
1026 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Champapukuria water supply scheme in Basirhat-II block of North 24 Parganas Distruct under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000776/2022-2023 | 3473/BD | 01/12/2022 | 90 | UTPAL CONSTRUCTION & CO. | 211.02 | 192.42 | 92
1027 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2022-2023 | 2308/BD | 03/08/2022 | 0 | Resource Division | 2.43 | 0 | 0
1028 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000159/2023-2024 | 4418/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0
1029 | Barasat Division | Bangaon Sub-Division | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Bongaon S.D. Hospital w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000081/2025-2026 | 532/Bon | 22/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0
1030 | Barasat Division | Bangaon Sub-Division | Installation of CCTV Camera Connection at Pump house no 1 & 2 for Chhaygharia (Zone-I) w/s scheme, Bongaon Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000082/2025-2026 | 533/Bon | 22/04/2025 | 7 | ELDORADO | 0.55 | 0 | 0
1031 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chhayagharia Water Supply Scheme (Z-I), Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000347/2024-2025 | 2420/BD | 23/08/2024 | 60 | ACHINTA KUMAR HALDER. | 28.75 | 0 | 0
1032 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chhaighoria (Zone-I) water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000794/2023-2024 | 2683/BD | 04/09/2023 | 30 | DHELA BABA ENTERPRISE | 16.17 | 0 | 100
1033 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chhayagharia(Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000824/2022-2023 | 3604/BD | 09/12/2022 | 90 | MONDAL ENTERPRISE. (BARASAT) | 462.8 | 461.39 | 1
1034 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chhayageria (Zone-I) water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001169/2023-2024 | 2691/BD | 04/09/2023 | 540 | JOY HIND TUBEWELLS. | 16.16 | 0 | 100
1035 | Barasat Division | Bangaon Sub-Division | Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Chhaygharia (Zone-I) W/S Scheme under Bongaon block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001460/2024-2025 | 1504/Bon | 30/12/2024 | 150 | IMPULSE INTERNATIONAL | 4.79 | 0 | 100
1036 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st Tube Well & 2nd Tube Well site under Augmentation of Chhaygharia (Zone-I) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001743/2023-2024 | 559/BD | 22/02/2024 | 495 | KAMAL HALDER. | 7.2 | 0 | 60
1037 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chhaygharia (Zone-I) Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002770/2021-2022 | 123/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 3.45 | 1
1038 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Chhayageria Zone-I water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002949/2021-2022 | 533/BD | 03/11/2021 | 21 | DURGA ENTERPRISE. | 2.52 | 2.48 | 1
1039 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000098/2022-2023 | 3655/BD | 13/12/2022 | 0 | Resource Division | 20.38 | 0 | 0
1040 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000119/2022-2023 | 3688/BD | 14/12/2022 | 0 | Resource Division | 35.66 | 0 | 0
1041 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection(FHTC) for Augmentation of Shimulpur water supply scheme under Bongaon Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2023-2024 | 1126/BD | 11/04/2023 | 720 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 639.23 | 486.6 | 100
1042 | Barasat Division | Bangaon Sub-Division | Construction of Latrine at Head Work site for Augmentation of Shimulpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000616/2025-2026 | 672/Bon | 26/05/2025 | 45 | A.D.ENTERPRISE. | 1.75 | 0 | 0
1043 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Shimulpur water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000797/2023-2024 | 2697/BD | 04/09/2023 | 30 | NADIA TUBEWELLS | 16.16 | 0 | 100
1044 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Shimulpur Water Supply Scheme (2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001113/2023-2024 | 2936/BD | 27/09/2023 | 442 | JOY GURU ENTERPRISE | 16.12 | 0 | 100
1045 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Shimulpur Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001348/2021-2022 | 144/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.34 | 0 | 1
1046 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site, 2nd Pump House Site & 3rd Pump House Site under Augmentation of Shimulpur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001747/2023-2024 | 564/BD | 22/02/2024 | 45 | M/S SUKANTA ENTERPRISE. | 12.72 | 0 | 100
1047 | Barasat Division | Bangaon Sub-Division | Formal work order for Additional laying of UPVC pipe with allied works to connect every house hold connection under Augmentation work at Simulpur W/S Scheme Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001767/2023-2024 | 610/BD | 27/02/2024 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 102.67 | 0 | 100
1048 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Shimulpur Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001784/2023-2024 | 628/BD | 28/02/2024 | 45 | TAPAN GHOSH. | 6.03 | 0 | 100
1049 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Shimulpur Water Supply Scheme in Gaighata Block withinthe Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002899/2021-2022 | 144/ BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.34 | 4.32 | 1
1050 | Barasat Division | Bangaon Sub-Division | Work order for repairing & renovation of Pump House and allied works of Simulpur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002943/2021-2022 | 587/ BON | 15/12/2021 | 21 | ONKAR ENTERPRISE. | 2.52 | 2.32 | 1
1051 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Shimulur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002972/2021-2022 | 631/ BON | 31/12/2021 | 15 | ONKAR ENTERPRISE. | 1.26 | 1.15 | 1
1052 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000095/2022-2023 | 3654/BD | 13/12/2022 | 0 | Resource Division | 40.85 | 0 | 0
1053 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000114/2022-2023 | 3690/BD | 14/12/2022 | 0 | Resource Division | 52.1 | 0 | 0
1054 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000010/2024-2025 | 1535/BD | 07/06/2024 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 13.15 | 0 | 100
1055 | Barasat Division | Habra Sub-Division | Formal work order fior Laying of DI rising main, UPVC distribution pipe line and Providing Functional Household Tap Connection for augmentation of Matiagacha Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000033/2023-2024 | 1356/BD | 04/05/2023 | 720 | M/S R.K. ENTERPRISE | 231.73 | 98.26 | 80
1056 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Matiagachha W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (SM/11667) | Assistant Engineer | Junior Engineer | ORD/000643/2024-2025 | 3130/BD | 12/11/2024 | 180 | M/S SUKANTA ENTERPRISE. | 115.81 | 0 | 30
1057 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site & 2nd Pump House site under Augmentation of Matiagachha Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001746/2023-2024 | 563/BD | 22/02/2024 | 45 | M/S SANDHYA CONSTRUCTION | 9.88 | 0 | 100
1058 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & DPR Preparation for Matiagacha W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002763/2021-2022 | 128/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.35 | 3.27 | 1
1059 | Barasat Division | Habra Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Matiagacha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002937/2021-2022 | 530/BON | 03/11/2021 | 21 | KAMAL HALDER. | 2.52 | 2.5 | 1
1060 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000007/2023-2024 | 1252/BD | 25/04/2023 | 0 | Resource Division | 8.28 | 0 | 0
1061 | Barasat Division | Bangaon Sub-Division | Formal work order for Construction of 200 cum capacity CWR with pipe connection, Construction of Boundary wall, Approach Road, Earth Filling, Construction of 5.40 mtr. X 3.60 mtr. size Switch Room with sanitary and water supply arrangement and Laying of DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah pile at different places at Diara (Zone-II) Water Supply Scheme in connection with surface water based water supply scheme of Bongaon-Bagdah in the District of North 24 Parganas under Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2024-2025 | 2222/BD | 07/08/2024 | 270 | ROY CHOWDHURY CONSTRUCTION. | 108.24 | 0 | 60
1062 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long ribbed strainer at Head Work site for Augmentation of Diara (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000143/2025-2026 | 2042/BD | 20/06/2025 | 60 | JOY GURU ENTERPRISE | 16.37 | 0 | 0
1063 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit (3.15 m. dia. x 1.50 m. ht.) (including media) under Augmentation of Diara Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2025-2026 | 2074/BD | 24/06/2025 | 45 | ONKAR ENTERPRISE. | 21.65 | 0 | 0
1064 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Diara Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction and also to convert the 'Kapashati' mouza (JL No. 73) in to Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2025-2026 | 2859/BD | 14/08/2025 | 45 | ROY ENGINEERS. | 7.98 | 0 | 0
1065 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Diara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000782/2022-2023 | 3489/BD | 02/12/2022 | 90 | MONDAL & CO. (BASIRHAT). | 380.98 | 332.09 | 100
1066 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Diara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000796/2023-2024 | 2696/BD | 04/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.1 | 0 | 100
1067 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Diara Water Supply Scheme (2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001107/2023-2024 | 2920/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 0 | 100
1068 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Diara water Supply scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001481/2023-2024 | 4414/BD | 10/11/2023 | 60 | ACHINTA KUMAR HALDER. | 14.5 | 0 | 100
1069 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Diara Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001561/2023-2024 | 39/BD | 04/01/2024 | 391 | J AND T ENTERPRISE | 8.89 | 0 | 0
1070 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kola water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002912/2021-2022 | 516/Bon | 31/12/2021 | 21 | ROY ENGINEERS. | 2.52 | 0 | 1
1071 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000120/2022-2023 | 3711/BD | 15/12/2022 | 0 | Resource Division | 14.86 | 0 | 0
1072 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000151/2022-2023 | 78/BD | 10/01/2023 | 0 | Resource Division | 118.89 | 0 | 0
1073 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 500 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000792/2023-2024 | 2614/BD | 29/08/2023 | 365 | M/S B.K.ENTERPRISE. | 203.43 | 0 | 75
1074 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001135/2022-2023 | 517/BD | 20/02/2023 | 90 | M/S B.K.ENTERPRISE. | 372.13 | 241.24 | 100
1075 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with augmentation of Chaital water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001398/2024-2025 | 264/HSD | 30/01/2025 | 10 | M/S R.B.S.ENTERPRISE. | 0.62 | 0 | 100
1076 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Chaital water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002054/2023-2024 | 881/BD | 14/03/2024 | 90 | M/S B.K.ENTERPRISE. | 140.08 | 0 | 80
1077 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000259/2022-2023 | 921/BD | 22/03/2023 | 0 | Resource Division | 101.89 | 0 | 0
1078 | Barasat Division | Basirhat Sub-Division | Enhancement of GST for laying of distribution pipe line and providing FHTC for Augmentation of Sadiknagar Zone -I water supply scheme under Basirhat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | BILL/01247/2024-2025 | BP-2024-25-391 | 04/10/2024 | 0 | PUSPA ENTERPRISE. | 13.91 | 0 | 0
1079 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sadik Nagar Zone-I water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000825/2022-2023 | 3605/BD | 09/12/2022 | 90 | PUSPA ENTERPRISE. | 406.99 | 295.91 | 100
1080 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-I Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002782/2021-2022 | 206/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.15 | 3.96 | 1
1081 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000139/2022-2023 | 3816/BD | 23/12/2022 | 0 | Resource Division | 17.46 | 0 | 0
1082 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000158/2023-2024 | 4404/BD | 10/11/2023 | 0 | Resource Division | 18.48 | 0 | 0
1083 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing and repairing work for 500cum capacity 20mtr. staging height R.C.C Over Head Reservoir for Augmentation of Gadpukur (Zone-I) Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000017/2024-2025 | 1536/BD | 07/06/2024 | 45 | ONKAR ENTERPRISE. | 20.09 | 0 | 100
1084 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Additional laying of UPVC pipe to connect every house hold FHTC with Augmentation work at Gadpukuria (Zone-I) W/S Scheme under Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000022/2025-2026 | 1699/BD | 23/05/2025 | 60 | THE TOWER CONSTRUCTION | 14.88 | 0 | 0
1085 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection (FHTC) for augmentation of Gadpukuria (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000048/2023-2024 | 1396/BD | 08/05/2023 | 899 | M/S DIPAK ENTERPRISE | 343.41 | 120.02 | 90
1086 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gadpukuria (Zone-I) Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001152/2023-2024 | 2926/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.12 | 0 | 100
1087 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Gadpukuria (Zone-I) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001472/2023-2024 | 4411/BD | 10/11/2023 | 60 | GHOSH CONSTRUCTION. | 19.46 | 0 | 100
1088 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Gadpukuria (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001493/2023-2024 | 4462/BD | 21/11/2023 | 23 | A.D.ENTERPRISE. | 11.48 | 0 | 100
1089 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation of 103 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Gadpukuria (Zone-I) water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001542/2023-2024 | 13/BD | 02/01/2024 | 365 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 77.74 | 0 | 100
1090 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2023-2024 | 1240/BD | 25/04/2023 | 0 | Resource Division | 13.72 | 0 | 0
1091 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gadpukuria (Zone - II) Water Supply Scheme at H/W Site & 2nd T/W Site under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001014/2023-2024 | 2831/BD | 15/09/2023 | 60 | B.M.ENGINEERING. & CONSTRUCTION. | 32.24 | 0 | 100
1092 | Barasat Division | Bangaon Sub-Division | Hiring of Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:- 01/08/2023 to 31/01/ 2024). | Assistant Engineer | Junior Engineer | ORD/001199/2023-2024 | 591/Bon | 31/07/2023 | 184 | ROY ENGINEERS. | 0.87 | 0 | 100
1093 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head work site for Augmentation of Gadpukuria (Zone-II) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001478/2023-2024 | 4410/BD | 10/11/2023 | 60 | PRABIR KUMAR MONDAL. | 15.9 | 0 | 85
1094 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Gadpukuria (Zone-II) water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001496/2023-2024 | 4486/BD | 23/11/2023 | 414 | MA CONSTRUCTION. | 9.25 | 0 | 45
1095 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis ( from 01.01.2024 to 31.03.2024) for the office use of Deputy Superintending Engineer, Planning Circle-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001624/2023-2024 | 4876/BD | 29/12/2023 | 91 | M/S B.K.ENTERPRISE. | 0.43 | 0 | 100
1096 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Withdrawing & relaying of existing UPVC distribution system along the same alignment due to widening and strengthening of Zilla Parishad road from Buzar Bagee Kalitala to Chatar Bagee inconnection with augmentation work at Godpukuria (Zone-II) W/S Scheme under Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001790/2023-2024 | 652/BD | 29/02/2024 | 30 | R.K.MANDAL & CO. | 8.92 | 0 | 100
1097 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Hiring Diesel Luxury Car on Daily basis for the office use of Deputy Superintending Engineer, Planning Circle-I, PHE Dte.(01-04-2024 to 30-06-2024). | Assistant Engineer | Junior Engineer | ORD/002056/2023-2024 | 926/BD | 15/03/2024 | 91 | M/S B.K.ENTERPRISE. | 0.43 | 0 | 100
1098 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of 5.40 mtr. X 3.60mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at Head Work site at Gadpukuria w/s scheme (Zone-II), Bagdah Block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002212/2023-2024 | 608/BD | 23/02/2024 | 45 | UPWARDS ENGINEERING PRIVATE LIMITED. | 5.57 | 0 | 100
1099 | Barasat Division | Bangaon Sub-Division | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Gadpukuria w/s scheme (Zone-II), Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002273/2023-2024 | 210/Bon | 27/02/2024 | 45 | ONKAR ENTERPRISE. | 4.35 | 0 | 100
1100 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Gadpukuria (Zone-II) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002777/2021-2022 | 129/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 1
1101 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000092/2023-2024 | 1860/BD | 23/06/2023 | 0 | Resource Division | 5.56 | 0 | 0
1102 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000109/2022-2023 | 3686/BD | 14/12/2022 | 0 | Resource Division | 76.22 | 0 | 0
1103 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Kapileswarpur water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000736/2022-2023 | 3305/BD | 10/11/2022 | 90 | KINGS & CO. | 240.31 | 149.2 | 90
1104 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Kapileswarpur Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002759/2021-2022 | 445/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 4.04 | 1
1105 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000149/2022-2023 | 3810/BD | 23/12/2022 | 0 | Resource Division | 2.38 | 0 | 0
1106 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase II) | Assistant Engineer | Junior Engineer | ORD/000564/2021-2022 | 1952/BD | 08/10/2021 | 30 | SUDHAMAY MAJUMDAR. | 58.36 | 0 | 1
1107 | Barasat Division | Basirhat Sub-Division | Hiring Diesel Luxury Car on daily basis (for 12 months from 01.07.2022 to 30.06.2023) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001344/2022-2023 | 857/BHT | 27/06/2022 | 365 | DEB KUMAR DAS. | 1.73 | 1.84 | 0
1108 | Barasat Division | Basirhat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-II Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - C) | Assistant Engineer | Junior Engineer | ORD/001488/2024-2025 | 151/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 90
1109 | Barasat Division | Basirhat Sub-Division | Continuation Order for Hiring Diesel Luxury Car on daily basis (for 4 months from 01.03.2022 to 30.06.2022) for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002654/2021-2022 | 178/BHTSD | 25/02/2022 | 120 | DEB KUMAR DAS. | 0.58 | 1.83 | 1
1110 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Pipuldaha w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 1684/BD | 07/06/2023 | 366 | GHOSH CONSTRUCTION. | 205.49 | 0 | 75
1111 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PIPULDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002731/2021-2022 | 307/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.26 | 4.26 | 1
1112 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PIPULDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002991/2021-2022 | 307/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.26 | 0 | 1
1113 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000206/2022-2023 | 888/BD | 22/03/2023 | 0 | Resource Division | 168.16 | 0 | 0
1114 | Barasat Division | Barasat Sadar Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-V under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000612/2022-2023 | 673/BSD | 31/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.61 | 1
1115 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Boundary wall at Berachampa Zone - V 1st Tubewell site at Kaukepara Mouza within Deganga Block under Barasat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001041/2024-2025 | 3702/BD | 26/12/2024 | 30 | DEBAPRASAD MONDAL. | 27.57 | 0 | 0
1116 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 550 cum capacity 20 Mtr. staging height RCC Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for augmentation of Berachampa Zone-V Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001200/2023-2024 | 4070/BD | 16/10/2023 | 687 | DEBAPRASAD MONDAL. | 567.01 | 0 | 45
1117 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tubewell by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-V Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001927/2023-2024 | 804/BD | 12/03/2024 | 30 | ACME CONSTRUCTION | 13.08 | 0 | 100
1118 | Barasat Division | Barasat Sadar Sub-Division | Construction of Pump House with latrine at Berachampa Zone-V water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002154/2023-2024 | 1245/BSD | 15/03/2024 | 31 | SANTU GHOSH. | 4.91 | 0 | 90
1119 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000044/2023-2024 | 1288/BD | 25/04/2023 | 0 | Resource Division | 48.13 | 0 | 0
1120 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000107/2023-2024 | 3089/BD | 10/10/2023 | 0 | Resource Division | 21.99 | 0 | 0
1121 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000134/2023-2024 | 4366/BD | 10/11/2023 | 0 | Resource Division | 38.51 | 0 | 0
1122 | Barasat Division | Bangaon Sub-Division | Formal work order for Construction of 200 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation and laying of Rising Main, Distribution Main with Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Paschim Huda Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (New Scheme) | Assistant Engineer | Junior Engineer | ORD/000247/2023-2024 | 2056/BD | 14/07/2023 | 627 | R.K.MANDAL & CO. | 323.01 | 130.41 | 100
1123 | Barasat Division | Bangaon Sub-Division | Survey, Design, Drawing & DPR preparation for new PWSS at Paschim Huda water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division, P.H.E.Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000850/2022-2023 | 346/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
1124 | Barasat Division | Bangaon Sub-Division | Survey, Design, Drawing & DPR preparation for new PWSS at Paschim Huda water supply scheme in the Bongaon Block under Bongaon Sub-Division, under Barasat Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000851/2022-2023 | 347/Bon | 07/07/2022 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.39 | 0.39 | 1
1125 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. new 300 mm. x 200 mm. dia. 300 mtr deep Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Paschim Huda Piped Water Supply Scheme at H/W Site under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001020/2023-2024 | 2833/BD | 15/09/2023 | 30 | NADIA TUBEWELLS | 21.56 | 0 | 100
1126 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000098/2023-2024 | 1865/BD | 23/06/2023 | 0 | Resource Division | 7.45 | 0 | 0
1127 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for construction of 5 nos. different capacity OHR, Land development, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at different Zonal Head work site including Laying Distribution System and FHTC of surface based water supply scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2023-2024 | 2714/BD | 05/09/2023 | 1095 | S & P ENTERPRISE | 5112.52 | 0 | 40
1128 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for construction of 5 nos. different capacity OHR, Land development, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at different Zonal Head work site including Laying Distribution System and FHTC of surface based water supply scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2023-2024 | 2714/BD | 05/09/2023 | 1095 | S & P ENTERPRISE | 5112.52 | 0 | 40
1129 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Construction of 2 nos. switch room cum chlorine room (Size-5.40x3.60 mtr.) for Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000028/2025-2026 | 1428/BD | 06/05/2025 | 90 | SUPER ENTERPRISE | 14.14 | 0 | 0
1130 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Biswajit Ghosh & other places in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000054/2025-2026 | 1613/BD | 19/05/2025 | 30 | ANKUSH CONSTRUCTION & CO. | 12.24 | 0 | 0
1131 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000537/2024-2025 | 2903/BD | 03/10/2024 | 60 | M/S RAJPATH CONSTRUCTION. | 51.59 | 0 | 0
1132 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-5 & 6 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000735/2023-2024 | 2489/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 51.63 | 0 | 100
1133 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Hingalganj Zone - II Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000772/2022-2023 | 636/HSD | 08/04/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.39 | 4.39 | 0
1134 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Rabiul Gazi & Enamul Gazi in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000995/2024-2025 | 3740/BD | 27/12/2024 | 30 | CHITTARANJAN MONDAL | 8.19 | 0 | 0
1135 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at N/H/O Abdul Dhali & Anar Dhali in connection with Augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000996/2024-2025 | 3499/BD | 11/12/2024 | 912 | SARKAR ENTERPRISE | 8.51 | 0 | 0
1136 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Protection wall for protection of UPVC distribution pipe line at pond of Monojit Gayen and near shop of Abdul Alim Gazi in connection with Augmentation of Hingalganj W/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000997/2024-2025 | 3500/BD | 11/12/2024 | 30 | S.K.ENTERPRISE. | 8.64 | 0 | 0
1137 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Hingalganj water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001161/2022-2023 | 700/BD | 03/03/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 313.44 | 239.91 | 40
1138 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room (3.60x3.00) with sanitary and water supply arrangement including plinth protection for Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001415/2024-2025 | 145/BD | 13/01/2025 | 75 | ABDUL HAMID GAZI. | 10.59 | 0 | 0
1139 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at different places in 4 & 8 no Sandelerbill in Sandelerbill mouza in connection with augmentation of Hingalganj w/s scheme (Z-II), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001518/2024-2025 | 381/HSD | 10/02/2025 | 10 | S.K.ENTERPRISE. | 0.96 | 0 | 100
1140 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001680/2023-2024 | 527/BD | 20/02/2024 | 406 | UTPAL CONSTRUCTION & CO. | 49.99 | 0 | 100
1141 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for inking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001684/2023-2024 | 525/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 49.99 | 0 | 100
1142 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-5 & 6 in connection with Augmentation for Hingalganj w/s (Z-II) scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001845/2023-2024 | 271/HSD | 06/03/2024 | 10 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0 | 100
1143 | Barasat Division | Habra Sub-Division | Formal work order for Construction of 1 no. 1250 Cum capacity OHR, Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zone-IX Head work site including Laying Distribution System and FHTC of Habra-Gaighata surface water based water supply scheme under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001216/2023-2024 | 4138/BD | 18/10/2023 | 1095 | S & P ENTERPRISE | 1608.93 | 0 | 20
1144 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. X 200mm.dia. 190.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long filter for Augmentation of Berachampa Zone-I Water Supply Scheme at 2nd Tube well Site under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2024-2025 | 2192/BD | 05/08/2024 | 30 | M/S K.P.PAL. | 13.3 | 0 | 100
1145 | Barasat Division | Barasat Sadar Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2022-2023 | 658/BSD | 18/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 3.86 | 1
1146 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 700cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing FHTC for Augmentation of Berachampa Zone-I water supply Scheme under Barasat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000759/2023-2024 | 2552/BD | 24/08/2023 | 1096 | MONDAL ENTERPRISE. (BARASAT) | 777.6 | 0 | 24
1147 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-II and Deganga block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000980/2024-2025 | 393/BD | 05/02/2025 | 120 | MONDAL ENTERPRISE. (BARASAT) | 167.48 | 0 | 0
1148 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Boundary Wall in Hosenpur Mouza Water Supply Scheme at Berachampa Zone - I within Deganga Block under Barasat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001043/2024-2025 | 56/BD | 07/01/2025 | 120 | JIT CONSTRUCTION | 27.29 | 0 | 40
1149 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Additional Laying of HDPE pipe line and allied work in connection with Augmentation Berachampa Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001049/2024-2025 | 54/BD | 07/01/2025 | 30 | MONDAL ENTERPRISE. (BARASAT) | 36.88 | 0 | 0
1150 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Renovation of Iron Elimination Plant at Berachampa Zone-I Water Supply Scheme within Deganga Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001154/2024-2025 | 99/BD | 09/01/2025 | 40 | JAGANNATH CONSTRUCTION. | 9.19 | 0 | 0
1151 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1 (one) no. Diesel Luxary Car on daily basis (for 01.09.2024 to 28.02.2025) for office use of the Assistant Engineer, R.W.S, Barasat Sub- Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001179/2024-2025 | 983/BST | 30/08/2024 | 181 | DEBAPRASAD MONDAL. | 0.86 | 0 | 0
1152 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-C | Assistant Engineer | Junior Engineer | ORD/001843/2023-2024 | 1119./BSD | 09/02/2024 | 4 | S.M.TRADERS. | 0.88 | 0 | 100
1153 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tube well by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-I Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001925/2023-2024 | 802/BD | 15/03/2024 | 30 | ACME CONSTRUCTION | 13.08 | 0 | 80
1154 | Barasat Division | Barasat Sadar Sub-Division | Construction of Pump House with latrine at Berachampa Zone-I water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002151/2023-2024 | 1242/BSD | 15/03/2024 | 31 | ROMI TREDERS. | 4.86 | 0 | 100
1155 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000040/2023-2024 | 1284/BD | 25/04/2023 | 0 | Resource Division | 211.19 | 0 | 0
1156 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000103/2023-2024 | 3093/BD | 10/10/2023 | 0 | Resource Division | 24.61 | 0 | 0
1157 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000130/2023-2024 | 4374/BD | 10/11/2023 | 0 | Resource Division | 9.49 | 0 | 0
1158 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000008/2023-2024 | 1151/BD | 13/04/2023 | 90 | UMWELT ENGINEER PVT.LTD. | 851.89 | 328.32 | 100
1159 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Kalitala Bazar at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2025-2026 | 930/HSD | 29/05/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.82 | 0 | 0
1160 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-I) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000216/2023-2024 | 1731/BD | 08/06/2023 | 1096 | M/S PROGATI ENTERPRISE. | 141.21 | 0 | 0
1161 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 300 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kalitala (Zone-II) water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000218/2023-2024 | 1733/BD | 08/06/2023 | 730 | M/S NIRMAN CONSTRUCTION. | 150.78 | 0 | 75
1162 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000565/2024-2025 | 1005/HSD | 29/08/2024 | 10 | ABDUL ALIM MONDAL. | 0.99 | 0 | 100
1163 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places from N/H/O Narayan Biswas to Naskar para culvert in connection with Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000567/2024-2025 | 1007/HSD | 29/08/2024 | 10 | ABDUL ALIM MONDAL. | 0.99 | 0 | 100
1164 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000726/2023-2024 | 2476/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 63.24 | 0 | 98
1165 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000728/2023-2024 | 2477/BD | 18/08/2023 | 30 | M/S PROGATI ENTERPRISE. | 63.27 | 0 | 71
1166 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kalitala water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001148/2022-2023 | 654/BD | 28/02/2023 | 90 | SUPRITI ENTERPRISE. | 610.1 | 453.86 | 60
1167 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Retrofitting work at Samsernagar river side area in connection with Augmentation of Kalitala w/s scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001309/2024-2025 | 155/HSD | 27/01/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.98 | 0 | 100
1168 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Withdrawing & relaying of 90 mm dia. UPVC pipe line near Paschim Kalitala in connection with Augmentation of Kalitala W/S Scheme, Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001310/2024-2025 | 156/HSD | 27/01/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.95 | 0 | 100
1169 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly restored UPVC distribution pipeline by Bamboo pilling at Hatkhola area in connection with augmentation of Kalitala w/s scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001311/2024-2025 | 157/HSD | 27/01/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.87 | 0 | 100
1170 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipe line in connection with retrofitting work at different places at near Laskar para at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001388/2024-2025 | 254/HSD | 30/01/2025 | 10 | ABDUL ALIM MONDAL. | 0.97 | 0 | 100
1171 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent repairing of existing FHTC in connection with retrofitting work at Duckbunglow at Kalitala mouza in connection with augmentation of Kalitala w/s scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001456/2024-2025 | 336/HSD | 06/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.96 | 0 | 100
1172 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of old rising main pipeline with UC Bullah pilling at Kamalakhali more at Kalitala mouza within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001476/2024-2025 | 349/HSD | 06/02/2025 | 10 | CHANCHAL ENTERPRISE & CO. | 0.94 | 0 | 100
1173 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001681/2023-2024 | 529/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 61.24 | 0 | 100
1174 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kalitala w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001682/2023-2024 | 528/BD | 20/02/2024 | 45 | UTPAL CONSTRUCTION & CO. | 61.24 | 0 | 100
1175 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000162/2023-2024 | 4509/BD | 28/11/2023 | 0 | Resource Division | 17.23 | 0 | 0
1176 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000254/2022-2023 | 925/BD | 22/03/2023 | 0 | Resource Division | 280.28 | 0 | 0
1177 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of UPVC distribution pipe line with restoration works near Gazikhali Sasan in connection with Augmentation of Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000035/2025-2026 | 1525/BD | 14/05/2025 | 30 | PRITAM MUKHOPADHYAY. | 10.77 | 0 | 0
1178 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000476/2024-2025 | 2735/BD | 20/09/2024 | 30 | M/S NIRMAN CONSTRUCTION. | 283.68 | 0 | 58
1179 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 & 4 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000540/2024-2025 | 2929/BD | 03/10/2024 | 80 | TITUMIR INTERNATIONAL | 51.66 | 0 | 100
1180 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Bermajur Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000770/2022-2023 | 634/HSD | 08/04/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.32 | 4.32 | 0
1181 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bermajur water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001166/2022-2023 | 701/BD | 03/03/2023 | 90 | M/S DATTA ENTERPRISE. | 242.46 | 208.82 | 38
1182 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site at PH No.-1 within Jhupkhali w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001271/2024-2025 | 355/BD | 31/01/2025 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 27.86 | 0 | 0
1183 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001668/2023-2024 | 296/BD | 30/01/2024 | 45 | M/S RAJPATH CONSTRUCTION. | 51.76 | 0 | 100
1184 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000244/2022-2023 | 914/BD | 22/03/2023 | 0 | Resource Division | 36.68 | 0 | 0
1185 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 550cum capacity 20Mtr staging Height R.C.C. Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Swetpur Zone-I Water Supply Scheme under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000563/2023-2024 | 2382/BD | 10/08/2023 | 732 | M/S BISWAS BROTHERS. | 461.4 | 0 | 55
1186 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000611/2022-2023 | 672/BSD | 30/08/2022 | 30 | RADIANT | 3.28 | 0 | 100
1187 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Boundary wall at Sohai Swetpur Zone-I within Deganga Block under Barasat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001044/2024-2025 | 3703/BD | 26/12/2024 | 30 | GIRIDHARI DAS | 12.8 | 0 | 0
1188 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001841/2023-2024 | 1117/BSD | 09/02/2024 | 4 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
1189 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Repair & Renovation work at Different site in connection with Augmentation of Sohai Swetpur, Zone-I Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002017/2024-2025 | 1026/BD | 28/03/2025 | 45 | M/S S.HAQUE & CO. | 12.75 | 0 | 100
1190 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000108/2023-2024 | 3090/BD | 10/10/2023 | 0 | Resource Division | 7.26 | 0 | 0
1191 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC within Rupmari w/s scheme (Zone-III to VI), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 940/HSD | 07/06/2022 | 15 | M/S DATTA ENTERPRISE. | 3.08 | 3.08 | 1
1192 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Withdrawing & relaying of 75 mm dia. HDPE pipe line from near Halda High School towards Kumirmari kheya Ghat for damage portion within Rupmari W/S Scheme (Z-III & IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2022-2023 | 941/HSD | 07/06/2022 | 10 | M/S PROGATI ENTERPRISE. | 4.92 | 4.92 | 1
1193 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in Rupmari & Bastali mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Rupmari W/S scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001074/2021-2022 | 95/BD | 17/01/2022 | 45 | M/S DATTA ENTERPRISE. | 96.84 | 96.43 | 1
1194 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Anchor block for resting of 100 mm dia DI Distribution main for low areas at different places within Rupmari w/s scheme, Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001644/2021-2022 | 400/HSD | 04/03/2022 | 15 | M/S PROGATI ENTERPRISE. | 3.86 | 3.86 | 1
1195 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 100 mm dia. DI distribution main from near PH No-3 towards Halda more for damage portion within Rupmari w/s scheme (Zone-III), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001646/2021-2022 | 402/HSD | 04/03/2022 | 10 | M/S PROGATI ENTERPRISE. | 1.53 | 1.53 | 1
1196 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001647/2021-2022 | 403/HSD | 04/03/2022 | 10 | M/S DATTA ENTERPRISE. | 4.93 | 4.91 | 1
1197 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001648/2021-2022 | 404/HSD | 04/03/2022 | 10 | M/S PROGATI ENTERPRISE. | 4.95 | 5 | 1
1198 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-IV to VI), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001989/2021-2022 | 253/HSD | 07/02/2022 | 10 | M/S DATTA ENTERPRISE. | 4.86 | 3.46 | 1
1199 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-I to III), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001990/2021-2022 | 256/HSD | 07/02/2022 | 10 | M/S PROGATI ENTERPRISE. | 3.46 | 3.46 | 1
1200 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000150/2022-2023 | 44/BD | 04/01/2023 | 0 | Resource Division | 61.6 | 0 | 0
1201 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000169/2022-2023 | 1153/BD | 12/04/2022 | 240 | M/S S.S.ENTERPRISE. (SOUTH) | 146.26 | 49.03 | 1
1202 | Barasat Division | Hasnabad Sub-Division | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Sehara Radhanagar mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000666/2022-2023 | 2921/BD | 26/09/2022 | 30 | TRISHA ENTERPRISE & CO. | 24 | 23.99 | 1
1203 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/001355/2022-2023 | 1153/BD. | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 143.13 | 55.22 | 95
1204 | Barasat Division | Bangaon Sub-Division | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Panchita Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000009/2022-2023 | 1209/BD | 21/04/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 393.47 | 386.33 | 0
1205 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Panchita PWSS (180 cum) and ancillary structures, Bongaon Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2024-2025 | 691/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 3.53 | 0 | 100
1206 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Connection of 1 no. newly sunk Replaced Tube well with rising main by DI pipe, additional laying of pipe line with UPVC pipe due to damage of existing pipe line and allied works for Augmentation of Panchita W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000080/2025-2026 | 1903/BD | 05/06/2025 | 120 | PRABIR KUMAR MONDAL. | 15.49 | 0 | 0
1207 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Panchita W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (PART-A). | Assistant Engineer | Junior Engineer | ORD/000083/2024-2025 | 1768/BD | 01/07/2024 | 15 | PRABIR KUMAR MONDAL. | 12.13 | 0 | 100
1208 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Panchita W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (PART-B). | Assistant Engineer | Junior Engineer | ORD/000088/2024-2025 | 1769/BD | 01/07/2024 | 284 | A.D.ENTERPRISE. | 24.28 | 0 | 100
1209 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repair and renovation works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir alongwith rising main connection with 2nd Tube well for Augmentation of Panchita Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000452/2024-2025 | 3038/BD | 22/10/2024 | 45 | DEBAPRASAD MONDAL. | 15.61 | 0 | 0
1210 | Barasat Division | Bangaon Sub-Division | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2023-2024 | 615/Bon | 08/08/2023 | 21 | PRABIR KUMAR MONDAL. | 4.15 | 4.11 | 100
1211 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000634/2023-2024 | 617/Bon | 08/08/2023 | 17 | KAMAL HALDER. | 2.94 | 0 | 100
1212 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repair & renovation of Pump House at 2nd T/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000676/2023-2024 | 604/Bon | 04/08/2023 | 21 | PRABIR KUMAR MONDAL. | 1.78 | 0 | 100
1213 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Panchita water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2022-2023 | 3591/BD | 08/12/2022 | 15 | SAHA CONSTRUCTION & CO | 15.12 | 13.73 | 0
1214 | Barasat Division | Bangaon Sub-Division | Urgently repairing and laying of badly damaged pipe line and FHTC connection due to construction of Gram Panchayat surface drain at Nakful area of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000897/2023-2024 | 625/Bon | 08/08/2023 | 15 | PRABIR KUMAR MONDAL. | 0.71 | 0 | 100
1215 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road at 2ndT/W site for Augmentation of Panchita Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000971/2023-2024 | 559/Bon | 18/07/2023 | 15 | PRABIR KUMAR MONDAL. | 0.87 | 0 | 100
1216 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Panchita Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001740/2023-2024 | 536/BD | 21/02/2024 | 45 | PRABIR KUMAR MONDAL. | 14.25 | 0 | 100
1217 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2022-2023 | 1367/BD | 13/05/2022 | 0 | Resource Division | 19.79 | 0 | 0
1218 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2022-2023 | 1672/BD | 13/06/2022 | 0 | Resource Division | 19.79 | 0 | 0
1219 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augmentation of Deara Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. Sl. No.-21 | Assistant Engineer | Junior Engineer | ORD/000314/2022-2023 | 568/BSD | 29/06/2022 | 30 | RADIANT | 2.97 | 0 | 100
1220 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction of Boundary Wall at Deara Water Supply Scheme under Barasat-II Block, under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000569/2024-2025 | 3081/BD | 29/10/2024 | 30 | M/S SANJAY ADHIKARI | 32.14 | 0 | 0
1221 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 450cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing FHTC for Augmentation of Deara water supply Scheme under Barasat Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000760/2023-2024 | 2561/BD | 24/08/2023 | 366 | SINGHA ROY & CO. | 507.92 | 0 | 25
1222 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Additional Laying of UPVC pipe line and allied work in connection with Augmentation Deara Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001048/2024-2025 | 53/BD | 07/01/2025 | 30 | SINGHA ROY & CO. | 27.35 | 0 | 0
1223 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Renovation of Iron Elimination Plant at Deara Water Supply Scheme within Barasat-II Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001156/2024-2025 | 375/BD | 04/02/2025 | 40 | TALUKDER & CO. | 9.19 | 0 | 0
1224 | Barasat Division | Barasat Sadar Sub-Division | Construction of Pump House with latrine at Deara water Supply Scheme under Barasat-II Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001383/2024-2025 | 1021/BSD | 03/01/2025 | 40 | M.ENTERPRISE. | 4.87 | 0 | 0
1225 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000036/2023-2024 | 1267/BD | 25/04/2023 | 0 | Resource Division | 99.41 | 0 | 0
1226 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000115/2023-2024 | 4020/BD | 12/10/2023 | 0 | Resource Division | 17.25 | 0 | 0
1227 | Barasat Division | Bangaon Sub-Division | Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Bongaon Sub-Division P.H.E. Dte. (Period from 01.02.2022 to 31.01.2023.) | Assistant Engineer | Junior Engineer | ORD/002673/2021-2022 | 45/Bon | 31/01/2022 | 12 | ROY ENGINEERS. | 1.73 | 0 | 1
1228 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02No. Pump House and allied works at Dhalani water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002905/2021-2022 | 595/BON | 22/12/2021 | 21 | TAPAN GHOSH. | 2.52 | 0 | 1
1229 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000053/2022-2023 | 2860/BD | 21/09/2022 | 0 | Resource Division | 3.08 | 0 | 0
1230 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000054/2022-2023 | 2865/BD | 21/09/2022 | 0 | Resource Division | 1.23 | 0 | 0
1231 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DAKSHIN BAGUNDI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001944/2021-2022 | 200/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.76 | 2.63 | 1
1232 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of different dia UPVC pipe line for damage portion at different places due widening of PWD road of Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2022-2023 | 914/HSD | 07/06/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.9 | 4.9 | 1
1233 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia. UPVC/DI pipe line at different places in Mamudpur mouza within Hingalganj W/S/Scheme(Z-I). Hingalganj Block under Hasnabad Sub -Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000237/2021-2022 | 1461/BD | 13/08/2021 | 15 | M/S K.B.ENTERPRISE. | 16.06 | 14 | 1
1234 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia. UPVC pipe line at different places in Hingalganj mouza within Hingalganj W/S/Scheme(Z-I).Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000238/2021-2022 | 1462/BD | 13/08/2021 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 14.98 | 3.49 | 1
1235 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road with cement concrete and other allied works at PH No.- 3 within Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000270/2022-2023 | 1192/HSD | 13/07/2022 | 15 | PRASANTA MITRA. | 3.44 | 3.08 | 91
1236 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House No.-3 & 4, construction of boundary wall & approach road at P.H.No.-3 & other allied works within Hingalganj w/s scheme (Old), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000297/2023-2024 | 2112/BD | 19/07/2023 | 21 | GOBINDA DAS. | 9.21 | 4.11 | 46
1237 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 90 mm dia. UPVC pipe line from Boltala Kalupara More to near Katakhali Madrasa within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000377/2022-2023 | 937/HSD | 07/06/2022 | 10 | TRISHA ENTERPRISE & CO. | 3.19 | 3.19 | 1
1238 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid 200mm dia. UPVC pipe line at N/H/O Susanta Ghosh at Hingalganj within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000378/2022-2023 | 935/HSD | 07/06/2022 | 10 | MONDAL & CO. (BASIRHAT). | 2.36 | 0 | 1
1239 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of different dia. UPVC pipe line for damage portion due to construction of concrete road at Mamudpur Purba & Paschim para within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 936/HSD | 07/06/2022 | 10 | MONDAL & CO. (BASIRHAT). | 3.37 | 3.37 | 1
1240 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration by laying of 75 mm dia. HDPE distribution pipe line from PWD road to Hingalganj Police Station, PWD road to Hingalganj BDO office & BDO office to BDO quarter for damage portion in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000394/2022-2023 | 1333/HSD | 02/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.83 | 4.83 | 1
1241 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration by laying of 90 mm dia. HDPE distribution pipe line from near Electric power house to Bankra Bazar due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2022-2023 | 1340/HSD | 02/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.81 | 1
1242 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration by laying of 160/110 mm dia. HDPE distribution pipe line from near SBI bank to Bankra Bazar due to widening & strengthening of PWD road in connection with retrofitting of Hingalganj w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2022-2023 | 1355/HSD | 03/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.74 | 4.74 | 1
1243 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing household tap connection at different places due to widening of PWD road from Boltala to Bankra Bazar in connection with retrofitting of Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000431/2022-2023 | 1357/HSD | 03/08/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.64 | 4.64 | 1
1244 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House No.-2 within Hingalganj w/s scheme (Old), Hingalgan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000474/2022-2023 | 1399/HSD | 08/08/2022 | 21 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 3.46 | 3.46 | 1
1245 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for damaged portion at PH No-2 within Hingalganj w/s scheme (Old), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000477/2022-2023 | 1402/HSD | 08/08/2022 | 21 | M/S RAJPATH CONSTRUCTION. | 3.62 | 3.61 | 1
1246 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of DI rising main from near Sahapur more to near OHR for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000757/2022-2023 | 619/HSD | 07/04/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.67 | 1
1247 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000760/2022-2023 | 622/HSD | 07/04/2022 | 15 | M/S NIRMAN CONSTRUCTION. | 2.34 | 0 | 1
1248 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new DI/UPVC pipe line within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000762/2022-2023 | 629/HSD | 08/04/2022 | 15 | MONDAL & CO. (BASIRHAT). | 2.45 | 2.45 | 1
1249 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of different dia. UPVC pipe line for damage portion due to construction of concrete road at Mamudpur Purba & Paschim para within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000887/2022-2023 | 936/HSD | 07/06/2022 | 10 | MONDAL & CO. (BASIRHAT). | 3.37 | 0 | 1
1250 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid 200mm dia. UPVC pipe line at N/H/O Susanta Ghosh at Hingalganj within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000915/2022-2023 | 935/HSD | 07/07/2022 | 10 | MONDAL & CO. (BASIRHAT). | 2.36 | 2.35 | 1
1251 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 90 mm dia. UPVC pipe line from Boltala Kalupara More to near Katakhali Madrasa within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000917/2022-2023 | 937/HSD | 07/07/2022 | 10 | TRISHA ENTERPRISE & CO. | 3.19 | 0 | 1
1252 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in Mamudpur & Hingalganj mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001087/2021-2022 | 142/BD | 18/01/2022 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 390.88 | 350.49 | 1
1253 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in Mamudpur mouza for Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001137/2021-2022 | 232/BD | 25/01/2022 | 30 | MONDAL & CO. (BASIRHAT). | 31.2 | 31.43 | 1
1254 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for for protection works for newly laid different dia. UPVC/DI pipe line at different. places in Hingalganj mouza for Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001147/2021-2022 | 235/BD | 25/01/2022 | 15 | MONDAL & CO. (BASIRHAT). | 18.36 | 18.36 | 1
1255 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-IV to VI), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001180/2021-2022 | 253/HSD | 07/02/2022 | 10 | M/S DATTA ENTERPRISE. | 3.46 | 0 | 1
1256 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-I to III), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001183/2021-2022 | 256/HSD | 07/02/2022 | 10 | M/S PROGATI ENTERPRISE. | 3.46 | 0 | 1
1257 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at OHR site & CWR site with approach road at CWR site within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001444/2021-2022 | 528/BD | 23/02/2022 | 30 | PRITAM MUKHOPADHYAY. | 19.65 | 15.84 | 1
1258 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of HDPE rising main pipe line by bamboo piling from near Krishnapada Smriti More to N/H/O Ramesh Gayen for Rejuvenation of Durgapur Baylani w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001924/2021-2022 | 527/HSD | 15/03/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.47 | 0 | 1
1259 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Land development at Head Work Site within Hingalganj w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001992/2021-2022 | 1664/HSD | 05/10/2021 | 10 | MONDAL & CO. (BASIRHAT). | 4.85 | 4.84 | 1
1260 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of different dia. DI distribution pipe line from near Bankra Bazar to near culvert for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002873/2021-2022 | 581/HSD | 28/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 3.74 | 3.67 | 1
1261 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 100/150 mm dia DI pipeline by concrete block at different places within Hingalganj w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002876/2021-2022 | 584/HSD | 28/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 3.09 | 3.06 | 1
1262 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of DI rising main from near culvert to near Sahapur more for damaged portion due to widening & strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002879/2021-2022 | 588/HSD | 28/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.85 | 4.8 | 1
1263 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent withdrawing & relaying of different dia. UPVC pipe line at Hingalganj Bazar area, Hingalganj Hospital, BDO Office, Dk. Hingalganj, Garhpara, Sahapur & other places for damaged portion within Hingalganj W/S Scheme (Z-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002883/2021-2022 | 592/HSD | 29/03/2022 | 15 | SARKAR ENTERPRISE | 4.87 | 4.87 | 1
1264 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of UPVC pipe line from Hingalganj Kalibari to Hingalganj GP office for damaged portion due to widening & strengthening of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002887/2021-2022 | 596/HSD | 31/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.18 | 4.18 | 1
1265 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of UPVC pipe line from near Hingalganj GP office to Dakshin Hingalganj at different places (SI office, Garpara, BDO office, Sahapur) for damaged portion within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002891/2021-2022 | 600/HSD | 31/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.42 | 4.42 | 1
1266 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of different dia. UPVC pipe line from near Hingalganj Kalibari to near Sahapur more for damaged portion due to widening & Strengthing of PWD road within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002893/2021-2022 | 602/HSD | 31/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.26 | 4.26 | 1
1267 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000089/2023-2024 | 1814/BD | 19/06/2023 | 0 | Resource Division | 30.8 | 0 | 0
1268 | Barasat Division | Bangaon Sub-Division | Formal Work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ICHHAPUR Water Supply Scheme at Gaighata Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001161/2021-2022 | 313/BD | 01/02/2022 | 90 | MONDAL & CO. (BASIRHAT). | 123.07 | 121.07 | 1
1269 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Ichhapur Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001349/2021-2022 | 145/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.21 | 4.19 | 1
1270 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000104/2022-2023 | 3659/BD | 13/12/2022 | 0 | Resource Division | 15.1 | 0 | 0
1271 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000070/2022-2023 | 2993/BD | 29/09/2022 | 0 | Resource Division | 0.08 | 0 | 0
1272 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Gotra Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I). | Assistant Engineer | Junior Engineer | ORD/000350/2021-2022 | 1676/BD | 08/09/2021 | 45 | M/S NIRMAN CONSTRUCTION. | 86.18 | 84.63 | 1
1273 | Barasat Division | Basirhat Sub-Division | Hiring Diesel Luxury Car on daily basis for the office use of the Assistant Engineer, Basirhat Sub-Division P.H.E. Dte. (Period 01.07.2023 to 31.12.2023 for Six Month) | Assistant Engineer | Junior Engineer | ORD/000785/2023-2024 | 604/BHTSD | 28/06/2023 | 184 | DEB KUMAR DAS. | 0.87 | 0 | 33
1274 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Talsa W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000938/2021-2022 | 559/HAB | 20/12/2021 | 10 | UMWELT ENGINEER PVT.LTD. | 3.67 | 3.7 | 1
1275 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chhaimalpur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000986/2021-2022 | 2169/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.79 | 2.79 | 1
1276 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOTRA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001940/2021-2022 | 196/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.3 | 4.16 | 1
1277 | Barasat Division | Basirhat Sub-Division | Formal Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Bara Bankra Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000573/2021-2022 | 1974/BD | 26/10/2021 | 90 | PUSPA ENTERPRISE. | 192.09 | 179.4 | 1
1278 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Gabbaria Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000993/2021-2022 | 2173/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 3.39 | 3.39 | 1
1279 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Khulna Bhandarkhali Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000998/2021-2022 | 2178/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.08 | 2.08 | 1
1280 | Barasat Division | Basirhat Sub-Division | Route Survey,design drawing & DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002495/2021-2022 | 460 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 0 | 1
1281 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for NABATKATI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002496/2021-2022 | 459 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.81 | 0 | 1
1282 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002499/2021-2022 | 456 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 0 | 1
1283 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for NALABARA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002501/2021-2022 | 455 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 0 | 1
1284 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for NALABARA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002502/2021-2022 | 454 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 0 | 1
1285 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002505/2021-2022 | 453 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0 | 1
1286 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002506/2021-2022 | 452 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.75 | 0 | 1
1287 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for PATUA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002516/2021-2022 | 444 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 0 | 1
1288 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DAKSHIN CHATRA ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002518/2021-2022 | 442 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 0 | 1
1289 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BARA BANKRA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002681/2021-2022 | 441 /BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.57 | 4.57 | 1
1290 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000055/2022-2023 | 2862/BD | 21/09/2022 | 0 | Resource Division | 36.2 | 0 | 0
1291 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Raharhati Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000345/2021-2022 | 1674/BD | 08/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 57.32 | 55.29 | 1
1292 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Hasnabad Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000966/2021-2022 | 2163/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.21 | 4.21 | 1
1293 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAHARHATI Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001969/2021-2022 | 343/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.34 | 2.97 | 1
1294 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Gokna Water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001166/2021-2022 | 315/BD | 01/02/2022 | 90 | KINGS & CO. | 220.6 | 214.18 | 1
1295 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOKNA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001988/2021-2022 | 360/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 1
1296 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for GOKNA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001991/2021-2022 | 361/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.59 | 4.53 | 1
1297 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000068/2022-2023 | 2986/BD | 29/09/2022 | 0 | Resource Division | 0.06 | 0 | 0
1298 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep as replacement Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 250mm dia 36 mtr. long housing pipe & 150mm dia 30 mtr. long filter at Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000174/2022-2023 | 1893/BD | 05/07/2022 | 30 | BABUSONA CONSTRUCTION. | 43.55 | 37.54 | 0
1299 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of 90 mm dia. UPVC pipe line at different places of Rajbari W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000759/2022-2023 | 621/HSD | 07/04/2022 | 15 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 1.52 | 1.5 | 1
1300 | Barasat Division | Hasnabad Sub-Division | Formal Work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 900 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chunchura & Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division,PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003031/2021-2022 | 767/Bd | 16/03/2022 | 12 | S. GHOSH & ASSOCIATES PVT. LTD. | 563.09 | 95.49 | 100
1301 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir & other allied work for Augmentation of Asharia Narayanpur water supply scheme, Hasnabad block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2023-2024 | 1430/BD | 11/05/2023 | 45 | B.S.ENTERPRISE. (BASIRHAT) | 27.62 | 26.62 | 100
1302 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Ashariya Narayanpur w/s scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000355/2022-2023 | 2235/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.42 | 18.62 | 1
1303 | Barasat Division | Hasnabad Sub-Division | Formal work order for for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Ashariya Narayanpur water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000517/2022-2023 | 2399/BD | 17/08/2022 | 90 | M/S DATTA ENTERPRISE. | 271.42 | 268.98 | 1
1304 | Barasat Division | Hasnabad Sub-Division | Formal work order for Repairing & renovation of existing AIRP capacity 54m3/hr for Augmentation of Ashariya Narayanpur w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001040/2024-2025 | 3713/BD | 26/12/2024 | 180 | WIST WATER SOLUTIONS PVT. LTD. | 57.54 | 0 | 0
1305 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000037/2022-2023 | 2469/BD | 24/08/2022 | 0 | Resource Division | 15.08 | 0 | 0
1306 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 of Gaighata water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000047/2023-2024 | 1408/BD | 08/05/2023 | 30 | NADIA TUBEWELLS | 28.98 | 25.15 | 100
1307 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary Wall (110 m Length) for Pump House No - 1 of Gaighata water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 2283/BD | 13/08/2024 | 160 | PUSPA CONSTRUCTION. | 16.34 | 0 | 0
1308 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary Wall (70 m Length) for Pump House No - 2 of Gaighata water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000341/2024-2025 | 2285/BD | 13/08/2024 | 20 | VAI ENTERPRISE. | 11.03 | 0 | 100
1309 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of at Gaighata Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000559/2022-2023 | 2533/BD | 29/08/2022 | 990 | SUPRITI ENTERPRISE. | 482.07 | 335.91 | 90
1310 | Barasat Division | Bangaon Sub-Division | Construction of Service Road 45 Mtr. Length X 2 Mtr. Width for Pump House No 1 of Gaighata Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000604/2024-2025 | 917/HAB | 30/10/2024 | 10 | M/S DAS & CO. | 2.75 | 0 | 0
1311 | Barasat Division | Bangaon Sub-Division | Construction of Service Road 17 Mtr. Length X 2 Mtr. Width for Pump House No 2 of Gaighata Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000605/2024-2025 | 919/HAB | 30/10/2024 | 10 | DEBANJAN GHOSH. | 1.04 | 0 | 0
1312 | Barasat Division | Bangaon Sub-Division | Special repair and renovation of pump house and other Allied Works for Pump House No - 1 of Gaighata WS scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2024-2025 | 921/HAB | 30/10/2024 | 20 | DEBASISH SARKAR. | 2.65 | 0 | 0
1313 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 3 for Augmentation of Gaighata water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000903/2023-2024 | 2778/BD | 11/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 14.47 | 0 | 100
1314 | Barasat Division | Bangaon Sub-Division | Repairing & renovation of Pump House No. - 1 & 2 of Gaighata W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002978/2021-2022 | 494/HAB | 02/12/2021 | 30 | M/S SANKAR ENTERPRISE. | 2.95 | 2.9 | 1
1315 | Barasat Division | Bangaon Sub-Division | Repairing & renovation of Pump House No. ¿ 3 of Gaighata W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002982/2021-2022 | 511/HAB | 10/12/2021 | 30 | M/S SANKAR ENTERPRISE. | 1.47 | 1.45 | 1
1316 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000054/2023-2024 | 1555/BD | 23/05/2023 | 0 | Resource Division | 7.44 | 0 | 0
1317 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000079/2022-2023 | 3106/BD | 18/10/2022 | 0 | Resource Division | 14.06 | 0 | 0
1318 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000125/2022-2023 | 3796/BD | 22/12/2022 | 0 | Resource Division | 177.61 | 0 | 0
1319 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation) | Assistant Engineer | Junior Engineer | ORD/000004/2022-2023 | 1004/BD | 04/04/2022 | 90 | M/S DIPAK ENTERPRISE | 298.46 | 282.74 | 1
1320 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household of Chanda, Gangrapota, Gobrapur and Kamalapur mouzas including laying of UPVC pipe with pile work under Augmentation work at Gangrapota W/S Scheme Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000020/2025-2026 | 1387/BD | 30/04/2025 | 90 | ONKAR ENTERPRISE. | 76.95 | 0 | 0
1321 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Gangrapota water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000827/2022-2023 | 3621/BD | 12/12/2022 | 15 | DHELA BABA ENTERPRISE | 15.12 | 13.34 | 0
1322 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road at 2nd Pump House site for Augmentation of Gangrapota Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000967/2023-2024 | 555/Bon | 18/07/2023 | 15 | M/S SAYAN ENTERPRISE. | 0.8 | 0 | 100
1323 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 2928/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 0 | 100
1324 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Gangrapota Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001759/2023-2024 | 519/BD | 20/02/2024 | 30 | S.D. CONSTRUCTION. | 15.09 | 0 | 100
1325 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002958/2021-2022 | 536/BON | 03/11/2021 | 21 | GHOSH CONSTRUCTION. | 2.52 | 2.48 | 1
1326 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 01No. Pump House (PH-III) and allied works at Gangrapota water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002968/2021-2022 | 635/ BON | 31/12/2021 | 15 | GHOSH CONSTRUCTION. | 1.26 | 1.15 | 1
1327 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2022-2023 | 1369/BD | 13/05/2022 | 0 | Resource Division | 26.76 | 0 | 0
1328 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2022-2023 | 1675/BD | 13/06/2022 | 0 | Resource Division | 76.64 | 0 | 0
1329 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Special Repairing work in connection with augmentation work at total command area of Chikanpara Water Supply Scheme, to repair the damaged pipeline due to road widening and drain construction, to extend the Backwash line and also to convert the mouzas into Swajal Gram within Bongaon Sub Division, under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000074/2025-2026 | 1904/BD | 05/06/2025 | 120 | MA CONSTRUCTION. | 13.57 | 0 | 0
1330 | Barasat Division | Bangaon Sub-Division | Repairing and renovation of 150 Cum C.W.R. for Augmentation of Chikanpara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000399/2025-2026 | 816/Bon | 26/06/2025 | 45 | MA CONSTRUCTION. | 1.8 | 0 | 0
1331 | Barasat Division | Bangaon Sub-Division | Construction of Latrine at Head Work site and Renovation of P/H No-1 for Chikanpara Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000566/2025-2026 | 638/Bon | 21/05/2025 | 45 | MA CONSTRUCTION. | 4.31 | 0 | 0
1332 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chikanpara Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000864/2022-2023 | 3762/BD | 20/12/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 481.61 | 397.68 | 100
1333 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chikanpara water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001167/2023-2024 | 2686/BD | 04/09/2023 | 420 | JOY HIND TUBEWELLS. | 16.16 | 0 | 100
1334 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chikanpara water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001168/2023-2024 | 2690/BD | 04/09/2023 | 510 | JOY HIND TUBEWELLS. | 16.16 | 0 | 100
1335 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation & repairing of Boundary wall at Head work site for Augmentation of Chikanpara water Supply scheme, Gaighata Block within jurisdiction of Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001480/2023-2024 | 4413/BD | 10/11/2023 | 60 | VAI ENTERPRISE. | 10.85 | 0 | 100
1336 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at 3rd Tube Well site and Construction of Approach Road at 3rd Tube Well site and Head work site under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001559/2023-2024 | 40/BD | 04/01/2024 | 23 | M/S.RAJESH CONTRUCTION | 8.42 | 0 | 100
1337 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001565/2023-2024 | 54/BD | 05/01/2024 | 30 | MONDAL & CO.(BON) | 6.02 | 0 | 100
1338 | Barasat Division | Bangaon Sub-Division | Renovation and repairing of Boundary wall and Construction of Approach Road at 2nd Tube Well site under Augmentation of Chikanpara Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002349/2023-2024 | 977/Bon | 27/12/2023 | 30 | M/S SAYAN ENTERPRISE. | 4.84 | 0 | 0
1339 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02No. Pump House and allied works at Chikonpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002934/2021-2022 | 586/BON | 15/12/2021 | 21 | MA CONSTRUCTION. | 2.52 | 2.34 | 1
1340 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Chikonpara water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002935/2021-2022 | 632/BON | 31/12/2021 | 21 | MA CONSTRUCTION. | 1.26 | 1.19 | 1
1341 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2022-2023 | 1368/BD | 13/05/2022 | 0 | Resource Division | 46.36 | 0 | 0
1342 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 of Bira Rajibpur water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000045/2023-2024 | 1410/BD | 08/05/2023 | 30 | M/S K.P.PAL. | 39.12 | 0 | 100
1343 | Barasat Division | Habra Sub-Division | Continuation work order Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.09.24 to 28.02.25) = six months | Assistant Engineer | Junior Engineer | ORD/000400/2024-2025 | 780/HAB | 28/08/2024 | 184 | M/S SUKANTA ENTERPRISE. | 0.86 | 0 | 100
1344 | Barasat Division | Habra Sub-Division | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Bira Rajibpur Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000533/2022-2023 | 2447/BD | 23/08/2022 | 1251 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 619.57 | 197.69 | 75
1345 | Barasat Division | Habra Sub-Division | Continuation work order for Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from : 01.12.24 to 31.05.25) | Assistant Engineer | Junior Engineer | ORD/000985/2024-2025 | 993/HAB | 29/11/2024 | 182 | M/S LATIKA CONSTRUCTION. | 0.86 | 0 | 0
1346 | Barasat Division | Habra Sub-Division | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-01-2023 to 30-06-2023). | Assistant Engineer | Junior Engineer | ORD/000995/2022-2023 | 3867/BD | 30/12/2022 | 181 | DIPANKAR NASKAR. | 0.86 | 1.85 | 1
1347 | Barasat Division | Habra Sub-Division | Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from: 01.12.2023 to 30.11.24) | Assistant Engineer | Junior Engineer | ORD/001630/2023-2024 | 720/HAB | 23/11/2023 | 366 | M/S LATIKA CONSTRUCTION. | 1.74 | 0 | 60
1348 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. - 1 & 2 of BiraRajibpur W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002974/2021-2022 | 499/HAB | 02/12/2021 | 30 | B.M.ENTERPRISE. | 2.15 | 2.1 | 1
1349 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000044/2022-2023 | 2518/BD | 25/08/2022 | 0 | Resource Division | 21.54 | 0 | 0
1350 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000053/2023-2024 | 1554/BD | 23/05/2023 | 0 | Resource Division | 13.55 | 0 | 0
1351 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000130/2022-2023 | 3793/BD | 22/12/2022 | 0 | Resource Division | 272.77 | 0 | 0
1352 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Rajnagar water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000814/2022-2023 | 3587/BD | 08/12/2022 | 30 | B.S.ENTERPRISE. (BASIRHAT) | 62.54 | 62.4 | 100
1353 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002780/2021-2022 | 208/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.72 | 2.63 | 1
1354 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000169/2022-2023 | 485/BD | 17/02/2023 | 0 | Resource Division | 0.44 | 0 | 0
1355 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Bajitpur Zone-II water supply scheme (Zone-II), in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2023-2024 | 1190/BD | 19/04/2023 | 738 | DIVINE | 330.08 | 251.84 | 50
1356 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2023-2024 | 1236/BD | 25/04/2023 | 0 | Resource Division | 4.59 | 0 | 0
1357 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000061/2023-2024 | 1633/BD | 01/06/2023 | 0 | Resource Division | 10.1 | 0 | 0
1358 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000071/2023-2024 | 1646/BD | 02/06/2023 | 0 | Resource Division | 13.76 | 0 | 0
1359 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Special repair and renovation of existing structures like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Itinda Panitor, Joypur Gopmahal, Kachua Swarupnagar, Mathurapur, Mirzanagar, Nalkora, Paikardanga, Pifa and Gobindapur Water Supply Scheme of different block under Basirhat Sub-Division within Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2025-2026 | 2474/BD | 17/07/2025 | 150 | SAHA CONSTRUCTION & CO | 91.3 | 0 | 0
1360 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 2 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Mirjanagar Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000771/2024-2025 | 3259/BD | 25/11/2024 | 137 | ANJALI ENTERPRISE. | 21.75 | 0 | 100
1361 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Mirjanagar water supply scheme in Basirhat-II block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2022-2023 | 3476/BD | 01/12/2022 | 90 | SUPER SKILL. | 288.66 | 187.65 | 90
1362 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat II Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001010/2024-2025 | 3554/BD | 16/12/2024 | 30 | M/S MAA TARA ENTERPRISE | 29.52 | 0 | 0
1363 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000185/2022-2023 | 606/BD | 23/02/2023 | 0 | Resource Division | 10.48 | 0 | 0
1364 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000200/2022-2023 | 856/BD | 20/03/2023 | 0 | Resource Division | 23.33 | 0 | 0
1365 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 300 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Shibalaya water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000148/2023-2024 | 1713/BD | 08/06/2023 | 731 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 364.71 | 0 | 80
1366 | Barasat Division | Barasat Sadar Sub-Division | Arrangement of Block Level Orientation Programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks (Barasat-I & II) in North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000246/2024-2025 | 171/BSD | 10/06/2024 | 7 | IMAGIN | 0.98 | 0 | 100
1367 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Shibalaya PWSS (1st Tubewell site - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000459/2024-2025 | 578/BSD | 10/09/2024 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.2 | 0 | 100
1368 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Shibalaya PWSS (1st Tubewell site - Pump House). | Assistant Engineer | Junior Engineer | ORD/000460/2024-2025 | 579/BSD | 10/09/2024 | 20 | RANA ENTERPRISE | 2.66 | 0 | 100
1369 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Shibalaya PWSS (2nd Tubewell site - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000461/2024-2025 | 580/BSD | 10/09/2024 | 20 | B. S. ENTERPRISE (BANAMALIPUR) | 2.77 | 0 | 100
1370 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Shibalaya PWSS (2nd Tubewell site - Pump House). | Assistant Engineer | Junior Engineer | ORD/000463/2024-2025 | 581/BSD | 10/09/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.65 | 0 | 100
1371 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Shibalaya Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000608/2022-2023 | 667/BSD | 25/08/2022 | 30 | RADIANT | 3.07 | 0 | 100
1372 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000037/2023-2024 | 1283/BD | 25/04/2023 | 0 | Resource Division | 36.84 | 0 | 0
1373 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2023-2024 | 1672/BD | 06/06/2023 | 0 | Resource Division | 15.2 | 0 | 0
1374 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Nabatkati Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2022-2023 | 1135/BD | 12/04/2022 | 90 | UTPAL CONSTRUCTION & CO. | 184.62 | 36.58 | 12
1375 | Barasat Division | Basirhat Sub-Division | Relaying of 75mm dia UPVC pipe line and repairing of FHTC connections due to damaged during construction of road by WBSRDA at Node no. 100 to 175 of Nabatkati water Supply Scheme under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000445/2024-2025 | 1169/BHTSD | 30/07/2024 | 15 | M/S. WAY CON. | 0.88 | 0 | 50
1376 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nabatkati water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001140/2022-2023 | 513/BD | 20/02/2023 | 824 | UTPAL CONSTRUCTION & CO. | 285.35 | 164.85 | 60
1377 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Nabatkati Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002753/2021-2022 | 459/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.81 | 3.81 | 1
1378 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000202/2022-2023 | 858/BD | 20/03/2023 | 0 | Resource Division | 0.84 | 0 | 0
1379 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-3 in connection within Mallickgheri water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2025-2026 | 942/HSD | 29/05/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0
1380 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Mallickgheri water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2025-2026 | 998/HSD | 04/06/2025 | 10 | M/S DATTA ENTERPRISE. | 0.72 | 0 | 0
1381 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Mallick Gheri W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000765/2023-2024 | 2579/BD | 25/08/2023 | 1096 | M/S DATTA ENTERPRISE. | 500.78 | 194.21 | 75
1382 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MALLIKGHERI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002724/2021-2022 | 289/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.81 | 2.81 | 0
1383 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MALLIKGHERI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002727/2021-2022 | 288/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 0
1384 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000216/2022-2023 | 894/BD | 22/03/2023 | 0 | Resource Division | 33.53 | 0 | 0
1385 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03461/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 76.53 | 0 | 0
1386 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-II water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000030/2023-2024 | 1301/BD | 26/04/2023 | 855 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 766.02 | 0 | 29
1387 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-I B water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000128/2023-2024 | 1694/BD | 08/06/2023 | 683 | SUPRITI ENTERPRISE. | 581.97 | 0 | 20
1388 | Barasat Division | Basirhat Sub-Division | Hiring Diesel Luxury Car on daily basis for the supervision of work and office uses under Basirhat Sub-Division P.H.E. Dte. (Period: 01.07.2024 to 31.12.2024), Sl.No. - 02 | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 1018/BHTSD | 28/06/2024 | 184 | DEB KUMAR DAS. | 0.87 | 0 | 0
1389 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gokna Zone-I A water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2023-2024 | 1726/BD | 08/06/2023 | 90 | SUJIT KUMAR SAHA | 224.48 | 0 | 10
1390 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Baduria Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001008/2024-2025 | 3553/BD | 16/12/2024 | 390 | PRITAM MUKHOPADHYAY. | 60.15 | 0 | 0
1391 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000025/2023-2024 | 1248/BD | 25/04/2023 | 0 | Resource Division | 520.48 | 0 | 0
1392 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000138/2023-2024 | 4424/BD | 10/11/2023 | 0 | Resource Division | 47.88 | 0 | 0
1393 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Niruli w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000099/2023-2024 | 1544/BD | 22/05/2023 | 863 | DEBAPRASAD MONDAL. | 348.43 | 120.26 | 85
1394 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (NIRULI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002723/2021-2022 | 290/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
1395 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (NIRULI Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002728/2021-2022 | 291/HSD | 10/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.05 | 1.05 | 1
1396 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000214/2022-2023 | 882/BD | 22/03/2023 | 0 | Resource Division | 18.22 | 0 | 0
1397 | Barasat Division | Barasat Sadar Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-III under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000609/2022-2023 | 668/BSD | 25/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.73 | 3.73 | 1
1398 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 3 nos 300mm. X 200mm.dia. 200.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long UPVC Medium Well Screen (RMS) Pipes with Ribs at Berachampa Zone-II( H/W site & 2nd T/W site) & Berachampa Zone-III( 2nd T/W site) Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001503/2024-2025 | 646/BD | 28/02/2025 | 60 | JOY GURU ENTERPRISE | 42.76 | 0 | 0
1399 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-E | Assistant Engineer | Junior Engineer | ORD/001847/2023-2024 | 1120/BSD | 09/02/2024 | 4 | S.M.TRADERS. | 0.87 | 0 | 100
1400 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 185 mtr deep Tube well by D.R. Rig method having 300 mm dia 42.0 mtr. long PVC housing pipe & 200 mm dia 30.0 mtr. long filter for Augmentation Berachampa Zone-III Water Supply Scheme (Head Work Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001926/2023-2024 | 803/BD | 12/03/2024 | 30 | ACME CONSTRUCTION | 13.08 | 0 | 100
1401 | Barasat Division | Barasat Sadar Sub-Division | Construction of Pump House with latrine at Berachampa Zone-III water Supply Scheme under Deganga Block size of 5.40m x 3.60m within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002152/2023-2024 | 1243/BSD | 15/03/2024 | 277 | D.K.CONSTRUCTION | 4.91 | 0 | 80
1402 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2023-2024 | 1270/BD | 25/04/2023 | 0 | Resource Division | 37.17 | 0 | 0
1403 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000105/2023-2024 | 3088/BD | 10/10/2023 | 0 | Resource Division | 17.77 | 0 | 0
1404 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000132/2023-2024 | 4370/BD | 10/11/2023 | 0 | Resource Division | 90.94 | 0 | 0
1405 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Uchildaha W/S Scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000766/2023-2024 | 2581/BD | 25/08/2023 | 366 | MONDAL & CO. (BASIRHAT). | 488.99 | 200.61 | 75
1406 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Atpukur (Z-I) and Uchildaha w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001497/2024-2025 | 633/BD | 28/02/2025 | 45 | SHIBU BISWAS. | 51.76 | 0 | 0
1407 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (UCHILDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002736/2021-2022 | 312/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
1408 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (UCHILDAHA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002737/2021-2022 | 313/HSD | 15/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.89 | 3.89 | 0
1409 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000222/2022-2023 | 877/BD | 22/03/2023 | 0 | Resource Division | 30.59 | 0 | 0
1410 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution System, Providing FHTC, Construction of Office cum Guard room, Land development and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XX) i.e. Matikumra / (Zone-XXII) i.e. Chikanpara under Habra-Gaighata surface based PWSS, of Gaighata Block under Barasat Division, P.H.E. Dte. GAIGHATA BLOCK, PART-B / Gaighata Block, PART-D | Assistant Engineer | Junior Engineer | ORD/001214/2023-2024 | 4073/BD | 16/10/2023 | 730 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2790.09 | 0 | 88
1411 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area & Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works at Head work site of Zone-I within Amdanga Block of surface based Water Supply Scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001177/2023-2024 | 3007/BD | 05/10/2023 | 90 | KINGS & CO. | 894.25 | 0 | 0
1412 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000117/2023-2024 | 4024/BD | 12/10/2023 | 0 | Resource Division | 123.26 | 0 | 0
1413 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing FHTC (Functional Household Tap Connection) by Augmentation for Rajapur Water Supply Scheme in Baduria Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000237/2023-2024 | 1735/BD | 08/06/2023 | 838 | DEBAPRASAD MONDAL. | 353.44 | 98.19 | 50
1414 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAJAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001984/2021-2022 | 356/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.16 | 4.13 | 0
1415 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2023-2024 | 1279/BD | 25/04/2023 | 0 | Resource Division | 66.17 | 0 | 0
1416 | Barasat Division | Habra Sub-Division | Enhancement of GST for the work providing FHTC for augmentation of Bergum water supply scheme | Assistant Engineer | Junior Engineer | BILL/00272/2024-2025 | BP-2024-25-54 | 19/06/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 33.93 | 0 | 0
1417 | Barasat Division | Habra Sub-Division | Construction of Service Road (20 Mtr. Length & 2 Mtr. Width) for Pump House No:3 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000358/2024-2025 | 702/HAB | 30/07/2024 | 15 | ANJALI CONSTRUCTION. | 1.11 | 0 | 0
1418 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Bergum Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 2534/BD | 29/08/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 654.34 | 638.03 | 1
1419 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of the Boundary wall in Pump House No. 3 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000701/2024-2025 | 3159/BD | 14/11/2024 | 45 | AREOCON. | 8.62 | 0 | 0
1420 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 of Bergum water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001535/2023-2024 | 06/BD | 02/01/2024 | 30 | M/S B.K.ENTERPRISE. | 19.45 | 0 | 100
1421 | Barasat Division | Habra Sub-Division | Construction of Service Road (10 Mtr. Length & 2 Mtr. Width) for Pump House No:1 of Bergum Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001885/2023-2024 | 132/HAB | 05/02/2024 | 15 | DEBASISH SARKAR. | 0.75 | 0 | 100
1422 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. ? 1 & 2 of Bergum W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002980/2021-2022 | 502/HAB | 03/12/2021 | 30 | AREOCON. | 2.07 | 2.06 | 1
1423 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000081/2022-2023 | 3109/BD | 18/10/2022 | 0 | Resource Division | 17.8 | 0 | 0
1424 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000127/2022-2023 | 3789/BD | 22/12/2022 | 0 | Resource Division | 26.74 | 0 | 0
1425 | Barasat Division | Basirhat Sub-Division | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Sadiknagar Zone-II Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2022-2023 | 3474/BD | 01/12/2022 | 90 | TIRUPATI ENTERPRISES | 214.95 | 109.83 | 80
1426 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Sadiknagar zone - II W/S Scheme at Basirhat - II Block under Basirhat Sub Division, PHE Dte. Capacity - 56.25 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002025/2023-2024 | 919/BD | 15/03/2024 | 60 | MONDAL PRECISION PVT.LTD | 29.4 | 0 | 100
1427 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000028/2022-2023 | 2305/BD | 03/08/2022 | 0 | Resource Division | 4.84 | 0 | 0
1428 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000166/2022-2023 | 484/BD | 17/02/2023 | 0 | Resource Division | 4.43 | 0 | 0
1429 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2023-2024 | 1204/BD | 20/04/2023 | 30 | M/S DATTA ENTERPRISE. | 42.94 | 37.37 | 100
1430 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000021/2023-2024 | 1207/BD | 20/04/2023 | 30 | M/S PROGATI ENTERPRISE. | 42.94 | 36.11 | 0
1431 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Rupmari water supply scheme (Zone - I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000243/2023-2024 | 2031/BD | 13/07/2023 | 739 | SARKAR ENTERPRISE & CO. | 114.21 | 0 | 100
1432 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Rupmari water supply scheme (Zone - II), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000244/2023-2024 | 2032/BD | 13/07/2023 | 626 | DEBAPRASAD MONDAL. | 114.2 | 0 | 85
1433 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no-5 in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000260/2023-2024 | 786/HSD | 13/07/2023 | 10 | SARKAR ENTERPRISE | 0.88 | 0.88 | 100
1434 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at Pump House No-1, 2 & 5 for damaged portion and repairing of existing boundary wall within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000283/2023-2024 | 822/HSD | 14/07/2023 | 15 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.38 | 0 | 0
1435 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at Pump House No-1, 2 & 5 for damaged portion and repairing of existing boundary wall within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000284/2023-2024 | 822/HSD | 14/07/2023 | 15 | ANKUSH CONSTRUCTION & CO. | 4.38 | 4.37 | 100
1436 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000310/2024-2025 | 881/HSD | 07/08/2024 | 10 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.93 | 0 | 100
1437 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection works for protection of UPVC distribution pipe line at different places and other allied works in connection with Augmentation of Rupmari w/s scheme (Z-I & II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000415/2024-2025 | 2866/BD | 30/09/2024 | 120 | UTPAL CONSTRUCTION & CO. | 132.55 | 0 | 100
1438 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Rupamari w/s scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000542/2024-2025 | 2974/BD | 04/10/2024 | 60 | TALUKDER & CO. | 13.56 | 0 | 0
1439 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of Office cum Godown with sanitary & water supply arrangement i/c plinth protection at OHR site (Size-5.40x3.60 mtr.) for Augmentation of Rupamari w/s scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2024-2025 | 3023/BD | 22/10/2024 | 360 | LAHIRI CONSTRUCTION. | 13.58 | 0 | 50
1440 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000730/2023-2024 | 2479/BD | 18/08/2023 | 30 | ABDUL ALIM MONDAL. | 25.81 | 0 | 77
1441 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Pump connection at PH No-5 & other allied works for Augmentation of Rupmari w/s scheme, Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2022-2023 | 616/HSD | 07/04/2022 | 15 | GOBINDA DAS. | 1.97 | 1.97 | 1
1442 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Rupmari water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001068/2022-2023 | 403/BD | 09/02/2023 | 90 | M/S DATTA ENTERPRISE. | 348.91 | 292.16 | 85
1443 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rupmari (Zone-II water supply scheme, Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001120/2022-2023 | 405/BD | 09/02/2023 | 90 | M/S NIRMAN CONSTRUCTION. | 345.89 | 289.76 | 1
1444 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001832/2023-2024 | 261/HSD | 06/03/2024 | 10 | M/S NIRMAN CONSTRUCTION. | 0.93 | 0 | 100
1445 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001833/2023-2024 | 262/HSD | 06/03/2024 | 10 | M/S DATTA ENTERPRISE. | 0.93 | 0 | 85
1446 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 100 mm dia DI pipeline at different places in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001834/2023-2024 | 264/HSD | 06/03/2024 | 10 | M/S DATTA ENTERPRISE. | 0.93 | 0 | 85
1447 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connection with Augmentation of Rupmari w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001850/2023-2024 | 275/HSD | 06/03/2024 | 10 | SARKAR ENTERPRISE & CO. | 0.83 | 0 | 79
1448 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of RUPMARI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002687/2021-2022 | 228/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.81 | 4.81 | 1
1449 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Augmentation of RUPMARI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002700/2021-2022 | 229/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.04 | 1.04 | 1
1450 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000175/2022-2023 | 519/BD | 20/02/2023 | 0 | Resource Division | 145.86 | 0 | 0
1451 | Barasat Division | Barasat Sadar Sub-Division | Arrangement of Block Level Orientation Programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks (Amdanga & Deganga) in North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000247/2024-2025 | 172/BSD | 10/06/2024 | 7 | IMAGIN | 0.98 | 0 | 100
1452 | Barasat Division | Barasat Sadar Sub-Division | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Berachampa Water Supply Scheme Zone-II under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000606/2022-2023 | 659/BSD | 18/08/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.58 | 1
1453 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Renovation of Iron Elimination Plant at Berachampa Zone-II Water Supply Scheme within Deganga Block under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001155/2024-2025 | 615/BD | 27/02/2025 | 40 | ANJALI ENTERPRISE. | 9.21 | 0 | 0
1454 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 3 nos 300mm. X 200mm.dia. 200.00mtr. deep tube well by direct rotary rig method, having 300mm.dia. 42.0mtr. long PVC housing pipe & 200mm.dia. 30.0mtr. long UPVC Medium Well Screen (RMS) Pipes with Ribs at Berachampa Zone-II( H/W site & 2nd T/W site) & Berachampa Zone-III( 2nd T/W site) Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001503/2024-2025 | 646/BD | 28/02/2025 | 60 | JOY GURU ENTERPRISE | 42.76 | 0 | 0
1455 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Deganga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-D | Assistant Engineer | Junior Engineer | ORD/001844/2023-2024 | 1119/1/BSD | 09/02/2024 | 4 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
1456 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (P.H. No-IV) and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002945/2021-2022 | 832/BSD | 16/12/2021 | 30 | ROMI TREDERS. | 1.25 | 1.18 | 1
1457 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 02 Nos. Pump House (P.H. No.-II & III) and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002953/2021-2022 | 831/BSD | 16/12/2021 | 30 | KABASI ENTERPRISE. | 2.51 | 2.39 | 1
1458 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Berachampa Water Supply Scheme Zone-II under Barasat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002954/2021-2022 | 830/BSD | 16/12/2021 | 30 | P.ENTERPRISE. | 1.85 | 1.75 | 1
1459 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2023-2024 | 1269/BD | 25/04/2023 | 0 | Resource Division | 32.07 | 0 | 0
1460 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000104/2023-2024 | 3087/BD | 10/10/2023 | 0 | Resource Division | 18.46 | 0 | 0
1461 | Barasat Division | Bangaon Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gadpukuria Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/003014/2021-2022 | 1356/BD. | 03/08/2021 | 90 | ORIENT CONSTRUCTION. | 131.31 | 0 | 1
1462 | Barasat Division | Bangaon Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gadpukuria Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-II). | Assistant Engineer | Junior Engineer | ORD/001732/2020-2021 | 423/BD. | 19/02/2021 | 45 | M/S S.S.ENTERPRISE. (SOUTH) | 84.66 | 49.4 | 1
1463 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Gadpukuria water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002925/2021-2022 | 531/Bon | 03/11/2021 | 21 | MA CONSTRUCTION. | 2.52 | 2.49 | 1
1464 | Barasat Division | Bangaon Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/002294/2020-2021 | 79/BD. | 18/01/2021 | 60 | ORIENT CONSTRUCTION. | 57.85 | 0 | 0
1465 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000052/2022-2023 | 2866/BD | 21/09/2022 | 0 | Resource Division | 2.83 | 0 | 0
1466 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2022-2023 | 1152/BD | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 97.05 | 30.31 | 1
1467 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000664/2022-2023 | 1152/ BD | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 97.05 | 18.73 | 0
1468 | Barasat Division | Hasnabad Sub-Division | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Rajbari mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000668/2022-2023 | 2923/BD | 26/09/2022 | 30 | ABDUL HAMID GAZI. | 11.33 | 11.32 | 1
1469 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (PH No-1) within Chunchura & Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001303/2023-2024 | 4376/BD | 10/11/2023 | 90 | MONDAL & CO. (BASIRHAT). | 23.88 | 0 | 0
1470 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) from existing distribution system at Talsa & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte.( For balance work of Retrofitting). | Assistant Engineer | Junior Engineer | ORD/000838/2022-2023 | 3583/ BD | 08/12/2022 | 30 | TRISHA ENTERPRISE & CO. | 42.66 | 42.65 | 1
1471 | Barasat Division | Habra Sub-Division | Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Talsa & Adjoining Mouzas Water Supply Scheme at Habra-II Block under Barasat Division, PHE Dte. (Phase-II). | Assistant Engineer | Junior Engineer | ORD/001841/2020-2021 | 388/BD. | 18/02/2021 | 90 | PUSPA ENTERPRISE. | 84.95 | 20.23 | 1
1472 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at Humaipur OHR site under Humipur Water Supply Scheme within Barasat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000043/2025-2026 | 1724/BD | 27/05/2025 | 120 | MONDAL ENTERPRISE. (BARASAT) | 31.87 | 0 | 0
1473 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Banspol, Dariala & Birpur mouzas within Humaipur Water Supply Scheme at Barasat-II Block under Barasat Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2022-2023 | 2626/BD | 05/09/2022 | 30 | M/S K.B.ENTERPRISE. | 43.06 | 38.98 | 1
1474 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Repair & Renovation work at Head work site in connection with Augmentation of Humaipur Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002061/2024-2025 | 1033/BD | 28/03/2025 | 45 | MUKHERJEE CONSTRUCTION (NADIA) | 19.71 | 0 | 0
1475 | Barasat Division | Bangaon Sub-Division | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-07-2022 to 30-09-2022) for the Office of the Assistant Engineer (HQ), Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000221/2022-2023 | 1863/BD | 30/06/2022 | 92 | M/S SAMIT CHANDRA DEY. | 0.44 | 0.71 | 1
1476 | Barasat Division | Bangaon Sub-Division | Renovation and repairing of Boundary wall at 2nd T/W site for Augmentation of Sindrani (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000570/2023-2024 | 616/Bon | 08/08/2023 | 21 | VAI ENTERPRISE. | 1.86 | 0 | 100
1477 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Sindrani (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000635/2023-2024 | 618/Bon | 08/08/2023 | 25 | ROY ENGINEERS. | 4.51 | 4.51 | 100
1478 | Barasat Division | Bangaon Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Sindrani (Zone-I) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000751/2021-2022 | 2387/BD | 09/12/2021 | 45 | DEBAPRASAD MONDAL. | 73.93 | 73.41 | 1
1479 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Sahebkhali (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000952/2021-2022 | 2146/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 1
1480 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road at 2ndT/W site for Augmentation of Sindrani (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000972/2023-2024 | 562/Bon | 18/07/2023 | 15 | ONKAR ENTERPRISE. | 0.89 | 0 | 0
1481 | Barasat Division | Bangaon Sub-Division | Laying of distribution pipe line for smoothly water supply all over back site villagers and other allied works at Koniara water supply scheme under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2022-2023 | 404/Bon | 23/08/2022 | 15 | ROY CHOWDHURY CONSTRUCTION. | 3.49 | 3.47 | 1
1482 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for additional Survey Work For DPR Preparation of Sahebkhali (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000953/2021-2022 | 2147/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.84 | 2.79 | 1
1483 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KONIARA Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001105/2021-2022 | 164/BD | 19/01/2022 | 30 | ROY CHOWDHURY CONSTRUCTION. | 35.78 | 35.74 | 1
1484 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000050/2022-2023 | 2868/BD | 21/09/2022 | 0 | Resource Division | 2.14 | 0 | 0
1485 | Barasat Division | Bangaon Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gaighata Water Supply Scheme at Gaighata Block within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000642/2021-2022 | 2174/BD | 18/11/2021 | 90 | SINGHA ROY & CO. | 133.93 | 129.03 | 1
1486 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Estimate for Additional Survey Work For DPR Preparation of Bhabanipur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000978/2021-2022 | 2157/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.47 | 3.44 | 1
1487 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & DPR Preparation for Bagdah Water Supply Scheme under Bongaon Sub-Division, under Barasat Division,PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001114/2021-2022 | 608/Bon | 31/12/2021 | 20 | UMWELT ENGINEER PVT.LTD. | 4.27 | 4.27 | 1
1488 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & DPR Preparation for Sindrani (Zone-I) Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002033/2021-2022 | 609/Bon | 31/12/2021 | 20 | UMWELT ENGINEER PVT.LTD. | 4.14 | 4.14 | 1
1489 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2021-2022 | 252/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
1490 | Barasat Division | Habra Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Maslandapur Water Supply Scheme(Zone-I) at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000816/2021-2022 | 2436/BD | 13/12/2021 | 90 | SUPRITI ENTERPRISE. | 113.29 | 109.24 | 1
1491 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & DPR Preparation for Sindrani (Zone-II) Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001116/2021-2022 | 610/Bon | 31/12/2021 | 20 | UMWELT ENGINEER PVT.LTD. | 3.48 | 3.48 | 1
1492 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000012/2021-2022 | 249/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
1493 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of Head Work Pump House site and allied works at Helencha water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000624/2022-2023 | 409/Bon | 23/08/2022 | 12 | KAMAL HALDAR. | 3 | 2.96 | 1
1494 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Helencha Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001334/2021-2022 | 134/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
1495 | Barasat Division | Bangaon Sub-Division | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2023 to 31/07/2023). | Assistant Engineer | Junior Engineer | ORD/001341/2022-2023 | 99/Bon | 31/01/2023 | 181 | ROY ENGINEERS. | 0.86 | 1.26 | 100
1496 | Barasat Division | Bangaon Sub-Division | Hiring of 1(one) no Luxury Car (Diesel/Driven) for the office use of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. (Period from:-01/02/2023 to 31/07/2023). | Assistant Engineer | Junior Engineer | ORD/001480/2022-2023 | 99/.BON | 31/01/2023 | 181 | ROY ENGINEERS. | 0.86 | 0.65 | 100
1497 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 of Janaphul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000043/2023-2024 | 1407/BD | 08/05/2023 | 30 | M/S K.P.PAL. | 14.5 | 0 | 100
1498 | Barasat Division | Habra Sub-Division | Acceptance cum work order for construction of the Boundary wall in Pump House No. 2 of Janaphul Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000162/2024-2025 | 1799/BD | 01/07/2024 | 45 | AREOCON. | 5.19 | 0 | 0
1499 | Barasat Division | Habra Sub-Division | Formal Work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of at Janaphul Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000546/2022-2023 | 2461/BD | 23/08/2022 | 90 | UTPAL CONSTRUCTION & CO. | 230.82 | 150.55 | 100
1500 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 for Augmentation of Janaphul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000911/2023-2024 | 2777/BD | 11/09/2023 | 30 | M/S K.P.PAL. | 14.5 | 0 | 0
1501 | Barasat Division | Habra Sub-Division | Improvement of Iron Elimination Plant at Janaphul W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001424/2023-2024 | 692/HAB | 02/11/2023 | 30 | GHOSH CONSTRUCTION | 4.51 | 0 | 100
1502 | Barasat Division | Habra Sub-Division | Special repair & renovation of boundary wall and other allied Works for Pump House No - 1 of Janaphul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001876/2023-2024 | 131/HAB | 05/02/2024 | 20 | DEBANJAN GHOSH. | 0.77 | 0 | 100
1503 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. ? 1 & 2 of Janaphul W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002981/2021-2022 | 503/HAB | 03/12/2021 | 30 | AREOCON. | 1.3 | 1.24 | 1
1504 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000055/2023-2024 | 1556/BD | 23/05/2023 | 0 | Resource Division | 0.92 | 0 | 0
1505 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000080/2022-2023 | 3106/BD | 18/10/2022 | 0 | Resource Division | 8.11 | 0 | 0
1506 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000126/2022-2023 | 3797/BD | 22/12/2022 | 0 | Resource Division | 6.17 | 0 | 0
1507 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Kanmari W/S scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000573/2024-2025 | 1117/HSD | 19/09/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.9 | 0 | 100
1508 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with retofitting of Kanmari w/s scheme (Zone-II), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000974/2022-2023 | 100/BD | 11/01/2023 | 90 | M/S PROGATI ENTERPRISE. | 297.96 | 291.19 | 1
1509 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Nazat mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2023-2024 | 1084/HSD | 31/08/2023 | 10 | M/S PROGATI ENTERPRISE. | 0.95 | 0 | 100
1510 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Hatgachi mouza due to erosion of soil for heavy rain fall during monsoon season within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001002/2023-2024 | 1085/HSD | 31/08/2023 | 10 | M/S PROGATI ENTERPRISE. | 0.94 | 0 | 100
1511 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Kanmari mouza within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001813/2023-2024 | 231/HSD | 29/02/2024 | 10 | SARKAR ENTERPRISE | 0.93 | 0 | 100
1512 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Nalkora mouza within Kanmari w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001815/2023-2024 | 232/HSD | 29/02/2024 | 10 | SARKAR ENTERPRISE | 0.93 | 0 | 100
1513 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Hatgachi mouza within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001816/2023-2024 | 233/HSD | 29/02/2024 | 10 | M/S PROGATI ENTERPRISE. | 0.94 | 0 | 100
1514 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Nazat mouza within Kanmari w/s scheme (Z-II), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001818/2023-2024 | 234/HSD | 29/02/2024 | 10 | M/S PROGATI ENTERPRISE. | 0.95 | 0 | 100
1515 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional land development for connecting road at tube well site-1 (H/W site) within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000113/2022-2023 | 930/HSD | 07/06/2022 | 21 | M/S DATTA ENTERPRISE. | 2.01 | 2.01 | 1
1516 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional land development at tube well site-1 (H/W site) within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000114/2022-2023 | 931/HSD | 07/06/2022 | 21 | M/S PROGATI ENTERPRISE. | 4.53 | 4.53 | 1
1517 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) within Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000209/2022-2023 | 1889/BD | 05/07/2022 | 60 | BABUSONA CONSTRUCTION. | 12.5 | 12.63 | 10
1518 | Barasat Division | Hasnabad Sub-Division | Acceptance Cum Work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2022-2023 | 2245/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 54.44 | 36.84 | 0
1519 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Geotechnical investigation for the construction of proposed OHR (Capacity 400 M3 ) at HW site within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 1380/HSD | 04/08/2022 | 30 | RANJIT MITRA SUPPLIERS | 0.73 | 0.73 | 0
1520 | Barasat Division | Hasnabad Sub-Division | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection & Construction of 400 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Department design, drawing & specification including bored pile & pile cap in connection with Nityaberia water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000721/2023-2024 | 2577/BD | 25/08/2023 | 1096 | KINGS & CO. | 859.85 | 0 | 25
1521 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for protection of 2nd pump house at canal side by UC bullah pilling within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000860/2023-2024 | 1046/HSD | 31/08/2023 | 10 | BABUSONA CONSTRUCTION. | 0.95 | 0 | 100
1522 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line and other allied works within Nityaberia water supply scheme Sandeshkhali-I Block and Surface Water Based Piped Water Supply Scheme for Hasnabad, under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001020/2024-2025 | 3745/BD | 27/12/2024 | 360 | KINGS & CO. | 163.99 | 0 | 25
1523 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Land development at tube well site-1 within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001025/2021-2022 | 13/HSD | 04/01/2022 | 15 | M/S DATTA ENTERPRISE. | 4.93 | 4.87 | 1
1524 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Land development at tube well site-2 within Nityabaria w/s scheme, Sandeshkhali-I under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001027/2021-2022 | 15/HSD | 04/01/2022 | 10 | M/S PROGATI ENTERPRISE. | 1.59 | 1.59 | 1
1525 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 No. 360.00 mtr. Deep 100 X 40 mm. dia. trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001039/2021-2022 | 25/HSD | 04/01/2022 | 15 | GOBINDA DAS. | 3.14 | 2.7 | 1
1526 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 No. 360.00 mtr. Deep 100 X 40 mm. dia. trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-2 for Nityabaria w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001041/2021-2022 | 27/HSD | 04/01/2022 | 15 | M/S GHOSH CONSTRUCTION. | 3.14 | 2.58 | 1
1527 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional height for construction of PH No- 2 & other allied works at located canal side within Nityaberia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001289/2023-2024 | 1411/HSD | 06/11/2023 | 10 | BABUSONA CONSTRUCTION. | 0.97 | 0 | 100
1528 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 for Nityaberia water supply scheme, Sandeskhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001532/2024-2025 | 387/HSD | 10/02/2025 | 10 | KINGS & CO. | 0.95 | 0 | 0
1529 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2024-2025 | 3478/BD | 10/12/2024 | 0 | Resource Division | 34.89 | 0 | 0
1530 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & strainer having 300mm dia 36 mtr. Long housing pipe & 200 mm dia 30 mtr. long filter at Bharatpur water supply scheme under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000363/2022-2023 | 2241/BD | 28/07/2022 | 30 | MONDAL ENTERPRISE. (BARASAT) | 14.32 | 12.4 | 1
1531 | Barasat Division | Bangaon Sub-Division | Construction of Boundary wall at 2nd T/W site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000568/2023-2024 | 613/Bon | 08/08/2023 | 21 | ONKAR ENTERPRISE. | 4.08 | 0 | 0
1532 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000639/2023-2024 | 622/Bon | 08/08/2023 | 12 | SAMBHU RAY CHOWDHURY. | 1.51 | 0 | 100
1533 | Barasat Division | Bangaon Sub-Division | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Bharatpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000773/2022-2023 | 3470/BD | 01/12/2022 | 90 | ONKAR ENTERPRISE. | 140.49 | 140.43 | 1
1534 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of 150 cum. capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile, pile cap & Soil Investigation within command area for Augmentation of Bharatpur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000884/2023-2024 | 2793/BD | 12/09/2023 | 730 | B.M.ENGINEERING. & CONSTRUCTION. | 91.92 | 0 | 60
1535 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road at 2ndT/W site for Augmentation of Bharatpur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000968/2023-2024 | 556/Bon | 18/07/2023 | 15 | GHOSH CONSTRUCTION. | 0.92 | 0 | 100
1536 | Barasat Division | Bangaon Sub-Division | Carriage of different dia D.I. K-9 pipes with loading & unloading from Hasnabad Rampur to Bongaon Municipality (Zone-II) H/W site under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001498/2024-2025 | 958/Bon | 02/08/2024 | 9 | KAMAL HALDER. | 0.53 | 0 | 100
1537 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Bharatpur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001742/2023-2024 | 538/BD | 21/02/2024 | 45 | LAXMEE ENTERPRISE | 7.27 | 0 | 100
1538 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Bharatpur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002773/2021-2022 | 126/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 1
1539 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Bharatpur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002938/2021-2022 | 633/BON | 31/12/2021 | 21 | GHOSH CONSTRUCTION. | 1.26 | 1.2 | 1
1540 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000097/2022-2023 | 3666/BD | 13/12/2022 | 0 | Resource Division | 7.57 | 0 | 0
1541 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000118/2022-2023 | 3692/BD | 14/12/2022 | 0 | Resource Division | 0.41 | 0 | 0
1542 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Bouthakurani water supply scheme (Z-II) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2024-2025 | 630/HSD | 12/06/2024 | 10 | PRITAM MUKHOPADHYAY. | 1.02 | 0 | 100
1543 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-3 & 4 in connection with Augmentation for Bouthakurani water supply scheme (Z-I) , Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2024-2025 | 631/HSD | 12/06/2024 | 10 | PRITAM MUKHOPADHYAY. | 1.02 | 0 | 100
1544 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 3 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 776/HSD | 13/07/2023 | 10 | PRITAM MUKHOPADHYAY. | 0.73 | 0.73 | 100
1545 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000253/2023-2024 | 779/HSD | 13/07/2023 | 10 | NURJAHAN ENTERPRISE. | 0.79 | 0 | 100
1546 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Emergent restoration of approach road for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000254/2023-2024 | 780/HSD | 13/07/2023 | 10 | SHYAM SUNDAR DAS. | 0.55 | 0 | 0
1547 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000255/2023-2024 | 781/HSD | 13/07/2023 | 10 | PRITAM MUKHOPADHYAY. | 0.6 | 0.6 | 100
1548 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000256/2023-2024 | 782/HSD | 13/07/2023 | 10 | NURJAHAN ENTERPRISE. | 0.93 | 0 | 100
1549 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing & construction of boundary wall for movement of rig machineries for sinking of big dia TW at PH no- 4 in connection with Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000258/2023-2024 | 784/HSD | 13/07/2023 | 10 | SHYAM SUNDAR DAS. | 0.71 | 0 | 100
1550 | Barasat Division | Hasnabad Sub-Division | Formal work order for for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000520/2022-2023 | 2402/BD | 17/08/2022 | 90 | M/S PROGATI ENTERPRISE. | 238.52 | 236.38 | 1
1551 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bouthakurani water supply scheme (Zone-I), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000521/2022-2023 | 2403/BD | 17/08/2022 | 90 | R.K.MANDAL & CO. | 239.51 | 236.33 | 1
1552 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-IIblock under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000719/2023-2024 | 2472/BD | 18/08/2023 | 30 | M/S DATTA ENTERPRISE. | 26.97 | 21.39 | 100
1553 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Sandeshkhali and Bouthakurani (Z-II) w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000791/2024-2025 | 3332/BD | 28/11/2024 | 60 | UTPAL CONSTRUCTION & CO. | 63.3 | 0 | 0
1554 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia DI/UPVC rising/distribution pipe line by UC bullah/Bamboo pile for Augmentation of Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000849/2023-2024 | 2657/BD | 01/09/2023 | 30 | R.K.MANDAL & CO. | 80.57 | 80.45 | 81
1555 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-I), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001175/2022-2023 | 788/BD | 13/03/2023 | 30 | M/S DATTA ENTERPRISE. | 47.05 | 38.83 | 0
1556 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bouthakurani w/s scheme (Z-II), Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001176/2022-2023 | 789/BD | 13/03/2023 | 30 | M/S DATTA ENTERPRISE. | 47.04 | 37.49 | 1
1557 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-5 in connection with Augmentation for Bouthakuranii (Z-I) water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001305/2024-2025 | 151/HSD | 27/01/2025 | 10 | PRITAM MUKHOPADHYAY. | 0.73 | 0 | 100
1558 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Bouthakurani water supply scheme (Z-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001375/2024-2025 | 242/HSD | 30/01/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.84 | 0 | 100
1559 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 100 & 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces in connection with augmentation of Bouthakurani water supply scheme (Z-II), Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001470/2024-2025 | 344/HSD | 06/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.6 | 0 | 100
1560 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection for the leftout portion at Dholkhali Mouza in connection with Augmentation of Bouthakurani water supply scheme (Z- I), Sandeskhali-II Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001531/2024-2025 | 386/HSD | 10/02/2025 | 10 | HASAN ENTERPRISE | 0.97 | 0 | 0
1561 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places in connection with augmentation of Bouthakurani W/S Scheme Z-II, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. (Phase-III) | Assistant Engineer | Junior Engineer | ORD/001535/2024-2025 | 390/HSD | 10/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0 | 100
1562 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of BOUTHAKURANI Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002688/2021-2022 | 230/HSD | 02/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.81 | 4.81 | 1
1563 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000038/2022-2023 | 2470/BD | 24/08/2022 | 0 | Resource Division | 8.3 | 0 | 0
1564 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000085/2022-2023 | 3365/BD | 17/11/2022 | 0 | Resource Division | 3.05 | 0 | 0
1565 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Basghata Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000353/2024-2025 | 2358/BD | 20/08/2024 | 420 | MD.SALIM GAZI. | 25.84 | 0 | 75
1566 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer at Augmentation of Bansghata Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001156/2023-2024 | 518/BD | 20/02/2024 | 300 | M/S N.K. BUILDERS | 30.51 | 0 | 100
1567 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Di rising main, DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Bansghata Water Supply Scheme, Bagdah Block, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001171/2022-2023 | 760/BD | 10/03/2023 | 90 | UMWELT ENGINEER PVT.LTD. | 747.85 | 511.9 | 100
1568 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at 1st Tube Well & 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Bansghata water Supply scheme, Bagdah Block within jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001500/2023-2024 | 4471/BD | 22/11/2023 | 414 | ROY CHOWDHURY CONSTRUCTION. | 12.67 | 0 | 73
1569 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Bansghata Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002790/2021-2022 | 142/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
1570 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000006/2023-2024 | 1246/BD | 25/04/2023 | 0 | Resource Division | 113.03 | 0 | 0
1571 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2023-2024 | 1864/BD | 23/06/2023 | 0 | Resource Division | 31.18 | 0 | 0
1572 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Gabberia w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000723/2023-2024 | 2475/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 63.23 | 0 | 92
1573 | Barasat Division | Hasnabad Sub-Division | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 300 cum capacity 20rntr. staging height R.C.C. Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection with Augmentaion of Gabberia water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000761/2023-2024 | 2526/BD | 23/08/2023 | 707 | BALAJEE ENTERPRISES | 550.99 | 202.79 | 79
1574 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000247/2022-2023 | 938/BD | 22/03/2023 | 0 | Resource Division | 19.76 | 0 | 0
1575 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) by augmentation for Ghona water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000685/2022-2023 | 3184/BD | 01/11/2022 | 90 | SHIBU BISWAS. | 179.98 | 98.31 | 85
1576 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000144/2022-2023 | 3821/BD | 23/12/2022 | 0 | Resource Division | 27.91 | 0 | 0
1577 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000160/2023-2024 | 4405/BD | 10/11/2023 | 0 | Resource Division | 3.08 | 0 | 0
1578 | Barasat Division | Basirhat Sub-Division | Dismantling of a dilapidated Room due to construction of Bio Eco Tech Plant at the Head Work site of Dakshin Chatra Zone I Water Supply Scheme under Barasat Division, P.H.E. | Assistant Engineer | Junior Engineer | ORD/000467/2024-2025 | 942/BHTSD | 24/05/2024 | 7 | N.R. ENTERPRISE | 0.97 | 0 | 100
1579 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Swarupnagar Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001009/2024-2025 | 3625/BD | 20/12/2024 | 90 | PUSPA CONSTRUCTION. | 57.26 | 0 | 0
1580 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection) for Augmentation of Dakshin Chatra Zone-II Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001186/2022-2023 | 1041/BD | 31/03/2023 | 773 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 378.49 | 56.3 | 37
1581 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Dakshin Chatra Zone II Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002754/2021-2022 | 442/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 4.04 | 1
1582 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2023-2024 | 1239/BD | 25/04/2023 | 0 | Resource Division | 69.2 | 0 | 0
1583 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000064/2023-2024 | 1627/BD | 01/06/2023 | 0 | Resource Division | 19.43 | 0 | 0
1584 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2022-2023 | 2438/BD | 22/08/2022 | 30 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 22.14 | 54
1585 | Barasat Division | Hasnabad Sub-Division | Formal Work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nurpur water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000516/2022-2023 | 2398/BD | 17/08/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 183.61 | 179.26 | 1
1586 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Nurpur water supply scheme, Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001251/2023-2024 | 4181/BD | 30/10/2023 | 730 | SARKAR ENTERPRISE & CO. | 122.36 | 0 | 100
1587 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000036/2022-2023 | 2475/BD | 24/08/2022 | 0 | Resource Division | 4.91 | 0 | 0
1588 | Barasat Division | Bangaon Sub-Division | Enhancement amount of GST for laying of DI/UPVC distribution pipe line and providing FHTC for Augmentation Kamlanbas wsscheme. | Assistant Engineer | Junior Engineer | BILL/01248/2024-2025 | BP-2024-25-416 | 07/10/2024 | 0 | BANERJEE CONSTRUCTION. ( BARASAT) | 7.08 | 0 | 0
1589 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Restoration of existing 140 mm dia UPVC pipe line along the main road by UC Ballah pilling due to soil erosion at the bank of Ichhamati river near Holor Ghat (Chalk Jhitkipota) under Augmentation work of Kamalabas W/S Scheme, Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000025/2025-2026 | 1523/BD | 14/05/2025 | 180 | ANARUL KHAN. | 61.45 | 0 | 40
1590 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kamalabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2448/BD | 15/07/2025 | 45 | MONDAL ENTERPRISE. (BARASAT) | 23.45 | 0 | 0
1591 | Barasat Division | Bangaon Sub-Division | Emergent works for repairing pipe line, FHTC refining, ferrule wash with supply of sluice valve and construction of valve chamber under Augmentation work at Kamlabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2024-2025 | 490/Bon | 04/04/2024 | 15 | MONDAL & CO.(BON) | 4.97 | 0 | 100
1592 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kamalabas Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000836/2022-2023 | 3630/BD | 12/12/2022 | 90 | BANERJEE CONSTRUCTION. ( BARASAT) | 181.45 | 131.1 | 0
1593 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep replacement T/W by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamlabas Water Supply Scheme (2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001012/2023-2024 | 2829/BD | 15/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.14 | 0 | 100
1594 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram with laying of UPVC pipe line, Tube Well connection and pipe protection work under Augmentation work at Kamalabas W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001042/2024-2025 | 3620/BD | 20/12/2024 | 150 | MONDAL & CO.(BON) | 10.13 | 0 | 100
1595 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kamalabas Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001151/2023-2024 | 2944/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 0 | 100
1596 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001738/2023-2024 | 534/BD | 21/02/2024 | 45 | REAL TIME | 12.89 | 0 | 100
1597 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at Head Work & 2nd T/W site under Augmentation of Kamlabas Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001750/2023-2024 | 558/BD | 22/02/2024 | 450 | S.S. INFRASTRUCTURE | 10.36 | 0 | 100
1598 | Barasat Division | Bangaon Sub-Division | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Kamlabas w/s scheme Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002274/2023-2024 | 211/Bon | 27/02/2024 | 45 | MONDAL & CO.(BON) | 4.39 | 0 | 100
1599 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Kamlabas water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002955/2021-2022 | 592/BON | 22/12/2021 | 21 | MONDAL & CO.(BON) | 2.52 | 2.31 | 1
1600 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000153/2022-2023 | 1259/BD | 25/04/2023 | 0 | Resource Division | 17.95 | 0 | 0
1601 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for special repair and renovation of existing structures like Pump House, boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Champapukur, Chandipur, Dakhin Debipur, Dhopaberia, Srinagar and Sangrampur Water Supply Scheme of different block under Basirhat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2025-2026 | 2424/BD | 14/07/2025 | 150 | DAS ENTERPRISE | 82.86 | 0 | 0
1602 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Srinagar water supply scheme in Basirhat-II Block of North 24 Parganas district under under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000955/2022-2023 | 92/BD | 11/01/2023 | 90 | CHANDA CONSTRUCTION. | 376.97 | 290.43 | 82
1603 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SRINAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002793/2021-2022 | 342/ BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.1 | 3.92 | 1
1604 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000167/2022-2023 | 482/BD | 17/02/2023 | 0 | Resource Division | 70.46 | 0 | 0
1605 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000187/2022-2023 | 596/BD | 23/02/2023 | 0 | Resource Division | 16.4 | 0 | 0
1606 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Raharhati water supply scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000738/2022-2023 | 3306/BD | 10/11/2022 | 90 | M/S PRADIP KUMAR PAL | 139.59 | 128.96 | 99
1607 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. big dia. 300 mtr deep Tubewell by D.R. Rig method, with 300 mm dia 36.0 mtr. long PVC having 200mm dia 30 mtr. long filter for Augmentation of Raharati Water Supply Scheme in Basirhat-II Block of Basirhat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001924/2023-2024 | 769/BD | 11/03/2024 | 30 | SHEKH ENTERPRISE | 21.75 | 0 | 0
1608 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000141/2022-2023 | 3818/BD | 23/12/2022 | 0 | Resource Division | 27.79 | 0 | 0
1609 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000020/2023-2024 | 1206/BD | 20/04/2023 | 30 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 31.03 | 24.86 | 51
1610 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Monipur water supply scheme, Sandeshkhali-II Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2023-2024 | 1721/BD | 08/06/2023 | 642 | R.K.MANDAL & CO. | 150.42 | 0 | 90
1611 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Monipur water supply scheme,Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte. under barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000522/2022-2023 | 2446/BD | 23/08/2022 | 90 | APURBA MANDAL | 278.15 | 252.56 | 1
1612 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000722/2023-2024 | 2474/BD | 18/08/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 31.64 | 0 | 100
1613 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Korakati and Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000775/2024-2025 | 3333/BD | 28/11/2024 | 60 | UTPAL CONSTRUCTION & CO. | 63.34 | 0 | 0
1614 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2023-2024 | 2654/BD | 01/09/2023 | 30 | M/S K.B.ENTERPRISE. | 27.43 | 27.39 | 85
1615 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Paschim Monipur FP School, East Monipur Khargeswar Adibasi FP School within the command area of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000865/2023-2024 | 1051/HSD | 31/08/2023 | 7 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 0.48 | 0 | 0
1616 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Monipur water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001291/2023-2024 | 1413/HSD | 06/11/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0 | 100
1617 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply, fitting & fixing of sluice valve with valve chember at HW & 2nd TW site in connection with augmentation of Monipur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001294/2023-2024 | 1416/HSD | 06/11/2023 | 7 | BADAL GHOSH. | 0.97 | 0 | 100
1618 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2022-2023 | 2473/BD | 24/08/2022 | 0 | Resource Division | 13.91 | 0 | 0
1619 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Bachhra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 1690/BD | 07/06/2023 | 366 | R.K.MANDAL & CO. | 267.07 | 131.99 | 85
1620 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection within Bachra water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2025-2026 | 1477/HSD | 14/07/2025 | 10 | M/S SOURAV DAS | 0.72 | 0 | 0
1621 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Bachra water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001905/2024-2025 | 541/HSD | 10/03/2025 | 10 | M/S SOURAV DAS | 0.72 | 0 | 0
1622 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BACHHRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002701/2021-2022 | 244/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.8 | 4.8 | 1
1623 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000221/2022-2023 | 876/BD | 22/03/2023 | 0 | Resource Division | 30.63 | 0 | 0
1624 | Barasat Division | Hasnabad Sub-Division | Strengthening and improvement of RIDF road | Assistant Engineer | Junior Engineer | BILL/00602/2024-2025 | BP-2024-25-220 | 02/09/2024 | 0 | EXECUTIVE ENGINEER (HPIU), WBSRDA ,BARASAT DIVISION | 45.3 | 0 | 0
1625 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Dakshin Bhebia water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2023-2024 | 2593/BD | 28/08/2023 | 1097 | H.I.ENTERPRISE. | 937.45 | 0 | 65
1626 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Ph No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Dakshin Bhebia w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001016/2024-2025 | 3577/BD | 18/12/2024 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 77.52 | 0 | 68
1627 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Surging and development of Big dia tubewell by Carrying out surging and back blowing of existing tube well including installation of suitable education pipes of adequate diameter upto required depth along with suitable airline pipes for injecting compressed air under pressure at the appropriates depth inside the tube well within Hasnabad Sub-Division PHE Dte. under Barasat Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2024-2025 | 172/BD | 15/01/2025 | 210 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 30.65 | 0 | 60
1628 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection in connection with augmentation of Dakshin Bhebia W/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001934/2024-2025 | 1024/BD | 28/03/2025 | 75 | ABDUR RAHIM GAZI | 7.49 | 0 | 0
1629 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000165/2023-2024 | 4508/BD | 28/11/2023 | 0 | Resource Division | 33.88 | 0 | 0
1630 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000238/2022-2023 | 930/BD | 22/03/2023 | 0 | Resource Division | 86.74 | 0 | 0
1631 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Zafarpur Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000831/2021-2022 | 2461/BD | 15/12/2021 | 45 | SHIBU BISWAS. | 81.63 | 81.47 | 1
1632 | Barasat Division | Basirhat Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different villages of various PWSS of Basirhat-II Block within the jurisdiction of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/001484/2024-2025 | 150/BHTSD | 29/01/2025 | 20 | BIBHAS PAL. | 0.88 | 0 | 90
1633 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for ZAFARPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001947/2021-2022 | 203/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.3 | 4.19 | 1
1634 | Barasat Division | Barasat Sadar Sub-Division | Laying of UPVC pipe line at village Khudramangalgathi in connection with FHTC work under Sohai Swetpur Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. Sl.-1 | Assistant Engineer | Junior Engineer | ORD/000491/2022-2023 | 309/BSD | 11/04/2022 | 7 | RAKESH ENTERPRISE. | 4.5 | 4.5 | 1
1635 | Barasat Division | Barasat Sadar Sub-Division | Laying of UPVC pipe line at Culvert More towards Khudramangalgathi in connection with FHTC work under Sohai Swetpur Zone-I Water Supply Scheme within Barasat Sub Division, P.H.E.Dte. Sl. No.-02 | Assistant Engineer | Junior Engineer | ORD/000494/2022-2023 | 310/BSD | 11/04/2022 | 7 | RAKESH ENTERPRISE. | 4.27 | 4.27 | 1
1636 | Barasat Division | Barasat Sadar Sub-Division | Road restoration work at Kalitala More to Pump House no.-1 via Swetpur Bazar in connection with laying of distribution system of pipe line with Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E.Dte. Sl. No.-07 | Assistant Engineer | Junior Engineer | ORD/000497/2022-2023 | 336/BSD | 12/04/2022 | 7 | SUN ENTERPRISE. | 4.58 | 4.58 | 1
1637 | Barasat Division | Barasat Sadar Sub-Division | Road restoration work at Pump House no.-1 to Mirjapur High School via Pump House No.-2 in connection with laying of distribution system of pipe line with Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E.Dte. Sl. No.-08 | Assistant Engineer | Junior Engineer | ORD/000498/2022-2023 | 337/BSD | 12/04/2022 | 7 | SUN ENTERPRISE. | 4.55 | 4.55 | 1
1638 | Barasat Division | Barasat Sadar Sub-Division | Fomal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kshudra Mangalgathi, Mirzzapur, Swetpur, Daibagnapol, Mongal Nagar, Noajispur, Bajitnagar, Mobarakpur & Bara Bisweswarpur mouzas (Part) within Sohai Swetpur Zone-I Water Supply Scheme at Deganga Block under Barasat Division, PHE Dte. Part-A Phase-I | Assistant Engineer | Junior Engineer | ORD/000574/2021-2022 | 1975/BD | 26/10/2021 | 90 | H.I.ENTERPRISE. | 225.34 | 210.13 | 1
1639 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (P.H. No-II) and allied works at Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. Sl. No.-7 | Assistant Engineer | Junior Engineer | ORD/001469/2021-2022 | 817/BSD | 10/12/2021 | 30 | JIBON BOSE. | 1.25 | 1.1 | 0
1640 | Barasat Division | Barasat Sadar Sub-Division | Repairing & Renovation of 1 No. Pump House (Size- 5.20 x 7.20) of Head Work Site and allied works at Sohai Swetpur Water Supply Scheme Zone-I under Barasat Sub-Division, P.H.E.Dte. Sl. No.-6 | Assistant Engineer | Junior Engineer | ORD/001483/2021-2022 | 816/BSD | 10/12/2021 | 30 | M/S S.HAQUE & CO. | 1.84 | 1.74 | 0
1641 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line,Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Chutkia Radhanagar w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000039/2023-2024 | 1439/BD | 11/05/2023 | 692 | R.K.MANDAL & CO. | 290.05 | 137.78 | 100
1642 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Strengthing of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No- 2 within Chutkia Radhanagar w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000886/2023-2024 | 1128/HSD | 05/09/2023 | 7 | NURJAHAN ENTERPRISE. | 1.69 | 0 | 100
1643 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection at Chikar more end within Chutkia Radhanagar w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001536/2024-2025 | 111/BD | 09/01/2025 | 150 | TARUN KUMAR LAHA | 7.47 | 0 | 0
1644 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (CHUTKIA RADHANAGAR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002706/2021-2022 | 249/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 0
1645 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (CHUTKIA RADHANAGAR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002708/2021-2022 | 271/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.85 | 0.85 | 1
1646 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000213/2022-2023 | 883/BD | 22/03/2023 | 0 | Resource Division | 28.59 | 0 | 0
1647 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 100 cum capacity CWR, pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Kachurhula w/s scheme (Z-I), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2023-2024 | 1693/BD | 07/06/2023 | 731 | TRISHA ENTERPRISE & CO. | 166.1 | 0 | 16
1648 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 Nos. 300.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe & strainers at T/W site-1 for Kachurhula w/s scheme (Zone-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001105/2023-2024 | 1190/HSD | 22/09/2023 | 10 | ROY CHOWDHURY CONSTRUCTION. | 2.63 | 0 | 100
1649 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kachurhula w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001768/2023-2024 | 553/BD | 22/02/2024 | 495 | SAHA CONSTRUCTION & CO | 33.41 | 0 | 50
1650 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-H). | Assistant Engineer | Junior Engineer | ORD/001942/2023-2024 | 273/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.88 | 0 | 100
1651 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002717/2021-2022 | 280/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.5 | 4.5 | 1
1652 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KACHURHULA Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002995/2021-2022 | 280/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.5 | 0 | 1
1653 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000210/2022-2023 | 892/BD | 22/03/2023 | 0 | Resource Division | 17.66 | 0 | 0
1654 | Barasat Division | Habra Sub-Division | Formal work order for Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zonal Head work site - XV i.e. Bergum including Laying Distribution System within the jurisdiction of (Zone-XV) & Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project under Habra Sub Division within Barasat Division, P.H.E. Dte. Habra-I Block PART-D. | Assistant Engineer | Junior Engineer | ORD/001207/2023-2024 | 4046/BD | 13/10/2023 | 1095 | H.I.ENTERPRISE. | 1322.52 | 0 | 92
1655 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Augmentation of Chhoto Sehara Piped Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000767/2022-2023 | 631/HSD | 08/04/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.78 | 2.78 | 0
1656 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional laying of 160 mm dia. HDPE pipe line from old pump house no- 1 & 2 to near Roy para, protection works & other allied works within Kalinagar W/s scheme (Z-I), Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000981/2024-2025 | 3669/BD | 24/12/2024 | 270 | CHANCHAL ENTERPRISE & CO. | 163.96 | 0 | 60
1657 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC/DI distribution pipe line and providing Functional Household Tap Connection for Augmentation of Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001201/2022-2023 | 830/BD | 15/03/2023 | 90 | MONDAL & CO. (BASIRHAT). | 227.81 | 209.69 | 0
1658 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at head Work site (PH No-1 ) within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001306/2023-2024 | 4380/BD | 10/11/2023 | 539 | M/S DATTA ENTERPRISE. | 27.13 | 0 | 100
1659 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chotto Sehara water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/001355/2022-2023 | 1153/BD. | 12/04/2022 | 240 | S.S.ENTERPRISE. (BAMANGACHI) | 143.13 | 0 | 95
1660 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000242/2022-2023 | 936/BD | 22/03/2023 | 0 | Resource Division | 28.95 | 0 | 0
1661 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000090/2023-2024 | 1441/BD | 11/05/2023 | 60 | ROYAL CONSTRUCTION | 16.03 | 0 | 62
1662 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Uttar Kalibari Adhikary House to PH No- 2 within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000279/2023-2024 | 806/HSD | 13/07/2023 | 7 | SARKAR ENTERPRISE | 0.9 | 0 | 100
1663 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 no. pump connection at PH No.-1 & 2 in connection with Augmentation for Mohanpur water supply scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000300/2024-2025 | 868/HSD | 07/08/2024 | 7 | ANKUSH CONSTRUCTION & CO. | 1.17 | 0 | 100
1664 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 150 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Mohanpur Zone-II in connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2024-2025 | 2275/BD | 12/08/2024 | 365 | M/S B.K.ENTERPRISE. | 100.39 | 0 | 0
1665 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 250 mtr deep Tubewell by D.R. Rig method at PH No.-2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000720/2023-2024 | 2473/BD | 18/08/2023 | 30 | ABDUL ALIM MONDAL. | 16.45 | 13.27 | 100
1666 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-I), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001070/2022-2023 | 401/BD | 09/02/2023 | 90 | M/S PROGATI ENTERPRISE. | 306.25 | 293.07 | 1
1667 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional Household Tap Connection in Connection with Augmentation of Mohanpur water supply scheme (Zone-II), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001121/2022-2023 | 404/BD | 09/02/2023 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 283.51 | 213.35 | 1
1668 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Zone-I), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001174/2022-2023 | 787/BD | 13/03/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 21.45 | 14.51 | 0
1669 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2022-2023 | 794/BD | 13/03/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 42.87 | 33.12 | 0
1670 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Mohanpur water supply scheme (Zone-I), Minakhan Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001263/2023-2024 | 4193/BD | 30/10/2023 | 365 | M/S RAJPATH CONSTRUCTION. | 114.56 | 0 | 0
1671 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work by bamboo piling in different places in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001429/2024-2025 | 309/HSD | 04/02/2025 | 10 | SARKAR ENTERPRISE | 0.94 | 0 | 100
1672 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001430/2024-2025 | 310/HSD | 04/02/2025 | 10 | M/S RAJPATH CONSTRUCTION. | 0.81 | 0 | 100
1673 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Kalibari and Tangramari in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001509/2024-2025 | 373/HSD | 10/02/2025 | 10 | SARKAR ENTERPRISE | 0.96 | 0 | 100
1674 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with augmentation of Mohanpur w/s scheme (Z-I), Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001510/2024-2025 | 374/HSD | 10/02/2025 | 10 | ANKUSH CONSTRUCTION & CO. | 0.32 | 0 | 100
1675 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work by bamboo piling in different places of Kalibari in connection with augmentation of Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001511/2024-2025 | 375/HSD | 10/02/2025 | 10 | SARKAR ENTERPRISE | 0.94 | 0 | 100
1676 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 150 mm dia. DI rising main from PH No-1 to Uttar Kalibari Adhikary House within Mohanpur w/s scheme (Z-II), Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002499/2023-2024 | 803/HSD | 13/07/2023 | 7 | SARKAR ENTERPRISE | 0.98 | 0 | 100
1677 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000260/2022-2023 | 917/BD | 22/03/2023 | 0 | Resource Division | 2.48 | 0 | 0
1678 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-I and Amdanga Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2025-2026 | 1306/BD | 24/04/2025 | 120 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 99.64 | 0 | 0
1679 | Barasat Division | Barasat Sadar Sub-Division | Construction of New Pump House (Digha Mouza) with latrine at Chandrapur Water Supply Scheme under Barasat-I Block, size of 3.00m x 3.60m with latrine within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000030/2024-2025 | 166/BSD | 07/06/2024 | 30 | JIBON BOSE. | 4.18 | 0 | 100
1680 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Chandrapur Water Supply Scheme under JJM programme in Barasat-I block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2024-2025 | 2004/BD | 18/07/2024 | 630 | KINGS & CO. | 682.84 | 0 | 34
1681 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Chandrapur PWSS (1st Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000429/2024-2025 | 561/BSD | 09/09/2024 | 20 | S.MUKHERJEE. | 4.1 | 0 | 0
1682 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Chandrapur PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000430/2024-2025 | 562/BSD | 09/09/2024 | 20 | JIBON BOSE. | 2.95 | 0 | 0
1683 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Chandrapur PWSS (2nd Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000432/2024-2025 | 564/BSD | 09/09/2024 | 20 | M/S SANKAR ENTERPRISE. | 2.93 | 0 | 100
1684 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Chandrapur PWSS (3rd Tubewell - Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000433/2024-2025 | 565/BSD | 09/09/2024 | 20 | SUN ENTERPRISE. | 3.78 | 0 | 0
1685 | Barasat Division | Barasat Sadar Sub-Division | Construction of Culvert at Pump House - V of Chandrapur W/S Scheme under Barasat Sub. Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2024-2025 | 509/BSD | 30/08/2024 | 15 | S.MUKHERJEE. | 0.86 | 0 | 100
1686 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Chandrapur PWSS (3rd Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000522/2024-2025 | 566/BSD | 09/09/2024 | 20 | B. S. ENTERPRISE (BANAMALIPUR) | 2.33 | 0 | 100
1687 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Chandrapur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000679/2022-2023 | 456/BSD | 20/05/2022 | 30 | RADIANT | 4.58 | 0 | 100
1688 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 1200cum capacity 20mtr.Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and Providing FHTC for Augmentation of Chandrapur Water Supply Scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001189/2023-2024 | 3062/BD | 09/10/2023 | 1027 | MONDAL ENTERPRISE. (BARASAT) | 1459.09 | 0 | 46
1689 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001851/2023-2024 | 1121/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0 | 100
1690 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 months from w.e.f. 01.12.2023) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001855/2023-2024 | 857/BSD | 29/11/2023 | 183 | MADHAB CHANDRA DAS | 0.87 | 0 | 0
1691 | Barasat Division | Barasat Sadar Sub-Division | Construction of New Pump House (Charkhara Mouza) with latrine at Chandrapur Water Supply Scheme under Barasat-I Block, size of 3.00m x 3.60m with latrine within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002150/2023-2024 | 1241/BSD | 15/03/2024 | 31 | S.MUKHERJEE. | 4.18 | 0 | 0
1692 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2023-2024 | 1276/BD | 25/04/2023 | 0 | Resource Division | 208.17 | 0 | 0
1693 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000113/2023-2024 | 4022/BD | 12/10/2023 | 0 | Resource Division | 55.3 | 0 | 0
1694 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Champapukuria Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000336/2021-2022 | 1651/BD | 07/09/2021 | 45 | UTPAL CONSTRUCTION & CO. | 71.61 | 70.23 | 1
1695 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for CHAMPAPUKURIA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001970/2021-2022 | 344/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.43 | 3.42 | 1
1696 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household of Kundipur, Kundipur Jalkar and Keutipara mouza including laying of UPVC pipe under Augmentation work at additional Gangrapota & Gangrapota W/S Scheme, Bongaon block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2025-2026 | 1650/BD | 21/05/2025 | 90 | REAL TIME | 43.26 | 0 | 0
1697 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing and renovation works for 450 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Gangrapota Water Supply Scheme,Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000020/2024-2025 | 1537/BD | 07/06/2024 | 270 | MONDAL ENTERPRISE. (BARASAT) | 18.37 | 0 | 100
1698 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system within command area at Gangrapota(Additional) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 2030/BD | 13/07/2023 | 90 | RAJ KUMAR MONDAL | 175.4 | 0 | 70
1699 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Gangrapota Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2023-2024 | 2928/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.13 | 0 | 100
1700 | Barasat Division | Bangaon Sub-Division | Hiring of Luxury Car (Diesel) for the office use of the Assistant Engineer Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002518/2023-2024 | 87/Bon | 30/01/2024 | 182 | ROY ENGINEERS. | 0.86 | 0 | 0
1701 | Barasat Division | Bangaon Sub-Division | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002530/2023-2024 | 484/Bon | 30/06/2023 | 184 | VAI ENTERPRISE. | 0.87 | 0 | 100
1702 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000095/2023-2024 | 1862/BD | 23/06/2023 | 0 | Resource Division | 12.63 | 0 | 0
1703 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000102/2023-2024 | 2093/BD | 18/07/2023 | 0 | Resource Division | 12.63 | 0 | 0
1704 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Sindrani (Zone-II) PWSS (135 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000013/2024-2025 | 686/Bon | 07/06/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.91 | 0 | 100
1705 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Sindrani (Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000111/2022-2023 | 1649/BD | 09/06/2022 | 90 | MONDAL ENTERPRISE. (BARASAT) | 324.72 | 324.48 | 1
1706 | Barasat Division | Bangaon Sub-Division | Acceptance cum wok order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Sindrani (Zone-II) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000829/2022-2023 | 3623/BD | 12/12/2022 | 15 | NADIA TUBEWELLS | 15.07 | 12.82 | 0
1707 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Sindrani (Zone - II) Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001109/2023-2024 | 2922/BD | 26/09/2023 | 30 | B.M.ENGINEERING. & CONSTRUCTION. | 16.1 | 0 | 100
1708 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Sindrani (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001240/2023-2024 | 790/Bon | 10/10/2023 | 15 | UPWARDS ENGINEERING PRIVATE LIMITED | 3.53 | 0 | 100
1709 | Barasat Division | Bangaon Sub-Division | Hiring of Vehicle for the (Diesel) for the office use as well as sites inspection of the Assistant Engineer Bongaon Sub-Division, P.H.E. Dte. Under Barasat Division P.H.E. Dte. Period from 01.01.2023 to 31.06.2023. for 6 (six) months. | Assistant Engineer | Junior Engineer | ORD/001266/2022-2023 | 676/BON | 30/12/2022 | 182 | VAI ENTERPRISE. | 0.86 | 0 | 100
1710 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Sindrani Zone-II Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001700/2024-2025 | 707/BD | 06/03/2025 | 60 | ONKAR ENTERPRISE. | 7.1 | 0 | 0
1711 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Sindrani (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001728/2023-2024 | 522/BD | 20/02/2024 | 30 | A.D.ENTERPRISE. | 16.87 | 0 | 100
1712 | Barasat Division | Bangaon Sub-Division | Construction of 3.60 mtr. X 3.00mtr. size Switch room with sanitary and water supply arrangement incl. plinth protection at 2nd Tube Well site at Sindrani w/s scheme (Zone-II), Bagdah block within the jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002299/2023-2024 | 209/Bon | 27/02/2024 | 45 | SAMBHU RAY CHOWDHURY. | 4.41 | 0 | 100
1713 | Barasat Division | Bangaon Sub-Division | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.03.22 to 31.08.22=184 days. | Assistant Engineer | Junior Engineer | ORD/003034/2021-2022 | 386/HSD | 28/02/2022 | 184 | SUSMITA MANDAL. | 2.74 | 8.87 | 100
1714 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2022-2023 | 1669/BD | 13/06/2022 | 0 | Resource Division | 14.85 | 0 | 0
1715 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000089/2022-2023 | 3410/BD | 22/11/2022 | 0 | Resource Division | 7.9 | 0 | 0
1716 | Barasat Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 2181/BD | 02/08/2024 | 0 | Resource Division | 13.02 | 0 | 0
1717 | Barasat Division |  | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 2181/BD | 02/08/2024 | 0 | Resource Division | 17.29 | 0 | 0
1718 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system with in command area at Sindrani (Zone-I) Water Supply Scheme under Bongaon Sub-Division, PHE Dte.(Augmentation). | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 1210/BD | 21/04/2022 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 299.02 | 42.84 | 1
1719 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Sindrani (Zone-I) PWSS (135 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000012/2024-2025 | 685/Bon | 07/06/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 3.12 | 0 | 100
1720 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and tube well connection under Augmentation work at Sindrani W/S Scheme (Zone - I) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000085/2024-2025 | 1766/BD | 01/07/2024 | 15 | ONKAR ENTERPRISE. | 19.03 | 0 | 100
1721 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Sindrani (Zone-I) water supply scheme (Head Works site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000828/2022-2023 | 3622/BD | 12/12/2022 | 15 | NADIA TUBEWELLS | 15.06 | 12.32 | 0
1722 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Sindrani Zone-I Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001698/2024-2025 | 704/BD | 06/03/2025 | 60 | ONKAR ENTERPRISE. | 7.1 | 0 | 0
1723 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Sindrani(ZI&II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002939/2021-2022 | 594/BON | 22/12/2021 | 21 | GHOSH CONSTRUCTION. | 2.52 | 2.34 | 1
1724 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2022-2023 | 1364/BD | 13/05/2022 | 0 | Resource Division | 33.31 | 0 | 0
1725 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2022-2023 | 1675/BD | 13/06/2022 | 0 | Resource Division | 16.72 | 0 | 0
1726 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2022-2023 | 2374/BD | 12/08/2022 | 0 | Resource Division | 60.89 | 0 | 0
1727 | Barasat Division | Habra Sub-Division | Construction of Service Road (35 Mtr. Length X 2 Mtr. Width) for Pump House No:3 of kankpul Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000343/2024-2025 | 694/HAB | 25/07/2024 | 10 | DEBASISH SARKAR. | 2.14 | 0 | 0
1728 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of Boundary Wall (75 m Length) for Pump House No - 3 of Kankpul water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000405/2024-2025 | 2581/BD | 05/09/2024 | 45 | NEW MA TARA ENTERPRISE. | 11.91 | 0 | 0
1729 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Hiring Petrol Luxury Car on Daily basis (from20.08.2024 to 28.02.2025) for the office use of the Assistant Engineer(HQ), Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/000406/2024-2025 | 2341/BD | 16/08/2024 | 193 | M/S B.K.ENTERPRISE. | 0.92 | 0 | 0
1730 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Kankpul Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000562/2022-2023 | 2678/BD | 08/09/2022 | 90 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 328.95 | 236.52 | 1
1731 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Kankpul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2024-2025 | 924/HAB | 05/11/2024 | 20 | VAI ENTERPRISE. | 2.66 | 0 | 100
1732 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other Allied Works for Pump House No - 2 of Kankpul W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000897/2024-2025 | 930/HAB | 05/11/2024 | 20 | VAI ENTERPRISE. | 2.6 | 0 | 0
1733 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tube well by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Kankpul water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000913/2023-2024 | 2775/BD | 11/09/2023 | 583 | B.M.ENGINEERING. & CONSTRUCTION. | 28.92 | 0 | 100
1734 | Barasat Division | Habra Sub-Division | Continuation work order Hiring of 1 no. of Diesel Luxury Car (Euro - IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, For supervision of J.J.M. related work, executed within the entire Jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte.(For the period from: 01.03.2024 to 31.08.24) | Assistant Engineer | Junior Engineer | ORD/001795/2023-2024 | 211/HAB | 28/02/2024 | 182 | M/S SUKANTA ENTERPRISE. | 0.87 | 0 | 0
1735 | Barasat Division | Habra Sub-Division | Acceptance cum work order for construction of Service Road(15 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Kankpul Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001896/2023-2024 | 169/HAB | 19/02/2024 | 15 | M/S LATIKA CONSTRUCTION. | 0.92 | 0 | 0
1736 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000082/2022-2023 | 3107/BD | 18/10/2022 | 0 | Resource Division | 9.23 | 0 | 0
1737 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000133/2022-2023 | 3799/BD | 22/12/2022 | 0 | Resource Division | 90.58 | 0 | 0
1738 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Withdrawing, relaying of different dia. UPVC pipe line at Chaktangramari para in connection with augmentation of Hasnabad water supply scheme under Hasnabad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2025-2026 | 1005/HSD | 04/06/2025 | 10 | SARKAR ENTERPRISE | 0.95 | 0 | 0
1739 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 2 nos Blocks ( Hasnabad & Hingalganj) in North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2024-2025 | 754/HSD | 19/07/2024 | 10 | IMAGIN | 0.98 | 0 | 100
1740 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road, North side boundary wall & other allied works at PH no-1 within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 820/HSD | 14/07/2023 | 21 | ABDUL ALIM MONDAL. | 2.73 | 2.69 | 100
1741 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall at North side for damaged portion, construction of approach road & other allied works at PH No-2 within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000282/2023-2024 | 821/HSD | 14/07/2023 | 10 | SARKAR ENTERPRISE | 3.87 | 3.87 | 100
1742 | Barasat Division | Hasnabad Sub-Division | Formal work order for "Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 350 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Hasnabad water supply scheme, Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000779/2023-2024 | 2601/BD | 28/08/2023 | 582 | M/S S.S.ENTERPRISE. (SOUTH) | 793.69 | 0 | 70
1743 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional tap connection at Rameswarpur Union Adarsha Bidyalaya at Rameswarpur in connection with augmentation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000864/2023-2024 | 1050/HSD | 01/09/2023 | 10 | SARKAR ENTERPRISE | 0.6 | 0 | 0
1744 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000240/2022-2023 | 932/BD | 22/03/2023 | 0 | Resource Division | 221.49 | 0 | 0
1745 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for road restoration work damaged during pipe laying work under JJM in different water supply scheme under Barasat-I and Amdanga Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000005/2025-2026 | 1306/BD | 24/04/2025 | 120 | PIYALI CONSTRUCTION & GENERAL ORDER SUPPLIER | 99.64 | 0 | 0
1746 | Barasat Division | Barasat Sadar Sub-Division | Hiring 1(One) No. Diesel Luxury Car on Daily basis. (for 6 (six) months from w.e.f. 01.06.2024) for the office use of the Assistant Engineer, Barasat Sub Division, P.H.E. Dte. @ Rs. 475.00 (Rupees four hundred & seventy five only) per day Excluding fuel. (Period for 01/06/2024 to 30/11/2024) | Assistant Engineer | Junior Engineer | ORD/000049/2024-2025 | 140/BSD | 28/05/2024 | 184 | MADHAB CHANDRA DAS | 0.87 | 0 | 0
1747 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Additional pipeline and other allied works as per revised LDS in connection with Augmentation of Bodai-I Water Supply Scheme under JJM programme in Amdanga block within Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2024-2025 | 2580/BD | 05/09/2024 | 90 | A.P POWER & CONCRETE | 325.89 | 0 | 0
1748 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Bodai Water Supply Scheme Zone-I under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | Assistant Engineer | Junior Engineer | ORD/000287/2022-2023 | 548/BSD | 29/06/2022 | 30 | RADIANT | 3.7 | 0 | 100
1749 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 900 cum capacity 20mtr Height R.C.C Over Head Reservoir and laying of Rising main & distribution pipe line by DI & UPVC and providing FHTC for Augmentation of Bodai Zone-I Water Supply Scheme under Barasat Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001196/2023-2024 | 3080/BD | 10/10/2023 | 722 | PUSPA ENTERPRISE. | 1051.63 | 0 | 64
1750 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/001836/2023-2024 | 1116/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0 | 89
1751 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Amdanga Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001838/2023-2024 | 1116./1/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0 | 100
1752 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000111/2023-2024 | 3094/BD | 10/10/2023 | 0 | Resource Division | 26.86 | 0 | 0
1753 | Barasat Division | Basirhat Sub-Division | Special repairing of pipe line at different location of Sankhchura Water Supply Scheme under Basirhat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000058/2024-2025 | 914/BHTSD | 24/05/2024 | 7 | SOUMIT CONSTRUCTION | 0.31 | 0 | 100
1754 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Sankchura water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000134/2023-2024 | 1708/BD | 08/06/2023 | 723 | UTPAL CONSTRUCTION & CO. | 444.98 | 0 | 50
1755 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Sankchura Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000699/2024-2025 | 3255/BD | 25/11/2024 | 120 | M/S K.P.PAL. | 21.75 | 0 | 100
1756 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000009/2023-2024 | 1249/BD | 25/04/2023 | 0 | Resource Division | 114.4 | 0 | 0
1757 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000148/2023-2024 | 4406/BD | 10/11/2023 | 0 | Resource Division | 15.4 | 0 | 0
1758 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000185/2023-2024 | 385/BD | 07/02/2024 | 0 | Resource Division | 65.63 | 0 | 0
1759 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 350 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Nebadhui Duttapukur (Zone - I) water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000149/2023-2024 | 1712/BD | 08/06/2023 | 731 | DIAMOND ENGINEER'S CO-OP. SOCIETY LTD. | 386.46 | 0 | 75
1760 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (1st Tubewell - Pump House). | Assistant Engineer | Junior Engineer | ORD/000453/2024-2025 | 574/BSD | 10/09/2024 | 20 | CHAKRABORTY SUPPLIERS & CONSTRUCTION. | 3.24 | 0 | 100
1761 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Nebadhui Duttapukur Zone-I PWSS (3rd Tubewell -Pump House, Boundary Wall & Service Road). | Assistant Engineer | Junior Engineer | ORD/000458/2024-2025 | 577/BSD | 10/09/2024 | 20 | ROMI TREDERS. | 3.09 | 0 | 100
1762 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2023-2024 | 1280/BD | 25/04/2023 | 0 | Resource Division | 45.73 | 0 | 0
1763 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000076/2023-2024 | 1674/BD | 06/06/2023 | 0 | Resource Division | 14.7 | 0 | 0
1764 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000126/2023-2024 | 4373/BD | 10/11/2023 | 0 | Resource Division | 16.37 | 0 | 0
1765 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Dholkhali & Tongtala mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 1670/BD | 08/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 49.88 | 31.41 | 1
1766 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Radhanagar mouza within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2024-2025 | 994/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0 | 100
1767 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000555/2024-2025 | 997/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.84 | 0 | 100
1768 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 150mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000557/2024-2025 | 999/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0 | 100
1769 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 200mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000559/2024-2025 | 1001/HSD | 29/08/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0 | 100
1770 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Chotto Sehara mouza within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2024-2025 | 1172/HSD | 26/09/2024 | 10 | TRISHA ENTERPRISE & CO. | 0.97 | 0 | 100
1771 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Radhanagar laskar para, majher para, Singh para & Tati Para within Chhoto Sehara W/S/Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002120/2021-2022 | 1467/BD. | 13/08/2021 | 30 | M/S DATTA ENTERPRISE. | 31.6 | 4.63 | 1
1772 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Gobindapur Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001332/2021-2022 | 132/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.21 | 4.19 | 1
1773 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & DPR Preparation for Ashudi W/S Scheme in Habra - II Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002024/2021-2022 | 127/HAB | 16/03/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.13 | 3.09 | 1
1774 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Masia Nabastia water Supply Scheme at Baduria Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001243/2021-2022 | 401/BD | 10/02/2022 | 45 | PREMANANDA ROY BISWAS. | 49.45 | 49.25 | 1
1775 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for MASIA-NABASTIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001994/2021-2022 | 375/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.22 | 3.19 | 1
1776 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000069/2022-2023 | 2992/BD | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0
1777 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ghatpatila (Zone-I) Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001162/2021-2022 | 314/BD | 01/02/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 113.02 | 112.46 | 1
1778 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Ghatpatila (Zone-I) Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001329/2021-2022 | 130/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.11 | 4.11 | 1
1779 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Eojnagar Water Supply Scheme at Basirhat - II Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001249/2021-2022 | 403/BD | 10/02/2022 | 45 | UTPAL CONSTRUCTION & CO. | 91.51 | 0 | 1
1780 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for EOJNAGAR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001955/2021-2022 | 306/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.94 | 3.86 | 1
1781 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000073/2022-2023 | 2990/BD | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0
1782 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Sankchura Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001156/2021-2022 | 245/BD | 27/01/2022 | 45 | SHIBU BISWAS. | 78.21 | 77.09 | 1
1783 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SANKCHURA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001945/2021-2022 | 201/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.37 | 4.25 | 1
1784 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000071/2022-2023 | 2984/BD | 29/09/2022 | 0 | Resource Division | 0.02 | 0 | 0
1785 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of UPVC rising main by UC bullah pile at Joygram Fisheries for Rejuvenation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000585/2021-2022 | 1851/HSD | 17/11/2021 | 15 | ABDUL ALIM MONDAL. | 3.36 | 3.34 | 1
1786 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection Emergent restoration of concrete road for damage portion at different places for providing FHTC within Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000696/2021-2022 | 1984/HSD | 02/12/2021 | 7 | ABDUL ALIM MONDAL. | 2.46 | 2.46 | 1
1787 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Kumarjole w/s scheme, Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000926/2021-2022 | 1995/HSD.. | 02/12/2021 | 15 | ABDUL ALIM MONDAL. | 3.5 | 3.5 | 1
1788 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at N/H of Majed Gazi at Uttar Kumarjole Purba para for Retrofitting of Kumarjole W/S Scheme, Minakhan Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002303/2020-2021 | 2055/BD | 18/09/2020 | 10 | RUDRA DAS. | 3.27 | 3.27 | 0
1789 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000084/2023-2024 | 1817/BD | 19/06/2023 | 0 | Resource Division | 52.67 | 0 | 0
1790 | Barasat Division | Habra Sub-Division | Formal Work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIRA RAJIBPUR Water Supply Scheme at Habra -II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000914/2021-2022 | 2623/BD | 27/12/2021 | 90 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 189.09 | 156.26 | 1
1791 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Ashari Narayanpur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000987/2021-2022 | 2170/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.61 | 3.59 | 1
1792 | Barasat Division | Habra Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Kankpul Water Supply Scheme at Habra-II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000752/2021-2022 | 2388/BD | 09/12/2021 | 45 | S.S.ENTERPRISE. (BAMANGACHI) | 82.85 | 71.02 | 1
1793 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & DPR Preparation for Kankpul W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000939/2021-2022 | 567/HAB | 22/12/2021 | 10 | UMWELT ENGINEER PVT.LTD. | 4.02 | 4.02 | 1
1794 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Korakati Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000990/2021-2022 | 2172/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.12 | 4.12 | 1
1795 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road Head Work at site for Augmentation of Kurulia (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000731/2023-2024 | 621/Bon | 08/08/2023 | 25 | GHOSH CONSTRUCTION. | 4.75 | 0 | 100
1796 | Barasat Division | Bangaon Sub-Division | Improvement of Iron Elimination Plant and other related allied works at Kurulia (Zone - II) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000891/2023-2024 | 638/Bon | 14/08/2023 | 15 | SAMBHU RAY CHOWDHURY. | 2.49 | 0 | 100
1797 | Barasat Division | Bangaon Sub-Division | Formal work order for Improvement of Iron Elimination Plant and other related allied works at Kurulia (Zone-I) W/S Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000896/2023-2024 | 637/Bon | 14/08/2023 | 15 | TAPAN GHOSH. | 2.45 | 0 | 99
1798 | Barasat Division | Bangaon Sub-Division | Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001049/2023-2024 | 643/Bon | 14/08/2023 | 21 | M/S SAYAN ENTERPRISE. | 1.59 | 0 | 100
1799 | Barasat Division | Bangaon Sub-Division | Construction of Approach Road at 2ndT/W site for Augmentation of Kurulia (Zone-I) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001065/2023-2024 | 558/Bon | 18/07/2023 | 15 | ROY ENGINEERS. | 0.93 | 0 | 100
1800 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2023-2024 | 1202/BD | 20/04/2023 | 30 | TRISHA ENTERPRISE & CO. | 31.02 | 23.48 | 0
1801 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 200 mm dia. DI distribution main from PH No- 1 to PH No-2 & PH No- 2 to N/H/O Sudip Gayen for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000264/2022-2023 | 1186/HSD | 13/07/2022 | 15 | R.K.MANDAL & CO. | 4.25 | 4.25 | 1
1802 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 150 mm dia. DI distribution main from near PH No-1 to N/H/O Prasanta Mondal, N/H/O Sudip Gayen to Chanchal Chatterjee & Sudip Gayen to Santanu Joardar for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2022-2023 | 1189/HSD | 13/07/2022 | 15 | R.K.MANDAL & CO. | 4.27 | 4.27 | 1
1803 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 100mm dia. DI distribution main from N/H/O Chanchal Chatterjee to N/H/O Kritanta Mondal & Biswajit Baidya for damage portion within Korakati w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000269/2022-2023 | 1191/HSD | 13/07/2022 | 10 | R.K.MANDAL & CO. | 2.17 | 2.17 | 1
1804 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from Joygram Bazar Idgah to near Pintu Molla Garage for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000317/2022-2023 | 1238/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 0 | 1
1805 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from Pintu Molla Garage to N/H/O Sahidul Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000319/2022-2023 | 1240/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 0 | 1
1806 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from Near Julfikar Molla shop to N/H/O Sariful Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000323/2022-2023 | 1244/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 3.39 | 0 | 1
1807 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from N/H/O Sahidul Molla to near Julfikar Molla shop for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2022-2023 | 1246/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 0 | 1
1808 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Korakati water supply scheme, Sandeshkhali-II Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2022-2023 | 2675/BD | 08/09/2022 | 90 | PATHIK PABAN NANDI | 274.1 | 265.59 | 1
1809 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works in different places for protection of different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile for Augmention of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000844/2023-2024 | 2680/BD | 04/09/2023 | 30 | ANKIT CONSTRUCTION | 66.88 | 0 | 82
1810 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000854/2023-2024 | 1041/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100
1811 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000855/2023-2024 | 1042/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0.9 | 100
1812 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other allied machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000856/2023-2024 | 1042-HSD. | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 0
1813 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentaion of Korakati water supply scheme, Sandeshkhali-II Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001253/2023-2024 | 4190/BD | 30/10/2023 | 465 | M/S K.B.ENTERPRISE. | 140.14 | 0 | 85
1814 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation for Korakati water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001290/2023-2024 | 1412/HSD | 06/11/2023 | 7 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0 | 59
1815 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion, protection works & other allied works in connection with Augmentation of Korakati w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001295/2024-2025 | 865/BD | 19/03/2025 | 360 | M/S K.B.ENTERPRISE. | 102.2 | 0 | 30
1816 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000046/2022-2023 | 2576/BD | 31/08/2022 | 0 | Resource Division | 6.15 | 0 | 0
1817 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000257/2022-2023 | 918/BD | 22/03/2023 | 0 | Resource Division | 10.9 | 0 | 0
1818 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 250 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000395/2024-2025 | 873/HSD | 07/08/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.95 | 0 | 100
1819 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, construction of 350 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap Connection in connection with Augmentation of Murarisha water supply scheme, Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000764/2023-2024 | 2591/BD | 28/08/2023 | 581 | S.S.ENTERPRISE. (BAMANGACHI) | 576.34 | 121.46 | 98
1820 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Withdrawing & relaying of 110 mm dia. UPVC pipe line from PH no- 1 towards Adibasi Sonali Sangha of Murarisha W/S Scheme,Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001293/2022-2023 | 378/HSD | 31/03/2023 | 10 | MD.SALIM GAZI. | 0.9 | 0.9 | 0
1821 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Withdrawing & relaying of 110 mm dia. UPVC pipe line from PH no- 1 towards Adibasi Sonali Sangha of Murarisha W/S Scheme,Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001348/2022-2023 | 378/HSD | 31/03/2023 | 10 | MD.SALIM GAZI. | 0.9 | 0 | 0
1822 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site in connection with Augmentation of Murarisha W/S scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001831/2023-2024 | 259/HSD | 06/03/2024 | 10 | S.S.ENTERPRISE. (BAMANGACHI) | 0.94 | 0 | 37
1823 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 150 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001837/2023-2024 | 268/HSD | 06/03/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.92 | 0 | 100
1824 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 200 mm dia DI pipeline at different places in connection with Augmentation of Murarisha w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001848/2023-2024 | 274/HSD | 06/03/2024 | 10 | NEW MANGES INDUSTRIAL CORPORATION | 0.95 | 0 | 80
1825 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2023-2024 | 4510/BD | 28/11/2023 | 0 | Resource Division | 18.1 | 0 | 0
1826 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000241/2022-2023 | 934/BD | 22/03/2023 | 0 | Resource Division | 27.49 | 0 | 0
1827 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at OHR site under Augmentation work at Malidah W/S Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000042/2025-2026 | 1541/BD | 15/05/2025 | 120 | NISHITH BANERJEE | 31.89 | 0 | 0
1828 | Barasat Division | Bangaon Sub-Division | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Malidah Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000774/2022-2023 | 3471/BD | 01/12/2022 | 90 | R.K.MANDAL & CO. | 243.9 | 167.03 | 100
1829 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying and repair of UPVC pipe and allied works in connection with Augmentation work at Malidah W/S Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000861/2024-2025 | 3386/BD | 03/12/2024 | 90 | VAI ENTERPRISE. | 11.41 | 0 | 100
1830 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repair and renovation works of 250cum capacity 20mtr. staging height R.C.C. over Head Reservoir for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000898/2024-2025 | 3404/BD | 04/12/2024 | 180 | PRABIR KUMAR MONDAL. | 7.9 | 0 | 100
1831 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 (two) nos. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Malidah Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001013/2023-2024 | 2830/BD | 15/09/2023 | 60 | DHELA BABA ENTERPRISE | 32.28 | 0 | 100
1832 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001452/2023-2024 | 4407/BD | 10/11/2023 | 60 | BHABANI ENTERPRISE. | 11.49 | 0 | 100
1833 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Malidah Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001486/2023-2024 | 4465/BD | 21/11/2023 | 23 | KAMAL HALDER. | 7.15 | 0 | 100
1834 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Malidah Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002785/2021-2022 | 140/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.74 | 3.72 | 1
1835 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Malidah water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002970/2021-2022 | 526/ BON | 01/11/2021 | 21 | TAPAN GHOSH. | 2.52 | 2.48 | 1
1836 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000115/2022-2023 | 3686/BD | 14/12/2022 | 0 | Resource Division | 12.95 | 0 | 0
1837 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000122/2022-2023 | 3712/BD | 15/12/2022 | 0 | Resource Division | 1.79 | 0 | 0
1838 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Bansjhari Mallikpur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000743/2022-2023 | 3341/BD | 16/11/2022 | 867 | UTPAL CONSTRUCTION & CO. | 227.32 | 169.23 | 90
1839 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000138/2022-2023 | 3813/BD | 23/12/2022 | 0 | Resource Division | 98.04 | 0 | 0
1840 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000154/2023-2024 | 4415/BD | 10/11/2023 | 0 | Resource Division | 9.24 | 0 | 0
1841 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion with protection work in connection with Augmentation of Dakshin Bhebia water supply scheme (Z-II), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001032/2024-2025 | 3623/BD | 20/12/2024 | 360 | H.I.ENTERPRISE. | 178.87 | 0 | 50
1842 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Surging and development of Big dia tubewell by Carrying out surging and back blowing of existing tube well including installation of suitable education pipes of adequate diameter upto required depth along with suitable airline pipes for injecting compressed air under pressure at the appropriates depth inside the tube well within Hasnabad Sub-Division PHE Dte. under Barasat Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2024-2025 | 172/BD | 15/01/2025 | 210 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 30.65 | 0 | 60
1843 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of 225 mm dia. UPVC pipe line due to construction of drain at Kharampur more within Dakshin Bhebia W/S Scheme (Z-II), Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001298/2023-2024 | 1420/HSD | 06/11/2023 | 523 | SARKAR ENTERPRISE | 0.92 | 0 | 100
1844 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000119/2023-2024 | 4173/BD | 30/10/2023 | 0 | Resource Division | 37.95 | 0 | 0
1845 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000166/2023-2024 | 4559/BD | 01/12/2023 | 0 | Resource Division | 74.49 | 0 | 0
1846 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000239/2022-2023 | 912/BD | 22/03/2023 | 0 | Resource Division | 163.73 | 0 | 0
1847 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03460/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 18.45 | 0 | 0
1848 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Arsula water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 1217/BD | 20/04/2023 | 860 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 667.97 | 133.09 | 55
1849 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Baduria Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001008/2024-2025 | 3553/BD | 16/12/2024 | 390 | PRITAM MUKHOPADHYAY. | 60.15 | 0 | 0
1850 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000019/2023-2024 | 1237/BD | 25/04/2023 | 0 | Resource Division | 141.41 | 0 | 0
1851 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000139/2023-2024 | 4425/BD | 10/11/2023 | 0 | Resource Division | 17.4 | 0 | 0
1852 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna programme within command area of Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000081/2022-2023 | 1492/BD | 25/05/2022 | 90 | M/S S.S.ENTERPRISE. (SOUTH) | 164.51 | 125.08 | 1
1853 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid different dia. UPVC/DI distribution pipeline at different places in Daudpur Mouza of Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000850/2023-2024 | 2658/BD | 01/09/2023 | 30 | M/S PROGATI ENTERPRISE. | 34.09 | 33.95 | 100
1854 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within laukhali mouza due to erosion of soil for heavy rain fall during monsoon season within Daudpur w/s scheme, Sandeshkhali-II block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 1055/HSD | 31/08/2023 | 10 | ABDUL ALIM MONDAL. | 0.97 | 0 | 100
1855 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of Additional 1 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001025/2024-2025 | 3580/BD | 18/12/2024 | 30 | SUBHAJIT SAHA | 31.69 | 0 | 0
1856 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column structure at head Work site within Daudpur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001305/2023-2024 | 4378/BD | 10/11/2023 | 90 | RAJPATH ENGINEERS-CO-OPERATIVE SOCIETY LTD. | 23.09 | 0 | 100
1857 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Nalkora water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000815/2022-2023 | 3588/BD | 08/12/2022 | 30 | SARKAR ENTERPRISE & CO. | 69.53 | 62.47 | 99
1858 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Nalkora W/S Scheme including increasing the height of back wash tank at Basirhat - I Block under Basirhat Sub Division, PHE Dte. Capacity - 10.81 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002026/2023-2024 | 920/BD | 15/03/2024 | 240 | MONDAL PRECISION PVT.LTD | 23.26 | 0 | 60
1859 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for NALKORA Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002858/2021-2022 | 202/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.79 | 2.61 | 1
1860 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000142/2022-2023 | 3819/BD | 23/12/2022 | 0 | Resource Division | 23.93 | 0 | 0
1861 | Barasat Division | Bangaon Sub-Division | Enhancement of GST for providing Functional Household Tap Connection (FHTC) in connection with JJM and Jal Swapna Programme within command area of Ghatpatila Zone-I WS Scheme | Assistant Engineer | Junior Engineer | BILL/00832/2024-2025 | BP-02024-25-262 | 12/09/2024 | 0 | H.I.ENTERPRISE. | 22.17 | 0 | 0
1862 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and Tube well connection under Augmentation work at Ghatpatila W/S Scheme (Zone - I), Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000078/2024-2025 | 1770/BD | 01/07/2024 | 315 | ROY CHOWDHURY CONSTRUCTION. | 22.88 | 0 | 100
1863 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Ghatpatila (Zone-I) water supply scheme (Head Work Site) under Bongaon Sub-Division P.H.E.Dte. Part-A | Assistant Engineer | Junior Engineer | ORD/000097/2023-2024 | 1548/BD | 22/05/2023 | 30 | SAHA CONSTRUCTION & CO | 16.16 | 0 | 100
1864 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order forSinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer at Ghatpatila (Zone-I) water supply scheme (2nd T/W Site) under Bongaon Sub-Division P.H.E.Dte.-- Part- B | Assistant Engineer | Junior Engineer | ORD/000098/2023-2024 | 1547/BD | 22/05/2023 | 30 | SAHA CONSTRUCTION & CO | 16.17 | 0 | 100
1865 | Barasat Division | Bangaon Sub-Division | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Ghatpatila Zone-I Water Supply Scheme in Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000775/2022-2023 | 3469/BD | 01/12/2022 | 90 | H.I.ENTERPRISE. | 471.66 | 413.3 | 0
1866 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Ghatpatila (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001454/2023-2024 | 4408/BD | 10/11/2023 | 60 | ONKAR ENTERPRISE. | 11.79 | 0 | 100
1867 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Ghatpatila (Zone-I) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001487/2023-2024 | 4464/BD | 21/11/2023 | 23 | KAMAL HALDER. | 6.86 | 0 | 60
1868 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Ghatpatila (Zone-I) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002929/2021-2022 | 539/Bon | 03/11/2021 | 21 | ROY CHOWDHURY CONSTRUCTION. | 2.52 | 2.49 | 1
1869 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000116/2022-2023 | 3687/BD | 14/12/2022 | 0 | Resource Division | 7.03 | 0 | 0
1870 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000123/2022-2023 | 3710/BD | 15/12/2022 | 0 | Resource Division | 18.47 | 0 | 0
1871 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000154/2022-2023 | 1255/BD | 25/04/2023 | 0 | Resource Division | 73.62 | 0 | 0
1872 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Chowberia Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000352/2024-2025 | 2418/BD | 23/08/2024 | 420 | M/S B.K.ENTERPRISE. | 35.07 | 0 | 100
1873 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Chowberia Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000788/2022-2023 | 3546/BD | 06/12/2022 | 90 | M/S B.K.ENTERPRISE. | 279.32 | 227.89 | 1
1874 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chauberia water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000795/2023-2024 | 2695/BD | 04/09/2023 | 30 | DHELA BABA ENTERPRISE | 16.17 | 0 | 100
1875 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Chauberia Water Supply Scheme (H/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001110/2023-2024 | 2923/BD | 26/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.14 | 0 | 100
1876 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall aand Construction of Approach Road at 1st T/W site under Augmentation of Chauberia water Supply scheme, Bongaon Block within jurisdiction of Bongaon Sub-Division, under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001499/2023-2024 | 4485/BD | 23/11/2023 | 23 | TAPAN GHOSH. | 5.58 | 0 | 100
1877 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Chauberia Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/001564/2023-2024 | 53/BD | 05/01/2024 | 420 | TAPAN GHOSH. | 6.03 | 0 | 100
1878 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Chowberia Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002788/2021-2022 | 127/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.45 | 3.43 | 1
1879 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Chowberia water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/003000/2021-2022 | 532/Bon | 03/11/2021 | 21 | A.D.ENTERPRISE. | 2.52 | 2.51 | 1
1880 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2022-2023 | 3662/BD | 13/12/2022 | 0 | Resource Division | 14 | 0 | 0
1881 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000111/2022-2023 | 3689/BD | 14/12/2022 | 0 | Resource Division | 124.58 | 0 | 0
1882 | Barasat Division | Bangaon Sub-Division | Connection of 2 nos. newly sunk Replaced Tube well with rising main by DI pipe and I.E.P. back wash pipe line with UPVC pipe, Construction of Valve Chamber and Inspection pit and repairing Air-Blower and Air-Compressor of existing I.E.P. due to submerged in water during moon soon for Augmentation of Ramnagar W/S Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000398/2025-2026 | 815/Bon | 26/06/2025 | 45 | A.D.ENTERPRISE. | 4.96 | 0 | 0
1883 | Barasat Division | Bangaon Sub-Division | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Ramnagar Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000766/2022-2023 | 3472/BD | 01/12/2022 | 90 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 200.08 | 199.57 | 1
1884 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ramnagar water supply scheme at Head Work Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000778/2023-2024 | 2685/BD | 04/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.17 | 0 | 100
1885 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Replacement of Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ramnagar water supply scheme at 2nd T/W Site under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000793/2023-2024 | 2684/BD | 04/09/2023 | 30 | SAHA CONSTRUCTION & CO | 16.17 | 0 | 100
1886 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Ramnagar Water Supply Scheme in Gaighata Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001350/2021-2022 | 146/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.98 | 2.98 | 1
1887 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing of Boundary wall at Head Work site, Construction of Boundary wall at 2nd Pump House site and Construction of Approach Road at Head Work site and 2nd T/W Site under Augmentation of Ramnagar Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001748/2023-2024 | 565/BD | 22/02/2024 | 45 | JP CONSTRUCTION & SUPPLIERS. | 12.84 | 0 | 100
1888 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Ramnagar Water Supply Scheme, Gaighata Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001786/2023-2024 | 630/BD | 28/02/2024 | 45 | GHOSH CONSTRUCTION | 5.97 | 0 | 100
1889 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02No. Pump House and allied works at Ramnagar water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002904/2021-2022 | 541/BON | 03/11/2021 | 21 | MA CONSTRUCTION. | 2.52 | 2.47 | 1
1890 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000096/2022-2023 | 3663/BD | 13/12/2022 | 0 | Resource Division | 7.98 | 0 | 0
1891 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000117/2022-2023 | 3691/BD | 14/12/2022 | 0 | Resource Division | 12.68 | 0 | 0
1892 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Iron Elimination Plant at Taranipur zone - I W/S Scheme (50.0 m3/hr) at Swarupnagar Block and Akhipur W/S Scheme (33.375m3/hr) at Basirhat - II Block under Basirhat Sub division, PHE Dte of Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2025-2026 | 2022/BD | 18/06/2025 | 120 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 19.65 | 0 | 70
1893 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Balance work of Providing FHTC (Functional Household Tap Connection) by Augmentation For Akipur Water Supply Scheme in Basirhat-II Block of North 24 Parganas District within Basirhat Sub-Division under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2025-2026 | 2000/BD | 17/06/2025 | 360 | M/S MITRA CONSTRUCTION. | 56.17 | 0 | 0
1894 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Akipur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000749/2022-2023 | 3374/BD | 18/11/2022 | 90 | SUPER SKILL. | 145.01 | 23.53 | 50
1895 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Balance FHTC works and Eucalyptus Bullah Pilling with earth filling in different location for protection of DI / UPVC distribution Pipe line for Augmentation of Akipur water supply scheme in Basirhat - II Block under Basirhat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001760/2023-2024 | 512/BD | 20/02/2024 | 30 | SUPER SKILL. | 41.71 | 0 | 0
1896 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000002/2023-2024 | 1100/BD | 06/04/2023 | 0 | Resource Division | 11.42 | 0 | 0
1897 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2022-2023 | 2309/BD | 03/08/2022 | 0 | Resource Division | 11.42 | 0 | 0
1898 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC Distribution System pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Sankarpur water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000820/2022-2023 | 3602/BD | 09/12/2022 | 923 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 459.43 | 254.12 | 76
1899 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Basirhat I Block under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001036/2024-2025 | 3626/BD | 20/12/2024 | 180 | NISHITH BANERJEE | 45.36 | 0 | 100
1900 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Iron Elimination Plant at Shankarpur W/S Scheme at Basirhat- I Block under Basirhat Sub division, PHE Dte. Capacity- 93.0625 m3/hr. | Assistant Engineer | Junior Engineer | ORD/002036/2023-2024 | 922/BD | 15/03/2024 | 60 | NEER UDYOG | 16.57 | 0 | 80
1901 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000141/2023-2024 | 4420/BD | 10/11/2023 | 0 | Resource Division | 9.36 | 0 | 0
1902 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000163/2022-2023 | 490/BD | 17/02/2023 | 0 | Resource Division | 89.49 | 0 | 0
1903 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000182/2022-2023 | 604/BD | 23/02/2023 | 0 | Resource Division | 9.83 | 0 | 0
1904 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Kalil Khal N/H/O Rajjack Molla (Between node point 101 to 294) for Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000009/2024-2025 | 1528/BD | 07/06/2024 | 271 | RUDRA DAS. | 9.89 | 0 | 85
1905 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Jhikra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000138/2023-2024 | 1704/BD | 08/06/2023 | 1086 | M/S NIRMAN CONSTRUCTION. | 403.64 | 0 | 80
1906 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Jhikra W/S scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000309/2024-2025 | 879/HSD | 07/08/2024 | 10 | M/S NIRMAN CONSTRUCTION. | 0.75 | 0 | 100
1907 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Pankaj Mondal at Jhikra Majher para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000988/2024-2025 | 3642/BD | 23/12/2024 | 120 | GAZI ENTERPRISE | 9.32 | 0 | 100
1908 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at near Jhikra Radhagobinda Mandir at Jhikra Purba para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000989/2024-2025 | 3465/BD | 09/12/2024 | 30 | STAR CONSTRUCTION. | 9.41 | 0 | 0
1909 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for protection of newly laid UPVC distribution pipe line at N/H/O Utpal Mondal at Jhikra Paschim para within Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000991/2024-2025 | 3676/BD | 24/12/2024 | 30 | A. M. ENTERPRISE (BASIRHAT) | 9.06 | 0 | 0
1910 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of RCC culvert, cut-off wall, approach road and other allied works at Over Head Reservoir site (HW site) for Jhikra w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001814/2023-2024 | 677/BD | 01/03/2024 | 14 | NURJAHAN ENTERPRISE. | 8.5 | 0 | 86
1911 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with column structure at Head Work site (PH No-1) & PH No- 2 within Jhikra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002264/2024-2025 | 1027/BD | 28/03/2025 | 90 | M/S NIRMAN CONSTRUCTION. | 31.11 | 0 | 0
1912 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002715/2021-2022 | 278/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
1913 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002716/2021-2022 | 279/HSD | 09/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.46 | 1.46 | 1
1914 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002996/2021-2022 | 279/HSD | 09/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.46 | 0 | 1
1915 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (JHIKRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002997/2021-2022 | 278/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 0 | 1
1916 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000220/2022-2023 | 873/BD | 22/03/2023 | 0 | Resource Division | 17.57 | 0 | 0
1917 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.- 1 (Defunct tube well site) with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Rupmari w/s scheme (Zone-V), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2022-2023 | 1750/BD | 20/06/2022 | 30 | M/S K.P.PAL. | 21.33 | 13.02 | 1
1918 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000077/2022-2023 | 2991/BD | 29/09/2022 | 0 | Resource Division | 0.2 | 0 | 0
1919 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000193/2022-2023 | 678/BD | 01/03/2023 | 0 | Resource Division | 24.64 | 0 | 0
1920 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at P.H. No.-1 (Size-5.40 x 3.60 mtr.) & P.H. No.-2 (Size-3.60 x 3.00 mtr.) for Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000146/2023-2024 | 1706/BD | 08/06/2023 | 1096 | MONDAL & CO. (BASIRHAT). | 462.55 | 0 | 86
1921 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Arrangement Of Block Level Orientation programe involving stakeholders of PRI bodies including refreshments, training materials and related activities for 1 no Block (Minakhan) in North 24 Parganas under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2024-2025 | 756/HSD | 19/07/2024 | 10 | IMAGIN | 0.49 | 0 | 100
1922 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Bamanpukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000416/2024-2025 | 2736/BD | 20/09/2024 | 300 | M.R.CONSTRUCTION. | 130.43 | 0 | 70
1923 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Bamanpukuria & Khariberia w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001500/2024-2025 | 635/BD | 28/02/2025 | 45 | ACME CONSTRUCTION | 51.71 | 0 | 0
1924 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BAMANPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002703/2021-2022 | 246/HSD | 03/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.99 | 3.99 | 1
1925 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BAMANPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002704/2021-2022 | 245/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
1926 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000205/2022-2023 | 887/BD | 22/03/2023 | 0 | Resource Division | 17.54 | 0 | 0
1927 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03471/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 24.25 | 0 | 0
1928 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Bithari Zone-II A water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000136/2023-2024 | 1710/BD | 08/06/2023 | 629 | UTPAL CONSTRUCTION & CO. | 234.15 | 0 | 50
1929 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 330 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Bithari Zone-IIB water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000977/2023-2024 | 2801/BD | 12/09/2023 | 30 | DHELA BABA ENTERPRISE | 23.31 | 0 | 0
1930 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Bithari Z-II Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/002966/2021-2022 | 452/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.75 | 4.75 | 1
1931 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for BITHARI ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002967/2021-2022 | 453/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.63 | 0.63 | 1
1932 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2023-2024 | 1263/BD | 25/04/2023 | 0 | Resource Division | 52.64 | 0 | 0
1933 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000142/2023-2024 | 4427/BD | 10/11/2023 | 0 | Resource Division | 23.94 | 0 | 0
1934 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Mohanpur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000973/2021-2022 | 2140/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.77 | 4.77 | 1
1935 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Mohanpur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000974/2021-2022 | 2141/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.33 | 2.32 | 1
1936 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Sandeshkhali Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000975/2021-2022 | 2148/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.92 | 3.92 | 1
1937 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Sandeshkhali Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000976/2021-2022 | 2149/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 1.17 | 1.17 | 1
1938 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Shankarpur Supply Scheme at Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001842/2020-2021 | 488/BD. | 26/02/2021 | 90 | UMWELT ENGINEER PVT.LTD. | 96.9 | 27.67 | 1
1939 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SANKARPUR Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001936/2021-2022 | 192/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.24 | 4.24 | 1
1940 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Debitala w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000137/2023-2024 | 1703/BD | 08/06/2023 | 911 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 399.18 | 140.46 | 86
1941 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection of different dia. UPVC pipeline by UC bullah & Bamboo pile at diff. places and emergent restoration of road at HW site in Debitala w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001034/2024-2025 | 3624/BD | 20/12/2024 | 180 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 147.18 | 0 | 85
1942 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection within Debitala water supply scheme , Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001883/2024-2025 | 528/HSD | 10/03/2025 | 10 | SARKAR ENTERPRISE | 0.72 | 0 | 0
1943 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BARGAN GOPALPUR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002705/2021-2022 | 248/HSD | 03/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 3.2 | 3.2 | 1
1944 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DEBITALA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002709/2021-2022 | 272/HSD | 09/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.82 | 4.82 | 1
1945 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DEBITALA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002710/2021-2022 | 273/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.48 | 2.48 | 1
1946 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000212/2022-2023 | 895/BD | 22/03/2023 | 0 | Resource Division | 27.76 | 0 | 0
1947 | Barasat Division | Habra Sub-Division | Formal work order for Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zonal Head work site - XIV i.e. Kumra /Zonal Head work site - XVI i.e.Nangla including Laying Distribution System within the jurisdiction of (Zone-XIV) /(Zone-XVI), Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project within Barasat Division, P.H.E. Dte. Habra-I Block PART-C / Habra-I Block PART-E. | Assistant Engineer | Junior Engineer | ORD/001613/2023-2024 | 110/BD | 10/01/2024 | 910 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3691.85 | 0 | 88
1948 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XXI) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001162/2023-2024 | 2953/BD | 29/09/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1791.33 | 0 | 85
1949 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution system, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain, Land development and other allied works and Providing FHTC within the jurisdiction of (Zone-XIX) under Habra-Gaighata surface based PWSS of Gaighata Block under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001161/2023-2024 | 2954/BD | 29/09/2023 | 721 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1879.95 | 0 | 95
1950 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for construction of 5 nos. different capacity OHR, Land development, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at different Zonal Head work site including Laying Distribution System and FHTC of surface based water supply scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2023-2024 | 2714/BD | 05/09/2023 | 1095 | S & P ENTERPRISE | 5112.52 | 0 | 40
1951 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of Distribution System, Providing FHTC, Construction of Office cum Guard room, Land development and Switch cum Chlorine Room, Boundary wall, Surface drain and other allied works within the jurisdiction of (Zone-XX) i.e. Matikumra / (Zone-XXII) i.e. Chikanpara under Habra-Gaighata surface based PWSS, of Gaighata Block under Barasat Division, P.H.E. Dte. GAIGHATA BLOCK, PART-B / Gaighata Block, PART-D | Assistant Engineer | Junior Engineer | ORD/001214/2023-2024 | 4073/BD | 16/10/2023 | 730 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2790.09 | 0 | 88
1952 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 No. 400.00 mtr. Deep 100 X 50 mm. dia. Trial-cum-production Tube well fitted with Indian Mark - II pump with PVC pipe and strainers at T/W site-1 for Bhanderkhali w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2025-2026 | 845-HSD | 19/05/2025 | 10 | M/S NIRMAN CONSTRUCTION. | 4.15 | 0 | 0
1953 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No- 2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Bhandarkhali water supply scheme, Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000725/2023-2024 | 2512/BD | 22/08/2023 | 366 | M/S NIRMAN CONSTRUCTION. | 521.98 | 0 | 60
1954 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Bhanderkhali w/s scheme, Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001983/2023-2024 | 918/BD | 15/03/2024 | 60 | SAHA CONSTRUCTION & CO | 77.65 | 0 | 0
1955 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BHANDARKHALI Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002693/2021-2022 | 235/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
1956 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BHANDARKHALI Water Supply Scheme) in HINGALGANJ BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002694/2021-2022 | 236/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
1957 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000231/2022-2023 | 869/BD | 22/03/2023 | 0 | Resource Division | 45.98 | 0 | 0
1958 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Bargan Gopalpur w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000147/2023-2024 | 1707/BD | 08/06/2023 | 732 | M/S PROGATI ENTERPRISE. | 403.93 | 160.21 | 100
1959 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Strengthening of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No-1 within Bargan Gopalpur w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000880/2023-2024 | 2715/BD | 05/09/2023 | 10 | PRITAM MUKHOPADHYAY. | 8.46 | 0 | 100
1960 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Strengthening of existing concrete road for movement of rig machineries for sinking of big dia Tube well at PH No 2 within Bargan Gopalpur w/s scheme, Minakhan block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000910/2023-2024 | 2732/BD | 07/09/2023 | 7 | GIRIDHARI DAS | 5 | 0 | 100
1961 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (BARGAN GOPALPUR Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002702/2021-2022 | 247/HSD | 03/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 0
1962 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000204/2022-2023 | 890/BD | 22/03/2023 | 0 | Resource Division | 46.13 | 0 | 0
1963 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03467/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 40.09 | 0 | 0
1964 | Barasat Division | Basirhat Sub-Division | Formal work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Taranipur Water Supply Scheme Zone - II at Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2022-2023 | 1176/BD | 19/04/2022 | 90 | UTPAL CONSTRUCTION & CO. | 137.41 | 25.64 | 13
1965 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Taranipur Zone-II water supply scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000038/2023-2024 | 1353/BD | 04/05/2023 | 676 | M/S JAYDEEP DASGUPTA | 159.14 | 75.39 | 56
1966 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Taranipur zone - II W/S Scheme including increasing the height of back wash water tank at Swarupnagar Block under Basirhat Sub Division, PHE Dte. Capacity- 50.00 Cum/hr. | Assistant Engineer | Junior Engineer | ORD/002023/2023-2024 | 894/BD | 15/03/2024 | 60 | M/S R.K. ENTERPRISE | 18.02 | 0 | 0
1967 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for TARANIPUR ZONE -2 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002513/2021-2022 | 447 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.4 | 3.4 | 1
1968 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2023-2024 | 1261/BD | 25/04/2023 | 0 | Resource Division | 17.18 | 0 | 0
1969 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method at Pump House 2 using PVC pipe & strainer having 300 mm Dia 42 mtr. long Housing Pipe and 200mm Dia 30 mtr. long filter for Augmentation of Eojnagar Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000769/2024-2025 | 3257/BD | 25/11/2024 | 90 | GHOSH CONSTRUCTION. | 21.75 | 0 | 0
1970 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Eojnagar water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000823/2022-2023 | 3603/BD | 09/12/2022 | 990 | KINGS & CO. | 361.31 | 257.81 | 74
1971 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000164/2022-2023 | 488/BD | 17/02/2023 | 0 | Resource Division | 57.91 | 0 | 0
1972 | Barasat Division | Basirhat Sub-Division | Restoration of sub-base of bituminous road from Node 68 to 63 to 50 to 48 to 34 to 32 to 21 in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000062/2024-2025 | 917/BHTSD | 24/05/2024 | 7 | M/S MAA TARA ENTERPRISE | 0.92 | 0 | 100
1973 | Barasat Division | Basirhat Sub-Division | Restoration of sub-base of bituminous road from Node 40 to 2 to 65 to 62 to 68 in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000063/2024-2025 | 918/BHTSD | 24/05/2024 | 7 | M/S MAA TARA ENTERPRISE | 0.64 | 0 | 100
1974 | Barasat Division | Basirhat Sub-Division | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Chak Farasatpur Mouza between Node Number 124 & 126 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of piling work = 32 m) | Assistant Engineer | Junior Engineer | ORD/000084/2024-2025 | 937/BHTSD | 24/05/2024 | 7 | TAJMAHAL ENTERPRISE | 0.98 | 0 | 100
1975 | Barasat Division | Basirhat Sub-Division | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Chak Farasatpur Mouza between Node Number 123 & 124 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 33) | Assistant Engineer | Junior Engineer | ORD/000087/2024-2025 | 938/BHTSD | 24/05/2024 | 7 | PRASANTA KUMAR PAUL. | 0.98 | 0 | 0
1976 | Barasat Division | Basirhat Sub-Division | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Ramnarayanpur Mouza between Node Number 27 & 29 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 30) | Assistant Engineer | Junior Engineer | ORD/000089/2024-2025 | 939/BHTSD | 24/05/2024 | 7 | J.D.ENTERPRISE. (BASIRHAT) | 0.91 | 0 | 0
1977 | Barasat Division | Basirhat Sub-Division | Eucalyptus Bullah Piling for Emergency protection Work of Pipe line at Ramnarayanpur Mouza between Node Number 27 & 28 of Gobindapur Dhokra Water Supply Scheme under Basirhat Sub Division under Barasat Division P.H.E. Dte. (Length of Piling Work = 24) | Assistant Engineer | Junior Engineer | ORD/000091/2024-2025 | 940/BHTSD | 24/05/2024 | 7 | SELIM GAZI. | 0.73 | 0 | 100
1978 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 711 to 718, 542 to 546, 552 to 554 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2024-2025 | 1165/BHTSD | 30/07/2024 | 15 | SWADESH MONDAL. | 0.95 | 0 | 100
1979 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 549 to 551, 511 to 538, 575 to 579 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000442/2024-2025 | 1166/BHTSD | 30/07/2024 | 15 | PRASANTA KUMAR PAUL. | 0.97 | 0 | 100
1980 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 82 to 84, 84 to 86, 725 to 726, 545 to 549, 546 to 552 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000443/2024-2025 | 1167/BHTSD | 30/07/2024 | 15 | M/S MAA TARA ENTERPRISE | 0.99 | 0 | 100
1981 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 72 to 80 to 81, 73 to 74, 80 to 82, 538 to 539, 736 to 737 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2024-2025 | 1168/BHTSD | 30/07/2024 | 15 | MD AMIRUL MOLLA. | 0.98 | 0 | 100
1982 | Barasat Division | Basirhat Sub-Division | Repair of OHR & Pump House and emergency repairing of pipeline in Gobindapur Dhokra W/S Scheme Under Basirhat Sub-Division P.H.E. Dte.Under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000447/2024-2025 | 1170/BHTSD | 30/07/2024 | 15 | SELIM GAZI. | 0.95 | 0 | 100
1983 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 293 to 295, 101 to 422) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000448/2024-2025 | 1161/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.95 | 0 | 100
1984 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 230 to 230A, 293 to 294, 232 to 233) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000449/2024-2025 | 1162/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.9 | 0 | 100
1985 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 266A to 266B, 276 to 277, 290 to 293) of Gobindapur Dhokra pwss under Basirhat Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000450/2024-2025 | 1163/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.78 | 0 | 100
1986 | Barasat Division | Basirhat Sub-Division | Repair of damaged concrete road due to laying of pipe line in various place (node 129 to 130, 291 to 296, 509 to 507, 503 to 507, 571 to 573, 573 tp 575, 554 to 555, 65 to 66, 456 to 457 ) of Gobindapur Dhokra pwss under Basirhat to Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000455/2024-2025 | 1164/BHTSD | 30/07/2024 | 15 | MALLICK ENTERPRISE | 0.95 | 0 | 100
1987 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur Dhokra water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001009/2022-2023 | 172/BD | 19/01/2023 | 90 | M/S MALLICK ENTERPRISE | 373.91 | 275.7 | 100
1988 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOBINDAPUR DHOKRA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002781/2021-2022 | 205/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.86 | 3.77 | 1
1989 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2023-2024 | 1062/BD | 04/04/2023 | 0 | Resource Division | 53.92 | 0 | 0
1990 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method at PH No.- 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Durgapur Baylani w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000002/2023-2024 | 1097/BD | 06/04/2023 | 30 | M/S RAJPATH CONSTRUCTION. | 21.46 | 16.98 | 0
1991 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Durgapur Baylani water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000947/2022-2023 | 89/BD | 11/01/2023 | 90 | M/S DATTA ENTERPRISE. | 349.57 | 348.44 | 0
1992 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 300 cum capacity 20 mtr staging height R.C.C Over Head Reservoir as per Deptt. design, drawing & specification including bored pile with pile cap for Augmentation of Durgapur Baylani water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001095/2023-2024 | 3021/BD | 05/10/2023 | 365 | ABDUL ALIM MONDAL. | 122.76 | 0 | 100
1993 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection for the leftout portion at Kakaria, Dhanikhali & Paschim Khejurberia Mouza in connection with Augmentation of Durgapur Baylani water supply scheme (Z- II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001313/2024-2025 | 159/HSD | 27/01/2025 | 10 | PRASANTA MITRA. | 0.92 | 0 | 100
1994 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000174/2022-2023 | 521/BD | 20/02/2023 | 0 | Resource Division | 138.01 | 0 | 0
1995 | Barasat Division | Barasat Sadar Sub-Division | Restoration works | Assistant Engineer | Junior Engineer | BILL/00743/2024-2025 | BP-2024-25-240 | 06/09/2024 | 0 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 16.77 | 0 | 0
1996 | Barasat Division | Barasat Sadar Sub-Division | Restoration works | Assistant Engineer | Junior Engineer | BILL/00744/2024-2025 | BP-2024-25-240 | 06/09/2024 | 0 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 2.8 | 0 | 0
1997 | Barasat Division | Barasat Sadar Sub-Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur Chandigarh Mouza (Part) within Humaipur Water Supply Scheme at Barasat II Block under Barasat Division, PHE Dte. Part-I Sl.No.4 | Assistant Engineer | Junior Engineer | ORD/000789/2020-2021 | 171/BSD | 18/02/2021 | 14 | ANJALI ENTERPRISE. | 2.18 | 1.91 | 1
1998 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur Chandigarh Mouza (Part-I), and Dariala, Birpur, Banspol mouzas within Humaipur Water Supply Scheme at Barasat II Block under Barasat Division, PHE Dte. Part-A(Phase-II). | Assistant Engineer | Junior Engineer | ORD/001121/2021-2022 | 182/BD | 20/01/2022 | 45 | MONDAL ENTERPRISE. (BARASAT) | 88.28 | 86.9 | 1
1999 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2021-2022 | 2239/BD | 24/11/2021 | 0 | Resource Division | 10.26 | 0 | 0
2000 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000102/2022-2023 | 3664/BD | 13/12/2022 | 0 | Resource Division | 2.09 | 0 | 0
2001 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Hariharpur Water Supply Scheme in Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001333/2021-2022 | 133/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.14 | 3.14 | 1
2002 | Barasat Division | Hasnabad Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Durgamandop Water Supply scheme Sandeshkhali-II Block under Hasnabad Sub-Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000481/2021-2022 | 1739/BD | 14/09/2021 | 45 | M/S B.K.ENTERPRISE. | 77.69 | 77.6 | 1
2003 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001018/2023-2024 | 1062/HSD | 31/08/2023 | 10 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0.97 | 100
2004 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for construction of additional 1 no. switch room cum chlorine room (5.40x3.60) with sanitary and water supply arrangement including plinth protection for augmentation of Durgamandop w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001440/2024-2025 | 110/BD | 09/01/2025 | 75 | MD.SALIM GAZI. | 11.68 | 0 | 0
2005 | Barasat Division | Habra Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Kamarpur & its adjoining mouzas Water Supply Scheme at Habra-II Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000754/2021-2022 | 2390/BD | 09/12/2021 | 45 | SHIBU BISWAS. | 53.39 | 50.82 | 1
2006 | Barasat Division | Habra Sub-Division | Route Survey, Design Drawing & DPR Preparation for Bergum W/S Scheme within the jurisdiction of the Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000970/2021-2022 | 571/HAB | 23/12/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.71 | 4.71 | 1
2007 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Dakshin Bhebia Zone-II Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001001/2021-2022 | 2181/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.93 | 3.93 | 1
2008 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) from existing distribution system at Bergum Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte.( For balance work of Retrofitting). | Assistant Engineer | Junior Engineer | ORD/000837/2022-2023 | 3582/ BD | 08/12/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.19 | 15.18 | 1
2009 | Barasat Division | Habra Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Bergum Water Supply Scheme at Habra-I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, PHE Dte. (Phase-I). | Assistant Engineer | Junior Engineer | ORD/000864/2021-2022 | 2484/BD | 17/12/2021 | 1890 | UNICON INDIA. | 163.67 | 123.7 | 100
2010 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Chaital Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000967/2021-2022 | 2164/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.49 | 4.48 | 1
2011 | Barasat Division | Habra Sub-Division | Continuation work order for Hiring Diesel Luxury Car on Daily basis (for 6 months from 01.04.2023 to 30.06.2023) for the office use of the Executive Engineer, Barasat Division, PHE Dte | Assistant Engineer | Junior Engineer | ORD/001306/2022-2023 | 1044/BD | 31/03/2023 | 91 | MADHAB CHANDRA DAS | 0.45 | 0 | 100
2012 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2021-2022 | 250/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
2013 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Nityanandakati Balti Water Supply Scheme at Swarupnagar Block under Barasat Division, PHE Dte. (Phase I) | Assistant Engineer | Junior Engineer | ORD/000830/2021-2022 | 2460/BD | 15/12/2021 | 45 | SHIBU BISWAS. | 66.16 | 65.92 | 1
2014 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Monipur Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000954/2021-2022 | 2150/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
2015 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Durgamondop Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000994/2021-2022 | 2175/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.15 | 4.15 | 1
2016 | Barasat Division | Basirhat Sub-Division | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Gobindapur Water Supply Scheme at Baduria Block, Dist- North 24 Parganas under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000822/2021-2022 | 2438/BD | 13/12/2021 | 90 | UTPAL CONSTRUCTION & CO. | 224.17 | 222.04 | 1
2017 | Barasat Division | Basirhat Sub-Division | Continuation work order for the work of Hiring Diesel Luxury Car on daily basis (for 6months from 01-01-2022 to 30-06-2022) for the Office of the Assistant Engineer (HQ), Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001167/2021-2022 | 2686/BD | 31/12/2021 | 181 | M/S SAMIT CHANDRA DEY. | 0.86 | 0.8 | 1
2018 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for MAMINPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001954/2021-2022 | 305/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 0 | 1
2019 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BITHARI ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002508/2021-2022 | 450 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 0 | 1
2020 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DOBILA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002511/2021-2022 | 449 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 0 | 1
2021 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GOKULPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002512/2021-2022 | 448 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.32 | 0 | 1
2022 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for TARANIPUR ZONE -1 Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002514/2021-2022 | 446 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 1
2023 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for KAPILESWARPUR Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002515/2021-2022 | 445 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.04 | 0 | 1
2024 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BARA BANKRA Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002519/2021-2022 | 441 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.57 | 0 | 1
2025 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for NITYANANDAKATI BALTI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002520/2021-2022 | 440 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 0 | 1
2026 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2022-2023 | 2859/BD | 21/09/2022 | 0 | Resource Division | 27.73 | 0 | 0
2027 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection(FHTC) from existing and new proposed distribution system within the command area of Debog Water Supply Scheme at Basirhat - I Block under Barasat Division, PHE Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/001143/2021-2022 | 222/BD | 24/01/2022 | 45 | J.D.J.ENTERPRISE. (TRADERS PVT.LTD) | 91.48 | 35.12 | 1
2028 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for DEBHOG Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001935/2021-2022 | 191/BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.7 | 3.6 | 1
2029 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000066/2022-2023 | 2339/BD | 26/09/2022 | 0 | Resource Division | 61.51 | 0 | 0
2030 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001070/2021-2022 | 94/BD | 17/01/2022 | 45 | MONDAL & CO. (BASIRHAT). | 80.01 | 79.76 | 1
2031 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001178/2021-2022 | 251/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.62 | 4.62 | 1
2032 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new UPVC pipe line within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001179/2021-2022 | 252/HSD | 07/02/2022 | 7 | MONDAL & CO. (BASIRHAT). | 2.06 | 0 | 1
2033 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of 75 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2021-2022 | 254/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.54 | 4.54 | 1
2034 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of 50 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001182/2021-2022 | 255/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.54 | 4.54 | 1
2035 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Laying of 63 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001720/2021-2022 | 257/HSD | 07/02/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.52 | 4.52 | 1
2036 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Kalitala Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001000/2021-2022 | 2180/HSD | 28/12/2021 | 21 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 2.52 | 2.52 | 1
2037 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & DPR Preparation for Panchita Water Supply Scheme under Bongaon Sub-Division, under Barasat Division,PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001119/2021-2022 | 613/Bon | 31/12/2021 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 3.8 | 1
2038 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAGDAH Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/002056/2021-2022 | 990/BD. | 27/05/2021 | 45 | UMWELT ENGINEER PVT.LTD. | 89.35 | 7.1 | 1
2039 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Additional Survey Work For DPR Preparation of Kaniakati Kathalberia Zone I/A & Zone I/B Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002089/2021-2022 | 2145/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.99 | 1.96 | 1
2040 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order Route Survey, Design Drawing & DPR Preparation for Kaniakati Kathalberia Zone I/A & Zone I/B Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002090/2021-2022 | 2144/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.76 | 1
2041 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kaniakati Kathalberia Zone II/A & Zone II/B Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002091/2021-2022 | 2142/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 4.73 | 1
2042 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order Additional Survey Work For DPR Preparation of Kaniakati Kathalberia Zone II/A & Zone II/B Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002092/2021-2022 | 2143/HSD | 28/12/2021 | 21 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.21 | 2.19 | 1
2043 | Barasat Division | Habra Sub-Division | Enhancement of GST for the work providing FHTC for Augmentation of Maslandapur (Zone-I) W/S Scheme | Assistant Engineer | Junior Engineer | BILL/00274/2024-2025 | BP-2024-25-778 | 10/07/2024 | 0 | UMWELT ENGINEER PVT.LTD. | 25.55 | 0 | 0
2044 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 no. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Head Work Site of Maslandapur water supply scheme (Zone - I) within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000046/2023-2024 | 1409/BD | 08/05/2023 | 30 | NADIA TUBEWELLS | 14.49 | 0 | 100
2045 | Barasat Division | Habra Sub-Division | Acceptance cum work order for repairing of Boundary Wall in the Head Work site of Maslandapur I Piped water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000165/2024-2025 | 1800/BD | 01/07/2024 | 135 | NEW MA TARA ENTERPRISE. | 5.94 | 0 | 100
2046 | Barasat Division | Habra Sub-Division | Acceptance cum work order for construction of the Boundary wall in Pump House No 2 & Pump House No. 3 of Maslandapur- I Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000166/2024-2025 | 1801/BD | 01/07/2024 | 45 | ANJALI CONSTRUCTION. | 6.11 | 0 | 0
2047 | Barasat Division | Habra Sub-Division | Acceptance cum work order for construction of the Service Road (88.00 Mtr. Length & 3.00 Mtr. Wide while 1.00 Mtr. wide road already existing) in Head Work Site of Maslandapur- I Piped Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000167/2024-2025 | 2209/BD | 06/08/2024 | 15 | PUSPA CONSTRUCTION. | 5.6 | 0 | 0
2048 | Barasat Division | Habra Sub-Division | Repair and renovation of High Lift Pump House, Clorine Room and CWR in the Head Work site of Maslandapur I Piped water supply scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000197/2024-2025 | 690/HAB | 24/07/2024 | 105 | TALUKDER & CO. | 4.13 | 0 | 100
2049 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Maslandapur Water Supply Scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000618/2022-2023 | 2720/BD | 14/09/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 512.52 | 480.61 | 1
2050 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 2 & 3 for Augmentation of Maslandapur (Zone - I) water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000954/2023-2024 | 2773/BD | 11/09/2023 | 60 | NADIA TUBEWELLS | 28.96 | 0 | 0
2051 | Barasat Division | Habra Sub-Division | Continuation order for one motor launch (M.V. JOYMAKALI) on daily hire basis for use of Hasnabad Sub-Division, P.H.E. Dte. Period : 01.03.23 to 31.08.23 = 184 days. | Assistant Engineer | Junior Engineer | ORD/001146/2022-2023 | 0255/HSD | 28/02/2023 | 184 | SUSMITA MANDAL. | 2.74 | 8.46 | 100
2052 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily basis for smooth implementation of JJM work under office of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.02.23 to 31.07.23. | Assistant Engineer | Junior Engineer | ORD/001349/2022-2023 | 137/HSD | 31/01/2023 | 181 | SARKAR ENTERPRISE | 0.86 | 1.85 | 100
2053 | Barasat Division | Habra Sub-Division | Improvement of Iron Elimination Plant at Maslandapur W/S Scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001430/2023-2024 | 693/HAB | 02/11/2023 | 30 | ANJALI CONSTRUCTION. | 4.78 | 0 | 100
2054 | Barasat Division | Habra Sub-Division | Continuation order for Hiring of one no. Disel Motor Cab (BS-IV) on daily hire basis for use of the Assistant Engineer, Hasnabad Sub-Division, PHE Dte. Period from 01.10.2022 to 30.09.2023. | Assistant Engineer | Junior Engineer | ORD/001479/2022-2023 | 1656/HSD | 28/09/2022 | 365 | SUSMITA MANDAL. | 1.72 | 3.72 | 50
2055 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. - 1, 2 & 3 of Maslandapur W/S scheme (Zone - I) within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002976/2021-2022 | 489/HAB | 30/11/2021 | 30 | ANJALI CONSTRUCTION. | 2.77 | 2.71 | 1
2056 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000056/2023-2024 | 1557/BD | 23/05/2023 | 0 | Resource Division | 3.08 | 0 | 0
2057 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000134/2022-2023 | 3794/BD | 22/12/2022 | 0 | Resource Division | 21.91 | 0 | 0
2058 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Kurulia (Zone-I) PWSS (225 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000015/2024-2025 | 688/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.05 | 0 | 100
2059 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Kurulia (Zone-II) PWSS (225 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000016/2024-2025 | 689/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.53 | 0 | 100
2060 | Barasat Division | Bangaon Sub-Division | Construction of Latrine at Head Work site for Augmentation of Kurulia (Zone II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000615/2025-2026 | 670/Bon | 26/05/2025 | 45 | SAMBHU RAY CHOWDHURY. | 1.76 | 0 | 0
2061 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and tube well connection under Augmentation work at Kurulia W/S Scheme (Zone - II) Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000644/2024-2025 | 3170/BD | 18/11/2024 | 30 | MA CONSTRUCTION. | 59.19 | 0 | 0
2062 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1(one) no. 300mm x 200 mm. dia. Tube well 250 mtr deep by D.R. method with UPVC pipe & UPVC ribbed strainer for Augmentation at Kurulia (Zone-II) water supply scheme (2nd T/W site) under Bongaon Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000818/2022-2023 | 3590/BD | 08/12/2022 | 15 | M/S SUKANTA ENTERPRISE. | 15.04 | 11.7 | 100
2063 | Barasat Division | Bangaon Sub-Division | Repairing and renovation of Boundary wall, Pump House and construction of Approach Road at 2nd Tube Well site for Augmentation of Kurulia (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001055/2024-2025 | 1081/Bon | 02/09/2024 | 15 | M/S SAYAN ENTERPRISE. | 4.38 | 0 | 0
2064 | Barasat Division | Bangaon Sub-Division | Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Kurulia (Zone-II) Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001239/2023-2024 | 789/Bon | 10/10/2023 | 15 | A.D.ENTERPRISE. | 1.59 | 0 | 100
2065 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Hire and labour charges for staging and scaffolding, bamboo baricading and removal of rubbish for dismantling of existing OHR at Head work Site of Kurulia Zone-II Water Supply Scheme Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. | Assistant Engineer | Junior Engineer | ORD/001601/2024-2025 | 706/BD | 06/03/2025 | 60 | HAQUE ENTERPRISE | 8.76 | 0 | 0
2066 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Kurulia (Zone-I & II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001729/2023-2024 | 521/BD | 20/02/2024 | 30 | PRABIR KUMAR MONDAL. | 13.94 | 0 | 100
2067 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Kurulia (Zone-II) Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001731/2023-2024 | 520/BD | 20/02/2024 | 330 | ACHINTA KUMAR HALDER. | 13.7 | 0 | 100
2068 | Barasat Division | Bangaon Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within command area of Kurulia(Zone-II) Water Supply Scheme under Bongaon Sub-Division, PHE Dte. (Augmentation). | Assistant Engineer | Junior Engineer | ORD/002038/2021-2022 | 988/BD | 31/03/2022 | 90 | H.I.ENTERPRISE. | 360.51 | 360.44 | 1
2069 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation 2(Two) nos of Pump House and allied works of Kurulia (Zone-I&II) water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002909/2021-2022 | 593/Bon | 22/12/2021 | 21 | PRABIR KUMAR MONDAL. | 2.52 | 2.34 | 1
2070 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000010/2022-2023 | 1365/BD | 13/05/2022 | 0 | Resource Division | 18.73 | 0 | 0
2071 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2022-2023 | 1673/BD | 13/06/2022 | 0 | Resource Division | 17.77 | 0 | 0
2072 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000283/2025-2026 | 1493/HSD | 14/07/2025 | 10 | ABDUL ALIM MONDAL. | 0.84 | 0 | 0
2073 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000372/2022-2023 | 2437/BD | 22/08/2022 | 30 | AUXILIARY TUBE WELL DRILLERS. | 44.41 | 32.03 | 100
2074 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from Joygram Bazar Idgah to near Pintu Molla Garage for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000528/2022-2023 | 1238/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 4.67 | 1
2075 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from Pintu Molla Garage to N/H/O Sahidul Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000529/2022-2023 | 1240/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.74 | 4.67 | 1
2076 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from Near Julfikar Molla shop to N/H/O Sariful Molla for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000530/2022-2023 | 1244/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 3.39 | 3.26 | 1
2077 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Restoration of RCC drain from N/H/O Sahidul Molla to near Julfikar Molla shop for damaged portion due to laying of 150 mm dia DI Rising main of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000531/2022-2023 | 1246/HSD | 20/07/2022 | 21 | JESMINE ENTERPRISE. | 4.76 | 4.42 | 1
2078 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Kumarjole water supply scheme, Minakhan Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000597/2022-2023 | 2676/BD | 08/09/2022 | 90 | JAL PRAVAHIKA PVT. LTD. | 260 | 259.94 | 1
2079 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 400cum capacity 20mtr staging height R.C.C Over Head Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Kumarjole water supply Scheme, Minakhan Block under Hasnabad Sub-Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000755/2023-2024 | 2612/BD | 29/08/2023 | 365 | S.S.ENTERPRISE. (BAMANGACHI) | 153.33 | 0 | 100
2080 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 1 in connection with Augmentation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001431/2024-2025 | 311/HSD | 04/02/2025 | 10 | ABDUL ALIM MONDAL. | 0.81 | 0 | 0
2081 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the left out portion in connection with Augmentation of Kumarjole water supply scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001455/2024-2025 | 571/BD | 21/02/2025 | 120 | JAL PRAVAHIKA PVT. LTD. | 196.02 | 0 | 0
2082 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 2 nos. pump connection at PH No.-1 & 2 in connection with Augmentation of Kumarjole water supply scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001857/2023-2024 | 37/HSD | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.83 | 0 | 100
2083 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000040/2022-2023 | 2472/BD | 24/08/2022 | 0 | Resource Division | 8.92 | 0 | 0
2084 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work for newly laid UPVC pipe line at different places of Ghoshpur, Kalinagar & Roypur Mouza in connection with retrofitting of Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000040/2023-2024 | 1358/BD | 04/05/2023 | 30 | UMWELT ENGINEER PVT.LTD. | 134.62 | 77.5 | 100
2085 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Kalinagar W/s scheme (Zone-I), Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2022-2023 | 1570/BD | 01/06/2022 | 90 | UMWELT ENGINEER PVT.LTD. | 274.51 | 255.99 | 1
2086 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of pump house & boundary wall at PH No.-2 within Kalinagar w/s scheme (Old), Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000295/2023-2024 | 2106/BD | 19/07/2023 | 21 | M/S GHOSH CONSTRUCTION. | 7.1 | 7.1 | 58
2087 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of pump house & boundary wall at P.H.-3 within Kalinagar w/s scheme (Old), Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000299/2023-2024 | 2114/BD | 19/07/2023 | 21 | GOBINDA DAS. | 7.21 | 7.21 | 59
2088 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Ghoshpur mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000874/2023-2024 | 1060/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.93 | 0.93 | 100
2089 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Roypur mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000875/2023-2024 | 1061/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.96 | 0.96 | 100
2090 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of existing FHTC along with pipe line in connection with retrofitting work at different places within Kalinagar mouza due to erosion of soil for heavy rain fall during monsoon season within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000876/2023-2024 | 1063/HSD | 31/08/2023 | 10 | M/S RAJPATH CONSTRUCTION. | 0.97 | 0.97 | 100
2091 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of existing boundary wall and other allied works at Pump House No.-1 within Kalinagar w/s scheme (Old), Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000909/2023-2024 | 2720/BD | 05/09/2023 | 21 | ABDUL ALIM MONDAL. | 9.09 | 9.09 | 100
2092 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with RCC column & brick masonry & RCC Column structure at Head Work site & PH No- 3 within Kalinagar w/s scheme (Z-I), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001339/2023-2024 | 4435/BD | 10/11/2023 | 720 | ABDUL HAMID GAZI. | 31.93 | 0 | 80
2093 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) for left out house holds under the command area of Kalinagar water supply scheme (Z-I) in order to provide Har Ghar Jal Certification, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001730/2023-2024 | 429/BD | 09/02/2024 | 30 | ABDUL ALIM MONDAL. | 70.78 | 0 | 75
2094 | Barasat Division | Hasnabad Sub-Division | Formal work order for Protection work in different places of Chunchura, Boyermari, Sankardaha & Sankardaha Abad Mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 1696/BD | 08/06/2023 | 30 | AMAL DUTTA ROY | 140.16 | 62.46 | 81
2095 | Barasat Division | Hasnabad Sub-Division | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Jal Swapna Programme within command area of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000163/2022-2023 | 1667/BD | 13/06/2022 | 90 | S. GHOSH & ASSOCIATES PVT. LTD. | 266.33 | 243.28 | 1
2096 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sibu Sardar at Boyermari Sardar para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000384/2022-2023 | 1322/HSD | 02/08/2022 | 10 | M/S ANUBHAB CONSTRUCTION. | 4.42 | 4.42 | 1
2097 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sibu Gayen at Boyermari Das para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 1323/HSD | 02/08/2022 | 10 | M/S ANUBHAB CONSTRUCTION. | 4.5 | 4.5 | 1
2098 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Shibcharan Mahato, Chottu Mahato, Arabinda Mahato, Gopal Mahato & Chitta Mahato at Boyermari Mahato para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2022-2023 | 1324/HSD | 02/08/2022 | 10 | KABASI ENTERPRISE. | 4.72 | 4.71 | 1
2099 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sankar Pradhan, Uttam Das at Pradhan para & N/H/O Asraf Molla at Gazi para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000387/2022-2023 | 1325/HSD | 02/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.82 | 0 | 1
2100 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Nishith Patra, Tapas Patra at Boyermari Patra para & N/H/O Ramesh Mahato at Boyermari Mahato para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 1326/HSD | 02/08/2022 | 10 | SARKAR ENTERPRISE | 4.81 | 4.79 | 1
2101 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Sukumar Mahato to N/H/O Mansaram Mahato at 6 no. Boyermari in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000389/2022-2023 | 1327/HSD | 02/08/2022 | 10 | M/S K.B.ENTERPRISE. | 4.52 | 4.52 | 1
2102 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at N/H/O Nirmal Sardar, Rohit Sardar, Naren Mali, Basudeb Mali at Boyermari Mali para & N/H/O Bablu Singh at Boyermari Choto Singh para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 1328/HSD | 02/08/2022 | 10 | M/S LALTI ENTERPRISE | 3.63 | 3.63 | 1
2103 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid UPVC pipe line by bamboo pilling at different places of Boyermari Pandab para & Boyermari Gazipara in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000418/2022-2023 | 1350/HSD | 03/08/2022 | 10 | ABDUL HAMID GAZI. | 4.38 | 4.35 | 1
2104 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Laltu Sardar at Boyermari Sardar para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000419/2022-2023 | 1351/HSD | 03/08/2022 | 10 | BASIRHAT ANCHALICK SHARAMICK THIKADARY SAMABAY SAMITY LTD. | 4.42 | 4.37 | 1
2105 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in Chunchura mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000473/2022-2023 | 1398/HSD | 08/08/2022 | 15 | ABDUL ALIM MONDAL. | 4.8 | 4.8 | 1
2106 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places within Boyermari mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000479/2022-2023 | 1404/HSD | 08/08/2022 | 15 | M/S RAJPATH CONSTRUCTION. | 4.78 | 4.78 | 1
2107 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection work for newly laid different dia. UPVC/DI distribution pipeline at different places in Bayermari Mouza of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000487/2022-2023 | 2368/BD | 10/08/2022 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 60.68 | 60.66 | 1
2108 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC/DI distribution pipeline by UC bullah pile at different places within Chunchura Mouza in Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000543/2022-2023 | 1811/ BD | 27/06/2022 | 30 | MONDAL & CO. (BASIRHAT). | 76.73 | 76.7 | 1
2109 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia UPVC/DI pipeline by UC bullah pile at N/H/O Sankar Pradhan, Uttam Das at Pradhan para & N/H/O Asraf Molla at Gazi para in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000620/2022-2023 | 1325/HSD | 02/08/2022 | 10 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.82 | 4.81 | 1
2110 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places within Boyermari mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002795/2021-2022 | 355/HSD | 23/02/2022 | 15 | ABDUL ALIM MONDAL. | 4.78 | 4.78 | 1
2111 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with retrofitting of Chunchura mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002796/2021-2022 | 356/hsd | 23/02/2022 | 15 | M/S RAJPATH CONSTRUCTION. | 4.8 | 4.8 | 1
2112 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional emergent restoration of road for damage portion due to newly laid different dia DI/UPVC distribution pipe line at different places in connection with retrofitting of Chunchura, Boyermari, Sankardaha Abad, Khas Sankardaha mouza in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002797/2021-2022 | 357/HSD | 23/02/2022 | 15 | M/S RAJPATH CONSTRUCTION. | 4.8 | 4.77 | 1
2113 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 250/200 mm dia DI pipeline by concrete block over existing concrete wall beside Basanti Highway at different places for Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002847/2021-2022 | 563/HSD | 22/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.41 | 4.3 | 1
2114 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional emergent resting of 150/100 mm dia DI pipeline by concrete block over existing concrete wall beside Basanti Highway at different places for Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002848/2021-2022 | 564/HSD | 22/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.41 | 4.41 | 1
2115 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent casing of UPVC pipe line at different locations over Khal, channel, culverts, roads within Chunchura W/S Scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002849/2021-2022 | 565/HSD | 22/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.38 | 4.37 | 1
2116 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 100/150/200 mm dia DI pipeline by concrete block at different places from Kalupara more to N/H/O Sukumar Mahato within Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002850/2021-2022 | 566/HSD | 22/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.32 | 4.03 | 1
2117 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of 100/150/200 mm dia DI pipeline by concrete block at different places from N/H/O Sukumar Mahato to Dheknimari High School within Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002851/2021-2022 | 567/HSD | 22/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.32 | 4.29 | 1
2118 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of different dia UPVC/DI pipeline by UC bullah pile at different places in different mouza while laying of pipeline in connection with retrofitting of Chunchura w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002857/2021-2022 | 573/HSD | 23/03/2022 | 15 | S. GHOSH & ASSOCIATES PVT. LTD. | 2.83 | 2.82 | 1
2119 | Barasat Division | Hasnabad Sub-Division | Formal Work order for Laying of DI rising main and DI/UPVC distribution pipe line and Construction of 900 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Chunchura & Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division,PHE Dte. under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003031/2021-2022 | 767/Bd | 16/03/2022 | 12 | S. GHOSH & ASSOCIATES PVT. LTD. | 563.09 | 179.21 | 100
2120 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Deora Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2023-2024 | 1191/BD | 19/04/2023 | 90 | CHANDA CONSTRUCTION. | 267.73 | 0 | 100
2121 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Special repair & renovation of boundary wall and other allied Works for Pump House No - 1 of Deora W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000160/2024-2025 | 1798/BD | 01/07/2024 | 30 | M/S SUKANTA ENTERPRISE. | 5.27 | 0 | 0
2122 | Barasat Division | Basirhat Sub-Division | construction of Service Road (55 Mtr. Length and 2 Mtr. Width) for Pump House No:1 of Deora Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000196/2024-2025 | 689/HAB | 24/07/2024 | 15 | M/S SUKANTA ENTERPRISE. | 3.52 | 0 | 0
2123 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 2 no. 300 mm. x 200 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 300 mm. dia. 36 mtr. long housing pipe & 200 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Deora water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000974/2023-2024 | 2780/BD | 11/09/2023 | 60 | M/S SUKANTA ENTERPRISE. | 39.1 | 0 | 80
2124 | Barasat Division | Basirhat Sub-Division | Hiring of 1 no. of Diesel Luxury Car (Euro ¿ IV/VI) in good condition (traffic worthy) on daily basis for office use of the Assistant Engineer, for supervision of J.J.M. related work, executed within the entire jurisdiction of Habra Sub-Division, under Barasat Division P.H.E. Dte. (For the period from :01.09.23 to 29.02.24) | Assistant Engineer | Junior Engineer | ORD/001226/2023-2024 | 476/HAB | 31/08/2023 | 182 | M/S SUKANTA ENTERPRISE. | 0.86 | 0 | 10
2125 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000059/2023-2024 | 1559/BD | 23/05/2023 | 0 | Resource Division | 7.62 | 0 | 0
2126 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Nityananda Kati Balti water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001141/2022-2023 | 514/BD | 20/02/2023 | 766 | UTPAL CONSTRUCTION & CO. | 272.4 | 114.31 | 52
2127 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Nityanadakati Balti Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002761/2021-2022 | 440/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.69 | 3.69 | 1
2128 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000150/2023-2024 | 4411/BD | 10/11/2023 | 0 | Resource Division | 7.39 | 0 | 0
2129 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000203/2022-2023 | 860/BD | 20/03/2023 | 0 | Resource Division | 60.86 | 0 | 0
2130 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional Household Tap Connection for Augmentation of Simla Durgapur Zone-I water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000037/2023-2024 | 1355/BD | 04/05/2023 | 775 | CHANCHAL ENTERPRISE & CO. | 300.04 | 120.15 | 71
2131 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Simla Durgapur (Zone-II)water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000158/2023-2024 | 1717/BD | 08/06/2023 | 698 | UTPAL CONSTRUCTION & CO. | 446.82 | 0 | 48
2132 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Shimla Durgapur Zone-II water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001003/2023-2024 | 2804/BD | 12/09/2023 | 717 | SAHA CONSTRUCTION & CO | 21.53 | 0 | 100
2133 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001995/2021-2022 | 376/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.96 | 4.96 | 1
2134 | Barasat Division | Basirhat Sub-Division | Additional survey work for DPR Preparation for SIMLA DURGAPUR Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002897/2021-2022 | 377/BHTSD | 16/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.66 | 1.65 | 1
2135 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000026/2023-2024 | 1247/BD | 25/04/2023 | 0 | Resource Division | 49.35 | 0 | 0
2136 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000062/2023-2024 | 1626/BD | 01/06/2023 | 0 | Resource Division | 44.17 | 0 | 0
2137 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000070/2023-2024 | 1647/BD | 02/06/2023 | 0 | Resource Division | 13.76 | 0 | 0
2138 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Kanaikathi Kathalberia water supply scheme (Z-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000098/2024-2025 | 1717/BD | 26/06/2024 | 271 | KINGS & CO. | 148.51 | 0 | 80
2139 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House No.-1 with allied works for Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000286/2023-2024 | 824/HSD | 14/07/2023 | 15 | STAR CONSTRUCTION. | 4.69 | 4.57 | 100
2140 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of approach road with cement concrete at PH No- 1 & 2 for Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000287/2023-2024 | 825/HSD | 14/07/2023 | 10 | STAR CONSTRUCTION. | 3.92 | 3.84 | 100
2141 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of Pump House No-2 & other allied works for Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000288/2023-2024 | 826/HSD | 14/07/2023 | 10 | PRASANTA MITRA. | 4.2 | 3.74 | 100
2142 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for front & left side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000440/2022-2023 | 1366/HSD | 03/08/2022 | 21 | SHYAM SUNDAR DAS. | 2.68 | 2.66 | 1
2143 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for right & back side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 1367/HSD | 03/08/2022 | 21 | NEW LIFE CONSTRUCTION. | 3.22 | 3.22 | 1
2144 | Barasat Division | Hasnabad Sub-Division | Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000743/2023-2024 | 2495/BD | 18/08/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.9 | 0 | 70
2145 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection in connection with Augmentation of Kanaikati Kathalberia water supply scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001136/2022-2023 | 516/BD | 20/02/2023 | 811 | KINGS & CO. | 434.98 | 353.67 | 100
2146 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-II), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001179/2022-2023 | 792/BD | 13/03/2023 | 30 | M/S PROGATI ENTERPRISE. | 26.25 | 21.62 | 100
2147 | Barasat Division | Hasnabad Sub-Division | Formal work order for construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap in connection with Augmentaion of Kanaikati Kathalberia water supply scheme (Zone-II), Hingalganj Block of Hasnabad Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001264/2023-2024 | 4191/BD | 30/10/2023 | 365 | ABDUL ALIM MONDAL. | 139.6 | 0 | 58
2148 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of temporary approach road for moving of rig machineries at PH No- 1 within Kanaikati Kathalberia w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001612/2023-2024 | 40/HSD | 09/01/2024 | 10 | M/S PROGATI ENTERPRISE. | 0.76 | 0 | 100
2149 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000253/2022-2023 | 919/BD | 22/03/2023 | 0 | Resource Division | 34.37 | 0 | 0
2150 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03464/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 28.09 | 0 | 0
2151 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Dobila Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000232/2023-2024 | 1736/BD | 08/06/2023 | 905 | M/S B.N ENTERPRISE | 223.65 | 0 | 36
2152 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for special repair and renovation of existing structure like Pump House, Boundary Wall, High Lift Pump House, AIRP Pump House, Godown, Pathway etc. and allied pipe line work at Dobila, Eojnogar, Gobindapur Dhokra, Goknasree Gobindapur, Gotra, Sankchura and Mominpur Water Supply Scheme of different block within Basirhat Sub-Division under Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000287/2025-2026 | 2464/BD | 16/07/2025 | 150 | M/S TARAFDAR CONSTRUCTION | 81.09 | 0 | 0
2153 | Barasat Division | Basirhat Sub-Division | Laying of pipe line at Dobila W/s scheme due to widening of PWD ROAD at Dobila Water supply scheme of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000463/2022-2023 | 837 /BHTSD | 23/06/2022 | 10 | M/S SUKANTA ENTERPRISE. | 2.86 | 2.81 | 0
2154 | Barasat Division | Basirhat Sub-Division | Sand filling due laying of pipe line at Dobila W/s scheme of Basirhat Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000505/2022-2023 | 845 /BHTSD | 23/06/2022 | 10 | M/S SUKANTA ENTERPRISE. | 2.64 | 2.63 | 1
2155 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads under different water supply schemes of Swarupnagar Block within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001009/2024-2025 | 3625/BD | 20/12/2024 | 90 | PUSPA CONSTRUCTION. | 57.26 | 0 | 0
2156 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for Dobila Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002756/2021-2022 | 449/ BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.5 | 3.5 | 1
2157 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000047/2023-2024 | 1273/BD | 25/04/2023 | 0 | Resource Division | 94.49 | 0 | 0
2158 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000149/2023-2024 | 4407/BD | 10/11/2023 | 0 | Resource Division | 5.73 | 0 | 0
2159 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of 350 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Augmentation of Boyermari Abad water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000217/2023-2024 | 1732/BD | 08/06/2023 | 661 | M/S DATTA ENTERPRISE. | 152.98 | 0 | 72
2160 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Dismantling & Re-construction of boundary wall for movement of rig & other machineries for sinking of big dia TW at PH no- 2 in connection with Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000259/2023-2024 | 785/HSD | 13/07/2023 | 10 | MD.SALIM GAZI. | 0.87 | 0.87 | 100
2161 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at Pump House No.- 1 & 2 with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000359/2022-2023 | 2237/BD | 28/07/2022 | 30 | M/S K.P.PAL. | 44.4 | 28.38 | 1
2162 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, Providing FHTC for the leftout portion (River side), protection works & other allied works in connection with Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000512/2024-2025 | 3129/BD | 12/11/2024 | 270 | S.S.ENTERPRISE. (BAMANGACHI) | 245.45 | 0 | 0
2163 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Boyermari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000582/2024-2025 | 1179/HSD | 30/09/2024 | 10 | M/S DATTA ENTERPRISE. | 0.89 | 0 | 100
2164 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Boyermari Abad water supply scheme, Sandeshkhali-I Block within Hasnabad Sub-Division, under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000669/2022-2023 | 2928/BD | 26/09/2022 | 90 | S.S.ENTERPRISE. (BAMANGACHI) | 370.05 | 365.77 | 1
2165 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order Sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Boyermari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000890/2024-2025 | 3377/BD | 02/12/2024 | 60 | M/S K.P.PAL. | 25.88 | 0 | 100
2166 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent withdrawing, relaying and laying of different dia. UPVC/DI pipe line at Boyermari Abad water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E.Dte | Assistant Engineer | Junior Engineer | ORD/001405/2024-2025 | 512/BD | 17/02/2025 | 60 | MUKHERJEE CONSTRUCTION (NADIA) | 17.75 | 0 | 0
2167 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000246/2022-2023 | 931/BD | 22/03/2023 | 0 | Resource Division | 9.92 | 0 | 0
2168 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall, Approach Road, Earth Filling and Construction of 3.60 mtr. X 3.00 mtr. size Guard Room with sanitary and water supply arrangement incl. plinth protection at OHR site of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000350/2024-2025 | 2417/BD | 23/08/2024 | 60 | ROY CHOWDHURY CONSTRUCTION. | 37.8 | 0 | 0
2169 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Kalupur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000954/2022-2023 | 93/BD | 11/01/2023 | 900 | M/S S.S.ENTERPRISE. (SOUTH) | 454.09 | 351.97 | 90
2170 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia. Tube well 250 mtr deep Replacement Tube well by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Kalupur Water Supply Scheme (H/W Site & 2nd T/W Site) within the Jurisdiction of Bongaon Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001111/2023-2024 | 2924/BD | 26/09/2023 | 60 | SAHA CONSTRUCTION & CO | 32.29 | 0 | 100
2171 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 1st Tube well site for Augmentation of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001744/2023-2024 | 560/BD | 22/02/2024 | 45 | MA CONSTRUCTION. | 9.33 | 0 | 100
2172 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at 2nd Tube Well site and Construction of Approach Road at 1st T/W & 2nd T/W site under Augmentation of Kalupur Water Supply Scheme, Bongaon Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001751/2023-2024 | 562/BD | 22/02/2024 | 45 | RAJ ENTERPRISE. | 7.53 | 0 | 100
2173 | Barasat Division | Bangaon Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kalupur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002789/2021-2022 | 122/BON | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 3.77 | 1
2174 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000091/2022-2023 | 3659/BD | 13/12/2022 | 0 | Resource Division | 21.27 | 0 | 0
2175 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000105/2022-2023 | 3685/BD | 14/12/2022 | 0 | Resource Division | 117.82 | 0 | 0
2176 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC distribution main and Providing FHTC (Functional Household Tap Connection ) by augmentation for Dakshin Bagundi water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000785/2022-2023 | 3511/BD | 02/12/2022 | 30 | ROY CHOWDHURY CONSTRUCTION. | 50.96 | 43.28 | 85
2177 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Construction of Boundary Wall at the site of Pump House 1 of Dakshin Bagundi Water Supply Scheme under Basirhat Sub-Division within Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001038/2024-2025 | 3701/BD | 26/12/2024 | 270 | JEET ENTERPRISE. | 7.96 | 0 | 0
2178 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000143/2022-2023 | 3814/BD | 23/12/2022 | 0 | Resource Division | 17.36 | 0 | 0
2179 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of Concrete roads and emergency protection work under different places of Kachua Swarupnagar Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000403/2025-2026 | 2673/BD | 30/07/2025 | 30 | ALAM ENTERPRISE | 7.99 | 0 | 0
2180 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Kachua Swarupnagar water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000790/2022-2023 | 3548/BD | 06/12/2022 | 90 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 395.76 | 348.51 | 65
2181 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000140/2022-2023 | 3817/BD | 23/12/2022 | 0 | Resource Division | 87.92 | 0 | 0
2182 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000146/2023-2024 | 4422/BD | 10/11/2023 | 0 | Resource Division | 9.24 | 0 | 0
2183 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000189/2022-2023 | 607/BD | 23/02/2023 | 0 | Resource Division | 8.6 | 0 | 0
2184 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Repairing and renovation works of 200 cum. capacity 20mtr. Staging height R.C.C. Over Head water Reservoir for Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000029/2024-2025 | 1538/BD | 07/06/2024 | 45 | A. R CONS | 12.57 | 0 | 100
2185 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe under Augmentation work at Ashudi W/S Scheme at Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000706/2024-2025 | 3228/BD | 21/11/2024 | 120 | NEW MILLENNIUM ENGG'S CO-OP-SO-LTD. | 45.8 | 0 | 100
2186 | Barasat Division | Habra Sub-Division | Laying of badly damaged distribution pipe line with bamboo pile beside road and other allied works at Ashudi water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000748/2023-2024 | 603/Bon | 04/08/2023 | 15 | ROY CHOWDHURY CONSTRUCTION. | 1.62 | 1.61 | 100
2187 | Barasat Division | Habra Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Ashudi Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000793/2022-2023 | 3550/BD | 06/12/2022 | 90 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 156.77 | 99.89 | 0
2188 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Ashudi Water Supply Scheme (H/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001148/2023-2024 | 2943/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.12 | 0 | 100
2189 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Repairing of Boundary wall and Construction of Approach Road at Head Work site and 2nd Pump House site under Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001749/2023-2024 | 571/BD | 22/02/2024 | 45 | BHABANI ENTERPRISE. | 10.39 | 0 | 100
2190 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Improvement of existing IEP & other related allied works and including adding 1 no. Polishing unit and Repairing & renovation of Compressor Room for Iron Elimination Plant under Augmentation of Ashudi Water Supply Scheme, Habra-II Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001782/2023-2024 | 626/BD | 28/02/2024 | 45 | R.K.MANDAL & CO. | 22.68 | 0 | 100
2191 | Barasat Division | Habra Sub-Division | Repairing & Renovation of 01No. Pump House and allied works at Ashudi water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002933/2021-2022 | 528/BON | 01/11/2021 | 21 | A.D.ENTERPRISE. | 2.52 | 2.48 | 1
2192 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000113/2022-2023 | 3697/BD | 14/12/2022 | 0 | Resource Division | 21.19 | 0 | 0
2193 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as to convert the mouzas into Swajal Gram including laying of UPVC pipe, Pump Connection of 1 no. newly sunk Replacement Tube well with rising main by DI pipe and allied works under Augmentation of Gobindapur Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2025-2026 | 1384/BD | 30/04/2025 | 60 | M/S SAYAN ENTERPRISE. | 11.5 | 0 | 0
2194 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Gobindapur Water Supply Scheme under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000781/2022-2023 | 3488/BD | 02/12/2022 | 90 | M/S NIRMAN CONSTRUCTION. | 341.88 | 287.62 | 99
2195 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repair and renovation works of 350cum capacity 20mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Gobindapur Water Supply Scheme, Bagdah Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000896/2024-2025 | 3403/BD | 04/12/2024 | 90 | UPWARDS ENGINEERING PRIVATE LIMITED. | 8.62 | 0 | 100
2196 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gobindapur water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001007/2022-2023 | 170/BD | 19/01/2023 | 858 | KINGS & CO. | 437.87 | 190.66 | 66
2197 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Gobindapur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002971/2021-2022 | 585/ BON | 15/12/2021 | 21 | M/S SAYAN ENTERPRISE. | 2.52 | 2.31 | 1
2198 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) for Augmentation of Hariharpur Water Supply Scheme, Bagdah Block under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001006/2022-2023 | 175/BD | 19/01/2023 | 900 | M/S R.K. ENTERPRISE | 173.76 | 68.74 | 100
2199 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 300 mm. x 200 mm. dia. 250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Hariharpur Water Supply Scheme (H/W Site)within the jurisdiction of BongaonSub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001116/2023-2024 | 2939/BD | 27/09/2023 | 30 | JOY GURU ENTERPRISE | 16.11 | 0 | 100
2200 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation of 35 Cum/hr of capacity AIRP and allied works at Head work site for Augmentation of Hariharpur Water Supply Scheme under Bongaon Sub-Division, Barasat Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001765/2023-2024 | 511/BD | 20/02/2024 | 60 | DEBAPRASAD MONDAL. | 38.43 | 0 | 100
2201 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing and renovation of Compressor Room for AIRP, Construction of Approach Road at 2nd Tube Well site and Construction of Boundary wall and Approach Road at Head Work and 2nd T/W site under Augmentation of Hariharpur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001781/2023-2024 | 625/BD | 28/02/2024 | 45 | JEET ENTERPRISE. | 7.66 | 0 | 100
2202 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Construction of Boundary wall at Head Work site for Augmentation of Hariharpur Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001791/2023-2024 | 648/BD | 29/02/2024 | 30 | A.D.ENTERPRISE. | 13.35 | 0 | 100
2203 | Barasat Division | Bangaon Sub-Division | Repairing & Renovation of 02Nos. Pump House and allied works at Hariharpur water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002973/2021-2022 | 521/ BON | 28/10/2021 | 21 | ANKIT CONSTRUCTION | 2.51 | 2.46 | 1
2204 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000152/2022-2023 | 1256/BD | 25/04/2023 | 0 | Resource Division | 12.08 | 0 | 0
2205 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Maminpur water supply scheme in Basirhat-II block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000742/2022-2023 | 3340/BD | 16/11/2022 | 769 | MONDAL PRECISION PVT.LTD | 194.77 | 155.27 | 83
2206 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300mm. x 200 mm. big dia 300 mtr deep Tube well by Direct Rotary Rig method for pump house no - 1 & 2 using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Mominpur Water Supply Scheme in Basirhat - II Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001151/2022-2023 | 674/BD | 01/03/2023 | 30 | DHELA BABA ENTERPRISE | 42.67 | 0 | 0
2207 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for MAMINPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002760/2021-2022 | 305/ BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 2.98 | 1
2208 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000145/2022-2023 | 3820/BD | 23/12/2022 | 0 | Resource Division | 16.81 | 0 | 0
2209 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000157/2023-2024 | 4417/BD | 10/11/2023 | 0 | Resource Division | 11.09 | 0 | 0
2210 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Rajendrapur Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2025-2026 | 2452/BD | 16/07/2025 | 30 | ABDUL CHHAMAD MANDAL | 9.09 | 0 | 0
2211 | Barasat Division | Basirhat Sub-Division | Repairing of Pump House No 1 at Rajandrapur Water Supply Scheme under Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2021-2022 | 1236 /BHTSD | 16/09/2021 | 20 | MD AMIRUL MOLLA. | 0.64 | 0.45 | 1
2212 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Rajendrapur water supply scheme in Basirhat-II Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/001012/2022-2023 | 174/BD | 19/01/2023 | 799 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 376.42 | 288.61 | 70
2213 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for RAJENDRAPUR Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002965/2021-2022 | 311/BHT | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.19 | 3.85 | 1
2214 | Barasat Division | Basirhat Sub-Division | Repairing of Pump House No 1 at Rajandrapur Water Supply Scheme under Basirhat Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002987/2021-2022 | 1237/BHT | 16/09/2021 | 20 | PROBAHA ENGINEER'S CO-OP-SOCIETY LTD. | 0.66 | 0.45 | 1
2215 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000155/2023-2024 | 4416/BD | 10/11/2023 | 0 | Resource Division | 12.32 | 0 | 0
2216 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000199/2022-2023 | 855/BD | 20/03/2023 | 0 | Resource Division | 71.29 | 0 | 0
2217 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Restoration of roads and emergency protection work under different places of Dhopaberia Water Supply Scheme within Basirhat Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000001/2025-2026 | 1111/BD | 08/04/2025 | 30 | MD AMIRUL MOLLA. | 23.39 | 0 | 0
2218 | Barasat Division | Basirhat Sub-Division | Formal work order for laying of DI/UPVC distribution pipe line and Providing Functional House Hold Tap Connection (FHTC) For Augmentation of Dhopaberia-Ganrakupia Water Supply Scheme in Basirhat-II Block of North 24 Parganas District under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000846/2022-2023 | 3475/ BD | 01/12/2022 | 90 | DIVINE | 311.55 | 279.59 | 93
2219 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000143/2023-2024 | 4420/BD | 10/11/2023 | 0 | Resource Division | 4.93 | 0 | 0
2220 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000165/2022-2023 | 486/BD | 17/02/2023 | 0 | Resource Division | 22.66 | 0 | 0
2221 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000184/2022-2023 | 597/BD | 23/02/2023 | 0 | Resource Division | 6.69 | 0 | 0
2222 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipeline and Providing FHTC (Functional Household Tap Connection ) for augmentation of Gachharati water supply scheme in Basirhat-I block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000670/2022-2023 | 2934/BD | 26/09/2022 | 90 | SANJOY BAKSHI | 140.52 | 34.84 | 46
2223 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1nos. 300mm. x 200 mm. big dia 270 mtr deep Tube well by Direct Rotary Rig method at Pump House No.-1 using PVC pipe & strainer having 300 mm Dia 36 mtr. long Housing Pipe and 200 mm Dia 30 mtr. long filter for Augmentation of Gachharati Water Supply Scheme in Basirhat - I Block of Basirhat Sub- Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001152/2022-2023 | 675/BD | 01/03/2023 | 30 | DHELA BABA ENTERPRISE | 19.62 | 0 | 100
2224 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GACHHARATI Water Supply Scheme in Basirhat-I Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002783/2021-2022 | 199/ BHTSD | 28/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.69 | 2.63 | 1
2225 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000137/2022-2023 | 3812/BD | 23/12/2022 | 0 | Resource Division | 0.33 | 0 | 0
2226 | Barasat Division | Habra Sub-Division | Preparation of geo-referenced GIS mapping with integrated software showing georeferenced location of Households, Piped water supply scheme and Distribution network to be incorporated into map by using both GIS & CAD software keeping the essential Technical aspect of 6 numbers scheme namely Gobindapur Dhokra, Rajnagar, Sadiknagar Zone-I, Bithari Zone-I, Bithari Zone-II and Simla Durgapur of North 24 Pgs. District under the jurisdiction of Basirhat Sub-Division. | Assistant Engineer | Junior Engineer | ORD/000551/2022-2023 | 945 / BHT SD | 19/07/2022 | 15 | M/S TECHVISION. | 2.91 | 2.91 | 1
2227 | Barasat Division | Habra Sub-Division | Formal Work Order cor Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MASLANDAPUR Water Supply Scheme(ZONE-II) at Habra - I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I). | Assistant Engineer | Junior Engineer | ORD/000944/2021-2022 | 01/BD | 03/01/2022 | 90 | M/S B.K.ENTERPRISE. | 145.09 | 139.68 | 1
2228 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2021-2022 | 251/BD | 27/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
2229 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection ) for augmentation of Masia Nabastia water supply scheme in Baduria block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000747/2022-2023 | 3372/BD | 18/11/2022 | 90 | GHOSH CONSTRUCTION. | 146.63 | 123.78 | 85
2230 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000032/2022-2023 | 2307/BD | 03/08/2022 | 0 | Resource Division | 12.12 | 0 | 0
2231 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000162/2022-2023 | 492/BD | 17/02/2023 | 0 | Resource Division | 12.12 | 0 | 0
2232 | Barasat Division | Basirhat Sub-Division | Enhancement of GST for laying of distribution pipe line and providing FHTC for Augmentation of Gotra water supply scheme under Basirhat Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | BILL/01246/2024-2025 | BP-2024-25-393 | 04/10/2024 | 0 | BALAJI UDDYOG | 16 | 0 | 0
2233 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Gotra water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000789/2022-2023 | 3547/BD | 06/12/2022 | 90 | BALAJI UDDYOG | 468.63 | 181.56 | 57
2234 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000170/2022-2023 | 487/BD | 17/02/2023 | 0 | Resource Division | 237.82 | 0 | 0
2235 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000183/2022-2023 | 609/BD | 23/02/2023 | 0 | Resource Division | 19.95 | 0 | 0
2236 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Laying of UPVC Distribution pipe line and providing FHTC for augmentation of Pifa water Supply Scheme within Basirhat - I Block under Basirhat Sub-Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000594/2024-2025 | 3131/BD | 12/11/2024 | 180 | M/S MITRA CONSTRUCTION. | 49.39 | 0 | 100
2237 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Pipha water supply scheme in Basirhat-I Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000842/2022-2023 | 3631/BD | 12/12/2022 | 787 | SANDIP BISWAS | 318.65 | 0 | 95
2238 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000137/2023-2024 | 4423/BD | 10/11/2023 | 0 | Resource Division | 6.16 | 0 | 0
2239 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000160/2022-2023 | 495/BD | 17/02/2023 | 0 | Resource Division | 44.41 | 0 | 0
2240 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000181/2022-2023 | 599/BD | 23/02/2023 | 0 | Resource Division | 7.47 | 0 | 0
2241 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Ghipukuria w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000144/2023-2024 | 1698/BD | 08/06/2023 | 1096 | TIRUPATI ENTERPRISES | 270.61 | 0 | 70
2242 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002711/2021-2022 | 274/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
2243 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002712/2021-2022 | 275/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.83 | 0.83 | 1
2244 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (GHIPUKURIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002990/2021-2022 | 275/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 0.83 | 0 | 1
2245 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000211/2022-2023 | 891/BD | 22/03/2023 | 0 | Resource Division | 15.9 | 0 | 0
2246 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Tapla Kusangra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 1682/BD | 07/06/2023 | 1029 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 328.77 | 106.63 | 80
2247 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall with column structure at Head Work site within Tapla Kusangra w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002263/2024-2025 | 1031/BD | 28/03/2025 | 90 | ACHARJEE AND ASSOCIATES | 17.53 | 0 | 0
2248 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (TAPLA KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002734/2021-2022 | 310/HSD | 15/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.82 | 4.82 | 1
2249 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (TAPLA KUSANGRA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002735/2021-2022 | 311/HSD | 15/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 0.52 | 0.52 | 1
2250 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000219/2022-2023 | 887/BD | 22/03/2023 | 0 | Resource Division | 12.08 | 0 | 0
2251 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent fencing work for protecting the adjacent land of PH no-1 within Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2023-2024 | 793/HSD | 13/07/2023 | 10 | NEW LIFE CONSTRUCTION. | 0.91 | 0 | 0
2252 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Repairing of pump house & construction of approach road with cement concrete at PH No.-2 for Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000302/2023-2024 | 2116/BD | 19/07/2023 | 15 | M/S K.B.ENTERPRISE. | 5.59 | 5.35 | 100
2253 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of 150 cum capacity CWR , pipe connection and cost of pipes, specials for Augmentation of Kanaikati Kathalberia water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000402/2024-2025 | 2520/BD | 02/09/2024 | 180 | SARKAR ENTERPRISE & CO. | 43.88 | 0 | 0
2254 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line and Providing Functional Household Tap Connection for the leftout portion in connection with Augmentation of Kanaikathi Kathalberia water supply scheme (Z-I), Hingalganj Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000414/2024-2025 | 3051/BD | 24/10/2024 | 30 | KINGS & CO. | 101.79 | 0 | 0
2255 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for Back & Left side at PH No.-1 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000436/2022-2023 | 1362/HSD | 03/08/2022 | 21 | BADAL GHOSH. | 3.87 | 3.84 | 1
2256 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for Front & Right side at PH No.-1 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 1363/HSD | 03/08/2022 | 21 | LAHIRI CONSTRUCTION. | 3.34 | 3.33 | 1
2257 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for right & back side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000438/2022-2023 | 1364/HSD | 03/08/2022 | 21 | STAR CONSTRUCTION. | 3.26 | 3.23 | 1
2258 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of boundary wall for front & left side at PH No.-2 within Kanaikati Kathalberia w/s scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000439/2022-2023 | 1365/HSD | 03/08/2022 | 21 | STAR CONSTRUCTION. | 2.66 | 2.66 | 1
2259 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000742/2023-2024 | 2494/BD | 18/08/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.9 | 0 | 33
2260 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 1 nos. 300 mm. x 200 mm. dia. 300 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 36 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Kanaikati Kathalberia w/s scheme (Z-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001178/2022-2023 | 791/BD | 13/03/2023 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 26.26 | 18.02 | 7
2261 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and providing Functional Household Tap connection for Augmentation of Kanaikati Kathalberia water Supply Scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/001190/2023-2024 | 4201/BD | 31/10/2023 | 540 | KINGS & CO. | 707.01 | 0 | 80
2262 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000252/2022-2023 | 916/BD | 22/03/2023 | 0 | Resource Division | 13.65 | 0 | 0
2263 | Barasat Division | Bangaon Sub-Division | Health assessment of existing OHR of Helencha PWSS (350 cum) and ancillary structures, Bagdah Block conducting Non-Destructive Test and through visual observation at within the jurisdiction Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000018/2024-2025 | 690/Bon | 07/06/2024 | 15 | SIRCON ENGINEERING SERVICES | 4.58 | 0 | 100
2264 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Repairing & renovation of Boundary wall, Earth Filling, Concreting and Repairing & renovation of 3.60 mtr. X 3.00 mtr. size Pump House with sanitary and water supply arrangement at 2nd TW Site of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000077/2025-2026 | 1902/BD | 05/06/2025 | 120 | KAMAL HALDER. | 10.52 | 0 | 0
2265 | Barasat Division | Bangaon Sub-Division | Repairing and renovation of 150 Cum C.W.R. for Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000400/2025-2026 | 817/Bon | 26/06/2025 | 45 | KAMAL HALDER. | 2.15 | 0 | 0
2266 | Barasat Division | Bangaon Sub-Division | Construction of Latrine at Head Work site for Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000610/2025-2026 | 640/Bon | 21/05/2025 | 45 | KAMAL HALDER. | 2.4 | 0 | 0
2267 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the mouzas into Swajal Gram including laying of UPVC pipe and allied works under Augmentation work at Helencha W/S Scheme Bagdah block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. (Part-B). | Assistant Engineer | Junior Engineer | ORD/000767/2024-2025 | 3267/BD | 25/11/2024 | 300 | ABDUL HAMID GAZI. | 27.07 | 0 | 35
2268 | Barasat Division | Bangaon Sub-Division | Repairing and renovation of Pump House No.- 3 under Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2024-2025 | 1396/Bon | 27/11/2024 | 20 | KAMAL HALDER. | 1.76 | 0 | 100
2269 | Barasat Division | Bangaon Sub-Division | Hiring of an Additional Vehicle (Diesel) for the site inspection of different Bongaon ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. (Period from:-01/09/2024 to 28/02/ 2025) | Assistant Engineer | Junior Engineer | ORD/001035/2024-2025 | 1076/Bon | 30/08/2024 | 182 | PRIYAM ENTERPRISE | 0.86 | 0 | 0
2270 | Barasat Division | Bangaon Sub-Division | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. period from 01.07.2024 to 31.08.2024. | Assistant Engineer | Junior Engineer | ORD/001065/2024-2025 | 801/Bon | 28/06/2024 | 61 | VAI ENTERPRISE. | 0.29 | 0 | 0
2271 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Sinking of 2 (two) no. 300 mm. x 200 mm. dia.250 mtr deep Replacement Tubewell by D.R. Rig method with UPVC pipe & UPVC ribbed strainer for Augmentation of Helencha Water Supply Scheme (H/W Site & 2nd T/W Site) under Bongaon Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001117/2023-2024 | 2941/BD | 27/09/2023 | 60 | JOY GURU ENTERPRISE | 32.22 | 0 | 100
2272 | Barasat Division | Bangaon Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line and Providing (FHTC) for augmentation of Helencha Water Supply Scheme, Bagdah Block, under Bongaon Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001170/2022-2023 | 754/BD | 09/03/2023 | 90 | MONDAL ENTERPRISE. (BARASAT) | 684.22 | 425.85 | 100
2273 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Renovation and repairing of Boundary wall at Head Work site for Augmentation of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001741/2023-2024 | 537/BD | 21/02/2024 | 360 | ACHINTA KUMAR HALDER. | 15.42 | 0 | 100
2274 | Barasat Division | Bangaon Sub-Division | Acceptance cum work order for Improvement of Iron Elimination Plant and other related allied works and Construction of Approach Road at Head work site under Augmentation of Helencha Water Supply Scheme, Bagdah Block within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001785/2023-2024 | 629/BD | 28/02/2024 | 675 | NEER UDYOG | 8.93 | 0 | 0
2275 | Barasat Division | Bangaon Sub-Division | Repairing and renovation of Compressor Room for Iron Elimination Plant under Augmentation of Helencha Water Supply Scheme within the jurisdiction of Bongaon Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002506/2023-2024 | 640/Bon | 14/08/2023 | 21 | MONDAL & CO.(BON) | 1.59 | 0 | 100
2276 | Barasat Division | Bangaon Sub-Division | Hiring of an Additional Vehicle (Diesel) for the site inspection of different ongoing schemes under JJM Program at Bongaon Sub-Division, P.H.E.Dte. period from 01.01.2024 to 30.06.2024. | Assistant Engineer | Junior Engineer | ORD/002553/2023-2024 | 1022/Bon | 29/12/2023 | 183 | VAI ENTERPRISE. | 0.86 | 0 | 0
2277 | Barasat Division | Bangaon Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000155/2022-2023 | 1258/BD | 25/04/2023 | 0 | Resource Division | 147.75 | 0 | 0
2278 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing FHTC (Functional Household Tap Connection) for Augmentation of Parui Zone-I water supply scheme in Swarupnagar Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000073/2023-2024 | 1440/BD | 11/05/2023 | 90 | SANJIB DEY | 113.91 | 63.96 | 60
2279 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI / UPVC distribution pipe line & Providing FHTC (Functional Household Tap Connection) by Augmentation for Parui (Zone - II) water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000150/2023-2024 | 1711/BD | 08/06/2023 | 749 | ALOK ENTERPRSE. (A UNIT OF SAKET TREXIM PVT.LTD) | 583.8 | 90.71 | 25
2280 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Renovation of Arsenic cum Iron Removal Plant at Parui W/S Scheme including increasing the height of back wash tank at Swarupnagar Block under Basirhat Sub Division, PHE Dte. capacity - 160.00 cum/hr. | Assistant Engineer | Junior Engineer | ORD/002034/2023-2024 | 925/BD | 15/03/2024 | 360 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 37.26 | 0 | 50
2281 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE | Assistant Engineer | Junior Engineer | ORD/002494/2021-2022 | 461 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.04 | 2.04 | 1
2282 | Barasat Division | Basirhat Sub-Division | Route Survey,design drawing & DPR Preparation for PARUI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002888/2021-2022 | 460/BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.84 | 4.84 | 1
2283 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000013/2023-2024 | 1262/BD | 25/04/2023 | 0 | Resource Division | 190.25 | 0 | 0
2284 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000069/2023-2024 | 1645/BD | 02/06/2023 | 0 | Resource Division | 10.32 | 0 | 0
2285 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000144/2023-2024 | 4421/BD | 10/11/2023 | 0 | Resource Division | 39.07 | 0 | 0
2286 | Barasat Division | Basirhat Sub-Division | Regarding Restoration charges for road damages. | Assistant Engineer | Junior Engineer | BILL/03463/2023-2024 | BP-2023-24-830 | 15/03/2024 | 0 | EXECUTIVE ENGINEER BARASAT HIGHWAY DIVISION NO -I P.W. (ROADS) DIRECTORATE | 48.02 | 0 | 0
2287 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Aturia Zone-II water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000032/2023-2024 | 1305/BD | 26/04/2023 | 90 | JAL PRAVAHIKA PVT. LTD. | 282.82 | 0 | 31
2288 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of DI/UPVC distribution pipe line and providing Functional Household Tap Connection for Augmentation of Aturia (Zone-I) water supply scheme in Baduria Block under Barasat Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 1702/BD | 08/06/2023 | 876 | EFFLUENT & WATERTREATMENT ENGINEERS (P) LTD. | 546.47 | 67.11 | 41
2289 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Sinking of 1 no. 300 mm. x 200 mm. big dia. 300 mtr deep tubewell by D.R. Rig method using PVC pipe & strainer having 300 mm dia. 36 mtr. long filter for Augmentation of Aturia Zone-II water supply scheme in Baduria Block of Basirhat Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000999/2023-2024 | 2803/BD | 12/09/2023 | 30 | SAHA CONSTRUCTION & CO | 21.53 | 0 | 0
2290 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Eucalyptus Bullah Pilling for Emergency protection Work of Pipe line at different places for Augmentation of Aturia Zone-I Water Supply Scheme of Basirhat Sub Division under Barasat Division P.H.E. | Assistant Engineer | Junior Engineer | ORD/001560/2024-2025 | 724/BD | 07/03/2025 | 30 | SHIBU BISWAS. | 44.01 | 0 | 0
2291 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for ATURIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001976/2021-2022 | 348/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.97 | 4.97 | 1
2292 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for ATURIA Water Supply Scheme in Baduria Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001977/2021-2022 | 349/BHTSD | 14/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.98 | 1.91 | 1
2293 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2023-2024 | 1253/BD | 25/04/2023 | 0 | Resource Division | 86.25 | 0 | 0
2294 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000140/2023-2024 | 4409/BD | 10/11/2023 | 0 | Resource Division | 42.27 | 0 | 0
2295 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line with Protection works in Sankardaha, Khariberia, Bargan Gopalpur & Mallickgheri mouzas under Khariberia w/s scheme within Minakhan block, Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2025-2026 | 1798/BD | 30/05/2025 | 30 | ATCO ENTERPRISE | 118.72 | 0 | 0
2296 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 250 Cum capacity 20 mtr staging height R.C.C Over Head water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap, Construction of switch room cum chlorine room with sanitary & water supply arrangement i/c plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.) for Khariberia w/s scheme, Minakhan Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000139/2023-2024 | 1705/BD | 08/06/2023 | 1095 | M/S PROGATI ENTERPRISE. | 400.07 | 155.68 | 90
2297 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Bamanpukuria & Khariberia w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001500/2024-2025 | 635/BD | 28/02/2025 | 45 | ACME CONSTRUCTION | 51.71 | 0 | 0
2298 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIBARIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002719/2021-2022 | 282/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 0
2299 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (KHARIBARIA Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B). | Assistant Engineer | Junior Engineer | ORD/002720/2021-2022 | 283/HSD | 09/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.49 | 2.49 | 0
2300 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000217/2022-2023 | 896/BD | 22/03/2023 | 0 | Resource Division | 18.77 | 0 | 0
2301 | Barasat Division | Habra Sub-Division | Formal work order for Land development, Construction of Office cum Guard room and Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at Zonal Head work site - XIV i.e. Kumra /Zonal Head work site - XVI i.e.Nangla including Laying Distribution System within the jurisdiction of (Zone-XIV) /(Zone-XVI), Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Surface Water based Water Supply Scheme for Arsenic Affected Areas of Habra-Gaighata & Adjoining Mouzas under North 24 Parganas District project within Barasat Division, P.H.E. Dte. Habra-I Block PART-C / Habra-I Block PART-E. | Assistant Engineer | Junior Engineer | ORD/001613/2023-2024 | 110/BD | 10/01/2024 | 910 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3691.85 | 0 | 88
2302 | Barasat Division | Habra Sub-Division | Formal work order for construction of 5 nos. different capacity OHR, Land development, Construction of Office cum Guard room, Switch cum Chlorine Room, Boundary wall, Surface drain and related allied works at different Zonal Head work site including Laying Distribution System and FHTC of surface based water supply scheme for arsenic affected areas of Habra-Gaighata & adjoining mouzas in the district North 24 Parganas under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000798/2023-2024 | 2714/BD | 05/09/2023 | 1095 | S & P ENTERPRISE | 5112.52 | 0 | 40
2303 | Barasat Division | Barasat Sadar Sub-Division | Formal work order for Construction of 200 cum capacity 20 mtr. height R.C.C. Over Head Reservoir as per Deptt. design, drawing & specification including bored pile & pile cap, laying of DI rising main & distribution pipe line by DI/UPVC and Providing FHTC for Augmentaion of Kashimpur water supply scheme under Barasat Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000157/2023-2024 | 1716/BD | 08/06/2023 | 366 | S.S.ENTERPRISE. (BAMANGACHI) | 318.43 | 65.89 | 90
2304 | Barasat Division | Barasat Sadar Sub-Division | Different works in connection with Augmentation Kashimpur PWSS (1st Tubewell site - Pump House). | Assistant Engineer | Junior Engineer | ORD/000471/2024-2025 | 586/BSD | 10/09/2024 | 20 | K.C. ENTERPRISE | 3.53 | 0 | 100
2305 | Barasat Division | Barasat Sadar Sub-Division | Preparation of DPR in connection of augumentation of Kashimpur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000607/2022-2023 | 666/BSD | 25/08/2022 | 30 | RADIANT | 3.04 | 0 | 100
2306 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. dia. 300 mtr deep as a Replacement of Tubewell by D.R. Rig method, having 250mm dia 36.0 mtr. long UPVC housing pipe & 150mm dia 30 mtr. long UPVC ribbed strainer for Augmentation of Kashimpur Water Supply Scheme at Head Work Site under Barasat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000683/2023-2024 | 2460/BD | 17/08/2023 | 30 | M/S K.P.PAL. | 16.08 | 11.87 | 100
2307 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Hiring diesel luxury car daily basis (From 22.11.2023 to 31.05.2024) for the Office uses of the Assistant Engineer (HQ) Barasat Division, P.H.Dte. | Assistant Engineer | Junior Engineer | ORD/001422/2023-2024 | 4461/BD | 21/11/2023 | 192 | KRISHNA SAHA. | 0.91 | 0 | 18
2308 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-01-2024 to 31-03-2024). | Assistant Engineer | Junior Engineer | ORD/001461/2023-2024 | 4696/BD | 12/12/2023 | 91 | DIPANKAR NASKAR. | 0.43 | 0 | 100
2309 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Sinking of 1 (one) no. 250 mm. x 150 mm. big dia. 210 mtr deep Tubewell by D.R. Rig method having 250 mm dia 42.0 mtr. long PVC housing pipe & 150 mm dia 30.0 mtr. long filter for Augmentation Kashimpur Water Supply Scheme (2nd T/W Site) of Barasat Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001770/2023-2024 | 587/BD | 23/02/2024 | 30 | SUBHAJIT SAHA | 11.22 | 0 | 100
2310 | Barasat Division | Barasat Sadar Sub-Division | Installation of Har Ghar Jal (HGJ) Display Board at different village of verious PWSS of Barasat-I Block within Barasat Sub Division under Barasat Division, P.H.E. Dte. Part-B | Assistant Engineer | Junior Engineer | ORD/001853/2023-2024 | 1121./1/BSD | 09/02/2024 | 4 | BIBHAS PAL. | 0.88 | 0 | 100
2311 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for the work of Hiring Diesel Luxury Car on daily basis for the Office of the Dy. Superintending Engineer-I, Monitoring Cell, PHE Dte. (Period from 01-04-2024 to 30-09-2024). | Assistant Engineer | Junior Engineer | ORD/001928/2023-2024 | 914/BD | 15/03/2024 | 183 | DIPANKAR NASKAR. | 0.87 | 0 | 100
2312 | Barasat Division | Barasat Sadar Sub-Division | Acceptance cum work order for Hiring diesel luxury car daily basis (From 01.06.2024 to 30.11.2024) for the Office uses of the Assistant Engineer (HQ) Barasat Division, P.H.Dte. | Assistant Engineer | Junior Engineer | ORD/002257/2023-2024 | 845/BD | 13/03/2024 | 183 | KRISHNA SAHA. | 0.87 | 0 | 0
2313 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2023-2024 | 1282/BD | 25/04/2023 | 0 | Resource Division | 13.18 | 0 | 0
2314 | Barasat Division | Barasat Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000074/2023-2024 | 1671/BD | 06/06/2023 | 0 | Resource Division | 9.76 | 0 | 0
2315 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SADPUR Water Supply Scheme at Habra - I Block within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. (Phase - I) | Assistant Engineer | Junior Engineer | ORD/000592/2022-2023 | 2627/BD | 05/09/2022 | 660 | M/S SUKANTA ENTERPRISE. | 48.49 | 26.76 | 100
2316 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Restoration of different diameter existing pipe lines by laying UPVC pipes and allied works of Sadpur W/S scheme due to up gradation of different roads within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/003033/2021-2022 | 2047//BD | 21/09/2021 | 30 | MONDAL ENTERPRISE. (BARASAT) | 26.59 | 11.14 | 100
2317 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of anchor block for resting of 250/200 mm dia DI distribution main pipeline over existing concrete wall beside Basanti Highway at different places for Mathbari Abad w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000262/2025-2026 | 2348/BD | 08/07/2025 | 60 | M/S DATTA ENTERPRISE. | 6.1 | 0 | 0
2318 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Mathbari Abad w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000524/2024-2025 | 2796/BD | 25/09/2024 | 90 | M/S PROGATI ENTERPRISE. | 140.81 | 0 | 70
2319 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of road for damage portion at different places in connection with retrofitting of Boyermari within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2024-2025 | 992/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.9 | 0 | 100
2320 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000554/2024-2025 | 996/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.91 | 0 | 100
2321 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of pipeline with bamboo pilling at different places at Khas Sankardaha & Sankardaha Abad within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000556/2024-2025 | 998/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.97 | 0 | 100
2322 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 200 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000558/2024-2025 | 1000/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.79 | 0 | 100
2323 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of pipeline with UC Bullah pilling at different places at Boyermari within Mathbari Abad w/s scheme (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000563/2024-2025 | 1003/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 100
2324 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of pipeline with UC Bullah pilling at different places at Khas Sankardaha & Sankardaha Abad within Mathbari Abad w/s scheme (Scheme code-SM/15825), Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000566/2024-2025 | 1006/HSD | 29/08/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 100
2325 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 250 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000583/2024-2025 | 1160/HSD | 25/09/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.83 | 0 | 100
2326 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Supply and installation of 150 mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Mathbari Abad (Scheme code-SM/15825) water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000585/2024-2025 | 1171/HSD | 26/09/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.79 | 0 | 100
2327 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent resting of pipeline with bamboo pilling at different places at Boyermari within Mathbari Abad (Scheme code-SM/15825) w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2024-2025 | 1178/HSD | 30/09/2024 | 10 | ANKUSH CONSTRUCTION & CO. | 0.99 | 0 | 100
2328 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile, Construction of 250 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap within Mathbari Abad W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000900/2023-2024 | 2704/BD | 04/09/2023 | 1094 | M/S DATTA ENTERPRISE. | 442.43 | 0 | 85
2329 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Mathbari Abad W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001910/2023-2024 | 282/HSD | 06/03/2024 | 10 | M/S DATTA ENTERPRISE. | 0.84 | 0 | 22
2330 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-1 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002482/2023-2024 | 36/HSD | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 100
2331 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Hiring of one no. DIESEL MOTOR CAB (BS-VI) on daily hire basis for use of the Assistant Engineer, HASNABAD SUB-DIVISION, PHE DTE. Period from 01.11.23 to 30.04.24 | Assistant Engineer | Junior Engineer | ORD/002507/2023-2024 | 1315/HSD | 30/10/2023 | 183 | RANJIT KUMAR MANDAL | 0.86 | 0 | 0
2332 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002520/2023-2024 | ABDULALIMMONDAL | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 0
2333 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for 1 no. pump connection at PH No.-2 in connection with Augmentation of Gabberia water supply scheme, Sandeshkhali-II block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002521/2023-2024 | 35/HSD. | 09/01/2024 | 10 | ABDUL ALIM MONDAL. | 0.79 | 0 | 100
2334 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A). | Assistant Engineer | Junior Engineer | ORD/002744/2021-2022 | 348/HSD | 21/02/2022 | 15 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 4.83 | 4.83 | 1
2335 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (MATBARI ABAD Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002745/2021-2022 | 349/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 1
2336 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000232/2022-2023 | 868/BD | 22/03/2023 | 0 | Resource Division | 23.84 | 0 | 0
2337 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 & 3 (Size-3.60x3.00 mtr.), Laying of DI rising main, DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. UPVC/DI distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Atpukur W/S Scheme (Zone-I), Minakhan Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000851/2023-2024 | 2616/BD | 29/08/2023 | 1096 | M/S PROGATI ENTERPRISE. | 461.22 | 166.52 | 37
2338 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for within Atpukur (Z-I) and Uchildaha w/s scheme, Minakhan block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001497/2024-2025 | 633/BD | 28/02/2025 | 45 | SHIBU BISWAS. | 51.76 | 0 | 0
2339 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-I). | Assistant Engineer | Junior Engineer | ORD/001905/2023-2024 | 277/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
2340 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-J). | Assistant Engineer | Junior Engineer | ORD/001906/2023-2024 | 278/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
2341 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-C). | Assistant Engineer | Junior Engineer | ORD/001911/2023-2024 | 283/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
2342 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-F). | Assistant Engineer | Junior Engineer | ORD/001915/2023-2024 | 287/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
2343 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-G). | Assistant Engineer | Junior Engineer | ORD/001917/2023-2024 | 289/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.87 | 0 | 100
2344 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Minakhan block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-I). | Assistant Engineer | Junior Engineer | ORD/001919/2023-2024 | 291/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.87 | 0 | 100
2345 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-A). | Assistant Engineer | Junior Engineer | ORD/001934/2023-2024 | 256/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
2346 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-D). | Assistant Engineer | Junior Engineer | ORD/001937/2023-2024 | 263/HSD | 06/03/2024 | 10 | S.M.TRADERS. | 0.88 | 0 | 100
2347 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-E). | Assistant Engineer | Junior Engineer | ORD/001938/2023-2024 | 265-HSD. | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
2348 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-F). | Assistant Engineer | Junior Engineer | ORD/001939/2023-2024 | 267/HSD | 06/03/2024 | 10 | BIBHAS PAL. | 0.88 | 0 | 100
2349 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-B). | Assistant Engineer | Junior Engineer | ORD/001940/2023-2024 | 258/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
2350 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Installation of scheme information board at different villages of various PWSS of Hasnabad block within Hasnasbad Sub-Division under Barasat Division, P.H.E.Dte. (Part-G). | Assistant Engineer | Junior Engineer | ORD/001941/2023-2024 | 270/HSD | 06/03/2024 | 10 | M.R.CONSTRUCTION. | 0.88 | 0 | 100
2351 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002697/2021-2022 | 239/HSD | 02/02/2022 | 15 | UMWELT ENGINEER PVT.LTD. | 4.83 | 4.83 | 0
2352 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (ATPUKUR Z-I Water Supply Scheme) in MINAKHAN BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002698/2021-2022 | 240/HSD | 02/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.6 | 3.6 | 0
2353 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000224/2022-2023 | 875/BD | 22/03/2023 | 0 | Resource Division | 28.4 | 0 | 0
2354 | Barasat Division | Hasnabad Sub-Division | Formal work order for Additional Laying of UPVC distribution pipe line, protection works & other allied works within Petua Dhanihati w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000473/2024-2025 | 2734/BD | 20/09/2024 | 150 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 169.19 | 0 | 100
2355 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Temporary approach road for movement of winch machine and other allied machineries at Head Work site within Petua Dhanihati W/S scheme, Sandeshkhali-I block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000564/2024-2025 | 1004/HSd | 29/08/2024 | 10 | S.K.ENTERPRISE. | 0.9 | 0 | 100
2356 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary & water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No-2 (Size-3.60x3.00 mtr.), Laying of DI rising main and DI/UPVC distribution pipe line, Providing Functional Household Tap Connection, Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places, Construction of 200 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap for Petua Dhanihati W/S Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000901/2023-2024 | 2705/BD | 04/09/2023 | 1096 | M/S NIRMAN CONSTRUCTION. | 379.24 | 0 | 70
2357 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PETUA DHANIHATI Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/002746/2021-2022 | 350/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 1
2358 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (PETUA DHANIHATI Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer | Junior Engineer | ORD/002747/2021-2022 | 351/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.51 | 4.51 | 1
2359 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000227/2022-2023 | 879/BD | 22/03/2023 | 0 | Resource Division | 23.37 | 0 | 0
2360 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Fakirtakia mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Fakirtakia w/s scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001113/2021-2022 | 180/BD | 20/01/2022 | 45 | R.K.MANDAL AND CO. | 74.88 | 74.79 | 1
2361 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001761/2021-2022 | 471/HSD | 10/03/2022 | 10 | JESMINE ENTERPRISE. | 3.82 | 3.82 | 1
2362 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Fakirtakia w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001762/2021-2022 | 472/HSD | 10/03/2022 | 10 | M/S MITRA CONSTRUCTION. | 3.89 | 3.89 | 1
2363 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000088/2023-2024 | 1821/BD | 19/06/2023 | 0 | Resource Division | 16.88 | 0 | 0
2364 | Barasat Division | Basirhat Sub-Division | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area of Ghona Water Supply Scheme at Basirhat-II Block under Barasat Division, PHE Dte.(Phase-I). | Assistant Engineer | Junior Engineer | ORD/000332/2021-2022 | 1653/BD | 07/09/2021 | 30 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 57.32 | 55.48 | 1
2365 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kumarjole Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000988/2021-2022 | 2171/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.24 | 4.24 | 1
2366 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for GHONA Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001958/2021-2022 | 309/BHTSD | 07/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.15 | 3.15 | 1
2367 | Barasat Division | Basirhat Sub-Division | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kumarjole Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002037/2021-2022 | 2171/HSD | 28/12/2021 | 21 | UMWELT ENGINEER PVT.LTD. | 4.24 | 0 | 1
2368 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for sinking of Additional 1 no. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter within Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000892/2024-2025 | 3376/BD | 02/12/2024 | 60 | M/S K.P.PAL. | 25.88 | 0 | 0
2369 | Barasat Division | Hasnabad Sub-Division | Formal work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2,3,4 (Size-3.60x3.00 mtr),Laying of DI rising main and DI/UPVC distribution pipe line,Providing Functional Household Tap Connection,Protection works for different dia. DI/UPVC rising/distribution pipeline by UC bullah/Bamboo pile at different places,Construction of 450 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Dakshin Akhratala water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/001208/2023-2024 | 4047/BD | 13/10/2023 | 1091 | M/S DATTA ENTERPRISE. | 753.32 | 0 | 80
2370 | Barasat Division | Hasnabad Sub-Division | Route Survey, Design Drawing & Preparation of DPR for Kalupur Water Supply Scheme in Bongaon Block within the Jurisdiction of Bongaon Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/001315/2021-2022 | 122/Bon | 18/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.8 | 0 | 1
2371 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Additional Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection for Dakshin Akhratala w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001414/2024-2025 | 144/BD | 13/01/2025 | 75 | JESMINE ENTERPRISE. | 10.58 | 0 | 0
2372 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-A) | Assistant Engineer |  | ORD/002738/2021-2022 | 314/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100
2373 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-B) | Assistant Engineer |  | ORD/002739/2021-2022 | 315/HSD | 15/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.82 | 4.82 | 100
2374 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Survey, Design Drawing & DPR Preparation for NEW PWSS (DAKSHIN AKHRATALA Water Supply Scheme) in SANDESHKHALI-I BLOCK under Barasat Division, PHE Dte. (PART-C) | Assistant Engineer |  | ORD/002740/2021-2022 | 336/HSD | 21/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.83 | 4.83 | 100
2375 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000008/2024-2025 | 3442/BD | 06/12/2024 | 0 | Resource Division | 38.05 | 0 | 0
2376 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer |  | RTOR000226/2022-2023 | 872/BD | 22/03/2023 | 0 | Resource Division | 296.35 | 0 | 0
2377 | Barasat Division | Basirhat Sub-Division | Formal work order for Laying of UPVC distribution pipe line and Providing FHTC (Functional Household Tap Connection) for Augmentation of Banglani Water Supply Scheme in Swarupnagar Block of North 24 Parganas District under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000717/2023-2024 | 2518/BD | 22/08/2023 | 676 | KINGS & CO. | 606.14 | 0 | 59
2378 | Barasat Division | Basirhat Sub-Division | Additional Survey work for DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002498/2021-2022 | 457 / BHTSD | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 1.07 | 1.07 | 100
2379 | Barasat Division | Basirhat Sub-Division | Route Survey, Design Drawing & DPR Preparation for BANGLANI Water Supply Scheme in Swarupnagar Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003053/2021-2022 | 456/BHT | 22/03/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.95 | 4.95 | 100
2380 | Barasat Division | Basirhat Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2023-2024 | 1238/BD | 25/04/2023 | 0 | Resource Division | 146.14 | 0 | 0
2381 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Protection works for rising main of 150mm dia. DI pipe line at pond of Muyajjem Husien Molla within Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000234/2022-2023 | 1143/HSD | 12/07/2022 | 10 | MONDAL & CO. (BASIRHAT). | 4.69 | 4.65 | 1
2382 | Barasat Division | Hasnabad Sub-Division | Construction of boundary wall within brick structure & approach road at O.H.R. site within Sultanpur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002645/2021-2022 | 548/BD. | 23/02/2022 | 30 | MONDAL & CO. (BASIRHAT). | 14.69 | 14.69 | 1
2383 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Patkelpota Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002871/2021-2022 | 579/HSD | 28/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.55 | 4.13 | 1
2384 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Turia Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002878/2021-2022 | 587/HSD | 28/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.57 | 4.12 | 1
2385 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Joykrishnapur Mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002880/2021-2022 | 589/HSD | 28/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.53 | 4.04 | 1
2386 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places of Patkelpota abad mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002882/2021-2022 | 591/HSD | 29/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.51 | 4.24 | 1
2387 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of 90mm dia. UPVC pipe line at different places of Joykrishnapur mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002884/2021-2022 | 593/HSD | 29/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.86 | 4.53 | 1
2388 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of different dia. UPVC pipe line at different places of Turia mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002886/2021-2022 | 595/HSD | 31/03/2022 | 15 | MONDAL & CO. (BASIRHAT). | 4.81 | 4.15 | 1
2389 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of 90 mm dia. UPVC pipe line at different places of Patkelpota abad mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002890/2021-2022 | 599/HSD | 31/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.56 | 4.45 | 1
2390 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by laying of different dia. UPVC pipe line at different places of Patkelpota mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002892/2021-2022 | 601/HSD | 31/03/2022 | 15 | TRISHA ENTERPRISE & CO. | 4.53 | 4.29 | 1
2391 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Emergent restoration of pipeline by withdrawing & relaying of different dia. UPVC pipe line at different places of Turia mouza within Sultanpur W/S Scheme, Minakhan block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002894/2021-2022 | 603/HSD | 31/03/2022 | 15 | ANKUSH CONSTRUCTION & CO. | 4.78 | 4.61 | 1
2392 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000079/2023-2024 | 1816/BD | 19/06/2023 | 0 | Resource Division | 40.04 | 0 | 0
2393 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Construction of switch room cum chlorine room with sanitary and water supply arrangement including plinth protection at PH No.-1 (Size-5.40x3.60 mtr.) & PH No.-2 (Size-3.60x3.00 mtr.) for Augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000026/2025-2026 | 1516/BD | 13/05/2025 | 90 | M/S MONDAL CONSTRUCTION | 17.62 | 0 | 0
2394 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Land development at Pump House No-1 in connection with augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000055/2025-2026 | 842/HSD | 15/05/2025 | 10 | MD.SALIM GAZI. | 1.49 | 0 | 0
2395 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Laying of 50 mm dia. UPVC pipe line for providing 3 nos. tap connection at near Sulkuni Abad area within Bhabanipur W/S Scheme, Hasnabad block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000296/2023-2024 | 792/HSD | 13/07/2023 | 7 | M/S K.B.ENTERPRISE. | 0.86 | 0 | 0
2396 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, Construction of 600 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap and providing Functional Household Tap Connection in connection with Augmentaion of Bhabanipur water supply scheme (Zone-II), Hasnabad Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000784/2023-2024 | 2600/BD | 28/08/2023 | 579 | M/S S.S.ENTERPRISE. (SOUTH) | 956.1 | 0 | 70
2397 | Barasat Division | Hasnabad Sub-Division | Formal work order for Laying of DI rising main, DI/UPVC distribution pipe line, construction of 400cum capacity 20mtr staging height R.C.C Over head Reservoir as per Dept. design, drawing & specification including bored pile with pile cap and providing Functional Household Tap connection in connection with Augmentation of Bhabanipur Water Supply Scheme(Zone-I), Hasnabad Block under Hasnabad Sub-Division, PHE Dte. under Barasat Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000852/2023-2024 | 2651/BD | 01/09/2023 | 366 | SUPRITI ENTERPRISE. | 867.51 | 0 | 45
2398 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 3 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tube well by D.R. Rig method at PH No.-1, 2 & 3 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bhabanipur w/s scheme (Z-II), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001933/2023-2024 | 916/BD | 15/03/2024 | 60 | M/S K.P.PAL. | 89.28 | 0 | 100
2399 | Barasat Division | Hasnabad Sub-Division | Acceptance cum work order for Sinking of 2 nos. 300 mm. x 200 mm. dia. 360 mtr deep Tubewell by D.R. Rig method at PH No.-1 & 2 with PVC pipe & strainer having 300mm dia 48 mtr. long housing pipe & 200mm dia 30 mtr. long filter for Augmentation of Bhabanipur w/s scheme (Z-I), Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002031/2023-2024 | 931/BD | 15/03/2024 | 45 | AAHAN CONSTRUCTION | 59.17 | 0 | 0
2400 | Barasat Division | Hasnabad Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000235/2022-2023 | 911/BD | 22/03/2023 | 0 | Resource Division | 348.37 | 0 | 0
2401 | Barasat Division | Habra Sub-Division | Formal work order for Providing Functional House Hold Tap Connection (FHTC) from existing and new proposed distribution system for Augmentation of Kosdelpur & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000353/2022-2023 | 2200/BD | 26/07/2022 | 90 | H.I.ENTERPRISE. | 333.61 | 316.31 | 1
2402 | Barasat Division | Habra Sub-Division | Construction of Service Road (30 Mtr. Length X 2 Mtr. Width) for Pump House No:1 of khosdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000475/2024-2025 | 696/HAB | 25/07/2024 | 10 | M/S GUHA CONSTRUCTION. | 1.83 | 0 | 0
2403 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Repairing of Boundary Wall for PH-1 of Khasdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000592/2024-2025 | 3063/BD | 25/10/2024 | 30 | ANJALI CONSTRUCTION. | 5.08 | 0 | 0
2404 | Barasat Division | Habra Sub-Division | Construction of Boundary Wall 30 m Length for Pump House No - 2 of Khosdelpur water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction Habra Sub-Division under Barasat Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000596/2024-2025 | 912/HAB | 30/10/2024 | 40 | M/S SUKANTA ENTERPRISE. | 4.83 | 0 | 0
2405 | Barasat Division | Habra Sub-Division | Special repair and renovation of pump house and other Allied Works for Pump House No - 2 of Khosdelpur and Adj. Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000602/2024-2025 | 915/HAB | 30/10/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.6 | 0 | 0
2406 | Barasat Division | Habra Sub-Division | Special repair & renovation of pump house and other Allied Works for Pump House No - 1 of Khosdelpur & Adj. Mouzas W/S scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000893/2024-2025 | 925/HAB | 05/11/2024 | 20 | M/S SUKANTA ENTERPRISE. | 2.66 | 0 | 0
2407 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Sinking of 2 nos. 250 mm. x 150 mm. dia. 270 mtr deep tubewell by D.R. Rig method having 250 mm. dia. 36 mtr. long housing pipe & 150 mm. dia. 30 mtr. long Filter at Pump House No. - 1 & 2 for Augmentation of Khosdelpur & Adjoining Mouzas water supply scheme within the jurisdiction of Habra Sub-Division, under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000914/2023-2024 | 2774/BD | 11/09/2023 | 60 | ANJALI ENTERPRISE. | 28.99 | 0 | 80
2408 | Barasat Division | Habra Sub-Division | Improvement of Iron Elimination Plant at Khosdelpur & adj. Mouzas W/S Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001434/2023-2024 | 688/HAB | 01/11/2023 | 30 | M/S SUKANTA ENTERPRISE. | 3.51 | 0 | 100
2409 | Barasat Division | Habra Sub-Division | Acceptance cum work order for Construction of Service Road (15 Mtr. Length X 2 Mtr. Width) for Pump House No:2 of Khosdelpur Water Supply Scheme in connection with Augmentation work under JJM project within the jurisdiction of Habra Sub-Division under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001898/2023-2024 | 170/HAB | 19/02/2024 | 15 | M/S SUKANTA ENTERPRISE. | 0.92 | 0 | 0
2410 | Barasat Division | Habra Sub-Division | Repairing & renovation of Pump House No. 1 & 2 of Khosdelpur& adj. mouzas W/S scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002983/2021-2022 | 513/HAB | 10/12/2021 | 30 | M/S SUKANTA ENTERPRISE. | 1.56 | 1.5 | 1
2411 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000078/2022-2023 | 3105/BD | 18/10/2022 | 0 | Resource Division | 0.02 | 0 | 0
2412 | Barasat Division | Habra Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000131/2022-2023 | 3798/BD | 22/12/2022 | 0 | Resource Division | 9.95 | 0 | 0
Total | [10 empty] | 210514.72 | 51353.03