## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Murshidabad Division | Kandi Sub-Division | Kamalakantapur PWSS to accommodate FHTC of 1518 nos household under Jal Jeevan Mission of Bharatpur-I Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER |  | ORD/000255/2023-2024 | 2492/MURD | 11/08/2023 | 60 | RATAN DUTTA | 80.18 | 0 | 15
2 | Murshidabad Division | Berhampur M/E Division | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 10
3 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
4 | Murshidabad Division | Berhampur M/E Division | Renovation of Filter Media of Existing Modified AIRP of (Capacity 180 Cum/hr.) at Garaimari Zone-I Water Supply Scheme of Domkal Block under Murshidabad Division, P.H.Eengineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000252/2024-2025 | 228/MURD | 27/01/2025 | 45 | SOM CONSTRUCTION AGENCY | 28.21 | 0 | 0
5 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
6 | Murshidabad Division | Kandi Sub-Division | Providing FHTC Connection to 274 nos household , Laying of Distribution System,Rising Main , Construction of Pump House with sanitary and Water Supply Arrangement , Pump House cum Blower room And Boundary Wall for work of MATUA PWSS Bharatpur II Block under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000157/2023-2024 | 1932/MURD | 18/07/2023 | 602 | SANTA TRADING | 60.51 | 0 | 60
7 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMLAI and MATHUA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000393/2023-2024 | 2795/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
8 | Murshidabad Division | Kandi Sub-Division | Construction of Pump House, Boundary Wall , Path Way of Matua PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000830/2023-2024 | 780/MURD | 14/03/2024 | 45 | SANTA TRADING | 14.19 | 0 | 90
9 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000217/2023-2024 | 1219/MURD/10 | 03/05/2023 | 0 | Resource Division | 0.76 | 0 | 0
10 | Murshidabad Division | Berhampur M/E Division | Augmentation of BILASPUR PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000079/2023-2024 | 1385/MURD | 22/05/2023 | 650 | ULTRA CONSTRUCTION. | 227.02 | 0 | 45
11 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
12 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000155/2023-2024 | 1180/MURD/04 | 29/04/2023 | 0 | Resource Division | 19.59 | 0 | 0
13 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System of MIRHATI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000854/2022-2023 | 789/MURD | 21/03/2023 | 742 | SUBHANKAR ROY | 139.07 | 0 | 30
14 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000084/2023-2024 | 1129/MURD/7 | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
15 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000340/2023-2024 | 79/MURD/07 | 09/01/2024 | 0 | Resource Division | 3.63 | 0 | 0
16 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000358/2023-2024 | MURD/439/03 | 08/02/2024 | 0 | Resource Division | 0.13 | 0 | 0
17 | Murshidabad Division | Berhampur M/E Division | Restoretion of Road State Highway at Najairpur to Islampore Road from chainge 0.00 kmp to 1.350 km shoulder damage amounting to Rs 637462.00 and Akheriganj to Katlamari road from chainge 8.00 km to 9.30 km. | ASSISTANT ENGINEER-I | Junior engineer-II | BILL/01231/2024-2025 | 492-MSD/2024-25 | 04/10/2024 | 0 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 34.8 | 0 | 0
18 | Murshidabad Division | Berhampur M/E Division | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000071/2024-2025 | 2022/MURD | 11/07/2024 | 345 | DHPE | 15.34 | 0 | 25
19 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Islampur PWSS Laying Distribution System, Laying Rising Main in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000249/2023-2024 | 2465/MURD | 09/08/2023 | 719 | M/S GUHA AND ROY | 333.65 | 0 | 25
20 | Murshidabad Division | Berhampur M/E Division | Augmentation of Islampur PWSS Repairing of Boundary Wall, Pump House & Existing OHR, Construction of 900 Cum OHR, P.H, B.W in Raninagar-I Block , under Murshidabad Division , PHE.Dte.PART_B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000316/2023-2024 | 2673/MURD | 24/08/2023 | 365 | M/S. UDYOG AND CO | 335.68 | 0 | 0
21 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
22 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Islampur PWSS of accommodate Providing Functional Household Tap Connection (1394 Nos) in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_C | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000355/2023-2024 | 2669/MURD | 24/08/2023 | 90 | M/S B.M. INDUSTRIES | 182.87 | 0 | 31
23 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000233/2023-2024 | 1219/MURD/07 | 03/05/2023 | 0 | Resource Division | 551.66 | 0 | 0
24 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0
25 | Murshidabad Division | Kandi Sub-Division | Augmentation of SATITARA under Jal Jeevan Mission of BURWAN Block, Kandi Sub Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000571/2023-2024 | 3291/MURD | 19/10/2023 | 713 | M/S. S. DAS AND ENTERPRISE | 1459.34 | 0 | 10
26 | Murshidabad Division | Kandi Sub-Division | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Satitara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000721/2023-2024 | 3874/MURD | 18/12/2023 | 30 | DIPAYAN DEY | 5.35 | 0 | 100
27 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000370/2023-2024 | MURD/439/05 | 08/02/2024 | 0 | Resource Division | 4.1 | 0 | 0
28 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 0 | 100
29 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
30 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000092/2023-2024 | 1147/MURD/7 | 27/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
31 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | Junior Engineer | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 0 | 100
32 | Murshidabad Division | Islampur Sub-Division | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000440/2023-2024 | 2888/MURD | 12/09/2023 | 750 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 75
33 | Murshidabad Division | Islampur Sub-Division | Cleaning the chokage of AC/DI/CI/UPVC pipes in the existing pipeline by split bamboo for Garibpur Zone-II PWSS under Islampur Sub-Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000508/2023-2024 | 401/ISD | 29/09/2023 | 7 | RAJAKINI ENTERPRISE | 0.81 | 0 | 100
34 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MADNA Zone-I Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000041/2025-2026 | 1156/MURD | 20/05/2025 | 60 | AUDY ENGINEERING | 23 | 0 | 0
35 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
36 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
37 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
38 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000093/2023-2024 | 1147/MURD/8 | 27/04/2023 | 0 | Resource Division | 128.8 | 0 | 0
39 | Murshidabad Division | Berhampur M/E Division | SITARAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000012/2023-2024 | 978/MURD | 10/04/2023 | 1279 | HOQUEDAR ALI | 389.19 | 0 | 15
40 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
41 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SITARAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000618/2023-2024 | 3393/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 50
42 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000278/2023-2024 | 1230/MURD/20 | 04/05/2023 | 0 | Resource Division | 29.01 | 0 | 0
43 | Murshidabad Division | Berhampur M/E Division | Augmentation of MURADPUR JALANGI ZONE-I PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000531/2023-2024 | 3114/MURD | 05/10/2023 | 543 | ARINDAM MAJUMDAR | 187.44 | 0 | 60
44 | Murshidabad Division | Berhampur M/E Division | Refilling of sand layers, Activated Alumina & existing gravel after washing along with allied works of AIRP at Saikhpara Area (Capacity 100 Cum/hr.) & Muradpur Jalangi Z-I (Capacity 54.00 Cum/hr.) Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000842/2023-2024 | 820/MURD | 15/03/2024 | 244 | M/S. S. DAS AND ENTERPRISE | 70.68 | 0 | 40
45 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
46 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000235/2023-2024 | 1219/MURD/15 | 03/05/2023 | 0 | Resource Division | 26 | 0 | 0
47 | Murshidabad Division | Kandi Sub-Division | Formal work order for MANDALSAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Khargram Block of Murshidabad District under Kandi Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000803/2022-2023 | 625/MURD | 03/03/2023 | 972 | MOTI RAHAMAN | 359.46 | 0 | 30
48 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000058/2023-2024 | 1075/MURD/2 | 19/04/2023 | 0 | Resource Division | 31.87 | 0 | 0
49 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System, Rising Main Connection, FHTC connections, Construction of 2 Nos Pump House Room, 100 Mtr Boundary Wall, for Augmentation of Aurangabad Zone-I PWSS of Suti-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior Engineer 3,Junior engineer-III | ORD/000088/2025-2026 | 1510/MURD | 03/07/2025 | 90 | H.I.ENTERPRISE | 133.86 | 0 | 0
50 | Murshidabad Division | Berhampur M/E Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior Engineer 3,Junior engineer-III | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 100
51 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior Engineer 3,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
52 | Murshidabad Division | Kandi Sub-Division | Allied work of Laying rising main and distribution system with FHTC including Construction Pump House Cum Chlorine Room , Boundary wall at 2nd Tube Well Site and Earth filling at both site of Padamkandi Water Supply Scheme , under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000040/2024-2025 | 1926/MURD | 03/07/2024 | 60 | ARJIMA CONSTRUCTION | 19.18 | 0 | 80
53 | Murshidabad Division | Kandi Sub-Division | Formal work order for PADAM KANDI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000837/2022-2023 | 732/MURD | 15/03/2023 | 749 | APURBA SAHA CHOWDHURY | 145.12 | 0 | 90
54 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000061/2023-2024 | 1075/MURD/5 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
55 | Murshidabad Division | Berhampur M/E Division | Construction of 700 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte._PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000297/2023-2024 | 2647/MURD | 23/08/2023 | 819 | SATELLITE CONSTRUCTION | 257.98 | 0 | 20
56 | Murshidabad Division | Berhampur M/E Division | Augmentation Work Laying Distribution System, Rising Main Connection, FHTC of Herampur Zone-I PWS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. (PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000572/2023-2024 | 3296/MURD | 20/10/2023 | 893 | J.S. CONSTRUCTION | 443.2 | 0 | 20
57 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000695/2023-2024 | 3768/MURD | 08/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 100
58 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
59 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000230/2023-2024 | 1219/MURD/20 | 03/05/2023 | 0 | Resource Division | 109.49 | 0 | 0
60 | Murshidabad Division | Berhampur Sub-Division | Augmentation of SURANGAPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000003/2023-2024 | 952/MURD | 05/04/2023 | 696 | M/S NIRAPADA BHATTACHARJEE | 329.64 | 0 | 100
61 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 91days from 21/06/2025 to 19/09/2025. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000101/2025-2026 | 122/BSD | 20/06/2025 | 91 | ABIDA CONSTRUCTION | 0.53 | 0 | 0
62 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490,91days from 01/09/2025 to 30/11/2025. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000155/2025-2026 | 125/BSD | 01/09/2025 | 91 | ABIDA CONSTRUCTION | 0.53 | 0 | 0
63 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 160 days from 12/01/2025 to 20/06/2025. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000249/2024-2025 | 06/BSD | 08/01/2025 | 160 | ABIDA CONSTRUCTION | 0.93 | 0 | 0
64 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
65 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 80
66 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000008/2024-2025 | 1811/MURD/07 | 20/06/2024 | 0 | Resource Division | 34.58 | 0 | 0
67 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000171/2023-2024 | 1180/MURD/15 | 29/04/2023 | 0 | Resource Division | 61.77 | 0 | 0
68 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000396/2023-2024 | 711/MURD | 07/03/2024 | 0 | Resource Division | 26 | 0 | 0
69 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 754 nos. household, Rising Main, Repairing Vertical extension of Boundary wall and repairing of Pump House and overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Mahesail (Zone-II) PWSS in Suti-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000802/2022-2023 | 564/MURD | 28/02/2023 | 180 | BISWAS ENTERPRISE. | 63.88 | 0 | 95
70 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution System for Augmentation work of Mahesail (Zone-II) PWSS in Suti-II Block under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000860/2022-2023 | 806/MURD | 22/03/2023 | 180 | M/S. BIMALENDU BOSE | 190.73 | 0 | 100
71 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000200/2023-2024 | 1210/MURD/27 | 02/05/2023 | 0 | Resource Division | 26.32 | 0 | 0
72 | Murshidabad Division | Kandi Sub-Division | Allied work for KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000052/2024-2025 | 1977/MURD | 08/07/2024 | 60 | DAS TRADING CO. | 70.58 | 0 | 0
73 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000679/2022-2023 | 38/MURD | 04/01/2023 | 818 | PRADIP KUMAR DAS | 720.99 | 0 | 35
74 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000045/2023-2024 | 1067/MURD | 18/04/2023 | 0 | Resource Division | 15.98 | 0 | 0
75 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of JHILLI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000700/2022-2023 | 123/MURD | 16/01/2023 | 867 | M/S RUBIET HOSSAIN | 616.31 | 0 | 10
76 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000046/2023-2024 | 1067/MURD/1 | 18/04/2023 | 0 | Resource Division | 21.94 | 0 | 0
77 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
78 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
79 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000086/2022-2023 | 1147/MURD | 27/04/2023 | 0 | Resource Division | 32.39 | 0 | 0
80 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000086/2023-2024 | 1147/MURD | 27/04/2023 | 0 | Resource Division | 32.39 | 0 | 0
81 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Punrapara & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000039/2023-2024 | 1099/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 0 | 100
82 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUNRAPARA, Augmentation of Bahara & Pacchipara Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000269/2023-2024 | 2587/MURD | 21/08/2023 | 438 | INDRAJIT MAZUMDAR | 18.43 | 0 | 60
83 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC for PUNRAPARA Water Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000675/2023-2024 | 3656/MURD | 29/11/2023 | 120 | AJAY MONDAL | 270.3 | 0 | 30
84 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall for PUNRAPARA PWSS in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000844/2022-2023 | 756/MURD | 16/03/2023 | 747 | JIT CONSTRUCTION | 194.6 | 0 | 10
85 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000025/2023-2024 | 1210/MURD/33 | 02/05/2023 | 0 | Resource Division | 16.9 | 0 | 0
86 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Srinarayanpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000494/2023-2024 | 3060/MURD | 29/09/2023 | 60 | DAS ENTERPRISE (SUBRATA DAS) | 32.43 | 0 | 0
87 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bansbere village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000497/2023-2024 | 3061/MURD | 29/09/2023 | 60 | AGNIBESH CHATTERJEE | 24.79 | 0 | 0
88 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000499/2023-2024 | 3080/MURD | 03/10/2023 | 60 | NOBEL CONSTRUCTION | 32.52 | 0 | 0
89 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Talbona village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000500/2023-2024 | 3081/MURD | 03/10/2023 | 60 | ARJU CONSTRUCTION | 32.52 | 0 | 0
90 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chak Ramprasad village, Block:- Jalangi, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000510/2023-2024 | 3082/MURD | 03/10/2023 | 60 | CHATTERJEE ENTERPRISE | 30.55 | 0 | 0
91 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Durajjay Palsa village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000511/2023-2024 | 3100/MURD | 04/10/2023 | 60 | SOUMYA KANTI SINHA | 32.21 | 0 | 0
92 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kalikapur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000517/2023-2024 | 3612/MURD | 24/11/2023 | 60 | KUNTAL SAHA | 31.83 | 0 | 0
93 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Padmalabhbati village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000519/2023-2024 | 3102/MURD | 04/10/2023 | 60 | SANJAY DUTTA | 28.02 | 0 | 0
94 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chak Palasi village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000521/2023-2024 | 3120/MURD | 05/10/2023 | 60 | SUJIT CHOWDHURY | 19.89 | 0 | 0
95 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Mamudpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000522/2023-2024 | 3121/MURD | 05/10/2023 | 60 | ASIT KUMAR ROY | 34.58 | 0 | 0
96 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Hari Nagar village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000526/2023-2024 | 3122/MURD | 05/10/2023 | 1033 | SANDESH CONSTRUCTION | 26.83 | 0 | 0
97 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000529/2023-2024 | 3135/MURD | 06/10/2023 | 877 | M/S ROY & BOSE ENTERPRISE | 34.81 | 0 | 10
98 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Daspara village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000548/2023-2024 | 3150/MURD | 09/10/2023 | 996 | MONDAL CONSTRUCTION | 31.8 | 0 | 70
99 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chak Gupura-Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000566/2023-2024 | 3276/MURD | 17/10/2023 | 60 | FIROJ AHAMMED BISWAS | 22.09 | 0 | 0
100 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000567/2023-2024 | 3277/MURD | 17/10/2023 | 793 | JIYAUL HAQUE | 32.83 | 0 | 0
101 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Khansama Danga village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000595/2023-2024 | 3350/MURD | 30/10/2023 | 60 | CREATIVE | 24.03 | 0 | 0
102 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bajitpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000598/2023-2024 | 3351/MURD | 30/10/2023 | 60 | SOUNAK ENTERPRISE | 34.62 | 0 | 0
103 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Gopalpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000599/2023-2024 | 3352/MURD | 30/10/2023 | 60 | M/S ATISH SINHA | 30.15 | 0 | 0
104 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Rasulpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000602/2023-2024 | 3364/MURD | 31/10/2023 | 60 | SUDIPTA GHOSH | 34.01 | 0 | 0
105 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Katigram village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000604/2023-2024 | 3365/MURD | 31/10/2023 | 640 | M/S. BOJLUR RAHAMAN | 26.08 | 0 | 40
106 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Srikrishnapur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000605/2023-2024 | 3366/MURD | 31/10/2023 | 60 | M/S MONDAL ASSOCIATES | 32.52 | 0 | 0
107 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000606/2023-2024 | 3367/MURD | 31/10/2023 | 883 | DEBEN RAJAK | 27.1 | 0 | 10
108 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Gangarampur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000607/2023-2024 | 3368/MURD | 31/10/2023 | 793 | M/S HALDAR CONSTRUCTION (PROP:- ANIRBAN HALDAR ) | 32.52 | 0 | 90
109 | Murshidabad Division | Berhampur Sub-Division | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000102/2024-2025 | 2152/MURD | 29/07/2024 | 480 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 80
110 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000134/2022-2023 | 1232/MURD | 11/05/2022 | 60 | PRADIP KUMAR DAS | 78.92 | 0 | 0
111 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of laying Rising main & Distribution System of GANGADHARI Water Supply Scheme under Berhampore Sub-Division, Murshidabad Division, P.H.Engg Dte. In the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000172/2022-2023 | 1303/MURD | 20/05/2022 | 120 | PRADIP KUMAR DAS | 300.61 | 0 | 0
112 | Murshidabad Division | Berhampur Sub-Division | Balance work for Laying of Distribution Pipeline, Repair and Renovation of OHR of 200 cum Capacity and Providing Functional Household Connection of 590 nos household of Gangadhari (village code-314589) of Berhampore Sub-Division under Murshidabad Division,P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000449/2023-2024 | 2969/MURD | 20/09/2023 | 559 | DAS TRADING CO. | 80.23 | 0 | 100
113 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gangadhari Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000595/2022-2023 | 3069/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 0 | 100
114 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GANGADHARI PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000843/2021-2022 | 3276/MURD | 05/10/2021 | 60 | RADIANT | 3.51 | 0 | 1
115 | Murshidabad Division | Berhampur Sub-Division | Construction of 200 Cum OHR, Boundary Wall, Pump House for Augmentation of GANGADHARI PWSS in NAWDA Block, Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000850/2023-2024 | 825/MURD | 15/03/2024 | 566 | SOM CONSTRUCTION AGENCY | 93.75 | 0 | 25
116 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000386/2023-2024 | MURD/514 | 16/02/2024 | 0 | Resource Division | 21.35 | 0 | 0
117 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 05 |  |  | VCH/000755/2022-2023 | 309-MSD/22-23 | 29/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 13.05 | 0 | 0
118 | Murshidabad Division | Berhampur Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000055/2022-2023 | 160/BSD | 12/04/2022 | 15 | BARMAN ENTERPRISE | 4.84 | 0 | 0
119 | Murshidabad Division | Berhampur Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000057/2022-2023 | 162BSD | 12/04/2022 | 15 | A.S. MONDAL ENTERPRISE | 4.84 | 0 | 0
120 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-II | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000063/2022-2023 | 168/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.86 | 0 | 0
121 | Murshidabad Division | Berhampur Sub-Division | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000064/2022-2023 | 169/BSD | 12/04/2022 | 15 | M/S.S.S. ENTERPRISE | 4.84 | 0 | 0
122 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-I | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000065/2022-2023 | 170/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.85 | 0 | 0
123 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Raypur, Kanapara, Sakua, Madhupur (Village code 315531, 315541, 315542, 315532) under Surangapur Ground Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005182885) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001339/2021-2022 | 479/MURD | 22/02/2022 | 1348 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 398.73 | 0 | 30
124 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000001/2022-2023 | 889/A/MURD | 05/04/2022 | 0 | Resource Division | 58.9 | 0 | 0
125 | Murshidabad Division | Berhampur Sub-Division | LAYING OF 140MM DIA FHTC ........ RAYPUR UNDER SURANGAPUR W/S SCHEME UNDER MSD PHE DTE. TENDER NO 213 OF 21-22 | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000317/2022-2023 | 177-MSD/22-23 | 17/05/2022 | 0 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.84 | 0 | 0
126 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER |  | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
127 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HUMAIPUR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000501/2021-2022 | 336/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 0 | 0
128 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Basabari (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001156/2021-2022 | 2643 /MURD | 27/08/2021 | 60 | AZAD ENTERPRISE | 21.66 | 0 | 0
129 | Murshidabad Division | Berhampur Sub-Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Malibari PWSS under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER |  | ORD/001720/2021-2022 | 154/ISD | 17/03/2022 | 30 | MABCO GEOTEST ASSOCIATES | 1.48 | 0 | 1
130 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 720 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Alampur ( Village Code -313932) under Ghorapakhiagangin Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000033/2022-2023 | 1054/MURD | 25/04/2022 | 30 | PROSENJIT DAS | 34.86 | 0 | 0
131 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 540/5/MURD | 25/02/2022 | 0 | Resource Division | 3.95 | 0 | 0
132 | Murshidabad Division |  | Continuation order for Holding Awarness Programme / Campaigning programs at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, & Rangamati Chandpara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. |  |  | ORD/000114/2020-2021 | 690/MURD | 23/02/2021 | 30 | S.S.INFRASTRUCTURE | 3.18 | 3.18 | 0
133 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagharpur Ramna (Village code 314665) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-12) |  |  | ORD/000719/2020-2021 | 3117 / MURD | 09/12/2020 | 180 | M/S NIRAPADA BHATTACHARJEE | 95.68 | 0 | 0
134 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) |  |  | VCH/000006/2021-2022 | 07/MSD/21-22 | 16/07/2021 | 0 | M/S NIRAPADA BHATTACHARJEE | 38.35 | 0 | 0
135 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAGHARPUR RAMNA (Village Code 314665) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 66 of 20-21 by SE MC |  |  | VCH/001514/2021-2022 | 402-MSD/21-22 | 23/03/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 28.13 | 0 | 0
136 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). |  |  | ORD/000171/2020-2021 | 594/MURD | 09/02/2021 | 60 | SUJIT KUMAR SAHA | 46.24 | 0 | 1
137 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria ( Village Code -314729) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344). |  |  | ORD/000729/2020-2021 | 584/MURD | 09/02/2021 | 60 | DAS ENTERPRISE (SUBRATA DAS) | 21.07 | 0 | 1
138 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). |  |  | ORD/000740/2020-2021 | 594 / MURD | 09/02/2021 | 60 | SUJIT KUMAR SAHA | 46.24 | 0 | 1
139 | Murshidabad Division |  | Relaying of different dia UPVC pipeline for Balance Providing Functional Household Tap connection (FHTC) of 94 nos in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Jhaubaria (Village Code-314729) under Juginda Ground water based water suply scheme for Arsenic affected areas of DomkalBlock, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0001723344) |  |  | ORD/001835/2021-2022 | 767/MURD | 22/03/2022 | 20 | MONDAL ENTERPRISE | 6.65 | 0 | 1
140 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of village JHAUBARIA (Village Code: 314729) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL, Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID : 0001723344) Tender no- 825 of 20-21 by EE / MURD |  |  | VCH/000189/2021-2022 | 15-MSD / 21-22 | 10/08/2021 | 0 | DAS ENTERPRISE (SUBRATA DAS) | 14.24 | 0 | 0
141 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAKSHIN NAGAR (Village Code: 314728) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 003 of 20-21 by EE / MSD |  |  | VCH/000226/2021-2022 | 17-MSD / 21-22 | 13/08/2021 | 0 | SUJIT KUMAR SAHA | 36.26 | 0 | 0
142 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block(Teghori, Kasiadanga,Laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) |  |  | ORD/000068/2021-2022 | 125 /JSD | 25/05/2021 | 30 | S.S.INFRASTRUCTURE | 1.58 | 0 | 0
143 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshijala ( Village Code -314127) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) |  |  | ORD/000075/2021-2022 | 1468/MURD | 21/06/2021 | 60 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0
144 | Murshidabad Division |  | Allied work for rectrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Babupur (Village Code-314126) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001274/2021-2022 | 391/JSD | 31/12/2021 | 30 | BENGAL ENTERPRISE | 4.83 | 0 | 0
145 | Murshidabad Division |  | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD |  |  | VCH/000029/2022-2023 | 25-MSD/22-23 | 11/04/2022 | 0 | PRADIP DAS | 4.67 | 0 | 0
146 | Murshidabad Division |  | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD |  |  | VCH/000092/2022-2023 | 25-MSD/22-23(RE | 28/04/2022 | 0 | PRADIP DAS | 4.67 | 0 | 0
147 | Murshidabad Division |  | IEC PROGRAM AND VIDEO DOCUMENTARY AND OTHER AWARENESS WORK OF FHTC AT DIFFERENT PLACES UNDER LSD |  |  | VCH/000589/2021-2022 |  | 24/09/2021 | 0 | S.S.INFRASTRUCTURE | 9.91 | 0 | 0
148 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00" x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Lalgola G.P, Paharpur G.P, Amdahara G.P, Kolan G.P, Kantanagar G.P, Mahammodpur G.P,Amarkundu G.P. & Shibpur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. , tno- 13/21-22/AE LSD |  |  | VCH/000821/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 2.32 | 0 | 0
149 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection (FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte. (Shibpur G.P, Amarkundu G.P, Lalgola G.P. & Bilborakopra G.P., TNO- 15/21-22/AELSD |  |  | VCH/000822/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0
150 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte.(Amdahara GP, Mahammadpur GP & Kantanagar GP), TNO-14/21-22/EE |  |  | VCH/000823/2021-2022 | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 3.26 | 0 | 0
151 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD |  |  | VCH/001465/2021-2022 | 362-MSD/21-22 | 11/03/2022 | 0 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0
152 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babupur ( Village Code 314126) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852) |  |  | VCH/001473/2021-2022 | 380-MSD/21-22 | 16/03/2022 | 0 | BENGAL ENTERPRISE | 18.97 | 0 | 0
153 | Murshidabad Division | Islampur Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1467 nos in connection with (Jal Jeevan Mission ) and under command area of village of Juranpur ( Village Code -314720) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000204/2022-2023 | 1380/MURD | 26/05/2022 | 60 | M/S. S. DAS AND ENTERPRISE | 72.04 | 0 | 40
154 | Murshidabad Division | Islampur Sub-Division | Extension of pipeline from different (Juranpur & Tekaraipur) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000319/2021-2022 | 380/1/ISD | 26/07/2021 | 30 | M/S. SAJEDA ENTERPRISE | 4.02 | 0 | 1
155 | Murshidabad Division | Islampur Sub-Division | Extension of pipeline from different (Shibnagar laskarpur, juranpur, Juginda Zone-II, Tekaraipur, Garibpur Z-I, Aminabad) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002124/2021-2022 | 381/1/ISD | 26/07/2021 | 30 | NABIRUL ISLAM | 4.14 | 0 | 0
156 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Domkal (Village code 314695) under Domkal Ground Water Based Water Supply Scheme & & Barabil Raghunathpur (Village code 314626) for Arsenic Affected Area of Domkal & Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-15) |  |  | ORD/000206/2020-2021 | 3110/MURD | 09/12/2020 | 180 | ARINDAM MAJUMDAR | 48.25 | 0 | 80
157 | Murshidabad Division |  | Formal Work Order for Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Barabil Raghunathpur ( Village Code -314626) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723213) in the District of Murshidabad.(Sl-30) |  |  | ORD/000636/2020-2021 | 525/MURD | 04/02/2021 | 180 | MITRA CONSTRUCTION | 138.32 | 0 | 0
158 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village BARABIL RAGHUNATHPUR (Village Code-314626) under BARABIL RAGHUNATHPUR Ground Water Supply Scheme Arsenic Affected Area of Jalangi Block of Murshidabad District under Murshidabad Division, PHE Dte. Scheme ID 0001723213 |  |  | VCH/000236/2021-2022 | 26-MSD / 21-22 | 19/08/2021 | 0 | MITRA CONSTRUCTION | 52.92 | 0 | 0
159 | Murshidabad Division |  | Additional work for Providing of Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village JOYRAMPUR (Village Code 314693) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 99 of 21-22 by EE MURD |  |  | VCH/001549/2021-2022 | 372-MSD/21-22 | 18/03/2022 | 0 | SAHABUDDIN BISWAS | 18.52 | 0 | 0
160 | Murshidabad Division |  | SHIFTING OF HT OVERHEAD LINE BR ERECTION XLPE UG CABLE AT GHANSHYAM CHAK PUMP HOUSE NO-I, ZONE-II |  |  | BILL/00507/2022-2023 | 588-MSD/22-23 | 06/03/2023 | 0 | WBSEDCL | 3.92 | 0 | 0
161 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Giria,Sekendra, Mithipur,Jotkamal,Dayarampur & Sammatinagar ) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte.(PART-A) |  |  | ORD/000066/2021-2022 | 122 /JSD | 22/05/2021 | 30 | S.S.INFRASTRUCTURE | 2.38 | 0 | 1
162 | Murshidabad Division |  | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. |  |  | ORD/000758/2022-2023 | 445/MURD | 17/02/2023 | 846 | NAYLA CONSTRUCTION | 255.21 | 0 | 90
163 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS SEKENDRA PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001139/2021-2022 | 3256/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.68 | 6.68 | 1
164 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of SEKENDRA (Village code 314064) under SEKENDRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184141 |  |  | ORD/001188/2021-2022 | 3977/MURD | 21/12/2021 | 180 | DOBAY CONSTRUCTION | 159.44 | 0 | 1
165 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 540/13/MURD | 25/02/2022 | 0 | Resource Division | 21.96 | 0 | 0
166 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) of 1579 nos in connection with Jal Swapna (Jal Jeevan Mission ) under Command area of Village of Selalpur, Uttar Ramna, Simla, Dhalo, Kanchanpur, Paikar & Panchanpara ( Village Code -314023,314051,314020,314036,314049,314038,314044) under Raghunathganj-I Surface Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000002/2022-2023 | 895/MURD | 05/04/2022 | 60 | MOTI RAHAMAN | 97.06 | 0 | 1
167 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) of 1190 nos in connection with Jal Swapna (Jal Jeevan Mission ) under Command area of Village of Birthamba, Sendajamuar & Mandalpur ( Village Code -314006, 314007, 314008) under Raghunathganj-I Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. . |  |  | ORD/000108/2022-2023 | 1137/MURD | 02/05/2022 | 60 | PRADIP KUMAR DAS | 64.77 | 0 | 0
168 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mirzapur (Village code 314057) under Surface Water Based water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. |  |  | ORD/000165/2021-2022 | 1580/MURD | 25/06/2021 | 180 | APURBA SAHA CHOWDHURY | 45.85 | 0 | 80
169 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Sujapur(P) ( Village Code -313996) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | ORD/000194/2020-2021 | 958/MURD | 24/03/2021 | 180 | SAMBHU NATH ROY | 46.33 | 4.98 | 0
170 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Dafarpur (C.T.) ( Village Code -314055) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | ORD/000195/2020-2021 | 959/MURD | 24/03/2021 | 180 | SAMBHU NATH ROY | 107.46 | 17.86 | 0
171 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Rajnagar (Village code 314041) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. |  |  | ORD/000254/2021-2022 | 1653/MURD | 29/06/2021 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 45.88 | 0 | 80
172 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Siddhikhali (Village Code 314021) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000259/2020-2021 | 2395/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.73 | 0 | 0
173 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Talai(Village code 314018) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-7) |  |  | ORD/000304/2020-2021 | 3118/MURD | 09/12/2020 | 180 | DECON INDIA | 55.72 | 0 | 1
174 | Murshidabad Division |  | Allied work of pipeline and Platform at DEULI village under Raghunathganj Surface Based Water Supply Scheme for HGJ of Jangipur Sub-Division under Murshidabad Division, PHE Dte. |  |  | ORD/000476/2023-2024 | 3033/MURD | 27/09/2023 | 30 | SAMBHU NATH ROY | 6.17 | 0 | 100
175 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jarur(Village code 314011) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-8) |  |  | ORD/000497/2020-2021 | 3066/MURD | 08/12/2020 | 180 | NOVELTY CONSTRUCTION | 54.9 | 0 | 1
176 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village of Jethia( Village Code-314030)under Surface Water Based Water Supply Scheme form Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000554/2020-2021 | 2527/MURD | 30/09/2020 | 45 | DEBASIS BOSE | 34.11 | 0 | 100
177 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission) " from existing Distribution system within the Command area of village BAIDPUR (Village Code 314026) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000576/2020-2021 | 2553/MURD | 01/10/2020 | 45 | S. DUTTA | 13.25 | 0 | 0
178 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village JAGADANANDABATI(Village Code 314028) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . |  |  | ORD/000620/2020-2021 | 2559 /MURD | 01/10/2020 | 45 | SUDIPA SINGHA ROY | 16.27 | 0 | 0
179 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Siddhikhali(Village Code 314021) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000630/2020-2021 | 2395/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.73 | 0 | 1
180 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jarur(Village code 314011) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-8) |  |  | ORD/000649/2020-2021 | 3066 / MURD | 08/12/2020 | 180 | NOVELTY CONSTRUCTION | 54.9 | 0 | 1
181 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village GANKAR (Village Code 314037) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000667/2020-2021 | 2561/MURD | 01/10/2020 | 45 | DECON INDIA | 41.51 | 0 | 1
182 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Natun(Village code 314043) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-5) |  |  | ORD/000669/2020-2021 | 3056/MURD | 08/12/2020 | 180 | AJAY MONDAL | 46.31 | 0 | 1
183 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village BIJOYPUR (Village Code 314032) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | ORD/000716/2020-2021 | 2562/MURD | 01/10/2020 | 45 | SAMBHU NATH ROY | 19.69 | 0 | 0
184 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Deuli(Village code 313998) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-11) |  |  | ORD/000718/2020-2021 | 3065/MURD | 08/12/2020 | 180 | SANJAY BISWAS | 57.02 | 0 | 1
185 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village KULRI (Village Code 314022) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . |  |  | ORD/000728/2020-2021 | 2554/MURD | 01/10/2020 | 45 | JAMIRUL CONSTRUCTION | 14.17 | 0 | 0
186 | Murshidabad Division |  | Road Restoration work because of damaging due to laying of different dia UPVC pipe line in connection with FHTC Work at Khidirpur (Village code- 313993) under Surface water based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Jangipur Sub-Division under Murshidabad Division, P.H.E Dte in the district of Murshidabad. |  |  | ORD/000734/2023-2024 | 19/MURD | 03/01/2024 | 30 | M/S. SABANA CONSTRUCTION (PROP:MD. SAIDUR RAHAMAN) | 3.78 | 0 | 0
187 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village BAINDA (Village Code 314003) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad |  |  | ORD/000741/2020-2021 | 2552/MURD | 01/10/2020 | 45 | SAMBHU NATH ROY | 21.88 | 0 | 0
188 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission )" from existing Distribution system within the Command area of village AMGACHHI (Village Code 314031) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . |  |  | ORD/000768/2020-2021 | 2557/MURD | 01/10/2020 | 45 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 19.24 | 0 | 100
189 | Murshidabad Division |  | Work of Extension of Existing Boundary wall along with painting work at Jotkamal (Zone-I) water supply scheme , under Raghunathganj-II Block, under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. |  |  | ORD/001264/2021-2022 | 383/JSD | 31/12/2021 | 30 | MOLLA ENTERPRISE | 4.83 | 0 | 1
190 | Murshidabad Division |  | Laying of 250 mm D.I Pipe for clear water rising main by Open-Cut method from Umarpur more (Chainage 0.00 KM) to Mitrapur (Chainage 7.50 KM) along right hand flank of bituminous road,PWD for Raghunathganj Surface Water Based Water Supply Scheme (Raghunathganj-I Block) of Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/001595/2021-2022 | 397/MURD | 16/02/2022 | 45 | SANJAY BISWAS | 31.87 | 0 | 100
191 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000028/2021-2022 | 540/1/MURD | 25/02/2022 | 0 | Resource Division | 15.28 | 0 | 0
192 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of KANKARIA VILLAGE OF Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 761/2020-21/EE |  |  | VCH/000005/2021-2022 | 01/MSD/21-22 | 15/07/2021 | 0 | MAMATA USHA ENTERPRISE | 20.68 | 0 | 0
193 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of VILLAGE SANTOSHPUR UNDER Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District, TNO- 502/20-21/EE |  |  | VCH/000007/2021-2022 | 06/MSD/21-22 | 16/07/2021 | 0 | MODERN CONSTRUCTION | 10.59 | 0 | 0
194 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NATUN (Village Code 314043) and adjoining habitation under Raghunathganj-I Surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 56 of 21-22 by SE MC |  |  | VCH/000033/2022-2023 | 34-MSD/22-23 | 14/04/2022 | 0 | AJOY MONDAL | 37.08 | 0 | 0
195 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SANTOSHPUR (Village Code 314045) under surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 502 of 20-21 by EE MURD |  |  | VCH/000034/2022-2023 | 32-MSD/21-22 | 21/04/2022 | 0 | MODERN CONSTRUCTION | 2.37 | 0 | 0
196 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION )' from existing Distribution system within the Command area of village SONATIKRI ( Village Code -313995) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | VCH/000056/2022-2023 | 72-MSD/22-23 | 26/04/2022 | 0 | J.S. CONSTRUCTION | 27.59 | 0 | 0
197 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village JARUR (Village Code 314011) under Surface Based Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 47 of 20-21 by SE MC (NEW) |  |  | VCH/000095/2022-2023 | 36-MSD/22-23 | 23/04/2022 | 0 | NOVELTY CONSTRUCTION | 5.22 | 0 | 0
198 | Murshidabad Division |  | Laying of 200 mm dia MS Water Carring pipe with 600 mm dia MS PIPE as casing at chainge Raghunathganj Surface Water Based W/S Scheme block Raghunathganj-I Block under MSD PHE DTE. Tender no - 930 of 20-21 by EE MURD |  |  | VCH/000096/2022-2023 | 37-MSD/22-23 | 14/04/2022 | 0 | SAMBHU NATH ROY | 24.74 | 0 | 0
199 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village Ramakantapur (Village Code- 314029) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 65 of 20-21 by SE / MC |  |  | VCH/000200/2021-2022 | 08 -MSD / 21-22 | 06/08/2021 | 0 | MS SINHA AND SONS | 39.66 | 0 | 0
200 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village JEETHIA (Village Code: 314030) under surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 488 of 20-21 by EE / MSD |  |  | VCH/000220/2021-2022 | 21-MSD / 21-22 | 13/08/2021 | 0 | DEBASIS BOSE | 15.79 | 0 | 0
201 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAFARPUR (Village Code: 314055) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 113 of 20-21 by SE / MC |  |  | VCH/000221/2021-2022 | 23-MSD / 21-22 | 11/08/2021 | 0 | SAMBHU NATH ROY | 23.13 | 0 | 0
202 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village SUJAPUR (Village Code: 313996) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 114 of 20-21 by SE / MC |  |  | VCH/000222/2021-2022 | 22-MSD / 21-22 | 11/08/2021 | 0 | SAMBHU NATH ROY | 13.29 | 0 | 0
203 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village JARUR (Village Code: 314011) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 47 of 20-21 by SE / MC |  |  | VCH/000225/2021-2022 | 19-MSD / 21-22 | 06/08/2021 | 0 | NOVELTY CONSTRUCTION | 39.68 | 0 | 0
204 | Murshidabad Division |  | Holding Awarness programme / Campaigning programs at Chandpur GP Radharghar I & II GP Ramnagar Bachhara GP Somprra =I GP Doulabad GP & Chhaighari GP connection with functional household tap connection FHTC under MSD PHE DTE. Tenter no 154 of 21-22 by EE |  |  | VCH/000239/2021-2022 | 33-MSD/21-22 | 23/08/2021 | 0 | IMAGIN COMMUNICATION | 3.17 | 0 | 0
205 | Murshidabad Division |  | Holding Awarness programme / Campaigning programs at Nowda GP, Roypur GP, Madhupur GP, Sarbangpur GP, Choa GP, Hariharpara GP, Mahula GP & Rangamati Chandpara GP connection with functional household tap connection FHTC under MSD PHE DTE. Tenter no 153 of 21-22 by EE |  |  | VCH/000240/2021-2022 | 32-MSD/21-22 | 23/08/2021 | 0 | S.S.INFRASTRUCTURE | 3.18 | 0 | 0
206 | Murshidabad Division |  | Holding Awarness Progmramme /Campaigning programms at Chandpur-I , II GP, Bali GP, Patikabari GP, Madhupur GP, Kedar Chandpur GP, Khidirpur GP, Humaipur GP, Rampara-I GP, Andulberia GP, Dadpur GP Rampara-II GP Mirjapur GP Kumarpur Sujapur GP in connection with Functional Household Tap Connection FHTC under MSD PHE DTE. Tender no 155 of 21-22 by EE |  |  | VCH/000241/2021-2022 | 34-MSD/21-22 | 23/08/2021 | 0 | IMAGIN | 4.77 | 0 | 0
207 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Talai (Village code 314018) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. Tender no - 57 of SE/MC OF 20-21 |  |  | VCH/000269/2021-2022 | 54-MSD/21-22 | 14/09/2021 | 0 | DECON INDIA | 26.12 | 0 | 0
208 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of SEKENDRA (Village code 314064) under SEKENDRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184141 |  |  | VCH/000292/2022-2023 | 91-MSD/22-23 | 02/05/2022 | 0 | DOBAY CONSTRUCTION | 54.19 | 0 | 0
209 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with Jal Swapna (Jal Jeevan Mission) from existing Distribution system within the command area of village AMGACHHI (Village Code -314031) under surface Water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-I Block in the Dist of MSD under Murshidabad Division P.H.E Dte. |  |  | VCH/000371/2021-2022 | 57-MSD/21-22 | 14/09/2021 | 0 | M/S. GHOSH ENTERPRISE | 4.47 | 0 | 0
210 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Sujapur(P) ( Village Code -313996) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | VCH/000435/2022-2023 | 162-MSD/22-23 | 17/05/2022 | 0 | SAMBHU NATH ROY | 20.19 | 0 | 0
211 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna OF DEULI VILLAGE (313998)(JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District. TNO- |  |  | VCH/000574/2021-2022 | 136-MSD/21-22 | 07/10/2021 | 0 | SANJAY BISWAS | 41.68 | 0 | 0
212 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) RAMAKANTAPUR VILLAGE CODE 314029 of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 65/20-21/SE-MC |  |  | VCH/000651/2021-2022 | 125-MSD/21-22 | 07/10/2021 | 0 | M/S. SINHA & SONS | 17.47 | 0 | 0
213 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) VILALGE NAIT BAIDHARA CODE-314004 of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 53/20-21/EE |  |  | VCH/000652/2021-2022 | 126-MSD/21-22 | 11/10/2021 | 0 | SANJAY BISWAS | 17.94 | 0 | 0
214 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION )' from existing Distribution system within the Command area of village SONATIKRI ( Village Code -313995) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. 2566/MURD, 01/10/2020 |  |  | VCH/000672/2021-2022 | 175-MSD/21-22 | 02/11/2021 | 0 | J.S. CONSTRUCTION | 16.47 | 0 | 0
215 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) VILLAGE CODE- 314009, TNO- 75/20-21/SE-MC |  |  | VCH/000777/2021-2022 | 194-MSD/21-22 | 18/11/2021 | 0 | M/S UNIVERSAL TRADING | 41.08 | 0 | 0
216 | Murshidabad Division |  | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 57/21-22/EE |  |  | VCH/000868/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 3.98 | 0 | 0
217 | Murshidabad Division |  | Deposit of way leave charges for-Way leave permission for crossing of 200 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 216/9-217/0 under Malda Division of Eastern Railway, Way leave permission for crossing of 200 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 212/0-1 under Malda Division of Eastern Railway, Way leave permission for crossing of 150 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 210/9-211/0 under Malda Division of Eastern Railway and Way leave permission for crossing of 100 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between station Ahiron Halt & Jangipur Road at km. 204/2-3 under Malda Division of Eastern Rail. REF:MEMO NO-1050/MURD, DT- 05/04/21. |  |  | VCH/000833/2022-2023 | 292-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 32.2 | 0 | 0
218 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of RAMNAGAR VILLAGE CODE 314056 Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District |  |  | VCH/000869/2021-2022 | 207-MSD/21-22 | 08/12/2021 | 0 | TRIDIP MAZUMDER | 25.05 | 0 | 0
219 | Murshidabad Division |  | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. WORK ORDER NO & DT. - 223 / HQ DATE- 26/05/2022 |  |  | VCH/000967/2022-2023 | 325-MSD/22-23 | 30/09/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0
220 | Murshidabad Division |  | Continuation work order for Hiring of one no. Bolero Car/Marshal (CAR 57- 9120) Same category for official use of the Assistant Engineer, JSD, P.H.Engineering Dte. Berhampore, Murshidabad. WORK ORDER NO & DT. - 88 / JSD DATE- 22/02/2022. |  |  | VCH/000968/2022-2023 | 334-MSD/22-23 | 30/09/2022 | 0 | MANUAR HOSSAIN | 0.4 | 0 | 0
221 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) |  |  | VCH/001289/2021-2022 |  | 17/02/2022 | 0 | S. DUTTA | 13.24 | 0 | 0
222 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with 'Jal Swapna (Jal Jeevan Mission ) 'from existing Distribution system within the Command area of village BARALA (Village Code 314009) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 75 of 20-21 by SE MC |  |  | VCH/001379/2021-2022 | 330-MSD/21-22 | 25/02/2022 | 0 | M/S UNIVERSAL TRADING | 7.36 | 0 | 0
223 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission) " from existing Distribution system within the Command area of village BAIDPUR (Village Code 314026) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 501 of 20-21 by EE MURD |  |  | VCH/001394/2021-2022 | 325-MSD/21-22 | 22/02/2022 | 0 | S. DUTTA | 13.24 | 0 | 0
224 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JAL SWAPNA(JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Khidirpur(Village Code 313993) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. |  |  | VCH/001395/2021-2022 | 326-MSD/21-22 | 24/02/2022 | 0 | M/S. SABANA CONSTRUCTION (PROP:MD. SAIDUR RAHAMAN) | 30.82 | 0 | 0
225 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NISTA (Village Code 314017) under Surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 619 of 21-22 by EE MURD |  |  | VCH/001396/2021-2022 | 328-MSD/21-22 | 25/02/2022 | 0 | M/S. S. DAS AND ENTERPRISE | 15.54 | 0 | 0
226 | Murshidabad Division |  | PAYMENT OF FEES OF ONLINE APPLICATION OF RAIL CROSSING PROCESS. |  |  | VCH/001462/2021-2022 | 363-MSD/21-22 | 11/03/2022 | 0 | FA & CAO EASTERN RAILWAY | 2.02 | 0 | 0
227 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Dafarpur (C.T.) ( Village Code -314055) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. |  |  | VCH/001474/2021-2022 | 383-MSD/21-22 | 17/03/2022 | 0 | SAMBHU NATH ROY | 59.53 | 0 | 0
228 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village CHAR DAFARPUR (Village Code 314047) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 497 of 20-21 by EE MURD |  |  | VCH/001511/2021-2022 | 409-MSD/21-22 | 23/03/2022 | 0 | GOUTAM CHAKRABORTY | 36.1 | 0 | 0
229 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- B village, Block:- Khargram, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000230/2023-2024 | 2341/MURD | 03/08/2023 | 1033 | J.S. CONSTRUCTION | 30.54 | 0 | 15
230 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- C village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000231/2023-2024 | 2342/MURD | 03/08/2023 | 60 | M/S SAJAHAN CHOWDHURY | 30.48 | 0 | 10
231 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- E village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000233/2023-2024 | 2343/MURD | 03/08/2023 | 60 | SUGATA CHOWDHURY | 30.55 | 0 | 10
232 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Kharsa Part- D village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000478/2023-2024 | 3035/MURD | 27/09/2023 | 852 | S.N. ENTERPRISE | 29.6 | 0 | 10
233 | Murshidabad Division | Kandi Sub-Division | CHHATRAPUR PWSS under Jal Jeevan Mission of BHARATPUR -I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000477/2023-2024 | 3034/MURD | 27/09/2023 | 705 | MONDAL ENTERPRISE | 133.95 | 0 | 30
234 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - I Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000626/2023-2024 | 3410/MURD | 02/11/2023 | 500 | GENUINE | 18.43 | 0 | 100
235 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000068/2023-2024 | 1075/MURD/10 | 19/04/2023 | 0 | Resource Division | 2.47 | 0 | 0
236 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000400/2023-2024 | 2807/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
237 | Murshidabad Division | Kandi Sub-Division | Construction of Ground Water Based ALAMPUR AND ADJOINING MOUZAS PWSS of accommodate FHTC( 960 Nos), Laying Distribution System, Laying Rising Main,, Switch Room, Boundary Wall, 150 CUM OHR in Kandi Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000581/2023-2024 | 3316/MURD | 22/10/2023 | 710 | H.MONDAL CONSTRUCTION | 234.45 | 0 | 50
238 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000079/2023-2024 | 1129/MURD/2 | 25/04/2023 | 0 | Resource Division | 22.13 | 0 | 0
239 | Murshidabad Division | Berhampur Sub-Division | Construction of 450 Cum OHR, Pump House with sanitary and Water Supply Arrangement , Pump House cum Blower room And Boundary Wall for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000234/2023-2024 | 2405/MURD | 07/08/2023 | 365 | ABHISHEK BHATTACHARYA | 198.86 | 0 | 0
240 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 3199 nos household , Laying of Distribution System, Rising Main for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART _A. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000246/2023-2024 | 2467/MURD | 09/08/2023 | 180 | SARAJIT KUMAR MAJUMDER | 306.82 | 0 | 0
241 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
242 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MOHULA PWSS Scheme, Block - Beldanga-I) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | ORD/000840/2021-2022 | 3273/MURD | 05/10/2021 | 60 | RADIANT | 10.24 | 0 | 1
243 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III,JUNIOR ENGINEER_RAGHUNATHGANJ - II BLOCK | RTOR000218/2023-2024 | 1290/MURD/02 | 03/05/2023 | 0 | Resource Division | 0.41 | 0 | 0
244 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. (PART B- 55.0MTR.)_Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000024/2023-2024 | 1028/MURD | 13/04/2023 | 30 | ABA CONTRACTOR | 4.63 | 0 | 100
245 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-I(Part -B) Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000030/2025-2026 | 1023/MURD | 05/05/2025 | 60 | TANUSHREE ENTERPRISE | 23.01 | 0 | 0
246 | Murshidabad Division | Berhampur Sub-Division | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 537 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 75
247 | Murshidabad Division | Berhampur Sub-Division | Providing 1612 nos FHTC Connection for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000051/2024-2025 | 1976/MURD | 08/07/2024 | 45 | DIPAK BHOWMIK | 84.07 | 0 | 0
248 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000134/2023-2024 | 1745/MURD | 06/07/2023 | 180 | BENGAL ENTERPRISE | 84.67 | 0 | 70
249 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
250 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sarbangapur Zone -IB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000708/2023-2024 | 3806/MURD | 12/12/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 100
251 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundwary Wall , Pump House (Two nos), Construction of PCC approach road for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000846/2023-2024 | 779/MURD | 14/03/2024 | 624 | STARK ENTERPRISE | 43.61 | 0 | 70
252 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 1
253 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000018/2024-2025 | 1811/MURD/17 | 20/06/2024 | 0 | Resource Division | 9.93 | 0 | 0
254 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000215/2023-2024 | 1219/MURD/01 | 03/05/2023 | 0 | Resource Division | 9.73 | 0 | 0
255 | Murshidabad Division |  | Last mile connectivity and providing 8317 nos Functional House Hold Connection from Zone- XII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte |  |  | ORD/000334/2023-2024 | 2691/MURD | 25/08/2023 | 120 | MAMATA USHA ENTERPRISE | 487.03 | 0 | 0
256 | Murshidabad Division |  | Last mile connectivity and providing 7237 nos Functional House Hold Connection from Zone- XV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000337/2023-2024 | 2694/MURD | 25/08/2023 | 120 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 427.97 | 0 | 0
257 | Murshidabad Division |  | Last mile connectivity and providing 3451 nos Functional House Hold Connection from Zone- XVII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000339/2023-2024 | 2696/MURD | 25/08/2023 | 120 | M/S. BIMALENDU BOSE | 206.76 | 0 | 0
258 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kelai & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000038/2023-2024 | 1105/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 0 | 100
259 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System Part-A , Rising Main Connection FHTC, for Kelai water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000051/2023-2024 | 1257/MURD | 08/05/2023 | 180 | M/S CARE | 352.42 | 0 | 10
260 | Murshidabad Division | Kandi Sub-Division | Formal work order for KELAI (PART-B) & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000843/2022-2023 | 753/MURD | 16/03/2023 | 1022 | NURTAJ SHAIKH | 217.79 | 0 | 18
261 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
262 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 779 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
263 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 811 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
264 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
265 | Murshidabad Division |  | Last mile connectivity and providing 5696 nos Funcational House Hold Connection from Zone-VII of Surface water based BALIA water supply scheme in Sagardighi Block under Murshidabad Division PHE Dte . |  |  | ORD/000028/2024-2025 | 1848/MURD | 25/06/2024 | 120 | M/S BOSE & CO. | 334.91 | 0 | 0
266 | Murshidabad Division |  | Last mile connectivity and providing 4285 nos Functional House Hold Connection from Zone- VI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000441/2023-2024 | 2920/MURD | 14/09/2023 | 120 | DOBAY CONSTRUCTION | 244.28 | 0 | 0
267 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-I of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gokarna & adjoining mouzas Water Supply Scheme at Head work site at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000031/2023-2024 | 1106/MURD | 24/04/2023 | 526 | INDRAJIT MAZUMDAR | 10.68 | 0 | 90
268 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte.(PART-C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000042/2023-2024 | 1140/MURD | 26/04/2023 | 1071 | M/S.TAPAS KUMAR CHAKRABORTY | 358.04 | 0 | 30
269 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000043/2023-2024 | 1141/MURD | 26/04/2023 | 1071 | M/S.TAPAS KUMAR CHAKRABORTY | 252.26 | 0 | 30
270 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS GOKARNA PWSS Scheme, Block-KANDI to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/002151/2021-2022 | 3258/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.11 | 0 | 1
271 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000059/2022-2023 | 1043/MURD/3 | 17/04/2023 | 0 | Resource Division | 31.92 | 0 | 0
272 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000310/2023-2024 | 1295/MURD/05 | 11/05/2023 | 0 | Resource Division | 61.11 | 0 | 0
273 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000342/2023-2024 | 79/MURD/09 | 09/01/2024 | 0 | Resource Division | 31.88 | 0 | 0
274 | Murshidabad Division | Berhampur Sub-Division | Construction of Approach Road , Drain and Drum sheet walling work at Rejinagar Zone - IV PWSS in Beldanga-II Block of Berhampore Sub-Division under Murshidabad P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000187/2024-2025 | 3176/MURD | 05/12/2024 | 30 | MUKTI ENTERPRISE | 15.17 | 0 | 0
275 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 1050 nos household , Construction of 450 Cum OHR, Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement for Augmentation work of REJINAGAR ZONE-IV Beldanga -II Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000258/2023-2024 | 2469/MURD | 09/08/2023 | 1006 | M/S. S.C. CIVIL ENTERPRISES | 482.41 | 0 | 45
276 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 100
277 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000023/2024-2025 | 1811/MURD/22 | 20/06/2024 | 0 | Resource Division | 6.47 | 0 | 0
278 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000221/2023-2024 | 1219/MURD/24 | 03/05/2023 | 0 | Resource Division | 51.16 | 0 | 0
279 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
280 | Murshidabad Division | Berhampur M/E Division | Formal work order for MADHUPUR PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jiban Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000822/2022-2023 | 686/MURD | 10/03/2023 | 365 | M/S KHAN CHOWDHURY BROTHERS AND CO | 224.5 | 0 | 0
281 | Murshidabad Division | Berhampur M/E Division | MADHUPUR PWSS Construction to accommodate FHTC, Laying Distribution System , Rising Main under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000874/2022-2023 | 883/MURD | 28/03/2023 | 918 | SHYAMAL KUMAR SAHA | 231.54 | 0 | 40
282 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000287/2023-2024 | 1230/MURD/28 | 04/05/2023 | 0 | Resource Division | 33.76 | 0 | 0
283 | Murshidabad Division | Berhampur M/E Division | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000105/2024-2025 | 2195/MURD | 31/07/2024 | 30 | SARKAR WATER SUPPLY AGENCY | 23.56 | 0 | 50
284 | Murshidabad Division | Berhampur M/E Division | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 10
285 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
286 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000251/2023-2024 | 1219/MURD/36 | 03/05/2023 | 0 | Resource Division | 48.16 | 0 | 0
287 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000376/2023-2024 | 495/MURD/05 | 15/02/2024 | 0 | Resource Division | 23.89 | 0 | 0
288 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHARJJUNA Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000289/2023-2024 | 2635/MURD | 23/08/2023 | 587 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 67
289 | Murshidabad Division | Kandi Sub-Division | KHARJJUNA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000437/2023-2024 | 2885/MURD | 12/09/2023 | 659 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 1366.57 | 0 | 35
290 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000229/2023-2024 | 1219/MURD/19 | 03/05/2023 | 0 | Resource Division | 35.82 | 0 | 0
291 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
292 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
293 | Murshidabad Division | Berhampur M/E Division | Augmentation of AMINABAD ZONE-I Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000725/2023-2024 | 3952/MURD | 26/12/2023 | 724 | M/S GUHA & ROY ENTERPRISE | 446.08 | 0 | 75
294 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000195/2023-2024 | 1210/MURD/07 | 02/05/2023 | 0 | Resource Division | 69.83 | 0 | 0
295 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, FHTC of AOCHA water supply scheme of BHARATPUR-II Block under Murshidabad Division, PHE Dte. in the District of Murshidabad Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000221/2023-2024 | 2326/MURD | 02/08/2023 | 937 | M/S GUHA & ROY ENTERPRISE | 380.76 | 0 | 35
296 | Murshidabad Division | Kandi Sub-Division | Construction of 500 Cum OHR, Pump House Boundary Wall, Land Development, Rising Main Connection, Laying Distribution System of AOCHA water supply scheme of BHARATPUR-II Block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000245/2023-2024 | 2433/MURD | 08/08/2023 | 1242 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 461.64 | 0 | 10
297 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AOCHA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000285/2023-2024 | 2633/MURD | 23/08/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 27.64 | 0 | 30
298 | Murshidabad Division | Kandi Sub-Division | Allied & Balance work for Road Restoration of Damaged During Laying of pipeline and Laying of distribution pipe line of AOCHA Piped Water Supply Scheme, Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000840/2023-2024 | 818/MURD | 15/03/2024 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.81 | 0 | 10
299 | Murshidabad Division | Kandi Sub-Division | Formal work order for KALGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000850/2022-2023 | 780/MURD | 20/03/2023 | 1278 | SOFIQUL ISLAM | 329.98 | 0 | 20
300 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000060/2023-2024 | 1075/MURD/4 | 19/04/2023 | 0 | Resource Division | 20.47 | 0 | 0
301 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gafulia & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000049/2023-2024 | 1218/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 100
302 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC in GAFULIA Water at Supply Scheme in Burwan Block , under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000152/2023-2024 | 1900/MURD | 17/07/2023 | 120 | MITRA CONSTRUCTION | 263.45 | 0 | 31
303 | Murshidabad Division | Kandi Sub-Division | Formal work order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall of GAFULIA PWSS, in Burwan Block under Murshidabad Division ,PHE.Dte. [ (i)Amount for LDS , R. Main : Rs. 52,45,981.00 & (ii) Amount for OHR, & Pump House : Rs. 1,56,36,015.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000792/2022-2023 | 592/MURD | 01/03/2023 | 853 | H.L. CONSTRUCTION (TITAN BISWAS) | 208.8 | 0 | 53
304 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000073/2022-2023 | 1278/MURD/17 | 10/05/2023 | 0 | Resource Division | 27.87 | 0 | 0
305 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000334/2023-2024 | 79/MURD/01 | 09/01/2024 | 0 | Resource Division | 12.43 | 0 | 0
306 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000366/2023-2024 | MURD/439/10 | 08/02/2024 | 0 | Resource Division | 0.56 | 0 | 0
307 | Murshidabad Division | Kandi Sub-Division | Laying Distribution system, of Gunanadabati PWSS in Bharatpur-I Block of Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000183/2024-2025 | 3147/MURD | 03/12/2024 | 179 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 21.46 | 0 | 80
308 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GUNANANDABATI PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-I Block under Kandi SubDivision, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000659/2022-2023 | 3404/MURD | 22/12/2022 | 45 | M/S D. PALIT & CO. | 16.81 | 0 | 100
309 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-A) of Gunanandabati PWSS at Bharatpur-I Block, Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000698/2022-2023 | 131/MURD | 16/01/2023 | 697 | HARAPRASAD DAS | 132.64 | 0 | 85
310 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of GUNANANDABATI PWSS in Bharatpur-I Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,31,40,916.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,38,880.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000763/2022-2023 | 479/MURD | 20/02/2023 | 365 | S.&P. ENTERPRISE | 280.74 | 0 | 0
311 | Murshidabad Division | Kandi Sub-Division | Construction of RCC Retaining Wall for Gunanandabati PWSS at Bharatpur-I Block under Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000825/2023-2024 | 767/MURD | 13/03/2024 | 483 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 20.69 | 0 | 100
312 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000012/2023-2024 | 1210/MURD/43 | 02/05/2023 | 0 | Resource Division | 20.97 | 0 | 0
313 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of PARULIA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362284S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000693/2022-2023 | 165/MURD | 17/01/2023 | 1353 | M/S.TAPAS KUMAR CHAKRABORTY | 677.2 | 0 | 41
314 | Murshidabad Division | Kandi Sub-Division | Allied work of PARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000741/2023-2024 | 66/MURD | 08/01/2024 | 479 | M/S.TAPAS KUMAR CHAKRABORTY | 53.37 | 0 | 10
315 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000040/2023-2024 | 1004/MURD/15 | 17/04/2023 | 0 | Resource Division | 46.68 | 0 | 0
316 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000116/2022-2023 | 1199/MURD | 10/05/2022 | 45 | NADIA TUBEWELLS | 16.6 | 0 | 100
317 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tikar Bariakalkihara ( Village Code -314642) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000479/2020-2021 | 579/MURD | 09/02/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 40.1 | 0 | 100
318 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000670/2022-2023 | 3411/MURD | 22/12/2022 | 984 | R.K. DRILLING SERVICES | 8.4 | 0 | 100
319 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bazeosmanpur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000404/2023-2024 | 2829/MURD | 07/09/2023 | 60 | KALAM SK. | 24.4 | 0 | 60
320 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Jot Sundar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000405/2023-2024 | 2830/MURD | 07/09/2023 | 907 | FRIENDS CONSTRUCTION | 34.71 | 0 | 40
321 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Raghupur village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000406/2023-2024 | 2832/MURD | 07/09/2023 | 60 | MINA DAS | 34.79 | 0 | 0
322 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Chator village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000407/2023-2024 | 2834/MURD | 07/09/2023 | 725 | SUMAN ENTERPRISE AND SUMAN AQUA | 39.37 | 0 | 25
323 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Lakshmipur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000409/2023-2024 | 2828/MURD | 07/09/2023 | 847 | DEBOJYOTI CONSTRUCTION | 24.68 | 0 | 60
324 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Gangin village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000411/2023-2024 | 2835/MURD | 07/09/2023 | 60 | PRASANTA BISWAS | 24.4 | 0 | 0
325 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Ramdova village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000416/2023-2024 | 2836/MURD | 07/09/2023 | 847 | K. B. CONSTRUCTION (PROP.KUNTAL BHATTACHARYA) | 26.05 | 0 | 65
326 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000417/2023-2024 | 2837/MURD | 07/09/2023 | 60 | JYOTI TRADERS | 26.44 | 0 | 0
327 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bhairab Danga village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000433/2023-2024 | 2869/MURD | 11/09/2023 | 60 | SAIF TRADERS | 34.71 | 0 | 0
328 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Sudna village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000434/2023-2024 | 2871/MURD | 11/09/2023 | 60 | SO-FINE AQUARIUM | 36.59 | 0 | 50
329 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Char Juranpur village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000435/2023-2024 | 2872/MURD | 11/09/2023 | 60 | R.S CONSTRUCTION (PART- ROBIN ROY) | 23.3 | 0 | 0
330 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Nagri village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000448/2023-2024 | 2970/MURD | 20/09/2023 | 834 | DAS CONSTRACTION (MUNNA DAS) | 28.21 | 0 | 40
331 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Par Debidaspur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000466/2023-2024 | 2988/MURD | 21/09/2023 | 527 | PRADIP MAHATO | 37.08 | 0 | 60
332 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Baje Chuator village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000467/2023-2024 | 2985/MURD | 21/09/2023 | 680 | PARTHA BHASKAR | 36.59 | 0 | 10
333 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Berbari village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000468/2023-2024 | 2986/MURD | 21/09/2023 | 60 | PAMIR ROY | 33.05 | 0 | 0
334 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Mas Danga village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000469/2023-2024 | 2987/MURD | 21/09/2023 | 60 | SHIBAM ENTERPRISE | 28.21 | 0 | 0
335 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Jot Raghu village, Block:- Farakka, Jangipur Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000470/2023-2024 | 2984/MURD | 21/09/2023 | 833 | RAJIB SAHA | 28.21 | 0 | 30
336 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000554/2023-2024 | 3215/MURD | 13/10/2023 | 811 | BISWAJIT ROY | 29.49 | 0 | 80
337 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Bilkurul village, Block:- Bharatpur-I, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000642/2023-2024 | 3464/MURD | 06/11/2023 | 60 | SK CONSTRUCTION (NAJIR SK.) | 30.77 | 0 | 0
338 | Murshidabad Division | Kandi Sub-Division | Ground Water based mini piped water supply scheme for Abbhla village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000643/2023-2024 | 3465/MURD | 06/11/2023 | 60 | RURAL CONSTRUCTION | 31.63 | 0 | 0
339 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
340 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
341 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 06(SIX)Months.(Period from 01.07.2022 to 31.12.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000357/2022-2023 | 264/BSD | 22/06/2022 | 183 | SISIR KUMAR DE | 0.91 | 0 | 100
342 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMPUR-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000518/2021-2022 | 350/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
343 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2022 to 31.05.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000619/2022-2023 | 326/HQ | 25/11/2022 | 181 | DULAL CHOWDHURY | 0.91 | 0 | 0
344 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 03(Three)Months.(Period from 01.04.2022 to 30.06.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001626/2021-2022 | 98/BSD | 22/03/2022 | 3 | SISIR KUMAR DE | 0.91 | 0 | 0
345 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2022 to 30/09/2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001800/2021-2022 | 151/HQ | 25/03/2022 | 6 | SISIR KUMAR DE | 0.91 | 0 | 0
346 | Murshidabad Division | Berhampur Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 0 | 1
347 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANDIBANDHA (Village Code 315327) under SAHAJADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 832 of 20-21 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000728/2022-2023 | 256-MSD/22-23 | 12/08/2022 | 0 | MAJUMDER CONSTRUCTION | 9.67 | 0 | 0
348 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR EE-MSD, OCT-22 NOV-22 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001076/2022-2023 | 434-MSD/22-23 | 08/12/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0
349 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR OF SE-MC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001078/2022-2023 | 435-MSD/22-23 | 10/12/2022 | 0 | HASNA BEWA | 1.02 | 0 | 0
350 | Murshidabad Division | Berhampur Sub-Division | HIRING OF VEHICLE OF AE-JSD...FROM 01/09/2022 TO 26/10/2022 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001101/2022-2023 | 444-MSD/22-23 | 15/12/2022 | 0 | MADAN MOHAN SASMAL | 0.42 | 0 | 0
351 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR FOR AE-KSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001248/2022-2023 | 524-MSD/22-23 | 03/02/2023 | 0 | SISIR KUMAR DE | 5.4 | 0 | 0
352 | Murshidabad Division | Berhampur Sub-Division | HIRING OF CAR FOR AE-JSD, W/O NO- 29/MURD, 06/01/2022 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001250/2022-2023 | 526-MSD/22-23 | 11/02/2023 | 0 | MADAN MOHAN SASMAL | 0.48 | 0 | 0
353 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Madhupur (Village code 315333) under Arazi Madhupur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184184 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000013/2022-2023 | 873/MURD | 01/04/2022 | 30 | M/S SAJAHAN CHOWDHURY | 35.47 | 0 | 0
354 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Arazi Madhupur(VILLAGE CODE-315333) Ground Based piped water supply scheme of Arazi Madhupur (south portion) & its adjoining mouzas under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000154/2022-2023 | 152/BSD | 12/04/2022 | 30 | PARUL ELECTRICAL INSTALLER | 3.99 | 0 | 80
355 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Arazi Madhupur (315333) Ground Based piped water supply scheme of south portion of the scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001785/2021-2022 | 109/BSD | 28/03/2022 | 853 | DATA ENTERPRISE | 4.29 | 0 | 90
356 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000017/2021-2022 | 539/2/MURD | 25/02/2022 | 0 | Resource Division | 5.23 | 0 | 0
357 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of MahishaThali( Village Code -313851) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105) |  |  | ORD/000608/2020-2021 | 598/MURD | 09/02/2021 | 60 | HARUN ALL RASHID & BROTHERS | 30.42 | 0 | 1
358 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MAHISHA THALI (Village Code 313851) under DOGACHHI Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 828 of 20-21 by EE MURD |  |  | VCH/001460/2021-2022 | 360-MSD/21-22 | 10/03/2022 | 0 | HARUN-AL-RASHID & BROTHERS | 17 | 0 | 0
359 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Division. PHE DTE.(SCHEME ID : 0001723328) TENDER NO 89 OF 20-21 BY SE / MC |  |  | VCH/000193/2021-2022 | 09 - MSD/21-22 | 04/08/2021 | 0 | M/S. GOUTAM CHAKRABORTY | 38.65 | 0 | 0
360 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sabdalpur (Village code 314704) under Shibnagar Laskarpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723328 in the District of Murshidabad. (Sl No-20) |  |  | VCH/000693/2022-2023 | 218-MSD/22-23 | 27/07/2022 | 0 | M/S. GOUTAM CHAKRABORTY | 26.57 | 0 | 0
361 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahadiar (Village code 314736) under Aminabad Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723383 (Sl No-6) |  |  | ORD/000288/2021-2022 | 1550/MURD | 23/06/2021 | 180 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 75.82 | 0 | 0
362 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna ( Jal Jeevan Mission) under command area of Aminabad (Village code 314730), under Aminabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723383) |  |  | ORD/000332/2022-2023 | 1699/MURD | 29/06/2022 | 120 | M/S. BIMALENDU BOSE | 113.8 | 0 | 0
363 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kuchemora (Village code 314735) under Aminabad Ground Water Supply Scheme for Arsenic Affected Area of DomkalBlock, under Murshidabad Division, PHE Dte. Scheme ID: 0001723383 (Sl-05) |  |  | ORD/000367/2021-2022 | 2533/MURD | 19/08/2021 | 180 | M/S UNIVERSAL TRADING | 89.39 | 0 | 0
364 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 541/4/MURD | 25/02/2022 | 0 | Resource Division | 1.2 | 0 | 0
365 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I), TNO- 112/20-21/SE-MC |  |  | VCH/000670/2021-2022 | 150-MSD/21-22 | 10/10/2021 | 0 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 53.58 | 0 | 0
366 | Murshidabad Division |  | HIRING OF CAR FOR JANGIPUR SUB DIVISION, PHE DTE. |  |  | BILL/00066/2022-2023 |  | 09/12/2022 | 0 | MADAN MOHAN SASMAL | 0.42 | 0 | 0
367 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barala (Village code 314009) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-9) |  |  | ORD/000294/2020-2021 | 48/MURD | 06/01/2021 | 180 | M/S UNIVERSAL TRADING | 63.12 | 0 | 100
368 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS MITHIPUR PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001141/2021-2022 | 3252/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.65 | 5.65 | 1
369 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MITHIPUR (Village code 314136) under MITHIPUR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005186173 |  |  | ORD/001154/2021-2022 | 3974/MURD | 21/12/2021 | 180 | M/S. SINHA & SONS | 108.7 | 0 | 0
370 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000039/2021-2022 | 540/12/MURD | 25/02/2022 | 0 | Resource Division | 15.81 | 0 | 0
371 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 419 of 21-22 by EE MURD |  |  | VCH/001369/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 0 | 0
372 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 420 of 21-22 by EE MURD |  |  | VCH/001371/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.65 | 0 | 0
373 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kalabaria ( Village Code -314662) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) |  |  | ORD/000299/2021-2022 | 1932/MURD | 22/07/2021 | 60 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 13.35 | 0 | 0
374 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village KALABARIA (Village Code 314662) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad. |  |  | ORD/000642/2020-2021 | 2572/MURD | 01/10/2020 | 45 | NATIONAL ENTERPRISE | 20.28 | 0 | 0
375 | Murshidabad Division |  | Balanced and Allied Works for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Domkol (Village code 314695) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184127 in the District of Murshidabad. |  |  | ORD/001650/2021-2022 | 309/MURD | 07/02/2022 | 60 | ARINDAM MAJUMDAR | 35.08 | 0 | 0
376 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DOMKAL (Village Code-314695) under DOMKAL Ground based Water Supply Scheme for Aesenic Affected area of Domkal Block under Murshidabad District under Murshidabad Division, PHE Dte. (Scheme Id 0005184127) in the dist of MSD. |  |  | VCH/000232/2021-2022 | 28-MSD / 21-22 | 25/08/2021 | 0 | ARINDAM MAJUMDAR | 14.32 | 0 | 0
377 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
378 | Murshidabad Division |  | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. |  |  | ORD/000110/2024-2025 | 2211/MURD | 02/08/2024 | 30 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0
379 | Murshidabad Division |  | Extension of Distribution UPVC pipeline and allied works for providing balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of mouzaAzmatpur ( Village Code -314776) of Azmatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme I.D.- 0005019112). (PART-I) |  |  | ORD/000287/2022-2023 | 276/ISD | 27/06/2022 | 30 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 4.75 | 0 | 1
380 | Murshidabad Division |  | Extension of Distribution UPVC pipeline and allied works for providing balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of mouzaAzmatpur ( Village Code -314776) of Azmatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme I.D.- 0005019112). (PART-II) |  |  | ORD/000328/2022-2023 | 277/ISD | 27/06/2022 | 30 | JAYANTA KUMAR ROY | 4.72 | 0 | 1
381 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Natkuli (Village code 314779) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000500/2020-2021 | 3230/MURD | 22/12/2020 | 60 | PAL TROCKNER (P) LTD. | 24.64 | 0 | 1
382 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Firojpur (Village code 314774) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000534/2020-2021 | 92/MURD | 08/01/2021 | 60 | DEBEN RAJAK | 5.58 | 0 | 1
383 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ichhabpur (Village code 314777) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005019112 in the District of Murshidabad. |  |  | ORD/000556/2020-2021 | 326/MURD | 28/01/2021 | 60 | NOBEL CONSTRUCTION | 6.11 | 0 | 0
384 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Firojpur (Village code 314774) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000609/2020-2021 | 92 /MURD | 08/01/2021 | 60 | DEBEN RAJAK | 5.58 | 0 | 1
385 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandpur (Village code 314772) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000610/2020-2021 | 89/MURD | 08/01/2021 | 60 | HARUN ALL RASHID & BROTHERS | 7.25 | 0 | 0
386 | Murshidabad Division |  | Laying of distribution system pipe line and connection with street stand post and Construction of soak well in connection with Dengue control for different Anganwadi Centres under Nowda Development Block 1 Chandpur kuthipara 2. Kulaichandi 3. Rathtalapara 4. Goghata uttarpara 5. Ghoghata ghatpara 6. Ghoghata halderpara 7.Chandpur Halderpara 8.Chandpur dey biswaspara. under Berhampore Sub division. P.H.E.Dte. |  |  | ORD/000742/2020-2021 | 3202/MURD | 18/12/2020 | 15 | PRANAB KUMAR GHOSH | 4.87 | 0 | 1
387 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village Char Hulaspur (Village code 314770) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000784/2020-2021 | 90./MURD | 08/01/2021 | 60 | SAMRAT MAZUMDER | 6.96 | 0 | 0
388 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raosannagar (Village code 314771) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000785/2020-2021 | 91./MURD | 08/01/2021 | 60 | AJAY MONDAL | 9.01 | 0 | 0
389 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village Paharpur (Village code 314773) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. |  |  | ORD/000786/2020-2021 | 3231/MURD | 22/12/2020 | 60 | PAL TROCKNER PVT. LTD. | 33.51 | 0 | 0
390 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mision (JJM) from existing distribution system within the command area of Village ICHHABPUR (Village Code- 314777) under AZMATPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block under Murshidabad District under Murshidabad Division, PHE Dte. Scheme id - 0005019112. Tender no- 797 of 20-21 by EE / MURD |  |  | VCH/000201/2021-2022 | 14-MSD / 21-22 | 06/08/2021 | 0 | NOBEL CONSTRUCTION | 4.66 | 0 | 0
391 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NATKULI (Village Code 314779) under AZMATPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-I Block in the District of Murshidabad. Tender no - 941 of 20-21 by EE MURD |  |  | VCH/001485/2021-2022 | 422-MSD/21-22 | 23/03/2022 | 0 | PAL TROCKNER (P) LTD. | 20.51 | 0 | 0
392 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilaspur (Village code 314681 ) under Bilaspur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723482 (Sl No-05) |  |  | ORD/000889/2021-2022 | 3334/MURD | 07/10/2021 | 1354 | SUDIPA SINGHA ROY | 60.39 | 0 | 50
393 | Murshidabad Division |  | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Approach Road under Bilashpur Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001238/2021-2022 | 44/ISD | 28/01/2022 | 30 | PARUL ELECTRICAL INSTALLER | 3.95 | 0 | 1
394 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- SAMANDI , CODE-315122, TNO- 573/2020-21/EE |  |  | VCH/002014/2020-2021 | 473/W | 08/03/2021 | 0 | APURBA SAHA CHOWDHURY | 16.4 | 0 | 0
395 | Murshidabad Division |  | LAND DEVELOPMENT AT HW SITE OF MAHALANDI Z-II WSS, TNO- 551/20-21/EE |  |  | VCH/002053/2020-2021 | 479/W | 12/03/2021 | 0 | APURBA SAHA CHOWDHURY | 4.76 | 0 | 0
396 | Murshidabad Division |  | SANITARY & PLUMBING ARRANGEMENT....HW SITE OF BAHARA WSS, TNO- 06/20-21/AE-KSD |  |  | VCH/002054/2020-2021 | 479/W | 12/03/2021 | 0 | AYAN ENTERPRISE | 1.19 | 0 | 0
397 | Murshidabad Division |  | LAYING OF UPVC PIPELINE FOR DIST SYSTEM...VULNERABLE POINT OF GOPAL NAGAR PRY.. SCHOOL.. UNDER DEULI OHR, RAGHUNATHGANJ SURFACE WSS, TNO- 072/20-21/EE |  |  | VCH/002055/2020-2021 | 479/W | 12/03/2021 | 0 | DEBASIS BOSE | 3.2 | 0 | 0
398 | Murshidabad Division |  | HIRING OF CAR BILL FOR AE-ISD, W/O NO- 200/ISD, DT- 25/09/2020 |  |  | VCH/002056/2020-2021 | 479/W | 12/03/2021 | 0 | MADAN MOHAN SASMAL | 0.77 | 0 | 0
399 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of ---BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - MATAI CODE- 315090 , TNO- 625/20-21/EE |  |  | VCH/002057/2020-2021 | 479/W | 12/03/2021 | 0 | M/S UNIQUE BUILDERS | 11.41 | 0 | 0
400 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ramnagar ( Village Code -315658) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000082/2021-2022 | 1562/MURD | 24/06/2021 | 60 | M/S. CHOWDHURY CONSTRUCTION | 41.52 | 0 | 1
401 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bidupara ( Village Code -315659) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000181/2021-2022 | 1568/MURD | 25/06/2021 | 60 | M/S GUHA & ROY ENTERPRISE | 36.04 | 35.92 | 1
402 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bachhara ( Village Code -315653) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000182/2021-2022 | 1571/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 68.02 | 28.11 | 1
403 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000450/2021-2022 | 300/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 4.34 | 0
404 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMNAGAR BACHHARA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000508/2021-2022 | 343/BSD | 27/08/2021 | 30 | M/S. S. DAS AND ENTERPRISE | 4.16 | 0 | 1
405 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mohammadpur ( Village Code -315650) under Bachhara Ground WaterBased Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001160/2021-2022 | 1569 /MURD | 25/06/2021 | 60 | M/S GUHA & ROY ENTERPRISE | 43.43 | 0 | 1
406 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (village code 315658) under Bachhara Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001732/2021-2022 | 92/BSD | 07/03/2022 | 15 | SUMAN CHOWDHURY | 4.83 | 0 | 0
407 | Murshidabad Division | Berhampur Sub-Division | Laying of different dia (75mm & 90mm) UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (village code 315658) under Bachhara Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001734/2021-2022 | 93/BSD | 07/03/2022 | 15 | SUMAN CHOWDHURY | 4.85 | 0 | 0
408 | Murshidabad Division | Berhampur Sub-Division | Laying of different dia 75 mm and 90mm dia UPVC pipeline in connection providing FHTC in connection with JJM and JS under command area of vilage of Ramnagar (Village code 315658) under Bachhara W/S Scheme in MSD PH DTE. Tender no - 186 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000015/2022-2023 | 18-MSD/22-23 | 21/04/2022 | 0 | SUMAN CHOWDHURY | 4.84 | 0 | 0
409 | Murshidabad Division | Berhampur Sub-Division | Laying of 110 mm dia UPVC pipeline in connection providing FHTC in connection with JJM and JS under command area of vilage of Ramnagar (Village code 315658) under Bachhara W/S Scheme in MSD PH DTE. Tender no - 185 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000016/2022-2023 | 17-MSD/22-23 | 21/04/2022 | 0 | SUMAN CHOWDHURY | 4.83 | 0 | 0
410 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BACHHARA (Village Code 315653) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 342 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000378/2022-2023 | 151-MSD/22-23 | 11/05/2022 | 0 | SWAPAN DAS | 39.79 | 0 | 0
411 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAMNAGAR HABITATION (Village Code 315658) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 274 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001464/2021-2022 | 361-MSD/21-22 | 11/03/2022 | 0 | M/S. CHOWDHURY CONSTRUCTION | 14.54 | 0 | 0
412 | Murshidabad Division | Berhampur Sub-Division | Additional work of providing Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BIDUPARA (Village Code 315659) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 344 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001550/2021-2022 | 365-MSD/21-22 | 12/03/2022 | 0 | MITHUN ROY | 26.44 | 0 | 0
413 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 90
414 | Murshidabad Division | Jangipur Sub-Division | Laying Distribution system, Rising Main Connection, FHTC(834 Nos) Construction of Boundary Wall , Pump House,Sinking of 300 x 200 mm dia Rig Bore Tubewell of Sikarpur PWSS in Farakka Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000744/2023-2024 | 60/MURD | 08/01/2024 | 724 | S.S. ENTERPRISE | 98.78 | 0 | 30
415 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 90
416 | Murshidabad Division | Berhampur M/E Division | Construction of Ground Water Based Gokul Chak PWSS of accommodate FHTC(834 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall in Domkal Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000726/2023-2024 | 3953/MURD | 26/12/2023 | 573 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 108.82 | 0 | 60
417 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000868/2023-2024 | 832/MURD | 15/03/2024 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 100
418 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
419 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000133/2023-2024 | 1769/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 18.45 | 0 | 100
420 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
421 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000557/2023-2024 | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0
422 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000176/2023-2024 | 1180/MURD/25 | 29/04/2023 | 0 | Resource Division | 39.84 | 0 | 0
423 | Murshidabad Division | Jangipur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDHUA ZONE -III Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000749/2023-2024 | 114/MURD | 11/01/2024 | 21 | HARUN ALL RASHID & BROTHERS | 23.53 | 0 | 50
424 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 35
425 | Murshidabad Division | Jangipur Sub-Division | Continuation work order for preparation of D.P.R. for Augmentation of Andhua Zone- II & Zone - III PWSS in Farakka Block in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000879/2023-2024 | 3720/MURD | 05/12/2023 | 30 | M/S SOBHA & CO. | 4.51 | 0 | 100
426 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000170/2023-2024 | 1180/MURD/19 | 29/04/2023 | 0 | Resource Division | 65.79 | 0 | 0
427 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000388/2023-2024 | 2778/MURD | 01/09/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.21 | 0 | 100
428 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 90
429 | Murshidabad Division | Kandi Sub-Division | Formal work order for BHAGULIA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000805/2022-2023 | 619/MURD | 03/03/2023 | 760 | SUMAN ENTERPRISE AND SUMAN AQUA | 183.62 | 0 | 50
430 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000074/2023-2024 | 1075/MURD/16 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
431 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000338/2023-2024 | 79/MURD/05 | 09/01/2024 | 0 | Resource Division | 3.82 | 0 | 0
432 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000357/2023-2024 | MURD/439/02 | 08/02/2024 | 0 | Resource Division | 0.03 | 0 | 0
433 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
434 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORAMARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000619/2023-2024 | 3394/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 50
435 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of GHORAMARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000733/2022-2023 | 375/MURD | 10/02/2023 | 365 | PRODEEP KUMAR GHOSH | 295.5 | 0 | 0
436 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000270/2023-2024 | 1230/MURD/14 | 04/05/2023 | 0 | Resource Division | 14.54 | 0 | 0
437 | Murshidabad Division | Kandi Sub-Division | Formal work order for SYAMPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of BURWAN Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000858/2022-2023 | 803/MURD | 22/03/2023 | 1381 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 448.94 | 0 | 75
438 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000063/2023-2024 | 1075/MURD/6 | 19/04/2023 | 0 | Resource Division | 10.59 | 0 | 0
439 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000119/2023-2024 | 1771/MURD | 06/07/2023 | 684 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 40
440 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHACHANDA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000271/2023-2024 | 2589/MURD | 21/08/2023 | 587 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 100
441 | Murshidabad Division | Berhampur M/E Division | CHACHANDA PWSS to accommodate FHTC under Jal Jeevan Mission of SAMSERGANJ Block, Sub Division - Jangipur of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000451/2023-2024 | 2983/MURD | 21/09/2023 | 558 | M/S NIRAPADA BHATTACHARJEE | 567.03 | 0 | 15
442 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
443 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ADWAITA NAGAR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000283/2023-2024 | 2631/MURD | 23/08/2023 | 495 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
444 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
445 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of ADWAITA NAGAR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jiban Mission of Samserganj Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000820/2022-2023 | 621/MURD | 03/03/2023 | 758 | ARPAN PANDIT | 342.16 | 0 | 40
446 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000281/2023-2024 | 1230/MURD/23 | 04/05/2023 | 0 | Resource Division | 37.63 | 0 | 0
447 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
448 | Murshidabad Division | Jangipur Sub-Division | Laying of Distribution System for Augmentation of KADOA (ZONE-I) Part B PWSS in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000862/2022-2023 | 807/MURD | 22/03/2023 | 741 | M/S GUNGUN CONSTRUCTION | 137.96 | 0 | 92
449 | Murshidabad Division | Jangipur Sub-Division | Providing FHTC Connection to 923 no household and Overhauling of RCC 450 Cum OHR for Augmentation of KADOA (ZONE-I) Part B Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000866/2022-2023 | 829/MURD | 23/03/2023 | 1099 | SAMAR MUKHERJEE | 127.28 | 0 | 90
450 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000198/2023-2024 | 1210/MURD/06 | 02/05/2023 | 0 | Resource Division | 137.87 | 0 | 0
451 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000385/2023-2024 | 495/MURD/11 | 15/02/2024 | 0 | Resource Division | 25.47 | 0 | 0
452 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
453 | Murshidabad Division | Kandi Sub-Division | INDRANI (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000172/2023-2024 | 1988/MURD | 21/07/2023 | 865 | DHIRENDRANATH MONDAL | 569.67 | 0 | 10
454 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000670/2022-2023 | 3411/MURD | 22/12/2022 | 984 | R.K. DRILLING SERVICES | 8.4 | 0 | 100
455 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
456 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000053/2023-2024 | 1067/MURD/9 | 18/04/2023 | 0 | Resource Division | 69.6 | 0 | 0
457 | Murshidabad Division | Kandi Sub-Division | Allied work for Laying Distribution System, Construction of Boundary Wall, Approach Road & Land Development of Jajan PWSS in Bhratpur-I Block , KANDI Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000835/2023-2024 | 768/MURD | 13/03/2024 | 366 | GOURANGA MONDAL | 59.79 | 0 | 10
458 | Murshidabad Division | Kandi Sub-Division | JAJAN & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000838/2022-2023 | 758/MURD | 16/03/2023 | 777 | GOURANGA MONDAL | 343.34 | 0 | 10
459 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000065/2023-2024 | 1075/MURD/8 | 19/04/2023 | 0 | Resource Division | 22.01 | 0 | 0
460 | Murshidabad Division | Kandi Sub-Division | Balance work of Construction of Boundary wall of 55 m length at Tentulia PWSS in Kandi block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000078/2025-2026 | 1345/MURD | 11/06/2025 | 60 | AMIT KUMAR SAHA | 6.83 | 0 | 0
461 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of TENTULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000708/2022-2023 | 122/MURD | 13/01/2023 | 1173 | SOUNAK ENTERPRISE | 271.09 | 0 | 10
462 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000052/2023-2024 | 1067/MURD/8 | 18/04/2023 | 0 | Resource Division | 1.31 | 0 | 0
463 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 60 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for FATELLAPUR Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000038/2025-2026 | 1155/MURD | 20/05/2025 | 60 | WATER TECH | 33.62 | 0 | 0
464 | Murshidabad Division | Berhampur M/E Division | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Fatellapur Water Supply Scheme at Suti-I Block of Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000098/2024-2025 | 2131/MURD | 26/07/2024 | 224 | KHOKAN BISWAS | 11.76 | 0 | 100
465 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
466 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at FATELLAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000712/2023-2024 | 3837/MURD | 14/12/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 0 | 100
467 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main & Distribution System for Augmentation of FATELLAPUR Piped Water Supply in SUTI-I Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000839/2022-2023 | 743/MURD | 16/03/2023 | 1151 | RAJU ENTERPRISE | 66.32 | 0 | 36
468 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 1823 no household, Overhauling of RCC 350 Cum OHR & Repair of Boundary Wall =150 m at T/W-I site & T/W-II site for Augmentation of FATELLAPUR Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000878/2022-2023 | 903/MURD | 29/03/2023 | 180 | M/S M.S. ENTERPRISE | 106.37 | 0 | 0
469 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000190/2023-2024 | 1210/MURD/18 | 02/05/2023 | 0 | Resource Division | 24.99 | 0 | 0
470 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of SURANGAPUR Zone-I / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000373/2022-2023 | 2087/MURD | 27/07/2022 | 365 | MOTI RAHAMAN | 222.6 | 0 | 50
471 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-I Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000596/2022-2023 | 3070/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 0 | 100
472 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 0 | 1
473 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000009/2024-2025 | 1811/MURD/08 | 20/06/2024 | 0 | Resource Division | 34.58 | 0 | 0
474 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000295/2023-2024 | 1278/MURD/1 | 10/05/2023 | 0 | Resource Division | 75.24 | 0 | 0
475 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000353/2023-2024 | 305/MURD/02 | 29/01/2024 | 0 | Resource Division | 62.68 | 0 | 0
476 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of KHAYRAMARI (Part-B) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000334/2022-2023 | 1721/MURD | 04/07/2022 | 1276 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 262.6 | 0 | 30
477 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000033/2024-2025 | MURD/2481/05 | 04/09/2024 | 0 | Resource Division | 5.07 | 0 | 0
478 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000042/2022-2023 | 2780/K/MURD | 01/10/2022 | 0 | Resource Division | 5.07 | 0 | 0
479 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-II & adjoining mouzas Water Supply Scheme at 3rd work site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000035/2023-2024 | 1110/MURD | 24/04/2023 | 708 | HARUN ALL RASHID & BROTHERS | 10.58 | 0 | 60
480 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-I & adjoining mouzas Water Supply Scheme at Head work site & 3 r d Site at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000125/2023-2024 | 1775/MURD | 06/07/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 23.52 | 0 | 100
481 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000612/2023-2024 | 3377/MURD | 31/10/2023 | 730 | M/S GHOSH & CO. | 1181.6 | 0 | 20
482 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS MIRZAPUR (Except Gankar Mouza) PWSS Scheme,Block-Raghunathgaunge-I) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000687/2021-2022 | 2743/MURD | 03/09/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 0 | 1
483 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-27 |  |  | BILL/00090/2022-2023 | 471-MSD/22-23 | 29/12/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.18 | 0 | 0
484 | Murshidabad Division |  | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000853/2022-2023 | 755/MURD | 16/03/2023 | 90 | SAMBHU NATH ROY | 62.1 | 0 | 0
485 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) |  |  | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 180 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 12
486 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 235/8 & 235/9) on railway land of mouza Joykrishnapur & Connecting with existing 160 mm dia UPVC distribution main line of Joykrishnapur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001645/2021-2022 | 510/MURD | 23/02/2022 | 60 | SAMBHU NATH ROY | 27.25 | 0 | 0
487 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000005/2022-2023 | 889/F/MURD | 05/04/2022 | 0 | Resource Division | 5.44 | 0 | 0
488 | Murshidabad Division |  | Renovation of U.P.V.C of pipe line from Shib Mandir to Kartik Mandir due to widening of Bituminous Road of Prosadpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. |  |  | ORD/000722/2020-2021 | 3328 / MURD | 31/12/2020 | 45 | ARJU CONSTRUCTION | 4.99 | 0 | 0
489 | Murshidabad Division |  | Renovation of UPVC pipe line from Dulal kali to Kartik Mandir due to widening of Bituminous Road of Prosadpur W/S Scheme in an emergency basis under Jangipur Sub-Division under Murshidabad Division, PHE Dte. |  |  | ORD/000723/2020-2021 | 79/JSD | 26/02/2021 | 30 | T.R. CONSTRUCTION | 5 | 0 | 0
490 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
491 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Laskarpur ( Village Code -313850) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019105) |  |  | ORD/000625/2020-2021 | 595/MURD | 09/02/2021 | 60 | ARABINDA GHOSH | 71.56 | 0 | 1
492 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Samserganj Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001176/2021-2022 | 365/JSD | 22/12/2021 | 30 | IMAGIN COMMUNICATION | 2.77 | 0 | 1
493 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. |  |  | ORD/001438/2021-2022 | 557/MURD | 28/02/2022 | 180 | M/S. NANDY ENTERPRISE | 268.47 | 0 | 1
494 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2021-2022 | 3632/A/MURD | 23/11/2021 | 0 | Resource Division | 18.39 | 0 | 0
495 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-I PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 415 of 21-22 by EE MURD |  |  | VCH/001372/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.73 | 0 | 0
496 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-II PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 408 of 21-22 by EE MURD |  |  | VCH/001374/2021-2022 | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.72 | 0 | 0
497 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikhanr Diar (Village code 314638) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad |  |  | ORD/000255/2021-2022 | 1654/MURD | 29/06/2021 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.11 | 0 | 0
498 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
499 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
500 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Azimganjagola( Village Code -314692) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) |  |  | ORD/000313/2021-2022 | 1725/MURD | 08/07/2021 | 60 | MAMATA USHA ENTERPRISE | 35.34 | 0 | 1
501 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Azimganjagola(Village code 314692) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-14) |  |  | ORD/000570/2020-2021 | 3064/MURD | 08/12/2020 | 180 | MAMATA USHA ENTERPRISE | 96.39 | 0 | 1
502 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-52 |  |  | VCH/000875/2022-2023 | 360-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 3.42 | 0 | 0
503 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-53 |  |  | VCH/000876/2022-2023 | 360-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.91 | 0 | 0
504 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-53 |  |  | VCH/000878/2022-2023 |  | 21/09/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.91 | 0 | 0
505 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-HWH-2021-WL-54 |  |  | VCH/000944/2022-2023 | 371-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.97 | 0 | 0
506 | Murshidabad Division |  | Additional works of Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AZIMGANJGOLA (Village Code 314692) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 377 of 210-22 by EE MURD |  |  | VCH/001459/2021-2022 | 357-MSD/21-22 | 09/03/2022 | 0 | MAMATA USHA ENTERPRISE | 29.56 | 0 | 0
507 | Murshidabad Division |  | Repair and Renovation of office cum godown at Head work site for Improvement work of Bhandara Water Supply Scheme under Lalbagh Sub Division,P.H.E. Dte.in the District Murshidabad |  |  | ORD/000057/2020-2021 | 560/MURD | 08/02/2021 | 45 | ARNAB SAHA | 5.93 | 0 | 0
508 | Murshidabad Division |  | Pipe connection from new tube well to rising main including supply of material at Head Work Site of Bhandara Water Supply Scheme under Lalbagh Sub-Division, under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/000077/2022-2023 | 104/LSD | 13/04/2022 | 30 | MAA CONSTRUCTION | 2.1 | 0 | 1
509 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at AMDAHARA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000403/2021-2022 | 246/LSD | 18/08/2021 | 30 | TINA ROY | 4.18 | 0 | 1
510 | Murshidabad Division |  | Providing Functional Household Tap Connections (1296 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Balarampur (Village Code -3144756) & Palasbati (Village Code-314476) under Bhandara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhawangola I & II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000636/2023-2024 | 3457/MURD | 06/11/2023 | 45 | SALAUDDIN MD SIRAJI | 35.76 | 0 | 0
511 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
512 | Murshidabad Division |  | Providing Functional Household Tap Connections ( 250 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Dhulauri ( Village Code -314671) under Dhulauri Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000106/2024-2025 | 2213/MURD | 02/08/2024 | 30 | SUJAUDDIN SHAIKH | 8.8 | 0 | 0
513 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan mission and Jal Swapna under command area of village of Pardiar (village code-314712)under Garibpur(Zone-I & Zone - II)Ground Water Based Water supply Scheme for arsenic affected areas of Domkal Block in Murshidabad District under Murshidabad Division PHE Dte.(scheme ID-0001723342) |  |  | ORD/000112/2022-2023 | 1196/MURD | 10/05/2022 | 30 | ADITYA ENTERPRISE | 11.7 | 0 | 1
514 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pardiar (Village code 314712) under Goribpur (Zone-I and Zone-II) Ground Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723342 |  |  | ORD/000951/2021-2022 | 3631/MURD | 23/11/2021 | 120 | M/S. M.G. CONSTRUCTION | 58.5 | 0 | 1
515 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandpur(Village code 314711) under Garibpur (Zone I and Zone II) Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723342 |  |  | ORD/001258/2021-2022 | 3577 / MURD | 16/11/2021 | 100 | M/S BHUBAN DAS | 52.35 | 0 | 1
516 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PARDIAR (Village Code 314712) under GORIBPUR (ZONE-I AND ZONE-II) Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 107 of 21-22 by SE MC |  |  | VCH/001476/2021-2022 | 385-MSD/21-22 | 16/03/2022 | 0 | M/S. M.G. CONSTRUCTION | 36.63 | 0 | 0
517 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 267 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jadabpur Nimtala ( Village Code -313796) under Jadabpur Nimtala Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000031/2022-2023 | 1089/MURD | 27/04/2022 | 20 | A.P. CONSTRUCTION | 11.9 | 0 | 0
518 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 267 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jadabpur Nimtala ( Village Code -313796) under Jadabpur Nimtala Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000767/2022-2023 | 1089 /MURD | 27/04/2022 | 20 | A.P. CONSTRUCTION | 11.9 | 0 | 0
519 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000029/2021-2022 | 540/2/MURD | 25/02/2022 | 0 | Resource Division | 1.47 | 0 | 0
520 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
521 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of ---BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - MATAI CODE- 315090 , TNO- 625/20-21/EE |  |  | VCH/002057/2020-2021 | 479/W | 12/03/2021 | 0 | M/S UNIQUE BUILDERS | 11.41 | 0 | 0
522 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
523 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
524 | Murshidabad Division | Kandi Sub-Division | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur G.P, Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I G.P, Doulatabad G.P, & Chhaighari G.P connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000112/2020-2021 | 689/MURD | 23/02/2021 | 30 | IMAGIN COMMUNICATION | 3.17 | 3.17 | 0
525 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001278/2021-2022 | 141/MURD | 19/01/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 383.18 | 0 | 1
526 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | RTOR000002/2021-2022 | 3632/B/MURD | 23/11/2021 | 0 | Resource Division | 18.67 | 0 | 0
527 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Khagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Murshidabad District. T NO- 626/20-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000004/2021-2022 | 05/MSD/21-22 | 16/07/2021 | 0 | SOUMYADIP MISRA | 15.24 | 0 | 0
528 | Murshidabad Division | Kandi Sub-Division | Providing FHTC Connection to 510 nos household , Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement & Construction Pump House cum Blower room cum Chlorine room with out sanitary and Water Supply Arrangement RANAGRAM PWSS KANDI Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000244/2023-2024 | 2432/MURD | 08/08/2023 | 180 | R.R. CONSTRUCTION | 70.39 | 0 | 30
529 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000028/2023-2024 | 1129/MURD | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
530 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bharatpur Zone-IB Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000117/2023-2024 | 1768/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 23.58 | 0 | 0
531 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE - I B) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000205/2023-2024 | 2070/MURD | 28/07/2023 | 300 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 478.38 | 0 | 0
532 | Murshidabad Division | Kandi Sub-Division | HAMIDPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000872/2022-2023 | 872/MURD | 27/03/2023 | 857 | PRATIMA CONSTRUCTION | 159.76 | 0 | 5
533 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000070/2023-2024 | 1075/MURD/12 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
534 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000107/2023-2024 | 1749/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 0 | 40
535 | Murshidabad Division | Berhampur M/E Division | Augmentation BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part -A) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000312/2023-2024 | 2676/MURD | 24/08/2023 | 1317 | J.S. CONSTRUCTION | 459.33 | 0 | 40
536 | Murshidabad Division | Berhampur M/E Division | Augmentation of BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000313/2023-2024 | 2677/MURD | 24/08/2023 | 600 | AEF ENTERPRISE (PROP: MAHBUB AKHTAR) | 222.14 | 0 | 20
537 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold Tap Connection of 03(Three) nos existing commisioned PWSS Domkol Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Katakopra Water Supply Scheme Zone-I & II, Bhagarpur Ramna Water Supply Scheme,Baniakhali & Its Adjoining Mouzas Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000345/2022-2023 | 1924/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.09 | 0 | 100
538 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000637/2023-2024 | 3458/MURD | 06/11/2023 | 30 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0
539 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000147/2023-2024 | 1167/MURD/37 | 28/04/2023 | 0 | Resource Division | 153.51 | 0 | 0
540 | Murshidabad Division | Kandi Sub-Division | Allied work for road restoration work liable to be damaged due to pipeline laying at Parbotipur PWSS under Kandi sub-Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000037/2024-2025 | 1912/MURD | 02/07/2024 | 60 | DIPAK KUMAR GHOSH | 42.14 | 0 | 100
541 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW- III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PARBATIPUR AND ADJOINING MOUJAS Water Supply Scheme at 3rd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000402/2023-2024 | 2821/MURD | 07/09/2023 | 421 | INDRAJIT MAZUMDAR | 9.22 | 0 | 100
542 | Murshidabad Division | Kandi Sub-Division | Formal work order for PARBATIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KANDI of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000818/2022-2023 | 675/MURD | 09/03/2023 | 1029 | DIPAK KUMAR GHOSH | 467.48 | 0 | 25
543 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000080/2023-2024 | 1129/MURD/3 | 25/04/2023 | 0 | Resource Division | 15.8 | 0 | 0
544 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000339/2023-2024 | 79/MURD/06 | 09/01/2024 | 0 | Resource Division | 12.55 | 0 | 0
545 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
546 | Murshidabad Division | Berhampur M/E Division | Augmentation of Barabil Raghunathpur Zone-II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 200 m, Construction of 400 Cum OHR(1 no) with sub soil investigation , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging hight 20 mtr under Jal Jeevan Mission of Jalangi Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000590/2023-2024 | 3332/MURD | 23/10/2023 | 766 | ORKID CONSTRUCTION | 217.95 | 0 | 50
547 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000172/2023-2024 | 1180/MURD/22 | 29/04/2023 | 0 | Resource Division | 290.13 | 0 | 0
548 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
549 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 35
550 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000142/2023-2024 | 1167/MURD/40 | 28/04/2023 | 0 | Resource Division | 3.79 | 0 | 0
551 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 20
552 | Murshidabad Division | Berhampur M/E Division | Augmentation of NARASINGHAPUR ZONE-I PWSS Laying Distribution System, Rising Main Connection of JALANGI Block, under Murshidabad Division PHE. Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000558/2023-2024 | 3219/MURD | 13/10/2023 | 180 | M/S UNIVERSAL TRADING | 273.87 | 0 | 20
553 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 1
554 | Murshidabad Division | Berhampur M/E Division | Construction of Pump House, Boundary wall & Providing Functional Household Tap Connection for Augmentation of Narasinghapur Zone-I PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division , PHE. Dte. Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000588/2023-2024 | 3330/MURD | 23/10/2023 | 120 | TRIYA CONSTRUCTION | 105.54 | 0 | 30
555 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000243/2023-2024 | 1219/MURD/21 | 03/05/2023 | 0 | Resource Division | 104.53 | 0 | 0
556 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UMARPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000277/2023-2024 | 2606/MURD | 22/08/2023 | 21 | INDRAJIT MAZUMDAR | 27.66 | 0 | 70
557 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
558 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000282/2023-2024 | 1230/MURD/24 | 04/05/2023 | 0 | Resource Division | 132.07 | 0 | 0
559 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000379/2023-2024 | 495/MURD/02 | 15/02/2024 | 0 | Resource Division | 31.56 | 0 | 0
560 | Murshidabad Division | Berhampur M/E Division | CHARKA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Raghunathganj-I Block, Jangipur Sub Division of Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000199/2023-2024 | 2058/MURD | 27/07/2023 | 280 | DECON INDIA | 482.22 | 0 | 0
561 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHARKA Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj ¿ I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000272/2023-2024 | 2603/MURD | 22/08/2023 | 741 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 30
562 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
563 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000269/2023-2024 | 1230/MURD/13 | 04/05/2023 | 0 | Resource Division | 33.69 | 0 | 0
564 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
565 | Murshidabad Division | Kandi Sub-Division | BHARWAN (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000175/2023-2024 | 1991/MURD | 21/07/2023 | 365 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 389 | 0 | 25
566 | Murshidabad Division | Kandi Sub-Division | BHARWAN (Part-B) & adjoining mouzas PWSS to accommodate Of LDS, and FHTC, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000189/2023-2024 | 1990/MURD | 21/07/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 672.95 | 0 | 40
567 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
568 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000024/2023-2024 | 1210/MURD/36 | 02/05/2023 | 0 | Resource Division | 27.73 | 0 | 0
569 | Murshidabad Division | Kandi Sub-Division | KOGRAM & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000013/2023-2024 | 983/MURD | 10/04/2023 | 631 | HIRANMAY GHOSH | 599.93 | 0 | 50
570 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000242/2023-2024 | 1219/MURD/17 | 03/05/2023 | 0 | Resource Division | 14.53 | 0 | 0
571 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
572 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of PUNIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000692/2022-2023 | 164/MURD | 17/01/2023 | 1404 | M/S.TAPAS KUMAR CHAKRABORTY | 561.45 | 0 | 26
573 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000049/2023-2024 | 1067/MURD/4 | 18/04/2023 | 0 | Resource Division | 12.28 | 0 | 0
574 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000335/2023-2024 | 79/MURD/02 | 09/01/2024 | 0 | Resource Division | 17.24 | 0 | 0
575 | Murshidabad Division | Kandi Sub-Division | BHATPARA & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte.( Scheme ID -PH222362289S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000193/2023-2024 | 1989/MURD | 21/07/2023 | 365 | ASTRA | 789.69 | 0 | 0
576 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000033/2023-2024 | 1043/MURD/3 | 17/04/2023 | 0 | Resource Division | 208.28 | 0 | 0
577 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
578 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
579 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 6,Junior engineer-III | RTOR000096/2023-2024 | 1147/MURD/11 | 27/04/2023 | 0 | Resource Division | 19.36 | 0 | 0
580 | Murshidabad Division | Berhampur M/E Division | Preparation of D.p.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (DHUSARIPARA PWSS Scheme,Block- SAMSERGAUNGE to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/002048/2021-2022 | 3251/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.94 | 0 | 1
581 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000127/2023-2024 | 1167/MURD/27 | 28/04/2023 | 0 | Resource Division | 11.5 | 0 | 0
582 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Samserganj Block(Protapganj,Nimtita & Chachonda) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) |  |  | ORD/000070/2021-2022 | 127 /JSD | 27/05/2021 | 30 | IMAGIN COMMUNICATION | 1.19 | 0 | 0
583 | Murshidabad Division |  | Laying of Different dia UPVC pipeline at South Krishnanagar & Krishnanagar area in connection with Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) under command area of village of Ratanpur ( Village Code -313841) & Malancha (village code-313840) under Bhasaipaikar Zone-I,II &III Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samsherganj Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001723333) |  |  | ORD/000205/2022-2023 | 1381/MURD | 26/05/2022 | 60 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 41.19 | 0 | 0
584 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Ratanpur (Village code 313841) , Malancha (Village code 313840) ,under Bhasaipaikar Zone-I,II & III Ground Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723333) |  |  | ORD/001211/2021-2022 | 31/MURD | 06/01/2022 | 180 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 301.33 | 0 | 0
585 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Bhasaipaikar (Village code 313879) under Bhasaipaikar Zone-I,II & III Ground Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723333) |  |  | ORD/001231/2021-2022 | 16/MURD | 05/01/2022 | 180 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 235.91 | 0 | 0
586 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000035/2021-2022 | 540/8/MURD | 25/02/2022 | 0 | Resource Division | 67.97 | 0 | 0
587 | Murshidabad Division |  | ¿ Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village Srikrishnapur (Village Code 314737) under Aminabad Ground Water Based Water Supply Scheme for arsenic affected areas of Domkol Block in the District of Murshidabad¿. |  |  | ORD/000715/2020-2021 | 3227/MURD | 22/12/2020 | 60 | PAL TROCKNER (P) LTD. | 43.57 | 0 | 100
588 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Ja lSwapna under command area of village Paikmari (Village code 314672) under Dhulauri Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723245 in the District of Murshidabad. |  |  | ORD/000455/2020-2021 | 32/MURD | 05/01/2021 | 60 | MUNNA AGROTECH ENTERPRISE PRO: MIRAJUL ISLAM | 44.55 | 0 | 0
589 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Paikmari (Village code 314672) under Dhulauri Ground Water Based Water SupplyScheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723245 in the District of Murshidabad. |  |  | ORD/000592/2020-2021 | 32/MURD | 05/01/2021 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 44.55 | 7 | 0
590 | Murshidabad Division | Kandi Sub-Division | Laying of rising main of Pachhipara W/S scheme and protection of Head Work site at Kamalakantapur under Murshidabad Division, P.H.Engineering Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000207/2023-2024 | 2310/MURD | 01/08/2023 | 632 | APU CONSTRUCTION | 10.42 | 0 | 97
591 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Construction of 300 Cum capacity 20.00 mtr staging hight RCC elevated Over Head Reservoir on pile foundation (Ref:- DRG. NO. PC-I/OHR/7/2012 & D D-II/OHR/957/III/JAN 2020) including delivery, inlet and overflow pipe connection etc all complete of BAHARA Water Supply Scheme of Kandi Sub-Division under Murshidabad Division , P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000635/2020-2021 | 3053/MURD | 08/12/2020 | 270 | ROY ENTERPRISE | 78.02 | 0 | 100
592 | Murshidabad Division | Kandi Sub-Division | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001597/2021-2022 | 375/KSD | 19/01/2022 | 30 | ROY ENTERPRISE | 4.53 | 0 | 100
593 | Murshidabad Division | Kandi Sub-Division | Construction of boundary wall at Front side of Head work site including gate & R.B.T concertina fencing on wall top of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001600/2021-2022 | 378/KSD | 19/01/2022 | 45 | ROY ENTERPRISE | 4.29 | 0 | 100
594 | Murshidabad Division | Kandi Sub-Division | Continuatioin order for hiring of one no car use of the Executive Engineer Murshidabad Div PHE DTE. Vechle no 57-D - 9090. W/O - 223-HQ dated 26.05.2022 | ASSISTANT ENGINEER |  | VCH/000740/2022-2023 | 262-MSD/22-23 | 18/08/2022 | 0 | DULAL CHOWDHURY | 0.79 | 0 | 0
595 | Murshidabad Division | Kandi Sub-Division | Work Order for hiring of one no car use of the Superintending Engineer Murshidabad Circle PHE DTE. NIB 02/MC/PHE/20-21. W/O - 289-MC dated 01.04.2021 | ASSISTANT ENGINEER |  | VCH/000741/2022-2023 | 263-MSD/22-23 | 18/08/2022 | 0 | SOUMYADIP MISRA | 1.17 | 0 | 0
596 | Murshidabad Division | Kandi Sub-Division | Hiring of one no car use of the JSD PHE DTE. Note sheet approved date 07/01/2022. | ASSISTANT ENGINEER |  | VCH/000743/2022-2023 | 264-MSD/22-23 | 18/08/2022 | 0 | MADAN MOHAN SASMAL | 0.59 | 0 | 0
597 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00"x 4"00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I & II G.P, Doulatabad G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P & Niyallishpara G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000234/2021-2022 | 233/BSD | 14/07/2021 | 30 | S.S.INFRASTRUCTURE | 3.77 | 1.43 | 0
598 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00 x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, Rampur-I & II G.P Rangamati Chandpara G.P. Satui Chowrigachha G.P, Shaktipur G.P. & Chhaighari G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000235/2021-2022 | 142/BSD | 21/06/2021 | 30 | IMAGIN | 3.77 | 3.77 | 0
599 | Murshidabad Division | Kandi Sub-Division | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000409/2020-2021 | 534/MURD | 04/02/2021 | 60 | J.S. CONSTRUCTION | 44.75 | 44.37 | 1
600 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SHIBARAMBATI (Village Code 315980) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000744/2020-2021 | 3034/MURD | 07/12/2020 | 45 | SOUMYA KANTI SINHA | 18.57 | 0 | 1
601 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-III ) TNO- 764/20-21/EE | ASSISTANT ENGINEER |  | VCH/000009/2021-2022 |  | 12/04/2021 | 0 | SOUMYA KANTI SINHA | 17.54 | 0 | 0
602 | Murshidabad Division | Kandi Sub-Division | Safe Drinking Water Supply (Modified ATU) arrangement for Char Sarandajpur Primary School under ISD under Murshidabad Div PHE DTE. Tender no - 74 of 21-22 by AE / ISD | ASSISTANT ENGINEER |  | VCH/000697/2021-2022 | 92-MSD/2021-22 | 20/09/2021 | 0 | SARTHAK SK. | 4.76 | 0 | 0
603 | Murshidabad Division | Kandi Sub-Division | Fault defection of Repairing or replacing the damaged material Pannel board submerssible pump existing chlorinetaror of other direc existing chlonator and other direc Mahadebnagar Z-II W/S Scheme under JSD PHE DTE. TNO- 41 of 21-22 by AE/JSD | ASSISTANT ENGINEER |  | VCH/000698/2021-2022 | 104-MSD/2021-22 | 20/09/2021 | 0 | ARYA CONSTRUCTION | 3.81 | 0 | 0
604 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ramna Etbarnagar Basantapur (Village code 314691) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. |  |  | ORD/000948/2021-2022 | 3615/MURD | 22/11/2021 | 100 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 53.5 | 0 | 0
605 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAMNA ETBARNAGAR (Village Code 314691) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 106 of 21-22 by EE MURD |  |  | VCH/001503/2021-2022 | 410-MSD/21-22 | 22/03/2022 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 22.28 | 0 | 0
606 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI Z-II-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE-BHALKUNDI , CODE- 315091, TNO- 43/2020-21/SEMC |  |  | VCH/002024/2020-2021 | 512/W | 30/03/2021 | 0 | M/S BHUBAN DAS | 28.84 | 0 | 0
607 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- KOLAN RADHAKANTAPUR , CODE-314523, TNO- 50/2020-21/SE-MC |  |  | VCH/002025/2020-2021 | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 33.58 | 0 | 0
608 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Bewa (P)(Village code 313794), of Bewa Zone-II Ground Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723418) |  |  | ORD/000223/2022-2023 | 1458/MURD | 02/06/2022 | 120 | KISMAT ARA BEGUM | 104.36 | 0 | 0
609 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
610 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
611 | Murshidabad Division | Kandi Sub-Division | Laying of parallel UPVC pipeline from Masadda Shib Mandir to Masadda Durga Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000007/2022-2023 | 09 / KSD | 06/04/2022 | 30 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 4.82 | 0 | 1
612 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village RANIARA MASADDA (Village Code 315905) under Burwan Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000156/2020-2021 | 3219/MURD | 18/12/2020 | 60 | DEBASISH SARKAR | 12.49 | 0 | 0
613 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000260/2020-2021 | 2391/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 0 | 1
614 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000416/2021-2022 | 216/KSD | 11/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0
615 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000462/2021-2022 | 231/KSD | 27/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 4.17 | 0 | 0
616 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000463/2021-2022 | 232/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
617 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SAHORA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000475/2021-2022 | 243/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0
618 | Murshidabad Division | Kandi Sub-Division | Holding Awarness Programme / Campaigning programms at Burwan-I & II G.P, Sahora G.P, Panchthupi G.P and Sabalpur G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-C). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000555/2021-2022 | 251/KSD | 31/08/2021 | 30 | IMAGIN COMMUNICATION | 3.99 | 0 | 0
619 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000629/2020-2021 | 2391/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 0 | 1
620 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniara Masadda (VILL CODE-315905) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) tNO- 791/20-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000266/2021-2022 | 41-MSD / 21-22 | 24/08/2021 | 0 | DEBASISH SARKAR | 9.94 | 0 | 0
621 | Murshidabad Division | Kandi Sub-Division | Laying of parallel UPVC pipeline from Masadda Bus Stand to Masadda Shib Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000536/2022-2023 | 194-MSD/22-23 | 30/06/2022 | 0 | MAA CONSTRUCTION (NAJMUL HAQUE) | 4.58 | 0 | 0
622 | Murshidabad Division | Kandi Sub-Division | Hiring of 1 (One) no Diesel Scorpio car for fJangipur Sub Div. under MSD PHE DTE. Period 01.04.2022 to 10.06.2022 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000554/2022-2023 | 200-MSD/2022-23 | 06/07/2022 | 0 | MADAN MOHAN SASMAL | 0.41 | 0 | 0
623 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001297/2021-2022 |  | 17/02/2022 | 0 | DAS CONSTRACTION | 5.48 | 0 | 0
624 | Murshidabad Division | Kandi Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric. Tender no - 850 of 20-21 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001454/2021-2022 | 343-MSD/21-22 | 05/03/2022 | 0 | DAS CONSTRACTION (MUNNA DAS) | 5.48 | 0 | 0
625 | Murshidabad Division |  | Laying of HDPE (Materials grade PE-100 & Pressure Rating: PN6) pipe line & allied works of Retrofitting of Functional Household Tap Connections (FHTC) at village Bhalkundi (Village code-315091) Bhalkundi water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000025/2022-2023 | 29/KSD | 08/04/2022 | 30 | TIRUPATI CONSTRUCTION | 4.59 | 0 | 1
626 | Murshidabad Division |  | Laying of HDPE (Materials grade PE -100 & Pressure Rating : PN 6) Pipe Line due to widening of PWD Roads & construction of drain at village Bhalkundi (Village Code-315091) under Bhalkundi Water Supply Scheme of Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/000227/2022-2023 | 98 / KSD | 06/06/2022 | 30 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 4.83 | 0 | 1
627 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Joypur (Village code 315086) under Bhalkundi (Zone-I) Ground Water Based water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-08) |  |  | ORD/000306/2020-2021 | 165/MURD | 15/01/2021 | 180 | SOUMYADIP MISRA | 56.13 | 0 | 1
628 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JOYPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000461/2021-2022 | 230/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
629 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village TELSUNDI (Village Code 315121) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. |  |  | ORD/000516/2020-2021 | 3020/MURD | 04/12/2020 | 45 | M/S GUNGUN CONSTRUCTION | 19.58 | 0 | 1
630 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. |  |  | ORD/000526/2020-2021 | 3026/MURD | 04/12/2020 | 45 | SOM CONSTRUCTION AGENCY | 15.45 | 0 | 0
631 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhalkundi(Village code 315091) under Bhalkundi (Zone-II)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-09) |  |  | ORD/000553/2020-2021 | 3045/MURD | 07/12/2020 | 180 | M/S BHUBAN DAS | 47.51 | 0 | 1
632 | Murshidabad Division |  | Balance FHTC works of extension of distribution pipeline and restoration works of damage pipeline at Bhalkundi (Zone-II) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad |  |  | ORD/001137/2021-2022 | 318/KSD | 16/11/2021 | 30 | M/S BHUBAN DAS | 4.77 | 0 | 1
633 | Murshidabad Division |  | Balance work of distribution pipeline at Shri Krishnapur Village under Bhalkundi (Zone-I) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. |  |  | ORD/001195/2021-2022 | 337/KSD | 30/11/2021 | 30 | SOUMYADIP MISRA | 4.8 | 0 | 1
634 | Murshidabad Division |  | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of PALSANDA ( Village Code -315119) under Bhalkundi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001808/2021-2022 | 818/MURD | 25/03/2022 | 30 | M/S. GOURI ENTERPRISE | 9.52 | 0 | 1
635 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000043/2021-2022 | 541/3/MURD | 25/02/2022 | 0 | Resource Division | 2.7 | 0 | 0
636 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village Palsanda (315119) of Bhalkundi under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block of Murshidabad District . Tender no 540 of 20-21 by EE |  |  | VCH/000596/2021-2022 | 143-MSD/21-22 | 11/10/2021 | 0 | M/S. GOURI ENTERPRISE | 32.46 | 0 | 0
637 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JALSWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. Tender no - 694 of 20-21 by EE MURD |  |  | VCH/001445/2021-2022 | 334-MSD/21-22 | 05/03/2022 | 0 | SOM CONSTRUCTION AGENCY | 3.38 | 0 | 0
638 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connection (FHTC) of 69 nos left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Syampur (Village code 314658) under Beniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.(Scheme ID- 0001723470) |  |  | ORD/000019/2022-2023 | 878/MURD | 01/04/2022 | 30 | RAJU ENTERPRISE | 18.78 | 0 | 0
639 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Syampur (314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II), TNO- 737/2020-21/EE |  |  | VCH/000586/2021-2022 | 130-MSD/21-22 | 11/10/2021 | 0 | RAJU ENTERPRISE | 4.33 | 0 | 0
640 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SARBANGAPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PARESNATHPUR , CODE-315529, TNO- 604/2020-21/EE |  |  | VCH/002015/2020-2021 | 512/W | 30/03/2021 | 0 | RATAN DUTTA | 25.78 | 0 | 0
641 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
642 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
643 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000123/2023-2024 | 1773/MURD | 06/07/2023 | 695 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 80
644 | Murshidabad Division | Berhampur M/E Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 100
645 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
646 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 243/5 & 243/6) on railway land of mouza-Jigari kulgachi & Connecting with existing 150 mm dia Rising main line of Mahadevnagar Zone - I ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000424/2021-2022 | 2478/MURD | 16/08/2021 | 60 | DECON INDIA | 26.25 | 0 | 100
647 | Murshidabad Division | Berhampur M/E Division | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0
648 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Rejinagar Zone-I PWSS of accommodate with Repairing of Switch Room, Repairing of Boundary Wall, 400 CUM OHR, in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [Part B] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000527/2023-2024 | 3118/MURD | 05/10/2023 | 180 | JIT CONSTRUCTION | 155.69 | 0 | 0
649 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 279 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-I PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000584/2023-2024 | 3334/MURD | 23/10/2023 | 520 | AJAY MONDAL | 201.09 | 0 | 70
650 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
651 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0
652 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000020/2024-2025 | 1811/MURD/19 | 20/06/2024 | 0 | Resource Division | 6.64 | 0 | 0
653 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000135/2023-2024 | 1167/MURD/51 | 28/04/2023 | 0 | Resource Division | 127.23 | 0 | 0
654 | Murshidabad Division | Kandi Sub-Division | Repair work of concrete road between node point 52-53 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000158/2024-2025 | 149/KSD | 28/10/2024 | 30 | M/S BHUBAN DAS | 0.96 | 0 | 0
655 | Murshidabad Division | Kandi Sub-Division | Repair work of concrete road between node point 28-41-45-50 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000159/2024-2025 | 150/KSD | 28/10/2024 | 30 | M/S BHUBAN DAS | 0.97 | 0 | 0
656 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000260/2023-2024 | 1230/MURD/08 | 04/05/2023 | 0 | Resource Division | 19.32 | 0 | 0
657 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
658 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Seikhpara PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing & Construction of Switch Room, Repairing of Boundary Wall, Repairing of 600 CUM OHR, Construction of 400 CUM OHR in Raninagar II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000610/2023-2024 | 3373/MURD | 31/10/2023 | 609 | M/S.TAPAS KUMAR CHAKRABORTY | 1378.3 | 0 | 20
659 | Murshidabad Division | Berhampur M/E Division | Refilling of sand layers, Activated Alumina & existing gravel after washing along with allied works of AIRP at Saikhpara Area (Capacity 100 Cum/hr.) & Muradpur Jalangi Z-I (Capacity 54.00 Cum/hr.) Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000842/2023-2024 | 820/MURD | 15/03/2024 | 244 | M/S. S. DAS AND ENTERPRISE | 70.68 | 0 | 40
660 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000179/2023-2024 | 1180/MURD/23 | 29/04/2023 | 0 | Resource Division | 256.66 | 0 | 0
661 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based SIMULIA & JAULIA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000587/2023-2024 | 3322/MURD | 22/10/2023 | 649 | VISION ENTERPRISE | 355.14 | 0 | 10
662 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Simulia Jaulia Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000709/2023-2024 | 3807/MURD | 12/12/2023 | 629 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 100
663 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
664 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional HouseHold Connection of different existing PWSS (SIMULIA & JAMULIA PWSS Scheme, Block- BHARATPUR-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000822/2021-2022 | 3261/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.78 | 0 | 1
665 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000003/2023-2024 | 1004/MURD/1 | 11/04/2023 | 0 | Resource Division | 13.32 | 0 | 0
666 | Murshidabad Division | Berhampur Sub-Division | Allied work of connection of Rising and Distribution main with supply of materials and construction of sluice valve chamber at Char Mahula water supply scheme under Berhampore sub division, P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000054/2024-2025 | 1985/MURD | 08/07/2024 | 60 | SUPIA CONSTRUCTION | 4.47 | 0 | 85
667 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
668 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
669 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000017/2024-2025 | 1811/MURD/16 | 20/06/2024 | 0 | Resource Division | 20.22 | 0 | 0
670 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000152/2023-2024 | 1180/MURD/02 | 29/04/2023 | 0 | Resource Division | 18.43 | 0 | 0
671 | Murshidabad Division | Kandi Sub-Division | Laying of Rising Main , Distribution System, FHTC, OHR Repairing (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-I PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000439/2023-2024 | 2887/MURD | 12/09/2023 | 150 | BURIMA CONSTRUCTION | 250.71 | 0 | 20
672 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
673 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000007/2023-2024 | 1004/MURD/2 | 11/04/2023 | 0 | Resource Division | 49.59 | 0 | 0
674 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-III Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000051/2025-2026 | 1226/MURD | 28/05/2025 | 60 | INDRAJIT DUBEY | 19.62 | 0 | 0
675 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
676 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
677 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000091/2023-2024 | 1147/MURD/6 | 27/04/2023 | 0 | Resource Division | 0.55 | 0 | 0
678 | Murshidabad Division | Berhampur M/E Division | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 0 | 56
679 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 1
680 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000255/2023-2024 | 1219/MURD/40 | 03/05/2023 | 0 | Resource Division | 69.3 | 0 | 0
681 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000388/2023-2024 | 526/MURD/05 | 19/02/2024 | 0 | Resource Division | 14.88 | 0 | 0
682 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 0 | 100
683 | Murshidabad Division | Berhampur M/E Division | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000440/2023-2024 | 2888/MURD | 12/09/2023 | 750 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 75
684 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SANTOSHPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000658/2022-2023 | 3415/MURD | 22/12/2022 | 45 | HARUN ALL RASHID & BROTHERS | 16.64 | 0 | 80
685 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-B), Construction of Boundary Wall & Pump house for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for Laying Distribution System: Rs.1,54,12,147.00 & (ii) Amount for Boundary Wall & Pump House: Rs. 41,19,886.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000727/2022-2023 | 176/MURD | 18/01/2023 | 1018 | MOTI RAHAMAN | 195.28 | 0 | 35
686 | Murshidabad Division | Kandi Sub-Division | Formal work order for construction of 250 Cum OHR , Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for LDS , R.Main & FHTC: Rs.2,44,40,742.00 & (ii) Amount for OHR: Rs.1,03,92,477.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000764/2022-2023 | 480/MURD | 20/02/2023 | 862 | S.&P. ENTERPRISE | 348.26 | 0 | 15
687 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000019/2023-2024 | 1210/MURD/32 | 02/05/2023 | 0 | Resource Division | 23.42 | 0 | 0
688 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000317/2023-2024 | 1936/MURD/5 | 19/07/2023 | 0 | Resource Division | 23.42 | 0 | 0
689 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000344/2023-2024 | 112/MURD/01 | 11/01/2024 | 0 | Resource Division | 13.66 | 0 | 0
690 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 0 | 100
691 | Murshidabad Division | Jangipur Sub-Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
692 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | RTOR000211/2023-2024 | 1210/MURD/26 | 02/05/2023 | 0 | Resource Division | 149.38 | 0 | 0
693 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000568/2023-2024 | 3288/MURD | 19/10/2023 | 180 | BIJAY CHOWDHURY | 861.6 | 0 | 35
694 | Murshidabad Division | Berhampur M/E Division | Replacing of Filter media of Existing AIRP (Modified Sujapur Sadhipur Model ) of (Capacity 120 Cum/hr.) at Kankramari Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division, PHEngineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000823/2023-2024 | 744/MURD | 12/03/2024 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 42.03 | 0 | 100
695 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
696 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000246/2023-2024 | 1219/MURD/29 | 03/05/2023 | 0 | Resource Division | 53.62 | 0 | 0
697 | Murshidabad Division | Kandi Sub-Division | Formal Work Order ForConstruction of 100 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JUGASWARA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362271S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,38,33,206.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,13,02,060.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000757/2022-2023 | 416/MURD | 15/02/2023 | 730 | SHYAMAL KUMAR SAHA | 251.3 | 0 | 90
698 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JUGASWARA PWSS at Head Work Site & 2nd Tube Well Site in Burwan Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000770/2022-2023 | 485/MURD | 20/02/2023 | 45 | NADIA TUBEWELLS | 16.81 | 0 | 100
699 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000008/2023-2024 | 1210/MURD/37 | 02/05/2023 | 0 | Resource Division | 1.42 | 0 | 0
700 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000346/2023-2024 | 112/MURD/03 | 11/01/2024 | 0 | Resource Division | 4.88 | 0 | 0
701 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of EROALI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362274S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000711/2022-2023 | 90/MURD | 11/01/2023 | 841 | M/S. S. DAS AND ENTERPRISE | 833.44 | 0 | 38
702 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
703 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000036/2023-2024 | 1004/MURD/11 | 17/04/2023 | 0 | Resource Division | 47.05 | 0 | 0
704 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000369/2023-2024 | MURD/439/1 | 08/02/2024 | 0 | Resource Division | 27.28 | 0 | 0
705 | Murshidabad Division | Berhampur M/E Division | Construction 400 Cum OHR for Augmentation of Sekendra Ground water based Piped water supply scheme in Raghunathganj -II Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000002/2023-2024 | 944/MURD | 05/04/2023 | 365 | PRODEEP KUMAR GHOSH | 132.12 | 0 | 50
706 | Murshidabad Division | Berhampur M/E Division | Construction of Boundary wall of 60 m length and pumphouse (5.9 m x 4.825 m) at site no 4 at Sekendra Pwss in Raghunathganj-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000069/2025-2026 | 1246/MURD | 29/05/2025 | 60 | KALACHAND DAS | 19.25 | 0 | 0
707 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000110/2024-2025 | 2211/MURD | 02/08/2024 | 30 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0
708 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000758/2022-2023 | 445/MURD | 17/02/2023 | 846 | NAYLA CONSTRUCTION | 255.21 | 0 | 90
709 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000372/2023-2024 | 495/MURD/09 | 15/02/2024 | 0 | Resource Division | 33.66 | 0 | 0
710 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744, 314745, 314746, 314747, 314753, 314754, 314755, 314756 of Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000128/2022-2023 | 1211/MURD | 10/05/2022 | 60 | SOURAV DEY | 32.44 | 0 | 0
711 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Melanpur (Village code 314755) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000721/2020-2021 | 532/MURD | 04/02/2021 | 60 | BHOWMIK CONSTRUCTION | 3.72 | 0 | 0
712 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000137/2022-2023 | 1239/MURD | 11/05/2022 | 1056 | MAMATA USHA ENTERPRISE | 33.22 | 0 | 100
713 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilpachakopra ( Village Code -314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184055). | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000476/2020-2021 | 575/MURD | 09/02/2021 | 60 | NOVELTY CONSTRUCTION | 29.68 | 0 | 0
714 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone-II / Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000467/2022-2023 | 2372/MURD | 16/08/2022 | 958 | MAMATA USHA ENTERPRISE | 670.9 | 0 | 100
715 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-A Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000585/2022-2023 | 3054/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 1
716 | Murshidabad Division | Berhampur M/E Division | Allied work of OHR & HDPE Pipeline for Augmentation of Jalangi Zone-II Part-A ground water based PWSS to accommodate FHTC in Jalangi Block in the district of Murshidabad under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000761/2023-2024 | 183/MURD | 18/01/2024 | 90 | MAMATA USHA ENTERPRISE | 123.49 | 0 | 90
717 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000029/2024-2025 | MURD/2481/02 | 04/09/2024 | 0 | Resource Division | 24.04 | 0 | 0
718 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000035/2022-2023 | 2780/D/MURD | 01/10/2022 | 0 | Resource Division | 21.86 | 0 | 0
719 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000057/2022-2023 | 3294/MURD | 12/12/2022 | 0 | Resource Division | 21.86 | 0 | 0
720 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000157/2023-2024 | 1180/MURD/6 | 29/04/2023 | 0 | Resource Division | 143.36 | 0 | 0
721 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000332/2023-2024 | 3849/MURD/1 | 14/12/2023 | 0 | Resource Division | 1.98 | 0 | 0
722 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000351/2023-2024 | 305/MURD | 29/01/2024 | 0 | Resource Division | 22.47 | 0 | 0
723 | Murshidabad Division |  | Supplying and Laying of 160mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. |  |  | ORD/000527/2020-2021 | 121/BSD | 19/02/2021 | 15 | CHATTERJEE ENTERPRISE | 4.83 | 0 | 0
724 | Murshidabad Division |  | Supplying and Laying of 90mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. (Part-II) |  |  | ORD/000528/2020-2021 | 122/BSD | 19/02/2021 | 15 | DAS CONSTRACTION | 4.83 | 0 | 0
725 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. |  |  | ORD/000529/2020-2021 | 123/BSD | 19/02/2021 | 15 | NATIONAL ENTERPRISE | 4.83 | 0 | 0
726 | Murshidabad Division |  | Supplying and Laying of 90mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. (Part-I) |  |  | ORD/000530/2020-2021 | 124/BSD | 19/02/2021 | 15 | LONDON WHARFIES | 4.85 | 0 | 0
727 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dudhsar (Village code 315521) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723279 in the District of Murshidabad. |  |  | ORD/000615/2020-2021 | 34/MURD | 05/01/2021 | 60 | CHATTERJEE ENTERPRISE | 19.26 | 0 | 0
728 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1173 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Santoshpur ( Village Code -314329) & Chandanbati ( Village code-314330) under Sagardighi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000641/2023-2024 | 3438/MURD | 03/11/2023 | 45 | MAA SANKARI ENTERPRISE | 36.58 | 0 | 0
729 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village ACHHOAN (Village Code 315979) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. |  |  | ORD/000773/2020-2021 | 3036/MURD | 07/12/2020 | 45 | LAXMI CONSTRUCTION | 7.78 | 0 | 0
730 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dighirpahar (Village code 314794) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-08) |  |  | ORD/000350/2021-2022 | 2503/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 70.56 | 0 | 1
731 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Islampur(CT) (Village code 314805) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. |  |  | ORD/000359/2021-2022 | 2506/MURD | 17/08/2021 | 1629 | NAYLA CONSTRUCTION | 109.99 | 0 | 40
732 | Murshidabad Division |  | Restoration work of distribution pipeline by using UPVC pipeline from Nashipur Graveyard to Kathal bariya Jumma Masjid and new construction of street stand post under Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. |  |  | ORD/002075/2021-2022 | 467/ISD | 03/09/2021 | 30 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.8 | 0 | 0
733 | Murshidabad Division |  | Extension of pipeline at uncovered habitation of Nashipur Biswaspara from Enamul Biswas house to Khalek Biswas house and Rafikul Sk house to Mokbul Mondal house at Nashipur Panthipara under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. |  |  | ORD/002102/2021-2022 | 469/ISD | 03/09/2021 | 30 | S. DUTTA | 4.7 | 0 | 0
734 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BALIA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000467/2021-2022 | 235/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
735 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Bele Habitation under Bele Village(JL NO-152) of Bele Water Supply Scheme(Ground Water Based) under Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000547/2020-2021 | 2526/MURD | 30/09/2020 | 45 | R.M. BHATTA | 39.32 | 0.99 | 0
736 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BANPUR (Village Code.315191) under Bele Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000551/2020-2021 | 3030/MURD | 07/12/2020 | 45 | M/S. SINHA & SONS | 28.3 | 0 | 0
737 | Murshidabad Division | Kandi Sub-Division | Balance works of laying of UPVC distribution pipeline at Chandra Singha Bati village in connection of FHTC work of Bele Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001132/2021-2022 | 319/KSD | 16/11/2021 | 30 | BHOLEBABA CONSTRUCTION CO | 4.84 | 0 | 0
738 | Murshidabad Division | Kandi Sub-Division | Balance work for extension of distribution pipeline from Bainpara, Kandapara, Banur & Seikhpara area under Bele Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001187/2021-2022 | 321/KSD | 16/11/2021 | 30 | SUKUMAR ROY | 4.83 | 0 | 0
739 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/001229/2021-2022 | 213/KSD | 11/08/2021 | 30 | IMAGIN COMMUNICATION | 3.25 | 0 | 0
740 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village CHANDBATI (Village Code- 315210) under BELE Water Supply Scheme of KHORGARM BLOCK Murshidabad District under Murshidabad Division, PHE Dte. TNO- 54/20-21/EE | ASSISTANT ENGINEER |  | VCH/000227/2021-2022 | 18-MSD / 21-22 | 10/08/2021 | 0 | M/S . SUKUMAR SINHA | 23.36 | 0 | 0
741 | Murshidabad Division | Kandi Sub-Division | BALALNCE WORK OF LAYING OF UPVC PIPE LIN E AT CHANDRASINGHA BATI IN CONNECTION OF FHTC WORK UNDER BELE WSS, TNO- 36/21-22/AEKSD | ASSISTANT ENGINEER |  | VCH/001440/2021-2022 | 340 -MSD/21-22 | 03/03/2022 | 0 | BHOLEBABA CONSTRUCTION CO | 4.84 | 0 | 0
742 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BANPUR (Village Code 315191) under BELE Ground Water Based Water Supply Scheme for arsenic affected areas of KHARGRAM Block in the District of Murshidabad. Tender no - 831 of 20-21 by EE MURD | ASSISTANT ENGINEER |  | VCH/001463/2021-2022 | 364-MSD/21-22 | 11/03/2022 | 0 | M/S. SINHA & SONS | 27.15 | 0 | 0
743 | Murshidabad Division | Kandi Sub-Division | Balance work for extention og distibution pipeline form Bainpara, Kandapara, burwan & Seikhpara area under Bele W/S Scheme under Kandi Sub Div. PHE DTE. Tender no - 41 of 21-22 by AE KSD | ASSISTANT ENGINEER |  | VCH/001478/2021-2022 | 386-MSD/21-22 | 23/03/2022 | 0 | SUKUMAR ROY | 4.82 | 0 | 0
744 | Murshidabad Division |  | Connection of Rising Main at Pump House No. II & Newly Sunk tubewell of Pump House No. I and other allied works under Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad |  |  | ORD/000286/2022-2023 | 275/ISD | 27/06/2022 | 30 | PARTHA PRATIM DAS | 3.74 | 0 | 0
745 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Harharia Chak (Village code 314806 ) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-06) |  |  | ORD/000434/2021-2022 | 2599/MURD | 25/08/2021 | 1621 | SHYAMAL KUMAR SAHA | 101.35 | 0 | 40
746 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District (Part-IV) |  |  | VCH/001290/2021-2022 |  | 17/02/2022 | 0 | M/S. UNIQUE BUILDERS | 74.29 | 0 | 0
747 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
748 | Murshidabad Division | Kandi Sub-Division | PULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000097/2023-2024 | 1698/MURD | 28/06/2023 | 972 | ESCON INDIA | 134.38 | 0 | 10
749 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000078/2023-2024 | 1129/MURD/1 | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
750 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for LOKNATHPUR ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000037/2025-2026 | 1130/MURD | 16/05/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 23.01 | 0 | 0
751 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Loknathpur zone-II PWSS to accommodate FHTC of 600 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 170 m and Soil Investigation & 200 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000538/2023-2024 | 3147/MURD | 09/10/2023 | 220 | M H SUPPLIERS | 210.2 | 0 | 8
752 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LOKENATHPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000711/2023-2024 | 3812/MURD | 12/12/2023 | 497 | TRIYA CONSTRUCTION | 27.6 | 0 | 100
753 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
754 | Murshidabad Division | Berhampur Sub-Division | Laying Distribution System For Augmentation of Loknathpur Zone-II (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000868/2022-2023 | 847/MURD | 24/03/2023 | 950 | SOMA CONSTRUCTION | 154.95 | 0 | 40
755 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0
756 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000024/2024-2025 | 1811/MURD/23 | 20/06/2024 | 0 | Resource Division | 7.29 | 0 | 0
757 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000181/2023-2024 | 1180/MURD/29 | 29/04/2023 | 0 | Resource Division | 45.89 | 0 | 0
758 | Murshidabad Division | Kandi Sub-Division | JAGANNATHPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000659/2023-2024 | 3528/MURD | 10/11/2023 | 507 | SOUMYADIP MISRA | 367.89 | 0 | 25
759 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagannathpur and Burwan Zone- II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Burwan Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000724/2023-2024 | 3925/MURD | 21/12/2023 | 395 | NADIA TUBEWELLS | 18.43 | 0 | 100
760 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000077/2023-2024 | 1075/MURD/19 | 19/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
761 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone-II & Giria Zone - I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000122/2023-2024 | 1767/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 23.58 | 0 | 100
762 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
763 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
764 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000557/2023-2024 | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0
765 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000177/2023-2024 | 1180/MURD/24 | 29/04/2023 | 0 | Resource Division | 62.68 | 0 | 0
766 | Murshidabad Division | Lalbag Sub-Division | Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. For 176 Days i.e. form 08.04.2025 to 30.09.2025. (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order). (Vehicle No.WB58AX9595) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000005/2025-2026 | 133/LSD | 07/04/2025 | 176 | BARI ENTERPRISE | 0.86 | 0 | 0
767 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 0 | 100
768 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
769 | Murshidabad Division | Lalbag Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-I Water Supply Scheme at Head work Site site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000698/2023-2024 | 3783/MURD | 11/12/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 11.77 | 0 | 0
770 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000125/2023-2024 | 1167/MURD/16 | 28/04/2023 | 0 | Resource Division | 18.84 | 0 | 0
771 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHASIPAIKAR ZONE-IIB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000555/2023-2024 | 3194/MURD | 12/10/2023 | 21 | TAPAN DAS | 23.72 | 0 | 50
772 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
773 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000121/2023-2024 | 1167/MURD/26 | 28/04/2023 | 0 | Resource Division | 61.81 | 0 | 0
774 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Nagar Zone II PWSS of accommodate FHTC( 1909 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall, 300 CUM OHR in Khargram Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000574/2023-2024 | 3299/MURD | 20/10/2023 | 773 | CREATIVE CONSTRUCTION | 394.26 | 0 | 10
775 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nagar Zone- II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000717/2023-2024 | 3834/MURD | 14/12/2023 | 21 | MAMATA USHA ENTERPRISE | 23.59 | 0 | 50
776 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000016/2023-2024 | 1004/MURD/6 | 11/04/2023 | 0 | Resource Division | 24.92 | 0 | 0
777 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000114/2023-2024 | 1167/MURD/15 | 28/04/2023 | 0 | Resource Division | 20.22 | 0 | 0
778 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000388/2023-2024 | 2778/MURD | 01/09/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.21 | 0 | 100
779 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0
780 | Murshidabad Division | Kandi Sub-Division | Augmentation of DAKSHIN KHANDA (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000537/2023-2024 | 3146/MURD | 09/10/2023 | 815 | DHIRENDRANATH MONDAL | 457.09 | 0 | 10
781 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dakshin Kanda Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000697/2023-2024 | 3782/MURD | 11/12/2023 | 630 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 100
782 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
783 | Murshidabad Division | Berhampur M/E Division | Balance work of Laying Distribution System , Road Restoration and other ancillary works of Tejsinghapur Water Supply Scheme within Raninagar-II Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000073/2025-2026 | 1259/MURD | 30/05/2025 | 60 | DAS TRADING CO. | 64.29 | 0 | 0
784 | Murshidabad Division | Berhampur M/E Division | Augmentation of TEJSINGHAPUR PWSS under Jal Jivan Mission of RANINAGAR - II Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000078/2023-2024 | 1383/MURD | 22/05/2023 | 955 | PRADIP KUMAR DAS | 294.57 | 0 | 86
785 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000104/2023-2024 | 1746/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
786 | Murshidabad Division | Berhampur M/E Division | Augmentation of TEJSINGHAPUR PWSS under Jal Jeevan Mission of RANINAGAR - II Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000164/2023-2024 | 1933/MURD | 18/07/2023 | 898 | VOICE CONSTRUCTION | 293.06 | 0 | 35
787 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Tajsinghapur PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000832/2021-2022 | 3265/MURD | 05/10/2021 | 60 | RADIANT | 4.74 | 0 | 1
788 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000150/2023-2024 | 1167/MURD/39 | 28/04/2023 | 0 | Resource Division | 79.35 | 0 | 0
789 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Aminabad (Zone-II) & Katakobra Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000121/2023-2024 | 1762/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 35.37 | 0 | 66
790 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System for Augmentation of Katakopra Zone -I & II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkol Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000172/2024-2025 | 2994/MURD | 13/11/2024 | 450 | M/S. BIMALENDU BOSE | 389.64 | 0 | 0
791 | Murshidabad Division | Berhampur M/E Division | Augmentation KATAKOPRA (Zone -I) under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000474/2023-2024 | 3031/MURD | 27/09/2023 | 600 | M/S HANNAN KHAN CONSTRUCTION | 300.03 | 0 | 15
792 | Murshidabad Division | Berhampur M/E Division | Augmentation of KATAKOPRA (Zone-I) PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE Dte. (Part-A) | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000479/2023-2024 | 3050/MURD | 29/09/2023 | 825 | M/S. BIMALENDU BOSE | 466.19 | 0 | 90
793 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000868/2023-2024 | 832/MURD | 15/03/2024 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 100
794 | Murshidabad Division | Berhampur M/E Division | Inter connection with Tubewell and rising main etc. at Head work sites of Katakopra Water Supply scheme (Katakopra Z-I & Z-II both) and allied works under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001237/2021-2022 | 43/ISD | 28/01/2022 | 60 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 4.33 | 0 | 100
795 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000136/2023-2024 | 1167/MURD/33 | 28/04/2023 | 0 | Resource Division | 22 | 0 | 0
796 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000140/2023-2024 | 1167/MURD/35 | 28/04/2023 | 0 | Resource Division | 198.12 | 0 | 0
797 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE -IIA) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000501/2023-2024 | 3088/MURD | 03/10/2023 | 1114 | SOFIQUL ISLAM | 423.46 | 0 | 50
798 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
799 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
800 | Murshidabad Division | Berhampur M/E Division | Allied work in connection with Augmentation & Rejuvenation of Birendranagar (Zone-II) Pipe water supply scheme, Block- Raghunathganj-II, District-Murshidabad, Under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000027/2024-2025 | 1842/MURD | 25/06/2024 | 30 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 17.49 | 0 | 100
801 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
802 | Murshidabad Division | Berhampur M/E Division | Renovation of Existing AIRP (Capacity 15 Cu.M/hr) for changing of filter media of 1 no Polishing Unit (2.50 m dia x 1.5 m HOS) & 1 no Primary Unit (2.50 m dia x 2.00 m HOS) and painting all vessel, pipes etc. all complete at Birendranagar (Zone-II) W/S Scheme under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000810/2023-2024 | 618/MURD | 28/02/2024 | 240 | S. DUTTA | 16.94 | 0 | 100
803 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System with FHTC to 560nos household, Rising Main, OHR Repair of 90 cum capacity, Extension of Boundary Wall &Two Nos. of Pump House Repair for Augmentation of Birendranagar (Zone-II) Pipe water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte (i)Amount for Construction Part: 15,60,995.00/ (ii)Amount for Pipeline Part: 57,32,731.00/- (Attached as Annexure -V) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000826/2022-2023 | 656/MURD | 06/03/2023 | 900 | HARUN ALL RASHID & BROTHERS | 72.21 | 0 | 40
804 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000189/2023-2024 | 1210/MURD/19 | 02/05/2023 | 0 | Resource Division | 2.25 | 0 | 0
805 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
806 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000369/2023-2024 | 2721/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
807 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
808 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
809 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
810 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000094/2023-2024 | 1147/MURD/9 | 27/04/2023 | 0 | Resource Division | 34.37 | 0 | 0
811 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
812 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000370/2023-2024 | 2722/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
813 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
814 | Murshidabad Division | Berhampur M/E Division | Formal work order for GHORSALA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of raghunathganj-I Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000855/2022-2023 | 794/MURD | 21/03/2023 | 833 | DHIRENDRANATH MONDAL | 431.52 | 0 | 25
815 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000280/2023-2024 | 1230/MURD/22 | 04/05/2023 | 0 | Resource Division | 30.14 | 0 | 0
816 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000378/2023-2024 | 495/MURD/03 | 15/02/2024 | 0 | Resource Division | 9.2 | 0 | 0
817 | Murshidabad Division | Berhampur M/E Division | COST OF RESTORATION OF ROAD CONNECTTED TO NH-34 DHULIAN PAKUR ROAD AT CH. 4.275 TO 4.600. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | BILL/01019/2024-2025 | 369-MSD/2024-20 | 12/09/2024 | 0 | MURSHIDABAD HIGHWAY DIVISION-1 | 13.3 | 0 | 0
818 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
819 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well,120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HILORA - II & KOHETPUR Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000016/2024-2025 | 1755/MURD | 13/06/2024 | 464 | R.K. DRILLING SERVICES | 11.79 | 0 | 100
820 | Murshidabad Division | Berhampur M/E Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 100
821 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KOHETPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000275/2023-2024 | 2605/MURD | 22/08/2023 | 741 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 50
822 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
823 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
824 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000668/2022-2023 | 3409/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 0
825 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of KOHETPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | ORD/000812/2022-2023 | 670/MURD | 09/03/2023 | 762 | PRAFULLYA CONSTRUCTION | 379.82 | 0 | 22
826 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | RTOR000286/2023-2024 | 1230/MURD/29 | 04/05/2023 | 0 | Resource Division | 22.56 | 0 | 0
827 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior Engineer 3,Junior engineer-II | RTOR000373/2023-2024 | 495/MURD/08 | 15/02/2024 | 0 | Resource Division | 8.37 | 0 | 0
828 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
829 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
830 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
831 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000089/2023-2024 | 1147/MURD/3 | 27/04/2023 | 0 | Resource Division | 128.8 | 0 | 0
832 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Aminabad (Zone-II) & Katakobra Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000121/2023-2024 | 1762/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 35.37 | 0 | 66
833 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 0 | 100
834 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Aminabad Zone-II Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000846/2022-2023 | 773/MURD | 17/03/2023 | 881 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 726.14 | 0 | 35
835 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000197/2023-2024 | 1210/MURD/15 | 02/05/2023 | 0 | Resource Division | 37.48 | 0 | 0
836 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAHARAGACHI AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000365/2023-2024 | 2720/MURD | 29/08/2023 | 581 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 100
837 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
838 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of BAHARAGACHI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000821/2022-2023 | 655/MURD | 06/03/2023 | 1032 | ARINDAM MAJUMDAR | 266.77 | 0 | 25
839 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000273/2023-2024 | 1230/MURD/16 | 04/05/2023 | 0 | Resource Division | 21.39 | 0 | 0
840 | Murshidabad Division | Jangipur Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
841 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
842 | Murshidabad Division | Jangipur Sub-Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
843 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000087/2023-2024 | 1147/MURD/1 | 27/04/2023 | 0 | Resource Division | 177.04 | 0 | 0
844 | Murshidabad Division | Kandi Sub-Division | Laying UPVC Pipe line , Road Restoration & FHTCs of Dakshin Raypur PWSS in Khargram Block of Kandi Sub Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000188/2024-2025 | 3146/MURD | 03/12/2024 | 30 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 19.79 | 0 | 0
845 | Murshidabad Division | Kandi Sub-Division | Formal work order for DAKSHIN RAYPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of BURWAN Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000804/2022-2023 | 623/MURD | 03/03/2023 | 730 | DIPAYAN DEY | 393.85 | 0 | 31
846 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000059/2023-2024 | 1075/MURD/3 | 19/04/2023 | 0 | Resource Division | 13 | 0 | 0
847 | Murshidabad Division | Kandi Sub-Division | Construction of Boundwary Wall , PCC Approach road of Basantapur PWSS in Khargram Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000010/2025-2026 | 898/MURD | 23/04/2025 | 60 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 10.43 | 0 | 0
848 | Murshidabad Division | Kandi Sub-Division | Construction of Pump House , Land Development Work of Basantapur PWSS in Khargram Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000012/2025-2026 | 901/MURD | 23/04/2025 | 343 | NOBEL CONSTRUCTION | 10.68 | 0 | 50
849 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Basantapur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000037/2023-2024 | 1104/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 0 | 50
850 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASANTPUR AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000290/2023-2024 | 2656/MURD | 24/08/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0
851 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System , Rising Main Connection FHTC, Construction of Pump House & Boundary Wall for Basantapur water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000892/2022-2023 | 929/MURD | 31/03/2023 | 793 | PARTHA PRATIM DAS | 61.73 | 0 | 30
852 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000071/2022-2023 | 1075/MURD/7 | 19/04/2023 | 0 | Resource Division | 18.61 | 0 | 0
853 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for GHORAPAKHIA GANGIN Zone -II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000016/2025-2026 | 965/MURD | 30/04/2025 | 60 | M/S. UNIQUE BUILDERS | 23.01 | 0 | 0
854 | Murshidabad Division | Berhampur M/E Division | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ghorapakhiagangin Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000111/2024-2025 | 2290/MURD | 09/08/2024 | 15 | JOY GURU ENTERPRISE | 11.67 | 0 | 95
855 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
856 | Murshidabad Division | Berhampur M/E Division | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion in between N.P 04-05-30-07 to 06 (From Dalim Sk house to Sanaul Sk house) for smooth water supply arrangement in Ghorapakhiagangin Zone-I W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000451/2020-2021 | 13/JSD | 13/01/2021 | 30 | LAXMI CONSTRUCTION | 2.88 | 0 | 1
857 | Murshidabad Division | Berhampur M/E Division | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion in between N.P 05 to 06 (Prymary school to kriti mondal's House) for smooth water supply arrangement in Ghorapakhiagangin Zone-I W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000452/2020-2021 | 14/JSD | 13/01/2021 | 30 | DEBOJYOTI CONSTRUCTION | 1.64 | 0 | 1
858 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Ahiran Halt Station to Jangipur Road Station (TP NO 217/5 & 217/6) at Ghorapakhia Gangin mouza & Connecting with existing 110 mm dia uPVC distribution main line of Ghorapakhia Gangin Zone- II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000514/2021-2022 | 2484/MURD | 16/08/2021 | 60 | M/S. SINHA & SONS | 21.58 | 0 | 0
859 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
860 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000210/2023-2024 | 1210/MURD/13 | 02/05/2023 | 0 | Resource Division | 58.4 | 0 | 0
861 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of GARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000690/2022-2023 | 144/MURD | 17/01/2023 | 1445 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 583.49 | 0 | 35
862 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000047/2023-2024 | 1067/MURD/2 | 18/04/2023 | 0 | Resource Division | 27.8 | 0 | 0
863 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000337/2023-2024 | 79/MURD/04 | 09/01/2024 | 0 | Resource Division | 18.58 | 0 | 0
864 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of Saktipur Zone-III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000529/2022-2023 | 2539/MURD | 02/09/2022 | 365 | BIJAY CHOWDHURY | 314.93 | 0 | 2
865 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-III Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000671/2022-2023 | 3412/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 100
866 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 0 | 0
867 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000007/2024-2025 | 1811/MURD/06 | 20/06/2024 | 0 | Resource Division | 19.32 | 0 | 0
868 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000300/2023-2024 | 1278/MURD/8 | 10/05/2023 | 0 | Resource Division | 58.86 | 0 | 0
869 | Murshidabad Division | Berhampur Sub-Division | Construction of Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) of 4th Tubewell ,Air Compressor Room with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) , 210 mtr Boundary wall , 86 mtr Drain and Renovation of IEP (Rapid Gravity Filter) at Chandpur W/S Scheme under Berhampore sub-Division , P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000017/2025-2026 | 966/MURD | 30/04/2025 | 60 | MODERN CONSTRUCTION | 63.48 | 0 | 0
870 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000359/2022-2023 | 2083/MURD | 27/07/2022 | 991 | TINA ROY | 355.12 | 0 | 85
871 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
872 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Chandpur Zone-I, II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000599/2022-2023 | 3073/MURD | 17/11/2022 | 60 | MERCURY ENGINEERING COMPANY | 31.74 | 0 | 100
873 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 0 | 1
874 | Murshidabad Division | Berhampur Sub-Division | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/001346/2021-2022 | 12/BSD | 10/01/2022 | 15 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0
875 | Murshidabad Division | Berhampur Sub-Division | Repairing of R.C.C. elevated reservoir (375 Cum capacity) of staging hight 18.5 Mtr. At Chandpur Water Supply under Berhampore Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | ORD/001647/2021-2022 | 554/MURD | 28/02/2022 | 45 | ULTRA CONSTRUCTION. | 11.25 | 0 | 0
876 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | RTOR000004/2024-2025 | 1811/MURD/03 | 20/06/2024 | 0 | Resource Division | 40.95 | 0 | 0
877 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,JUNIOR ENGINEER 5 MURSHIDABAD CIRCLE,Junior engineer-II | RTOR000302/2023-2024 | 1278/MURD/4 | 10/05/2023 | 0 | Resource Division | 92.15 | 0 | 0
878 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Momenpur Water Supply Scheme of 2nd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000580/2022-2023 | 3063/MURD | 17/11/2022 | 30 | SUJIT KUMAR SAHA | 9.21 | 0 | 0
879 | Murshidabad Division | Berhampur M/E Division | Formal work order Augmentation of MOMENPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000655/2022-2023 | 3436/MURD | 23/12/2022 | 365 | M/S. ROY TRADING CO. | 408.18 | 0 | 30
880 | Murshidabad Division | Berhampur M/E Division | Construction of approach road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001234/2021-2022 | 604/ISD | 31/12/2021 | 60 | MANAB KUMAR GHOSH | 4.49 | 0 | 1
881 | Murshidabad Division | Berhampur M/E Division | Construction of approch road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/002063/2021-2022 | 40/ISD | 28/01/2022 | 60 | MANAB KUMAR GHOSH | 4.49 | 0 | 1
882 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000031/2024-2025 | MURD/2481/04 | 04/09/2024 | 0 | Resource Division | 11.73 | 0 | 0
883 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000162/2023-2024 | 1180/MURD/09 | 29/04/2023 | 0 | Resource Division | 25.98 | 0 | 0
884 | Murshidabad Division | Berhampur M/E Division | Repairing & Renovation of the pump House No-1 & 2 and allied works under Momenpur water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | VCH/000715/2022-2023 | 235-MSD/22-23 | 15/08/2022 | 0 | SOUVIK HALDER | 3.6 | 0 | 0
885 | Murshidabad Division | Berhampur M/E Division | Inter connection with Tubewell and rising main etc. at Head work sites (T/W-1) &(T/W-2) Both & Allied Works Under Momenpur Water Supply scheme under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | VCH/000720/2022-2023 | 245-MSD/22-23 | 12/08/2022 | 0 | B.G. ENTERPRISE | 3.04 | 0 | 0
886 | Murshidabad Division | Berhampur Sub-Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Bhagabanbati (315342) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000118/2022-2023 | 1201/MURD | 10/05/2022 | 60 | DIPAYAN DEY | 32.59 | 0 | 0
887 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 810 nos household under command area of village of Bhagabanbati( Village Code -315342) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001723177) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000219/2022-2023 | 1449/MURD | 01/06/2022 | 1127 | S. K. ENTERPRISE (PROP:SHAMIM ISLAM) | 36.57 | 0 | 0
888 | Murshidabad Division | Jangipur Sub-Division | Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works & Repair of Boundary Wall (140m + 50m)=190 m at T/W-I site & T/W-II site and Construction of approach road of 80 m ,3 mtr wide and 150 mm depth with 1:2:4 ordinary cement concrete with 75 mm sand filling and BFS for Augmentation of Ahiron Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte.(Attached as Annexure -I) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000661/2023-2024 | 3561/MURD | 21/11/2023 | 60 | ASHEM ENTERPRISE | 8.58 | 0 | 100
889 | Murshidabad Division | Jangipur Sub-Division | Laying distribution pipe lines with allied works in connection With Augmentation of Ahiron Water Supply Scheme In Suti - I Block Of Murshidabad District under Murshidabad Division,P.H.E Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000688/2022-2023 | 130/MURD | 16/01/2023 | 60 | M/S RUBIET HOSSAIN | 94.31 | 0 | 0
890 | Murshidabad Division | Jangipur Sub-Division | AHIRON & adjoining mouzas PWSS to accommodate Rising Main with allied Laying Distribution under Jal Jeevan Mission, Block- SUTI-I of JANGIPUR Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000839/2023-2024 | 822/MURD | 15/03/2024 | 60 | S. DUTTA | 6.88 | 0 | 100
891 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000104/2023-2024 | 1167/MURD/1 | 28/04/2023 | 0 | Resource Division | 68.84 | 0 | 0
892 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID 0005019112 in the District of Murshidabad. |  |  | ORD/001377/2021-2022 | 1617 / MURD | 28/06/2021 | 60 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0
893 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. ( PART-II ) |  |  | VCH/001296/2021-2022 |  | 17/02/2022 | 0 | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0
894 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no - 241 of 21-22 by EE MURD |  |  | VCH/001456/2021-2022 | 342-MSD/21-22 | 05/03/2022 | 0 | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0
895 | Murshidabad Division |  | Cleaning & Washing of pipe line at Village Bara Jumla (Village Code-314144) & Krishna Sail (Village Code- 314143) in cinnection with FHTC work under Putia Water Supply Scheme) |  |  | ORD/000315/2022-2023 | 259/JSD | 01/06/2022 | 30 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 4.02 | 0 | 0
896 | Murshidabad Division |  | Laying pipe line at village Bara Jumla (Village Code- 314144) & Krishnaa Sail (Village Code-314143) in connection with FHTC work under Putia Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte.https://app2.wbphed.gov.in/phed_v3/FAF00242/openDetail01new.html |  |  | ORD/000338/2022-2023 | 274/JSD | 01/06/2022 | 30 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.85 | 0 | 0
897 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) |  |  | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 180 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 12
898 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 889/D/MURD | 05/04/2022 | 0 | Resource Division | 30.5 | 0 | 0
899 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline and road restrostion work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000058/2022-2023 | 163/BSD | 12/04/2022 | 15 | SUDIPTA GHOSH | 4.84 | 0 | 0
900 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000066/2022-2023 | 171/BSD | 12/04/2022 | 15 | BARMAN ENTERPRISE | 4.83 | 0 | 0
901 | Murshidabad Division | Berhampur Sub-Division | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000067/2022-2023 | 172/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.85 | 0 | 0
902 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000068/2022-2023 | 173/BSD | 12/04/2022 | 15 | M/S SUKESH GHOSH | 4.95 | 0 | 0
903 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000515/2021-2022 | 347/BSD | 27/08/2021 | 30 | IMAGIN | 4.16 | 0 | 0
904 | Murshidabad Division | Berhampur Sub-Division | Relaying of UPVC pipe line from the house of Akbar Miya to the house of Yasin Sk under command area of Choa Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001611/2021-2022 | 21/BSD | 20/01/2022 | 15 | SWAPAN DAS | 4.81 | 0 | 0
905 | Murshidabad Division | Berhampur Sub-Division | Relaying of UPVC pipeline from the house of Akbar Miya to the house of Yasin SK under command area of choa W/S Scheme under BSD PHE DTE. Tender no - 176 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/001553/2021-2022 | 448-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.81 | 0 | 0
906 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Keyadanga (Village code 313966) under Keyadanga Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723355 in the District of Murshidabad. |  |  | ORD/001783/2021-2022 | 804/MURD | 24/03/2022 | 30 | AZAD ENTERPRISE | 25.19 | 0 | 0
907 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 540/4/MURD | 25/02/2022 | 0 | Resource Division | 3.12 | 0 | 0
908 | Murshidabad Division |  | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A |  |  | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
909 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (2145 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Mahadeb Nagar ( Village Code -313823) under Mahadebnagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000653/2023-2024 | 3498/MURD | 08/11/2023 | 90 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 77.63 | 0 | 0
910 | Murshidabad Division |  | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. |  |  | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0
911 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Farakka Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001181/2021-2022 | 368/JSD | 22/12/2021 | 30 | IMAGIN | 3.1 | 0 | 0
912 | Murshidabad Division |  | HIRING OF CAR FOR EE-MSD, MSD DIVN, W/O NO- 293/HQ, DT-29/11/2021 |  |  | VCH/000497/2022-2023 | 186-MSD/22-23 | 24/06/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0
913 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-10 |  |  | VCH/000753/2022-2023 | 289-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.29 | 0 | 0
914 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-11 |  |  | VCH/000754/2022-2023 | 289-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.29 | 0 | 0
915 | Murshidabad Division |  | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Kankuria (Village Code-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme ID- 0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/000093/2022-2023 | 239/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.42 | 0 | 1
916 | Murshidabad Division |  | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Kankuria (Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme Id:-0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. |  |  | ORD/000094/2022-2023 | 240/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.6 | 0 | 1
917 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jafrabad ( Village Code -313872) & (adjoining habitation) (Part-IV) under Kankuria & Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) |  |  | ORD/000404/2021-2022 | 2536/MURD | 19/08/2021 | 60 | M/S. M.R. CONSTRUCTION (PROP: MASUD RANA) | 67.49 | 0 | 0
918 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jafrabad ( Village Code -313872 & adjoining habitation (Part-III) under Kankuria&Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) |  |  | ORD/000409/2021-2022 | 2539/MURD | 19/08/2021 | 1680 | IKON CONSTRUCTION | 80.14 | 0 | 30
919 | Murshidabad Division |  | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-D) |  |  | ORD/001257/2021-2022 | 377/JSD | 31/12/2021 | 30 | R.K.CONSTRUCTION(SOHEL RANA KHAN) | 4.77 | 0 | 0
920 | Murshidabad Division |  | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-A). |  |  | ORD/001259/2021-2022 | 379/JSD | 31/12/2021 | 30 | S.D PROJECT | 4.77 | 0 | 0
921 | Murshidabad Division |  | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-B). |  |  | ORD/001260/2021-2022 | 380/JSD | 31/12/2021 | 30 | S.D PROJECT | 4.77 | 0 | 0
922 | Murshidabad Division |  | Work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-C) |  |  | ORD/001288/2021-2022 | 395/JSD | 31/12/2021 | 30 | M/S. SRM ENTERPRISE | 4.77 | 0 | 0
923 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-E) |  |  | ORD/001749/2021-2022 | 118/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.85 | 0 | 0
924 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-F). |  |  | ORD/001750/2021-2022 | 119/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.84 | 0 | 0
925 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-H). |  |  | ORD/001751/2021-2022 | 120/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.76 | 0 | 0
926 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-G). |  |  | ORD/001759/2021-2022 | 125/JSD | 22/03/2022 | 30 | YOUSUF ENTERPRISE | 4.8 | 0 | 0
927 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 540/10/MURD | 25/02/2022 | 0 | Resource Division | 12.11 | 0 | 0
928 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) |  |  | VCH/001291/2021-2022 |  | 17/02/2022 | 0 | NILKAMAL BASAK | 91.86 | 0 | 0
929 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village JAFRABAD (Village Code 313872) under KANKURIA and jafrabad Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 475 of 21-22 by EE MURD |  |  | VCH/001430/2021-2022 | 347-MSD/21-22 | 05/03/2022 | 0 | NILKAMAL BASAK | 91.86 | 0 | 0
930 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD |  |  | VCH/001480/2021-2022 | 388-MSD/21-22 | 17/03/2022 | 0 | S.D PROJECT | 4.77 | 0 | 0
931 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD |  |  | VCH/001481/2021-2022 | 389-MSD/21-22 | 17/03/2022 | 0 | S.D PROJECT | 4.77 | 0 | 0
932 | Murshidabad Division |  | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2024-WL-64 |  |  | BILL/01535/2024-2025 | 545-MSD/2024-25 | 28/10/2024 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 0.11 | 0 | 0
933 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 492 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Sikdarpur ( Village Code -313858) under Sikdarpur & adjoining mouzas Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000049/2022-2023 | 1115/MURD | 29/04/2022 | 30 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 26.22 | 0 | 0
934 | Murshidabad Division |  | Work of Laying of U.P.V.C. Pipe line at Sikdarpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. |  |  | ORD/002103/2021-2022 | 387 /JSD | 31/12/2021 | 30 | DEBOJYOTI CONSTRUCTION | 4.63 | 0 | 1
935 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 540/3/MURD | 25/02/2022 | 0 | Resource Division | 2.7 | 0 | 0
936 | Murshidabad Division |  | Continuation work order for Hiring of 1 no of Car for official use of the eAE LSD PHE DTE. Work Order No 261 / LSD DATE 04.03.2021 |  |  | VCH/000598/2022-2023 | 202-MSD/2022-23 | 07/07/2022 | 0 | ARINDAM MAJUMDAR | 1.08 | 0 | 0
937 | Murshidabad Division |  | work order for Hiring of 1 no of Car for official use of the SE MC PHE DTE. Work Order No 10 / MC. DATE 05.01.2022 |  |  | VCH/000599/2022-2023 | 203-MSD/2022-23 | 07/07/2022 | 0 | HASNA BEWA | 0.62 | 0 | 0
938 | Murshidabad Division |  | Work order for Hiring of 1 no of Car for official use of the AE JSD PHE DTE. Work Order No 302 / JSD. DATE 25.11.2021 |  |  | VCH/000638/2022-2023 | 205-MSD/2022-23 | 08/07/2022 | 0 | MANUAR HOSSAIN | 1.19 | 0 | 0
939 | Murshidabad Division |  | Work order for Hiring of 1 no of Car for official use of the AE ISD PHE DTE. Work Order No 473 / ISD. DATE 03.09.2021 |  |  | VCH/000641/2022-2023 | 206-MSD/22-23 | 12/07/2022 | 0 | M/S SAJAHAN CHOWDHURY | 0.78 | 0 | 0
940 | Murshidabad Division |  | HIRING OF CAR FOR SE-MC |  |  | VCH/001016/2022-2023 | 358-MSD/22-23 | 19/10/2022 | 0 | HASNA BEWA | 0.6 | 0 | 0
941 | Murshidabad Division |  | CONTINUATION ORDER OF CAR HIRING OF AE-LSD 261/LSD DATE- 04/03/2021 |  |  | VCH/001017/2022-2023 | 359-MSD/22-23 | 19/10/2022 | 0 | ARINDAM MAJUMDAR | 0.61 | 0 | 0
942 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
943 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
944 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Dhusaripara colony village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-A). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000085/2022-2023 | 231/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.84 | 0 | 1
945 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Hasimpur, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-B). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000086/2022-2023 | 232/JSD | 05/05/2022 | 30 | BARMAN ENTERPRISE | 4.82 | 0 | 1
946 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Hasimpur, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-C). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000087/2022-2023 | 233/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.8 | 0 | 1
947 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Jyatkundu, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-D). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000088/2022-2023 | 234/JSD | 05/05/2022 | 30 | APU CONSTRUCTION | 4.83 | 0 | 1
948 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line in connection with FHTC work at Jyatkundu, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-E). | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000090/2022-2023 | 236/JSD | 05/05/2022 | 30 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 4.82 | 0 | 1
949 | Murshidabad Division | Kandi Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village RAMAKANTAPUR (Village code 314029) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756489 in the District of Murshidabad. (Sl No-1) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000762/2020-2021 | 3115/MURD | 09/12/2020 | 180 | M/S. SINHA & SONS | 65.21 | 0 | 100
950 | Murshidabad Division | Kandi Sub-Division | Laying of DI pipeline and supplying of CI specials for interconnection of 2nd Tubewell site at Kankuria Jafrabad & Dogachi(zone-II) and 1st Tubewell site at Hasimpur& Bhasaipaikar(zone-I) and of Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000811/2022-2023 | 569/MURD | 28/02/2023 | 30 | MAA CONSTRUCTION | 2.6 | 0 | 100
951 | Murshidabad Division | Kandi Sub-Division | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hasimpur ( Village Code -313861) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723174) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001594/2021-2022 | 398/MURD | 16/02/2022 | 60 | DIPAYAN DEY | 71.07 | 0 | 1
952 | Murshidabad Division |  | New laying of different dia UPVC pipeline to restore the distribution system (Besides of Sukdevmati Bridge) in Retrofitting Providing Functional House Hold Tap Connection FHTC in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Chainpara (314804) under Herampur Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000351/2022-2023 | 302/ISD | 20/07/2022 | 30 | PRATICHI ENTERPRISE | 3.31 | 0 | 0
953 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raghunathpur (Village code 314783) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756480 in the District of Murshidabad. |  |  | ORD/000623/2020-2021 | 321/MURD | 28/01/2021 | 60 | M/S BAPPA ENTERPRISE | 13.73 | 0 | 1
954 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990). |  |  | ORD/000717/2020-2021 | 590/MURD | 09/02/2021 | 60 | PRIYANKA CONSTRUCTION | 26.4 | 0 | 1
955 | Murshidabad Division |  | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990) |  |  | ORD/001776/2021-2022 | 857/MURD | 31/03/2022 | 60 | PRIYANKA CONSTRUCTION | 49.23 | 0 | 0
956 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Gobindapur (Village Code -314687) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) |  |  | ORD/000140/2021-2022 | 1615/MURD | 28/06/2021 | 60 | BISWAS CONSTRUCTION | 27.63 | 24.37 | 0
957 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mamudpur ( Village Code -314685) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) |  |  | ORD/000335/2021-2022 | 2438/MURD | 12/08/2021 | 60 | JOY BISHNU ENGINEERING CO. | 28.13 | 0 | 0
958 | Murshidabad Division |  | Construction of P.C.C approach road at Head work site of Juginda Zone-I Water Supply Scheme under Domkal Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000796/2021-2022 | 477/ISD | 03/09/2021 | 30 | M/S SAJAHAN CHOWDHURY | 1.62 | 0 | 1
959 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SALAR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000468/2021-2022 | 236/KSD | 27/08/2021 | 60 | IMAGIN | 4.15 | 0 | 0
960 | Murshidabad Division |  | Holding Awarness Programme / Campaigning programms at Salar G.P, Talibpur G.P, Kagram G.P, Tenya Baidyapur G.P and Simulia G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-D). |  |  | ORD/000556/2021-2022 | 252/KSD | 31/08/2021 | 30 | IMAGIN | 4 | 0 | 0
961 | Murshidabad Division |  | Repairing of rising main & distribution line at Rail gate & Block road etc with construction of thrust block & laying of pipe line of new habitation of Salar Water Supply scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000871/2021-2022 | 296/KSD | 07/10/2021 | 30 | DAS CONSTRACTION (MUNNA DAS) | 4.1 | 0 | 10
962 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SALAR (Village code 315742) under SALAR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte.( Scheme ID 0005252601) |  |  | ORD/001163/2021-2022 | 3975/MURD | 21/12/2021 | 180 | MAMATA USHA ENTERPRISE | 153.26 | 0 | 1
963 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SALAR (Village Code 315742) under SALAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 127 of 21-22 by SE MC |  |  | VCH/000065/2022-2023 | 84-MSD/22-23 | 28/04/2022 | 0 | MAMATA USHA ENTERPRISE | 38.32 | 0 | 0
964 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) |  |  | ORD/000295/2021-2022 | 2300/MURD | 02/08/2021 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 90.75 | 51.51 | 0
965 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-II) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) |  |  | ORD/000334/2021-2022 | 2435/MURD | 12/08/2021 | 60 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 92.84 | 0 | 1
966 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-III) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) |  |  | ORD/000352/2021-2022 | 2501/MURD | 17/08/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 88.6 | 0 | 1
967 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000449/2021-2022 | 299/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.34 | 4.34 | 0
968 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Khairamari PWSS Scheme,Block- Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 367 of 21-22 by EE MSD, and Scheme Code: 8200 |  |  | VCH/000039/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 8.31 | 0 | 0
969 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) |  |  | VCH/001294/2021-2022 |  | 17/02/2022 | 0 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0
970 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harekrishnapur ( Village Code -314624) under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 243 of 21-22 by EE MURD |  |  | VCH/001385/2021-2022 | 333-MSD/21-22 | 25/02/2022 | 0 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0
971 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 244 of 21-22 by EE MURD |  |  | VCH/001439/2021-2022 | 338-MSD/21-22 | 03/03/2022 | 0 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 31.7 | 0 | 0
972 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723172 in the District of Murshidabad. |  |  | ORD/000169/2021-2022 | 1652/MURD | 29/06/2021 | 180 | HARAPRASAD DAS | 75.04 | 57.92 | 100
973 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 0 | 1
974 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 539/9/MURD | 25/02/2022 | 0 | Resource Division | 2.54 | 0 | 0
975 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MAHAMMADPUR (Village Code 315549) under MAHAMMADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 04 of 20-21 by SE MC |  |  | VCH/001477/2021-2022 | 384-MSD/21-22 | 19/03/2022 | 0 | HARAPRASAD DAS | 16.56 | 0 | 0
976 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000029/2022-2023 | 1082/MURD | 27/04/2022 | 45 | MARUTI CONSTRUCTION AND CO | 62.56 | 0 | 0
977 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 540/7/MURD | 25/02/2022 | 0 | Resource Division | 6.92 | 0 | 0
978 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- KOLAN RADHAKANTAPUR , CODE-314523, TNO- 50/2020-21/SE-MC |  |  | VCH/002025/2020-2021 | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 33.58 | 0 | 0
979 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 539/2020-21/EE |  |  | VCH/002027/2020-2021 | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 10.66 | 0 | 0
980 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- BHANDARA , CODE-314524, TNO- 51/2020-21/SE-MC |  |  | VCH/002029/2020-2021 | 512/W | 30/03/2021 | 0 | DEBASIS BOSE | 30.48 | 0 | 0
981 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dighirpahar (Village code 314794) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-08) |  |  | ORD/000350/2021-2022 | 2503/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 70.56 | 0 | 1
982 | Murshidabad Division |  | Hiring of 01(one) no. Diesel Bolero / Marshal Car for official use having licence for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. Murshidabad for the period from 01-10-2021 to 30-09-2022 (i.e. twelve months) |  |  | ORD/001162/2021-2022 | 473/ISD. | 03/09/2021 | 365 | M/S SAJAHAN CHOWDHURY | 2.05 | 0 | 1
983 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 734 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dighirpahar (Village code 314794) under Islampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005182977). |  |  | ORD/001703/2021-2022 | 670/MURD | 10/03/2022 | 20 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 12.64 | 0 | 0
984 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
985 | Murshidabad Division |  | Laying of UPVC pipeline at Bagpur and Gantla Village for FHTC work of Gantla Village ( Village Code- 315215) of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | ORD/000004/2022-2023 | 06 / KSD | 06/04/2022 | 30 | ABHIJIT MONDAL | 4.85 | 0 | 1
986 | Murshidabad Division |  | Construction of pathway at Head work Site of Mahalandi (Zone-I) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000012/2022-2023 | 13 / KSD | 06/04/2022 | 30 | HERITAZE CONSTRUCTION | 3.92 | 0 | 1
987 | Murshidabad Division |  | Laying of UPVC pipeline from Danarul Sk Shop to Gantla Ashram for FHTC work of Gantla Village (Village Code- 315215) of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | ORD/000330/2022-2023 | 106 / KSD | 17/06/2022 | 30 | DEBJYOTI MUKHERJEE | 4.83 | 0 | 1
988 | Murshidabad Division |  | Construction of surface drain and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000419/2022-2023 | 123/KSD | 25/07/2022 | 30 | KAKALI ENTERPRISE | 3.58 | 0 | 1
989 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHALANDI-I G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000458/2021-2022 | 227/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
990 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KUMARSANDA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000459/2021-2022 | 228/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.15 | 0 | 0
991 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahalandi under Mahalandi (Zone-I)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block, under Murshidabad Division, PHE Dte. Scheme ID ¿ 0007585495 in the District of Murshidabad. |  |  | ORD/000499/2020-2021 | 692/MURD | 23/02/2021 | 180 | M/S . SUKUMAR SINHA | 113.1 | 0 | 0
992 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal JeevanMission and Jal Swapna under command area of village Gantla under Mahalandi (Zone-II) Ground Based Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block under Murshidabad Division, PHE Dte. Scheme ID 0007585495 in the District of Murshidabad. (Sl No-20) |  |  | ORD/000515/2020-2021 | 3051/MURD | 08/12/2020 | 180 | M/S. BIMALENDU BOSE | 69.15 | 0 | 95
993 | Murshidabad Division |  | Holding Awarness Programme / Campaigning programms at Jasahari Anukha-I & II G.P, Mahalandi-I G.P, Kumarsanda G.P and Gokarna-I G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-A). |  |  | ORD/000553/2021-2022 | 249/KSD | 31/08/2021 | 30 | IMAGIN | 4 | 0 | 0
994 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BELUN (Village Code : 315216) under Mahalandi Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. |  |  | ORD/000555/2020-2021 | 3038/MURD | 07/12/2020 | 1606 | PRIME CONSTRUCTION | 19.31 | 0 | 50
995 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahalandi under Mahalandi (Zone-I)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block, under Murshidabad Division, PHE Dte. Scheme ID 0007585495 in the District of Murshidabad. |  |  | ORD/000680/2020-2021 | 692 / MURD | 23/02/2021 | 180 | M/S . SUKUMAR SINHA | 113.1 | 0 | 1
996 | Murshidabad Division |  | Laying of DI pipe in between node point 1A to 29 & supplying of C.I specials of Mahalandi (Zone-I) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the District of Murshidabad. |  |  | ORD/000771/2022-2023 | 211/KSD | 17/02/2023 | 830 | JYOTI TRADERS | 0.97 | 0 | 60
997 | Murshidabad Division |  | Laying of UPVC pipe line from Head work site to near house of Kalimuddin Sk for drain out of OHR overflow water under Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000774/2022-2023 | 212 / KSD | 17/02/2023 | 30 | A.P. CONSTRUCTION | 0.97 | 0 | 1
998 | Murshidabad Division |  | Repairing of leakage & bursting of UPVC pipe line of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000775/2022-2023 | 213 / KSD | 17/02/2023 | 30 | A.P. CONSTRUCTION | 0.96 | 0 | 1
999 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/001228/2021-2022 | 212/KSD | 11/08/2021 | 30 | IMAGIN | 4.33 | 0 | 0
1000 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sole Para ( Village Code -315217) under Mahalandi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007585495) |  |  | ORD/001479/2021-2022 | 305/MURD | 07/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 61.94 | 0 | 1
1001 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000041/2021-2022 | 541/1/MURD | 25/02/2022 | 0 | Resource Division | 6.96 | 0 | 0
1002 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BELUN (Village Code 315216) under MAHALANDI Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. Tender no - 476 of 21-22 by EE MURD |  |  | VCH/001491/2021-2022 | 394-MSD/21-22 | 22/03/2022 | 0 | PRIME CONSTRUCTION | 11.24 | 0 | 0
1003 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHAR GARAMGARIDAIR(Village code 314792) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, in the District of Murshidabad. |  |  | ORD/000262/2020-2021 | 259/MURD | 25/01/2021 | 45 | AMAL KUMAR DAS | 29.36 | 0 | 0
1004 | Murshidabad Division |  | Extension of pipeline at uncovered habitation of Kanthaliapara Year Ali to Fajit Sk house via Ali Box Sk house & Jalit Sk house under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. |  |  | ORD/002128/2021-2022 | 468/ISD | 03/09/2021 | 30 | M/S. DIPTI ENTERPRISE | 3.06 | 0 | 0
1005 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgiri (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District. |  |  | VCH/000865/2021-2022 | 221-MSD/21-22 | 09/12/2021 | 0 | AMAL KUMAR DAS | 7.7 | 0 | 0
1006 | Murshidabad Division |  | Holding Awardness Programme FHTC |  |  | VCH/000866/2021-2022 | 208-MSD/21-22 | 08/12/2021 | 0 | IMAGIN COMMUNICATION | 3.57 | 0 | 0
1007 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
1008 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1009 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1010 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Nandalalpur (Village code 314628) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad. (Sl No-29) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000297/2020-2021 | 961/MURD | 24/03/2021 | 180 | S.M. ENTERPRISE | 50.52 | 0 | 1
1011 | Murshidabad Division | Kandi Sub-Division | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000745/2021-2022 | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0
1012 | Murshidabad Division | Kandi Sub-Division | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
1013 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Borakuli (Village code 314789) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756480 in the District of Murshidabad. |  |  | ORD/000408/2020-2021 | 325/MURD | 28/01/2021 | 60 | MADAN MOHAN SASMAL | 14.03 | 10.36 | 1
1014 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village Tekaraipur (Village code-314788) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0001756480) |  |  | ORD/000537/2022-2023 | 2686/MURD | 22/09/2022 | 120 | S.D. PROJECT | 132.63 | 0 | 100
1015 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Balumati (Village code 314790) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756480 in the District of Murshidabad. |  |  | ORD/000596/2020-2021 | 33/MURD | 05/01/2021 | 60 | DOBAY CONSTRUCTION | 36.55 | 0 | 1
1016 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAGHUNATHPUR (Village Code 314783) under TEKARAIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 695 of 20-21 by EE MURD |  |  | VCH/000295/2022-2023 | 105-MSD/22-23 | 06/05/2022 | 0 | M/S BAPPA ENTERPRISE | 13.72 | 0 | 0
1017 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dayarampur (Village code 314617) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. |  |  | ORD/000468/2020-2021 | 531/MURD | 04/02/2021 | 60 | M/S. BIMALENDU BOSE | 44.35 | 0 | 1
1018 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramasia (Village code 314622) under Narasinghapur Ground Water Supply Scheme for Arsenic Affected Area of Jalangi Block. under Murshidabad Division, PHE Dte. Scheme ID 0005184090 |  |  | ORD/000528/2022-2023 | 2418/MURD | 22/08/2022 | 180 | M/S. SINHA & SONS | 49.87 | 0 | 0
1019 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baramasia (Village code 314622) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. |  |  | ORD/000578/2020-2021 | 530/MURD | 04/02/2021 | 60 | RELIABLE ENTERPRISE | 44.77 | 0 | 1
1020 | Murshidabad Division |  | Formal Work Order for ¿Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Narasinghapur (Village code 314620) under Narasinghapur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184090 in the District of Murshidabad. (Sl No-18) |  |  | ORD/000628/2020-2021 | 697/MURD | 24/02/2021 | 180 | MANAB KUMAR GHOSH | 64.64 | 0 | 0
1021 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dayarampur (Village code 314617) under Narasinghapur Ground Water Supply Scheme for Arsenic Affected Area of Jalangi Block. under Murshidabad Division, PHE Dte. Scheme ID 0005184090 (SlNo-17) |  |  | ORD/001051/2021-2022 | 3684/MURD | 26/11/2021 | 180 | BENOY DOBAY | 46.91 | 0 | 1
1022 | Murshidabad Division |  | Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Giria, Sekendra, Mithipur, Jotkamal, Dayarampur, Sammatinagar, Teghari, Kasiadanga, laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. |  |  | ORD/001183/2021-2022 | 371/JSD | 22/12/2021 | 30 | IMAGIN | 3.99 | 0 | 1
1023 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Godagari ( Village Code -314615) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184090) |  |  | ORD/001465/2021-2022 | 280/MURD | 03/02/2022 | 60 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 59.67 | 0 | 1
1024 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 495 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Narasinghpur (Village code 314620) under Narasinghpur Ground water based water supply scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005184090). |  |  | ORD/001723/2021-2022 | 705/MURD | 14/03/2022 | 15 | M/S. GHOSH ENTERPRISE | 12.87 | 0 | 1
1025 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 395/MURD | 16/02/2022 | 0 | Resource Division | 8.08 | 0 | 0
1026 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DAYARAMPUR (Village Code 314617) under NARASINGHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 295 of 21-22 by EE MURD |  |  | VCH/001488/2021-2022 | 418-MSD/21-22 | 23/03/2022 | 0 | M/S. BIMALENDU BOSE | 32.54 | 0 | 0
1027 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GODAGARI (Village Code 314615) under NARSINGHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 664 of 21-22 by EE MURD |  |  | VCH/001509/2021-2022 | 404-MSD/21-22 | 22/03/2022 | 0 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 26.24 | 0 | 0
1028 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- A village, Block:- Burwan, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000194/2023-2024 | 2024/MURD | 25/07/2023 | 60 | M/S S.R.K. ENTERPRISE | 30.55 | 0 | 0
1029 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- B village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000212/2023-2024 | 2322/MURD | 02/08/2023 | 60 | KESHAB CHANDRA DAS | 30.54 | 0 | 0
1030 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- C village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000213/2023-2024 | 2323/MURD | 02/08/2023 | 60 | M/S. MONDAL ENTERPRISE | 30.25 | 0 | 0
1031 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Hatisala Part- D village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000216/2023-2024 | 2327/MURD | 02/08/2023 | 60 | U.S BUILDERS | 30.54 | 0 | 0
1032 | Murshidabad Division |  | Last mile connectivity and providing 6918 nos Functional House Hold Connection from Zone- XIV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte |  |  | ORD/000336/2023-2024 | 2693/MURD | 25/08/2023 | 120 | M/S GUHA AND ROY | 413.64 | 0 | 0
1033 | Murshidabad Division |  | Last mile connectivity and providing 3452 nos Functional House Hold Connection from Zone- XVI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000338/2023-2024 | 2695/MURD | 25/08/2023 | 120 | TEKNO ENTERPRISE | 207.53 | 0 | 0
1034 | Murshidabad Division | Kandi Sub-Division | Additional work for Augmentation of Burwan (Zone-I) PWSS of accommodate FHTC, Laying of Distribution System, Road Restoration work and Land Development in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000034/2025-2026 | 1111/MURD | 15/05/2025 | 60 | MOTI RAHAMAN | 87.4 | 0 | 0
1035 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Burwan Zone-I PWSS of accommodate FHTC( 1848 Nos), Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Boundary Wall, 200 CUM OHR, Repairing of 272 CUM OHR in Burwan Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000351/2023-2024 | 2678/MURD | 24/08/2023 | 586 | MOTI RAHAMAN | 360.93 | 0 | 10
1036 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Burwan Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000727/2023-2024 | 3917/MURD | 21/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 0
1037 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1038 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1039 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000010/2023-2024 | 1004/MURD/3 | 11/04/2023 | 0 | Resource Division | 70.9 | 0 | 0
1040 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
1041 | Murshidabad Division | Kandi Sub-Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Nagar Zone-I PWSS in Khargram Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000575/2023-2024 | 3298/MURD | 20/10/2023 | 805 | SAMIMA ENTERPRISE | 492.21 | 0 | 10
1042 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1043 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000014/2023-2024 | 1004/MURD/5 | 11/04/2023 | 0 | Resource Division | 62.48 | 0 | 0
1044 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000362/2023-2024 | MURD/439/07 | 08/02/2024 | 0 | Resource Division | 20.57 | 0 | 0
1045 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000244/2023-2024 | 1219/MURD/33 | 03/05/2023 | 0 | Resource Division | 18.54 | 0 | 0
1046 | Murshidabad Division | Kandi Sub-Division | Construction of Drain, Laying of UPVC pipeline and road restoration work of Gayespur Water Supply Scheme in Khargram Block of Kandi Sub-Division, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000202/2024-2025 | 3285/MURD | 16/12/2024 | 30 | DAS ENTERPRISE (SUBRATA DAS) | 38.28 | 0 | 0
1047 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GAYESPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000628/2023-2024 | 3424/MURD | 02/11/2023 | 21 | NADIA TUBEWELLS | 18.43 | 0 | 100
1048 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000082/2023-2024 | 1129/MURD/5 | 25/04/2023 | 0 | Resource Division | 13.5 | 0 | 0
1049 | Murshidabad Division | Berhampur Sub-Division | Allied work of laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Maradighi ( Village Code -315674) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000053/2024-2025 | 1984/MURD | 08/07/2024 | 176 | SUPIA CONSTRUCTION | 15.86 | 0 | 80
1050 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 100
1051 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC connection to 1016 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-III PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000383/2023-2024 | 2769/MURD | 01/09/2023 | 731 | MITRA CONSTRUCTION | 159.63 | 0 | 100
1052 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Rejinagar Zone III PWSS of accommodate with Boundary Wall, 400 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000589/2023-2024 | 3331/MURD | 23/10/2023 | 844 | NEW INDIA CONSTRUCTION | 188.69 | 0 | 80
1053 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1054 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000022/2024-2025 | 1811/MURD/21 | 20/06/2024 | 0 | Resource Division | 8.44 | 0 | 0
1055 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000138/2023-2024 | 1167/MURD/48 | 28/04/2023 | 0 | Resource Division | 33.47 | 0 | 0
1056 | Murshidabad Division | Berhampur M/E Division | Augmentation of JURANPUR (PART-A) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub Division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000082/2023-2024 | 1384/MURD | 22/05/2023 | 1147 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 456.53 | 0 | 20
1057 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-A) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000127/2023-2024 | 1764/MURD | 06/07/2023 | 1045 | NADIA TUBEWELLS | 35.34 | 0 | 90
1058 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
1059 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000158/2023-2024 | 1180/MURD/07 | 29/04/2023 | 0 | Resource Division | 134.73 | 0 | 0
1060 | Murshidabad Division | Berhampur M/E Division | Additional work for Laying of UPVC pipeline, Construction of Culvert and Approach road of LOKHAIPUR Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000003/2025-2026 | 783/MURD | 03/04/2025 | 45 | AZAD ENTERPRISE | 47.72 | 0 | 0
1061 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1062 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LOKAIPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000616/2023-2024 | 3388/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 80
1063 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for LOKAIPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000829/2022-2023 | 694/MURD | 10/03/2023 | 365 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 239.71 | 0 | 30
1064 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000285/2023-2024 | 1230/MURD/26 | 04/05/2023 | 0 | Resource Division | 18.15 | 0 | 0
1065 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000374/2023-2024 | 495/MURD/07 | 15/02/2024 | 0 | Resource Division | 4.1 | 0 | 0
1066 | Murshidabad Division | Berhampur M/E Division | NEZAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Suti-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000015/2023-2024 | 979/MURD | 10/04/2023 | 723 | M/S. M.S. ENTERPRISE | 207.04 | 0 | 30
1067 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1068 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NEZAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000615/2023-2024 | 3387/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 100
1069 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000279/2023-2024 | 1230/MURD/19 | 04/05/2023 | 0 | Resource Division | 15.35 | 0 | 0
1070 | Murshidabad Division | Islampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - I ) Part - A Water Supply Scheme at Head Work Site, 2nd Site site at Domkal Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000120/2023-2024 | 1761/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 23.58 | 0 | 50
1071 | Murshidabad Division | Islampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sultanpur (Village code 314726) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000242/2020-2021 | 85/MURD | 08/01/2021 | 60 | DECON INDIA | 33.63 | 0 | 1
1072 | Murshidabad Division | Islampur Sub-Division | Formal work order for Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part- A under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000808/2022-2023 | 622/MURD | 03/03/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 508 | 0 | 20
1073 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
1074 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000207/2023-2024 | 1210/MURD/11 | 02/05/2023 | 0 | Resource Division | 147.5 | 0 | 0
1075 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/01/2025 to 16/07/2025. [ Vehicle No:- WB 58 CD 3758] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000244/2024-2025 | 15/JSD | 17/01/2025 | 181 | HASSAN CONSTRUCTION | 0.88 | 0 | 0
1076 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Aurangabad Zone-II Piped Water Supply Scheme to accommodate with FHTC (586 Nos), Laying of Rising Main , Laying of Distribution System , construction of 600 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000294/2023-2024 | 2668/MURD | 24/08/2023 | 365 | KUNDU CONSTRUCTION | 371.15 | 0 | 0
1077 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
1078 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000222/2023-2024 | 1219/MURD/08 | 03/05/2023 | 0 | Resource Division | 47.69 | 0 | 0
1079 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - II ) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000358/2023-2024 | 2701/MURD | 25/08/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 0 | 95
1080 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 0 | 100
1081 | Murshidabad Division | Berhampur M/E Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II) under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000728/2023-2024 | 4005/MURD | 28/12/2023 | 735 | M/S. BIMAL MISRA | 838.96 | 0 | 35
1082 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000209/2023-2024 | 1210/MURD/14 | 02/05/2023 | 0 | Resource Division | 241.41 | 0 | 0
1083 | Murshidabad Division | Kandi Sub-Division | Construction of 200 Cum OHR, Pump House Boundwary Wall, , Rising Main Connection, Laying Distribution System of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000021/2023-2024 | 995/MURD | 11/04/2023 | 1086 | APORUPA CONSTRUCTION | 226.95 | 0 | 65
1084 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, FHTC of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. in the District of Murshidabad Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000025/2023-2024 | 1032/MURD | 13/04/2023 | 872 | DIPAYAN DEY | 188.8 | 0 | 10
1085 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURIA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000288/2023-2024 | 2634/MURD | 23/08/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 18.43 | 0 | 100
1086 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000079/2022-2023 | 1936/MURD/4 | 18/07/2023 | 0 | Resource Division | 15.94 | 0 | 0
1087 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MAHAMMADPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000710/2022-2023 | 143/MURD | 17/01/2023 | 1094 | SUJIT KUMAR SAHA | 315.18 | 0 | 70
1088 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000023/2023-2024 | 1067/MURD/6 | 18/04/2023 | 0 | Resource Division | 24.66 | 0 | 0
1089 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000336/2023-2024 | 79/MURD/03 | 09/01/2024 | 0 | Resource Division | 8.45 | 0 | 0
1090 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000350/2023-2024 | 112/MURD/07 | 11/01/2024 | 0 | Resource Division | 8.45 | 0 | 0
1091 | Murshidabad Division | Islampur Sub-Division | Formal work order for Augmentation of P T Rasulpur (Part - B) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000800/2022-2023 | 608/MURD | 02/03/2023 | 975 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 363.24 | 0 | 20
1092 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000394/2023-2024 | 526/MURD/04 | 19/02/2024 | 0 | Resource Division | 3.66 | 0 | 0
1093 | Murshidabad Division | Berhampur Sub-Division | Renovation of Existing IEP (Capacity 50 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chamber of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augmentation of Bachara Z-II Pipe Water supply scheme under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000081/2024-2025 | 2074/MURD | 19/07/2024 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 4.84 | 0 | 100
1094 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, Laying of Distribution System (part_A) , Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity, Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-II PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000145/2023-2024 | 1870/MURD | 14/07/2023 | 795 | M/S. S.C. CIVIL ENTERPRISES | 280 | 0 | 30
1095 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 100
1096 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
1097 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 324 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for for Augmentation work of BACHHRA ZONE-II PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000869/2022-2023 | 848/MURD | 24/03/2023 | 180 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 103.19 | 0 | 50
1098 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000013/2024-2025 | 1811/MURD/12 | 20/06/2024 | 0 | Resource Division | 1.4 | 0 | 0
1099 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000083/2022-2023 | 1278/MURD/18 | 10/05/2023 | 0 | Resource Division | 13.02 | 0 | 0
1100 | Murshidabad Division | Berhampur M/E Division | Augmentation of KISHOREPUR(PART-A) Pipe water supply scheme, to accommodate FHTC under Jal Jeevan Mission under Jangipur Sub Division Block- SUTI-II, of Murshidabad Division,District-Murshidabad PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000016/2023-2024 | 980/MURD | 10/04/2023 | 1032 | A ONE CONSTRUCTION | 203.06 | 0 | 50
1101 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 0 | 100
1102 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000261/2023-2024 | 1230/MURD/07 | 04/05/2023 | 0 | Resource Division | 25.86 | 0 | 0
1103 | Murshidabad Division | Berhampur M/E Division | Allied work of Repair & Renovation of Pump House and Boundary Wall at Head Work Site of Teghari (Zone-I) Water Supply Scheme under Jangipur Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000064/2024-2025 | 2014/MURD | 11/07/2024 | 444 | AZAD ENTERPRISE | 17.13 | 0 | 80
1104 | Murshidabad Division | Berhampur M/E Division | Allied works for Laying of Rising Main & Distribution System (Part-A) of TEGHARI (ZONE-I) Water Supply Scheme of Raghunathgani-II Block in Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000163/2024-2025 | 2908/MURD | 29/10/2024 | 154 | RIDAUAN ENTERPRISE | 55.78 | 0 | 60
1105 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System and Overhauling of R.C.C. elevated reservoir 800 Cum capacity of staging height 20 mtr for Augmentation work of Teghari (Zone-I) PWSS (PART-A) in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000176/2023-2024 | 1994/MURD | 21/07/2023 | 626 | BABUSONA CONSTRUCTION | 100.73 | 0 | 30
1106 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System for Augmentation work of Teghari (Zone-I) PWSS (PART-B) in Raghunathganj-II Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000177/2023-2024 | 1995/MURD | 21/07/2023 | 180 | M/S. CHOWDHURY CONSTRUCTION | 112.17 | 0 | 20
1107 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 2516 nos. household for Augmentation work of Teghari (Zone-I) PWSS(PART-A) in Raghunathganj-II Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000191/2023-2024 | 2022/MURD | 25/07/2023 | 180 | ARABINDA GHOSH | 124.91 | 0 | 0
1108 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at TEGHARI ZONE - I, MAHESAIL ZONE-III & SERPUR (CT) Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000236/2023-2024 | 2407/MURD | 07/08/2023 | 552 | NADIA TUBEWELLS | 35.34 | 0 | 100
1109 | Murshidabad Division | Berhampur M/E Division | Allied works for Laying of Rising Main & Distribution System (Part-B) of TEGHARI (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000241/2024-2025 | 192/MURD | 21/01/2025 | 60 | SUMAN CHOWDHURY | 43.88 | 0 | 0
1110 | Murshidabad Division | Berhampur M/E Division | Allied work for vertical extension of head works site boundary wall , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top and construction of Wash out pipe line from OHR to pond of Teghari Water Supply Scheme of Raghunathganj-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000242/2023-2024 | 2409/MURD | 07/08/2023 | 30 | MOLLA ENTERPRISE | 9.43 | 0 | 100
1111 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 2500 nos household for Augmentation work of Teghari (Zone-I) PWSS (PART-B) in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000378/2023-2024 | 2756/MURD | 01/09/2023 | 845 | DEBASIS BOSE | 124.54 | 0 | 30
1112 | Murshidabad Division | Berhampur M/E Division | Allied work for Repairing & Renovation of 800 Cum Capacity and 20 mtr staging height R.C.C. Elevated Reservoir & construction of surface drain for Augmentation work of TEGHARI (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000841/2023-2024 | 819/MURD | 15/03/2024 | 60 | BABUSONA CONSTRUCTION | 10.9 | 0 | 0
1113 | Murshidabad Division | Berhampur M/E Division | Allied work for Renovation of Pump House and Boundary Wall at 2nd Site of Teghari (Zone-I) Water Supply Scheme under Jangipur Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000852/2023-2024 | 828/MURD | 15/03/2024 | 30 | NIRMAN ENTERPRISE | 5.29 | 0 | 0
1114 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
1115 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000148/2023-2024 | 1167/MURD/52 | 28/04/2023 | 0 | Resource Division | 115.2 | 0 | 0
1116 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of EKPAHARIA (Part-A) & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000718/2022-2023 | 104/MURD | 13/01/2023 | 1084 | DOBAY CONSTRUCTION | 422.08 | 0 | 18
1117 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of EKPAHARIA( Part-B) & adjoining moujas PWSS to accommodate Construction Tube Well, Pump House Cum Chlorine Room & Blower room and Laying Distribution System under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000719/2022-2023 | 105/MURD | 13/01/2023 | 180 | MOTI RAHAMAN | 203.57 | 0 | 45
1118 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000050/2023-2024 | 1067/MURD/5 | 18/04/2023 | 0 | Resource Division | 25.69 | 0 | 0
1119 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-I Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000022/2023-2024 | 994/MURD | 11/04/2023 | 720 | SUJIT KUMAR SAHA | 222.84 | 0 | 60
1120 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000132/2023-2024 | 1758/MURD | 06/07/2023 | 576 | R.K. DRILLING SERVICES | 23.58 | 0 | 70
1121 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
1122 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1123 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000031/2023-2024 | 1043/MURD/1 | 17/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
1124 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000062/2022-2023 | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 2.38 | 0 | 0
1125 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MAHISAR & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362278S000 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000678/2022-2023 | 37/MURD | 04/01/2023 | 1062 | NAYLA CONSTRUCTION | 611.61 | 0 | 50
1126 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000038/2023-2024 | 1043/MURD/13 | 17/04/2023 | 0 | Resource Division | 26.09 | 0 | 0
1127 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BASUDEBPUR Zone ¿I Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000021/2025-2026 | 986/MURD | 02/05/2025 | 60 | J.S. CONSTRUCTION | 23.01 | 0 | 0
1128 | Murshidabad Division | Berhampur M/E Division | Balance work of Laying of UPVC Pipe , Construction of approach road , Modification of R.C.C. Elevated Reservoir and Pump House, Boundary wall, for Augmentation of Basudevpur (Zone-I) Water Supply Scheme in Suti-I Block of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000242/2024-2025 | 191/MURD | 21/01/2025 | 223 | MOLLA ENTERPRISE | 40.58 | 0 | 35
1129 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Basudevpur Halt Station to Dhulianganga Station (TP NO 235/2 & 235/3) at Basudevpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Basudevpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000426/2021-2022 | 2483/MURD | 16/08/2021 | 60 | SANJAY BISWAS | 22.75 | 0 | 100
1130 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 650 nos household , Repairing & Vertical Extention of Boundary Wall ,Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & Pump House repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr. (Shaft wall ) for Augmentation work of Basudebpur (Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000787/2022-2023 | 541/MURD | 24/02/2023 | 1110 | MOLLA ENTERPRISE | 49.98 | 0 | 25
1131 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System for Augmentation work of Basudebpur(Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000893/2022-2023 | 902/MURD | 29/03/2023 | 720 | JAI BHARAT COMMERCIAL CORPORATION | 112.15 | 0 | 40
1132 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
1133 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000143/2023-2024 | 1167/MURD/47 | 28/04/2023 | 0 | Resource Division | 11.06 | 0 | 0
1134 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000187/2023-2024 | 1210/MURD/23 | 02/05/2023 | 0 | Resource Division | 4.02 | 0 | 0
1135 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Jagtai Piped Water Supply Scheme to accommodate with FHTC (1730 Nos), Laying of Rising Main , Laying of Distribution System , construction of 200 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000314/2023-2024 | 2670/MURD | 24/08/2023 | 730 | GREENLEAF CONSTRUCTION | 336.47 | 0 | 40
1136 | Murshidabad Division | Berhampur M/E Division | Repair of Pump Houses , Construction of toilet , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top & approach road for JAGTAI Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000637/2022-2023 | 3167/MURD | 30/11/2022 | 30 | M/S JOY MA BANAMALI | 7.11 | 0 | 0
1137 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
1138 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000041/2024-2025 | MURD/2991 | 13/11/2024 | 0 | Resource Division | 25.25 | 0 | 0
1139 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000224/2023-2024 | 1219/MURD/29 | 03/05/2023 | 0 | Resource Division | 18.03 | 0 | 0
1140 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE I) Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000106/2023-2024 | 1748/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
1141 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of Augmentation of JITPUR ZONE-I & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000702/2022-2023 | 124/MURD | 16/01/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 488.01 | 0 | 15
1142 | Murshidabad Division | Berhampur M/E Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1143 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
1144 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000186/2023-2024 | 1210/MURD/10 | 02/05/2023 | 0 | Resource Division | 2.76 | 0 | 0
1145 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000391/2023-2024 | 526/MURD/01 | 19/02/2024 | 0 | Resource Division | 9.83 | 0 | 0
1146 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II,III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE II) Water Supply Scheme at Head Work Site, 2nd & 3rd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000105/2023-2024 | 1747/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 0 | 100
1147 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of JITPUR (Zone-II) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000796/2022-2023 | 603/MURD | 02/03/2023 | 1036 | M/S.TAPAS KUMAR CHAKRABORTY | 752.45 | 0 | 40
1148 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000182/2023-2024 | 1180/MURD/20 | 30/04/2023 | 0 | Resource Division | 30.1 | 0 | 0
1149 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000392/2023-2024 | 526/MURD/02 | 19/02/2024 | 0 | Resource Division | 6.83 | 0 | 0
1150 | Murshidabad Division | Jangipur Sub-Division | Renovation of Existing AIRP (Capacity 11 Cu.M) for changing of filter media of 1 No Polishing unit (2.17 M dia x 1.50 M HOS) & 1 No Primary Unit ( 2.17 M dia x 2.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000807/2023-2024 | 616/MURD | 28/02/2024 | 30 | M/S BAPPA ENTERPRISE | 13.7 | 0 | 0
1151 | Murshidabad Division | Jangipur Sub-Division | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 11 Cu.M/hr) at Dakhin Sekhalipur W/S Scheme in connection with Augmentation of Dakhin Sekhalipur PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000833/2023-2024 | 783/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 7.56 | 0 | 0
1152 | Murshidabad Division | Jangipur Sub-Division | Providing Functional Household Tap Connections (FHTC) with laying of Pipeline for last mile connectivity in village Dakshin Sekhalipur (314102) & Paschim Khandua(314103) Village in connection with Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/000891/2022-2023 | 914/MURD | 30/03/2023 | 120 | PROSENJIT DAS | 72.6 | 0 | 85
1153 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
1154 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 6 | RTOR000112/2023-2024 | 1167/MURD/5 | 28/04/2023 | 0 | Resource Division | 0.33 | 0 | 0
1155 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of CHANDPUR Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000521/2022-2023 | 2496/MURD | 30/08/2022 | 945 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 388.72 | 0 | 80
1156 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 0 | 1
1157 | Murshidabad Division | Berhampur Sub-Division | Repair and Renovation of Pump high lift pupm house at head works site of Chandpur water supply scheme under Berhampore Sub Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001676/2021-2022 | 13/BSD | 10/01/2022 | 30 | MASUM CONSTRUCTION | 3.55 | 0 | 0
1158 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000005/2024-2025 | 1811/MURD/04 | 20/06/2024 | 0 | Resource Division | 21.13 | 0 | 0
1159 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000303/2023-2024 | 1278/MURD/5 | 10/05/2023 | 0 | Resource Division | 11.58 | 0 | 0
1160 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000355/2023-2024 | 305/MURD/04 | 29/01/2024 | 0 | Resource Division | 10.27 | 0 | 0
1161 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Selamatipur PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | ORD/000834/2021-2022 | 3267/MURD | 05/10/2021 | 60 | RADIANT | 3.23 | 0 | 0
1162 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | RTOR000003/2024-2025 | 1811/MURD/02 | 20/06/2024 | 0 | Resource Division | 16.77 | 0 | 0
1163 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR ENGINEER_BERHAMPORE BLOCK | RTOR000301/2023-2024 | 1278/MURD/2 | 10/05/2023 | 0 | Resource Division | 10.58 | 0 | 0
1164 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000343/2022-2023 | 1875/MURD | 15/07/2022 | 1165 | DOBAY CONSTRUCTION | 250.61 | 0 | 40
1165 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-I Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000584/2022-2023 | 3053/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 1
1166 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000028/2024-2025 | MURD/2481/01 | 04/09/2024 | 0 | Resource Division | 13.39 | 0 | 0
1167 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000036/2022-2023 | 2780/E/MURD | 01/10/2022 | 0 | Resource Division | 13.39 | 0 | 0
1168 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000173/2023-2024 | 1180/MURD/16 | 29/04/2023 | 0 | Resource Division | 235.38 | 0 | 0
1169 | Murshidabad Division | Berhampur M/E Division | Construction of 200 Cum OHR, Pump House at Head Work Site Laying Distribution System, Rising Main Connection, FHTC Connection, for Augmentation of Ramakantapur PWSS in Suti-I Block, under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000087/2025-2026 | 2374/MURD | 19/11/2025 | 365 | MOTI RAHAMAN | 278.11 | 0 | 0
1170 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
1171 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (RAMAKANTAPUR PWSS Scheme,Block- SUTI-I to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/002049/2021-2022 | 3253/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.1 | 0 | 1
1172 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000204/2023-2024 | 1210/MURD/03 | 02/05/2023 | 0 | Resource Division | 60.48 | 0 | 0
1173 | Murshidabad Division | Berhampur M/E Division | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/001225/2021-2022 | 413/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 4.88 | 0 | 0
1174 | Murshidabad Division |  | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 18/01/2024 to 15/07/2024. [ Vehicle No:- WB 58 BU 9284] |  |  | BILL/01159/2024-2025 | 430-MSD/2024-25 | 01/10/2024 | 0 | ABIDA CONSTRUCTION | 0.24 | 0 | 0
1175 | Murshidabad Division |  | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days |  |  | BILL/01536/2024-2025 | 569-MSD/2024-25 | 26/11/2024 | 0 | HAMIDUL ISLAM | 0.35 | 0 | 0
1176 | Murshidabad Division |  | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days |  |  | BILL/01537/2024-2025 | 569-MSD/2024-25 | 26/11/2024 | 0 | HAMIDUL ISLAM | 0.34 | 0 | 0
1177 | Murshidabad Division |  | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Dy Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year]. Period from i.e. 07/02/2024 to 05/02/2025 [Vehicle No.WB58AR/5026] |  |  | BILL/01572/2024-2025 | 575-MSD/2024-25 | 29/11/2024 | 0 | MD MUKLESUR RAHAMAN | 0.29 | 0 | 0
1178 | Murshidabad Division |  | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/07/2024 to 16/01/2025. [ Vehicle No:- WB 58 CD 3758] |  |  | BILL/01678/2024-2025 | 577-MSD/2024-25 | 29/11/2024 | 0 | HASSAN CONSTRUCTION | 0.4 | 0 | 0
1179 | Murshidabad Division |  | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte.for 06 (Six) Months i.e. from 08.07.2024 to 07.01.2025. |  |  | ORD/000034/2024-2025 | 54/LSD | 02/07/2024 | 184 | BARI ENTERPRISE | 0.89 | 0 | 0
1180 | Murshidabad Division |  | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 16/07/2024 to 11/01/2025. [ Vehicle No:- WB 58 BU 9284] |  |  | ORD/000087/2024-2025 | 48/JSD | 15/07/2024 | 180 | ABIDA CONSTRUCTION | 0.88 | 0 | 0
1181 | Murshidabad Division |  | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 |  |  | ORD/000120/2024-2025 | 237/BSD | 05/08/2024 | 160 | ABIDA CONSTRUCTION | 0.93 | 0 | 0
1182 | Murshidabad Division |  | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 182 Days] w.e.f 01/11/2024 to 01/04/2025. Vehicle No [WB58CA/1034] |  |  | ORD/000165/2024-2025 | 390/MSD | 29/10/2024 | 182 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0 | 0
1183 | Murshidabad Division |  | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2024 to 30/04/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc as per order) |  |  | ORD/000166/2024-2025 | 2911/MURD | 29/10/2024 | 182 | M/S JOY MA BANAMALI | 1.05 | 0 | 100
1184 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (323 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Tegharia ( Village Code -315683) under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000625/2023-2024 | 3563/MURD | 21/11/2023 | 30 | ARJU CONSTRUCTION | 11.66 | 0 | 0
1185 | Murshidabad Division |  | Hiring of one no. Mahindra & Mahindra make Bolero Diesel Passenger car for official use of the Assistant Engineer, Berhampore Sub-Division, P.H.Engineering Dte. for 06 (six) Months. (Period from 01/01/2024 to 30/06/2024) |  |  | ORD/000757/2023-2024 | 128/BSD | 28/12/2023 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 0 | 0
1186 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1187 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1188 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000069/2022-2023 | 174/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 0
1189 | Murshidabad Division | Berhampur Sub-Division | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000070/2022-2023 | 175/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.84 | 0 | 0
1190 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000071/2022-2023 | 176/BSD | 12/04/2022 | 15 | M/S LOKNATH CONSTRUCTION | 4.85 | 0 | 0
1191 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000134/2022-2023 | 1232/MURD | 11/05/2022 | 60 | PRADIP KUMAR DAS | 78.92 | 0 | 0
1192 | Murshidabad Division | Berhampur Sub-Division | Balanced work of Boundary wall and R.B.T fencing work at Gangadhari Water Supply Scheme under Berhampore Sub Division,Murshidabad Division P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001592/2021-2022 | 27/BSD | 14/01/2022 | 30 | MAA DURGA ENTERPRISE | 4.46 | 0 | 0
1193 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000021/2021-2022 | 539/6/MURD | 25/02/2022 | 0 | Resource Division | 9.82 | 0 | 0
1194 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1195 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1196 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1329 nos in connection with Jal Swapna (Jal Jeevan Mission ) & Laying of Distribution system of Selamatpur ( Village Code -315421) under Selamatpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000047/2022-2023 | 1058/MURD | 25/04/2022 | 60 | M/S. S. DAS AND ENTERPRISE | 94.54 | 0 | 90
1197 | Murshidabad Division | Kandi Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000056/2022-2023 | 161/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.84 | 0 | 0
1198 | Murshidabad Division | Kandi Sub-Division | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000059/2022-2023 | 164/BSD | 12/04/2022 | 15 | M/S SUKESH GHOSH | 4.84 | 0 | 0
1199 | Murshidabad Division | Kandi Sub-Division | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000060/2022-2023 | 165/BSD | 12/04/2022 | 15 | AMIT KUMAR SAHA | 4.85 | 0 | 0
1200 | Murshidabad Division | Kandi Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000061/2022-2023 | 166/BSD | 12/04/2022 | 15 | M/S LOKENATH CONSTRUCTION | 4.83 | 0 | 0
1201 | Murshidabad Division | Kandi Sub-Division | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000062/2022-2023 | 167/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.84 | 0 | 0
1202 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 35nos FHTC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000167/2022-2023 | 156/BSD | 12/04/2022 | 30 | ALOK BANERJEE ENTERPRISE | 4.84 | 0 | 0
1203 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) of Ground Based piped water supply scheme under Berhampore Sub-Division, Murshidabad Division, PHE Dte. For 35 nos FHTC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | ORD/000545/2022-2023 | 156/BSD | 12/04/2022 | 30 | ALOK BANERJEE ENTERPRISE | 4.84 | 0 | 100
1204 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | RTOR000018/2021-2022 | 539/3/MURD | 25/02/2022 | 0 | Resource Division | 7.3 | 0 | 0
1205 | Murshidabad Division | Kandi Sub-Division | Laying of 110mm dia upvc ppeline FHTC .......................SELAMATPUR UNDER SELAMATPUR W/S SCHEME. TENDER NO 210 -21-22 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1,JUNIOR ENGINEER ESTIMATING SECTION | VCH/000313/2022-2023 | 179-MSD/22-23 | 26/05/2022 | 0 | M/S LOKNATH CONSTRUCTION | 4.83 | 0 | 0
1206 | Murshidabad Division | Berhampur Sub-Division |  | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00025/2023-2024 | 48-MSD/2023-24 | 11/05/2023 | 0 | BURIMA TELECOM SYSTEM | 0.39 | 0 | 0
1207 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sungai (Village code 315363 under Sungai Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723237 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001467/2021-2022 | 278/MURD | 03/02/2022 | 60 | MAHATO ENTERPRISE | 9.29 | 0 | 0
1208 | Murshidabad Division | Berhampur Sub-Division | Physical site visit to check the okd RC overhead water tank at satitara and Gokarna at Kandi under MSD PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00153/2023-2024 | 31-MSD/2023-24 | 05/05/2023 | 0 | SRCC NIT DURGAPUR | 1.18 | 0 | 0
1209 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1210 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1211 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kumarpur (Village code 315597) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 000958825 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000034/2020-2021 | 541/MURD | 05/02/2021 | 180 | DECON INDIA | 56.35 | 0 | 1
1212 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barua (P) (Village code 315619) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.Scheme ID 000958825 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000182/2020-2021 | 3135/MURD | 11/12/2020 | 60 | AMAL KUMAR DAS | 41.32 | 0 | 1
1213 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jalalpur (Village code 315595) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 000958825 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000360/2021-2022 | 2535/MURD | 19/08/2021 | 60 | M/S. BIMALENDU BOSE | 19.82 | 0 | 0
1214 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahyampur (Village code 315612) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.(Sl No-02) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000423/2021-2022 | 2538/MURD | 19/08/2021 | 180 | TEKNO ENTERPRISE | 216.16 | 0 | 1
1215 | Murshidabad Division | Berhampur Sub-Division | Name of Work:- Hiring of Maxi cab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 01 (One) year. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000559/2022-2023 | 291/LSD | 08/07/2022 | 365 | BARI ENTERPRISE | 1.78 | 0 | 40
1216 | Murshidabad Division | Berhampur Sub-Division | Repairing of Rising main pipe line and allied works along the Rising main pipe line at western side of Beldanga C.R.G.S School , Diamond Nursing home, Beside Beldanga Rural Hospital and Panchraha More connection with FHTC work in the village Madda( Village Code-315603) Under Beldanga Municipality Water Supply scheme under Berhampore Sub Division P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000574/2022-2023 | 2942/MURD | 03/11/2022 | 20 | PRADIP DAS | 3.05 | 0 | 0
1217 | Murshidabad Division | Berhampur Sub-Division | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000623/2022-2023 | 205/JSD | 18/04/2022 | 365 | MAJIBUR RAHAMAN | 4.76 | 0 | 0
1218 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line and connection with street stand post and Construction of soat well in connection with Dengue control for different Health Sub Centre (1) Miezapur Mid section Sc 2) Mirzapur Sitalpara Sc.3) Mahyampur SC.4) Notunpara RCH SC under Berhampore Sub division. P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000736/2020-2021 | 269/BSD | 13/10/2020 | 15 | PRADIP MAHATO | 1.97 | 0 | 1
1219 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission under command area of village of Jalalpur (Village Code -315595) Part-B under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. In the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000736/2022-2023 | 260/BSD | 31/05/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.36 | 0 | 0
1220 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kumarpur (Village Code -315597) Part B under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000737/2022-2023 | 262/BSD | 31/05/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.14 | 0 | 0
1221 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kumarpur (Village Code -315597) Part C under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000741/2022-2023 | 268/BSD | 24/06/2022 | 30 | BIJOY KUMAR SANYAL | 4.14 | 0 | 0
1222 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-E under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000747/2022-2023 | 275/BSD | 24/06/2022 | 30 | MASTER CONSTRUCTION | 4.72 | 0 | 100
1223 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-C under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000751/2022-2023 | 276/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.68 | 0 | 100
1224 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-A under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000752/2022-2023 | 277/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.67 | 0 | 100
1225 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-D under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000753/2022-2023 | 278/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.67 | 0 | 100
1226 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) PART-B under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000754/2022-2023 | 279/BSD | 30/06/2022 | 30 | NAYLA CONSTRUCTION | 4.72 | 0 | 100
1227 | Murshidabad Division | Berhampur Sub-Division | Further to Hiring of one no. Mahindra & Mahindra make Bolero Diesel passenger car for official use of the Assistant Engineer, Berhampore Sub-Division,P. H. Engineering Dte. for 06(Six) Months. (Period from 01.07.2022 to 31.12.2022) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000760/2022-2023 | 283/BSD | 24/06/2022 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 0 | 0
1228 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Barua (p) (Village Code -315619) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000762/2022-2023 | 284/BSD | 24/06/2022 | 30 | MD. MASUD SK. | 4.43 | 0 | 100
1229 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mirzapur(Village code 315615) under Mahyampur Surface Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. (Scheme ID 000958825) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000853/2021-2022 | 3328/MURD | 07/10/2021 | 180 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 225.77 | 0 | 0
1230 | Murshidabad Division | Berhampur Sub-Division | Hiring of 01 (One) no . Diesel Bolero /Marshal Car for official use having for contract carriage permit from the Reginal Transport Authority for the office of the Assistant Engineer , Islampur Sub-Division, P.HE Dte, Murshidabad for the period from 01/10/2022 to 31/03/2023 (i.e six months). (Vechicle No. W.B-57E-9142) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000895/2022-2023 | 415/ISD | 29/09/2022 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 0
1231 | Murshidabad Division | Berhampur Sub-Division | Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months (120 days) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000896/2022-2023 | 164/ISD | 31/03/2023 | 183 | HAMIDUL ISLAM | 0.69 | 0 | 100
1232 | Murshidabad Division | Berhampur Sub-Division | Further to Hiring of one no. Mahindra & Mahindra make Bolero Diesel passenger car for official use of the Assistant Engineer, Berhampore Sub-Division,P. H. Engineering Dte. for 06(Six) Months. (Period from 01.01.2023 to 30.06.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000931/2022-2023 | 291/BSD | 16/12/2022 | 182 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 0 | 100
1233 | Murshidabad Division | Berhampur Sub-Division | Construction of approach road with Cement Concrete for Head works site of Loknathpur Zone-II Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000965/2022-2023 | 259/BSD | 31/05/2022 | 30 | MONDAL CONSTRUCTION | 2.33 | 0 | 100
1234 | Murshidabad Division | Berhampur Sub-Division | Repairing And Renovation of R.C.C. elevated reservoir (1.50 Lakh Gallon capacity) of staging hight 24.0 Mtr. At Mahyampur Water Supply under Berhampore Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001646/2021-2022 | 555/MURD | 28/02/2022 | 45 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 17.67 | 0 | 0
1235 | Murshidabad Division | Berhampur Sub-Division | Additional work of laying of distribution system pipe line for providing Funtional Household Tap connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Kumarpur (village code 315597) under Mahyampur surface Water Supply Scheme for Arsenic affected areas of Beldanga-I Block in Murshidabad Division PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001769/2021-2022 | 102/BSD | 28/03/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.68 | 0 | 0
1236 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of February 2022 to January 2023 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/002101/2021-2022 | 168/MURD | 24/01/2022 | 365 | HASNA BEWA | 4.8 | 0 | 0
1237 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village MIRZAPUR (Village Code 315615) under MAHYAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block under Murshidabad Div Phe DTE in the District of Murshidabad. Tender no - 65 of 21-22 by SE MC | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000012/2022-2023 | 05-MSD/22-23 | 20/04/2022 | 0 | S.ENTERPRISE | 78.9 | 0 | 0
1238 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of village Kumarpur (Villagae Code 315597) under MAHYAMPUR surface based water supply scheme for arsenic affected aread of Beldanga-I Block in the dist of MSD PHE DTE. Tender no 88 of 21-21 by SE MC | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000244/2021-2022 | 35-MSD / 21-22 | 27/08/2021 | 0 | DECON INDIA | 31.77 | 0 | 0
1239 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barua (P) (Village code 315619) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.Scheme ID 000958825 in the District of Murshidabad.3135/MURD, 11/12/2020 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/000669/2021-2022 | 173-MSD/21-22 | 01/11/2021 | 0 | AMAL KUMAR DAS | 21.03 | 0 | 0
1240 | Murshidabad Division | Berhampur Sub-Division | Supply of different dia Sluice Valve, CI Specials & Different dia jeffy coupling under LSD PHE DTE. Tender no - 27 of 21-22 by AE LSD | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001380/2021-2022 | 317-MSD/21-22 | 17/02/2022 | 0 | MADAN MOHAN SASMAL | 3.86 | 0 | 0
1241 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION)' from existing Distribution system within the Command area of village MAHYAMPUR (Village Code 315612) under MAHYAMPUR Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga-I Block in the District of Murshidabad. Tender no - 18 of 21-22 by SE MC | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/001517/2021-2022 | 425-MSD/21-22 | 31/03/2022 | 0 | TEKNO ENTERPRISE | 96.69 | 0 | 0
1242 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) of 1878 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Sarbangapur Partrly ( Village Code -315522) under Sarbangapur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000027/2022-2023 | 1057/MURD | 25/04/2022 | 60 | MAMATA USHA ENTERPRISE | 93.87 | 0 | 1
1243 | Murshidabad Division |  | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000075/2022-2023 | 180/BSD | 12/04/2022 | 15 | AMIT KUMAR SAHA | 4.83 | 0 | 1
1244 | Murshidabad Division |  | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000076/2022-2023 | 181/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.86 | 0 | 1
1245 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sonatikri (Village code 315528) under Sarbangapur Ground Water Based water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID 00051723279 in the District of Murshidabad. (Sl No-02) |  |  | ORD/000083/2020-2021 | 291/MURD | 27/01/2021 | 180 | M/S. S. DAS AND ENTERPRISE | 99.82 | 0 | 0
1246 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pareshnathpur (Village code 315529) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723279 in the District of Murshidabad. |  |  | ORD/000215/2020-2021 | 3239/MURD | 22/12/2020 | 60 | RATAN DUTTA | 33.87 | 4.72 | 0
1247 | Murshidabad Division |  | Additional work of providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sonatikuri (village code 315528) under Sarbangapur Zone-II Water Supply Scheme of Nowda Block in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000337/2021-2022 | 2436/MURD | 12/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 46.04 | 0 | 0
1248 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dudhsar (Village code 315521) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723279 in the District of Murshidabad. |  |  | ORD/000540/2020-2021 | 34/MURD | 05/01/2021 | 60 | CHATTERJEE ENTERPRISE | 19.26 | 0 | 1
1249 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/001731/2021-2022 | 78/BSD | 07/03/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 1
1250 | Murshidabad Division |  | Supplying and Laying of 160mm dia UPVC pipeline in connection providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/001733/2021-2022 | 79/BSD | 07/03/2022 | 15 | SWAPAN DAS | 4.85 | 0 | 1
1251 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000027/2021-2022 | 539/1/MURD | 25/02/2022 | 0 | Resource Division | 10.31 | 0 | 0
1252 | Murshidabad Division |  | Additional work of providing Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village of Sonatikri Village Code (315528) under SARBANGAPUR ZONE-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District under Murshidabad Division, PHE Dte. tender No - 343 of 21-22 by EE |  |  | VCH/000562/2021-2022 | 118-MSD/21-22 | 05/10/2021 | 0 | M/S. S. DAS AND ENTERPRISE | 46.02 | 0 | 0
1253 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission and jal swapna under command area of village of Sarbangapur under Sarbangapur Zone-I W/S Scheme un MSD PHE DTE. Tender No- 178 of 2021-2022 BY AE BSD |  |  | VCH/001554/2021-2022 | 449-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.83 | 0 | 0
1254 | Murshidabad Division |  | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission and jal swapna under command area of village of Sarbangapur under Sarbangapur Zone-I W/S Scheme un MSD PHE DTE. Tender No- 177 of 2021-2022 BY AE BSD |  |  | VCH/001555/2021-2022 | 449-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.85 | 0 | 0
1255 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 235 nos household under command area of village of Uttar Gopalpur, Molladanga, Arizpur, Purandanpur, Purushottampur, Bota,Durgapur ( Village Code-314744, 314745, 314746, 314747, 314753, 314754, 314756) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756484) |  |  | ORD/000129/2022-2023 | 1212/MURD | 10/05/2022 | 30 | BARMAN ENTERPRISE | 12.4 | 0 | 1
1256 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur( Village Code -314756) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar_I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) |  |  | ORD/000196/2021-2022 | 1747/MURD | 09/07/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.77 | 0 | 1
1257 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Purushottampur (Village code 314753) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 in the District of Murshidabad. (Sl No-04) |  |  | ORD/000351/2021-2022 | 2502/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 85.13 | 53.62 | 1
1258 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Molladanga (Village code 314745) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 |  |  | ORD/000411/2021-2022 | 2556/MURD | 23/08/2021 | 120 | M/S TRADE ASSOCIATE | 69.82 | 0 | 1
1259 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bota (Village code 314754) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. |  |  | ORD/000496/2020-2021 | 35/MURD | 05/01/2021 | 60 | SINGHA AND CO. | 14.46 | 0 | 1
1260 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arizpur (Village code 314746) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad.¿ |  |  | ORD/000565/2020-2021 | 36/MURD | 05/01/2021 | 60 | ARJU CONSTRUCTION | 5.82 | 0 | 1
1261 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. |  |  | ORD/000820/2020-2021 | 031/MURD | 05/01/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0
1262 | Murshidabad Division |  | Additional Works for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BOTA ( Village Code -314754) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) |  |  | ORD/001245/2021-2022 | 52/ISD | 28/01/2022 | 30 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.8 | 0 | 1
1263 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connections (FHTC) of 559 Nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Molladanga (Village code 314745) under Purusattampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 000175684). |  |  | ORD/001701/2021-2022 | 671/MURD | 10/03/2022 | 30 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 17.21 | 0 | 1
1264 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bota, 314754 of Purushottampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-I), TNO- 929/20-21/EE |  |  | VCH/000655/2021-2022 | 127-MSD/21-22 | 07/10/2021 | 0 | SINHA & COMPANY | 12.65 | 0 | 0
1265 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MOLLADANGA (Village Code 314745) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 17 of 21-22 by SE MC |  |  | VCH/001487/2021-2022 | 420-MSD/21-22 | 23/03/2022 | 0 | M/S TRADE ASSOCIATE | 46.29 | 0 | 0
1266 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DURGAPUR (Village Code 314756) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 291 of 20-21 by EE MURD |  |  | VCH/001510/2021-2022 | 405-MSD/21-22 | 23/03/2022 | 0 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 31.84 | 0 | 0
1267 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jhaubaria (Village Code -314585) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006086670) |  |  | ORD/000290/2021-2022 | 2297/MURD | 02/08/2021 | 60 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 97.86 | 43.69 | 1
1268 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Village Code -314589)(Katlamari & Ramnagarpara& adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000291/2021-2022 | 2298/MURD | 02/08/2021 | 60 | HIRANMAY GHOSH | 97.89 | 58.99 | 100
1269 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000437/2021-2022 | 2641/MURD | 27/08/2021 | 60 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 97.88 | 0 | 70
1270 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000448/2021-2022 | 298/BSD | 13/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 4.34 | 0
1271 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Babaltali ( Village Code -314583)( Nojorana&Panipia& adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000489/2021-2022 | 2680/MURD | 31/08/2021 | 60 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 97.62 | 0 | 0
1272 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari ( Village Code -314589) (Mohongonj &Kaharpara & adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/001714/2021-2022 | 716/MURD | 15/03/2022 | 60 | SOFIQUL ISLAM | 80.52 | 0 | 0
1273 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing Balance Functional Household Tap Connections (FHTC) of 1180 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria (Village code 314585) under Saikhpara Area Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670). |  |  | ORD/001716/2021-2022 | 703/MURD | 14/03/2022 | 15 | AZAD ENTERPRISE | 12.2 | 0 | 0
1274 | Murshidabad Division |  | Extension of Distribution UPVC pipeline and providing balance Functional Household Tap Connections (FHTC) of 633 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Villagecode-314589)(Katlamari, Ramnagarpara & adjoining habitation) under Seikhpara Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670) |  |  | ORD/001805/2021-2022 | 854/MURD | 31/03/2022 | 15 | HIRANMAY GHOSH | 8.27 | 0 | 100
1275 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BABALTALI (Village Code 314583) under (SAIKHPARA AND BABALTALI adjoining habitation SAIKHPARA Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 360 of 21-22 by EE MURD |  |  | VCH/001513/2021-2022 | 415-MSD/21-22 | 22/03/2022 | 0 | MITRA CONSTRUCTION | 45.89 | 0 | 0
1276 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | VCH/001530/2021-2022 | 438-MSD/21-22 | 30/03/2022 | 0 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 51.77 | 0 | 0
1277 | Murshidabad Division |  | Laying of parallel distribution pipe line in between node point 15F to 23A and extension of distribution pipe line left & right side of canal of Alugram village (Village Code-315806) of Bharatpur water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000005/2022-2023 | 07 / KSD | 06/04/2022 | 30 | AGNIBESH CHATTERJEE | 4.84 | 0 | 1
1278 | Murshidabad Division |  | Extension of UPVC pipeline for FHTC work at Daspara, Ghoshpara, Kurulpara, Anchalpara, Gobardhanpara and Bagdipara in the Village of Alugram of Bharatpur Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. |  |  | ORD/000009/2022-2023 | 11 / KSD | 06/04/2022 | 30 | M/S. RAHAMAN CONSTRUCTION CO | 4.84 | 0 | 0
1279 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Alugram under Bharatpur Ground Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0007336059 in the District of Murshidabad. (Sl No-18) |  |  | ORD/000288/2020-2021 | 3270/MURD | 24/12/2020 | 180 | M/S . SUKUMAR SINHA | 109.97 | 20.53 | 100
1280 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at ALUGRAM G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000466/2021-2022 | 234/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0
1281 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIJGRAM G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000472/2021-2022 | 240/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
1282 | Murshidabad Division |  | Repairing of rising main pipe line including supplying of C.I specials, valves, construction of valve chamber & surface drain for the FHTC work of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. (SL-04) |  |  | ORD/000520/2022-2023 | 157/KSD | 31/08/2022 | 30 | PRANAB KUMAR GHOSH | 4.77 | 0 | 0
1283 | Murshidabad Division |  | Holding Awarness Programme / Campaigning programms at Alugram G.P, Bharatpur G.P and Sijgram G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 12 nos) (Part-E). |  |  | ORD/000557/2021-2022 | 253/KSD | 31/08/2021 | 30 | S.S.INFRASTRUCTURE | 2.4 | 0 | 0
1284 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SUNIA (Village Code 315806) under Bharatpur Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-I Block in the District of Murshidabad. |  |  | ORD/000571/2020-2021 | 3037/MURD | 07/12/2020 | 45 | NAMDAR ALI | 8.6 | 0 | 1
1285 | Murshidabad Division |  | Supplying of C.I specials, valves & construction of valve chamber of different location for FHTC work of Alugram village of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. |  |  | ORD/000627/2022-2023 | 3182/MURD | 30/11/2022 | 20 | U.S BUILDERS | 4.97 | 0 | 100
1286 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Madanpur Dafarpur ( Village Code -315810) under BHARATPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007336059) |  |  | ORD/001718/2021-2022 | 731/MURD | 16/03/2022 | 45 | MOTI RAHAMAN | 40.35 | 0 | 45
1287 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 541/2/MURD | 25/02/2022 | 0 | Resource Division | 5.12 | 0 | 0
1288 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD |  |  | VCH/001466/2021-2022 | 366-MSD/21-22 | 11/03/2022 | 0 | NAMDAR ALI | 4.55 | 0 | 0
1289 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tungi ( Village Code -315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000058/2021-2022 | 1211/MURD | 10/05/2021 | 60 | MOTI RAHAMAN | 90.75 | 82.69 | 0
1290 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna ( Jal Jeevan Mission) and under command area of village of Chandpur (Village code 315552)under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000284/2022-2023 | 1561/MURD | 16/06/2022 | 1348 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 126.1 | 0 | 40
1291 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000359/2022-2023 | 2083/MURD | 27/07/2022 | 991 | TINA ROY | 355.12 | 0 | 85
1292 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000435/2021-2022 | 1699/MURD | 07/07/2021 | 60 | M/S JAN MOHAMMAD | 52.35 | 0 | 40
1293 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) village of Patikabari (Village Code-315550) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000522/2022-2023 | 2498/MURD | 30/08/2022 | 120 | M/S. SINHA & SONS | 183.88 | 0 | 0
1294 | Murshidabad Division | Berhampur Sub-Division | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001345/2021-2022 | 12/BSD | 10/01/2022 | 15 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0
1295 | Murshidabad Division | Berhampur Sub-Division | Providing 365 nos Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna within command area of village Tungi (Village code 315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186507 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001710/2021-2022 | 701/MURD | 14/03/2022 | 60 | MOTI RAHAMAN | 98.18 | 0 | 0
1296 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000022/2021-2022 | 539/7/MURD | 25/02/2022 | 0 | Resource Division | 1.46 | 0 | 0
1297 | Murshidabad Division | Berhampur Sub-Division | AND REFILLING OF FILTER MEDIA WITH ALLIED WORKS OF IEP OF CHANDPUR WSS, TNO- 143/21-22/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000042/2022-2023 | 38-MSD/22-23 | 21/04/2022 | 0 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0
1298 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. ( 55.0MTR.)_PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000752/2023-2024 | 131/MURD | 15/01/2024 | 30 | PAL CONSTRUCTION | 4.44 | 0 | 100
1299 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Sarbangapur Zone-IA PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Repairing of Boundary Wall, Repairing of 450 CUM OHR in Nawda Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000753/2023-2024 | 130/MURD | 15/01/2024 | 411 | NILKAMAL BASAK | 323.16 | 0 | 70
1300 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000159/2023-2024 | 1180/MURD/27 | 29/04/2023 | 0 | Resource Division | 97.75 | 0 | 0
1301 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
1302 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 240/8 & 240/9) at Ratanpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Bhasipaikar Zone - III ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000422/2021-2022 | 2479/MURD | 16/08/2021 | 60 | ACQUA CONSTRACTION CONSORTIAM | 22.97 | 0 | 90
1303 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
1304 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone-III Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000692/2023-2024 | 3767/MURD | 08/12/2023 | 480 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 50
1305 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000122/2023-2024 | 1167/MURD/30 | 28/04/2023 | 0 | Resource Division | 33.07 | 0 | 0
1306 | Murshidabad Division | Berhampur M/E Division | Augmentation of KUPILA PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000077/2023-2024 | 1380/MURD | 22/05/2023 | 1044 | S.S. ENTERPRISE | 413.75 | 0 | 30
1307 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000107/2023-2024 | 1749/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 0 | 40
1308 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 20
1309 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000346/2022-2023 | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 0 | 100
1310 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000695/2023-2024 | 3768/MURD | 08/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 100
1311 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000149/2023-2024 | 1167/MURD/38 | 28/04/2023 | 0 | Resource Division | 5.48 | 0 | 0
1312 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000395/2023-2024 | 526/MURD/08 | 19/02/2024 | 0 | Resource Division | 2.46 | 0 | 0
1313 | Murshidabad Division | Lalbag Sub-Division | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000090/2025-2026 | 1829/MURD | 18/08/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0
1314 | Murshidabad Division | Lalbag Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000135/2024-2025 | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 40
1315 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 0 | 100
1316 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
1317 | Murshidabad Division | Lalbag Sub-Division | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000623/2023-2024 | 3372/MURD | 31/10/2023 | 270 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0
1318 | Murshidabad Division | Lalbag Sub-Division | Augmentation of BHANDARA (ZONE - II B) PWSS under Jal Jeevan Mission of Bhagawangola-I Block, Lalbagh Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000853/2023-2024 | 829/MURD | 15/03/2024 | 300 | CHAKRABORTY CONSTRUCTION | 407.22 | 0 | 0
1319 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
1320 | Murshidabad Division | Kandi Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 181 Days] w.e.f 02/04/2025 to 30/09/2025. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000515/2024-2025 | 607/MSD | 28/03/2025 | 181 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0 | 0
1321 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE - II B) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000759/2023-2024 | 184/MURD | 18/01/2024 | 714 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 415.23 | 0 | 43
1322 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
1323 | Murshidabad Division | Berhampur M/E Division | Balance work for Repair & Renovation of Existing AIRP (Modified Sujapur Sadhipur Model) of (Capacity 72 Cu.M/hr) at Harua Water Supply Scheme at Suti-I Block, of Jangipur Sub-Division under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000067/2025-2026 | 1243/MURD | 29/05/2025 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 27.06 | 0 | 0
1324 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
1325 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Harua Part A Piped Water Supply Scheme to accommodate with Laying of Rising Main , Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000144/2023-2024 | 1868/MURD | 14/07/2023 | 902 | PAL CONSTRUCTION | 31 | 0 | 28
1326 | Murshidabad Division | Berhampur M/E Division | Refilling of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 72.00Cum/hr.) at Harua Water Supply Scheme under Jal Jivan Mission of Suti-I Block under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000822/2023-2024 | 743/MURD | 12/03/2024 | 535 | SUMAN ENTERPRISE AND SUMAN AQUA | 63.59 | 0 | 50
1327 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000223/2023-2024 | 1219/MURD/22 | 03/05/2023 | 0 | Resource Division | 20.71 | 0 | 0
1328 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KUSUMGACHI Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000023/2025-2026 | 982/MURD | 02/05/2025 | 60 | M/S SAJAHAN CHOWDHURY | 22.96 | 0 | 0
1329 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone- I A & Kusumgachi Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000137/2023-2024 | 1772/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 27.67 | 0 | 100
1330 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
1331 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 800 nos household, Laying of Rising Main, Laying of Distribution System, Overhauling of RCC 180 Cum OHR, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works, Construction of Boundary Wall, Repair of Boundary Wall & Construction of RCC approach road for Augmentation of KUSUMGACHI Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000880/2022-2023 | 904/MURD | 29/03/2023 | 881 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 174.93 | 0 | 50
1332 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000199/2023-2024 | 1210/MURD/05 | 02/05/2023 | 0 | Resource Division | 50.19 | 0 | 0
1333 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1334 | Murshidabad Division | Berhampur M/E Division | Augmentation of JUGINDA (Zone - I) Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000377/2023-2024 | 2772/MURD | 01/09/2023 | 180 | PRADIP KUMAR DAS (PROPRIETORSHIP) | 600.58 | 0 | 0
1335 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000206/2023-2024 | 1210/MURD/22 | 02/05/2023 | 0 | Resource Division | 133.91 | 0 | 0
1336 | Murshidabad Division | Jangipur Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1337 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
1338 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 35
1339 | Murshidabad Division | Jangipur Sub-Division | Allied works for Laying of U.P.V.C Pipeline of 160 mm,125 mm & 90 mm dia at Head work site of Arjunpur Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000742/2023-2024 | 50/MURD | 05/01/2024 | 30 | SK CONSTRUCTION (NAJIR SK.) | 5.71 | 0 | 100
1340 | Murshidabad Division | Jangipur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1341 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000139/2023-2024 | 1167/MURD/41 | 28/04/2023 | 0 | Resource Division | 25.97 | 0 | 0
1342 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System and FHTC at Bara Biadyapur Village (Village Code-315733), Tenya Village (Village-315737), Ghoshpara Village ( Village Code- 315735), Kechunia Village (Village Code-315722), Korgram Village (Village Code- 315736) & Nowapara Village (Village Code-315734) & Repairing of Over Head Reservoir (350 Cum), Pump House & Boundary wall for Augmentation of TENYA Zone-II PWSS in BHARATPUR-II Block , under Murshidabad Division,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000041/2023-2024 | 1139/MURD | 26/04/2023 | 1122 | TANUSHREE ENTERPRISE | 172.7 | 0 | 20
1343 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.06.2025 to 30.09.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000094/2025-2026 | 83/KSD | 21/05/2025 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1344 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000109/2023-2024 | 1751/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 27.64 | 0 | 50
1345 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.10.2025 to 31.01.2026) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000263/2025-2026 | 121/KSD | 08/09/2025 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1346 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 28.09.2024 to 31.01.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000371/2024-2025 | 141/KSD | 26/09/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1347 | Murshidabad Division | Kandi Sub-Division | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 95
1348 | Murshidabad Division | Kandi Sub-Division | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2025 to 31.05.2025) VEHICLE NO - WB 57E 5422 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000389/2024-2025 | 25/KSD | 24/01/2025 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
1349 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1350 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1351 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000001/2023-2024 | 969 | 06/04/2023 | 0 | Resource Division | 28.48 | 0 | 0
1352 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000004/2023-2024 | 1004/MURD | 11/04/2023 | 0 | Resource Division | 28.48 | 0 | 0
1353 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-I Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000022/2025-2026 | 983/MURD | 02/05/2025 | 60 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 19.61 | 0 | 0
1354 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
1355 | Murshidabad Division | Berhampur M/E Division | Allied work for Laying of UPVC pipeline, Construction of Culvert and Approach road for PROSADPUR (ZONE-I) Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000194/2024-2025 | 3213/MURD | 09/12/2024 | 30 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 36.51 | 0 | 0
1356 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 225/3 & 225/4) at Khanpur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000425/2021-2022 | 2482/MURD | 16/08/2021 | 60 | DECON INDIA | 20.38 | 0 | 100
1357 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System (Part-A) & FHTC work at Khanpur, Bhairabpur, Khidirpur, Parulia village of PROSADPUR (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000731/2023-2024 | 18/MURD | 03/01/2024 | 729 | BISWAS ENTERPRISE (PROP. SAMIUL ISLAM)) | 84.13 | 0 | 41
1358 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 1034 no household, Laying Distribution System, Vertical extension of Boundary wall and repairing Pump House and Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Prosadpur (Zone-I) PWSS under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000886/2022-2023 | 905/MURD | 29/03/2023 | 887 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 139.2 | 0 | 50
1359 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000202/2023-2024 | 1210/MURD/28 | 02/05/2023 | 0 | Resource Division | 1.51 | 0 | 0
1360 | Murshidabad Division | Kandi Sub-Division | Allied work for Construction of Pump House at Head Works Site &2nd T.W. Site,FHTC, Boundary Wall,Rising Main Connection, Laying Distribution System for Bathur PWSS in Khargram Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000038/2024-2025 | 1929/MURD | 03/07/2024 | 272 | NOVELTY CONSTRUCTION | 43.95 | 0 | 10
1361 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bathur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000040/2023-2024 | 1100/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 0 | 100
1362 | Murshidabad Division | Kandi Sub-Division | Formal work order for construction of Pump House at Head Work Site & 2nd Tube well site ,FHTC, Boundwary Wall, Rising Main Connection, Laying Distribution System for BATHUR PWSS in Khargram Block under Murshidabad Division ,PHE.Dte [ (i)Amount for LDS , R. Main, FHTC : Rs. 73,83,365.00 &(ii) Amount for Pump House, B.Wall : Rs. 35,86,277.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000793/2022-2023 | 593/MURD | 01/03/2023 | 615 | NOVELTY CONSTRUCTION | 109.53 | 0 | 37
1363 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000333/2023-2024 | 79 | 09/01/2024 | 0 | Resource Division | 3.37 | 0 | 0
1364 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos. of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MUNIGARM AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000270/2023-2024 | 2588/MURD | 21/08/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 80
1365 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MUNIGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000715/2022-2023 | 106/MURD | 13/01/2023 | 931 | PRANAB KUMAR GHOSH | 279.43 | 0 | 30
1366 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000051/2023-2024 | 1067/MURD/7 | 18/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
1367 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000364/2023-2024 | MURD/439/13 | 08/02/2024 | 0 | Resource Division | 6.34 | 0 | 0
1368 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1369 | Murshidabad Division | Kandi Sub-Division | Balance work for laying of CI/DI pipe line including supporting structure at Gaysabad PWSS at Bharatpur - I Block under Kandi Sub-Division, Murshidabad Division, PHE Dte in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000009/2025-2026 | 888/MURD | 22/04/2025 | 344 | M/S BHUBAN DAS | 122.18 | 0 | 0
1370 | Murshidabad Division | Kandi Sub-Division | GAYSABAD (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000174/2023-2024 | 1992/MURD | 21/07/2023 | 954 | M/S BHUBAN DAS | 418.26 | 0 | 10
1371 | Murshidabad Division | Kandi Sub-Division | GAYSABAD (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000202/2023-2024 | 2059/MURD | 27/07/2023 | 644 | DHIRENDRANATH MONDAL | 438.55 | 0 | 5
1372 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000055/2023-2024 | 1067/MURD/11 | 18/04/2023 | 0 | Resource Division | 77.6 | 0 | 0
1373 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
1374 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Raturi Zone II Piped Water Supply Scheme to accommodate with FHTC (297 Nos), Laying of Rising Main , Laying of Distribution System , construction of 100 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000309/2023-2024 | 2699/MURD | 25/08/2023 | 560 | SAMBHU NATH ROY | 161.08 | 0 | 30
1375 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000226/2023-2024 | 1219/MURD/19 | 03/05/2023 | 0 | Resource Division | 15.13 | 0 | 0
1376 | Murshidabad Division |  | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 1000 Cu.M of staging height 20 Meter at Head Work site within BUZRAK FATEPUR (Zone XI) W/S Scheme, Block-Saghardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. |  |  | ORD/000068/2024-2025 | 2023/MURD | 11/07/2024 | 90 | BIJAY CHOWDHURY | 85.49 | 0 | 85
1377 | Murshidabad Division |  | Last mile connectivity and providing 6309 nos Functional House Hold Connection from Zone- XI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000175/2024-2025 | 3076/MURD | 26/11/2024 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 265.37 | 0 | 0
1378 | Murshidabad Division |  | Last mile connectivity and providing 6292 nos Funcational House Hold Connection from Zone- III of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000330/2023-2024 | 2687/MURD | 25/08/2023 | 120 | J.S. CONSTRUCTION | 348.56 | 0 | 0
1379 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000043/2023-2024 | 1004/MURD/18 | 17/04/2023 | 0 | Resource Division | 24.48 | 0 | 0
1380 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000116/2022-2023 | 1199/MURD | 10/05/2022 | 45 | NADIA TUBEWELLS | 16.6 | 0 | 100
1381 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Faridpur Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000418/2022-2023 | 2085/MURD | 27/07/2022 | 1040 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 477.83 | 0 | 75
1382 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000025/2022-2023 | 2507/G/MURD | 31/08/2022 | 0 | Resource Division | 26.31 | 0 | 0
1383 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000038/2024-2025 | MURD/2481/10 | 04/09/2024 | 0 | Resource Division | 15.32 | 0 | 0
1384 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000160/2023-2024 | 1180/MURD/08 | 29/04/2023 | 0 | Resource Division | 26.31 | 0 | 0
1385 | Murshidabad Division | Lalbag Sub-Division | Laying of 200 mm dia DI pipeline from Near Shop of Nazir Sk to Jain Temple More, Lalgola including supply of specials in connection with FHTC work of Village of Lalgola (Village Code 314224 ) under Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. (Part-A). | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000097/2022-2023 | 175/LSD | 06/05/2022 | 20 | MADAN MOHAN SASMAL | 2.32 | 0 | 0
1386 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilbarakpara (Village code 314225) under Lalgola Ground Water Based water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186640 in the District of Murshidabad. (Sl No-01) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000137/2020-2021 | 559/MURD | 08/02/2021 | 180 | AQUATHERM WATER TREATMENT PVT.LTD. | 255.81 | 0 | 0
1387 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
1388 | Murshidabad Division | Lalbag Sub-Division | Laying of 200 mm dia DI pipeline from Near Shop to Nazir Sk to Head Work Site Lalgola. including supply of specials in connection with FHTC work of Village of Lalgola (Village Code 314224 ) Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. (248.M) (Part-B) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000225/2022-2023 | 200/LSD | 11/05/2022 | 25 | SUGATA CHOWDHURY | 2.14 | 0 | 0
1389 | Murshidabad Division | Lalbag Sub-Division | Laying of different dia UPVC pipeline from M.N. Academy more to Rajgurupara in connection with"Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000249/2022-2023 | 221/LSD | 11/05/2022 | 30 | SUGATA CHOWDHURY | 4.06 | 0 | 0
1390 | Murshidabad Division | Lalbag Sub-Division | Restoration work by cement concrete (1:1.5:3) after laying of DI pipe in connection with FHTC work of Village of Lalgola (Village Code 314224 ) Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000250/2022-2023 | 222/LSD | 11/05/2022 | 30 | MADAN MOHAN SASMAL | 3.94 | 0 | 0
1391 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Krishnapur (314153) Habitation Madiapara of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- C. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000255/2022-2023 | 227/LSD | 11/05/2022 | 30 | JYOTSNA PUTATUNDA | 4.93 | 0 | 0
1392 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Lalgola (314224) of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- E. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000256/2022-2023 | 228/LSD | 11/05/2022 | 30 | AEF ENTERPRISE | 4.84 | 0 | 0
1393 | Murshidabad Division | Lalbag Sub-Division | Laying of diffrent dia UPVC pipe line in connection with (FHTC) work at village Krishnapur (Village Code- 314153) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-A. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000259/2022-2023 | 231/LSD | 11/05/2022 | 30 | AEF ENTERPRISE | 4.99 | 0 | 0
1394 | Murshidabad Division | Lalbag Sub-Division | Laying of diffrent dia UPVC pipe line in connection with(FHTC) work at village Krishnapur (Village Code- 314153) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-B. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000260/2022-2023 | 232/LSD | 11/05/2022 | 30 | RIZZ ENTERPRISE | 4.56 | 0 | 0
1395 | Murshidabad Division | Lalbag Sub-Division | Laying of diffrent dia UPVC pipe line in connection with (FHTC) work at village Lalgola (Village Code- 314224) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-A. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000261/2022-2023 | 233/LSD | 11/05/2022 | 30 | M/S JOY MA BANAMALI | 4.99 | 0 | 0
1396 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Krishnapur (314153) Habitation Manic Chak of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- C. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000265/2022-2023 | 236/LSD | 11/05/2022 | 30 | M/S.S.S. ENTERPRISE | 4.89 | 0 | 0
1397 | Murshidabad Division | Lalbag Sub-Division | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Lalgola (314224) of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- B. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000270/2022-2023 | 241/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.98 | 0 | 0
1398 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000273/2020-2021 | 46/MURD | 06/01/2021 | 180 | BIJAY CHOWDHURY | 152 | 0 | 0
1399 | Murshidabad Division | Lalbag Sub-Division | Restoration of road for laying of different dia UPVC/CI/DI pipelines in connection with FHTC work from BDO Office More to M.N. Academy Ground area under Lalgola Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000352/2022-2023 | 294/LSD | 12/07/2022 | 30 | MADAN MOHAN SASMAL | 0.96 | 0 | 0
1400 | Murshidabad Division | Lalbag Sub-Division | Restoration of road for laying of different dia UPVC/CI/DI pipelines in connection with FHTC work from Jain Mandir to PHE OHR more via Rathbari more, Battala more & PWD (Roads) more under Lalgola Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000353/2022-2023 | 295/LSD | 12/07/2022 | 30 | SUGATA CHOWDHURY | 4.8 | 0 | 0
1401 | Murshidabad Division | Lalbag Sub-Division | Allied work for laying of 110 mm dia upvc pipeline at Minister para-area in connection with " Retrofitting providing FHTC in connection with JJM under command area of village of Lalgola (village code-314224) under Lalgola Ground Water Based Water Supply Scheme for arsenic affected areas of Lalgola Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000660/2023-2024 | 3545/MURD | 17/11/2023 | 30 | SUGATA CHOWDHURY | 2.18 | 0 | 70
1402 | Murshidabad Division | Lalbag Sub-Division | Allied work for Laying of different dia UPVC Pipeline at Radhabagh area in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilborakopra ( Village Code 314225) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. (Part-B). | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000303/2022-2023 | 112-MSD/22-23 | 06/05/2022 | 0 | SUGATA CHOWDHURY | 4.7 | 0 | 0
1403 | Murshidabad Division | Lalbag Sub-Division | Allied work for laying of different dia UPVC pipeline at radhabagh area in connection with Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBORAKOPRA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 59 of 21-22 by AE LSD | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000304/2022-2023 | 113-MSD/22-23 | 06/05/2022 | 0 | MADAN MOHAN SASMAL | 4.84 | 0 | 0
1404 | Murshidabad Division | Lalbag Sub-Division | Allied work for laying of different dia UPVC pipeline at radhabagh area in connection with Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBORAKOPRA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 57 of 21-22 by AE LSD | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000306/2022-2023 | 115-MSD/22-23 | 06/05/2022 | 0 | DEB SANKER BHATTACHARYA | 4.81 | 0 | 0
1405 | Murshidabad Division | Lalbag Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBARAKPARA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 106 of 20-21 by EE MURD | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000311/2022-2023 | 118-MSD/22-23 | 10/05/2022 | 0 | AQUATHERM WATER TREATMENT PVT.LTD. | 31.91 | 0 | 0
1406 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilbarakpara (Village code 314225) under Lalgola Ground Water Based water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186640 in the District of Murshidabad. (Sl No-01) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000436/2022-2023 | 168-MSD/22-23 | 17/05/2022 | 0 | AQUATHERM WATER TREATMENT PVT.LTD. | 90.43 | 0 | 0
1407 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000495/2022-2023 | 123-MSD/22-23 | 07/05/2022 | 0 | BIJAY CHOWDHURY | 37.56 | 0 | 0
1408 | Murshidabad Division | Lalbag Sub-Division | Laying of different dia UPVC Pipeline form Jain Mondir to Fish Market More & H/O of Kailash Vakat to Lalgola P.S. in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000532/2022-2023 | 189-MSD/22-23 | 29/06/2022 | 0 | MADAN MOHAN SASMAL | 2.98 | 0 | 0
1409 | Murshidabad Division | Lalbag Sub-Division | Laying of different dia UPVC Pipeline form H/O of Niaz Biswas to H/O of Moni Saha & H/O of Helal Maulabi to Fish Market More in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000533/2022-2023 | 190-MSD/22-23 | 29/06/2022 | 0 | SUGATA CHOWDHURY | 4.28 | 0 | 0
1410 | Murshidabad Division | Lalbag Sub-Division | Allied work for Laying of different dia UPVC Pipeline at Krishnapur area (Near Hospital) in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilborakopra ( Village Code 314225) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000673/2022-2023 | 214-MSD/22-23 | 20/07/2022 | 0 | PROSENJIT DAS | 4.7 | 0 | 0
1411 | Murshidabad Division | Lalbag Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | VCH/000772/2022-2023 | 266-MSD/22-23 | 26/08/2022 | 0 | BIJAY CHOWDHURY | 96.48 | 0 | 0
1412 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections ( 210 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Habaspur ( Village Code -314487) under Habaspur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhawangola-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000107/2024-2025 | 2212/MURD | 02/08/2024 | 272 | NOBEL CONSTRUCTION | 7.61 | 0 | 100
1413 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
1414 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 500 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kasiadanga Zone I & II PWSS in Raghunathganj II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000552/2023-2024 | 3190/MURD | 12/10/2023 | 365 | ASTRA | 861.48 | 0 | 0
1415 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000042/2024-2025 | MURD/2991/01 | 13/11/2024 | 0 | Resource Division | 41.24 | 0 | 0
1416 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000100/2023-2024 | 1167/MURD/7 | 28/04/2023 | 0 | Resource Division | 40.3 | 0 | 0
1417 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MARADIGHI (Village Code 315674) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. |  |  | ORD/000634/2020-2021 | 3008/MURD | 04/12/2020 | 45 | SUPIA CONSTRUCTION | 11.14 | 0 | 0
1418 | Murshidabad Division |  | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Pilkhna ( Village Code -315666) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. |  |  | ORD/000746/2022-2023 | 274/BSD | 24/06/2022 | 30 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 4.84 | 0 | 0
1419 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
1420 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pirojpur (Village code 314723) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. |  |  | ORD/000114/2022-2023 | 1197/MURD | 10/05/2022 | 30 | KESHAB CHANDRA DAS | 7.33 | 0 | 1
1421 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village MadhurKol (Village code 314724) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. |  |  | ORD/000498/2020-2021 | 88/MURD | 08/01/2021 | 60 | GOUTAM CHAKRABORTY | 44.07 | 0 | 1
1422 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pirojpur (Village code 314723) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. |  |  | ORD/000505/2020-2021 | 87/MURD | 08/01/2021 | 60 | GOUTAM CHAKRABORTY | 23.78 | 0 | 100
1423 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26) |  |  | ORD/000152/2020-2021 | 557/MURD | 08/02/2021 | 180 | MAMATA USHA ENTERPRISE | 144.81 | 46.83 | 0
1424 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), TNO-107/20-21/SE-MC |  |  | VCH/000308/2022-2023 | 116-MSD/22-23 | 06/05/2022 | 0 | MAMATA USHA ENTERPRISE | 42.57 | 0 | 0
1425 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), 557/MURD, 08/02/2021 |  |  | VCH/000778/2021-2022 | 186-MSD/21-22 | 12/11/2021 | 0 | MAMATA USHA ENTERPRISE | 35.48 | 0 | 0
1426 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1427 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
1428 | Murshidabad Division | Kandi Sub-Division | Allied work for Rising main connection to OHR & AIRP in connection with FHTC work of Village of JAGTAI(Village Code-313979) under JAGTAI Water Supply Scheme (Scheme ID- 0005184165) under Jangipur Sub Division,P.H.E. Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000089/2022-2023 | 235/JSD | 05/05/2022 | 30 | MAA CONSTRUCTION | 3.84 | 0 | 0
1429 | Murshidabad Division | Kandi Sub-Division | Allied work of laying of HDPE Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village JAGTAI (Village Code-313979)"( Bara Masjid Para) under command area of Jagtai Ground Water based Water supply scheme for Arsenic Affected Areas of Suti-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184165) in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000095/2022-2023 | 241/JSD | 05/05/2022 | 30 | MONDAL CONSTRUCTION | 4.77 | 0 | 0
1430 | Murshidabad Division | Kandi Sub-Division | Laying of HDPE pipeline and FHTC of 191 nos. household for retrofitting works in Jagtai Ground water-based w/s scheme for arsenic affected areas of Suti-II Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme ID- 0005184165) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000173/2023-2024 | 1935/MURD | 18/07/2023 | 30 | HOQUEDAR ALI | 41.12 | 0 | 100
1431 | Murshidabad Division | Kandi Sub-Division | EXTENSION OF PIPELINE AT AURANGABAD PHE SUB CENTRE & JAGTAI SUB CENTRE UNDER SUTI -II BLOCK | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000627/2019-2020 | 228/JSD | 15/01/2020 | 2192 | SUJIT CHOWDHURY | 1.97 | 0 | 100
1432 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna Jal Jeevan Mission and under command area of village of JAGTAI (Village code 313979) under JAGTAI Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184165 | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001184/2021-2022 | 4023/MURD | 24/12/2021 | 180 | HOQUEDAR ALI | 91.83 | 0 | 1
1433 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001332/2021-2022 | 51/JSD | 25/01/2022 | 30 | IMAGIN | 4.16 | 0 | 0
1434 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/001333/2021-2022 | 52/JSD | 25/01/2022 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
1435 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ghoramara (Village code 315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000386/2020-2021 | 3143/MURD | 11/12/2020 | 60 | M/S M.S. ENTERPRISE | 31.09 | 0 | 1
1436 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandabad (Village code 315517) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000550/2020-2021 | 3137/MURD | 11/12/2020 | 60 | M/S. CHOWDHURY CONSTRUCTION | 23.85 | 0 | 1
1437 | Murshidabad Division | Berhampur Sub-Division | Retrofiting of Function al Household Tap Connection FHTC and allied works in connection with Jal Swapna from existing distribution system within the command area of village fatepur under Ghoramara Ground W/S Scheme for arsenic affected areas of Berhampore Block in the Dist of MSD PHE DTE. Tender no 903 of 20+-21 by EE MSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000242/2021-2022 | 45-MSD / 21-22 | 31/08/2021 | 0 | M/S M.S. ENTERPRISE | 17.75 | 0 | 0
1438 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GHORAMARA (Village Code 315515) under GHORAMARA Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 903 of 20-21 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/001451/2021-2022 | 352-MSD/21-22 | 05/03/2022 | 0 | M/S M.S. ENTERPRISE | 11.41 | 0 | 0
1439 | Murshidabad Division | Berhampur Sub-Division | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/002012/2020-2021 | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 4.64 | 0 | 0
1440 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --PANCHTHUPI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- ACHHOAN, CODE-315979, TNO- 605/2020-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/002013/2020-2021 | 473/W | 08/03/2021 | 0 | LAXMI CONSTRUCTION | 6.24 | 0 | 0
1441 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- SAMANDI , CODE-315122, TNO- 573/2020-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/002014/2020-2021 | 473/W | 08/03/2021 | 0 | APURBA SAHA CHOWDHURY | 16.4 | 0 | 0
1442 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.06.2023 to 30.11.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000084/2023-2024 | 100/HQ | 30/05/2023 | 184 | DULAL CHOWDHURY | 0.91 | 0 | 100
1443 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of one no. Diesel Bolero/ Marshal/Ambassador car (WB57B-4454) for official use of the Assistant Engineer, Kandi Sub-Division, P.H.Engineering Dte. for 06(SIX) Months. (Period from 01.07.2023 to 31.12.2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000154/2023-2024 | 43/BSD | 23/06/2023 | 183 | SISIR KUMAR DE | 0.91 | 0 | 0
1444 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Loknathpur (Village code 315681) under Loknathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723426 (Sl No-35) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000295/2020-2021 | 960/MURD | 24/03/2021 | 180 | AJAY MONDAL | 68.75 | 0 | 1
1445 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ekdala (Village code 315682)under Lokenathpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723426 in the District of Murshidabad | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000493/2020-2021 | 3142/MURD | 11/12/2020 | 60 | NATIONAL ENTERPRISE | 29.41 | 0 | 1
1446 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ekdala ( Village Code -315682) under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000740/2022-2023 | 267/BSD | 24/06/2022 | 953 | NATIONAL ENTERPRISE (APU GHOSH) | 4.84 | 0 | 100
1447 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Loknathpur (Village Code -315681) Part-A under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000755/2022-2023 | 280/BSD | 24/06/2022 | 30 | MONDAL CONSTRUCTION | 4.59 | 0 | 0
1448 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Loknathpur (Village Code -315681) Part-B under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000756/2022-2023 | 281/BSD | 24/06/2022 | 30 | MONDAL CONSTRUCTION | 4.73 | 0 | 0
1449 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jainagar(Village code 315680) under Loknathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Bedanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723426 in the District of Murshidabad. (Sl No-36) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000849/2021-2022 | 3285/MURD | 05/10/2021 | 180 | M/S. BIMAL MISRA | 76.59 | 0 | 48
1450 | Murshidabad Division | Berhampur Sub-Division | Repair and renovation work of Boundary wall at Head Work of MahamadpurWater Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/001290/2021-2022 | 460/BSD | 15/12/2021 | 30 | ARINDAM MAJUMDAR | 4.74 | 0 | 100
1451 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilaspur Nachharerpara (Village code 314639) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 |  |  | ORD/000408/2021-2022 | 2537/MURD | 19/08/2021 | 180 | M/S. UNIQUE BUILDERS | 74.3 | 0 | 0
1452 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. |  |  | ORD/000731/2020-2021 | 3032/MURD | 07/12/2020 | 45 | DOBAY CONSTRUCTION | 20.91 | 0 | 100
1453 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) [Near house of Shiltu fro Rajak Talar More] under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001242/2021-2022 | 49/ISD | 28/01/2022 | 30 | M/S BHATTACHARJEE & CO | 4.85 | 0 | 0
1454 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) [Near house of Jobarma Nanda Primary School to Subeder More] under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001243/2021-2022 | 50/ISD | 28/01/2022 | 30 | M/S BIREN BHATTACHARYYA | 4.85 | 0 | 0
1455 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/001244/2021-2022 | 51/ISD | 28/01/2022 | 30 | ABA CONTRACTOR | 4.24 | 0 | 0
1456 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under BARABIL RAGHUNATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 127 of 21-22 by AE ISD |  |  | VCH/000299/2022-2023 | 109-MSD/22-23 | 06/05/2022 | 0 | M/S BIREN BHATTACHARYYA | 4.84 | 0 | 0
1457 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under BARABIL RAGHUNATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 126 of 21-22 by AE ISD |  |  | VCH/000300/2022-2023 | 110-MSD/22-23 | 11/05/2022 | 0 | M/S BHATTACHARJEE & CO | 4.84 | 0 | 0
1458 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
1459 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mamenpur (Village code 314732) under Mamenpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 000958860 (Sl No-13) |  |  | VCH/000022/2022-2023 | 22-MSD/22-23 | 14/04/2022 | 0 | M/S. BIMALENDU BOSE | 4.42 | 0 | 0
1460 | Murshidabad Division |  | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bhagirathpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 375 of 21-22 by EE MSD, and Scheme Code: 7678 |  |  | VCH/000036/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.73 | 0 | 0
1461 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) in Connection with Jal Jeevan Mission & Jal Swapna of village of Momenpur Village Code (314732) Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District. PHE DTE Tender no-117 of 20-21 by SE / MC |  |  | VCH/000191/2021-2022 |  | 13/07/2021 | 0 | M/S. BIMALENDU BOSE | 60.35 | 0 | 0
1462 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kanai (Village code 314674) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID ¿ 0001723374 in the District of Murshidabad. (Sl No-10) |  |  | ORD/000263/2020-2021 | 180/MURD | 19/01/2021 | 180 | UMWELT ENGINEER PVT LTD | 81.67 | 45.71 | 1
1463 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Par Raghunathpur (Village code 314677) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 in the District of Murshidabad. (Sl No-11) |  |  | ORD/000264/2020-2021 | 181/MURD | 19/01/2021 | 180 | UMWELT ENGINEER PVT LTD | 79.2 | 23.7 | 0
1464 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. |  |  | ORD/000820/2020-2021 | 031/MURD | 05/01/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0
1465 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Radhakantapur(Village code 314670) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 (Sl No-12) |  |  | ORD/000846/2021-2022 | 3286/MURD | 05/10/2021 | 180 | M/S M.S. ENTERPRISE | 51.18 | 0 | 1
1466 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of JITPUR (Village code 314669) under JITPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 |  |  | ORD/001192/2021-2022 | 4024/MURD | 24/12/2021 | 180 | SUJIT KUMAR SAHA | 119 | 0 | 1
1467 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 372 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Radhakantapur (Village code 314670) under Jitpur Ground water based water supply scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0001723374) |  |  | ORD/001735/2021-2022 | 704/MURD | 14/03/2022 | 20 | M/S M.S. ENTERPRISE | 14.28 | 0 | 1
1468 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 21/MURD | 05/01/2022 | 0 | Resource Division | 15.08 | 0 | 0
1469 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-17 |  |  | VCH/000874/2022-2023 | 361-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 35.91 | 0 | 0
1470 | Murshidabad Division |  | Continuation work order for Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/000092/2023-2024 | 1607/MURD | 09/06/2023 | 60 | PRADIP KUMAR DAS | 3.68 | 0 | 0
1471 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) of Mouja Bhabanipur (Village Code-313820), of Arjunpur &adjoining mouja under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005184170) |  |  | ORD/000374/2022-2023 | 2086/MURD | 27/07/2022 | 120 | DIPAYAN DEY | 88.99 | 0 | 0
1472 | Murshidabad Division |  | Replacement of media for Renovation of I.E Plant at Arjunpur W/S Scheme, of Jangipur Sub-Division under Murshidabad Division P.H.E.Dte. |  |  | ORD/000564/2022-2023 | 2941/MURD | 03/11/2022 | 20 | SUMAN ENTERPRISE AND SUMAN AQUA | 10.21 | 0 | 1
1473 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001654/2021-2022 | 508/MURD | 23/02/2022 | 60 | PRADIP KUMAR DAS | 36.8 | 0 | 0
1474 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/30 & 247/32) at Bhabanipur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001655/2021-2022 | 509/MURD | 23/02/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 37.5 | 0 | 0
1475 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-19 |  |  | VCH/000984/2022-2023 | 399-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.19 | 0 | 0
1476 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-24 |  |  | VCH/000986/2022-2023 | 399-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0
1477 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of AHIRON (Village code 313929) under AHIRON Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184152 |  |  | ORD/001130/2021-2022 | 3756/MURD | 01/12/2021 | 180 | DHIRENDRANATH MONDAL | 87.54 | 0 | 0
1478 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AHIRON (Village Code 313929) under AHIRON Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 116 of 21-22 by SE MC |  |  | VCH/001479/2021-2022 | 387-MSD/21-22 | 17/03/2022 | 0 | DHIRENDRANATH MONDAL | 87.54 | 0 | 0
1479 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000453/2021-2022 | 303/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 4.34 | 0
1480 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-II G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000507/2021-2022 | 342/BSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 0 | 1
1481 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad |  |  | ORD/000725/2020-2021 | 3122 / MURD | 09/12/2020 | 60 | TANUSHREE ENTERPRISE | 39.34 | 0 | 1
1482 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of SAKTIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- MAHATA, CODE-315638, TNO- 538/20-21/EE |  |  | VCH/002010/2020-2021 | 473/W | 08/03/2021 | 0 | SO-FINE AQUARIUM | 11.52 | 0 | 0
1483 | Murshidabad Division |  | LAYING OF UPVC PIPELINE AT JOYPUR PASCHIMPARA....BHALKUNDI Z-I WSS, TNO- 05/20-21/AEKSD |  |  | VCH/002011/2020-2021 | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 1.6 | 0 | 0
1484 | Murshidabad Division |  | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE |  |  | VCH/002012/2020-2021 | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 4.64 | 0 | 0
1485 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nishindra Para and adjoining habitations under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000076/2021-2022 | 1486/MURD | 21/06/2021 | 60 | PRIYANKA CONSTRUCTION | 27.85 | 0 | 1
1486 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Karbala and adjoining habitations under Mahadeb Nagar(CT)( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000080/2021-2022 | 1547/MURD | 23/06/2021 | 60 | MOLLA ENTERPRISE | 27.32 | 25.34 | 0
1487 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tarapur under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000083/2021-2022 | 1563/MURD | 24/06/2021 | 60 | SUMAN CHOWDHURY | 33.18 | 0 | 0
1488 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Pashim Jikri & Natun Momrajpur and adjoining habitations under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000160/2021-2022 | 1662/MURD | 02/07/2021 | 60 | MONDAL ENTERPRISE | 21.09 | 19.42 | 0
1489 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Gopalnagar and adjoining habitations under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000180/2021-2022 | 1710/MURD | 07/07/2021 | 60 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 28.28 | 0 | 1
1490 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jaladipur and adjoining habitations under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000184/2021-2022 | 1572/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 30.89 | 0 | 0
1491 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000203/2021-2022 | 1724/MURD | 08/07/2021 | 60 | NOVELTY CONSTRUCTION | 35.58 | 0 | 0
1492 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balidapukur under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000209/2021-2022 | 1746/MURD | 09/07/2021 | 60 | RAHAMAN CONSTRUCTION | 30.9 | 0 | 0
1493 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Maddham Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000248/2021-2022 | 1727/MURD | 08/07/2021 | 60 | A.S. CONSTRUCTION | 31.14 | 0 | 0
1494 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Uttar Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | ORD/000249/2021-2022 | 1726/MURD | 08/07/2021 | 60 | SARASWATI ENTERPRISE | 39.81 | 0 | 1
1495 | Murshidabad Division |  | Allied work of laying U.P.V.C pipe line for " Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village Nishindra Para & adjoining habitation under Mahadebnagar(CT) (Village code 313837) under Mahadebnagar Ground water Based water supply scheme for Arsenic Affected Area of Farakka Block under Murshidabad Division, P.H.E. Dte. Scheme ID-0001723329 in the District Murshidabad. |  |  | ORD/001270/2021-2022 | 389/JSD | 31/12/2021 | 30 | HERITAZE CONSTRUCTION | 4.67 | 0 | 0
1496 | Murshidabad Division |  | Allied work of laying UPVC Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village Mahadebnagar (CT) (Village Code-313837)" under command area of Mahadevnagar Zone-I Water supply scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723329) in the district of Murshidabad. (Part-I). |  |  | ORD/001754/2021-2022 | 122/JSD | 22/03/2022 | 30 | MOTI RAHAMAN | 4.99 | 0 | 0
1497 | Murshidabad Division |  | Allied work of laying UPVC Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village Mahadebnagar (CT) (Village Code-313837)" under command area of Mahadevnagar Zone-I Water supply scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723329) in the district of Murshidabad. (Part-II). |  |  | ORD/001755/2021-2022 | 123/JSD | 22/03/2022 | 30 | APU CONSTRUCTION | 4.98 | 0 | 0
1498 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nishindra Para and adjoining habitations under Mahadeb Nagar(CT) (Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) |  |  | VCH/000231/2021-2022 | 27-MSD / 21-22 | 18/08/2021 | 0 | PRIYANKA CONSTRUCTION | 25.58 | 0 | 0
1499 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-25 |  |  | VCH/000987/2022-2023 | 398-MSD/22-23 | 11/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 4.38 | 0 | 0
1500 | Murshidabad Division | Berhampur M/E Division | CHANDNI DAHA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main ,Construction of OHR of 300 cum capacity, Construction Pump House cum Chlorine Room (5.90m x 4.1m) & Pump House (4.10m x 3.5m) with sanitary and Water Supply Arrangement) & Construction of 190 m Boundary wall under Jal Jeevan Mission of Samserganj Block, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000447/2023-2024 | 2968/MURD | 20/09/2023 | 752 | M/S GOLAM KIBRIA | 431.64 | 0 | 12
1501 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
1502 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1503 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000227/2023-2024 | 1219/MURD/14 | 03/05/2023 | 0 | Resource Division | 19.83 | 0 | 0
1504 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bharatpur Zone- I A Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur -I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000118/2023-2024 | 1770/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 18.45 | 0 | 0
1505 | Murshidabad Division | Kandi Sub-Division | Augmentation of BHARATPUR (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 1 BLOCK | ORD/000204/2023-2024 | 2078/MURD | 31/07/2023 | 300 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 478.38 | 0 | 0
1506 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Rosora (P) Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000239/2023-2024 | 2417/MURD | 08/08/2023 | 967 | SUKUMAR ROY | 30.55 | 0 | 50
1507 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Rosora (P) Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000241/2023-2024 | 2423/MURD | 08/08/2023 | 60 | C. R. CONSTRUCTION | 30.55 | 0 | 0
1508 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0
1509 | Murshidabad Division | Kandi Sub-Division | Augmentation of DAKSHIN KHANDA ZONE - II PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000577/2023-2024 | 3301/MURD | 20/10/2023 | 300 | M/S GHOSH & CO. | 536.15 | 0 | 0
1510 | Murshidabad Division | Berhampur Sub-Division | Feasibility study to select a suitable location for proposed intake jetty for drawal of 23.00 MLD raw water from River Bhagirathi at Kumarpur, Beldanga-I Block. For surface water supply Scheme under Murshidabad Division in Murshidabad District. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | BILL/01075/2024-2025 | 380-MSD/2024-25 | 18/09/2024 | 0 | SYAMA PRASAD MOOKERJEE PORT, KOLKATA | 60.66 | 0 | 0
1511 | Murshidabad Division | Berhampur Sub-Division | Surveying, Sub Soil investigation , Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Pump House over M.S Intake barge (Floating), Bank Protection, Raw Water Rising Main, Construction of 22.1 MLD capacity Water Treatment Plant based on Conventional Technologies including Administrative Building, Substation Building ,Electro- Mechanical Works , Staff quarter & other components and SCADA on EPC turnkey basis in a single package as per detail scope of work / direction by E-I-C including 3 (Three) months Trial Run and Operation & Maintenance for 1(One) year for Surface Water Based piped W/S scheme in the uncovered areas of arsenic affected Beldanga-I Block in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | ORD/000030/2024-2025 | 1883/MURD | 28/06/2024 | 822 | GBC INFRASTRUCTURE PRIVATE LIMITED | 4480 | 0 | 0
1512 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 ESTIMATOR MSD DIVISION | RTOR000001/2024-2025 | MSD/1735 | 11/06/2024 | 0 | Resource Division | 6.55 | 0 | 0
1513 | Murshidabad Division | Kandi Sub-Division | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000873/2022-2023 | 882/MURD | 28/03/2023 | 280 | BANAMALI ENTERPRISES | 224.42 | 0 | 35
1514 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000067/2023-2024 | 1075/MURD/9 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1515 | Murshidabad Division | Kandi Sub-Division | BAIDYNATHPUR & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000222/2023-2024 | 2366/MURD | 04/08/2023 | 1001 | M/S.TAPAS KUMAR CHAKRABORTY | 867.57 | 0 | 10
1516 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000399/2023-2024 | 2806/MURD | 05/09/2023 | 589 | INDRAJIT MAZUMDAR | 27.64 | 0 | 100
1517 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000232/2023-2024 | 1219/MURD/16 | 03/05/2023 | 0 | Resource Division | 9.79 | 0 | 0
1518 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1519 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAPARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000621/2023-2024 | 3408/MURD | 02/11/2023 | 21 | TAPAN DAS | 9.28 | 0 | 100
1520 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000668/2022-2023 | 3409/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 0
1521 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of NAPARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | ORD/000735/2022-2023 | 376/MURD | 10/02/2023 | 902 | MANDAL CONSTRUCTION AND CO. | 241.91 | 0 | 45
1522 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | RTOR000268/2023-2024 | 1230/MURD/11 | 04/05/2023 | 0 | Resource Division | 22.61 | 0 | 0
1523 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II,JUNIOR ENGINEER_SAMSERGANJ BLOCK | RTOR000383/2023-2024 | 495/MURD/14 | 15/02/2024 | 0 | Resource Division | 5.03 | 0 | 0
1524 | Murshidabad Division | Kandi Sub-Division | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000098/2023-2024 | 1721/MURD | 04/07/2023 | 638 | M/S. S. DAS AND ENTERPRISE | 443.38 | 0 | 80
1525 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIDDHESWARI & ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000379/2023-2024 | 2776/MURD | 01/09/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 60
1526 | Murshidabad Division | Kandi Sub-Division | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000518/2023-2024 | 3116/MURD | 05/10/2023 | 300 | MOTI RAHAMAN | 407.86 | 0 | 10
1527 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000066/2023-2024 | 1075/MURD/7 | 19/04/2023 | 0 | Resource Division | 20.78 | 0 | 0
1528 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at TEGHARI ZONE - I, MAHESAIL ZONE-III & SERPUR (CT) Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000236/2023-2024 | 2407/MURD | 07/08/2023 | 552 | NADIA TUBEWELLS | 35.34 | 0 | 100
1529 | Murshidabad Division | Berhampur M/E Division | Augmentation Work of Mahesail Zone-III Piped Water Supply Scheme to accommodate with FHTC (1034 Nos), Laying of Rising Main , Laying of Distribution System , construction of 350 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000256/2023-2024 | 2466/MURD | 09/08/2023 | 754 | GHOSH ENTERPRISE | 337.02 | 0 | 60
1530 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000225/2023-2024 | 1219/MURD/07 | 03/05/2023 | 0 | Resource Division | 16.33 | 0 | 0
1531 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
1532 | Murshidabad Division | Berhampur M/E Division | Renovation of Existing AIRP (Capacity 16 Cu.M/hr) for changing of filter media of 1 no Polishing Unit (2.50 m dia x 1.5 m HOS) & 1 no Primary Unit (2.50 m dia x 2.00 m HOS) and painting all vessel, pipes etc. all complete at Birendranagar (Zone-I) W/S Scheme under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000808/2023-2024 | 617/MURD | 28/02/2024 | 30 | M/S BAPPA ENTERPRISE | 16.7 | 0 | 0
1533 | Murshidabad Division | Berhampur M/E Division | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 16 Cu.M/hr) at Birendranagar (Zone-I) W/S Scheme in connection with Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000832/2023-2024 | 782/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 10.09 | 0 | 0
1534 | Murshidabad Division | Berhampur M/E Division | Allied works In connection with Bypass line connection from AIRP to Distribution main at Birendranagar (Zone-I) Water Supply Scheme for the work of Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000838/2023-2024 | 821/MURD | 15/03/2024 | 30 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 3.27 | 0 | 100
1535 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System with FHTC to 752 nos household, Rising Main & OHR Repair of 90 cum capacity for Augmentation of Birendranagar (Zone-I) Pipe water supply scheme in Raghunathganj-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000865/2022-2023 | 830/MURD | 23/03/2023 | 1080 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 103.52 | 0 | 30
1536 | Murshidabad Division | Berhampur M/E Division | Work of Extension of Existing Boundary Wall and Painting of the same at Birendranagar (Zone-I) Water supply scheme , under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001275/2021-2022 | 392/JSD | 31/12/2021 | 30 | S. ROY & CO. | 4.79 | 0 | 0
1537 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000188/2023-2024 | 1210/MURD/21 | 02/05/2023 | 0 | Resource Division | 2.46 | 0 | 0
1538 | Murshidabad Division | Berhampur M/E Division | Augmentation of MURADPUR JALANGI ZONE-II PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000153/2023-2024 | 1901/MURD | 17/07/2023 | 180 | AZAD ENTERPRISE | 75.52 | 0 | 30
1539 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
1540 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000236/2023-2024 | 1219/MURD/27 | 03/05/2023 | 0 | Resource Division | 12.69 | 0 | 0
1541 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000399/2023-2024 | 2806/MURD | 05/09/2023 | 589 | INDRAJIT MAZUMDAR | 27.64 | 0 | 100
1542 | Murshidabad Division | Kandi Sub-Division | SANTOSHPUR PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000546/2023-2024 | 3179/MURD | 11/10/2023 | 553 | GARAI INFRA PROJECT | 260.08 | 0 | 45
1543 | Murshidabad Division | Kandi Sub-Division | SUNUTI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, BHARARPUR-I of Murshidabad District under Kandi sub division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000867/2022-2023 | 846/MURD | 24/03/2023 | 730 | M/S. BIMALENDU BOSE | 471.09 | 0 | 10
1544 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000057/2023-2024 | 1075/MURD/1 | 19/04/2023 | 0 | Resource Division | 19.17 | 0 | 0
1545 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of SERPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000716/2022-2023 | 78/MURD | 10/01/2023 | 1118 | RADIANT | 557.06 | 0 | 35
1546 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1547 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000048/2023-2024 | 1067/MURD/3 | 18/04/2023 | 0 | Resource Division | 25.58 | 0 | 0
1548 | Murshidabad Division | Kandi Sub-Division | Sahapur (Part-A) & adjoining mouzas PWSS to accommodate Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000143/2023-2024 | 1885/MURD | 17/07/2023 | 899 | HOQUEDAR ALI | 256.56 | 0 | 25
1549 | Murshidabad Division | Kandi Sub-Division | SAHAPUR (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000147/2023-2024 | 1897/MURD | 17/07/2023 | 968 | M/S JAN MAHAMMAD | 520.42 | 0 | 20
1550 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at BHARATPUR -I Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000401/2023-2024 | 2808/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
1551 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000054/2023-2024 | 1067/MURD/10 | 18/04/2023 | 0 | Resource Division | 52.37 | 0 | 0
1552 | Murshidabad Division | Kandi Sub-Division | CONSTRUCTION OF ROAD FROM GOKARNA TO ASOLAMPUR, PACKAGE NO- WB-13 -365, LENG- 10.215 KM , BLOCK KANDI, IN THE DIST MUSHIDABAD | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | BILL/01077/2024-2025 | 403-MSD/2024-25 | 23/09/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 5.19 | 0 | 0
1553 | Murshidabad Division | Kandi Sub-Division | Laying of UPVC pipeline from Head Work Site to Node point 16, laying of parallel line for FHTC work and Construction of approach road of UDAYCHANDPUR & Adjoining Mouzas Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000056/2024-2025 | 1987/MURD | 08/07/2024 | 450 | MARUTI CONSTRUCTION AND CO. | 76.01 | 0 | 40
1554 | Murshidabad Division | Kandi Sub-Division | Construction of Boundary Wall & Pump House with sanitary & plumbing work (H.W & 4th T/W Site) of Mahalandi (Zone-I) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000084/2024-2025 | 2088/MURD | 23/07/2024 | 60 | AHAMMED ENTERPRISE | 21.22 | 0 | 0
1555 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000132/2023-2024 | 1758/MURD | 06/07/2023 | 576 | R.K. DRILLING SERVICES | 23.58 | 0 | 70
1556 | Murshidabad Division | Kandi Sub-Division | Laying of Distribution System (Part-A), Construction of Over Head Reservoir (400 Cum), Pump House (3rd Site), Boundary wall (3rd Site), Repairing of Pump House & Boundary wall (H.W & 2nd Site), Repairing of Over Head Reservoir (250 Cum) and accommodate FHTC work at Mahalandi Village (Village Code-315231) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000471/2023-2024 | 3014/MURD | 26/09/2023 | 1132 | PREKSHITA CONSTRUCTION | 248.32 | 0 | 10
1557 | Murshidabad Division | Kandi Sub-Division | Laying of Distribution System (Part-B) and FHTC work at Mahalandi Village (Village Code-315231) & Durlabhpur Village (Village Code-315218) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme in Kandi Block under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000481/2023-2024 | 3052/MURD | 29/09/2023 | 873 | PRIYANKA CONSTRUCTION | 286.61 | 0 | 20
1558 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000068/2022-2023 | 1043/MURD/7 | 17/04/2023 | 0 | Resource Division | 84.58 | 0 | 0
1559 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000314/2023-2024 | 1936/MURD | 18/07/2023 | 0 | Resource Division | 84.58 | 0 | 0
1560 | Murshidabad Division | Kandi Sub-Division | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000006/2025-2026 | 835/MURD | 11/04/2025 | 234 | M/S JATIN | 69.3 | 0 | 5
1561 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1562 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BUNDAI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000653/2022-2023 | 3403/MURD | 22/12/2022 | 45 | M/S SUBHAJIT BISWAS | 16.8 | 0 | 75
1563 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,40,40,803.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,29,128.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000750/2022-2023 | 413/MURD | 15/02/2023 | 1263 | M/S TRADE ASSOCIATE | 289.47 | 0 | 20
1564 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1565 | Murshidabad Division | Kandi Sub-Division | Balance work of road restoration damaged during laying of pipeline and laying of distribution pipe line of Bundai Piped Water Supply Scheme, Kandi Block, Kandi Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000845/2023-2024 | 827/MURD | 15/03/2024 | 15 | PRASANTA SANA | 20.72 | 0 | 50
1566 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of Laying Distribution System (PART-A) for Augmentation of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000973/2022-2023 | 130./MURD | 16/01/2023 | 897 | PRASANTA SANA | 108.95 | 0 | 60
1567 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000316/2023-2024 | 1936/MURD/3 | 18/07/2023 | 0 | Resource Division | 25.21 | 0 | 0
1568 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1569 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of MARURA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362239S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000714/2022-2023 | 93/MURD | 11/01/2023 | 365 | M/S.TAPAS KUMAR CHAKRABORTY | 815.38 | 0 | 0
1570 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000035/2023-2024 | 1043/MURD/10 | 17/04/2023 | 0 | Resource Division | 76.92 | 0 | 0
1571 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at SURANGAPUR PWSS (ZONE- II ) PART-B Water Supply Scheme at Head Work Site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000112/2023-2024 | 1754/MURD | 06/07/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 11.79 | 0 | 100
1572 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of SURANGAPUR Zone-II / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000527/2022-2023 | 2493/MURD | 30/08/2022 | 365 | SUJIT KUMAR SAHA | 203.27 | 0 | 85
1573 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 0 | 1
1574 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000296/2023-2024 | 1278/MURD/9 | 10/05/2023 | 0 | Resource Division | 68.77 | 0 | 0
1575 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000348/2023-2024 | 112/MURD/05 | 11/01/2024 | 0 | Resource Division | 38.22 | 0 | 0
1576 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000352/2023-2024 | 305/MURD/01 | 29/01/2024 | 0 | Resource Division | 65.38 | 0 | 0
1577 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of BHAGIRATHPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000335/2022-2023 | 1722/MURD | 04/07/2022 | 365 | M/S BHUBAN DAS | 331.21 | 0 | 65
1578 | Murshidabad Division | Berhampur M/E Division | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000623/2023-2024 | 3372/MURD | 31/10/2023 | 270 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0
1579 | Murshidabad Division | Berhampur M/E Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1580 | Murshidabad Division | Berhampur M/E Division | Sinking of replacement tube well of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhagirathpur Water Supply Scheme of TW-I, P.H-1 under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000953/2021-2022 | 3591/MURD | 17/11/2021 | 15 | A ONE ENTERPRISE | 8.39 | 0 | 1
1581 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000017/2022-2023 | 1236/MURD | 11/05/2022 | 0 | Resource Division | 46.42 | 0 | 0
1582 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000019/2022-2023 | 2507/A/MURD | 31/08/2022 | 0 | Resource Division | 11.3 | 0 | 0
1583 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000029/2022-2023 | 2508/A/MURD | 31/08/2022 | 0 | Resource Division | 1.45 | 0 | 0
1584 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000040/2024-2025 | MURD/2481/12 | 04/09/2024 | 0 | Resource Division | 19.48 | 0 | 0
1585 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000167/2023-2024 | 1180/MURD/13 | 29/04/2023 | 0 | Resource Division | 16.75 | 0 | 0
1586 | Murshidabad Division | Jangipur Sub-Division | Providing FHTC Connection to 322 nos household , Laying of Distribution System, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works for Augmentation work of Manigram Balarambati PWSS within Sagardighi Block under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000592/2023-2024 | 3340/MURD | 28/10/2023 | 520 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 96.91 | 0 | 45
1587 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS MANIGRAM-BALARAMBATI PWSS Scheme, Block-SAGARDIGHI to be Augmentation/Rejuvination under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/002171/2021-2022 | 3250/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 4.48 | 0 | 50
1588 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer 3 | RTOR000153/2023-2024 | 1180/MURD/28 | 29/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1589 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Jalangi Zone-IV Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000339/2022-2023 | 1807/MURD | 11/07/2022 | 993 | H.I.ENTERPRISE | 351.37 | 0 | 95
1590 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-IV Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000589/2022-2023 | 3058/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 23.55 | 0 | 1
1591 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000023/2022-2023 | 2507/E/MURD | 31/08/2022 | 0 | Resource Division | 12.41 | 0 | 0
1592 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000026/2024-2025 | MURD/2482 | 04/09/2024 | 0 | Resource Division | 14.2 | 0 | 0
1593 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000041/2022-2023 | 2780/J/MURD | 01/10/2022 | 0 | Resource Division | 14.2 | 0 | 0
1594 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000166/2023-2024 | 1180/MURD/12 | 29/04/2023 | 0 | Resource Division | 11.14 | 0 | 0
1595 | Murshidabad Division | Berhampur M/E Division | Providing FHTCs 2500 nos household, Construction of 300 Cum OHR , Repairing & Renovation of R.C.C. elevated reservoir 450 Cum capacity of staging hight 20 mtr., Construction of Boundary Wall 50 mtr, Construction of RCC approach road of 50 mtr & Road Restoration due to laying of pipeline ,Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works ,Repair of Boundary Wall for Augmentation work of Kankuria Jafrabad (Zone-I) PWSS in Samsherganj Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000025/2024-2025 | 1815/MURD | 20/06/2024 | 502 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 295.71 | 0 | 30
1596 | Murshidabad Division | Berhampur M/E Division | Laying of pipeline at Babupur village adjacent to OHR of Kankuria Jafrabad Water Supply Scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000170/2023-2024 | 1974/MURD | 20/07/2023 | 30 | JOY BISHNU ENGINEERING CO. | 2.07 | 0 | 100
1597 | Murshidabad Division | Berhampur M/E Division | Renovation of Filter Media of Existing IEP of (Capacity 45 Cum/hr.) at Kankuria Jafrabad Water Supply Scheme under Murshidabad Division , PHE engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000247/2024-2025 | 230/MURD | 27/01/2025 | 30 | M/S.DAS ENTERPRISE | 16.84 | 0 | 0
1598 | Murshidabad Division | Berhampur M/E Division | Boundary wall at 2-nd Tube Well Site of Kankuria Jafrabad Water supply Scheme under Jangipur Sub-Division, P.H.Engg. Dte. in the District of Murshidabad.Length of Boundary Wall- 96 Mtr. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000501/2020-2021 | 663/MURD | 19/02/2021 | 45 | HARUN ALL RASHID & BROTHERS | 4.49 | 0 | 0
1599 | Murshidabad Division | Berhampur M/E Division | Supply of UPVC pipe and RDS filter for the work of Sinking of (300 mm x 200 mm ) dia Big Dia tube well at Village Kankuria(Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water SupplyScheme(Scheme Id:0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000530/2022-2023 | 240/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.6 | 0 | 1
1600 | Murshidabad Division | Berhampur M/E Division | Supply of (300 mm x 200 mm ) dia Big Dia tube well 75 mtr. Deep by direct rotary rig method using UPVC pipe and RDS filter at Village Kankuria(Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme(SchemeId:0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000531/2022-2023 | 239/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.42 | 0 | 1
1601 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000705/2023-2024 | 3813/MURD | 12/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 11.77 | 0 | 100
1602 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying Distribution System and Rising Main Connection For Augmentation of Kankuria Jafrabad (Zone-I) PWSS of Samserganj Block in Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000832/2022-2023 | 719/MURD | 14/03/2023 | 988 | TARIKUL SK | 157.47 | 0 | 40
1603 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000039/2024-2025 | MURD/2481/11 | 04/09/2024 | 0 | Resource Division | 57.32 | 0 | 0
1604 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000077/2022-2023 | 1295/MURD/01 | 11/05/2023 | 0 | Resource Division | 11.5 | 0 | 0
1605 | Murshidabad Division | Berhampur Sub-Division | Edrakpur & Adjoining Mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nowda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000014/2023-2024 | 982/MURD | 10/04/2023 | 1124 | SANJAY BISWAS | 643.42 | 0 | 85
1606 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for EDRAKPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000027/2025-2026 | 1021/MURD | 05/05/2025 | 60 | SANJAY BISWAS | 40.44 | 0 | 0
1607 | Murshidabad Division | Berhampur Sub-Division | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000102/2024-2025 | 2152/MURD | 29/07/2024 | 480 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 80
1608 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
1609 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Edrakpur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000583/2022-2023 | 3067/MURD | 17/11/2022 | 30 | M/S B.R. SUPPLIERS | 10.6 | 0 | 100
1610 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Edrakpur PWSS Scheme, Block - Nowda) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000842/2021-2022 | 3275/MURD | 05/10/2021 | 60 | RADIANT | 6.22 | 0 | 1
1611 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000184/2023-2024 | 1210/MURD/01 | 02/05/2023 | 0 | Resource Division | 11.39 | 0 | 0
1612 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000349/2023-2024 | 112/MURD/06 | 11/01/2024 | 0 | Resource Division | 26.32 | 0 | 0
1613 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000354/2023-2024 | 305/MURD/3 | 29/01/2024 | 0 | Resource Division | 9.58 | 0 | 0
1614 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Palasi Sonadanga(Village code 314527) under Bhandara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division,PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-06) |  |  | ORD/000650/2020-2021 | 3131/MURD | 10/12/2020 | 180 | M/S. SINHA & SONS | 46.65 | 0 | 0
1615 | Murshidabad Division |  | Laying of UPVC pipeline for allied works of retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Jeevan mission and Jal Swapna under command area of village of BHANDARA(village code- 314524) under Bhandara Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola-I & II Block under Murshidabad Division ,PHE Dte. in the district of Murshidabad.(Schemre ID- 0005104709) |  |  | ORD/000143/2022-2023 | 1240/MURD | 11/05/2022 | 30 | DEBASIS BOSE | 9.86 | 0 | 0
1616 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhandara(Village code 314524) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-07) |  |  | ORD/000549/2020-2021 | 3047/MURD | 07/12/2020 | 180 | DEBASIS BOSE | 57.23 | 0 | 0
1617 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagdanga (Village code 314725) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. |  |  | ORD/000243/2020-2021 | 84/MURD | 08/01/2021 | 60 | DOBAY CONSTRUCTION | 41.95 | 20.67 | 0
1618 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna ( Jal Jeevan Mission) Mouja Sibnagar Laskarpur (Village code 314702)under Sibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723328) |  |  | ORD/000283/2022-2023 | 1562/MURD | 16/06/2022 | 120 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 151.41 | 0 | 1
1619 | Murshidabad Division |  | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A |  |  | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
1620 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur ( Village Code -314570) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019111). |  |  | ORD/000183/2020-2021 | 597/MURD | 09/02/2021 | 60 | SANJAY BISWAS | 67.55 | 34.42 | 0
1621 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 493 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur (Village code 314570) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111) |  |  | ORD/001879/2021-2022 | 855/MURD | 31/03/2022 | 20 | SUBHENDRA MOHAN SARKAR | 12.24 | 0 | 100
1622 | Murshidabad Division | Kandi Sub-Division | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur-I II G.P, Bali G.P, Patikabari G.P, Madhupur G.P, Kedar Chandpur-I G.P, Khidirpur G.P, Humaipur G.P, Rampara-I G.P, Andulberia G.P, Dadpur G.P, Rampara-II G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P, Niyallishpara G.P, Satui Chowrigachha G.P, Shaktipur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000115/2020-2021 | 691/MURD | 23/02/2021 | 30 | IMAGIN | 4.77 | 4.77 | 0
1623 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Muniadihi (Village Code- 315982) under Panchthupi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division, P.H.E.Dte. (SL-02) | ASSISTANT ENGINEER |  | ORD/000518/2022-2023 | 155/KSD | 31/08/2022 | 45 | SARTHAK SK. | 4.81 | 0 | 0
1624 | Murshidabad Division | Kandi Sub-Division | Restoration work of UPVC pipeline & road restoration work including laying of CI/DI pipeline for smooth supply of drinking water at Panchthuppi Bus Stand area under Panchthuppi Water Supply Scheme under Kandi Sub-Division, P.H.E. Dte.in the District Murshidabad | ASSISTANT ENGINEER |  | ORD/001136/2021-2022 | 320/KSD | 16/11/2021 | 30 | SUPTI ENTERPRISE | 4.83 | 0 | 0
1625 | Murshidabad Division | Kandi Sub-Division | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Muslim Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001189/2021-2022 | 322/KSD | 16/11/2021 | 30 | APURBA SAHA CHOWDHURY | 4.83 | 0 | 0
1626 | Murshidabad Division | Kandi Sub-Division | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001191/2021-2022 | 324/KSD | 16/11/2021 | 30 | DECON INDIA | 4.84 | 0 | 0
1627 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/001230/2021-2022 | 214/KSD | 11/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0
1628 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of Togra ( 315978 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-II ) TNO- 736/20-21/EE | ASSISTANT ENGINEER |  | VCH/000008/2021-2022 | 04/MSD/21-22 | 16/07/2021 | 0 | SUPTI ENTERPRISE | 7.26 | 0 | 0
1629 | Murshidabad Division | Kandi Sub-Division | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village MUNIADIHI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.23 Tender no 63 SE/MC 20-21 | ASSISTANT ENGINEER |  | VCH/000038/2021-2022 | 03/MSD/21-22 | 16/07/2021 | 0 | DECON INDIA | 23.9 | 0 | 0
1630 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan of Togra (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no-736 of 20-21 by EE / MSD | ASSISTANT ENGINEER |  | VCH/000141/2021-2022 |  | 01/07/2021 | 0 | SUPTI ENTERPRISE | 7.26 | 0 | 0
1631 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village TOGRA (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | VCH/000534/2022-2023 | 192-MSD/22-23 | 29/06/2022 | 0 | SUPTI ENTERPRISE (PROP.DEBAPRIYA SAHA) | 3.11 | 0 | 0
1632 | Murshidabad Division | Kandi Sub-Division | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Chatterjee Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. Tender no: 39 of 21-22 by AE KSD | ASSISTANT ENGINEER |  | VCH/001423/2021-2022 | 356-MSD/21-22 | 05/03/2022 | 0 | DECON INDIA | 4.82 | 0 | 0
1633 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MUNIADIHI under PANCHTHUPUI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block under Murshidabad Div PHE DTE in the District of Murshidabad. Tender no - 63 of 20-21 by SE MC | ASSISTANT ENGINEER |  | VCH/001452/2021-2022 | 355-MSD/21-22 | 07/03/2022 | 0 | DECON INDIA | 15.99 | 0 | 0
1634 | Murshidabad Division | Kandi Sub-Division | Laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi Panchthupi W/S Scheme under KSD PHE DTE. Tender no - 40 of 21-22 by AE KSD | ASSISTANT ENGINEER |  | VCH/001455/2021-2022 | 354-MSD/21-22 | 05/03/2022 | 0 | DECON INDIA | 4.81 | 0 | 0
1635 | Murshidabad Division |  | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 |  |  | VCH/002045/2020-2021 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0
1636 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -PANCHTHUPI- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- JANARDHANPUR , CODE-315981 , 632 /2020-21/EE |  |  | VCH/002049/2020-2021 | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 21.08 | 0 | 0
1637 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BURWAN- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- GOURINAGAR , CODE-315951 , 631/2020-21/EE |  |  | VCH/002050/2020-2021 | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 9.08 | 0 | 0
1638 | Murshidabad Division | Kandi Sub-Division | Laying of rising main (DI) from tube well to 300 Cum OHR and laying of distribution main (DI) from OHR to distribution system including supply of C.I. specials and restoration work of concrete road of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000003/2022-2023 | 05/KSD | 06/04/2022 | 30 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.85 | 0 | 1
1639 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Gokarna-II G.P, Mahalandi-I G.P, Kumarsanda G.P, Jasahari Anukha-I & II G.P, Burwan- I & II G.P, Panchthupi G.P & Sohara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000078/2021-2022 | 176/KSD | 28/05/2021 | 30 | IMAGIN | 2.61 | 0 | 1
1640 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAHARA (Village Code 315291) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000185/2020-2021 | 3021/MURD | 04/12/2020 | 45 | M/S. BIMALENDU BOSE | 25.13 | 0 | 0
1641 | Murshidabad Division | Kandi Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000415/2021-2022 | 215/KSD | 11/08/2021 | 30 | IMAGIN COMMUNICATION | 4.33 | 0 | 0
1642 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000441/2021-2022 | 225/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0
1643 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-II G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000457/2021-2022 | 226/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
1644 | Murshidabad Division | Kandi Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at GOKARNA-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000474/2021-2022 | 242/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
1645 | Murshidabad Division | Kandi Sub-Division | Construction of valve chamber & laying of upvc pipe line including supply of C.I. specials and valves in connection with FHTC work of Bahara village (Village Code-315810) under Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. (SL-01) | ASSISTANT ENGINEER |  | ORD/000517/2022-2023 | 154/KSD | 31/08/2022 | 30 | BISWAS CONSTRUCTION | 4.55 | 0 | 1
1646 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) of Bahara & Ghoshbati habitation under command area of Bahara village (Village Code- 315291) of Bahara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad.(SL_03) | ASSISTANT ENGINEER |  | ORD/000519/2022-2023 | 156/KSD | 31/08/2022 | 45 | SIMA ENTERPRISE | 4.84 | 0 | 1
1647 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village LAHARPARA (Village Code 315282) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000585/2020-2021 | 2880/MURD | 12/11/2020 | 45 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 32.21 | 0 | 0
1648 | Murshidabad Division | Kandi Sub-Division | Laying of pipe line for distribution system from node point 1B to 1C & laying of rising main from H.W Site to 2nd tube well site under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000707/2020-2021 | 3109/MURD | 09/12/2020 | 30 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.84 | 0 | 0
1649 | Murshidabad Division | Kandi Sub-Division | Laying of different dia UPVC pipe line from node point 45 to node point 3 & node point 45 to node point 1E for distribution network with supply of materials for pipe line under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000727/2020-2021 | 3222/MURD | 18/12/2020 | 30 | KUNTAL SAHA | 4.86 | 0 | 1
1650 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of BHANDIRA habitation under Bhandira (Village Code: 315292) under BAHARA Surface Water Based Water Supply Scheme for arsenic affected areas of KANDI Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 398 of 20-21 by EE / MSD | ASSISTANT ENGINEER |  | VCH/000198/2021-2022 | 08 -MSD / 21-22 | 04/08/2021 | 0 | M/S GUNGUN CONSTRUCTION | 22.54 | 0 | 0
1651 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village Malatipur (Village code 314698) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. |  |  | ORD/000567/2020-2021 | 80/MURD | 08/01/2021 | 60 | M/S. GHOSH ENTERPRISE | 26.36 | 0 | 1
1652 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village Joragacha (Village code 314690) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. |  |  | ORD/000568/2020-2021 | 81/MURD | 08/01/2021 | 60 | M/S. GHOSH ENTERPRISE | 30.67 | 0 | 1
1653 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MALATIPUR (Village Code 314698) under JORGACHA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 846 of 20-21 by EE MURD |  |  | VCH/000296/2022-2023 | 106-MSD/22-23 | 07/05/2022 | 0 | M/S. GHOSH ENTERPRISE | 23.7 | 0 | 0
1654 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JORGACHA (Village Code 314690) under JORGACHA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 847 of 20-21 by EE MURD |  |  | VCH/001483/2021-2022 | 391-MSD/21-22 | 22/03/2022 | 0 | M/S. GHOSH ENTERPRISE | 28.9 | 0 | 0
1655 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Bhagirathpur (Village Code -314699) under Bhagirathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000642/2022-2023 | 3342/MURD | 15/12/2022 | 30 | PROSENJIT DAS | 34.64 | 0 | 0
1656 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Momenpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 376 of 21-22 by EE MSD, and Scheme Code: 8272 |  |  | VCH/000035/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.88 | 0 | 0
1657 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna Mission under command area of village of BHAGIRATHPUR (VILLAGE CODE 314699) under BHAGIRATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 105 of 20-21 by SE / MC |  |  | VCH/000219/2021-2022 | 20-MSD / 21-22 | 06/08/2021 | 0 | PROJECT INDIA | 47.31 | 0 | 0
1658 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BHAGIRATHPUR (Village Code 314699) under BHAGIRATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 105 of 20-21 by SE MC |  |  | VCH/001458/2021-2022 | 358-MSD/21-22 | 09/03/2022 | 0 | PROJECT INDIA | 56.97 | 0 | 0
1659 | Murshidabad Division | Jangipur Sub-Division | Allied work for construction of culvert at Paschim Puranpara(CT) Zone -I H/W site and approach road for H/W site Augmentation work under Jangipur sub division P.H.E Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000104/2024-2025 | 2182/MURD | 31/07/2024 | 335 | M/S MONDAL CONSTRUCTION | 16.73 | 0 | 100
1660 | Murshidabad Division | Jangipur Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1661 | Murshidabad Division | Jangipur Sub-Division | Paschim Punropara Zone - I PWSS to accommodate FHTC of 4363 nos household, Laying Distribution System, Laying Rising Main under Jal Jivan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part-1) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000745/2023-2024 | 83/MURD | 09/01/2024 | 365 | M/S. BIMALENDU BOSE | 432.11 | 0 | 0
1662 | Murshidabad Division | Jangipur Sub-Division | Paschim Punropara Zone - I PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 2nos, Construction of Boundary Wall of 220 m, Construction 750 Cum OHR with sub soil investigation Jal Jivan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE. Dte. (part-B) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000748/2023-2024 | 105/MURD | 10/01/2024 | 934 | M/S. A.T.D. PROJECTS | 289.17 | 0 | 0
1663 | Murshidabad Division | Jangipur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1664 | Murshidabad Division | Kandi Sub-Division | Ground Water based water supply scheme for Sujapur Part- B village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer, Estimating Section,Junior engineer-II | ORD/000209/2023-2024 | 2320/MURD | 02/08/2023 | 822 | SOUVIK HALDER | 30.54 | 0 | 60
1665 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Sujapur Part- A village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer, Estimating Section,Junior engineer-II | ORD/000495/2023-2024 | 3054/MURD | 29/09/2023 | 824 | M/S BHATTACHARJEE & CO | 30.55 | 0 | 42
1666 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
1667 | Murshidabad Division | Jangipur Sub-Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
1668 | Murshidabad Division | Jangipur Sub-Division | Laying Distribution System, Rising Main, , Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of BEWA Zone-II Water at Supply Scheme in FARAKKA Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000603/2023-2024 | 3357/MURD | 30/10/2023 | 120 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 120.09 | 0 | 40
1669 | Murshidabad Division | Jangipur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BEWA -II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000701/2023-2024 | 3769/MURD | 08/12/2023 | 540 | HARUN ALL RASHID & BROTHERS | 35.3 | 0 | 100
1670 | Murshidabad Division | Jangipur Sub-Division | Balance Work of Road restoration damaged during laying of pipeline of Bewa Zone-II Piped Water Supply Scheme, Farakka Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER | Junior Engineer 3 | ORD/000849/2023-2024 | 824/MURD | 15/03/2024 | 624 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 11.51 | 0 | 100
1671 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Jaulia Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000219/2023-2024 | 2328/MURD | 02/08/2023 | 942 | SARTHAK SK. | 30.55 | 0 | 25
1672 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMLAI and MATHUA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000393/2023-2024 | 2795/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
1673 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000438/2023-2024 | 2886/MURD | 12/09/2023 | 842 | DHIRENDRANATH MONDAL | 591.68 | 0 | 10
1674 | Murshidabad Division | Kandi Sub-Division | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000735/2023-2024 | 55/MURD | 05/01/2024 | 605 | DHIRENDRANATH MONDAL | 53.07 | 0 | 10
1675 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000238/2023-2024 | 1219/MURD/26 | 03/05/2023 | 0 | Resource Division | 19.9 | 0 | 0
1676 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
1677 | Murshidabad Division | Berhampur Sub-Division | Laying Distribution System for Augmentation of Loknathpur Zone-I (Part-A) PWSS of Beldanga-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000267/2023-2024 | 2575/MURD | 18/08/2023 | 180 | SAMBHU NATH ROY | 239.31 | 0 | 85
1678 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 100
1679 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Loknathpur zone-I PWSS to accommodate FHTC of 922 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 250 m and Soil Investigation & 150 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Beldanga-II Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000569/2023-2024 | 3290/MURD | 19/10/2023 | 365 | VISION ENTERPRISE | 215.41 | 0 | 0
1680 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Lokenathpur Zone -I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000719/2023-2024 | 3863/MURD | 15/12/2023 | 305 | KHOKAN BISWAS | 27.6 | 0 | 100
1681 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000019/2024-2025 | 1811/MURD/18 | 20/06/2024 | 0 | Resource Division | 5.51 | 0 | 0
1682 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000387/2023-2024 | 514/MURD/01 | 16/02/2024 | 0 | Resource Division | 90.69 | 0 | 0
1683 | Murshidabad Division | Lalbag Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1684 | Murshidabad Division | Lalbag Sub-Division | Laying Distribution System , FHTC for Augmentation of Bhandara Zone-I Water Supply Scheme in Bhawangola-II Block , under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000026/2024-2025 | 1841/MURD | 25/06/2024 | 554 | DHIMAN SARKAR | 336.88 | 0 | 2
1685 | Murshidabad Division | Lalbag Sub-Division | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000090/2025-2026 | 1829/MURD | 18/08/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0
1686 | Murshidabad Division | Lalbag Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000135/2024-2025 | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 40
1687 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 0 | 100
1688 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
1689 | Murshidabad Division | Lalbag Sub-Division | Construction of 600 Cum OHR, Rising Main, Pump House cum Chlorine Room with Sanitary and Water Supply Arrangement & Boundary Wall with R.C.C. column at Head Work Site & 2nd Tube Well Site for Augmentation of BHANDARA Zone-I Ground Based Water Supply Scheme under Bhawangola-I Block under Lalbagh Sub Division, Murshidabad Division ,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000506/2023-2024 | 3089/MURD | 03/10/2023 | 699 | NAMITA ENTERPRISE | 257.87 | 0 | 2
1690 | Murshidabad Division | Lalbag Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 80
1691 | Murshidabad Division | Lalbag Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1692 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1693 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000259/2023-2024 | 1230/MURD/02 | 04/05/2023 | 0 | Resource Division | 36.51 | 0 | 0
1694 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-III Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000024/2025-2026 | 984/MURD | 02/05/2025 | 60 | M/S J.S. ENTERPRISE | 22.99 | 0 | 0
1695 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
1696 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
1697 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
1698 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000095/2023-2024 | 1147/MURD/10 | 27/04/2023 | 0 | Resource Division | 25.8 | 0 | 0
1699 | Murshidabad Division | Berhampur M/E Division | DAFAHAT CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE. Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000227/2023-2024 | 2403/MURD | 07/08/2023 | 720 | MOTI RAHAMAN | 378.32 | 0 | 95
1700 | Murshidabad Division | Berhampur M/E Division | DAFAHAT CT PWSS to accommodate 700 cum OHR ( Dept Drg No.PC-I/OHR/6/2012), 2 Nos Pump House, 2 No Boundary Wall & Path Way under Jal Jeevan Mission of Suti - II Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000240/2023-2024 | 2410/MURD | 07/08/2023 | 725 | M/S. MAYA CONSTRUCTION | 270.75 | 0 | 5
1701 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at DAFAHAT (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Suti -II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000403/2023-2024 | 2822/MURD | 07/09/2023 | 21 | M. R. ENTERPRISE | 27.81 | 0 | 0
1702 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1703 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000271/2023-2024 | 1230/MURD/12 | 04/05/2023 | 0 | Resource Division | 57.56 | 0 | 0
1704 | Murshidabad Division | Berhampur M/E Division | SRIKANTABATI (Part A) PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- RAGHUNATHGANJ-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000280/2023-2024 | 2644/MURD | 23/08/2023 | 365 | BIJAY CHOWDHURY | 941.07 | 0 | 0
1705 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI (CT) PART- A Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj - I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000408/2023-2024 | 2824/MURD | 07/09/2023 | 21 | M. R. ENTERPRISE | 18.54 | 0 | 0
1706 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1707 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000250/2023-2024 | 1219/MURD/36 | 03/05/2023 | 0 | Resource Division | 29.51 | 0 | 0
1708 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000369/2023-2024 | 2721/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
1709 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
1710 | Murshidabad Division | Berhampur M/E Division | Formal work order for Khodarampur CT PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000816/2022-2023 | 674/MURD | 09/03/2023 | 365 | R.K. CONSTRUCTTION | 227.03 | 0 | 0
1711 | Murshidabad Division | Berhampur M/E Division | Khodarampur CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000894/2022-2023 | 930/MURD | 31/03/2023 | 180 | TEKNO ENTERPRISE | 345.69 | 0 | 0
1712 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000283/2023-2024 | 1230/MURD/25 | 04/05/2023 | 0 | Resource Division | 29.19 | 0 | 0
1713 | Murshidabad Division | Berhampur M/E Division | Construction of Pump House, Boundary Wall, Rising Main Connection, Laying Distribution System and FHTC & Special Reaparing of 02 (Two) Nos Pump House for Augmentation of Tekaraipara Ground water based piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) with Raninagar -I Block of Murshidabad District under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000023/2024-2025 | 1814/MURD | 20/06/2024 | 560 | S.D. PROJECT | 448.97 | 0 | 50
1714 | Murshidabad Division | Berhampur M/E Division | Rising Main Connection (D.I-K9) , Laying Distribution System (D.I-K7 & HDPE PE-100), and Balance Portion of Functional Household Tap Connection (1052 Nos) and Reconnection of Functional Household Tap Connection (4370 Nos) for Augmentation of Tekaraipara Ground water based Piped water supply scheme within Raninagar-I Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000100/2025-2026 | 1671/MURD | 24/07/2025 | 240 | S.D. PROJECT | 219.58 | 0 | 50
1715 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 1
1716 | Murshidabad Division | Kandi Sub-Division | MASLA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000188/2023-2024 | 1996/MURD | 21/07/2023 | 300 | A.K. INSDUSTRIES | 239.5 | 0 | 75
1717 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000072/2023-2024 | 1075/MURD/14 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
1718 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Putia Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000591/2023-2024 | 3343/MURD | 28/10/2023 | 365 | MARUTI CONSTRUCTION AND CO. | 143.58 | 0 | 0
1719 | Murshidabad Division | Berhampur M/E Division | Augmentation of Putia Zone - II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 150 m & Construction of 400 Cum OHR with sub soil investigation under Jal Jeevan Mission of Raghunathganj II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000593/2023-2024 | 3341/MURD | 28/10/2023 | 365 | DADA BHAI CONSTRUCTION | 185.23 | 0 | 0
1720 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
1721 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000116/2023-2024 | 1167/MURD/10 | 28/04/2023 | 0 | Resource Division | 24.14 | 0 | 0
1722 | Murshidabad Division | Berhampur Sub-Division | Construction Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr Boundary wall at 3rd Tubewell site of Sarbangapur Zone -II Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000039/2024-2025 | 1927/MURD | 03/07/2024 | 60 | M/S S.R.K. ENTERPRISE | 16.6 | 0 | 0
1723 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-II Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000052/2025-2026 | 1227/MURD | 28/05/2025 | 60 | M/S.S.S. ENTERPRISE | 19.62 | 0 | 0
1724 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 193 nos household for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000136/2023-2024 | 1819/MURD | 12/07/2023 | 60 | A.M. CONSTRUCTION | 21.14 | 0 | 0
1725 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System, Rising Main for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000292/2023-2024 | 2646/MURD | 23/08/2023 | 709 | DOBAY CONSTRUCTION | 229.82 | 0 | 70
1726 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
1727 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, repairing & Overhauling of R.C.C. elevated reservoir 350 Cum capacity for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000601/2023-2024 | 3345/MURD | 28/10/2023 | 730 | SHEEMAH CONSTRUCTION | 93.54 | 0 | 75
1728 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 1
1729 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000014/2024-2025 | 1811/MURD/13 | 20/06/2024 | 0 | Resource Division | 4.08 | 0 | 0
1730 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000214/2023-2024 | 1219/MURD/05 | 03/05/2023 | 0 | Resource Division | 46.14 | 0 | 0
1731 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MAHAMMADPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000028/2025-2026 | 1022/MURD | 05/05/2025 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 23 | 0 | 0
1732 | Murshidabad Division | Berhampur Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHAMMADPUR Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000108/2023-2024 | 1750/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 67
1733 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
1734 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 390 nos household , Laying of Distribution System, Rising Main , Construction of Pump House & Boundary Wall, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr, Special repair and renovation of existing Pump House and Alied Works, Repairing & Vertical Extention of Boundary Wall for Augmentation work of MAHAMMADPUR PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000876/2022-2023 | 898/MURD | 29/03/2023 | 1073 | AJOY GHOSH | 171.58 | 0 | 40
1735 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 1
1736 | Murshidabad Division | Berhampur Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001810/2021-2022 | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 0 | 1
1737 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
1738 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based HAFANIA (ZONE-II) & KEYADANGA PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000819/2022-2023 | 801/MURD | 22/03/2023 | 831 | ATIKUL SAIKH | 367.41 | 0 | 100
1739 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000266/2023-2024 | 1230/MURD/09 | 04/05/2023 | 0 | Resource Division | 18.97 | 0 | 0
1740 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000375/2023-2024 | 495/MURD/06 | 15/02/2024 | 0 | Resource Division | 7.85 | 0 | 0
1741 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1742 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BACHHRA ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block underMurshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000031/2025-2026 | 1194/MURD | 23/05/2025 | 60 | M/S UNIVERSAL TRADING | 19.62 | 0 | 0
1743 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, Laying of Distribution System (part_A), Rising Main , Special repair and renovation of existing 1 (One) Nos PumpHouse and Allied Works, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity for Augmentation work of BACHHRA ZONE-I PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte.(part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000138/2023-2024 | 1820/MURD | 12/07/2023 | 720 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 330.74 | 0 | 5
1744 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
1745 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of December 2024 to April 2025 [Vehicle No.WB25M1561] (i.e. from 01/12/2024 to 30/04/2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000199/2024-2025 | 3127/MURD | 30/11/2024 | 151 | M/S B K ENTERPRISE | 0.87 | 0 | 0
1746 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
1747 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BACHHRA ZONE ¿ I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000551/2023-2024 | 3193/MURD | 12/10/2023 | 482 | NADIA TUBEWELLS | 23.56 | 0 | 100
1748 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1749 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 573 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-I PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000890/2022-2023 | 913/MURD | 30/03/2023 | 694 | AYUSH ENTERPRISE | 103.18 | 0 | 80
1750 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0
1751 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000012/2024-2025 | 1811/MURD/11 | 20/06/2024 | 0 | Resource Division | 6.03 | 0 | 0
1752 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000208/2023-2024 | 1210/MURD/24 | 02/05/2023 | 0 | Resource Division | 4.36 | 0 | 0
1753 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone - II Water Supply Scheme at Head Work Site, 2nd Site site at KHARGRAM Block under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000110/2023-2024 | 1752/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 23.56 | 0 | 0
1754 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
1755 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1756 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000063/2022-2023 | 1043/MURD/4 | 17/04/2023 | 0 | Resource Division | 1.46 | 0 | 0
1757 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 1118 nos household ,Laying of Distribution System, Rising Main , Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works ,for Augmentation work of JAGAIPUR , NAWDA Block under Murshidabad Division , PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000353/2023-2024 | 2666/MURD | 24/08/2023 | 949 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 265.09 | 0 | 70
1758 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
1759 | Murshidabad Division | Berhampur Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000498/2024-2025 | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0
1760 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 1
1761 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000011/2024-2025 | 1811/MURD/10 | 20/06/2024 | 0 | Resource Division | 11.14 | 0 | 0
1762 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000220/2023-2024 | 1219/MURD/04 | 03/05/2023 | 0 | Resource Division | 26.87 | 0 | 0
1763 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I,III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khargram & adjoining mouzas Water Supply Scheme at Head work site & 3rd Site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000359/2023-2024 | 2702/MURD | 25/08/2023 | 585 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 100
1764 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000066/2022-2023 | 1278/MURD/15 | 10/05/2023 | 0 | Resource Division | 26.34 | 0 | 0
1765 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000343/2023-2024 | 79/MURD/10 | 09/01/2024 | 0 | Resource Division | 28.5 | 0 | 0
1766 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II | RTOR000361/2023-2024 | MURD/439/14 | 08/02/2024 | 0 | Resource Division | 25.58 | 0 | 0
1767 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
1768 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main Connection, FHTC, Repairing of Existing OHR, Pump House, Construction of New Boundary Wall for Augmentation of BELE Ground water based Piped water supply scheme in Khargram Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000027/2023-2024 | 1076/MURD | 19/04/2023 | 1139 | M/S. BIMALENDU BOSE | 270.95 | 0 | 25
1769 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bele & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000032/2023-2024 | 1107/MURD | 24/04/2023 | 20 | SARKAR WATER SUPPLY AGENCY | 10.68 | 0 | 100
1770 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
1771 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
1772 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000060/2022-2023 | 1936/MURD/1 | 18/07/2023 | 0 | Resource Division | 30.08 | 0 | 0
1773 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000315/2023-2024 | 1936/MURD/2 | 18/07/2023 | 0 | Resource Division | 2.74 | 0 | 0
1774 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System PART-B,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte.Part-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000017/2023-2024 | 991/MURD | 11/04/2023 | 120 | S.K. ENTERPRISE (SANDIP GHOSH) | 175.23 | 0 | 35
1775 | Murshidabad Division | Kandi Sub-Division | Construction of 350 Cum OHR, Boundwary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000029/2023-2024 | 1087/MURD | 20/04/2023 | 730 | MOTI RAHAMAN | 301.83 | 0 | 25
1776 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 723 | INDRAJIT MAZUMDAR | 10.68 | 0 | 100
1777 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Executive Engineer, Murshidabad Division, P.H.E. Dte. For (06) Six Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order) [Period for 06 (Six) Months].for the month of April 2025 to October 2025 [Vehicle No.WB93B0287] (i.e. from 05/04/2025 to 04/10/2025) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000085/2025-2026 | 784/MURD | 03/04/2025 | 183 | M/S. S. DAS AND ENTERPRISE | 0.75 | 0 | 25
1778 | Murshidabad Division | Kandi Sub-Division | Construction of surface drain of length 50 m at the Head work site of Gobarhati PWSS and Southern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000166/2023-2024 | 1971/MURD | 20/07/2023 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.88 | 0 | 100
1779 | Murshidabad Division | Kandi Sub-Division | Supplying fitting and fixing of R.B. T Concertina fencing on wall top of Gobarhati PWSS and Kandi Stack Yard under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000167/2023-2024 | 1972/MURD | 20/07/2023 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 5.14 | 0 | 80
1780 | Murshidabad Division | Kandi Sub-Division | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/02/2025 to 12/07/2025].for the month of February 2025 to July2025 [Vehicle No.WB58AR5026] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000475/2024-2025 | 390/MURD | 13/02/2025 | 150 | MD MUKLESUR RAHAMAN | 0.87 | 0 | 0
1781 | Murshidabad Division | Kandi Sub-Division | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Gokarna /Gobarhati Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000737/2023-2024 | 61/MURD | 08/01/2024 | 30 | MD SAJAHAN ALI | 5.47 | 0 | 100
1782 | Murshidabad Division | Kandi Sub-Division | Construction of surface drain of length 40.35 m at the Head work site of Gobarhati PWSS and eastern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000747/2023-2024 | 106/MURD | 10/01/2024 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.06 | 0 | 100
1783 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GABARHATI PWSS Scheme, Block - KANDI) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/002140/2021-2022 | 3257/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.51 | 0 | 1
1784 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000065/2022-2023 | 1043/MURD/2 | 17/04/2023 | 0 | Resource Division | 8.9 | 0 | 0
1785 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000307/2023-2024 | 1295/MURD/02 | 11/05/2023 | 0 | Resource Division | 8.9 | 0 | 0
1786 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-I water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000542/2022-2023 | 2716/MURD | 26/09/2022 | 365 | M/S. TAPAS KUMAR CHAKRABORTY | 334.37 | 0 | 95
1787 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Deputipara (Village Code -314582) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.EDte. (Scheme I.D.-0005186259). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000730/2020-2021 | 578/ MURD | 09/02/2021 | 60 | M/S ROY & BOSE ENTERPRISE | 17.93 | 0 | 1
1788 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 0 | 0
1789 | Murshidabad Division | Berhampur M/E Division | Restoration work of pipeline by relaying of UPVC pipeline of Godhanpara area (Kacharipara Gram Node Point 46 of 47) under command area of Godhanpara Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000797/2021-2022 | 503/ISD | 25/10/2021 | 30 | DEBEN RAJAK | 4.48 | 0 | 1
1790 | Murshidabad Division | Berhampur M/E Division | Restoration work of pipeline by relaying of UPVC pipeline of Godhanpara area (Deputipara paniparia Gram Node Point 9 of 17(A), Raninagar Bazarpara Node Point 3(A) to 4) under command area of Godhanpara Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000860/2021-2022 | 505/ISD | 25/10/2021 | 30 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.79 | 0 | 1
1791 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000044/2022-2023 | 3037/A/MURD | 16/11/2022 | 0 | Resource Division | 31.28 | 0 | 0
1792 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000048/2022-2023 | 3052/A/MURD | 17/11/2022 | 0 | Resource Division | 12.45 | 0 | 0
1793 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000292/2023-2024 | 1278/MURD/10 | 10/05/2023 | 0 | Resource Division | 25.62 | 0 | 0
1794 | Murshidabad Division | Berhampur Sub-Division | Allied work of Pipeline Laying of Distribution system and Construction of Pump House, Boundary Wall, of Shaktipur Zone-II Ground Based piped water supply scheme of Shaktipur Zone-II under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000042/2024-2025 | 1928/MURD | 03/07/2024 | 60 | HOQUEDAR ALI | 65.09 | 0 | 30
1795 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of Saktipur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000516/2022-2023 | 2497/MURD | 30/08/2022 | 1007 | CHAKRABORTY CONSTRUCTION | 286.01 | 0 | 60
1796 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000598/2022-2023 | 3072/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 21.18 | 0 | 1
1797 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 0 | 0
1798 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000006/2024-2025 | 1811/MURD/05 | 20/06/2024 | 0 | Resource Division | 17.54 | 0 | 0
1799 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000299/2023-2024 | 1278/MURD/7 | 10/05/2023 | 0 | Resource Division | 41.67 | 0 | 0
1800 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur (313919,313910,313912,313920) of Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000131/2022-2023 | 1230/MURD | 11/05/2022 | 60 | MOTI RAHAMAN | 32.62 | 0 | 0
1801 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Panchgachhia (Village code 313919) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000155/2020-2021 | 526/MURD | 04/02/2021 | 60 | DIPAYAN DEY | 17.32 | 0 | 0
1802 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000109/2022-2023 | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 20
1803 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juginda (Zone-II) Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000129/2023-2024 | 1766/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 35.34 | 0 | 90
1804 | Murshidabad Division | Berhampur M/E Division | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Entrance Gate under Karimpur Jalangi (Zone-I) Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000217/2021-2022 | 276/ISD | 03/06/2021 | 60 | ROBIN ROY | 3.32 | 0 | 1
1805 | Murshidabad Division | Berhampur M/E Division | Renovation of Pump House No. 1 of Karimpur Jalangi (Zone-I) Water Supply Scheme under Jalangi Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte.in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000301/2021-2022 | 382/A/ISD | 26/07/2021 | 60 | ROBIN ROY | 2.25 | 0 | 1
1806 | Murshidabad Division | Berhampur M/E Division | Relaying of distribution pipeline on damaged line from Node Point 24 to 25 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000307/2021-2022 | 388/ISD | 26/07/2021 | 30 | ROBIN ROY | 4.83 | 0 | 1
1807 | Murshidabad Division | Berhampur M/E Division | Relaying of distribution pipeline on damaged line from Node Point 21 to 22 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000309/2021-2022 | 382/ISD | 26/07/2021 | 30 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 4.82 | 0 | 1
1808 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Karimpur Jalangi Zone-I(Part-B) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000356/2022-2023 | 1996/MURD | 21/07/2022 | 1430 | M/S. BIMALENDU BOSE | 267.14 | 0 | 81
1809 | Murshidabad Division | Berhampur M/E Division | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000740/2023-2024 | 65/MURD | 08/01/2024 | 60 | S.S.INFRASTRUCTURE | 134.77 | 0 | 10
1810 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000035/2024-2025 | MURD/2481/07 | 04/09/2024 | 0 | Resource Division | 18.05 | 0 | 0
1811 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000043/2022-2023 | 2780/L/MURD | 01/10/2022 | 0 | Resource Division | 18.05 | 0 | 0
1812 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000164/2023-2024 | 1180/MURD/10 | 29/04/2023 | 0 | Resource Division | 64.63 | 0 | 0
1813 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 371 of 21-22 by EE MSD. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000354/2022-2023 | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.24 | 0 | 0
1814 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Karimpur- Jalangi Zone-I PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 370 of 21-22 by EE MSD. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000355/2022-2023 | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 9.77 | 0 | 0
1815 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-III PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 372 of 21-22 by EE MSD. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000356/2022-2023 | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.38 | 0 | 0
1816 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-A Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000587/2022-2023 | 3056/MURD | 17/11/2022 | 30 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 1
1817 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of JALANGI ZONE-III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000813/2022-2023 | 671/MURD | 09/03/2023 | 906 | MAMATA USHA ENTERPRISE | 637.19 | 0 | 100
1818 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000245/2023-2024 | 1219/MURD/28 | 03/05/2023 | 0 | Resource Division | 65.29 | 0 | 0
1819 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- A. |  |  | ORD/000234/2022-2023 | 206/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0
1820 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- B. |  |  | ORD/000235/2022-2023 | 207/LSD | 11/05/2022 | 30 | AMIT KUMAR SAHA | 4.91 | 0 | 0
1821 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- C. |  |  | ORD/000236/2022-2023 | 208/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.86 | 0 | 0
1822 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- A. |  |  | ORD/000245/2022-2023 | 217/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.91 | 0 | 0
1823 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- B. |  |  | ORD/000246/2022-2023 | 218/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0
1824 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- G. |  |  | ORD/000273/2022-2023 | 244/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0
1825 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- I. |  |  | ORD/000275/2022-2023 | 246/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.86 | 0 | 0
1826 | Murshidabad Division |  | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- K. |  |  | ORD/000277/2022-2023 | 248/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.75 | 0 | 0
1827 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Dahapara Dham Station ( TP NO 174/24 & 174/22) at Aminabazar Rail Gumit mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000426/2020-2021 | 543/MURD | 05/02/2021 | 30 | M/S. GOUTAM CHAKRABORTY | 33.47 | 0 | 0
1828 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000442/2020-2021 | 544/MURD | 05/02/2021 | 30 | J.S. CONSTRUCTION | 15.55 | 0 | 0
1829 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000463/2020-2021 | 545/MURD | 05/02/2021 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 0 | 0
1830 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm diaUPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _1 |  |  | ORD/000887/2022-2023 | 407/MURD | 15/02/2023 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 0 | 0
1831 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _2 |  |  | ORD/000888/2022-2023 | 408/MURD | 15/02/2023 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 0 | 0
1832 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000889/2022-2023 | 409/MURD | 15/02/2023 | 30 | J.S. CONSTRUCTION | 15.55 | 0 | 0
1833 | Murshidabad Division | Berhampur M/E Division | Installation of flow measuring devices on distribution network of MITHIPUR WATER SUPPLY SCHEME OF JANGIPUR SUB-DIVISION UNDER MURSHIDABAD DIVISION, PHE DTE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000070/2025-2026 | 1245/MURD | 29/05/2025 | 30 | DHPE | 3.21 | 0 | 0
1834 | Murshidabad Division | Berhampur M/E Division | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000071/2024-2025 | 2022/MURD | 11/07/2024 | 345 | DHPE | 15.34 | 0 | 25
1835 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mithipur Water Supply Scheme as required at Raghunathganj-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000102/2023-2024 | 1743/MURD | 06/07/2023 | 619 | NADIA TUBEWELLS | 11.78 | 0 | 100
1836 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System and Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & 2(two) nos Pump House Office cum godown repairing., for Augmentation of MITHIPUR PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000704/2022-2023 | 145/MURD | 17/01/2023 | 90 | MONDAL ENTERPRISE | 82.55 | 0 | 80
1837 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Augmentation MITHIPUR Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000705/2022-2023 | 119/MURD | 13/01/2023 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 49.44 | 0 | 100
1838 | Murshidabad Division | Berhampur M/E Division | Construction of 250 Cum OHR for Augmentation of Mithipur Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | ORD/000722/2022-2023 | 172/MURD | 18/01/2023 | 1079 | SANJIB GHOSH | 94.37 | 0 | 100
1839 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | RTOR000025/2024-2025 | MURD/2481 | 04/09/2024 | 0 | Resource Division | 23.69 | 0 | 0
1840 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,Junior engineer-II | RTOR000306/2023-2024 | 1295/MURD/06 | 11/05/2023 | 0 | Resource Division | 6.13 | 0 | 0
1841 | Murshidabad Division | Berhampur M/E Division | Restoration of Road which were damaged during laying of Pipeline under Islampore Sub Division PHE DTE. under Murshidabad Division PHE DTE. Ref Memo No: 488/ISD Dt. 26.09.2024 of the AE/ISD PHE DTE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/01230/2024-2025 | 493-MSD/2024-25 | 04/10/2024 | 0 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 9.19 | 0 | 0
1842 | Murshidabad Division | Berhampur M/E Division | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000043/2022-2023 | 1116/MURD | 29/04/2022 | 120 | CHAKRABORTY CONSTRUCTION | 317.51 | 0 | 1
1843 | Murshidabad Division | Berhampur M/E Division | Construction of One no Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Laying of Rising Main, Construction of 450 Cum OHR, Land Development Works at Nabipur Water Supply scheme at Raninagar-II Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000112/2024-2025 | 2302/MURD | 12/08/2024 | 250 | PRAFULLYA CONSTRUCTION | 207.59 | 0 | 0
1844 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Nabipur, Bilpachakopra (Village Code -314590,314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000641/2022-2023 | 3337/MURD | 15/12/2022 | 1140 | AZAD ENTERPRISE | 58.72 | 0 | 70
1845 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (NABIPUR PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000830/2021-2022 | 3263/MURD | 05/10/2021 | 60 | RADIANT | 6.45 | 0 | 1
1846 | Murshidabad Division | Berhampur M/E Division | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000903/2022-2023 | 1116 /MURD | 29/04/2022 | 1120 | CHAKRABORTY CONSTRUCTION | 317.51 | 0 | 80
1847 | Murshidabad Division | Berhampur M/E Division | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Nabipur PWSS under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/001719/2021-2022 | 153/ISD | 17/03/2022 | 30 | G MITRA & ASSOCIATES | 1.48 | 0 | 100
1848 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000022/2022-2023 | 2507/D/MURD | 31/08/2022 | 0 | Resource Division | 11.45 | 0 | 0
1849 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000054/2022-2023 | 3052/G/MURD | 17/11/2022 | 0 | Resource Division | 23.03 | 0 | 0
1850 | Murshidabad Division | Berhampur M/E Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILPACHAKOPRA (Village Code 314584) under NABIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 54 of 20-21 by EE MURD | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | VCH/001501/2021-2022 | 36-MSD/22-23 | 23/04/2022 | 0 | NOVELTY CONSTRUCTION | 6.31 | 0 | 0
1851 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHHAIGHARI G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001193/2021-2022 | 355/LSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 0 | 0
1852 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jadupur (Village code 315357) under Jadupur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184179 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001774/2021-2022 | 816/MURD | 25/03/2022 | 30 | M/S. CHOWDHURY CONSTRUCTION | 24.32 | 0 | 0
1853 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000020/2021-2022 | 539/5/MURD | 25/02/2022 | 0 | Resource Division | 2.92 | 0 | 0
1854 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
1855 | Murshidabad Division |  | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 227/3 & 227/4) at Khidirpur mouza & Connecting with existing 200 mm dia uPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. |  |  | ORD/001715/2021-2022 | 511/MURD | 23/02/2022 | 60 | PRADIP KUMAR DAS | 32.67 | 0 | 0
1856 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-20 |  |  | VCH/000985/2022-2023 | 400-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0
1857 | Murshidabad Division |  | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Garaimari (Village code 314734) under Garaimari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. (Scheme ID 0005019114) |  |  | ORD/000188/2020-2021 | 665/MURD | 19/02/2021 | 180 | ALOK ENTERPRISE | 390.36 | 0 | 1
1858 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GORAIMARI (Village Code 314734) under GORAIMARI Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. |  |  | VCH/001486/2021-2022 | 421-MSD/21-22 | 23/03/2022 | 0 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 137.73 | 0 | 0
1859 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lakshminathpur (Village code 314696) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-01) |  |  | ORD/000349/2021-2022 | 2500/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 65.1 | 0 | 0
1860 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 329 in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshminathpur (Village code 314696) under Domkal Ground water based water supply scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005184127). |  |  | ORD/001708/2021-2022 | 693/MURD | 14/03/2022 | 30 | SUJIT KUMAR SAHA | 19.11 | 0 | 1
1861 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SARBANGAPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PARESNATHPUR , CODE-315529, TNO- 604/2020-21/EE |  |  | VCH/002015/2020-2021 | 512/W | 30/03/2021 | 0 | RATAN DUTTA | 25.78 | 0 | 0
1862 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --AMARKUNDU-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- RAINDA , CODE- 315025, TNO- 684/2020-21/EE |  |  | VCH/002019/2020-2021 | 512/W | 30/03/2021 | 0 | SAMAR MUKHERJEE | 21.62 | 0 | 0
1863 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAZAESAU (Village Code 315629) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000566/2020-2021 | 3012/MURD | 04/12/2020 | 45 | SANJAY BISWAS | 26.55 | 0 | 0
1864 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Saktipur ( Village Code -315633) under Saktipur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, P.H.E Dte. Scheme Id - 5185583 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000764/2020-2021 | 45/MURD | 06/01/2021 | 1547 | CHAKRABORTY CONSTRUCTION | 119.73 | 0 | 45
1865 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MAHATA (Village Code 315638) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000769/2020-2021 | 3014/MURD | 04/12/2020 | 45 | SO-FINE AQUARIUM | 12.76 | 0 | 0
1866 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village KATAIKONA (Village Code 315631) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000770/2020-2021 | 3013/MURD | 04/12/2020 | 45 | MAJUMDER CONSTRUCTION | 35.53 | 0 | 50
1867 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village MAIN(Village Code 315632) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000771/2020-2021 | 3018/MURD | 04/12/2020 | 45 | MAJUMDER CONSTRUCTION | 34.29 | 0 | 40
1868 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JANPUR (Village Code 315676) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000187/2020-2021 | 3009/MURD | 04/12/2020 | 45 | KUNDU CONSTRUCTION | 20.35 | 0 | 0
1869 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Takipur(Village code 315667) under Rejinagar Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723375 in the District of Murshidabad. (Sl No-10) | ASSISTANT ENGINEER |  | ORD/000286/2020-2021 | 3049/MURD | 08/12/2020 | 180 | RAJKUMAR MONDAL | 80.54 | 0 | 1
1870 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000451/2021-2022 | 301/BSD | 13/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 4.34 | 0
1871 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village RAMNA DADPUR (Village Code 315668) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000461/2020-2021 | 3007/MURD | 04/12/2020 | 45 | R.R. CONSTRACTION | 31.15 | 0 | 0
1872 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village PILKHANA (Village Code 315666) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000482/2020-2021 | 3011/MURD | 04/12/2020 | 45 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 20.18 | 0 | 1
1873 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village AMARPUR (Village Code 315675) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000575/2020-2021 | 3006/MURD | 04/12/2020 | 45 | M/S. S. DAS AND ENTERPRISE | 39.98 | 0 | 0
1874 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village JAGAMOHANPUR (Village Code 315677) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000641/2020-2021 | 3010/MURD | 04/12/2020 | 45 | PARTHA BHASKAR | 15.79 | 0 | 1
1875 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ramna Dadpur (Village Code -315668) Part-B under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000738/2022-2023 | 265/BSD | 24/06/2022 | 30 | R.R. CONSTRUCTION | 4.74 | 0 | 0
1876 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ramna Dadpur ( Village Code -315668) Part-A under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000739/2022-2023 | 266/BSD | 24/06/2022 | 30 | R.R. CONSTRUCTION | 4.52 | 0 | 0
1877 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Rajinagar (Village code 315663) under Rejinagar Ground Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHEDte. Scheme ID 0001723375 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/001150/2021-2022 | 3960/MURD | 20/12/2021 | 120 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 64.06 | 0 | 1
1878 | Murshidabad Division | Berhampur Sub-Division | Providing Balance Functional Household Tap Connection (FHTC) of 208 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janpur (Village code 315676) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.(Scheme ID- 0001723470) | ASSISTANT ENGINEER |  | ORD/001747/2021-2022 | 784/MURD | 23/03/2022 | 20 | KUNDU CONSTRUCTION | 15 | 0 | 1
1879 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER |  | RTOR000023/2021-2022 | 539/8/MURD | 25/02/2022 | 0 | Resource Division | 1.14 | 0 | 0
1880 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JANPUR (Village Code 315676) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. NIeT No- WBPHED/EE/MSD/03 OF 2020-2021 _SL_04, 3009/MURD | ASSISTANT ENGINEER |  | VCH/000687/2021-2022 | 169-MSD/2021-22 | 01/11/2021 | 0 | KUNDU CONSTRUCTION | 19.96 | 0 | 0
1881 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur (315668) of Rejinagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block of Murshidabad District (PART-I) | ASSISTANT ENGINEER |  | VCH/001295/2021-2022 |  | 17/02/2022 | 0 | R.R. CONSTRUCTION | 27.41 | 0 | 0
1882 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Takipur (Village code 315667) under Rejinagar Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723375 in the District of Murshidabad. (Sl No-10). Tender no - 52 of 21-22 by SE MC | ASSISTANT ENGINEER |  | VCH/001387/2021-2022 | 335-MSD/21-22 | 25/02/2022 | 0 | RAJKUMAR MONDAL | 35.53 | 0 | 0
1883 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AMARPUR (Village Code 315675) under REJINAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 618 of 21-22 by EE MURD | ASSISTANT ENGINEER |  | VCH/001427/2021-2022 | 348-MSD/21-22 | 05/03/2022 | 0 | M/S. S. DAS AND ENTERPRISE | 36.35 | 0 | 0
1884 | Murshidabad Division | Berhampur Sub-Division | Additional works for Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PILKHANA (Village Code 315666) under REJINAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block under Murshidabad Division PHE DTE. Tender no - 544 of 20-21 by EE MURD | ASSISTANT ENGINEER |  | VCH/001449/2021-2022 | 349-MSD/21-22 | 05/03/2022 | 0 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 12.47 | 0 | 0
1885 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur (315668) of Rejinagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block of Murshidabad District under Murshidabad Division PHE DTE. Tender no - 830 of 20-21 by EE MURD | ASSISTANT ENGINEER |  | VCH/001457/2021-2022 | 345-MSD/21-22 | 05/03/2022 | 0 | R.R. CONSTRUCTION | 27.41 | 0 | 0
1886 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER | Junior Engineer | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
1887 | Murshidabad Division | Islampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Barabil Raghunathpur Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000592/2022-2023 | 3062/MURD | 17/11/2022 | 30 | GENUINE | 11.75 | 0 | 100
1888 | Murshidabad Division | Islampur Sub-Division | Augmentation of Ground Water Based Barabil Raghunathpur zone-I PWSS to accommodate FHTC of 105 nos household, Laying Distribution System, Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works,Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging hight 20 mtr. for Barabil Raghunathpur ( ZONE-I ) Ground water based Piped water supply scheme at Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | ORD/000600/2023-2024 | 3355/MURD | 30/10/2023 | 150 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 155.66 | 0 | 30
1889 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | Junior Engineer | RTOR000161/2023-2024 | 1180/MURD/31 | 29/04/2023 | 0 | Resource Division | 55.46 | 0 | 0
1890 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
1891 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
1892 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
1893 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000119/2023-2024 | 1167/MURD/13 | 28/04/2023 | 0 | Resource Division | 122.55 | 0 | 0
1894 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I B Water Supply Scheme at Head Work Site, 2nd Site site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000124/2023-2024 | 1774/MURD | 06/07/2023 | 21 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0
1895 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
1896 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000129/2023-2024 | 1167/MURD/29 | 28/04/2023 | 0 | Resource Division | 24.86 | 0 | 0
1897 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SIKDARPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000015/2025-2026 | 962/MURD | 30/04/2025 | 60 | SAMAR MUKHERJEE | 19.62 | 0 | 0
1898 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
1899 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
1900 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000557/2023-2024 | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0
1901 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sikdarpur Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000715/2023-2024 | 3833/MURD | 14/12/2023 | 627 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 40
1902 | Murshidabad Division | Lalbag Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000135/2024-2025 | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 40
1903 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 0 | 100
1904 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
1905 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kantanagar PWSS in Bhagwangola-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000586/2023-2024 | 3321/MURD | 22/10/2023 | 557 | M/S GUHA AND ROY | 625.7 | 0 | 40
1906 | Murshidabad Division | Lalbag Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1907 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000124/2023-2024 | 1167/MURD/24 | 28/04/2023 | 0 | Resource Division | 17.33 | 0 | 0
1908 | Murshidabad Division | Berhampur Sub-Division | Construction of 100 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 65 Cum capacity for Augmentation of SUNGAI PWSS in Berhampore Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000146/2023-2024 | 1869/MURD | 14/07/2023 | 764 | BABLU ENTERPRISE | 94.57 | 0 | 30
1909 | Murshidabad Division | Berhampur Sub-Division | FHTC Connection to 349 nos household, Laying of Distribution System for Augmentation of SUNGAI PWSS in Berhampore Block , Berhampore Sub-Division under Murshidabad Division , PHE. Dte.(Part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000235/2023-2024 | 2406/MURD | 07/08/2023 | 205 | ANKITA ENTERPRISE | 58.83 | 0 | 60
1910 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1911 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall (Fornt Side) at SUNAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001213/2021-2022 | 63/BSD | 24/02/2022 | 45 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.85 | 0 | 100
1912 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall (East Side) at SUNGAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001660/2021-2022 | 65/BSD | 24/02/2022 | 30 | PRASANTA BISWAS | 4.82 | 0 | 100
1913 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
1914 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall (North Side) at SUNAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/002045/2021-2022 | 64/BSD | 24/02/2022 | 45 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.84 | 0 | 100
1915 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000015/2024-2025 | 1811/MURD/14 | 20/06/2024 | 0 | Resource Division | 2.55 | 0 | 0
1916 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000216/2023-2024 | 1219/MURD/06 | 03/05/2023 | 0 | Resource Division | 14.2 | 0 | 0
1917 | Murshidabad Division | Berhampur M/E Division | Augmentation of Domkal Zone-II (Part-A) Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000055/2023-2024 | 1311/MURD | 11/05/2023 | 916 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 593.84 | 0 | 10
1918 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 0 | 100
1919 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Domkal Zone-I (Part-B) & Domkal Zone - II (Part - A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000828/2022-2023 | 692/MURD | 10/03/2023 | 280 | M/S. J. A. CONSTRUCTION | 107.58 | 0 | 10
1920 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000254/2023-2024 | 1219/MURD/39 | 03/05/2023 | 0 | Resource Division | 78.66 | 0 | 0
1921 | Murshidabad Division | Kandi Sub-Division | SALU & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000279/2023-2024 | 2642/MURD | 23/08/2023 | 584 | M/S. CHAKRABORTY & COMPANY | 601.12 | 0 | 20
1922 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000062/2023-2024 | 1043/MURD/12 | 18/04/2023 | 0 | Resource Division | 13.2 | 0 | 0
1923 | Murshidabad Division | Kandi Sub-Division | Construction of pathway and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000006/2022-2023 | 08 / KSD | 06/04/2022 | 45 | BIMALENDU BOSE | 4.84 | 0 | 1
1924 | Murshidabad Division | Kandi Sub-Division | Supplying fitting and fixing of R.B.T Concertina fencing on wall top and construction of surface drain at Head work site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000011/2022-2023 | 12 / KSD | 06/04/2022 | 45 | DEBJYOTI MUKHERJEE | 4.73 | 0 | 1
1925 | Murshidabad Division | Kandi Sub-Division | Construction of Boundary Wall & Pump House with sanitary & plumbing work (3rd & 4th T/W Site) of Mahalandi (Zone-II) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000082/2024-2025 | 2075/MURD | 19/07/2024 | 60 | AHAMMED ENTERPRISE | 28.77 | 0 | 0
1926 | Murshidabad Division | Kandi Sub-Division | Construction of boundary wall at Northern side of Head work site of Mahalandi (Zone-I) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000110/2020-2021 | 2976/MURD | 01/12/2020 | 45 | JYOTI TRADERS | 4.14 | 0 | 1
1927 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000132/2023-2024 | 1758/MURD | 06/07/2023 | 576 | R.K. DRILLING SERVICES | 23.58 | 0 | 70
1928 | Murshidabad Division | Kandi Sub-Division | Providing FHTC Connection to 818 nos. household , Construction of 300 Cum OHR, Laying of Distribution System, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 200 Cum capacity of staging height 20 mtr. Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works , Construction of Pump House with sanitary and Water Supply Arrangement & Boundary Wall, for Augmentation work of MAHALANDI ZONE-II Kandi Block under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000247/2023-2024 | 2468/MURD | 09/08/2023 | 876 | M/S. BIMALENDU BOSE | 451.48 | 0 | 10
1929 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-II Water Supply Scheme at HW Site under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000597/2022-2023 | 3071/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 0 | 100
1930 | Murshidabad Division | Kandi Sub-Division | Construction of boundary wall at Front side of Head work site including gate of Mahalandi (Zone-II) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001194/2021-2022 | 336/KSD | 30/11/2021 | 45 | A.P. CONSTRUCTION | 4.92 | 0 | 1
1931 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000002/2023-2024 | 1043/MURD/6 | 17/04/2023 | 0 | Resource Division | 150.69 | 0 | 0
1932 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for GHORAMARA Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000043/2025-2026 | 1190/MURD | 23/05/2025 | 60 | M/S. GOUTAM CHAKRABORTY | 23.01 | 0 | 0
1933 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at GHORAMARA Water Supply Scheme atHead Work Site, 2nd Site site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000116/2023-2024 | 1760/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 18.45 | 0 | 100
1934 | Murshidabad Division | Berhampur Sub-Division | Balance and allied works for providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and under command area of village of GHORAMARA (Village Code -315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000165/2022-2023 | 154/BSD | 12/04/2022 | 30 | M/S M.S. ENTERPRISE | 4.69 | 0 | 1
1935 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
1936 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
1937 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 176 nos household ,Construction of 200 Cum OHR, Rising Main , for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000882/2022-2023 | 906/MURD | 22/03/2023 | 1320 | PRATICHI ENTERPRISE | 120.97 | 0 | 80
1938 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000884/2022-2023 | 901/MURD | 29/03/2023 | 917 | M/S RUBIET HOSSAIN | 172.57 | 0 | 20
1939 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 1
1940 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 0 | 100
1941 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
1942 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000097/2023-2024 | 1147/MURD/12 | 27/04/2023 | 0 | Resource Division | 110.07 | 0 | 0
1943 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Faridpur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000535/2022-2023 | 2642/MURD | 19/09/2022 | 1096 | PRADIP KUMAR DAS | 742.15 | 0 | 45
1944 | Murshidabad Division | Berhampur M/E Division | Restoration work of Distribution Pipeline by laying of UPVC pipe at different location of Vulnerable Area of command area of Faridpur-II W/S Scheme under Islampur Sub-Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000577/2022-2023 | 277/ISD | 03/06/2022 | 30 | SHIBAM ENTERPRISE | 4.8 | 0 | 1
1945 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000030/2022-2023 | 2508/B/MURD | 31/08/2022 | 0 | Resource Division | 3.41 | 0 | 0
1946 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000030/2024-2025 | MURD/2481/03 | 04/09/2024 | 0 | Resource Division | 34.04 | 0 | 0
1947 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000034/2022-2023 | 2780/C/MURD | 01/10/2022 | 0 | Resource Division | 24.7 | 0 | 0
1948 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000046/2022-2023 | 3037/C/MURD | 16/11/2022 | 0 | Resource Division | 107.03 | 0 | 0
1949 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000154/2023-2024 | 1180/MURD/03 | 29/04/2023 | 0 | Resource Division | 107.03 | 0 | 0
1950 | Murshidabad Division | Berhampur M/E Division | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Ramnarayanpara (314614) of Narasinghapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000115/2022-2023 | 1198/MURD | 10/05/2022 | 60 | NADIA TUBEWELLS | 32.63 | 0 | 100
1951 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ramnarayanpara (Village code 314614) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000507/2020-2021 | 86/MURD | 08/01/2021 | 60 | M/S. MONDAL ENTERPRISE | 12.66 | 0 | 0
1952 | Murshidabad Division | Berhampur Sub-Division | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2023-WL-01 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00290/2023-2024 | 157-MSD/2023-24 | 28/06/2023 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 5.5 | 0 | 0
1953 | Murshidabad Division | Berhampur Sub-Division | Allied work of Laying Distribution System, Rising Main, Construction of Boundary wall, Service Road of Arazi Madhupur & adjoining moujas PWSS under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000035/2024-2025 | 1911/MURD | 02/07/2024 | 403 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 79.82 | 0 | 65
1954 | Murshidabad Division | Berhampur Sub-Division | Relaying of pipe line for connection of Gobindapur Junior High School and 29, Gobindapur Junior Basic School under command area of ARAJIMADHUPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000058/2020-2021 | 3176/MURD | 16/12/2020 | 15 | DATA ENTERPRISE | 4.58 | 0 | 0
1955 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Arazi Madhupur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000593/2022-2023 | 3066/MURD | 17/11/2022 | 30 | NADIA TUBEWELLS | 10.6 | 0 | 0
1956 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of Arazi Madhupur & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Berhampore Block within Berhampore Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000604/2022-2023 | 3171/MURD | 30/11/2022 | 1036 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 200.36 | 0 | 80
1957 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ARAZI MADHUPUR Water Supply Scheme at 2nd Site site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000707/2023-2024 | 3809/MURD | 12/12/2023 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 90
1958 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
1959 | Murshidabad Division | Berhampur Sub-Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Kanthalia Road (KTLR) Station to Karna Subarna (KNSN) (TP NO 151/33 & 151/36) at Karna Subarna Station Gumti mouza & Connecting with existing 140mm dia HDPE distribution main line of Arazi Madhupur Ground Based W/S Scheme , Berhampore Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000821/2023-2024 | 742/MURD | 12/03/2024 | 363 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 34.02 | 0 | 80
1960 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (ARAJI MADHUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000836/2021-2022 | 3269/MURD | 05/10/2021 | 60 | RADIANT | 3.15 | 0 | 1
1961 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000185/2023-2024 | 1210/MURD/02 | 02/05/2023 | 0 | Resource Division | 4.99 | 0 | 0
1962 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Gria,Sekendra, Mithipur,Jotkomal,Dayarampur & Samatinagar) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000017/2020-2021 | 68 /JSD | 25/02/2021 | 30 | S.S.INFRASTRUCTURE | 2.38 | 0 | 0
1963 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kanupur(Village code 313992) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-12) |  |  | ORD/000531/2020-2021 | 3067/MURD | 08/12/2020 | 180 | MODERN CONSTRUCTION | 75.3 | 0 | 0
1964 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-I Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001180/2021-2022 | 367/JSD | 22/12/2021 | 30 | IMAGIN | 1.88 | 0 | 0
1965 | Murshidabad Division | Lalbag Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kolan Radhakantapur(Village code 314523) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-04) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000261/2022-2023 | 207-MSD/22-23 | 15/07/2022 | 0 | M/S GUNGUN CONSTRUCTION | 31.97 | 0 | 0
1966 | Murshidabad Division |  | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. |  |  | ORD/001241/2021-2022 | 47/ISD | 28/01/2022 | 60 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 3.46 | 0 | 0
1967 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001174/2021-2022 | 364/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0
1968 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-I). |  |  | ORD/001752/2021-2022 | 121/JSD | 22/03/2022 | 30 | DIPAYAN DEY | 4.2 | 0 | 0
1969 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-III). |  |  | ORD/001760/2021-2022 | 126/JSD | 22/03/2022 | 30 | DIPAYAN DEY | 3.73 | 0 | 0
1970 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-IV). |  |  | ORD/001761/2021-2022 | 127/JSD | 22/03/2022 | 30 | MOTI RAHAMAN | 3.5 | 0 | 0
1971 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-II). |  |  | ORD/001762/2021-2022 | 128/JSD | 22/03/2022 | 30 | MURSHID ALOM | 3.87 | 0 | 90
1972 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 540/11/MURD | 25/02/2022 | 0 | Resource Division | 2.2 | 0 | 0
1973 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Jhamra ( 314121 ) under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - I Block of Murshidabad District PHE DTE. (Scheme ID: 0001756852). Tender no 786 of 20-21 by EE |  |  | VCH/000190/2021-2022 | 16-MSD / 21-22 | 04/08/2021 | 0 | MOTI RAHAMAN | 30.49 | 0 | 0
1974 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-II ) TNO- 786/20-21/EE |  |  | VCH/000864/2021-2022 | 206-MSD/21-22 | 25/11/2021 | 0 | MOTI RAHAMAN | 2.76 | 0 | 0
1975 | Murshidabad Division |  | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 06/21-22/AE-LSD |  |  | VCH/000867/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 2.93 | 0 | 0
1976 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kusbaria (Village code 314722) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723334 |  |  | ORD/000420/2021-2022 | 2596/MURD | 25/08/2021 | 180 | M/S NIRAPADA BHATTACHARJEE | 73.51 | 0 | 1
1977 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Brindabanpur (Village Code -314567) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019111). |  |  | ORD/000445/2020-2021 | 582/MURD | 09/02/2021 | 60 | M/S. BIMALENDU BOSE | 64.07 | 36.02 | 0
1978 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 437 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Brindabanpur (Village code 314567) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111). |  |  | ORD/001798/2021-2022 | 856/MURD | 31/03/2022 | 15 | BIMALENDU BOSE | 9.64 | 0 | 0
1979 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kantanagar ( Village Code -314437) (Part-I) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186155) |  |  | ORD/000323/2021-2022 | 2396/MURD | 10/08/2021 | 60 | M/S. GHOSH ENTERPRISE | 94.58 | 0 | 0
1980 | Murshidabad Division |  | Allied work for Laying of different dia UPVC Pipeline at Chaipara, Kupkandi, Kalinagar, Dararkandi, Ashan para & Tikor para area of village Kantanagar ( Village Code 314437) in connection with "Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kantanagar ( Village Code 314437) (Part-I) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E. Dte. (Scheme I.D.- 0005186155)" (Part-C). |  |  | ORD/000354/2022-2023 | 296/LSD | 12/07/2022 | 30 | DEBASISH SARKAR | 4.76 | 0 | 0
1981 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kantanagar ( Village Code -314437) (Part-II) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.- 0005186155) |  |  | ORD/000398/2021-2022 | 2534/MURD | 19/08/2021 | 60 | J.S. CONSTRUCTION | 94.61 | 59.54 | 0
1982 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at LALGOLA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000399/2021-2022 | 243/LSD | 18/08/2021 | 30 | IMAGIN | 4.18 | 0 | 0
1983 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BILBORAKOPRA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000401/2021-2022 | 244/LSD | 18/08/2021 | 30 | IMAGIN COMMUNICATION | 4.18 | 0 | 0
1984 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KANTANAGAR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000405/2021-2022 | 247/LSD | 18/08/2021 | 30 | IMAGIN | 4.18 | 0 | 1
1985 | Murshidabad Division |  | Restoration of road for laying of different dia UPVC/CI/DI pipelines at jali Bagicha area under the Improvement work of Kantanagar Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. |  |  | ORD/001279/2021-2022 | 417/LSD | 31/12/2021 | 7 | ANUPA ENTERPRISE | 0.94 | 0 | 0
1986 | Murshidabad Division |  | Laying of Different dia UPVC Pipeline at Jalibagicha, Kupkandi, Kalinagar, Dararkandi, Ashan para & Tikor para area of village Kantanagar (Village Code-314437) in connection with " Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kantanagr (Village code 314437) Part-II & adjoining habitation under Kantanagar Ground water based water supply scheme for Arsenic Affected Area of Bhagwangola-I Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005186155). |  |  | ORD/001726/2021-2022 | 706/MURD | 14/03/2022 | 60 | J.S. CONSTRUCTION | 37.51 | 0 | 0
1987 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village KANTANAGAR (Village Code 314437) PART-I under KANTANAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHGWANGOLA-I Block in the District of Murshidabad. Tender no - 271 of 21-22 by EE MURD |  |  | VCH/001484/2021-2022 | 392-MSD/21-22 | 23/03/2022 | 0 | M/S. GHOSH ENTERPRISE | 61.6 | 0 | 0
1988 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gokulpur Gobindapur(Village code 314659) under Baniakhai Ground Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723470 in the District of Murshidabad. |  |  | ORD/000526/2021-2022 | 2619/MURD | 26/08/2021 | 180 | M/S PARIMAL DAS | 105.05 | 0 | 1
1989 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) |  |  | VCH/001293/2021-2022 |  | 17/02/2022 | 0 | M/S PARIMAL DAS | 103.01 | 0 | 0
1990 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gokulpur Gobindapur (314659) under Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under MSD PHE DTE. Tender No - 15 of 21-22 by SE MC |  |  | VCH/001426/2021-2022 | 344-MSD/21-22 | 04/03/2022 | 0 | M/S PARIMAL DAS | 103.01 | 0 | 0
1991 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sujanipara (Village code 313923) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. |  |  | ORD/000045/2020-2021 | 528/MURD | 04/02/2021 | 60 | R.K. CONSTRUCTION | 33.78 | 0 | 0
1992 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1837nos household under command area of village of Panchgachhia, Arazi Ramakantapur,Gotha,Sadkpur( Village Code-313919, 313910, 313912, 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756899) |  |  | ORD/000130/2022-2023 | 1214/MURD | 10/05/2022 | 60 | SWAPAN DAS | 79.18 | 0 | 1
1993 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID : 0001756899 in the District of Murshidabad. |  |  | ORD/000162/2020-2021 | 542/MURD | 05/02/2021 | 60 | SHIRSHENDU MUKHERJEE | 7.73 | 0 | 1
1994 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madna(CT) (Village code 313940) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. |  |  | ORD/000344/2021-2022 | 2476/MURD | 16/08/2021 | 60 | NOVELTY CONSTRUCTION | 39.3 | 0 | 1
1995 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikpur (Village code 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. |  |  | ORD/000514/2020-2021 | 524/MURD | 04/02/2021 | 60 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 33.02 | 0 | 1
1996 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Ramakantapur (Village code 313910) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. |  |  | ORD/000564/2020-2021 | 533/MURD | 04/02/2021 | 60 | M H SUPPLIERS | 16.7 | 16.7 | 1
1997 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. |  |  | ORD/000684/2020-2021 | 542 / MURD | 05/02/2021 | 60 | SHIRSHENDU MUKHERJEE | 7.73 | 0 | 1
1998 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHGACHHIA (Village Code 313919) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 790 of 20-21 by EE MURD |  |  | VCH/000294/2022-2023 | 104-MSD/22-23 | 06/05/2022 | 0 | DIPAYAN DEY | 15.99 | 0 | 0
1999 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sujanipara (313923) of Madna under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District (PART-I) |  |  | VCH/001288/2021-2022 |  | 17/02/2022 | 0 | R.K. CONSTRUCTION | 33.77 | 0 | 0
2000 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SUJANIPARA (Village Code 313923) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 44 of 21-22 by EE MURD |  |  | VCH/001448/2021-2022 | 350-MSD/21-22 | 04/03/2022 | 0 | R.K. CONSTRUCTION | 33.77 | 0 | 0
2001 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balarambati ( Village Code -314285) under Monigram Balarambati Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005252584) |  |  | ORD/000057/2021-2022 | 1210/MURD | 10/05/2021 | 60 | TARIKUL SK | 43.33 | 0 | 1
2002 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Manigram (Village code 314284) under Monigram Balarambati Ground Water Based Water Supply Scheme for Arsenic Affected Area of Sagardighi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005252584 in the District of Murshidabad. |  |  | ORD/000533/2020-2021 | 527/MURD | 04/02/2021 | 60 | AMAL KUMAR DAS | 43.9 | 0 | 1
2003 | Murshidabad Division | Berhampur M/E Division | BAJITPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000011/2023-2024 | 959/MURD | 05/04/2023 | 850 | CHABDAR ALI TRADERS | 233.79 | 0 | 85
2004 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2005 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | RTOR000275/2023-2024 | 1230/MURD/18 | 04/05/2023 | 0 | Resource Division | 29.58 | 0 | 0
2006 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | RTOR000377/2023-2024 | 495/MURD/04 | 15/02/2024 | 0 | Resource Division | 5.54 | 0 | 0
2007 | Murshidabad Division | Kandi Sub-Division | BABARPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000151/2023-2024 | 1899/MURD | 17/07/2023 | 120 | DIPAYAN DEY | 157.25 | 0 | 40
2008 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000075/2023-2024 | 1075/MURD/17 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
2009 | Murshidabad Division | Berhampur M/E Division | Paschim Purnopara Zone - II PWSS to accommodate Laying Distribution System & Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000480/2023-2024 | 3051/MURD | 29/09/2023 | 477 | SOFIQUL ISLAM | 293.57 | 0 | 0
2010 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000497/2024-2025 | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0
2011 | Murshidabad Division | Berhampur M/E Division | Paschim Purnopara Zone - II PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000573/2023-2024 | 3297/MURD | 20/10/2023 | 180 | M H SUPPLIERS | 305.91 | 0 | 0
2012 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2013 | Murshidabad Division | Berhampur M/E Division | Paschim Purnopara Zone - II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 2 nos, Construction of Boundary Wall of 220 m, Construction 1000 Cum OHR with sub soil investigation Jal Jeevan Mission of Suti-II Block, Murshidabad. . (Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000578/2023-2024 | 3314/MURD | 22/10/2023 | 680 | M/S. A.T.D. PROJECTS | 364.02 | 0 | 15
2014 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2015 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000506/2024-2025 | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0
2016 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000400/2023-2024 | 2807/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 100
2017 | Murshidabad Division | Kandi Sub-Division | BIPRA SEKHAR PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Burwan Block , Kandi Sub-Division, of Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000863/2022-2023 | 823/MURD | 23/03/2023 | 831 | DILIP KUMAR MONDAL | 657.71 | 0 | 50
2018 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000234/2023-2024 | 1219/MURD/11 | 03/05/2023 | 0 | Resource Division | 21.03 | 0 | 0
2019 | Murshidabad Division | Berhampur M/E Division | SAHAJADPUR CT PWSS to accommodate FHTC, Laying Rising Main , OHR as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/17/2012), 4 Nos Pump House, Boundary Wall (5Nos Site) , Approach Road (5Nos Site) & FHTC of SAHAJADPUR CT PWSS at RAGHUNATHGANJ-II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000228/2023-2024 | 2402/MURD | 07/08/2023 | 365 | NAYLA CONSTRUCTION | 353.57 | 0 | 0
2020 | Murshidabad Division | Berhampur M/E Division | SAHAJADPUR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jeevan Mission of Raghunathganj-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000229/2023-2024 | 2401/MURD | 07/08/2023 | 782 | M/S.TAPAS KUMAR CHAKRABORTY | 499.42 | 0 | 5
2021 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAJADPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000398/2023-2024 | 2796/MURD | 04/09/2023 | 21 | M. R. ENTERPRISE | 18.53 | 0 | 0
2022 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2023 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER,Junior engineer-II | RTOR000290/2023-2024 | 1230/MURD/31 | 04/05/2023 | 0 | Resource Division | 65.31 | 0 | 0
2024 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
2025 | Murshidabad Division | Berhampur M/E Division | BHABKI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- SUTI-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000224/2023-2024 | 2368/MURD | 04/08/2023 | 606 | B.B.R.C. INFRASTRUCTURE PVT. LTD. | 495.36 | 0 | 12
2026 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2027 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000276/2023-2024 | 1230/MURD/18 | 04/05/2023 | 0 | Resource Division | 33.71 | 0 | 0
2028 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000371/2023-2024 | 495/MURD/10 | 15/02/2024 | 0 | Resource Division | 13.53 | 0 | 0
2029 | Murshidabad Division | Berhampur M/E Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 100
2030 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 10
2031 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2032 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer 3,JUNIOR ENGINEER 6,Junior engineer-II | RTOR000248/2023-2024 | 1219/MURD/34 | 03/05/2023 | 0 | Resource Division | 2.92 | 0 | 0
2033 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at FATELLAPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000274/2023-2024 | 2604/MURD | 22/08/2023 | 741 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 30
2034 | Murshidabad Division | Berhampur M/E Division | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000287/2023-2024 | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 10
2035 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2036 | Murshidabad Division | Berhampur M/E Division | Providing FHTC to 1200 nos household and OHR Repair of 45 cum capacity for Augmentation of Giria Zone -I and Zone-II Piped water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000097/2024-2025 | 2090/MURD | 23/07/2024 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 60.76 | 0 | 0
2037 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone-II & Giria Zone - I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000122/2023-2024 | 1767/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 23.58 | 0 | 100
2038 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 0 | 100
2039 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Giria Zone-I PWS accommodate FHTC of 2614 nos household, Laying Distribution System, Laying Rising Main,Construction of Pump House (4.10m x 3.5m with sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of length 48 m, Repairing & maintenance of 2(two) nos Pump House ,existing boundary wall and Overhauling of R.C.C. elevated reservoir of 450 Cum capacity of staging hight 20 mtr. in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000585/2023-2024 | 3320/MURD | 22/10/2023 | 814 | S.B. ASSOCIATES | 245.83 | 0 | 75
2040 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000115/2023-2024 | 1167/MURD/9 | 28/04/2023 | 0 | Resource Division | 5.26 | 0 | 0
2041 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based GIRIA KISMAT PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000009/2023-2024 | 951/MURD | 05/04/2023 | 1002 | SUNRISE CONSTRUCTION | 354.38 | 0 | 0
2042 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 0 | 100
2043 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000264/2023-2024 | 1230/MURD/05 | 04/05/2023 | 0 | Resource Division | 46.51 | 0 | 0
2044 | Murshidabad Division | Berhampur M/E Division | Augmentation of BRINDABANPUR Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000273/2023-2024 | 2607/MURD | 22/08/2023 | 741 | J.S. CONSTRUCTION | 288.62 | 0 | 10
2045 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
2046 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000262/2023-2024 | 1230/MURD/03 | 04/05/2023 | 0 | Resource Division | 20.39 | 0 | 0
2047 | Murshidabad Division | Kandi Sub-Division | Allied works for Construction of Approach road, Guard Wall and Laying UPVC Pipeline & Soil Investigation Study of Gourinagar Water Supply Scheme in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000181/2024-2025 | 3144/MURD | 03/12/2024 | 180 | ABDUL JABBAR DEWAN | 27.17 | 0 | 60
2048 | Murshidabad Division | Kandi Sub-Division | Formal work order for GOURI NAGAR & adjoining mouzas PWSS to accommodate FHTC under Jal Jiban Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000798/2022-2023 | 607/MURD | 02/03/2023 | 1255 | ABDUL JABBAR DEWAN | 218.13 | 0 | 65
2049 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000274/2023-2024 | 1230/MURD/17 | 04/05/2023 | 0 | Resource Division | 2.89 | 0 | 0
2050 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-III Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000028/2023-2024 | 1077/MURD | 19/04/2023 | 861 | SUJIT KUMAR SAHA | 162.99 | 0 | 30
2051 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone-III & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000033/2023-2024 | 1108/MURD | 24/04/2023 | 20 | SARKAR WATER SUPPLY AGENCY | 10.67 | 0 | 100
2052 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
2053 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
2054 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000064/2022-2023 | 1043/MURD/5 | 17/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
2055 | Murshidabad Division | Kandi Sub-Division | Allied work of Construction of 2nos. Box Culvert, approach road at Sijgram PWSS at Bharatpur -I Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000046/2024-2025 | 1893/MURD | 01/07/2024 | 242 | RIM CONSTRUCTION | 44.07 | 0 | 10
2056 | Murshidabad Division | Kandi Sub-Division | Balance work for laying of distribution pipe line and allied works of Sijgram Water Supply Scheme, Bharatpur - I Block, Kandi Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000633/2023-2024 | 3441/MURD | 03/11/2023 | 698 | JIBENDRA NARAYAN SUKUL | 28.37 | 0 | 50
2057 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIJGRAM PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000660/2022-2023 | 3405/MURD | 22/12/2022 | 45 | M/S D. PALIT & CO. | 16.81 | 0 | 100
2058 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART -A) of SIJGRAM PWSS of Bharatpur - I Block, Kandi Sub Division under Murshidabad District, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000697/2022-2023 | 132 / MURD | 16/01/2023 | 775 | JIBENDRA NARAYAN SUKUL | 136.47 | 0 | 67
2059 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SIJGRAM PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362356S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,23,22,548.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,57,06,711.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000745/2022-2023 | 412/MURD | 15/02/2023 | 1020 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 280.01 | 0 | 11
2060 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000013/2023-2024 | 1210/MURD/34 | 02/05/2023 | 0 | Resource Division | 42.92 | 0 | 0
2061 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of LOHADAHA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362288S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000707/2022-2023 | 146/MURD | 17/01/2023 | 1445 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 492.18 | 0 | 78
2062 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000042/2023-2024 | 1004/MURD/17 | 17/04/2023 | 0 | Resource Division | 36.62 | 0 | 0
2063 | Murshidabad Division | Berhampur M/E Division | Allied work for Construction of Boundary Wall & Approach Road at Katlamari ZONE-II Ground water based Piped water supply scheme within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000049/2024-2025 | 1948/MURD | 04/07/2024 | 330 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 38.57 | 0 | 80
2064 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Katlamari Zone-II Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000591/2022-2023 | 3060/MURD | 17/11/2022 | 45 | GENUINE | 23.5 | 0 | 0
2065 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution System (part-II) and Providing Functional Household Tap Connection to 550 nos household & Sub-soil Investigation and Construction of OHR (500 cum) of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000611/2022-2023 | 3244/MURD | 06/12/2022 | 1116 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 214.83 | 0 | 18
2066 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution (part-III) and Providing Functional Household Connection to 670 nos household & Construction of Boundary wall of Katlamari Zone -II of Islampur Sub Division under Murshidabad Division,P.H.E Dte.[(i)Amount for LDS & FHTC: Rs.14312870.00 & (ii)Amount for Construction of Boundary wall : Rs.897464.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000676/2022-2023 | 57/MURD | 06/01/2023 | 60 | SOM CONSTRUCTION AGENCY | 132.94 | 0 | 10
2067 | Murshidabad Division | Berhampur M/E Division | Formal work order Laying of Distribution System (part-I) , Rising Main and Providing Functional Household Tap Connection to 790 nos household & Construction of Pump House of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [ (i)Amount for LDS,R. Main & FHTC:: Rs.1,38,47,328.00 & (ii)Amount for Construction of Pump House : Rs.15,28,347.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000685/2022-2023 | 162/MURD | 17/01/2023 | 1111 | SOUNAK ENTERPRISE | 153.68 | 0 | 10
2068 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 0 | 1
2069 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000052/2022-2023 | 3052/E/MURD | 17/11/2022 | 0 | Resource Division | 9.64 | 0 | 0
2070 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000103/2023-2024 | 1167/MURD | 28/04/2023 | 0 | Resource Division | 57.64 | 0 | 0
2071 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-III water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000543/2022-2023 | 2729/MURD | 27/09/2022 | 1435 | PRIYANKA CONSTRUCTION | 270.88 | 0 | 80
2072 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Godhanpara Zone-III Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000590/2022-2023 | 3059/MURD | 17/11/2022 | 45 | GENUINE | 23.5 | 0 | 100
2073 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 0 | 0
2074 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000045/2022-2023 | 3037/D/MURD | 16/11/2022 | 0 | Resource Division | 40.31 | 0 | 0
2075 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000050/2022-2023 | 3052/C/MURD | 17/11/2022 | 0 | Resource Division | 17.71 | 0 | 0
2076 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000294/2023-2024 | 1278/MURD/12 | 10/05/2023 | 0 | Resource Division | 37.4 | 0 | 0
2077 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Sagarpara Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000532/2022-2023 | 2540/MURD | 02/09/2022 | 1052 | M/S GUHA AND ROY | 333.77 | 0 | 8
2078 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-B Water Supply Scheme of TW-I,II,III at Head Work Site & 2nd Tube Well Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000669/2022-2023 | 3410/MURD | 22/12/2022 | 60 | R.K. DRILLING SERVICES | 35.34 | 0 | 90
2079 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA PART-B Water Supply Scheme and Chandkati Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000722/2023-2024 | 3907/MURD | 20/12/2023 | 392 | NADIA TUBEWELLS | 18.43 | 0 | 100
2080 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000032/2022-2023 | 2780/A/MURD | 01/10/2022 | 0 | Resource Division | 30.95 | 0 | 0
2081 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000313/2023-2024 | 3037/MURD/2 | 27/09/2023 | 0 | Resource Division | 111.86 | 0 | 0
2082 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Sagarpara PWSS Scheme,Block- Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | VCH/000736/2022-2023 | 260-MSD/22-23 | 18/08/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 11.08 | 0 | 0
2083 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000038/2022-2023 | 2780/G/MURD | 01/10/2022 | 0 | Resource Division | 11.59 | 0 | 0
2084 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000168/2023-2024 | 1180/MURD/14 | 29/04/2023 | 0 | Resource Division | 11.83 | 0 | 0
2085 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nimtita ( Village Code -313863) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723174). | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000720/2020-2021 | 639/MURD | 18/02/2021 | 60 | AZAD ENTERPRISE | 25.44 | 0 | 1
2086 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at JADUPUR Water Supply Scheme, Rangamati Chandpara G.P under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. Length-55.0Mtr. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000073/2020-2021 | 3171/MURD | 16/12/2020 | 30 | SOM CONSTRUCTION AGENCY | 4.98 | 0 | 100
2087 | Murshidabad Division | Berhampur Sub-Division | Relaying of pipe line at Chandpara village under command area of JADUPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000525/2020-2021 | 119/BSD | 19/02/2021 | 15 | M/S.S.S. ENTERPRISE | 4.85 | 0 | 0
2088 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jadupur Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000594/2022-2023 | 3068/MURD | 17/11/2022 | 30 | NADIA TUBEWELLS | 10.6 | 0 | 0
2089 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Construction 200 Cum OHR, Laying Distribution System & Rising Main in Connection with Augmentation of Jadupur Ground water based Piped water supply scheme within Berhampore Block of Murshidabad District under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000687/2022-2023 | 129/MURD | 16/01/2023 | 1061 | SOFIQUL ISLAM | 135.86 | 0 | 5
2090 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2091 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (JADUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000835/2021-2022 | 3268/MURD | 05/10/2021 | 60 | RADIANT | 2.28 | 0 | 1
2092 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000002/2024-2025 | 1811/MURD/01 | 20/06/2024 | 0 | Resource Division | 4.49 | 0 | 0
2093 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000106/2023-2024 | 1167/MURD/2 | 28/04/2023 | 0 | Resource Division | 3.11 | 0 | 0
2094 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Suti-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001178/2021-2022 | 366/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0
2095 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kadamtala (Village code 313953) under Mahisali Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723341 in the District of Murshidabad. |  |  | ORD/001577/2021-2022 | 304/MURD | 07/02/2022 | 60 | M/S. M.G. CONSTRUCTION | 27.86 | 0 | 0
2096 | Murshidabad Division |  | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Sagardighi-I Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. |  |  | ORD/001182/2021-2022 | 369/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.46 | 0 | 0
2097 | Murshidabad Division | Kandi Sub-Division | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Balia G.P, Joypur G.P, Alugram G.P, bharatpur G.P, Sijgram G.P, Salar G.P, Simulia G.P, Kagram G.P, Talibpur G.P & Tenya Baidyapur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER |  | ORD/000079/2021-2022 | 177/KSD | 28/05/2021 | 30 | IMAGIN COMMUNICATION | 2.9 | 0 | 0
2098 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur ( Village Code -313864) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723174). |  |  | ORD/000574/2020-2021 | 633/MURD | 18/02/2021 | 60 | HOQUEDAR ALI | 43.59 | 0 | 0
2099 | Murshidabad Division |  | Retrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of DURGAPUR (Village Code -313864) under HASIMPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block in the Dist of MSD under Murshidabad Division P.H.E Dte. Scheme ID 0001723174 |  |  | VCH/000369/2021-2022 |  | 25/08/2021 | 0 | HOQUEDAR ALI | 33.41 | 0 | 0
2100 | Murshidabad Division |  | Retrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of DURGAPUR (Village Code -313864) under HASIMPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block in the Dist of MSD under Murshidabad Division P.H.E Dte. Scheme ID 0001723174 Tender No 858/20-21/EE |  |  | VCH/000663/2021-2022 | 49- MSD / 21-22 | 13/09/2021 | 0 | HOQUEDAR ALI | 33.41 | 0 | 0
2101 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Shaikh para & Babultali ) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) |  |  | ORD/000333/2021-2022 | 2386/MURD | 09/08/2021 | 60 | MITRA CONSTRUCTION | 98.09 | 0 | 1
2102 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1676 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000627/2023-2024 | 3423/MURD | 02/11/2023 | 60 | SUMAN CHOWDHURY | 55.3 | 0 | 40
2103 | Murshidabad Division |  | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. |  |  | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 0 | 0
2104 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1005 nos household under command area of village of Sekhalipara ( Village Code -314580) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0005185646) |  |  | ORD/000136/2022-2023 | 1238/MURD | 11/05/2022 | 60 | BRISTI CONSTRUCTION | 52.34 | 0 | 1
2105 | Murshidabad Division | Berhampur Sub-Division | Additional Laying and distribution of UPVC pipiline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000186/2022-2023 | 193/BSD | 28/04/2022 | 30 | S.G CONSTRUCTION , | 4.36 | 0 | 0
2106 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER |  | ORD/000447/2021-2022 | 297/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 4.34 | 0
2107 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KHIDIRPUR G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000500/2021-2022 | 335/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
2108 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Fatepur (Village code 315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723484 in the District of Murshidabad. | ASSISTANT ENGINEER |  | ORD/000511/2020-2021 | 78/MURD | 08/01/2021 | 60 | RELIABLE ENTERPRISE | 26.51 | 20.89 | 0
2109 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Brindabanpur Chak (Village code 314703) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. |  |  | ORD/000774/2020-2021 | 83./MURD | 08/01/2021 | 60 | ULTRA CONSTRUCTION. | 43.61 | 0 | 0
2110 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Faridpur ( Village Code -314641) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) |  |  | ORD/000300/2021-2022 | 2349/MURD | 05/08/2021 | 60 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 87.31 | 0 | 1
2111 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bhaduria Para( Village Code -314643) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) |  |  | ORD/000509/2020-2021 | 655/MURD | 18/02/2021 | 60 | ASHOK KUMAR SINHA | 81.32 | 0 | 0
2112 | Murshidabad Division |  | Extension of Distribution UPVC pipeline for Providing Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Bhaduriapara (Village Code-314643) under Faridpur Ground water based water suply scheme for Arsenic affected areas of Jalangi Block, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0005184121) |  |  | ORD/001834/2021-2022 | 766/MURD | 22/03/2022 | 30 | M/S. SINHA & SONS | 36.38 | 0 | 0
2113 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) inconnection with the Functional Household Connection of different existing PWSS(Faridpur Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 369 of 21-22 by EE MSD, and Scheme Code: 7919 |  |  | VCH/000037/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 7.25 | 0 | 0
2114 | Murshidabad Division |  | Preparation of D.P.R(Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Faridpur Zone-I PWSS Scheme,Block-Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 368 of 21-22 by EE MSD, and Scheme Code: 7919 |  |  | VCH/000038/2022-2023 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 5.36 | 0 | 0
2115 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION)' from existing Distribution system within the Command area of village FARIDPUR (Village Code 314641) under FARIDPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 246 of 21-22 by EE MURD |  |  | VCH/001494/2021-2022 | 395-MSD/21-22 | 23/03/2022 | 0 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 11.79 | 0 | 0
2116 | Murshidabad Division |  | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. |  |  | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 0 | 1
2117 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SHIBPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000407/2021-2022 | 249/LSD | 18/08/2021 | 30 | IMAGIN COMMUNICATION | 4.18 | 0 | 0
2118 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (JalJeevan Mission ) "from existing Distribution system within the Command area of village AMARKUNDU (Village Code 315017) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block in the District of Murshidabad . |  |  | ORD/000627/2020-2021 | 2570/MURD | 01/10/2020 | 45 | MAJUMDER CONSTRUCTION | 38.26 | 0 | 1
2119 | Murshidabad Division |  | Additional extension of UPVC pipeline at Sankuria and Madhunia (Adibashipara) under the Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division, P.H.E. Dte.in the District Murshidabad. |  |  | ORD/000918/2021-2022 | 361/LSD | 17/11/2021 | 45 | SARAJIT KUMAR MAJUMDER | 4.43 | 0 | 0
2120 | Murshidabad Division |  | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/001225/2021-2022 | 413/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 4.88 | 0 | 0
2121 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) of 200 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amarkundu (Village code 315017) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001806/2021-2022 | 803/MURD | 24/03/2022 | 20 | S.K. CONSTRUCTION (TABLU) | 11.79 | 0 | 0
2122 | Murshidabad Division |  | Operation & Maintenance of distribution system and allied works of Siddhikhali (Zone-III)Surface W/S Scheme Raghunathganj-I Block from 01.05.2019 to 29.02.2020 |  |  | VCH/000933/2020-2021 | 489/W | 17/03/2021 | 0 | SUDIPA SINGHA ROY | 4.99 | 0 | 0
2123 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
2124 | Murshidabad Division |  | CONT WORK OF OPERATION & GUARDING OF PUMPING MACHINERY FOR MAHESAIL W/S SCHEME PH-I , TNO- 894/19-20/EE |  |  | VCH/002042/2020-2021 | 489/W | 17/03/2021 | 0 | RELIABLE ENTERPRISE | 1.41 | 0 | 0
2125 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC |  |  | VCH/002052/2020-2021 | 504/W | 22/03/2021 | 0 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0
2126 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kochgiria(Village code 314481) under Bhandara Ground Based Water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-03) |  |  | ORD/000427/2020-2021 | 3130/MURD | 10/12/2020 | 180 | M/S OBAIDUR RAHAMAN | 54.51 | 0 | 70
2127 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHHAKA NAGAR (Village code 314478) under BHANDARA Ground water based Water Supply Scheme for Arsenic Affected Area of Bhagwangola - I & II Block, under Murshidabad Division, PHE Dte. Tender no 492 of 20-21 by EE MSD |  |  | VCH/000271/2021-2022 |  | 18/08/2021 | 0 | PRANAB KUMAR GHOSH | 21.76 | 0 | 0
2128 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHHAKA NAGAR (Village code 314478) under BHANDARA Ground water based Water Supply Scheme for Arsenic Affected Area of Bhagwangola - I & II Block, under Murshidabad Division, PHE Dte. Tender no 492 of 20-21 by EE MSD |  |  | VCH/000664/2021-2022 | 50- MSD / 21-22 | 14/09/2021 | 0 | PRANAB KUMAR GHOSH | 21.76 | 0 | 0
2129 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BAGHARPUR RAMNA (Village Code -314665) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. . Tender no - 66 of 20-21 by SE MC. |  |  | VCH/000721/2022-2023 | 254-MSD/22-23 | 12/08/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 10.04 | 0 | 0
2130 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Baniakhali( Village Code -314660) under Baniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723470) |  |  | ORD/000345/2021-2022 | 2181/MURD | 28/07/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 12.08 | 0 | 0
2131 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village BANIAKHALI (Village Code 314660) under Baniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . |  |  | ORD/000594/2020-2021 | 2578/MURD | 01/10/2020 | 45 | M/S NIRAPADA BHATTACHARJEE | 35.6 | 0 | 1
2132 | Murshidabad Division |  | ADITIONAL WORK OF FHTC OF BANIAKHALI (314660) WSS, TNO- 641/21-22/EE, WO- 2181/MURD |  |  | VCH/000333/2022-2023 | 130-MSD/22-23 | 11/05/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 5.91 | 0 | 0
2133 | Murshidabad Division |  | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC |  |  | VCH/002047/2020-2021 | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0
2134 | Murshidabad Division |  | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000637/2023-2024 | 3458/MURD | 06/11/2023 | 30 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0
2135 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --AMARKUNDU-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- RAINDA , CODE- 315025, TNO- 684/2020-21/EE |  |  | VCH/002019/2020-2021 | 512/W | 30/03/2021 | 0 | SAMAR MUKHERJEE | 21.62 | 0 | 0
2136 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JURANPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PIROJPUR , CODE-314723, TNO- 667/2020-21/EE |  |  | VCH/002021/2020-2021 | 512/W | 30/03/2021 | 0 | GOUTAM CHAKRABORTY | 10.4 | 0 | 0
2137 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
2138 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
2139 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | BILL/01002/2023-2024 | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
2140 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) 1305 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ballalpur ( Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | ORD/000021/2022-2023 | 1052/MURD | 25/04/2022 | 45 | TARIKUL SK | 60.99 | 0 | 10
2141 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | RTOR000033/2021-2022 | 540/6/MURD | 25/02/2022 | 0 | Resource Division | 7.16 | 0 | 0
2142 | Murshidabad Division | Kandi Sub-Division | Planning, design, investigation, construction, erection, installation, completion, testing and commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & iron present in ground water in diff. connection to acceptable limit as recommended by CPHEEO manual on basis of departmental process drawing (Modified Sujapur Sadipur Model) incld. 3 months Trail Run & 9 months O&M of diff. blocks in the district of Murshidabad, PHE Dte., (JAGAIPUR W/S SCHEME) | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/002037/2020-2021 | 478/W | 12/03/2021 | 0 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 27.52 | 0 | 0
2143 | Murshidabad Division | Kandi Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER ESTIMATING SECTION | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
2144 | Murshidabad Division | Berhampur M/E Division | Allied & Balance Work for Construction of Boundary wall, Land Development ,Road restoration damaged during laying of pipeline, Path Way & Soil Test for Over Head Reservoir of Paschim Char Majhardiar & Adjoining Mouzas Water Supply Scheme in Rani Nagar-I Block of Islampur Sub-Division, under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000195/2024-2025 | 3230/MURD | 10/12/2024 | 369 | M/S. SARKAR CONSTRUCTION | 71.53 | 0 | 0
2145 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 90
2146 | Murshidabad Division | Berhampur M/E Division | Construction of Ground Water Based Paschim Char Majhardiar PWSS of accommodate FHTC(2246 Nos), Laying Distribution System, Laying Rising Main,Over Head Reservoir ( 500 CUM Capacity), Switch Room, Boundary Wall in Raninagar - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000758/2023-2024 | 140/MURD | 16/01/2024 | 716 | M/S. SARKAR CONSTRUCTION | 468.58 | 0 | 80
2147 | Murshidabad Division | Kandi Sub-Division | GUNDIRIA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000149/2023-2024 | 1898/MURD | 17/07/2023 | 624 | MAA MANSAHA CONSTRUCTION | 119.11 | 0 | 65
2148 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UJUNIA SISUA AND GUNDIRIA Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur I & II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000624/2023-2024 | 3409/MURD | 02/11/2023 | 472 | GENUINE | 18.43 | 0 | 100
2149 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000069/2023-2024 | 1075/MURD/11 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0
2150 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 100 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Boundary wall and approach road for Augmentation of Jotsundar PWSS in Raghunathganj-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000391/2023-2024 | 2771/MURD | 01/09/2023 | 730 | M/S AFSHAN CONSTRUCTION | 265.01 | 0 | 21
2151 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000562/2022-2023 | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 0 | 100
2152 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jot Sundar Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Raghunathganj-II Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000706/2023-2024 | 3808/MURD | 12/12/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 23.54 | 0 | 100
2153 | Murshidabad Division | Berhampur M/E Division | Work of Interconnection of D.I pipe line between 2nd Tube well Pump house to Rising main at Jot Sundar Water Supply Scheme under Jangipur Sub-Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001267/2021-2022 | 386/JSD | 31/12/2021 | 30 | SAMAR MUKHERJEE | 1.9 | 0 | 0
2154 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000146/2023-2024 | 1167/MURD/50 | 28/04/2023 | 0 | Resource Division | 9.38 | 0 | 0
2155 | Murshidabad Division | Berhampur M/E Division | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme (Scheme ID- 0001723333) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000091/2022-2023 | 237/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.42 | 0 | 0
2156 | Murshidabad Division | Berhampur M/E Division | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000092/2022-2023 | 238/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.61 | 0 | 0
2157 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone- I A & Kusumgachi Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000137/2023-2024 | 1772/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 27.67 | 0 | 100
2158 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2159 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
2160 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing and Approved from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carrying Pipe, 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jacking Technique method across at chainage 276+100 of the N.H- 34 of at Mouza-Ratanpur of Bhasaipaikar W/S Scheme under Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | ORD/000824/2023-2024 | 745/MURD | 12/03/2024 | 90 | M/S. GOUTAM ROY | 37 | 0 | 0
2161 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,JUNIOR ENGINEER 3,Junior engineer-II | RTOR000118/2023-2024 | 1167/MURD/12 | 28/04/2023 | 0 | Resource Division | 73.37 | 0 | 0
2162 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
2163 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDHUA ZONE -I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000710/2023-2024 | 3814/MURD | 12/12/2023 | 537 | HARUN ALL RASHID & BROTHERS | 23.52 | 0 | 100
2164 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 35
2165 | Murshidabad Division | Berhampur M/E Division | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000898/2022-2023 | 1082/ MURD | 27/04/2022 | 45 | MARUTI CONSTRUCTION AND CO. | 62.56 | 0 | 0
2166 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000163/2023-2024 | 1180/MURD/26 | 29/04/2023 | 0 | Resource Division | 52.49 | 0 | 0
2167 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Hazipur Part- B village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000214/2023-2024 | 2329/MURD | 02/08/2023 | 60 | SHIRSHENDU MUKHERJEE | 30.55 | 0 | 0
2168 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Hazipur Part- A village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000259/2023-2024 | 2495/MURD | 11/08/2023 | 510 | MUKTI ENTERPRISE | 30.47 | 0 | 100
2169 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000228/2023-2024 | 1219/MURD/12 | 03/05/2023 | 0 | Resource Division | 14.34 | 0 | 0
2170 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
2171 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 779 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
2172 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 811 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
2173 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2174 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
2175 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000258/2023-2024 | 1230/MURD/01 | 04/05/2023 | 0 | Resource Division | 30.12 | 0 | 0
2176 | Murshidabad Division | Kandi Sub-Division | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.08.2025 TO 31.12.2025. VEHICLE NO - WB57F2352 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000097/2025-2026 | 97/KSD | 17/07/2025 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
2177 | Murshidabad Division | Kandi Sub-Division | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 95
2178 | Murshidabad Division | Kandi Sub-Division | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 28.02.2025 TO 31.07.2025. VEHICLE NO - WB57F2352 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000474/2024-2025 | 41/KSD | 25/02/2025 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
2179 | Murshidabad Division | Kandi Sub-Division | Laying of Rising main , Distribution System, FHTC, OHR Repairing (Capacity 600 cum), , Sinking of Tube Well , Construction of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-III PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000613/2023-2024 | 3375/MURD | 31/10/2023 | 793 | H.ENTERPRISE | 499.38 | 0 | 53
2180 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000005/2023-2024 | 1004/MURD/A | 11/04/2023 | 0 | Resource Division | 122.58 | 0 | 0
2181 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000029/2023-2024 | 1004/MURD/7 | 11/04/2023 | 0 | Resource Division | 42.04 | 0 | 0
2182 | Murshidabad Division | Berhampur M/E Division | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. for 03 (Three) Months i.e. from 08.01.2025 to 07.04.2025. (Vehicle No.WB-58AX-9595). | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000232/2024-2025 | 05/LSD | 06/01/2025 | 90 | BARI ENTERPRISE | 0.44 | 0 | 0
2183 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
2184 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 1250 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone -III PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000649/2023-2024 | 3475/MURD | 07/11/2023 | 545 | HANNAN BUILDERS PVT.LTD. | 1434.58 | 0 | 1
2185 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000700/2023-2024 | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 80
2186 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000101/2023-2024 | 1167/MURD/18 | 28/04/2023 | 0 | Resource Division | 49.7 | 0 | 0
2187 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
2188 | Murshidabad Division | Berhampur Sub-Division | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 537 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 75
2189 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 1159 nos household for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE.Dte. (part_C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000100/2023-2024 | 1699/MURD | 28/06/2023 | 277 | S. ROY & CO. | 67.64 | 0 | 0
2190 | Murshidabad Division | Berhampur Sub-Division | Construction of 300 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 180 Cum capacity, Construction of Boundary Wall for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte. (part_A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000195/2023-2024 | 2038/MURD | 26/07/2023 | 730 | SATELLITE CONSTRUCTION | 177.33 | 0 | 0
2191 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System, Construction Pump House with sanitary and Water Supply Arrangement, Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing Pump House and Allied Works for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte.(part _B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000196/2023-2024 | 2037/MURD | 26/07/2023 | 180 | AMIT KUMAR GUPTA | 176.87 | 0 | 0
2192 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
2193 | Murshidabad Division | Berhampur Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2194 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
2195 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000016/2024-2025 | 1811/MURD/15 | 20/06/2024 | 0 | Resource Division | 8.19 | 0 | 0
2196 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000212/2023-2024 | 1219/MURD/03 | 03/05/2023 | 0 | Resource Division | 22.93 | 0 | 0
2197 | Murshidabad Division | Berhampur Sub-Division | Construction of Pump House cum Chlorine Room with sanitary and Water Supply Arrangement at Basabari PWSS at Berhampore Block under Berhampore Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000058/2024-2025 | 1989/MURD | 08/07/2024 | 186 | ANIRBAN CHATTERJEE | 7.39 | 0 | 100
2198 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
2199 | Murshidabad Division | Berhampur Sub-Division | Laying of Distribution System including Refixing the existing FHTCs connection on new distribution system of Basabari Ground Based piped water supply scheme of in Berhampore Block of Berhampore Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000419/2024-2025 | 511/MURD | 28/02/2025 | 60 | M/S. M.G. CONSTRUCTION | 40.27 | 0 | 0
2200 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
2201 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Basabari PWSS to accommodate FHTC of 673 nos household Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Construction of Boundary Wall of 270 m and Soil Investigation & 250 Cum Construction of OHR at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000550/2023-2024 | 3180/MURD | 11/10/2023 | 730 | SAMBHU NATH ROY | 223.72 | 0 | 10
2202 | Murshidabad Division | Berhampur Sub-Division | Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-C). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000593/2020-2021 | 503/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 100
2203 | Murshidabad Division | Berhampur Sub-Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASABARI & CHHAIGHARI Water Supply Scheme at Head work site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000723/2023-2024 | 3875/MURD | 18/12/2023 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 100
2204 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000725/2020-2021 | 3122 / MURD | 09/12/2020 | 60 | TANUSHREE ENTERPRISE | 39.34 | 0 | 1
2205 | Murshidabad Division | Berhampur Sub-Division | Laying Distribution System For Augmentation of Basabari (Part-A) PWSS of Berhampore Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000769/2022-2023 | 496/MURD | 21/02/2023 | 727 | SANDHAN ADHIKARI | 73.69 | 0 | 85
2206 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
2207 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000001/2025-2026 | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0
2208 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000119/2023-2024 | 1771/MURD | 06/07/2023 | 684 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 40
2209 | Murshidabad Division | Berhampur M/E Division | ANUP NAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000232/2023-2024 | 2404/MURD | 07/08/2023 | 180 | SUJIT KUMAR SAHA | 428.3 | 0 | 0
2210 | Murshidabad Division | Berhampur M/E Division | ANUPNAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000250/2023-2024 | 2464/MURD | 09/08/2023 | 365 | M/S RUBIET HOSSAIN | 230.08 | 0 | 0
2211 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2212 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000289/2023-2024 | 1230/MURD/32 | 04/05/2023 | 0 | Resource Division | 35.78 | 0 | 0
2213 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000568/2023-2024 | 3288/MURD | 19/10/2023 | 180 | BIJAY CHOWDHURY | 861.6 | 0 | 35
2214 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2215 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000247/2023-2024 | 1219/MURD/31 | 03/05/2023 | 0 | Resource Division | 49.41 | 0 | 0
2216 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000109/2023-2024 | 1751/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 27.64 | 0 | 50
2217 | Murshidabad Division | Kandi Sub-Division | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000223/2023-2024 | 2367/MURD | 04/08/2023 | 300 | M/S. S. DAS AND ENTERPRISE | 859.33 | 0 | 40
2218 | Murshidabad Division | Kandi Sub-Division | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000576/2023-2024 | 3300/MURD | 20/10/2023 | 804 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 261.54 | 0 | 35
2219 | Murshidabad Division | Kandi Sub-Division | Providing Functional Household Tap Connections (FHTC) (1222 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Parsalika, Panchhipara & Andulia ( Village Code -315953, 315966, 315967) under Kurulia & Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000679/2023-2024 | 3657/MURD | 29/11/2023 | 45 | S. DUTTA | 36.75 | 0 | 0
2220 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000085/2023-2024 | 1129/MURD/8 | 25/04/2023 | 0 | Resource Division | 38.73 | 0 | 0
2221 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KADOA Zone -I A Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000014/2024-2025 | 1753/MURD | 13/06/2024 | 201 | R.K. DRILLING SERVICES | 35.37 | 0 | 100
2222 | Murshidabad Division | Berhampur M/E Division | Allied work of construction of culvert at kadoa Zone-I 2nd T.W site and approach road for H/W site & 2nd T.W site for Augmentation work under Jangipur sub division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000067/2024-2025 | 1988/MURD | 08/07/2024 | 60 | M/S BAPPA ENTERPRISE | 16.72 | 0 | 0
2223 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2224 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Work, Construction of Boundary Wall (For T/W-I) =100 mtrs & Repair of Boundary Wall (50m +50m) =100 m at T/W-II site for Augmentation of KADOA (Zone - I) Part-A Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. (i)Amount for Construction Part: 5,87,696.00/ (ii)Amount for Pipeline Part: 22,96,300.00/- (Attached as Annexure -XII) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000781/2022-2023 | 685/MURD | 10/03/2023 | 180 | M/S BAPPA ENTERPRISE | 28.81 | 0 | 0
2225 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000196/2023-2024 | 1210/MURD/16 | 02/05/2023 | 0 | Resource Division | 7.37 | 0 | 0
2226 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2227 | Murshidabad Division | Berhampur M/E Division | Formal work order for BAURIPUNI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000851/2022-2023 | 788/MURD | 21/03/2023 | 365 | KISMAT ARA BEGAM | 355.05 | 0 | 10
2228 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000288/2023-2024 | 1230/MURD/30 | 04/05/2023 | 0 | Resource Division | 21.71 | 0 | 0
2229 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000381/2023-2024 | 495/MURD/13 | 15/02/2024 | 0 | Resource Division | 7.53 | 0 | 0
2230 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2231 | Murshidabad Division | Berhampur M/E Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000134/2024-2025 | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 100
2232 | Murshidabad Division | Berhampur M/E Division | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000501/2024-2025 | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0
2233 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000556/2023-2024 | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 5
2234 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000090/2023-2024 | 1147/MURD/5 | 27/04/2023 | 0 | Resource Division | 31.5 | 0 | 0
2235 | Murshidabad Division | Berhampur M/E Division | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/000375/2023-2024 | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 95
2236 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER-II | Junior engineer-III | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
2237 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-II | Junior engineer-III | RTOR000237/2023-2024 | 1219/MURD/25 | 03/05/2023 | 0 | Resource Division | 10.21 | 0 | 0
2238 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KADOA Zone ¿II Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000020/2025-2026 | 985/MURD | 02/05/2025 | 60 | ARINDAM MAJUMDAR | 23.01 | 0 | 0
2239 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2240 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000553/2023-2024 | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 21
2241 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000088/2023-2024 | 1147/MURD/2 | 27/04/2023 | 0 | Resource Division | 26.13 | 0 | 0
2242 | Murshidabad Division | Kandi Sub-Division | BINDARPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-I of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000286/2023-2024 | 2641/MURD | 23/08/2023 | 740 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 606.88 | 0 | 20
2243 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000056/2023-2024 | 1075/MURD | 19/04/2023 | 0 | Resource Division | 31.02 | 0 | 0
2244 | Murshidabad Division | Berhampur M/E Division | Rectification work from Raturi to Kalinagar in the road of Dangapara more to Raturi via HILORA, Kalinagar Road under berhampore Division-I PWD during the year of 2023-2024. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | BILL/01020/2023-2024 | 468-MSD/2023-24 | 04/01/2024 | 0 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 78.16 | 0 | 0
2245 | Murshidabad Division | Berhampur M/E Division | Providing FHTC of 1415 nos. household, Laying of Rising Main, Repair & Renovation of RCC 130 Cum OHR, special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works Augmentation work of Raturi (Zone-I) PWSS in SUTI-I Block under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000085/2023-2024 | 1455/MURD | 01/06/2023 | 180 | R.M. BHATTA | 91.23 | 0 | 15
2246 | Murshidabad Division | Berhampur M/E Division | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000105/2024-2025 | 2195/MURD | 31/07/2024 | 30 | SARKAR WATER SUPPLY AGENCY | 23.56 | 0 | 50
2247 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2248 | Murshidabad Division | Berhampur M/E Division | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000170/2024-2025 | 2957/MURD | 11/11/2024 | 15 | GAYEN ENTERPRISE | 11.73 | 0 | 0
2249 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RATURI ZONE -I Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000713/2023-2024 | 3838/MURD | 14/12/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 0 | 50
2250 | Murshidabad Division | Berhampur M/E Division | Allied work for Road restoration damaged during laying of pipeline of Raturi Zone-I Piped Water Supply Scheme, Suti Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000826/2023-2024 | 769/MURD | 13/03/2024 | 30 | S. DUTTA | 48.28 | 0 | 0
2251 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000205/2023-2024 | 1210/MURD/20 | 02/05/2023 | 0 | Resource Division | 27.82 | 0 | 0
2252 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
2253 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2254 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 231/4 & 231/5) on railway land of mouza Hafania & Connecting with existing 160 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000512/2021-2022 | 2480/MURD | 16/08/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 28.91 | 0 | 100
2255 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 230/6 & 230/7) at Hafania mouza & Connecting with existing 110 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000513/2021-2022 | 2481/MURD | 16/08/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 21.58 | 0 | 100
2256 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Ground Water Based HAFANIA (ZONE-I) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000842/2022-2023 | 745/MURD | 16/03/2023 | 747 | PAROMITA DEB | 416.04 | 0 | 40
2257 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000265/2023-2024 | 1230/MURD/04 | 04/05/2023 | 0 | Resource Division | 10.57 | 0 | 0
2258 | Murshidabad Division | Berhampur M/E Division | Construction of Boundwary Wall , Pump House , PCC approach road , Land Development for Augmentation of Jorgacha PWSS in Domkol Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000011/2025-2026 | 899/MURD | 23/04/2025 | 90 | EMCO CONSTRUCTION | 23 | 0 | 0
2259 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jorgacha Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000131/2023-2024 | 1757/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 23.58 | 0 | 50
2260 | Murshidabad Division | Berhampur M/E Division | Formal work order for the work of Augmentation of JORGACHA Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000732/2022-2023 | 365/MURD | 09/02/2023 | 926 | ULTRA CONSTRUCTION. | 272.97 | 0 | 100
2261 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
2262 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000305/2023-2024 | 1278/MURD/14 | 10/05/2023 | 0 | Resource Division | 74.66 | 0 | 0
2263 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
2264 | Murshidabad Division | Kandi Sub-Division | Laying of UPVC pipeline from Head Work Site to Node point 16, laying of parallel line for FHTC work and Construction of approach road of UDAYCHANDPUR & Adjoining Mouzas Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000056/2024-2025 | 1987/MURD | 08/07/2024 | 450 | MARUTI CONSTRUCTION AND CO. | 76.01 | 0 | 40
2265 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UDAY CHANDPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte.. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000662/2022-2023 | 3407/MURD | 22/12/2022 | 45 | MAMATA USHA ENTERPRISE | 16.82 | 0 | 80
2266 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of Boundwary Wall, Pump House & Laying Distribution System(PART-B) Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000734/2022-2023 | 385/MURD | 10/02/2023 | 964 | MARUTI CONSTRUCTION AND CO. | 158.53 | 0 | 35
2267 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 300 Cum OHR, Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000859/2022-2023 | 793/MURD | 21/03/2023 | 365 | M/S. SINHA & SONS | 363.73 | 0 | 10
2268 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000020/2023-2024 | 1210/MURD/40 | 02/05/2023 | 0 | Resource Division | 26.76 | 0 | 0
2269 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
2270 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOLLA PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division,P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000742/2022-2023 | 381/MURD | 10/02/2023 | 45 | NADIA TUBEWELLS | 16.81 | 0 | 95
2271 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Construction of 150 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of MOLLA PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362345S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,98,91,791.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,23,31,559.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | ORD/000749/2022-2023 | 415/MURD | 15/02/2023 | 1141 | M/S NIRAPADA BHATTACHARJEE | 322.07 | 0 | 5
2272 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER ESTIMATING SECTION,Junior engineer-II | RTOR000009/2023-2024 | 1210/MURD/42 | 02/05/2023 | 0 | Resource Division | 32.6 | 0 | 0
2273 | Murshidabad Division | Berhampur M/E Division | Laying of Distribution System for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000032/2024-2025 | 1891/MURD | 01/07/2024 | 365 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 77.48 | 0 | 40
2274 | Murshidabad Division | Berhampur M/E Division | Overhauling of 350 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-II Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000045/2024-2025 | 1949/MURD | 04/07/2024 | 303 | MOTI INDUSTRIES | 93.51 | 0 | 40
2275 | Murshidabad Division | Berhampur M/E Division | Laying of balance work of HDPE pipe Risingmain and construction of approach road at Head Works Site of Dogachhi ( Zone-I) Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000062/2020-2021 | 282/MURD | 27/01/2021 | 30 | HARUN ALL RASHID & BROTHERS | 4.96 | 0 | 1
2276 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone -II Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000101/2023-2024 | 1742/MURD | 06/07/2023 | 635 | NADIA TUBEWELLS | 35.34 | 0 | 33
2277 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main & Distribution System (PART-B) for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000251/2024-2025 | 229/MURD | 27/01/2025 | 90 | M/S GUNGUN CONSTRUCTION | 89.6 | 0 | 0
2278 | Murshidabad Division | Berhampur M/E Division | Formal Work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Dy Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of April?2022 to March?2023 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000569/2022-2023 | 894/MURD | 05/04/2022 | 365 | SOUMYADIP MISRA | 4.78 | 0 | 1
2279 | Murshidabad Division | Berhampur M/E Division | Formal work order for Construction 250 Cum OHR & Rising Main in Connection with Augmentation of Dogachhi Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Samserganj Block of Murshidabad District under Murshidabad Division, PHE.Dte. [ (i)Amount for R. Main: Rs. 6,69,620.00 & (ii) Amount for OHR : Rs. 98,29,869.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000696/2022-2023 | 134/MURD | 16/01/2023 | 365 | IOTA CONSTRUCTION | 104.46 | 0 | 0
2280 | Murshidabad Division | Berhampur M/E Division | Geotechnical study of underground formation of the proposed Over Head Reservoir of Dogachhi (Zone-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000756/2023-2024 | 139/MURD | 16/01/2024 | 30 | IOTA CONSTRUCTION | 2.48 | 0 | 0
2281 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2282 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Augmentation of CHANDPUR Zone-I / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000342/2022-2023 | 1808/MURD | 11/07/2022 | 905 | MODERN CONSTRUCTION | 178.55 | 0 | 100
2283 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000844/2021-2022 | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 0 | 1
2284 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/002062/2021-2022 | 1699 / MURD | 07/07/2021 | 60 | M/S JAN MAHAMMAD | 52.35 | 0 | 1
2285 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000297/2023-2024 | 1278/MURD/6 | 10/05/2023 | 0 | Resource Division | 34.53 | 0 | 0
2286 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000347/2023-2024 | 112/MURD/04 | 11/01/2024 | 0 | Resource Division | 40.95 | 0 | 0
2287 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000356/2023-2024 | 305/MURD/05 | 29/01/2024 | 0 | Resource Division | 22.9 | 0 | 0
2288 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system, Rising Main, Sub-soil Investigation and construction of OHR (400 cum) and construction of Boundary wall and repairing of Pump-House in connection with Augmentation of Godhanpara Zone-II water supply scheme under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000579/2022-2023 | 3032/MURD | 16/11/2022 | 1094 | M/S GUHA & ROY ENTERPRISE | 412.1 | 0 | 80
2289 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000738/2021-2022 | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 0 | 0
2290 | Murshidabad Division | Berhampur M/E Division | Construction of new Boundary wall with R.B.T fencing with approach road (Pump No-II) under Godhanpara Zone-II Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/002061/2021-2022 | 275/ISD. | 03/06/2021 | 60 | AJOY GHOSH | 4.52 | 0 | 1
2291 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000049/2022-2023 | 3052/B/MURD | 17/11/2022 | 0 | Resource Division | 18.01 | 0 | 0
2292 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000293/2023-2024 | 1278/MURD/11 | 10/05/2023 | 0 | Resource Division | 14.88 | 0 | 0
2293 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotaryrig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasiadanga Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Raghunathganj-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000111/2023-2024 | 1753/MURD | 06/07/2023 | 21 | KALACHAND DAS | 35.27 | 0 | 70
2294 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000370/2023-2024 | 2722/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0
2295 | Murshidabad Division | Berhampur M/E Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
2296 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 500 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kasiadanga Zone I & II PWSS in Raghunathganj II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000552/2023-2024 | 3190/MURD | 12/10/2023 | 365 | ASTRA | 861.48 | 0 | 0
2297 | Murshidabad Division | Berhampur M/E Division | Painting Boundary wall and under ground pipe line for OHR wash out water of Kashiadanga (Zone-I) Water supply Scheme under Jangipur Sub-Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000660/2020-2021 | 23/JSD | 25/01/2021 | 30 | SUJIT KR DEY | 2.24 | 0 | 1
2298 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000043/2024-2025 | MURD/2991/02 | 13/11/2024 | 0 | Resource Division | 42.68 | 0 | 0
2299 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000099/2023-2024 | 1167/MURD/8 | 28/04/2023 | 0 | Resource Division | 34.82 | 0 | 0
2300 | Murshidabad Division | Berhampur M/E Division | Painting Boundary wall and under ground pipe line for OHR wash out water of Kashiadanga (Zone-I) Water supply Scheme under Jangipur Sub-Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | VCH/001068/2022-2023 |  | 29/11/2022 | 0 | SUJIT KANTI DEY | 2.24 | 0 | 0
2301 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kishorpur (Village code 313961) under Kishorpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723400 in the District of Murshidabad. |  |  | ORD/001609/2021-2022 | 426/MURD | 17/02/2022 | 60 | BISWAS CONSTRUCTION | 40.15 | 0 | 0
2302 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 889/C/MURD | 05/04/2022 | 0 | Resource Division | 5.21 | 0 | 0
2303 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HARIHARPARA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000516/2021-2022 | 348/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0
2304 | Murshidabad Division |  | Work of Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 22 to 23 & 125 mm Dia N.P 23 to 24 and 110 mm Dia N.P 24 to 25,N.P 25 to 26, 90mmOD N.P 26 to27,27 to 28 ;200mm dia N.P 3 to 4,N.P 19 to 20;160 mm OD N.P 21 to 22 at Kanaighat area at uncovered Habitation for smooth water supply arrangement in Kadoa W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. during COVID-19 affected period (Part-B). |  |  | ORD/001269/2021-2022 | 388/JSD | 31/12/2021 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 4.84 | 0 | 100
2305 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1250 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Popara under Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000648/2023-2024 | 3713/MURD | 05/12/2023 | 60 | SANDIP KUMAR BISWAS | 44.69 | 0 | 0
2306 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) of mouza Bara Jumla (Village Code-314144, Krishnaa Sail(Village Code-314143) of Putia and ajoining moujas under Ground water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj II Block & mouza Joykrishnapur (Village Code-313880), of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, and mouza Popara (Village Code-314326) of Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005019109), 0001723441 & 0005184147) |  |  | ORD/001601/2021-2022 | 341/MURD | 10/02/2022 | 180 | CHAKRABORTY CONSTRUCTION | 416 | 0 | 12
2307 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 889/E/MURD | 05/04/2022 | 0 | Resource Division | 15.53 | 0 | 0
2308 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Nandalalpur (Village code 314628) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad. (Sl No-29) |  |  | ORD/000297/2020-2021 | 961/MURD | 24/03/2021 | 180 | S.M. ENTERPRISE | 50.52 | 0 | 1
2309 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dakshin Jitpur (Village code 314713) under Garibpur (Zone-I & Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723342 in the District of Murshidabad. |  |  | ORD/000607/2020-2021 | 322 /MURD | 28/01/2021 | 60 | MOLLA ENTERPRISE (REHENA BIBI) | 22.64 | 10.78 | 0
2310 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1851 nos in connection with (Jal Jeevan Mission ) and under command area of village of Debkunda ( Village Code -315602) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000111/2022-2023 | 1195/MURD | 10/05/2022 | 60 | SOURAV DEY | 82.09 | 0 | 0
2311 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bishannagar ( Village Code -315605) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000287/2020-2021 | 599/MURD | 09/02/2021 | 60 | NAYLA CONSTRUCTION | 95.64 | 0 | 0
2312 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603)adjoining habitation under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000316/2021-2022 | 2384/MURD | 09/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 63.64 | 0 | 0
2313 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603) & adjoining habitation (Part-I) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000317/2021-2022 | 2385/MURD | 09/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 65.45 | 0 | 10
2314 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dalua ( Village Code -315580) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000492/2020-2021 | 591/MURD | 09/02/2021 | 1540 | S. ROY & CO. | 51.49 | 0 | 100
2315 | Murshidabad Division | Berhampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Debkunda (Village code-315602) under Madda Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000552/2022-2023 | 2833/MURD | 17/10/2022 | 120 | AMAL KUMAR DAS | 119.55 | 0 | 0
2316 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000025/2021-2022 | 539/10/MURD | 25/02/2022 | 0 | Resource Division | 10.18 | 0 | 0
2317 | Murshidabad Division | Berhampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BISHANNAGAR (Village Code 315605) under BELDANGA MUNICIPALITY Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block in the District of Murshidabad. Tender no - 905 of 21-22 by EE MURD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/001450/2021-2022 | 346-MSD/21-22 | 05/03/2022 | 0 | NAYLA CONSTRUCTION | 79.01 | 0 | 0
2318 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kupila (Village code 314741) under Kupila Ground Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723481 (Sl-1) |  |  | ORD/001144/2021-2022 | 3675/MURD | 25/11/2021 | 1588 | M/S. SINHA & SONS | 119.26 | 0 | 75
2319 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 395/A/MURD | 16/02/2022 | 0 | Resource Division | 11.77 | 0 | 0
2320 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Malibari (Village code 314569) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184027 in the District of Murshidabad. |  |  | ORD/001590/2021-2022 | 307/MURD | 07/02/2022 | 60 | ULTRA CONSTRUCTION. | 31.15 | 0 | 0
2321 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000046/2021-2022 | 576/MURD | 03/03/2022 | 0 | Resource Division | 1.17 | 0 | 0
2322 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Muradpur Dair ( Village Code -314651) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723429) |  |  | ORD/000247/2021-2022 | 1681/MURD | 05/07/2021 | 60 | PRANAB KUMAR SAHA | 12.14 | 0 | 0
2323 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MURADPUR DAIR (Village Code 314651) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. |  |  | ORD/000638/2020-2021 | 3033/MURD | 07/12/2020 | 45 | PRANAB KUMAR SAHA | 19.83 | 0 | 1
2324 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MURADPUR DAIR (Village Code 314651) under MURADPUR JALANGI Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 294 of 21-22 by EE MURD |  |  | VCH/001547/2021-2022 | 373-MSD/21-22 | 15/03/2022 | 0 | PRANAB KUMAR SAHA | 10.13 | 0 | 0
2325 | Murshidabad Division |  | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | BILL/00257/2024-2025 | 173-MSD/2024-25 | 21/06/2024 | 0 | J.S. CONSTRUCTION | 0.05 | 0 | 0
2326 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati (315980) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District, TNO- 764/2020-21/EE |  |  | BILL/00259/2024-2025 | 172-MSD/2024-25 | 21/06/2024 | 0 | SOUMYA KANTI SINHA | 1.02 | 0 | 0
2327 | Murshidabad Division |  | Construction of Sluice valve chamber & laying of upvc pipeline in connection with retrofitting work at Panchthupi Village (315983) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000023/2022-2023 | 27/KSD | 08/04/2022 | 30 | CHAND ENTERPRISE | 4.72 | 0 | 100
2328 | Murshidabad Division |  | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Village Code-315983)(Mokanpara) under Panchthupi Water Supply Scheme under Kandi Sub Division , P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/000226/2022-2023 | 97 / KSD | 06/06/2022 | 30 | M/S GUHA AND ROY | 4.83 | 0 | 1
2329 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Panchthupi ( Village Code -315983) under Panchthupi Ground Based Water Supply Scheme for Arsenic Affected Area of Burwan Block, under Murshidabad Division, PHE Dte. Scheme ID 0007335523 in the District of Murshidabad. (Sl No-24) |  |  | ORD/000734/2020-2021 | 3050 / MURD | 08/12/2020 | 1850 | M/S GUHA & ROY ENTERPRISE | 113.53 | 0 | 90
2330 | Murshidabad Division |  | Balance work of distribution pipeline in connection with FHTC work at Shibrambati Village under Panchthupi Water Supply Scheme under Kandi Sub Division , P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/001596/2021-2022 | 374/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.73 | 0 | 0
2331 | Murshidabad Division |  | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Dakshin Para & Kesi Para) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/001598/2021-2022 | 376/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.81 | 0 | 0
2332 | Murshidabad Division |  | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Ghosh Para) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. In the district of Murshidabad. |  |  | ORD/001613/2021-2022 | 380/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.51 | 0 | 0
2333 | Murshidabad Division |  | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village PANCHTHUPI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.24 Tender no 70 SE/MC 20-21 |  |  | VCH/000037/2021-2022 | 02/MSD/21-22 | 16/07/2021 | 0 | M/S GUHA & ROY ENTERPRISE | 37.93 | 0 | 0
2334 | Murshidabad Division |  | Laying of Distribution pipeline in connection with FHTC work at PANCHTHUPI Village (Ghosh Para) under PANCHTHUPI W/Sb Scheme under KSD PHE DTE. Tender no - 58 of 21-22 by AE KSD |  |  | VCH/000301/2022-2023 | 111-MSD/22-23 | 07/05/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 4.5 | 0 | 0
2335 | Murshidabad Division |  | BALANCE work of Distribution pipeline in connection with FHTC work at SHIBRAMBATI Village under PANCHTHUPI W/S Scheme under KSD PHE DTE. Tender no - 56 of 21-22 by AE KSD |  |  | VCH/000302/2022-2023 | 111-MSD/22-23 | 07/05/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 4.73 | 0 | 0
2336 | Murshidabad Division |  | Laying of Distribution pipeline in connection with FHTC work at PANCHTHUPI Village (DAKSHIN PARA AND KESI PARA) under PANCHTHUPI W/S Scheme under KSD PHE DTE. Tender no - 57of 21-22 by AE KSD |  |  | VCH/000372/2022-2023 | 143-MSD/22-23 | 11/05/2022 | 0 | M/S GUHA AND ROY | 4.81 | 0 | 0
2337 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHTHUPI under PANCHTHUPI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block in the District of Murshidabad. Tender no - 70 of 20-21 by SE MC |  |  | VCH/001551/2021-2022 | 369-MSD/21-22 | 18/03/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 49.54 | 0 | 0
2338 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at AMARKUNDU G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000406/2021-2022 | 248/LSD | 18/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.18 | 0 | 1
2339 | Murshidabad Division |  | Extension of UPVC pipeline construction of RCC stand post with platform at Darerdanga under Improvement works of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/001227/2021-2022 | 415/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 3.79 | 0 | 1
2340 | Murshidabad Division |  | Balance and allied works For Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madhunia (Village code 315022) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001578/2021-2022 | 345/MURD | 11/02/2022 | 60 | S.K. ENTERPRISE (SANDIP GHOSH) | 14.32 | 0 | 0
2341 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagore (Village code 315019) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001772/2021-2022 | 817/MURD | 25/03/2022 | 30 | M/S. CHOWDHURY CONSTRUCTION | 12.2 | 0 | 0
2342 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000045/2021-2022 | 542/MURD | 25/02/2022 | 0 | Resource Division | 2.47 | 0 | 0
2343 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE |  |  | VCH/002041/2020-2021 | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0
2344 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1994 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Khidirpur ( Village Code -315469) under Kismat Emadpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000026/2022-2023 | 1056/MURD | 25/04/2022 | 60 | MAMATA USHA ENTERPRISE | 99.92 | 0 | 1
2345 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) of 1428 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalnagar ( Village Code -315471) under Kismat Emadpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000028/2022-2023 | 1055/MURD | 25/04/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 75.91 | 0 | 0
2346 | Murshidabad Division | Berhampur Sub-Division | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under KismatImadpur Water Supply Scheme under Berhampore Sub-Division under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000166/2022-2023 | 155/BSD | 12/04/2022 | 30 | SAMAR MUKHERJEE | 4.82 | 0 | 1
2347 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baruipara (Village code 315465) under Kismat Imadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID 5186280 in the District of Murshidabad. (Sl No-38) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000305/2020-2021 | 728/MURD | 25/02/2021 | 180 | SAMAR MUKHERJEE | 53.09 | 0 | 1
2348 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kismat Imadpur (Village code 315468) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.Scheme ID 5186280 (Sl-37) | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000532/2020-2021 | 696/MURD | 24/02/2021 | 180 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 162.04 | 0 | 1
2349 | Murshidabad Division | Berhampur Sub-Division | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under Kismat Imadpur Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000603/2022-2023 | 256/BSD | 31/05/2022 | 30 | SAMAR MUKHERJEE | 4.51 | 0 | 1
2350 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jamalpur (Village code 315469) under Kismat Imadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID - 5186280 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000614/2020-2021 | 3141 /MURD | 11/12/2020 | 60 | MEGHNA CONSTRUCTION (PROP.: ASARUL HOQUE) | 38.95 | 32.7 | 1
2351 | Murshidabad Division | Berhampur Sub-Division | Boundary wall at Head works site for part (B) of Kismat Emadpur water supply Scheme under Berhampore Sub Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001839/2021-2022 | 99/BSD | 22/03/2022 | 30 | AZAD ENTERPRISE | 4.52 | 0 | 0
2352 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | RTOR000019/2021-2022 | 539/4/MURD | 25/02/2022 | 0 | Resource Division | 18.8 | 0 | 0
2353 | Murshidabad Division | Berhampur Sub-Division | HOLDING AWARENESS PROGRESS AT DIFFERENT G.P, TNO- 339/21-22/EE | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | VCH/000863/2021-2022 | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 3.51 | 0 | 0
2354 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Gopjan (P) village, Block:- Berhampore, Berhampore Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000210/2023-2024 | 2321/MURD | 02/08/2023 | 60 | SUBHENDRA MOHAN SARKAR | 30.54 | 0 | 0
2355 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000755/2023-2024 | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 35
2356 | Murshidabad Division | Berhampur M/E Division | Continuation work order for preparation of D.P.R. for Augmentation of Andhua Zone- II & Zone - III PWSS in Farakka Block in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000879/2023-2024 | 3720/MURD | 05/12/2023 | 30 | M/S SOBHA & CO. | 4.51 | 0 | 100
2357 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000169/2023-2024 | 1180/MURD/21 | 29/04/2023 | 0 | Resource Division | 46.79 | 0 | 0
2358 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2359 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000609/2023-2024 | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0
2360 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000120/2023-2024 | 1167/MURD/25 | 28/04/2023 | 0 | Resource Division | 60.5 | 0 | 0
2361 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Khordda Narayanpur Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000237/2023-2024 | 2340/MURD | 03/08/2023 | 60 | CHOWDHURY CONSTRUCTION | 30.55 | 0 | 0
2362 | Murshidabad Division | Kandi Sub-Division | Ground Water based piped water supply scheme for Khordda Narayanpur Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000257/2023-2024 | 2493/MURD | 11/08/2023 | 60 | M/S GREAT INDIA CONSTRUCTION | 30.54 | 0 | 0
2363 | Murshidabad Division | Berhampur M/E Division | BAHAGALPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000498/2023-2024 | 3053/MURD | 29/09/2023 | 731 | ASTRA | 606.64 | 0 | 41
2364 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2365 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000252/2023-2024 | 1219/MURD/37 | 03/05/2023 | 0 | Resource Division | 50.34 | 0 | 0
2366 | Murshidabad Division | Jangipur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 90 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HASIMPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000019/2025-2026 | 964/MURD | 30/04/2025 | 60 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 37.67 | 0 | 0
2367 | Murshidabad Division | Jangipur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
2368 | Murshidabad Division | Jangipur Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
2369 | Murshidabad Division | Jangipur Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Hasimpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | ORD/000762/2023-2024 | 185/MURD | 18/01/2024 | 683 | SAMIRAN KUMAR CHAKRABORTY | 485.31 | 0 | 60
2370 | Murshidabad Division | Jangipur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 2 | RTOR000145/2023-2024 | 1210/MURD/30 | 02/05/2023 | 0 | Resource Division | 158.82 | 0 | 0
2371 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BALLALPUR Ground Based Water Supply Scheme in Farakka Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000055/2025-2026 | 1228/MURD | 28/05/2025 | 60 | MONDAL PRECISION PRIVATE LIMITED | 40.44 | 0 | 0
2372 | Murshidabad Division | Berhampur M/E Division | Providing balance Functional Household Tap Connections (FHTC) of 405 nos household in connection with Jal Jeevan Mission under command area of village of Ballalpur (Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000165/2023-2024 | 1934/MURD | 18/07/2023 | 30 | TARIKUL SK | 14.95 | 0 | 100
2373 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
2374 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2375 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main , Distribution System, 279 nos FHTC, construction of OHR (Capacity 400 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Ballalpur PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000516/2023-2024 | 3115/MURD | 05/10/2023 | 935 | M/S GANGWAL CONSTRUCTION CO | 338.54 | 0 | 85
2376 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III, IV of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ballalpur Water Supply Scheme at Head Work Site, 2nd Site site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000694/2023-2024 | 3780/MURD | 11/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 27.6 | 0 | 0
2377 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000175/2023-2024 | 1180/MURD/30 | 29/04/2023 | 0 | Resource Division | 91.87 | 0 | 0
2378 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000103/2023-2024 | 1744/MURD | 06/07/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.22 | 0 | 100
2379 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
2380 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 779 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
2381 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 811 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
2382 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- II B Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000696/2023-2024 | 3781/MURD | 11/12/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0
2383 | Murshidabad Division | Kandi Sub-Division | KOLLA PWSS to accommodate FHTC under Jal Jeevan Mission of Block-Bharatpur-I of Kandi Sub Division of Murshidabad District under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000018/2023-2024 | 981/MURD | 10/04/2023 | 1022 | SOM CONSTRUCTION AGENCY | 189.17 | 0 | 70
2384 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000071/2023-2024 | 1075/MURD/13 | 19/04/2023 | 0 | Resource Division | 1.38 | 0 | 0
2385 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2386 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHENDRAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti- II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000617/2023-2024 | 3389/MURD | 01/11/2023 | 541 | TAPAN DAS | 18.56 | 0 | 50
2387 | Murshidabad Division | Berhampur M/E Division | Installation of dual power based(Solar & electric) stand alone community purification plant(CWPP) FOR BALANCE 18 UNCOVERED habitations WHERE ARSENIC CONCENTRATION IS .01 TO .015 in the left out Arsenic affected habitations in the different block under Murshidabad Division P.H.E. Dte. at Murshidabad District. HABITATION-MAHENDRAPUR(4UNITS), VILLAGE-MAHENDRAPUR, BLOCK-SUTI-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/001629/2021-2022 | 459/MURD | 21/02/2022 | 45 | ULTRA CONSTRUCTION. | 51.83 | 0 | 10
2388 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000291/2023-2024 | 1230/MURD/33 | 04/05/2023 | 0 | Resource Division | 27.6 | 0 | 0
2389 | Murshidabad Division | Berhampur M/E Division | Construction of Ground Water Based Srikantabati Part B PWSS of accommodate FHTC(2619 Nos), Laying Distribution System, Laying Rising Main, 400 CUM OHR, Switch Room, Boundary Wall in Raghunathganj- I Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000308/2023-2024 | 2675/MURD | 24/08/2023 | 365 | KEYA CONSTRUCTION | 437.95 | 0 | 0
2390 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2391 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | ORD/000620/2023-2024 | 3395/MURD | 01/11/2023 | 21 | KALACHAND DAS | 18.4 | 0 | 100
2392 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000240/2023-2024 | 1219/MURD/32 | 03/05/2023 | 0 | Resource Division | 22.44 | 0 | 0
2393 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER,Junior engineer-II | RTOR000380/2023-2024 | 495/MURD/01 | 15/02/2024 | 0 | Resource Division | 16.13 | 0 | 0
2394 | Murshidabad Division | Berhampur M/E Division | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 0 | 56
2395 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 1
2396 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000257/2023-2024 | 1219/MURD/42 | 03/05/2023 | 0 | Resource Division | 27.39 | 0 | 0
2397 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000390/2023-2024 | 526/MURD/07 | 19/02/2024 | 0 | Resource Division | 18.07 | 0 | 0
2398 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
2399 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000141/2022-2023 | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 100
2400 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000547/2023-2024 | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 35
2401 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-I,Junior engineer-II,Junior engineer-III | RTOR000141/2023-2024 | 1210/MURD/31 | 02/05/2023 | 0 | Resource Division | 64.61 | 0 | 0
2402 | Murshidabad Division | Berhampur Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000177/2024-2025 | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0
2403 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at Head works site for Part-C of Kodla water supply Scheme under Berhampore Sub Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000367/2020-2021 | 3271/MURD | 24/12/2020 | 30 | CHATTERJEE ENTERPRISE | 4.58 | 0 | 0
2404 | Murshidabad Division | Berhampur Sub-Division | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000496/2024-2025 | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 75
2405 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Kodla PWSS to accommodate FHTC of 2000 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement),Construction of Boundary Wall of 250 m and Soil Investigation & 150 Cum Construction of OHR at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000570/2023-2024 | 3289/MURD | 19/10/2023 | 745 | MARUTI CONSTRUCTION AND CO. | 272.25 | 0 | 30
2406 | Murshidabad Division | Berhampur Sub-Division | Water Supply arrangement for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-F) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000652/2020-2021 | 506/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 81
2407 | Murshidabad Division | Berhampur Sub-Division | Water Supply arrangement for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-J) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000656/2020-2021 | 511/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 100
2408 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Construction of 400 CUM capacity 20.00 mtr staging height RCC elevated Over Head Reservoir on raft foundation as per drawing & design reference-PC-I/OHR/11/2012) including supply, delivery and errecting inlet and overflow pipe connection etc all complete at head work site of KODLA water supply scheme of Berhampore Sub-Division under Murshidabad Division Murshidabad District P.H.Engg Dept. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000661/2020-2021 | 3114/MURD | 09/12/2020 | 270 | M/S KAMRULA CONSTRUCTION CO. | 98.16 | 0 | 5
2409 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Laying Distribution System For Augmentation of Kodla (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000845/2022-2023 | 730/MURD | 15/03/2023 | 1086 | SUDIPA SINGHA ROY | 100.66 | 0 | 50
2410 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
2411 | Murshidabad Division | Berhampur M/E Division | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000366/2023-2024 | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 0 | 56
2412 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 1
2413 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000256/2023-2024 | 1219/MURD/41 | 03/05/2023 | 0 | Resource Division | 31.36 | 0 | 0
2414 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000389/2023-2024 | 526/MURD/06 | 19/02/2024 | 0 | Resource Division | 14.88 | 0 | 0
2415 | Murshidabad Division | Berhampur M/E Division | Augmentation of Domkal Zone-II (Part-B) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000001/2023-2024 | 946/MURD | 05/04/2023 | 1002 | GOUTAM MANDAL | 337.24 | 0 | 60
2416 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 10
2417 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2418 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-II | RTOR000249/2023-2024 | 1219/MURD/35 | 03/05/2023 | 0 | Resource Division | 45.55 | 0 | 0
2419 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/07/2024 to 16/01/2025. [ Vehicle No:- WB 58 CD 3758] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000090/2024-2025 | 52/JSD | 16/07/2024 | 184 | HASSAN CONSTRUCTION | 0.88 | 0 | 0
2420 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2421 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000064/2023-2024 | 1043/MURD/7 | 19/04/2023 | 0 | Resource Division | 25.05 | 0 | 0
2422 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of BRINDABANPUR ZONE-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000840/2022-2023 | 744/MURD | 16/03/2023 | 1021 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 487.63 | 0 | 45
2423 | Murshidabad Division | Berhampur M/E Division | Construction of Pump House, Boundary Wall, of BRINDABANPUR ZONE-II Ground water based Piped water supply scheme with in Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000844/2023-2024 | 778/MURD | 14/03/2024 | 524 | M/S S M ENTERPRISE | 28.51 | 0 | 65
2424 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
2425 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000263/2023-2024 | 1230/MURD/06 | 04/05/2023 | 0 | Resource Division | 4.02 | 0 | 0
2426 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bati & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000046/2023-2024 | 1216/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 50
2427 | Murshidabad Division | Kandi Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Uncovered BATI Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000706/2022-2023 | 120/MURD | 13/01/2023 | 30 | DEBASIS BOSE | 71.38 | 0 | 0
2428 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) for Uncoveded BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte.for [ (i) Amount for Laying Distribution System: Rs.72,79,775.00 & (ii) Amount for Pump House: Rs. 10,55,058.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000720/2022-2023 | 121/MURD | 13/01/2023 | 838 | M/S. GOURI ENTERPRISE | 84.16 | 0 | 50
2429 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for construction of 200 Cum OHR,,Laying Distribution System (PART-A),Rising Main Connection, Boundwary Wall, for Uncovered of BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division , PHE.Dte. [(i)Amount for LDS , R.Main: Rs.1,64,06,836.00 & (ii) Amount for OHR & B. Wall : Rs. 1,25,46,499.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000766/2022-2023 | 484/MURD | 20/02/2023 | 1046 | AJAY MONDAL | 289.48 | 0 | 30
2430 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000022/2023-2024 | 1210/MURD/33 | 02/05/2023 | 0 | Resource Division | 24.92 | 0 | 0
2431 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000368/2023-2024 | MURD/439/12 | 08/02/2024 | 0 | Resource Division | 8.91 | 0 | 0
2432 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of P.T.Rasulpur (Part - A) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000797/2022-2023 | 602/MURD | 02/03/2023 | 1035 | M/S.TAPAS KUMAR CHAKRABORTY | 521.15 | 0 | 30
2433 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
2434 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000191/2023-2024 | 1210/MURD/12 | 02/05/2023 | 0 | Resource Division | 110.91 | 0 | 0
2435 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000393/2023-2024 | 526/MURD/03 | 19/02/2024 | 0 | Resource Division | 5.48 | 0 | 0
2436 | Murshidabad Division | Kandi Sub-Division | RESTORATION OF DAMAGED ROAD DUE TO LAYING OF PHE PIPELINE OF MAHADIA-DURGAPUR ROAD FROM 0.30 KM TO 2.10 KM UNDER MSD HIGHWAY DIVISION.-II DURING THE YEAR OF 2024-25 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | BILL/01073/2024-2025 | 393-MSD/2024-25 | 19/09/2024 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 13.77 | 0 | 0
2437 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of ANDULIA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362266S000 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000694/2022-2023 | 147/MURD | 17/01/2023 | 988 | M/S. CHOWDHURY BUILDERS | 605.19 | 0 | 25
2438 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000037/2023-2024 | 1004/MURD/12 | 17/04/2023 | 0 | Resource Division | 24.19 | 0 | 0
2439 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000039/2023-2024 | 1043/MURD/14 | 17/04/2023 | 0 | Resource Division | 34.54 | 0 | 0
2440 | Murshidabad Division |  | Last mile connectivity and providing 3874 nos Functional House Hold Connection from Zone- IX of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000332/2023-2024 | 2689/MURD | 25/08/2023 | 120 | SUJIT KUMAR SAHA | 223.42 | 0 | 0
2441 | Murshidabad Division |  | Last mile connectivity and providing 8231 nos Functional House Hold Connection from Zone- X of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000333/2023-2024 | 2690/MURD | 25/08/2023 | 120 | HANNAN BUILDERS PVT.LTD. | 475.31 | 0 | 0
2442 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JASOHARI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000652/2022-2023 | 3400/MURD | 22/12/2022 | 45 | M/S B.R. SUPPLIERS | 16.8 | 0 | 0
2443 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JASOHARI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362341S000) [ (i)Amount for LDS , R. Main & FHTC: Rs. 1,91,63,541.00 & (ii) Amount for OHR,Boundwary Wall & Pump House : Rs. 1,56,48,969.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | ORD/000765/2022-2023 | 481/MURD | 20/02/2023 | 365 | M/S. NANDY ENTERPRISE | 347.6 | 0 | 0
2444 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KANDI BLOCK | RTOR000006/2023-2024 | 1004/MURD/8 | 11/04/2023 | 0 | Resource Division | 24.37 | 0 | 0
2445 | Murshidabad Division | Berhampur M/E Division | Overhauling of 450 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur, Dogachhi village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-I Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000004/2025-2026 | 762/MURD | 02/04/2025 | 90 | H.MONDAL CONSTRUCTION | 89.23 | 0 | 0
2446 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone - I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000114/2023-2024 | 1756/MURD | 06/07/2023 | 21 | HARUN ALL RASHID & BROTHERS | 35.28 | 0 | 90
2447 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution System, Rising Main, Construction of Boundary wall , Repairing & Renovation of Pump House in connection with Augmentation of Dogachhi Zone-I Water Supply Scheme in Samsherganj Block of Murshidabad District under Murshidabad Division, PHE Dte. [(i)Amount for LDS & R.Main: Rs.1,51,21,932.00 & (ii) Amount for Construction of Boundary Wall and repairing of Pump House : Rs. 22,74,098.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000689/2022-2023 | 128/MURD | 16/01/2023 | 60 | M/S. N. ISLAM AND CO. | 173.87 | 0 | 40
2448 | Murshidabad Division | Berhampur M/E Division | Formal work order for Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection by Construction/ installation of Comiunity Purification Plant (CPP) unit including Tubewell (125 x 50 mm dia ) with Submersible pump (for Population 351-500 & Raw Water As concentration upto 0.15 ppm) at Diffarent habitations [For-8 nos Unit] in different Villages of Block of Suti-I (2 Nos),Shamsherganj (6 nos) under Murshidabad Division , P.H.E. Dte. in the District of Murshidabad. (SITE LIST Of S/L 15) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/000862/2021-2022 | 3320/MURD | 07/10/2021 | 75 | TEKNO ENTERPRISE | 104.28 | 0 | 50
2449 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2450 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,JUNIOR ENGINEER 6,Junior engineer-II | RTOR000111/2023-2024 | 1167/MURD/4 | 28/04/2023 | 0 | Resource Division | 32.69 | 0 | 0
2451 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA ZONE-I Water Supply Scheme at Head Work Site, 2nd Site site at Jalangi Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000389/2023-2024 | 2793/MURD | 04/09/2023 | 21 | A.M. ENTERPRISE | 27.45 | 0 | 0
2452 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Sagarpara Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block in the District of Murshidabad under Murshidabad Division, P H Engg Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000534/2022-2023 | 2641/MURD | 19/09/2022 | 365 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 798.75 | 0 | 60
2453 | Murshidabad Division | Berhampur M/E Division | Allied Work of OHR & HDPE Pipe line for Augmentation of Sagarpara Part-A Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block in the District of Murshidabad under Murshidabad Division, P H Engg Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000750/2023-2024 | 119/MURD | 11/01/2024 | 180 | M/S.TAPAS KUMAR CHAKRABORTY | 120.98 | 0 | 60
2454 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000033/2022-2023 | 2780/B/MURD | 01/10/2022 | 0 | Resource Division | 20.63 | 0 | 0
2455 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000047/2022-2023 | 3037/B/MURD | 16/11/2022 | 0 | Resource Division | 118.48 | 0 | 0
2456 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village PARASPUR (Village Code 314616) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. |  |  | ORD/000597/2020-2021 | 3031/MURD | 07/12/2020 | 45 | KALYAN CHAKROBORTY | 10.37 | 0 | 0
2457 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of Chandabad west side ( Village Code _315517) of Ghoramara Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000161/2022-2023 | 150/BSD | 12/04/2022 | 30 | M/S S.R.K.ENTERPPRISE, | 4.7 | 0 | 0
2458 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandabad (Village code 315517) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/000591/2020-2021 | 3137/MURD | 11/12/2020 | 60 | M/S. CHOWDHURY CONSTRUCTION | 23.85 | 23.62 | 0
2459 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of Chandabad east side ( Village Code _315517) of Ghoramara Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 3 | ORD/001778/2021-2022 | 107/BSD | 28/03/2022 | 30 | SUMAN CHOWDHURY | 4.82 | 0 | 0
2460 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dighirpar( Village Code -314125) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852). |  |  | ORD/000184/2020-2021 | 576/MURD | 09/02/2021 | 60 | JAMIRUL CONSTRUCTION | 41.39 | 38.25 | 0
2461 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DIGHIRPAR (Village Code-314125) under sarface water based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the dist of Murshidabad District under Murshidabad Division, PHE Dte. Scheme ID: 0001756852 in the dist of MSD |  |  | VCH/000233/2021-2022 |  | 06/08/2021 | 0 | JAMIRUL CONSTRUCTION | 38.25 | 0 | 0
2462 | Murshidabad Division |  | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 05/21-22/AE-LSD |  |  | VCH/000870/2021-2022 | 209-MSD/21-22 | 08/12/2021 | 0 | S.S.INFRASTRUCTURE | 2.12 | 0 | 0
2463 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalupur ( Village Code -313890) under Kusumgachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723224) |  |  | ORD/000506/2020-2021 | 596/MURD | 09/02/2021 | 60 | PRATAP KUMAR SINHA | 6.24 | 0 | 1
2464 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hilora ( Village Code -313898) under Kusumgachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723224) |  |  | ORD/000512/2020-2021 | 593/MURD | 09/02/2021 | 60 | HOQUEDAR ALI | 64.7 | 0 | 1
2465 | Murshidabad Division |  | Interconnection of DI pipe line between allied balance work of ¿¿HILORA ¿..under Murshidabad Div PHE DTE. Tender no - 67 of 21-22 by AE JSD |  |  | VCH/000002/2022-2023 | 01-MSD/22-23 | 14/04/2022 | 0 | SAMAR MUKHERJEE | 4.85 | 0 | 0
2466 | Murshidabad Division |  | Construction of allied balance work of ¿¿HILORA ¿..under JSD PHE DTE. Tender no - 66 of 21-22 by AE JSD |  |  | VCH/000003/2022-2023 | 02-MSD/22-23 | 14/04/2022 | 0 | SAMAR MUKHERJEE | 4.97 | 0 | 0
2467 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village LALUPUR (Village Code: 313890) under KASUMGACHHI Ground Water Based Water Supply Scheme for arsenic affected areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID- 0001723224). Tender no- 782 of 20-21 by EE / MSD |  |  | VCH/000192/2021-2022 | 10-MSD / 21-22 | 06/08/2021 | 0 | M/S PRATAP KUMAR SINHA | 4.24 | 0 | 0
2468 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District (PART-I), tno- 895/20-21/EE |  |  | VCH/000682/2021-2022 | 171-MSD/21-22 | 28/10/2021 | 0 | HOQUEDAR ALI | 59.07 | 0 | 0
2469 | Murshidabad Division |  | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion 90 mm dia U.P.C Pipe in between N.P 3(Pry. School) to N.P 12 via N.P 15 upto N.P 16(Bansabati G.P Member Loton Sara's House) for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. |  |  | ORD/000293/2021-2022 | 198/JSD | 30/07/2021 | 30 | GAUTAM KUMAR CHAUDHURI | 3.81 | 0 | 1
2470 | Murshidabad Division |  | Laying of U.P.V.C New Extention pipeline of 90 mm dia in between N.P 6(Durga Mandir) to N.P 12 Upto Pond for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. |  |  | ORD/000296/2021-2022 | 199/JSD | 30/07/2021 | 15 | GAUTAM KUMAR CHAUDHURI | 1.43 | 0 | 1
2471 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000465/2020-2021 | 547/MURD | 05/02/2021 | 30 | PRADIP KUMAR DAS | 39.01 | 0 | 100
2472 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) |  |  | ORD/001659/2021-2022 | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0
2473 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000004/2021-2022 | 3632/C/MURD | 23/11/2021 | 0 | Resource Division | 22.88 | 0 | 0
2474 | Murshidabad Division |  | Preparation of D.P.R (Consultancy work) in connection of different existing PWSS Scheme, Block-SUTI-I to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 402 of 21-22 by EE MURD |  |  | VCH/001447/2021-2022 | 301-MSD/21-22 | 04/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.77 | 0 | 0
2475 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000261/2020-2021 | 2392/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 0 | 1
2476 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIMULIA G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000469/2021-2022 | 237/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0
2477 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000632/2020-2021 | 2392/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 0 | 0
2478 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) |  |  | ORD/001278/2021-2022 | 141/MURD | 19/01/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 383.18 | 0 | 1
2479 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2021-2022 | 3632/D/MURD | 23/11/2021 | 0 | Resource Division | 23.38 | 0 | 0
2480 | Murshidabad Division | Lalbag Sub-Division | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000135/2024-2025 | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 40
2481 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000349/2022-2023 | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 0 | 100
2482 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 0 | 100
2483 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
2484 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 400 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Habaspur PWSS in Bhagwagola- I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000658/2023-2024 | 3516/MURD | 09/11/2023 | 874 | M/S. GOUTAM CHAKRABORTY | 717.52 | 0 | 10
2485 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000123/2023-2024 | 1167/MURD/19 | 28/04/2023 | 0 | Resource Division | 22.34 | 0 | 0
2486 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
2487 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2488 | Murshidabad Division | Berhampur M/E Division | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 244/5 & 244/6) at Monrajpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Mahadevnagar Zone - II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000421/2021-2022 | 2477/MURD | 16/08/2021 | 60 | ACQUA CONSTRACTION CONSORTIAM | 23.65 | 0 | 0
2489 | Murshidabad Division | Kandi Sub-Division | BADDA PWSS under Jal Jivan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000095/2023-2024 | 1692/MURD | 28/06/2023 | 1004 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 226.02 | 0 | 10
2490 | Murshidabad Division | Kandi Sub-Division | BADDA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. (Part A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000142/2023-2024 | 1866/MURD | 14/07/2023 | 902 | DHIRENDRANATH MONDAL | 344.64 | 0 | 10
2491 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BADDA AND IT'S ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000392/2023-2024 | 2794/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.45 | 0 | 100
2492 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000076/2023-2024 | 1075/MURD/18 | 19/04/2023 | 0 | Resource Division | 24.74 | 0 | 0
2493 | Murshidabad Division |  | Permission for laying pipeline (200 mm dia) along the NH-12 within the utility corridor from Moregram to gangadda of sagardighi surface water based drinking water supply scheme block sagardighi, district-Murshidabad under Murshidabad Division, P.H.E.Dte. |  |  | BILL/01075/2023-2024 | 543-MSD/2023-24 | 16/02/2024 | 0 | CHIEF ENGINEER CIVIL MINISTRY OF ROAD TRANSPORT AND HIGHWAYS KOLKATA | 3.18 | 0 | 0
2494 | Murshidabad Division |  | Last mile connectivity and providing 1803 nos Funcational House Hold Connection from Zone- II of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000329/2023-2024 | 2686/MURD | 25/08/2023 | 120 | AJAY MONDAL | 114.49 | 0 | 0
2495 | Murshidabad Division |  | Last mile connectivity and providing 5600 nos Functional House Hold Connection from Zone- XIII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . |  |  | ORD/000335/2023-2024 | 2692/MURD | 25/08/2023 | 120 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 352.9 | 0 | 0
2496 | Murshidabad Division |  | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 900 CuM of staging height 20 Meter at Head Work site within BANYESWAR(Zone-XIII) W/S Scheme, Block-Sagardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. |  |  | ORD/000836/2023-2024 | 785/MURD | 14/03/2024 | 60 | BIJAY CHOWDHURY | 84.81 | 0 | 85
2497 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BISWANATHPUR Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | ORD/000387/2023-2024 | 2777/MURD | 01/09/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 90
2498 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_KHARGRAM BLOCK | RTOR000081/2023-2024 | 1129/MURD/4 | 25/04/2023 | 0 | Resource Division | 1.78 | 0 | 0
2499 | Murshidabad Division | Kandi Sub-Division | Construction of Valve Chamber, M.S Gate, Laying Distribution System of UPVC Pipeline for Augmentation of Kamalakantapur / Bahara Water Supply Scheme in Bharatpur- I Block, of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000191/2024-2025 | 3148/MURD | 03/12/2024 | 45 | ABDUL ENTERPRISE | 45.91 | 0 | 0
2500 | Murshidabad Division | Kandi Sub-Division | Construction of Boundary wall at 1st Tubewell site of Khasra PWSS & Bahara PWSS of Kandi Block in Kandi Sub-Division under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000196/2024-2025 | 3214/MURD | 09/12/2024 | 266 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 12.9 | 0 | 5
2501 | Murshidabad Division | Kandi Sub-Division | Design, Drawing, Fabrication, Erection Iron Elimination Plant (IEP) of 45 m3/hr & 40m3/hr Capacity as per Departmental approved model including comossing trial run (3months) of 2 nos Construction of Blower Room (H.W.Site), Pump House (3rd Site), Boundary Wall (3rd Site), Laying of UPVC Pipe of Bahara Water Supply Scheme in Kandi Block of Kandi Sub Division, under Murshidabad Division P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000240/2024-2025 | 190/MURD | 21/01/2025 | 420 | ANIRUDDHYA BOSE | 94.01 | 0 | 30
2502 | Murshidabad Division | Kandi Sub-Division | Construction 200 Cum OHR, Laying Distribution System Part-A, FHTC at Brahmanpara Village (Village Code-315290), Bahara Village (Village Code-315291) & Bhandira Village (Village Code-315292), Repairing of Existing Pump house (H.W), Boundary Wall, Existing OHR for Augmentation of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE. Dte Part-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000248/2023-2024 | 2463/MURD | 09/08/2023 | 1180 | ROY ENTERPRISE | 182.7 | 0 | 21
2503 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC work at Dohalia Village (Village Code-315294), Baje Dohalia Village (Village Code-315293) & Bhandira Village (Village Code-315292) for Augmentation of of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000251/2023-2024 | 2462/MURD | 09/08/2023 | 150 | M/S.S.S. ENTERPRISE | 215.67 | 0 | 20
2504 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUNRAPARA, Augmentation of Bahara & Pacchipara Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000269/2023-2024 | 2587/MURD | 21/08/2023 | 438 | INDRAJIT MAZUMDAR | 18.43 | 0 | 60
2505 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-II,III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bahara & adjoining mouzas Water Supply Scheme at 2nd & 3 r d Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000343/2023-2024 | 2679/MURD | 24/08/2023 | 586 | HARUN ALL RASHID & BROTHERS | 21.15 | 0 | 60
2506 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000396/2023-2024 | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 75
2507 | Murshidabad Division | Kandi Sub-Division | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001597/2021-2022 | 375/KSD | 19/01/2022 | 30 | ROY ENTERPRISE | 4.53 | 0 | 100
2508 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000044/2023-2024 | 1043/MURD/8 | 17/04/2023 | 0 | Resource Division | 95.05 | 0 | 0
2509 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000061/2022-2023 | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 95.05 | 0 | 0
2510 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000360/2023-2024 | MURD/439/06 | 08/02/2024 | 0 | Resource Division | 4.9 | 0 | 0
2511 | Murshidabad Division | Berhampur M/E Division | SUBMISSION OF ONE NO REPAIRING ESTIMATE OF ROAD WHICH IS DAMAGED DURING PHE PIPE LINE LAYING IE. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00655/2024-2025 | 282-MSD/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 20.84 | 0 | 0
2512 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Narsinghpur Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000276/2023-2024 | 2617/MURD | 22/08/2023 | 793 | RAJKUMAR MONDAL | 202.06 | 0 | 55
2513 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000561/2022-2023 | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 0 | 1
2514 | Murshidabad Division | Berhampur M/E Division | Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundary wall for Augmentation of NARASINGHAPUR Zone-II PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte.PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000594/2023-2024 | 3333/MURD | 23/10/2023 | 555 | GOUTAM MANDAL | 142.16 | 0 | 40
2515 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000241/2023-2024 | 1219/MURD/23 | 03/05/2023 | 0 | Resource Division | 16.53 | 0 | 0
2516 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System Part-A, Rising Main, Construction of 200 Cum OHR, Boundwary Wall, Pump House, for Kapasdanga water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000020/2023-2024 | 993/MURD | 11/04/2023 | 996 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 189.09 | 0 | 70
2517 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kapasdanga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000045/2023-2024 | 1103/MURD | 24/04/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 65
2518 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0
2519 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000070/2022-2023 | 1936/MURD/5 | 18/07/2023 | 0 | Resource Division | 17.68 | 0 | 0
2520 | Murshidabad Division | Islampur Sub-Division | Augmentation of JURANPUR (Part-B) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000080/2023-2024 | 1382/MURD | 22/05/2023 | 955 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 122.02 | 0 | 20
2521 | Murshidabad Division | Islampur Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-B) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000128/2023-2024 | 1765/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 35.34 | 0 | 80
2522 | Murshidabad Division | Islampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000390/2023-2024 | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 0 | 100
2523 | Murshidabad Division | Islampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000151/2023-2024 | 1180/MURD/01 | 29/04/2023 | 0 | Resource Division | 1.11 | 0 | 0
2524 | Murshidabad Division | Kandi Sub-Division | Construction of 300 Cum OHR, Pump House, Boundwary Wall, Rising Main Connection & Repairing work of Existing OHR, Boundwary Wall , Pump House for Augmentation of Kagram water supply scheme of Bharatpur-II Block under Murshidabad Division, PHE Dte. PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000019/2023-2024 | 992/MURD | 11/04/2023 | 721 | DALIM BISWAS ENTERPRISE | 157.49 | 0 | 15
2525 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kagram & Salar Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000048/2023-2024 | 1102/MURD | 24/04/2023 | 20 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0
2526 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System & FHTC, for Augmentation of Kagram water supply scheme of Bharatpur-II Block under Murshidabad Division, PHE Dte. PART_B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000050/2023-2024 | 1232/MURD | 04/05/2023 | 365 | M/S NIRAPADA BHATTACHARJEE | 272.58 | 0 | 30
2527 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2528 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
2529 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000030/2023-2024 | 1043/MURD | 17/04/2023 | 0 | Resource Division | 37.46 | 0 | 0
2530 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000069/2022-2023 | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 66.52 | 0 | 0
2531 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000359/2023-2024 | MURD/439/04 | 08/02/2024 | 0 | Resource Division | 4.1 | 0 | 0
2532 | Murshidabad Division | Berhampur M/E Division | Formal work order for Augmentation of Garibpur Zone-I (Part - A) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000807/2022-2023 | 624/MURD | 03/03/2023 | 1123 | M/S. S. DAS AND ENTERPRISE | 590.43 | 0 | 40
2533 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
2534 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000201/2023-2024 | 1210/MURD/25 | 02/05/2023 | 0 | Resource Division | 217 | 0 | 0
2535 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000123/2023-2024 | 1773/MURD | 06/07/2023 | 695 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 80
2536 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UTTAR MAHAMMADPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000284/2023-2024 | 2632/MURD | 23/08/2023 | 587 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 50
2537 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2538 | Murshidabad Division | Berhampur M/E Division | Formal work order for UTTAR MAHAMMADPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000841/2022-2023 | 742/MURD | 16/03/2023 | 1021 | CREATIVE CONSTRUCTION | 413.33 | 0 | 20
2539 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000284/2023-2024 | 1230/MURD/27 | 04/05/2023 | 0 | Resource Division | 47.71 | 0 | 0
2540 | Murshidabad Division | Berhampur M/E Division | Augmentation of GARIBPUR (Zone-II) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000081/2023-2024 | 1381/MURD | 22/05/2023 | 1123 | DOBAY CONSTRUCTION | 241.39 | 0 | 85
2541 | Murshidabad Division | Berhampur M/E Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. from 01/10/2025 to 31/03/2026 (120 days) [WB-26T-1742] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000174/2025-2026 | 390/ISD | 25/09/2025 | 181 | HAMIDUL ISLAM | 0.59 | 0 | 0
2542 | Murshidabad Division | Berhampur M/E Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.,e. from 01/01/2025 to 30/06/2025 (Vehicle No. W.B-57E-9142) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000508/2024-2025 | 626/ISD | 31/12/2024 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 0
2543 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
2544 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000144/2023-2024 | 1167/MURD/36 | 28/04/2023 | 0 | Resource Division | 44.55 | 0 | 0
2545 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KEYADANGA Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000053/2025-2026 | 1225/MURD | 28/05/2025 | 60 | M/S . SUKUMAR SINHA | 19.62 | 0 | 0
2546 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000357/2023-2024 | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 0 | 100
2547 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based HAFANIA (ZONE-II) & KEYADANGA PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | ORD/000819/2022-2023 | 801/MURD | 22/03/2023 | 831 | ATIKUL SAIKH | 367.41 | 0 | 100
2548 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 6,Junior engineer-III | RTOR000267/2023-2024 | 1230/MURD/10 | 04/05/2023 | 0 | Resource Division | 9.94 | 0 | 0
2549 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well,120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HILORA - II & KOHETPUR Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000016/2024-2025 | 1755/MURD | 13/06/2024 | 464 | R.K. DRILLING SERVICES | 11.79 | 0 | 100
2550 | Murshidabad Division | Berhampur M/E Division | Allied work of laying of additional pipeline of 125 mm dia, Land Development, connecting road and construction of soakwell and construction of surface drain of 150 m lenth at Hilora zone 2 PWSS at suti -1 Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000021/2024-2025 | 1812/MURD | 20/06/2024 | 587 | M H SUPPLIERS | 53.94 | 0 | 50
2551 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000054/2025-2026 | 1224/MURD | 28/05/2025 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 23.01 | 0 | 0
2552 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System and Road Restoration of Hilora Zone-II PWSS in Suti-I Block , Jangipur Sub-Division under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000075/2025-2026 | 1332/MURD | 10/06/2025 | 60 | PARTHA PRATIM DAS | 22.91 | 0 | 0
2553 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2554 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000133/2023-2024 | 1769/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 18.45 | 0 | 100
2555 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 1424 nos household, Special repair and renovation of existing 2 (Two) Nos Pump House & Alied Works and Repair of Boundary Wall (140m + 50m) =190 m at T/W-I site & T/W-II site for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000870/2022-2023 | 849/MURD | 24/03/2023 | 889 | JAMIRUL CONSTRUCTION | 79.6 | 0 | 85
2556 | Murshidabad Division | Berhampur M/E Division | Laying of Rising Main, Laying of Distribution System and Overhauling of RCC 180 Cum OHR for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block in Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | ORD/000871/2022-2023 | 850/MURD | 24/03/2023 | 1066 | M H SUPPLIERS | 71.55 | 0 | 70
2557 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-III | RTOR000193/2023-2024 | 1210/MURD/09 | 02/05/2023 | 0 | Resource Division | 48.45 | 0 | 0
2558 | Murshidabad Division | Kandi Sub-Division | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of SALINDA PWSS in Bharatpur-I Block, of Kandi Sub-Division under Murshidabad Division ,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000180/2024-2025 | 3143/MURD | 03/12/2024 | 90 | DHIRENDRANATH MONDAL | 38.56 | 0 | 30
2559 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250 mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SALINDA PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000667/2022-2023 | 3406/MURD | 22/12/2022 | 45 | INDRAJIT MAZUMDAR | 16.8 | 0 | 100
2560 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Laying of Distribution System (Part-A) and Construction of Boundary wall of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000699/2022-2023 | 161/MURD | 17/01/2023 | 952 | TANUSHREE ENTERPRISE | 145.06 | 0 | 35
2561 | Murshidabad Division | Kandi Sub-Division | Formal Work Order For Laying of Distribution System (Part-B) and Construction of Pump House for Augmentation of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000701/2022-2023 | 160/MURD | 16/01/2023 | 989 | SOM CONSTRUCTION AGENCY | 146.49 | 0 | 39
2562 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 350 Cum OHR,Laying Distribution System (PART-C),Rising Main Connection, FHTC , for Uncovered of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000729/2022-2023 | 340/MURD | 08/02/2023 | 1301 | DHIRENDRANATH MONDAL | 387.6 | 0 | 25
2563 | Murshidabad Division | Kandi Sub-Division | Additional & Balance Work Laying of Distribution System , Land Devolapement of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000733/2023-2024 | 54/MURD | 05/01/2024 | 30 | DHIRENDRANATH MONDAL | 17.25 | 0 | 80
2564 | Murshidabad Division | Kandi Sub-Division | Construction of Pump House Cum Chlorine Room, Boundary Wall, Approach Road & Land Development of Salinda PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | ORD/000848/2023-2024 | 823/MURD | 15/03/2024 | 60 | M/S RELIABLE | 27.67 | 0 | 0
2565 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 5,Junior engineer-II | RTOR000017/2023-2024 | 1210/MURD/41 | 02/05/2023 | 0 | Resource Division | 46.94 | 0 | 0
2566 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000282/2023-2024 | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 10
2567 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jotkomol Zone-II Water Supply Scheme of TW-I HW Site under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000582/2022-2023 | 3065/MURD | 17/11/2022 | 30 | M/S B.R. SUPPLIERS | 10.6 | 0 | 100
2568 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000620/2023-2024 | 3395/MURD | 01/11/2023 | 21 | KALACHAND DAS | 18.4 | 0 | 100
2569 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JOTKOMAL ZONE-II Water Supply Scheme as required at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000630/2023-2024 | 3425/MURD | 02/11/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 0 | 100
2570 | Murshidabad Division | Berhampur M/E Division | Renovation of Existing IEP (Capacity 58 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chember of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of JOTKOMAL ZONE-II Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000662/2023-2024 | 3560/MURD | 21/11/2023 | 30 | M/S BAPPA ENTERPRISE | 4.89 | 0 | 100
2571 | Murshidabad Division | Berhampur M/E Division | Allied works for Renovation of Existing IEP (Capacity 54 Cu.M/hr) at Jotkamal Zone-II W/S Scheme in connection with Augmentation of Jotkamal (Zone-II) PWSS under Murshidabad Division P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/000834/2023-2024 | 784/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 11.26 | 0 | 0
2572 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 6,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2573 | Murshidabad Division | Berhampur M/E Division | Construction of Boundwary Wall , Pump House T.W-III , PCC approach road , Land Development for Augmentation of Katlamari PWSS in Raninagar-II Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000083/2025-2026 | 1460/MURD | 26/06/2025 | 90 | SANJITA CONSTRUCTION | 22.83 | 0 | 0
2574 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATLAMARI PWSS (ZONE- I ) Water Supply Scheme at Head Work Site, 2nd Site site at Raninagar-II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000113/2023-2024 | 1755/MURD | 06/07/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 18.44 | 0 | 100
2575 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system (Part-B) and Providing Functional Household Tap Connection to 665 nos household & Construction of Boundary Wall and repairing of Pump House of Katlamari Zone -I of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [(i)Amount for LDS & FHTC: Rs.14057282.00 & (ii) Amount for Construction of Boundary Wall and repairing of Pump House : Rs. 2963929.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000601/2022-2023 | 3150/MURD | 28/11/2022 | 60 | J.S. CONSTRUCTION | 170.18 | 0 | 50
2576 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system (Part-C) and Providing Functional Household Tap Connection to 670 nos household & Construction of Pump House of Katlamari Zone-I of Islampur Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000606/2022-2023 | 3191/MURD | 01/12/2022 | 1038 | ULTRA CONSTRUCTION. | 110.88 | 0 | 92
2577 | Murshidabad Division | Berhampur M/E Division | Formal work order for Laying of Distribution system(Part-A) , Rising Main, Providing Functional Household Tap Connection to 670 nos household & Repair and Renovation of OHR of 500 cum Capacity of Katlamari Zone -I Water Supply Scheme of Islampur Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000626/2022-2023 | 3278/MURD | 09/12/2022 | 60 | ARINDAM MAJUMDAR | 135.29 | 0 | 30
2578 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000739/2021-2022 | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 0 | 1
2579 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000051/2022-2023 | 3052/D/MURD | 17/11/2022 | 0 | Resource Division | 27.08 | 0 | 0
2580 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of Saktipur Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000540/2022-2023 | 2860/MURD | 19/10/2022 | 895 | M/S. ROY TRADING CO. | 302.59 | 0 | 80
2581 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000598/2022-2023 | 3072/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 21.18 | 0 | 1
2582 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000833/2021-2022 | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 0 | 0
2583 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | RTOR000298/2023-2024 | 1278/MURD/3 | 10/05/2023 | 0 | Resource Division | 129.08 | 0 | 0
2584 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000036/2024-2025 | MURD/2481/08 | 04/09/2024 | 0 | Resource Division | 7.57 | 0 | 0
2585 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000040/2022-2023 | 2780/I/MURD | 01/10/2022 | 0 | Resource Division | 7.57 | 0 | 0
2586 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000165/2023-2024 | 1180/MURD/11 | 29/04/2023 | 0 | Resource Division | 8.83 | 0 | 0
2587 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000183/2023-2024 | 1210/MURD/29 | 02/05/2023 | 0 | Resource Division | 10.21 | 0 | 0
2588 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kadkhali ( Village Code -315657) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000183/2021-2022 | 1570/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 23.43 | 0 | 0
2589 | Murshidabad Division | Berhampur Sub-Division | Additional work of providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kadkhali (village code 315657) under Bachhara Water Supply Scheme of Beldanga-II Block in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-III | ORD/000433/2021-2022 | 2594/MURD | 25/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 16.76 | 0 | 0
2590 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (963 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jehelinagar ( Village Code -313928) & Rosanpur ( Village Code -313930) under Ghorapakhiagangin Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000634/2023-2024 | 3439/MURD | 03/11/2023 | 45 | SHIRSHENDU MUKHERJEE | 33.92 | 0 | 0
2591 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-12 |  |  | VCH/000861/2022-2023 |  | 21/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 54.26 | 0 | 0
2592 | Murshidabad Division |  | APPLICATION ID: ER-MLDT-2022-WL-12, SCHEME CODE: 9751, SCHEME NAME: GHORAPAKHIAGANGIN ZONE - II, IMIS CODE: 40019398 (SINHA AND SONS) PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-12 |  |  | VCH/001018/2022-2023 | 369-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 54.26 | 0 | 0
2593 | Murshidabad Division |  | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B |  |  | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2594 | Murshidabad Division |  | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000412/2023-2024 | 2862/MURD | 08/09/2023 | 30 | PRADIP KUMAR DAS | 5.94 | 0 | 100
2595 | Murshidabad Division |  | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000465/2020-2021 | 547/MURD | 05/02/2021 | 30 | PRADIP KUMAR DAS | 39.01 | 0 | 100
2596 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-I G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/001337/2021-2022 | 55/JSD | 25/01/2022 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
2597 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-II G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/001338/2021-2022 | 56/JSD | 25/01/2022 | 30 | IMAGIN | 4.16 | 0 | 0
2598 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Mahesail (Village code 313954) & Amuha (Village code 313955) under Mahisail Ground Based Water Supply Scheme for Arsenic Affected Areas of Suti-II Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723341) |  |  | ORD/001636/2021-2022 | 502/MURD | 23/02/2022 | 180 | DECON INDIA | 239.71 | 0 | 80
2599 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHAMMADPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000402/2021-2022 | 245/LSD | 18/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.18 | 0 | 0
2600 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amdahara Haziganja (Village code 314497) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl -05) |  |  | ORD/001804/2021-2022 | 596/MURD | 03/03/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 57.24 | 0 | 0
2601 | Murshidabad Division |  | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000072/2022-2023 | 177/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.85 | 0 | 0
2602 | Murshidabad Division |  | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000073/2022-2023 | 178/BSD | 12/04/2022 | 15 | M/S.S.S. ENTERPRISE | 4.83 | 0 | 90
2603 | Murshidabad Division |  | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under EdrakpurWater Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. |  |  | ORD/000074/2022-2023 | 179/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 0
2604 | Murshidabad Division |  | Supply of C.I specials to join existing AC pipe with UPVC pipe in connection with FHTC of Edrakpur piped water supply scheme of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000138/2022-2023 | 188/BSD | 28/04/2022 | 30 | PM CONSTRUCTION | 3.39 | 0 | 0
2605 | Murshidabad Division |  | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000139/2022-2023 | 187/BSD | 28/04/2022 | 30 | RAFIKUL HASAN | 4.51 | 0 | 0
2606 | Murshidabad Division |  | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000140/2022-2023 | 189/BSD | 28/04/2022 | 30 | RAFIKUL HASAN | 4.76 | 0 | 0
2607 | Murshidabad Division |  | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme of Nawda village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000183/2022-2023 | 190/BSD | 28/04/2022 | 30 | MOINAK CHATTOPADHYAY | 4.76 | 0 | 0
2608 | Murshidabad Division |  | Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000187/2022-2023 | 196/BSD | 28/04/2022 | 30 | KISMAT ARA BEGAM | 3.95 | 0 | 0
2609 | Murshidabad Division |  | Supply and Delivery for Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. |  |  | ORD/000188/2022-2023 | 197/BSD | 28/04/2022 | 30 | KISMAT ARA BEGAM | 4.65 | 0 | 0
2610 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) of mouza Edrakpur (Village code 315547), of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0005182896) |  |  | ORD/001209/2021-2022 | 17/MURD | 05/01/2022 | 180 | KISMAT ARA BEGUM | 99.02 | 0 | 0
2611 | Murshidabad Division |  | LAYING OF 110 MM DIA UPVC PIPELINE FOR PROVIDING FHTC IN CONNECTION WITH JJM EDRAKPUR UNDER EDRAKPUR W/S SCHEME UNDER MSD. PHE DTE TENDER NO 222 OF 21-22 AE BSD |  |  | VCH/000316/2022-2023 | 177-MSD/22-23 | 17/05/2022 | 0 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.83 | 0 | 0
2612 | Murshidabad Division | Berhampur Sub-Division | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00974/2023-2024 |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
2613 | Murshidabad Division | Berhampur Sub-Division | HIRE OF CAR FOR AE-JSD, W/O NO- 52/MURD, DT-16/07/2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01212/2024-2025 | 341-MSD/2024-25 | 30/08/2024 | 0 | HASSAN CONSTRUCTION | 0.33 | 0 | 0
2614 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01291/2023-2024 | 559-MSD/2023-24 | 20/02/2024 | 0 | MD MUKLESUR RAHAMAN | 0.79 | 0 | 0
2615 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte.Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01439/2023-2024 | 630-MSD/2023-24 | 19/03/2024 | 0 | MERCHANDISE-INDIA | 2.39 | 0 | 0
2616 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 182 Days] w.e.f 03/05/2024 to 31/10/2024. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000002/2024-2025 | 158/MSD | 29/04/2024 | 182 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 0 | 0
2617 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.06.2024 to 30.11.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000010/2024-2025 | 80/HQ | 31/05/2024 | 183 | DULAL CHOWDHURY | 0.91 | 0 | 30
2618 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000022/2024-2025 | 77/KSD | 25/04/2024 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
2619 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/04/2023 to 16/10/2023. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000053/2023-2024 | 437./A/JSD | 17/04/2023 | 183 | M/S JOY MA BANAMALI | 0.88 | 0 | 100
2620 | Murshidabad Division | Berhampur Sub-Division | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000093/2023-2024 | 437-/AA/JSD | 17/04/2023 | 365 | MAJIBUR RAHAMAN | 4.76 | 0 | 70
2621 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 03 (three) months i.e. from 01/10/2024 to 31/12/2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000167/2024-2025 | 489/ISD | 30/09/2024 | 92 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.45 | 0 | 0
2622 | Murshidabad Division | Berhampur Sub-Division | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of July2024 to November2024 [Vehicle No.WB25M1561] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000114/2024-2025 | 1887/MURD | 29/06/2024 | 150 | M/S B K ENTERPRISE | 0.87 | 0 | 100
2623 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2024 to 31/03/2025 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000168/2024-2025 | 490/ISD | 30/09/2024 | 120 | HAMIDUL ISLAM | 0.69 | 0 | 0
2624 | Murshidabad Division | Berhampur Sub-Division | Hiring of one no. Mahindra & Mahindra make Bolero Diesel Passenger car for official use of the Assistant Engineer, Berhampore Sub-Division, P.H.Engineering Dte. for 06 (six) Months.(Period from 01/07/2023 to 31/12/2023 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000278/2023-2024 | 44/A/BSD | 23/06/2023 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 0 | 100
2625 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tenya (Village code 315737) under Tenya(Zone-I) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154932 in the District of Murshidabad. (Sl No-21) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000447/2020-2021 | 47/MURD | 06/01/2021 | 180 | CHAKRABORTY CONSTRUCTION | 58.49 | 0 | 1
2626 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RANGAMATI CHANDPARA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000521/2021-2022 | 352/BSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 0 | 0
2627 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/10/2022 to 31/03/2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000539/2022-2023 | 295./HQ | 21/09/2022 | 181 | SISIR KUMAR DE | 0.91 | 0 | 100
2628 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000563/2022-2023 | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 90
2629 | Murshidabad Division | Berhampur Sub-Division | Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywere within any trouble on daily wage basis for official used under the control of the Assistant engineer (HQ), Murshidabad Division, P.H.E. Dte. For 1(One) year (on and from 01/11/2023 to 31/10/2024) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver , Taxes , Insurance , Fees etc..as applicable Excluding fuel, lubricant etc as per order) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000657/2023-2024 | 3381/MURD | 31/10/2023 | 365 | M/S JOY MA BANAMALI | 2.11 | 0 | 28
2630 | Murshidabad Division | Berhampur Sub-Division | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2023 to 31.05.2024) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000703/2023-2024 | 170/HQ | 29/11/2023 | 182 | DULAL CHOWDHURY | 0.91 | 0 | 50
2631 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2023 to 31/03/2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000730/2023-2024 | 403/ISD | 29/09/2023 | 182 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 100
2632 | Murshidabad Division | Berhampur Sub-Division | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months. i.e. from 08.01.2024 to 07.07.2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000732/2023-2024 | 02/LSD | 02/01/2024 | 182 | BARI ENTERPRISE | 0.89 | 0 | 51
2633 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2023 to 31/03/2024 (120 days) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000751/2023-2024 | 404/ISD | 29/09/2023 | 120 | HAMIDUL ISLAM | 0.69 | 0 | 30
2634 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 18/01/2024 to 15/07/2024. [ Vehicle No:- WB 58 BU 9284] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000760/2023-2024 | 892/JSD | 17/01/2024 | 180 | ABIDA CONSTRUCTION | 0.88 | 0 | 0
2635 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 168Days] i.e period form 17/11/2023 to 02/05/2024. Vehicle No [WB58CA/1034] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000763/2023-2024 | 398/MSD | 17/11/2023 | 168 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.82 | 0 | 25
2636 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Dy Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year]. Period from i.e. 07/02/2024 to 05/02/2025 [Vehicle No.WB58AR/5026] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000783/2023-2024 | 392/MURD | 06/02/2024 | 365 | MD MUKLESUR RAHAMAN | 2.11 | 0 | 50
2637 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 182 days | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000873/2023-2024 | 165/ISD | 28/03/2024 | 183 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 50
2638 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000874/2023-2024 | 166/ISD | 28/03/2024 | 120 | HAMIDUL ISLAM | 0.69 | 0 | 50
2639 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months. Vehicle No. WB-57E-9142 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000881/2022-2023 | 415/ISD | 29/09/2022 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 50
2640 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2023 to 30/09/2023) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000901/2022-2023 | 55/HQ | 28/03/2023 | 184 | SISIR KUMAR DE | 0.91 | 0 | 100
2641 | Murshidabad Division | Berhampur Sub-Division | Construction of pathway & painting of boundary wall including gate at Head work Site and development of land at 2nd tubewell site of Bahara water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001614/2021-2022 | 381 / KSD | 19/01/2022 | 30 | SUGATA CHOWDHURY | 4.82 | 0 | 100
2642 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002071/2021-2022 | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 0
2643 | Murshidabad Division |  | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Batkamari (Village code 314689) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. Tender no - 44 of 20-21 by EE MURD |  |  | VCH/001382/2021-2022 | 332-MSD/21-22 | 25/02/2022 | 0 | DAS TRADING CO. | 22.28 | 0 | 0
2644 | Murshidabad Division |  | Laying of balance work of HDPE pipe Risingmain of Basudebpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. |  |  | ORD/000617/2020-2021 | 654/MURD | 18/02/2021 | 60 | JOY BISHNU ENGINEERING CO. | 7.91 | 0 | 0
2645 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (1974 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jaladipur ( Village Code -313860) under Basudebpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000639/2023-2024 | 3440/MURD | 03/11/2023 | 60 | BHOWMIK CONSTRUCTION | 67.6 | 0 | 0
2646 | Murshidabad Division |  | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. |  |  | ORD/000853/2022-2023 | 755/MURD | 16/03/2023 | 90 | SAMBHU NATH ROY | 62.1 | 0 | 0
2647 | Murshidabad Division |  | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 15 |  |  | VCH/000862/2022-2023 | 370-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 20.99 | 0 | 0
2648 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) |  |  | ORD/000056/2021-2022 | 1349/MURD | 09/06/2021 | 60 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 77.6 | 41.34 | 0
2649 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Juginda (Village code 314727)under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723344) |  |  | ORD/000224/2022-2023 | 1468/MURD | 03/06/2022 | 120 | SUJIT KUMAR SAHA | 130.65 | 0 | 0
2650 | Murshidabad Division |  | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. |  |  | ORD/000455/2021-2022 | 305/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.33 | 4.33 | 0
2651 | Murshidabad Division |  | Protection of Over Head Reservoir by Masonry wall & construction of entrance gate of Head work site premises under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/002123/2021-2022 | 475/ISD | 03/09/2021 | 60 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.64 | 0 | 0
2652 | Murshidabad Division |  | Protection of Head work site & Pump House No-II premises by raising Boundary wall height by R.B.T fencing under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. |  |  | ORD/002130/2021-2022 | 474/ISD | 03/09/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.7 | 0 | 0
2653 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) TNO- 165/21-22/EE |  |  | VCH/001499/2021-2022 | 413-MSD/21-22 | 22/03/2022 | 0 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 27.35 | 0 | 0
2654 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-A). |  |  | ORD/000034/2022-2023 | 167/JSD | 01/04/2022 | 30 | S.D PROJECT | 4.85 | 0 | 1
2655 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-B). |  |  | ORD/000035/2022-2023 | 168/JSD | 01/04/2022 | 30 | S.D PROJECT | 4.81 | 0 | 1
2656 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-C). |  |  | ORD/000036/2022-2023 | 169/JSD | 01/04/2022 | 30 | M/S G.M ENTERPRISE (MD. GOLAM MEHABUB) | 4.84 | 0 | 1
2657 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-D). |  |  | ORD/000037/2022-2023 | 170/JSD | 01/04/2022 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 4.84 | 0 | 1
2658 | Murshidabad Division |  | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-E). |  |  | ORD/000048/2022-2023 | 178/JSD | 01/04/2022 | 30 | M/S JOY MA BANAMALI | 4.8 | 0 | 1
2659 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kasiadanga (Village Code -314124) (Part-I) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) |  |  | ORD/000294/2021-2022 | 2299/MURD | 02/08/2021 | 60 | KISMAT ARA BEGUM | 69.04 | 48.16 | 0
2660 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) laying pipeline in connection with under command area of village of BAHARA (Village Code-314123) & KULGACHHI (Village Code-314119) under KASIADANGA Ground water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-II Block, under Murshidabad Division,PHE Dte. |  |  | ORD/000341/2022-2023 | 1837/MURD | 13/07/2022 | 150 | DHIRENDRANATH MONDAL | 192.87 | 0 | 0
2661 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kasiadanga ( Village Code -314124) (Part-II) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) |  |  | ORD/000418/2021-2022 | 2595/MURD | 25/08/2021 | 60 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 70.36 | 0 | 0
2662 | Murshidabad Division |  | Laying of UPVC pipeline at village Laxmijola (East Side) in connection with FHTC work under Kasiadanga (Zone-II) Water Supply Scheme under Jangipur Sub-Division,P.H.E. Dte. in the District of Murshidabad. |  |  | ORD/001281/2021-2022 | 419./LSD | 31/12/2021 | 30 | MARUTI CONSTRUCTION AND CO | 3.8 | 0 | 70
2663 | Murshidabad Division | Berhampur Sub-Division |  | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/00243/2023-2024 | 97-MSD/2023-24 | 08/06/2023 | 0 | DULAL CHOWDHURY | 0.8 | 0 | 0
2664 | Murshidabad Division | Berhampur Sub-Division | ENGAGEMENT OF CAR FOR SE-MC, PHE DTE. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | BILL/01173/2024-2025 | 342-MSD/2024-25 | 06/09/2024 | 0 | SOUMYADIP MISRA | 0.21 | 0 | 0
2665 | Murshidabad Division | Berhampur Sub-Division | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000093/2023-2024 | 437-/AA/JSD | 17/04/2023 | 365 | MAJIBUR RAHAMAN | 4.76 | 0 | 70
2666 | Murshidabad Division | Berhampur Sub-Division | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000135/2023-2024 | 165/ISD | 01/04/2023 | 183 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 0 | 100
2667 | Murshidabad Division | Berhampur Sub-Division | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months i.e. from 08.07.2023 to 07.01.2024. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000148/2023-2024 | 24/LSD | 30/06/2023 | 184 | BARI ENTERPRISE | 0.9 | 0 | 100
2668 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chhota Satui (Village code 315343) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID- 1723177 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000168/2021-2022 | 1651/MURD | 29/06/2021 | 180 | DAS TRADING CO. | 80.05 | 39.75 | 1
2669 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000186/2020-2021 | 3136/MURD | 11/12/2020 | 60 | UTTAM MUKHERJEE | 39.68 | 0 | 1
2670 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000456/2021-2022 | 306/BSD | 13/08/2021 | 30 | IMAGIN | 3.26 | 3.26 | 0
2671 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOWRIGACHHA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000522/2021-2022 | 353/BSD | 27/08/2021 | 30 | TINA ROY | 4.16 | 0 | 1
2672 | Murshidabad Division | Berhampur Sub-Division | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000623/2022-2023 | 205/JSD | 18/04/2022 | 365 | MAJIBUR RAHAMAN | 4.76 | 0 | 0
2673 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000897/2022-2023 | 329/MURD | 07/02/2023 | 365 | MD MUKLESUR RAHAMAN | 4.78 | 0 | 1
2674 | Murshidabad Division | Berhampur Sub-Division | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year].for the month of April¿2023 to March¿2024 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000900/2022-2023 | 330/MURD | 07/02/2023 | 365 | SOUMYADIP MISRA | 4.78 | 0 | 32
2675 | Murshidabad Division | Berhampur Sub-Division | Continuation work for Hiring of 1 (one) no. Diesel Bolero/Marshal car (WB-57C 9120) for official use of the Assistant Engineer, Jangipur Sub Division, Murshidabad Division P.H.E. Dte. for the period from 01.03.2022 to 31.05.2022 (i.e) 3 (Three) months (vehicle No.-WB-57C/9120). | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001722/2021-2022 | 88/JSD | 22/02/2022 | 89 | MANUAR HOSSAIN | 0.45 | 0 | 100
2676 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001777/2021-2022 | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 90
2677 | Murshidabad Division | Berhampur Sub-Division | Extension of Distribution UPVC pipeline at Hanumandanga, Poradanga & Haldepara area for Providing Balance Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Choto Satui (Village Code-315343) under Bara Satui Ground water based water suply scheme for Arsenic affected areas of Berhampore Block, under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001807/2021-2022 | 768/MURD | 22/03/2022 | 30 | DAS TRADING CO. | 42.34 | 0 | 1
2678 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/002071/2021-2022 | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 0
2679 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad.3136/MURD, 11/12/2020 | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000674/2021-2022 | 172-MSD/21-22 | 01/11/2021 | 0 | UTTAM MUKHERJEE | 32.45 | 0 | 0
2680 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of JOYRAMPUR( Village Code -314693) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184127) |  |  | ORD/000072/2021-2022 | 1548/MURD | 23/06/2021 | 60 | SAHABUDDIN BISWAS | 28.24 | 0 | 0
2681 | Murshidabad Division |  | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of MAHABUBNAGAR ( Village Code -314668) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184127) |  |  | ORD/000073/2021-2022 | 1549/MURD | 23/06/2021 | 60 | H.L. CONSTRUCTION (TITAN BISWAS) | 38.29 | 0 | 0
2682 | Murshidabad Division |  | ADDITIONAL WORKS FOR FHTC OF VILLAGE CODE MAHABUBNAGAR (CODE- 314668) UNDER DOMKAL WSS, TNO- 98/21-22/EE |  |  | VCH/000779/2021-2022 |  | 29/10/2021 | 0 | H.L. CONSTRUCTION (TITAN BISWAS) | 33.18 | 0 | 0
2683 | Murshidabad Division |  | ADDITIONAL WORKS FOR FHTC OF VILLAGE CODE MAHABUBNAGAR (CODE- 314668) UNDER DOMKAL WSS, TNO- 98/21-22/EE |  |  | VCH/000916/2021-2022 | 189-MSD/21-22 | 12/11/2021 | 0 | H.L. CONSTRUCTION (TITAN BISWAS) | 33.18 | 0 | 0
2684 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of villageMAHABUR (Village Code 314668) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. Tender no - 500 of 20-21 by EE MURD |  |  | VCH/001389/2021-2022 | 323-MSD/21-22 | 21/02/2022 | 0 | DECON INDIA | 9.57 | 0 | 0
2685 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
2686 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of HETANPUR( Village Code -314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) |  |  | ORD/000246/2021-2022 | 1693/MURD | 06/07/2021 | 60 | SUDIPA SINGHA ROY | 13.33 | 0 | 0
2687 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with ";Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village HETANPUR (Village Code 314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . |  |  | ORD/000552/2020-2021 | 2576/MURD | 01/10/2020 | 45 | SUDIPA SINGHA ROY | 17.38 | 0 | 0
2688 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village MASIMPUR (Village Code 314663) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad. |  |  | ORD/000643/2020-2021 | 2575/MURD | 01/10/2020 | 45 | CHATTERJEE ENTERPRISE | 19.86 | 0 | 0
2689 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Hetanpur (314664) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District(Part-VII) |  |  | VCH/001292/2021-2022 |  | 17/02/2022 | 0 | SUDIPA SINGHA ROY | 19.98 | 0 | 0
2690 | Murshidabad Division |  | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with ';Jal Swapna (Jal Jeevan Mission ) 'from existing Distribution system within the Command area of village HETANPUR (Village Code 314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . Tender no - 504 of 20-21 by EE MURD |  |  | VCH/001434/2021-2022 | 337-MSD/21-22 | 03/03/2022 | 0 | SUDIPA SINGHA ROY | 13.68 | 0 | 0
2691 | Murshidabad Division |  | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of HETANPUR ( Village Code -314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. Tender no - 365 of 21-22 by EE MURD |  |  | VCH/001437/2021-2022 | 336-MSD/21-22 | 03/03/2022 | 0 | SUDIPA SINGHA ROY | 6.3 | 0 | 0
2692 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC |  |  | VCH/002023/2020-2021 | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0
2693 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI Z-II-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE-BHALKUNDI , CODE- 315091, TNO- 43/2020-21/SEMC |  |  | VCH/002024/2020-2021 | 512/W | 30/03/2021 | 0 | M/S BHUBAN DAS | 28.84 | 0 | 0
2694 | Murshidabad Division |  | Laying of pipe line at Nawapara Village (Village Code-315734) in connection with FHTC work at Tenya (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000022/2022-2023 | 26/KSD | 08/04/2022 | 1030 | PARTHA RAJAK | 4.52 | 0 | 1
2695 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tenya (Village code 315737) under Tenya(Zone-I) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154932 in the District of Murshidabad. (Sl No-21) |  |  | ORD/000447/2020-2021 | 47/MURD | 06/01/2021 | 180 | CHAKRABORTY CONSTRUCTION | 58.49 | 0 | 1
2696 | Murshidabad Division |  | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at TENYA BAIDYAPUR G.P. under Murshidabad Division, P.H.E.Dte. |  |  | ORD/000470/2021-2022 | 238/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0
2697 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village NAWAPARA (Village Code : 315734) under Tenya Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000579/2020-2021 | 3221/MURD | 18/12/2020 | 60 | HARUN ALL RASHID & BROTHERS | 6.26 | 0 | 1
2698 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village GHOSHPARA(Village Code 315735) under Tenya Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-II Block in the District of Murshidabad. |  |  | ORD/000783/2020-2021 | 3035/MURD | 07/12/2020 | 45 | MAA DURGA ENTERPRISE | 8.95 | 0 | 0
2699 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Baidyapur (Village code 315733) under Tenya(Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division,PHE Dte. Scheme ID 0006154932 in the District of Murshidabad.(sl-02) |  |  | ORD/000973/2021-2022 | 3487/MURD | 03/11/2021 | 100 | SOM CONSTRUCTION AGENCY | 45 | 0 | 1
2700 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bara Hati ( Village Code -315738) Korgram ( Village Code -315736) under Tenya Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006154932) |  |  | ORD/001576/2021-2022 | 306/MURD | 07/02/2022 | 60 | DAS ASSOCIATED | 38.03 | 0 | 100
2701 | Murshidabad Division |  | Providing Balance Functional Household Tap Connection (FHTC) of 219 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ghoshpara (Village code 315735) under Tenya Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001809/2021-2022 | 813/MURD | 25/03/2022 | 20 | MAA DURGA ENTERPRISE | 15.69 | 0 | 100
2702 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 889/B/MURD | 05/04/2022 | 0 | Resource Division | 5.08 | 0 | 0
2703 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna Mission (JJM) from existing distribution system within the command area of village Ghoshpara (Village code - 315735) of Tenya under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur - II Block of Murshidabad District. PHE DTE. Tender no-633 / 20-21 by EE / MURD |  |  | VCH/000199/2021-2022 | 13-MSD / 21-22 | 10/08/2021 | 0 | MAA DURGA ENTERPRISE | 6.4 | 0 | 0
2704 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) and connection with Jal Jeevan Mission (JJM) under command area of Village TENYA (Village Code-315737) under TENYA (ZONE-I) Ground Water Based Water Supply Scheme for arsenic affected area of Bharatpur-II Block under Murshidabad Division, PHE Dte. |  |  | VCH/000234/2021-2022 | 29-MSD / 21-22 | 27/08/2021 | 0 | CHAKRABORTY CONSTRUCTION | 18.07 | 0 | 0
2705 | Murshidabad Division |  | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoshpara 315735 OF Tenya under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur - II Block of Murshidabad District (PART-I) TNO- 633/20-21/EE |  |  | VCH/000656/2021-2022 | 129-MSD/21-22 | 11/10/2021 | 0 | MAA DURGA ENTERPRISE | 2.49 | 0 | 0
2706 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village TENYA (Village Code 315737) under TENYA (ZONE-I) Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 77 of 20-21 by SE MC |  |  | VCH/001519/2021-2022 | 427-MSD/21-22 | 31/03/2022 | 0 | CHAKRABORTY CONSTRUCTION | 11.93 | 0 | 0
2707 | Murshidabad Division | Kandi Sub-Division | rESTORATION OF DAMAGE PORTION LYING OF PHE PIPE LINE OF HIZOLE UNDER MSD HIGHWAY DIV-II | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | BILL/00960/2023-2024 |  | 12/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0
2708 | Murshidabad Division | Kandi Sub-Division | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000006/2025-2026 | 835/MURD | 11/04/2025 | 234 | M/S JATIN | 69.3 | 0 | 5
2709 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000034/2023-2024 | 1109/MURD | 24/04/2023 | 723 | INDRAJIT MAZUMDAR | 10.68 | 0 | 100
2710 | Murshidabad Division | Kandi Sub-Division | Allied works Pertaining to Construction of Cross Drain , Surface Drain, Office cum godown, Steel Structure Shade of Hizole-I PWSS at Kandi of Kandi-Sub Division under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000193/2024-2025 | 3211/MURD | 09/12/2024 | 357 | M/S JATIN | 53.73 | 0 | 10
2711 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-I) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000336/2022-2023 | 1723/MURD | 04/07/2022 | 1277 | M/S. TAPAS KUMAR CHAKRABORTY | 676.45 | 0 | 1
2712 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-II) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000355/2022-2023 | 1992/MURD | 21/07/2022 | 120 | M/S. S. DAS AND ENTERPRISE | 501.06 | 0 | 1
2713 | Murshidabad Division | Kandi Sub-Division | Construction of 700 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- I) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000596/2023-2024 | 3342/MURD | 28/10/2023 | 886 | M/S JATIN | 374.61 | 0 | 5
2714 | Murshidabad Division | Kandi Sub-Division | Construction of 600 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- II) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000597/2023-2024 | 3344/MURD | 28/10/2023 | 885 | M/S JATIN | 345.77 | 0 | 20
2715 | Murshidabad Division | Kandi Sub-Division | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site, 2nd Site & 3rd site of Hizole( Zone-II) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001739/2021-2022 | 783/MURD | 23/03/2022 | 30 | NADIA TUBEWELLS | 16.75 | 0 | 1
2716 | Murshidabad Division | Kandi Sub-Division | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site ,2nd Site & 3rd site of Hizole( Zone-I) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001756/2021-2022 | 782/MURD | 23/03/2022 | 30 | MAMATA USHA ENTERPRISE | 16.77 | 0 | 1
2717 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000031/2022-2023 | 2662/MURD | 20/09/2022 | 0 | Resource Division | 98.85 | 0 | 0
2718 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000039/2022-2023 | 2780/H/MURD | 01/10/2022 | 0 | Resource Division | 40.23 | 0 | 0
2719 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000056/2022-2023 | 3233/B/MURD | 02/12/2022 | 0 | Resource Division | 46.99 | 0 | 0
2720 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000098/2023-2024 | 1167/MURD/6 | 28/04/2023 | 0 | Resource Division | 99.41 | 0 | 0
2721 | Murshidabad Division | Kandi Sub-Division | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-18 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000761/2022-2023 | 290-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 40.56 | 0 | 0
2722 | Murshidabad Division | Kandi Sub-Division | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-16 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | VCH/000762/2022-2023 | 290-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 4.08 | 0 | 0
2723 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Sehalai Part- A village, Block:- Bharatpur- I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000238/2023-2024 | 2418/MURD | 08/08/2023 | 744 | M/S RELIABLE | 30.55 | 0 | 64
2724 | Murshidabad Division | Berhampur M/E Division | Ground Water based piped water supply scheme for Sehalai Part- B village, Block:- Bharatpur- I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER-II | Junior engineer-II | ORD/000253/2023-2024 | 2491/MURD | 11/08/2023 | 60 | M/S. GHOSH ENTERPRISE RAJ GHOSH | 30.54 | 0 | 0
2725 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000103/2023-2024 | 1744/MURD | 06/07/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.22 | 0 | 100
2726 | Murshidabad Division | Berhampur M/E Division | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2024 to 30.05.2024) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000788/2023-2024 | 17/KSD | 16/01/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 70
2727 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of Augmentation of KHAYRAMARI PART-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000809/2022-2023 | 657/MURD | 06/03/2023 | 843 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 466.36 | 0 | 95
2728 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000032/2024-2025 | MURD/2481/04 | 04/09/2024 | 0 | Resource Division | 5.07 | 0 | 0
2729 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000178/2023-2024 | 1180/MURD/18 | 29/04/2023 | 0 | Resource Division | 179.05 | 0 | 0
2730 | Murshidabad Division | Kandi Sub-Division | Allied works for laying pipeline and construction of approach road for Fatepur Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000063/2024-2025 | 1978/MURD | 08/07/2024 | 542 | ABIDA CONSTRUCTION | 19.77 | 0 | 70
2731 | Murshidabad Division | Kandi Sub-Division | FATEPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000141/2023-2024 | 1867/MURD | 14/07/2023 | 968 | ABIDA CONSTRUCTION | 124.31 | 0 | 65
2732 | Murshidabad Division | Kandi Sub-Division | Laying and distribution of UPVC pipeline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000185/2022-2023 | 192/BSD | 28/04/2022 | 30 | SURAJIT MONDAL | 4.77 | 0 | 100
2733 | Murshidabad Division | Kandi Sub-Division | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000500/2024-2025 | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0
2734 | Murshidabad Division | Kandi Sub-Division | Repair and renovation work of Switch room and Boundary wall at Head Work and 2nd TW site of Fatepur Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/001680/2021-2022 | 17/BSD | 10/01/2022 | 30 | MADAN MOHAN SASMAL | 4.85 | 0 | 100
2735 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000318/2023-2024 | 1936/MURD/6 | 19/07/2023 | 0 | Resource Division | 1.09 | 0 | 0
2736 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
2737 | Murshidabad Division | Berhampur M/E Division | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000612/2023-2024 | 3377/MURD | 31/10/2023 | 730 | M/S GHOSH & CO. | 1181.6 | 0 | 20
2738 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site 3RD Site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000699/2023-2024 | 3784/MURD | 11/12/2023 | 21 | GENUINE | 35.34 | 0 | 0
2739 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-III | RTOR000126/2023-2024 | 1167/MURD/17 | 28/04/2023 | 0 | Resource Division | 30.59 | 0 | 0
2740 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000348/2022-2023 | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 10
2741 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000705/2023-2024 | 3813/MURD | 12/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 11.77 | 0 | 100
2742 | Murshidabad Division | Berhampur M/E Division | Providing FHTC Connection to 268 nos household, Laying of Rising Main, Laying of Distribution System, overhauling of RCC 45 Cum OHR, Construction of Boundary Wall (For T/W-I) =100mtr, Special repair and renovation of existing 1 (One) Nos Pump House and Allied Works and Construction of RCC approach road =140 mtr for Augmentation of Jadabpur Nimtala Piped Water Supply Scheme in Farakka Block under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000819/2023-2024 | 740/MURD | 12/03/2024 | 60 | PAL CONSTRUCTION | 57.61 | 0 | 50
2743 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | RTOR000194/2023-2024 | 1210/MURD/08 | 02/05/2023 | 0 | Resource Division | 9.5 | 0 | 0
2744 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000119/2023-2024 | 1771/MURD | 06/07/2023 | 684 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 40
2745 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000208/2022-2023 | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 1
2746 | Murshidabad Division | Berhampur M/E Division | Renovation of Modified Sujapur Sadhipur Model of AIRP (Capacity 123 Cum/hr.) at Mahadebnagar Zone I Water Supply Scheme of Farakka Block Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000248/2024-2025 | 226/MURD | 27/01/2025 | 45 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 77.24 | 0 | 0
2747 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000397/2023-2024 | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 30
2748 | Murshidabad Division | Kandi Sub-Division | Allied work for Construction of Boundary wall, Road repair & 1 no. Box Culvert at Kirtipur PWSS at Khargram Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000062/2024-2025 | 1990/MURD | 08/07/2024 | 597 | ARIZ ENTERPRISE | 36.54 | 0 | 10
2749 | Murshidabad Division | Kandi Sub-Division | Formal work order for KIRTTIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000848/2022-2023 | 781/MURD | 20/03/2023 | 1144 | ARIZ ENTERPRISE | 343.69 | 0 | 11
2750 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000083/2023-2024 | 1129/MURD/6 | 25/04/2023 | 0 | Resource Division | 10.76 | 0 | 0
2751 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000341/2023-2024 | 79/MURD/08 | 09/01/2024 | 0 | Resource Division | 9.85 | 0 | 0
2752 | Murshidabad Division | Kandi Sub-Division | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kagram & Salar Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000048/2023-2024 | 1102/MURD | 24/04/2023 | 20 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0
2753 | Murshidabad Division | Kandi Sub-Division | Continuation Work Order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months.(Period From 31.05.2024 to 27.09.2024) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000079/2024-2025 | 92/KSD | 27/05/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0
2754 | Murshidabad Division | Kandi Sub-Division | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000504/2024-2025 | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 20
2755 | Murshidabad Division | Kandi Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 779 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
2756 | Murshidabad Division | Kandi Sub-Division | Augmentation of Salar PWSS Zone-IA,IB,IIA,IIB to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 4 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 4no, Construction of Boundary Wall of 600 m, Construction of 400 Cum OHR(1 no) & 300 Cum OHR(2 nos) with sub soil investigation under Jal Jeevan Mission of Bharatpur II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B). | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000647/2023-2024 | 3474/MURD | 07/11/2023 | 811 | SUJIT KUMAR SAHA | 575.6 | 0 | 10
2757 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur -II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000718/2023-2024 | 3835/MURD | 14/12/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
2758 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2759 | Murshidabad Division | Kandi Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1 | ORD/001470/2021-2022 | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 0 | 76
2760 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UJUNIA SISUA AND GUNDIRIA Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur I & II Block under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000624/2023-2024 | 3409/MURD | 02/11/2023 | 472 | GENUINE | 18.43 | 0 | 100
2761 | Murshidabad Division | Kandi Sub-Division | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000873/2022-2023 | 882/MURD | 28/03/2023 | 280 | BANAMALI ENTERPRISES | 224.42 | 0 | 35
2762 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000272/2023-2024 | 1230/MURD/15 | 04/05/2023 | 0 | Resource Division | 1.09 | 0 | 0
2763 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000350/2022-2023 | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 0 | 100
2764 | Murshidabad Division | Lalbag Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000394/2023-2024 | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0 | 100
2765 | Murshidabad Division | Lalbag Sub-Division | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 600 cum) and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- IV PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | ORD/000646/2023-2024 | 3466/MURD | 06/11/2023 | 365 | M/S. SINHA & SONS | 796.64 | 0 | 0
2766 | Murshidabad Division | Lalbag Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-III | RTOR000180/2023-2024 | 1180/MURD/19 | 29/04/2023 | 0 | Resource Division | 27.58 | 0 | 0
2767 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Purushottampur PWSS of accommodate Laying Distribution System, in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_B | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000293/2023-2024 | 2667/MURD | 24/08/2023 | 180 | J.S. CONSTRUCTION | 346.34 | 0 | 0
2768 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000347/2022-2023 | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 100
2769 | Murshidabad Division | Berhampur M/E Division | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House, B.W, Rising Main Connection & FHTC for Augmentation of PURUSOTTAMPUR PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte.PART_A | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000352/2023-2024 | 2674/MURD | 24/08/2023 | 365 | M/S BIKASH ENTERPRISE | 342.01 | 0 | 0
2770 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER-I | Junior engineer-II | RTOR000239/2023-2024 | 1219/MURD/18 | 03/05/2023 | 0 | Resource Division | 198.03 | 0 | 0
2771 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000281/2023-2024 | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 0 | 100
2772 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 870 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-II PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000582/2023-2024 | 3317/MURD | 22/10/2023 | 528 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 195.25 | 0 | 85
2773 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Rejinagar Zone II PWSS of accommodate with Switch Room, Boundary Wall, 300 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000583/2023-2024 | 3318/MURD | 22/10/2023 | 544 | MODERN CONSTRUCTION | 163.25 | 0 | 0
2774 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000021/2024-2025 | 1811/MURD/20 | 20/06/2024 | 0 | Resource Division | 5.36 | 0 | 0
2775 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000137/2023-2024 | 1167/MURD/42 | 28/04/2023 | 0 | Resource Division | 34.04 | 0 | 0
2776 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000399/2023-2024 | 2806/MURD | 05/09/2023 | 589 | INDRAJIT MAZUMDAR | 27.64 | 0 | 100
2777 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Laying Distribution System of DHANDANGA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000835/2022-2023 | 741/MURD | 16/03/2023 | 747 | APORUPA CONSTRUCTION | 180.78 | 0 | 10
2778 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000073/2023-2024 | 1075/MURD/15 | 19/04/2023 | 0 | Resource Division | 14.18 | 0 | 0
2779 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at TEGHARI ZONE - I, MAHESAIL ZONE-III & SERPUR (CT) Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000236/2023-2024 | 2407/MURD | 07/08/2023 | 552 | NADIA TUBEWELLS | 35.34 | 0 | 100
2780 | Murshidabad Division | Berhampur M/E Division | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000578/2022-2023 | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 0 | 100
2781 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SERPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000614/2023-2024 | 3386/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 0 | 45
2782 | Murshidabad Division | Berhampur M/E Division | Formal work order for SERPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000794/2022-2023 | 594/MURD | 01/03/2023 | 1036 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 446.76 | 0 | 15
2783 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000277/2023-2024 | 1230/MURD/21 | 04/05/2023 | 0 | Resource Division | 25.58 | 0 | 0
2784 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000384/2023-2024 | 495/MURD/12 | 15/02/2024 | 0 | Resource Division | 13.47 | 0 | 0
2785 | Murshidabad Division | Berhampur M/E Division | Laying Distribution System, Rising Main Connection, FHTC connections, for Augmentation of Teghari Zone-II PWSS of Raghunathganj-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000162/2025-2026 | 2127/MURD | 23/09/2025 | 90 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 279.55 | 0 | 0
2786 | Murshidabad Division | Berhampur M/E Division | Augmentation of Teghari zone II PWSS Construction of 500 Cum OHR with subsoil investigation, Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) (1no)& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) (3 no) & construction of boundary wall of 250 mtr of Raghunathganj - II Block, under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000580/2023-2024 | 3315/MURD | 22/10/2023 | 250 | VISION ENTERPRISE | 235.76 | 0 | 0
2787 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2788 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000117/2023-2024 | 1167/MURD/11 | 28/04/2023 | 0 | Resource Division | 77.93 | 0 | 0
2789 | Murshidabad Division | Berhampur M/E Division | Augmentation of Ground Water Based Herampur Zone-II PWSS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000311/2023-2024 | 2671/MURD | 24/08/2023 | 586 | CAPITAL CONSTRUCTION | 279.7 | 0 | 30
2790 | Murshidabad Division | Berhampur M/E Division | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000350/2023-2024 | 2672/MURD | 24/08/2023 | 769 | M/S. UNI TRADERS | 143.17 | 0 | 30
2791 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001670/2021-2022 | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 0 | 100
2792 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000231/2023-2024 | 1219/MURD/13 | 03/05/2023 | 0 | Resource Division | 13.89 | 0 | 0
2793 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMJUA PWSS at Head Work Site & 2nd Tube Well Site in Khargram Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000657/2022-2023 | 380/MURD | 10/02/2023 | 45 | SUJIT KUMAR SAHA | 16.81 | 0 | 100
2794 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-C), FHTC (PART-C), for Uncovered of AMJUA PWSS at AMJUA ( Village Code-315107) , CHURIGRAM ( Village Code-315108) , DURGARAMPUR ( Village Code-315109) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000730/2022-2023 | 339/MURD | 08/02/2023 | 90 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 146.33 | 0 | 34
2795 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 400 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, FHTC (PART-A), for Uncovered of AMJUA PWSS at RAHIGRAM Village in Khargram Block, Kandi Sub-Division under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000748/2022-2023 | 414/MURD | 15/02/2023 | 1141 | M/S.TAPAS KUMAR CHAKRABORTY | 306.3 | 0 | 10
2796 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution System (PART-B), FHTC (PART-B), Boundary wall for Uncovered of AMJUA PWSS at UTTAR GANGARAMPUR ( Village Code-315100) , SADAL ( Village Code-315101) , BHAT KANDA ( Village Code-315102) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [(i)Amount for LDS & FHTC: Rs.2,54,73,199.00 & (ii) Amount for Boundwary Wall: Rs. 31,33,915.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000759/2022-2023 | 453/MURD | 17/02/2023 | 960 | PRADIP KUMAR DAS | 285.93 | 0 | 5
2797 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2798 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000018/2023-2024 | 1210/MURD/35 | 02/05/2023 | 0 | Resource Division | 21.05 | 0 | 0
2799 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/05/2025 to 31/10/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000013/2025-2026 | 946/MURD | 29/04/2025 | 183 | M/S JOY MA BANAMALI | 0.9 | 0 | 20
2800 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000126/2022-2023 | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 0 | 100
2801 | Murshidabad Division | Berhampur M/E Division | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere with in any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2025 to 30/04/2026) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes ,Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000187/2025-2026 | 2239/MURD | 31/10/2025 | 181 | M/S JOY MA BANAMALI | 0.89 | 0 | 0
2802 | Murshidabad Division | Berhampur M/E Division | Laying M.S pipe for interconnection Between A.I.R.P & O.H.R and Clearing chokage of Rising main at GHORAPAKIAGANGING Zone-I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | ORD/000825/2022-2023 | 652/MURD | 06/03/2023 | 30 | LAXMI CONSTRUCTION | 1.86 | 0 | 100
2803 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-III | RTOR000192/2023-2024 | 1210/MURD/17 | 02/05/2023 | 0 | Resource Division | 34.57 | 0 | 0
2804 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-C) and FHTC for KUNDAL PWSS in Burwan Block under Murshidabad Division ,PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000178/2023-2024 | 1997/MURD | 21/07/2023 | 120 | KISMAT ARA BEGAM | 214.39 | 0 | 60
2805 | Murshidabad Division | Kandi Sub-Division | Construction of 450 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, for Uncovered of KUNDAL PWSS at KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code- 315845) in Burwan Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000190/2023-2024 | 1993/MURD | 21/07/2023 | 773 | M/S UNIVERSAL TRADING | 361.74 | 0 | 60
2806 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System (PART-B), FHTC (PART-A) , Boundary wall for Uncovered of KUNDAL PWSS at JHIKARHATI (PART) (Village Code- 315835) , KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code315845) and JHIKARHATI (PART)in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000192/2023-2024 | 2023/MURD | 25/07/2023 | 120 | DIPAYAN DEY | 182.24 | 0 | 50
2807 | Murshidabad Division | Kandi Sub-Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kundal & adjoining mouzas Water Supply Scheme at Head Work Site, 2nd Site & 3 rd site at Burwan Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000203/2023-2024 | 2071/MURD | 28/07/2023 | 585 | NADIA TUBEWELLS | 32.03 | 0 | 60
2808 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000021/2023-2024 | 1210/MURD/39 | 02/05/2023 | 0 | Resource Division | 39.23 | 0 | 0
2809 | Murshidabad Division | Kandi Sub-Division | Functional Household Tap Connection (FHTC) under Jal Jeevan Mission in the command area of NABADURGA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. (PART-B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000005/2023-2024 | 945/MURD | 05/04/2023 | 667 | M/S. UNIQUE BUILDERS | 152.42 | 0 | 0
2810 | Murshidabad Division | Kandi Sub-Division | Laying Distribution System of NABADURGA PWSS in Burwan Block , under Murshidabad Division ,PHE.Dte. .(PART-C) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000044/2023-2024 | 1138/MURD | 26/04/2023 | 706 | DHIRENDRANATH MONDAL | 341.13 | 0 | 60
2811 | Murshidabad Division | Kandi Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nabadurga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000047/2023-2024 | 1217/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 60
2812 | Murshidabad Division | Kandi Sub-Division | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000794/2023-2024 | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 80
2813 | Murshidabad Division | Kandi Sub-Division | Formal Work Order for Construction of 350 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundwary Wall Rising Main Connection, of NABADURGA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. (PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | ORD/000849/2022-2023 | 782/MURD | 20/03/2023 | 1018 | AMAL KUMAR DAS | 181.67 | 0 | 32
2814 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior engineer-II,JUNIOR ENGINEER_BURWAN BLOCK | RTOR000067/2022-2023 | 1278/MURD/16 | 10/05/2023 | 0 | Resource Division | 30.04 | 0 | 0
2815 | Murshidabad Division | Berhampur M/E Division | Renovation of Filter media of Existing AIRP (Capacity 135 Cum/hr.) of Putia (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000033/2024-2025 | 1892/MURD | 01/07/2024 | 60 | M/S BAPPA ENTERPRISE | 47.01 | 0 | 0
2816 | Murshidabad Division | Berhampur M/E Division | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUTIA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d , 4th site at RAGHUNATHGANJ - II Block under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000115/2023-2024 | 1759/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 0 | 80
2817 | Murshidabad Division | Berhampur M/E Division | Construction of approach road from pucca road to Head Work site of Putia Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000656/2022-2023 | 3375/MURD | 20/12/2022 | 940 | JAMIRUL CONSTRUCTION | 4.62 | 0 | 50
2818 | Murshidabad Division | Berhampur M/E Division | Repairing of 550Cum OHR and FHTC for Augmentation of PUTIA (ZONE-I) ground water based piped water supply scheme within Raghunathganj-II Block under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000779/2022-2023 | 507/MURD | 22/02/2023 | 60 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 60.86 | 0 | 50
2819 | Murshidabad Division | Berhampur M/E Division | Formal work order for the construction of Pump House, Vertical extension of Boundary wall and Pump House repairing , Laying Distribution System, Rising Main Connection for Augmentation of PUTIA ( ZONE-I ) Ground water based Piped water supply scheme Raghunathganj -II Block under Murshidabad Division, P.H.E. Dte. [ (i)Amount for LDS, R.Main : Rs. 1,47,25,982.00 & (ii) Amount for Vertical B.Wall Extention & P.House Repairing : Rs. 13,13,446.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000810/2022-2023 | 810/MURD | 22/03/2023 | 710 | JAYANTA KUMAR CHANDRA | 160.12 | 0 | 50
2820 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/001472/2021-2022 | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 0 | 100
2821 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000076/2022-2023 | 1278/MURD/19 | 10/05/2023 | 0 | Resource Division | 34.76 | 0 | 0
2822 | Murshidabad Division | Berhampur Sub-Division | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000044/2024-2025 | 1930/MURD | 03/07/2024 | 537 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 75
2823 | Murshidabad Division | Berhampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for CHANDKATHI Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000044/2025-2026 | 1189/MURD | 23/05/2025 | 60 | PRADIP KUMAR DAS | 23.01 | 0 | 0
2824 | Murshidabad Division | Berhampur Sub-Division | Repair and renovation work of Boundary wall and allied work at Head Work site of Chandkathi Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000192/2022-2023 | 201/BSD | 28/04/2022 | 30 | LATIFUDDIN | 4.78 | 0 | 1
2825 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000395/2023-2024 | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0
2826 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandkati (Village code 315533) under Chandkati Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723218 in the District of Murshidabad. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000410/2020-2021 | 79/MURD | 08/01/2021 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 12.25 | 0 | 90
2827 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA PART-B Water Supply Scheme and Chandkati Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000722/2023-2024 | 3907/MURD | 20/12/2023 | 392 | NADIA TUBEWELLS | 18.43 | 0 | 100
2828 | Murshidabad Division | Berhampur Sub-Division | Providing FHTC Connection to 986 nos household , Laying of Distribution System (Part_B) NODE 198 TO NODE 385, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for for Augmentation work of CHANDKATI PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/000885/2022-2023 | 907/MURD | 29/03/2023 | 180 | DAS TRADING CO. | 136.61 | 0 | 90
2829 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior engineer-II,JUNIOR HARIHARPARA BLOCK | ORD/001471/2021-2022 | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 0 | 1
2830 | Murshidabad Division |  | Last mile connectivity and providing 7512 nos Funcational House Hold Connection from Zone- I of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte |  |  | ORD/000315/2023-2024 | 2685/MURD | 25/08/2023 | 120 | MANASH GHOSH | 376.07 | 0 | 0
2831 | Murshidabad Division |  | Last mile connectivity and providing 5090 nos Functional House Hold Connection from Zone- V of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. |  |  | ORD/000331/2023-2024 | 2688/MURD | 25/08/2023 | 120 | SARAJIT KUMAR MAJUMDER | 270.74 | 0 | 0
2832 | Murshidabad Division | Kandi Sub-Division | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000008/2024-2025 | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 0 | 100
2833 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of PETARI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362276S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000717/2022-2023 | 79/MURD | 10/01/2023 | 1268 | MAMATA USHA ENTERPRISE | 754.5 | 0 | 60
2834 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000041/2023-2024 | 1004/MURD/16 | 17/04/2023 | 0 | Resource Division | 23.72 | 0 | 0
2835 | Murshidabad Division | Kandi Sub-Division | Formal work order for Laying Distribution system (PART-A) at SADPUR PWSS of Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000744/2022-2023 | 382/MURD | 10/02/2023 | 811 | S.K. ENTERPRISE (SANDIP GHOSH) | 136.23 | 0 | 85
2836 | Murshidabad Division | Kandi Sub-Division | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SADPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362342S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,30,41,399.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,56,32,356.00] | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000761/2022-2023 | 475/MURD | 20/02/2023 | 771 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 286.71 | 0 | 21
2837 | Murshidabad Division | Kandi Sub-Division | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SADPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000786/2022-2023 | 542/MURD | 24/02/2023 | 45 | INDRAJIT MAZUMDAR | 16.8 | 0 | 80
2838 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000015/2023-2024 | 1210/MURD/38 | 02/05/2023 | 0 | Resource Division | 29.54 | 0 | 0
2839 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000345/2023-2024 | 112/MURD/02 | 11/01/2024 | 0 | Resource Division | 11.89 | 0 | 0
2840 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000367/2023-2024 | MURD/439/11 | 08/02/2024 | 0 | Resource Division | 5.94 | 0 | 0
2841 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of KUMAR SANDA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362351S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | ORD/000713/2022-2023 | 92/MURD | 11/01/2023 | 1086 | ACQUA CONSTRACTION CONSORTIAM | 678.7 | 0 | 20
2842 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | JUNIOR ENGINEER 2,Junior engineer-II | RTOR000034/2023-2024 | 1043/MURD/9 | 17/04/2023 | 0 | Resource Division | 32.79 | 0 | 0
2843 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000104/2023-2024 | 1746/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
2844 | Murshidabad Division | Berhampur M/E Division | Formal work order for the Work of Augmentation of Dhulauri Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/000703/2022-2023 | 350/MURD | 08/02/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 419.15 | 0 | 48
2845 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | ORD/001469/2021-2022 | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 1
2846 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-III | RTOR000304/2023-2024 | 1278/MURD/13 | 10/05/2023 | 0 | Resource Division | 34.6 | 0 | 0
2847 | Murshidabad Division | Kandi Sub-Division | Laying of Distribution Pipeline and Land Development work at Kandra PWSS of Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000007/2025-2026 | 889/MURD | 22/04/2025 | 45 | PAL CONSTRUCTION (SUBHAM PAL) | 12.06 | 0 | 0
2848 | Murshidabad Division | Kandi Sub-Division | Formal work order for the work of KANDARA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362286S000) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | ORD/000695/2022-2023 | 89/MURD | 10/01/2023 | 365 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 649.94 | 0 | 18
2849 | Murshidabad Division | Kandi Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-II,Junior engineer-III,JUNIOR ENGINEER_BHARATPUR 2 BLOCK | RTOR000032/2023-2024 | 1043/MURD/2 | 17/04/2023 | 0 | Resource Division | 38.45 | 0 | 0
2850 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Augmentation of SURANGAPUR Zone-II (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000501/2022-2023 | 2417/MURD | 22/08/2022 | 922 | M/S GUHA AND ROY | 343.47 | 0 | 100
2851 | Murshidabad Division | Berhampur Sub-Division | Augmentation of Ground Water Based Surangapur Zone - II (PART -A), Salar PWSS Zone-IA, IB, IIA & IIB accommodate 2752 Nos FHTC, Laying Distribution System, Laying Rising Main in Nowda & Bharatpur - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000543/2023-2024 | 3148/MURD | 09/10/2023 | 779 | M/S GUHA & ROY ENTERPRISE | 996.68 | 0 | 20
2852 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipe line of 280 mm dia. HDPE pipe line From Node Point J-22 to J-27 ,J-6 to J-822 & J-82 to J-83 and Laying of 150, 250 mm dia ( For casing ) at Surangapur Zone -II PWSS under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000739/2023-2024 | 53/MURD | 05/01/2024 | 30 | M/S GUHA AND ROY | 30.62 | 0 | 100
2853 | Murshidabad Division | Berhampur Sub-Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000743/2022-2023 | 383/MURD | 10/02/2023 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 100
2854 | Murshidabad Division | Berhampur Sub-Division | Construction of Boundary wall at H/O site, land Development & Approach Road in connection with Augmentation of Surangapur Zone - II PWSS under Murshidabad Division , PHE Dte. Length -266 mtr. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000746/2023-2024 | 82/MURD | 09/01/2024 | 60 | BENGAL ENTERPRISE (PROP:-HADIKUL MOLLA) | 29.85 | 0 | 80
2855 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | ORD/000841/2021-2022 | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 0 | 1
2856 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000010/2024-2025 | 1811/MURD/09 | 20/06/2024 | 0 | Resource Division | 38.22 | 0 | 0
2857 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000099/2022-2023 | 702/MURD | 13/03/2023 | 0 | Resource Division | 48.15 | 0 | 0
2858 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 3,Junior engineer-II | RTOR000174/2023-2024 | 1180/MURD/17 | 29/04/2023 | 0 | Resource Division | 48.15 | 0 | 0
2859 | Murshidabad Division | Berhampur M/E Division | Payment Cost of repairing road from Biswaspara (SH) to Jortala More PWD Road under Jalangi Block in Murshidabad District vide packeage no WB 13-409. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | BILL/00826/2024-2025 | 303-MSD/2024-25 | 29/08/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 32.83 | 0 | 0
2860 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone III Part B Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000340/2022-2023 | 1806/MURD | 11/07/2022 | 1270 | HOQUEDAR ALI | 149.27 | 0 | 50
2861 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000588/2022-2023 | 3057/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 23.55 | 0 | 100
2862 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000020/2022-2023 | 2507/B/MURD | 31/08/2022 | 0 | Resource Division | 74.09 | 0 | 0
2863 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Jalangi PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | VCH/000353/2022-2023 | 183-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 16.77 | 0 | 0
2864 | Murshidabad Division | Berhampur M/E Division | Augmentation Work for Construction of 900 Cum OHR, Laing of Rising Main, Laing Distribution System, Construction of 3 Nos Pump House & Construction of Boundary Wall of Kankuria Jafrabad (Zone-II) PWSS under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-II | Junior Engineer 3,Junior engineer-II | ORD/000340/2023-2024 | 2697/MURD | 25/08/2023 | 365 | SAMIRAN KUMAR CHAKRABORTY | 446.57 | 0 | 0
2865 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of Jalangi Zone II Part-B Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) within Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000327/2022-2023 | 1691/MURD | 28/06/2022 | 1099 | KISMAT ARA BEGAM | 131.01 | 0 | 75
2866 | Murshidabad Division | Berhampur M/E Division | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000586/2022-2023 | 3055/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 1
2867 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000037/2024-2025 | MURD/2481/09 | 04/09/2024 | 0 | Resource Division | 14.57 | 0 | 0
2868 | Murshidabad Division | Berhampur M/E Division | Formal Work Order for Augmentation of KARIMPUR Jalangi Zone-I( Part A) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000358/2022-2023 | 2047/MURD | 26/07/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 692.97 | 0 | 40
2869 | Murshidabad Division | Berhampur M/E Division | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | ORD/000740/2023-2024 | 65/MURD | 08/01/2024 | 60 | S.S.INFRASTRUCTURE | 134.77 | 0 | 10
2870 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000034/2024-2025 | MURD/2481/06 | 04/09/2024 | 0 | Resource Division | 27.07 | 0 | 0
2871 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000037/2022-2023 | 2780/F/MURD | 01/10/2022 | 0 | Resource Division | 27.07 | 0 | 0
2872 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | JUNIOR ENGINEER 1,Junior engineer-II | RTOR000156/2023-2024 | 1180/MURD/05 | 29/04/2023 | 0 | Resource Division | 220.24 | 0 | 0
2873 | Murshidabad Division | Berhampur M/E Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID - 0005019112 in the District of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000239/2021-2022 | 1617/MURD | 28/06/2021 | 60 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0
2874 | Murshidabad Division | Berhampur M/E Division | Construction of Two nos Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Construction of RCC approach road (3 Mtr Wide)of 100 mtr length, Laying of Rising Main, Construction of 450 Cum OHR, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works and Land Development Works for Augmentation of Malibari Water Supply scheme at Raninagar-II Block under Murshidabad Division,PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000024/2024-2025 | 1816/MURD | 20/06/2024 | 560 | M/S B.M. INDUSTRIES | 282.92 | 0 | 50
2875 | Murshidabad Division | Berhampur M/E Division | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MALIBARI Ground Based Water Supply Scheme in Raninagar -II Block under Murshidabad Division , PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000029/2025-2026 | 1024/MURD | 05/05/2025 | 60 | M/S. S. DAS AND ENTERPRISE | 40.44 | 0 | 0
2876 | Murshidabad Division | Berhampur M/E Division | Balance & Allied Work for Laying Distribution System , FHTC of Malibari Water Supply Scheme in Raninagar-II Block ,under Murshidabad Division , PHE.Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000055/2024-2025 | 1986/MURD | 08/07/2024 | 363 | DAS TRADING CO. | 95.72 | 0 | 60
2877 | Murshidabad Division | Berhampur M/E Division | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based MALIBARI PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000170/2022-2023 | 1316/MURD | 20/05/2022 | 120 | NAYLA CONSTRUCTION | 217.49 | 0 | 100
2878 | Murshidabad Division | Berhampur M/E Division | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Malibari Water Supply Scheme of 3rd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000581/2022-2023 | 3064/MURD | 17/11/2022 | 30 | SUJIT KUMAR SAHA | 9.21 | 0 | 0
2879 | Murshidabad Division | Berhampur M/E Division | Formal work order for Functional Household Tap Connections (FHTC) in Bilchatra & Malibari Village ( Village Code -314568 ,314569 ) in connection with Augmentation of Malibari Ground Water Based Water Supply Scheme Raninagar-II Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000686/2022-2023 | 163/MURD | 17/01/2023 | 60 | KUNDU CONSTRUCTION | 170.31 | 0 | 95
2880 | Murshidabad Division | Berhampur M/E Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilchatra (Village Code -314568) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184027) | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000714/2020-2021 | 581/MURD | 09/02/2021 | 60 | ULTRA CONSTRUCTION. | 27.7 | 0 | 1
2881 | Murshidabad Division | Berhampur M/E Division | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MALIBARI PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | ORD/000831/2021-2022 | 3264/MURD | 05/10/2021 | 60 | RADIANT | 5.89 | 0 | 1
2882 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000021/2022-2023 | 2507/C/MURD | 31/08/2022 | 0 | Resource Division | 9.22 | 0 | 0
2883 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000044/2024-2025 | MURD/2991/03 | 13/11/2024 | 0 | Resource Division | 30.01 | 0 | 0
2884 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000053/2022-2023 | 3052/F/MURD | 17/11/2022 | 0 | Resource Division | 23.33 | 0 | 0
2885 | Murshidabad Division | Berhampur M/E Division | Material Requisition To Resource Division | ASSISTANT ENGINEER,ASSISTANT ENGINEER-I | Junior Engineer,Junior engineer-II | RTOR000110/2023-2024 | 1167/MURD/3 | 28/04/2023 | 0 | Resource Division | 27.6 | 0 | 0
2886 | Murshidabad Division | Berhampur Sub-Division | Laying of 160mm dia UPVC pipeline and road restoration work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000153/2022-2023 | 148/BSD | 12/04/2022 | 30 | SANJIB GHOSH | 4.84 | 0 | 0
2887 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHULA G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000517/2021-2022 | 349/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 0 | 0
2888 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Charmahula ( Village Code-315354) under Charmahula Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme I.D.-0001723196) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001466/2021-2022 | 279/MURD | 03/02/2022 | 60 | MAA CONSTRUCTION | 42.13 | 0 | 0
2889 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001641/2021-2022 | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0
2890 | Murshidabad Division | Berhampur Sub-Division | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001671/2021-2022 | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 1
2891 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001730/2021-2022 | 91/BSD | 07/03/2022 | 15 | S. DUTTA | 4.81 | 0 | 0
2892 | Murshidabad Division | Berhampur Sub-Division | Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with JJM and Jal Swapna under command area of village of Char Mahula Village code 315354 under Char Mahula W/S Scheme in the dist of MSD PHE DTE. Tender no - 182 of 21-22 by AE BSD | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000004/2022-2023 | 03-MSD/22-23 | 14/04/2022 | 0 | S. DUTTA | 4.81 | 0 | 0
2893 | Murshidabad Division | Berhampur Sub-Division | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-I G.P. under Murshidabad Division, P.H.E.Dte. | ASSISTANT ENGINEER |  | ORD/000506/2021-2022 | 341/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 0 | 0
2894 | Murshidabad Division | Islampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hari Sankarpur ( Village Code -314740) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000743/2020-2021 | 651 /MURD | 18/02/2021 | 60 | M/S SUBHA CONSTRUCTION | 43.8 | 0 | 1
2895 | Murshidabad Division | Islampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD | ASSISTANT ENGINEER | Junior Engineer | VCH/000270/2021-2022 |  | 18/08/2021 | 0 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0
2896 | Murshidabad Division | Islampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD | ASSISTANT ENGINEER | Junior Engineer | VCH/000722/2021-2022 | 51-MSD/21-22 | 13/09/2021 | 0 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0
2897 | Murshidabad Division |  | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Samserganj Block(Kanchantala, Dogachi-nowpara,Bhasaipaikar,Gagingar,Tinpakuria & Bogdadnagar ) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-A) |  |  | ORD/000069/2021-2022 | 126 /JSD | 26/05/2021 | 30 | IMAGIN COMMUNICATION | 2.38 | 0 | 0
2898 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) and under command area of village of Alamsahi ( Village Code -313853) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105). |  |  | ORD/000548/2020-2021 | 574/MURD | 09/02/2021 | 60 | BARUN DUTTA | 6.31 | 0 | 0
2899 | Murshidabad Division |  | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balbalpara ( Village Code -313852) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105) . |  |  | ORD/000624/2020-2021 | 634/MURD | 18/02/2021 | 60 | ARABINDA GHOSH | 41.65 | 0 | 0
2900 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BALBALPARA (Village Code 313852) under DOGACHHI (ZONE-II) Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 927 of 21-22 by EE MURD |  |  | VCH/000017/2022-2023 | 20-MSD/22-23 | 20/04/2022 | 0 | ARABINDA GHOSH | 41.65 | 0 | 0
2901 | Murshidabad Division |  | RESTORATION OF DAMAGED BALCK TOP AND ROAD FLANK OCCURED DUE TO CUTTING OF ROAD STRETCHES FOR LAYING OF PHE PIPELINE AT GUNANADABATI WATER SULLY SCHEME UNDER KANDI SUB DIVISION. |  |  | BILL/00622/2023-2024 | 267-MSD/2023-24 | 19/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 4.38 | 0 | 0
2902 | Murshidabad Division |  | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.10.2024 TO 27.02.2025. VEHICLE NO - WB57F2352 |  |  | ORD/000161/2024-2025 | 136/KSD | 19/09/2024 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0
2903 | Murshidabad Division |  | Construction of balance portion office cum godown including sanitary and plumbing work at H.W. Site and laying of UPVC pipeline in between node point 77 to 78, 78 to 89 & 78 to 79 of Pachhipara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. |  |  | ORD/000530/2023-2024 | 3117/MURD | 05/10/2023 | 30 | M.I CONSTRUCTION | 13.74 | 0 | 70
2904 | Murshidabad Division |  | Providing Functional Household Tap Connections (FHTC) (241 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Pashupatibati & Bolpara ( Village Code -315948, 315966, 315952) under Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. |  |  | ORD/000632/2023-2024 | 3437/MURD | 03/11/2023 | 30 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 9.36 | 0 | 70
2905 | Murshidabad Division |  | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.01.2022 to 31.03.2022. Work Order No 303 / BSD. DATE 15.12.2021 |  |  | VCH/000660/2022-2023 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 0.83 | 0 | 0
2906 | Murshidabad Division |  | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.07.2021 to 03.01.2022. Work Order No 230 / BSD. DATE 02.07.2021 |  |  | VCH/000661/2022-2023 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 1.84 | 0 | 0
2907 | Murshidabad Division |  | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.06.2021 to 03.07.2021. Work Order No 185 / BSD. DATE 30.07.2020 |  |  | VCH/000662/2022-2023 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 0.42 | 0 | 0
2908 | Murshidabad Division | Islampur Sub-Division | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khidir Para ( Village Code -314739) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | ASSISTANT ENGINEER | Junior Engineer | ORD/000513/2020-2021 | 580/MURD | 09/02/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.55 | 0 | 80
2909 | Murshidabad Division | Islampur Sub-Division | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Raypur (Village code-314582) under KatakobraGround Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005185646) | ASSISTANT ENGINEER | Junior Engineer | ORD/000549/2022-2023 | 2765/MURD | 29/09/2022 | 120 | SOFIQUL ISLAM | 154.82 | 0 | 100
2910 | Murshidabad Division | Islampur Sub-Division | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-I water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | ASSISTANT ENGINEER | Junior Engineer | ORD/001240/2021-2022 | 46/ISD | 28/01/2022 | 60 | PRAVAT KUMAR GHOSH | 3.65 | 0 | 1
2911 | Murshidabad Division | Islampur Sub-Division | Repairing & Renovation of the Boundary wall of pump House No-2 Both & Allied works under Katakopra Zone- I & II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | ASSISTANT ENGINEER | Junior Engineer | ORD/002122/2021-2022 | 48/ISD | 28/01/2022 | 30 | PARTHA RAJAK | 1.95 | 0 | 1
2912 | Murshidabad Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DEPUTIPAR (Village Code-314582) under GODHANPARA Ground Water Supply Scheme for Arsenic Affected Area of RANINAGAR-II BLOCK under Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | Junior Engineer | VCH/000235/2021-2022 | 31-MSD / 21-22 | 27/08/2021 | 0 | M/S ROY & BOSE ENTERPRISE | 10.92 | 0 | 0
2913 | Murshidabad Division |  | Extension of distribution system for supply of safe potable drinking water at Charakdanga Adibashi Para, Madhunia Primay School & Madhunia SSKAdibashi Para under Amarkundu Water Supply Scheme under Lalbagh Sub-Division,PHE Dte. |  |  | ORD/000884/2021-2022 | 349/LSD | 09/11/2021 | 30 | GHOSH & COMPANY | 2.74 | 0 | 0
2914 | Murshidabad Division |  | Construction of RCC Stand Post including platforms at AmarkunduVillage, Kanakpara Village, Nandigram Village, Bagor Village & Madhunia Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/000919/2021-2022 | 362/LSD | 17/11/2021 | 30 | SARAJIT KUMAR MAJUMDER | 2.43 | 0 | 0
2915 | Murshidabad Division |  | Extension of UPVC pipeline construction of RCC stand post with platform at Ghoshkula area (Kanakpara) under Improvement of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/001226/2021-2022 | 414/LSD | 27/12/2021 | 30 | SANJIB KUMAR SINGHA | 4.89 | 0 | 0
2916 | Murshidabad Division |  | Balance and allied works For Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sankuria (Village code 315024) and Chayan Nagar (Village code 315023) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. |  |  | ORD/001615/2021-2022 | 308/MURD | 07/02/2022 | 60 | PARTHA PRATIM DAS | 16.51 | 0 | 1
2917 | Murshidabad Division |  | Extension of UPVC pipeline construction of RCC stand post with platform at Ghoshkula area (Kanakpara) under Improvement of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. |  |  | ORD/002073/2021-2022 | 414 /LSD | 27/12/2021 | 30 | SANJIB KUMAR SINGHA | 4.89 | 0 | 0
2918 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BURWAN- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- GOURINAGAR , CODE-315951 , 631/2020-21/EE |  |  | VCH/002050/2020-2021 | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 9.08 | 0 | 0
2919 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC |  |  | VCH/002052/2020-2021 | 504/W | 22/03/2021 | 0 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0
2920 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gopjan (Village code 315447) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000001/2022-2023 | 1126/MURD | 29/04/2022 | 45 | PRATICHI ENTERPRISE | 24.48 | 0 | 40
2921 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) 67 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Raniswar( Village Code -315314) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000030/2022-2023 | 1083/MURD | 27/04/2022 | 30 | DEBASISH SARKAR | 33.33 | 0 | 1
2922 | Murshidabad Division | Berhampur Sub-Division | Laying distribution pipeline in connection with Jal Swapna (Jal Jeevan Mission) of Nialispara ( village code: 315317 ) and Budhorpara village of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000184/2022-2023 | 191/BSD | 28/04/2022 | 30 | MOBIDUR RAHAMAN | 4.67 | 0 | 80
2923 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 18nos FHTC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000193/2022-2023 | 202/BSD | 28/04/2022 | 30 | SURAJIT MONDAL | 4.81 | 0 | 100
2924 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 28nos FHTC | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000194/2022-2023 | 203/BSD | 28/04/2022 | 30 | ABIDA CONSTRUCTION | 4.85 | 0 | 80
2925 | Murshidabad Division | Berhampur Sub-Division | Providing Functional Household Tap Connections (FHTC) 69 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Nialispara ( Village Code -315317) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000195/2022-2023 | 1185/MURD | 09/05/2022 | 30 | AMAL KUMAR DAS | 37.93 | 0 | 0
2926 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Budharpara (Village code 315320) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID - 5182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000443/2021-2022 | 2644/MURD | 27/08/2021 | 60 | M/S. BIMALENDU BOSE | 21.87 | 0 | 0
2927 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tikiapara (Village code 315318) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001468/2021-2022 | 281/MURD | 03/02/2022 | 60 | M/S SWAPAN KUMAR NATH AND CO. | 19.7 | 0 | 100
2928 | Murshidabad Division | Berhampur Sub-Division | Material Requisition To Resource Division | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | RTOR000026/2021-2022 | 539/11/MURD | 25/02/2022 | 0 | Resource Division | 0.49 | 0 | 0
2929 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Moktarpur (Village code 315321) under Sahajadpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID 1723365 in the District of Murshidabad. (Sl No-34) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000060/2021-2022 | 1231/MURD | 13/05/2021 | 180 | M/S GUHA & ROY ENTERPRISE | 80.38 | 35.41 | 1
2930 | Murshidabad Division | Berhampur Sub-Division | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000454/2021-2022 | 304/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.34 | 4.34 | 0
2931 | Murshidabad Division | Berhampur Sub-Division | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Balarampur (Village code 315322)under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of BERHAMPORE Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723365 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/000462/2020-2021 | 3139/MURD | 11/12/2020 | 60 | M/S M.S. ENTERPRISE | 27.16 | 0 | 1
2932 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bahurul (Village code 315329) under Sahajadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID 1723365 in the District of Murshidabad.(Sl-4) | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001138/2021-2022 | 2460/MURD | 26/08/2022 | 180 | SANJAY BISWAS | 70.29 | 0 | 0
2933 | Murshidabad Division | Berhampur Sub-Division | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sahajadpur (Village code 315326) under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID 1723365 in the District of Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | ORD/001142/2021-2022 | 3840/MURD | 08/12/2021 | 90 | J.S. CONSTRUCTION | 54.01 | 0 | 1
2934 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at North Durgapur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000732/2022-2023 | 257-MSD/22-23 | 17/08/2022 | 0 | MITHUN ROY | 4.8 | 0 | 0
2935 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at Muktarpur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000733/2022-2023 | 257-MSD/22-23 | 17/08/2022 | 0 | MITHUN ROY | 1.54 | 0 | 0
2936 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at South Durgapur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000734/2022-2023 | 258-MSD/22-23 | 18/08/2022 | 0 | M/S GUHA AND ROY | 5 | 0 | 0
2937 | Murshidabad Division | Berhampur Sub-Division | Laying of distribution pipeline in connection with FHTC work at Muktarpur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | ASSISTANT ENGINEER | JUNIOR ENGINEER 1 | VCH/000735/2022-2023 | 258-MSD/22-23 | 18/08/2022 | 0 | M/S GUHA AND ROY | 4.84 | 0 | 0
2938 | Murshidabad Division |  | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of AURANGABAD (Village code 313981) under AURANGABAD Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte.Scheme ID 0005184162 |  |  | ORD/001155/2021-2022 | 3976/MURD | 21/12/2021 | 180 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 309.91 | 0 | 1
2939 | Murshidabad Division |  | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 540/9/MURD | 25/02/2022 | 0 | Resource Division | 42.35 | 0 | 0
2940 | Murshidabad Division |  | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village AURANGABAD (Village Code 313981) under AURANGABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-II Block in the District of Murshidabad. TENDER NO -129 OF 21-22 SE MC |  |  | VCH/000642/2022-2023 | 253-MSD/22-23 | 11/08/2022 | 0 | S.ENTERPRISE | 67.38 | 0 | 0
Total | [10 empty] | 305148.21 | 1233.49