## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in Barasukjora(zone-I)PWSS |  |  | VCH/000609/2021-2022 | 84438 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 6.18 | 0 | 0
2 | Midnapore Division |  | DATA ENTRY FOR FHTC |  |  | VCH/000837/2021-2022 | 844389 | 13/09/2021 | 0 | GANESH CH NANDY | 0.02 | 0 | 0
3 | Midnapore Division |  | DATA ENTRY FOR FHTC |  |  | VCH/000838/2021-2022 | 844389 | 13/09/2021 | 0 | PARTHA PRATIM PAL | 0.04 | 0 | 0
4 | Midnapore Division |  | DATA ENTRY FOR FHTC |  |  | VCH/000840/2021-2022 | 844389 | 13/09/2021 | 0 | SOVANDEB MANNA | 0.02 | 0 | 0
5 | Midnapore Division |  | DATA ENTRY FOR FHTC |  |  | VCH/000842/2021-2022 | 844389 | 13/09/2021 | 0 | TANMOY BERA | 0.08 | 0 | 0
6 | Midnapore Division |  | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001411/2020-2021 | 8443460 | 26/03/2021 | 0 | PAPPU SHAW | 0.2 | 0 | 0
7 | Midnapore Division |  | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001412/2020-2021 | 8443460 | 26/03/2021 | 0 | KOUSHIK PAL | 0.26 | 0 | 0
8 | Midnapore Division |  | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001413/2020-2021 | 8443460 | 26/03/2021 | 0 | SANDIP BISWAS | 0.16 | 0 | 0
9 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-I) PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | VCH/001703/2021-2022 | 844340 | 09/03/2022 | 0 | ASIS KUMAR SARANGI | 7.15 | 0 | 0
10 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000267/2020-2021 | 1464/MD | 26/11/2020 | 180 | DULAL CHANDRA DAS | 80.8 | 49.63 | 0
11 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Panpara W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000259/2020-2021 | 1456/MD | 26/11/2020 | 1859 | BANERJEE CONSTRUCTION | 94.34 | 48.69 | 5
12 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000254/2020-2021 | 1450/MD | 26/11/2020 | 180 | HARIPADA PATTANAYAK | 96.05 | 35.03 | 96
13 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001308/2021-2022 | 844397 | 25/01/2022 | 0 | UTTAM KUMAR DAS | 17.78 | 0 | 0
14 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001476/2021-2022 | 844397 | 25/01/2022 | 0 | UTTAM KUMAR DAS | 14.42 | 0 | 0
15 | Midnapore Division | Kharagpur Sub-Division | Supply & installation of 20 KVA output diesel Generator set on monthly hire basis including day to day operation and maintenance of the same for alternative electrical arrangement in the office of Assistant Engineer, Kharagpur Sub Division and also Kharagpur WTP Water Testing Lab situated within the Inda PHE Complex etc. under Midnapore Division, PHE Dte. [Period from 03.02.2021 to 02.02.2022] | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000881/2020-2021 | 57/AE/KSD | 02/02/2021 | 12 | PULLOCK KUMAR GHOSH | 0.86 | 0 | 0
16 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | VCH/001286/2021-2022 | 844364 | 18/01/2022 | 0 | ANIRBAN CHAKRABORTY | 0.2 | 0 | 0
17 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | VCH/001287/2021-2022 | 844364 | 18/01/2022 | 0 | SOVANDEB MANNA | 0.1 | 0 | 0
18 | Midnapore Division | RWS Midnapur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | VCH/001404/2020-2021 | 8443458 | 26/03/2021 | 0 | TANMOY BERA | 0.2 | 0 | 0
19 | Midnapore Division | RWS Midnapur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | VCH/001405/2020-2021 | `8443458 | 26/03/2021 | 0 | GANESH CH NANDY | 0.27 | 0 | 0
20 | Midnapore Division | RWS Midnapur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | VCH/001406/2020-2021 | 8443458 | 26/03/2021 | 0 | SHRABONTI BERA | 0.29 | 0 | 0
21 | Midnapore Division | Ghatal Subdivision | Security Deposit/Caution money for electric quotation. [MB No:- 2948/MMD] {Shimulia W/S Scheme.} | AE Ghatal Sub-division | JE1 Ghatal Sub-division | BILL/00285/2023-2024 |  | 05/07/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 0.93 | 0 | 0
22 | Midnapore Division | Ghatal Subdivision | Electric Quotation bill for the WBSEDCL. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | BILL/00317/2023-2024 | BP-2023-24-177 | 20/07/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 0.93 | 0 | 0
23 | Midnapore Division | Ghatal Subdivision | Retrofitting of Shimulia PWSS to accommodate FHTC in Ghatal block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000047/2022-2023 | 840/MD | 02/05/2022 | 30 | ANUSKA ENTERPRISE | 26.82 | 0 | 100
24 | Midnapore Division | Kharagpur Sub-Division | Retrofitting of Warda PWSS (Zone-II) to accommodate FHTC in Kharagpur- II block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000087/2022-2023 | 1134/MD | 13/06/2022 | 21 | M/S. D.K.H.CONSTRUCTION | 24.23 | 0 | 0
25 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Warda (Zone-II) PWSS under Kharagpur-II Block in Paschim Medinipur District. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000859/2021-2022 | 423/MD | 04/03/2022 | 30 | S.T. ENTERPRISE | 38.17 | 0 | 0
26 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | RTOR000099/2024-2025 | 3414/MD | 25/11/2024 | 0 | Resource Division | 10.63 | 0 | 0
27 | Midnapore Division | Kharagpur Sub-Division | Retrofitting of Kanchangeria PWSS to accommodate FHTC in Debra Block under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000072/2022-2023 | 1012/MD | 27/05/2022 | 1311 | M/S. A.R. ENTERPRISE. | 56.15 | 0 | 65
28 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhengasole, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000566/2020-2021 | 60/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.08 | 1.82 | 0
29 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Dhengasole Uttar Para in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-01) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000718/2020-2021 | 98/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.8 | 0 | 0
30 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Dhengasole Dakshinpara in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-02) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000723/2020-2021 | 99/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.72 | 0 | 0
31 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Jharbhanga in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-03) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000740/2020-2021 | 100/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.82 | 0 | 0
32 | Midnapore Division | Kharagpur Sub-Division | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
33 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lachhmi Chak (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000622/2021-2022 | 175/MD | 01/02/2022 | 150 | BIDHAN CHANDRA PATRA | 22.21 | 0 | 80
34 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lachhmi Chak (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000623/2021-2022 | 176/MD | 01/02/2022 | 150 | BIDHAN CHANDRA PATRA | 21.5 | 0 | 90
35 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000011/2021-2022 | 2127/MD | 14/12/2021 | 0 | Resource Division | 1.3 | 0 | 0
36 | Midnapore Division | Kharagpur Sub-Division | Sinking of (1 St) mniX 100 mm.X 150rnir) RBCM by Rnla.ry method at lJaspnr writes *«mix scheme. tube we11 no. I of Sabang i3lock of Paschim Midnapur District under Midtidpur Mechanical Division P.II.E Eite. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000383/2022-2023 |  | 03/08/2022 | 0 | DEBJYOTI BASU | 3.95 | 0 | 0
37 | Midnapore Division | Kharagpur Sub-Division | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Lachhmi Chak & its adjoining mouzas. Block - Sabang, District - Paschim Medinipur | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000458/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.3 | 0 | 0
38 | Midnapore Division | Kharagpur Sub-Division | Purchasing of materials. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001689/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.3 | 0 | 0
39 | Midnapore Division | Kharagpur Sub-Division | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001823/2021-2022 | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.9 | 0 | 0
40 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bamanda W/S Scheme, Block: - Dantan-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000148/2020-2021 | 1320/MD | 06/11/2020 | 180 | SANKAR PRASAD MAITY | 27.77 | 0 | 0
41 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Barsahara (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000331/2022-2023 | 1892/MD | 12/09/2022 | 60 | DULAL CHANDRA DAS | 50.39 | 0 | 50
42 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Barsahara PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000425/2021-2022 | 1657/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.14 | 0 | 100
43 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Pump House for Sansahara & Manikarah villages within Barsahara PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000665/2022-2023 | 584/MD | 23/02/2023 | 60 | DULAL CHANDRA DAS | 17.7 | 0 | 10
44 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bajpara PWSS under Midnapore Sadar Block in Paschim Medinipur District. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000406/2021-2022 | 2005/MD | 01/12/2021 | 30 | M/S. CARE | 64.02 | 0 | 0
45 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC (350 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sche-80/20mm dia.) HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Balarampur W/S Scheme within Kharagpur-II Dev. block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000474/2022-2023 | 2269/MD | 09/11/2022 | 21 | SUBRATA DAS | 13.21 | 0 | 100
46 | Midnapore Division | Kharagpur Sub-Division | Extension of laying of distribution uPVC Pipe line Left-out portion and all allied works at i) Balarampur village (North side), ii) Balarampur village (South side) and Madhpur, iii) Some part of Krishnapur & Ramchandrapur and iv) Some part of Gobindanagar & Kanchantala under JJM of Balarampur & its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000477/2022-2023 | 2272/MD | 09/11/2022 | 30 | S.T. ENTERPRISE | 21.85 | 0 | 100
47 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Balarampur PWSS under Kharagpur-II Block in Paschim Medinipur District. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000492/2021-2022 | 2185/MD | 17/12/2021 | 30 | S.T. ENTERPRISE | 61.78 | 0 | 0
48 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground water based piped water supply scheme for Sartla (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur Districct Under Medinipur Division PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000184/2022-2023 | 1479/MD | 25/07/2022 | 45 | GOBINDA MAITY | 61.29 | 0 | 100
49 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Sartla PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000438/2021-2022 | 1676/MD | 29/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.23 | 0 | 100
50 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of pipe line damaged due to construction of PMGSY roads, village Roads over existing pipe line Sartla & its adjoining mouzas (Rampura, Kororda, Cheena) W/S Scheme at Sabang Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000489/2021-2022 | 2182/MD | 17/12/2021 | 45 | GOBINDA MAITY | 43.21 | 0 | 100
51 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in Barasukjora(zone-II)PWSS |  |  | VCH/000607/2021-2022 | 84437 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 1.99 | 0 | 0
52 | Midnapore Division |  | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001143/2020-2021 | 8443109 | 12/02/2021 | 0 | MAHADEV DAS | 0.09 | 0 | 0
53 | Midnapore Division |  | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. |  |  | VCH/001144/2020-2021 | 8443109 | 12/02/2021 | 0 | DEBAPRASAD PAL | 0.03 | 0 | 0
54 | Midnapore Division |  | FHTC data entry. |  |  | VCH/001288/2021-2022 | 844365 | 18/01/2022 | 0 | NABOGOPAL ADHIKARI | 0.1 | 0 | 0
55 | Midnapore Division |  | FHTC Data Entry. |  |  | VCH/001289/2021-2022 | 844365 | 18/01/2022 | 0 | PRATHA PRATIM PAL | 0.11 | 0 | 0
56 | Midnapore Division |  | For payment of liabilities. |  |  | VCH/001290/2021-2022 | 844365 | 18/01/2022 | 0 | RINTU SAMANTA | 0.07 | 0 | 0
57 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-II) PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | VCH/001704/2021-2022 | 844357 | 08/03/2022 | 0 | ASIS KUMAR SARANGI | 20.82 | 0 | 0
58 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in Barasukjora (Zone-II) PWSS of Binpur-II Block under Jhargram Division, PHE Dte. |  |  | VCH/001913/2021-2022 | 844357 | 08/03/2022 | 0 | ASIS KUMAR SARANGI | 0.37 | 0 | 0
59 | Midnapore Division | Jhargram Division | Transfer to EE/JSD, PHE Dte. ( Standalone PWSS) | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00612/2022-2023 |  | 20/12/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 102.67 | 0 | 0
60 | Midnapore Division | Jhargram Division | Transfer to EE/JSD, PHE Dte. ( Standalone PWSS) | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00667/2022-2023 | BP-2022-23-465 | 24/12/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 94.84 | 0 | 0
61 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_4 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000056/2022-2023 | 876/MD | 10/05/2022 | 180 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 177.59 | 0 | 0
62 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Sankrail_3_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000057/2022-2023 | 877/MD | 10/05/2022 | 180 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT. LTD. | 150.3 | 0 | 99
63 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_5 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000644/2021-2022 | 185/MD | 01/02/2022 | 180 | GOBINDA MAITY | 177.73 | 0 | 0
64 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_14 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000645/2021-2022 | 186/MD | 01/02/2022 | 180 | GOBINDA MAITY | 177.71 | 0 | 1
65 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Installation of Iron Elemention Plant (IEP), Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Nayagram_4_15 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000646/2021-2022 | 187/MD | 01/02/2022 | 180 | GOBINDA MAITY | 177.7 | 0 | 1
66 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000648/2021-2022 | 189/MD | 01/02/2022 | 180 | PROVAT KUMAR DE | 106.64 | 0 | 0
67 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000649/2021-2022 | 190/MD | 01/02/2022 | 180 | SUJATA CONSTRUCTION | 106.99 | 0 | 1
68 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_6 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000651/2021-2022 | 192/MD | 01/02/2022 | 180 | M/S. B. N. ENTERPRISES | 107.25 | 0 | 0
69 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC for drought like situation prone areas at different location under location Id Nayagram_1_7 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000652/2021-2022 | 193/MD | 01/02/2022 | 180 | DIPAK KUMAR BAKLY | 108.29 | 0 | 0
70 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000654/2021-2022 | 195/MD | 01/02/2022 | 180 | KISHORE GHOSH | 133.21 | 0 | 0
71 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_3 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000655/2021-2022 | 196/MD | 01/02/2022 | 180 | SUNIL DULE | 134.69 | 0 | 1
72 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Gopiballavpur-II_2_1 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000705/2021-2022 | 301/MD | 15/02/2022 | 180 | ASIS KUMAR SARANGI | 135.09 | 0 | 1
73 | Midnapore Division | Jhargram Division | Standalone Water Supply System comprising of Pump House and Distribution Pipeline with Community Tank & provision of FHTC including Sinking of 150 mm X 100 mm X 135 m Rig Bored Tube Well for drought like situation prone areas at different location under location Id Jhargram_2_2 under Jhargram Division in the District of Jhargram. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000706/2021-2022 | 302/MD | 15/02/2022 | 180 | LALIT BIHARI MAITY | 132.67 | 0 | 1
74 | Midnapore Division | Jhargram Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | RTOR000007/2022-2023 | 1851/MD | 07/09/2022 | 0 | Resource Division | 30.75 | 0 | 0
75 | Midnapore Division | Jhargram Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | RTOR000008/2022-2023 | 1868/MD | 08/09/2022 | 0 | Resource Division | 30.75 | 0 | 0
76 | Midnapore Division | Jhargram Division | Standalone units for Drought like situation Prone 08 Blocks of Jhargram District (Model standalone Grid power operated W/S System for Habitations/mouzas with 400 & more population) under mid-trem plan of master plan. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000373/2022-2023 | BP-2022-23-57 | 13/05/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 73.7 | 0 | 0
77 | Midnapore Division | Jhargram Division | For WBSEDCL quotations i.c.t. Construction of RBTW under standalone pipe water supply scheme. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000468/2022-2023 | BP-2022-23-230 | 22/08/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 4.18 | 0 | 0
78 | Midnapore Division | Jhargram Division | Standalone units for drought line situation prone 8 blocks of Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000617/2022-2023 | BP-2022-23-121 | 18/06/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 75.97 | 0 | 0
79 | Midnapore Division | Jhargram Division | Requisition of fund for ASHA Incentive in the activity of onsite drinking water testing at the village level by trained ASHAs in Jhargram District. | Assistant Engineer,Assistant Engineer Headquarter,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/000717/2022-2023 | BP-2022-23-157 | 12/07/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI JHARGRAM HEALTH DISTRICT | 3.65 | 0 | 0
80 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary wall at 1st Tube well site for Augmentation of Amlagora PWSS, Block - Garhbeta-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Total length 120 mtr., Column size 250X250mm, 3.00M, C/C ht.- 2.300 mtr. from G.L.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000104/2024-2025 | 2850/MD | 09/09/2024 | 60 | AJITESH ACHARJEE | 11.39 | 0 | 0
81 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipeline, Soil test and Construction of RCC Over Head Reservoir of capacity 200 CuM and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Amlagora W/S Scheme to accommodate FHTC with Garhbeta-I Dev. Block under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. Dist.- Paschim Medinipur. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000376/2022-2023 | 1959/MD | 20/09/2022 | 180 | BANERJEE CONSTRUCTION | 606.57 | 0 | 33
82 | Midnapore Division | Midnapur Sadar Sub-Division | Repair and Renovation of Switch Room cum Chlorine Room No. 1 of Amlagora Water Supply Scheme within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001030/2022-2023 | 982/AE/MSSD | 17/03/2023 | 15 | MR GOUTAM GHOSH, | 0.97 | 0 | 10
83 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Amlagora (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001032/2021-2022 | 1624/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.01 | 0 | 0
84 | Midnapore Division | Midnapur Sadar Sub-Division | Repair and Renovation of Switch Room cum Chlorine Room No. 2 of Amlagora Water Supply Scheme within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. (SL No-02) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001032/2022-2023 | 983/AE/MSSD | 17/03/2023 | 15 | MR GOUTAM GHOSH, | 0.97 | 0 | 10
85 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Amlagora (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001033/2021-2022 | 1625/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.66 | 0 | 0
86 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000016/2022-2023 | 2322/MD | 17/11/2022 | 0 | Resource Division | 32.25 | 0 | 0
87 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000021/2022-2023 | 137/MD | 11/01/2023 | 0 | Resource Division | 32.25 | 0 | 0
88 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000115/2022-2023 | 244/MD | 18/01/2023 | 0 | Resource Division | 100.02 | 0 | 0
89 | Midnapore Division | Midnapur Sadar Sub-Division | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Amlagora, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001391/2021-2022 | BP-2021-22-387 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.05 | 0 | 0
90 | Midnapore Division | Midnapur Sadar Sub-Division | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Amlagora, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001393/2021-2022 | BP-2021-22-383 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.11 | 0 | 0
91 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001812/2021-2022 | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0
92 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000126/2023-2024 | 2524/MD | 18/07/2023 | 840 | NABA KUMAR BHUNIA | 1870.43 | 0 | 82
93 | Midnapore Division | Kharagpur Sub-Division | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000180/2024-2025 | 3165/MD | 05/10/2024 | 255 | NABA KUMAR BHUNIA | 78.57 | 0 | 50
94 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000032/2023-2024 | 1171/MD | 26/04/2023 | 0 | Resource Division | 32 | 0 | 0
95 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000077/2023-2024 | 1226/MD | 27/04/2023 | 0 | Resource Division | 13.53 | 0 | 0
96 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000210/2023-2024 | 2827/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 1515.85 | 0 | 15
97 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000029/2023-2024 | 1177/MD | 26/04/2023 | 0 | Resource Division | 38.98 | 0 | 0
98 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000108/2023-2024 | 1242/MD | 27/04/2023 | 0 | Resource Division | 24.38 | 0 | 0
99 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 & 450 cum OHRs (Intze type) & Accommodate FHTC (4,203 Nos.) under JJM with allied work for (1) Gohaldanga & (2) Haridharpur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000252/2023-2024 | 3147/MD | 29/08/2023 | 718 | BANERJEE CONSTRUCTION | 1062.73 | 0 | 30
100 | Midnapore Division | Ghatal Subdivision | Laying of rising main & interconnection for Gohaldanga & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000434/2024-2025 | 319/MD | 29/01/2025 | 45 | ASHOK BANERJEE | 5.11 | 0 | 0
101 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000003/2024-2025 | 3324/MD | 25/11/2024 | 0 | Resource Division | 6.78 | 0 | 0
102 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000068/2022-2023 | 89/MD | 10/01/2023 | 0 | Resource Division | 6.9 | 0 | 0
103 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
104 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000107/2024-2025 | 3443/MD | 25/11/2024 | 0 | Resource Division | 4.68 | 0 | 0
105 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000272/2023-2024 | 3985/MD | 06/10/2023 | 0 | Resource Division | 23.4 | 0 | 0
106 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000158/2022-2023 | 1154/MD | 25/04/2023 | 0 | Resource Division | 33.11 | 0 | 0
107 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
108 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000084/2022-2023 | 191/MD | 16/01/2023 | 0 | Resource Division | 20.75 | 0 | 0
109 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000120/2024-2025 | 3456/MD | 25/11/2024 | 0 | Resource Division | 19.88 | 0 | 0
110 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000239/2023-2024 | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 33
111 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
112 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000115/2024-2025 | 3451/MD | 25/11/2024 | 0 | Resource Division | 15.4 | 0 | 0
113 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (1430 Nos) including 1 years operation & maintenance For Bikrampur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000204/2023-2024 | 2820/MD | 07/08/2023 | 540 | GOBINDA MAITY | 416.11 | 0 | 55
114 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
115 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000013/2023-2024 | 1144/MD | 25/04/2023 | 0 | Resource Division | 16.01 | 0 | 0
116 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000124/2023-2024 | 1315/MD | 28/04/2023 | 0 | Resource Division | 27.89 | 0 | 0
117 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
118 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000091/2023-2024 | 1234/MD | 27/04/2023 | 0 | Resource Division | 22.17 | 0 | 0
119 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 200 Cum OHR (Intze type with Raft foundation) & under JJM with allied work for Augmentation of Shanrpur PWSS in Debra block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000302/2024-2025 | 3398/MD | 25/11/2024 | 180 | KISHORE GHOSH | 194.76 | 0 | 0
120 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of pipe line damaged due to construction of roads & Construction of Sluice Valve Chamber within Shanrpur & its adjoining mouzas (Gayeshpur, Kolkuria, Bhuiabasan, Bar Bhuiabasan, Bhainagar etc.) W/S Scheme at Debra Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000478/2021-2022 | 2172/MD | 17/12/2021 | 45 | UCON | 42.21 | 0 | 0
121 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Shanrpur PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001008/2021-2022 | 518/MD | 17/03/2022 | 10 | SIRCON ENGINEERING SERVICES | 2.62 | 0 | 100
122 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
123 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000111/2023-2024 | 1245/MD | 27/04/2023 | 0 | Resource Division | 51.32 | 0 | 0
124 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000061/2023-2024 | 1204/MD | 26/04/2023 | 0 | Resource Division | 22.73 | 0 | 0
125 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 75
126 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000224/2023-2024 | 1515/MD | 12/05/2023 | 0 | Resource Division | 23.72 | 0 | 0
127 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 (Two) Nos. Tube well for Bulanpur & its adjoining mouzas (Zone-I) PWSS in Garhbeta-II block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000138/2023-2024 | 2622/MD | 24/07/2023 | 30 | M/S BISWANATH CONSTRUCTION | 17.57 | 0 | 100
128 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (202 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000174/2023-2024 | 2676/MD | 26/07/2023 | 721 | NIMAI HAZRA | 33.52 | 0 | 70
129 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Boundary wall, Pump House alongwith 20 CuM OHR (Zone-2) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme with Standalone in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000175/2023-2024 | 2677/MD | 26/07/2023 | 840 | ANNAPURNA TUBEWELL WORKS | 36.74 | 0 | 15
130 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of Rising main, Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (400 Nos.) including 2 years operation & maintenance under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000418/2023-2024 | 5154/MD | 07/11/2023 | 60 | SAIKAT DANDAPAT | 111.63 | 0 | 3
131 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (200 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000433/2023-2024 | 5189/MD | 08/11/2023 | 45 | A.K. SIKDAR | 47.78 | 0 | 70
132 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 150 CuM OHR (Torch type with Solid raft) (Zone-1) & Accommodate FHTC (300 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000540/2024-2025 | 731/MD | 18/03/2025 | 180 | DEVJYOTI BERA | 88.31 | 0 | 0
133 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
134 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000264/2023-2024 | 2040/MD | 18/05/2023 | 0 | Resource Division | 26.77 | 0 | 0
135 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Duki PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000461/2024-2025 | 376/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 10.8 | 0 | 0
136 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000056/2023-2024 | 1195/MD | 26/04/2023 | 0 | Resource Division | 30.12 | 0 | 0
137 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000073/2024-2025 | 3423/MD | 25/11/2024 | 0 | Resource Division | 14.32 | 0 | 0
138 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000132/2023-2024 | 1325/MD | 28/04/2023 | 0 | Resource Division | 18.04 | 0 | 0
139 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 (Two) Nos. Tube well for Amlasuli & its adjoining mouzas (Zone-I) PWSS in Garhbeta-II block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000116/2023-2024 | 2517/MD | 18/07/2023 | 30 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.57 | 0 | 30
140 | Midnapore Division | Midnapur Sadar Sub-Division | Accommodate FHTC (218 Nos.) & Construction of Boundary wall under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000144/2023-2024 | 2628/MD | 24/07/2023 | 45 | M/S. BLUE BIRD | 31.54 | 0 | 25
141 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Boundary wall, Pump House alongwith 20 CuM OHR (Zone-2) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme with Standalone in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000145/2023-2024 | 2636/MD | 24/07/2023 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.73 | 0 | 15
142 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (400 Nos.) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000173/2023-2024 | 2675/MD | 26/07/2023 | 45 | EVEREST CONSULTANT SERVICES | 66.12 | 0 | 80
143 | Midnapore Division | Midnapur Sadar Sub-Division | Improvement of approach road of Bhansra PWSS Head Work Site under Kashiery Block within Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000384/2024-2025 | 10101/MD | 20/11/2024 | 30 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 0 | 0 | 0
144 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 250 CuM OHR (Intze type with Solid raft) (Zone-1) & Accommodate FHTC (500 Nos.) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000418/2024-2025 | 199/MD | 17/01/2025 | 360 | DIPAK KUMAR BAKLY | 111.02 | 0 | 0
145 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of Rising main, Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years operation & maintenance under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000421/2024-2025 | 200/MD | 17/01/2025 | 360 | DIPAK KUMAR BAKLY | 117.81 | 0 | 0
146 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
147 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000263/2023-2024 | 2039/MD | 18/05/2023 | 0 | Resource Division | 27.2 | 0 | 0
148 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 100 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (459 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Kashba & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/000066/2023-2024 | 2147/MD | 08/06/2023 | 992 | A.J. ENTERPRISE | 205.4 | 0 | 65
149 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | RTOR000074/2024-2025 | 3424/MD | 25/11/2024 | 0 | Resource Division | 2.83 | 0 | 0
150 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | RTOR000089/2022-2023 | 195/MD | 16/01/2023 | 0 | Resource Division | 15.49 | 0 | 0
151 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,647 nos.) under JJM with allied work for Kushman PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000036/2023-2024 | 1338/MD | 28/04/2023 | 884 | M/S. D.K.H.CONSTRUCTION | 444.51 | 0 | 8
152 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Kuran & its adjoining Mouzas PWSS AND (2) Kushman & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000660/2022-2023 | 1766/MD | 24/08/2022 | 30 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.92 | 0 | 0
153 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000035/2024-2025 | 3362/MD | 25/11/2024 | 0 | Resource Division | 10.15 | 0 | 0
154 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000059/2022-2023 | 64/MD | 09/01/2023 | 0 | Resource Division | 17.03 | 0 | 0
155 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
156 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000086/2023-2024 | 1232/MD | 27/04/2023 | 0 | Resource Division | 33.16 | 0 | 0
157 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000014/2023-2024 | 934/MD | 04/04/2023 | 758 | NIMAI HAZRA | 35.97 | 0 | 100
158 | Midnapore Division | Ghatal Subdivision | Sinking of 250 X 150 mm dia. X 165 depth Tube well under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000015/2023-2024 | 935/MD | 04/04/2023 | 14 | MEHER ALI KHAN. | 8.3 | 0 | 100
159 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Rising main & 2 years operation & maintenance under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000080/2023-2024 | 2427/MD | 13/07/2023 | 952 | DEVJYOTI BERA | 29.63 | 0 | 47
160 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000081/2023-2024 | 2428/MD | 13/07/2023 | 45 | MALLICK ENTERPRISE | 9.89 | 0 | 0
161 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 100
162 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000040/2024-2025 | 3358/MD | 25/11/2024 | 0 | Resource Division | 2.94 | 0 | 0
163 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,225 nos.) under JJM with allied work for Dwandbipur PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000035/2023-2024 | 1337/MD | 28/04/2023 | 884 | M/S. D.K.H.CONSTRUCTION | 460.32 | 0 | 35
164 | Midnapore Division | Ghatal Subdivision | Laying additional distribution system pipe line for Dwandbipur W/S Scheme under JJM within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000102/2024-2025 | 2848/MD | 09/09/2024 | 181 | M/S. D.K.H.CONSTRUCTION | 27.43 | 0 | 100
165 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Dwandbipur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000657/2022-2023 | 1755/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.94 | 0 | 100
166 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000032/2024-2025 | 3359/MD | 25/11/2024 | 0 | Resource Division | 13.71 | 0 | 0
167 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000056/2022-2023 | 62/MD | 09/01/2023 | 0 | Resource Division | 19.15 | 0 | 0
168 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
169 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000086/2022-2023 | 196/MD | 16/01/2023 | 0 | Resource Division | 7.32 | 0 | 0
170 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000125/2024-2025 | 3461/MD | 25/11/2024 | 0 | Resource Division | 10.39 | 0 | 0
171 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000068/2023-2024 | 1278/MD | 28/04/2023 | 0 | Resource Division | 21.02 | 0 | 0
172 | Midnapore Division | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF AMDA PWSS. REF CONSUMER ID-204283798, APPLICATION NO-2004695716, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KESHIARY CCC, NAME OF BLOCK-KESHIARY | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00551/2024-2025 | BP-2024-25-458 | 12/11/2024 | 0 | WBSEDCL | 13.84 | 0 | 0
173 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000115/2023-2024 | 1306/MD | 28/04/2023 | 0 | Resource Division | 27.48 | 0 | 0
174 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
175 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000048/2023-2024 | 1188/MD | 26/04/2023 | 0 | Resource Division | 27.58 | 0 | 0
176 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000054/2023-2024 | 1193/MD | 26/04/2023 | 0 | Resource Division | 5 | 0 | 0
177 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000247/2020-2021 | 1446/MD | 26/11/2020 | 180 | MIDNAPUR PIPE CONCERN | 48.96 | 0 | 0
178 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000516/2022-2023 | 2534/MD | 12/12/2022 | 14 | MIDNAPUR PIPE CONCERN | 7 | 0 | 50
179 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | VCH/000751/2020-2021 |  | 15/12/2020 | 0 | MIDNAPUR PIPE CONCERN | 10 | 0 | 0
180 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Khanjapur W/S Scheme, Block: - Daspur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | VCH/001875/2021-2022 | 8443244 | 29/03/2022 | 0 | MIDNAPUR PIPE CONCERN | 10 | 0 | 0
181 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Birsingha, Block - Ghatal) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000121/2021-2022 | 1011/MD | 25/06/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 3.25 | 0 | 0
182 | Midnapore Division | Ghatal Subdivision | Laying distribution pipeline, providing FHTC including Sinking of 250mm X 150mm X 190 m deep tube well for Augmentation of Birsingha Water Supply Scheme within Ghatal block under Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000501/2022-2023 | 2412/MD | 25/11/2022 | 745 | DIPAK KUMAR BAKLY | 91 | 0 | 90
183 | Midnapore Division | Ghatal Subdivision | Special Exigent Repair of Head work site & its adjoining structures of Birsingha W/S Scheme in consultation with district administration in the model village of Birsingha (Birth place of Iswarchandra Vidyasagar) under Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000536/2022-2023 | 2605/MD | 20/12/2022 | 15 | HIRAK KUMAR GHOSH | 9.99 | 0 | 94
184 | Midnapore Division | Ghatal Subdivision | Laying additional pipe line, interconnection, FHTC & other allied works for continuation of laying distribution system, sinking of tube well, FHTC for Augmentation of Birsingha W/S Scheme within Ghatal block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000638/2023-2024 | 138/MD | 18/01/2024 | 401 | DIPAK KUMAR BAKLY | 29.75 | 0 | 90
185 | Midnapore Division | Ghatal Subdivision | Special Exigent Repair of Head work site & its adjoining structures of Birsingha W/S Scheme in consultation with district administration in the model village of Birsingha (Birth place of Iswarchandra Vidyasagar) under Ghatal Sub-Division of Midnapore Division, PHE Dte. [PHASE-II] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000669/2022-2023 | 722/MD | 09/03/2023 | 21 | PULLOCK KUMAR GHOSH | 14.3 | 0 | 100
186 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000039/2024-2025 | 3366/MD | 25/11/2024 | 0 | Resource Division | 0.83 | 0 | 0
187 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000205/2023-2024 | 1421/MD | 04/05/2023 | 0 | Resource Division | 18.02 | 0 | 0
188 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
189 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000047/2023-2024 | 1187/MD | 26/04/2023 | 0 | Resource Division | 81.82 | 0 | 0
190 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube wells Laying distribution pipe line, Pump House, Soil investigation, Construction of 300 cum OHR (Pile Foundation) & Accommodate FHTC (164 Nos.) under JJM with allied work for Augmentation of Baita PWSS in Mohanpur block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000175/2024-2025 | 3158/MD | 04/10/2024 | 180 | SUBRATA DAS | 231.09 | 0 | 0
191 | Midnapore Division | Midnapur Mechanical Sub Division-I | Repair & renovation of switch room cum chlorine room at 1st Tube well site of Baita Pipe Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000472/2024-2025 | 437/AE/HQ/MD | 07/02/2025 | 30 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 1.07 | 0 | 100
192 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of additional distribution pipe line, Rising main including interconnection of Tube well No. 2 and Construction of Sluice Valve Chamber including Supply of CIDF Sluice Valve for Augmentation of Baita PWSS within Mohanpur block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000763/2023-2024 | 375/MD | 12/02/2024 | 45 | A-PLUS | 22.32 | 0 | 0
193 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baita, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001470/2020-2021 | 565/MD | 16/03/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.16 | 0 | 100
194 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000155/2022-2023 | 538/MD | 21/02/2023 | 0 | Resource Division | 28.21 | 0 | 0
195 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,033 nos.) under JJM with allied work including 02 (Two) years Operation & Maintenance for Markha PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000223/2023-2024 | 2923/MD | 16/08/2023 | 927 | DULAL CHANDRA DAS | 812.19 | 0 | 47
196 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000016/2023-2024 | 1165/MD | 26/04/2023 | 0 | Resource Division | 107.5 | 0 | 0
197 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000036/2023-2024 | 1178/MD | 26/04/2023 | 0 | Resource Division | 26.89 | 0 | 0
198 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000081/2023-2024 | 1230/MD | 27/04/2023 | 0 | Resource Division | 26.85 | 0 | 0
199 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000267/2023-2024 | 2225/MD | 15/06/2023 | 0 | Resource Division | 26.2 | 0 | 0
200 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Gholshahi & (ii) Krishnaballavpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000241/2021-2022 | 1308/MD | 12/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.16 | 0 | 0
201 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Gholshahi (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000638/2022-2023 | 556/MD | 22/02/2023 | 465 | KISHORE GHOSH | 45.54 | 0 | 70
202 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Gholshahi (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000639/2022-2023 | 557/MD | 22/02/2023 | 465 | KISHORE GHOSH | 41.91 | 0 | 50
203 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000043/2024-2025 | 3352/MD | 25/11/2024 | 0 | Resource Division | 2.41 | 0 | 0
204 | Midnapore Division | Ghatal Subdivision | Laying additional pipeline to provide balance FHTC under JJM in Bachhrakundu PWSS under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000038/2024-2025 | 2218/MD | 19/07/2024 | 45 | ASHOK BANERJEE | 28.06 | 0 | 0
205 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (280 Nos.) under JJM with allied work for Augmentation of Bacchra Kundu Pipe W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000136/2023-2024 | 2620/MD | 24/07/2023 | 60 | ASHOK BANERJEE | 52.8 | 0 | 0
206 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 0 | 100
207 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 0 | 100
208 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000196/2023-2024 | 1418/MD | 04/05/2023 | 0 | Resource Division | 2.93 | 0 | 0
209 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting of Ground Water Based Water Supply Scheme for Rohini PWSS to Accommodate FHTC in Block - Sankrail under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000254/2021-2022 | 1526/MD | 10/09/2021 | 60 | ASIS KUMAR SARANGI | 136.63 | 0 | 0
210 | Midnapore Division | Gopiballavpur Sub Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rohini PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000272/2021-2022 | 61/JSD | 18/06/2021 | 14 | ROY CHOWDHURY ASSOCIATES | 4.38 | 0 | 1
211 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
212 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000017/2023-2024 | 1160/MD | 25/04/2023 | 0 | Resource Division | 31.04 | 0 | 0
213 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
214 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000025/2023-2024 | 1169/MD | 26/04/2023 | 0 | Resource Division | 12.88 | 0 | 0
215 | Midnapore Division | Ghatal Subdivision | Sinking of Tube wells, Construction of 450 CuM Capacity R.C.C Over Head Reservoirs (Over Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6507) for Bagchhari & Mangrul Pipe W/S Scheme including Two years O&M within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000209/2023-2024 | 2825/MD | 07/08/2023 | 783 | GOBINDA MAITY | 1766.48 | 0 | 70
216 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000006/2024-2025 | 3327/MD | 25/11/2024 | 0 | Resource Division | 8.98 | 0 | 0
217 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000284/2023-2024 | 4058/MD | 12/10/2023 | 0 | Resource Division | 40.25 | 0 | 0
218 | Midnapore Division | Ghatal Subdivision | Laying of Rising main & interconnection for Maheshpur & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000473/2024-2025 | 459/MD | 11/02/2025 | 45 | DULAL CHANDRA DAS | 10.5 | 0 | 0
219 | Midnapore Division | Ghatal Subdivision | Installation of Display Board for JJM work at different Piped Water Supply Scheme under different block within Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000784/2023-2024 | 506/MD | 27/02/2024 | 10 | PULLOCK KUMAR GHOSH | 0.96 | 0 | 100
220 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000066/2022-2023 | 72/MD | 09/01/2023 | 0 | Resource Division | 34.76 | 0 | 0
221 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000187/2023-2024 | 1508/MD | 12/05/2023 | 0 | Resource Division | 12.26 | 0 | 0
222 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Shaldahara PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000459/2024-2025 | 375/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 12.25 | 0 | 0
223 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000156/2023-2024 | 1302/MD | 28/04/2023 | 0 | Resource Division | 20.4 | 0 | 0
224 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
225 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Dhuipara & its adjoining Mouzas PWSS AND (2) Nilda & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000742/2022-2023 | 818/MD | 21/03/2023 | 30 | ENVIROTECH SOLUTIONS | 7.66 | 0 | 100
226 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000161/2023-2024 | 1452/MD | 08/05/2023 | 0 | Resource Division | 21.57 | 0 | 0
227 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
228 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000160/2023-2024 | 1453/MD | 08/05/2023 | 0 | Resource Division | 23.16 | 0 | 0
229 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of distribution, Rising main & Accommodate balance FHTC (70 Nos.) including 2 years O & M under JJM with allied work for Augmentation of Dhamsai & its adjoining mouzas W/S scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Medinipur Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000176/2023-2024 | 2716/MD | 31/07/2023 | 790 | M/S. D.K.H.CONSTRUCTION | 118.46 | 0 | 0
230 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhamsai, Block - Keshpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/001089/2021-2022 | 1113/MD | 09/07/2021 | 10 | CIVIL FOUNDATION ENGINEERING | 1.29 | 0 | 100
231 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000185/2023-2024 | 1394/MD | 03/05/2023 | 0 | Resource Division | 16.27 | 0 | 0
232 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 250 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (1,871 Nos.) including Two years O&M under JJM with allied work for Dakshin Parshura & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000232/2023-2024 | 2956/MD | 17/08/2023 | 902 | M/S. D.K.H.CONSTRUCTION | 728.65 | 0 | 15
233 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000051/2024-2025 | 3371/MD | 25/11/2024 | 0 | Resource Division | 11.53 | 0 | 0
234 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube wells, Construction of 400 CuM Capacity R.C.C Over Head Reservoirs (Over Raft / Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6,875 Nos.) for Jagannathchak & Barbasi Pipe W/S Scheme including 2 years O&M within Kharagpur-II Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000248/2023-2024 | 3101/MD | 25/08/2023 | 772 | GOBINDA MAITY | 1932.69 | 0 | 25
235 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000242/2023-2024 | 1529/MD | 12/05/2023 | 0 | Resource Division | 308.47 | 0 | 0
236 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000091/2023-2024 | 2465/MD | 14/07/2023 | 808 | GOBINDA MAITY | 1571.51 | 0 | 42
237 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000089/2024-2025 | 3441/MD | 25/11/2024 | 0 | Resource Division | 21.6 | 0 | 0
238 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000100/2022-2023 | 181/MD | 16/01/2023 | 0 | Resource Division | 48.33 | 0 | 0
239 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Shila Rajnagar & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000653/2022-2023 | 1751/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.97 | 0 | 100
240 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000038/2024-2025 | 3365/MD | 25/11/2024 | 0 | Resource Division | 17.22 | 0 | 0
241 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000063/2022-2023 | 71/MD | 09/01/2023 | 0 | Resource Division | 15.92 | 0 | 0
242 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,311 Nos.) under JJM with allied work for Kashinathpur & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000383/2023-2024 | 5057/MD | 26/10/2023 | 883 | DULAL CHANDRA DAS | 602 | 0 | 25
243 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000029/2024-2025 | 3348/MD | 25/11/2024 | 0 | Resource Division | 14.24 | 0 | 0
244 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000032/2022-2023 | 75/MD | 09/01/2023 | 0 | Resource Division | 22.89 | 0 | 0
245 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000470/2023-2024 | 5382/MD | 04/12/2023 | 574 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 50
246 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000202/2023-2024 | 1412 | 04/05/2023 | 0 | Resource Division | 24.76 | 0 | 0
247 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 & 300 cum OHRs (Intze type with pile foundation) & Accommodate FHTC(5,344 Nos.) under JJM with allied work for Goura (Zone-I,II,III & IV) & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000384/2023-2024 | 5058/MD | 26/10/2023 | 973 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1390.82 | 0 | 30
248 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000028/2024-2025 | 3347/MD | 25/11/2024 | 0 | Resource Division | 32.92 | 0 | 0
249 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000041/2022-2023 | 109/MD | 10/01/2023 | 0 | Resource Division | 41.59 | 0 | 0
250 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,915) under JJM with allied work for KALLA PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000251/2023-2024 | 3146/MD | 29/08/2023 | 180 | SATYABRATA CHAKRABORTY | 792.07 | 0 | 0
251 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | RTOR000250/2023-2024 | 1585/MD | 15/05/2023 | 0 | Resource Division | 85.7 | 0 | 0
252 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
253 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Gopal Bandh & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 435 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000414/2024-2025 | 195/MD | 17/01/2025 | 45 | M/S. S.S. ENTERPRISE | 5.73 | 0 | 0
254 | Midnapore Division | Midnapur Sadar Sub-Division | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, (HQ) Midnapur Division PHE Dte.for12(twelve)months.(Period From-01.01.2024 to 31.12.2024) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000580/2023-2024 | 925/AE/MSSD | 13/12/2023 | 366 | NAFISA ENTERPRISE | 1.73 | 0 | 0
255 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000061/2024-2025 | 3381/MD | 25/11/2024 | 0 | Resource Division | 17 | 0 | 0
256 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum (Intze type with Pile Foundation) OHR & Accommodate FHTC (2,792 Nos.) including 02(Two) years O&M under JJM with allied work for Khari Gerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000385/2023-2024 | 5059/MD | 26/10/2023 | 700 | M/S. CARE | 871.34 | 0 | 35
257 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000255/2023-2024 | 1589/MD | 15/05/2023 | 0 | Resource Division | 34.55 | 0 | 0
258 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000184/2020-2021 | 1412/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 36.77 | 27.31 | 80
259 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Alampur PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000201/2020-2021 | 1398/MD | 26/11/2020 | 180 | ASHIM KUMAR DEY | 50.2 | 50.18 | 0
260 | Midnapore Division | Jhargram Sub-Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN 1NO.PWSS WITHIN GOPIBALLAVPUR-1&2 NOS PWSS WITHIN GOPIBALLAVPUR-II | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000612/2021-2022 | 844310 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 0.82 | 0 | 0
261 | Midnapore Division | Jhargram Sub-Division | Extension of Distribution pipe line for left out Habitation in Phul Baria Mouza (0264) in connection with FHTC under Alampur W/S Scheme within Gopiballavpur-I Block Under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001201/2021-2022 | 844350 | 09/12/2021 | 0 | ASIM KUMAR DEY. | 2.67 | 0 | 0
262 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Nakrasuli PWSS of Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000193/2020-2021 | 1419/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 4.81 | 4.36 | 0
263 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Ragra PWSS of Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer Sankrail block | ORD/000199/2020-2021 | 1402/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 60.82 | 46.98 | 1
264 | Midnapore Division | Gopiballavpur Sub Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN 2NOS.PWSS WITHIN SANKRAIL | Assistant Engineer | Junior Engineer Sankrail block | VCH/000610/2021-2022 | 84439 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 0.8 | 0 | 0
265 | Midnapore Division | Ghatal Subdivision | Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at The Head work site Midnapore Divison , PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | BILL/00729/2022-2023 | 8443129 | 31/03/2023 | 0 | M/S. OXFORD SECURITY SERVICE | 1.03 | 0 | 0
266 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000209/2020-2021 | 1430/MD | 26/11/2020 | 180 | DIPAK KUMAR DOLAI | 94.96 | 70.49 | 0
267 | Midnapore Division | Ghatal Subdivision | Laying additional pipe line for retrofitting to accommodate FHTC under JJM in Harekrishnapur PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division PHE.Dte. (For the Villages- Mahabatpur, nabin Simla & Sridharpur) | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000460/2020-2021 | 82/AE/GSD | 25/02/2021 | 20 | SUBHASIS DOLAI | 4.78 | 9.63 | 0
268 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate balance FHTC under JJM in HAREKRISHNAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000655/2020-2021 | 450/MD | 26/02/2021 | 30 | SUBHASIS DOLAI | 13.85 | 13.15 | 0
269 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | VCH/000740/2020-2021 |  | 15/12/2020 | 0 | DIPAK KUMAR DOLAI | 98.16 | 0 | 0
270 | Midnapore Division | Midnapur Mechanical Sub Division-I | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000272/2020-2021 | 1469/MD | 26/11/2020 | 180 | HARIPADA PATTANAYAK | 83.93 | 33.53 | 100
271 | Midnapore Division | Midnapur Mechanical Sub Division-I | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000730/2020-2021 |  | 15/12/2020 | 0 | HARIPADA PATTANAYAK | 30 | 0 | 0
272 | Midnapore Division | Midnapur Mechanical Sub Division-I | FHTC imis data entry. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001623/2021-2022 | 8443150 | 24/03/2022 | 0 | PARTHA PRATIM PAL | 0.09 | 0 | 0
273 | Midnapore Division | Midnapur Mechanical Sub Division-I | FHTC imis data entry. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001624/2021-2022 | 8443150 | 24/03/2022 | 0 | RINTU SAMANTA | 0.05 | 0 | 0
274 | Midnapore Division | Midnapur Mechanical Sub Division-I | FHTC imis data entry. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001625/2021-2022 | 8443150 | 24/03/2022 | 0 | TANMOY BERA | 0.14 | 0 | 0
275 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-IV) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000237/2020-2021 | 1441/MD | 26/11/2020 | 180 | M/S. CARE | 52.92 | 0 | 0
276 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-IV) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000716/2020-2021 |  | 15/12/2020 | 0 | M/S. CARE | 7.86 | 0 | 0
277 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr, FHTC with allied work for Nabin Maheshpur & its adjoining mouzas W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000011/2022-2023 | 608/MD | 04/04/2022 | 819 | DIPAK KUMAR DOLAI | 210.12 | 0 | 100
278 | Midnapore Division | Kharagpur Sub-Division | Extension of Pipeline at Mouza Gourbar Muslim Para within Sabang Augmentation Water Supply Scheme (Zone-I) at Sabang Block for FHTC Work under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000063/2022-2023 | 490/AE/KSD | 01/08/2022 | 30 | PALASH KUMAR DAS | 4.7 | 0 | 0
279 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Sabang (Zone-I) PWSS under Sabang Block in Paschim Medinipur District. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000493/2021-2022 | 2186/MD | 17/12/2021 | 1111 | MASUM ALI KHAN | 53.37 | 0 | 100
280 | Midnapore Division | RWS Midnapur Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 Cum OHR (Intze type with solid Raft foundation) & Accommodate FHTC (1,486 nos.) under JJM with allied work for Gurguripal & its adjoining mouzas PWSS in Midnapore sadar Block including supply of all labour & materials including 02 (Two) years Operation & Maintenance under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000061/2024-2025 | 2657/MD | 29/08/2024 | 180 | CREATION CONSTRUCTION | 254.08 | 0 | 0
281 | Midnapore Division | Kharagpur Sub-Division | onstruction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Talda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00719/2022-2023 | BP-2022-23-407 | 01/02/2023 | 0 | MIDNAPUR PIPE CONCERN | 18.52 | 0 | 0
282 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Talda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000488/2021-2022 | 2181/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 32.63 | 0 | 10
283 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Dantardabatitaki, (ii) Fate Chak & (iii) Haripura of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000450/2021-2022 | 1277/MD | 05/08/2021 | 10 | GOBINDA MAITY | 4.36 | 0 | 0
284 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Dantardabatitaki, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000485/2021-2022 | 2178/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 26.09 | 0 | 90
285 | Midnapore Division | Kharagpur Sub-Division | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001815/2021-2022 | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.82 | 0 | 0
286 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Dhaneswarpur PWSS, Block - Pingla in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000532/2020-2021 | 416/MD | 26/02/2021 | 30 | GOBINDA MAITY | 71.49 | 70.09 | 100
287 | Midnapore Division | Kharagpur Sub-Division | Trial run of distribution system & rising main (CI/DI/HDPE/UPVC) with all related structure i.e.OHR etc. Dhaneswarpur and its adjoining mouza W/S Scheme within Pingla Block under Midnapore Division P.H.E. Dte. ( for 120 days). | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000674/2021-2022 | 112/AE/KSD | 09/03/2022 | 4 | GOBINDA MAITY | 1.14 | 0 | 0
288 | Midnapore Division | Kharagpur Sub-Division | Construction of Valve Chamber and Supplying, Fitting, Fixing G.I. Pipe including allied works at Paschim Pathri PWSS within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/000218/2022-2023 | 519/AE/KSD | 18/08/2022 | 30 | MAITY ENTERPRISE | 1.66 | 0 | 0
289 | Midnapore Division | Kharagpur Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Paschim Pathri PWSS to accommodate FHTC under JJM under Kharagpur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/000475/2021-2022 | 2169/MD | 17/12/2021 | 60 | MAITY ENTERPRISE | 48.5 | 0 | 0
290 | Midnapore Division | Kharagpur Sub-Division | Sinking of additional 150 X 100 mm dia. X 170 Mtr. Depth Rig bored Tube well for Paschim Pathri W/S Scheme under Kharagpur-I Dev. Block within Kharagpur Sub-Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/000502/2022-2023 | 2413/MD | 25/11/2022 | 7 | FIROJ KHAN | 5.47 | 0 | 100
291 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Paschim Pathri, Block - Kharagpur-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/000568/2020-2021 | 63/MD | 11/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.22 | 2.16 | 0
292 | Midnapore Division | Kharagpur Sub-Division | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-I) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000366/2021-2022 | 469/AE/KSD | 16/11/2021 | 30 | M/S. GEO | 4.81 | 0 | 100
293 | Midnapore Division | Kharagpur Sub-Division | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-II) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000367/2021-2022 | 470/AE/KSD | 16/11/2021 | 30 | M/S. GEO | 4.83 | 0 | 0
294 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Satkui PWSS, Block - Kharagpur-I in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000531/2020-2021 | 415/MD | 26/02/2021 | 30 | DULAL CHANDRA DAS | 61.89 | 0 | 0
295 | Midnapore Division | Kharagpur Sub-Division | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-IV) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000544/2021-2022 | 107/AE/KSD | 09/03/2022 | 30 | M/S. GEO | 4.61 | 0 | 0
296 | Midnapore Division | Kharagpur Sub-Division | Restoration of distribution pipe line of Satkui and its adjoining Mouza Water Supply Scheme Kharagpur-I Block in the district of Paschim Medinipur. (PART-III) | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000889/2021-2022 | 106/AE/KSD | 09/03/2022 | 30 | A-PLUS | 4.79 | 0 | 0
297 | Midnapore Division | Jhargram Sub-Division | Transfer to EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. PFMS bank account. |  | Junior Engineer-III | BILL/00727/2022-2023 | BP-2022-23-690 | 10/03/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 9.21 | 0 | 0
298 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Dhamro PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-III | ORD/000275/2021-2022 | 102/JSD | 13/07/2021 | 14 | M/S R. DUTTA & CO | 1.59 | 0 | 1
299 | Midnapore Division | Jhargram Sub-Division | Retrofitting and allied works to accommodate FHTC under JJM in Dhamro PWSS within Binpur-I Block under Jhargram Division, PHE Dte. |  | Junior Engineer-III | ORD/000283/2021-2022 | 1690/MD | 30/09/2021 | 15 | SAIKAT DANDAPAT | 33.29 | 0 | 1
300 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting and allied works to accommodate FHTC under JJM in Sasarah PWSS within Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | ORD/000265/2021-2022 | 1606/MD | 17/09/2021 | 21 | SUNIL DULE | 44.65 | 32.74 | 1
301 | Midnapore Division | Gopiballavpur Sub Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Sasarah PWSS in Gopiballavpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer Gopiballavpur-I block | VCH/001378/2021-2022 | BP-2021-22-370 | 23/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 1.8 | 0 | 0
302 | Midnapore Division | Midnapur Mechanical Sub Division-I | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00239/2022-2023 |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0
303 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. (Consultancy work) in connection with the Proposed Mini Pipe W/S Scheme for Chaulkuri mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000420/2021-2022 | 1334/MD | 18/08/2021 | 10 | GOBINDA MAITY | 3.06 | 0 | 0
304 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
305 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000903/2021-2022 | 521/MD | 21/03/2022 | 150 | USHA CONCERN | 44.75 | 0 | 92
306 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000904/2021-2022 | 522/MD | 21/03/2022 | 150 | BISWAJIT BAG | 42.43 | 0 | 100
307 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-III), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000905/2021-2022 | 523/MD | 21/03/2022 | 150 | BISWAJIT BAG | 49.24 | 0 | 100
308 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chaulkuri (Zone-IV), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000906/2021-2022 | 524/MD | 21/03/2022 | 150 | BISWAJIT BAG | 38.24 | 0 | 0
309 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000015/2021-2022 | 2126/MD | 14/12/2021 | 0 | Resource Division | 5.54 | 0 | 0
310 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001697/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.54 | 0 | 0
311 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001819/2021-2022 | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 15.57 | 0 | 0
312 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of Rising main & interconnection pipeline for Amjor & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length - 675.00 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000052/2024-2025 | 2449/MD | 08/08/2024 | 45 | ASHIM KUMAR DEY | 5.41 | 0 | 50
313 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations (250 CuM) under Amjor & its adjoining mouzas W/S scheme within Garhbeta-II block in Paschim Medinipur District through Jadavpur University. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000126/2022-2023 | 1285/MD | 27/06/2022 | 7 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0
314 | Midnapore Division | Midnapur Sadar Sub-Division | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000185/2023-2024 | 403/AE/MSSD | 14/07/2023 | 366 | PULLOCK KUMAR GHOSH | 4.65 | 0 | 60
315 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of R.C.C. Over Head Reservoir of capacity 250 Cum and staging height 20.00 mtr., Pump House (5.40 mtr X 3.60 mtr), Boundary wall including Sinking of 250 X 200 mm dia. X 200 Mtr. depth deep Tube well & FHTC under JJM with allied work for AMJOR & its adjoining mouzas W/S Scheme in Garhbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Part-B) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000307/2022-2023 | 1878/MD | 09/09/2022 | 180 | ASHIM KUMAR DEY | 152.15 | 0 | 30
316 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Construction of Pump House (3.6 mtr X 3.00 mtr.) & Boundary wall including Sinking of 250 X 200 mm dia. X 200 Mtr. depth deep Tube well under JJM with allied work for AMJOR and its adjoining mouzas W/S Scheme in Garhbeta -II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. (Part-A) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000543/2022-2023 | 2674/MD | 30/12/2022 | 60 | ASHIM KUMAR DEY | 169.73 | 0 | 10
317 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation work order for Hire charges for hiring of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 06 ( Six) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer ,Midnapore Sadar Sub-Division under Midnapur Division PHE Dte. (period from 01.01.2023 to 30.06.2023) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000768/2022-2023 | 762/AE/MSSD | 30/12/2022 | 182 | M/S. ZAMAN ENTERPRISE | 1.01 | 0 | 50
318 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work order for Hire charges for hiring of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 05 (Five) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer ,Midnapore Sadar Sub-Division under Midnapur Division PHE Dte.(Preferably it would be used only the 'Jal Swapna 'Program inaugurated by Honorable C.M) upto 15.07.2023 | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000769/2022-2023 | 865/AE/MSSD | 10/02/2023 | 150 | SANJIT SINHA | 0.84 | 0 | 80
319 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000024/2022-2023 | 134/MD | 11/01/2023 | 0 | Resource Division | 8.33 | 0 | 0
320 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000116/2022-2023 | 245/MD | 18/01/2023 | 0 | Resource Division | 17.74 | 0 | 0
321 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Chandipur PWSS under Daspur-I Block in Paschim Medinipur District. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000405/2021-2022 | 2004/MD | 01/12/2021 | 45 | M/S. EL-CON | 79.5 | 0 | 0
322 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kapasda (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000226/2022-2023 | 1733/MD | 23/08/2022 | 60 | SUNIL DULE | 71.9 | 0 | 100
323 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Kapasda PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000433/2021-2022 | 1666/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.25 | 0 | 100
324 | Midnapore Division | Midnapur Sadar Sub-Division | Electric Quotation Bill. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00175/2023-2024 |  | 15/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.84 | 0 | 0
325 | Midnapore Division | Midnapur Sadar Sub-Division | Restoration of damage shoulder & flank etc to the different roads under Midnapore Highway Division (Damage caused during laying pipe line by public Health Engineering Department. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00368/2022-2023 |  | 19/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 138 | 0 | 0
326 | Midnapore Division | Midnapur Sadar Sub-Division | PWD road challan | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00704/2022-2023 | BP-2022-23-704 | 23/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 90 | 0 | 0
327 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshpur W/S Scheme with in Keshpur Block under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02162/2023-2024 | BP-2023-24-514 | 20/12/2023 | 0 | M/S. A.R. ENTERPRISE | 1.84 | 0 | 0
328 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 550 Cum and staging height 20.00 mtr. with allied work for Augmentation of Keshpur and its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000229/2022-2023 | 1722/MD | 22/08/2022 | 1269 | M/S. A.R. ENTERPRISE. | 605.9 | 0 | 80
329 | Midnapore Division | Midnapur Sadar Sub-Division | Additional distribution pipe line under JJM with allied works for Augmentation of Keshpur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000403/2023-2024 | 5105/MD | 31/10/2023 | 60 | M/S. A.R. ENTERPRISE | 52.81 | 0 | 80
330 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshpur W/S Scheme with in Keshpur Block under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000571/2022-2023 | 121/MD | 10/01/2023 | 30 | M/S. A.R. ENTERPRISE. | 41.34 | 0 | 70
331 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Keshpur (Block-Keshpur) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001036/2021-2022 | 1644/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.04 | 0 | 0
332 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000015/2022-2023 | 2322/MD | 17/11/2022 | 0 | Resource Division | 23.96 | 0 | 0
333 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000019/2022-2023 | 2473/MD | 06/12/2022 | 0 | Resource Division | 41.87 | 0 | 0
334 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keshpur, Block - Keshpur) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001421/2021-2022 | BP-2021-22-397 | 22/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 0 | 0
335 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric quotation for KHASBAZAR Water Supply Scheme T/W-(Ref. ID - 204024556) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00545/2023-2024 | BP-2023-24-288 | 31/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.53 | 0 | 0
336 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Water Supply Scheme of Khasbazar (Part) to accommodate FHTC under JJM within Debra Dev. Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000185/2022-2023 | 1484/MD | 26/07/2022 | 60 | SHAKEEL KHAN | 57.44 | 0 | 100
337 | Midnapore Division | Midnapur Mechanical Sub Division-I | Cleaning the Chokage of pipe in the existing line at Khasbazar PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000312/2024-2025 | 3405/MD | 25/11/2024 | 21 | SUBRATA DAS | 4.53 | 0 | 100
338 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Khasbazar PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000434/2021-2022 | 1667/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.28 | 0 | 100
339 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Ragra PWSS of Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | ORD/000199/2020-2021 | 1402/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 60.82 | 0 | 1
340 | Midnapore Division | Gopiballavpur Sub Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rogra PWSS in Sankrail Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | VCH/000306/2022-2023 | BP-2022-23-96 | 04/06/2022 | 0 | RADIANT | 1.86 | 0 | 0
341 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bural (Zone-II) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000269/2020-2021 | 1466/MD | 26/11/2020 | 1887 | BANERJEE CONSTRUCTION | 97 | 46.9 | 100
342 | Midnapore Division |  | Sinking of 250mm X 150mm dia. & depth 135 Mtr. Rig bore Tube well (Replacement) for Augmentation of Khasjungal W/S Scheme within Binpur-I block under Jhargram Division, PHE Dte. |  |  | ORD/000016/2022-2023 | 613/MD | 04/04/2022 | 15 | TAPAS KUMAR GIRI | 6.13 | 0 | 1
343 | Midnapore Division |  | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khasjungle PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001383/2021-2022 | BP-2021-22-409 | 23/02/2022 | 0 | RADIANT | 1.35 | 0 | 0
344 | Midnapore Division | Jhargram Sub-Division | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well for Augmentation of Chichira W/S Scheme under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000018/2022-2023 | 615/MD | 04/04/2022 | 15 | NRIPENDRA NATH SINGHA | 6.58 | 0 | 0
345 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Chichira PWSS in Jamboni Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | VCH/001385/2021-2022 | BP-2021-22-394 | 22/02/2022 | 0 | RADIANT | 1.38 | 0 | 0
346 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of pipe line damaged due to construction of concrete road at Kholageria village & excess length of pipe in connection with FHTC work at Chandkuri (Zone I) W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000078/2022-2023 | 1067/MD | 03/06/2022 | 21 | DULAL CHANDRA DAS | 19.68 | 0 | 80
347 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of pipe line damaged due to construction of road at Chandkuri market & excess pipeline in connection with FHTC work at Chandkuri (Zone II) W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000079/2022-2023 | 1068/MD | 03/06/2022 | 21 | DULAL CHANDRA DAS | 24.23 | 0 | 80
348 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Zone-I) (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000206/2022-2023 | 1671/MD | 12/08/2022 | 45 | DULAL CHANDRA DAS | 44.9 | 0 | 80
349 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Chandkuri (Zone-II) (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000207/2022-2023 | 1672/MD | 12/08/2022 | 45 | DULAL CHANDRA DAS | 50.82 | 0 | 100
350 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Chandkuri PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000430/2021-2022 | 1662/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.33 | 0 | 100
351 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of Rising Main including interconnection for Sabra and its adjoining mouzas Water Supply Scheme within Dantan-II Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000639/2023-2024 | 139/MD | 18/01/2024 | 30 | GOBINDA MAITY | 8.07 | 0 | 0
352 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Sabra & its adjoining Mouzas, Block: - Dantan-II, District: - Paschim Midnapore. (Total Length = 15,893.00 Mtr.) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000663/2022-2023 | 676/MD | 02/03/2023 | 60 | GOBINDA MAITY | 78.34 | 0 | 0
353 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000096/2023-2024 | 1285/MD | 28/04/2023 | 0 | Resource Division | 22.66 | 0 | 0
354 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000123/2022-2023 | 336/MD | 31/01/2023 | 0 | Resource Division | 84.48 | 0 | 0
355 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000135/2023-2024 | 1259/MD | 28/04/2023 | 0 | Resource Division | 23.52 | 0 | 0
356 | Midnapore Division | Midnapur Sadar Sub-Division | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub-Division under Midnapur Division PHE Dte. (Period From 15.07.2023 to 14.07.2024) Note :- The vehicle will normally engaged on the all working days ,including all exigency duty and normal disaster. The working days might be enhanced as per additional portfolio entrusted to the dedicated officer . no protest by the vehicle owner will be entertained. the vehicle may be called for (24 x 7) in case of any exigency like Covid19, natural cyclone etc. Fuel-HSD=1Litre/12KM Fuel-Mobil-1Litre/500KM | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000186/2023-2024 | 404/AE/MSSD | 14/07/2023 | 366 | M/S. ZAMAN ENTERPRISE | 1.79 | 0 | 0
357 | Midnapore Division | Midnapur Sadar Sub-Division | Hire charges of 1 no Motor Cab ( standard ) Commercial with Catalytic Converter attachment with Bharat stage as per prevalent applicable standard compliant new / not old than 30 ( Thirty ) months from the date of 1st. registration on daily hire rate basis for 12 ( Twelve) months only having contract carriage permit for plying with in West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub-Division PHE Dte. (Preferably it would be used only for the JJM Programme for Period of 01 year). | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000467/2023-2024 | 487/AE/MSSD | 08/08/2023 | 366 | SANJIT SINHA | 1.91 | 0 | 0
358 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000063/2023-2024 | 1212/MD | 27/04/2023 | 0 | Resource Division | 53.41 | 0 | 0
359 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (250 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000104/2023-2024 | 2486/MD | 17/07/2023 | 659 | GOUTAM RAY | 47.26 | 0 | 70
360 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Two nos. 250 X 150 mm dia. X 160 mtr. depth deep tube well by direct rotary method under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000111/2023-2024 | 2512/MD | 18/07/2023 | 21 | FIROJ KHAN | 16.16 | 0 | 100
361 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 250 CuM OHR (Intez type with solid raft) & Accommodate FHTC (435 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000176/2024-2025 | 3159/MD | 04/10/2024 | 540 | D M CONSTRUCTION | 107.46 | 0 | 0
362 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (250 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000242/2023-2024 | 3097/MD | 25/08/2023 | 60 | PULLOCK KUMAR GHOSH | 46.42 | 0 | 10
363 | Midnapore Division | Midnapur Sadar Sub-Division | Construction Pump House, Boundary wall & Accommodate FHTC (350 Nos.) under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000268/2023-2024 | 3242/MD | 11/09/2023 | 842 | MIDNAPUR PIPE CONCERN | 53.54 | 0 | 51
364 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Rising main, Laying distribution pipe line, & Accommodate FHTC (450 Nos.) including 2 years O & M under JJM with allied work for Karnagar PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000269/2023-2024 | 3243/MD | 11/09/2023 | 60 | ASHIM KUMAR DEY | 185.94 | 0 | 10
365 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000179/2023-2024 | 1358/MD | 02/05/2023 | 0 | Resource Division | 29.51 | 0 | 0
366 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000470/2023-2024 | 5382/MD | 04/12/2023 | 574 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 50
367 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000201/2023-2024 | 1411 | 04/05/2023 | 0 | Resource Division | 35.33 | 0 | 0
368 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
369 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000014/2023-2024 | 1159/MD | 25/04/2023 | 0 | Resource Division | 24.02 | 0 | 0
370 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
371 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000075/2023-2024 | 1219/MD | 27/04/2023 | 0 | Resource Division | 26.64 | 0 | 0
372 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000138/2023-2024 | 1255/MD | 28/04/2023 | 0 | Resource Division | 20.96 | 0 | 0
373 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
374 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
375 | Midnapore Division | Kharagpur Sub-Division | Hiring of 1 (One) Motor Cab (Standard) commercial with Catalytic Converter attachment with Bharat Stage as per prevalent application standard compliant new/not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from the Regional Transport Authority for the use of the Assistant Engineer (H/Q), Midnapore Division, P.H.E. Dte. for the period of 05 (Five) months from 01.01.2025 to 31.05.2025. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001086/2024-2025 | 3838/AE/HQ/MD | 27/12/2024 | 151 | NAFISA ENTERPRISE | 0.72 | 0 | 0
376 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000220/2023-2024 | 1482 | 10/05/2023 | 0 | Resource Division | 36.86 | 0 | 0
377 | Midnapore Division | Kharagpur Sub-Division | Continuation Work Order for "Hiring of 1 (One) Motor Cab (Standard) commercial with Catalytic Converter attachment with Bharat Stage as per prevalent application standard compliant new/not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from the Regional Transport Authority for the use of the Assistant Engineer (H/Q), Midnapore Division, P.H.E. Dte. for the period of 05 (Five) months from 01.06.2025 to 31.10.2025." | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000218/2025-2026 | 1231/AE/HQ/MD | 27/05/2025 | 150 | NAFISA ENTERPRISE | 0.71 | 0 | 0
378 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
379 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000095/2022-2023 | 184/MD | 16/01/2023 | 0 | Resource Division | 14.27 | 0 | 0
380 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000113/2024-2025 | 3449/MD | 25/11/2024 | 0 | Resource Division | 12.04 | 0 | 0
381 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
382 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000239/2023-2024 | 1520/MD | 12/05/2023 | 0 | Resource Division | 29.35 | 0 | 0
383 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000107/2023-2024 | 1241/MD | 27/04/2023 | 0 | Resource Division | 24.53 | 0 | 0
384 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well (2nd), Construction of Pump House & Laying rising main pipeline for Augmentation of Gobardhanpur PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000329/2024-2025 | 3572/MD | 06/12/2024 | 300 | ARNAB PATRA | 12.74 | 0 | 50
385 | Midnapore Division | Kharagpur Sub-Division | Construction of approach road (concrete road) for Augmentation of Gobardhanpur PWSS Head Work Site at Ratrapur in Pingla Block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000442/2024-2025 | 348/MD | 30/01/2025 | 330 | M/S BAKLY CONSTRUCTION | 6.1 | 0 | 1
386 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall with allied work for Augmentation of Gobardhanpur & its adjoining mouzas W/S Scheme in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000504/2022-2023 | 2517/MD | 09/12/2022 | 1142 | DIPAK KUMAR BAKLY | 159.48 | 0 | 10
387 | Midnapore Division | Kharagpur Sub-Division | Construction of 5.40 X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Augmentation of Gobardhanpur W/S Scheme in Pingla block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (Considering G.L. 1950 mm below Road Level) {Type-B}. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000825/2023-2024 | 706/MD | 12/03/2024 | 720 | CHANDAN YADAV | 7.21 | 0 | 50
388 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Gobardhanpur PWSS within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001011/2021-2022 | 530/MD | 21/03/2022 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.95 | 0 | 100
389 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000076/2022-2023 | 93/MD | 10/01/2023 | 0 | Resource Division | 12.24 | 0 | 0
390 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric quotation for PALASHI Water Supply Scheme T/W-(Ref. ID - 204024556) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00547/2023-2024 | BP-2023-24-286 | 31/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.24 | 0 | 0
391 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for Laying Balance Distribution Pipe line for Rejuvenation of Palashi and its adjoining mouzas Pipe Water Supply Scheme under Debra Block within Midnapore Division, P.H.E. Dte. (Total Length = 6,236.00 Mtr.) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000053/2023-2024 | 949/MD | 06/04/2023 | 45 | MASUM ALI KHAN | 28.34 | 0 | 100
392 | Midnapore Division | Midnapur Mechanical Sub Division-I | Retrofitting to accommodate FHTC under JJM in Palashi W/S Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000262/2020-2021 | 1459/MD | 26/11/2020 | 1496 | GOBINDA MAITY | 86.73 | 0 | 100
393 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall for Rejuvination of Palashi PWSS in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000568/2022-2023 | 118/MD | 10/01/2023 | 723 | MASUM ALI KHAN | 171.56 | 0 | 100
394 | Midnapore Division | Midnapur Mechanical Sub Division-I | Constructing and fitting fixing MS ladder in diff. level and painting OHR of Palashi and its adjoining mouza water supply scheme within Debra Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000679/2021-2022 | 109/AE/KSD | 09/03/2022 | 30 | GOUTAM PARIA | 4.23 | 0 | 100
395 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Additional Retrofitting to accommodate FHTC under JJM in Palashi Water Supply Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000752/2022-2023 | 709/MD | 06/03/2023 | 45 | GOBINDA MAITY | 31.01 | 0 | 100
396 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Palashi PWSS within Debra Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001007/2021-2022 | 517/MD | 17/03/2022 | 10 | GOBINDA MAITY | 2.81 | 0 | 100
397 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
398 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000084/2023-2024 | 1295/MD | 28/04/2023 | 0 | Resource Division | 26.26 | 0 | 0
399 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying Distribution pipe line under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000008/2024-2025 | 1902/MD | 20/06/2024 | 90 | ASHIM KUMAR DEY | 308.72 | 0 | 0
400 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
401 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube well, Laying of Rising main, Pump House, Boundary wall, Construction of 300 CuM OHR (Intze type with solid raft) & Accommodate FHTC (1942 Nos.) including 2 yrs. O & M under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000847/2023-2024 | 824/MD | 15/03/2024 | 180 | ASHIM KUMAR DEY | 231.98 | 0 | 0
402 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000154/2022-2023 | 537/MD | 21/02/2023 | 0 | Resource Division | 34.53 | 0 | 0
403 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000079/2023-2024 | 1228/MD | 27/04/2023 | 0 | Resource Division | 26.92 | 0 | 0
404 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Jheta Jamboni & its adjoining mouzas PWSS, Block - Keshpur, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 500 Mtr.). | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000003/2025-2026 | 918/MD | 08/04/2025 | 45 | JULFIKAR ALI KHAN | 5.6 | 0 | 0
405 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
406 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000047/2024-2025 | 3367/MD | 25/11/2024 | 0 | Resource Division | 15.78 | 0 | 0
407 | Midnapore Division | Ghatal Subdivision | Restoration of damage shoulder & flank etc to the different roads under Midnapore Highway Division (Damage caused during laying pipe line by public Health Engineering Department. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00368/2022-2023 |  | 19/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 138 | 0 | 0
408 | Midnapore Division | Ghatal Subdivision | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution pipe line and Rising main for IRPALA water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000175/2022-2023 | 400/AE/GSD | 11/07/2022 | 7 | M/S. GEO | 4.85 | 0 | 0
409 | Midnapore Division | Ghatal Subdivision | Construction of swith rooms and its boundary wall, laying rising main & accommodated FHTC etc. of Irpala Water Supply Scheme within Ghatal Block under Midnapore Division PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2022-2023 | 1677/MD | 12/08/2022 | 846 | DULAL CHANDRA DAS | 111.18 | 0 | 60
410 | Midnapore Division | Ghatal Subdivision | Construction of Retaining Wall at Head work site of IRPALA Water Supply Scheme under Ghatal Sub- Division PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000471/2023-2024 | 5384/MD | 04/12/2023 | 15 | A-PLUS | 6.31 | 0 | 0
411 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Soil test and Construction of R.C.C. Elevated Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied works including supply of all labour & materials of IRPALA & its adjoining mouzas Water Supply Scheme within Ghatal Dev. Block under Ghatal sub-division of Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000473/2021-2022 | 2167/MD | 17/12/2021 | 1617 | M/S. A.R. ENTERPRISE. | 291.14 | 0 | 70
412 | Midnapore Division | Ghatal Subdivision | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 200 Mtr. depth deep tube well by Direct Rotary Method for Head Work Site & 2nd tube well site of Irpala W/S Scheme with in Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000701/2021-2022 | 297/MD | 15/02/2022 | 15 | ANNAPURNA TUBEWELL WORKS | 20.56 | 0 | 100
413 | Midnapore Division | Ghatal Subdivision | River Crossing below river bed by laying HDPE pipe with bed and bank anchoring arrangement at nodal point (NP: 63 to 64) of Irpala W/S Scheme within Ghatal Block under Ghatal Sub- Division of Midnapore Division, PHE Dte. (Length = 100.00 Mtr.) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000918/2021-2022 | 537/MD | 22/03/2022 | 21 | M/S. A.R. ENTERPRISE. | 11.39 | 0 | 100
414 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000027/2022-2023 | 2508/MD | 09/12/2022 | 0 | Resource Division | 48.91 | 0 | 0
415 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Installation of 10 Cum Capacity PVC Over Head Reservoir works with laying rising main, distribution system, Sinking of Tube well, Pump House & Providing FHTC (102 Nos.) with 1 year O&M for Barbhuna Basan PWSS within Debra block under Kharagpur Sub Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000041/2024-2025 | 2256/MD | 23/07/2024 | 282 | BLUE BIRD | 44.33 | 0 | 50
416 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000174/2023-2024 | 1357/MD | 02/05/2023 | 0 | Resource Division | 0.63 | 0 | 0
417 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000121/2023-2024 | 1307/MD | 28/04/2023 | 0 | Resource Division | 23.16 | 0 | 0
418 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of different capacity R.C.C. Over Head Reservoir Pile / Raft Foundation works with Laying rising main, Distribution system, Sinking of Tube well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,137 Nos.) including 1 year operation & maintenance for Gopinathpur Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. under Paschim Medinipur district. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000037/2023-2024 | 1340/MD | 28/04/2023 | 180 | SUJATA CONSTRUCTION | 367.16 | 0 | 45
419 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
420 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 20
421 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000066/2023-2024 | 1280/MD | 28/04/2023 | 0 | Resource Division | 28.62 | 0 | 0
422 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
423 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000709/2022-2023 | 834/MD | 22/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0
424 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000223/2023-2024 | 1483 | 10/05/2023 | 0 | Resource Division | 36.49 | 0 | 0
425 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
426 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000089/2023-2024 | 1297/MD | 28/04/2023 | 0 | Resource Division | 26.1 | 0 | 0
427 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
428 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Gamaria & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 2,320 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000413/2024-2025 | 194/MD | 17/01/2025 | 60 | M/S. S.S. ENTERPRISE | 13.11 | 0 | 0
429 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000053/2024-2025 | 3373/MD | 25/11/2024 | 0 | Resource Division | 9.7 | 0 | 0
430 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000083/2023-2024 | 1231/MD | 27/04/2023 | 0 | Resource Division | 27.76 | 0 | 0
431 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Ragpur PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000276/2022-2023 | 551/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 2.88 | 0 | 0
432 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000073/2022-2023 | 96/MD | 10/01/2023 | 0 | Resource Division | 2.56 | 0 | 0
433 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000094/2024-2025 | 3421/MD | 25/11/2024 | 0 | Resource Division | 14.91 | 0 | 0
434 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000143/2023-2024 | 1262/MD | 28/04/2023 | 0 | Resource Division | 17.2 | 0 | 0
435 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation , 250 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (1488 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Narasinghapur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000073/2023-2024 | 2146/MD | 08/06/2023 | 180 | A.J. ENTERPRISE | 425.75 | 0 | 40
436 | Midnapore Division | Kharagpur Sub-Division | Route survey & way leave permission along & across of National Highway in Narasinghapur PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000504/2024-2025 | 587/MD | 03/03/2025 | 21 | DONA ASSOCIATES | 10.04 | 0 | 0
437 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000077/2024-2025 | 3427/MD | 25/11/2024 | 0 | Resource Division | 9.17 | 0 | 0
438 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000088/2022-2023 | 197/MD | 16/01/2023 | 0 | Resource Division | 35.4 | 0 | 0
439 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Shanrpur PWSS, Block :- Debra in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000433/2020-2021 | 305/MD | 22/02/2021 | 40 | UCON | 86.59 | 40.52 | 0
440 | Midnapore Division | Kharagpur Sub-Division | Preparation of DPR of Chhotokhena W/S Scheme. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | VCH/001926/2021-2022 | BP-2021-22-280 | 16/03/2022 | 0 | SIRCON ENGINEERING SERVICES | 0.06 | 0 | 0
441 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum (Intze type with Pile Foundation) & Accommodate FHTC (3,208 Nos.) including Two years O&M under JJM with allied work for Dosatina & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000230/2023-2024 | 2954/MD | 17/08/2023 | 863 | M/S. D.K.H.CONSTRUCTION | 822.63 | 0 | 51
442 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000192/2023-2024 | 1405/MD | 04/05/2023 | 0 | Resource Division | 35.42 | 0 | 0
443 | Midnapore Division | RWS Midnapur Sub-Division | Extension of Distribution pipeline at Mouza Kural(Adibasipara near Hutpara) & Satpukuria within Kurul PWSS under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000064/2022-2023 | 236/AE/KSD | 12/05/2022 | 30 | RELIABLE ENTERPRISES | 3.3 | 0 | 0
444 | Midnapore Division | RWS Midnapur Sub-Division | Extension of Distribution pipeline at Mouza Santoshpur & Piling work near pond within Kurul PWSS under Kharagpur Sub-Division Within Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000136/2022-2023 | 382/AE/KSD | 30/06/2022 | 30 | RELIABLE ENTERPRISES | 3.4 | 0 | 0
445 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Kurul PWSS under Dantan-II Block in Paschim Medinipur District. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000402/2021-2022 | 2001/MD | 01/12/2021 | 30 | M/S. EL-CON | 59.12 | 0 | 0
446 | Midnapore Division | Midnapur Mechanical Sub Division-I | Quotation as per WBSEDCL procedure-A (2010) electric quotation bill. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00413/2022-2023 | BP-2022-23-678 | 09/03/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0
447 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Adasimla PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000424/2021-2022 | 1654/MD | 27/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.14 | 0 | 0
448 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Adasimla (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000614/2022-2023 | 440/MD | 10/02/2023 | 60 | SAI TUBE CO. | 62.67 | 0 | 100
449 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (317) for Augmentation of Anandapur Sundarpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000179/2023-2024 | 2719/MD | 31/07/2023 | 60 | MIDNAPUR PIPE CONCERN | 107.87 | 0 | 10
450 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000135/2022-2023 | 408/MD | 07/02/2023 | 0 | Resource Division | 2.72 | 0 | 0
451 | Midnapore Division | Ghatal Subdivision | Quotation as per WBSEDCL under Banpatna, Kankuria, Dudkomra, Nabinmanua, Jateghanashyam, Nischintapur, Jagannathur, Gochhati, Arit and Bhuta Water Supply Scheme. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00128/2023-2024 | 23-24-78-79-84 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.29 | 0 | 0
452 | Midnapore Division | Ghatal Subdivision | Electric Quotation Bill of Mararampur, Basudevpur & Dharma Mini | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00203/2023-2024 | 23-24-128-29-30 | 19/06/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.38 | 0 | 0
453 | Midnapore Division | Ghatal Subdivision | Ghanarmpur, Paikpara-I, Paikpara-II, Murakata, Basanchora, Peardanga, Karasia, Nischintapur, Gargarighat, Kharsa, Hematpur, Bala W/S Scheme. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00294/2023-2024 |  | 05/07/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.51 | 0 | 0
454 | Midnapore Division | Ghatal Subdivision | Electric quotation bill for Ghanarampur mini PWSS Tube Well in connection Chandrakona Town CCC for payment to WBSEDCL. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00343/2023-2024 | BP-2023-24-173 | 20/07/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.51 | 0 | 0
455 | Midnapore Division | Ghatal Subdivision | Electric quotation bill of WBSEDCL. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00370/2023-2024 |  | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0
456 | Midnapore Division | Ghatal Subdivision | Electric quotation bill of WBSEDCL. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00527/2023-2024 | BP-2023-24-273 | 28/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 0.13 | 0 | 0
457 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Karasia, JL-77 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000025/2023-2024 | 965/MD | 06/04/2023 | 14 | BENGAL TRADERS | 9.59 | 0 | 90
458 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-I at Mouza-Dharma, JL-145 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000026/2023-2024 | 966/MD | 06/04/2023 | 14 | OM UDYUG | 9.45 | 0 | 90
459 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Nischintapur, JL-230 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000027/2023-2024 | 964/MD | 06/04/2023 | 14 | SAJAL JANA | 9.59 | 0 | 100
460 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Basanchora, JL-68 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000028/2023-2024 | 968/MD | 06/04/2023 | 14 | OM UDYUG | 9.54 | 0 | 90
461 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Paikpara, JL-267 in Paschim Medinipur District under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000029/2023-2024 | 967/MD | 06/04/2023 | 14 | MALLIK CONSTRUCTION | 9.54 | 0 | 0
462 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Gochhati, JL-161 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000054/2023-2024 | 1436/MD | 04/05/2023 | 14 | M/S. BLUE BIRD | 9.58 | 0 | 98
463 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jote Ganashyam, JL-240 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000055/2023-2024 | 1437/MD | 04/05/2023 | 14 | M/S. BLUE BIRD | 9.58 | 0 | 98
464 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jagannathpur, JL-85 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000098/2023-2024 | 2473/MD | 14/07/2023 | 14 | MAHAPRABHU ENTERPRISE | 9.59 | 0 | 90
465 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Peardanga, JL-79 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000134/2023-2024 | 2593/MD | 21/07/2023 | 14 | SARADA CONSTRUCTION | 9.5 | 0 | 100
466 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme Within Block Chandrakona-I at Mouza-Hematpur JL-209 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000666/2022-2023 | 734/MD | 10/03/2023 | 14 | HYDRO TECH ASSOCIATES | 9.28 | 0 | 90
467 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed 26 nos. Mini Pipe W/S Scheme within Block Chandrakona-II (1 nos.), (i) at Mouza-Kharsa JL-231 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000667/2022-2023 | 735/MD | 10/03/2023 | 14 | TARUN MAHATA | 9.5 | 0 | 0
468 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur -II (1 no), (i)At Mouza- Dudkorma, JL-245 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000668/2022-2023 | 738/MD | 10/03/2023 | 14 | A.R. CONSTRUCTION | 9.57 | 0 | 100
469 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-I at Mouza-Basudevpur, JL-63 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000671/2022-2023 | 750/MD | 13/03/2023 | 14 | DEBASIS DATTA | 9.5 | 0 | 90
470 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Paikpara, JL-267 in Paschim Medinipur District under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000673/2022-2023 | 782/MD | 17/03/2023 | 14 | PRITI ENTERPRISE | 9.32 | 0 | 90
471 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Ghanarampur, JL-257 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000674/2022-2023 | 784/MD | 17/03/2023 | 14 | M/S. SUBHAS CHANDRA KUNDU | 9.18 | 0 | 100
472 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Bhuta, JL-187 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000675/2022-2023 | 785/MD | 17/03/2023 | 14 | S.K. CONSTRUCTION | 9.53 | 0 | 90
473 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed 26 nos. Mini Pipe W/S Scheme within Block Daspur -I (1 nos),(i) At Mouza-Makrampur JL no-125& in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000677/2022-2023 | 803/MD | 20/03/2023 | 14 | S.M. ENTERPRISE | 9.3 | 0 | 100
474 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Kharagpur-I at Mouza-Kankuria, JL-281 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000726/2022-2023 | 868/MD | 28/03/2023 | 14 | AJITESH ACHARJEE | 9.52 | 0 | 90
475 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Kharagpur-I at Mouza-Banpatna, JL-340 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000727/2022-2023 | 867/MD | 28/03/2023 | 14 | RITESH AGARWALL | 9.59 | 0 | 90
476 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Arit, JL-220 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000728/2022-2023 | 869/MD | 28/03/2023 | 14 | A R ENTERPRISE | 9.59 | 0 | 90
477 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-I at Mouza-Nischintapur, JL-264 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000729/2022-2023 | 870/MD | 28/03/2023 | 14 | M/S. INDRAJIT ROY | 9.54 | 0 | 90
478 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Chandrakona-II at Mouza-Murakata, JL-49 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000817/2023-2024 | 653/MD | 07/03/2024 | 14 | M/S. INDRAJIT ROY | 9.53 | 0 | 0
479 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Jotekanuramgarh, JL-212 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000834/2023-2024 | 742/MD | 13/03/2024 | 183 | ARNAB PATRA | 9.59 | 0 | 97
480 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC with 3 (three) months trial run for proposed Mini Pipe W/S Scheme within Block Daspur-II at Mouza-Nabinmanua, JL-155 in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000835/2023-2024 | 743/MD | 13/03/2024 | 201 | S.K. CONSTRUCTION | 9.58 | 0 | 97
481 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),JE RWS Ghatal Sub-Division(CK-II),JE RWS Ghatal Sub-Division(Daspur-I),JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000082/2024-2025 | 3433/MD | 25/11/2024 | 0 | Resource Division | 16.02 | 0 | 0
482 | Midnapore Division | Ghatal Subdivision | Laying rising main & interconnection for Khukurdaha & its adjoining mouzas PWSS within Daspur-II block, Paschim Medinipur district under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000502/2024-2025 | 585/MD | 03/03/2025 | 90 | GOBINDA MAITY | 9.16 | 0 | 95
483 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,442) under JJM with allied work for Khukur Daha & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000651/2023-2024 | 142/MD | 18/01/2024 | 796 | MASUM ALI KHAN | 804.29 | 0 | 30
484 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000030/2024-2025 | 3349/MD | 25/11/2024 | 0 | Resource Division | 21.2 | 0 | 0
485 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000031/2022-2023 | 76/MD | 09/01/2023 | 0 | Resource Division | 25.83 | 0 | 0
486 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
487 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000228/2023-2024 | 1485 | 10/05/2023 | 0 | Resource Division | 39.42 | 0 | 0
488 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. (Consultancy work) in connection with the Proposed Mini Pipe W/S Scheme for Uchitpur mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000418/2021-2022 | 1331/MD | 17/08/2021 | 10 | GOBINDA MAITY | 1.94 | 0 | 0
489 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uchitpur (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000630/2021-2022 | 183/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 37.49 | 0 | 100
490 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uchitpur (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000858/2021-2022 | 422/MD | 04/03/2022 | 150 | GOUTAM PARIA | 24.89 | 0 | 80
491 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000009/2021-2022 | 2118/MD | 13/12/2021 | 0 | Resource Division | 1.93 | 0 | 0
492 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Uchitpur mouzas. Block - Sabang. District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000454/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.93 | 0 | 0
493 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001693/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.93 | 0 | 0
494 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001827/2021-2022 | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 8.13 | 0 | 0
495 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
496 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Approach Road (3m width) of Dhuipara Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000397/2024-2025 | 153/MD | 15/01/2025 | 30 | GOBINDA MAITY | 1.64 | 0 | 100
497 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Dhuipara & its adjoining Mouzas PWSS & (2) Nilda & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000762/2022-2023 | 1117/MD | 09/06/2022 | 30 | ENVIROTECH SOLUTIONS | 4.15 | 0 | 100
498 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000162/2023-2024 | 1454/MD | 08/05/2023 | 0 | Resource Division | 30.9 | 0 | 0
499 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 250 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,745 Nos.) including 2 years operation & maintenance under JJM with allied work for Baguyan & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000246/2023-2024 | 3053/MD | 23/08/2023 | 857 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 452.52 | 0 | 40
500 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000204/2023-2024 | 1413 | 04/05/2023 | 0 | Resource Division | 37.1 | 0 | 0
501 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric Quotation Bill for the West Bengal State Electricty Distribution Company LTD. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00250/2023-2024 | BP-2023-24-142 | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 3.27 | 0 | 0
502 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying Rising main pipe line, Construction of Pump House & Boundary wall under JJM with allied work for Monoharpur & its adjoining mouzas PWSS in Dantan-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000203/2023-2024 | 2817/MD | 07/08/2023 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.64 | 0 | 76
503 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. & FHTC under JJM with allied work for Monoharpur and its adjoining mouzas W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000472/2022-2023 | 2190/MD | 01/11/2022 | 1078 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 583.38 | 0 | 35
504 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 2 (Two) nos. 300 X 200 mm dia. X 200 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Monoharpur PWSS with in Dantan - I block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000622/2022-2023 | 447/MD | 13/02/2023 | 14 | FIROJ KHAN | 23.18 | 0 | 0
505 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000003/2023-2024 | 941/MD | 05/04/2023 | 0 | Resource Division | 20.04 | 0 | 0
506 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000060/2022-2023 | 49/MD | 06/01/2023 | 0 | Resource Division | 25.82 | 0 | 0
507 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000164/2022-2023 | 802/MD | 20/03/2023 | 0 | Resource Division | 20.04 | 0 | 0
508 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (3,124 Nos.) including Two years O&M under JJM with allied work for Bagrui & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000508/2023-2024 | 5479/MD | 13/12/2023 | 720 | BALAJI UDDYOG | 1062.1 | 0 | 45
509 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000191/2023-2024 | 1404/MD | 04/05/2023 | 0 | Resource Division | 36.78 | 0 | 0
510 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Daspur (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000464/2022-2023 | 2184/MD | 01/11/2022 | 150 | S.N ENTERPRISE | 35.12 | 0 | 80
511 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Daspur (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000465/2022-2023 | 2185/MD | 01/11/2022 | 882 | S.T. ENTERPRISE | 37.32 | 0 | 80
512 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
513 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,702 nos.) under JJM with allied work for Torai PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000254/2023-2024 | 3149/MD | 29/08/2023 | 900 | BANERJEE CONSTRUCTION | 869.66 | 0 | 35
514 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Toria & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 625 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000435/2024-2025 | 320/MD | 29/01/2025 | 45 | MAA SARADA ENTERPRISE | 6.43 | 0 | 0
515 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000042/2022-2023 | 110/MD | 10/01/2023 | 0 | Resource Division | 15.28 | 0 | 0
516 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000048/2024-2025 | 3368/MD | 25/11/2024 | 0 | Resource Division | 16.64 | 0 | 0
517 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (3,056 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Dubraji & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000271/2023-2024 | 3258/MD | 12/09/2023 | 720 | TAPAS SANTRA | 927.59 | 0 | 75
518 | Midnapore Division | Kharagpur Sub-Division | Route survey & way leave permission along & across of National Highway in Dubraji PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000505/2024-2025 | 588/MD | 03/03/2025 | 21 | DONA ASSOCIATES | 10.21 | 0 | 0
519 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000086/2024-2025 | 3488/MD | 25/11/2024 | 0 | Resource Division | 18.82 | 0 | 0
520 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000101/2022-2023 | 178/MD | 16/01/2023 | 0 | Resource Division | 23.7 | 0 | 0
521 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Khasjangal / Dhansola PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  | Junior Engineer-III | ORD/000182/2020-2021 | 1406/MD | 26/11/2020 | 180 | SAIKAT DANDAPAT | 19.14 | 6.81 | 1
522 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Lakat PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  | Junior Engineer-III | ORD/000285/2020-2021 | 1583/MD | 11/12/2020 | 180 | S.B. TRADERS | 8.2 | 5.28 | 0
523 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Kechanda PWSS of Binpur-II Block under Jhargram Division, PHE Dte. [PART - 1/2] (Allotted for near about 50% of the total work) |  | Junior Engineer-III | ORD/000295/2020-2021 | 1598/MD | 14/12/2020 | 180 | DEBABRATA DUTTA | 7.72 | 7.32 | 0
524 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Kechanda PWSS of Binpur-II Block under Jhargram Division, PHE Dte. [PART - 2/2] (Allotted for near about 50% of the total work) |  | Junior Engineer-III | ORD/000296/2020-2021 | 1599/MD | 14/12/2020 | 180 | J.S.S. ENTERPRISE | 7.74 | 7.23 | 0
525 | Midnapore Division | Jhargram Sub-Division | Extension distribution pipe line to accommodation FHTC under JJM in Lakat PWSS Block-Binpur-I in the District of Jhargram. |  | Junior Engineer-III | VCH/000662/2022-2023 | 844313 | 06/07/2022 | 0 | S.B. TRADERS | 0.89 | 0 | 0
526 | Midnapore Division | Jhargram Sub-Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM AT BIRKANAR PWSS OF BINPUR-I BLOCK UNDER JHARGRAM DIVISION ,PHE DTE.. |  | Junior Engineer-III | VCH/001885/2021-2022 | 8443208 | 26/03/2022 | 0 | DEBABRATA DUTTA | 6.69 | 0 | 0
527 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Kantapahari PWSS of Binpur-I Block under Jhargram Division, PHE Dte. |  | Junior Engineer-III | VCH/001890/2021-2022 | 8443205 | 26/03/2022 | 0 | S.T. ENTERPRISE | 4.71 | 0 | 0
528 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Sartla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000258/2020-2021 | 1455/MD | 26/11/2020 | 180 | GOBINDA MAITY | 90.73 | 59.8 | 90
529 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Sartla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000728/2020-2021 |  | 15/12/2020 | 0 | GOBINDA MAITY | 20 | 0 | 0
530 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001145/2020-2021 | 8443017 | 12/02/2021 | 0 | TANMOY BERA | 0.2 | 0 | 0
531 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001146/2020-2021 | 8443107 | 12/02/2021 | 0 | GANESH CH NANDY | 0.2 | 0 | 0
532 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001147/2020-2021 | 8443107 | 12/02/2021 | 0 | PARTHA PRATIM PAL | 0.03 | 0 | 0
533 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001148/2020-2021 | 8443107 | 12/02/2021 | 0 | SHRABONTI BERA | 0.2 | 0 | 0
534 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000248/2020-2021 | 1447/MD | 26/11/2020 | 180 | SHAKEEL KHAN | 45.04 | 16.25 | 0
535 | Midnapore Division | Ghatal Subdivision | Restoration of road damaged during carrying of pipe line and allied works of KATAN water supply scheme within Ghatal Sub-Division under Midnapore Division, P.H.E. Dte. (Node- 102-105) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000502/2021-2022 | 806/AE/GSD | 16/12/2021 | 10 | DEVJYOTI BERA | 0.62 | 0 | 0
536 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate Additional FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Katan Water Supply Scheme (Paschim Para) within Ghatal Dev. Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000652/2022-2023 | 147/AE/GSD | 17/02/2023 | 30 | DEVJYOTI BERA | 3.57 | 0 | 0
537 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate Additional FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Katan Water Supply Scheme (Paschim Para) within Ghatal Dev. Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000766/2022-2023 | 149/AE/GSD | 21/02/2023 | 30 | DEVJYOTI BERA | 3.57 | 0 | 10
538 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000759/2020-2021 |  | 15/12/2020 | 0 | SHAKEEL KHAN | 30 | 0 | 0
539 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Katan W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/001369/2021-2022 | BP-2021-22-414 | 24/02/2022 | 0 | SHAKEEL KHAN | 14.25 | 0 | 0
540 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Beluria W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000278/2020-2021 | 1470/MD | 26/11/2020 | 180 | M/S. A.R. ENTERPRISE. | 92.63 | 69.1 | 100
541 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Beluria W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/000720/2020-2021 |  | 15/12/2020 | 0 | M/S. A.R. ENTERPRISE. | 35 | 0 | 0
542 | Midnapore Division | Kharagpur Sub-Division | Laying of additional distribution pipe line in different places and extention of pipe line for accomodation FHTC works of Chhotokhelna and its adjoining mouza Water Supply Scheme at Pingla Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000140/2022-2023 | 380/AE/KSD | 30/06/2022 | 30 | ASHIM KUMAR DEY | 4.55 | 0 | 0
543 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000211/2020-2021 | 1431/MD | 26/11/2020 | 180 | ASHIM KUMAR DEY | 93.67 | 50.77 | 80
544 | Midnapore Division | Kharagpur Sub-Division | Restoration of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Chhoto Khelna & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | VCH/001417/2021-2022 | BP-2021-22-373 | 17/02/2022 | 0 | WATER LINK | 15 | 0 | 0
545 | Midnapore Division | Kharagpur Sub-Division | Restoration of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Chhoto Khelna & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | VCH/001799/2021-2022 | 844328 | 08/03/2022 | 0 | WATER LINK | 0.41 | 0 | 0
546 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Barsahara W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000270/2020-2021 | 1467/MD | 26/11/2020 | 180 | DULAL CHANDRA DAS | 94.66 | 65.87 | 0
547 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House for Sansahara & Manikarah villages within Barsahara PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000665/2022-2023 | 584/MD | 23/02/2023 | 60 | DULAL CHANDRA DAS | 17.7 | 0 | 10
548 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Barsahara W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000724/2020-2021 |  | 15/12/2020 | 0 | DULAL CHANDRA DAS | 20 | 0 | 0
549 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001208/2021-2022 | 844335 | 08/12/2021 | 0 | ANIRBAN CHAKRABORTY | 0.09 | 0 | 0
550 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001209/2021-2022 | 844335 | 08/12/2021 | 0 | SHRABONTI BERA | 0.16 | 0 | 0
551 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001210/2021-2022 | 844335 | 08/12/2021 | 0 | SOVANDEB MANNA | 0.06 | 0 | 0
552 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001211/2021-2022 | 844335 | 08/12/2021 | 0 | TANMOY BERA | 0.07 | 0 | 0
553 | Midnapore Division | Kharagpur Sub-Division | Construction of Boundary wall & Land Development for Head work site of Kolanda & its adjoining mouzas Water Supply Scheme at Sabang Block under Midnapore Sadar Sub- Division within Midnapore Division, PHE. Dte. (81/EE/MD/2017-2018) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | BILL/00420/2023-2024 | 844338 | 10/05/2023 | 0 | KAILASH KUMAR AGARWALA | 1.44 | 0 | 0
554 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Kolanda W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000277/2020-2021 | 1452/MD | 26/11/2020 | 180 | M/S. A.R. ENTERPRISE. | 86.63 | 34.5 | 77
555 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Julkapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000257/2020-2021 | 1454/MD | 26/11/2020 | 180 | SUNIL DULE | 48.8 | 22.25 | 0
556 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Julkapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000725/2020-2021 | 844397 | 08/03/2021 | 0 | SUNIL DULE | 25 | 0 | 0
557 | Midnapore Division | Jhargram Sub-Division | Transfer to EE/JSD, PHE Dte. ( Aug. of Lalgarh PWSS) | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | BILL/00611/2022-2023 | BP-2022-23-464 | 20/12/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 98 | 0 | 0
558 | Midnapore Division | Jhargram Sub-Division | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 300 cum and staging height 20 mtr. with including supply of all labour & materials for Augmentation of Ground based Lalgarh PWSS in Binpur- I Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000055/2022-2023 | 875/MD | 10/05/2022 | 180 | DULAL CHANDRA DAS | 329.37 | 0 | 0
559 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Lalgarh PWSS in Binpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000237/2021-2022 | 143/JSD | 12/08/2021 | 14 | INDRANIL DUTTA & ASSOCIATES | 4.84 | 0 | 1
560 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000042/2021-2022 | 498/MD | 15/03/2022 | 0 | Resource Division | 18.23 | 0 | 0
561 | Midnapore Division |  | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work for Augmentation of Ground Water Based Odalchua PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  |  | ORD/000624/2021-2022 | 177/MD | 01/02/2022 | 45 | PROVAT KUMAR DE | 47.08 | 0 | 1
562 | Midnapore Division |  | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 2160/MD | 17/12/2021 | 0 | Resource Division | 1.36 | 0 | 0
563 | Midnapore Division |  | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Odalchua PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001380/2021-2022 | BP-2021-22-417 | 23/02/2022 | 0 | LEMNISCATE | 2.24 | 0 | 0
564 | Midnapore Division |  | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Odalchua PWSS under Jhargram Division P.H.E. Dte. |  |  | VCH/001733/2021-2022 | BP-2021-22-473 | 16/03/2022 | 0 | SAIKAT DANDAPAT | 1.77 | 0 | 0
565 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | RTOR000098/2024-2025 | 3415/MD | 25/11/2024 | 0 | Resource Division | 6.02 | 0 | 0
566 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Khasbar (Zone-I) PWSS under Ghatal Block in Paschim Medinipur District. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000494/2021-2022 | 2187/MD | 17/12/2021 | 721 | M/S. D.K.H.CONSTRUCTION | 75.89 | 0 | 50
567 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Khasbar (Zone-II) PWSS under Ghatal Block in Paschim Medinipur District. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000529/2021-2022 | 29/MD | 07/01/2022 | 30 | S.T. ENTERPRISE | 37.86 | 0 | 100
568 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Additional retrofitting to accommodate FHTC under JJM for Khasbar (Zone-II) PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000740/2022-2023 | 753/MD | 13/03/2023 | 45 | S.T. ENTERPRISE | 11.47 | 0 | 0
569 | Midnapore Division | Jhargram Sub-Division | Money transfer to EE/JSD. |  | Junior Engineer-III | BILL/00708/2022-2023 | BP-2022-23-691 | 10/03/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 3.63 | 0 | 0
570 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Rantua PWSS in Gopiballavpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-III | ORD/000222/2021-2022 | 113/JSD | 22/07/2021 | 14 | ROY CHOWDHURY ASSOCIATES | 4.49 | 0 | 1
571 | Midnapore Division | Jhargram Sub-Division | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250 X 150mm dia. X 120 Mtr. Depth Rig bored Tube well for Augmentation of Ground Based Rantua PWSS to Accommodate FHTC in Gopiballavpur-II Block within Jhargram District under Jhargram Division, PHE Dte. |  | Junior Engineer-III | ORD/000592/2021-2022 | 137/MD | 27/01/2022 | 60 | SUNIL DULE | 82.58 | 0 | 1
572 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division |  | Junior Engineer-III | RTOR000016/2021-2022 | 2164/MD | 17/12/2021 | 0 | Resource Division | 8.06 | 0 | 0
573 | Midnapore Division | Jhargram Sub-Division | Purchasing of Materials. |  | Junior Engineer-III | VCH/001686/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.68 | 0 | 0
574 | Midnapore Division | Kharagpur Sub-Division | Accommodate FHTC including supplying, laying, fitting, fixing pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Lutunia W/S Scheme under JJM within Sabang Dev. Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000017/2024-2025 | 2035/MD | 01/07/2024 | 484 | RITESH AGARWALL | 11.85 | 0 | 80
575 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Lutunia, Block - Sabang) to be Retrofitting under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000118/2021-2022 | 1007/MD | 24/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.7 | 0 | 0
576 | Midnapore Division | Kharagpur Sub-Division | Laying pipeline (Distribution System) at Mouza Lutunia (Prembazar) for Augmentation of ground water based piped water Supply Schemes to accommodate FHTC under JJM under Sabang Block under Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000168/2022-2023 | 419/AE/KSD | 19/07/2022 | 30 | PALASH KUMAR DAS | 4.69 | 0 | 0
577 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-L) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000453/2021-2022 | 542/AE/KSD | 17/12/2021 | 30 | M/S SARADA CONSTRUCTION | 4.85 | 0 | 0
578 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-A) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000462/2021-2022 | 531/AE/KSD | 17/12/2021 | 30 | BOSE & CO. | 4.84 | 0 | 0
579 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-C) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000463/2021-2022 | 533/AE/KSD | 17/12/2021 | 30 | HYDRO TECH ASSOCIATES | 4.85 | 0 | 0
580 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-G) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000464/2021-2022 | 537/AE/KSD | 17/12/2021 | 30 | RITESH AGARWALL | 4.85 | 0 | 0
581 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-H) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000465/2021-2022 | 538/AE/KSD | 17/12/2021 | 30 | M/S. BLUE BIRD | 4.85 | 0 | 0
582 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-I) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000466/2021-2022 | 539/AE/KSD | 17/12/2021 | 30 | SAJAL JANA | 4.84 | 0 | 0
583 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part- J) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000468/2021-2022 | 540/AE/KSD | 17/12/2021 | 30 | SUJOY RANJAN BHOWMICK | 4.85 | 0 | 0
584 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-M) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000469/2021-2022 | 543/AE/KSD | 17/12/2021 | 30 | S.K. CONSTRUCTION | 4.85 | 0 | 0
585 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-B) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000484/2021-2022 | 532/AE/KSD | 17/12/2021 | 30 | ADITYA ENTERPRISE | 4.85 | 0 | 0
586 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-K) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000496/2021-2022 | 541/AE/KSD | 17/12/2021 | 30 | M/S. SUBHAS CHANDRA KUNDU | 4.85 | 0 | 0
587 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-D) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000497/2021-2022 | 534/AE/KSD | 17/12/2021 | 30 | OM UDYUG | 4.85 | 0 | 0
588 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part- E) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000498/2021-2022 | 535/AE/KSD | 17/12/2021 | 30 | R. CONSTRUCTION | 4.85 | 0 | 0
589 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the Lutunia Water Supply Scheme, Block:- Sabang, within Midnapore Division, P.H.E. Dte. District :- Paschim Midnapore.(Part-F) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000499/2021-2022 | 536/AE/KSD | 17/12/2021 | 30 | FUTURE CONSTRUCTION | 4.85 | 0 | 0
590 | Midnapore Division | Kharagpur Sub-Division | Augmentation of Ground Water Based Piped W/S Scheme for Lutunia to Accommodate FHTC (Balance = 300 Nos.) under JJM under Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000591/2022-2023 | 342/MD | 31/01/2023 | 60 | UTTAM KUMAR DAS | 67.59 | 0 | 65
591 | Midnapore Division | Kharagpur Sub-Division | Distribution pipe line for accommodation of FHTC under JJM for the Lutunia Water Supply Scheme, Block-Sabang, District- Paschim Midnapore.(Part-I) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000676/2021-2022 | 66/AE/KSD | 03/02/2022 | 15 | M/S SARADA CONSTRUCTION | 4.01 | 0 | 0
592 | Midnapore Division | Kharagpur Sub-Division | Distribution pipe line for accommodation of FHTC under JJM for the Lutunia Water Supply Scheme, Block-Sabang, District- Paschim Midnapore.(Part-II) | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000677/2021-2022 | 67/AE/KSD | 03/02/2022 | 15 | SUJOY RANJAN BHOWMICK | 4 | 0 | 0
593 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | RTOR000014/2021-2022 | 2129/MD | 14/12/2021 | 0 | Resource Division | 7.59 | 0 | 0
594 | Midnapore Division | Kharagpur Sub-Division | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Lutunia to Accommodate PHTC. Block - Sabang. District - Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000461/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 7.59 | 0 | 0
595 | Midnapore Division | Kharagpur Sub-Division | Purchasing of Materials. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001688/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 7.59 | 0 | 0
596 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. (Phase-II) | AE Sadar Sub-division |  | ORD/000067/2021-2022 | 1059/MD | 02/07/2021 | 15 | NIMAI LAL GURIA | 7.53 | 0 | 1
597 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC (left out) at different mouzas and shifting of pipeline in connection with widenening and strengthening of road for Chaita PWSS & its adjoining mouzas W/S Scheme within Midnapore Division ,PHE Dte. (SL No-06) | AE Sadar Sub-division |  | ORD/000138/2022-2023 | 280/AE/MSSD | 15/06/2022 | 30 | AJITESH ACHARJEE | 3.98 | 0 | 0
598 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza ¿ Bagmari, Bhabrigeria in Chaita PWSS of Salboni Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000518/2020-2021 | 391/MD | 25/02/2021 | 30 | PRADIP KUMAR SAHA | 14.17 | 13.07 | 0
599 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Chatra in Chatra PWSS of Garhbeta-II Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000519/2020-2021 | 392/MD | 25/02/2021 | 15 | SUNIL DULE | 7.93 | 6.48 | 0
600 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Sutkujuri in Sutkijhuri PWSS of Garhbeta-II Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000520/2020-2021 | 393/MD | 25/02/2021 | 15 | SUNIL DULE | 7.93 | 6.83 | 0
601 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Amrakuchi in Amrakuchi PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000521/2020-2021 | 406/MD | 26/02/2021 | 15 | PULLOCK KUMAR GHOSH | 7.89 | 0 | 0
602 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Sekhuasol, Bhalukasol & Dalang in Dalang PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000522/2020-2021 | 407/MD | 26/02/2021 | 45 | M/S. D.K.H.CONSTRUCTION | 29.01 | 27.2 | 0
603 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Jagul, Raghabchak & Belpatri in Jagul PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000523/2020-2021 | 408/MD | 26/02/2021 | 45 | DULAL CHANDRA DAS | 29 | 28.23 | 0
604 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Abashgarh Paschim Para in Abashgarh PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I). | AE Sadar Sub-division |  | ORD/000524/2020-2021 | 409/MD | 26/02/2021 | 15 | WATER LINK | 7.15 | 5.46 | 0
605 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Benashuli, Nayagram & Bhadute in Nayagram PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000546/2020-2021 | 422/MD | 26/02/2021 | 30 | SANJIT SINHA | 19.29 | 5.52 | 0
606 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Pathra in Pathra PWSS of Midnapore Sadar Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | ORD/000547/2020-2021 | 423/MD | 26/02/2021 | 30 | SANJIT SINHA | 14.46 | 2.19 | 0
607 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Chaita in Chaita PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-04) | AE Sadar Sub-division |  | ORD/000675/2020-2021 | 96/AE/MSSD | 23/02/2021 | 15 | AJITESH ACHARJEE | 4.81 | 3.66 | 0
608 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Dhengasole Uttar Para in Dhengasole PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-01) | AE Sadar Sub-division |  | ORD/000718/2020-2021 | 98/AE/MSSD | 24/02/2021 | 15 | CHANDAN YADAV | 4.8 | 3.66 | 0
609 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Godamouli in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SLN o-08) | AE Sadar Sub-division |  | ORD/000724/2020-2021 | 102/AE/MSSD | 24/02/2021 | 15 | A R ENTERPRISE | 4.77 | 4.74 | 0
610 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Jamdoba in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-09) | AE Sadar Sub-division |  | ORD/000725/2020-2021 | 103/AE/MSSD | 24/02/2021 | 15 | A R ENTERPRISE | 1.96 | 1.15 | 0
611 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza - Sekhuasol, Bhalukasol & Dalang in Dalang PWSS of Keshpur Block in the district of Paschim Medinipur (Phase-I) | AE Sadar Sub-division |  | VCH/000960/2020-2021 |  | 09/03/2021 | 0 | M/S. D.K.H.CONSTRUCTION | 22 | 0 | 0
612 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Abashgarh Purba Para in Abashgarh PWSS in Midnapore Sadar Block in the District of Paschim Medinipore.(SL No-12) | AE Sadar Sub-division |  | VCH/001372/2021-2022 | BP-2021-22-413 | 24/02/2022 | 0 | WATER LINK | 4.84 | 0 | 0
613 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dalang W/S Scheme. | AE Sadar Sub-division |  | VCH/001924/2021-2022 | BP-2021-22-96 | 10/03/2022 | 0 | M/S. D.K.H.CONSTRUCTION | 1.28 | 0 | 0
614 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dalang W/S Scheme. | AE Sadar Sub-division |  | VCH/001927/2021-2022 | BP-2021-22-96 | 10/03/2022 | 0 | M/S. D.K.H.CONSTRUCTION | 0.49 | 0 | 0
615 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sutkijhuri, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000561/2020-2021 | 55/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.87 | 0 | 0
616 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sutkujhuri PWSS to accommodate FHTC under JJM under Garhbeta-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000682/2021-2022 | 281/MD | 15/02/2022 | 30 | MANISHIKA CONSTRUCTION | 21.78 | 0 | 100
617 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. 55/MD | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | VCH/001116/2020-2021 | 8443497 | 30/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.5 | 0 | 0
618 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Ukhla, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000562/2020-2021 | 56/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.49 | 2.39 | 0
619 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Ukhla PWSS to accommodate FHTC under JJM under Garhbeta -II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000683/2021-2022 | 282/MD | 15/02/2022 | 60 | GOUTAM RAY | 43.53 | 0 | 0
620 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Ukhla Purba Para in Ukhla PWSS in Garhbeta II Block in the District of Paschim Medinipore.(SL No-10) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000746/2020-2021 | 106/AE/MSSD | 26/02/2021 | 15 | AJIJUR RAHAMAN MALLICK | 4.83 | 3.94 | 10
621 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Ukhla Paschim Para in Ukhla PWSS (Part-B) in Garhbeta II Block in the District of Paschim Medinipore.(SL.NO-11) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000752/2020-2021 | 107/AE/MSSD | 26/02/2021 | 15 | AJIJUR RAHAMAN MALLICK | 4.83 | 3.22 | 0
622 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | VCH/001115/2020-2021 |  | 19/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 2.39 | 0 | 0
623 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Khasbazar W/S Scheme, Block: - Debra, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000263/2020-2021 | 1460/MD | 26/11/2020 | 180 | SUBRATA DAS | 92.69 | 59.03 | 0
624 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | VCH/001149/2020-2021 | 8443110 | 12/02/2021 | 0 | PAPPU SHAW | 0.19 | 0 | 0
625 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | VCH/001150/2020-2021 | 8443110 | 12/02/2021 | 0 | SIDDHESWAR BAG | 0.21 | 0 | 0
626 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | VCH/001151/2020-2021 | 8443110 | 12/02/2021 | 0 | SUBRATA CHAKRABORTY | 0.18 | 0 | 0
627 | Midnapore Division | Ghatal Subdivision | Chandrakona to Ghatal Road from Chainage 36.600 Kmp to 42.00 Kmp Restoration of damages due to laying of proposed underground pipeline by PHE Deptt in the district of Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00126/2023-2024 | BP-2023-24-81 | 08/05/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 80 | 0 | 0
628 | Midnapore Division | Ghatal Subdivision | Exigency basis laying casing pipe under Bitumineous pucca road crosssing (Near Baliaghata bus stop,Bablatola Maruti Showroom,Chanak para Soni Mandir) of Khakurda to Ghatal PWD Road of Ranapur W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000524/2022-2023 | 171/AE/GSD | 01/04/2022 | 2 | ANNAPURNA TUBEWELL WORKS | 3.64 | 0 | 0
629 | Midnapore Division | Ghatal Subdivision | Supply of C.I.D.F. Sluice valve C.I.Jeffy coupler for distribution and rising main pipe line for Augmentation of Ranirbazar water supply scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000644/2022-2023 | 108/AE/GSD | 13/02/2023 | 170 | M/S. GEO | 3.59 | 0 | 100
630 | Midnapore Division | Ghatal Subdivision | Continuation work order for the work of Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at different Places of Kharagpur Sub-Division Stores / Office premises stackyard etc. under Midnapore Division, PHE Dte. [For the period 4 months i.e. from 01.04.2021 to 31.07.2021] [Considering Zone - 'A' as per Joint Labour Commissioner order vide Memo No. - 352 /Stat/2RW/76/266/LCS/JLC, Dated - 27.12.2019] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000850/2020-2021 | 606/MD | 30/03/2021 | 122 | M/S. OXFORD SECURITY SERVICE | 3.75 | 0 | 0
631 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Ranirbazar (Block-Ghatal) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001039/2021-2022 | 1647/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.02 | 0 | 0
632 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000033/2021-2022 | 2278/MD | 31/12/2021 | 0 | Resource Division | 13.67 | 0 | 0
633 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000125/2022-2023 | 225/MD | 02/02/2023 | 0 | Resource Division | 74.42 | 0 | 0
634 | Midnapore Division | Ghatal Subdivision | Purchasing of materials for the augmentation of Ground Water Based Piped Water Supply Scheme for Ranirbazar to Accommodate FHTC, Block - Ghatal. District - Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000459/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 13.67 | 0 | 0
635 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chatra, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000560/2020-2021 | 54/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.6 | 0 | 0
636 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Paschim Beguni PWSS under Debra Block in Paschim Medinipur District. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000403/2021-2022 | 2002/MD | 01/12/2021 | 21 | M/S. EL-CON | 31.78 | 0 | 0
637 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashida & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000100/2022-2023 | 752/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 7.87 | 0 | 0
638 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Borai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000101/2022-2023 | 753/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 5.24 | 0 | 0
639 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sautia & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000102/2022-2023 | 754/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 6.68 | 0 | 0
640 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jarisai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000103/2022-2023 | 755/MD | 22/04/2022 | 20 | ENVIROTECH SOLUTIONS | 6.63 | 0 | 0
641 | Midnapore Division | Midnapur Mechanical Sub Division-I | Conducting of Route Survey and allied works in connection with the Functional Household Tap Connection of existing PWSS (Mohanpur, Block - Mohanpur) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000214/2021-2022 | 1136/MD | 16/07/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.04 | 0 | 100
642 | Midnapore Division | Midnapur Mechanical Sub Division-I | Design of Distribution Network and preparation of DPR in connection with the Functional Household Tap Connection of existing PWSS (Mohanpur, Block - Mohanpur) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000215/2021-2022 | 1144/MD | 19/07/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.49 | 0 | 100
643 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying Distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 550 Cum (Pile foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Augmentation of Mohanpur and its adjoining mouzas W/S scheme in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000378/2022-2023 | 1961/MD | 20/09/2022 | 1164 | GOBINDA MAITY | 658.99 | 0 | 95
644 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Laying Balance (Part) Distribution System to accommodate FHTC of Proposed Augmentation Pipe Water Supply Scheme for Mohanpur & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 18,000.00 Mtr.) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000610/2022-2023 | 382/MD | 03/02/2023 | 60 | GOBINDA MAITY | 87.47 | 0 | 79
645 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 1 (One) no. 250 X 150 mm dia. X 200 mtr. Depth deep tube well by direct rotary method for Augmentation of Mohanpur W/S Scheme within Mohanpur Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000621/2022-2023 | 446/MD | 13/02/2023 | 10 | GOBINDA MAITY | 11.7 | 0 | 100
646 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000171/2023-2024 | 1363/MD | 02/05/2023 | 0 | Resource Division | 61.09 | 0 | 0
647 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza ¿Kashijora in Kashijora PWSS in Salboni Block District Paschim Medinipore within Midnapore Division PHE Dte.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000343/2021-2022 | 532/AE/MSSD | 30/09/2021 | 15 | MAITY ENTERPRISE | 4.85 | 0 | 0
648 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza-Chhoto Bhursa in Kashijora PWSS in Salboni Block District Paschim Medinipore within Midnapore Division PHE Dte.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000508/2021-2022 | 653/AE/MSSD | 14/12/2021 | 15 | MAITY ENTERPRISE | 4.5 | 0 | 0
649 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza -Bara Bhursa in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000511/2021-2022 | 649/AE/MSSD | 14/12/2021 | 15 | MAITY ENTERPRISE | 4.5 | 0 | 0
650 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza -Deulkunda in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-03) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000516/2021-2022 | 656/AE/MSSD | 17/12/2021 | 15 | MAITY ENTERPRISE | 3.49 | 0 | 0
651 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza -Baradiha in Kashijora PWSS in Salboni Block District :- Paschim Medinipur within Midnapore Division, PHE Dte.(SL No-04) | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001649/2021-2022 | BP-2021-22-432 | 04/03/2022 | 0 | MAITY ENTERPRISE | 4.44 | 0 | 0
652 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Krishnaballabhpur, Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000594/2022-2023 | 345/MD | 31/01/2023 | 700 | M/S. SOMNATH | 43.6 | 0 | 90
653 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000045/2024-2025 | 3354/MD | 25/11/2024 | 0 | Resource Division | 1.15 | 0 | 0
654 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000283/2020-2021 | 1582/MD | 11/12/2020 | 180 | RAMENDRA NATH KAR | 15.06 | 0 | 80
655 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00720/2022-2023 | 22-23-707,8,9 | 13/03/2023 | 0 | GOBINDA MAITY | 61 | 0 | 0
656 | Midnapore Division | Ghatal Subdivision | Laying additional distribution system pipe line & accommodate FHTC (650 Nos.) for Ranichak W/S Scheme under JJM within Daspur-II Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000076/2024-2025 | 2789/MD | 03/09/2024 | 424 | GOBINDA MAITY | 60.71 | 0 | 30
657 | Midnapore Division | Ghatal Subdivision | Construction of Approach Road, Land development (workable to running const. work) at Head Works of Ranichak Water Supply Scheme, Block: - Daspur- I, District: - Paschim Medinipur under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000101/2023-2024 | 2476/MD | 14/07/2023 | 21 | GOBINDA MAITY | 8.23 | 0 | 100
658 | Midnapore Division | Ghatal Subdivision | Laying of Rising main including interconnection of Ranichak & its adjoining mouzas W/S Scheme under Daspur-II block within Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000416/2024-2025 | 197/MD | 17/01/2025 | 30 | PALASH KUMAR DAS | 6.38 | 0 | 100
659 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000499/2022-2023 | 2364/MD | 21/11/2022 | 1242 | GOBINDA MAITY | 1460.37 | 0 | 58
660 | Midnapore Division | Ghatal Subdivision | Construction of M.S. Fabricated and R.C.C Supporting Structure including aligning pipe line in connection of laying distribution main of Jote Kanuramgarh & Ranichak Water supply scheme under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000628/2022-2023 | 453/MD | 13/02/2023 | 60 | GOBINDA MAITY | 50.85 | 0 | 60
661 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000027/2024-2025 | 3346/MD | 25/11/2024 | 0 | Resource Division | 17 | 0 | 0
662 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000165/2022-2023 | 881/MD | 29/03/2023 | 0 | Resource Division | 37.57 | 0 | 0
663 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000168/2022-2023 | 903/MD | 31/03/2023 | 0 | Resource Division | 37.56 | 0 | 0
664 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000210/2023-2024 | 2827/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 1515.85 | 0 | 15
665 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000034/2023-2024 | 1174/MD | 26/04/2023 | 0 | Resource Division | 30.14 | 0 | 0
666 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
667 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
668 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000236/2023-2024 | 1528/MD | 12/05/2023 | 0 | Resource Division | 33.2 | 0 | 0
669 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000110/2023-2024 | 1244/MD | 27/04/2023 | 0 | Resource Division | 20.52 | 0 | 0
670 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Pump House & Accommodate FHTC (150 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000046/2023-2024 | 1429/MD | 04/05/2023 | 60 | AJITESH ACHARJEE | 22.19 | 0 | 30
671 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000047/2023-2024 | 1430/MD | 04/05/2023 | 45 | M/S. ZAMAN ENTERPRISE | 24.56 | 0 | 10
672 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 nos. Tube well under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000140/2023-2024 | 2624/MD | 24/07/2023 | 30 | MASUM CONSTRUCTION | 16.28 | 0 | 95
673 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Boundary wall & Accommodate FHTC (400 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000196/2023-2024 | 2810/MD | 07/08/2023 | 60 | APURBA PATRA | 86.47 | 0 | 10
674 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of Rising main, distribution pipe line & Accommodate FHTC (397 Nos.) including 2 years operation & maintenance under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000235/2023-2024 | 3005/MD | 21/08/2023 | 60 | SUDHAMAY MAJUMDAR | 115.72 | 0 | 0
675 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 200 cum OHR (Intze type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied work for Benucha & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000552/2024-2025 | 800/MD | 24/03/2025 | 180 | M/S BISWANATH CONSTRUCTION | 96.22 | 0 | 0
676 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000128/2022-2023 | 375/MD | 03/02/2023 | 0 | Resource Division | 26.6 | 0 | 0
677 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
678 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000098/2022-2023 | 189/MD | 16/01/2023 | 0 | Resource Division | 15.7 | 0 | 0
679 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000110/2024-2025 | 3446/MD | 25/11/2024 | 0 | Resource Division | 8.57 | 0 | 0
680 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0
681 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000118/2023-2024 | 1309/MD | 28/04/2023 | 0 | Resource Division | 33.81 | 0 | 0
682 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000142/2023-2024 | 1261/MD | 28/04/2023 | 0 | Resource Division | 19.58 | 0 | 0
683 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000127/2023-2024 | 1319/MD | 28/04/2023 | 0 | Resource Division | 29.75 | 0 | 0
684 | Midnapore Division | Kharagpur Sub-Division | Improvement of approach road of Kasbasanda PWSS Head work site under Narayangarh block within Midnapore Division, PHE Dte. [Length 60.0 Mtr. X Width 2.0 Mtr. (av.) X Depth 1.50 Mtr. (av.)] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000005/2025-2026 | 996/AE/HQ/MD | 22/04/2025 | 30 | GOURMOHAN DAS | 2.31 | 0 | 0
685 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
686 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000026/2023-2024 | 1175/MD | 26/04/2023 | 0 | Resource Division | 28.44 | 0 | 0
687 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
688 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000019/2023-2024 | 1161/MD | 25/04/2023 | 0 | Resource Division | 21.02 | 0 | 0
689 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2374 Nos.) under JJM with allied work for Radhaballavpur & its adjoining mouzas W/S scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000641/2022-2023 | 578/MD | 23/02/2023 | 1147 | DULAL CHANDRA DAS | 647.61 | 0 | 4
690 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Rising main from 2nd tube well to 1st tube well to OHR for Radhaballavpur & its adjoining mouzas W/S Scheme within Keshpur block under Midnapore Division, PHE Dte. (Length of pipe line = 360.00 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000761/2023-2024 | 374/MD | 12/02/2024 | 30 | MAMPI ENTERPRISE | 9.73 | 0 | 0
691 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000040/2022-2023 | 99/MD | 10/01/2023 | 0 | Resource Division | 28.38 | 0 | 0
692 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000063/2024-2025 | 3383/MD | 25/11/2024 | 0 | Resource Division | 14.62 | 0 | 0
693 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000062/2023-2024 | 1283/MD | 28/04/2023 | 0 | Resource Division | 29.58 | 0 | 0
694 | Midnapore Division | Ghatal Subdivision | Laying of Rising main pipeline for Uttarbar (Zone-I) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000057/2024-2025 | 2580/MD | 22/08/2024 | 45 | FIROJ KHAN | 6.19 | 0 | 0
695 | Midnapore Division | Ghatal Subdivision | Laying of Rising main pipeline for Uttarbar (Zone-II) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000058/2024-2025 | 2581/MD | 22/08/2024 | 45 | FIROJ KHAN | 4.91 | 0 | 0
696 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000514/2022-2023 | 2556/MD | 15/12/2022 | 1238 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 18
697 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000004/2023-2024 | 943/MD | 05/04/2023 | 0 | Resource Division | 32.7 | 0 | 0
698 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000022/2024-2025 | 3342/MD | 25/11/2024 | 0 | Resource Division | 31.37 | 0 | 0
699 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
700 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000058/2023-2024 | 1202/MD | 26/04/2023 | 0 | Resource Division | 22.29 | 0 | 0
701 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000125/2023-2024 | 1316/MD | 28/04/2023 | 0 | Resource Division | 25.89 | 0 | 0
702 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
703 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
704 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000215/2023-2024 | 1479 | 10/05/2023 | 0 | Resource Division | 33.34 | 0 | 0
705 | Midnapore Division | Kharagpur Sub-Division | Accommodate FHTC (3,350 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Balichak W/S Scheme within Debra Dev. block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000040/2024-2025 | 2220/MD | 19/07/2024 | 60 | ASHIM KUMAR DEY | 144.99 | 0 | 0
706 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Balichak, Block - Debra) to be Retrofitting under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000117/2021-2022 | 996/MD | 23/06/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 3.59 | 0 | 0
707 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 300 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,763 Nos.) including 2 years operation & maintenance under JJM with allied work for Malighati & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000247/2023-2024 | 3054/MD | 23/08/2023 | 857 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 448.29 | 0 | 40
708 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000225/2023-2024 | 1509/MD | 12/05/2023 | 0 | Resource Division | 26.87 | 0 | 0
709 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Radhakantapur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Kalara & its adjoining Mouzas PWSS instead of Radhakantapur & its adjoining Mouzas PWSS] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000105/2022-2023 | 1055/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.43 | 0 | 100
710 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
711 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000042/2023-2024 | 1197 | 26/04/2023 | 0 | Resource Division | 22.67 | 0 | 0
712 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, Boundary Wall, 300 cum OHR (Intze type with solid raft) & Accommodate FHTC (1,832 Nos.) including 2 years operation & maintenance under JJM with allied work for Ramchandrapur & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000279/2023-2024 | 3822/MD | 20/09/2023 | 876 | ASIS KUMAR SARANGI | 525.39 | 0 | 58
713 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000269/2023-2024 | 2227/MD | 15/06/2023 | 0 | Resource Division | 36.62 | 0 | 0
714 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000041/2023-2024 | 1183/MD | 26/04/2023 | 0 | Resource Division | 42.44 | 0 | 0
715 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000043/2023-2024 | 1184/MD | 26/04/2023 | 0 | Resource Division | 22.88 | 0 | 0
716 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000136/2023-2024 | 1254/MD | 28/04/2023 | 0 | Resource Division | 22.46 | 0 | 0
717 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (1946 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Chakabdulla & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000389/2023-2024 | 5063/MD | 26/10/2023 | 720 | MIDNAPUR PIPE CONCERN | 522.11 | 0 | 55
718 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000076/2024-2025 | 3426/MD | 25/11/2024 | 0 | Resource Division | 11.99 | 0 | 0
719 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000107/2022-2023 | 205/MD | 16/01/2023 | 0 | Resource Division | 17.35 | 0 | 0
720 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, Construction of 400 CuM OHR (Intze type with Pile Foundation) & Accommodate FHTC (2,576 Nos.) under JJM with allied works for Kalagram PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapur Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000030/2023-2024 | 947/MD | 06/04/2023 | 1089 | DULAL CHANDRA DAS | 652.22 | 0 | 40
721 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000035/2022-2023 | 101/MD | 10/01/2023 | 0 | Resource Division | 23.52 | 0 | 0
722 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000062/2024-2025 | 3382/MD | 25/11/2024 | 0 | Resource Division | 16.98 | 0 | 0
723 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking Of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2790 Nos) under JJM with allied work for Kharika & its adjoining mouzas W/S scheme in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000068/2023-2024 | 2421/MD | 13/07/2023 | 902 | BANERJEE CONSTRUCTION | 819.46 | 0 | 45
724 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Kharika & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 320 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000437/2024-2025 | 322/MD | 29/01/2025 | 45 | MAA SARADA ENTERPRISE | 5 | 0 | 0
725 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000043/2022-2023 | 98/MD | 10/01/2023 | 0 | Resource Division | 18.9 | 0 | 0
726 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000064/2024-2025 | 3384/MD | 25/11/2024 | 0 | Resource Division | 17.19 | 0 | 0
727 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
728 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000027/2023-2024 | 1176/MD | 26/04/2023 | 0 | Resource Division | 27.09 | 0 | 0
729 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000067/2023-2024 | 1279/MD | 28/04/2023 | 0 | Resource Division | 40.33 | 0 | 0
730 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000044/2023-2024 | 1185/MD | 26/04/2023 | 0 | Resource Division | 42.58 | 0 | 0
731 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Maligram PWSS Within Pingla Block under Midnapore Division P.H.E. Dte | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000272/2022-2023 | 547/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 3.06 | 0 | 100
732 | Midnapore Division | Kharagpur Sub-Division | Additional work in connection of Laying of Distribution pipe line for Augmentation of Maligram Pipe Water Supply Scheme under Pingla Block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000311/2024-2025 | 3404/MD | 25/11/2024 | 90 | UTTAM KUMAR DAS | 80.7 | 0 | 0
733 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Maligram PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000586/2022-2023 | 297/MD | 24/01/2023 | 813 | M/S. D.K.H.CONSTRUCTION | 282.94 | 0 | 61
734 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000168/2023-2024 | 1368/MD | 02/05/2023 | 0 | Resource Division | 38.07 | 0 | 0
735 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
736 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000108/2022-2023 | 209/MD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0
737 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000123/2024-2025 | 3459/MD | 25/11/2024 | 0 | Resource Division | 13.88 | 0 | 0
738 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
739 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000060/2023-2024 | 1203/MD | 26/04/2023 | 0 | Resource Division | 81.81 | 0 | 0
740 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
741 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000099/2023-2024 | 1236/MD | 27/04/2023 | 0 | Resource Division | 19.02 | 0 | 0
742 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000145/2023-2024 | 1264/MD | 28/04/2023 | 0 | Resource Division | 26.72 | 0 | 0
743 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Kolanda PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000435/2021-2022 | 1668/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.11 | 0 | 100
744 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of pipe line damaged due to construction of roads (Koptipur, Rautarabari, Bangaldari, Hijaltol Batitaki, Batuabazar etc.) & excess length of pipe in connection with FHTC work at Kolanda W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000613/2022-2023 | 439/MD | 10/02/2023 | 45 | M/S. A.R. ENTERPRISE. | 68.31 | 0 | 100
745 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well & Accommodate FHTC (200 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000016/2023-2024 | 936/MD | 04/04/2023 | 45 | ANNAPURNA TUBEWELL WORKS | 29.28 | 0 | 100
746 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (500 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000017/2023-2024 | 1023/MD | 12/04/2023 | 60 | ASHIM KUMAR DEY | 137.59 | 0 | 0
747 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (470 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000018/2023-2024 | 937/MD | 04/04/2023 | 710 | J.K. BUILDERS | 82.89 | 0 | 100
748 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (307 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VII] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000019/2023-2024 | 938/MD | 04/04/2023 | 60 | GOUTAM RAY | 52.89 | 0 | 53
749 | Midnapore Division | Midnapur Sadar Sub-Division | Construction Pump House, Boundary wall, Soil investigation, Construction of 450 cum OHR (Intze type with solid raft) & Accommodate FHTC (500 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000035/2024-2025 | 2144/MD | 11/07/2024 | 360 | KISHORE GHOSH | 179.06 | 0 | 5
750 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Rising main, Pump House, Boundary wall, Accommodate FHTC (450 nos.) & 2 years operation & maintenance under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000036/2024-2025 | 2145/MD | 11/07/2024 | 357 | KISHORE GHOSH | 130.76 | 0 | 30
751 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of tube well & Accommodate FHTC (200 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VIII] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000041/2023-2024 | 1385/MD | 02/05/2023 | 45 | DEBJIT PATRA | 29.29 | 0 | 50
752 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of additional distribution pipeline for Piasala & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000518/2024-2025 | 699/MD | 12/03/2025 | 60 | SAFTI PRIVATE LIMITED | 11.63 | 0 | 0
753 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000271/2023-2024 | 3983/MD | 06/10/2023 | 0 | Resource Division | 54.29 | 0 | 0
754 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
755 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 350 Cum RCC Over Head Reservoir (Intze type with solid raft) & Accommodate FHTC (1976 Nos.) including Two years O&M under JJM with allied work for Raghunathpur & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000128/2023-2024 | 2526/MD | 18/07/2023 | 180 | ANIRUDDHA BAG | 582.89 | 0 | 96
756 | Midnapore Division | Kharagpur Sub-Division | Laying balance distribution system to accommodate FHTC (350 Nos.) for Raghunathpur & its adjoining mouzas W/S Scheme, Block - Kharagpur-I, District - Paschim Medinipur under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000879/2024-2025 | 206/MD | 17/01/2025 | 75 | ANIRUDDHA BAG | 56.29 | 0 | 0
757 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000078/2024-2025 | 3429/MD | 25/11/2024 | 0 | Resource Division | 12.17 | 0 | 0
758 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000093/2022-2023 | 190/MD | 16/01/2023 | 0 | Resource Division | 13.79 | 0 | 0
759 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Chhota Khelna PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000273/2022-2023 | 548/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 3.31 | 0 | 100
760 | Midnapore Division | Kharagpur Sub-Division | Disinfection of different type of spot sources at flood affected area of Sultanpur GP. Of Ghatal Block within Ghatal Sub-Division, under Midnapore Division PHE. Dte. In the District of Paschim Medinipur. (Period for ¿July & August-2021) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001077/2021-2022 | 559/AE/GSD | 06/08/2021 | 5 | SANJIT SINHA | 2.47 | 0 | 100
761 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000072/2022-2023 | 92/MD | 10/01/2023 | 0 | Resource Division | 4.88 | 0 | 0
762 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000092/2024-2025 | 3419/MD | 25/11/2024 | 0 | Resource Division | 23.16 | 0 | 0
763 | Midnapore Division | Kharagpur Sub-Division | Laying balance Distribution pipeline for Augmentation of Karkai PWSS under Pingla block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000002/2025-2026 | 917/MD | 08/04/2025 | 75 | SUBRATA KUMAR BERA | 71.62 | 0 | 45
764 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Karkai PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000274/2022-2023 | 549/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 3.06 | 0 | 0
765 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall to accommodate FHTC (327 Nos.) for Augmentation of Karkai PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000629/2022-2023 | 454/MD | 13/02/2023 | 831 | GOBINDA MAITY | 309.44 | 0 | 90
766 | Midnapore Division | Kharagpur Sub-Division | Continuation Work Order for the work of Laying balance distribution pipe line for Augmentation of Karkai & its adjoining mouzas Pipe Water Supply Scheme under Pingla Block within Midnapore Division, P.H.E. Dte. (Total Length = 4,100.00 Mtr.) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000741/2022-2023 | 845/MD | 24/03/2023 | 648 | GOBINDA MAITY | 26.29 | 0 | 98
767 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000071/2022-2023 | 113/MD | 10/01/2023 | 0 | Resource Division | 1.26 | 0 | 0
768 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000093/2024-2025 | 3420/MD | 25/11/2024 | 0 | Resource Division | 16.87 | 0 | 0
769 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 75
770 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000227/2023-2024 | 1510/MD | 12/05/2023 | 0 | Resource Division | 22.87 | 0 | 0
771 | Midnapore Division | Ghatal Subdivision | Restoration of damaged pipeline due to irrigation works of PRATAPPUR water supply scheme within Ghatal block under Ghatal Sub-Division within Midnapore Division, PHE.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000032/2024-2025 | 1274/AE/GSD | 28/06/2024 | 15 | SUBHASIS DOLAI | 0.48 | 0 | 100
772 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (502) for Augmentation of Pratappur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000170/2023-2024 | 2672/MD | 26/07/2023 | 737 | DIPAK KUMAR DOLAI | 67.82 | 0 | 10
773 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000133/2022-2023 | 406/MD | 07/02/2023 | 0 | Resource Division | 3.97 | 0 | 0
774 | Midnapore Division | Ghatal Subdivision | Laying additional pipe line to provide balance FHTC under JJM in Mansuka PWSS (Part of Kgaragpur Village) under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000169/2023-2024 | 2671/MD | 26/07/2023 | 30 | A-PLUS | 21.1 | 0 | 100
775 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (522 Nos.) under JJM with allied work for Augmentation of Mansuka Pipe W/S Scheme in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000182/2023-2024 | 2722/MD | 31/07/2023 | 732 | DIPAK KUMAR DOLAI | 111.12 | 0 | 10
776 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 2 Nos. PWSS within Ghatal & Chandrakona-I blocks under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000737/2022-2023 | 2684/MD | 30/12/2022 | 21 | SIRCON ENGINEERING SERVICES | 8.23 | 0 | 100
777 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000195/2023-2024 | 1419/MD | 04/05/2023 | 0 | Resource Division | 4.04 | 0 | 0
778 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution Pipeline & Accommodate FHTC (241 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000005/2024-2025 | 1838/MD | 12/06/2024 | 45 | DEBASISH DOGRA | 40.29 | 0 | 60
779 | Midnapore Division | Kharagpur Sub-Division | Laying Pipeline (Distribution system & Rising main), Switch Room, Land development & Accommodate FHTC (164 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000006/2024-2025 | 1839/MD | 12/06/2024 | 420 | A R ENTERPRISE | 48.59 | 0 | 86
780 | Midnapore Division | Kharagpur Sub-Division | Sinking of 3 (Three) Nos. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-I) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000118/2023-2024 | 2518/MD | 18/07/2023 | 40 | DEBASISH DOGRA | 18.02 | 0 | 90
781 | Midnapore Division | Kharagpur Sub-Division | Sinking of 1 (One) No. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-II) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000119/2023-2024 | 2519/MD | 18/07/2023 | 15 | THE TILES | 6.19 | 0 | 100
782 | Midnapore Division | Kharagpur Sub-Division | Sinking of 3 (Three) Nos. Tube well for Rupnarayanpur & its adjoining mouzas (Zone-III) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000120/2023-2024 | 2520/MD | 18/07/2023 | 40 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.74 | 0 | 100
783 | Midnapore Division | Kharagpur Sub-Division | Construction of 150 CuM OHR (Torch type with Solid raft), Pump House, Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000320/2024-2025 | 3550/MD | 04/12/2024 | 180 | BIDYUT KUMAR SANTRA | 108.07 | 0 | 0
784 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution Pipeline & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000843/2023-2024 | 745/MD | 13/03/2024 | 45 | NIMAI LAL GURIA | 40.38 | 0 | 65
785 | Midnapore Division | Kharagpur Sub-Division | Laying Rising main, Distribution Pipeline & Accommodate FHTC (200 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000851/2023-2024 | 828/MD | 15/03/2024 | 45 | PULLOCK KUMAR GHOSH | 42.81 | 0 | 0
786 | Midnapore Division | Kharagpur Sub-Division | Construction of 150 CuM OHR (Torch type with Solid raft) & Boundary wall under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000860/2023-2024 | 833/MD | 15/03/2024 | 180 | SUBRATA KUMAR BERA | 89.95 | 0 | 0
787 | Midnapore Division | Kharagpur Sub-Division | Laying Rising main, Distribution Pipeline & Accommodate FHTC (206 Nos.) including 2 yrs. O&M under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000861/2023-2024 | 834/MD | 15/03/2024 | 45 | SAI TUBE CO. | 51.27 | 0 | 65
788 | Midnapore Division | Kharagpur Sub-Division | Construction of Pump House & Accommodate FHTC (240 Nos.) under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000862/2023-2024 | 835/MD | 15/03/2024 | 60 | HYDROTECH ASSOCIATES | 20.6 | 0 | 60
789 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution Pipeline under JJM with allied work for Rupnarayanpur & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000898/2023-2024 | 836/MD | 15/03/2024 | 45 | S.B. ENTERPRISE | 25.73 | 0 | 88
790 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000276/2023-2024 | 4049/MD | 12/10/2023 | 0 | Resource Division | 15.84 | 0 | 0
791 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (2835 Nos.) under JJM with allied work for Augmentation of Srinagar Pipe W/S Scheme in Chandrakona-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000181/2023-2024 | 2721/MD | 31/07/2023 | 1059 | M/S. D.K.H.CONSTRUCTION | 239.56 | 0 | 11
792 | Midnapore Division | Ghatal Subdivision | Damaged UPVC pipeline & withdrawing of CI PIPE and replace with DI pipe & allied works in Srinagar W/S Scheme under Ghatal Sub-Division PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000379/2023-2024 | 4041/MD | 11/10/2023 | 15 | SAYEEDI CONSTRUCTION | 2.12 | 0 | 100
793 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 2 Nos. PWSS within Ghatal & Chandrakona-I blocks under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000737/2022-2023 | 2684/MD | 30/12/2022 | 21 | SIRCON ENGINEERING SERVICES | 8.23 | 0 | 100
794 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000199/2023-2024 | 1420/MD | 04/05/2023 | 0 | Resource Division | 18.38 | 0 | 0
795 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum OHR each (Intze type with pile foundation) & Accommodate FHTC (6283 Nos.) under JJM with allied work for Purshuri & Ramkrishnapur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000075/2023-2024 | 2422/MD | 13/07/2023 | 808 | GOBINDA MAITY | 1504.9 | 0 | 60
796 | Midnapore Division | Ghatal Subdivision | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000380/2024-2025 | 55/MD | 07/01/2025 | 266 | GOBINDA MAITY | 79.62 | 0 | 60
797 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000119/2022-2023 | 1162/MD | 25/04/2023 | 0 | Resource Division | 52.06 | 0 | 0
798 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 300 Cum & 400 Cum RCC Over Head Reservoir (Intze type with Pile Foundation) & Accommodate FHTC (4,797 Nos.) including Two years O&M under JJM with allied work for Teghari & Thaur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000224/2023-2024 | 2924/MD | 16/08/2023 | 927 | M/S. A.R. ENTERPRISE. | 1490.96 | 0 | 49
799 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000022/2023-2024 | 1163/MD | 26/04/2023 | 0 | Resource Division | 33.8 | 0 | 0
800 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Basanchhara & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000098/2022-2023 | 1018/MD | 27/05/2022 | 20 | SIRCON ENGINEERING SERVICES | 6 | 0 | 100
801 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,044 Nos.) under JJM including Two years O&M with allied work for Basanchhara PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000273/2023-2024 | 3260/MD | 12/09/2023 | 907 | M/S. D.K.H.CONSTRUCTION | 776.36 | 0 | 70
802 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000013/2024-2025 | 3334/MD | 25/11/2024 | 0 | Resource Division | 10.6 | 0 | 0
803 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000289/2023-2024 | 4061/MD | 12/10/2023 | 0 | Resource Division | 47.34 | 0 | 0
804 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000038/2022-2023 | 111/MD | 10/01/2023 | 0 | Resource Division | 32.36 | 0 | 0
805 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000167/2023-2024 | 1456/MD | 08/05/2023 | 0 | Resource Division | 10.16 | 0 | 0
806 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway under Saiyadpur PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000456/2024-2025 | 373/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 11.88 | 0 | 0
807 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000152/2023-2024 | 1271/MD | 28/04/2023 | 0 | Resource Division | 21.29 | 0 | 0
808 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
809 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000165/2023-2024 | 1451/MD | 08/05/2023 | 0 | Resource Division | 29.23 | 0 | 0
810 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well ,Laying of Rising Main ,Laying distribution pipe line, Pump House , Boundary Wall , soil investigation , 100 cum OHR( Torch type with solid raft ) & Accommodate FHTC (529 Nos.) including 2 years operation & maintenance under JJM with allied work for Nanasol & its adjoining mouzas W/S scheme in Salbani Block including supply of all labour & materials within Medinipur Sadar Sub-division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000390/2023-2024 | 5064/MD | 26/10/2023 | 180 | ASHIM KUMAR DEY | 218.49 | 0 | 15
811 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000266/2023-2024 | 2224/MD | 15/06/2023 | 0 | Resource Division | 20.41 | 0 | 0
812 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Augmentation of Salboni PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000191/2025-2026 | 1630/MD | 06/08/2025 | 21 | PIONEER SURVEYORS | 10.84 | 0 | 0
813 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Soil investigation, 450 cum OHR (Intze type with solid Raft) & Accommodate FHTC (3,272 Nos.) under JJM with allied work for Augmentation of Salboni Pipe Water Supply Scheme under Salbani Block including supply of all labour & materials within Medinipur Sadar Sub-Division under Medinipur Division, PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000395/2023-2024 | 5069/MD | 26/10/2023 | 752 | IJABUL SEKH | 552.44 | 0 | 70
814 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 150 cum OHR (Intze type with solid raft) & Accommodate FHTC (1014 Nos) including 2 years operation & maintenance under JJM with allied work for Shyampur & its adjoining mouzas W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000236/2023-2024 | 3039/MD | 22/08/2023 | 720 | CREATION CONSTRUCTION | 272.66 | 0 | 70
815 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000222/2023-2024 | 1513/MD | 12/05/2023 | 0 | Resource Division | 28.97 | 0 | 0
816 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 500 & 600 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,406 nos.) under JJM with allied work for Gopalnagar & Kalara PWSS in Daspur-I Block including supply of all labour & materials including Two (02) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000229/2023-2024 | 2953/MD | 17/08/2023 | 772 | GOBINDA MAITY | 1693.15 | 0 | 20
817 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kalara & its adjoining Mouzas PWSS instead Radhakantapur its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000745/2022-2023 | 1263/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.73 | 0 | 100
818 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000015/2024-2025 | 3336/MD | 25/11/2024 | 0 | Resource Division | 17.48 | 0 | 0
819 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000067/2022-2023 | 95/MD | 10/01/2023 | 0 | Resource Division | 192.26 | 0 | 0
820 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000160/2022-2023 | 1156/MD | 25/04/2023 | 0 | Resource Division | 33.76 | 0 | 0
821 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 & 450 cum OHRs (Intze type) & Accommodate FHTC (4,203 Nos.) under JJM with allied work for (1) Gohaldanga & (2) Haridharpur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000252/2023-2024 | 3147/MD | 29/08/2023 | 718 | BANERJEE CONSTRUCTION | 1062.73 | 0 | 30
822 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000004/2024-2025 | 3325/MD | 25/11/2024 | 0 | Resource Division | 19.11 | 0 | 0
823 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000069/2022-2023 | 91/MD | 10/01/2023 | 0 | Resource Division | 31.55 | 0 | 0
824 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum & 150 cum OHRs & Accommodate FHTC (3,462 Nos.) including Two years O&M under JJM with allied work for Bhetia (Zone-I, II, III & IV) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000753/2023-2024 | 216/MD | 31/01/2024 | 786 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1062.32 | 0 | 70
825 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000018/2023-2024 | 1164/MD | 26/04/2023 | 0 | Resource Division | 72.2 | 0 | 0
826 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 350 Cum & 300 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,209 Nos) including 2 years operation & maintenance For Golegram and Kanakpur Pipe water supply Scheme within Debra Block under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000386/2023-2024 | 5060/MD | 26/10/2023 | 613 | IJABUL SEKH | 992.27 | 0 | 45
827 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000219/2023-2024 | 1516/MD | 12/05/2023 | 0 | Resource Division | 34.57 | 0 | 0
828 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Bhutna & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000093/2022-2023 | 673/MD | 11/04/2022 | 20 | GOBINDA MAITY | 8.37 | 0 | 100
829 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, 350 Cum & 250 cum OHR (Zone- I & II) (Intze type with pile foundation) & Accommodate FHTC (3,339 Nos.) including Two years O&M under JJM with allied work for Bhuta (Zone- I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000392/2023-2024 | 5066/MD | 26/10/2023 | 898 | M/S. SOURABH KUMAR ROY | 838.26 | 0 | 0
830 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000241/2023-2024 | 1523/MD | 12/05/2023 | 0 | Resource Division | 59.93 | 0 | 0
831 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000021/2021-2022 | 2165/MD | 17/12/2021 | 0 | Resource Division | 0.05 | 0 | 0
832 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000043/2021-2022 | 498/MD | 15/03/2022 | 0 | Resource Division | 15.18 | 0 | 0
833 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Chandalbandh PWSS in Nayagram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | VCH/001386/2021-2022 | BP-2021-22-395 | 22/02/2022 | 0 | RADIANT | 3.78 | 0 | 0
834 | Midnapore Division |  | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR / CWR locations of different proposed piped water supply scheme at Jhargram district under Drinking Water Mitigation Master Plan. [Name of proposed Scheme - Sankrail, Bakra, Ragra (Zone-I & Zone-II) & Nakrasuli of Sankrail Block, Pithapura, Chorchita, Mahapal, Dhadangiri, Kendana, Tentulia, Gohal Mara & Kuliana of Gopiballavpur-II Block, Sijua, Shaluka & Bandarboni of Binpur-I Block, Naharia of Jamboni Block in Jhargram district.] |  |  | ORD/000543/2021-2022 | 53/MD | 13/01/2022 | 60 | DR. GOKUL MONDAL (PHD, PROFESSOR), | 81.24 | 0 | 0
835 | Midnapore Division |  | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR / CWR locations of different proposed piped water supply scheme at Jhargram district under Drinking Water Mitigation Master Plan. [Name of proposed Scheme - Sankrail, Bakra, Ragra (Zone-I & Zone-II) & Nakrasuli of Sankrail Block, Pithapura, Chorchita, Mahapal, Dhadangiri, Kendana, Tentulia, Gohal Mara & Kuliana of Gopiballavpur-II Block, Sijua, Shaluka & Bandarboni of Binpur-I Block, Naharia of Jamboni Block in Jhargram district.] |  |  | VCH/000288/2022-2023 | BP-2021-22-553 | 04/04/2022 | 0 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0
836 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Aulia PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000181/2020-2021 | 1410/MD | 26/11/2020 | 180 | GOUTAM PARIA | 14.09 | 12.14 | 0
837 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Simulpal PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000185/2020-2021 | 1408/MD | 26/11/2020 | 180 | GOUTAM RAY | 14.62 | 12.54 | 0
838 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Netai PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000286/2020-2021 | 1584/MD | 11/12/2020 | 180 | BIDYUT KUMAR SANTRA | 40.78 | 19.54 | 1
839 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Khasjungle PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001366/2021-2022 | 8443122 | 25/02/2022 | 0 | M/S. SOMNATH | 7.01 | 0 | 0
840 | Midnapore Division | Ghatal Subdivision | Hire bill of vehicle No. WB 25L3164 for the month of March 2023 Under the O/O the SE/WC, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | BILL/00503/2023-2024 | 8443133 | 26/06/2023 | 0 | BISWADIP SIKDAR | 0.4 | 0 | 0
841 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Ranapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000207/2020-2021 | 1429/MD | 26/11/2020 | 180 | KISHORE GHOSH | 92.88 | 73.29 | 0
842 | Midnapore Division | Ghatal Subdivision | Exingeny basis laying casing pipe under Bitumineous pucca road crosssing near Oil Meal,Mondal Hard Works of Khakurda to Ghatal PWD Road of Ranapur W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000525/2022-2023 | 172/AE/GSD | 01/04/2022 | 2 | WATER LINK | 2.22 | 0 | 0
843 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Ranapur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000742/2020-2021 |  | 15/12/2020 | 0 | KISHORE GHOSH | 90 | 0 | 0
844 | Midnapore Division | Kharagpur Sub-Division | Extension of pipe line From Adasimla G.P. office to Harijan Pally under Adasimla & its adjoining mouzas water supply Scheme at Sabang Block under Kharagpur Sub Division within Midnapore Division, P.H.E.Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000106/2021-2022 | 311/AE/KSD | 16/07/2021 | 30 | SAI TUBE CO. | 4.78 | 0 | 0
845 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Adasimla W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000281/2020-2021 | 1462/MD | 26/11/2020 | 1643 | SAI TUBE CO. | 94.76 | 49.55 | 100
846 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Adasimla Piped Water Supply Scheme | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001413/2022-2023 | 844397 | 30/11/2022 | 0 | SAI TUBE CO. | 4.64 | 0 | 0
847 | Midnapore Division | Kharagpur Sub-Division | FHTC imis data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001636/2021-2022 | 8443147 | 24/03/2022 | 0 | PAPPU SHAW | 0.15 | 0 | 0
848 | Midnapore Division | Kharagpur Sub-Division | FHTC imis data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001637/2021-2022 | 8443147 | 24/03/2022 | 0 | SIDDHESWAR BAG | 0.16 | 0 | 0
849 | Midnapore Division | Kharagpur Sub-Division | FHTC imis data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001638/2021-2022 | 8443147 | 24/03/2022 | 0 | SUBRATA CHAKRABORTY | 0.09 | 0 | 0
850 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Barisha (Zone-II) W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000216/2020-2021 | 1434/MD | 26/11/2020 | 180 | UTTAM KUMAR DAS | 97.01 | 44.07 | 0
851 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | RTOR000105/2024-2025 | 3408/MD | 25/11/2024 | 0 | Resource Division | 12.42 | 0 | 0
852 | Midnapore Division | Kharagpur Sub-Division | Construction of SSP & Soak Pit at different places laying of pipe line of Barisha Zone -II . | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/000276/2022-2023 | BP-2022-23-34 | 29/04/2022 | 0 | BIDHAN CHANDRA PATRA | 2.82 | 0 | 0
853 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000271/2020-2021 | 1468/MD | 26/11/2020 | 180 | MASUM ALI KHAN | 86.17 | 35.71 | 100
854 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bhemwa (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000729/2020-2021 |  | 15/12/2020 | 0 | MASUM ALI KHAN | 20 | 0 | 0
855 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001414/2020-2021 | 8443461 | 26/03/2021 | 0 | ARUP KR ADAK | 0.07 | 0 | 0
856 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001415/2020-2021 | 8443461 | 26/03/2021 | 0 | PRATHA PRATIM PAL | 0.2 | 0 | 0
857 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data entry in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001416/2020-2021 | 8443461 | 26/03/2021 | 0 | ANIRBAN CHAKRABORTY | 0.17 | 0 | 0
858 | Midnapore Division | Kharagpur Sub-Division | FHTC imis data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001626/2021-2022 | 8443148 | 24/03/2022 | 0 | MANABENDRA DAS | 0.15 | 0 | 0
859 | Midnapore Division | Kharagpur Sub-Division | FHTC imis data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001627/2021-2022 | 8443148 | 24/03/2022 | 0 | NABOGOPAL ADHIKARI | 0.08 | 0 | 0
860 | Midnapore Division | Kharagpur Sub-Division | FHTC imis data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001629/2021-2022 | 8443148 | 24/03/2022 | 0 | SANDIP MANNA | 0.09 | 0 | 0
861 | Midnapore Division | Kharagpur Sub-Division | Laying of Rising main including interconnection pipeline for Gopinathpur W/S Scheme within Pingla block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Length - 350.00 Mtr.) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000313/2024-2025 | 3406/MD | 25/11/2024 | 45 | MAA SARADA ENTERPRISE | 3.62 | 0 | 0
862 | Midnapore Division | Kharagpur Sub-Division | Laying additional distribution pipeline to accommodate FHTC & allied work for Gopinathpur PWSS under Pingla block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000327/2024-2025 | 3570/MD | 06/12/2024 | 75 | ASHOK BANERJEE | 82.67 | 0 | 0
863 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Gopinathpur W/S Scheme in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000471/2022-2023 | 2189/MD | 01/11/2022 | 180 | BANERJEE CONSTRUCTION | 410.37 | 0 | 56
864 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000011/2023-2024 | 1146/MD | 25/04/2023 | 0 | Resource Division | 16.15 | 0 | 0
865 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM at Mouza Pitanaw PWSS water supply scheme. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | BILL/00726/2022-2023 | BP-2022-23-518 | 01/02/2023 | 0 | AJITESH ACHARJEE | 0.52 | 0 | 0
866 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Pitanow PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000049/2022-2023 | 869/MD | 10/05/2022 | 15 | AJITESH ACHARJEE | 6 | 0 | 0
867 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Sankrail PWSS of Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000051/2021-2022 | 878/MD | 08/06/2021 | 15 | PULLOCK KUMAR GHOSH | 5.5 | 5.15 | 0
868 | Midnapore Division | Gopiballavpur Sub Division | Sinking of 200 mm x 150 mm dia and depth 110 mtr. Rig bore Tubewell (Replacement) for Pathardhara W/S Scheme i.c.w providing F.H.T.C. under Jhargram Sub Division within Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000277/2021-2022 | 238/JSD | 24/09/2021 | 14 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.67 | 0 | 1
869 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Bartilaboni PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000359/2020-2021 | 580/JSD | 01/02/2021 | 10 | J.S.S. ENTERPRISE | 0.71 | 0 | 0
870 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Logan PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000361/2020-2021 | 582/JSD | 01/02/2021 | 30 | J.S.S. ENTERPRISE | 4.38 | 0 | 0
871 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Barabaria PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000363/2020-2021 | 587/JSD | 01/02/2021 | 15 | BISHNU PADA NANDI | 2.27 | 2.02 | 0
872 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS of Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000364/2020-2021 | 588/JSD | 01/02/2021 | 15 | DHUMKETU ENGINEERING PRIVATE LIMITED | 2.53 | 2.38 | 0
873 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Baratilaboni PWSS (Phase-II) Block - Binpur-I in the District of Jhargram | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000396/2021-2022 | 348/JSD | 23/11/2021 | 7 | J.S.S. ENTERPRISE | 2.59 | 0 | 1
874 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Bhangabandh PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000508/2020-2021 | 381/MD | 25/02/2021 | 15 | SAIKAT DANDAPAT | 7.78 | 7.95 | 0
875 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Domsole PWSS of Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000509/2020-2021 | 382/MD | 25/02/2021 | 15 | S.B. TRADERS | 5.24 | 3.95 | 1
876 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting to accommodate FHTC under JJM in Bhera PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | VCH/001388/2021-2022 | BP-2021-22-393 | 22/02/2022 | 0 | NIRMAL DUTTA | 1.43 | 0 | 0
877 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Dontarda, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000486/2021-2022 | 2179/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 31.32 | 0 | 100
878 | Midnapore Division | Kharagpur Sub-Division | Sinking of different Tube-well. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001806/2021-2022 | BP-2021-22-523 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.66 | 0 | 0
879 | Midnapore Division | Kharagpur Sub-Division | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001816/2021-2022 | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.08 | 0 | 0
880 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sitanathpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000567/2020-2021 | 61/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.57 | 1.44 | 0
881 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sitanathpur PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. (2nd Call) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000631/2021-2022 | 184/MD | 01/02/2022 | 1155 | DEBJIT PATRA | 25.18 | 0 | 75
882 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte.61/MD | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001117/2020-2021 |  | 19/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.49 | 0 | 0
883 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Bhimpur PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000684/2021-2022 | 234/MD | 08/02/2022 | 45 | DIPAK KUMAR BAKLY | 36.72 | 0 | 0
884 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Bhimpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000864/2020-2021 | 348/MD | 25/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.99 | 1.97 | 0
885 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Kalaimuri PWSS to accommodate FHTC under JJM under Salboni Block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000506/2021-2022 | 2248/MD | 28/12/2021 | 45 | NIMAI HAZRA | 25.66 | 0 | 0
886 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kalaimuri, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000569/2020-2021 | 64/MD | 11/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.14 | 1.57 | 0
887 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001120/2020-2021 |  | 19/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.57 | 0 | 0
888 | Midnapore Division | Gopiballavpur Sub Division | Retrofitting and allied works to accommodate FHTC under JJM in Laudaha PWSS within Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | ORD/000227/2021-2022 | 1535/MD | 13/09/2021 | 15 | S.T. ENTERPRISE | 29.73 | 18.15 | 1
889 | Midnapore Division | Gopiballavpur Sub Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Sasarah PWSS in Gopiballavpur-I Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer | JE (M),Junior Engineer Sankrail block | VCH/001596/2021-2022 | BP-2021-22-403 | 23/02/2022 | 0 | ROY CHOWDHURY ASSOCIATES | 1.67 | 0 | 0
890 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS (2nd Phase), Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000188/2021-2022 | 1464/MD | 07/09/2021 | 45 | M/S. D.K.H.CONSTRUCTION | 73.12 | 35.9 | 0
891 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Bhabanipur PWSS (2nd Phase), Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000207/2021-2022 | 1443/MD | 03/09/2021 | 15 | SAMIT PAL | 23.91 | 8.18 | 0
892 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Pratappur PWSS (2nd Phase) in Ghatal Block in the district of Paschim Medinipur. | AE Ghatal Sub-division |  | ORD/000210/2021-2022 | 1445/MD | 03/09/2021 | 60 | DIPAK KUMAR DOLAI | 135.13 | 18.3 | 0
893 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS (2nd Phase), Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000231/2021-2022 | 1469/MD | 07/09/2021 | 10 | M/S ZAMAN ENTERPRISE | 10.84 | 0 | 0
894 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum (Intze type with Pile Foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Dasha Gram and its adjoining mouzas W/S Scheme in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000372/2022-2023 | 1956/MD | 20/09/2022 | 1271 | M/S. A.R. ENTERPRISE. | 512.44 | 0 | 60
895 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Proposed Pipe Water Supply Scheme for Dashagram & its adjoining mouza within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000439/2021-2022 | 1691/MD | 30/09/2021 | 10 | GOBINDA MAITY | 2.74 | 0 | 0
896 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of Rising Main including Interconnection, Construction of Pump House & Boundary wall for Dasha Gram & its adjoining mouzas W/S Scheme in Sabang block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000615/2022-2023 | 441/MD | 10/02/2023 | 963 | M/S. A.R. ENTERPRISE. | 44.01 | 0 | 20
897 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000002/2023-2024 | 940/MD | 05/04/2023 | 0 | Resource Division | 28.23 | 0 | 0
898 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000026/2022-2023 | 137/MD | 11/01/2023 | 0 | Resource Division | 15.83 | 0 | 0
899 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000143/2022-2023 | 514/MD | 20/02/2023 | 0 | Resource Division | 28.24 | 0 | 0
900 | Midnapore Division | Ghatal Subdivision | Electric Quotation. {Enter in MB No:- 3068, Page No:- 165} | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00061/2022-2023 | BP-2022-23-468 | 27/12/2022 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.46 | 0 | 0
901 | Midnapore Division | Ghatal Subdivision | QUOTATION MONEY FOR PANNA WATER SUPPLY SCHEME, T W NO 2, [ BLOCK GHATAL ] JJM WORKS, SCHEME CODE SM/110065, APPLICATION NO 2004843733, REFERENCE ID 204368914, GHATAL CCC, WBSEDCL | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00499/2024-2025 | BP-2024-25-458 | 12/11/2024 | 0 | WBSEDCL | 5.57 | 0 | 0
902 | Midnapore Division | Ghatal Subdivision | Sinking of 200 mm x 100 mm dia. X 156 Mtr. Depth Rig bored Tube wells at Head Works cum 1st Tube well site with Laying of uPVC (Class-III) & DI pipeline, Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room & Boundary wall for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- A) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000208/2022-2023 | 1673/MD | 12/08/2022 | 872 | M/S. D.K.H.CONSTRUCTION | 65.06 | 0 | 100
903 | Midnapore Division | Ghatal Subdivision | Sinking of 200 mm x 100 mm dia. X 156 Mtr. Depth Rig bored Tube wells at 2nd Tube well site with Laying of uPVC (Class-III) & DI pipeline with FHTC works, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room & Boundary wall, Laying of Rising main at 2nd T/W site for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- B) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000466/2022-2023 | 2186/MD | 01/11/2022 | 878 | S.N ENTERPRISE | 67.2 | 0 | 5
904 | Midnapore Division | Ghatal Subdivision | Soil investigation work in connection with Construction of RCC OHR, Construction & Commissioning of 150 CuM RCC OHR with FHTC works for Panna W/S Scheme within Ghatal Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART- C) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000542/2022-2023 | 2673/MD | 30/12/2022 | 880 | CHAKRABORTTI ENTERPRISE | 86.3 | 0 | 12
905 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000007/2023-2024 | 1134/MD | 24/04/2023 | 0 | Resource Division | 21.77 | 0 | 0
906 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000029/2022-2023 | 135/MD | 11/01/2023 | 0 | Resource Division | 4.73 | 0 | 0
907 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000166/2022-2023 | 888/MD | 30/03/2023 | 0 | Resource Division | 21.77 | 0 | 0
908 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground water based piped water supply scheme for Bhikni Nischintapur (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur District Under Midnapur Division PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000151/2022-2023 | 1420/MD | 15/07/2022 | 45 | WATER LINK | 50.72 | 0 | 80
909 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Bhikni Nischintapur PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000428/2021-2022 | 1660/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.12 | 0 | 100
910 | Midnapore Division | Ghatal Subdivision | Sinking of (Two) nos. 250 X 150 mm dia. X 120 mtr. Depth deep tube well by direct rotary method for Kutulpur & adjoining mouzas W/S Scheme within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000109/2023-2024 | 2491/MD | 17/07/2023 | 14 | MIDNAPUR PIPE CONCERN | 13.37 | 0 | 100
911 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 250 Cum ( Pile Foundation) and staging height 20.00 mtr. & FHTC under JJM with allied work for Kotulpur and its adjoining mouzas W/S scheme in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000374/2022-2023 | 1957/MD | 20/09/2022 | 1271 | DIPAK KUMAR DOLAI | 306.49 | 0 | 72
912 | Midnapore Division | Ghatal Subdivision | Laying of rising main & inter connection for Kutulpur & its adjoining mouzas PWSS within block - Ghatal, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000511/2024-2025 | 621/MD | 05/03/2025 | 45 | SUBHASIS DOLAI | 5.67 | 0 | 0
913 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000124/2022-2023 | 337/MD | 31/01/2023 | 0 | Resource Division | 18.14 | 0 | 0
914 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric Quotation for Antla PWSS Tube well-I in connection Mohanpur CCC. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00073/2023-2024 | BP-2023-24-31 | 01/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.72 | 0 | 0
915 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric Quotation for Antla PWSS Tube well-II in connection Mohanpur CCC. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00074/2023-2024 | BP-2023-24-30 | 01/05/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 2.99 | 0 | 0
916 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric quotation bill for Atla Water supply Scheme at PH-II (Consumar Id-860286126) [MB-No- 3179/MMD] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00990/2023-2024 | BP-2023-24-509 | 15/12/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 2.88 | 0 | 0
917 | Midnapore Division | Midnapur Mechanical Sub Division-I | Supply & delivery of different dia. C.I.D.F. Sluice Valves for laying of Distribution main pipeline for Antla Piped water Supply Scheme within Mohanpur Block under Kharagpur Sub-division of Midnapore Division, PHE Dte. In Paschim Medinipur District (Part -II) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000085/2022-2023 | 312/AE/KSD | 10/06/2022 | 15 | GOBINDA MAITY | 3.51 | 0 | 0
918 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of distribution HDPE Pipe line of Left-Out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division of Midnapore Division, PHE Dte. (Phase-I) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000231/2022-2023 | 536/AE/KSD | 23/08/2022 | 30 | PALASH KUMAR DAS | 4.81 | 0 | 0
919 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-II) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000232/2022-2023 | 537/AE/KSD | 23/08/2022 | 30 | PALASH KUMAR DAS | 4.78 | 0 | 0
920 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of distribution HDPE pipe line of Left-out portion and all allied works at Antla and its adjoining mouzas W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. (Phase-III) Location Mathuribar ICDS & Kharpara | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000233/2022-2023 | 538/AE/KSD | 23/08/2022 | 30 | PALASH KUMAR DAS | 4.85 | 0 | 0
921 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for Second Tube Well Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type -A) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000239/2022-2023 | 544/AE/KSD | 23/08/2022 | 30 | PRITI ENTERPRISE | 2.79 | 0 | 0
922 | Midnapore Division | Midnapur Mechanical Sub Division-I | Soil Investigation, Construction of R.C.C. Elevated Reservoir of Capacity 400 cum and staging height 20.00 mtr. (Pile Foundation) with allied works, Laying Distribution System of HDPE (PE-100) and Providing of FHTC for Antla and its adjoining mouzas Water Supply Scheme within Mohanpur Block in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000515/2021-2022 | 2255/MD | 28/12/2021 | 1250 | MASUM ALI KHAN | 332.28 | 0 | 99
923 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Pipe Water Supply Scheme for Antla & its adjoining Mouzas, Block: - Mohanpur, District: - Paschim Midnapore. (Total Length = 11,200.00 Mtr.) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000611/2022-2023 | 383/MD | 03/02/2023 | 60 | MASUM ALI KHAN | 53.34 | 0 | 0
924 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site under Antla W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type - A) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000619/2022-2023 | 444/MD | 13/02/2023 | 60 | MASUM ALI KHAN | 5.21 | 0 | 0
925 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 220 Mtr. Depth deep tube well by Direct Rotary Method for Head Work site & 2nd Tube well site of Antla W/S Scheme with in Mohanpur block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000692/2021-2022 | 289/MD | 15/02/2022 | 15 | KISHORE GHOSH | 21.82 | 0 | 100
926 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000001/2023-2024 | 932/MD | 04/04/2023 | 0 | Resource Division | 57.12 | 0 | 0
927 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000004/2022-2023 | `2430/MD | 29/11/2022 | 0 | Resource Division | 82.33 | 0 | 0
928 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000038/2021-2022 | 148/MD | 28/01/2022 | 0 | Resource Division | 10.97 | 0 | 0
929 | Midnapore Division | Kharagpur Sub-Division | Continuation Work order For "Casual hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of (01.08.2024 to 31.01.2025) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use under Midnapore Division, PHE Dte." | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000062/2024-2025 | 2338/MD | 30/07/2024 | 183 | PULLOCK KUMAR GHOSH | 0.87 | 0 | 0
930 | Midnapore Division | Kharagpur Sub-Division | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000119/2021-2022 | 1008/MD | 24/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 4.22 | 0 | 100
931 | Midnapore Division | Kharagpur Sub-Division | Preparation of DPR with allied works in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000120/2021-2022 | 1009/MD | 24/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.19 | 0 | 100
932 | Midnapore Division | Kharagpur Sub-Division | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block ¿ Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000153/2021-2022 | 965/MD | 18/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.9 | 0 | 100
933 | Midnapore Division | Kharagpur Sub-Division | Construction of Boundary wall at Head work site for Augmentation of Belda (Zone-I) W/S Scheme within Narayangarh Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000382/2024-2025 | 57/MD | 07/01/2025 | 360 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 13.65 | 0 | 75
934 | Midnapore Division | Kharagpur Sub-Division | Repairing of Damage pipe line (AC) at Mouza Deuli, Kusmuri, Sarisha of Belda Zone II W/S Scheme within Narayangarh Block under Kharagpur Sub-Division under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000397/2021-2022 | 496/AE/KSD | 30/11/2021 | 30 | NIMAI LAL GURIA | 0.52 | 0 | 100
935 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 200 Cum and staging height 20.00 mtr. with allied work under Augmentation of Belda Zone-II & its adjoining moujas Water Supply Scheme within Narayangarh Dev. Block including supply of all labour & materials under Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000470/2022-2023 | 2188/MD | 01/11/2022 | 180 | BANERJEE CONSTRUCTION | 558.93 | 0 | 50
936 | Midnapore Division | Kharagpur Sub-Division | Continuation Work order For "Casual hiring of Inspection vehicle for Jal Jeevan Mission as and when required basis Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure from 01.02.2025 to 31.07.2025 only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use under Midnapore Division, PHE Dte." | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000548/2024-2025 | 308/MD | 28/01/2025 | 180 | PULLOCK KUMAR GHOSH | 0.86 | 0 | 0
937 | Midnapore Division | Kharagpur Sub-Division | Sinking of (Two) nos. 300 X 200 mm dia. X 200mtr. depth deep tube well by direct rotary method for Augmentation of Belda PWSS (Zone-I & II) with in Narayangarh Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000664/2022-2023 | 583/MD | 23/02/2023 | 14 | M/S. A.R. ENTERPRISE. | 23.69 | 0 | 80
938 | Midnapore Division | Kharagpur Sub-Division | Continuation Work Order for the work of Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Belda, Block - Narayangarh) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001090/2021-2022 | 1108/MD | 09/07/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.74 | 0 | 100
939 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000025/2022-2023 | 132/MD | 11/01/2023 | 0 | Resource Division | 38.43 | 0 | 0
940 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000130/2024-2025 | 3466/MD | 25/11/2024 | 0 | Resource Division | 1.63 | 0 | 0
941 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000170/2023-2024 | 1364/MD | 02/05/2023 | 0 | Resource Division | 49.19 | 0 | 0
942 | Midnapore Division | Ghatal Subdivision | Laying of Rising main pipeline for Kelegoda PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000060/2024-2025 | 2651/MD | 28/08/2024 | 180 | SAMIR PATRA | 5.12 | 0 | 100
943 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000514/2022-2023 | 2556/MD | 15/12/2022 | 1238 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 18
944 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kelegoda & its adjoining Mouzas PWSS Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000928/2021-2022 | 529/MD | 21/03/2022 | 20 | GOBINDA MAITY | 4.86 | 0 | 0
945 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000005/2023-2024 | 944/MD | 05/04/2023 | 0 | Resource Division | 26.63 | 0 | 0
946 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000024/2024-2025 | 3343/MD | 25/11/2024 | 0 | Resource Division | 10.47 | 0 | 0
947 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000131/2023-2024 | 1321/MD | 28/04/2023 | 0 | Resource Division | 25.15 | 0 | 0
948 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
949 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000101/2023-2024 | 1238/MD | 27/04/2023 | 0 | Resource Division | 23.72 | 0 | 0
950 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000119/2023-2024 | 1311/MD | 28/04/2023 | 0 | Resource Division | 30.52 | 0 | 0
951 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
952 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000099/2022-2023 | 185/MD | 16/01/2023 | 0 | Resource Division | 15.33 | 0 | 0
953 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000111/2024-2025 | 3447/MD | 25/11/2024 | 0 | Resource Division | 14.89 | 0 | 0
954 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000141/2023-2024 | 1260/MD | 28/04/2023 | 0 | Resource Division | 22.87 | 0 | 0
955 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000057/2023-2024 | 1201/MD | 26/04/2023 | 0 | Resource Division | 26.92 | 0 | 0
956 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Bhagirathpur (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000222/2022-2023 | 1729/MD | 23/08/2022 | 150 | PULLOCK KUMAR GHOSH | 43.24 | 0 | 75
957 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Bhagirathpur (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000223/2022-2023 | 1730/MD | 23/08/2022 | 150 | PULLOCK KUMAR GHOSH | 50.14 | 0 | 70
958 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Jamira & (ii) Bhagirathpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000414/2021-2022 | 1312/MD | 16/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.75 | 0 | 0
959 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000041/2024-2025 | 3350/MD | 25/11/2024 | 0 | Resource Division | 2.87 | 0 | 0
960 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 20
961 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000065/2023-2024 | 1281/MD | 28/04/2023 | 0 | Resource Division | 29.36 | 0 | 0
962 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
963 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000090/2023-2024 | 1292/MD | 28/04/2023 | 0 | Resource Division | 31.46 | 0 | 0
964 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000103/2023-2024 | 2485/MD | 17/07/2023 | 521 | A R ENTERPRISE | 18.49 | 0 | 70
965 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 Nos. Tube well & Accommodate FHTC (100 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000110/2023-2024 | 2511/MD | 18/07/2023 | 45 | DEBASISH DOGRA | 21.94 | 0 | 70
966 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Rising main & Accommodate FHTC (400 Nos.) including 2 yrs. O & M under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000148/2023-2024 | 2639/MD | 24/07/2023 | 723 | GOUTAM RAY | 138.15 | 0 | 70
967 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Pump House, Boundary wall & Accommodate FHTC (216 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000416/2023-2024 | 5152/MD | 07/11/2023 | 663 | BISWAS CONSTRUCTION | 45.23 | 0 | 81
968 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (200 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000521/2023-2024 | 5500/MD | 14/12/2023 | 45 | MAHARAJA CONSTRUCTION CO. | 43.39 | 0 | 40
969 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of RCC OHR (150 CuM) & Accommodate FHTC (200 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000547/2024-2025 | 738/MD | 19/03/2025 | 180 | SAMIT PAL | 83.17 | 0 | 0
970 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000153/2022-2023 | 536/MD | 21/02/2023 | 0 | Resource Division | 9.38 | 0 | 0
971 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
972 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000052/2024-2025 | 3372/MD | 25/11/2024 | 0 | Resource Division | 14.24 | 0 | 0
973 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 65
974 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
975 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000012/2023-2024 | 1145/MD | 25/04/2023 | 0 | Resource Division | 22.96 | 0 | 0
976 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0
977 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000130/2023-2024 | 1322/MD | 28/04/2023 | 0 | Resource Division | 28.03 | 0 | 0
978 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
979 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000106/2022-2023 | 217/MD | 16/01/2023 | 0 | Resource Division | 14.02 | 0 | 0
980 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000121/2024-2025 | 3457/MD | 25/11/2024 | 0 | Resource Division | 11.03 | 0 | 0
981 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
982 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 20
983 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000083/2022-2023 | 192/MD | 16/01/2023 | 0 | Resource Division | 17.1 | 0 | 0
984 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000122/2024-2025 | 3458/MD | 25/11/2024 | 0 | Resource Division | 14.16 | 0 | 0
985 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Pump House under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000090/2023-2024 | 2467/MD | 14/07/2023 | 658 | ARNAB PATRA | 7.17 | 0 | 60
986 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) Nos. Tube well for Mahasol & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. (Part-II) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000113/2023-2024 | 2514/MD | 18/07/2023 | 15 | BADAL CHANDRA MAIKAP | 8.13 | 0 | 100
987 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Rising main, distribution pipe line, 2 nos. Pump House, Boundary wall & Accommodate FHTC (800 Nos.) including 2 years operation & maintenance under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000177/2023-2024 | 2717/MD | 31/07/2023 | 754 | M/S. D.K.H.CONSTRUCTION | 241.48 | 0 | 40
988 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000219/2023-2024 | 2872/MD | 10/08/2023 | 45 | DEBJIT PATRA | 16.83 | 0 | 0
989 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 (Two) Nos. Tube well for Mahasol & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. (Part-I) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000220/2023-2024 | 2873/MD | 10/08/2023 | 30 | DEBJIT PATRA | 16.28 | 0 | 100
990 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 250 cum OHR (Intze type with solid raft) & Accommodate FHTC (526 Nos.) under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000335/2024-2025 | 3578/MD | 06/12/2024 | 180 | A R CONSTRUCTION | 111.83 | 0 | 0
991 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000070/2024-2025 | 3388/MD | 25/11/2024 | 0 | Resource Division | 9.4 | 0 | 0
992 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall, soil investigation, 250 Cum OHR ((Intze type with solid raft ) & Accommodate FHTC (2,237 nos.) under JJM with allied work for Kuldiha & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials including 02(Two) Years Operation & Maintanance under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/000010/2024-2025 | 1964/MD | 26/06/2024 | 360 | ANIRUDDHA BAG | 517.34 | 0 | 25
993 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) Nos. Tube well for Kuldiha & its adjoining mouzas PWSS in Kharagpur-II block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/000137/2023-2024 | 2621/MD | 24/07/2023 | 623 | R. CONSTRUCTION | 16.52 | 0 | 50
994 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | RTOR000177/2023-2024 | 1362/MD | 02/05/2023 | 0 | Resource Division | 29.38 | 0 | 0
995 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 200 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1396 Nos.) under JJM with allied work for Kuran PWSS in Ghatal Block including supply of all labour & materials including 2 (Two) years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000640/2022-2023 | 577/MD | 23/02/2023 | 1133 | SUJATA CONSTRUCTION | 385.35 | 0 | 32
996 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Kuran & its adjoining Mouzas PWSS AND (2) Kushman & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000660/2022-2023 | 1766/MD | 24/08/2022 | 30 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.92 | 0 | 0
997 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000034/2024-2025 | 3361/MD | 25/11/2024 | 0 | Resource Division | 8.6 | 0 | 0
998 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000055/2022-2023 | 68/MD | 09/01/2023 | 0 | Resource Division | 15.87 | 0 | 0
999 | Midnapore Division | Ghatal Subdivision | Laying Distribution system pipe line for Shrirampur W/S Scheme under JJM within Ghatal Block under Ghatal Sub-Division under Midnapore Division, PHE Dte. (PART - 'E') | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000034/2024-2025 | 2262/MD | 23/07/2024 | 45 | BHOWMIK CONSTRUCTION | 14.53 | 0 | 0
1000 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000049/2023-2024 | 1432/MD | 04/05/2023 | 608 | AJITESH ACHARJEE | 14.56 | 0 | 40
1001 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Operation & maintenance of 2 years under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000122/2023-2024 | 2493/MD | 17/07/2023 | 60 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.45 | 0 | 60
1002 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000147/2023-2024 | 2637/MD | 24/07/2023 | 313 | HYDRO TECH ASSOCIATES | 9.71 | 0 | 90
1003 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 100
1004 | Midnapore Division | Ghatal Subdivision | Construction of Boundary wall, Soil investigation, 100 cum OHR (Torch type with solid raft) & Accommodate FHTC (667 nos.) under JJM with allied work for Shrirampur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000846/2023-2024 | 807/MD | 15/03/2024 | 180 | M/S. SOURAV MAHAPATRA | 103.06 | 0 | 30
1005 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000136/2022-2023 | 409/MD | 07/02/2023 | 0 | Resource Division | 7.09 | 0 | 0
1006 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House , Boundary Wall soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1809 Nos) under JJM with allied work for Pirachak PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000061/2023-2024 | 2419/MD | 13/07/2023 | 718 | BANERJEE CONSTRUCTION | 484.55 | 0 | 30
1007 | Midnapore Division | Ghatal Subdivision | Laying of rising main & interconnection for Pirchak & its adjoining mouzas PWSS, Block: - Chandrakona-I, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000432/2024-2025 | 318/MD | 29/01/2025 | 45 | MAA SARADA ENTERPRISE | 7.33 | 0 | 0
1008 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000064/2022-2023 | 74/MD | 09/01/2023 | 0 | Resource Division | 34.58 | 0 | 0
1009 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000189/2023-2024 | 1455/MD | 08/05/2023 | 0 | Resource Division | 11.14 | 0 | 0
1010 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
1011 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000033/2023-2024 | 1170/MD | 26/04/2023 | 0 | Resource Division | 33.08 | 0 | 0
1012 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
1013 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Eluni & its adjoining mouzas PWSS, Block ¿ Keshpur, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 1,040 Mtr.). | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000376/2024-2025 | 51/MD | 07/01/2025 | 45 | SAYEEDI CONSTRUCTION | 6.84 | 0 | 0
1014 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000049/2024-2025 | 3369/MD | 25/11/2024 | 0 | Resource Division | 10.82 | 0 | 0
1015 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Rising main & Accommodate FHTC (250 Nos.) including 2 yrs. O & M under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000004/2024-2025 | 1837/MD | 12/06/2024 | 541 | S.T. ENTERPRISE | 141.14 | 0 | 0
1016 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of RCC OHR (150 CuM), Boundary wall & Accommodate FHTC (400 Nos.) under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000306/2024-2025 | 3402/MD | 25/11/2024 | 360 | S.T. ENTERPRISE | 113.63 | 0 | 0
1017 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Pump House & Accommodate FHTC (300 Nos.) under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000850/2023-2024 | 827/MD | 15/03/2024 | 660 | MIDNAPUR PIPE CONCERN | 75.01 | 0 | 40
1018 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000156/2022-2023 | 539/MD | 21/02/2023 | 0 | Resource Division | 14 | 0 | 0
1019 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000144/2023-2024 | 1263/MD | 28/04/2023 | 0 | Resource Division | 16.49 | 0 | 0
1020 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Raghunath chak PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000277/2022-2023 | 552/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 2.36 | 0 | 0
1021 | Midnapore Division | Kharagpur Sub-Division | Laying additional distribution pipeline to accommodate FHTC & allied work for Raghunath Chak PWSS under Pingla block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000328/2024-2025 | 3571/MD | 06/12/2024 | 60 | SANJIT SINHA | 34.47 | 0 | 0
1022 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well, Laying distribution pipe line, Pump House, Balance FHTC (109) & Repair of Pump House & for Augmentation of Raghunathchak PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000626/2022-2023 | 451/MD | 13/02/2023 | 689 | MASUM ALI KHAN | 95 | 0 | 82
1023 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000173/2023-2024 | 1371/MD | 02/05/2023 | 0 | Resource Division | 6.5 | 0 | 0
1024 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
1025 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000709/2022-2023 | 834/MD | 22/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0
1026 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000214/2023-2024 | 1478 | 10/05/2023 | 0 | Resource Division | 43.26 | 0 | 0
1027 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Beluria PWSS within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000426/2021-2022 | 1658/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.18 | 0 | 0
1028 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Rejuvenation of Beluria PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000623/2022-2023 | 448/MD | 13/02/2023 | 45 | BABUSONA CONSTRUCTION | 75.12 | 0 | 80
1029 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000095/2024-2025 | 3428/MD | 25/11/2024 | 0 | Resource Division | 6.27 | 0 | 0
1030 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000113/2023-2024 | 1320/MD | 28/04/2023 | 0 | Resource Division | 45.8 | 0 | 0
1031 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Shyamsundarpur PWSS (2nd Phase) in Sabang block in the district of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000216/2021-2022 | 1449/MD | 03/09/2021 | 60 | M/S. A.R. ENTERPRISE. | 122.79 | 60.6 | 75
1032 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Hatimasan PWSS to accommodate FHTC under JJM under Garhbeta-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000505/2021-2022 | 2247/MD | 28/12/2021 | 15 | NIMAI HAZRA | 17.04 | 0 | 0
1033 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Hatimasan, Block - Garhbeta-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000570/2020-2021 | 65/MD | 11/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.91 | 1.74 | 0
1034 | Midnapore Division | Midnapur Sadar Sub-Division | Accommodate balance FHTC (150 Nos.) and others allied works for Ground Water Based Bhimpur PWSS under JJM of Salboni Block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000107/2023-2024 | 2489/MD | 17/07/2023 | 30 | DIPAK KUMAR BAKLY | 13.72 | 0 | 95
1035 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Bhimpur, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000864/2020-2021 | 348/MD | 25/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.99 | 0 | 0
1036 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000251/2023-2024 | 1581/MD | 15/05/2023 | 0 | Resource Division | 51.23 | 0 | 0
1037 | Midnapore Division | Ghatal Subdivision | Sinking of 2 (Two) nos. 250 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Dhanyagachhi PWSS with in Chandrakona- II block under Midnapore Division, P.H.E Dte. [PART-F] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000004/2023-2024 | 973/MD | 10/04/2023 | 21 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.67 | 0 | 100
1038 | Midnapore Division | Ghatal Subdivision | Laying of Distribution pipe line for Dhanyagachhi & its adjoing mouza Water Supply Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000022/2023-2024 | 1024/MD | 12/04/2023 | 30 | R. CONSTRUCTION | 31.96 | 0 | 100
1039 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for Dhanyagachhi PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE. Dte. [PART-A] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000034/2023-2024 | 1142/MD | 25/04/2023 | 180 | SUJATA CONSTRUCTION | 262.98 | 0 | 30
1040 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000011/2024-2025 | 3332/MD | 25/11/2024 | 0 | Resource Division | 10.85 | 0 | 0
1041 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000082/2022-2023 | 203/MD | 16/01/2023 | 0 | Resource Division | 32.91 | 0 | 0
1042 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer Binpur-I block | ORD/000283/2020-2021 | 1582/MD | 11/12/2020 | 180 | RAMENDRA NATH KAR | 15.06 | 0 | 80
1043 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
1044 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000247/2023-2024 | 1584/MD | 15/05/2023 | 0 | Resource Division | 22.79 | 0 | 0
1045 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 75
1046 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000232/2023-2024 | 1511/MD | 12/05/2023 | 0 | Resource Division | 26.72 | 0 | 0
1047 | Midnapore Division | Kharagpur Sub-Division | Sinking of 1 (One) No. 200 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. [Part-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000106/2023-2024 | 2488/MD | 17/07/2023 | 10 | MAHALAKSHMI ENTERPRISE | 5.88 | 0 | 100
1048 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) Nos. 150 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000142/2023-2024 | 2626/MD | 24/07/2023 | 21 | MIDNAPUR PIPE CONCERN | 11.81 | 0 | 100
1049 | Midnapore Division | Kharagpur Sub-Division | Sinking of 1 (One) No. 200 X 100 mm dia. X 150 Mtr. depth deep tube wells drilling by direct rotary method for Keshuria & its adjoining mouzas PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. [Part-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000143/2023-2024 | 2627/MD | 24/07/2023 | 10 | GOPAL RANA | 6.01 | 0 | 0
1050 | Midnapore Division | Kharagpur Sub-Division | Construction of 250 Cum capacity R.C.C. Over Head Reservoirs including Sub-Soil Investigation work with Laying of distribution system, Pump Houses, Boundary Walls & providing Functional Household Tap Connection (1258 Nos.) including 02 (Two) years O & M for KESHURIA (ZONE-I,II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2025-2026 | 1778/MD | 08/09/2025 | 180 | CHAKRBORTTI ENTERPRISE | 334.01 | 0 | 0
1051 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000183/2023-2024 | 1366/MD | 02/05/2023 | 0 | Resource Division | 22.98 | 0 | 0
1052 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Approach Road (3m width) of Jarisai (Zone-II) Piped Water Supply Scheme at Mohanpur block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000401/2024-2025 | 157/MD | 15/01/2025 | 30 | GOBINDA MAITY | 1.31 | 0 | 100
1053 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 46
1054 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000212/2023-2024 | 1464 | 08/05/2023 | 0 | Resource Division | 36.82 | 0 | 0
1055 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000258/2023-2024 | 2006/MD | 16/05/2023 | 0 | Resource Division | 40.53 | 0 | 0
1056 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 46
1057 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashida & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000758/2022-2023 | 1113/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 1.69 | 0 | 100
1058 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000209/2023-2024 | 000209 | 08/05/2023 | 0 | Resource Division | 24.75 | 0 | 0
1059 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000245/2023-2024 | 1532/MD | 12/05/2023 | 0 | Resource Division | 0.67 | 0 | 0
1060 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000261/2023-2024 | 2010/MD | 16/05/2023 | 0 | Resource Division | 24.75 | 0 | 0
1061 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000038/2023-2024 | 1180/MD | 26/04/2023 | 0 | Resource Division | 28.14 | 0 | 0
1062 | Midnapore Division | Midnapur Mechanical Sub Division-I | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00239/2022-2023 |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0
1063 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Julkapur PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000432/2021-2022 | 1665/MD | 28/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.02 | 0 | 100
1064 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Julkapur (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000612/2022-2023 | 371/MD | 02/02/2023 | 60 | DEBASISH DOGRA | 27.86 | 0 | 100
1065 | Midnapore Division | Midnapur Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Intez type with solid raft) of capacity 200 cum and staging height 20 mtr., Boundary wall & Accommodate FHTC (500 Nos.) under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000022/2024-2025 | 2052/MD | 02/07/2024 | 360 | ADITYA MALLIK | 108.95 | 0 | 15
1066 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 cum and staging height 20 mtr. & Accommodate FHTC (1,423 Nos.) under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000037/2024-2025 | 2146/MD | 11/07/2024 | 540 | DIPAK KUMAR BAKLY | 175.22 | 0 | 5
1067 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary wall, Soil investigation, Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 200 cum and staging height 20 mtr & Accommodate FHTC (800 Nos.) under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000039/2024-2025 | 2219/MD | 19/07/2024 | 180 | ASHIM KUMAR DEY | 126.93 | 0 | 0
1068 | Midnapore Division | Midnapur Sadar Sub-Division | Accommodate FHTC (801 Nos.) including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM for Banpura PWSS within Midnapore Sadar Dev. Block under Midnapore Division in Paschim Medinipur district. [Mid-Term Plan under Master Plan] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000047/2025-2026 | 1067/MD | 02/05/2025 | 298 | MIDNAPUR PIPE CONCERN | 30.79 | 0 | 0
1069 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary wall, Soil investigation, Construction and Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 100 cum and staging height 20 mtr. & Accommodate FHTC (1,000 Nos.) including 2 years O&M under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000111/2024-2025 | 3044/MD | 25/09/2024 | 540 | WATER LINK | 139.11 | 0 | 0
1070 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (473 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-II) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000177/2024-2025 | 3160/MD | 04/10/2024 | 180 | ASHIM KUMAR DEY | 191.82 | 0 | 0
1071 | Midnapore Division | Midnapur Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 250 CuM & staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/10/2012) with allied works for Banpura & its adjoining mouzas water supply scheme within Midnapore Sadar Block including supply of all labour & materials under Midnapore Division, PHE Dte. (Mid- Term Plan under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000203/2025-2026 | 1777/MD | 08/09/2025 | 180 | M/S RAJKUMAR KHAN | 81.1 | 0 | 0
1072 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years O&M under JJM with allied work for Sholkamari & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000217/2023-2024 | 2870/MD | 10/08/2023 | 897 | MIDNAPUR PIPE CONCERN | 213.41 | 0 | 60
1073 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall & Accommodate FHTC (576 Nos.) including 2 years O&M under JJM with allied work for Mahadevchak & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000218/2023-2024 | 2871/MD | 10/08/2023 | 884 | MIDNAPUR PIPE CONCERN | 131.19 | 0 | 35
1074 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 250 (Intze type Raft Foundation) & Accommodate FHTC (2,237 Nos.) including Two years O&M under JJM with allied work for Panchkuri & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000226/2023-2024 | 2926/MD | 16/08/2023 | 180 | M/S. CARE | 462.61 | 0 | 10
1075 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Pump House, Boundary Wall & Accommodate FHTC (354 Nos.) under JJM with allied work for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000243/2023-2024 | 3098/MD | 25/08/2023 | 45 | PULLOCK KUMAR GHOSH | 36.04 | 0 | 5
1076 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House & Accommodate FHTC (304 Nos.) under JJM with allied work for Khangardihi & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000244/2023-2024 | 3099/MD | 25/08/2023 | 705 | PULLOCK KUMAR GHOSH | 83.11 | 0 | 25
1077 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line, Rising Main, Pump House, Boundary wall, & Accommodate FHTC (659 Nos.) including 2 years O&M under JJM with allied work for Pachra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000245/2023-2024 | 3100/MD | 25/08/2023 | 714 | M/S. D.K.H.CONSTRUCTION | 280.51 | 0 | 60
1078 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Construction of 300 Cum OHR (Intze type Raft Foundation) & Accommodate FHTC (2,400 Nos.) including Two years O&M under JJM with allied work for Pathra & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000265/2023-2024 | 3239/MD | 11/09/2023 | 530 | M/S. CARE | 492.38 | 0 | 10
1079 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 100 (Intze type Raft Foundation) & Accommodate FHTC (709 Nos.) including 2 years O&M under JJM with allied work for Chandipur (Zone-I) & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000287/2023-2024 | 3904/MD | 27/09/2023 | 180 | KISHORE GHOSH | 219.55 | 0 | 15
1080 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Rising Main & Accommodate FHTC (618 Nos.) including 2 years O&M under JJM with allied work for Hatihalka & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000288/2023-2024 | 3905/MD | 27/09/2023 | 766 | DIPAK KUMAR BAKLY | 61.27 | 0 | 60
1081 | Midnapore Division | Midnapur Sadar Sub-Division | Laying additional distribution pipeline, Land development at 1st Tube well cum Head work site & Accommodate FHTC (1,797 Nos.) including all allied works for Hatihalka PWSS within Midnapore Sadar block under Midnapore Division, PHE Dte. [Mid-Term Plan under Master Plan] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000309/2024-2025 | 3403/MD | 25/11/2024 | 450 | UTTAM KUMAR DAS | 84.05 | 0 | 0
1082 | Midnapore Division | Midnapur Sadar Sub-Division | Construction and commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr. as per approved drawing (No:- PC-I/OHR /10/15/2012) with allied works for Barua & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-C] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000336/2024-2025 | 3579/MD | 06/12/2024 | 360 | GOUTAM PARIA | 71.28 | 0 | 0
1083 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary Wall, Construction & Commissioning of RCC Over Head Reservoir (Torch type with solid raft) of capacity 150 cum and staging height 20 mtr. & Accommodate FHTC (691 Nos.) including 2 years O&M under JJM with allied work for Bishra & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-B] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000337/2024-2025 | 3580/MD | 06/12/2024 | 180 | DEBASISH DOGRA | 134.93 | 0 | 0
1084 | Midnapore Division | Midnapur Sadar Sub-Division | Laying rising main, Pump House & Accommodate FHTC (1,039 Nos.) including 2 yrs. O & M under JJM with allied work for Garhberia & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000444/2023-2024 | 5257/MD | 21/11/2023 | 421 | CREATION CONSTRUCTION | 94.26 | 0 | 40
1085 | Midnapore Division | Midnapur Sadar Sub-Division | Laying rising main, Pump House & Accommodate FHTC (1,212 Nos.) including 2 yrs. O & M under JJM with allied work for Gurehara & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000447/2023-2024 | 5258/MD | 21/11/2023 | 857 | SUNIL DULE | 119.03 | 0 | 60
1086 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipeline, Rising main, Pump House, Boundary Wall & Accommodate FHTC (546 Nos.) including 2 yrs. O & M under JJM with allied work for Shiromani & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) [PART-A] | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000636/2023-2024 | 140/MD | 18/01/2024 | 752 | MIDNAPUR PIPE CONCERN | 186.66 | 0 | 20
1087 | Midnapore Division | Midnapur Sadar Sub-Division | Laying rising main, Pump House & Accommodate FHTC (1,164 Nos.) including 2 yrs. O & M under JJM with allied work for Banpura & adjoining Mouza W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000637/2023-2024 | 141/MD | 18/01/2024 | 753 | MIDNAPUR PIPE CONCERN | 96.72 | 0 | 10
1088 | Midnapore Division | Midnapur Sadar Sub-Division | Laying rising main, Pump House & Accommodate FHTC (1,257 Nos.) including 2 yrs. O & M under JJM with allied work for Pathaisol & adjoining Mouza W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000755/2023-2024 | 218/MD | 31/01/2024 | 587 | ASIS KUMAR SARANGI | 104.62 | 0 | 95
1089 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type Pile Foundation) & Accommodate FHTC (3,719 Nos.) including Two years O&M under JJM with allied work for Juarhati & adjoining Mouza W/S Scheme in Midnapur Sadar Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. (Mid- Term Plan Under Master Plan) | AE Sadar Sub-division,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000773/2023-2024 | 438/MD | 20/02/2024 | 720 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 575.05 | 0 | 0
1090 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 (Intze type with Pile) & Accommodate FHTC (2,381 Nos.) including Two years O&M under JJM with allied work for Jankapur & its adjoining mouzas W/S Scheme in Datan-II Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000393/2023-2024 | 5067/MD | 26/10/2023 | 900 | DIPAK KUMAR BAKLY | 624.05 | 0 | 10
1091 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | RTOR000128/2024-2025 | 3464/MD | 25/11/2024 | 0 | Resource Division | 7.77 | 0 | 0
1092 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | RTOR000274/2023-2024 | 3987/MD | 06/10/2023 | 0 | Resource Division | 37.09 | 0 | 0
1093 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,366 nos.) under JJM with allied work for Ghoshpur PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000280/2023-2024 | 3842/MD | 21/09/2023 | 905 | M/S. A.R. ENTERPRISE. | 917.44 | 0 | 35
1094 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Ghoshpur & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 650 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000388/2024-2025 | 60/MD | 07/01/2025 | 45 | A-PLUS | 6.5 | 0 | 0
1095 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000039/2022-2023 | 79/MD | 09/01/2023 | 0 | Resource Division | 16.2 | 0 | 0
1096 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000066/2024-2025 | 3386/MD | 25/11/2024 | 0 | Resource Division | 20.73 | 0 | 0
1097 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Adasimla PWSS in Sabang Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000003/2021-2022 | 686/MD | 03/05/2021 | 45 | SAI TUBE CO. | 34.29 | 0 | 0
1098 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Bhikni Nischintapur PWSS, Block: - Sabang, in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000006/2021-2022 | 685/MD | 03/05/2021 | 25 | SAI TUBE CO. | 45.46 | 0 | 30
1099 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Maligram PWSS, Block: - Pingla, in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000007/2021-2022 | 684/MD | 03/05/2021 | 1423 | UTTAM KUMAR DAS | 94.86 | 0 | 76
1100 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000211/2020-2021 | 1431/MD | 26/11/2020 | 180 | ASHIM KUMAR DEY | 93.67 | 0 | 80
1101 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000254/2020-2021 | 1450/MD | 26/11/2020 | 180 | HARIPADA PATTANAYAK | 96.05 | 0 | 96
1102 | Midnapore Division | RWS Midnapur Sub-Division | Construction of Boundary wall & land development with approach road for 2nd T.W. Site of Maligram & its adjoining mouzas W/S Scheme at Pingla Block within Kharagpur Sub-Division under Midnapore Division, PHE Dte. (Total Length of the Boundary wall = 56.00 Mtr. & C/C distance of 250 X 250 mm size Column = 3.00 Mtr. & Height =2.45 Mtr. above GL) | AE/RWS Midnapore Sub Division |  | ORD/000370/2020-2021 | 261/MD | 12/02/2021 | 45 | SAKTI PADA BERA | 5.05 | 0 | 0
1103 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Narayanbar PWSS, Block: - Sabang, in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000375/2020-2021 | 266/MD | 12/02/2021 | 25 | BANERJEE CONSTRUCTION | 49.06 | 0 | 5
1104 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Bural (Zone-II) PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000436/2020-2021 | 307/MD | 22/02/2021 | 1772 | ASHOK BANERJEE | 53.72 | 0 | 45
1105 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Bural (Zone-I) PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000437/2020-2021 | 308/MD | 22/02/2021 | 1859 | ASHOK BANERJEE | 93.36 | 0 | 70
1106 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Gobardhanpur PWSS in Pingla Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000445/2020-2021 | 313/MD | 22/02/2021 | 1400 | DIPAK KUMAR BAKLY | 22.23 | 0 | 70
1107 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Panpara PWSS in Sabang Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000447/2020-2021 | 338/MD | 24/02/2021 | 1588 | BANERJEE CONSTRUCTION | 11.02 | 0 | 5
1108 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Chhotokhelna PWSS, Block :- Pingla in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000448/2020-2021 | 339/MD | 24/02/2021 | 40 | ASHIM KUMAR DEY | 64.56 | 0 | 15
1109 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Chandkuri (Zone-I) PWSS in Sabang Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000500/2020-2021 | 373/MD | 25/02/2021 | 30 | DULAL CHANDRA DAS | 16.68 | 0 | 75
1110 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Barsahara PWSS in Sabang Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000501/2020-2021 | 374/MD | 25/02/2021 | 15 | MAMPI ENTERPRISE | 4.32 | 0 | 0
1111 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Sartla PWSS in Sabang Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000502/2020-2021 | 375/MD | 25/02/2021 | 30 | GOBINDA MAITY | 26.59 | 0 | 100
1112 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Beluria PWSS in Pingla Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000503/2020-2021 | 376/MD | 25/02/2021 | 30 | M/S. A.R. ENTERPRISE. | 21.79 | 0 | 0
1113 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Karkai PWSS in Pingla Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000504/2020-2021 | 377/MD | 25/02/2021 | 1404 | GOBINDA MAITY | 22.16 | 0 | 100
1114 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Ragpur PWSS in Pingla Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000505/2020-2021 | 378/MD | 25/02/2021 | 1406 | GOBINDA MAITY | 9.25 | 0 | 100
1115 | Midnapore Division | RWS Midnapur Sub-Division | Restoration of laying of distribution pipe line damage due to construction of road by PMGSY in different mouzas required for covering FHTC works of Maligram & its adjoining mouza Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division |  | ORD/000531/2021-2022 | 30/MD | 07/01/2022 | 30 | HARIPADA PATTANAYAK | 18.99 | 0 | 95
1116 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Khasbazar PWSS in Debra Block in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division |  | ORD/000544/2020-2021 | 420/MD | 26/02/2021 | 45 | SUBRATA DAS | 31.59 | 0 | 67
1117 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | AE/RWS Midnapore Sub Division |  | RTOR000101/2024-2025 | 3412/MD | 25/11/2024 | 0 | Resource Division | 82.38 | 0 | 0
1118 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | VCH/000275/2022-2023 | BP-2022-23-33 | 29/04/2022 | 0 | SAI TUBE CO. | 12.05 | 0 | 0
1119 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Maligram W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | VCH/001735/2021-2022 | BP-2021-22-475 | 16/03/2022 | 0 | HARIPADA PATTANAYAK | 14.63 | 0 | 0
1120 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chhotokhelna W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | VCH/001777/2021-2022 | BP-2021-22-524 | 25/03/2022 | 0 | ASHIM KUMAR DEY | 15.66 | 0 | 0
1121 | Midnapore Division | Jhargram Sub-Division | Transfer money to EE/JSD PFMS bank account. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | BILL/00725/2022-2023 | BP-2022-23-692 | 10/03/2023 | 0 | EXECUTIVE ENGINEER, JHARGRAM CIVIL DIVISION, PHE DTE. | 8.33 | 0 | 0
1122 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Kaluasarn SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000061/2021-2022 | 824/MD | 03/06/2021 | 15 | PROVAT KUMAR DE | 7.43 | 0 | 0
1123 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Gokhurpal Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000062/2021-2022 | 825/MD | 03/06/2021 | 15 | PROVAT KUMAR DE | 9.07 | 0 | 1
1124 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Ruknimara Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000063/2021-2022 | 1055/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 5.82 | 0 | 1
1125 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Chirakuti Mini PWSS (Out of 45 Nos. Mini PWSS) at Sankrail Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000064/2021-2022 | 1056/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 8.95 | 0 | 1
1126 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Raipal Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000065/2021-2022 | 1057/MD | 02/07/2021 | 15 | ASIS KUMAR SARANGI | 8.25 | 0 | 1
1127 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Nayabasan, Khunti Village Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000066/2021-2022 | 1058/MD | 02/07/2021 | 15 | BISHNU PADA NANDI | 7.83 | 5.19 | 1
1128 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Bachurkhur Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000068/2021-2022 | 1064/MD | 02/07/2021 | 15 | NIMAI LAL GURIA | 7.76 | 7.64 | 1
1129 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Junsola PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. (Phase-II) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000122/2021-2022 | 817/MD | 03/06/2021 | 15 | SATYA RANJAN DAS | 4.96 | 0 | 1
1130 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Baharuna Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000123/2021-2022 | 826/MD | 03/06/2021 | 15 | SATYA RANJAN DAS | 8.01 | 0 | 1
1131 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Kui (Yatri Patikshaloy) Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000127/2021-2022 | 1223/MD | 29/07/2021 | 15 | RAMENDRA NATH KAR | 9.07 | 0 | 1
1132 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Hatikadua Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000128/2021-2022 | 1224/MD | 29/07/2021 | 15 | NIRMAL DUTTA | 5.99 | 0 | 0
1133 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Nepura Village Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000163/2021-2022 | 1286/MD | 09/08/2021 | 15 | SUNIL DULE | 6.4 | 0 | 1
1134 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Nuasai Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000164/2021-2022 | 1287/MD | 09/08/2021 | 15 | GOUTAM PARIA | 4.92 | 0 | 1
1135 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000184/2020-2021 | 1412/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 36.77 | 0 | 80
1136 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Nischintapur Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. (3rd Call) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000192/2021-2022 | 1375/MD | 25/08/2021 | 15 | A R ENTERPRISE | 4.95 | 4.58 | 1
1137 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Bansketia Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000202/2021-2022 | 1376/MD | 25/08/2021 | 15 | SAIKAT DANDAPAT | 6.19 | 0 | 1
1138 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Telidanga Jr. High School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000203/2021-2022 | 1377/MD | 25/08/2021 | 15 | SAIKAT DANDAPAT | 7.42 | 0 | 0
1139 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Hatipada Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000204/2021-2022 | 1378/MD | 25/08/2021 | 15 | S.B. TRADERS | 6.19 | 0 | 1
1140 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Tapsia Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000250/2021-2022 | 1211/MD | 28/07/2021 | 15 | MAMPI ENTERPRISE | 7.42 | 0 | 1
1141 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Jhitka PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000283/2020-2021 | 1582/MD | 11/12/2020 | 180 | RAMENDRA NATH KAR | 15.06 | 0 | 80
1142 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Pasro Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Jhargram Block under Jhargram Division, PHE Dte. (3rd Call) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000382/2021-2022 | 1939/MD | 24/11/2021 | 15 | DHUMKETU ENGINEERING PRIVATE LIMITED | 6.24 | 0 | 1
1143 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at BANISOLE Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000457/2020-2021 | 602/JSD | 09/02/2021 | 30 | PROVAT KUMAR DE | 3.31 | 3.04 | 0
1144 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at KADAMDIHA Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000459/2020-2021 | 603/JSD | 09/02/2021 | 30 | PROVAT KUMAR DE | 3.44 | 3.42 | 0
1145 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Jashpur Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000511/2020-2021 | 384/MD | 25/02/2021 | 15 | SUNIL DULE | 6.16 | 6.16 | 1
1146 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Sankhara Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000512/2020-2021 | 385/MD | 25/02/2021 | 15 | SUNIL DULE | 5.37 | 4.92 | 1
1147 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Balarampur Primary School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000513/2020-2021 | 386/MD | 25/02/2021 | 15 | SUNIL DULE | 4.96 | 0 | 1
1148 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Dakaisol SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000514/2020-2021 | 387/MD | 25/02/2021 | 15 | SAIKAT DANDAPAT | 5.78 | 0 | 0
1149 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Bhalaidiha Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000515/2020-2021 | 388/MD | 25/02/2021 | 15 | DEBABRATA DUTTA | 6.07 | 0 | 1
1150 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Salpatra SSK Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000516/2020-2021 | 389/MD | 25/02/2021 | 15 | J.S.S. ENTERPRISE | 5.24 | 0 | 1
1151 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Kalmapukuria, Dakshin Sadar Para Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000517/2020-2021 | 390/MD | 25/02/2021 | 15 | PROVAT KUMAR DE | 5.99 | 5.99 | 1
1152 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at CHULBATA Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000577/2020-2021 | 617/JSD | 22/02/2021 | 30 | SRIMANTA KUMAR DE | 4.29 | 3.95 | 0
1153 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at GARHDOAR Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000578/2020-2021 | 618/JSD | 22/02/2021 | 30 | SRIMANTA KUMAR DE | 4.75 | 4.29 | 0
1154 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at BHURURDIHI Mini PWSS (Out of 45 Nos. Mini PWSS) at GOPIBALLAVPUR-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000579/2020-2021 | 619/JSD | 22/02/2021 | 30 | SRIMANTA KUMAR DE | 4.29 | 4.22 | 0
1155 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Chandabila Pry. School Mini PWSS (Out of 45 Nos. Mini PWSS) at Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000580/2020-2021 | 620/JSD | 22/02/2021 | 30 | SUNIL DULE | 4.75 | 0 | 0
1156 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at AUSHPAL ADIBASHI PARA Mini PWSS (Out of 45 Nos. Mini PWSS) at JHARGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000581/2020-2021 | 621/JSD | 22/02/2021 | 30 | S.B. TRADERS | 4.55 | 3.37 | 0
1157 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at BARJHARIA ICDS Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000582/2020-2021 | 622/JSD | 22/02/2021 | 30 | DHUMKETU ENGINEERING PRIVATE LIMITED | 2.66 | 2.43 | 0
1158 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Bihankuria JR. High School Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000584/2020-2021 | 624/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 3.93 | 0 | 1
1159 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at BHURKUNDI Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000585/2020-2021 | 625/JSD | 22/02/2021 | 30 | THE TILES | 3.4 | 0 | 0
1160 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at DEHAGANJE Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000586/2020-2021 | 626/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.55 | 0 | 1
1161 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at BANKATI Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000587/2020-2021 | 627/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.38 | 0 | 0
1162 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at RANDEBPUR Mini PWSS (Out of 45 Nos. Mini PWSS) at SANKRAIL Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000588/2020-2021 | 628/JSD | 22/02/2021 | 30 | ASSOCIATED ENGINEERS & TRADERS | 2.74 | 0 | 1
1163 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Sijua Mini PWSS (Out of 45 Nos. Mini PWSS) at Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000656/2020-2021 | 451/MD | 26/02/2021 | 15 | BISHNU PADA NANDI | 5.98 | 5.45 | 0
1164 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Kashafulia Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000657/2020-2021 | 452/MD | 26/02/2021 | 15 | NIRMAL DUTTA | 5.99 | 0 | 0
1165 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Jamunasole Mini PWSS (Out of 45 Nos. Mini PWSS) at Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000658/2020-2021 | 453/MD | 26/02/2021 | 15 | NRIPENDRA NATH SINGHA | 5.99 | 0 | 1
1166 | Midnapore Division | Jhargram Sub-Division | Retrofitting with extension of distribution pipeline to accommodate FHTC under JJM in Barjharia Mini PWSS (out of 45 nos Mini pwss)(Phase-II) Block - Nayagram in the District of Jhargram | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000868/2021-2022 | 34/JSD | 01/02/2022 | 15 | PROVAT KUMAR DE | 3.07 | 0 | 1
1167 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC with extension of pipeline under JJM in Kui Mini PWSS (out of 45 Nos. Mini PWSS) (Phase-II) Block - Binpur-I in the district of Jhargram. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | ORD/000916/2021-2022 | 535/MD | 22/03/2022 | 15 | RAMENDRA NATH KAR | 5.62 | 0 | 1
1168 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Bhaliaghati Mini PWSS (Out of 45 Nos. Mini PWSS) at NAYAGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/001622/2021-2022 | BP-2021-22-425 | 02/03/2022 | 0 | BISHNU PADA NANDI | 3.38 | 0 | 0
1169 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at Nuasi Mini PWSS (Out of 45 Nos. Mini PWSS) at Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/001715/2021-2022 | BP-2021-22-455 | 11/03/2022 | 0 | GOUTAM PARIA | 4.91 | 0 | 0
1170 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM at AUSHPAL ADIBASHI PARA Mini PWSS (Out of 45 Nos. Mini PWSS) at JHARGRAM Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/001747/2021-2022 | BP-2021-22-490 | 16/03/2022 | 0 | S.B. TRADERS | 0.77 | 0 | 0
1171 | Midnapore Division | Jhargram Sub-Division | FHTC of 45 Drought. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer Binpur-I block,Junior Engineer Gopiballavpur-I block,Junior Engineer Gopiballavpur-II block,Junior Engineer Nayagram block,Junior Engineer Sankrail block,Junior Engineer-I,Junior Engineer-II,Junior Engineer-III | VCH/001929/2021-2022 | BP-2021-22-103 | 03/03/2022 | 0 | BISHNU PADA NANDI | 0.03 | 0 | 0
1172 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme, Block: - Ghatal, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000246/2020-2021 | 1445/MD | 26/11/2020 | 180 | M/S. D.K.H.CONSTRUCTION | 67.23 | 64.32 | 0
1173 | Midnapore Division | Kharagpur Sub-Division | Laying of Rising Main including interconnection for Augmentation of Mohanpur and its adjoining mouzas Water Supply Scheme within Mohanpur Block under Kharagpur Sub Division of Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000640/2023-2024 | 5568/MD | 26/12/2023 | 30 | GOBINDA MAITY | 6.55 | 0 | 0
1174 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/000745/2020-2021 |  | 15/12/2020 | 0 | M/S. D.K.H.CONSTRUCTION | 30 | 0 | 0
1175 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Mohanpur W/S Scheme. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/000857/2020-2021 |  | 05/02/2021 | 0 | PULLOCK KUMAR GHOSH | 5 | 0 | 0
1176 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001284/2021-2022 | 844363 | 18/01/2022 | 0 | SANDIP MANNA | 0.12 | 0 | 0
1177 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001285/2021-2022 | 844363 | 18/01/2022 | 0 | TANMOY BERA | 0.21 | 0 | 0
1178 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001407/2020-2021 | 8443459 | 26/03/2021 | 0 | MANABENDRA DAS | 0.16 | 0 | 0
1179 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001408/2020-2021 | 8443459 | 26/03/2021 | 0 | SUBRATA CHAKRABORTY | 0.17 | 0 | 0
1180 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001409/2020-2021 | 8443459 | 26/03/2021 | 0 | RINTU SAMANTA | 0.17 | 0 | 0
1181 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chaupanya w/s Scheme. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | BILL/00702/2024-2025 | 84434 | 03/05/2024 | 0 | M/S. A.R. ENTERPRISE | 33.39 | 0 | 0
1182 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chaupanya W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000276/2020-2021 | 1451/MD | 26/11/2020 | 1823 | M/S. A.R. ENTERPRISE. | 94.15 | 28.6 | 100
1183 | Midnapore Division | Kharagpur Sub-Division | Restoration of pipe line From Ramnagar to Mominpur SSK for Covering FHTC Work & Development of Land at H.W Site of Chaupanya PWSS within Kharagpur-II Block under Kharagpur Sub Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000504/2021-2022 | 2246/MD | 28/12/2021 | 21 | MAMPI ENTERPRISE | 9.04 | 0 | 100
1184 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | RTOR000103/2024-2025 | 3410/MD | 25/11/2024 | 0 | Resource Division | 12.21 | 0 | 0
1185 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chaupanya W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | VCH/000721/2020-2021 |  | 15/12/2020 | 0 | M/S. A.R. ENTERPRISE. | 25 | 0 | 0
1186 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Gobardhanpur W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000213/2020-2021 | 1432/MD | 26/11/2020 | 180 | DIPAK KUMAR BAKLY | 88.12 | 55.92 | 0
1187 | Midnapore Division | Jhargram Sub-Division | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Banspahari PWSS to Accommodate FHTC in Binpur -II Block within Jhargram District under Jhargram Division, PHE Dte. |  | Junior Engineer-II | ORD/000019/2022-2023 | 616/MD | 04/04/2022 | 21 | SUNIL DULE | 14.28 | 0 | 1
1188 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Banspahari PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | VCH/001375/2021-2022 | BP-2021-22-401 | 23/02/2022 | 0 | RADIANT | 1.8 | 0 | 0
1189 | Midnapore Division | Jhargram Sub-Division | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Banspahari PWSS under Jhargram Division P.H.E. Dte. |  | Junior Engineer-II | VCH/001732/2021-2022 | BP-2021-22-472 | 16/03/2022 | 0 | SUNIL DULE | 3.36 | 0 | 0
1190 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Malara W/S Scheme, Block: - Garhbeta-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-I) | ORD/000510/2020-2021 | 383/MD | 25/02/2021 | 30 | PULLOCK KUMAR GHOSH | 22.4 | 0 | 0
1191 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Dhaneswarpur PWSS to accommodate FHTC under JJM under Dantan-II block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000476/2021-2022 | 2170/MD | 17/12/2021 | 35 | UTTAM KUMAR DAS | 89.26 | 0 | 0
1192 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhaneswarpur, Block - Dantan-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000859/2020-2021 | 296/MD | 19/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.15 | 0 | 0
1193 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dhaneswarpur, Block - Dantan-II) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | VCH/001716/2021-2022 | BP-2021-22-456 | 11/03/2022 | 0 | SIRCON ENGINEERING SERVICES | 2.54 | 0 | 0
1194 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Keot Khalisha PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000528/2021-2022 | 28/MD | 07/01/2022 | 21 | SUNIL DULE | 48.62 | 0 | 0
1195 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keot Khalisha, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000861/2020-2021 | 298/MD | 19/02/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 1.94 | 0 | 0
1196 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keot Khalisha, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001419/2021-2022 | BP-2021-22-416 | 24/02/2022 | 0 | RISHAN ENGINEERING CONSULTANCY | 1.94 | 0 | 0
1197 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Sonakania PWSS to accommodate FHTC under JJM under Dantan-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000404/2021-2022 | 2003/MD | 01/12/2021 | 15 | M/S. EL-CON | 36.71 | 0 | 0
1198 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sonakania, Block - Dantan-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000558/2020-2021 | 52/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.3 | 0 | 0
1199 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Sonakania, Block - Dantan-I) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | VCH/001368/2021-2022 | BP-2021-22-417 | 24/02/2022 | 0 | SIRCON ENGINEERING SERVICES | 1.69 | 0 | 0
1200 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of "Retrofitting of Jot Ghanashyam Piped Water Supply Scheme to accommodate FHTC under Jal Swapna including Sinking of 1 nos. Tube Well and other allied Works in Daspur-II Block of Paschim Medinipur District under Midnapore Division, PHE Dte." | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000171/2022-2023 | 1242/MD | 20/06/2022 | 1239 | GOBINDA MAITY | 90.19 | 0 | 100
1201 | Midnapore Division | Ghatal Subdivision | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution and Rising main pipe line for Retrofitting of JOTGHANASHYAM water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000177/2022-2023 | 402/AE/GSD | 11/07/2022 | 7 | GOBINDA MAITY | 4.5 | 0 | 0
1202 | Midnapore Division | Ghatal Subdivision | Retrofitting of Jot Ghanashyam Piped Water Supply Scheme to accommodate FHTC under Jal Swapna including Sinking of 1 nos. Tube Well and other allied Works in Daspur-II Block of Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000410/2021-2022 | 2015/MD | 03/12/2021 | 90 | GOBINDA MAITY | 297.42 | 0 | 100
1203 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Jot Ghanashyam (Block-Daspur-II) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001041/2021-2022 | 1653/MD | 23/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.38 | 0 | 0
1204 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001813/2021-2022 | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0
1205 | Midnapore Division | Midnapur Mechanical Sub Division-I | Cleaning the Chokage of pipe in the existing line at Sarta-Sijua PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000048/2024-2025 | 2246/AE/HQ/MD | 22/07/2024 | 10 | PULLOCK KUMAR GHOSH | 0.9 | 0 | 100
1206 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying balance quantity of pipe line & accommodate FHTC (21 Nos.) with allied works for Augmentation of Sarta-Sijua W/S Scheme under Dantan-I block within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000103/2024-2025 | 2849/MD | 09/09/2024 | 45 | PROVAT KUMAR DE | 11.96 | 0 | 85
1207 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of (Left out & Damaged) Distribution pipe line including Supply of Valves for Augmentation Sarta-Sijua Pipe Water Supply Scheme in Dantan-I Block under Khargapur Sub-Division within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000289/2023-2024 | 3906/MD | 27/09/2023 | 45 | PROVAT KUMAR DE | 10.22 | 0 | 95
1208 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 100 Cum and staging height 20.00 mtr. with allied work including Sinking of 250mm x 150mm x 190m deep tube well for Augmentation of Sarta-Sijua W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000375/2022-2023 | 1958/MD | 20/09/2022 | 180 | PROVAT KUMAR DE | 111.93 | 0 | 99
1209 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying Rising Main system including inter-connection and By-Pass arrangement for Augmentation Sarta-Sijua PWSS in Dantan-I Block under Khargapur Sub-Division of Midnapur Division PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000380/2023-2024 | 4042/MD | 11/10/2023 | 30 | PROVAT KUMAR DE | 3.27 | 0 | 95
1210 | Midnapore Division | Midnapur Mechanical Sub Division-I | Repairing of 2nd Pump House & Boundary wall for Sarta-Sijua PWSS within Dantan-I block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000500/2024-2025 | 570/AE/HQ/MD | 28/02/2025 | 60 | PROVAT KUMAR DE | 3.65 | 0 | 100
1211 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000031/2021-2022 | 2276/MD | 31/12/2021 | 0 | Resource Division | 2.64 | 0 | 0
1212 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000169/2023-2024 | 1369/MD | 02/05/2023 | 0 | Resource Division | 12.34 | 0 | 0
1213 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Sarta-Sijua to Accommodate FHTC. Block - Dantan-I. District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | VCH/000460/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.64 | 0 | 0
1214 | Midnapore Division | Ghatal Subdivision | Flank restoration of Panskura Ghatal Road from 15.00 kmp to 17.00 kmp under Midnapore Highway Division in the District of Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00127/2023-2024 | BP-2023-24-80 | 08/05/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 20 | 0 | 0
1215 | Midnapore Division | Ghatal Subdivision | Construction of RCC Pile for Over Head Reservoir (in place of Intze type with solid raft) of capacity 300 CuM and Staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/07/2012) with allied works for Gobindanagar & its adjoining Mouzas W/S Scheme within Daspur-I block including supply of all labour & materials under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00706/2022-2023 | BP-2022-23-665 | 04/03/2023 | 0 | DIPAK KUMAR DOLAI | 24 | 0 | 0
1216 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Laying additional pipeline for Gobindanagar W/S Scheme in Daspur-I block within Ghatal Sub-Division under Midnapore Division PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000010/2023-2024 | 962/MD | 06/04/2023 | 60 | DIPAK KUMAR DOLAI | 52.61 | 0 | 95
1217 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, soil test, FHTC & construction of R.C.C. Over Head Reservoir of capacity 300 Cum and staging height 20.00 mtr. with allied work for Gobindanagar W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000045/2022-2023 | 838/MD | 02/05/2022 | 1425 | DIPAK KUMAR DOLAI | 238.12 | 0 | 81
1218 | Midnapore Division | Ghatal Subdivision | Sinking of 2 (Two) Nos. 200 X 100 mm dia. X 180 Mtr. depth Rig bored tube wells at Head Works cum 1st Tube well & 2nd tube well sites of Gobindanagar W/S Scheme within Daspur-I Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000125/2022-2023 | 1312/MD | 30/06/2022 | 15 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.8 | 0 | 100
1219 | Midnapore Division | Ghatal Subdivision | Supply of C.I.D.F Sluice Valve & C.I. Jeffy coupler for distribution and Rising main pipe line for GOBINDANAGAR water Supply Scheme under Ghatal Sub-Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000176/2022-2023 | 401/AE/GSD | 11/07/2022 | 7 | SUBHASIS DOLAI | 3.22 | 0 | 0
1220 | Midnapore Division | Ghatal Subdivision | Laying rising main, Pump houses (5.40 X 3.60 Mtr.) & (3.60 X 3.00 Mtr.), Boundary wall, Approach road for Gobindanagar Piped Water Supply Scheme within Daspur-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000381/2022-2023 | 1964/MD | 20/09/2022 | 60 | DEBASISH DOGRA | 34.31 | 0 | 65
1221 | Midnapore Division | Ghatal Subdivision | Construction of RCC Pile for Over Head Reservoir (in place of Intze type with solid raft) of capacity 300 CuM and Staging height 20 mtr. as per approved drawing (No:- PC-I/OHR/07/2012) with allied works for Gobindanagar & its adjoining Mouzas W/S Scheme within Daspur-I block including supply of all labour & materials under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000475/2022-2023 | 2270/MD | 09/11/2022 | 30 | DIPAK KUMAR DOLAI | 36.58 | 0 | 100
1222 | Midnapore Division | Ghatal Subdivision | Exigency basis laying casing pipe under Bitumineous pucca road crosssing near Goura Bridge,Sarala Ciname of Khakurda to Ghatal PWD Road of Gobindanagar W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000511/2022-2023 | 165/AE/GSD | 01/04/2022 | 2 | SUBHASIS DOLAI | 3.64 | 0 | 0
1223 | Midnapore Division | Ghatal Subdivision | Exigency basis laying casing pipe under Bitumineous pucca road crosssing Near Anapurna Nursing Home,Panchberia Bus Stop, Nirmal Paludhi house of Khakurda to Ghatal PWD Road of Gobindanagar W/S Scheme within Ghatal Sub-Division, PHE.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000512/2022-2023 | 166/AE/GSD | 01/04/2022 | 2 | SUBHASIS DOLAI | 3.64 | 0 | 0
1224 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Laying additional distribution pipe line for Gobindanagar Water Supply Scheme under Daspur-I block within Midnapore Division PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000595/2022-2023 | 219/MD | 16/01/2023 | 30 | DIPAK KUMAR DOLAI | 13.3 | 0 | 100
1225 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000130/2022-2023 | 378/MD | 03/02/2023 | 0 | Resource Division | 25.32 | 0 | 0
1226 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Narayanbar (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000251/2022-2023 | 1728/A/MD | 23/08/2022 | 1088 | BANERJEE CONSTRUCTION | 36.87 | 0 | 25
1227 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Narayanbar PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000436/2021-2022 | 1674/MD | 29/09/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 2.11 | 0 | 100
1228 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying pipeline at command area of Pump House No. 3 of Narayanbar PWSS to accommodate FHTC under JJM at Sabang block in Paschim Medinipur district under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000575/2022-2023 | 124/MD | 10/01/2023 | 21 | A-PLUS | 10.56 | 0 | 100
1229 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeri | AE Ghatal Sub-division | JE1 Ghatal Sub-division | BILL/00670/2023-2024 | BP-2022-23-608 | 01/09/2023 | 0 | PULLOCK KUMAR GHOSH | 4.25 | 0 | 0
1230 | Midnapore Division | Ghatal Subdivision | Retrofitting to accomodate FHTC under JJM ar Srinagar water supply scheme Block-Candrakona-I and II District Paschim Medinipur within Midnapore Division P.H.E.Dte. (Rejna) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000058/2023-2024 | 336/AE/GSD | 16/05/2023 | 20 | INDRAJIT ROY | 1.45 | 0 | 0
1231 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Rejna) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000059/2023-2024 | 337/AE/GSD | 16/05/2023 | 20 | INDRAJIT ROY | 1.45 | 0 | 100
1232 | Midnapore Division | Ghatal Subdivision | Laying additional pipelines regarding Balance work of Retrofitting to accommodate FHTC under JJM at SRINAGAR water supply scheme Block-Chandrakona-I & 2 District- Paschim Medinipur within Midnapore Division, PHE.Dte. (Muide, Jara Purba & Mahabala) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000128/2024-2025 | 1494/AE/GSD | 24/09/2024 | 15 | M/S JITEN BANARJEE | 3.48 | 0 | 100
1233 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Purba Para.) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000152/2022-2023 | 511/AE/GSD | 07/09/2022 | 20 | M/S JITEN BANARJEE | 4.33 | 0 | 100
1234 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Paschim Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000153/2022-2023 | 512/AE/GSD | 07/09/2022 | 20 | M/S JITEN BANARJEE | 4.33 | 0 | 20
1235 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Jara Uttar Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000154/2022-2023 | 513/AE/GSD | 07/09/2022 | 20 | TARUN MAHATA | 4.33 | 0 | 0
1236 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Jara Dakshin Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000155/2022-2023 | 514/AE/GSD | 07/09/2022 | 20 | KAMAKHYA ENTERPRISE | 4.33 | 0 | 100
1237 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Bashuli) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000156/2022-2023 | 515/AE/GSD | 07/09/2022 | 20 | PRITI ENTERPRISE | 4.33 | 0 | 100
1238 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeria) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000157/2022-2023 | 516/AE/GSD | 07/09/2022 | 20 | PULLOCK KUMAR GHOSH | 4.33 | 0 | 100
1239 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Narayanpur) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000158/2022-2023 | 517/AE/GSD | 07/09/2022 | 20 | BUNBA CONSTRUCTION | 4.33 | 0 | 100
1240 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Rejna) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000159/2022-2023 | 518/AE/GSD | 07/09/2022 | 20 | INDRAJIT ROY | 4.33 | 0 | 100
1241 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Sanpur) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000160/2022-2023 | 519/AE/GSD | 07/09/2022 | 20 | SURAJIT GHOSH | 4.33 | 0 | 100
1242 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. (Srinagar Purba Para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000161/2022-2023 | 520/AE/GSD | 07/09/2022 | 20 | MAHAPRABHU ENTERPRISE | 4.33 | 0 | 100
1243 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.(Srinagar) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000162/2022-2023 | 521/AE/GSD | 07/09/2022 | 20 | A.R. CONSTRUCTION | 4.33 | 0 | 0
1244 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Srinagar Madhya para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000163/2022-2023 | 522/AE/GSD | 07/09/2022 | 20 | PULLOCK KUMAR GHOSH | 4.33 | 0 | 100
1245 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Mahabala) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000164/2022-2023 | 523/AE/GSD | 07/09/2022 | 20 | M/S. ZAMAN ENTERPRISE | 4.33 | 0 | 100
1246 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Maide) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000165/2022-2023 | 524/AE/GSD | 07/09/2022 | 20 | M/S. ZAMAN ENTERPRISE | 3.31 | 0 | 0
1247 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte. ( Kochgeria) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/001075/2022-2023 | 107/AE.GSD | 13/02/2023 | 20 | PULLOCK KUMAR GHOSH | 0.85 | 0 | 100
1248 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at different places for Srinagar PWSS & its adjoining mouzas ( Phase -III) Under ChandraKona - I & II Block within Midnapore Division, PHE Dte.( Srinagar Madhya para) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/001076/2022-2023 | 109/AE/GSD | 13/02/2023 | 20 | PULLOCK KUMAR GHOSH | 0.4 | 0 | 100
1249 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000109/2023-2024 | 1243/MD | 27/04/2023 | 0 | Resource Division | 19.22 | 0 | 0
1250 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (5,751 Nos.) including 2 years operation & maintenance For Kunarpur, Murakata & Nayapukur Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000210/2023-2024 | 2827/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 1515.85 | 0 | 15
1251 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000031/2023-2024 | 1172/MD | 26/04/2023 | 0 | Resource Division | 29.08 | 0 | 0
1252 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000211/2023-2024 | 2826/MD | 07/08/2023 | 785 | GOBINDA MAITY | 1375.06 | 0 | 74
1253 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000200/2023-2024 | 1410 | 04/05/2023 | 0 | Resource Division | 36.06 | 0 | 0
1254 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000070/2023-2024 | 1214/MD | 27/04/2023 | 0 | Resource Division | 19.59 | 0 | 0
1255 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000117/2023-2024 | 1310/MD | 28/04/2023 | 0 | Resource Division | 21.97 | 0 | 0
1256 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
1257 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000111/2022-2023 | 211/MD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0
1258 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000124/2024-2025 | 3460/MD | 25/11/2024 | 0 | Resource Division | 14.78 | 0 | 0
1259 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000134/2023-2024 | 1257/MD | 28/04/2023 | 0 | Resource Division | 25.04 | 0 | 0
1260 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000087/2023-2024 | 1233/MD | 27/04/2023 | 0 | Resource Division | 25.56 | 0 | 0
1261 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000076/2023-2024 | 1220/MD | 27/04/2023 | 0 | Resource Division | 21.92 | 0 | 0
1262 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
1263 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000281/2023-2024 | 4053/MD | 12/10/2023 | 0 | Resource Division | 20.09 | 0 | 0
1264 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0
1265 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000123/2023-2024 | 1314/MD | 28/04/2023 | 0 | Resource Division | 27.15 | 0 | 0
1266 | Midnapore Division | Kharagpur Sub-Division | Laying of pipeline supportive to retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM for Augmentation of Satkui & its adjoining mouza W/S Scheme within Kharagpur-I Dev. block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000100/2023-2024 | 2475/MD | 14/07/2023 | 14 | ARNAB PATRA | 7.07 | 0 | 100
1267 | Midnapore Division | Kharagpur Sub-Division | Route survey & way leave permission along & across of National Highway under Augmentation of Satkui PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000489/2024-2025 | 523/MD | 19/02/2025 | 21 | PIONEER SURVEYORS | 9.11 | 0 | 0
1268 | Midnapore Division | Kharagpur Sub-Division | Sinking of 250 X 150 mm dia. X 215 Mtr. Depth deep tube well, Construction of Pump House & Boundary wall of 3rd tube well site and interconnection of 3rd tube well with distribution line and repair of OHR & Pump House-I for Augmentation of Satkui W/S Scheme within Kharagpur-I block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000515/2024-2025 | 669/MD | 10/03/2025 | 75 | M/S CHOWDHURY CONSTRUCTION (NEW) | 21.62 | 0 | 0
1269 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall & Construction of 200 CuM Capacity OHR with 20 m Staging height for Augmentation of Satkui PWSS in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000520/2022-2023 | 2572/MD | 16/12/2022 | 1159 | DULAL CHANDRA DAS | 196.05 | 0 | 42
1270 | Midnapore Division | Kharagpur Sub-Division | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Augmentation of Keshiary & its adjoining mouzas W/S Scheme within Keshiary block & (2) Augmentation of Satkui & its adjoining mouzas W/S Scheme within Kharagpur-I block in Paschim Medinipur District through Jadavpur University. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000617/2022-2023 | 471/MD | 15/02/2023 | 14 | JADAVPUR UNIVERSITY | 9.56 | 0 | 100
1271 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Satkui PWSS within Kharagpur-I Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001009/2021-2022 | 519/MD | 17/03/2022 | 10 | SIRCON ENGINEERING SERVICES | 2.24 | 0 | 100
1272 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000091/2022-2023 | 182/MD | 16/01/2023 | 0 | Resource Division | 15.15 | 0 | 0
1273 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000163/2022-2023 | 1151/MD | 25/04/2023 | 0 | Resource Division | 23.1 | 0 | 0
1274 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000088/2023-2024 | 1293/MD | 28/04/2023 | 0 | Resource Division | 28.04 | 0 | 0
1275 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Patharisol PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000192/2025-2026 | 1628/MD | 06/08/2025 | 21 | PIONEER SURVEYORS | 9.55 | 0 | 0
1276 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000037/2023-2024 | 1179/MD | 26/04/2023 | 0 | Resource Division | 28.94 | 0 | 0
1277 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 723 | MADE AND TRADE CO. | 1346.28 | 0 | 75
1278 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000221/2023-2024 | 1517/MD | 12/05/2023 | 0 | Resource Division | 11.96 | 0 | 0
1279 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2725 nos) under JJM with allied work for Raniar PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000069/2023-2024 | 2420/MD | 13/07/2023 | 839 | BANERJEE CONSTRUCTION | 800.44 | 0 | 66
1280 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Raniar & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 730 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000436/2024-2025 | 321/MD | 29/01/2025 | 45 | ASHOK BANERJEE | 6.81 | 0 | 0
1281 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000036/2022-2023 | 97/MD | 10/01/2023 | 0 | Resource Division | 15.44 | 0 | 0
1282 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000059/2024-2025 | 3379/MD | 25/11/2024 | 0 | Resource Division | 16.42 | 0 | 0
1283 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 250 Cum Capacity R.C.C Over Head Reservoir Over Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House, Soil Investigation, Boundary Wall & Providing Functional Household Tap Connection (1968 Nos.) including Two Years Operation & maintenance For Dumuria Pipe Water Supply Scheme within Garbeta-II Block Under Medinipur Sadar Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000394/2023-2024 | 5068/MD | 26/10/2023 | 463 | TITAS COSTRUCTION | 540.55 | 0 | 3
1284 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
1285 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000233/2023-2024 | 1525/MD | 12/05/2023 | 0 | Resource Division | 15.49 | 0 | 0
1286 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,184 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Kukrada & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/000459/2023-2024 | 5283/MD | 23/11/2023 | 720 | CREATION CONSTRUCTION | 530.64 | 0 | 60
1287 | Midnapore Division | Kharagpur Sub-Division | Route survey & way leave permission along & across of National Highway in Kukrada PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | ORD/000488/2024-2025 | 522/MD | 19/02/2025 | 21 | PIONEER SURVEYORS | 9.44 | 0 | 0
1288 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | RTOR000075/2024-2025 | 3425/MD | 25/11/2024 | 0 | Resource Division | 13.45 | 0 | 0
1289 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),JE/Midnapur Mechanical Sub-Division-I | RTOR000105/2022-2023 | 212/MD | 16/01/2023 | 0 | Resource Division | 42.05 | 0 | 0
1290 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000709/2022-2023 | 834/MD | 22/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0
1291 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000096/2022-2023 | 183/MD | 16/01/2023 | 0 | Resource Division | 17.04 | 0 | 0
1292 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000114/2024-2025 | 3450/MD | 25/11/2024 | 0 | Resource Division | 16.08 | 0 | 0
1293 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000080/2023-2024 | 1229/MD | 27/04/2023 | 0 | Resource Division | 30.35 | 0 | 0
1294 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ranjapur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000656/2022-2023 | 1754/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.93 | 0 | 100
1295 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000059/2023-2024 | 1276/MD | 28/04/2023 | 0 | Resource Division | 33.3 | 0 | 0
1296 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,783 nos.) under JJM with allied work for Sagarpur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000278/2023-2024 | 3821/MD | 20/09/2023 | 540 | KISHORE GHOSH | 559.14 | 0 | 10
1297 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000018/2024-2025 | 3355/MD | 25/11/2024 | 0 | Resource Division | 10.98 | 0 | 0
1298 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000048/2022-2023 | 107/MD | 10/01/2023 | 0 | Resource Division | 44.15 | 0 | 0
1299 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer | JE RWS Ghatal Sub-Division(CK-II),Junior Engineer,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000037/2022-2023 | 102/MD | 10/01/2023 | 0 | Resource Division | 32.36 | 0 | 0
1300 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer | JE RWS Ghatal Sub-Division(CK-II),Junior Engineer,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000164/2023-2024 | 1373/MD | 02/05/2023 | 0 | Resource Division | 10.87 | 0 | 0
1301 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000045/2023-2024 | 1186/MD | 26/04/2023 | 0 | Resource Division | 31.65 | 0 | 0
1302 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Dhobaberiya PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000464/2024-2025 | 379/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 10.59 | 0 | 0
1303 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000039/2023-2024 | 1181/MD | 26/04/2023 | 0 | Resource Division | 37.9 | 0 | 0
1304 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0
1305 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000122/2023-2024 | 1313/MD | 28/04/2023 | 0 | Resource Division | 46.06 | 0 | 0
1306 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying Rising main pipe line, Construction of Pump House & Boundary wall under JJM with allied work for Augmentation Chak Ismailpur PWSS in Dantan-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000349/2023-2024 | 4023/MD | 10/10/2023 | 60 | TARUN MAHATA | 24.51 | 0 | 0
1307 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 250 X 150 mm dia. X 200 Mtr. Depth tube well, Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 100 Cum and staging height 20.00 mtr. & FHTC (853 Nos.) under JJM with allied work for Augmentation of Chak Ismailpur and its adjoining mouzas W/S scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000630/2022-2023 | 455/MD | 13/02/2023 | 1005 | M/S. D.K.H.CONSTRUCTION | 200.6 | 0 | 82
1308 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR location for Augmentation of Chak Ismailpur W/S Scheme under Dantan-I Block of Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000732/2022-2023 | 706/MD | 06/03/2023 | 7 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0
1309 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chak Ismailpur, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000917/2020-2021 | 246/DP/MD | 10/02/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.77 | 0 | 100
1310 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000075/2022-2023 | 94/MD | 10/01/2023 | 0 | Resource Division | 16.53 | 0 | 0
1311 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
1312 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000246/2023-2024 | 1582/MD | 15/05/2023 | 0 | Resource Division | 26.86 | 0 | 0
1313 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 400 Cum OHR (Intze type with Pile Foundation) & Accommodate FHTC (2,882 Nos.) including Two years O&M under JJM with allied work for Hatkata & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000231/2023-2024 | 2955/MD | 17/08/2023 | 903 | M/S. D.K.H.CONSTRUCTION | 719.89 | 0 | 25
1314 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000194/2023-2024 | 1407/MD | 04/05/2023 | 0 | Resource Division | 68.4 | 0 | 0
1315 | Midnapore Division | Kharagpur Sub-Division | Construction of Pump House, Laying Rising main, Boundary wall, Laying distribution system pipe line, Accommodate FHTC (252 Nos.) including 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000011/2024-2025 | 1965/MD | 26/06/2024 | 300 | DEBASISH DOGRA | 97.72 | 0 | 55
1316 | Midnapore Division | Kharagpur Sub-Division | Construction of Pump House, Laying Rising main, Boundary wall, Laying distribution system pipe line, Accommodate FHTC (252 Nos.) including 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000043/2023-2024 | 1408/MD | 04/05/2023 | 749 | R. CONSTRUCTION | 88.64 | 0 | 65
1317 | Midnapore Division | Kharagpur Sub-Division | Installation of 250mm X 150mm X 150 Mtr. Depth Rig bore Tube well (2 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000078/2023-2024 | 2425/MD | 13/07/2023 | 21 | MIDNAPUR PIPE CONCERN | 15.62 | 0 | 100
1318 | Midnapore Division | Kharagpur Sub-Division | Laying distribution system pipe line & Accommodate FHTC (252 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000092/2023-2024 | 2468/MD | 14/07/2023 | 600 | WATER LINK | 69.34 | 0 | 70
1319 | Midnapore Division | Kharagpur Sub-Division | Laying distribution system pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000093/2023-2024 | 2469/MD | 14/07/2023 | 879 | GOUTAM PARIA | 44.55 | 0 | 75
1320 | Midnapore Division | Kharagpur Sub-Division | Laying distribution system pipe line & Accommodate FHTC (152 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000095/2023-2024 | 2470/MD | 14/07/2023 | 60 | BUNBA CONSTRUCTION | 34.51 | 0 | 68
1321 | Midnapore Division | Kharagpur Sub-Division | Laying distribution system pipe line & Accommodate FHTC (269 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000096/2023-2024 | 2471/MD | 14/07/2023 | 989 | MIDNAPUR PIPE CONCERN | 80.7 | 0 | 70
1322 | Midnapore Division | Kharagpur Sub-Division | Laying distribution system pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000097/2023-2024 | 2472/MD | 14/07/2023 | 60 | DEBASISH DOGRA | 47.36 | 0 | 95
1323 | Midnapore Division | Kharagpur Sub-Division | Construction of Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000146/2023-2024 | 2638/MD | 24/07/2023 | 60 | HYDRO TECH ASSOCIATES | 15.63 | 0 | 75
1324 | Midnapore Division | Kharagpur Sub-Division | Installation of 250mm X 150mm X 150 Mtr. Depth Rig bore Tube well (2 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000164/2023-2024 | 2640/MD | 24/07/2023 | 21 | MIDNAPUR PIPE CONCERN | 15.62 | 0 | 100
1325 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 Nos. Tube well under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000166/2023-2024 | 2669/MD | 26/07/2023 | 21 | DEBASISH DOGRA | 12.01 | 0 | 100
1326 | Midnapore Division | Kharagpur Sub-Division | Laying distribution system pipe line & Accommodate FHTC (152 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000171/2023-2024 | 2673/MD | 26/07/2023 | 45 | AJIJUR RAHAMAN MALLICK | 26.72 | 0 | 80
1327 | Midnapore Division | Kharagpur Sub-Division | Construction of RCC OHR (150 CuM), Pump House, Boundary wall & Accommodate FHTC (335 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000303/2024-2025 | 3399/MD | 25/11/2024 | 180 | A K SIKDAR | 110.39 | 0 | 15
1328 | Midnapore Division | Kharagpur Sub-Division | Construction of RCC OHR (150 CuM), Pump House, Boundary wall & Accommodate FHTC (324 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000314/2024-2025 | 3479/MD | 26/11/2024 | 360 | DEBASISH DOGRA | 109.07 | 0 | 20
1329 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line with Rising Main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, Development H/W site FHTC (117 Nos.) & 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000844/2023-2024 | 805/MD | 15/03/2024 | 60 | AJIJUR RAHAMAN MALLICK | 42.9 | 0 | 92
1330 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000181/2023-2024 | 1365/MD | 02/05/2023 | 0 | Resource Division | 36.92 | 0 | 0
1331 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000091/2023-2024 | 2465/MD | 14/07/2023 | 808 | GOBINDA MAITY | 1571.51 | 0 | 42
1332 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000072/2024-2025 | 3422/MD | 25/11/2024 | 0 | Resource Division | 11.76 | 0 | 0
1333 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000112/2022-2023 | 208/MD | 16/01/2023 | 0 | Resource Division | 30.42 | 0 | 0
1334 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, soil investigation, 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2432 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Dhitpur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000063/2023-2024 | 2144/MD | 08/06/2023 | 840 | M/S. EL-CON | 649.48 | 0 | 60
1335 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000085/2022-2023 | 194/MD | 16/01/2023 | 0 | Resource Division | 21.9 | 0 | 0
1336 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well for boosting purpose including FHTC, Valve chamber and other ancillary works of under Augmentation of Abasgarh W/S Scheme under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000670/2022-2023 | 723/MD | 09/03/2023 | 35 | WATER LINK | 11.31 | 0 | 50
1337 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Abasgarh PWSS within Midnapore Saar Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001012/2021-2022 | 531/MD | 21/03/2022 | 10 | GOBINDA MAITY | 2.26 | 0 | 100
1338 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000206/2023-2024 | 1422/MD | 04/05/2023 | 0 | Resource Division | 18.38 | 0 | 0
1339 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line and Accommodate FHTC (459 Nos.) work for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-V] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000006/2023-2024 | 975/MD | 10/04/2023 | 60 | J.K. BUILDERS | 77.87 | 0 | 100
1340 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 4 (four) nos. 250 X 150 mm dia. X 180 mtr. Depth deep tube well by direct rotary method for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-VII] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000079/2023-2024 | 2426/MD | 13/07/2023 | 45 | MIDNAPUR PIPE CONCERN | 34.6 | 0 | 80
1341 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and FHTC work (440 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-III] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000102/2023-2024 | 2484/MD | 17/07/2023 | 60 | MIDNAPUR PIPE CONCERN | 96.29 | 0 | 70
1342 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line and Accommodate FHTC (440 Nos.) work for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-IV] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000123/2023-2024 | 2522/MD | 18/07/2023 | 590 | S.N ENTERPRISE | 66.39 | 0 | 80
1343 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line, Rising main, Construction of Pump House, Boundary wall, FHTC work (360 Nos.) with 2 years operation & maintenance for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-II] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000194/2023-2024 | 2808/MD | 07/08/2023 | 637 | CHANDAN ROY | 157.84 | 0 | 2
1344 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and FHTC work (300 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-VI] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000234/2023-2024 | 3004/MD | 21/08/2023 | 838 | A.K. SIKDAR | 118.98 | 0 | 70
1345 | Midnapore Division | Midnapur Sadar Sub-Division | Construction and Commissioning of 450 Cum Capacity (Intze type with Pile) Over Headed Reservoir, Soil Investigation, Construction of Pump House, Boundary wall & accommodate FHTC (600 Nos.) for Proposed Sasha Bedia & its adjoining mouzas PWSS, Block-Garhbeta-II, Dist:- Paschim Medinipore under Midnapur Division, PHE Dte. [PART-I] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000854/2023-2024 | 831/MD | 15/03/2024 | 721 | SUNIL DULE | 183.79 | 0 | 30
1346 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000140/2023-2024 | 1299/MD | 28/04/2023 | 0 | Resource Division | 72.43 | 0 | 0
1347 | Midnapore Division | Ghatal Subdivision | Sinking of 2 (Two) nos. 250 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Bandipur PWSS with in Chandrakona- II block under Midnapore Division, P.H.E Dte. [PART-D] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000077/2023-2024 | 2424/MD | 13/07/2023 | 517 | MR GOUTAM GHOSH, | 20.39 | 0 | 100
1348 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Accommodate FHTC, Laying Rising main, Operation & Maintenance under JJM with allied work for Bandipur PWSS in Chandrakona-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000285/2023-2024 | 3902/MD | 27/09/2023 | 762 | M/S. D.K.H.CONSTRUCTION | 327.58 | 0 | 30
1349 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | RTOR000010/2024-2025 | 3331/MD | 25/11/2024 | 0 | Resource Division | 15.69 | 0 | 0
1350 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | RTOR000081/2022-2023 | 202/MD | 16/01/2023 | 0 | Resource Division | 37.26 | 0 | 0
1351 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 350 Cum & 300 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,209 Nos) including 2 years operation & maintenance For Golegram and Kanakpur Pipe water supply Scheme within Debra Block under Kharagpur Sub Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000386/2023-2024 | 5060/MD | 26/10/2023 | 613 | IJABUL SEKH | 992.27 | 0 | 45
1352 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000248/2023-2024 | 1583/MD | 15/05/2023 | 0 | Resource Division | 27.82 | 0 | 0
1353 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
1354 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Samsara & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000743/2022-2023 | 819/MD | 21/03/2023 | 20 | ENVIROTECH SOLUTIONS | 5.39 | 0 | 100
1355 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Samsara & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000761/2022-2023 | 1116/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 2.4 | 0 | 100
1356 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000163/2023-2024 | 1373/MD | 02/05/2023 | 0 | Resource Division | 27.23 | 0 | 0
1357 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
1358 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sautia & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000757/2022-2023 | 1112/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 1.49 | 0 | 100
1359 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000208/2023-2024 | 1460 | 08/05/2023 | 0 | Resource Division | 10.52 | 0 | 0
1360 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000259/2023-2024 | 2008/MD | 16/05/2023 | 0 | Resource Division | 27.68 | 0 | 0
1361 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying distribution pipe line & accommodate FHTC (118 Nos.) including 2 years O&M under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000040/2023-2024 | 1356/MD | 02/05/2023 | 60 | PULLOCK KUMAR GHOSH | 54.56 | 0 | 85
1362 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 100 CuM OHR (Torch type with solid raft) & Accommodate FHTC (250 Nos.) under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000110/2024-2025 | 3043/MD | 25/09/2024 | 540 | WATER LINK | 114.3 | 0 | 30
1363 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe under JJM with allied work for Augmentation of Amrakuchi & its adjoining mouzas W/S Scheme in Keshpur block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000139/2023-2024 | 2623/MD | 24/07/2023 | 45 | M/S. BLUE BIRD | 21.94 | 0 | 71
1364 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R {Consultancy work} in connection with the Functional House Hold Tap connection for Rejuvenation /Augmentation of existing AMRAKUCHI PWSS within Keshpur Block under Midnapore Division PHE Dte. (SL No-01) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000296/2022-2023 | 461/AE/MSSD | 05/08/2022 | 15 | ROY DESIGN & INFRASTRUCTURE | 2.15 | 0 | 100
1365 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000129/2022-2023 | 377/MD | 03/02/2023 | 0 | Resource Division | 27.13 | 0 | 0
1366 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
1367 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Borai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000759/2022-2023 | 1114/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 0.57 | 0 | 100
1368 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000213/2023-2024 | 1465 | 08/05/2023 | 0 | Resource Division | 37.96 | 0 | 0
1369 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000256/2023-2024 | 2007/MD | 16/05/2023 | 0 | Resource Division | 55.28 | 0 | 0
1370 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE2 Sadar Sub-division | RTOR000055/2023-2024 | 1194/MD | 26/04/2023 | 0 | Resource Division | 115 | 0 | 0
1371 | Midnapore Division | Kharagpur Sub-Division | Laying of uPVC distribution system, Rising Main, Construction of supporting structure of 10 Cum Water Tank, Switch Room cum Chlorine Room & Accommodate FHTC (124 Nos.) under JJM with allied work & 1 year O&M for Arka Markandapur Mini Water Supply Scheme in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000105/2023-2024 | 2487/MD | 17/07/2023 | 992 | A R ENTERPRISE | 36.71 | 0 | 60
1372 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000178/2023-2024 | 1372/MD | 02/05/2023 | 0 | Resource Division | 1.57 | 0 | 0
1373 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 200 Cum & 300 Cum Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (4,806 Nos.) including 2 years operation & maintenance For Bakalsabakram, Bhagabanpur and Chak Prayag Pipe water supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000470/2023-2024 | 5382/MD | 04/12/2023 | 574 | M/S. KAMAK ENGINEERS AND CO. | 1277.59 | 0 | 50
1374 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000198/2023-2024 | 1409 | 04/05/2023 | 0 | Resource Division | 24.77 | 0 | 0
1375 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000211/2023-2024 | 2826/MD | 07/08/2023 | 785 | GOBINDA MAITY | 1375.06 | 0 | 74
1376 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000001/2024-2025 | 2108/MD | 08/07/2024 | 0 | Resource Division | 6.49 | 0 | 0
1377 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000288/2023-2024 | 4060/MD | 12/10/2023 | 0 | Resource Division | 29.73 | 0 | 0
1378 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,416 nos.) under JJM with allied work for Sinnibar PWSS in Keshpur Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000258/2023-2024 | 3232/MD | 11/09/2023 | 848 | M/S. A.R. ENTERPRISE. | 917.01 | 0 | 40
1379 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Sinnibar & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 675 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000389/2024-2025 | 61/MD | 07/01/2025 | 45 | A-PLUS | 6.58 | 0 | 0
1380 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000044/2022-2023 | 104/MD | 10/01/2023 | 0 | Resource Division | 22.51 | 0 | 0
1381 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000057/2024-2025 | 3377/MD | 25/11/2024 | 0 | Resource Division | 21.04 | 0 | 0
1382 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well & Construction of Pump House under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division |  | ORD/000463/2023-2024 | 5345/MD | 29/11/2023 | 300 | ANNAPURNA TUBEWELL WORKS | 31.46 | 0 | 10
1383 | Midnapore Division | Ghatal Subdivision | Laying additional pipeline regarding balance work of distribution network for Jhakra & its adjoining mouza W/S Scheme under Chandrakona-II block within Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000478/2024-2025 | 481/MD | 13/02/2025 | 150 | NIMAI HAZRA | 37.52 | 0 | 0
1384 | Midnapore Division | Ghatal Subdivision | Laying distribution pipeline, Rising main, Accommodate FHTC (1140 Nos.) including 2yrs. O & M under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division |  | ORD/000633/2023-2024 | 5562/MD | 26/12/2023 | 756 | M/S. D.K.H.CONSTRUCTION | 388.07 | 0 | 5
1385 | Midnapore Division | Ghatal Subdivision | Construction of RCC OHR (400 CuM), Soil investigation, Boundary wall & Accommodate FHTC (1431 Nos.) under JJM with allied work for Jhakra PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division |  | ORD/000849/2023-2024 | 826/MD | 15/03/2024 | 720 | M/S R.N. ENTERPRISE | 233.69 | 0 | 30
1386 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division |  | RTOR000149/2022-2023 | 532/MD | 21/02/2023 | 0 | Resource Division | 52.71 | 0 | 0
1387 | Midnapore Division | Ghatal Subdivision | Construction of RCC OHR (450 CuM), Soil investigation, Boundary wall & Accommodate FHTC (919 Nos.) under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division |  | ORD/000003/2024-2025 | 1836/MD | 12/06/2024 | 180 | S.N ENTERPRISE | 216.01 | 0 | 0
1388 | Midnapore Division | Ghatal Subdivision | Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/000028/2024-2025 | 1220/AE/GSD | 10/06/2024 | 183 | HIRAK KUMAR GHOSH | 0.76 | 0 | 0
1389 | Midnapore Division | Ghatal Subdivision | Continuation work order for Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/000344/2025-2026 | 962/AE/GSD | 09/12/2025 | 159 | HIRAK KUMAR GHOSH | 0.9 | 0 | 0
1390 | Midnapore Division | Ghatal Subdivision | Hiring of Inspection vehicle for Jal Jeevan Mission on an ¿as and when required¿ basis, Motor cab (Standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older than 30 (Thirty) months from the date of 1st Registration on daily hire basis for the tenure of 06 (Six months) only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, Ghatal Sub-Division, P.H.E Dte. | AE Ghatal Sub-division |  | ORD/000353/2024-2025 | 1687/AE/GSD | 09/12/2024 | 182 | HIRAK KUMAR GHOSH | 0.85 | 0 | 0
1391 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Construction of Pump House & Accommodate FHTC (910 Nos.) under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division |  | ORD/000460/2023-2024 | 5326/MD | 28/11/2023 | 60 | PULLOCK KUMAR GHOSH | 83.89 | 0 | 30
1392 | Midnapore Division | Ghatal Subdivision | Laying distribution pipeline, Rising main, Accommodate FHTC (910 Nos.) including 2yrs. O & M under JJM with allied work for Kuapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division |  | ORD/000461/2023-2024 | 5327/MD | 28/11/2023 | 759 | M/S. D.K.H.CONSTRUCTION | 367.84 | 0 | 40
1393 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division |  | RTOR000150/2022-2023 | 533/MD | 21/02/2023 | 0 | Resource Division | 57.85 | 0 | 0
1394 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division |  | RTOR000166/2023-2024 | 1457/MD | 08/05/2023 | 0 | Resource Division | 16.87 | 0 | 0
1395 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 450 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,335 nos.) under JJM with allied work for Makarampur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000397/2023-2024 | 5090/MD | 30/10/2023 | 875 | SWACH ENVIRONMENT PRIVATE LIMITED | 733.83 | 0 | 55
1396 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000016/2024-2025 | 3337/MD | 25/11/2024 | 0 | Resource Division | 14.38 | 0 | 0
1397 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000049/2022-2023 | 108/MD | 10/01/2023 | 0 | Resource Division | 103.9 | 0 | 0
1398 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Tararui W/S Scheme in the District of Paschim Medinipore. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | BILL/00734/2022-2023 | BP-2022-23-345 | 01/02/2023 | 0 | DIPAK KUMAR BAKLY | 1.54 | 0 | 0
1399 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 150 X 100 mm dia. X 150 mtr. Depth Rig bored Tube wells for proposed additionally (boosting) to existing Tararui W/S Scheme, Dantan-I Block under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000108/2023-2024 | 2490/MD | 17/07/2023 | 15 | M/S BAKLY CONSTRUCTION | 5.91 | 0 | 80
1400 | Midnapore Division | RWS Midnapur Sub-Division | Laying of pipe line at Tararui East (Nimapada), Tararui Paschim (Ghosh Para) for supporting FHTC works of Tararui and its adjoining mouza W/S Scheme within Kharagpur Sub Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000213/2023-2024 | 455/RWS/MID | 10/08/2023 | 30 | ASMA CONSTRUCTION | 1.22 | 0 | 100
1401 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Trarui PWSS, Block :- Dantan-I in the District of Paschim Medinipur. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000439/2020-2021 | 309/MD | 22/02/2021 | 35 | DIPAK KUMAR BAKLY | 74.94 | 25.66 | 98
1402 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III) | RTOR000074/2023-2024 | 1218/MD | 27/04/2023 | 0 | Resource Division | 76.55 | 0 | 0
1403 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
1404 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Khas Jangal & its adjoining mouzas PWSS, Block - Keshpur, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 420 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000539/2024-2025 | 730/MD | 18/03/2025 | 45 | MALLICK ENTERPRISE | 5.4 | 0 | 0
1405 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000058/2024-2025 | 3378/MD | 25/11/2024 | 0 | Resource Division | 12.14 | 0 | 0
1406 | Midnapore Division | Ghatal Subdivision | Sinking of Three nos. 250 X 150 mm dia. X 200 mtr. Depth deep tube well by direct rotary method under JJM with allied work for Tatarpur PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000184/2023-2024 | 2737/MD | 01/08/2023 | 30 | SAJAL JANA | 35.06 | 0 | 100
1407 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Tatarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000750/2022-2023 | 1269/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.39 | 0 | 100
1408 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 700 cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,529 nos.) under JJM with allied work for Tatarpur PWSS in Daspur -I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000828/2023-2024 | 741/MD | 13/03/2024 | 361 | KHAN ENTERPRISE | 820.87 | 0 | 35
1409 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000151/2022-2023 | 534/MD | 21/02/2023 | 0 | Resource Division | 239.55 | 0 | 0
1410 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,760 nos.) under JJM with allied work for Dharmmapur PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000237/2023-2024 | 3040/MD | 22/08/2023 | 900 | BANERJEE CONSTRUCTION | 939.5 | 0 | 28
1411 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000034/2022-2023 | 100/MD | 10/01/2023 | 0 | Resource Division | 19.61 | 0 | 0
1412 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | RTOR000054/2024-2025 | 3374/MD | 25/11/2024 | 0 | Resource Division | 17.55 | 0 | 0
1413 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
1414 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000216/2023-2024 | 1480 | 10/05/2023 | 0 | Resource Division | 54.64 | 0 | 0
1415 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
1416 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of rising main & interconnection for Kusumdahari & its adjoining mouzas PWSS, Block: - Keshpur, District: - Paschim Midnapore under Midnapore Division, PHE Dte. (Length = 560 Mtr.) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000415/2024-2025 | 196/MD | 17/01/2025 | 45 | M/S. S.S. ENTERPRISE | 6.2 | 0 | 0
1417 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000055/2024-2025 | 3375/MD | 25/11/2024 | 0 | Resource Division | 11.51 | 0 | 0
1418 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube wells, Construction of 400 CuM Capacity R.C.C Over Head Reservoirs (Over Raft / Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6,875 Nos.) for Jagannathchak & Barbasi Pipe W/S Scheme including 2 years O&M within Kharagpur-II Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000248/2023-2024 | 3101/MD | 25/08/2023 | 772 | GOBINDA MAITY | 1932.69 | 0 | 25
1419 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000253/2023-2024 | 1587/MD | 15/05/2023 | 0 | Resource Division | 70.34 | 0 | 0
1420 | Midnapore Division | Jhargram RWS Sub Division | Retrofitting to accommodate FHTC under JJM in Banshia PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000183/2020-2021 | 1411/MD | 26/11/2020 | 180 | BISHNU PADA NANDI | 3.52 | 3.22 | 0
1421 | Midnapore Division | Jhargram RWS Sub Division | Retrofitting to accommodate FHTC under JJM in Chichira PWSS of Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000249/2020-2021 | 1581/MD | 11/12/2020 | 180 | SUNIL DULE | 31 | 12.55 | 0
1422 | Midnapore Division | Jhargram RWS Sub Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | VCH/001156/2020-2021 | 8443106 | 12/02/2021 | 0 | SANDIP MANNA | 0.15 | 0 | 0
1423 | Midnapore Division | Jhargram RWS Sub Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | VCH/001157/2020-2021 | 8443106 | 12/02/2021 | 0 | SOVANDEB MANNA | 0.03 | 0 | 0
1424 | Midnapore Division | Jhargram RWS Sub Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | VCH/001158/2020-2021 | 8443106 | 12/02/2021 | 0 | ARUP KR ADAK | 0.07 | 0 | 0
1425 | Midnapore Division | Jhargram RWS Sub Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | VCH/001159/2020-2021 | 8443106 | 12/02/2021 | 0 | ANIRBAN CHAKRABORTY | 0.18 | 0 | 0
1426 | Midnapore Division | Jhargram RWS Sub Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | Assistant Engineer | Junior Engineer-II | VCH/001410/2022-2023 | 844368 | 30/11/2022 | 0 | SUNIL DULE | 2.35 | 0 | 0
1427 | Midnapore Division | Jhargram RWS Sub Division | Retrofitting to accommodate FHTC under JJM in 2 Nos. P.W.S.S. within Gopiballavpur - I & 1 No. P.W.S.S. within Jamboni | Assistant Engineer | Junior Engineer-II | VCH/001411/2022-2023 | 844368 | 30/11/2022 | 0 | SUNIL DULE | 13 | 0 | 0
1428 | Midnapore Division | Jhargram RWS Sub Division | Retrofitting to accommodate FHTC under JJM in Chhatinasole PWSS of Gopiballavpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer | Junior Engineer-II | VCH/001635/2021-2022 | 8443115 | 23/03/2022 | 0 | CHAKRABORTTI ENTERPRISE | 23.06 | 0 | 0
1429 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. (Phase-II) | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000067/2021-2022 | 1059/MD | 02/07/2021 | 15 | NIMAI LAL GURIA | 7.53 | 6.88 | 1
1430 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Lohamelya PWSS of Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000187/2020-2021 | 1414/MD | 26/11/2020 | 180 | NIMAI LAL GURIA | 7.76 | 6.84 | 0
1431 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Barajharia PWSS of Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000191/2020-2021 | 1417/MD | 26/11/2020 | 180 | PROVAT KUMAR DE | 6.04 | 5.3 | 0
1432 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Jamboni PWSS of Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000192/2020-2021 | 1418/MD | 26/11/2020 | 180 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 4.47 | 3.11 | 0
1433 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Balibandh PWSS of Jamboni Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | ORD/000294/2020-2021 | 1589/MD | 11/12/2020 | 180 | NIRMAL DUTTA | 8.06 | 7.48 | 0
1434 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Chhenpara PWSS of Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | VCH/000149/2021-2022 | 844331 | 28/04/2021 | 0 | NIPENDRANATH SINGHA | 0.42 | 0 | 0
1435 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Chandalbandh PWSS of Nayagram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | VCH/000923/2021-2022 | 844353 | 17/01/2022 | 0 | PROVAT KUMAR DE | 7.38 | 0 | 0
1436 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Chhenpara PWSS of Jhargram block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | VCH/001465/2020-2021 | 8443377 | 24/03/2021 | 0 | NRIPENDRA NATH SINGHA | 3.84 | 0 | 0
1437 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Chhenpara PWSS of Jhargram Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | VCH/001630/2021-2022 | 8443154 | 24/03/2022 | 0 | NRIPENDRA NATH SINGHA | 0.55 | 0 | 0
1438 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Raskundu W/S Scheme, Block: - Garhbeta-III, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | ORD/000205/2020-2021 | 1427/MD | 26/11/2020 | 180 | M/S. EL-CON | 40.7 | 36.19 | 0
1439 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Tilabani W/S Scheme, Block: - Salboni, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | ORD/000206/2020-2021 | 1428/MD | 26/11/2020 | 180 | M/S. CARE | 30.62 | 17.61 | 0
1440 | Midnapore Division | Midnapur Sadar Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000267/2021-2022 | 8443116 | 31/05/2021 | 0 | MANABENDAN DAS | 0.08 | 0 | 0
1441 | Midnapore Division | Midnapur Sadar Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000268/2021-2022 | 8443116 | 31/05/2021 | 0 | PAPPU SHAW | 0.09 | 0 | 0
1442 | Midnapore Division | Midnapur Sadar Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000269/2021-2022 | 8443116 | 31/05/2021 | 0 | SIDDHESWAR BAG | 0.12 | 0 | 0
1443 | Midnapore Division | Midnapur Sadar Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000270/2021-2022 | 8443116 | 31/05/2021 | 0 | SUBRATA CHAKRABORTY | 0.05 | 0 | 0
1444 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000635/2021-2022 | 8443122 | 23/08/2021 | 0 | ANIRBAN CHAKRABORTY | 0.03 | 0 | 0
1445 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000636/2021-2022 | 8443122 | 23/08/2021 | 0 | SANDIP MANNA | 0.02 | 0 | 0
1446 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-III),JE2 Sadar Sub-division | VCH/000637/2021-2022 | 8443122 | 23/08/2021 | 0 | TANMOY BERA | 0.04 | 0 | 0
1447 | Midnapore Division | RWS Midnapur Sub-Division | Quotation as per WBSEDCL procedure-A (2010) electric quotation bill. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00412/2022-2023 | BP-2022-23-683 | 09/03/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.19 | 0 | 0
1448 | Midnapore Division | RWS Midnapur Sub-Division | Electric Bill of WBSEDCL. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00732/2022-2023 | BP-2022-23-683 | 09/03/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.19 | 0 | 0
1449 | Midnapore Division | RWS Midnapur Sub-Division | Accommodate FHTC( 70 ) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Maliara Water Supply Scheme within Medinipur Sadar Dev. Block under Midnapur Sadar Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. (SL No-02) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/02171/2023-2024 | BP-2023-24-601 | 02/02/2024 | 0 | HIRAK KUMAR GHOSH | 0.23 | 0 | 0
1450 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Maliara W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000203/2020-2021 | 1426/MD | 26/11/2020 | 180 | M/S. EL-CON | 40.92 | 25.45 | 0
1451 | Midnapore Division | RWS Midnapur Sub-Division | Additional Laying of Distribution pipe line at (Kalgunj ,Madhypara, Gourangapally & other different left out area) within Maliara Pipe Water Supply Scheme under Medinipore Sadar Block within Midnapore Division ,PHE Dte. (SL No-01) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000215/2023-2024 | 481/AE/MSSD | 08/08/2023 | 10 | HIRAK KUMAR GHOSH | 4.18 | 0 | 100
1452 | Midnapore Division | RWS Midnapur Sub-Division | Accommodate FHTC( 70 ) including supplying, laying, fitting, fixing of 15mm dia. NB PVC(Sch-80)/20mm dia. HDPE(PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Maliara Water Supply Scheme within Medinipur Sadar Dev. Block under Midnapur Sadar Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. (SL No-02) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000221/2023-2024 | 482/AEMSSD | 08/08/2023 | 10 | HIRAK KUMAR GHOSH | 4.44 | 0 | 100
1453 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of One no Additional Rig bored Tube Well 150 X 100 mm dia. X 120 Mtr. Depth for Maliara Pipe W/S Scheme under Midnapur Sadar Sub Division Within Midnapore Division, PHE Dte. (SL No-01) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000286/2022-2023 | 464./AE/MSSD | 08/08/2022 | 10 | HIRAK KUMAR GHOSH | 4.74 | 0 | 0
1454 | Midnapore Division | RWS Midnapur Sub-Division | Continuation for the work of "Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre , Health Care Institution etc" under Midnapur Division,PHE Dte. for the period of 03 months (from 01.04.2022 to 30.06.2022) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001014/2021-2022 | 147/AE/MSSD | 28/03/2022 | 3 | PULLOCK KUMAR GHOSH | 1.52 | 0 | 0
1455 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Maliara W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000715/2020-2021 |  | 15/12/2020 | 0 | M/S. EL-CON | 27.28 | 0 | 0
1456 | Midnapore Division | Midnapur Sadar Sub-Division | Functional Household Tap Connection data uploading charges in JJM_IMIS portal in Paschim Medinipur & Jhargram District under Jal Jeevan Mission | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00732/2023-2024 | 844336 | 12/09/2023 | 0 | PULLOCK KUMAR GHOSH | 2.04 | 0 | 0
1457 | Midnapore Division | Midnapur Sadar Sub-Division | Hire charges of Car No WB 33 D 6299 including supply of fuel and lubricants for the office of the Dy. SE, WC, PHE Dte. for the month of August. (MB No 3634/MD) | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/02032/2023-2024 | 84439 | 02/02/2024 | 0 | PULLOCK KUMAR GHOSH | 1.69 | 0 | 0
1458 | Midnapore Division | Midnapur Sadar Sub-Division | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/02048/2023-2024 |  | 20/02/2024 | 0 | PULLOCK KUMAR GHOSH | 2.33 | 0 | 0
1459 | Midnapore Division | Midnapur Sadar Sub-Division | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre, Health Care Institution etc. under Midnapore Division PHE Dte. Period from (15.07.2023 to 14.07.2024) | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/02177/2023-2024 | 844369 | 22/02/2024 | 0 | PULLOCK KUMAR GHOSH | 2.33 | 0 | 0
1460 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000236/2020-2021 | 1440/MD | 26/11/2020 | 180 | M/S. EL-CON | 70.72 | 27.4 | 100
1461 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation work order ¿ Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre ,Health Care Institution etc¿. under Midnapore Division PHE Dte.for the period of 06 (months), from (01.01.2023 to 30.06.2023) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000635/2022-2023 | 764/MSSD | 31/12/2022 | 181 | PULLOCK KUMAR GHOSH | 2.04 | 0 | 0
1462 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000632/2021-2022 | 8443121 | 23/08/2021 | 0 | PARTHA PRATIM PAL | 0.01 | 0 | 0
1463 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000634/2021-2022 | 8443121 | 23/08/2021 | 0 | SHRABONTI BERA | 0.1 | 0 | 0
1464 | Midnapore Division | Midnapur Sadar Sub-Division | Data Entry of FHTC. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000850/2021-2022 | 844386 | 13/09/2021 | 0 | PAPPU SHAW | 0.05 | 0 | 0
1465 | Midnapore Division | Midnapur Sadar Sub-Division | For FHTC Data Entry. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000851/2021-2022 | 844386 | 13/09/2021 | 0 | SIDDHESWAR BAG | 0.1 | 0 | 0
1466 | Midnapore Division | Midnapur Sadar Sub-Division | For FHTC Data Entry. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000852/2021-2022 | 844386 | 13/09/2021 | 0 | SUBRATA CHAKRABORTY | 0.02 | 0 | 0
1467 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000266/2020-2021 | 1463/MD | 26/11/2020 | 180 | DULAL CHANDRA DAS | 87.43 | 37.47 | 0
1468 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chandkuri (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000727/2020-2021 |  | 15/12/2020 | 0 | DULAL CHANDRA DAS | 20 | 0 | 0
1469 | Midnapore Division | Jhargram RWS Sub Division | Material Requisition To Resource Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | RTOR000017/2021-2022 | 2162/MD | 17/12/2021 | 0 | Resource Division | 5.58 | 0 | 0
1470 | Midnapore Division | Jhargram RWS Sub Division | Purchasing of Materials. | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | VCH/001683/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 5.58 | 0 | 0
1471 | Midnapore Division | Jhargram Division | Sinking of 250mm X 150mm dia. & depth 150 Mtr. Rig bore Tube well - II for Augmentation of Pakuria W/S Scheme within Jhargram block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000017/2022-2023 | 614/MD | 04/04/2022 | 15 | TAPAS KUMAR GIRI | 6.58 | 0 | 1
1472 | Midnapore Division | Jhargram Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Pukuria PWSS in Jhargram Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000247/2021-2022 | 147/JSD | 12/08/2021 | 14 | INDRANIL DUTTA & ASSOCIATES | 2.94 | 0 | 1
1473 | Midnapore Division | Jhargram Division | Laying of Clear Water Rising Main / Distribution pipe line and FHTC work including Sinking of 250mm X 150mm dia. & 150 Mtr. Depth Rig bored Tube well for Augmentation of Ground Water Based Pukuria PWSS to Accommodate FHTC in Jhargram Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000626/2021-2022 | 179/MD | 01/02/2022 | 60 | ASHIM KUMAR DEY | 96.77 | 0 | 1
1474 | Midnapore Division | Jhargram Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000011/2022-2023 | 2164/MD | 21/10/2022 | 0 | Resource Division | 5.12 | 0 | 0
1475 | Midnapore Division | Jhargram Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000020/2021-2022 | 2163/MD | 17/12/2021 | 0 | Resource Division | 1.81 | 0 | 0
1476 | Midnapore Division | Jhargram Division | Purchasing of Materials. | Assistant Engineer,Assistant Engineer Headquarter,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | VCH/001684/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.21 | 0 | 0
1477 | Midnapore Division |  | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Kechenda PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  |  | VCH/001374/2021-2022 | BP-2021-22-402 | 23/02/2022 | 0 | RADIANT | 1.36 | 0 | 0
1478 | Midnapore Division | Ghatal Subdivision | Laying interconnection in between Rising main pipe line and distribution pipe line with OHR and allied works of KASANDA W/S Scheme within Candrakona-I Block, under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | BILL/00232/2023-2024 | BP-2023-24-16 | 28/04/2023 | 0 | M/S. A.R. ENTERPRISE. | 0.55 | 0 | 0
1479 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Kasanda PWSS under Chandrakona-I block in Paschim Medinipur district (Phase-II). | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000014/2022-2023 | 611/MD | 04/04/2022 | 15 | DEVJYOTI BERA | 7.67 | 0 | 0
1480 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Kasanda W/S Scheme, Block: - Chandrakona-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000287/2020-2021 | 1585/MD | 11/12/2020 | 180 | DEVJYOTI BERA | 24.31 | 0 | 0
1481 | Midnapore Division | Jhargram RWS Sub Division | Retrofitting of Ground Water Based W/S Scheme for Baliband PWSS to accommodate FHTC in Block Jamboni under Jhargram Division P.H.E. Dte. (Phase-II) | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | ORD/000691/2021-2022 | 288/MD | 15/02/2022 | 45 | NRIPENDRA NATH SINGHA | 6.24 | 0 | 1
1482 | Midnapore Division | Jhargram RWS Sub Division | Material Requisition To Resource Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000022/2021-2022 | 2166/MD | 17/12/2021 | 0 | Resource Division | 0.32 | 0 | 0
1483 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Keudi PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000480/2021-2022 | 2174/MD | 17/12/2021 | 21 | DEBJIT PATRA | 8.45 | 0 | 0
1484 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chhoto Keundi, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000863/2020-2021 | 343/MD | 24/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.4 | 0 | 0
1485 | Midnapore Division | RWS Midnapur Sub-Division | Electric Quation for Khairullachaki PWSS Tube well-II in connection Mohanpur CCC. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00006/2023-2024 | BP-2023-24-12 | 24/04/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0
1486 | Midnapore Division | RWS Midnapur Sub-Division | Restoration of road shoulder flank etc. after laying pipeline by PHE Deptt. At NL Khan Link Road from 3.10 km to 4.20 km under PWD, Midnapur Division, in the district of Paschim Medinipur during the year 2022-23 | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00369/2022-2023 | BP-2022-23-631 | 23/02/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 10 | 0 | 0
1487 | Midnapore Division | RWS Midnapur Sub-Division | Laying distribution pipe line, soil test, FHTC & construction of R.C.C. Over Head Reservoir of capacity 150 Cum and staging height 20.00 mtr. with allied work including Sinking of Deep Tube Well of 250 mm x 150 mm x250 m for Augmentation of Khairullachak W/S Scheme in Midnapore Sadar Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000008/2022-2023 | 605/MD | 04/04/2022 | 180 | BANERJEE CONSTRUCTION | 411.2 | 0 | 21
1488 | Midnapore Division | RWS Midnapur Sub-Division | Construction of Chlorine storage room for Midnapore Sadar Sub-Division Store at Narampur P.H.E. Complex under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000069/2024-2025 | 2661/MD | 29/08/2024 | 60 | PULLOCK KUMAR GHOSH | 5 | 0 | 60
1489 | Midnapore Division | RWS Midnapur Sub-Division | Construction of 1 (One) No. 5.40 X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Augmentation of Khairullachak & its adjoining mouzas PWSS in block - Midnapore Sadar, District - Paschim Medinipur (Type-B). | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000845/2023-2024 | 806/MD | 15/03/2024 | 60 | BENGAL TRADERS | 7.12 | 0 | 91
1490 | Midnapore Division | RWS Midnapur Sub-Division | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Khairullachak (Block-Midnapore Sadar) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001037/2021-2022 | 1645/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.56 | 0 | 0
1491 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000027/2021-2022 | 2474/MD | 06/12/2022 | 0 | Resource Division | 13.36 | 0 | 0
1492 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000030/2021-2022 | 2275/MD | 31/12/2021 | 0 | Resource Division | 12.33 | 0 | 0
1493 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000114/2022-2023 | 218/MD | 16/01/2023 | 0 | Resource Division | 9.39 | 0 | 0
1494 | Midnapore Division | RWS Midnapur Sub-Division | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Khairullachak to Accommodate FHTC. Block - Midnapore. District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000462/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 12.33 | 0 | 0
1495 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Retrofitting to accommodate FHTC (additional quantity) under JJM in Jatra Bansiraisol PWSS in Salboni block within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000550/2022-2023 | 2382/MD | 23/11/2022 | 10 | PULLOCK KUMAR GHOSH | 1.82 | 0 | 0
1496 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Jatra & Banshirasol, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000565/2020-2021 | 59/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.06 | 0 | 0
1497 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001119/2020-2021 | 8443498 | 30/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 2.05 | 0 | 0
1498 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001381/2021-2022 | BP-2021-22-410 | 23/02/2022 | 0 | BANERJEE CONSTRUCTION | 15 | 0 | 0
1499 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accomodate FHTC under JJM in Kharika PWSS Block Sabang District Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001601/2021-2022 | BP-2021-22-410 | 23/02/2022 | 0 | BANERJEE CONSTRUCTION | 0.21 | 0 | 0
1500 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Sauri Kotbar PWSS, Block :- Dantan-II in the District of Paschim Medinipur. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000553/2020-2021 | 425/MD | 26/02/2021 | 40 | TARUN KUMAR BHATTACHARYA | 89.08 | 0 | 0
1501 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Sauri Kotbar & its adjoining mouzas W/S Scheme within Dantan-II Dev. Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000645/2022-2023 | 581/MD | 23/02/2023 | 30 | DIPAK KUMAR BAKLY | 22.43 | 0 | 100
1502 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Baita PWSS to accommodate FHTC under JJM under Mohanpur block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | ORD/000413/2021-2022 | 2018/MD | 03/12/2021 | 60 | M/S. A.R. ENTERPRISE. | 100.97 | 0 | 80
1503 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Baita, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur) | VCH/001420/2021-2022 | BP-2021-22-416 | 24/02/2022 | 0 | SIRCON ENGINEERING SERVICES | 2.47 | 0 | 0
1504 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.Rs. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Nilhat, (ii) Mirjapur & (iii) Lachhmi Chak & its adj. Mouzas of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000423/2021-2022 | 1337/MD | 18/08/2021 | 10 | GOBINDA MAITY | 4.39 | 0 | 0
1505 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Nilhat, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000627/2021-2022 | 180/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 36.44 | 0 | 100
1506 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000006/2021-2022 | 2115/MD | 13/12/2021 | 0 | Resource Division | 1.39 | 0 | 0
1507 | Midnapore Division | Kharagpur Sub-Division | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Nilhat mouzas, Block - Sabang, District - Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000456/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.39 | 0 | 0
1508 | Midnapore Division | Kharagpur Sub-Division | For payment of liabilities. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001691/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.39 | 0 | 0
1509 | Midnapore Division | Kharagpur Sub-Division | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001825/2021-2022 | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.19 | 0 | 0
1510 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.Rs. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Mangrajpur & (ii) Lejibheri of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000422/2021-2022 | 1336/MD | 18/08/2021 | 10 | GOBINDA MAITY | 2.79 | 0 | 10
1511 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
1512 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Lejibheri, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000628/2021-2022 | 181/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 23.48 | 0 | 100
1513 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000007/2021-2022 | 2116/MD | 13/12/2021 | 0 | Resource Division | 0.58 | 0 | 0
1514 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Lejibheri mouzas. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000455/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.58 | 0 | 0
1515 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of Materials. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001692/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.58 | 0 | 0
1516 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Naoyagan & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000449/2021-2022 | 1276/MD | 05/08/2021 | 10 | GOBINDA MAITY | 2.11 | 0 | 0
1517 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
1518 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Naoyagan (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000759/2021-2022 | 343/MD | 21/02/2022 | 150 | SANKAR PRASAD MAITY | 43.79 | 0 | 100
1519 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Naoyagan (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000760/2021-2022 | 344/MD | 21/02/2022 | 150 | SANKAR PRASAD MAITY | 41.8 | 0 | 70
1520 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000012/2021-2022 | 2125/MD | 14/12/2021 | 0 | Resource Division | 2.92 | 0 | 0
1521 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Naoyagan mouzas, Block - Sabang, District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000449/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.06 | 0 | 0
1522 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Naoyagan & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001396/2021-2022 | BP-2021-22-388 | 18/02/2022 | 0 | GOBINDA MAITY | 0.32 | 0 | 0
1523 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001700/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.92 | 0 | 0
1524 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001824/2021-2022 | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 8.11 | 0 | 0
1525 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground water based piped water supply scheme for Panpara (Part) to Accommodate FHTC under JJM under Sabang Block in Paschim Medinipur Districct Under Medinipur Division PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000209/2022-2023 | 1674/MD | 12/08/2022 | 1234 | BANERJEE CONSTRUCTION | 55.48 | 0 | 30
1526 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Panpara PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000437/2021-2022 | 1675/MD | 29/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.16 | 0 | 100
1527 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Jamira (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000224/2022-2023 | 1731/MD | 23/08/2022 | 150 | MIDNAPUR PIPE CONCERN | 45.86 | 0 | 80
1528 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Jamira (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000225/2022-2023 | 1732/MD | 23/08/2022 | 150 | MIDNAPUR PIPE CONCERN | 39.37 | 0 | 100
1529 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000044/2024-2025 | 3353/MD | 25/11/2024 | 0 | Resource Division | 2.34 | 0 | 0
1530 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Raghunathpur (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000129/2022-2023 | 1363/MD | 08/07/2022 | 150 | GOUTAM RAY | 43.98 | 0 | 100
1531 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Raghunathpur (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000149/2022-2023 | 1418/MD | 15/07/2022 | 150 | ASHIM KUMAR DEY | 41.83 | 0 | 0
1532 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Raghunathpur (Zone-III), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000150/2022-2023 | 1419/MD | 15/07/2022 | 150 | WATER LINK | 43.03 | 0 | 100
1533 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- Raghunathpur under Dewanchak¿II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000415/2021-2022 | 1328/MD | 17/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.18 | 0 | 0
1534 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000046/2024-2025 | 3356/MD | 25/11/2024 | 0 | Resource Division | 3.17 | 0 | 0
1535 | Midnapore Division | Kharagpur Sub-Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Bishnupur (Part) to Accommodate FHTC under JJM at Sabang Block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000379/2022-2023 | 1962/MD | 20/09/2022 | 45 | KISHORE GHOSH | 49.7 | 0 | 60
1536 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Bishnupur PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000429/2021-2022 | 1661/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.16 | 0 | 100
1537 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bhabaninagar PWSS Block-Midnapore Sadar in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000412/2021-2022 | 2017/MD | 03/12/2021 | 60 | MASUM ALI KHAN | 113.43 | 0 | 80
1538 | Midnapore Division | Kharagpur Sub-Division | Retrofitting of Krishnapriya PWSS to accommodate FHTC in Pingla block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000046/2022-2023 | 839/MD | 02/05/2022 | 30 | ANUSKA ENTERPRISE | 36.17 | 0 | 99
1539 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | RTOR000097/2024-2025 | 3416/MD | 25/11/2024 | 0 | Resource Division | 5.4 | 0 | 0
1540 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-II), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000021/2022-2023 | 618/MD | 04/04/2022 | 637 | DEVJYOTI BERA | 36.33 | 0 | 90
1541 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-I), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000715/2021-2022 | 319/MD | 17/02/2022 | 150 | PULLOCK KUMAR GHOSH | 39.42 | 0 | 100
1542 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Masharpur (Zone-I), Block ¿ Ghatal, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001077/2022-2023 | 433/MD | 10/02/2023 | 15 | PULLOCK KUMAR GHOSH | 0.84 | 0 | 100
1543 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000034/2021-2022 | 2273/MD | 31/12/2021 | 0 | Resource Division | 1.64 | 0 | 0
1544 | Midnapore Division | Ghatal Subdivision | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Masharpur mouza under SAGY, Block - Ghatal. GP - Dewanchak-11, PS - Ghatal, Dist.- Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000442/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.64 | 0 | 0
1545 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00720/2022-2023 | 22-23-707,8,9 | 13/03/2023 | 0 | GOBINDA MAITY | 61 | 0 | 0
1546 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00721/2022-2023 | 2022-23-723,24 | 20/03/2023 | 0 | GOBINDA MAITY | 4.92 | 0 | 0
1547 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00722/2022-2023 | 2022-23-780-781 | 29/03/2023 | 0 | GOBINDA MAITY | 28.72 | 0 | 0
1548 | Midnapore Division | Ghatal Subdivision | Preliminarily ground protection works (i.e. Driving Eucalyptus Bullah Piles, Land Development etc.) in connection with Construction of R.C.C. OHR at Head Works site of Jote Kanuramgar W/S Scheme under Midnapore Division, PHE Dte. (Total Length of Double row piling works @ 500 C/C = 100.00 Mtr.) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000070/2024-2025 | 2662/MD | 29/08/2024 | 30 | GOBINDA MAITY | 18.98 | 0 | 0
1549 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000499/2022-2023 | 2364/MD | 21/11/2022 | 1242 | GOBINDA MAITY | 1460.37 | 0 | 58
1550 | Midnapore Division | Ghatal Subdivision | Construction of M.S. Fabricated and R.C.C Supporting Structure including aligning pipe line in connection of laying distribution main of Jote Kanuramgarh & Ranichak Water supply scheme under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000628/2022-2023 | 453/MD | 13/02/2023 | 60 | GOBINDA MAITY | 50.85 | 0 | 60
1551 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000025/2024-2025 | 3344/MD | 25/11/2024 | 0 | Resource Division | 18.02 | 0 | 0
1552 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000145/2022-2023 | 516/MD | 20/02/2023 | 0 | Resource Division | 40.67 | 0 | 0
1553 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000169/2022-2023 | 904/MD | 31/03/2023 | 0 | Resource Division | 40.66 | 0 | 0
1554 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00720/2022-2023 | 22-23-707,8,9 | 13/03/2023 | 0 | GOBINDA MAITY | 61 | 0 | 0
1555 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00721/2022-2023 | 2022-23-723,24 | 20/03/2023 | 0 | GOBINDA MAITY | 4.92 | 0 | 0
1556 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00722/2022-2023 | 2022-23-780-781 | 29/03/2023 | 0 | GOBINDA MAITY | 28.72 | 0 | 0
1557 | Midnapore Division | Ghatal Subdivision | Laying additional distribution system pipe line & accommodate FHTC (350 Nos.) for Ramkrishnapur W/S Scheme under JJM within Daspur-II Block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000075/2024-2025 | 2788/MD | 03/09/2024 | 75 | GOBINDA MAITY | 44.45 | 0 | 0
1558 | Midnapore Division | Ghatal Subdivision | Supply & Delivery of DI Specials for laying of Rising Main & distribution system including interconnection for Ramkrishnapur and its adjoining mouzas Water Supply Scheme within Daspur-II Block under Ghatal Sub Division of Midnapore Division, P.H.E.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000457/2023-2024 | 799/AE/GSD | 10/11/2023 | 7 | GOBINDA MAITY | 1.26 | 0 | 100
1559 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 400 CuM OHR (Intze type with pile foundation) & Accommodate FHTC under JJM with allied work for (i) Ranichak & its adjoining mouzas W/S Scheme, (ii) Jote Kanu Ramgarh & its adjoining mouzas W/S Scheme, (iii) Ramkrishnapur & its adjoining mouzas W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000499/2022-2023 | 2364/MD | 21/11/2022 | 1242 | GOBINDA MAITY | 1460.37 | 0 | 58
1560 | Midnapore Division | Ghatal Subdivision | Laying of Rising main including interconnection of Ramkrishnapur and its adjoining mouzas Water Supply Scheme under Daspur-II Block under Ghatal Sub-Division within Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000717/2023-2024 | 143/MD | 18/01/2024 | 20 | GOBINDA MAITY | 6.05 | 0 | 100
1561 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000026/2024-2025 | 3345/MD | 25/11/2024 | 0 | Resource Division | 10.33 | 0 | 0
1562 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000146/2022-2023 | 517/MD | 20/02/2023 | 0 | Resource Division | 16.87 | 0 | 0
1563 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
1564 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000035/2023-2024 | 1196 | 26/04/2023 | 0 | Resource Division | 31.5 | 0 | 0
1565 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000147/2023-2024 | 1266/MD | 28/04/2023 | 0 | Resource Division | 22.99 | 0 | 0
1566 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000051/2023-2024 | 1190/MD | 26/04/2023 | 0 | Resource Division | 23.87 | 0 | 0
1567 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
1568 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000100/2023-2024 | 1237/MD | 27/04/2023 | 0 | Resource Division | 26.22 | 0 | 0
1569 | Midnapore Division | Midnapur Mechanical Sub Division-I | Installation of Display Board for JJM work at different Piped Water Supply Scheme under different block within Midnapore Division, PHE Dte. [PART-B] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000785/2023-2024 | 507/MD | 27/02/2024 | 10 | HIRAK KUMAR GHOSH | 0.96 | 0 | 100
1570 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000105/2023-2024 | 1284/MD | 28/04/2023 | 0 | Resource Division | 39.41 | 0 | 0
1571 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000239/2023-2024 | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 33
1572 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
1573 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000116/2024-2025 | 3452/MD | 25/11/2024 | 0 | Resource Division | 8 | 0 | 0
1574 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
1575 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
1576 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000218/2023-2024 | 1481 | 10/05/2023 | 0 | Resource Division | 37.4 | 0 | 0
1577 | Midnapore Division | Midnapur Mechanical Sub Division-I | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-181] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00806/2024-2025 | BP-2024-25-444 | 07/10/2024 | 0 | SOUTH EASTERN RAILWAY | 6.32 | 0 | 0
1578 | Midnapore Division | Midnapur Mechanical Sub Division-I | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-182] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00807/2024-2025 | BP-2024-25-444 | 07/10/2024 | 0 | SOUTH EASTERN RAILWAY | 6.24 | 0 | 0
1579 | Midnapore Division | Midnapur Mechanical Sub Division-I | Joint inspection regarding laying of water supply pipe line of under ground Railway track crossing of 600mm dia M.S. carrier pipe by jack pushing method by PHE at Km 171/06/08-171/05-07 between DNT-AGV under the jurisdiction of ADEN/South/KGP. [Application ID - SER-KGP-2024-WL-182] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00808/2024-2025 | BP-2024-25-444 | 07/10/2024 | 0 | SOUTH EASTERN RAILWAY | 5.93 | 0 | 0
1580 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000069/2023-2024 | 1277/MD | 28/04/2023 | 0 | Resource Division | 27.29 | 0 | 0
1581 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000159/2022-2023 | 1153/MD | 25/04/2023 | 0 | Resource Division | 23.29 | 0 | 0
1582 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
1583 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000097/2022-2023 | 188/MD | 16/01/2023 | 0 | Resource Division | 16.01 | 0 | 0
1584 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000112/2024-2025 | 3448/MD | 25/11/2024 | 0 | Resource Division | 12.2 | 0 | 0
1585 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
1586 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000049/2023-2024 | 1199 | 26/04/2023 | 0 | Resource Division | 13.34 | 0 | 0
1587 | Midnapore Division | Ghatal Subdivision | Laying of Rising main pipeline for Chaipat (Zone-I) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000360/2024-2025 | 3787/MD | 24/12/2024 | 45 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 6.2 | 0 | 0
1588 | Midnapore Division | Ghatal Subdivision | Laying of Rising main pipeline for Chaipat (Zone-II) PWSS under Daspur-II block within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000361/2024-2025 | 3788/MD | 24/12/2024 | 45 | ENVIROEXCELSIOR SOLUTIONS PRIVATE LIMITED | 5.32 | 0 | 0
1589 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 2 nos. 400 cum OHR (Intze type with pile foundation) & 3 Nos. 300 Cum OHR & Accommodate FHTC (10,944 Nos,) under JJM with allied work for (i) Chaipat (Zone-I & Zone-II) & its adjoining mouzas W/S scheme (ii) Kelegoda & its adjoining mouzas W/S Scheme (iii) Uttarbar (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000514/2022-2023 | 2556/MD | 15/12/2022 | 1238 | M/S. S.S. ENTERPRISE | 2473.34 | 0 | 18
1590 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000023/2024-2025 | 3341/MD | 25/11/2024 | 0 | Resource Division | 25.58 | 0 | 0
1591 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000082/2023-2024 | 1296/MD | 28/04/2023 | 0 | Resource Division | 23.21 | 0 | 0
1592 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000116/2023-2024 | 1308/MD | 28/04/2023 | 0 | Resource Division | 32.28 | 0 | 0
1593 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
1594 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000097/2023-2024 | 1288/MD | 28/04/2023 | 0 | Resource Division | 34.59 | 0 | 0
1595 | Midnapore Division | Kharagpur Sub-Division | Construction of approach road for Head work site of Radhanagar Piped Water Supply Scheme within Narayangarh Block under Midnapore Division, PHE Dte. [200 Mtr. Long X 3 Mtr. Width] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000004/2025-2026 | 995/AE/HQ/MD | 22/04/2025 | 30 | GOURMOHAN DAS | 2.28 | 0 | 0
1596 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
1597 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000028/2023-2024 | 1168/MD | 26/04/2023 | 0 | Resource Division | 28.05 | 0 | 0
1598 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000113/2022-2023 | 213/MD | 16/01/2023 | 0 | Resource Division | 18.54 | 0 | 0
1599 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000151/2023-2024 | 1270/MD | 28/04/2023 | 0 | Resource Division | 24.42 | 0 | 0
1600 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000146/2023-2024 | 1265/MD | 28/04/2023 | 0 | Resource Division | 24.15 | 0 | 0
1601 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 200 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1188 nos) under JJM with allied work for Dontiara PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000125/2023-2024 | 2523/MD | 18/07/2023 | 180 | SUJATA CONSTRUCTION | 350.99 | 0 | 0
1602 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 100
1603 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000062/2022-2023 | 70/MD | 09/01/2023 | 0 | Resource Division | 15.8 | 0 | 0
1604 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000126/2023-2024 | 2524/MD | 18/07/2023 | 840 | NABA KUMAR BHUNIA | 1870.43 | 0 | 82
1605 | Midnapore Division | Kharagpur Sub-Division | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000180/2024-2025 | 3165/MD | 05/10/2024 | 255 | NABA KUMAR BHUNIA | 78.57 | 0 | 50
1606 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000118/2024-2025 | 3454/MD | 25/11/2024 | 0 | Resource Division | 19.82 | 0 | 0
1607 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000126/2023-2024 | 2524/MD | 18/07/2023 | 840 | NABA KUMAR BHUNIA | 1870.43 | 0 | 82
1608 | Midnapore Division | Kharagpur Sub-Division | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000180/2024-2025 | 3165/MD | 05/10/2024 | 255 | NABA KUMAR BHUNIA | 78.57 | 0 | 50
1609 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000119/2024-2025 | 3455/MD | 25/11/2024 | 0 | Resource Division | 16.23 | 0 | 0
1610 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000110/2022-2023 | 206/MD | 16/01/2023 | 0 | Resource Division | 22.06 | 0 | 0
1611 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000127/2024-2025 | 3463/MD | 25/11/2024 | 0 | Resource Division | 21.44 | 0 | 0
1612 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
1613 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh, Dantan-I & Dantan-II Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (A) Narayangarh block- (1) Kasba, (B) Dantan-I block - (1) Birbhadrapur, (2) Menakapur & (3) Benapura, (C) Dantan-II block - (1) Kusumda (Turkakasba)] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000733/2022-2023 | 707/MD | 06/03/2023 | 35 | JADAVPUR UNIVERSITY | 23.9 | 0 | 20
1614 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000030/2023-2024 | 1173/MD | 26/04/2023 | 0 | Resource Division | 26.77 | 0 | 0
1615 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube well, Laying of Rising Main, Laying distribution pipe line, Pump House & Accommodate FHTC (437 Nos.) including 2 years operation & maintenance under JJM with allied work for Godapiyasol & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. in Paschim Medinipur District. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000117/2023-2024 | 2492/MD | 17/07/2023 | 841 | MIDNAPUR PIPE CONCERN | 154.62 | 0 | 40
1616 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Boundary wall, 150 cum OHR (Torch type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied work for Godapiyasol & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. in Paschim Medinipur District. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000334/2024-2025 | 3577/MD | 06/12/2024 | 540 | MIDNAPUR PIPE CONCERN | 115.89 | 0 | 0
1617 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000127/2022-2023 | 374/MD | 03/02/2023 | 0 | Resource Division | 24.83 | 0 | 0
1618 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000114/2023-2024 | 1317/MD | 28/04/2023 | 0 | Resource Division | 25.94 | 0 | 0
1619 | Midnapore Division | Kharagpur Sub-Division | Extension of pipe line in connection with of FHTC Work at Mouza Kapasda, Uttar Bansboni, Rambar, Khepal at Kapasda PWSS within Sabang Block under Kharagpur Sub-Division Within Midnapore Division, Phe.Dte. District- Paschim Midnapore. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000885/2021-2022 | 68/AE/KSD | 03/02/2022 | 15 | KRISHNENDU SEKHAR DAS | 4.83 | 0 | 0
1620 | Midnapore Division | Kharagpur Sub-Division | Continuation Work for Hiring of Bharat Stage-II/III/diesel motor cab(Lusury Taxi)(Standard Non-AC) having contract carriage permit from the reginal transport authority for the office of the Assistant Engineer, Kharagpur Sub-Division, P.H.E. Dte.(For 3 Months) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/001071/2022-2023 | 116/AE/KSD | 30/01/2023 | 90 | GOBINDA MAITY | 0.48 | 0 | 100
1621 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Rising Main, Boundary wall, Soil investigation, 350 CuM OHR (Intze type with pile foundation) & Accommodate FHTC (264 Nos.) under JJM with allied work for Augmentation of Dharma Pipe W/S Scheme in Daspur-I Block including supply of all labour & materials within Ghtaal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000542/2024-2025 | 734/MD | 18/03/2025 | 180 | KHAN ENTERPRISE (PARTNER - MD. BABAR ALI KHAN & MD. SHAIN KHAN) | 324.3 | 0 | 0
1622 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE1 Ghatal Sub-division | RTOR000197/2023-2024 | 1417/MD | 04/05/2023 | 0 | Resource Division | 29.1 | 0 | 0
1623 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (342) for Augmentation of Mulgram PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000197/2023-2024 | 2811/MD | 07/08/2023 | 753 | SAMIT PAL | 47.99 | 0 | 12
1624 | Midnapore Division | Ghatal Subdivision | Balance allied works for construction of OHR at Head Works Site of Mulgram water supply Scheme within Ghatal Sub-Division under Midnapore Division PHE.Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000677/2023-2024 | 733/AE/GSD | 12/10/2023 | 10 | SUBHASIS DOLAI | 1.84 | 0 | 100
1625 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000132/2022-2023 | 405/MD | 07/02/2023 | 0 | Resource Division | 3.21 | 0 | 0
1626 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 (Intze type with Pile Foundation) & Accommodate FHTC (2,554 Nos.) including Two years O&M under JJM with allied work for Bhatuigerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000263/2023-2024 | 3237/MD | 11/09/2023 | 924 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 837.38 | 0 | 37
1627 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000193/2023-2024 | 1406/MD | 04/05/2023 | 0 | Resource Division | 57.13 | 0 | 0
1628 | Midnapore Division | Kharagpur Sub-Division | Hiring of Bharat Stage IV/V diesel Motor Cabs usury AC), having contract Carriage permit from the Regional Transport Authority for the offies of the Assistant Engineer, Kharagpur Sub-Division, PILE. Die. (For 06 months). period for 23.03.2024 to 22.09.2024 | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000934/2023-2024 | 1598/AE/KSD | 22/03/2024 | 180 | M/S. SOMNATH | 1.01 | 0 | 0
1629 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000079/2024-2025 | 3430/MD | 25/11/2024 | 0 | Resource Division | 29.45 | 0 | 0
1630 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000103/2022-2023 | 180/MD | 16/01/2023 | 0 | Resource Division | 36.49 | 0 | 0
1631 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 300 Cum & 400 Cum RCC Over Head Reservoir (Intze type with Pile Foundation) & Accommodate FHTC (4,797 Nos.) including Two years O&M under JJM with allied work for Teghari & Thaur & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials within Midnapur Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000224/2023-2024 | 2924/MD | 16/08/2023 | 927 | M/S. A.R. ENTERPRISE. | 1490.96 | 0 | 49
1632 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000023/2023-2024 | 1167/MD | 26/04/2023 | 0 | Resource Division | 6.66 | 0 | 0
1633 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000065/2024-2025 | 3385/MD | 25/11/2024 | 0 | Resource Division | 12.62 | 0 | 0
1634 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Bagdoba PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000463/2024-2025 | 378/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 9.39 | 0 | 0
1635 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
1636 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000052/2023-2024 | 1191/MD | 26/04/2023 | 0 | Resource Division | 20.91 | 0 | 0
1637 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (1844 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Manibpur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000129/2023-2024 | 2538/MD | 19/07/2023 | 1031 | SUJATA CONSTRUCTION | 435.01 | 0 | 25
1638 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000117/2022-2023 | 1461/MD | 08/05/2023 | 0 | Resource Division | 62.18 | 0 | 0
1639 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000148/2023-2024 | 1267/MD | 28/04/2023 | 0 | Resource Division | 61.53 | 0 | 0
1640 | Midnapore Division | Kharagpur Sub-Division | QUOTATION MONEY FOR KHEMASOLI WATER SUPPLY SCHEME, ZONE-I, T W NO I, [ KEMASOLI], JJM WORKS, SCHEME CODE SM/15590, APPLICATION NO 2004825735, REFERENCE ID 204360220, NIMPURA CCC, WBSEDCL | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00388/2024-2025 | BP-2024-25-294 | 27/08/2024 | 0 | WBSEDCL | 3.1 | 0 | 0
1641 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (281 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000002/2024-2025 | 1797/MD | 07/06/2024 | 301 | A K SIKDAR | 60.48 | 0 | 57
1642 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (261 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000024/2023-2024 | 946/MD | 05/04/2023 | 1000 | GOUTAM PARIA | 55.7 | 0 | 95
1643 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well, Laying distribution pipe line with Rising main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20.00 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (121 Nos.) & Two years O & M under JJM with allied work for Khemasoli & its adjoining mouzas W/S Scheme (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000855/2023-2024 | 832/MD | 15/03/2024 | 60 | RITESH AGARWALL | 41.32 | 0 | 0
1644 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000080/2024-2025 | 3431/MD | 25/11/2024 | 0 | Resource Division | 4.18 | 0 | 0
1645 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube well, Laying distribution pipeline & Construction of Pump House for Rejuvenation of Ground Water Based PWSS for Bhemwa (Part) under JJM of Sabang block in Paschim Medinipur District under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000083/2023-2024 | 2430/MD | 13/07/2023 | 597 | SANKAR PRASAD MAITY | 94.81 | 0 | 85
1646 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Bhemwa PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000427/2021-2022 | 1659/MD | 27/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.31 | 0 | 0
1647 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 200 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (1847 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Chakkeshi & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000127/2023-2024 | 2525/MD | 18/07/2023 | 983 | SUJATA CONSTRUCTION | 482.35 | 0 | 75
1648 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000083/2024-2025 | 3434/MD | 25/11/2024 | 0 | Resource Division | 11.38 | 0 | 0
1649 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000090/2022-2023 | 198/MD | 16/01/2023 | 0 | Resource Division | 26.69 | 0 | 0
1650 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000078/2023-2024 | 1227/MD | 27/04/2023 | 0 | Resource Division | 38.62 | 0 | 0
1651 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Shyamsundarpur Water Supply Scheme within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000001/2023-2024 | 953/MD | 06/04/2023 | 825 | CREATION CONSTRUCTION | 222.15 | 0 | 90
1652 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000079/2022-2023 | 200/MD | 16/01/2023 | 0 | Resource Division | 1.26 | 0 | 0
1653 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 450 cum OHR each (Intze type with pile foundation) & Accommodate FHTC (6283 Nos.) under JJM with allied work for Purshuri & Ramkrishnapur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000075/2023-2024 | 2422/MD | 13/07/2023 | 808 | GOBINDA MAITY | 1504.9 | 0 | 60
1654 | Midnapore Division | Ghatal Subdivision | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000380/2024-2025 | 55/MD | 07/01/2025 | 266 | GOBINDA MAITY | 79.62 | 0 | 60
1655 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000008/2024-2025 | 3329/MD | 25/11/2024 | 0 | Resource Division | 21.66 | 0 | 0
1656 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000070/2022-2023 | 78/MD | 09/01/2023 | 0 | Resource Division | 32.78 | 0 | 0
1657 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,583 Nos.) under JJM with allied work for Manikkunda PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000259/2023-2024 | 3233/MD | 11/09/2023 | 898 | M/S. A.R. ENTERPRISE. | 959.94 | 0 | 0
1658 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000065/2022-2023 | 73/MD | 09/01/2023 | 0 | Resource Division | 56.53 | 0 | 0
1659 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000188/2023-2024 | 1507/MD | 12/05/2023 | 0 | Resource Division | 15.91 | 0 | 0
1660 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with laying distribution system , Sinking of Tube Well , Pump House, Boundary Wall, laying of Rising Main & Providing Functional Household Tap Connection (4740 Nos) including 2 years Operation & Maintenance For Dingal, Duan and Gobindapur Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000211/2023-2024 | 2826/MD | 07/08/2023 | 785 | GOBINDA MAITY | 1375.06 | 0 | 74
1661 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000231/2023-2024 | 1519/MD | 12/05/2023 | 0 | Resource Division | 24.68 | 0 | 0
1662 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying of Rising Main, Laying distribution pipe line, Pump House, 350 cum OHR (Intze type with solid raft) & Accommodate FHTC (2,170 Nos.) including 2 years operation & maintenance under JJM with allied work for Khaskendu Bagicha & its adjoining mouzas W/S scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000388/2023-2024 | 5062/MD | 26/10/2023 | 180 | CIVCON CONSTRUCTION PVT. LTD. | 548.71 | 0 | 0
1663 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division(Debra),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000249/2023-2024 | 1580/MD | 15/05/2023 | 0 | Resource Division | 25.74 | 0 | 0
1664 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Different Capacity OHR (Intze type with solid raft/ Pile Foundation) & Accommodate FHTC (11,004 Nos.) including Two years O&M under JJM with allied work for Borai, Dhuipara, Nilda Zone-I & II ,Samsara Zone-I & II & Sautia Zone-I & II within Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000396/2023-2024 | 5070/MD | 26/10/2023 | 794 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 3699.83 | 0 | 55
1665 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000207/2023-2024 | 1459 | 08/05/2023 | 0 | Resource Division | 7.86 | 0 | 0
1666 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000260/2023-2024 | 2009/MD | 16/05/2023 | 0 | Resource Division | 24.11 | 0 | 0
1667 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000157/2022-2023 | 1155/MD | 25/04/2023 | 0 | Resource Division | 18.05 | 0 | 0
1668 | Midnapore Division | Ghatal Subdivision | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 190 mtr. depth deep tube well by direct rotary method for Head work site & 2nd tube well site of Krishnapur PWSS within Chandrakona-II block under Midnapore Division, P.H.E Dte. [PART-I] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000076/2023-2024 | 2423/MD | 13/07/2023 | 21 | SAJAL JANA | 22.7 | 0 | 50
1669 | Midnapore Division | Ghatal Subdivision | Laying distribution system & Accommodate FHTC (300 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000086/2023-2024 | 2433/MD | 13/07/2023 | 60 | DEV KUMAR ADAK | 44.86 | 0 | 0
1670 | Midnapore Division | Ghatal Subdivision | Laying distribution system & Accommodate FHTC (200 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000087/2023-2024 | 2434/MD | 13/07/2023 | 60 | M/S JITEN BANARJEE | 37.78 | 0 | 0
1671 | Midnapore Division | Ghatal Subdivision | Laying distribution system & Accommodate FHTC (200 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000088/2023-2024 | 2435/MD | 13/07/2023 | 45 | SUBHASIS DOLAI | 28.79 | 0 | 0
1672 | Midnapore Division | Ghatal Subdivision | Laying distribution system with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-G] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000133/2023-2024 | 2592/MD | 21/07/2023 | 30 | LOWADA HI-TECHTONIC ENGINEER,S CO. OP. SOCIETY LTD. | 18.92 | 0 | 0
1673 | Midnapore Division | Ghatal Subdivision | Laying distribution system & Accommodate FHTC (500 Nos.) with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000135/2023-2024 | 2594/MD | 21/07/2023 | 60 | R. CONSTRUCTION | 92.24 | 0 | 40
1674 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Rising main & Accommodate FHTC (500 Nos.) including 2 years operation & maintenance with allied work under JJM for Krishnapur PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000195/2023-2024 | 2809/MD | 07/08/2023 | 812 | M/S. D.K.H.CONSTRUCTION | 149.24 | 0 | 35
1675 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | RTOR000012/2024-2025 | 3333/MD | 25/11/2024 | 0 | Resource Division | 21.7 | 0 | 0
1676 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | RTOR000030/2022-2023 | 77/MD | 09/01/2023 | 0 | Resource Division | 38.5 | 0 | 0
1677 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 46
1678 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000210/2023-2024 | 1462 | 08/05/2023 | 0 | Resource Division | 13.6 | 0 | 0
1679 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000262/2023-2024 | 2011/MD | 16/05/2023 | 0 | Resource Division | 37.87 | 0 | 0
1680 | Midnapore Division | Ghatal Subdivision | Sinking of Tube wells, Construction of 450 CuM Capacity R.C.C Over Head Reservoirs (Over Pile Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (6507) for Bagchhari & Mangrul Pipe W/S Scheme including Two years O&M within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000209/2023-2024 | 2825/MD | 07/08/2023 | 783 | GOBINDA MAITY | 1766.48 | 0 | 70
1681 | Midnapore Division | Ghatal Subdivision | Laying of rising main & additional distribution pipe line due to re-design of mouzas Pipe W/S Schemes [Mangrul / Ramkrishnapur / Bagchhari / Purshuri] at Chandrakona-I block under Ghatal Sub-Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000380/2024-2025 | 55/MD | 07/01/2025 | 266 | GOBINDA MAITY | 79.62 | 0 | 60
1682 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000285/2023-2024 | 4056/MD | 12/10/2023 | 0 | Resource Division | 46.13 | 0 | 0
1683 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube well, Laying distribution pipe line, Pump House, Soil investigation, Construction of 200 cum OHR & Accommodate FHTC (125 Nos.) under JJM with allied work for Augmentation of Sonakania Pipe W/S Scheme in Dantan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000172/2024-2025 | 3143/MD | 04/10/2024 | 360 | SAI TUBE CO. | 156.46 | 0 | 18
1684 | Midnapore Division | Midnapur Mechanical Sub Division-I | Repairing of 2nd Pump House & Boundary wall for Sonakania PWSS within Dantan-I block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000499/2024-2025 | 569/AE/HQ/MD | 28/02/2025 | 45 | PROVAT KUMAR DE | 1.86 | 0 | 100
1685 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000141/2022-2023 | 421/MD | 08/02/2023 | 0 | Resource Division | 3.52 | 0 | 0
1686 | Midnapore Division | Ghatal Subdivision | Sinking of 150 X 100 mm dia. X 165 mtr. depth deep boosting tube well by direct rotary method for Deulbere PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000121/2023-2024 | 2521/MD | 18/07/2023 | 10 | ANNAPURNA TUBEWELL WORKS | 6.18 | 0 | 100
1687 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Accommodate FHTC (135 Nos.) under JJM with allied work including 1 year O & M for Deulbere PWSS in Chandrakona-II block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000172/2023-2024 | 2674/MD | 26/07/2023 | 45 | SUBHASIS DOLAI | 27.2 | 0 | 90
1688 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000182/2023-2024 | 1360/MD | 02/05/2023 | 0 | Resource Division | 0.83 | 0 | 0
1689 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Gopalnagar & its adjoining Mouzas PWSS instead of Dadpur & its adjoining Mouzas PWSS] | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000109/2022-2023 | 1065/MD | 02/06/2022 | 20 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.24 | 0 | 100
1690 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 500 & 600 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,406 nos.) under JJM with allied work for Gopalnagar & Kalara PWSS in Daspur-I Block including supply of all labour & materials including Two (02) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000229/2023-2024 | 2953/MD | 17/08/2023 | 772 | GOBINDA MAITY | 1693.15 | 0 | 20
1691 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Gopalnagar & its adjoining Mouzas PWSS instead Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000747/2022-2023 | 1266/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.16 | 0 | 100
1692 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000014/2024-2025 | 3335/MD | 25/11/2024 | 0 | Resource Division | 15.82 | 0 | 0
1693 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000057/2022-2023 | 63/MD | 09/01/2023 | 0 | Resource Division | 104.79 | 0 | 0
1694 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Mangrajpur, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000256/2023-2024 | 3165/MD | 31/08/2023 | 547 | SANKAR PRASAD MAITY | 29.51 | 0 | 100
1695 | Midnapore Division | Kharagpur Sub-Division | Laying of Distribution pipe line (extension) for Barisha (Zone-1) PWSS under Pingla Block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000387/2024-2025 | 59/MD | 07/01/2025 | 375 | KRISHNENDU SEKHAR DAS | 48.99 | 0 | 10
1696 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall for Augmentation of Barisha (Zone-I) PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000558/2023-2024 | 5512/MD | 15/12/2023 | 726 | KRISHNENDU SEKHAR DAS | 221.3 | 0 | 35
1697 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of 250 Cum OHR including Soil Investigation, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Barisha (Zone-II) PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000559/2023-2024 | 5513/MD | 15/12/2023 | 180 | NIRMAL UDYOG | 366.33 | 0 | 5
1698 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000024/2023-2024 | 1166/MD | 26/04/2023 | 0 | Resource Division | 14.14 | 0 | 0
1699 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (3,567 nos.) under JJM with allied work including 02 (Tow) Years Operation & Maintenance for Melerchak PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000274/2023-2024 | 3275/MD | 13/09/2023 | 720 | TAPAS SANTRA | 973.12 | 0 | 73
1700 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000087/2024-2025 | 3439/MD | 25/11/2024 | 0 | Resource Division | 21.97 | 0 | 0
1701 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000102/2022-2023 | 179/MD | 16/01/2023 | 0 | Resource Division | 16.2 | 0 | 0
1702 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000120/2023-2024 | 1312/MD | 28/04/2023 | 0 | Resource Division | 25.9 | 0 | 0
1703 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Bhabanipur W/S Scheme within Chandrakona-I Dev. Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Ghatal Sub-division |  | BILL/00624/2023-2024 | BP-2023-24-246 | 23/08/2023 | 0 | SAMIT PAL | 5.25 | 0 | 0
1704 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate balance FHTC under JJM in RAJNAGAR (PASCHIM) PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division |  | ORD/000441/2020-2021 | 311/MD | 22/02/2021 | 30 | ASHOK BANERJEE | 11.93 | 0 | 0
1705 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM of Bhabanipur W/S Scheme within Chandrakona-I Dev. Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Ghatal Sub-division |  | ORD/000479/2022-2023 | 2169/MD | 21/10/2022 | 30 | SAMIT PAL | 17.77 | 0 | 100
1706 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at Manikkundu in Bhabanipur PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000495/2020-2021 | 370/MD | 25/02/2021 | 15 | SAMIT PAL | 12.53 | 11.23 | 0
1707 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Pratappur PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000497/2020-2021 | 371/MD | 25/02/2021 | 15 | DIPAK KUMAR DOLAI | 18.46 | 15.43 | 0
1708 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at Madhya Para in Pratappur PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000498/2020-2021 | 372/MD | 25/02/2021 | 15 | SUBHASIS DOLAI | 9.63 | 7.98 | 0
1709 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Birsingha PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000526/2020-2021 | 410/MD | 26/02/2021 | 15 | SAMIT PAL | 6.95 | 6.7 | 0
1710 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Bhabanipur PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000527/2020-2021 | 411/MD | 26/02/2021 | 15 | JIT ENTERPRISE | 15.04 | 13.63 | 0
1711 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Srinagar PWSS within Chandrakona-I Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000528/2020-2021 | 412/MD | 26/02/2021 | 15 | M/S JITEN BANARJEE | 11.44 | 0 | 0
1712 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division, PHE Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000529/2020-2021 | 413/MD | 26/02/2021 | 15 | DEV KUMAR ADAK | 11.41 | 0 | 0
1713 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate balance FHTC under JJM in HAREKRISHNAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division |  | ORD/000655/2020-2021 | 450/MD | 26/02/2021 | 30 | SUBHASIS DOLAI | 13.85 | 0 | 0
1714 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Daulatchak PWSS within Ghatal Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000714/2020-2021 | 97/AE/GSD | 25/02/2021 | 7 | DEV KUMAR ADAK | 4.84 | 0 | 0
1715 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at Dolai Para in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000717/2020-2021 | 99/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.72 | 4.26 | 0
1716 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at Nandanpur-II in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division |  | ORD/000719/2020-2021 | 100/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.76 | 4.24 | 0
1717 | Midnapore Division | Ghatal Subdivision | Electrical maintenance instrument for the O/F of the EE/MD, PHE Dte. | AE Ghatal Sub-division |  | VCH/000580/2021-2022 | BP-2021-22-86 | 16/07/2021 | 0 | PULLOCK KUMAR GHOSH | 0.14 | 0 | 0
1718 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline & Accommodate FHTC (260 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000026/2024-2025 | 2079/MD | 04/07/2024 | 242 | A R CONSTRUCTION | 84.14 | 0 | 68
1719 | Midnapore Division | Kharagpur Sub-Division | Construction of 400 CuM OHR, Pump House & Boundary wall under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000105/2025-2026 | 1237/MD | 28/05/2025 | 180 | M/S P.B. ENTERPRISE | 141.67 | 0 | 0
1720 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) Nos. Tube well for Tangasol & its adjoining mouzas (Zone-I) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000201/2023-2024 | 2815/MD | 07/08/2023 | 30 | ANNAPURNA TUBEWELL WORKS | 19.43 | 0 | 100
1721 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) Nos. Tube well for Tangasol & its adjoining mouzas (Zone-II i.e. II/I & II/II) PWSS in Kharagpur-I block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000202/2023-2024 | 2816/MD | 07/08/2023 | 30 | MANNA COMPUTER | 11.83 | 0 | 100
1722 | Midnapore Division | Kharagpur Sub-Division | Laying Rising main pipeline & Accommodate FHTC (100 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000402/2023-2024 | 5104/MD | 31/10/2023 | 30 | CHANDAN DAS | 15.96 | 0 | 68
1723 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline, Switch Room, Land development & Accommodate FHTC (75 Nos.) under JJM with allied work for Tangasol (Zone-II) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000419/2023-2024 | 5155/MD | 07/11/2023 | 440 | RITESH AGARWALL | 25.25 | 0 | 62
1724 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline & Accommodate FHTC (346 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VII] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000420/2023-2024 | 5156/MD | 07/11/2023 | 798 | GOUTAM PARIA | 53.34 | 0 | 80
1725 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline & Accommodate FHTC (300 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VIII] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000421/2023-2024 | 5157/MD | 07/11/2023 | 60 | R. CONSTRUCTION | 71.32 | 0 | 55
1726 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline & Accommodate FHTC (300 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000464/2023-2024 | 5358/MD | 30/11/2023 | 45 | S.N.A. CONSTRUCTION | 63.8 | 0 | 72
1727 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline & Accommodate FHTC (260 Nos.) including 2 yrs. O&M under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000524/2023-2024 | 5501/MD | 14/12/2023 | 514 | EVEREST CONSULTANT SERVICES | 143.94 | 0 | 30
1728 | Midnapore Division | Kharagpur Sub-Division | Laying Distribution pipeline & Accommodate FHTC (330 Nos.) under JJM with allied work for Tangasol (Zone-I) & its adjoining mouzas W/S Scheme in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000525/2023-2024 | 5502/MD | 14/12/2023 | 482 | SK. SANAMAJ | 85.43 | 0 | 65
1729 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000175/2023-2024 | 1367/MD | 02/05/2023 | 0 | Resource Division | 69.43 | 0 | 0
1730 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (3,186 Nos.) under JJM with allied work including 02 (Two) years Operation & Maintenance for Rautmani & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the distrist of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000240/2023-2024 | 3049/MD | 23/08/2023 | 927 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 876.48 | 0 | 15
1731 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | RTOR000118/2022-2023 | 1506/MD | 12/05/2023 | 0 | Resource Division | 39.69 | 0 | 0
1732 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (3,476 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Radhakishor & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000348/2023-2024 | 4000/MD | 06/10/2023 | 904 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 1051.83 | 0 | 70
1733 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | RTOR000085/2024-2025 | 3437/MD | 25/11/2024 | 0 | Resource Division | 21.41 | 0 | 0
1734 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | RTOR000104/2022-2023 | 207/MD | 16/01/2023 | 0 | Resource Division | 76.02 | 0 | 0
1735 | Midnapore Division | Kharagpur Sub-Division | Supplying, laying of 9 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 9 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination &Sanitary Arrangement, Boundary Wall, Service Road for 50 M length, Improvement of Land for each site, Renovation of 4 nos. Existing OHRs. surface Drain, Campus lighting & other provisional works etc for Pingla Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation& Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000837/2023-2024 | 801/MD | 15/03/2024 | 915 | G B CONSTRUCTION & UMWELT JV | 7243.56 | 0 | 10
1736 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | RTOR000002/2024-2025 | 2240/MD | 22/07/2024 | 0 | Resource Division | 237.7 | 0 | 0
1737 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Palashpai & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000117/2022-2023 | 689/MD | 13/04/2022 | 20 | GOBINDA MAITY | 12.29 | 0 | 100
1738 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Rising Main Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Zone- I & II) ( Intze type with pile foundation) & Accommodate FHTC (4,261 Nos.) including Two years O&M under JJM with allied work for Palashpai (Zone- I & Zone-II) & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000260/2023-2024 | 3234/MD | 11/09/2023 | 180 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 938.92 | 0 | 0
1739 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000244/2023-2024 | 1521/MD | 12/05/2023 | 0 | Resource Division | 74.13 | 0 | 0
1740 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accomdate 80(Eighty) nos FHTC under JJM at different places for Barisha (Zone -I) and its adjoining Mouzas Water Supply Scheme Within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000001/2022-2023 | 213/AE/KSD | 29/04/2022 | 15 | SK. TASLIM | 4.82 | 0 | 0
1741 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate balance FHTC under JJM at different places for Barisha (Zone-I) & its adj. mouzas W/S Scheme within Pingla block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000020/2022-2023 | 617/MD | 04/04/2022 | 1003 | NUTAN BAZAR ENGINEER,S CO-OPERATIVE SOCIETY LTD. | 39.19 | 0 | 100
1742 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Barisha (Zone-I) W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000273/2020-2021 | 1471/MD | 26/11/2020 | 180 | SK. SALIM | 96.82 | 34.85 | 0
1743 | Midnapore Division | Kharagpur Sub-Division | Laying of UPVC (Class-III) pipe line supportive to retrofitting to accommodate FHTC including supplying, laying, fitting, fixing of 15mm dia. NB PVC (Sch-80)/20mm dia. HDPE (PE-100, PN-16) Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials under JJM at Barisha (Zone-I) and its adjoining mouza Water Supply Scheme within Pingla Dev. Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000482/2022-2023 | 2278/MD | 09/11/2022 | 21 | AJIJUR RAHAMAN MALLICK | 10.96 | 0 | 0
1744 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | RTOR000106/2024-2025 | 3407/MD | 25/11/2024 | 0 | Resource Division | 12.53 | 0 | 0
1745 | Midnapore Division | Kharagpur Sub-Division | FHTC DATA ENTRY | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/000763/2021-2022 | 8443208 | 27/09/2021 | 0 | PAPPU SHAW | 0.2 | 0 | 0
1746 | Midnapore Division | Kharagpur Sub-Division | FHTC DATA ENTRY | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/000764/2021-2022 | 8443208 | 27/09/2021 | 0 | SUBRATA CHAKRABORTY | 0.12 | 0 | 0
1747 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001205/2021-2022 | 844337 | 08/12/2021 | 0 | GANESH CH NANDY | 0.11 | 0 | 0
1748 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001206/2021-2022 | 844337 | 08/12/2021 | 0 | PAPPU SHAW | 0.12 | 0 | 0
1749 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001207/2021-2022 | 844337 | 08/12/2021 | 0 | SUBRATA CHAKRABORTY | 0.07 | 0 | 0
1750 | Midnapore Division | Kharagpur Sub-Division | FHTC Data Entry. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001278/2021-2022 | 844360 | 18/01/2022 | 0 | PAPPU SHAW | 0.17 | 0 | 0
1751 | Midnapore Division | Kharagpur Sub-Division | FHTC Data Entry. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | VCH/001279/2021-2022 | 844360 | 18/01/2022 | 0 | SIDDHESWAR BAG | 0.21 | 0 | 0
1752 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Debhog W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000265/2020-2021 | 1461/MD | 26/11/2020 | 180 | MIDNAPUR PIPE CONCERN | 67.06 | 58.97 | 100
1753 | Midnapore Division | Kharagpur Sub-Division | Continuation Work Order for the work of Retrofitting to accommodate additional FHTC under JJM in Debhog W/S Scheme, Block :- Sabang, District :- Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000515/2022-2023 | 2533/MD | 12/12/2022 | 14 | MIDNAPUR PIPE CONCERN | 13.69 | 0 | 50
1754 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Debhog W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000722/2020-2021 |  | 15/12/2020 | 0 | MIDNAPUR PIPE CONCERN | 30 | 0 | 0
1755 | Midnapore Division | Kharagpur Sub-Division | FHTC DATA ENTRY | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000765/2021-2022 | 8443211 | 27/09/2021 | 0 | SHRABONTI BERA | 0.2 | 0 | 0
1756 | Midnapore Division | Kharagpur Sub-Division | FHTC DATA ENTRY | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000766/2021-2022 | 8443211 | 27/09/2021 | 0 | TANMOY BERA | 0.17 | 0 | 0
1757 | Midnapore Division | Kharagpur Sub-Division | For FHTC Data Entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000853/2021-2022 | 844375 | 10/09/2021 | 0 | SHRABONTI BERA | 0.17 | 0 | 0
1758 | Midnapore Division | Kharagpur Sub-Division | For FHTC Data Entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000854/2021-2022 | 844375 | 08/09/2021 | 0 | SUBHAJIT GANGULY | 0.01 | 0 | 0
1759 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001212/2021-2022 | 844336 | 08/12/2021 | 0 | RINTU SAMANTA | 0.07 | 0 | 0
1760 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001213/2021-2022 | 844336 | 08/12/2021 | 0 | SANDIP MANNA | 0.06 | 0 | 0
1761 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001214/2021-2022 | 844336 | 08/12/2021 | 0 | PRATHA PRATIM PAL | 0.07 | 0 | 0
1762 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001215/2021-2022 | 844336 | 03/12/2021 | 0 | NABOGOPAL ADHIKARI | 0.06 | 0 | 0
1763 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001282/2021-2022 | 844362 | 18/01/2022 | 0 | MANABENDAN DAS | 0.2 | 0 | 0
1764 | Midnapore Division | Kharagpur Sub-Division | FHTC data entry. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001283/2021-2022 | 844362 | 18/01/2022 | 0 | SHRABONTI BERA | 0.2 | 0 | 0
1765 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bural (Zone-I) W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000268/2020-2021 | 1465/MD | 26/11/2020 | 1887 | BANERJEE CONSTRUCTION | 96.92 | 24.87 | 80
1766 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Rajnagar (Paschim) W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000245/2020-2021 | 1444/MD | 26/11/2020 | 180 | BANERJEE CONSTRUCTION | 96.09 | 21.36 | 0
1767 | Midnapore Division | Ghatal Subdivision | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000278/2021-2022 | 8443118 | 31/05/2021 | 0 | ANIRBAN CHAKRABORTY | 0.05 | 0 | 0
1768 | Midnapore Division | Ghatal Subdivision | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000279/2021-2022 | 8443118 | 31/05/2021 | 0 | TANMOY BERA | 0.11 | 0 | 0
1769 | Midnapore Division | Ghatal Subdivision | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000280/2021-2022 | 8443118 | 28/05/2021 | 0 | SHRABONTI BERA | 0.17 | 0 | 0
1770 | Midnapore Division | Ghatal Subdivision | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000281/2021-2022 | 8443118 | 31/05/2021 | 0 | SOVANDEB MANNA | 0.05 | 0 | 0
1771 | Midnapore Division | Ghatal Subdivision | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000282/2021-2022 | 8443118 | 31/05/2021 | 0 | ARUP KR ADAK | 0 | 0 | 0
1772 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Rajnagar W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000747/2020-2021 |  | 15/12/2020 | 0 | BANERJEE CONSTRUCTION | 30 | 0 | 0
1773 | Midnapore Division | Ghatal Subdivision | FHTC DATA ENTRY | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000767/2021-2022 | 8443210 | 27/09/2021 | 0 | NABOGOPAL ADHIKARI | 0.1 | 0 | 0
1774 | Midnapore Division | Ghatal Subdivision | FHTC DATA ENTRY | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000768/2021-2022 | 8443210 | 27/09/2021 | 0 | PARTHA PRATIM PAL | 0.11 | 0 | 0
1775 | Midnapore Division | Ghatal Subdivision | FHTC DATA ENTRY | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000769/2021-2022 | 8443210 | 27/09/2021 | 0 | SANDIP MANNA | 0.1 | 0 | 0
1776 | Midnapore Division | Jhargram Sub-Division | Extension of Distribution pipe line and FHTC work for Augmentation of Ground based Tamajuri PWSS to Accommodate FHTC in Binpur-II Block within Jhargram District under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | ORD/000625/2021-2022 | 178/MD | 01/02/2022 | 1259 | WATER LINK | 48.15 | 0 | 50
1777 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | RTOR000019/2021-2022 | 2161/MD | 17/12/2021 | 0 | Resource Division | 1.44 | 0 | 0
1778 | Midnapore Division | Jhargram Sub-Division | Purchasing of materials for the Retrofitting to Accommodate FHTC incl. Augmentation of Source under UM in Ground water based Rantua Water Supply Scheme at Gopiballavpur-1I Block within Jhargram District under Jhargram Division. PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | VCH/000464/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0
1779 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Tamajuri PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | VCH/001373/2021-2022 | BP-2021-22-408 | 23/02/2022 | 0 | LEMNISCATE | 2.28 | 0 | 0
1780 | Midnapore Division | Jhargram Sub-Division | Purchasing of Materials. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | VCH/001685/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.05 | 0 | 0
1781 | Midnapore Division | Jhargram Sub-Division | Sinking of 200 mm dia. X 165 mm dia. X 200 M depth Rig Bored Tubwell (Replacement) by DTH Method for Augmentation of Source of Tamajuri PWSS under Jhargram Division P.H.E. Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | VCH/001731/2021-2022 | BP-2021-22-471 | 16/03/2022 | 0 | BIDYUT KUMAR SANTRA | 3.62 | 0 | 0
1782 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000017/2022-2023 | 2395/MD | 24/11/2022 | 0 | Resource Division | 36.34 | 0 | 0
1783 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | RTOR000045/2021-2022 | 498/MD | 15/03/2022 | 0 | Resource Division | 15.18 | 0 | 0
1784 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Belaberia PWSS in Gopi-IIBlock for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. | Assistant Engineer, Jhargram Sub-Division,DIC(D)_MMSD(D) | JE (M),Junior Engineer-III | VCH/001718/2021-2022 | BP-2021-22-458 | 11/03/2022 | 0 | LEMNISCATE | 3.01 | 0 | 0
1785 | Midnapore Division | Jhargram Sub-Division | Extension of distribution pipe line and FHTC work for Augmentation of Ground Based Khamar PWSS to accommodate FHTC in Binpur-II block within Jhargram district under Jhargram Division, PHE Dte. |  | Junior Engineer-II | ORD/000015/2022-2023 | 612/MD | 04/04/2022 | 21 | M/S. SANKAR KUMAR NAG | 10.11 | 0 | 0
1786 | Midnapore Division | Jhargram Sub-Division | Preparation of D.P.R (Consultancy Work) in connection with the Functional House Hold Tap Connection (FHTC) of Khamar PWSS in Binpur-II Block for Augmentation / Rejuvenation / Retrofitting etc. under Jhargram Division, P.H.E. Dte. |  | Junior Engineer-II | VCH/001379/2021-2022 | BP-2021-22-406 | 23/02/2022 | 0 | M/S R. DUTTA & CO | 1.34 | 0 | 0
1787 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of Rising main & interconnection pipeline for Augmentation of Goaltore & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length - 950.00 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000053/2024-2025 | 2448/MD | 08/08/2024 | 45 | ARNAB PATRA | 7.64 | 0 | 50
1788 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & its adjoining mouzas within Midnapore Division, PHE Dte. (Phase-F) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000080/2022-2023 | 1069/MD | 03/06/2022 | 21 | MAITY ENTERPRISE | 22.04 | 0 | 0
1789 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & its adjoining mouzas within Midnapore Division, PHE Dte. (Phase-G) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000081/2022-2023 | 1070/MD | 03/06/2022 | 1120 | MAITY ENTERPRISE | 72.11 | 0 | 20
1790 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Goaltore, Block - Garhbeta-II) to be Retrofitting under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000115/2021-2022 | 994/MD | 23/06/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.8 | 0 | 0
1791 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-A) (SL No-01) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000605/2022-2023 | 794/AE/MSSD | 10/01/2023 | 15 | A R ENTERPRISE | 4.66 | 0 | 0
1792 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-B) (SL No-02) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000606/2022-2023 | 797/AE/MSSD | 10/01/2023 | 15 | ARNAB PATRA | 4.67 | 0 | 0
1793 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-C) (SL No-03) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000607/2022-2023 | 798/AE/MSSD | 10/01/2023 | 15 | CHANDAN YADAV | 4.67 | 0 | 0
1794 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-D) (SL No-04) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000608/2022-2023 | 799/AE/MSSD | 10/01/2023 | 15 | RUPKUMAR KARMAKAR | 4.67 | 0 | 0
1795 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at different places for Goaltore PWSS & Its adjoining mouzas within Midnapore Division ,PHE Dte.(PHASE-E) (SL No-05) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000609/2022-2023 | 804/AE/MSSD | 11/01/2023 | 15 | JIT ENTERPRISE | 4.62 | 0 | 100
1796 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of R.C.C. Over Head Reservoir (Raft Foundation) of capacity 600 CuM and staging height 20.00 mtr. as per approved drawing (PC-I/OHR/13/2012) with allied works under Goaltore Augmentation W/S Scheme within Garhbeta-II Block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | VCH/001794/2021-2022 | BP-2021-22-544 | 29/03/2022 | 0 | ASHIM KUMAR DEY | 20 | 0 | 0
1797 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for mouza (i) Nankarnila, (ii) Dontarda & (iii) Talda of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000451/2021-2022 | 1278/MD | 05/08/2021 | 10 | GOBINDA MAITY | 4.46 | 0 | 0
1798 | Midnapore Division | Kharagpur Sub-Division | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Nankarnila, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000487/2021-2022 | 2180/MD | 17/12/2021 | 150 | MIDNAPUR PIPE CONCERN | 29.46 | 0 | 90
1799 | Midnapore Division | Kharagpur Sub-Division | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001817/2021-2022 | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.87 | 0 | 0
1800 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of ?Retrofitting to accommodate FHTC under JJM for Basantapur PWSS, Block- Daspur-I in the district of Paschim Medinipur.? | AE Ghatal Sub-division |  | ORD/000169/2022-2023 | 1241/MD | 20/06/2022 | 21 | MASUM ALI KHAN | 30.95 | 0 | 0
1801 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Basantapur PWSS, Block ¿ Daspur-I in the district of Paschim Medinipur. | AE Ghatal Sub-division |  | ORD/000533/2020-2021 | 417/MD | 26/02/2021 | 40 | MASUM ALI KHAN | 95.51 | 53.11 | 0
1802 | Midnapore Division | Kharagpur Sub-Division | Accomdation of FHTC under JJM for the leftout Portion of Jamna Water Supply Scheme catchment area as per site reconnaissance, Block: - Pingla , within Midnapore Division, P.H.E. Dte. District: - Paschim Midnapore. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000007/2022-2023 | 217/AE/KSD | 29/04/2022 | 30 | GOBINDA MAITY | 4.57 | 0 | 100
1803 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Jamna PWSS, Block - Pingla in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000642/2020-2021 | 445/MD | 26/02/2021 | 1405 | GOBINDA MAITY | 41.65 | 25.06 | 100
1804 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | RTOR000100/2024-2025 | 3413/MD | 25/11/2024 | 0 | Resource Division | 5.17 | 0 | 0
1805 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Jamdoba & Godamauli, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000563/2020-2021 | 57/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.79 | 0 | 0
1806 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Jamdoba in Jamdoba PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-09) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000725/2020-2021 | 103/AE/MSSD | 24/02/2021 | 15 | A R ENTERPRISE | 1.96 | 0.45 | 0
1807 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of DPR in connection with the Functional House Hold connection of different existing PWSS to Retrofitting under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001118/2020-2021 | 8443496 | 30/03/2021 | 0 | SIRCON ENGINEERING SERVICES | 1.49 | 0 | 0
1808 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Mugbasan PWSS, Block - Keshpur in the district of Paschim Medinipur. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000070/2021-2022 | 1065/MD | 02/07/2021 | 30 | MIDNAPUR PIPE CONCERN | 68.71 | 37.42 | 0
1809 | Midnapore Division | Ghatal Subdivision | Laying pipe line to provide balance FHTC under JJM in DHARMA PWSS under Ghatal Sub-Division in the District of Paschim Medinipur | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000465/2023-2024 | 5359/MD | 30/11/2023 | 25 | SK REAJUL HOSSAIN | 6.49 | 0 | 100
1810 | Midnapore Division | Ghatal Subdivision | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Dharma PWSS to accommodate FHTC under JJM under Daspur-I block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000495/2021-2022 | 2188/MD | 17/12/2021 | 60 | M/S. D.K.H.CONSTRUCTION | 85.4 | 0 | 100
1811 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at Dolai Para in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000717/2020-2021 | 99/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.72 | 0 | 0
1812 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM at Nandanpur-II in Dharma PWSS within Daspur-I Block under Ghatal Sub-Division of Midnapore Division P.H.E.Dte. (Phase-I) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000719/2020-2021 | 100/AE/GSD | 25/02/2021 | 7 | PBA INFRASTRUCTURE | 4.76 | 0 | 0
1813 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Dharma, Block - Ghatal) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/001404/2021-2022 | BP-2021-22-380 | 17/02/2022 | 0 | SIRCON ENGINEERING SERVICES | 3.09 | 0 | 0
1814 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | VCH/001152/2020-2021 | 8443105 | 12/02/2021 | 0 | NABOGOPAL ADHIKARI | 0.16 | 0 | 0
1815 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | VCH/001153/2020-2021 | 8443105 | 12/02/2021 | 0 | KOUSHIK PAL | 0.15 | 0 | 0
1816 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | VCH/001154/2020-2021 | 8443105 | 09/02/2021 | 0 | RINTU SAMANTA | 0.19 | 0 | 0
1817 | Midnapore Division | Kharagpur Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | VCH/001155/2020-2021 | 8443105 | 12/02/2021 | 0 | MANABENDAN DAS | 0.19 | 0 | 0
1818 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Rig bored Tube well of 150 X 100 mm dia. X 200 Mtr. Depth for boosting perpose of Pirakata Water supply Scheme under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000339/2023-2024 | 700/AE/MSSD | 06/10/2023 | 15 | SANJIT SINHA | 7.01 | 0 | 100
1819 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Pirakata PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000481/2021-2022 | 2175/MD | 17/12/2021 | 45 | SANJIT SINHA | 52.54 | 0 | 0
1820 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Khandibundh & Pathra in Pirakata PWSS in Salboni Block District :-Paschim Medinipore within Midnapore Division PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000524/2021-2022 | 675/AE/MSSD | 24/12/2021 | 15 | DEBJIT PATRA | 4.48 | 0 | 0
1821 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Pirakata, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000564/2020-2021 | 58/MD | 08/01/2021 | 10 | SIRCON ENGINEERING SERVICES | 3.68 | 0 | 0
1822 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM at Mouza Khadibandh in Pirakata PWSS in Salboni Block in the District of Paschim Medinipore.(SL No-06) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001770/2021-2022 | BP-2021-22-516 | 25/03/2022 | 0 | DEBJIT PATRA | 1.02 | 0 | 0
1823 | Midnapore Division | Midnapur Sadar Sub-Division | Car Bill | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00314/2023-2024 | BP-2023-24-001 | 01/04/2023 | 0 | SUKUMAR SANTRA | 0.8 | 0 | 0
1824 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 125 mm X 80 mm.dia. & 138 Mtr. Depth, Tubewell Including installation of pumping machinery and accessories etc at Chandrakona Road Headwork site in the district of Pashcim Medinipur under Midnapore Division, P.H.E. Dte. (SL No-05) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000069/2022-2023 | 223/AE/MSSD | 13/05/2022 | 20 | CHANDAN YADAV | 3.03 | 0 | 90
1825 | Midnapore Division | Midnapur Sadar Sub-Division | Hiring of 01 (one) no, Motor Cab(standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 12 (twelve) months only having contract carriage permit for plying within west Bengal from Regional Transport Authority for the use of the Executive Engineer,Midnapore Division PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000357/2021-2022 | 474/AE/MSSD | 30/08/2021 | 365 | SUKUMAR SANTRA | 1.7 | 0 | 100
1826 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipeline, Providing FHTC, Soil test and Construction of RCC Over Head Reservoir of capacity 550 CuM (Intez type with solid raft) and staging height 20.00 mtr. with allied work including Sinking of Rig bored tube well for Augmentation of Chandrakona Road Rly. Station (Zone-I) Water Supply Scheme in Garhbeta-III block including supply of all labour & materials within Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000377/2022-2023 | 1960/MD | 20/09/2022 | 180 | BANERJEE CONSTRUCTION | 588.73 | 0 | 25
1827 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Hiring of 01 (one) no. Motor Cab (standard) commercial with catalytic converter attachment with Bharat Stage as perprevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 6 (six) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Executive Engineer, Midnapore Division, PHE Dte. w.e.f. 01.09.2022 to 28.02.2023. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000409/2022-2023 | 503/AE/MSSD | 29/08/2022 | 160 | SUKUMAR SANTRA | 0.9 | 0 | 100
1828 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Augmentation of Chandrakona Road Railway Station (Zone-I) PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000460/2024-2025 | 372/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 11.47 | 0 | 0
1829 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Rising main from Common manifold to OHR for Augmentation of Chandrakona Road ( Zone-II ) W/S scheme within Garhbeta-III Block under Midnapur Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000602/2022-2023 | 853/AE/MSSD | 03/02/2023 | 879 | GOBINDA MAITY | 3.33 | 0 | 70
1830 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work order for Hiring of 1 (one) no, Motor Cab (standard) Commercial with Catalytic Converter attachment with Bharat Stage as per prevalent applicable standard compliant new /not older than 30 (thirty) months from the date of 1st registration on daily hire rate basis for 06 (Six) months only having contract carriage permit for plying within West Bengal from Regional Transport Authority for the use of the Assistant Engineer, (HQ) under Midnapore Division PHE Dte. for the Period of 6 ( Six ) months. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000755/2022-2023 | 680/AE/MSSD | 30/11/2022 | 182 | PULLOCK KUMAR GHOSH | 1.01 | 0 | 0
1831 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Providing FHTC and Sinking of Rig Bored Tube well for Augmentation of Chandrakona Road Rly. Station (Zone-II) W/S Scheme in Garhbeta-III Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000908/2021-2022 | 526/MD | 21/03/2022 | 1361 | GOBINDA MAITY | 459.24 | 0 | 75
1832 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Chandrakona (Block-Garhbeta-III) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001030/2021-2022 | 1622/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.06 | 0 | 100
1833 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Chandrakona (Block-Garhbeta-III) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001031/2021-2022 | 1623/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.9 | 0 | 100
1834 | Midnapore Division | Midnapur Sadar Sub-Division | Repair and Rennovation of Switch Room cum Chlorine Room ( No. 2 ) of Chandrakona Road Water Supply Scheme ( Zone-II ) within Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. (SL No-03) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001036/2022-2023 | 984/AE/MSSD | 17/03/2023 | 15 | NAYAN CONSTRUCTION | 0.97 | 0 | 100
1835 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000006/2023-2024 | 1121/MD | 20/04/2023 | 0 | Resource Division | 111.82 | 0 | 0
1836 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000069/2024-2025 | 3387/MD | 25/11/2024 | 0 | Resource Division | 58.96 | 0 | 0
1837 | Midnapore Division | Midnapur Sadar Sub-Division | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 2,27,000 Ltr.) at Head work Site of Chandrakona Road Railway Station Water Supply Scheme (Zone-I) within Garhbeta-III Block under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001620/2021-2022 | BP-2021-22-424 | 02/03/2022 | 0 | BISWAJIT BAG | 4.72 | 0 | 0
1838 | Midnapore Division | Midnapur Sadar Sub-Division | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Block - Garhbeta-III) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001729/2021-2022 | BP-2021-22-468 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.28 | 0 | 0
1839 | Midnapore Division | Midnapur Sadar Sub-Division | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Block - Garhbeta-III) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001730/2021-2022 | BP-2021-22-469 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.21 | 0 | 0
1840 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001810/2021-2022 | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0
1841 | Midnapore Division | Ghatal Subdivision | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for 2nd. Tube Well site of Augmentation of Sonakhali water supply scheme within Ghatal Sub-Division under Midnapore Division, PHE Dte. (Considering G.L. 1950 mm below Road Level) {TYPE - B} | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000129/2024-2025 | 1495/AE/GSD | 24/09/2024 | 169 | SK REAJUL HOSSAIN | 3.64 | 0 | 100
1842 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line, Pump House, FHTC & Construction of R.C.C. Over Head Reservoir of capacity 600 Cum (including Pile) and staging height 20.00 mtr. with allied work for Augmentation of Sonakhali W/S Scheme in Daspur-II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000217/2022-2023 | 1688/MD | 16/08/2022 | 1320 | GOBINDA MAITY | 757.01 | 0 | 60
1843 | Midnapore Division | Ghatal Subdivision | Sinking of 3 (Three) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Sonakhali W/S Scheme with in Daspur-II Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000570/2022-2023 | 120/MD | 10/01/2023 | 21 | PRANTIK DRILLING AGENCY | 29.59 | 0 | 100
1844 | Midnapore Division | Ghatal Subdivision | Day to day operation & maintenance of distribution system & Rising main (CI/DI/HDPE/UPVC) with all related structure i.e. OHR etc. of Sonakhali W/S Scheme under Midnapore Division P.H.E. Dte. (Period from 01/11/2021 to 31/12/2021) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000575/2021-2022 | 743/A/AE/GSD | 26/10/2021 | 61 | SUBHASIS DOLAI | 0.88 | 0 | 100
1845 | Midnapore Division | Ghatal Subdivision | Preliminarily Ground Protection works (i,e, Construction R.C.C. Retaining wall, Land development) And Rising main in connection with Construction of Boundary wall, OHR, Switch Room etc. at Head Works site of Augmentation of Sonakhali W/S Scheme under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000627/2022-2023 | 452/MD | 13/02/2023 | 30 | GOBINDA MAITY | 25.92 | 0 | 25
1846 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Sonakhali (Block-Daspur-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001034/2021-2022 | 1642/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.78 | 0 | 0
1847 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Sonakhali (Block-Daspur-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001035/2021-2022 | 1643/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0 | 0
1848 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000013/2022-2023 | 133/MD | 11/01/2023 | 0 | Resource Division | 28.24 | 0 | 0
1849 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000148/2022-2023 | 531/MD | 21/02/2023 | 0 | Resource Division | 75.94 | 0 | 0
1850 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000167/2022-2023 | 901/MD | 31/03/2023 | 0 | Resource Division | 75.94 | 0 | 0
1851 | Midnapore Division | Ghatal Subdivision | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Sonakhali, Block - Daspur-II) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001395/2021-2022 | BP-2021-22-385 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.4 | 0 | 0
1852 | Midnapore Division | Ghatal Subdivision | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Sonakhali, Block ¿ Daspur-II) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001414/2021-2022 | BP-2021-22-386 | 23/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.87 | 0 | 0
1853 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Chandrakona Road Railway Station, Amlagora, Jot Ghanashyam & Sonakhali in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001814/2021-2022 | BP-2021-22-470 | 11/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.19 | 0 | 0
1854 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in Pathardahara PWSS (Phase-II) Block - Nayagram in the District of Jhargram |  |  | ORD/000035/2022-2023 | 201/JSD | 04/04/2022 | 21 | DHUMKETU ENGINEERING PRIVATE LIMITED | 4.05 | 0 | 0
1855 | Midnapore Division | Midnapur Sadar Sub-Division | Garbeta to Hoomgarh Road from chainage 0.00 Km- Restoration of damages due to laying of proposed underground pipeline by PHE in the district of Paschim Medinipur under Midnapore Division, P.W.D during the year 2022-23 | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00146/2023-2024 | BP-2023-24-82 | 11/05/2023 | 0 | EXECUTIVE ENGINEER, P.W.D | 5 | 0 | 0
1856 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Providing FHTC, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 500 Cum (Intze type with solid raft) and staging height 20.00 mtr. with allied work including Construction of 150 Cum capacity CWR for Augmentation of Garhbeta W/S Scheme in Garhbeta-I Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000044/2022-2023 | 837/MD | 02/05/2022 | 180 | BANERJEE CONSTRUCTION | 580.16 | 0 | 72
1857 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Kadra Nimnapalli, Pratiharpara, Mouza Kadra , J.L. No. 867, G.P - Kadra Uttarbil within Garhbeta-I Block under Midnapore Division PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000130/2023-2024 | 2585/MD | 21/07/2023 | 15 | M/S. ZAMAN ENTERPRISE | 5.91 | 0 | 100
1858 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Saradapara Manasatala, Mouza - Mohanpur, J.L. No. 838, G.P. - Kadra Uttarbil within Garhbeta-I Block under Midnapore Division PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000131/2023-2024 | 2586/MD | 21/07/2023 | 15 | MANNA COMPUTER | 5.91 | 0 | 100
1859 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 150 X 100 mm dia. X 150 Mtr. Depth Rig bored Tube well at Mouza Pochadohora, J.L No.618, G.P - Shyamnagar within Garhbeta -I Block under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000132/2023-2024 | 2587/MD | 21/07/2023 | 15 | RUPKUMAR KARMAKAR | 5.91 | 0 | 100
1860 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 125mm X 80mm dia. & 150 Mtr.Depth, Deep Tubewell by Water Jet System at Garhbeta Water Testing Lab Premises in the district of Paschim Medinipore under Midnapore Division PHE Dte.(SL No-01) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000194/2021-2022 | 438/AE/MSSD | 10/08/2021 | 15 | S.T. ENTERPRISE | 2.87 | 0 | 0
1861 | Midnapore Division | Midnapur Sadar Sub-Division | Repairing of damaged (due to flood) Rising main from river bank Tube Well to CWR of Garhbeta & its adjoining Mouzas W/S Scheme within Garhbeta Block under Midnapore Division PHE Dte. (SL No-02) | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000258/2022-2023 | 467/AE/MSSD | 08/08/2022 | 45 | CHANDAN YADAV | 0.81 | 0 | 0
1862 | Midnapore Division | Midnapur Sadar Sub-Division | Hiring of 1 (one) no, Motor Cab(standard) commercial with catalytic converter attachment with Bharat Stage as per prevalent applicable standard compliant new/not older then 30 (thirty) months from the date of 1st registration on daily hire basis for 12 (twelve) months only having contract carriage permit for plying within west Bengal from Regional Transport Authority for the use of the Assistant Engineer, Midnapore Sadar Sub- Division PHE Dte. (It would be used only the 'JAL SWAPNA" Schematic Programme, inaugurated by Honorable C.M ) for the period of 06 (Six) months. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000259/2022-2023 | 470/AE/MSSD | 10/08/2022 | 184 | SANJIT SINHA | 0.85 | 0 | 0
1863 | Midnapore Division | Midnapur Sadar Sub-Division | Laying additional distribution pipeline for Augmentation of Garhbeta PWSS, Block - Garhbeta-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000557/2024-2025 | 811/MD | 25/03/2025 | 60 | KISHORE GHOSH | 51.54 | 0 | 10
1864 | Midnapore Division | Midnapur Sadar Sub-Division | Continuation Work Order for the work of Conducting of Route survey & Design with allied works in connection with the FHTC of existing PWSS Garhbeta (Block-Garhbeta-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001040/2021-2022 | 1652/MD | 23/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.69 | 0 | 0
1865 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000036/2021-2022 | 150/MD | 28/01/2022 | 0 | Resource Division | 25.21 | 0 | 0
1866 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000147/2022-2023 | 518/MD | 20/02/2023 | 0 | Resource Division | 90.05 | 0 | 0
1867 | Midnapore Division | Midnapur Sadar Sub-Division | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Garhbeta to Accommodate FHTC, Block - Garhbeta-I. District - Paschim Medinipur. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/000446/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 25.21 | 0 | 0
1868 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Garhbeta, Block - Garhbeta-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001384/2021-2022 | BP-2021-22-398 | 08/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.67 | 0 | 0
1869 | Midnapore Division | Midnapur Sadar Sub-Division | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 2,27,000 Ltr.) at Head work Site of Garhbeta Water Supply Scheme within Garhbeta-I Block under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/001611/2021-2022 | BP-2021-22-421 | 02/03/2022 | 0 | BISWAJIT BAG | 4.7 | 0 | 0
1870 | Midnapore Division | Kharagpur Sub-Division | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00239/2022-2023 |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0
1871 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 400 CuM and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Pingla & its adjoining mouzas Water Supply Scheme within Pingla Dev. Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. Dist. Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000124/2022-2023 | 1311/MD | 30/06/2022 | 1245 | GOBINDA MAITY | 668 | 0 | 100
1872 | Midnapore Division | Kharagpur Sub-Division | Balance work to accommodate FHTC of Augmentation Pipe Water Supply Scheme for Pingla & its adjoining mouzas, Block - Pingla, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000377/2024-2025 | 52/MD | 07/01/2025 | 75 | GOBINDA MAITY | 62.68 | 0 | 100
1873 | Midnapore Division | Kharagpur Sub-Division | Continuation Work Order for the work of Laying Balance Distribution System to accommodate FHTC of Proposed Augmentation Pipe Water Supply Scheme for Pingla & its adjoining Mouzas, Block: - Pingla, District: - Paschim Midnapore. Total Length = 12,600.00 Mtr. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000539/2022-2023 | 2467/MD | 05/12/2022 | 60 | GOBINDA MAITY | 68.72 | 0 | 0
1874 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Pingla W/S Scheme with in Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000579/2022-2023 | 229/MD | 17/01/2023 | 14 | GOBINDA MAITY | 20.68 | 0 | 0
1875 | Midnapore Division | Kharagpur Sub-Division | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Pingla (Block-Pingla) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001038/2021-2022 | 1646/MD | 22/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.15 | 0 | 0
1876 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000023/2022-2023 | 139/MD | 11/01/2023 | 0 | Resource Division | 21.67 | 0 | 0
1877 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000122/2022-2023 | 335/MD | 31/01/2023 | 0 | Resource Division | 20.85 | 0 | 0
1878 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Pingla, Block - Pingla) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001389/2021-2022 | BP-2021-22-396 | 22/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 0 | 0
1879 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Debhog PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000431/2021-2022 | 1664/MD | 28/09/2021 | 10 | SIRCON ENGINEERING SERVICES PVT. LTD. | 2.19 | 0 | 100
1880 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Debhog (Part) to accommodate FHTC under JJM of Sabang Block in Paschim Medinipur District under Medinipur Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000476/2022-2023 | 2271/MD | 09/11/2022 | 45 | S.T. ENTERPRISE | 46.36 | 0 | 77
1881 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 150 Cum & 100 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (1904 Nos) including 2 years operation & maintenance For Chak Bajit and Kankara Shibram Pipe Water Supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000387/2023-2024 | 5061/MD | 26/10/2023 | 638 | ANIRUDDHA BAG | 561.96 | 0 | 75
1882 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000229/2023-2024 | 1512/MD | 12/05/2023 | 0 | Resource Division | 27.4 | 0 | 0
1883 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bishnupur PWSS, Block :- Sabang in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000440/2020-2021 | 310/MD | 22/02/2021 | 1114 | KISHORE GHOSH | 90.52 | 31.27 | 80
1884 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000050/2023-2024 | 1189/MD | 26/04/2023 | 0 | Resource Division | 76.51 | 0 | 0
1885 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
1886 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
1887 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000109/2024-2025 | 3445/MD | 25/11/2024 | 0 | Resource Division | 4.39 | 0 | 0
1888 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000278/2023-2024 | 4051/MD | 12/10/2023 | 0 | Resource Division | 23.01 | 0 | 0
1889 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
1890 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
1891 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000254/2023-2024 | 1588/MD | 15/05/2023 | 0 | Resource Division | 25.71 | 0 | 0
1892 | Midnapore Division | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-I OF JAHALDA PWSS. REF CONSUMER ID-204373753, APPLICATION NO-2004852919, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00447/2024-2025 | BP-2024-25-294 | 27/08/2024 | 0 | WBSEDCL | 13.22 | 0 | 0
1893 | Midnapore Division | Midnapur Mechanical Sub Division-I | ELECTRIC QUOTATION BILL FOR TW NO-II OF JAHALDA PWSS. REF CONSUMER ID-204373747, APPLICATION NO-2004852930, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-KHAKURDA CCC, NAME OF BLOCK-DANTAN-II | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | BILL/00449/2024-2025 | BP-2024-25-294 | 27/08/2024 | 0 | WBSEDCL | 9.12 | 0 | 0
1894 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
1895 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000098/2023-2024 | 1287/MD | 28/04/2023 | 0 | Resource Division | 24.63 | 0 | 0
1896 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Belun PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000275/2022-2023 | 550/AE/KSD | 23/08/2022 | 30 | GOBINDA MAITY | 2.26 | 0 | 0
1897 | Midnapore Division | Kharagpur Sub-Division | Laying additional distribution pipe line to accommodate FHTC (200 Nos.) of Belun Pipe Water Supply Scheme within Pingla Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000479/2024-2025 | 482/MD | 13/02/2025 | 60 | NIMAI HAZRA | 17.07 | 0 | 0
1898 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Balance FHTC (127) & Repair of Pump House & or Augmentation of Belun PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000625/2022-2023 | 450/MD | 13/02/2023 | 689 | MASUM ALI KHAN | 55.11 | 0 | 100
1899 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(Pingla),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000172/2023-2024 | 1370/MD | 02/05/2023 | 0 | Resource Division | 5.84 | 0 | 0
1900 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
1901 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000094/2023-2024 | 1235/MD | 27/04/2023 | 0 | Resource Division | 37.87 | 0 | 0
1902 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
1903 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
1904 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000235/2023-2024 | 1526/MD | 12/05/2023 | 0 | Resource Division | 29.35 | 0 | 0
1905 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 65
1906 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
1907 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000009/2023-2024 | 1148/MD | 25/04/2023 | 0 | Resource Division | 14.87 | 0 | 0
1908 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Keshiary Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Bhansra (JL.- 138, Plot-455/738), (2) Gaganeshwar (JL.- 154, Plot- 454), (3) Haripura (JL.- 130, Plot-13), (4) Panchyar (JL.- 194, Plot-400), (5) Santrapur (JL.- 57, Plot-218)] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000651/2022-2023 | 746/MD | 13/03/2023 | 30 | JADAVPUR UNIVERSITY | 23.9 | 0 | 0
1909 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000071/2024-2025 | 3417/MD | 25/11/2024 | 0 | Resource Division | 12.22 | 0 | 0
1910 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000129/2023-2024 | 1323/MD | 28/04/2023 | 0 | Resource Division | 23.2 | 0 | 0
1911 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
1912 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000095/2023-2024 | 1289/MD | 28/04/2023 | 0 | Resource Division | 22.38 | 0 | 0
1913 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000093/2023-2024 | 1290/MD | 28/04/2023 | 0 | Resource Division | 20.99 | 0 | 0
1914 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
1915 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000053/2023-2024 | 1192/MD | 26/04/2023 | 0 | Resource Division | 13.69 | 0 | 0
1916 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000155/2023-2024 | 1304/MD | 28/04/2023 | 0 | Resource Division | 2.79 | 0 | 0
1917 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Benachapra PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000457/2024-2025 | 374/MD | 31/01/2025 | 21 | DONA ASSOCIATES | 11.64 | 0 | 0
1918 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000158/2023-2024 | 1258/MD | 28/04/2023 | 0 | Resource Division | 26.15 | 0 | 0
1919 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000067/2024-2025 | 3390/MD | 25/11/2024 | 0 | Resource Division | 3.79 | 0 | 0
1920 | Midnapore Division | Ghatal Subdivision | Laying of rising main & interconnection for Khandanga & its adjoining mouzas PWSS, Block: - Chandrakona-II, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000431/2024-2025 | 317/MD | 29/01/2025 | 45 | AMAL DUTTA ROY | 16.19 | 0 | 0
1921 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000009/2024-2025 | 3330/MD | 25/11/2024 | 0 | Resource Division | 23.3 | 0 | 0
1922 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000045/2022-2023 | 103/MD | 10/01/2023 | 0 | Resource Division | 34.55 | 0 | 0
1923 | Midnapore Division | Midnapur Sadar Sub-Division | Route survey & way leave permission along & across of National Highway in Shyamnagar PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000193/2025-2026 | 1629/MD | 06/08/2025 | 21 | PIONEER SURVEYORS | 8.64 | 0 | 0
1924 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
1925 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000161/2022-2023 | 1150/MD | 25/04/2023 | 0 | Resource Division | 54.02 | 0 | 0
1926 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000040/2023-2024 | 1182/MD | 26/04/2023 | 0 | Resource Division | 31.67 | 0 | 0
1927 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 (Two) Nos. 250 X 150 mm dia. X 180 mtr. Depth deep tube well by direct rotary method Proposed Pipe Water Supply Scheme for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-VI] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000005/2023-2024 | 974/MD | 10/04/2023 | 21 | ANNAPURNA TUBEWELL WORKS | 17.57 | 0 | 100
1928 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line and Accommodate FHTC (316 Nos.) under JJM with allied work for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-III] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000007/2023-2024 | 976/MD | 10/04/2023 | 60 | SANJIT SINHA | 49.38 | 0 | 70
1929 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line and accommodate FHTC work (320 Nos.) for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-V] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000008/2023-2024 | 977/MD | 10/04/2023 | 709 | S.T. ENTERPRISE | 95.59 | 0 | 70
1930 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line and Accommodate FHTC (320 Nos.) under JJM with allied work for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-II] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000042/2023-2024 | 1386/MD | 02/05/2023 | 60 | S.N. ENTERPRISE (PROP. DIBYENDU GUHA) | 76.5 | 0 | 66
1931 | Midnapore Division | Midnapur Sadar Sub-Division | Construction and Commissioning of 250 Cum Capacity (Intze Type with Pile) Over Headed Reservoir, Soil Investigation, Construction of Pump House, Boundary wall, Laying of Rising main, accommodate FHTC (320 Nos.) with 2 years operation & maintenance for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-I] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000042/2024-2025 | 2257/MD | 23/07/2024 | 180 | M/S R.N. ENTERPRISE | 136.16 | 0 | 0
1932 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution of Pipe line, Construction of Pump House, Boundary wall and Accommodate FHTC work (360 Nos.) for Proposed Chhoto Nakdana & its adjoining mouzas PWSS, Block-Garhbeta-II Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-IV] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000055/2024-2025 | 2578/MD | 22/08/2024 | 120 | S.N ENTERPRISE | 95.96 | 0 | 0
1933 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000139/2023-2024 | 1300/MD | 28/04/2023 | 0 | Resource Division | 27.76 | 0 | 0
1934 | Midnapore Division | Kharagpur Sub-Division | Construction of approach road for 2nd work site of Uttar Karkara Piped Water Supply Scheme within Narayangarh Block under Midnapore Division, PHE Dte. [100 Mtr. Long X 3 Mtr. Width] | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000006/2025-2026 | 997/AE/HQ/MD | 22/04/2025 | 30 | GOURMOHAN DAS | 1.14 | 0 | 0
1935 | Midnapore Division | Kharagpur Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection 14,471 Nos.) including 2 years operation & maintenance for Radhanagar, Akanda, Kashbaasanda, Kutki, Tarua, Trikalpur, Uttar Karkara and Shashinda Pipe Water Supply Scheme within Narayangarh block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000212/2023-2024 | 2823/MD | 07/08/2023 | 960 | S & P ENTERPRISE | 3925.58 | 0 | 20
1936 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000108/2024-2025 | 3444/MD | 25/11/2024 | 0 | Resource Division | 5.12 | 0 | 0
1937 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000279/2023-2024 | 4052/MD | 12/10/2023 | 0 | Resource Division | 25.14 | 0 | 0
1938 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Pump House & Boundary wall under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000019/2024-2025 | 2037/MD | 01/07/2024 | 420 | M/S. INDRAJIT ROY | 26.6 | 0 | 10
1939 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipeline & Accommodate FHTC (555 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000099/2023-2024 | 2474/MD | 14/07/2023 | 961 | WATER LINK | 81.95 | 0 | 50
1940 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 2 (Two) Nos. Tube well for Bag Basa & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000114/2023-2024 | 2515/MD | 18/07/2023 | 30 | ANNAPURNA TUBEWELL WORKS | 15.96 | 0 | 100
1941 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Pump House under JJM for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000179/2024-2025 | 3164/MD | 05/10/2024 | 120 | A R ENTERPRISE | 7.17 | 0 | 80
1942 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Rising main, Distribution pipeline & Accommodate FHTC (400 Nos.) including 2 years O & M under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000267/2023-2024 | 3241/MD | 11/09/2023 | 961 | MIDNAPUR PIPE CONCERN | 132.56 | 0 | 20
1943 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipeline & Accommodate FHTC (400 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000351/2023-2024 | 4002/MD | 06/10/2023 | 60 | SK. MAIDUL ISLAM | 50.44 | 0 | 50
1944 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 200 cum OHR (Intze type with solid raft) & Accommodate FHTC (400 Nos.) under JJM with allied works for Bag Basa & its adjoining mouzas W/S Scheme in Salbani block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000509/2024-2025 | 608/MD | 04/03/2025 | 360 | KRISHNENDU SEKHAR DAS | 88.98 | 0 | 0
1945 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000176/2023-2024 | 1359/MD | 02/05/2023 | 0 | Resource Division | 55.34 | 0 | 0
1946 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Radhanagr & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000658/2022-2023 | 1756/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.12 | 0 | 0
1947 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000037/2024-2025 | 3364/MD | 25/11/2024 | 0 | Resource Division | 16.7 | 0 | 0
1948 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line, Soil test, FHTC & Construction of R.C.C. Over Head Reservoir of capacity 300 Cum and staging height 20.00 mtr. with allied work for Augmentation of Kalaikunda W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000010/2022-2023 | 2411/MD | 25/11/2022 | 917 | ASHIM KUMAR DEY | 226.86 | 0 | 69
1949 | Midnapore Division | Kharagpur Sub-Division | Cleaning the chokage of pipe in the existing line at Kalaikunda PWSS under Kharagpur Sub-Division of Midnapur Division, P.H.E Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000339/2024-2025 | 3582/MD | 06/12/2024 | 30 | M/S. GEO | 4.56 | 0 | 100
1950 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kalaikunda, Block - Kharagpur-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001141/2020-2021 | 67/MD | 11/01/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.52 | 0 | 100
1951 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE3 Kharagpur Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000091/2024-2025 | 3418/MD | 25/11/2024 | 0 | Resource Division | 14.5 | 0 | 0
1952 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 980 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 75
1953 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000050/2024-2025 | 3370/MD | 25/11/2024 | 0 | Resource Division | 9.42 | 0 | 0
1954 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 65
1955 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000015/2023-2024 | 1143/MD | 25/04/2023 | 0 | Resource Division | 16.01 | 0 | 0
1956 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000149/2023-2024 | 1268/MD | 28/04/2023 | 0 | Resource Division | 22.39 | 0 | 0
1957 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000268/2023-2024 | 2226/MD | 15/06/2023 | 0 | Resource Division | 32.3 | 0 | 0
1958 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00724/2022-2023 | BP-2022-23-661 | 29/03/2023 | 0 | M/S. D.K.H.CONSTRUCTION | 3.05 | 0 | 0
1959 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-I), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000210/2022-2023 | 1675/MD | 12/08/2022 | 150 | M/S. D.K.H.CONSTRUCTION | 39.56 | 0 | 91
1960 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Chauka (Zone-II), Block: - Ghatal, District: - Paschim Midnapore under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000211/2022-2023 | 1676/MD | 12/08/2022 | 872 | M/S. D.K.H.CONSTRUCTION | 45.86 | 0 | 91
1961 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.Rs (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- (i) Chauka & (ii) Masarpur under Dewanchak-II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000417/2021-2022 | 1330/MD | 17/08/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 3.46 | 0 | 0
1962 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Ghatal),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000042/2024-2025 | 3351/MD | 25/11/2024 | 0 | Resource Division | 2.67 | 0 | 0
1963 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (325) for Augmentation of Ranapur PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000198/2023-2024 | 2812/MD | 07/08/2023 | 383 | KISHORE GHOSH | 82.99 | 0 | 70
1964 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 0 | 100
1965 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 0 | 100
1966 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000134/2022-2023 | 407/MD | 07/02/2023 | 0 | Resource Division | 3.42 | 0 | 0
1967 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (2,648 nos.) under JJM with allied work including 02 (Two ) Years Operation & Maintenance for Pelagerya & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000228/2023-2024 | 2952/MD | 17/08/2023 | 997 | A.J. ENTERPRISE | 605.48 | 0 | 61
1968 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000084/2024-2025 | 3435/MD | 25/11/2024 | 0 | Resource Division | 16.31 | 0 | 0
1969 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000087/2022-2023 | 193/MD | 16/01/2023 | 0 | Resource Division | 44.34 | 0 | 0
1970 | Midnapore Division | Ghatal Subdivision | Laying additional distribution system pipe line to provide balance FHTC for Augmentation of Supapursuri W/S Scheme, Block - Daspur-I, Dist.- Paschim Medinipur under Midnapore Division, PHE Dte. (PART-B) | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000101/2024-2025 | 2847/MD | 09/09/2024 | 204 | SK REAJUL HOSSAIN | 15.33 | 0 | 100
1971 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall & Balance FHTC (998) for Augmentation of Supapursuri PWSS in Daspur-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000180/2023-2024 | 2720/MD | 31/07/2023 | 819 | M/S. D.K.H.CONSTRUCTION | 127.08 | 0 | 15
1972 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Daspur-I block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000735/2022-2023 | 2682/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.76 | 0 | 100
1973 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing 3 Nos. PWSS within Ghatal block under Midnapore Division P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000736/2022-2023 | 2683/MD | 30/12/2022 | 21 | RISHAN ENGINEERING CONSULTANCY | 7.72 | 0 | 100
1974 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000138/2022-2023 | 413/MD | 07/02/2023 | 0 | Resource Division | 6.69 | 0 | 0
1975 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000068/2024-2025 | 3391/MD | 25/11/2024 | 0 | Resource Division | 11.09 | 0 | 0
1976 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 150 cum OHR (Intze type with pile foundation) & Accommodate FHTC (803 nos) under JJM with allied work for Ramchandrapur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000062/2023-2024 | 2416/MD | 13/07/2023 | 897 | SAI TUBE CO. | 284.53 | 0 | 80
1977 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000017/2024-2025 | 3338/MD | 25/11/2024 | 0 | Resource Division | 4.95 | 0 | 0
1978 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000047/2022-2023 | 106/MD | 10/01/2023 | 0 | Resource Division | 43.22 | 0 | 0
1979 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000240/2023-2024 | 1524/MD | 12/05/2023 | 0 | Resource Division | 53.67 | 0 | 0
1980 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall for Augmentation of Chakmakrampur PWSS in Kharagpur-II Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000032/2023-2024 | 948/MD | 06/04/2023 | 722 | ASIS KUMAR SARANGI | 292.42 | 0 | 45
1981 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing (i) Chakmakrampur PWSS within Kharagpur-II block & (ii) Shyamsundarpur PWSS within Sabang Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000496/2022-2023 | 2063/MD | 30/09/2022 | 15 | GOBINDA MAITY | 5.83 | 0 | 0
1982 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000077/2022-2023 | 204/MD | 16/01/2023 | 0 | Resource Division | 6.8 | 0 | 0
1983 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000096/2024-2025 | 3436/MD | 25/11/2024 | 0 | Resource Division | 18.82 | 0 | 0
1984 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Rising main, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 150 cum OHR (Intze type with pile foundation) & Accommodate FHTC (863 nos.) including 2 years of Operation & Maintenance under JJM with allied work for Rabidaspur PWSS in Daspur- I Block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000391/2023-2024 | 5065/MD | 26/10/2023 | 717 | ZENITH CONSTRUCTION | 310.14 | 0 | 10
1985 | Midnapore Division | Ghatal Subdivision | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Rabidaspur, Tiorberya & Ramchandrapur & its adjoining Mouzas PWSS instead Rabidaspur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000748/2022-2023 | 1267/MD | 23/06/2022 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.37 | 0 | 100
1986 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000252/2023-2024 | 1586/MD | 15/05/2023 | 0 | Resource Division | 43.26 | 0 | 0
1987 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Rising main, Pump House, Boundary wall & Accommodate FHTC (105 Nos.) including 2 yrs. O & M under JJM with allied work for Dwarkhola PWSS in Chandrakona-I block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000084/2023-2024 | 2431/MD | 13/07/2023 | 60 | WATER LINK | 53.82 | 0 | 35
1988 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000152/2022-2023 | 535/MD | 21/02/2023 | 0 | Resource Division | 7.23 | 0 | 0
1989 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well ,Laying Rising Main,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 100 cum OHR (Intze type foundation) & Accommodate FHTC (490nos) Including 2 years of Operation & Maintenance under JJM with allied work for Tiorberya PWSS in Daspur- I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000206/2023-2024 | 2822/MD | 07/08/2023 | 902 | ZENITH CONSTRUCTION | 222.1 | 0 | 20
1990 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000019/2024-2025 | 3389/MD | 25/11/2024 | 0 | Resource Division | 7.18 | 0 | 0
1991 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000282/2023-2024 | 4054/MD | 12/10/2023 | 0 | Resource Division | 32.99 | 0 | 0
1992 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 550 cum OHR (Intze type with pile foundation) & Accommodate FHTC (4,219 Nos.) under JJM with allied work for Jadabpur PWSS in Chandrakona-I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000227/2023-2024 | 2951/MD | 17/08/2023 | 773 | GOBINDA MAITY | 1057.25 | 0 | 65
1993 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000005/2024-2025 | 3326/MD | 25/11/2024 | 0 | Resource Division | 16.21 | 0 | 0
1994 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000050/2022-2023 | 59/MD | 09/01/2023 | 0 | Resource Division | 68.66 | 0 | 0
1995 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | RTOR000286/2023-2024 | 4057/MD | 12/10/2023 | 0 | Resource Division | 56.31 | 0 | 0
1996 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,304 Nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Dubrajpur & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Midnapore Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000261/2023-2024 | 3235/MD | 11/09/2023 | 1045 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 399.53 | 0 | 10
1997 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-II),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000243/2023-2024 | 1530/MD | 12/05/2023 | 0 | Resource Division | 36.37 | 0 | 0
1998 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Replacement tube well including allied works for Retrofitting of Ground Water Based Kalshibhanga PWSS to accommodate FHTC under JJM under Salboni block in Paschim Medinipur District under Midnapore Division, P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000856/2021-2022 | 420/MD | 04/03/2022 | 21 | CHANDAN YADAV | 9.91 | 0 | 0
1999 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chotto Kalsibhanga, Block - Salboni) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000862/2020-2021 | 299/MD | 19/02/2021 | 10 | SIRCON ENGINEERING SERVICES | 1.4 | 0 | 0
2000 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 450 Cum OHR (Intze type with Pile) & Accommodate FHTC (2,431 Nos.) including Two years O&M under JJM with allied work for Islampur W/S Scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000293/2023-2024 | 3965/MD | 05/10/2023 | 540 | M/S. MALLIK CONSTRUCTION | 607.53 | 0 | 53
2001 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | RTOR000270/2023-2024 | 3984/MD | 06/10/2023 | 0 | Resource Division | 34.8 | 0 | 0
2002 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well ,Laying of Rising Main ,Laying distribution pipe line, Pump House, 100 cum OHR( Intze type with solid raft ) & Accommodate FHTC (712 Nos) including 2 years operation & maintenance under JJM with allied work for Talbandi & its adjoining mouzas W/S scheme in Debra Block including supply of all labour & materials within Kharagpur Sub-division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000067/2023-2024 | 2148/MD | 08/06/2023 | 180 | M/S. RAJ KUMAR KHAN | 239.9 | 0 | 45
2003 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000230/2023-2024 | 1518/MD | 12/05/2023 | 0 | Resource Division | 20.4 | 0 | 0
2004 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000102/2023-2024 | 1286/MD | 28/04/2023 | 0 | Resource Division | 45.86 | 0 | 0
2005 | Midnapore Division | Kharagpur Sub-Division | Construction of boundary wall of Kharagpur Sub-Divisional Store cum Stack yard and Guard Room at Gopali, Mouza ¿ Rangametya, vide J.L. No. - 255, Plot No. - 75/570 under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the district of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000378/2024-2025 | 53/MD | 07/01/2025 | 75 | GOBINDA MAITY | 64.56 | 0 | 0
2006 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Wells, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of Two nos. 150 cum & 450 cum OHRs & Accommodate FHTC (3,044 Nos.) including Two years O&M under JJM with allied work for Gopali (Zone-I,II) & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000512/2023-2024 | 5480/MD | 13/12/2023 | 720 | SUJOY KUMAR MANDAL | 831.24 | 0 | 66
2007 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000088/2024-2025 | 3440/MD | 25/11/2024 | 0 | Resource Division | 18.75 | 0 | 0
2008 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000094/2022-2023 | 187/MD | 16/01/2023 | 0 | Resource Division | 35.98 | 0 | 0
2009 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Ragpur W/S Scheme, Block: - Pingla, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000253/2020-2021 | 1449/MD | 26/11/2020 | 1496 | GOBINDA MAITY | 94.99 | 27.37 | 100
2010 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | RTOR000102/2024-2025 | 3411/MD | 25/11/2024 | 0 | Resource Division | 12.39 | 0 | 0
2011 | Midnapore Division | Ghatal Subdivision | Laying Rising main pipe line for "Benai Zone-II" PWSS under Daspur-II Block within Ghatal Sub-Division under Midnapore Division, P.H.E.Dte | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000127/2024-2025 | 1493/AE/GSD | 24/09/2024 | 30 | M/S. A.R. ENTERPRISE | 3.17 | 0 | 0
2012 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR & 250 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (4,213 Nos.) under JJM with allied work for Benai (Zone- I & Zone-II) & its adjoining mouzas W/S scheme in Daspur- II Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000257/2023-2024 | 3231/MD | 11/09/2023 | 900 | M/S. A.R. ENTERPRISE. | 983.46 | 0 | 15
2013 | Midnapore Division | Ghatal Subdivision | Laying rising main pipeline for Benai (Zone-I) PWSS under Daspur-II block within Ghatal sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000332/2024-2025 | 3575/MD | 06/12/2024 | 405 | M/S. A.R. ENTERPRISE | 5.52 | 0 | 0
2014 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000020/2024-2025 | 3340/MD | 25/11/2024 | 0 | Resource Division | 25.95 | 0 | 0
2015 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | RTOR000033/2022-2023 | 112/MD | 10/01/2023 | 0 | Resource Division | 65.54 | 0 | 0
2016 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
2017 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000073/2023-2024 | 1217/MD | 27/04/2023 | 0 | Resource Division | 28.24 | 0 | 0
2018 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000280/2020-2021 | 1458/MD | 26/11/2020 | 1643 | SAI TUBE CO. | 91.84 | 75.6 | 100
2019 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Bhikni Nischintapur W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/000726/2020-2021 |  | 15/12/2020 | 0 | SAI TUBE CO. | 20 | 0 | 0
2020 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Jamna W/S Scheme. EE/MD/595/20-21 | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | VCH/001923/2021-2022 | BP-2021-22-140 | 10/03/2022 | 0 | GOBINDA MAITY | 12.45 | 0 | 0
2021 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,958 nos.) under JJM with allied work for Khirishmul PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000253/2023-2024 | 3148/MD | 29/08/2023 | 870 | BANERJEE CONSTRUCTION | 1014.08 | 0 | 35
2022 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000060/2024-2025 | 3380/MD | 25/11/2024 | 0 | Resource Division | 12.06 | 0 | 0
2023 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000061/2022-2023 | 65/MD | 09/01/2023 | 0 | Resource Division | 17.57 | 0 | 0
2024 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000239/2023-2024 | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 33
2025 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
2026 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000238/2023-2024 | 1527/MD | 12/05/2023 | 0 | Resource Division | 26.82 | 0 | 0
2027 | Midnapore Division | Ghatal Subdivision | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Block - Daspur-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000156/2021-2022 | 914/MD | 10/06/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.88 | 0 | 100
2028 | Midnapore Division | Ghatal Subdivision | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Block - Daspur-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000197/2021-2022 | 930/MD | 14/06/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.07 | 0 | 100
2029 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (5,245 Nos.) under JJM with allied work for Augmentation of Daspur (Zone-I & Zone-II) & its adjoining mouzas W/S Scheme in Daspur- I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000250/2023-2024 | 3145/MD | 29/08/2023 | 761 | GOBINDA MAITY | 1112.86 | 0 | 20
2030 | Midnapore Division | Ghatal Subdivision | Laying of rising main pipeline for Augmentation of Daspur (Zone-I & II) & its adj. mouzas Pipe W/S Scheme within block - Daspur-I, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000379/2024-2025 | 54/MD | 07/01/2025 | 60 | GOBINDA MAITY | 20.06 | 0 | 80
2031 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(Daspur-I),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000021/2024-2025 | 3339/MD | 25/11/2024 | 0 | Resource Division | 117.64 | 0 | 0
2032 | Midnapore Division |  | Retrofitting to accommodate FHTC under JJM in BAHADURPUR PWSS of Binpur-I Block under Jhargram Division, PHE Dte. ( PHASE - II) |  |  | ORD/000589/2020-2021 | 629/JSD | 22/02/2021 | 30 | MA LAXMI ENTERPRISE | 4.53 | 3.73 | 0
2033 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Harekrishnapur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000209/2020-2021 | 1430/MD | 26/11/2020 | 180 | DIPAK KUMAR DOLAI | 94.96 | 0 | 0
2034 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate balance FHTC under JJM in RANAPUR PWSS in Daspur-I Block in the District of Paschim Midnapore. | AE Ghatal Sub-division |  | ORD/000372/2020-2021 | 263/MD | 12/02/2021 | 30 | KISHORE GHOSH | 9.49 | 0 | 0
2035 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Narayanbar W/S Scheme, Block: - Sabang, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000260/2020-2021 | 1457/MD | 26/11/2020 | 1859 | BANERJEE CONSTRUCTION | 93.13 | 22.32 | 90
2036 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Distribution system connected with newly sunk tube well from Chaipur Sitala Mandir to Kundalboni pipe line at Dherua Zone -I piped water supply scheme with in Midnapore Sadar Block ( Within MSSD) under Midnapore Division PHE Dte.(SL No-01) | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00667/2024-2025 | 844334 | 09/05/2024 | 0 | SANJIT SINHA | 2.7 | 0 | 0
2037 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Distribution system connected with newly sunk tube well from Mohulboni to Chaipur Sitala Mandir pipe line at Dherua Zone -I piped water supply scheme with in Midnapore Sadar Block( Within MSSD) under Midnapore Division PHE Dte.(SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00711/2024-2025 | 844376 | 24/06/2024 | 0 | SANJIT SINHA | 3.47 | 0 | 0
2038 | Midnapore Division | Midnapur Sadar Sub-Division | Round the Clock Guarding Arrangements to protect the Govt. properties / materials etc. at The Head work site Midnapore Divison , PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00728/2022-2023 | 8443125 | 29/03/2023 | 0 | M/S. OXFORD SECURITY SERVICE | 3.28 | 0 | 0
2039 | Midnapore Division | Midnapur Sadar Sub-Division | Laying Distribution system connected with newly sunk tube well from Debra to Chuasole pipe line at Dherua Zone - IV piped water supply scheme with in Midnapore Sadar Block( Within MSSD) under Midnapore Division PHE Dte.(SL No-03) | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00976/2024-2025 | 844357 | 24/10/2024 | 0 | SANJIT SINHA | 1.48 | 0 | 0
2040 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-I) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000233/2020-2021 | 1438/MD | 26/11/2020 | 180 | M/S. EL-CON | 91.85 | 24.91 | 100
2041 | Midnapore Division | Midnapur Sadar Sub-Division | Damage of existing pipeline lies under the existing carriageway of the road at Chuasol (Zone ¿V) & Boylasole ,Siarboni (zone) under Dherua and its adjoining mouzas water supply scheme within Midnapore Sadar Sub-Division under Midnapore Division PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000618/2022-2023 | 785/AE/MSSD | 06/01/2023 | 30 | SANJIT SINHA | 1.78 | 0 | 0
2042 | Midnapore Division | Midnapur Sadar Sub-Division | Data Entry Operation for IMIS entry of all information collected during survey work of Schools, Anganwadies Centre ,Health Care Institution etc. under Midnapore Division PHE Dte.(SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000708/2020-2021 | 13/AE/MSSD | 06/01/2021 | 3 | PULLOCK KUMAR GHOSH | 1.48 | 1.47 | 0
2043 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000625/2021-2022 | 8443119 | 23/08/2021 | 0 | PAPPU SHAW | 0.04 | 0 | 0
2044 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000626/2021-2022 | 8443119 | 23/08/2021 | 0 | SIDDHESWAR BAG | 0.05 | 0 | 0
2045 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000627/2021-2022 | 8443119 | 23/08/2021 | 0 | SUBRATA CHAKRABORTY | 0.03 | 0 | 0
2046 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000833/2021-2022 | 844387 | 13/09/2021 | 0 | ANKITA HAZRA | 0.01 | 0 | 0
2047 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000834/2021-2022 | 844387 | 13/09/2021 | 0 | KOUSHIK PAL | 0.01 | 0 | 0
2048 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000835/2021-2022 | 844387 | 13/09/2021 | 0 | MANABENDRA DAS | 0.08 | 0 | 0
2049 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000839/2021-2022 | 844387 | 13/09/2021 | 0 | BIPLAB SHIT | 0.01 | 0 | 0
2050 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000841/2021-2022 | 844387 | 13/09/2021 | 0 | SANJOY DAS | 0.02 | 0 | 0
2051 | Midnapore Division | Midnapur Sadar Sub-Division | Milan Jana | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000875/2021-2022 | 844387 | 19/09/2021 | 0 | MILAN JANA | 0.01 | 0 | 0
2052 | Midnapore Division | Midnapur Sadar Sub-Division | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001059/2021-2022 | 844383 | 25/11/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0
2053 | Midnapore Division | Midnapur Sadar Sub-Division | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001060/2021-2022 | 844381 | 25/11/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0
2054 | Midnapore Division | Midnapur Sadar Sub-Division | Electric bill for the office of the Executive Engineer Mid. Mech. Divn. PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001061/2021-2022 | 844382 | 25/11/2021 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.11 | 0 | 0
2055 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC imis data entry. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001639/2021-2022 | 8443146 | 24/03/2022 | 0 | GANESH CH NANDY | 0.14 | 0 | 0
2056 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC imis data entry. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001641/2021-2022 | 8443146 | 24/03/2022 | 0 | RAJIB DEY | 0.15 | 0 | 0
2057 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC imis data entry. | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/001642/2021-2022 | 8443146 | 24/03/2022 | 0 | SOVANDEB MANNA | 0.09 | 0 | 0
2058 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00213/2023-2024 | 844335 | 19/04/2023 | 0 | M/S. EL-CON | 15 | 0 | 0
2059 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-II) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00406/2023-2024 | 844380 | 15/05/2023 | 0 | M/S. EL-CON | 7.51 | 0 | 0
2060 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-III) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00588/2023-2024 | 8443137 | 28/08/2023 | 0 | M/S. EL-CON | 2.48 | 0 | 0
2061 | Midnapore Division | Midnapur Sadar Sub-Division | Hiring of vehicle for the SE, WC PHE Dte. [01/11/2023 to 31/03/2024] | AE Sadar Sub-division | JE2 Sadar Sub-division | BILL/00676/2024-2025 | 844332 | 14/05/2024 | 0 | BISWADIP SIKDAR | 0.99 | 0 | 0
2062 | Midnapore Division | Midnapur Sadar Sub-Division | Supply and delivery of Sluice Valve for Dherua W/S Scheme (Zone-II & III) of Midnapore Sadar Block within Midnapore Divison PHE Dte.(SL No-02) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000181/2021-2022 | 443/AE/MSSD | 12/08/2021 | 15 | DIPAK KUMAR BAKLY | 2.33 | 2.33 | 0
2063 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dherua (Zone-II) W/S Scheme, Block: - Midnapore Sadar, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000234/2020-2021 | 1439/MD | 26/11/2020 | 180 | M/S. CARE | 91.69 | 62.56 | 100
2064 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000628/2021-2022 | 8443119 | 23/08/2021 | 0 | MANABENDRA DAS | 0.03 | 0 | 0
2065 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000629/2021-2022 | 8443119 | 23/08/2021 | 0 | NABOGOPAL ADHIKARI | 0.04 | 0 | 0
2066 | Midnapore Division | Midnapur Sadar Sub-Division | FHTC Data entry | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000631/2021-2022 | 8443119 | 23/08/2021 | 0 | RINTU SAMANTA | 0.04 | 0 | 0
2067 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000843/2021-2022 | 844388 | 13/09/2021 | 0 | ANIRBAN CHAKRABORTY | 0.02 | 0 | 0
2068 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000844/2021-2022 | 844388 | 13/09/2021 | 0 | NABOGOPAL ADHIKARI | 0.05 | 0 | 0
2069 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000845/2021-2022 | 844388 | 13/09/2021 | 0 | RINTU SAMANTA | 0.08 | 0 | 0
2070 | Midnapore Division | Midnapur Sadar Sub-Division | DATA ENTRY FOR FHTC | AE Sadar Sub-division | JE2 Sadar Sub-division | VCH/000846/2021-2022 | 844388 | 13/09/2021 | 0 | SANDIP MANNA | 0.05 | 0 | 0
2071 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Chandpur W/S Scheme, Block: - Daspur-I, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000244/2020-2021 | 1443/MD | 26/11/2020 | 180 | MASUM ALI KHAN | 76.1 | 66.12 | 0
2072 | Midnapore Division | Ghatal Subdivision | Retrofitting to accommodate FHTC under JJM in Chandpur W/S Scheme District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000746/2020-2021 |  | 15/12/2020 | 0 | MASUM ALI KHAN | 30 | 0 | 0
2073 | Midnapore Division | Ghatal Subdivision | FHTC DATA ENTRY | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000760/2021-2022 | 8443212 | 27/09/2021 | 0 | MANABENDRA DAS | 0.14 | 0 | 0
2074 | Midnapore Division | Ghatal Subdivision | FHTC DATA ENTRY | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000761/2021-2022 | 8443212 | 27/09/2021 | 0 | RINTU SAMANTA | 0.12 | 0 | 0
2075 | Midnapore Division | Ghatal Subdivision | FHTC DATA ENTRY | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000762/2021-2022 | 8443212 | 27/09/2021 | 0 | SIDDHESWAR BAG | 0.17 | 0 | 0
2076 | Midnapore Division | Ghatal Subdivision | Engagement of 1 (One) No. Orderly Peon,Contractrual Group-D, through Agency for different official purpose for office of the office of the Assistant Engineer, Ghatal Sub-Division, P.H.E. Dte. (For 12 months) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000986/2022-2023 | 8443171 | 26/09/2022 | 0 | SUBHASIS DOLAI | 0.16 | 0 | 0
2077 | Midnapore Division | Ghatal Subdivision | Engagement of 1(one) no Contractual Clerical staff cum office assistant for different official purpose for office of the Assistant Engineer, Ghatal Sub-Division, P.H.E. dte. (1st year) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/000995/2022-2023 | 844356 | 09/09/2022 | 0 | DEVJYOTI BERA | 0.18 | 0 | 0
2078 | Midnapore Division | Ghatal Subdivision | FHTC data entry. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/001203/2021-2022 | 844334 | 08/12/2021 | 0 | MANABENDRA DAS | 0.14 | 0 | 0
2079 | Midnapore Division | Ghatal Subdivision | FHTC data entry. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/001204/2021-2022 | 844334 | 08/12/2021 | 0 | SIDDHESWAR BAG | 0.14 | 0 | 0
2080 | Midnapore Division | Ghatal Subdivision | FHTC Data Entry. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/001280/2021-2022 | 844361 | 18/01/2022 | 0 | GANESH CH NANDY | 0.2 | 0 | 0
2081 | Midnapore Division | Ghatal Subdivision | FHTC data Entry. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | VCH/001281/2021-2022 | 844361 | 18/01/2022 | 0 | SUBRATA CHAKRABORTY | 0.12 | 0 | 0
2082 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Naupara PWSS of Gopiballavpur-II Block under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | JE (M),Junior Engineer-III | ORD/000184/2020-2021 | 1412/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 36.77 | 0 | 80
2083 | Midnapore Division | Jhargram Sub-Division | Laying of clear water rising main / distribution pipe line with FHTC work, Sinking of 250mm X 150mm dia. Rig bore Tube well, Construction & Commissioning of 150 CuM RCC OHR etc. for Rejuvenation of Ground Based Naupara PWSS to accommodate FHTC in Gopiballavpur-II block within Jhargram district under Jhargram Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | JE (M),Junior Engineer-III | ORD/000910/2021-2022 | 499/MD | 15/03/2022 | 180 | GHOSH ENTERPRISE | 77.25 | 0 | 0
2084 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer, Jhargram Sub-Division | JE (M),Junior Engineer-III | RTOR000044/2021-2022 | 498/MD | 15/03/2022 | 0 | Resource Division | 15.18 | 0 | 0
2085 | Midnapore Division | Jhargram Sub-Division | Material Requisition To Resource Division | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-II | RTOR000009/2022-2023 | 355 | 29/09/2022 | 0 | Resource Division | 0.22 | 0 | 0
2086 | Midnapore Division | Midnapur Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Dhamsai PWSS, Block - Keshpur in the district of Paschim Medinipur. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000482/2021-2022 | 2176/MD | 17/12/2021 | 30 | PRADIP KUMAR SAHA | 20.61 | 0 | 0
2087 | Midnapore Division | Midnapur Sadar Sub-Division | Laying of distribution system of uPVC pipeline due to damage portion road along the pipeline and including shifting under Dhamsai W/S Scheme in Keshpur Block under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | VCH/001141/2021-2022 | BP-2021-22-356 | 08/02/2022 | 0 | M/S. D.K.H.CONSTRUCTION | 6 | 0 | 0
2088 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric quotation for Debra Water Supply Scheme T/W-(Ref. ID - 204024559) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00546/2023-2024 | BP-2023-24-287 | 31/08/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 2.87 | 0 | 0
2089 | Midnapore Division | Midnapur Mechanical Sub Division-I | Supply of different material for Debra W/S Scheme. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00742/2022-2023 | BP-2022-23-359 | 01/02/2023 | 0 | GOBINDA MAITY | 4.64 | 0 | 0
2090 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying Distribution pipe line under JJM with allied work for Trilochanpur PWSS in Debra block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000008/2024-2025 | 1902/MD | 20/06/2024 | 90 | ASHIM KUMAR DEY | 308.72 | 0 | 0
2091 | Midnapore Division | Midnapur Mechanical Sub Division-I | Supply of CIDF valves and Jeffy Coupler for Augumentation of Debra and its adjoining Mouzas W/S Scheme under Debra Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte.(Sl.No. -01) | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000083/2022-2023 | 256/AE/KSD | 20/05/2022 | 15 | GOBINDA MAITY | 4.64 | 0 | 0
2092 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 1 No. 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site, 1 No. 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room without W.C. & Bath for 2nd Tube Well site and Laying of rising main & interconnection including supply of CIDF valves for Augmentation of Debra & its adjoining mouzas W/S Scheme of Debra Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000380/2022-2023 | 1963/MD | 20/09/2022 | 60 | DEBASISH DOGRA | 15.62 | 0 | 100
2093 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of boundary wall & allied works for Head Work site, 2nd Tube well site & 3rd Tube well site and Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room including W.C. for 3rd Tube well site for Augmentation of Debra PWSS within Debra Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000426/2024-2025 | 312/MD | 29/01/2025 | 240 | R. CONSTRUCTION | 24.48 | 0 | 60
2094 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Debra (Block- Debra) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001026/2021-2022 | 1616/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.48 | 0 | 0
2095 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Debra (Block- Debra) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001027/2021-2022 | 1617/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.16 | 0 | 0
2096 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000024/2021-2022 | 2432/MD | 29/11/2022 | 0 | Resource Division | 60.26 | 0 | 0
2097 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000032/2021-2022 | 2277/MD | 31/12/2021 | 0 | Resource Division | 18.73 | 0 | 0
2098 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Augmentation of Ground Water Based Piped Water Supply Scheme for Debra to Accommodate FHTC, Block - Debra. District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/000463/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 17.82 | 0 | 0
2099 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Madpur PWSS, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000183/2021-2022 | 1465/MD | 07/09/2021 | 1393 | DULAL CHANDRA DAS | 96.74 | 0 | 0
2100 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting to accommodate FHTC under JJM in Purulda PWSS, Block: - Dantan-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II) | ORD/000186/2021-2022 | 1466/MD | 07/09/2021 | 1474 | BANERJEE CONSTRUCTION | 90.08 | 0 | 15
2101 | Midnapore Division | Midnapur Mechanical Sub Division-I | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00239/2022-2023 |  | 31/01/2023 | 0 | BADAL CHANDRA BERA | 0.63 | 0 | 0
2102 | Midnapore Division | Midnapur Mechanical Sub Division-I | Professional fee bill for the Registration of Land under W.B registration rules 1962, at D.S.R-I, Midnapore for below mention details. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | BILL/00245/2022-2023 |  | 01/02/2023 | 0 | BADAL CHANDRA BERA | 0.07 | 0 | 0
2103 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
2104 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Mirjapur, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000857/2021-2022 | 421/MD | 04/03/2022 | 150 | A R ENTERPRISE | 17.21 | 0 | 90
2105 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000008/2021-2022 | 2119/MD | 13/12/2021 | 0 | Resource Division | 0.31 | 0 | 0
2106 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Mirjapur mouzas. Block - Sabang. District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000453/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.31 | 0 | 0
2107 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001694/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.31 | 0 | 0
2108 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza ¿ Haripura, Block ¿ Sabang, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000689/2021-2022 | 286/MD | 15/02/2022 | 150 | SAI TUBE CO. | 34.13 | 0 | 100
2109 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000004/2021-2022 | 2113/MD | 13/12/2021 | 0 | Resource Division | 1.04 | 0 | 0
2110 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Haripura mouzas. Block - Sabang. District - Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000452/2022-2023 |  | 11/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.04 | 0 | 0
2111 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001696/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.04 | 0 | 0
2112 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001821/2021-2022 | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 4.1 | 0 | 0
2113 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Fate Chak, Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000629/2021-2022 | 182/MD | 01/02/2022 | 1065 | MASUM ALI KHAN | 21.15 | 0 | 100
2114 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000010/2021-2022 | 2117/MD | 13/12/2021 | 0 | Resource Division | 0.67 | 0 | 0
2115 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Ground Based Mini Piped Water Supply Scheme for Fate Chak mouzas. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000450/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.67 | 0 | 0
2116 | Midnapore Division | Midnapur Mechanical Sub Division-I | For purchasing of liabilities. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001699/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 0.67 | 0 | 0
2117 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001820/2021-2022 | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.87 | 0 | 0
2118 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Khunkhunya & its adjoining mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000448/2021-2022 | 1275/MD | 05/08/2021 | 10 | GOBINDA MAITY | 1.67 | 0 | 0
2119 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza ¿ Khunkhunya, Block ¿ Sabang, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000690/2021-2022 | 287/MD | 15/02/2022 | 150 | SAI TUBE CO. | 42.01 | 0 | 100
2120 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000005/2021-2022 | 2114/MD | 13/12/2021 | 0 | Resource Division | 1.27 | 0 | 0
2121 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001701/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 1.27 | 0 | 0
2122 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001822/2021-2022 | BP-2021-22-505 | 25/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 3.66 | 0 | 0
2123 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. (Consultancy work) in connection with Proposed Mini Pipe W/S Scheme for Uttar Eral mouza of non-cover mouzas within Sabang Block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000419/2021-2022 | 1332/MD | 17/08/2021 | 10 | GOBINDA MAITY | 2.17 | 0 | 0
2124 | Midnapore Division | Midnapur Mechanical Sub Division-I | Restoration of damaged distribution system and other allied works in different locations of Single Village W/S Schemes (SVS) within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000477/2024-2025 | 480/MD | 13/02/2025 | 60 | A-PLUS | 22 | 0 | 100
2125 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uttar Eral (Zone-I), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000892/2021-2022 | 469/MD | 09/03/2022 | 150 | SUJATA CONSTRUCTION | 46.64 | 0 | 0
2126 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme for Mouza - Uttar Eral (Zone-II), Block - Sabang, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000893/2021-2022 | 470/MD | 09/03/2022 | 150 | SUJATA CONSTRUCTION | 37.67 | 0 | 0
2127 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000013/2021-2022 | 2128/MD | 14/12/2021 | 0 | Resource Division | 2.28 | 0 | 0
2128 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric quotation Chandkuri CCC? at L ttar Eral W/S Scheme i¿ui-721144 | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000381/2022-2023 |  | 02/08/2022 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0
2129 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric quotation Chandkuri CCC at Uttar Eral W/S Scheme Pin:- 721144 | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000382/2022-2023 |  | 03/08/2022 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.13 | 0 | 0
2130 | Midnapore Division | Midnapur Mechanical Sub Division-I | Jhargram Mechanical Electrical Bill. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000947/2022-2023 | 2022-23-210 | 18/08/2022 | 0 | EXECUTIVE ENGINEER, JHARGRAM MECHANICAL DIVISION, PHE DTE. | 0.25 | 0 | 0
2131 | Midnapore Division | Midnapur Mechanical Sub Division-I | For payment of liabilities. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001702/2021-2022 | BP-2021-22-445 | 08/03/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 2.28 | 0 | 0
2132 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of different dis T/W under mentioned Scheme of Sabang Block. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001829/2021-2022 | BP-2021-22-505 | 22/03/2022 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 7.98 | 0 | 0
2133 | Midnapore Division | Kharagpur Sub-Division | Construction of Sluice Valve/Air Valve/wash out valve Chamber Over the distribution pipe line at within Nonamadhachak & its adjoining mouzas water Supply Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte.(Part -I). | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000059/2022-2023 | 487/AE/KSD | 01/08/2022 | 30 | BADAL CHANDRA MAIKAP | 4.82 | 0 | 0
2134 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Nona Madhabchak PWSS Block-Sabang in the District of Paschim Medinipur. | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000411/2021-2022 | 2016/MD | 03/12/2021 | 60 | DULAL CHANDRA DAS | 101.79 | 0 | 0
2135 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate FHTC under JJM in Chakmakrampur W/S Scheme, Block: - Kharagpur-II, District: - Paschim Medinipur within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000238/2020-2021 | 1442/MD | 26/11/2020 | 180 | M/S. CARE | 89.58 | 50.8 | 0
2136 | Midnapore Division | Kharagpur Sub-Division | Retrofitting to accommodate balance FHTC under JJM in Chakmakrampur PWSS in Kharagpur-II Block in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000435/2020-2021 | 306/MD | 22/02/2021 | 45 | M/S. EL-CON | 32.11 | 0 | 0
2137 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | RTOR000104/2024-2025 | 3409/MD | 25/11/2024 | 0 | Resource Division | 12.07 | 0 | 0
2138 | Midnapore Division | Ghatal Subdivision | Preparation of D.P.R (Consultancy work) in connection with the Proposed Mini Pipe Water Supply Scheme for Mouza- Dewanchak under Dewanchak¿II Gram Panchayat of SAGY (Sanshad Adarshya Gram Yagona) within Ghatal Block under Midnapore Division, P.H.E. Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000416/2021-2022 | 1329/MD | 17/08/2021 | 10 | SIRCON ENGINEERING SERVICES | 2.34 | 0 | 0
2139 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-I), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000697/2021-2022 | 293/MD | 15/02/2022 | 150 | DIPAK KUMAR DOLAI | 42.69 | 0 | 100
2140 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-IV), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000698/2021-2022 | 294/MD | 15/02/2022 | 150 | SAMIT PAL | 39.22 | 0 | 100
2141 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-III), Block-Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000907/2021-2022 | 525/MD | 21/03/2022 | 150 | WATER LINK | 41.84 | 0 | 100
2142 | Midnapore Division | Ghatal Subdivision | Construction & Commissioning including FHTC (Civil Part) with 3 (three) months trial run for proposed Mini Pipe W/S Scheme under SAGY for Mouza- Dewanchak (Zone-II), Block - Ghatal, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000920/2021-2022 | 539/MD | 22/03/2022 | 150 | M/S. ZAMAN ENTERPRISE | 36.07 | 0 | 100
2143 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000035/2021-2022 | 2274/MD | 31/12/2021 | 0 | Resource Division | 4.04 | 0 | 0
2144 | Midnapore Division | Ghatal Subdivision | Submission of bill for cleaning head work site, supplying, fitting, fixing RCC demarcation pillers etc. of Mini pipe water supply schemes under SAGY. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000251/2022-2023 | BP-2022-23-01 | 18/04/2022 | 0 | SUBHASIS DOLAI | 0.25 | 0 | 0
2145 | Midnapore Division | Ghatal Subdivision | Submission of bill for cleaning head work site, supplying, fitting, fixing RCC demarcation pillers etc. of Mini pipe water supply schemes under SAGY. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000252/2022-2023 | BP-2022-23-02 | 18/04/2022 | 0 | SUBHASIS DOLAI | 0.42 | 0 | 0
2146 | Midnapore Division | Ghatal Subdivision | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000441/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 4.04 | 0 | 0
2147 | Midnapore Division | Ghatal Subdivision | Purchasing of materials for the ground Based Mini Piped Water Supply Scheme for Dewanchak mouza under SAGY. Block - Ghatal, GP - Dewanchak-II, PS - Ghatal, Dist.- Paschim Medinipur. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/000444/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 4.04 | 0 | 0
2148 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 125mm X 80 mm. dia. & 138 Mtr. Depth, Tubewell including installation of pumping machinery and accessories etc at Datan Headwork site in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000061/2022-2023 | 488/AE/KSD | 01/08/2022 | 30 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 2.5 | 0 | 0
2149 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 900 Cum and staging height 20.00 mtr. & FHTC under JJM with allied work for Augmentation of Datan and its adjoining mouzas W/S Scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000130/2022-2023 | 1364/MD | 08/07/2022 | 180 | CONCORD ENGINEERING | 1162.81 | 0 | 60
2150 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R. in connection with the Functional Household Tap Connection of existing PWSS (Daspur, Keshiary, Debra & Dantan in various blocks) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000152/2021-2022 | 951/MD | 17/06/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.77 | 0 | 100
2151 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Dantan W/S Scheme with in Datan-I Block under Midnapore Division, P.H.E. Dte. [Allotted for Sinking of 2 (Nos.) of Tube wells i.e. 50% of the total works] (Part-2/2) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000569/2022-2023 | 119/MD | 10/01/2023 | 30 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.67 | 0 | 100
2152 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Dantan W/S Scheme with in Datan-I Block under Midnapore Division, P.H.E. Dte. [Allotted for Sinking of 2 (Nos.) of Tube wells i.e. 50% of the total works] (Part-1/2) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000585/2022-2023 | 231/MD | 17/01/2023 | 30 | ANNAPURNA TUBEWELL WORKS | 20.67 | 0 | 100
2153 | Midnapore Division | Midnapur Mechanical Sub Division-I | Hiring charges of Bharat Stage ¿ III Diesel Indigo ECS Car / Motor Cabs (Luxury Taxi) having contract Carriage permit from the Regional Transport Authority valid for the State of West Bengal not older than 5 years from the date of 1st Registration on monthly hire rate basis for the period from 15.02.2022 to 14.02.2023(12 months) for the office of the Assistant Engineer, RWS Midnapore Sub-Division, P.H.E. Dte. The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, fees etc. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000986/2021-2022 | 28/RWS/MID | 11/02/2022 | 12 | S.K. CONSTRUCTION | 1.52 | 0 | 0
2154 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Dantan (Block- Dantan-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001024/2021-2022 | 1614/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3 | 0 | 0
2155 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Dantan (Block- Dantan-I) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001025/2021-2022 | 1615/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.97 | 0 | 0
2156 | Midnapore Division | Midnapur Mechanical Sub Division-I | Round the Clock Guarding Arrangements to protect the Govt. properties/materials etc. at Dantan Store within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [ for the period 01.02.2022 to30.11.2022] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001042/2021-2022 | 48./AE/KSD | 31/01/2022 | 303 | M/S. OXFORD SECURITY SERVICE | 4.58 | 0 | 0
2157 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000012/2022-2023 | 48/MD | 06/01/2023 | 0 | Resource Division | 48.12 | 0 | 0
2158 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000131/2022-2023 | 395/MD | 06/02/2023 | 0 | Resource Division | 16.56 | 0 | 0
2159 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000144/2022-2023 | 515/MD | 20/02/2023 | 0 | Resource Division | 48.12 | 0 | 0
2160 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000291/2023-2024 | 5251/MD | 21/11/2023 | 0 | Resource Division | 95.87 | 0 | 0
2161 | Midnapore Division | Midnapur Mechanical Sub Division-I | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Dantan, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001392/2021-2022 | BP-2021-22-382 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.87 | 0 | 0
2162 | Midnapore Division | Midnapur Mechanical Sub Division-I | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Dantan, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001394/2021-2022 | BP-2021-22-384 | 18/02/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.45 | 0 | 0
2163 | Midnapore Division | Midnapur Mechanical Sub Division-I | Hire and labour charges for staging and scaffolding, bamboo barricading and removal of rubbish for dismantling of existing OHR (Capacity 1,00,000 Gallon) at Head work Site of Dantan Water Supply Scheme within Dantan-I Block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001737/2021-2022 | BP-2021-22-477 | 16/03/2022 | 0 | BISWAJIT BAG | 8.57 | 0 | 0
2164 | Midnapore Division | Kharagpur Sub-Division | Augmentation of Ground water based piped water supply scheme for Chaupanya to Accommodate FHTC under JJM under Kharagpur-II Block in Paschim Medinipur Districct under Medinipur Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000519/2022-2023 | 2575/MD | 16/12/2022 | 966 | M/S. A.R. ENTERPRISE. | 116.89 | 0 | 100
2165 | Midnapore Division | Kharagpur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation / Augmentation of existing Chaupanya PWSS within Kharagpur-II Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001010/2021-2022 | 520/MD | 17/03/2022 | 10 | SIRCON ENGINEERING SERVICES | 2.7 | 0 | 100
2166 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000074/2022-2023 | 90/MD | 10/01/2023 | 0 | Resource Division | 21.98 | 0 | 0
2167 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary wall & Providing Functional Household Tap Connection (15,503 Nos.) including 2 years Operation & Maintenance for Baragarh, Benya, Jalimanda, Malihati, Brindabanpur, Satyapur, Nijpapan, Ashari, Radha Kantapur, Chak Narsingha and Bar Jhikuria Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000205/2023-2024 | 2821/MD | 07/08/2023 | 791 | GOBINDA MAITY | 4353.07 | 0 | 25
2168 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000046/2023-2024 | 1198 | 26/04/2023 | 0 | Resource Division | 25.26 | 0 | 0
2169 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 65
2170 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
2171 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000008/2023-2024 | 1149/MD | 25/04/2023 | 0 | Resource Division | 16.14 | 0 | 0
2172 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
2173 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000103/2023-2024 | 1239/MD | 27/04/2023 | 0 | Resource Division | 20.36 | 0 | 0
2174 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000104/2023-2024 | 1240/MD | 27/04/2023 | 0 | Resource Division | 27.19 | 0 | 0
2175 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7,515 Nos.) including 2 years operation & maintenance For BARAGOPAL, DURIA, GAHIRA & RAIPUR Pipe Water Supply Scheme within NARAYANGARH Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000239/2023-2024 | 3048/MD | 23/08/2023 | 975 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2197.07 | 0 | 33
2176 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- (1) Raipur (JL.- 452, Plot-926), (2) Asti (JL.- 706, Plot-496/850), (3) Babalpur (JL.- 350, Plot-876/906), (4) Bahurupa (JL.- 268, Plot-2137), (5) Barakalanki (JL.- 508, Plot-838/1168), (6) Bargopal (JL.- 480, Plot-228/620), (7) Duria (JL.- 583, Plot-686/1639), (8) Gahira (JL.- 727, Plot-1275/1539), (9) Gama (JL.- 545, Plot-532), (10) Govindapur Brahman Saran (JL.- 254, Plot-531/538), (11) Jamuna (JL.- 223, Plot-203), (12) Khursi (JL.- 601, Plot-701/942), (13) Pakurseni (JL.- 520, Plot-608/687), (14) Shuja (JL.- 403, Plot-111/751) & (15) Tutranga (JL.- 671, Plot-897) | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000597/2022-2023 | 396/MD | 02/02/2023 | 90 | JADAVPUR UNIVERSITY | 71.69 | 0 | 94
2177 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Kharagpur Sub Division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000117/2024-2025 | 3453/MD | 25/11/2024 | 0 | Resource Division | 9.23 | 0 | 0
2178 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000137/2023-2024 | 1253/MD | 28/04/2023 | 0 | Resource Division | 19.95 | 0 | 0
2179 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000020/2023-2024 | 1152/MD | 25/04/2023 | 0 | Resource Division | 18.15 | 0 | 0
2180 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000064/2023-2024 | 1213/MD | 27/04/2023 | 0 | Resource Division | 22.26 | 0 | 0
2181 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 150 Cum & 100 Cum Capacity R.C.C Over Head Reservoir (Intze type with solid raft) with laying rising main, distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (1904 Nos) including 2 years operation & maintenance For Chak Bajit and Kankara Shibram Pipe Water Supply Scheme within Debra Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000387/2023-2024 | 5061/MD | 26/10/2023 | 638 | ANIRUDDHA BAG | 561.96 | 0 | 75
2182 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000217/2023-2024 | 1514/MD | 12/05/2023 | 0 | Resource Division | 21.12 | 0 | 0
2183 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000085/2023-2024 | 1294/MD | 28/04/2023 | 0 | Resource Division | 25.64 | 0 | 0
2184 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000092/2023-2024 | 1291/MD | 28/04/2023 | 0 | Resource Division | 29.16 | 0 | 0
2185 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 846 | GOBINDA MAITY | 1960.6 | 0 | 65
2186 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
2187 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000010/2023-2024 | 1147/MD | 25/04/2023 | 0 | Resource Division | 14.87 | 0 | 0
2188 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000021/2023-2024 | 1157/MD | 25/04/2023 | 0 | Resource Division | 25.71 | 0 | 0
2189 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
2190 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000106/2023-2024 | 1298/MD | 28/04/2023 | 0 | Resource Division | 23.27 | 0 | 0
2191 | Midnapore Division | Ghatal Subdivision | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,690 Nos.) under JJM with allied work for Gopmahal PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000637/2022-2023 | 555/MD | 22/02/2023 | 180 | ASHIM KUMAR DEY | 353.2 | 0 | 15
2192 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Gopmahal urf Monaharpur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000659/2022-2023 | 1765/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.05 | 0 | 100
2193 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000033/2024-2025 | 3360/MD | 25/11/2024 | 0 | Resource Division | 4.77 | 0 | 0
2194 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000287/2023-2024 | 4059/MD | 12/10/2023 | 0 | Resource Division | 23.42 | 0 | 0
2195 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000072/2023-2024 | 1216/MD | 27/04/2023 | 0 | Resource Division | 21.29 | 0 | 0
2196 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000153/2023-2024 | 1303/MD | 28/04/2023 | 0 | Resource Division | 32.22 | 0 | 0
2197 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 200 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (837 nos.) under JJM with allied work including supply of all labour & materials for Chakmaoa & its adjoining mouzas PWSS within Kharagpur-II Block including 02 (Two) Years Operation & Maintenance under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000007/2024-2025 | 1848/MD | 13/06/2024 | 540 | DIPAK KUMAR BAKLY | 264.73 | 0 | 15
2198 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) Nos. Tube well for Chakmaoa & its adjoining mouzas PWSS in Kharagpur-II block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000112/2023-2024 | 2513/MD | 18/07/2023 | 30 | FIROJ KHAN | 16.41 | 0 | 100
2199 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Kharagpur Sub-Division(KGP-II),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000180/2023-2024 | 1361/MD | 02/05/2023 | 0 | Resource Division | 20.15 | 0 | 0
2200 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Chaksadi & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000655/2022-2023 | 1753/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.35 | 0 | 100
2201 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000031/2024-2025 | 3357/MD | 25/11/2024 | 0 | Resource Division | 10.72 | 0 | 0
2202 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000058/2022-2023 | 69/MD | 09/01/2023 | 0 | Resource Division | 22.68 | 0 | 0
2203 | Midnapore Division | Midnapur Sadar Sub-Division | Construction of 200 Cum capacity R.C.C. Over Head Reservoir over Raft Foundation works with Laying rising main, Distribution system, Sinking of Tube Well, Pump House, Soil investigation, Boundary Wall & Providing Functional Household Tap Connection (1538 Nos.) including Two years operation & maintenance for Gohaldanga Pipe Water Supply Scheme within Garbeta-II Block under Medinipur Sadar Sub-Division of Midnapore Division, PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000071/2023-2024 | 2152/MD | 08/06/2023 | 910 | M/S. D.C.M. CONSTRUCTION | 454.46 | 0 | 40
2204 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
2205 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000234/2023-2024 | 1522/MD | 12/05/2023 | 0 | Resource Division | 10.33 | 0 | 0
2206 | Midnapore Division | Ghatal Subdivision | Laying distribution pipe line & Pump House under JJM with allied work for Hemantapur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000082/2023-2024 | 2429/MD | 13/07/2023 | 538 | JIT ENTERPRISE | 31.13 | 0 | 100
2207 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 45 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 100
2208 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000137/2022-2023 | 410/MD | 07/02/2023 | 0 | Resource Division | 7.2 | 0 | 0
2209 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000140/2022-2023 | 410/MD | 07/02/2023 | 0 | Resource Division | 7.2 | 0 | 0
2210 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations for different W/S Schemes within Dantan-I (7 Nos. PWSS), Dantan-II (7 Nos. PWSS) & Debra (7 Nos. PWSS) blocks in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000531/2022-2023 | 2192/MD | 01/11/2022 | 90 | JADAVPUR UNIVERSITY | 100.36 | 0 | 90
2211 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000109/2022-2023 | 210/MD | 16/01/2023 | 0 | Resource Division | 18.39 | 0 | 0
2212 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000126/2024-2025 | 3462/MD | 25/11/2024 | 0 | Resource Division | 11.14 | 0 | 0
2213 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000126/2023-2024 | 1318/MD | 28/04/2023 | 0 | Resource Division | 43.67 | 0 | 0
2214 | Midnapore Division | RWS Midnapur Sub-Division | Sinking of 2 (Two) Nos. Tube well for Augmentation of Nayagram & its adjoining mouzas PWSS in Midnapore Sadar block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000115/2023-2024 | 2516/MD | 18/07/2023 | 30 | MIDNAPUR PIPE CONCERN | 23.44 | 0 | 55
2215 | Midnapore Division | RWS Midnapur Sub-Division | Laying distribution pipe line, Rising main, Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000178/2023-2024 | 2718/MD | 31/07/2023 | 179 | MIDNAPUR PIPE CONCERN | 112.05 | 0 | 40
2216 | Midnapore Division | RWS Midnapur Sub-Division | Construction of OHR (250 cum) & Accommodate FHTC (200 Nos.) under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000178/2024-2025 | 3163/MD | 05/10/2024 | 180 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 91.94 | 0 | 0
2217 | Midnapore Division | RWS Midnapur Sub-Division | Laying distribution pipeline under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000296/2023-2024 | 3966/MD | 05/10/2023 | 45 | AJIJUR RAHAMAN MALLICK | 24.77 | 0 | 60
2218 | Midnapore Division | RWS Midnapur Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing (i) Barisha PWSS within Pingla block & (ii) Nayagram PWSS within Midnapore Sadar Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000497/2022-2023 | 2064/MD | 30/09/2022 | 15 | GOBINDA MAITY | 7.34 | 0 | 0
2219 | Midnapore Division | RWS Midnapur Sub-Division | Accommodate FHTC (126 Nos.), Construction of Boundary wall, Switch Room under JJM with allied work for Augmentation of Nayagram & its adjoining mouzas W/S Scheme in Midnapore Sadar block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000634/2023-2024 | 5563/MD | 26/12/2023 | 60 | MODERN CONSTRUCTION | 18.35 | 0 | 0
2220 | Midnapore Division | RWS Midnapur Sub-Division | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000186/2023-2024 | 1395/MD | 03/05/2023 | 0 | Resource Division | 15.86 | 0 | 0
2221 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 450 (Intze type with pile foundation) & 250 & 400 cum OHRs (Intze type with solid raft) & Accommodate FHTC (6,370 Nos.) including Two years O&M under JJM with allied work for (1) Gokulpur (Zone-I,II & III ) and (2) Risa & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | ORD/000094/2023-2024 | 2466/MD | 14/07/2023 | 1009 | GOBINDA MAITY | 1715.83 | 0 | 30
2222 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | RTOR000051/2022-2023 | 67/MD | 09/01/2023 | 0 | Resource Division | 36.02 | 0 | 0
2223 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE/Midnapur Mechanical Sub-Division-I,JE3 Kharagpur Sub-division | RTOR000081/2024-2025 | 3432/MD | 25/11/2024 | 0 | Resource Division | 13.47 | 0 | 0
2224 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-II),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000112/2023-2024 | 1246 | 27/04/2023 | 0 | Resource Division | 4.78 | 0 | 0
2225 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Garbeta-III),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000071/2023-2024 | 1215/MD | 27/04/2023 | 0 | Resource Division | 18.54 | 0 | 0
2226 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
2227 | Midnapore Division | Kharagpur Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation at 3 Nos. of locations adjacent to the Bara Mahanpur of Narayangarh block in Paschim Medinipur district under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000734/2022-2023 | 708/MD | 06/03/2023 | 21 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0
2228 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000226/2023-2024 | 1484 | 10/05/2023 | 0 | Resource Division | 24.73 | 0 | 0
2229 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000150/2023-2024 | 1269/MD | 28/04/2023 | 0 | Resource Division | 20.93 | 0 | 0
2230 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000157/2023-2024 | 1305/MD | 28/04/2023 | 0 | Resource Division | 1.8 | 0 | 0
2231 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Maharajpur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000654/2022-2023 | 1752/MD | 24/08/2022 | 20 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.95 | 0 | 100
2232 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000036/2024-2025 | 3363/MD | 25/11/2024 | 0 | Resource Division | 13.44 | 0 | 0
2233 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Ghatal Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000054/2022-2023 | 60/MD | 09/01/2023 | 0 | Resource Division | 36.92 | 0 | 0
2234 | Midnapore Division | Jhargram Sub-Division | Retrofitting to accommodate FHTC under JJM in Ramgarh (Zone-I & II) PWSS of Binpur-I Block under Jhargram Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | ORD/000200/2020-2021 | 1403/MD | 26/11/2020 | 180 | ASIS KUMAR SARANGI | 76.93 | 46.49 | 1
2235 | Midnapore Division | Jhargram Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000271/2021-2022 | 8443117 | 31/05/2021 | 0 | NABOGOPAL ADHIKARI | 0.06 | 0 | 0
2236 | Midnapore Division | Jhargram Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000272/2021-2022 | 8443117 | 31/05/2021 | 0 | RINTU SAMANTA | 0.11 | 0 | 0
2237 | Midnapore Division | Jhargram Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000273/2021-2022 | 8443117 | 31/05/2021 | 0 | PARTHA PRATIM PAL | 0.06 | 0 | 0
2238 | Midnapore Division | Jhargram Sub-Division | Bill for FHTC data entry in IMIS in the District of Paschim Medinipur and Jhargram under Midnaproe Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000274/2021-2022 | 8443117 | 31/05/2021 | 0 | SANDIP MANNA | 0.04 | 0 | 0
2239 | Midnapore Division | Jhargram Sub-Division | RETROFITTING TO ACCOMMODATE FHTC UNDER JJM IN RAMGARH (ZONE-I/II)PWSS | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000614/2021-2022 | 844311 | 02/08/2021 | 0 | ASIS KUMAR SARANGI | 1.79 | 0 | 0
2240 | Midnapore Division | Jhargram Sub-Division | DATA ENTRY FOR FHTC | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000847/2021-2022 | 8443209 | 27/09/2021 | 0 | ANIRBAN CHAKRABORTY | 0.12 | 0 | 0
2241 | Midnapore Division | Jhargram Sub-Division | DATA ENTRY FOR FHTC | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000848/2021-2022 | 8443209 | 27/09/2021 | 0 | GANESH CH NANDY | 0.22 | 0 | 0
2242 | Midnapore Division | Jhargram Sub-Division | DATA ENTRY FOR FHTC | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/000849/2021-2022 | 8443209 | 27/09/2021 | 0 | SOVANDEB MANNA | 0.03 | 0 | 0
2243 | Midnapore Division | Jhargram Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001401/2020-2021 | 8443457 | 26/03/2021 | 0 | SOVANDEB MANNA | 0.17 | 0 | 0
2244 | Midnapore Division | Jhargram Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001402/2020-2021 | 8443357 | 26/03/2021 | 0 | NABOGOPAL ADHIKARI | 0.12 | 0 | 0
2245 | Midnapore Division | Jhargram Sub-Division | Bill of FHTC data in IMIS in the district of Paschim Medinipur and Jhargram under Midnapore Division, PHE Dte. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001403/2020-2021 | 8443457 | 26/03/2021 | 0 | SIDDHESWAR BAG | 0.2 | 0 | 0
2246 | Midnapore Division | Jhargram Sub-Division | FHTC imis data entry. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001644/2021-2022 | 8443206 | 26/03/2022 | 0 | ANIRBAN CHAKRABORTY | 0.15 | 0 | 0
2247 | Midnapore Division | Jhargram Sub-Division | FHTC imis data entry. | Assistant Engineer, Jhargram Sub-Division | Junior Engineer-III | VCH/001645/2021-2022 | 8443206 | 26/03/2022 | 0 | SHRABONTI BERA | 0.14 | 0 | 0
2248 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric Quation for Tanua Bandh mini PWSS Tube well-I in connection Mohanpur CCC. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00005/2023-2024 | BP-2023-24-14 | 24/04/2023 | 0 | EXECUTIVE ENGINEER,MIDNAPORE MECHANICAL DIVISION, PHE DTE. | 1.98 | 0 | 0
2249 | Midnapore Division | Midnapur Mechanical Sub Division-I | Electric Quation for Tanua Bandh PWSS Tube well-II in connection Mohanpur CCC. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | BILL/00010/2023-2024 | BP-2023-24-13 | 24/04/2023 | 0 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 1.9 | 0 | 0
2250 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 2 (Two) Nos. 300 X 200 mm dia. X 220 Mtr. Depth deep tube well by Direct Rotary Method for Head Work site & 2nd Tube well site of Tanuya W/S Scheme with in Mohanpur block under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000012/2022-2023 | 609/MD | 04/04/2022 | 15 | TAPAS KUMAR GIRI | 21.93 | 0 | 100
2251 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 5.40 Mtr. X 3.60 Mtr. Switch Room cum Chlorine Room with W.C. & Bath for Head Works Site under Tanuya W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type - A) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000045/2023-2024 | 981/MD | 10/04/2023 | 60 | BANERJEE CONSTRUCTION | 5.22 | 0 | 90
2252 | Midnapore Division | Midnapur Mechanical Sub Division-I | Supply & delivery of different dia. C.I.D. F. Sluice Valves for laying of Distribution main pipeline for Tanuya Piped Water Supply Scheme within Mohanpur Block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. In Paschim Medinipur District. (Sl.No.-03) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000086/2022-2023 | 313/AE/KSD | 10/06/2022 | 15 | ASHOK BANERJEE | 3.24 | 0 | 0
2253 | Midnapore Division | Midnapur Mechanical Sub Division-I | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room with out W.C. & Bath for Second Tube Well Site under Tanuya W/S Scheme within Midnapore Division, PHE Dte. (Considering G.L. 300 mm below road level) (Type -A) | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000238/2022-2023 | 543/AE/KSD | 23/08/2022 | 30 | PRITI ENTERPRISE | 2.8 | 0 | 0
2254 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of rising main including interconnection for Tanuya & its adjoining mouzas W/S Scheme within Mohanpur block under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000373/2024-2025 | 48/MD | 07/01/2025 | 45 | AJITESH ACHARJEE | 6.8 | 0 | 0
2255 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying distribution pipe line, Soil test and Construction of R.C.C. Elevated Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied works (Pile Foundation) including Providing FHTC of TANUYA & its adjoining mouzas Water Supply Scheme within Mohanpur Dev. Block in the district of Paschim Medinipur under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000536/2021-2022 | 33/MD | 07/01/2022 | 180 | BANERJEE CONSTRUCTION | 473.08 | 0 | 95
2256 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000005/2022-2023 | `2430/MD | 29/11/2022 | 0 | Resource Division | 58.77 | 0 | 0
2257 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000037/2021-2022 | 149/MD | 28/01/2022 | 0 | Resource Division | 13.62 | 0 | 0
2258 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000129/2024-2025 | 3465/MD | 25/11/2024 | 0 | Resource Division | 15.27 | 0 | 0
2259 | Midnapore Division | Midnapur Mechanical Sub Division-I | Purchasing of materials for the Tanuya Piped Water Supply Scheme. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | VCH/000443/2022-2023 |  | 10/08/2022 | 0 | EXECUTIVE ENGINEER,RESOURCES DIVISION PHE DTE. | 13.62 | 0 | 0
2260 | Midnapore Division | Midnapur Mechanical Sub Division-I | Route survey & way leave permission along & across of National Highway in Murakata PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000503/2024-2025 | 586/MD | 03/03/2025 | 21 | DONA ASSOCIATES | 8.74 | 0 | 0
2261 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000128/2023-2024 | 1324/MD | 28/04/2023 | 0 | Resource Division | 30.06 | 0 | 0
2262 | Midnapore Division | Ghatal Subdivision | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Lakshipur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000089/2022-2023 | 665/MD | 08/04/2022 | 20 | SIRCON ENGINEERING SERVICES | 4.89 | 0 | 100
2263 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,522 Nos.) under JJM including Two years O&M with allied work for Lakshipur PWSS in Chandrakona-I Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000264/2023-2024 | 3238/MD | 11/09/2023 | 928 | UNIQUE AGENCY | 619.92 | 0 | 72
2264 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000007/2024-2025 | 3328/MD | 25/11/2024 | 0 | Resource Division | 9.41 | 0 | 0
2265 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Ghatal Sub-Division(CK-I),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000283/2023-2024 | 4055/MD | 12/10/2023 | 0 | Resource Division | 42.67 | 0 | 0
2266 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000154/2023-2024 | 1301/MD | 28/04/2023 | 0 | Resource Division | 34.69 | 0 | 0
2267 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 960 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 0 | 41
2268 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE1 Kharagpur Sub-division,Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I | RTOR000237/2023-2024 | 1531/MD | 12/05/2023 | 0 | Resource Division | 73.62 | 0 | 0
2269 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube well, Laying distribution pipe line, Pump House, Soil investigation, Construction of 250 CuM OHR (Pile Foundation) & Accommodate FHTC (33 Nos.) under JJM with allied work for Augmentation Keot Khalisa PWSS in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000050/2024-2025 | 46/MD | 07/01/2025 | 180 | SAI TUBE CO. | 177.4 | 0 | 0
2270 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Keot Khalisha, Block - Mohanpur) to be Retrofitting under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001469/2020-2021 | 520/MD | 08/03/2021 | 10 | RISHAN ENGINEERING CONSULTANCY | 0.82 | 0 | 100
2271 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000203/2023-2024 | 1424/MD | 04/05/2023 | 0 | Resource Division | 8.94 | 0 | 0
2272 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of Tube Well, Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 200 Cum & 300 Cum OHR (Intze type with Solid raft/ Pile Foundation) & Accommodate FHTC (6,605 Nos.) including Two years O&M under JJM with allied work for Jarisai PWSS (Zone-I & Zone-II) & Kashida (Zone-I & Zone-II) with in Mohanpur Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000466/2023-2024 | 5360/MD | 30/11/2023 | 673 | GOBINDA MAITY | 2125.38 | 0 | 46
2273 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jarisai & its adjoining Mouzas PWSS, Block - Mohanpur under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000760/2022-2023 | 1115/MD | 09/06/2022 | 20 | ENVIROTECH SOLUTIONS | 1.61 | 0 | 100
2274 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000211/2023-2024 | 1463 | 08/05/2023 | 0 | Resource Division | 9.68 | 0 | 0
2275 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Mohanpur),Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000257/2023-2024 | 2005/MD | 16/05/2023 | 0 | Resource Division | 34.25 | 0 | 0
2276 | Midnapore Division | RWS Midnapur Sub-Division | Retrofitting of Manidaha PWSS to accommodate FHTC in Midnapore Sadar block under Midnapore Division, P.H.E. Dte. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000053/2022-2023 | 873/MD | 10/05/2022 | 1146 | DIPAK KUMAR BAKLY | 46.8 | 0 | 60
2277 | Midnapore Division | RWS Midnapur Sub-Division | Laying distribution pipe line, soil test and Construction and Commissioning of RCC Over Head Reservoir (Intze type with solid raft) of capacity 350 CuM and staging height 20 mtr. as per approved drawing (No:- PC-I /OHR /12/2012 ) with allied works for Manidaha Water Supply Scheme within Medinipur Sadar Block including supply of all labour & materials under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division | JE RWS Sadar Sub-Division(Sadar Block) | ORD/000503/2021-2022 | 2245/MD | 28/12/2021 | 180 | DIPAK KUMAR BAKLY | 230.53 | 0 | 70
2278 | Midnapore Division | Kharagpur Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Rising main, Pump House, Boundary wall, Soil investigation, Construction of 450 (Intze type with pile foundation) & 250 & 400 cum OHRs (Intze type with solid raft) & Accommodate FHTC (6,370 Nos.) including Two years O&M under JJM with allied work for (1) Gokulpur (Zone-I,II & III ) and (2) Risa & its adjoining mouzas W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000094/2023-2024 | 2466/MD | 14/07/2023 | 1009 | GOBINDA MAITY | 1715.83 | 0 | 30
2279 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000052/2022-2023 | 66/MD | 09/01/2023 | 0 | Resource Division | 54.01 | 0 | 0
2280 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | RTOR000090/2024-2025 | 3442/MD | 25/11/2024 | 0 | Resource Division | 25.77 | 0 | 0
2281 | Midnapore Division | Gopiballavpur Sub Division | Material Requisition To Resource Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | RTOR000002/2022-2023 | 1044/MD | 01/06/2022 | 0 | Resource Division | 157.59 | 0 | 0
2282 | Midnapore Division | Gopiballavpur Sub Division | Material Requisition To Resource Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | RTOR000018/2022-2023 | 2472/MD | 06/12/2022 | 0 | Resource Division | 61.6 | 0 | 0
2283 | Midnapore Division | Gopiballavpur Sub Division | Material Requisition To Resource Division | Assistant Engineer,DIC(D)_MMSD(D) | JE (M),Junior Engineer-II | RTOR000039/2021-2022 | 498/MD | 15/03/2022 | 0 | Resource Division | 30.36 | 0 | 0
2284 | Midnapore Division | Ghatal Subdivision | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 500 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,144 nos.) under JJM with allied work for Suratpur PWSS in Daspur- I Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance Charge within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000506/2023-2024 | 5514/MD | 15/12/2023 | 652 | MASUM ALI KHAN | 694.39 | 0 | 30
2285 | Midnapore Division | Ghatal Subdivision | Material Requisition To Resource Division | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | RTOR000159/2023-2024 | 1282/MD | 28/04/2023 | 0 | Resource Division | 190.54 | 0 | 0
2286 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, Construction of 350 cum OHR (Intze type with raft foundation) & Accommodate FHTC (2,353 nos.) under JJM with allied work for Amlabani PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000281/2023-2024 | 3843/MD | 21/09/2023 | 905 | M/S. A.R. ENTERPRISE. | 1033.27 | 0 | 43
2287 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000053/2022-2023 | 61/MD | 09/01/2023 | 0 | Resource Division | 16.89 | 0 | 0
2288 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000056/2024-2025 | 3376/MD | 25/11/2024 | 0 | Resource Division | 14.49 | 0 | 0
2289 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000133/2023-2024 | 1256/MD | 28/04/2023 | 0 | Resource Division | 23.45 | 0 | 0
2290 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 1(one) No. 125mm X 80mm dia. & 150 Mtr. Depth Deep Tube well including construction of Community Storage Tank (2000 Ltr. Capacity) and Installation of Submersible pumping machineries etc. for Creation of drinking water source at Chandana village, vide J.L.No. -47, Plot No.-1530(near house of Dhananjoy Mandi), GP- Khajra, Block- Keshiary under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in Paschim Medinipur District. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000058/2022-2023 | 486/AE/KSD | 01/08/2022 | 30 | ASSOCIATED ENGINEERS & TRADERS | 4.41 | 0 | 0
2291 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of distribution pipeline for left out node and to provide FHTC for Augmentation of Keshiary Piped Water Supply Scheme under Keshiary block within Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000097/2024-2025 | 2844/MD | 09/09/2024 | 420 | A-PLUS | 59.9 | 0 | 50
2292 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying distribution pipe line, Soil test and Construction of R.C.C. Over Head Reservoir of capacity 200 Cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Keshiary & its adjoining mouzas Water Supply Scheme to accomodate FHTC within Keshiary Block under Kharagpur Sub-Division of Midnapore Division, P.H.E.Dte. Dist. Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000227/2022-2023 | 1734/MD | 23/08/2022 | 1292 | M/S. A.R. ENTERPRISE. | 601.47 | 0 | 80
2293 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work order Hiring of Bharat Stage - IV/VI Diesel Motor Cabs (Standard), having contract Carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Kharagpur Sub-Division, P.H.E. Dte. for the period (23.09.2024 to 31.12.2024) Vehicle No-WB 05 9394 | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000317/2024-2025 | 519/AE/KSD | 23/09/2024 | 100 | M/S. SOMNATH | 0.56 | 0 | 0
2294 | Midnapore Division | Midnapur Mechanical Sub Division-I | Cleaning the Chokage of pipe in the existing line at Keshiary PWSS under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000338/2024-2025 | 3581/MD | 06/12/2024 | 30 | MAMPI ENTERPRISE | 4.59 | 0 | 100
2295 | Midnapore Division | Midnapur Mechanical Sub Division-I | Rendering Consultancy Services for Geotechnical Investigation and Report preparation of OHR locations under (1) Augmentation of Keshiary & its adjoining mouzas W/S Scheme within Keshiary block & (2) Augmentation of Satkui & its adjoining mouzas W/S Scheme within Kharagpur-I block in Paschim Medinipur District through Jadavpur University. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000617/2022-2023 | 471/MD | 15/02/2023 | 14 | JADAVPUR UNIVERSITY | 9.56 | 0 | 100
2296 | Midnapore Division | Midnapur Mechanical Sub Division-I | Sinking of 4 (Four) nos. 250 x 150 mm dia. X 220 mtr. depth deep tube well by direct rotary method for Augmentation of Keshiary W/S Scheme with in Keshiary block under Midnapore Division, P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000620/2022-2023 | 445/MD | 13/02/2023 | 30 | KISHORE GHOSH | 41.07 | 0 | 100
2297 | Midnapore Division | Midnapur Mechanical Sub Division-I | Laying of Rising Main pipe line and construction 2 (two) nos. Pump house for Augmentation of Keshiary & its adjoining mouzas W/S Scheme under JJM within Keshiary block under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. within the District of Paschim Medinipur. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000624/2022-2023 | 449/MD | 13/02/2023 | 878 | M/S. A.R. ENTERPRISE. | 13.49 | 0 | 0
2298 | Midnapore Division | Midnapur Mechanical Sub Division-I | Extension of laying of distribution UPVC pipe line in Gopalpur village Basti of Keshiary GP Within Keshiry W/S Scheme under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000671/2021-2022 | 114/AE/KSD | 09/03/2022 | 30 | NIMAI LAL GURIA | 2.55 | 0 | 100
2299 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work order for the work Hiring of Bharat Stage- II/III / diesel motor cab (Luxury Taxi) / Maruti Omni (Standard Non-AC) having contract carriage permit from the regional transport authority for the Office of the Assistant Engineer, Kharagpur Sub- Division, P.H.E. Dte. [Period for 04.02.2022 to 20.03.2022] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000896/2021-2022 | 59/AE/KSD | 03/02/2022 | 45 | SANJIT SINHA | 0.25 | 0 | 0
2300 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Design with allied works in connection with the FHTC of existing PWSS Keshiary (Block- Keshiary) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001028/2021-2022 | 1620/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.41 | 0 | 100
2301 | Midnapore Division | Midnapur Mechanical Sub Division-I | Continuation Work Order for the work of Conducting of Route survey in connection with the FHTC of existing PWSS Keshiary (Block- Keshiary) to be Augmentation/ Rejuvenation under Midnapore Division, P.H.E Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001029/2021-2022 | 1621/MD | 21/09/2021 | 10 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.87 | 0 | 100
2302 | Midnapore Division | Midnapur Mechanical Sub Division-I | Hiring of Bharat Stage- IV/V diesel motor cab (Luxury Taxi) (Standard Non-AC) having contract carriage permit from the regional transport authority for the Office of the Assistant Engineer, Kharagpur Sub- Division, P.H.E. Dte. ( For 12 MONTH )[ Perion fro 23.03.2023 to 22.03.2024] | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001038/2022-2023 | 342/1/AE/KSD | 23/03/2023 | 366 | M/S. SOMNATH | 1.35 | 0 | 100
2303 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000022/2022-2023 | 138/MD | 11/01/2023 | 0 | Resource Division | 29.36 | 0 | 0
2304 | Midnapore Division | Midnapur Mechanical Sub Division-I | Material Requisition To Resource Division | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000275/2023-2024 | 3988/MD | 06/10/2023 | 0 | Resource Division | 29.18 | 0 | 0
2305 | Midnapore Division | Midnapur Mechanical Sub Division-I | Design with allied works in connection with the Functional Household Tap Connection of existing PWSS (Keshiary, Block - Keshiary) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001727/2021-2022 | BP-2021-22-466 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.76 | 0 | 0
2306 | Midnapore Division | Midnapur Mechanical Sub Division-I | Conducting of Route Survey in connection with the Functional Household Tap Connection of existing PWSS (Keshiary, Block - Keshiary) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE/Midnapur Mechanical Sub-Division-I,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division( Keshiary),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | VCH/001728/2021-2022 | BP-2021-22-467 | 16/03/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.24 | 0 | 0
2307 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of Tube Well, Construction of RCC OHR (250 Cum & 100 Cum Capacity), Boundary Wall, Pump House and GLR (35 Cum & 75 Cum Capacity) to accommodate FHTC (1,140 Nos) under JJM for Piped Water Supply Scheme under JJM with allied work for Augmentation of Dherua W/S Scheme in Medinipur Sadar Block under Midnapore Sadar Sub Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000016/2024-2025 | 2034/MD | 01/07/2024 | 360 | M/S. MALLIK CONSTRUCTION | 964.38 | 0 | 30
2308 | Midnapore Division | Midnapur Sadar Sub-Division | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing Dherua PWSS within Midnapore Sadar Block under Midnapore Division P.H.E. Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000494/2022-2023 | 2191/MD | 01/11/2022 | 21 | UMWELT ENGINEER PVT. LTD. | 16.52 | 0 | 100
2309 | Midnapore Division | Midnapur Sadar Sub-Division | Laying distribution pipe line, Rising Main, Pump House, Boundary Wall, Soil investigation, Construction of 350 Cum (Intze type with Pile Foundation) & Accommodate FHTC (2904 Nos.) including Two years O&M under JJM with allied work for Bajgerya & its adjoining mouzas W/S Scheme in Keshpur Block including supply of all labour & materials including 02(Two) Years Operation & Mainatanance within Midnapur Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000015/2024-2025 | 2008/MD | 28/06/2024 | 180 | M/S. EL-CON | 971.71 | 0 | 0
2310 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Tube well for Bajgerya & its adjoining mouzas PWSS in Keshpur block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. [Part-II] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000056/2024-2025 | 2579/MD | 22/08/2024 | 15 | MANNA COMPUTER | 8.3 | 0 | 0
2311 | Midnapore Division | Midnapur Sadar Sub-Division | Sinking of 1 (One) No. Tube well for Bajgerya & its adjoining mouzas PWSS in Keshpur block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. [Part-I] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000200/2023-2024 | 2814/MD | 07/08/2023 | 15 | RUPKUMAR KARMAKAR | 8.3 | 0 | 100
2312 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE RWS Sadar Sub-Division(Keshpur),Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | RTOR000273/2023-2024 | 3986/MD | 06/10/2023 | 0 | Resource Division | 33.31 | 0 | 0
2313 | Midnapore Division | Midnapur Mechanical Sub Division-I | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvenation / Augmentation of existing Bural PWSS within Sabang Block under Midnapore Division P.H.E. Dte. | AE/Midnapur Mechanical Sub-Division-I,AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang),Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/000493/2022-2023 | 2048/MD | 28/09/2022 | 21 | GOBINDA MAITY | 10.93 | 0 | 100
2314 | Midnapore Division | Midnapur Sadar Sub-Division | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 90 | JADAVPUR UNIVERSITY | 109.92 | 0 | 35
2315 | Midnapore Division | Midnapur Sadar Sub-Division | Material Requisition To Resource Division | AE Sadar Sub-division,AE/Midnapur Mechanical Sub-Division-I | JE2 Sadar Sub-division,Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | RTOR000162/2022-2023 | 1158/MD | 25/04/2023 | 0 | Resource Division | 64.6 | 0 | 0
2316 | Midnapore Division | Kharagpur Sub-Division | Construction and Commissioning of 2 Nos. O.H.R [400 CuM capacity & 300 CuM Capacity (Both Intze type with pile)] & LDS (Zone-II) for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I & II) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapur Division, PHE Dte. [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000029/2024-2025 | 2118/MD | 09/07/2024 | 480 | JAY MATA DI ENTERPRISE | 244.46 | 0 | 0
2317 | Midnapore Division | Kharagpur Sub-Division | Laying of Distribution Pipe Line and FHTC (1182 nos.) work including 2 (Two) years O&M for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapore Division, PHE Dte. [PART-D] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000030/2024-2025 | 2119/MD | 09/07/2024 | 60 | BHUWALKA DEVELOPMENTS PRIVATE LIMITED | 228.56 | 0 | 0
2318 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) Nos. 200 X 100 X 170 mtr. depth deep Tube well (Zone-II) for Proposed Mohar-Katina & its adjoining mouzas (Zone-I & II) PWSS, Block- Sabong Dist:- Paschim Medinipore under Midnapore Division PHE Dte. [PART-E] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000187/2023-2024 | 2801/MD | 07/08/2023 | 21 | MANNA COMPUTER | 13.54 | 0 | 100
2319 | Midnapore Division | Kharagpur Sub-Division | Sinking of 2 (Two) nos. 250 X 150 X 170 mtr. depth deep Tube well (Zone-I) for Proposed Mohar- Katina & its adjoining mouzas PWSS, Block- Sabong, Dist:- Paschim Medinipur under Midnapur Division, PHE Dte. [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000188/2023-2024 | 2802/MD | 07/08/2023 | 21 | MANISHIKA CONSTRUCTION | 16.89 | 0 | 50
2320 | Midnapore Division | Kharagpur Sub-Division | Construction of Pump House, Boundary wall & Accommodate FHTC (842 nos.) under JJM in (Zone-I) for Proposed Mohar-Katina (Zone-I & II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000189/2023-2024 | 2803/MD | 07/08/2023 | 60 | SHAKEEL KHAN | 64.42 | 0 | 0
2321 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line & Accommodate FHTC (400 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000190/2023-2024 | 2804/MD | 07/08/2023 | 844 | SANKAR PRASAD MAITY | 64.97 | 0 | 40
2322 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line & Accommodate FHTC (300 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000191/2023-2024 | 2805/MD | 07/08/2023 | 726 | SANKAR PRASAD MAITY | 73.64 | 0 | 50
2323 | Midnapore Division | Kharagpur Sub-Division | Construction of Pump House, Boundary wall & Accommodate FHTC (568 nos.) under JJM with allied work for Mohar-Katina (Zone-II) PWSS in Sabang block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000192/2023-2024 | 2806/MD | 07/08/2023 | 60 | NUTAN BAZAR ENGINEER,S CO-OPERATIVE SOCIETY LTD. | 48.67 | 0 | 0
2324 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line & Accommodate FHTC (200 nos.) under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang. Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000241/2023-2024 | 3051/MD | 23/08/2023 | 30 | JOY GURU TRADING | 33.64 | 0 | 0
2325 | Midnapore Division | Kharagpur Sub-Division | Laying Rising Main & distribution of Pipe line, Construction of Pump House and Boundary wall and FHTC (786 nos.) work for Proposed Mohar-Katina & its adjoining Mouzas (Zone-I) PWSS, Block- Sabong, Dist: - Paschim Medinipur under Midnapore Division, PHE Dte. [PART-C] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000286/2023-2024 | 3903/MD | 27/09/2023 | 724 | M/S. D.K.H.CONSTRUCTION | 241.34 | 0 | 75
2326 | Midnapore Division | Kharagpur Sub-Division | Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (430 nos.) including 2 (Two) years O&M under JJM with allied work for Proposed Mohar-Katina (Zone-II) PWSS in Sabang. Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000400/2023-2024 | 5098/MD | 30/10/2023 | 548 | SAI TUBE CO. | 170.59 | 0 | 40
2327 | Midnapore Division | Kharagpur Sub-Division | Material Requisition To Resource Division | AE/RWS Midnapore Sub Division | JE RWS Kharagpur Sub-Division( Sabang) | RTOR000080/2022-2023 | 199/MD | 16/01/2023 | 0 | Resource Division | 45.97 | 0 | 0
Total | [10 empty] | 494023.06 | 2684.46