## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate FHTC under JJM within Barasubarnanagar PWSS Block Contai-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000031/2020-2021 | 2107/TD | 05/11/2020 | 180 | PRANAB KUMAR DAS | 96.08 | 31.17 | 100
2 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC under JJM Bara Subarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001254/2020-2021 | 992/W | 27/03/2021 | 0 | PRANAB KUMAR DAS | 56.48 | 0 | 0
3 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IX Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000131/2020-2021 | 2657/TD | 11/01/2021 | 60 | BARH CONSTRUCTION | 54.91 | 0.22 | 100
4 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. |  |  | VCH/001047/2020-2021 | 1122/W | 30/03/2021 | 0 | BARH CONSTRUCTION | 0.69 | 0 | 0
5 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Surface Water Based W/S Scheme under Zone - IX under Tamluk Division, PHE Dte. |  |  | VCH/001195/2020-2021 | 824/W | 10/03/2021 | 0 | BARH CONSTRUCTION | 54 | 0 | 0
6 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VI(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000120/2020-2021 | 2633/TD | 05/01/2021 | 60 | JAGANNATH MAKAR | 96.81 | 193.59 | 100
7 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-II within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000231/2021-2022 | 158/W | 30/07/2021 | 0 | MAA ANANDAMAYEE | 0.34 | 0 | 0
8 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Purba Bakulda PWSS Block Panskura-I in the District of Purba Medinipur. |  |  | ORD/000033/2020-2021 | 2110/TD | 05/11/2020 | 180 | BIDHAN MONDAL | 72.9 | 0 | 100
9 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000145/2021-2022 | 70/W | 24/06/2021 | 0 | BIDHAN MONDAL | 20.84 | 0 | 0
10 | Tamluk Division |  | Re-laying of D.I./G.I./UPVC pipe line under Purba Bakulda W/S Scheme within Panskura Block damaged due to upgradation of moorum road under Tamluk Division, PHE Dte. |  |  | VCH/000214/2021-2022 | 100/W | 05/07/2021 | 0 | BIDHAN MONDAL | 12.56 | 0 | 0
11 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Purba Bakulda W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001041/2020-2021 | 724/W | 18/02/2021 | 0 | BIDHAN MONDAL | 33.98 | 0 | 0
12 | Tamluk Division |  | Charges of entry of Household data in J.J.M website alongwith Household Addhar Details entry in J.J.M. website under Tamluk Division, PHE Dte. |  |  | VCH/001053/2020-2021 | 816/W | 25/02/2021 | 0 | MISHRA ENTERPRISE | 4.85 | 0 | 0
13 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Srirampur PWSS (Part-I) Block -Tamluk in the District of Purba Medinipur. |  |  | ORD/000223/2020-2021 | 2835/TD | 05/02/2021 | 45 | ARABINDA GHOSH | 113.61 | 0 | 100
14 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000348/2021-2022 | BP-2021-22-117 | 05/10/2021 | 0 | ARABINDA GHOSH | 13.82 | 0 | 0
15 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001099/2020-2021 |  | 12/03/2021 | 0 | ARABINDA GHOSH | 100.73 | 0 | 0
16 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Srirampur W/S Scheme within Tamluk Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001264/2020-2021 | 1079/W | 30/03/2021 | 0 | ARABINDA GHOSH | 100.54 | 0 | 0
17 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Majna Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000166/2021-2022 | 1170/TD | 01/12/2021 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.34 | 4.04 | 100
18 | Tamluk Division | Contai Sub-Division | Repair and Renovation of Pump House and others allied works for OHR & 2nd Tube well site at Majna Water Supply Scheme in Contai - Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000369/2024-2025 | 3398/TD | 28/10/2024 | 30 | SUBRATA KUMAR BERA | 1.92 | 0 | 100
19 | Tamluk Division | Contai Sub-Division | Augmentation of ground water based Majna Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir of Capacity 250 cum. And staging height 20.00 mtr. With allied work including Sub Soil Investigation within Contai-I Dev. Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000403/2021-2022 | 1845/TD | 15/02/2022 | 180 | DAS ENTERPRISE | 324.35 | 284.49 | 100
20 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site( Mouza- Nayabasan ,J.L. No-294, Plot No- 319), for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for West side & North Side) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000412/2022-2023 | 344/TD | 13/05/2022 | 28 | PARTHA CONSTRUCTION | 4.84 | 3.82 | 100
21 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Majna BPHC Premises for Majna W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side & South Side) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000415/2022-2023 | 373/TD | 17/05/2022 | 28 | BIBEKANANDA DAS | 3.85 | 3.5 | 100
22 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Majna Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000661/2021-2022 | 2216/TD | 22/03/2022 | 15 | BIBEKANANDA DAS | 4.06 | 4.06 | 100
23 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by UPVC pipes with allied works due to Construction of drain by Local Panchayet of Majna and its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000748/2023-2024 | 1714/CSD | 31/08/2023 | 30 | SUBRATA KUMAR BERA | 2.66 | 0 | 100
24 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Majna PWSS within Contai -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Laying rising main and other allied works Augmentation of Majna W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000861/2022-2023 | 3217/TD | 14/03/2023 | 40 | SUBRATA KUMAR BERA | 19.54 | 0 | 0
25 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000002/2022-2023 | 82/TD | 08/04/2022 | 0 | Resource Division | 20.19 | 0 | 0
26 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000022/2021-2022 | 1264/TD | 13/12/2021 | 0 | Resource Division | 13.16 | 0 | 0
27 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000057/2021-2022 | 1902/TD | 23/02/2022 | 0 | Resource Division | 13.73 | 0 | 0
28 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000086/2021-2022 | 2217/TD | 24/03/2022 | 0 | Resource Division | 20.19 | 0 | 0
29 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 150 nos] under JJM in Dariapur PWSS [Pratappur(507,part),Haripur(508,part),Ramchak Gopalchak(509,part),Purba Bamunia(511,part), Dariapur(512,part),Daulatpur(513,part),Kazichak(514,part),Chhota Subarnanagar(515,part),Nankar Gopinathpur(516,part),Durgapur Part-IV(608,part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | ORD/000268/2020-2021 | 2921/TD | 22/02/2021 | 20 | SK. NUR ISLAM | 10.94 | 0 | 100
30 | Tamluk Division |  | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000366/2021-2022 |  | 30/09/2021 | 0 | SK. NUR ISLAM | 10.63 | 0 | 0
31 | Tamluk Division |  | Retrofitting to accomodate FHTC 150 Nos. under Dariapur PWSS within Contai-II Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000422/2021-2022 | BP-2021-22-98 | 05/10/2021 | 0 | SK. NUR ISLAM | 10.63 | 0 | 0
32 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block- Egra-I in the District of Purba Medinipur.(Phase-II). | Assistant Engineer | Junior Engineer | ORD/000033/2021-2022 | 239/TD | 23/06/2021 | 60 | FIROZ KHAN | 172.05 | 214.65 | 100
33 | Tamluk Division | Digha Sub-Division | Laying distribution system of Chirulia-Chatla & its adjoining moujas Water Supply Scheme within Egra-I Dev. Block under Digha sub-division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000261/2021-2022 | 1453/TD | 31/12/2021 | 30 | AJIT KUMAR SOM | 29.22 | 29.22 | 100
34 | Tamluk Division |  | Retrofitting to accomodate FHTC (250 nos.) under JJM in Kanakpur PWSS under Potashpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PHASE-II) |  |  | ORD/000006/2021-2022 | 684/TD | 10/09/2021 | 20 | SRIMANTA KUMAR MAITY | 22.38 | 21.15 | 100
35 | Tamluk Division |  | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Kanakpur Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000356/2024-2025 | 3319/TD | 22/10/2024 | 30 | THE GODFATHER TRADING COMPANY | 1.45 | 0 | 0
36 | Tamluk Division |  | Retrofitting to accomodate FHTC (899 nos.) under JJM in Dona Zone-II PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) |  |  | ORD/000014/2021-2022 | 690/TD | 10/09/2021 | 30 | TARUN KOLEY | 41.48 | 0 | 100
37 | Tamluk Division |  | Retrofitting to accomodate FHTC (899 Nos.) under JJM in Dona Zone - II PWSS (Balance Work) Block-Moyna under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000353/2021-2022 | BP-2021-22-106 | 05/10/2021 | 0 | TARUN KOLEY | 41.31 | 0 | 0
38 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Amtalia PWSS Block- Contai-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000018/2021-2022 | 85/TD | 11/05/2021 | 30 | ARABINDA GHOSH | 90.23 | 65.29 | 80
39 | Tamluk Division |  | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline within Nodal point 160-161, 196-197, 196-199, 161-172 & 172-174 in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-A) |  |  | ORD/000125/2021-2022 | 1005/TD | 02/11/2021 | 30 | PULAK KUMAR SAMANTA | 11.81 | 11.81 | 100
40 | Tamluk Division |  | Retrofitting to accommodate FHTC (505 Nos) (Mouza- Rankinipur, J.L. No.-135) & Relaying of damaged pipeline in Hanubhunia Mouza, J.L. No.-133, under JJM in Gholepukuria (Zone-I) PWSS (Phase-III) balance part, Block- Nandigram-II in the District of Purba Medinipur. (Part-B) |  |  | ORD/000126/2021-2022 | 1006/TD | 02/11/2021 | 30 | ZENITH CONSTRUCTION | 28.92 | 28.84 | 100
41 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in KUDI PWSS Block - Egra-I in the District of Purba Medinipur |  |  | ORD/000139/2021-2022 | 1022/TD | 02/11/2021 | 20 | KESHOB ENTERPRISE | 12.26 | 12.22 | 100
42 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Dwariberia Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000034/2022-2023 | 133/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100
43 | Tamluk Division | Haldia Sub-Division | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (456 FHTC) of Dwariberia Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000110/2024-2025 | 1904/TD | 07/06/2024 | 367 | SK. NUR ISLAM | 56.28 | 0 | 50
44 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Dwariberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000253/2022-2023 | 1045/TD | 16/08/2022 | 45 | TARUN KHATUA | 4.09 | 3.82 | 100
45 | Tamluk Division | Haldia Sub-Division | Work Order for Laying of UPVC pipe line at Dwariberia Water supply Scheme (Node point 182-182A) within Haldia Development Block under Haldia Sub-Division of Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000262/2022-2023 | 571/HSD | 17/08/2022 | 15 | TAPAN BERA | 1.57 | 1.57 | 100
46 | Tamluk Division | Haldia Sub-Division | Work order for Make approach road to access Rig Machine for Boring of Tube well at Head work site of Dwariberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000263/2022-2023 | 572/HSD | 17/08/2022 | 7 | TAPAN BERA | 1.36 | 1.36 | 100
47 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dwariberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000390/2021-2022 | 1606/TD | 14/01/2022 | 20 | RADIANT | 3.58 | 3.56 | 100
48 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (1003 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000392/2021-2022 | 1851/TD | 16/02/2022 | 40 | SUDIPTA ROY | 75.32 | 73.42 | 100
49 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (927 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000393/2021-2022 | 1852/TD | 16/02/2022 | 40 | PALCON | 74.59 | 69.74 | 100
50 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (737 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000394/2021-2022 | 1853/TD | 16/02/2022 | 40 | JAI BHARAT COMMERCIAL CORPORATION | 74.58 | 74.45 | 100
51 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000395/2021-2022 | 1854/TD | 16/02/2022 | 20 | BUNBA CONSTRUCTION | 10.38 | 10.26 | 100
52 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (22 nos) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. " (Part-M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000396/2021-2022 | 1855/TD | 16/02/2022 | 20 | TAPAN BERA | 10.79 | 10.79 | 100
53 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000397/2021-2022 | 1860/TD | 17/02/2022 | 20 | SAYAN MAITY | 4.85 | 4.82 | 100
54 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000398/2021-2022 | 1861/TD | 17/02/2022 | 20 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.8 | 4.8 | 100
55 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000399/2021-2022 | 1862/TD | 17/02/2022 | 20 | MAHAPRABHU ENTERPRISE | 4.83 | 4.63 | 100
56 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000400/2021-2022 | 1863/TD | 17/02/2022 | 20 | MODERN CONSTRUCTION | 4.85 | 4.81 | 100
57 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000401/2021-2022 | 1864/TD | 17/02/2022 | 20 | TARUN KHATUA | 4.85 | 4.84 | 100
58 | Tamluk Division | Haldia Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Dwariberia & its adjoining moujas Water Supply Scheme within Haldia Block including supply of all labour & materials under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000482/2022-2023 | 1887/TD | 24/11/2022 | 828 | MAA ANANDAMAYEE | 131.54 | 53.53 | 98
59 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dwariberia Water Supply Scheme to accommodate FHTC (101 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000526/2021-2022 | 2000/TD | 08/03/2022 | 20 | A. K. SIKDAR | 35.52 | 35.15 | 100
60 | Tamluk Division | Haldia Sub-Division | Boundary wall including land development at Headwork site of Dwariberia Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000644/2023-2024 | 2596/TD | 10/10/2023 | 506 | ELITE CONSTRUCTION | 18.69 | 0 | 1
61 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000063/2021-2022 | 1874/TD | 18/02/2022 | 0 | Resource Division | 16 | 0 | 0
62 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000082/2021-2022 | 2069/TD | 16/03/2022 | 0 | Resource Division | 16.85 | 0 | 0
63 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-B) |  | Junior Engineer | ORD/000005/2022-2023 | 59/TD | 05/04/2022 | 60 | UCON | 164.31 | 161.84 | 100
64 | Tamluk Division | RWS Tamluk Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Muradpur Water Supply Scheme under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/000187/2021-2022 | 1196/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 6.38 | 6.38 | 100
65 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-A) |  | Junior Engineer | ORD/000423/2022-2023 | 1597/TD | 18/10/2022 | 30 | G. S. CONSTRUCTION | 25.21 | 24.82 | 100
66 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of Ground Water Based Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub-Division , PHE Dte. Dist. Purba Medinipur (Part-B) |  | Junior Engineer | ORD/000424/2022-2023 | 1598/TD | 18/10/2022 | 25 | TARUN KHATUA | 10.28 | 10.16 | 100
67 | Tamluk Division | RWS Tamluk Sub-Division | Pilling with Bamboo & bullah, retaining of OHR & laying leftout portion for Muradpur PWSS & its adjoining moujas with in Chandipur Dev. Block under Tamluk Sub Division of Tamluk Division, PHE Dte. Dist. Purba Medinipur. |  | Junior Engineer | ORD/000453/2023-2024 | 1471/TD | 13/07/2023 | 40 | G. S. CONSTRUCTION | 34.18 | 0 | 50
68 | Tamluk Division | RWS Tamluk Sub-Division | Rejuvenation & Retrofitting of ground water based Muradpur PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. (Part-A) |  | Junior Engineer | ORD/000631/2021-2022 | 2214/TD | 22/03/2022 | 90 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 237.6 | 236 | 100
69 | Tamluk Division | RWS Tamluk Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000046/2021-2022 | 2346/TD | 31/03/2022 | 0 | Resource Division | 10.33 | 0 | 0
70 | Tamluk Division | RWS Tamluk Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000196/2023-2024 | 1096/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
71 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Chandibhetti Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte., Purba medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000115/2022-2023 | 593/TD | 17/06/2022 | 60 | RAJ KUMAR SINGHA | 585.56 | 564.09 | 95
72 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Chandibhetti Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000127/2022-2023 | 627/TD | 23/06/2022 | 15 | SRIMANTA KUMAR MAITY | 4.59 | 4.59 | 100
73 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur,Basudevberia,Chandivety & Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II).(Supply at Mukutshila Store). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000171/2022-2023 | 775/TD | 08/07/2022 | 15 | SRIMANTA KUMAR MAITY | 3.49 | 3.49 | 100
74 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Chandibhetti Water Supply Scheme (Mouza - Banamaliberya, JL No. - 458, Plot No. - 8) within Contai-II (Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000237/2022-2023 | 978/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.38 | 100
75 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chandiveti Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2021-2022 | 1608/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.99 | 4.29 | 100
76 | Tamluk Division | Haldia Electrical Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2, Head Work site Boundary Wall and Boundary Wall of 2nd Tubewell Site under JJM with allied work of Chandivetty PWSS within Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000344/2024-2025 | 3329/TD | 22/10/2024 | 40 | SUBHENDU HAZRA | 18.38 | 0 | 0
77 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (Boundary Wall(as per Departmental Design & Drawing) at 3rd TW Site for Augmentation of Chandibhetty PWSS in Deshapran Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Length 65.00 mtr.) For Low Land. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000471/2023-2024 | 1497/TD | 17/07/2023 | 60 | SUBHENDU HAZRA | 10.3 | 0 | 100
78 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Chandibhetti W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000725/2023-2024 | 2970/TD | 28/11/2023 | 60 | BISWA NIRMAN ENTERPRISE. | 3.73 | 0 | 100
79 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000017/2022-2023 | 405/TD | 25/05/2022 | 0 | Resource Division | 42.06 | 0 | 0
80 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000080/2022-2023 | 1268/TD | 12/09/2022 | 0 | Resource Division | 23.08 | 0 | 0
81 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000132/2022-2023 | 693/TD | 27/06/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 736.14 | 584.44 | 98
82 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tubewell of Augmentation of Junbani Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000209/2023-2024 | 473/TD | 10/05/2023 | 60 | SUBHENDU HAZRA | 3.68 | 3.32 | 100
83 | Tamluk Division | Contai Sub-Division | Continuation W/O for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2024 to 30/06/2025. (12 Months), Vehicle no.-WB-31/6974 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000215/2024-2025 | 1788/CSD | 28/06/2024 | 365 | SABITA PRADHAN | 1.49 | 0 | 0
84 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Junbani Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000221/2022-2023 | 493/CSD | 02/08/2022 | 15 | GIRI CONSTRUCTION | 2.47 | 2.47 | 100
85 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional (3rd) Tubewell of Augmentation of Junbani Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000238/2022-2023 | 979/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.12 | 100
86 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Junbani Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000313/2021-2022 | 1547/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.58 | 4.76 | 100
87 | Tamluk Division | Contai Sub-Division | Repairing of R.C.C. Elevated Reservoir of capacity with allied works of Junbani PWSS within Contai - I Block including supply of all labour & materials under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000447/2024-2025 | 3614/TD | 27/11/2024 | 40 | CHARUBALA ENTERPRISE | 11.14 | 0 | 97
88 | Tamluk Division | Contai Sub-Division | Left Out pipeline, Piling and Road Restoration work for Augmentation of Junbani Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000638/2024-2025 | 850/TD | 19/03/2025 | 30 | BASANTA KUMAR MAITY | 41.02 | 0 | 0
89 | Tamluk Division | Contai Sub-Division | Boundary wall and Rising Main and under JJM with allied work for Jubani PWSS within Contai-I Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000753/2023-2024 | 3224/TD | 13/12/2023 | 40 | MAHAPRABHU ENTERPRISE | 35.37 | 0 | 16
90 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000010/2022-2023 | 102/TD | 11/04/2022 | 0 | Resource Division | 51.5 | 0 | 0
91 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000083/2022-2023 | 1270/TD | 12/09/2022 | 0 | Resource Division | 32.32 | 0 | 0
92 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money of Pump House No. ¿ III of Khejuri Zone-I PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01305/2023-2024 | BP-2023-24-583 | 22/11/2023 | 0 | WBSEDCL | 2.88 | 0 | 0
93 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000185/2022-2023 | 796/TD | 12/07/2022 | 969 | SUSANTA KUMAR KAR | 9.24 | 0 | 99
94 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000261/2022-2023 | 1078/TD | 23/08/2022 | 45 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 159.66 | 95
95 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000312/2022-2023 | 1225/TD | 07/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 71.86 | 0 | 100
96 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-S) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000469/2023-2024 | 1450/TD | 13/07/2023 | 30 | DEBABRATA DAS | 9.42 | 0 | 70
97 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Khejuri Zone-I PWSS within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000480/2024-2025 | 3769/TD | 10/12/2024 | 40 | GIRI CONSTRUCTION | 3.96 | 0 | 0
98 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line and Rising main, construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000539/2023-2024 | 1838/TD | 08/08/2023 | 40 | SK. SARFARAJ | 16.93 | 0 | 100
99 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (1557 Nos)with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000744/2022-2023 | 2551/TD | 24/01/2023 | 920 | TARUN KOLEY | 289.69 | 136.56 | 70
100 | Tamluk Division | Haldia Electrical Sub-Division | Repairing of existing Store Room with Guard Room with sanitary & water supply arrangements including Plinth Protection of OHR Site under Augmentation of Khejuri Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000767/2022-2023 | 2770/TD | 09/02/2023 | 30 | GIRI CONSTRUCTION | 9.94 | 0 | 100
101 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Barka saria Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000854/2023-2024 | 67/TD | 05/01/2024 | 7 | AMITAVA MONDAL | 0.96 | 0 | 100
102 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of Khejuri Mouja under Khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000855/2023-2024 | 68/TD | 05/01/2024 | 7 | TECHNO ENTERPRISE. | 0.96 | 0 | 100
103 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-L) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000891/2023-2024 | 246/TD | 11/01/2024 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.96 | 0 | 100
104 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-O) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000893/2023-2024 | 247/TD | 11/01/2024 | 20 | GITA ENTERPRISE | 9.75 | 0 | 90
105 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of Left out portion of khejuri Zone -I PWSS in Khajuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000897/2023-2024 | 244/TD | 11/01/2024 | 348 | ROY BISWAS CONSTRUCTION | 37.4 | 0 | 100
106 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
107 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 2898/TD | 21/11/2023 | 0 | Resource Division | 4.92 | 0 | 0
108 | Tamluk Division | Haldia Electrical Sub-Division | Quotation money payment to WBSEDCL for Simulia Water Supply Scheme of Tube Well No. - III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00537/2023-2024 | BP-2023-24-283 | 17/08/2023 | 0 | WBSEDCL | 4.34 | 0 | 0
109 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Simulia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000165/2021-2022 | 1169/TD | 01/12/2021 | 7 | RADIANT | 9.35 | 9.24 | 100
110 | Tamluk Division | Haldia Electrical Sub-Division | Pump House & Boundary Wall for Augmentation of Simulia Water Supply Scheme under Tamluk Development Block withen Tamluk Sub-Division under Tamluk Division, PHE Dte.in the district Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000470/2023-2024 | 1451/TD | 13/07/2023 | 413 | SK. SAHALAM | 12.36 | 4.42 | 40
111 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 550 cum and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Simulia Water Supply Scheme within Tamluk Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000499/2022-2023 | 1971/TD | 01/12/2022 | 1096 | SANKHA ENTERPRISE | 707.13 | 358.51 | 65
112 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Boundary wall , Pump Hose at Head Work site of Simulia Water Supply Scheme underTamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Length 402 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000625/2024-2025 | 737/TD | 07/03/2025 | 45 | M J A ENTERPRISE | 44.35 | 0 | 0
113 | Tamluk Division | Haldia Electrical Sub-Division | Laying of proposed Rising main line and supply & delivery of DI Specials M.S Structure for Canal crossing, Road crossing and Drum Sheet Piling at Simulia Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000710/2023-2024 | 2871/TD | 17/11/2023 | 25 | SANKHA ENTERPRISE | 58.27 | 0 | 0
114 | Tamluk Division | Haldia Electrical Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.10.2023 to 31.12.2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000824/2023-2024 | 1341/TSD | 27/09/2023 | 50 | DEBNATH MAITY | 0.24 | 0 | 100
115 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000020/2022-2023 | 408/TD | 25/05/2022 | 0 | Resource Division | 42.01 | 0 | 0
116 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000082/2022-2023 | 1262/TD | 12/09/2022 | 0 | Resource Division | 7.78 | 0 | 0
117 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000219/2023-2024 | 1118/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
118 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Monoharpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000436/2021-2022 | 1512/TD | 06/01/2022 | 20 | RADIANT | 3.55 | 3.45 | 100
119 | Tamluk Division | Haldia Sub-Division | Repairing & Renovation of Pump House No. "1" & Pump House No.- "2" at Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000652/2023-2024 | 2617/TD | 11/10/2023 | 470 | ANIRBAN BHOWMIK | 6.15 | 0 | 50
120 | Tamluk Division | Haldia Sub-Division | Laying of distribution pipe line to accommodate FHTC(2729 Nos) with new construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Manoharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000777/2022-2023 | 2861/TD | 17/02/2023 | 865 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.9 | 257.2 | 85
121 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line with inter connection at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000981/2023-2024 | 395/TD | 30/01/2024 | 274 | G. S. CONSTRUCTION | 9.36 | 0 | 50
122 | Tamluk Division | Haldia Sub-Division | Surging of Deep Tube well at different W/S Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001164/2023-2024 | 739/HSD, | 19/02/2024 | 15 | BUNBA CONSTRUCTION | 2.3 | 0 | 100
123 | Tamluk Division | Haldia Sub-Division | Construction of Boundary Wall, Protection work ,Earth Filling, Laying of left-out & Parallal Distribution line at Monaharpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001208/2023-2024 | 966/TD | 12/03/2024 | 693 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 112.45 | 0 | 10
124 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000024/2022-2023 | 412/TD | 25/05/2022 | 0 | Resource Division | 47.71 | 0 | 0
125 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000072/2022-2023 | 1266/TD | 12/09/2022 | 0 | Resource Division | 16.78 | 0 | 0
126 | Tamluk Division | Digha Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head work site for Narandiha W/S Scheme within Ramnagar -II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Lenght-146 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000194/2023-2024 | 395/TD | 27/04/2023 | 40 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.72 | 0 | 100
127 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Narandiha Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000325/2021-2022 | 1618/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.06 | 3.05 | 100
128 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of NARANDIA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000554/2022-2023 | 2182/TD | 20/12/2022 | 180 | MAITY CONSTRUCTION | 299.31 | 88.69 | 42
129 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of Pump House for Augmentation of NARANDIHA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000555/2022-2023 | 2181/TD | 20/12/2022 | 60 | MAITY CONSTRUCTION | 112.72 | 64.24 | 80
130 | Tamluk Division | Digha Sub-Division | Soil Investigation work in Connection of Construction of R.C.C. Over Head Reservoir (Capacity - 400 Cum) due to change of land with Laying of Balance Distribution Pipe Line for Provided balance FHTC and other allied works of Narandiha Piped Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000639/2024-2025 | 851/TD | 19/03/2025 | 30 | MAITY CONSTRUCTION | 48.33 | 0 | 0
131 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000280/2022-2023 | 2619/TD | 02/02/2023 | 0 | Resource Division | 41.76 | 0 | 0
132 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000285/2022-2023 | 2638/TD | 02/02/2023 | 0 | Resource Division | 19.64 | 0 | 0
133 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000129/2022-2023 | 2413/TD | 16/01/2023 | 0 | Resource Division | 19.96 | 0 | 0
134 | Tamluk Division | Contai Sub-Division | Sinking Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Boundary Wall, Soil investigation & Accommodate FHTC (1623 nos) including 2 years of Operation Maintenance under JJM with allied work for Chauddha Chuli & its adjoining moujas PWSS in Khajuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000851/2023-2024 | 74/TD | 05/01/2024 | 720 | SRIMANTA KUMAR MAITY | 501.66 | 0 | 40
135 | Tamluk Division | Contai Sub-Division | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Khejuri-I, Khejuri-II, Patashpur-I & Patashpur-II ) | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001291/2023-2024 | 563/CSD | 14/03/2024 | 10 | SAURAV HAZRA | 0.54 | 0 | 100
136 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000333/2022-2023 | 2982/TD | 27/02/2023 | 0 | Resource Division | 32.13 | 0 | 0
137 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000243/2023-2024 | 511/TD | 11/05/2023 | 30 | MANAS KUMAR SAHA | 93.6 | 0 | 30
138 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (300 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000294/2023-2024 | 583/TD | 16/05/2023 | 634 | RAJ KUMAR SINGHA | 172.52 | 34.27 | 22
139 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site & 2nd TW site ,Canal crossing & Approach Road of ground water based Erekhali Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000735/2023-2024 | 2987/TD | 29/11/2023 | 484 | A. R. CONSTRUCTION | 18 | 0 | 70
140 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000811/2022-2023 | 3080/TD | 28/02/2023 | 648 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.86 | 8.05 | 100
141 | Tamluk Division | Haldia Sub-Division | Ground water based Erekhali Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000812/2022-2023 | 3081/TD | 28/02/2023 | 20 | HYDROTECH ASSOCIATES | 10.01 | 8.28 | 85
142 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000164/2022-2023 | 2472/TD | 16/01/2023 | 0 | Resource Division | 18.44 | 0 | 0
143 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000189/2023-2024 | 638/W | 20/02/2024 | 0 | Resource Division | 10.55 | 0 | 0
144 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000016/2022-2023 | 50/TD | 05/04/2022 | 20 | RADIANT | 5.44 | 5.36 | 100
145 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 19.47 | 75
146 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000747/2022-2023 | 2594/TD | 30/01/2023 | 180 | RAJ KUMAR SINGHA | 986.55 | 507.95 | 65
147 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000093/2022-2023 | 1375/TD | 23/09/2022 | 0 | Resource Division | 52.31 | 0 | 0
148 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000235/2022-2023 | 2617/TD | 02/02/2023 | 0 | Resource Division | 139.61 | 0 | 0
149 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2095 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SARBERYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000227/2023-2024 | 453/TD | 04/05/2023 | 847 | TARUN KOLEY | 640.74 | 214.93 | 40
150 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000171/2023-2024 | 111/TD | 05/01/2024 | 0 | Resource Division | 12.91 | 0 | 0
151 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000174/2023-2024 | 289/TD | 17/01/2024 | 0 | Resource Division | 11.04 | 0 | 0
152 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000250/2022-2023 | 2719/TD | 06/02/2023 | 0 | Resource Division | 16.76 | 0 | 0
153 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000327/2023-2024 | 625/TD | 17/05/2023 | 30 | SOUVIK GHOSAL | 4.16 | 3.73 | 100
154 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2022-2023 | 1250/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 77.68 | 38.74 | 100
155 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000460/2021-2022 | 1725/TD | 01/02/2022 | 20 | RADIANT | 4.02 | 3.64 | 100
156 | Tamluk Division | Haldia Sub-Division | Laying Rising main work & construction of Approach Road of Chaitanyapur (Zone-II) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000645/2023-2024 | 2591/TD | 10/10/2023 | 20 | A. R. CONSTRUCTION | 24.5 | 0 | 70
157 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rd Tube Well site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000849/2022-2023 | 3169/TD | 10/03/2023 | 60 | MAITY TRADING | 4.6 | 0 | 85
158 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (4374 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000902/2022-2023 | 3458/TD | 27/03/2023 | 1187 | SANKHA ENTERPRISE | 625.57 | 72.53 | 32
159 | Tamluk Division | Haldia Sub-Division | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2024 to 31/12/2024. (12 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000992/2023-2024 | 623/HSD, | 28/12/2023 | 366 | SANTANU PATTANAYAK | 1.5 | 0 | 20
160 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000052/2022-2023 | 1203/TD | 06/09/2022 | 0 | Resource Division | 49.51 | 0 | 0
161 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000061/2022-2023 | 1202/TD | 06/09/2022 | 0 | Resource Division | 26.9 | 0 | 0
162 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC(764 nos), Laying Rising Main under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000141/2023-2024 | 282/TD | 20/04/2023 | 951 | NARAYAN MANDAL | 92.86 | 55.27 | 65
163 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC(700 nos),Construction of switch room cum cholorine room(2nd T/W site) , Construction of Boundary Wall (2nd t/w site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000288/2023-2024 | 581/TD | 16/05/2023 | 892 | NARAYAN MANDAL | 139.9 | 94.13 | 76
164 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & Construction of RCC over Head Reservoir of capacity 300 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), under JJM with allied work for Harshankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000295/2023-2024 | 584/TD | 16/05/2023 | 180 | RAJ KUMAR SINGHA | 112.97 | 0 | 2
165 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC(500 nos),Construction of switch room cum cholorine room(H/W site) , Construction of Boundary Wall (H/W site) under JJM with allied work for Harashankar PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000298/2023-2024 | 590/TD | 17/05/2023 | 803 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 88.84 | 0 | 30
166 | Tamluk Division | Tamluk Sadar Sub-Division | M.S. Structure for canel crossing for laying 150 mm DI (K9) Rising main and 200 mm DI (K7) pipes ( Nodal 379-382 ) of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Canal Length- = 20.00 mtr. ,Number of crossing -2 nos | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000300/2024-2025 | 3059/TD | 19/09/2024 | 400 | NARAYAN MANDAL | 8.28 | 0 | 0
167 | Tamluk Division | Tamluk Sadar Sub-Division | M.S. Structure for canel crossing for laying 110 mm OD uPVC pipe of Harasankar PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001197/2023-2024 | 825/TD | 05/03/2024 | 20 | NARAYAN MANDAL | 4.21 | 0 | 10
168 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC construction of switch room cum chlorine room (2nd T/W site), construction of Boundary wall (2nd T/W site), under JJM with allied work for Harasankar PWSS within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001206/2023-2024 | 887/TD | 06/03/2024 | 35 | NARAYAN MANDAL | 4.09 | 0 | 100
169 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000301/2022-2023 | 3005/TD | 27/02/2023 | 0 | Resource Division | 16.42 | 0 | 0
170 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000186/2022-2023 | 2445/TD | 16/01/2023 | 0 | Resource Division | 55.25 | 0 | 0
171 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000087/2024-2025 | 2955/TD | 12/09/2024 | 0 | Resource Division | 13.47 | 0 | 0
172 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000334/2022-2023 | 2981/TD | 27/02/2023 | 0 | Resource Division | 22.62 | 0 | 0
173 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1806 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KHAGA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000326/2023-2024 | 698/TD | 23/05/2023 | 801 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 581.3 | 0 | 40
174 | Tamluk Division | Contai Sub-Division | Laying Distribution System (Nodal-J-1 To J-2) of pipe line and its allied works for KHAGA water supply scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (As per Revised LDS Drawing) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001245/2023-2024 | 1080/TD | 16/03/2024 | 487 | S.S. ENTERPRISE | 23.86 | 0 | 80
175 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000153/2023-2024 | 89/TD | 05/01/2024 | 0 | Resource Division | 11.12 | 0 | 0
176 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000245/2022-2023 | 2722/TD | 06/02/2023 | 0 | Resource Division | 37.4 | 0 | 0
177 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (163 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000128/2023-2024 | 259/TD | 19/04/2023 | 30 | BADAL CHANDRA GOLE | 41.58 | 12.67 | 77
178 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Rajendrachak PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000159/2024-2025 | 2071/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
179 | Tamluk Division | Digha Sub-Division | Land Development at Head Works site of Rajendrachak W/S Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000280/2024-2025 | 3471/TD | 06/11/2024 | 7 | LAXMEE ENTERPRISE | 4.6 | 0 | 100
180 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 500 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.. (PART- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000281/2023-2024 | 553/TD | 12/05/2023 | 889 | SK. NUR ISLAM | 114.81 | 21.95 | 80
181 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 997 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000345/2023-2024 | 849/TD | 31/05/2023 | 784 | JAGANNATH MAKAR | 256.07 | 0 | 85
182 | Tamluk Division | Digha Sub-Division | Soil investigation, 250 cum OHR (Intze type with pile foundation) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000631/2023-2024 | 2439/TD | 19/09/2023 | 180 | ANUSKA ENTERPRISE | 104.2 | 0 | 0
183 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000322/2022-2023 | 2975/TD | 27/02/2023 | 0 | Resource Division | 18.5 | 0 | 0
184 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000054/2024-2025 | 1665/TD | 29/04/2024 | 0 | Resource Division | 7.01 | 0 | 0
185 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000152/2022-2023 | 2458/TD | 16/01/2023 | 0 | Resource Division | 40.42 | 0 | 0
186 | Tamluk Division | Tamluk Sadar Sub-Division | Work Order for Land development at Head Work Site of Mirikpur Water Supply Scheme within Tamluk Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000181/2024-2025 | 2252/TD | 15/07/2024 | 98 | GHOSH ENTERPRISE | 4.07 | 0 | 100
187 | Tamluk Division | Tamluk Sadar Sub-Division | Canal crossing for laying HDPE pipes of Mirikpur PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Nodal Point J-512 to J-517 ) Canal Length- =30.00 mtr. Number of crossing -1 nos | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000582/2024-2025 | 459/TD | 04/02/2025 | 25 | GHOSH ENTERPRISE | 6.25 | 0 | 0
188 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000221/2022-2023 | 2678/TD | 06/02/2023 | 0 | Resource Division | 38.97 | 0 | 0
189 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money for Anantapur Zone-I PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00611/2022-2023 | BP-2022-23-819 | 24/03/2023 | 0 | WBSEDCL | 2.38 | 0 | 0
190 | Tamluk Division | Haldia Electrical Sub-Division | Construction of new boundary wall around OHR and Repair and Renovation of Existing boundary wall , Pump house and chlorine room at Head work site and 2nd tube well site of Anantapur Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000386/2024-2025 | 3449/TD | 30/10/2024 | 40 | M J A ENTERPRISE | 9.09 | 0 | 0
191 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000397/2023-2024 | 1081/TD | 08/06/2023 | 45 | SK. SAHALAM | 5.1 | 0 | 100
192 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000461/2021-2022 | 1739/TD | 03/02/2022 | 20 | RADIANT | 3.86 | 3.83 | 100
193 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC(6217 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-I Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000480/2022-2023 | 1889/TD | 24/11/2022 | 859 | TARUN KOLEY | 622.31 | 266.45 | 90
194 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 400 mm dia. Additional length distribution pipe line with supply of DI specials under Anantapur Zone- I PWSS with in Tamluk Dev.Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000582/2023-2024 | 2203/TD | 01/09/2023 | 20 | TARUN KOLEY | 10.96 | 0 | 100
195 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 200 /250/300mm dia DI (K-9) for Rising main line from T/W-1 , T/W-2 ,T/W-3 and interconnection betn. T/W-1 to OHR including supply of DI specials , Construction of boundary wall & approach 3rd tube well site under Anantapur Zone- I PWSS with in Tamluk Dev.Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division,PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000584/2023-2024 | 2204/TD | 01/09/2023 | 368 | TARUN KOLEY | 13.81 | 0 | 95
196 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000031/2023-2024 | 1923/TD | 14/08/2023 | 0 | Resource Division | 33.23 | 0 | 0
197 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000047/2022-2023 | 1017/TD | 08/08/2022 | 0 | Resource Division | 67.14 | 0 | 0
198 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000056/2022-2023 | 1208/TD | 06/09/2022 | 0 | Resource Division | 38.23 | 0 | 0
199 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000224/2023-2024 | 1123/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
200 | Tamluk Division | Contai Sub-Division | Payment to WBSEDCL for Shifting of LTOH Line at Siulipur for Ilashpur PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00810/2024-2025 | BP-2024-25-382 | 29/08/2024 | 0 | WBSEDCL | 0.81 | 0 | 0
201 | Tamluk Division | Contai Sub-Division | Laying Distribution System (NP-2-27,27-38,38-45,45-47,47-53,53-57,57-61,61-63,63-65,65-67 & 67-71) of pipe line and its allied works for Ilashpur Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000140/2024-2025 | 1923/TD | 07/06/2024 | 25 | MMS CONSTRUCTIONS PVT. LTD. | 12.61 | 0 | 90
202 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2038 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of ILASHPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000217/2023-2024 | 448/TD | 04/05/2023 | 942 | TAPAS SANTRA | 657.13 | 264.73 | 58
203 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000142/2023-2024 | 88/TD | 05/01/2024 | 0 | Resource Division | 12.55 | 0 | 0
204 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000196/2022-2023 | 2385/TD | 16/01/2023 | 0 | Resource Division | 20.13 | 0 | 0
205 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (1841 nos.) under JJM in Chandibenia Zone- II PWSS Block - Moyna in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000391/2022-2023 | 1424/TD | 26/09/2022 | 25 | HARIPADA PATTANAYAK | 69.06 | 65.84 | 100
206 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000201/2023-2024 | 1101/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
207 | Tamluk Division | Tamluk Sadar Sub-Division | Bill for damage of Moyna Bridge approach road at 1.90 Km. Due to laying of water pipe line for Moyna Zone-II PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00992/2024-2025 | BP-2024-25-496 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.41 | 0 | 0
208 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Retaining Wall cun Guard wall and Approach Road beside pond at 3rd Tube well for Augmentation of Moyna Zone-II PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Divisionin the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000239/2024-2025 | 2678/TD | 22/08/2024 | 25 | GHOSH ENTERPRISE | 6.98 | 0 | 0
209 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (3870 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-II Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000443/2022-2023 | 1651/TD | 02/11/2022 | 1080 | ARABINDA GHOSH | 571.76 | 292.12 | 80
210 | Tamluk Division | Tamluk Sadar Sub-Division | Pump House , Boundary Wall, Rising Main, Dramsheet Pilling for Augmentation of Moyna Zone-II Water Supply Scheme under Moyna Development Block within Tamluk Sub-Division under Tamluk Division, PHE Dte.in the district Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000465/2023-2024 | 1445/TD | 13/07/2023 | 820 | GHOSH ENTERPRISE | 89.23 | 0 | 81
211 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000860/2021-2022 | 1469/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.37 | 3.98 | 100
212 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000051/2022-2023 | 1206/TD | 06/09/2022 | 0 | Resource Division | 109.03 | 0 | 0
213 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000059/2022-2023 | 1204/TD | 06/09/2022 | 0 | Resource Division | 7.03 | 0 | 0
214 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1155 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Silampur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000488/2023-2024 | 1565/TD | 19/07/2023 | 720 | ORIENT CONSTRUCTION | 431.66 | 0 | 60
215 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000256/2022-2023 | 2711/TD | 06/02/2023 | 0 | Resource Division | 42.6 | 0 | 0
216 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 20
217 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000324/2022-2023 | 2992/TD | 27/02/2023 | 0 | Resource Division | 26.09 | 0 | 0
218 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000092/2024-2025 | 2957/TD | 12/09/2024 | 0 | Resource Division | 10.46 | 0 | 0
219 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000121/2022-2023 | 2401/TD | 16/01/2023 | 0 | Resource Division | 41.93 | 0 | 0
220 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gokulnagar PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000871/2023-2024 | 193/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
221 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000007/2024-2025 | 1565/TD | 23/04/2024 | 0 | Resource Division | 14.91 | 0 | 0
222 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000179/2022-2023 | 2425/TD | 16/01/2023 | 0 | Resource Division | 6.8 | 0 | 0
223 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharui PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000165/2024-2025 | 2077/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
224 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000154/2023-2024 | 136/TD | 05/01/2024 | 0 | Resource Division | 15.86 | 0 | 0
225 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000273/2022-2023 | 2685/TD | 06/02/2023 | 0 | Resource Division | 73.85 | 0 | 0
226 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000145/2022-2023 | 2449/TD | 16/01/2023 | 0 | Resource Division | 32.88 | 0 | 0
227 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000159/2022-2023 | 2422/TD | 16/01/2023 | 0 | Resource Division | 39.03 | 0 | 0
228 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barnan PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000164/2024-2025 | 2076/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
229 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd T/W site Barnan W/S Scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000178/2024-2025 | 2182/TD | 08/07/2024 | 14 | S.D. CONSTRUCTION | 3.91 | 0 | 100
230 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000120/2023-2024 | 82//TD | 05/01/2024 | 0 | Resource Division | 6.85 | 0 | 0
231 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000274/2022-2023 | 2684/TD | 06/02/2023 | 0 | Resource Division | 19.64 | 0 | 0
232 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Gouranga Chak PWSS at Moyna block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000873/2023-2024 | 195/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
233 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2024-2025 | 1566/TD | 23/04/2024 | 0 | Resource Division | 8.79 | 0 | 0
234 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000169/2022-2023 | 2437/TD | 16/01/2023 | 0 | Resource Division | 25.43 | 0 | 0
235 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Syamraibar PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000154/2024-2025 | 2065/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
236 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000067/2024-2025 | 2978/TD | 12/09/2024 | 0 | Resource Division | 6.44 | 0 | 0
237 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000168/2022-2023 | 2391/TD | 16/01/2023 | 0 | Resource Division | 18.29 | 0 | 0
238 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well , Laying distribution system, Pump House at Head work site & 2nd tube well site, Soil Test, OHR ( 250 Cum ) FHTC ( (1636 nos ) Boundary wall and Rising Main and 2 Years Maintenance under JJM with allied work for Jumki PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000639/2023-2024 | 2485/TD | 26/09/2023 | 918 | AJIT KUMAR SOM | 442.63 | 0 | 65
239 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000316/2022-2023 | 2971/TD | 27/02/2023 | 0 | Resource Division | 19.96 | 0 | 0
240 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000450/2023-2024 | 1468/TD | 13/07/2023 | 777 | JAGANNATH MAKAR | 80.39 | 0 | 3
241 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000807/2022-2023 | 3076/TD | 28/02/2023 | 30 | PULAK KUMAR SAMANTA | 55.08 | 23.18 | 62
242 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000808/2022-2023 | 3077/TD | 28/02/2023 | 941 | J.M. CONSTRUCTION | 59.34 | 21.01 | 35
243 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000809/2022-2023 | 3078/TD | 28/02/2023 | 447 | R CONSTRUCTION | 42.52 | 34.39 | 100
244 | Tamluk Division | Haldia Sub-Division | Ground water based Sar Berya Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000810/2022-2023 | 3079/TD | 28/02/2023 | 20 | MADAN MOHAN MAITY | 36.48 | 17.65 | 100
245 | Tamluk Division | Haldia Sub-Division | Installation of display board at 2 (two) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IV) [Sarberia PWSS & Urddhabmal PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000832/2023-2024 | 620/HSD, | 21/12/2023 | 7 | SANTANU PATTANAYAK | 0.42 | 0 | 100
246 | Tamluk Division | Haldia Sub-Division | Orientation Programme under Haldia Sub-Division of Tamluk Division, PHE Dte. (For 5 nos Blocks, i.e. - i) Sutahata Dev. Block, ii) Mahishadal Dev. Block, iii) Haldia Dev. Block, iv) Nandigram - I Dev. Block & v) Nandigram - II Dev. Block) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001169/2023-2024 | 621/HSD, | 21/12/2023 | 2 | TAPAN BERA | 0.94 | 0 | 100
247 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site & Construction of Retaining wall of ground water based Sarberia Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001241/2023-2024 | 1083/TD | 16/03/2024 | 40 | JAGANNATH MAKAR | 13.42 | 0 | 0
248 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000137/2022-2023 | 2424/TD | 16/01/2023 | 0 | Resource Division | 39.36 | 0 | 0
249 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000170/2023-2024 | 112/TD | 05/01/2024 | 0 | Resource Division | 5.39 | 0 | 0
250 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000093/2024-2025 | 2963/TD | 12/09/2024 | 0 | Resource Division | 9.09 | 0 | 0
251 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000313/2022-2023 | 2969/TD | 27/02/2023 | 0 | Resource Division | 34.67 | 0 | 0
252 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (672 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of GHANTA SHALA PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000350/2023-2024 | 852/TD | 31/05/2023 | 940 | GHOSH CONSTRUCTION | 288.84 | 88.71 | 75
253 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000135/2023-2024 | 105/TD | 05/01/2024 | 0 | Resource Division | 4.14 | 0 | 0
254 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000266/2022-2023 | 2694/TD | 06/02/2023 | 0 | Resource Division | 26.6 | 0 | 0
255 | Tamluk Division | Contai Sub-Division | Schedule for Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Chistipur PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000174/2024-2025 | 2086/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
256 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000321/2022-2023 | 2994/TD | 27/02/2023 | 0 | Resource Division | 17.01 | 0 | 0
257 | Tamluk Division | Contai Sub-Division | Shifting of 11kv HT Line (Junput feeder) at BAGURAN JALPAI WS SCHEME, BLOCK-Contai-1,CCC-CONTAI. Ref memono.-CD-322 Dated-14.05.2024 Ref. ID-860299651 Application ID-100000107869 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00421/2024-2025 | BP-2024-25-142 | 27/05/2024 | 0 | WBSEDCL | 2.06 | 0 | 0
258 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baguran Jalpai PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000230/2024-2025 | 2427/TD | 30/07/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
259 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000071/2024-2025 | 2948/TD | 12/09/2024 | 0 | Resource Division | 8.06 | 0 | 0
260 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000173/2022-2023 | 2396/TD | 16/01/2023 | 0 | Resource Division | 35.66 | 0 | 0
261 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Nonakourda PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000156/2024-2025 | 2068/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
262 | Tamluk Division | Contai Sub-Division | Tube well, Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1018 nos) under JJM with allied work for Nonakourda- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000683/2023-2024 | 2684/TD | 16/10/2023 | 893 | RELIABLE CONSTRUCTIONS | 352.4 | 0 | 30
263 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000034/2024-2025 | 1661/TD | 29/04/2024 | 0 | Resource Division | 6.27 | 0 | 0
264 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000342/2022-2023 | 2997/TD | 27/02/2023 | 0 | Resource Division | 8.93 | 0 | 0
265 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (785 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BARAGECHA PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000223/2023-2024 | 458/TD | 04/05/2023 | 900 | TAPAS SANTRA | 308.25 | 0 | 50
266 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000118/2023-2024 | 97//TD | 05/01/2024 | 0 | Resource Division | 4.84 | 0 | 0
267 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000209/2022-2023 | 2469/TD | 16/01/2023 | 0 | Resource Division | 54.65 | 0 | 0
268 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000218/2023-2024 | 449/TD | 04/05/2023 | 698 | TARUN KOLEY | 549.23 | 0 | 75
269 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000220/2022-2023 | 2674/TD | 06/02/2023 | 0 | Resource Division | 13.79 | 0 | 0
270 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Shifting of LT line of Purba Nukha PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01993/2023-2024 | BP-2023-24-937 | 06/03/2024 | 0 | WBSEDCL | 2.98 | 0 | 0
271 | Tamluk Division | Tamluk Sadar Sub-Division | Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing vehicle no-WB 29C 2260 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.08.2024 to 31.01.2025.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000249/2024-2025 | 1110/TSD | 31/07/2024 | 184 | KISHORE KUMAR SEN | 0.87 | 0 | 80
272 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well , Laying Rising Main,Laying distribution pipe line, Pump House , Boundary Wall, Soil investigation , 350 Cum OHR (Intze type with pile foundation) and Accommodate FHTC 2344 nos including 02(Two) Years Operation & Maintanance for Two years including supply of all labour & materials with allied work under JJM for Purbanukha and Adjoining Moujas Piped Water Supply Scheme under Tamluk Block withen Tamluk Sub-Division under Tamluk Division, PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000485/2023-2024 | 1567/TD | 19/07/2023 | 180 | TARUN KOLEY | 549.36 | 0 | 65
273 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Additional Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.02.2025 to 31.07.2025.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000687/2024-2025 | 222/TSD | 28/01/2025 | 181 | KISHORE KUMAR SEN | 0.86 | 0 | 0
274 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000295/2022-2023 | 3009/TD | 27/02/2023 | 0 | Resource Division | 27.4 | 0 | 0
275 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of JHAUGERIA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004966048/QUOT/03 DT. 22-11-2024 Application NO- 2004966048 Application type-New connection Consumer Id- 204446057 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/01295/2024-2025 |  | 16/12/2024 | 0 | WBSEDCL | 2.54 | 0 | 0
276 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000145/2023-2024 | 124/TD | 05/01/2024 | 0 | Resource Division | 0.97 | 0 | 0
277 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000350/2022-2023 | 3016/TD | 27/02/2023 | 0 | Resource Division | 15.15 | 0 | 0
278 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000968/2022-2023 | 1058/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 3.6 | 3.06 | 100
279 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000037/2023-2024 | 2082/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
280 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000108/2023-2024 | 3011/TD | 29/11/2023 | 0 | Resource Division | 1.47 | 0 | 0
281 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VII). Name of sites:- i) Gopalpur PWSS's 4th Tube well Site, ii) Rangibasan PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. iii) Betkundu PWSS 1st Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000389/2024-2025 | 1072/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
282 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-VIII). Name of sites:- i) Betkundu PWSS's 2nd Tube well Site, and 3rd Tube well site, ii) Rajarampur PWSS's 1st Tube well Site and 2nd Tube well Site iii) Natshal Lakshya (Z-I) 1st Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000390/2024-2025 | 1073/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
283 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-IX). Name of sites: - i) Natshal Lakshya (Z-1) PWSS's 2nd Tube well Site, 3rd Tube well site, 4th Tube well site, 5th Tube well site ii) Natshal Lakshya (Z-II) PWSS's 1st Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000391/2024-2025 | 1074/HSD, | 05/11/2024 | 57 | SANTANU PATTANAYAK | 0.83 | 0 | 100
284 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XII) Name of sites: - i) Madhya Hingli PWSS's 1st Tube well Site, 2nd Tube well site, ii) Baksichak PWSS's 1st Tube well Site, iii) Mayachar 1st Tube well Site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000394/2024-2025 | 1077/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
285 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIII) Name of sites: - i) Lakshya PWSS¿s 1st Tube well Site, 2nd Tube well site, 3rd Tube well site ii) Keshabpur jalpai PWSS's 1st Tube well Site, 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000395/2024-2025 | 1078/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
286 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIV) Name of sites: - i) Bar Sundara PWSS's 3rd Tube well Site, ii) Simulberya PWSS's 1st Tube well site iii) Natshal Lakshya (Z-II) PWSS's 2nd Tube well Site and 3rd Tube well site. iv) Kesabpur Jalpai PWSS's 3rd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000396/2024-2025 | 1079/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
287 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVI) Name of sites: - i) Manoharpur PWSS¿s 1st Tube well site and 2nd Tube well Site. ii) Solat PWSS's 1st Tube well site and 2nd Tube well site, iii) Dakshinchak PWSS's 1st Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000398/2024-2025 | 1081/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
288 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVII) Name of sites: - i) Dakshinchak (Z-I) PWSS's 2nd Tube well Site, and 3rd Tube well site, ii) Dakshinchak (Z-II) PWSS's 1st Tube well Site (iii) Barsundara PWSS 1st Tube well site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000399/2024-2025 | 1082/HSD, | 05/11/2024 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
289 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XVIII) Name of sites:- i) Gholpukuria PWSS's (Z-1) 1st Tube well Site, 2nd Tube well site, 3rd Tube well site, ii) Gholpukuria PWSS's (Z-II) PWSS's 1st Tube well Site, 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000402/2024-2025 | 1083/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.83 | 0 | 100
290 | Tamluk Division | Haldia Sub-Division | Installation of 3 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XIX) Name of sites: - i) Jalpai Part -II PWSS's 1st Tube well Site, 2nd Tube well Site and 3rd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000403/2024-2025 | 1084/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.5 | 0 | 100
291 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XX) Name of sites:- i) Manikpur PWSS's 1st Tube well Site, 2nd Tube well site, 3rd Tube well site, ii) Tajpur PWSS's 1st Tube well Site and 2nd Tube well Site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000404/2024-2025 | 1085/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.83 | 0 | 100
292 | Tamluk Division | Haldia Sub-Division | Installation of 5 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXI) Name of sites: - i) Tajpur PWSS's 3rd Tube well Site ii) Mahammadpur PWSS's 1st Tube well Site, 2nd Tube well Site iii) Sonachura PWSS 1st Tube well Site and 2nd Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000405/2024-2025 | 1086/HSD | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.83 | 0 | 100
293 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS work sites for Open Land under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-XXII) Name of sites: - i) Solat Headwork site. ii) Chaitanyapur (Zone-II) 2nd Tube well site, 3rd Tube well site and 4th Tube well site. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000406/2024-2025 | 1087/HSD, | 05/11/2024 | 57 | G. S. A. CONSTRUCTION | 0.67 | 0 | 100
294 | Tamluk Division | Haldia Sub-Division | Ground water based Amritberya Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (450 cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000500/2023-2024 | 1688/TD | 26/07/2023 | 583 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 580.82 | 0 | 40
295 | Tamluk Division | Haldia Sub-Division | Installation of 3 Nos. Display Board regarding Har-Ggar-Jal (HGJ) of different villages within different PWSS Jurisdiction under Haldia Sub-Division of Tamluk Division, PHE Dte. (H.G.J. Phase-4) Location:- 1) Asathtalya of Asataliya G.P. within Asathtalya PWSS, 2) Barotala of Asataliya G.P. within Asathtalya PWSS, 3) Gopalpur of Kismat Naikundi G.P. within Gopalpur PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000524/2024-2025 | 23/HSD, | 09/01/2025 | 10 | G. S. A. CONSTRUCTION | 0.62 | 0 | 100
296 | Tamluk Division | Haldia Sub-Division | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2025 to 31/12/2025. (12 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000564/2024-2025 | 1285/HSD, | 27/12/2024 | 365 | SANTANU PATTANAYAK | 1.5 | 0 | 40
297 | Tamluk Division | Haldia Sub-Division | Supply and delivery of 3 nos Chairs (with arm rest), 11 nos Chairs (without arm rest) and 1 nos stainless steel Rack (72inch X 36inch X 15 inch with 5 selves) (all articles should be of Godrej Interio Brand) under Office of the Assistant Engineer, Haldia Sub-Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001013/2023-2024 | 689/HSD, | 31/01/2024 | 343 | MALLIK TRADERS | 0.97 | 0 | 100
298 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Amritberya PWSS at Mahisadal Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001043/2023-2024 | 373/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 0
299 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000113/2023-2024 | 77/TD | 05/01/2024 | 0 | Resource Division | 21.19 | 0 | 0
300 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000331/2022-2023 | 2984/TD | 27/02/2023 | 0 | Resource Division | 27.61 | 0 | 0
301 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining moujas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000090/2022-2023 | 432/TD | 27/05/2022 | 90 | JAGANNATH MAKAR | 234.25 | 229.76 | 95
302 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rasikachak Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000185/2021-2022 | 1194/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.62 | 4.62 | 100
303 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of Ground Water Based Rashikachak PWSS to Accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000243/2024-2025 | 2695/TD | 22/08/2024 | 30 | HARIPADA PATTANAYAK | 38.26 | 0 | 0
304 | Tamluk Division | Tamluk Sadar Sub-Division | Piling work and pond crossing of Rejuvenation & Retrofitting of ground water based Rashikachak PWSS & its adjoining mouzas within Chandipur Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000659/2022-2023 | 2344/TD | 10/01/2023 | 25 | JAGANNATH MAKAR | 29.39 | 28.47 | 0
305 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000195/2023-2024 | 1095/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
306 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , & Accommodate FHTC (147 nos) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000123/2023-2024 | 256/TD | 19/04/2023 | 857 | CHANDIMATA CONSTRUCTION | 84.7 | 0 | 70
307 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Boundary Wall & Rising main pipe line under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000125/2023-2024 | 257/TD | 19/04/2023 | 60 | SOUMYA ENTERPRISE | 49.45 | 20.51 | 45
308 | Tamluk Division | Digha Sub-Division | Soil investigation, 50 cum OHR ( type with pile foundation) under JJM with allied work for BANCHBERA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000416/2023-2024 | 1085/TD | 08/06/2023 | 180 | GOUTAM CONSTRUCTION | 38.56 | 0 | 50
309 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000352/2022-2023 | 3015/TD | 27/02/2023 | 0 | Resource Division | 16.09 | 0 | 0
310 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (190 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-XI Block - Kolaghat in the District of Purba Medinipur.(Phase-III)[PART-B] | Assistant Engineer | Junior Engineer | ORD/000121/2023-2024 | 252/TD | 19/04/2023 | 20 | MISHRA ENTERPRISE | 9.69 | 9.69 | 100
311 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (990 nos.) and laying of left-out portion UPVC pipeline due to uncovered area at different nodel point under JJM in Surface water based Water Supply Scheme for Zone-XI, Block- Kolaghat in the District of Purba Medinipur. (Phase-III) [PART-A) | Assistant Engineer | Junior Engineer | ORD/000247/2023-2024 | 512/TD | 11/05/2023 | 40 | TAPAS SANTRA | 81.84 | 69.61 | 85
312 | Tamluk Division | Digha Sub-Division | Payment to WBSEDCL for Shifting of 33 KV FEEDER HT Line at Sabitrapur for Kanpur Water Supply Scheme for Zone-V under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02086/2023-2024 | BP-2023-24-957 | 14/03/2024 | 0 | WBSEDCL | 3.05 | 0 | 0
313 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000459/2022-2023 | 1858/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 3.13 | 100
314 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 184 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000509/2023-2024 | 1731/TD | 31/07/2023 | 970 | ONKAR ENTERPRISE | 284.7 | 0 | 5
315 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (215 Nos) under JJM with allied work for KANPUR (Zone-V) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000591/2024-2025 | 491/TD | 06/02/2025 | 120 | GHOSH CONSTRUCTION | 87.4 | 0 | 80
316 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone-V PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000868/2023-2024 | 190/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
317 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000042/2023-2024 | 2067/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
318 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000094/2023-2024 | 2997/TD | 29/11/2023 | 0 | Resource Division | 1.13 | 0 | 0
319 | Tamluk Division | Contai Sub-Division | Bill for payment to WBSEDCL for New Pipe Construction at Panchgachia new Sawsahan for Fuleshwar PWSS under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02050/2023-2024 | BP-2023-24-962 | 14/03/2024 | 0 | WBSEDCL | 0.27 | 0 | 0
320 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000095/2024-2025 | 2958/TD | 12/09/2024 | 0 | Resource Division | 7.81 | 0 | 0
321 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000122/2022-2023 | 2403/TD | 16/01/2023 | 0 | Resource Division | 34.22 | 0 | 0
322 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000142/2022-2023 | 2442/TD | 16/01/2023 | 0 | Resource Division | 19.52 | 0 | 0
323 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000429/2023-2024 | 1413/TD | 12/07/2023 | 720 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 0 | 60
324 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000097/2024-2025 | 2959/TD | 12/09/2024 | 0 | Resource Division | 14.85 | 0 | 0
325 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000230/2022-2023 | 2709/TD | 06/02/2023 | 0 | Resource Division | 14.75 | 0 | 0
326 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
327 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 2896/TD | 21/11/2023 | 0 | Resource Division | 14.27 | 0 | 0
328 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -XII Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000192/2020-2021 | 2769/TD | 28/01/2021 | 60 | UMWELT ENGINEER PVT. LTD. | 96.7 | 0 | 100
329 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000132/2021-2022 | BP-2021-22-51 | 29/07/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 0.73 | 0 | 0
330 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000223/2021-2022 | 133/W | 15/07/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 4.15 | 0 | 0
331 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XII within Panskura - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001216/2020-2021 | 943/W | 19/03/2021 | 0 | UMWELT ENGINEER PVT. LTD. | 91.85 | 0 | 0
332 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC under JJM in Manikpur PWSS & Jalpai Part-II PWSS Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000283/2020-2021 | 2974/TD | 25/02/2021 | 70 | SANKHA ENTERPRISE | 164.85 | 0 | 100
333 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000243/2021-2022 | BP-2021-22-66 | 18/08/2021 | 0 | SANKHA ENTERPRISE | 70.63 | 0 | 0
334 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000895/2021-2022 | BP-2021-22-297 | 10/03/2022 | 0 | SANKHA ENTERPRISE | 80 | 0 | 0
335 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Manikpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000896/2021-2022 | BP-2021-22-298 | 10/03/2022 | 0 | SANKHA ENTERPRISE | 14.19 | 0 | 0
336 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Gogras Keshab bar,J.L. No-328 and Village-Gogras Kottaluk,J.L. No-329 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. |  |  | ORD/000104/2020-2021 | 2460/TD | 18/12/2020 | 30 | TARUN KOLEY | 37.07 | 0 | 100
337 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Beraberia,J.L. No-330 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. |  |  | ORD/000105/2020-2021 | 2461/TD | 18/12/2020 | 20 | TARUN KOLEY | 17.22 | 0 | 100
338 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Purushottampur,J.L. No-331 under JJM in Gogras Keshab Bar PWSS Block - Panskura - I in the District of Purba Medinipur. |  |  | ORD/000106/2020-2021 | 2462/TD | 18/12/2020 | 25 | TARUN KOLEY | 26.29 | 0 | 100
339 | Tamluk Division |  | Survey and data collection through mobile application regarding availability of drinking water, Sanitation facility, Rain water harvesting, greywater management and others parameters in High School, upper Primary School, Primary School, Sisu Siksha Kendra of 25 blocks areas under Tamluk Division PHE Dte within Purba Medinipur District. |  |  | ORD/000429/2022-2023 | 1618/TD | 20/10/2022 | 20 | SUDIP MANNA | 3.67 | 3.52 | 100
340 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Gogas Keshab Bar and Gogras Kottaluk Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001027/2020-2021 | 700/W | 02/02/2021 | 0 | TARUN KOLEY | 36.85 | 0 | 0
341 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Beraberia Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001028/2020-2021 | 701/W | 02/02/2021 | 0 | TARUN KOLEY | 17.09 | 0 | 0
342 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gogras Keshab Bar W/S Scheme within village Purushottampur Mouza under Tamluk Division, PHE Dte. |  |  | VCH/001029/2020-2021 | 702/W | 02/02/2021 | 0 | TARUN KOLEY | 25.18 | 0 | 0
343 | Tamluk Division |  | Annual Maintenance of Computer and Peripherals for different laboratories in Purba Medinipur District under Tamluk Division, PHE Dte. (Period from 01/11/20 to 28/02/2021) |  |  | VCH/000074/2021-2022 | 08/W | 05/05/2021 | 0 | MISHRA ENTERPRISE | 0.78 | 0 | 0
344 | Tamluk Division |  | Different work under Tamluk Division, PHE Dte. |  |  | VCH/000165/2020-2021 | 05 | 16/04/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 9.82 | 0 | 0
345 | Tamluk Division |  | Different work under Tamluk Division, PHE Dte. |  |  | VCH/000166/2020-2021 | 06 | 16/04/2020 | 0 | DIFFERENT CONTRACTOR OF TAMLUK DIVISION, PHE DTE. | 8.25 | 0 | 0
346 | Tamluk Division |  | Contigency Bill of NGO managed laboratory for the period from October, 2020 to March, 2021. under Tamluk Division, PHE Dte. |  |  | VCH/000215/2021-2022 | 161/W | 30/07/2021 | 0 | TAMRALIPTA GUCHHA SAMITY AND OTHERS | 2.45 | 0 | 0
347 | Tamluk Division |  | THIS BILL HAS BEEN RAISED FOR SURRENDER OF UNSPENT FUND TO THE SINGLE NODAL ACCOUNT AS PER CLAUSE 2(III) OF D.O. NO. F.1(13)PFMS/FCD/2020, DTD. 12TH APRIL, 2021 BY SECRETARY, EXPENDITURE, GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE AND CLAUSE 13 OF OFFICE MEMORANDUM. NO. F.I. (13) PFMS FCD / 2020 DTD. 23/03/2021 BY THE DIRECTOR (FCD), GOVT. OF INDIA, MINISTRY OF FINANCE, DEPARTMENT OF EXPENDITURE, PFMS DIVISION, AND VIDE MEMO NO. 2724/PHE-13011/7/2021-BUDGET CELL-DEPT. OF PHE Dte. |  |  | VCH/000706/2021-2022 | 452/W | 22/12/2021 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 7.13 | 0 | 0
348 | Tamluk Division |  | Instrument / Equipment for Digha Sub-Divisional Water Testing Laboratory under Digha Sub-Division of Tamluk Division, PHE Dte. |  |  | VCH/001059/2020-2021 | 1115/W | 30/03/2021 | 0 | LABARD INSTRUCHEM PVT. LTD. | 8.06 | 0 | 0
349 | Tamluk Division |  | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in TAMALDA piped water supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur District. |  |  | ORD/000132/2025-2026 | 145/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.66 | 0 | 0
350 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Tamalda PWSS Block -Egra-I in the District of Purba Medinipur. |  |  | ORD/000235/2020-2021 | 2866/TD | 10/02/2021 | 25 | AJIT KUMAR SOM | 44.61 | 0 | 100
351 | Tamluk Division |  | Laying distribution system of Tamalda & its adjoining moujas Water Supply Scheme to support the ongoing FHTC Connection within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. |  |  | ORD/000457/2021-2022 | 1930/TD | 28/02/2022 | 15 | SOM CONSTRUCTION | 4.84 | 4.84 | 100
352 | Tamluk Division |  | Functional Household Tap Connection for completion of 100 percent house hold coverage at Tamalda & Sonapada Mouza of Tamalda PWSS, GP-Panchroll, Block - Egra - I under Digha Sub-Division, within Tamluk Division, P.H.E.Dte. Purba Medinipur. |  |  | ORD/001217/2023-2024 | 981/TD | 13/03/2024 | 348 | SAURAV HAZRA | 3.16 | 0 | 100
353 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000436/2021-2022 | BP-2021-22-149 | 09/11/2021 | 0 | AJIT KUMAR SOM | 8.58 | 0 | 0
354 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Tamalda Piped Water Supply Scheme |  |  | VCH/001121/2020-2021 |  | 15/03/2021 | 0 | AJIT KUMAR SOM | 29.34 | 0 | 0
355 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Tamalda W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001261/2020-2021 | 1089/W | 30/03/2021 | 0 | AJIT KUMAR SOM | 29.34 | 0 | 0
356 | Tamluk Division |  | Retrofitting to accommodate FHTC (387 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II )_within Rankinipur JL-135(P) - (Rankinipur Uttar) &Gholepukuria JL-134(P) - (Madhya Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-A |  |  | ORD/000182/2020-2021 | 2748/TD | 27/01/2021 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.48 | 0 | 100
357 | Tamluk Division |  | Retrofitting to accommodate FHTC (397 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur - (Rankinipur Purba) JL-135(P) &Gholepukuria - (Gholepukuria Purba Uttar Para) JL-134(P) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B |  |  | ORD/000183/2020-2021 | 2749/TD | 27/01/2021 | 20 | ADHIKARY CONSTRUCTION | 20.1 | 0 | 100
358 | Tamluk Division |  | Retrofitting to accommodate FHTC (424 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Paschim) & GholepukuriaJL-134(P) - (Gholepukuria Dakshin Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. PART-C |  |  | ORD/000184/2020-2021 | 2750/TD | 27/01/2021 | 20 | FARID UDDIN AHMED | 21.27 | 4.5 | 100
359 | Tamluk Division |  | Retrofitting to accommodate FHTC (395 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Rankinipur JL-135(P) - (Rankinipur Dakshin) & Gholepukuria JL-134(P) - (Gholepukuria Uttar Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-D |  |  | ORD/000185/2020-2021 | 2751/TD | 27/01/2021 | 20 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 20.37 | 11.38 | 100
360 | Tamluk Division |  | Retrofitting to accommodate FHTC (121 nos) under JJM in Gholepukuria PWSS (Zone-I) (Phase -II) within Gholepukuria JL-134(P) - (Gholepukuria Dakshin Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-E |  |  | ORD/000186/2020-2021 | 2752/TD | 27/01/2021 | 20 | PULAK KUMAR SAMANTA | 6.33 | 0 | 100
361 | Tamluk Division |  | Retrofitting to accomodate FHTC 121 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-E) |  |  | VCH/000130/2021-2022 | BP-2021-22-49 | 29/07/2021 | 0 | PULAK KUMAR SAMANTA | 0.97 | 0 | 0
362 | Tamluk Division |  | Retrofitting to accomodate FHTC 387 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/000191/2021-2022 | BP-2021-22-56 | 13/08/2021 | 0 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.11 | 0 | 0
363 | Tamluk Division |  | Retrofitting to accomodate FHTC 397 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000354/2021-2022 | BP-2021-22-116 | 05/10/2021 | 0 | ADHIKARY CONSTRUCTION | 9.55 | 0 | 0
364 | Tamluk Division |  | Retrofitting to accomodate FHTC 424 Nos. connection under JJM Gholpukuria Zone - I W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/000416/2021-2022 | BP-2021-22-146 | 03/11/2021 | 0 | FARID UDDIN AHMED | 16.5 | 0 | 0
365 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001103/2020-2021 | 1101/W | 30/03/2021 | 0 | ADHIKARY CONSTRUCTION | 10.54 | 0 | 0
366 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001104/2020-2021 | 1094/W | 30/03/2021 | 0 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.1 | 0 | 0
367 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - I W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001106/2020-2021 | 1114/W | 30/03/2021 | 0 | PULAK KUMAR SAMANTA | 5.34 | 0 | 0
368 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001133/2020-2021 | 1100/W | 30/03/2021 | 0 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 8.89 | 0 | 0
369 | Tamluk Division |  | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- A (Mouza-Guria JL-45.) |  |  | ORD/000176/2020-2021 | 2742/TD | 27/01/2021 | 20 | MADAN MOHAN MAITY | 9.51 | 4.07 | 100
370 | Tamluk Division |  | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- B (Mouza-GuriaJL-45). |  |  | ORD/000177/2020-2021 | 2743/TD | 27/01/2021 | 20 | G. S. CONSTRUCTION | 9.5 | 0 | 100
371 | Tamluk Division |  | Functional Household Tap connection to the 200 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- C (Mouza-Guria JL-45). |  |  | ORD/000178/2020-2021 | 2744/TD | 27/01/2021 | 20 | SUDIP MANNA | 9.5 | 1.78 | 100
372 | Tamluk Division |  | Functional Household Tap connection to the 531 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- D (Mouza-Betalbasan & Ghatual (282+249= 531 nos), JL-47 & 50. |  |  | ORD/000179/2020-2021 | 2745/TD | 27/01/2021 | 25 | BHOLANATH DEY | 25.08 | 4.72 | 100
373 | Tamluk Division |  | Functional Household Tap connection to the 140 nos. Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- E (Mouza-Narayanpur,JL-46). |  |  | ORD/000180/2020-2021 | 2746/TD | 27/01/2021 | 20 | SK. NUR ISLAM | 6.64 | 0 | 100
374 | Tamluk Division |  | Functional Household Tap connection to the 300 nos Household of Guria W/S scheme within Nandakumar Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District PART- F (Mouza-Narayanpur,JL-46). |  |  | ORD/000181/2020-2021 | 2747/TD | 27/01/2021 | 20 | MAA KALI CONSTRUCTION | 14.3 | 2.16 | 100
375 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000207/2023-2024 | 1107/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
376 | Tamluk Division |  | Functional Household Tap Connection for Guria W/S Scheme within Nandakumar Block Tamluk Division, PHE Dte. |  |  | VCH/001063/2020-2021 | 1106/W | 30/03/2021 | 0 | G. S. CONSTRUCTION | 9.28 | 0 | 0
377 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001110/2020-2021 | 1112/W | 30/03/2021 | 0 | SUDIP MANNA | 8.61 | 0 | 0
378 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001111/2020-2021 | 1098/W | 30/03/2021 | 0 | MAA KALI CONSTRUCTION | 12.11 | 0 | 0
379 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Guria W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001112/2020-2021 | 1108/W | 30/03/2021 | 0 | SK. NUR ISLAM | 6.01 | 0 | 0
380 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001134/2020-2021 |  | 17/03/2021 | 0 | MADAN MOHAN MAITY | 7.46 | 0 | 0
381 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001135/2020-2021 | 1096/W | 30/03/2021 | 0 | BHOLANATH DEY | 22.75 | 0 | 0
382 | Tamluk Division |  | Retrofitting to accomodate FHTC 200 Nos. connection under JJM Guria W/S Scheme within Nandakumar Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/001259/2020-2021 | 1105/W | 30/03/2021 | 0 | MADAN MOHAN MAITY | 7.46 | 0 | 0
383 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Paya(Mahaprabhu) PWSS Block- Ramnagar-I in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000280/2020-2021 | 2996/TD | 25/02/2021 | 30 | MAITY CONSTRUCTION | 99.11 | 72.39 | 100
384 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Paya (Mahaprabhu) W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001108/2020-2021 | 1087/W | 30/03/2021 | 0 | MAITY CONSTRUCTION | 24.87 | 0 | 0
385 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Bheribaranga PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000044/2021-2022 | 694/TD | 10/09/2021 | 60 | DAS CONSTRUCTION | 97.49 | 60.11 | 80
386 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Bheribharanga PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000414/2021-2022 | BP-2021-22-144 | 03/11/2021 | 0 | DAS CONSTRUCTION | 37.37 | 0 | 0
387 | Tamluk Division |  | Retrofitting to accomodate FHTC (1100 nos.) under JJM in Alinan -I & II PWSS(Balance Work) Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District . (Phase- II). |  |  | ORD/000002/2021-2022 | 692/TD | 10/09/2021 | 45 | TAPAS SANTRA | 58.58 | 0 | 100
388 | Tamluk Division |  | Retrofitting to accomodate FHTC (1100 Nos.) under JJM in Alinan Zone - I & II PWSS (Balance Work) Block - Sahid Matangini under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000357/2021-2022 | BP-2021-22-107 | 05/10/2021 | 0 | TAPAS SANTRA | 56.73 | 0 | 0
389 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 300 nos] under JJM in Uttar Khasda PWSS [Kulbaria(119,part),DakshinKhasda(120,part), Harichak(121,part),Akgerya(123,part), Palta Beria(128,part), Paschim Teghari(129,part), Tedubi(184,part), Uttar Khasda(185,part), Ulu Bere(186,part), Naraharichak(187,part), Dhangan(188,part),Paschim Jagannathchak(189,part), Rautara(193,part)] within Contai-I Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | ORD/000270/2020-2021 | 2923/TD | 22/02/2021 | 20 | SRIMANTA KUMAR MAITY | 26.25 | 0 | 100
390 | Tamluk Division |  | Retrofitting to accomodate for 300 Nos. FHTC connection under JJM in Uttar Khasda W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000254/2021-2022 |  | 24/08/2021 | 0 | SRIMANTA KUMAR MAITY | 23.49 | 0 | 0
391 | Tamluk Division |  | Retrofitting to accomodate for 300 Nos. FHTC connection under JJM in Uttar Khasda W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000312/2021-2022 | BP-2021-22-71 | 04/09/2021 | 0 | SRIMANTA KUMAR MAITY | 23.49 | 0 | 0
392 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 0.5 | 100
393 | Tamluk Division | Contai Sub-Division | Repairing of staircase and related works for R.C.C. Over Head Reservoir of capacity 350 Cum at Contai-II Block within Baharchandberya W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000253/2021-2022 | 516 / CSD | 29/11/2021 | 21 | LAKSHMI NARAYAN ENTERPRISE | 0.55 | 0 | 0
394 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Baharchandberya PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000343/2024-2025 | 3328/TD | 22/10/2024 | 40 | S R TRADING CORPORATION | 12.55 | 0 | 0
395 | Tamluk Division | Contai Sub-Division | Land Development for approach road for entry of Rig Machine for Replacement of 2nd Tube Well of Baharchandberya W/S Scheme within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000609/2023-2024 | 1583/CSD | 16/08/2023 | 15 | ABHIJIT BERA | 0.49 | 0 | 100
396 | Tamluk Division |  | Retrofitting to accommodate FHTC (335 Nos.) under JJM in Manikpur PWSS & Jalpai Part-II PWSS (Balance Part) Block -Nandigram-I & Nandigram-II in the District of Purba Medinipur. |  |  | ORD/000153/2021-2022 | 1124/TD | 22/11/2021 | 20 | SANKHA ENTERPRISE | 36.47 | 26.1 | 100
397 | Tamluk Division |  | Work order for laying of left out HDPE pipe line at Manikpur & Champainagar mouja for Manikpur & its Adjoining Mouzas W/S Scheme within Nandigram - I Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000297/2022-2023 | 599/HSD | 30/08/2022 | 10 | SANKHA ENTERPRISE | 2.46 | 2.46 | 100
398 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of ground water based Bahichberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of RCC Over Head Reservoir 900 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000003/2022-2023 | 56/TD | 05/04/2022 | 922 | JAYANTA KUMAR MONDAL | 952.26 | 892.78 | 99
399 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Baichberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000104/2022-2023 | 480/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.39 | 0 | 0
400 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bahichberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000135/2023-2024 | 270/TD | 20/04/2023 | 630 | S.K. MONDAL | 29.92 | 0 | 80
401 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bainchberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000159/2021-2022 | 1163/TD | 01/12/2021 | 7 | HORIZEN | 9.35 | 9.23 | 100
402 | Tamluk Division | Tamluk Sadar Sub-Division | Laying left out portion of 90 mm dia UPVC pipe line ( 3991.00 mtr ) with allied works to facilitating the FHTC connection for Bainchberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000289/2024-2025 | 3054/TD | 19/09/2024 | 25 | HYDROTECH ASSOCIATES | 17.58 | 0 | 0
403 | Tamluk Division | Tamluk Sadar Sub-Division | Laying left out portion of 90 mm dia UPVC pipe line ( 4227.0 mtr) with allied works to facilitating the FHTC connection for Bainchberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. ( Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000290/2024-2025 | 3055/TD | 19/09/2024 | 173 | MISHRA ENTERPRISE | 19.13 | 0 | 100
404 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000323/2022-2023 | 1232/TD | 07/09/2022 | 15 | J.S. CONSTRUCTION | 3.61 | 3.61 | 100
405 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Bahichberia PWSS within Nandakumar Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000324/2022-2023 | 1231/TD | 07/09/2022 | 15 | J.S. CONSTRUCTION | 3.14 | 3.14 | 100
406 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing Vehicle No-WB-29F-4919 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 07.08.2025 to 06.02.2026.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000404/2025-2026 | 2671/TSD | 06/08/2025 | 184 | KHOKAN SAMANTA | 0.87 | 0 | 10
407 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bahichberia Water Supply Scheme under Tamluk Sub Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000632/2022-2023 | 2482/TD | 16/01/2023 | 30 | SK. NUR ISLAM | 4.85 | 4.85 | 25
408 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Bahichberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000639/2022-2023 | 2483/TD | 16/01/2023 | 30 | S.K. MONDAL | 3.53 | 3.52 | 0
409 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling work for entrance approach & 3rd tube well site of Bahichberia Water Supply Scheme for augmentation of Bahichberia pwss under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000746/2022-2023 | 1086/TSD | 22/08/2022 | 15 | J.S. CONSTRUCTION | 1.72 | 1.54 | 100
410 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000012/2022-2023 | 84/TD | 08/04/2022 | 0 | Resource Division | 53.93 | 0 | 0
411 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000034/2022-2023 | 650/TD | 27/06/2022 | 0 | Resource Division | 39.34 | 0 | 0
412 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000055/2024-2025 | 2002/TD | 14/06/2024 | 0 | Resource Division | 2.64 | 0 | 0
413 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000202/2023-2024 | 1103/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
414 | Tamluk Division | Tamluk Sadar Sub-Division | Quotation money payment to WBSEDCL for GobindanagarZone-II Water Supply Scheme of Tube Well No. - IV | Assistant Engineer | Junior Engineer | BILL/00599/2023-2024 | BP-2023-24-324 | 29/08/2023 | 0 | WBSEDCL | 4.39 | 0 | 0
415 | Tamluk Division | Tamluk Sadar Sub-Division | Charges for entry of Household data in J.J.M. website along with House hold Addhar detai1s and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. The work should be taken up as per direction of Engineer-In-Charge. N.B. This item should be exclusively used for IMIS entry through J.J.M. | Assistant Engineer | Junior Engineer | ORD/000029/2022-2023 | 90/TD | 11/04/2022 | 30 | MISHRA ENTERPRISE | 4.85 | 4.85 | 100
416 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer | Junior Engineer | ORD/000088/2022-2023 | 424/TD | 27/05/2022 | 15 | TARUN KOLEY | 4.32 | 4.32 | 100
417 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Gobindanagar Zone-I & II PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte.(PART-B) | Assistant Engineer | Junior Engineer | ORD/000089/2022-2023 | 425/TD | 27/05/2022 | 15 | TARUN KOLEY | 3.65 | 3.65 | 100
418 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gobindanagar (Zone-I & Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000183/2021-2022 | 1192/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 9.26 | 9.26 | 100
419 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, and providing of FHTC for Rejuvenation of GOBINDANAGAR & its adjoining moujas Water Supply Scheme within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000409/2021-2022 | 1899/TD | 23/02/2022 | 180 | TARUN KOLEY | 554.16 | 519.2 | 100
420 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000728/2022-2023 | 2558/TD | 24/01/2023 | 60 | TARUN KOLEY | 73.36 | 0 | 100
421 | Tamluk Division | Tamluk Sadar Sub-Division | Land development and making approach road of 3 (three) nos. Boosting Tube Well site at Gobindanagar Water Supply Scheme of Panskura-I Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000729/2023-2024 | 2980/TD | 29/11/2023 | 20 | M/S. S. A. CONSTRUCTION | 5.11 | 0 | 0
422 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000017/2021-2022 | 1259/TD | 13/12/2021 | 0 | Resource Division | 4.42 | 0 | 0
423 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000027/2022-2023 | 417/TD | 25/05/2022 | 0 | Resource Division | 2.19 | 0 | 0
424 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000049/2021-2022 | 1954/TD | 04/03/2022 | 0 | Resource Division | 23.84 | 0 | 0
425 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -X(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000117/2020-2021 | 2504/TD | 23/12/2020 | 60 | JAYANTA KUMAR MONDAL | 96.37 | 192.59 | 100
426 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
427 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 2901/TD | 21/11/2023 | 0 | Resource Division | 13.69 | 0 | 0
428 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money at 3rd Pump House of Chapbasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00192/2023-2024 | BP-2023-24-95 | 07/06/2023 | 0 | WBSEDCL | 1.74 | 0 | 0
429 | Tamluk Division | Tamluk Sadar Sub-Division | Restoration estimate with sand filling and jhama -metal consolidation of link road to NH-41 along the bank of Sankarara Khal Road due to cutting of hard shoulder for laying water pipeliones by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00230/2023-2024 | BP-2023-24-115 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.05 | 0 | 0
430 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money of Chapbasan W/S Scheme for Tube Well No. - 2 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00366/2022-2023 | BP-2022-23-715 | 24/02/2023 | 0 | WBSEDCL | 4.16 | 0 | 0
431 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money of Chapbasan W/S Scheme for Tube Well No. ¿ 1 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00367/2022-2023 | BP-2022-23-715 | 24/02/2023 | 0 | WBSEDCL | 4.58 | 0 | 0
432 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of Souther Eastern Railway Track for Application ID SER-KGP-2021-WL-01 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01199/2023-2024 | BP-2023-24-567 | 07/11/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.22 | 0 | 0
433 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Chapbasan Water Supply Scheme within Tamluk Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000133/2022-2023 | 692/TD | 27/06/2022 | 180 | TARUN KOLEY | 724.76 | 531.29 | 75
434 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chapbasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000157/2021-2022 | 1161/TD | 01/12/2021 | 7 | HORIZEN | 9.49 | 9.05 | 100
435 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no. Diesel Motor Cabs(Luxury taxi commercial standard non air conditioned) Bharat stage-IV, bearing vehicle no-WB 29C 2453 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Tamluk Sub Division under Tamluk Division ,PHE Dte. within Purba Medinipur District For the period from 01.07.2024 to 31.12.2024.(06 Months) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000245/2024-2025 | 949/TSD | 28/06/2024 | 183 | DEBNATH MAITY | 0.87 | 0 | 0
436 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) (Bharat stage-IV) bearing vehicle no- WB-29B-2278 on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte. under Tamluk Division for the period from 01.08.2022 to30.09.2022. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000255/2022-2023 | 991/TSD | 27/07/2022 | 62 | DEBNATH MAITY | 0.19 | 0.4 | 100
437 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs & Maxi cab with Engine Capacity More than 2000 C.C. with (Air Condition) on monthly haring (per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.07.2022 to 31.12.2022. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000330/2022-2023 | 783/TSD | 29/06/2022 | 183 | KRISHNA MONDAL | 1.09 | 1.97 | 100
438 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & Renovation work of Boundary wall, Staff Quarter, Godown & approach Road at Chapbassan Store of Tamluk Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000330/2025-2026 | 1725/TD | 30/06/2025 | 45 | GOUTAM DEY | 44.99 | 0 | 0
439 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000375/2022-2023 | 1339/TD | 16/09/2022 | 25 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 4.46 | 3.77 | 100
440 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th Tube Well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000376/2022-2023 | 1340/TD | 16/09/2022 | 25 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 4.46 | 3.98 | 100
441 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chapbasan Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000377/2022-2023 | 1341/TD | 16/09/2022 | 25 | SWAPAN KUMAR MAITY | 4.55 | 1.93 | 100
442 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division ,PHE Dte. under Tamluk Division for the period from 01.10.2022 to 30.09.2023. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000501/2022-2023 | 1297/TSD | 29/09/2022 | 239 | DEBNATH MAITY | 1.14 | 4.29 | 100
443 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 1(one) nos M.S. Structure over irrigation canal to support 200 mm dia. DI K9 Rising Main under Chapbasan Water Supply Scheme at Pipulberia under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000528/2024-2025 | 38/TSD | 08/01/2025 | 20 | PULAK KUMAR SAMANTA | 1.58 | 0 | 100
444 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one Diesel motor cabs & Maxi cab with Engine capacity more than 2000 C.C. with (Air Condition) on monthly hiring (Per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.07.2023 to 31.12.2023 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000559/2023-2024 | 913/TSD | 30/06/2023 | 184 | KRISHNA MONDAL | 1.09 | 0 | 100
445 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main From 3rd Tube Well & 4 th Tube Well Site to O.H.R. Site and other allied works at Chapbasan Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000666/2022-2023 | 2351/TD | 10/01/2023 | 330 | PULAK KUMAR SAMANTA | 9.84 | 0 | 100
446 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no Diesel Motor Cabs & Maxi cab with Engine Capacity More than 2000 C.C. with (Air Condition) on monthly haring (per day) (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Engineering Chief Govt of West Bengal PHE Deptt. for the period from 01.01.2023 to 30.06.2023. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000753/2022-2023 | 1675/TSD | 30/12/2022 | 182 | KRISHNA MONDAL | 1.09 | 2.39 | 100
447 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub-Division, PHE Dte under Tamluk Division for the period from 01.04.2024 to 30.06.2024. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001287/2023-2024 | 551/TSD | 28/03/2024 | 50 | DEBNATH MAITY | 0.24 | 0 | 100
448 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000005/2022-2023 | 100/TD | 11/04/2022 | 0 | Resource Division | 56.47 | 0 | 0
449 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000065/2021-2022 | 643/TD | 27/06/2022 | 0 | Resource Division | 44.53 | 0 | 0
450 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000221/2023-2024 | 1120/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
451 | Tamluk Division | Digha Sub-Division | Repaire of Pump House , Boundary Wall construction of boundary wall & Land development approch road under JJM with allied work for Madhabpur (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000379/2023-2024 | 1023/TD | 07/06/2023 | 40 | KAMAL KUMAR ROY | 41.68 | 0 | 0
452 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000487/2022-2023 | 1909/TD | 25/11/2022 | 912 | OSMAN SEKH | 69.99 | 0 | 100
453 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-I Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000553/2022-2023 | 2183/TD | 20/12/2022 | 180 | GUPTA ENTERPRISE. | 638.56 | 82.65 | 15
454 | Tamluk Division | Digha Sub-Division | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Madhakhali Zone-I & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000587/2023-2024 | 2189/TD | 01/09/2023 | 45 | SWARUPANANDA DAS | 95.53 | 0 | 98
455 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline to accommodate FHTC for Augmentation of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000604/2023-2024 | 2197/TD | 01/09/2023 | 25 | DEBABRATA DAS | 16.53 | 0 | 0
456 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000111/2022-2023 | 1665/TD | 03/11/2022 | 0 | Resource Division | 141.02 | 0 | 0
457 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000283/2022-2023 | 2636/TD | 02/02/2023 | 0 | Resource Division | 18.68 | 0 | 0
458 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Electric Quotation money of Dakshin Gumai Water Supply Scheme for Tube Well No.- III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00434/2023-2024 | BP-2023-24-218 | 02/08/2023 | 0 | WBSEDCL | 3.12 | 0 | 0
459 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Gumai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000156/2021-2022 | 1160/TD | 01/12/2021 | 7 | HORIZEN | 8.24 | 8.12 | 100
460 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Rising Mains for Agumentation of Dakshin Gumai Water Supply Scheme under Nandakumar Block, under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000242/2024-2025 | 2682/TD | 22/08/2024 | 125 | GHOSH ENTERPRISE | 10.8 | 0 | 100
461 | Tamluk Division | Tamluk Sadar Sub-Division | Left out FHTC 402 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk SubDivision of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000279/2024-2025 | 2895/TD | 10/09/2024 | 360 | ARABINDA GHOSH | 91.84 | 0 | 56
462 | Tamluk Division | Tamluk Sadar Sub-Division | Dismantling of existing OHR (Capacity 61550 Gallons or 341000 Ltr.) at Head work site of Dakshin Gumai Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000376/2023-2024 | 1029/TD | 07/06/2023 | 45 | BISWAJIT BAG | 9.42 | 0 | 100
463 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of Distribution pipe line to accommodate FHTC (5547 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Dakshin Gumai Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000387/2022-2023 | 1420/TD | 26/09/2022 | 979 | ARABINDA GHOSH | 944.7 | 665.64 | 85
464 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st & 2nd tube well site of Dakshin Gumai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000421/2024-2025 | 3477/TD | 06/11/2024 | 30 | GLOBAL TRADE | 4.06 | 0 | 100
465 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 3.6 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for water supply scheme with Boundary Wall (as per Deptt. drawing) at 3rd Tube well site of Dakshin Gumai Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000732/2023-2024 | 2983/TD | 29/11/2023 | 45 | BHOWMIK & SONS | 11.41 | 0 | 72
466 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs (Luxary Taxi) (standard non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Executive Engineer, Tamluk Division, PHE Dte. under Tamluk Division for the period from 12 (twelve) months, w.e.f. 01/11/2022 to 31/10/2023. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001001/2022-2023 | 1344/TSD | 28/10/2022 | 239 | TAPAS SANTRA | 1.14 | 1.6 | 75
467 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000043/2022-2023 | 1016/TD | 08/08/2022 | 0 | Resource Division | 232.04 | 0 | 0
468 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000073/2022-2023 | 1257/TD | 12/09/2022 | 0 | Resource Division | 34.11 | 0 | 0
469 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000208/2023-2024 | 1108/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
470 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of PURBA MUKUNDAPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004720948/QUOT/03 DT. 07-05-2024 Application NO- 2004720948 Application type-New connection Consumer Id- 204298864 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00444/2024-2025 | BP-2024-25-171 | 07/06/2024 | 0 | WBSEDCL | 36.92 | 0 | 0
471 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000682/2023-2024 | 2711/TD | 30/10/2023 | 790 | TAPAS SANTRA | 938.36 | 0 | 40
472 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000164/2023-2024 | 118/TD | 05/01/2024 | 0 | Resource Division | 7.8 | 0 | 0
473 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000275/2022-2023 | 2699/TD | 06/02/2023 | 0 | Resource Division | 20.82 | 0 | 0
474 | Tamluk Division | Haldia Sub-Division | Land Development work at Head work site of Jaynagar Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000006/2025-2026 | 1082/TD | 07/04/2025 | 315 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 3.29 | 0 | 0
475 | Tamluk Division | Haldia Sub-Division | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 1st & 2nd Tube well of Jaynagar Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000142/2024-2025 | 2015/TD | 14/06/2024 | 232 | PRANTIK DRILLING AGENCY | 30.07 | 0 | 100
476 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000324/2023-2024 | 686/TD | 23/05/2023 | 1130 | RELIABLE CONSTRUCTIONS | 172.01 | 0 | 20
477 | Tamluk Division | Haldia Sub-Division | Construction of Box Culvert (5.00Mtr. X 3.50Mtr.) at 2nd Tube Well site of Jaynagar W/S Scheme within Sutahata Dev. Block under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000721/2023-2024 | 2943/TD | 23/11/2023 | 600 | M/S SOURAV MAHAPATRA | 5.33 | 0 | 50
478 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000791/2022-2023 | 3042/TD | 27/02/2023 | 1029 | RELIABLE CONSTRUCTIONS | 90.11 | 49.23 | 68
479 | Tamluk Division | Haldia Sub-Division | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (774 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000792/2022-2023 | 3043/TD | 27/02/2023 | 951 | ZENITH CONSTRUCTION | 89.68 | 45.99 | 55
480 | Tamluk Division | Haldia Sub-Division | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-I) [Jaynagar PWSS, Mohanpur PWSS, Erekhali PWSS & Hariballavpur PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000829/2023-2024 | 617/HSD, | 21/12/2023 | 7 | SNEHASIS BERA | 0.83 | 0 | 100
481 | Tamluk Division | Haldia Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000895/2022-2023 | 3345/TD | 22/03/2023 | 25 | M R ENTERPRISE | 30.84 | 0 | 0
482 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Jaynagar PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001046/2023-2024 | 376/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
483 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000163/2022-2023 | 2473/TD | 16/01/2023 | 0 | Resource Division | 30.03 | 0 | 0
484 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000190/2023-2024 | 639/W | 20/02/2024 | 0 | Resource Division | 13.39 | 0 | 0
485 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges (SER-KGP-2024-WL-47) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00135/2024-2025 | BP-2024-25-78 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0
486 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility(SER-KGP-2024-WL-48) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00136/2024-2025 | BP-2024-25-79 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.25 | 0 | 0
487 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000633/2022-2023 | 2314/TD | 05/01/2023 | 995 | DAS CONSTRUCTION | 456.2 | 0 | 0
488 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 63
489 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - A) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000670/2022-2023 | 2311/TD | 05/01/2023 | 983 | DAS CONSTRUCTION | 230.47 | 0 | 0
490 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000025/2023-2024 | 610/TD | 17/05/2023 | 0 | Resource Division | 23.76 | 0 | 0
491 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000104/2022-2023 | 1660/TD | 03/11/2022 | 0 | Resource Division | 143.41 | 0 | 0
492 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Baghadanri, JL No. - 246, Plot No. -495/1489) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000036/2022-2023 | 135/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 0 | 100
493 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1st Tubewell of Head Works site (Mouza - Baghadanri, JL No. - 246, Plot No. - 1029) of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000037/2022-2023 | 136/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 11.76 | 100
494 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate 1933 nos FHTC with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000079/2022-2023 | 384/TD | 20/05/2022 | 45 | DAS ENTERPRISE | 223.21 | 185.41 | 98
495 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000099/2022-2023 | 475/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
496 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate 1900 nos FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000199/2022-2023 | 817/TD | 12/07/2022 | 180 | DAS ENTERPRISE | 477.83 | 410.56 | 98
497 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhakhali Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000243/2022-2023 | 1003/TD | 08/08/2022 | 180 | DAS ENTERPRISE | 512.49 | 431.94 | 90
498 | Tamluk Division | Contai Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site at Madhakhali Zone-I Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000269/2022-2023 | 1092/TD | 25/08/2022 | 60 | SWARUPANANDA DAS | 6.34 | 0 | 100
499 | Tamluk Division | Contai Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW (Head Work) site at Madhakhali Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000270/2022-2023 | 1093/TD | 25/08/2022 | 60 | BIBEKANANDA DAS | 6.63 | 0 | 100
500 | Tamluk Division | Contai Sub-Division | i) Laying Rising main and other allied works Augmentation of Madhakhali Zone-II W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) iii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iv) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-II PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000349/2023-2024 | 878/TD | 01/06/2023 | 880 | M/S. PRADIP PRADHAN | 49.33 | 0 | 70
501 | Tamluk Division | Contai Sub-Division | Land Development at Head Work Site of Madhakhali Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000399/2023-2024 | 1097/CSD | 07/06/2023 | 15 | BIBEKANANDA DAS | 0.97 | 0.97 | 100
502 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000402/2022-2023 | 1178/TD | 05/09/2022 | 840 | SWARUPANANDA DAS | 3.81 | 0 | 100
503 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-II W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000403/2022-2023 | 1177/TD | 05/09/2022 | 60 | PARTHA CONSTRUCTION | 3.81 | 0 | 100
504 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Madhakhali Zone-I W/S Scheme within Bhagwanpur- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000404/2022-2023 | 1179/TD | 05/09/2022 | 60 | M/S. NEW DINDA ENTERPRISE | 3.53 | 0 | 100
505 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000452/2021-2022 | 1696/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.15 | 4.15 | 100
506 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madakhali (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000453/2021-2022 | 1697/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 3.42 | 3.27 | 100
507 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000489/2022-2023 | 1929/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.64 | 7.64 | 100
508 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Madhakhali Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000490/2022-2023 | 1930/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.42 | 5.42 | 100
509 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000561/2023-2024 | 2047/TD | 25/08/2023 | 40 | PADMA ENGINEERING CO. | 38.21 | 0 | 44
510 | Tamluk Division | Contai Sub-Division | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Madhakhali Zone-I PWSS within Bhagwanpur -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Laying Rising main and other allied works Augmentation of Madhakhali Zone-I W/S Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000893/2022-2023 | 3393/TD | 24/03/2023 | 532 | SWARUPANANDA DAS | 19.31 | 0 | 100
511 | Tamluk Division | Contai Sub-Division | M.S. Structures and allied works under Madhakhali Zone-I Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001178/2023-2024 | 722/TD | 28/02/2024 | 30 | DAS ENTERPRISE | 17.77 | 0 | 0
512 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC pipes with allied works due to uncovered area under of Madhakhali Zone-II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part - A + B + C + D). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001209/2023-2024 | 965/TD | 12/03/2024 | 40 | DAS ENTERPRISE | 100.28 | 0 | 90
513 | Tamluk Division | Contai Sub-Division | Land Development at HeadWorks site of Madhakhali Zone-II W/S Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001293/2023-2024 | 375/CSD | 23/02/2024 | 15 | PARTHA CONSTRUCTION | 0.97 | 0 | 100
514 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2022-2023 | 99/TD | 11/04/2022 | 0 | Resource Division | 53.75 | 0 | 0
515 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000068/2021-2022 | 646/TD | 27/06/2022 | 0 | Resource Division | 23.67 | 0 | 0
516 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000069/2021-2022 | 647/TD | 27/06/2022 | 0 | Resource Division | 20.06 | 0 | 0
517 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VIA Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000022/2021-2022 | 81/TD | 11/05/2021 | 60 | TITAS CONSTRUCTION | 53.3 | 51.1 | 100
518 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (653 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000884/2022-2023 | 3241/TD | 15/03/2023 | 992 | S.D. CONSTRUCTION | 70.26 | 26.2 | 80
519 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall, Rising Main & Accommodate FHTC (400 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000885/2022-2023 | 3242/TD | 15/03/2023 | 992 | S.D. CONSTRUCTION | 70.03 | 16.05 | 70
520 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line & Accommodate FHTC (110 nos) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000889/2022-2023 | 3243/TD | 15/03/2023 | 992 | MISHRA ENTERPRISE | 9.53 | 3.16 | 100
521 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & construction of 200 cum OHR (Intze type with pile foundation) under JJM with allied work for JAMITTA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000892/2022-2023 | 3394/TD | 24/03/2023 | 1013 | TAPAS SANTRA | 99.27 | 0 | 70
522 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with silver sand and land development of approach road and other side at 1st. & 2nd. T/W site at Jamitta Water Supply scheme of Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001194/2023-2024 | 829/TD | 05/03/2024 | 24 | S.D. CONSTRUCTION | 4.77 | 0 | 100
523 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000144/2023-2024 | 123/TD | 05/01/2024 | 0 | Resource Division | 7.16 | 0 | 0
524 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000303/2022-2023 | 3002/TD | 27/02/2023 | 0 | Resource Division | 19.42 | 0 | 0
525 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000136/2022-2023 | 2420/TD | 16/01/2023 | 0 | Resource Division | 34.51 | 0 | 0
526 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 0 | 30
527 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000032/2024-2025 | 1658/TD | 29/04/2024 | 0 | Resource Division | 14.83 | 0 | 0
528 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000198/2022-2023 | 2454/TD | 16/01/2023 | 0 | Resource Division | 39.75 | 0 | 0
529 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (725nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000069/2023-2024 | 139/TD | 10/04/2023 | 720 | S. B. ASSOCIATES | 83.67 | 0 | 55
530 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000238/2023-2024 | 499/TD | 11/05/2023 | 844 | BARH CONSTRUCTION | 131.4 | 63.42 | 70
531 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000240/2023-2024 | 503/TD | 11/05/2023 | 590 | SUDIP MANNA | 20.62 | 15.51 | 75
532 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000241/2023-2024 | 504/TD | 11/05/2023 | 594 | TAPAN BERA | 20.43 | 17.05 | 100
533 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos)within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000813/2022-2023 | 3103/TD | 02/03/2023 | 604 | MUKHERJEE ENTERPRISE | 19.22 | 4.34 | 26
534 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (25 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000814/2022-2023 | 3104/TD | 02/03/2023 | 1068 | MODERN CONSTRUCTION | 10.75 | 3.17 | 36
535 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000815/2022-2023 | 3105/TD | 02/03/2023 | 15 | DEBDUT CONSTRUCTION | 16.69 | 0 | 68
536 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work(50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000816/2022-2023 | 3106/TD | 02/03/2023 | 665 | TAPAN BERA | 21.6 | 18.71 | 90
537 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (30 nos)within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000817/2022-2023 | 3107/TD | 02/03/2023 | 662 | ELECTIVA ENTERPRISE | 4.53 | 2.62 | 50
538 | Tamluk Division | Haldia Sub-Division | Ground water based Hariballabhpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (50 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000827/2022-2023 | 3120/TD | 02/03/2023 | 20 | TAPAN BERA | 20.42 | 0 | 0
539 | Tamluk Division | Haldia Sub-Division | Construction of R.C.C. approach road at Head work site of Hariballabhpur & its adjoining mouzas Water Supply Scheme within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E.Dte.(Length of Approach Road-45mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000863/2023-2024 | 240/TD | 11/01/2024 | 20 | G. S. CONSTRUCTION | 4.78 | 0 | 0
540 | Tamluk Division | Haldia Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Hariballabhpur Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000896/2022-2023 | 3346/TD | 22/03/2023 | 25 | PRANTIK DRILLING AGENCY | 30.88 | 0 | 100
541 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000162/2022-2023 | 2471/TD | 16/01/2023 | 0 | Resource Division | 18.07 | 0 | 0
542 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000188/2023-2024 | 637/W | 20/02/2024 | 0 | Resource Division | 10.66 | 0 | 0
543 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1870 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PURBA RADHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000406/2023-2024 | 1090/TD | 08/06/2023 | 754 | DAS ENTERPRISE | 595.42 | 0 | 65
544 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Purba Radhapur at Bhagwanpur - I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000585/2024-2025 | 461/TD | 04/02/2025 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
545 | Tamluk Division | Contai Sub-Division | Wideing of approach road of Head work Site of Purba Radhapur PWSS under Bhagabanpur-I. Block under Contai Sub-Division of Tamluk Division , P.H.E. Dte Dist- Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000739/2023-2024 | 3066/TD | 30/11/2023 | 20 | PARTHA CONSTRUCTION | 3.89 | 0 | 100
546 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000165/2023-2024 | 86/TD | 05/01/2024 | 0 | Resource Division | 11.52 | 0 | 0
547 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000197/2022-2023 | 2383/TD | 16/01/2023 | 0 | Resource Division | 47.81 | 0 | 0
548 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000371/2023-2024 | 879/TD | 01/06/2023 | 961 | SANKHA ENTERPRISE | 1144 | 0 | 30
549 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000201/2022-2023 | 2438/TD | 16/01/2023 | 0 | Resource Division | 19.42 | 0 | 0
550 | Tamluk Division | Contai Sub-Division | Sinking tube well ,Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1418 nos), Including 2 years of Operation & Maintenance under JJM with allied work of Abas Berya PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000425/2023-2024 | 1414/TD | 12/07/2023 | 180 | SUDHAMAY MAJUMDAR | 462.29 | 0 | 45
551 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Abas Beriya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000450/2024-2025 | 3479/TD | 06/11/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
552 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000111/2023-2024 | 75/TD | 05/01/2024 | 0 | Resource Division | 9.71 | 0 | 0
553 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000238/2022-2023 | 2729/TD | 06/02/2023 | 0 | Resource Division | 19.06 | 0 | 0
554 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 4th & 5th Tube well of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000196/2024-2025 | 2321/TD | 23/07/2024 | 40 | MANNA COMPUTER | 39.77 | 0 | 0
555 | Tamluk Division | Haldia Sub-Division | Supply and delivery of CIDF sluice valve,construction of sluice valve chamber ,Canal crossing & pilling work of ground water based Natshal Lakshya (Zone-I) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(for Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000338/2023-2024 | 803/TD | 30/05/2023 | 30 | BARH CONSTRUCTION | 25.52 | 0 | 40
556 | Tamluk Division | Haldia Sub-Division | Supply and delivery of CIDF sluice valve,construction of sluice valve chamber ,Canal crossing & Rising main & pilling work of ground water based Natshal Lakshya (Zone-I) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(for Part-C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000340/2023-2024 | 805/TD | 30/05/2023 | 640 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 92.32 | 64.02 | 100
557 | Tamluk Division | Haldia Sub-Division | G.I pipe column with M.S. Structure for laying of Rising main pipe line at Natshal Lakshya (Zone-I) Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. (Total Length= (33+13+18+13+10+67)=154 mtr, | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000455/2024-2025 | 3703/TD | 03/12/2024 | 30 | TAPAN BERA | 18.16 | 0 | 100
558 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000491/2022-2023 | 1877/TD | 22/11/2022 | 30 | MODERN CONSTRUCTION | 4.06 | 4.01 | 100
559 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000492/2022-2023 | 1878/TD | 22/11/2022 | 60 | M/S SOURAV MAHAPATRA | 5.03 | 4.99 | 100
560 | Tamluk Division | Haldia Sub-Division | Construction of (5.40 Mtr. X 3.60 Mtr.) Chlorine Room including Plinth Protection at Natshal Lakshya Store within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000542/2024-2025 | 204/TD | 15/01/2025 | 160 | BHOWMIK & SONS | 6.18 | 0 | 80
561 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000543/2023-2024 | 1905/TD | 10/08/2023 | 40 | AQUATECH ENGINEER | 58.34 | 0 | 45
562 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in OHR site of Natshal Lakshya (Zone-I) Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-155mtr) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000610/2023-2024 | 2254/TD | 05/09/2023 | 45 | PRAMANIK AND ROY CONSTRUCTION | 13.18 | 0 | 100
563 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000903/2022-2023 | 3459/TD | 27/03/2023 | 1187 | SANKHA ENTERPRISE | 609.47 | 0 | 25
564 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000046/2022-2023 | 1013/TD | 08/08/2022 | 0 | Resource Division | 106.84 | 0 | 0
565 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 900 cum RCC OHR at Betkundu PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000175/2024-2025 | 2087/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
566 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Betkundu Water Supply Scheme by providing Laying of Distribution pipe line, FHTC work, Construction of R.C.C. Over Head Reservoir of capacity 900 cum and staging height 20.00 mtr. and Sub-Soil Investigation within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000417/2022-2023 | 1577/TD | 14/10/2022 | 930 | RAJ KUMAR SINGHA | 1014.31 | 624.14 | 68
567 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bethkundu Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000440/2021-2022 | 1543/TD | 11/01/2022 | 20 | HORIZEN | 4.88 | 4.88 | 100
568 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 4th Tube well Site of Betkundu Water Supply Scheme within mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000565/2023-2024 | 2051/TD | 25/08/2023 | 25 | DEV & COMPANY | 20.17 | 0 | 100
569 | Tamluk Division | Haldia Sub-Division | Culvert, Approach Road and Guard wall cum Boundery wall including land development at Headwork site of Betkundu Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000625/2023-2024 | 2367/TD | 12/09/2023 | 60 | BABUL DAS | 55.26 | 0 | 41
570 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube well site of BETKUNDU Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001155/2023-2024 | 731/HSD, | 15/02/2024 | 273 | NASIR ENTERPRISE | 2.81 | 0 | 100
571 | Tamluk Division | Haldia Sub-Division | Laying of Leftout Pipeline, Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement at 4th Tube Well site, Construction new Boundary Wall at 4th Tube well site and Laying of proposed Rising main line and inter connection at Betkundu Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001215/2023-2024 | 979/TD | 13/03/2024 | 45 | RAJ KUMAR SINGHA | 111.15 | 0 | 10
572 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000109/2022-2023 | 1673/TD | 03/11/2022 | 0 | Resource Division | 48.38 | 0 | 0
573 | Tamluk Division | Contai Sub-Division | Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1808 nos) under JJM with allied work for Barahat & its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000638/2023-2024 | 2481/TD | 26/09/2023 | 977 | MAA ANANDAMAYEE | 547.32 | 0 | 35
574 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000323/2022-2023 | 2993/TD | 27/02/2023 | 0 | Resource Division | 2.69 | 0 | 0
575 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Rising main ,Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 150Cum OHR ( Intze type with pile foundatio ) Pipe Carrying canal crossing Structure & Accommodate FHTC ( 960 Nos) Including 2 years of Operation & Maintenance under JJM with allied work for Padima & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000548/2023-2024 | 1987/TD | 21/08/2023 | 864 | ONKAR ENTERPRISE | 339.12 | 77.85 | 50
576 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Padima PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000883/2023-2024 | 205/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
577 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000161/2023-2024 | 99/TD | 05/01/2024 | 0 | Resource Division | 5.91 | 0 | 0
578 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000311/2022-2023 | 2998/TD | 27/02/2023 | 0 | Resource Division | 23.63 | 0 | 0
579 | Tamluk Division | Contai Sub-Division | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Itaberia Mugberia Road from 1.25 Km. To 3.10 Km. for laying water pipe line of Dakshin Patherbaria PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00991/2024-2025 | BP-2024-25-494 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.12 | 0 | 0
580 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1373 nos) under JJM with allied work of DAKSHIN PATHAR BERYA AND IT'S ADJOINING MOUJAS PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000278/2023-2024 | 555/TD | 12/05/2023 | 900 | PATHIK PABAN NANDI | 460.76 | 0 | 50
581 | Tamluk Division | Contai Sub-Division | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Dakshin Patharberya PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000579/2024-2025 | 457/TD | 04/02/2025 | 40 | B. K. ENTERPRISE | 26.35 | 0 | 0
582 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000184/2023-2024 | 633/W | 20/02/2024 | 0 | Resource Division | 8.46 | 0 | 0
583 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000340/2022-2023 | 2967/TD | 27/02/2023 | 0 | Resource Division | 35.37 | 0 | 0
584 | Tamluk Division | Tamluk Sadar Sub-Division | Land development work at Headwork Site of Gathra Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000127/2024-2025 | 1925/TD | 07/06/2024 | 14 | S. P. ENTERPRISE (GSTIN- 19FLFPR7861R1ZS) | 4.23 | 0 | 100
585 | Tamluk Division | Tamluk Sadar Sub-Division | Work order for installation of 18 nos Dispaly Board at different PWSS works site under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000197/2024-2025 | 2279/TD | 18/07/2024 | 7 | GLOBAL TRADE | 3.95 | 0 | 100
586 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000134/2023-2024 | 129/TD | 05/01/2024 | 0 | Resource Division | 11.19 | 0 | 0
587 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000210/2022-2023 | 2468/TD | 16/01/2023 | 0 | Resource Division | 17.41 | 0 | 0
588 | Tamluk Division | Contai Sub-Division | Quotation money for shifting of 11 KV OH Henria Feeder at Bajkul for Bajukl Zone-I PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01686/2023-2024 | BP-2023-24-744 | 04/01/2024 | 0 | WBSEDCL | 2.08 | 0 | 0
589 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC(2596 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - I Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000486/2022-2023 | 1892/TD | 24/11/2022 | 1103 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 440.22 | 209.57 | 78
590 | Tamluk Division | Contai Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000560/2022-2023 | 2243/TD | 29/12/2022 | 40 | R K CONSTRUCTION | 39.67 | 12.07 | 0
591 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-I Water Supply Scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000575/2023-2024 | 2184/TD | 01/09/2023 | 936 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.41 | 0 | 70
592 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000888/2021-2022 | 1802/TD | 08/02/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.3 | 100
593 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2023-2024 | 607/TD | 17/05/2023 | 0 | Resource Division | 15.99 | 0 | 0
594 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000115/2022-2023 | 1670/TD | 03/11/2022 | 0 | Resource Division | 95.79 | 0 | 0
595 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-G ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000071/2023-2024 | 173/TD | 11/04/2023 | 1020 | AYSAN KHAN | 19.97 | 0 | 60
596 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 238 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000284/2023-2024 | 563/TD | 12/05/2023 | 1019 | LOKENATH ENTERPRISES | 119.04 | 0 | 60
597 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundatio ) & Accommodate FHTC ( 414 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000412/2023-2024 | 1098/TD | 08/06/2023 | 992 | FIROZ KHAN | 199.26 | 0 | 30
598 | Tamluk Division | Digha Sub-Division | Canal crossing Structure for laying of Distribution line from Sapua Bridge towards Chaulkhola parallel of NH-116B for Islampur & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000442/2024-2025 | 3538/TD | 13/11/2024 | 450 | AYSAN KHAN | 21.61 | 0 | 100
599 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000536/2023-2024 | 1839/TD | 08/08/2023 | 40 | MRINAL KANTI PRADHAN | 84.49 | 0 | 65
600 | Tamluk Division | Digha Sub-Division | Laying of Balance Distribution HDPE Pipe Line(225 mm dia) for Islampur Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000706/2023-2024 | 2872/TD | 17/11/2023 | 20 | A. K. SIKDAR | 9.42 | 0 | 99
601 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000865/2022-2023 | 3179/TD | 10/03/2023 | 1117 | LOKENATH ENTERPRISES | 84.26 | 0 | 65
602 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000866/2022-2023 | 3180/TD | 10/03/2023 | 15 | ANUPAM CONSTRUCTION | 19.85 | 0 | 62
603 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-F ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000868/2022-2023 | 3181/TD | 10/03/2023 | 15 | ANUPAM CONSTRUCTION | 19.87 | 0 | 60
604 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-H ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000869/2022-2023 | 3182/TD | 10/03/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 6.81 | 0 | 95
605 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000143/2023-2024 | 103/TD | 05/01/2024 | 0 | Resource Division | 13 | 0 | 0
606 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000157/2022-2023 | 2464/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0
607 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000105/2023-2024 | 170/TD | 10/04/2023 | 30 | SK MAIDUL ISLAM | 40.83 | 28.21 | 78
608 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000145/2024-2025 | 2061/TD | 24/06/2024 | 20 | KISHORE GHOSH | 14.87 | 0 | 0
609 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (450 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000248/2023-2024 | 526/TD | 11/05/2023 | 180 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 172.54 | 37 | 22
610 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) (Balance Part) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000275/2024-2025 | 2902/TD | 10/09/2024 | 520 | TARUN KHATUA | 68.16 | 0 | 50
611 | Tamluk Division | Tamluk Sadar Sub-Division | Land Development work at Head work site & 2nd Tube well site of Urddhabmal Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000381/2024-2025 | 1008/HSD, | 04/10/2024 | 480 | TARUN KHATUA | 4.85 | 0 | 50
612 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (260 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000784/2022-2023 | 3035/TD | 27/02/2023 | 60 | R K CONSTRUCTION | 97.19 | 26.22 | 30
613 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000785/2022-2023 | 3036/TD | 27/02/2023 | 30 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 39 | 22.77 | 65
614 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(137 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000786/2022-2023 | 3037/TD | 27/02/2023 | 20 | M/S BLUE BIRD | 15.92 | 0 | 0
615 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000787/2022-2023 | 3038/TD | 27/02/2023 | 20 | SAYAN MAITY | 20.13 | 17.36 | 87
616 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000788/2022-2023 | 3039/TD | 27/02/2023 | 20 | M/S BLUE BIRD | 15.99 | 13.44 | 85
617 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (120nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000789/2022-2023 | 3040/TD | 27/02/2023 | 20 | SUDIP MANNA | 15.47 | 9.32 | 65
618 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(130nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000790/2022-2023 | 3041/TD | 27/02/2023 | 20 | SAYAN MAITY | 19.92 | 14.14 | 72
619 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Urddhabmal Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000894/2022-2023 | 3344/TD | 22/03/2023 | 25 | M R ENTERPRISE | 30.86 | 0 | 50
620 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC(140 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000913/2022-2023 | 3559/TD | 29/03/2023 | 632 | S. B. ASSOCIATES | 57.43 | 46.53 | 85
621 | Tamluk Division | Tamluk Sadar Sub-Division | Ground water based Urddhabmal Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (230nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000914/2022-2023 | 3560/TD | 29/03/2023 | 1022 | S. B. ASSOCIATES | 67.13 | 40.57 | 65
622 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000160/2022-2023 | 2475/TD | 16/01/2023 | 0 | Resource Division | 17 | 0 | 0
623 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000192/2023-2024 | 641/W | 20/02/2024 | 0 | Resource Division | 11.07 | 0 | 0
624 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (850 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000258/2023-2024 | 536/TD | 12/05/2023 | 648 | GIRI CONSTRUCTION | 191.14 | 0 | 42
625 | Tamluk Division | Contai Sub-Division | Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (511 nos) under JJM with allied work of Manikjor PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000391/2023-2024 | 1050/TD | 07/06/2023 | 180 | TARUN KOLEY | 222.99 | 0 | 22
626 | Tamluk Division | Contai Sub-Division | Sinking of (2 nos.) 250 x 150mm Dia and 230mtr deep tubewell Drilling by Direct Rotary method with 150mm dia. uPVC Strainer of 30mtr length all complete including cost of materials for 1st & 2nd Tubewell of Manikjore PWSS under Bhagwanpur-II Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, Purba Medinipur PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000580/2024-2025 | 458/TD | 04/02/2025 | 40 | B. K. ENTERPRISE | 26.18 | 0 | 0
627 | Tamluk Division | Contai Sub-Division | Laying Distribution pipe line & Accommodate FHTC (330 nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000910/2022-2023 | 3465/TD | 27/03/2023 | 45 | SUBHENDU HAZRA | 76.59 | 0 | 60
628 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 180nos) under JJM with allied work of MANIKJOR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000911/2022-2023 | 3466/TD | 27/03/2023 | 302 | SUBRATA KUMAR BERA | 28.31 | 16.28 | 60
629 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000176/2023-2024 | 625/W | 20/02/2024 | 0 | Resource Division | 12.23 | 0 | 0
630 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000296/2022-2023 | 2961/TD | 27/02/2023 | 0 | Resource Division | 33.37 | 0 | 0
631 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line,Pump House, Accommodate FHTC & Boundary Wall (400 nos) under JJM with allied work for PANCH BAJARI PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000064/2023-2024 | 134/TD | 10/04/2023 | 719 | JAI BHARAT COMMERCIAL CORPORATION | 78.91 | 0 | 65
632 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Pump House & Accommodate FHTC (315 nos), Boundary Wall under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000065/2023-2024 | 135/TD | 10/04/2023 | 45 | SOUMYA ENTERPRISE | 53.18 | 0 | 67
633 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (100 nos) under JJM with allied work for PANCH BAJARI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000066/2023-2024 | 136/TD | 10/04/2023 | 1065 | SUDIP MANNA | 19.43 | 0 | 60
634 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Panch Bajari, Manikjor, Bahadurpur, Kayemgerya, & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001166/2023-2024 | 2327/CSD | 29/12/2023 | 15 | M/S. NEW DINDA ENTERPRISE | 0.83 | 0 | 100
635 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000175/2023-2024 | 624/W | 20/02/2024 | 0 | Resource Division | 6.25 | 0 | 0
636 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000294/2022-2023 | 2960/TD | 27/02/2023 | 0 | Resource Division | 33.17 | 0 | 0
637 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Tilkhoja PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000876/2023-2024 | 198/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
638 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000014/2024-2025 | 1570/TD | 23/04/2024 | 0 | Resource Division | 14.36 | 0 | 0
639 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000180/2022-2023 | 2432/TD | 16/01/2023 | 0 | Resource Division | 27.95 | 0 | 0
640 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Natshal Lakshya Water Supply Scheme (Zone- I) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000015/2022-2023 | 49/TD | 05/04/2022 | 20 | RADIANT | 5.76 | 5.75 | 100
641 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 19.25 | 75
642 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part -C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000336/2022-2023 | 1278/TD | 12/09/2022 | 90 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 416.22 | 307.87 | 80
643 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part -B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000338/2022-2023 | 1288/TD | 13/09/2022 | 60 | BARH CONSTRUCTION | 205.99 | 124.95 | 65
644 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (3772 Nos) work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000903/2022-2023 | 3459/TD | 27/03/2023 | 1187 | SANKHA ENTERPRISE | 609.47 | 0 | 25
645 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000045/2022-2023 | 1014/TD | 08/08/2022 | 0 | Resource Division | 15.11 | 0 | 0
646 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000071/2022-2023 | 1255/TD | 12/09/2022 | 0 | Resource Division | 50.47 | 0 | 0
647 | Tamluk Division | Haldia Sub-Division | Quotation payment for shifting of 11 KV line at Gobindapur on Full deposit of scheme of Asadtalia PWSS of Sutathat Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00538/2023-2024 | BP-2023-24-282 | 17/08/2023 | 0 | WBSEDCL | 2.92 | 0 | 0
648 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Asadtalia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000188/2021-2022 | 1197/TD | 02/12/2021 | 20 | RADIANT | 3.95 | 3.82 | 100
649 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2nd tube well site of Asadtalia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000257/2022-2023 | 1068/TD | 22/08/2022 | 45 | BUNBA CONSTRUCTION | 3.95 | 3.51 | 100
650 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Asadtalia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000374/2021-2022 | 1815/TD | 11/02/2022 | 1145 | HARIPADA PATTANAYAK | 303.25 | 227.69 | 85
651 | Tamluk Division | Haldia Sub-Division | Laying Rising main, laying left out pipe line, canal crossing and supporting work with Drum Sheet walling and Earth filling in Asadtalia Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000550/2022-2023 | 2168/TD | 19/12/2022 | 768 | HARIPADA PATTANAYAK | 64.43 | 54.65 | 100
652 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice Valve for Asadtalia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000625/2021-2022 | 2186/TD | 17/03/2022 | 20 | BAGLAMUKHI SECURITY SERVICE | 3.61 | 3.61 | 100
653 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000021/2021-2022 | 1263/TD | 13/12/2021 | 0 | Resource Division | 11.63 | 0 | 0
654 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000055/2021-2022 | 1868/TD | 17/02/2022 | 0 | Resource Division | 10.22 | 0 | 0
655 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (82 Nos) under JJM with allied work for FATEPUR PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000466/2024-2025 | 3722/TD | 04/12/2024 | 30 | MAITY CONSTRUCTION | 14.16 | 0 | 0
656 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000132/2023-2024 | 107/TD | 05/01/2024 | 0 | Resource Division | 2.32 | 0 | 0
657 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000269/2022-2023 | 2697/TD | 06/02/2023 | 0 | Resource Division | 4.51 | 0 | 0
658 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 210 Nos) under JJM with allied work for Chirulia-Chatla (Zone-III) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000407/2023-2024 | 1089/TD | 08/06/2023 | 1028 | AJIT KUMAR SOM | 233.68 | 0 | 85
659 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000495/2022-2023 | 1931./TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.46 | 100
660 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000034/2023-2024 | 2063/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
661 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000091/2023-2024 | 2994/TD | 29/11/2023 | 0 | Resource Division | 1.29 | 0 | 0
662 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000228/2023-2024 | 474/TD | 10/05/2023 | 60 | GIRI ENTERPRISE | 3.71 | 0 | 100
663 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000229/2023-2024 | 475/TD | 10/05/2023 | 60 | GIRI ENTERPRISE | 3.71 | 0 | 100
664 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting TW site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000230/2023-2024 | 476/TD | 10/05/2023 | 60 | GIRI CONSTRUCTION | 3.71 | 0 | 100
665 | Tamluk Division | Contai Sub-Division | Laying of 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 1(One) no. Boosting Tubewell for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri - I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000233/2023-2024 | 477/TD | 10/05/2023 | 300 | KOUSHIK MALLICK | 3.22 | 0 | 100
666 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000317/2023-2024 | 663/TD | 19/05/2023 | 30 | GIRI CONSTRUCTION | 6.94 | 0 | 100
667 | Tamluk Division | Contai Sub-Division | Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000318/2023-2024 | 664/TD | 19/05/2023 | 30 | DAS ENTERPRISE | 6.91 | 0 | 100
668 | Tamluk Division | Contai Sub-Division | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000394/2023-2024 | 1083/TD | 08/06/2023 | 20 | M/S. NEW DINDA ENTERPRISE | 5.07 | 0 | 100
669 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Mukutshila Zone-II PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.)For Low Land. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000438/2023-2024 | 1421/TD | 12/07/2023 | 30 | M/S. NEW DINDA ENTERPRISE | 6.93 | 0 | 0
670 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -N) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000456/2023-2024 | 1501/TD | 17/07/2023 | 20 | THE GODFATHER TRADING COMPANY | 5.24 | 0 | 65
671 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000124/2023-2024 | 106/TD | 05/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
672 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000268/2022-2023 | 2695/TD | 06/02/2023 | 0 | Resource Division | 4.13 | 0 | 0
673 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000082/2024-2025 | 2970/TD | 12/09/2024 | 0 | Resource Division | 6.11 | 0 | 0
674 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000171/2022-2023 | 2395/TD | 16/01/2023 | 0 | Resource Division | 25.23 | 0 | 0
675 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (291 nos) under JJM with allied work for ASTICHAK (ZONE-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000635/2023-2024 | 2444/TD | 19/09/2023 | 984 | HALDIA DEVELOPMENT CONSTRUCTION | 446.88 | 0 | 55
676 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000856/2021-2022 | 1472/TD | 03/01/2022 | 20 | APEX ENGINEERING | 3.99 | 3.99 | 100
677 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Astichak Zone-I PWSS at Egra-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001048/2023-2024 | 378/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
678 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000044/2023-2024 | 2078/TD | 28/08/2023 | 0 | Resource Division | 24.42 | 0 | 0
679 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000106/2023-2024 | 3009/TD | 29/11/2023 | 0 | Resource Division | 7.95 | 0 | 0
680 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 819 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 0 | 48
681 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000320/2022-2023 | 2974/TD | 27/02/2023 | 0 | Resource Division | 49.63 | 0 | 0
682 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. and repairing as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Kaktiya Water Supply Scheme within Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000135/2022-2023 | 690/TD | 27/06/2022 | 1188 | TAPAS SANTRA | 965.88 | 855.74 | 86
683 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 16.11 | 100
684 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanktya Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000367/2021-2022 | 1631/TD | 18/01/2022 | 20 | HORIZEN | 5.27 | 5.25 | 100
685 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000389/2022-2023 | 1428/TD | 26/09/2022 | 27 | PRANTIK DRILLING AGENCY | 49.66 | 15 | 80
686 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000657/2022-2023 | 2342/TD | 10/01/2023 | 40 | TARUN KHATUA | 5.11 | 5.1 | 0
687 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Kanktia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000658/2022-2023 | 2343/TD | 10/01/2023 | 40 | SUDIP MANNA | 5.11 | 5.11 | 100
688 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of rising main, Left out pipe line with FHTC (200 nos.) work for Kanktia PWSS in Sahid Matangini Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000854/2022-2023 | 3208/TD | 14/03/2023 | 1024 | TAPAS SANTRA | 68.55 | 46.63 | 72
689 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000037/2022-2023 | 653/TD | 27/06/2022 | 0 | Resource Division | 26.13 | 0 | 0
690 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000077/2022-2023 | 1260/TD | 12/09/2022 | 0 | Resource Division | 44.52 | 0 | 0
691 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (130Nos) under JJM with allied work for KANPUR (Zone -IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000316/2024-2025 | 3183/TD | 30/09/2024 | 240 | GHOSH CONSTRUCTION | 95.27 | 0 | 85
692 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000458/2022-2023 | 1857/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.38 | 100
693 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 209 Nos) under JJM with allied work for KANPUR (Zone-IV) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000508/2023-2024 | 1730/TD | 31/07/2023 | 970 | ONKAR ENTERPRISE | 308.34 | 0 | 40
694 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kanpur Zone- IV PWSS at Ramnagar - II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000869/2023-2024 | 191/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
695 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000043/2023-2024 | 2068/TD | 28/08/2023 | 0 | Resource Division | 13.67 | 0 | 0
696 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000102/2023-2024 | 3005/TD | 29/11/2023 | 0 | Resource Division | 1.29 | 0 | 0
697 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000018/2023-2024 | 116/TD | 06/04/2023 | 40 | AQUATECH ENGINEERS | 74.22 | 34.96 | 100
698 | Tamluk Division | Tamluk Sadar Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Habichak Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000305/2023-2024 | 602/TD | 17/05/2023 | 45 | SOUMEN KUMAR GHOSH | 25.91 | 0 | 100
699 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000003/2023-2024 | 352/TD | 26/04/2023 | 0 | Resource Division | 8.83 | 0 | 0
700 | Tamluk Division | Contai Sub-Division | Laying distribution System, Construction of Pump House Accommodate FHTC (1100 nos) & Rising Main including interconnection for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000432/2023-2024 | 1407/TD | 12/07/2023 | 80 | BARH CONSTRUCTION | 205.81 | 0 | 50
701 | Tamluk Division | Contai Sub-Division | Laying distribution System & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000433/2023-2024 | 1408/TD | 12/07/2023 | 80 | UCON | 204.9 | 0 | 25
702 | Tamluk Division | Contai Sub-Division | Laying distribution System & Accommodate FHTC (897 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000434/2023-2024 | 1409/TD | 12/07/2023 | 786 | SWADHIN KUMAR CHAKRABORTY | 211.86 | 0 | 40
703 | Tamluk Division | Contai Sub-Division | Laying distribution System, Construction of Pump House, Construction of Boundary Wall & Accommodate FHTC (1250 nos) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000435/2023-2024 | 1410/TD | 12/07/2023 | 716 | NARAYAN CHANDRA DAS | 200.01 | 0 | 45
704 | Tamluk Division | Contai Sub-Division | Soil investigation, R.C.C. Elevated Reservoir of capacity 550cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) for Nunhunda And Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000633/2023-2024 | 2441/TD | 19/09/2023 | 529 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 178.22 | 0 | 0
705 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000159/2023-2024 | 133/TD | 05/01/2024 | 0 | Resource Division | 27.7 | 0 | 0
706 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000293/2022-2023 | 2959/TD | 27/02/2023 | 0 | Resource Division | 54.95 | 0 | 0
707 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well, Construction of Pump House, 50 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (314 nos.), Installation of display Board, under JJM with allied work including 02 (two) Years Operation & Maintenance of Ajangechhya PWSS within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000077/2023-2024 | 208/TD | 13/04/2023 | 899 | RELIABLE CONSTRUCTIONS | 135.23 | 26.21 | 45
708 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000224/2022-2023 | 2675/TD | 06/02/2023 | 0 | Resource Division | 4.96 | 0 | 0
709 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000222/2022-2023 | 2677/TD | 06/02/2023 | 0 | Resource Division | 23.37 | 0 | 0
710 | Tamluk Division |  | Functional Household Tap Connection to the 1174 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Srirampur(118) Bagmari(116)] |  |  | ORD/000229/2020-2021 | 2864/TD | 09/02/2021 | 30 | SWARUPANANDA DAS | 57.51 | 0 | 100
711 | Tamluk Division |  | Functional Household Tap Connection to the 836 nos. Household of Bagmari W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [Dwarakapur(115) Rannagarpur(119) Dhusurda(239) Kashimpur(240) Joykrishnapur(114)PART] |  |  | ORD/000230/2020-2021 | 2865/TD | 09/02/2021 | 30 | S.K. MONDAL | 38.92 | 25.89 | 100
712 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000371/2021-2022 | BP-2021-22-114 | 05/10/2021 | 0 | SWARUPANANDA DAS | 7.5 | 0 | 0
713 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000429/2021-2022 | 302/W | 05/10/2021 | 0 | SWARUPANANDA DAS | 2.87 | 0 | 0
714 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001142/2020-2021 | 1118/W | 30/03/2021 | 0 | S.K. MONDAL | 25.94 | 0 | 0
715 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bagmari W/S Scheme within Potashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001219/2020-2021 | 965/W | 22/03/2021 | 0 | SWARUPANANDA DAS | 47.13 | 0 | 0
716 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Basudevpur PWSS Block Egra-II in the District of Purba Medinipur. |  |  | ORD/000125/2020-2021 | 2629/TD | 05/01/2021 | 60 | SNEHESH SEN | 87.4 | 87.39 | 100
717 | Tamluk Division |  | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0 | 65
718 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Bamunia PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000030/2020-2021 | 2106/TD | 05/11/2020 | 180 | JAYANTA KR. MONDAL | 74.72 | 0 | 100
719 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000374/2021-2022 | BP-2021-22-121 | 05/10/2021 | 0 | JAYANTA KUMAR MONDAL | 3.99 | 0 | 0
720 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000430/2021-2022 | 303/W | 05/10/2021 | 0 | JAYANTA KUMAR MONDAL | 5 | 0 | 0
721 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000601/2020-2021 | 639/W | 13/01/2021 | 0 | JAYANTA KUMAR MONDAL | 54.64 | 0 | 0
722 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Bamunia W/S Scheme within Contai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001242/2020-2021 | 995/W | 26/03/2021 | 0 | JAYANTA KUMAR MONDAL | 10.33 | 0 | 0
723 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -II(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000122/2020-2021 | 2631/TD | 05/01/2021 | 60 | MAA ANANDAMAYEE | 96.97 | 192 | 100
724 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS (Zone-I)Block -Nandigram-II in the District of Purba Medinipur. |  |  | ORD/000118/2020-2021 | 2503/TD | 23/12/2020 | 60 | M/S. CHANDI CHARAN MISHRA & CO. | 76.13 | 31.88 | 100
725 | Tamluk Division |  | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 0 | 100
726 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000464/2021-2022 | 296/W | 07/10/2021 | 0 | M/S. CHANDI CHARAN MISHRA & CO. | 21.89 | 0 | 0
727 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - I W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001207/2020-2021 | 936/W | 18/03/2021 | 0 | M/S. CHANDI CHARAN MISHRA & CO. | 22.35 | 0 | 0
728 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (409 nos) under JJM in Tajpur PWSS within Dijam Talya - JL No.-149 (Dijam Talya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000211/2020-2021 | 2823/TD | 05/02/2021 | 20 | MRITYUNJOY PARIA | 19.4 | 12.43 | 100
729 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (429 nos) under JJM in Tajpur PWSS within Bar Jamtalya - JL No.-148 (Bar Jamtalya) & Nandanayak Bar - J.L. - 179 (Nandanayak Bar) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000212/2020-2021 | 2824/TD | 05/02/2021 | 20 | SK. NUR ISLAM | 20.36 | 8.35 | 100
730 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Bartalya - JL No.-209 (Bartalya) & Chargalya (P) - J.L. - 150 (Chargalya) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000213/2020-2021 | 2825/TD | 05/02/2021 | 25 | KRISHNENDU SEKHAR DAS | 27.98 | 0 | 100
731 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (590 nos) under JJM in Tajpur PWSS within Chargalya (P) - J.L. - 150 (Chargalya) & Tajpur (P) - J.L. - 210 (Tajpur & Tajpur Paschim Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-G) | Assistant Engineer | Junior Engineer | ORD/000214/2020-2021 | 2826/TD | 05/02/2021 | 25 | DEBASIS DAS | 27.75 | 0 | 100
732 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (100 nos) under JJM in Mahammadpur PWSS within Khariberia JL No.-183 (Khariberia) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000261/2020-2021 | 2877/TD | 11/02/2021 | 20 | TAPAN BERA | 4.84 | 0 | 100
733 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (102 nos) under JJM in Tajpur PWSS within Tajpur (P) J.L.- 210 (Tajpur Dakshin Pally) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000262/2020-2021 | 2878/TD | 11/02/2021 | 20 | BUNBA CONSTRUCTION | 4.85 | 0 | 100
734 | Tamluk Division | Haldia Sub-Division | Retrofitting to accommodate FHTC (673 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185 (Dakshin Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-C) [2nd Call] | Assistant Engineer | Junior Engineer | ORD/000273/2020-2021 | 2926/TD | 22/02/2021 | 25 | TARUN KOLEY | 31.71 | 0 | 100
735 | Tamluk Division | Haldia Sub-Division | Laying Left Out UPVC pipe line of Mouza- Di-jamtalya for Tajpur & its adjoinin Mouzas Water Supply Scheme within Nandigram - I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000527/2021-2022 | 1944/TD | 03/03/2022 | 15 | MRITYUNJOY PARIA | 4.85 | 4.64 | 100
736 | Tamluk Division | Haldia Sub-Division | Construction of Approach Road for Mahammadpur PWSS RCC Elevated Reservoir of Capacity 350 Cum. Within Nandigram-I Block under Haldia Sub-Division of Tamluk Division., P.H.E. Dte.Length = 150.00 Mtr Width = 3.0 Mtr. Thickness = 150 mm | Assistant Engineer | Junior Engineer | ORD/001214/2023-2024 | 983/TD | 13/03/2024 | 40 | SATYABRATA BHAUMIK | 5.74 | 0 | 100
737 | Tamluk Division | Haldia Sub-Division | Retrofitting of accommodate FHTC 100 Nos. under JJM in Mahammadpur W/S Scheme within Nandigram - I Block. | Assistant Engineer | Junior Engineer | VCH/000192/2021-2022 | BP-2021-22-60 | 13/08/2021 | 0 | TAPAN BERA | 4.84 | 0 | 0
738 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC for Tajpur W/S Scheme | Assistant Engineer | Junior Engineer | VCH/000201/2021-2022 | BP-2021-22-62 | 13/08/2021 | 0 | BUMBA CONSTRUCTION | 4.84 | 0 | 0
739 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC 741 Nos. connection under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | VCH/000253/2021-2022 | BP-2021-22-72 | 04/09/2021 | 0 | NARAYAN CHANDRA DAS | 16.12 | 0 | 0
740 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate for 409 Nos. FHTC connection under JJM in Tajpur W/S Scheme within Nandigram - I Dev. Block Block under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer | VCH/000255/2021-2022 | BP-2021-22-69 | 04/09/2021 | 0 | MRITYUNJOY PARIA | 6.98 | 0 | 0
741 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC (673 Nos.) under JJM in Mahammadpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/000322/2021-2022 | BP-2021-22-88 | 05/10/2021 | 0 | TARUN KOLEY | 32.35 | 0 | 0
742 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC 590 Nos. connection under JJM Tajpur W/S Scheme within Nandigram - I Dev. Block under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer | Junior Engineer | VCH/000349/2021-2022 | BP-2021-22-118 | 05/10/2021 | 0 | KRISHNENDU SEKHAR DAS | 13.48 | 0 | 0
743 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001097/2020-2021 | 1102/W | 30/03/2021 | 0 | SK. NUR ISLAM | 12 | 0 | 0
744 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Tajpur W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001098/2020-2021 | 1095/W | 30/03/2021 | 0 | KRISHNENDU SEKHAR DAS | 14.5 | 0 | 0
745 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM Mahammadpur W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001109/2020-2021 | 1093/W | 30/03/2021 | 0 | NARAYAN CHANDRA DAS | 19.15 | 0 | 0
746 | Tamluk Division | Haldia Sub-Division | Retrofitting to accomodate FHTC under JJM in Tajpur W/S Scheme within Nandigram ¿ I Dev. Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001136/2020-2021 | 1097/W | 30/03/2021 | 0 | DEBASIS DAS | 13.78 | 0 | 0
747 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Keshabpur Jalpai PWSS Block - Mahishadal in the District of Purba Medinipur. |  |  | ORD/000225/2020-2021 | 2843/TD | 08/02/2021 | 70 | RAJ KUMAR SINGHA | 222.76 | 0 | 100
748 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000107/2021-2022 |  | 23/06/2021 | 0 | RAJ KUMAR SINGHA | 116.52 | 0 | 0
749 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000240/2021-2022 | BP-2021-22-34 | 23/07/2021 | 0 | RAJ KUMAR SINGHA | 116.52 | 0 | 0
750 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000310/2021-2022 |  | 16/09/2021 | 0 | RAJ KUMAR SINGHA | 78.17 | 0 | 0
751 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000423/2021-2022 | BP-2021-22-105 | 05/10/2021 | 0 | RAJ KUMAR SINGHA | 78.17 | 0 | 0
752 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Keshabpur Jalpai W/S Scheme within Mahishadal Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001137/2020-2021 | 1090/W | 30/03/2021 | 0 | RAJ KUMAR SINGHA | 28.06 | 0 | 0
753 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Sankarpur PWSS Block - Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000124/2020-2021 | 2637/TD | 05/01/2021 | 60 | MAITY CONSTRUCTION | 94.92 | 186.18 | 100
754 | Tamluk Division |  | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0 | 65
755 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block-Ramnagar-II in the District of Purba Medinipur. |  |  | ORD/000123/2020-2021 | 2634/TD | 05/01/2021 | 60 | BASANTA KUMAR MAITY | 96.58 | 3.47 | 100
756 | Tamluk Division |  | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0 | 65
757 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001037/2020-2021 | 715/W | 09/02/2021 | 0 | BASANTA KUMAR MAITY | 59.24 | 0 | 0
758 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001160/2020-2021 | BP-2021-22-29 | 19/07/2021 | 0 | BASANTA KUMAR MAITY | 13.32 | 0 | 0
759 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanpur W/S Scheme within Ramnagar - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001244/2020-2021 | 991/W | 26/03/2021 | 0 | BASANTA KUMAR MAITY | 20.5 | 0 | 0
760 | Tamluk Division |  | Rejuvenation to accommodate FHTC (670 nos.) under JJM in BADHIA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( Phase -II ) |  |  | ORD/000098/2021-2022 | 691/TD | 10/09/2021 | 20 | AJIT KUMAR SOM | 94.24 | 89.52 | 100
761 | Tamluk Division |  | Supply of C.I D.F sluice valve to accommodate FHTC under JJM in BADHYA PWSS Block-Ramnagar-I in the district of Purba Medinipur ( phase -II ) |  |  | ORD/000349/2021-2022 | 617/DSD | 31/01/2022 | 15 | AJIT KUMAR SOM | 1.03 | 1.03 | 100
762 | Tamluk Division |  | Laying ( Left Out ) UPVC pipe line to accommodate FHTC under JJM in Badhya PWSS within Ramnagar-I Block ( To support Phase-I FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. ( Mouza- Kachum, Bakharpur, Khandagram, Badhya) |  |  | ORD/000543/2021-2022 | 2003/TD | 08/03/2022 | 25 | R CONSTRUCTION | 10.79 | 10.79 | 100
763 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 1234/TD | 09/12/2021 | 0 | Resource Division | 0.08 | 0 | 0
764 | Tamluk Division |  | Retrofitting to accomodate FHTC (1487 nos.) under JJM in Paschim Kamarda PWSS Block - Contai-III under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) |  |  | ORD/000010/2021-2022 | 688/TD | 10/09/2021 | 50 | RAJ KUMAR SINGHA | 96.99 | 170.64 | 100
765 | Tamluk Division |  | Sinking of 2 (two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Tubewell Site (Mouza- Panbhuni, JL No. - 163, Plot No. 551) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube Tubewell Site (Mouza- Nilpur, JL No. - 160, Plot No. 318) of Paschim Kamarda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000271/2022-2023 | 1095/TD | 25/08/2022 | 21 | M/S SYCHROTECH INDUSTRY | 26.31 | 0 | 0
766 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block - Contai-II in the District of Purba Medinipur. Mouza- Sofiabad(497),Dholmari(498),Kultalia(500),(Phase-II) |  |  | ORD/000129/2021-2022 | 1009/TD | 02/11/2021 | 30 | RELIABLE CONSTRUCTIONS | 35.54 | 35.66 | 100
767 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000056/2024-2025 | 2162/TD | 05/07/2024 | 0 | Resource Division | 0.81 | 0 | 0
768 | Tamluk Division |  | Supply & Delivery of different dia C.I.D.F. Sluice Valve for Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the district of Purba Medinipur (Phase-II) under Contai Sub- Division, of Tamluk Division, PHE Dte. |  |  | ORD/000046/2022-2023 | 12/A/CSD | 05/04/2022 | 15 | SRIMANTA KUMAR MAITY | 1.89 | 1.89 | 100
769 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Haipur PWSS Block-Contai-I in the district of Purba Medinipur.(Phase-II) |  |  | ORD/000296/2021-2022 | 1637/TD | 19/01/2022 | 60 | SRIMANTA KUMAR MAITY | 118.38 | 105.84 | 100
770 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC (245 nos.) at Jashdumbur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000022/2022-2023 | 64/TD | 05/04/2022 | 20 | PULAK KUMAR SAMANTA | 28.02 | 23.63 | 100
771 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-1) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000095/2022-2023 | 455/TD | 01/06/2022 | 15 | GRAND CONSTRUCTION | 4.84 | 4.78 | 100
772 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-2) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000096/2022-2023 | 456/TD | 01/06/2022 | 15 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.84 | 4.82 | 100
773 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-3) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000097/2022-2023 | 457/TD | 01/06/2022 | 15 | MISHRA ENTERPRISE | 4.84 | 4.83 | 100
774 | Tamluk Division | Tamluk Sadar Sub-Division | AUGMENTATION OF GROUND WATER BASED BISHNUBAR PWSS TO ACCOMMODATE FHTC AT BISHNUBAR MOUZA IN TAMLUK BLOCK UNDER TAMLUK SUB DIVISION OF TAMLUK DIVISION IN PURBA MEDINIPUR DISTRICT (PART-B-A-4) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000098/2022-2023 | 458/TD | 01/06/2022 | 15 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100
775 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-A(PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000177/2023-2024 | 334/TD | 25/04/2023 | 30 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 58.58 | 54.39 | 100
776 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Bishnubar water supply scheme in Tamluk Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.PART-C-B(PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000178/2023-2024 | 335/TD | 25/04/2023 | 20 | PULAK KUMAR SAMANTA | 6.91 | 5.83 | 100
777 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling with earth of approach road and other side of 3rd T/W site at Bishnubar Water Supply scheme of Tamluk Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000206/2022-2023 | 857/TD | 21/07/2022 | 7 | KRISHNENDU SEKHAR DAS | 4.82 | 4.8 | 100
778 | Tamluk Division | Tamluk Sadar Sub-Division | Repair & renovation of exisiting pump house and boundary wall at OHR site & 2nd tube well site of Bishnubar PWSS Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000366/2023-2024 | 934/TD | 01/06/2023 | 30 | MOYNA TECHNOLINK ENGINEER'S CO-OP SOCIETY LTD. | 18.32 | 0 | 100
779 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bishnubar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000368/2021-2022 | 1632/TD | 18/01/2022 | 20 | HORIZEN | 3.35 | 3.35 | 100
780 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Purbakola Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- G ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000380/2022-2023 | 1364/TD | 22/09/2022 | 25 | SOUMYA ENTERPRISE | 30.53 | 30.43 | 30
781 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Bishnubar & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000447/2022-2023 | 1820/TD | 14/11/2022 | 870 | HARIPADA PATTANAYAK | 163.96 | 61.7 | 100
782 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Bishnubar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000546/2022-2023 | 2164/TD | 19/12/2022 | 60 | SK. SAHALAM | 5.11 | 5.1 | 100
783 | Tamluk Division | Tamluk Sadar Sub-Division | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at 3nd tube well site under Bishnubar Water Supply Scheme. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000547/2022-2023 | 2165/TD | 19/12/2022 | 45 | SK. SAHALAM | 5.83 | 5.81 | 0
784 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-A-5) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000606/2021-2022 | 2194/TD | 21/03/2022 | 20 | MADAN MOHAN MAITY | 23.06 | 22.96 | 100
785 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000607/2021-2022 | 2195/TD | 21/03/2022 | 30 | ROMEO ENGINEER'S CO-OP SOCIETY LTD. | 39.96 | 39.89 | 100
786 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Bishnubar Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-B-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000608/2021-2022 | 2196/TD | 21/03/2022 | 20 | CEM ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.98 | 20.77 | 100
787 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jashdumber Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-C-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000609/2021-2022 | 2197/TD | 21/03/2022 | 30 | GHOSH ENTERPRISE | 45.02 | 44.98 | 85
788 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Maishali Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000610/2021-2022 | 2198/TD | 21/03/2022 | 35 | BIDHAN MONDAL | 74.98 | 55.63 | 100
789 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Melahait & Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- E & I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000611/2021-2022 | 2199/TD | 21/03/2022 | 35 | KRISHNENDU SEKHAR DAS | 74.87 | 74.82 | 85
790 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Naikuri Jagannath Chak-I & Khas Panchpukhuria Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- F & J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000612/2021-2022 | 2200/TD | 21/03/2022 | 35 | S.K. MONDAL | 77.9 | 77.77 | 100
791 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Hirapur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-A ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000613/2021-2022 | 2201/TD | 21/03/2022 | 20 | G. S. CONSTRUCTION | 20.87 | 11.62 | 100
792 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Bishnubar PWSS to Accommodate FHTC at Jotankur Mouza in Tamluk Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (PART- H-B ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000614/2021-2022 | 2202/TD | 21/03/2022 | 20 | DEBDUT CONSTRUCTION | 20.89 | 20.57 | 100
793 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000003/2022-2023 | 80/TD | 08/04/2022 | 0 | Resource Division | 38.98 | 0 | 0
794 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000059/2021-2022 | 2350/TD | 31/03/2022 | 0 | Resource Division | 23.8 | 0 | 0
795 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000217/2023-2024 | 1117/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
796 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (2488 nos.) under JJM in MUKUNDAPUR PWSS Block- Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000041/2022-2023 | 172/TD | 25/04/2022 | 30 | M/S EL-CON | 90.6 | 0 | 60
797 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to damaged by the construction of connecting Road & to Accommodate balance FHTC (290 Nos) with allied work for Mukundapur Piped Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000296/2024-2025 | 3065/TD | 19/09/2024 | 30 | BASANTA KUMAR MAITY | 35.18 | 0 | 0
798 | Tamluk Division |  | Retrofitting to accommodate FHTC (300 Nos.) under JJM in Srirampur PWSS (PART-I) Block - Tamluk in the District of Purba Medinipur. |  |  | ORD/000154/2021-2022 | 1125/TD | 22/11/2021 | 40 | GHOSH ENTERPRISE | 19.58 | 18.98 | 100
799 | Tamluk Division | Contai Sub-Division | Renovation and new Construction of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Bhagabanpur Zone-II Water Supply Scheme in Bhagabanpur-I Dev. Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2025-2026 | 1077/TD | 07/04/2025 | 40 | RAI CONSTRUCTION | 18.27 | 0 | 0
800 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bhagwanpur Zone-II Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000151/2022-2023 | 726/TD | 04/07/2022 | 180 | TARUN KOLEY | 595.09 | 418.59 | 83
801 | Tamluk Division | Contai Sub-Division | Laying of 200 mm dia & 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well & 2nd Tube well to 3rd Tube Well (Additional) of Augmentation of Bhagwanpur Zone II & its adjoining mouzas Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000166/2023-2024 | 297/TD | 20/04/2023 | 30 | BARH CONSTRUCTION | 11.04 | 8.14 | 100
802 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-I Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000228/2022-2023 | 893/TD | 25/07/2022 | 15 | SRIMANTA KUMAR MAITY | 4.8 | 4.8 | 100
803 | Tamluk Division | Contai Sub-Division | Construction and Commissioning of R.C.C. Over Head Reservoir of capacity 500 cum and staging height 20.00 mtr, as per Departmental Drawing no-PC-1/O.H.R./5/2012 for Rejuvination of Bhagwanpur Zone-I Water Supply Scheme under Bhagwanpur-I Block of Contai sub-Division of Tamluk Division, P.H.E. Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000238/2020-2021 | 2839/TD | 05/02/2021 | 200 | DAS CONSTRUCTION | 118.1 | 15.5 | 90
804 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia UPVC pipe lines with allied works to accommodate Total 5666 nos FHTC of Augmentation of Bhagwanpur Zone-I & its adjoining mouzas W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000309/2023-2024 | 623/TD | 17/05/2023 | 30 | TAPAS SANTRA | 67.97 | 55.64 | 85
805 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000311/2022-2023 | 1224/TD | 07/09/2022 | 857 | B. K. ENTERPRISE | 34.31 | 0 | 0
806 | Tamluk Division | Contai Sub-Division | Repairing of Boundary Wall, and Pump House (1st & 2nd) under JJM with allied work for Augmentation of Bhagabanpur Zone -II PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000317/2024-2025 | 3216/TD | 01/10/2024 | 120 | SAMIT KUMAR MONDAL | 8.34 | 0 | 100
807 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main, Approach Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000333/2024-2025 | 3293/TD | 05/10/2024 | 120 | SAMIT KUMAR MONDAL | 31.76 | 0 | 60
808 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-II W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000348/2022-2023 | 1281/TD | 12/09/2022 | 60 | BISWA NIRMAN ENTERPRISE. | 3.82 | 0 | 100
809 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 125 mm dia & 80 mm dia Sluice Valve for Bhagwanpur Zone-II Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-B) (Supply at Mukutshila Store) 2nd Call. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000357/2022-2023 | 1299/TD | 13/09/2022 | 15 | NANDY UDYOG | 4.83 | 4.83 | 100
810 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-I piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000358/2022-2023 | 1297/TD | 13/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.41 | 3.41 | 100
811 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (4th) Tube Well site for Augmentation of Bhagwanpur Zone-I Water Supply Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000400/2022-2023 | 1344/TD | 19/09/2022 | 60 | M/S SOURAV MAHAPATRA | 3.82 | 0 | 0
812 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additional (3rd) Tube Well site for Augmentation of Bhagwanpur Zone-I W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000405/2022-2023 | 1345/TD | 19/09/2022 | 60 | GIRI CONSTRUCTION | 3.82 | 0 | 100
813 | Tamluk Division | Contai Sub-Division | Supply & Delivery of 100mm,150mm,200mm,250mm & 300mm dia Sluice Valve for Bhagwanpur Zone-II piped Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Part-A) (Supply at Mukutshila Store). 2nd Call. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000406/2022-2023 | 1300/TD | 13/09/2022 | 15 | PARTHA CONSTRUCTION | 3.23 | 3.23 | 100
814 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000445/2021-2022 | 1676/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.46 | 4.46 | 100
815 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhagawanpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000446/2021-2022 | 1677/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.19 | 4.19 | 100
816 | Tamluk Division | Contai Sub-Division | Interconection work Between 2nd pump and 3rd pump , of Augementation of Bhagabanpur Zone-II water supply scheme under Contai Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000568/2024-2025 | 2445/CSD | 22/10/2024 | 21 | BARH CONSTRUCTION | 0.52 | 0 | 0
817 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia UPVC Pipe Lines With allied works to accommodate Total 4010 nos FHTC of Augementation of Bhagabanpur Zone -II Water Supply Scheme within Bhagabanpur -I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000708/2023-2024 | 2874/TD | 17/11/2023 | 30 | TARUN KOLEY | 79.77 | 0 | 100
818 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main, Approch Road , Repairing work of Boundary wall and Pump House, under JJM with allied work for Augmentation of Bhagabanpur Zone -I PWSS in Bhagwanpur-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001180/2023-2024 | 725/TD | 28/02/2024 | 40 | M/S. PRADIP PRADHAN | 32.11 | 0 | 0
819 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000015/2022-2023 | 403/TD | 25/05/2022 | 0 | Resource Division | 102.66 | 0 | 0
820 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000016/2022-2023 | 404/TD | 25/05/2022 | 0 | Resource Division | 28.11 | 0 | 0
821 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000090/2022-2023 | 1272/TD | 12/09/2022 | 0 | Resource Division | 59.54 | 0 | 0
822 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Kapaseria Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 100 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000050/2022-2023 | 269/TD | 02/05/2022 | 1340 | MONDAL PRECISION PRIVATE LIMITED | 222.44 | 119.87 | 60
823 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kapasberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000163/2021-2022 | 1167/TD | 01/12/2021 | 7 | HORIZEN | 3.42 | 3.31 | 100
824 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.52 | 100
825 | Tamluk Division | Haldia Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kapaseria Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000387/2023-2024 | 1051/TD | 07/06/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.73 | 3.73 | 100
826 | Tamluk Division | Haldia Sub-Division | Construction of New Boundary Wall at H/W site & 2nd TW Site of Kapasaria Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall- 80mtr at H/W Site & 50mtr at 2nd TW Site) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000514/2024-2025 | 3948/TD | 23/12/2024 | 190 | ANIRBAN BHOWMIK | 15.18 | 0 | 0
827 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line and inter connection including repairing & renovation of switch room cum chlorine room at Head work site of Kapasaria Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000697/2023-2024 | 2737/TD | 01/11/2023 | 20 | R CONSTRUCTION | 8.2 | 0 | 10
828 | Tamluk Division | Haldia Sub-Division | Construction Temporary Approach road by Brick Bats & Carried Earth over Nayanjuli of PWD Roads for H/W Site of Kapasaria W/S Scheme for accessibility of Rig Machine and removal of road materials from Nayanjuli of PWD Roads under Haldia Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000812/2023-2024 | 576/HSD, | 08/12/2023 | 7 | SNEHASIS BERA | 0.8 | 0 | 100
829 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Kapaseria Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000822/2023-2024 | 3286/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.41 | 0 | 30
830 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000012/2021-2022 | 1254/TD | 13/12/2021 | 0 | Resource Division | 10.46 | 0 | 0
831 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000043/2021-2022 | 639/TD | 27/06/2022 | 0 | Resource Division | 5.6 | 0 | 0
832 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kalindi Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000172/2021-2022 | 1181/TD | 02/12/2021 | 20 | HORIZEN | 6.91 | 5.92 | 100
833 | Tamluk Division | Digha Sub-Division | Supply of 125 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000211/2022-2023 | 323/DSD | 15/07/2022 | 7 | BASANTA KUMAR MAITY | 1.32 | 1.32 | 100
834 | Tamluk Division | Digha Sub-Division | Supply of 80 mm.dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000371/2022-2023 | 1049/TD | 17/08/2022 | 7 | BASANTA KUMAR MAITY | 4.72 | 4.72 | 100
835 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house I & II, Boundary Wall at head works & 2nd tube well site of Kalindi Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000372/2024-2025 | 3401/TD | 28/10/2024 | 40 | DAS ENTERPRISE. | 9.65 | 0 | 0
836 | Tamluk Division | Digha Sub-Division | Supply & delevary of 100 mm,200mm,150mm & 250mm dia C.I D.F sluice valve for laying distribution & rising main pipe line of Kalindi W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000445/2022-2023 | 1155/TD | 31/08/2022 | 7 | BASANTA KUMAR MAITY | 4.28 | 4.28 | 100
837 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line by UPVC pipes with allied works for complete balance FHTC under Kalindi & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000468/2023-2024 | 1449/TD | 13/07/2023 | 30 | BASANTA KUMAR MAITY | 24.44 | 0 | 100
838 | Tamluk Division | Digha Sub-Division | Augmentation of ground water based Kalindi Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000605/2021-2022 | 2185/TD | 17/03/2022 | 180 | BASANTA KUMAR MAITY | 533.41 | 355.97 | 50
839 | Tamluk Division | Digha Sub-Division | Laying Rising Main Pipe Line With allied Works For Augmentation Of KALINDI Water Supply Scheme In Ramnagar-II Block Of Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000872/2022-2023 | 3223/TD | 14/03/2023 | 20 | ABHIJIT BERA | 6.86 | 0 | 100
840 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000018/2021-2022 | 1260/TD | 13/12/2021 | 0 | Resource Division | 21.19 | 0 | 0
841 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000051/2021-2022 | 2348/TD | 31/03/2022 | 0 | Resource Division | 16.82 | 0 | 0
842 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 53/TD | 05/04/2022 | 60 | MUNNA AGROTECH ENTERPRISE | 150.85 | 99.71 | 90
843 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Haur PWSS & its adjoining moujas within Panskura Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000038/2022-2023 | 137/TD | 19/04/2022 | 90 | ASIS KUMAR SARANGI | 192.27 | 114.53 | 90
844 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Haur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000182/2021-2022 | 1191/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.95 | 5.95 | 100
845 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Left out portion of pipe line Rejuvenation & Retrofitting of of HAUR PWSS under Tamluk Sub Division, PHE Dte. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000295/2024-2025 | 3064/TD | 19/09/2024 | 25 | KAMALA ENTERPRISE | 14.42 | 0 | 100
846 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of Boundary Wall ( 1mtr height) & Painting Pump House and Boundary wall & other allied works at 1 st TW site, Dismantling of Existing B/W & Construction of Boundary Wall with Gate and along PCC road & other allied works at 2nd TW site of Haur Pipe Water Supply Scheme, within Panskura-I Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000632/2024-2025 | 736/TD | 07/03/2025 | 40 | SINHA BUILDERS | 9.71 | 0 | 0
847 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000039/2021-2022 | 2343/TD | 31/03/2022 | 0 | Resource Division | 11.07 | 0 | 0
848 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000211/2023-2024 | 1111/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
849 | Tamluk Division | Contai Sub-Division | Bill for Restoration of damage of Heria Mugberia Road at 1.80 KM caused due to lying of PHE water pipe line across the road under Tamluk Highway Division of Mukutshilla Zone-II PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00989/2024-2025 | BP-2024-25-495 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.19 | 0 | 0
850 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000245/2022-2023 | 1002/TD | 08/08/2022 | 1257 | GIRI CONSTRUCTION | 106.79 | 73.24 | 88
851 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -B). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000248/2022-2023 | 1039/TD | 16/08/2022 | 45 | I. S. ENTERPRISE. | 154.56 | 102.85 | 70
852 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000258/2022-2023 | 1079/TD | 23/08/2022 | 1196 | RELIABLE CONSTRUCTIONS | 130.52 | 103.15 | 80
853 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000282/2022-2023 | 1112/TD | 29/08/2022 | 180 | M/S. CARE | 361.65 | 38 | 18
854 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000365/2022-2023 | 1332/TD | 16/09/2022 | 20 | PULAK KUMAR SAMANTA | 28 | 23.39 | 85
855 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000366/2022-2023 | 1333/TD | 16/09/2022 | 20 | SUBRATA KUMAR BERA | 35.6 | 23.71 | 70
856 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000367/2022-2023 | 1334/TD | 16/09/2022 | 25 | THREE MAA ENTERPRISE | 41.22 | 23.41 | 85
857 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000368/2022-2023 | 1335/TD | 16/09/2022 | 25 | ANUSKA ENTERPRISE | 51.96 | 26.54 | 75
858 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000374/2022-2023 | 1338/TD | 16/09/2022 | 30 | A. K. SIKDAR | 69.34 | 36.22 | 60
859 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2022-2023 | 1387/TD | 23/09/2022 | 25 | NEW STAR CONSTRUCTION | 76.73 | 56.18 | 85
860 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000529/2022-2023 | 2100/TD | 13/12/2022 | 1193 | M/S. NEW DINDA ENTERPRISE | 41.85 | 29.42 | 85
861 | Tamluk Division | Contai Sub-Division | Land Filling & allied works for Boosting Tube Well (5Th TW) site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000546/2023-2024 | 1488/A/CSD | 03/08/2023 | 15 | KAMAL KUMAR BERA | 0.72 | 0 | 100
862 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000564/2022-2023 | 2241/TD | 29/12/2022 | 20 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LIMITED | 32.16 | 19.73 | 65
863 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. (PART -I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000668/2022-2023 | 2341/TD | 10/01/2023 | 25 | MRINAL KANTI PRADHAN | 44.01 | 32.43 | 0
864 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000055/2022-2023 | 1195/TD | 06/09/2022 | 0 | Resource Division | 186.74 | 0 | 0
865 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000065/2022-2023 | 1197/TD | 06/09/2022 | 0 | Resource Division | 47.95 | 0 | 0
866 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID ¿ SER-KGP-2023-WL-33 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00373/2023-2024 | BP-2023-24-204 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
867 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-31 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00374/2023-2024 | BP-2023-24-202 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
868 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-32 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00375/2023-2024 | BP-2023-24-203 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
869 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone- II PWSS for Application ID ¿ SER-KGP-2023-WL-30 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00376/2023-2024 | BP-2023-24-201 | 25/07/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 1.06 | 0 | 0
870 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone-II PWSS for Application ID-SER-KGP-2023-WL-34 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00493/2023-2024 | BP-2023-24-256 | 10/08/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0
871 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-B for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000131/2024-2025 | 1911/TD | 07/06/2024 | 25 | DEBABRATA DAS | 14.72 | 0 | 90
872 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-D for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000137/2024-2025 | 1948/TD | 10/06/2024 | 244 | DEBABRATA DAS | 10.35 | 0 | 80
873 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of (PART M) for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri I Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000281/2024-2025 | 3036/TD | 18/09/2024 | 543 | M/S. NEW DINDA ENTERPRISE | 4.18 | 0 | 0
874 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 1000 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-II water supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART -A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000282/2022-2023 | 1112/TD | 29/08/2022 | 180 | M/S. CARE | 361.65 | 0 | 18
875 | Tamluk Division | Contai Sub-Division | Laying Distribution pipe line by HDPE pipes with allied works for Left Out Area of PART-K for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000286/2024-2025 | 3051/TD | 19/09/2024 | 542 | M/S. NEW DINDA ENTERPRISE | 49.94 | 0 | 0
876 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2022-2023 | 1223/TD | 07/09/2022 | 40 | KALPANA BUILDERS | 71.97 | 49.28 | 48
877 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorine Room & Boundary Wall at 2nd TW site & 1st TW site for Augmentation of Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000354/2024-2025 | 3317/TD | 22/10/2024 | 40 | M/S. NEW DINDA ENTERPRISE | 7.08 | 0 | 100
878 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-J for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000417/2024-2025 | 2184/CSD | 05/09/2024 | 150 | GIRI ENTERPRISE | 1.85 | 0 | 0
879 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-D) In between OHE MAST NO 33/1 & 33/2 , Nodal Point 5 to 109. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000556/2024-2025 | 138/CSD | 16/01/2025 | 20 | DEBABRATA DAS | 1.16 | 0 | 100
880 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-E) In between OHE MAST NO 31/13 & 31/14, Nodal Point 64 to 68. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000557/2024-2025 | 139/CSD | 16/01/2025 | 20 | M/S SREE DURGA ENTERPRISE | 1.16 | 0 | 100
881 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-F) In between OHE MAST NO 32/4 & 32/5, Nodal Point 18 to 19. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000558/2024-2025 | 140/CSD | 16/01/2025 | 20 | DEBABRATA DAS | 1.16 | 0 | 100
882 | Tamluk Division | Contai Sub-Division | Rising main 200mm dia DI(K9) Rising main pipeline with specials and other allied works at 4th Tube Well Site for Augmentation of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000600/2024-2025 | 590/TD | 19/02/2025 | 30 | M/S. NEW DINDA ENTERPRISE | 4.09 | 0 | 0
883 | Tamluk Division | Contai Sub-Division | Land Filling & allied works for 3rd TW site of Mukutshila Zone-II W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000606/2023-2024 | 1490/CSD | 04/08/2023 | 15 | GIRI ENTERPRISE | 0.96 | 0 | 100
884 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO 32/4 & 32/5 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =46 Mtr) Nodal Point 18 to 19. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000713/2023-2024 | 2945/TD | 23/11/2023 | 25 | ROY CONSTRUCTION | 64.87 | 0 | 100
885 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 31/13 & 31/14 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =38 Mtr) Nodal Point 64 to 68. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000714/2023-2024 | 2946/TD | 23/11/2023 | 25 | JOY GURU TRADING | 65.18 | 0 | 100
886 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/1 & 33/2 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 5 to 109. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000716/2023-2024 | 2947/TD | 23/11/2023 | 25 | BISWAJIT BAG | 71.16 | 0 | 100
887 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 33/17 & 33/18 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =61 Mtr) Nodal Point 55 to 58. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000717/2023-2024 | 2948/TD | 23/11/2023 | 25 | ROY CONSTRUCTION | 68.36 | 0 | 100
888 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 100 mm Dia GI (TATA Make) Carrier Pipe in between OHE MAST NO 34/2 & 34/3 within Contai Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =54 Mtr) Nodal Point 253 to 182. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000718/2023-2024 | 2949/TD | 23/11/2023 | 25 | ZENITH CONSTRUCTION | 69.67 | 0 | 100
889 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000723/2023-2024 | 0 | 28/11/2023 | 45 | GIRI CONSTRUCTION | 0 | 0 | 0
890 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room and Interconnection work of Rising Main at 1st TW site for Mukutshila Zone-II Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000842/2023-2024 | 2157/CSD | 04/12/2023 | 136 | GIRI CONSTRUCTION | 2.26 | 0 | 100
891 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District.(PART Work Order - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000847/2023-2024 | 58/TD | 05/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 8.43 | 0 | 100
892 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART Work Order- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000848/2023-2024 | 59/TD | 05/01/2024 | 20 | MAJI ENGINEERING WORKS | 0.96 | 0 | 0
893 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-G for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001149/2023-2024 | 569/TD | 15/02/2024 | 20 | NEW STAR CONSTRUCTION | 9.63 | 0 | 100
894 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-H for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001150/2023-2024 | 570/TD | 15/02/2024 | 20 | PULAK KUMAR SAMANTA | 6.98 | 0 | 80
895 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-C for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001151/2023-2024 | 577/TD | 15/02/2024 | 20 | RELIABLE CONSTRUCTIONS | 13.64 | 0 | 100
896 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 1000 cum RCC OHR at Mukutshila Z-II Water Supply Scheme at Khejuri-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001274/2023-2024 | 1048/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
897 | Tamluk Division | Contai Sub-Division | Laying of HDPE pipes with allied works at Left Out Portion of PART-L for Augmentation of Mukutshila Zone II & adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001280/2023-2024 | 726/TD | 28/02/2024 | 30 | ROY BISWAS CONSTRUCTION | 4.8 | 0 | 0
898 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000069/2022-2023 | 1193/TD | 06/09/2022 | 0 | Resource Division | 97.03 | 0 | 0
899 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000252/2022-2023 | 1051/TD | 18/08/2022 | 40 | AQUATECH ENGINEER | 54.66 | 0 | 32
900 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000020/2023-2024 | 358/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
901 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC (4893 Nos) with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000513/2022-2023 | 2063/TD | 09/12/2022 | 841 | TARUN KOLEY | 1059.62 | 741.67 | 80
902 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between NACHINDA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I (Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (TD-46/09-10) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000559/2024-2025 | 141/CSD | 16/01/2025 | 20 | SUBHENDU HAZRA | 1.16 | 0 | 0
903 | Tamluk Division | Contai Sub-Division | Pump House and Rising main, under Augmentation of Contai Saline Area Zone-III (Phase-B) PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000605/2023-2024 | 2199/TD | 01/09/2023 | 40 | S B ENTERPRISE | 25.16 | 0 | 100
904 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well of Augmentation of Contai Saline Area Zone-III (Phase-B) Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000667/2022-2023 | 2340/TD | 10/01/2023 | 40 | M/S SYCHROTECH INDUSTRY | 57.41 | 0 | 60
905 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000029/2023-2024 | 614/TD | 17/05/2023 | 0 | Resource Division | 30.14 | 0 | 0
906 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000108/2022-2023 | 1664/TD | 03/11/2022 | 0 | Resource Division | 325.57 | 0 | 0
907 | Tamluk Division | Contai Sub-Division | Repair and renovation of of Boundary Wall (as per Departmental Design & Drawing) at OHR site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (Length-78.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000199/2024-2025 | 2324/TD | 23/07/2024 | 40 | S.D. CONSTRUCTION | 10.42 | 0 | 0
908 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000202/2023-2024 | 396/TD | 27/04/2023 | 20 | MA SARADA ENTERPRISE | 8.14 | 8.14 | 100
909 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-I Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000203/2023-2024 | 397/TD | 27/04/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.02 | 2.02 | 100
910 | Tamluk Division | Contai Sub-Division | Laying of left out pipe line by HDPE pipes with allied works, Repair and renovation of Pump House, Toilet and others allied works at OHR's site under Shillaberia Zone-I Water Supply scheme (Augmentation) in Khjuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000236/2024-2025 | 2696/TD | 22/08/2024 | 240 | TAPAS SANTRA | 57.33 | 0 | 100
911 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000441/2022-2023 | 1653/TD | 02/11/2022 | 1032 | TAPAS SANTRA | 997.19 | 74.23 | 70
912 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Shilaberia Zone-I-1 no, Shilaberia Zone-II-1 no, Durmuth-1 no, Amarshikasba Zone-I-1 no, Amarshikasba Zone-II-1 no, Golaranij-1 no & Mukutshila Zone-I-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000509/2022-2023 | 809 / CSD | 21/10/2022 | 15 | THE GODFATHER TRADING COMPANY | 0.81 | 0.81 | 100
913 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-I PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000825/2022-2023 | 3144/TD | 09/03/2023 | 40 | B. K. ENTERPRISE | 35.19 | 0 | 100
914 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000102/2022-2023 | 1657/TD | 03/11/2022 | 0 | Resource Division | 106.02 | 0 | 0
915 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-I & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000862/2022-2023 | 3218/TD | 14/03/2023 | 843 | BARH CONSTRUCTION | 46.11 | 0 | 80
916 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000134/2023-2024 | 271/TD | 20/04/2023 | 846 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 97.2 | 0 | 60
917 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-V) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000144/2023-2024 | 272/TD | 20/04/2023 | 60 | MRINAL KANTI PRADHAN | 61.5 | 0 | 60
918 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VI) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000146/2023-2024 | 273/TD | 20/04/2023 | 737 | PARIA ENTERPRISE | 38.1 | 0 | 65
919 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000147/2023-2024 | 274/TD | 20/04/2023 | 25 | DEBABRATA DAS | 10.89 | 0 | 74
920 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-VIII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000148/2023-2024 | 275/TD | 20/04/2023 | 737 | PARIA ENTERPRISE | 46.77 | 0 | 85
921 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IV) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000242/2023-2024 | 509/TD | 11/05/2023 | 45 | B M ENTERPRISE | 81.75 | 0 | 60
922 | Tamluk Division | Contai Sub-Division | Pump House , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000257/2023-2024 | 537/TD | 12/05/2023 | 1047 | GIRI CONSTRUCTION | 139.39 | 60.63 | 80
923 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC under JJM with allied work for TIKASHI- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. East Medinipur. (PART-IX) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000383/2023-2024 | 1007/TD | 05/06/2023 | 25 | DEBABRATA DAS | 14.02 | 0 | 73
924 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Tikashi & Adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001175/2023-2024 | 2330/CSD | 29/12/2023 | 7 | M/S. NEW DINDA ENTERPRISE | 0.21 | 0 | 100
925 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000065/2024-2025 | 2979/TD | 12/09/2024 | 0 | Resource Division | 15.26 | 0 | 0
926 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000337/2022-2023 | 2978/TD | 27/02/2023 | 0 | Resource Division | 42.38 | 0 | 0
927 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Simulya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000193/2024-2025 | 2203/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
928 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SIMULYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000221/2023-2024 | 451/TD | 04/05/2023 | 876 | TARUN KOLEY | 663.05 | 17.18 | 35
929 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000242/2022-2023 | 2725/TD | 06/02/2023 | 0 | Resource Division | 58.93 | 0 | 0
930 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2039 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KAKRA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000219/2023-2024 | 450/TD | 04/05/2023 | 897 | TARUN KOLEY | 666.45 | 294.08 | 85
931 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000148/2023-2024 | 126/TD | 05/01/2024 | 0 | Resource Division | 12.56 | 0 | 0
932 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000240/2022-2023 | 2727/TD | 06/02/2023 | 0 | Resource Division | 18.4 | 0 | 0
933 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Accommodate FHTC (1012 nos) Construction of Switch Room cum Chlorine Room I & II and Interconnection of Risisng main with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A,MOUZA-RAMCHANDRAPUR) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000239/2023-2024 | 498/TD | 11/05/2023 | 837 | S.K. MONDAL | 138.29 | 0 | 80
934 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Accommodate FHTC (700 Nos) & Construction of Boundary Wall with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B,MOUZA-UTTAMPUR) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000244/2023-2024 | 523/TD | 11/05/2023 | 911 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 136.15 | 0 | 65
935 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & R.C.C. Elevated Reservoir of capacity 350cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000857/2023-2024 | 170/TD | 09/01/2024 | 180 | SATYABRATA BHAUMIK | 133.51 | 0 | 10
936 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System & Accommodate FHTC (520 nos) with allied works under JJM for Ramchandrapur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C,MOUZA-SHRI BRINDABAN CHAK) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000879/2022-2023 | 3215/TD | 14/03/2023 | 1083 | MAA KALI CONSTRUCTION | 71.8 | 0 | 55
937 | Tamluk Division | Tamluk Sadar Sub-Division | Retaining wall cum guard wall , Approach road, Earth filling at 2nd Tube Site under Ramchandrapur and Its adjoing Mouzas PWSS under Moyna Development Block under Tamluk Sub- Division in Tamluk Division PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000903/2023-2024 | 245/TD | 11/01/2024 | 343 | ANIRBAN MONDAL | 6.79 | 0 | 25
938 | Tamluk Division | Tamluk Sadar Sub-Division | Earth work in filling by carried earth and Construction of link Road for Ramchandrapur and its adjoining mouzas new Piped Water Supply Scheme at Head Work Site within Moyna Block, under Tamluk Sub-Divn. of Tamluk Division. P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001111/2023-2024 | 563/TD | 15/02/2024 | 20 | KIRON CONSTRUCTION | 5.66 | 0 | 11
939 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000012/2024-2025 | 1570/TD | 23/04/2024 | 0 | Resource Division | 13.75 | 0 | 0
940 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000188/2022-2023 | 2429/TD | 16/01/2023 | 0 | Resource Division | 23.04 | 0 | 0
941 | Tamluk Division | Haldia Sub-Division | Quotation bill for new service connection at TW-III of solat w/s scheme under Haldia block in the Dist. of purba medinipur under MMD,PHE Dte. Name of C.C.C.-Brajalalchak Application no.-2004898781 Reference ID-204397568 Contract Demand-12074watt Quotation Date-12/09/2024 Quotation Due Date-12/09/2025 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00955/2024-2025 | BP-2024-25-632 | 26/11/2024 | 0 | WBSEDCL | 10.59 | 0 | 0
942 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 19.05 | 63
943 | Tamluk Division | Haldia Sub-Division | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -1) Name of Work site :- 1) Asadtalia PWSS, 2) Rangibasan PWSS, 3) Kapaseria PWSS, 4) Rajarampur PWSS, 5) Begunberia PWSS, 6) Dhenkua PWSS, 7) Solat PWSS & 8) Gopalpur PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000438/2022-2023 | 721/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100
944 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Solat Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000459/2021-2022 | 1723/TD | 01/02/2022 | 20 | RADIANT | 3.65 | 3.58 | 100
945 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Solat Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000473/2023-2024 | 1499/TD | 17/07/2023 | 520 | ELECTIVA ENTERPRISE | 5.1 | 0 | 100
946 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000049/2022-2023 | 1019/TD | 08/08/2022 | 0 | Resource Division | 12.18 | 0 | 0
947 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000066/2022-2023 | 1201/TD | 06/09/2022 | 0 | Resource Division | 16.27 | 0 | 0
948 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Selmabad PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000451/2024-2025 | 3480/TD | 06/11/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
949 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000141/2022-2023 | 2443/TD | 16/01/2023 | 0 | Resource Division | 14.54 | 0 | 0
950 | Tamluk Division | Digha Sub-Division | Canal crossing structure for Distribution pipe line with allied works of Nijmaitana & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. N.P-From 1193 towards Kathmundi 45.0M & N.P 1190 to N.P 1191 15.0 M. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000126/2024-2025 | 1926/TD | 07/06/2024 | 15 | SNEHESH SEN | 4.87 | 0 | 100
951 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 700 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000283/2023-2024 | 564/TD | 12/05/2023 | 718 | SNEHESH SEN | 199.62 | 70.59 | 100
952 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 56 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000334/2023-2024 | 808/TD | 30/05/2023 | 762 | M/S. PRADIP PRADHAN | 9.31 | 0 | 100
953 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 1050 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED , Purba Medinipur ( Part - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000517/2023-2024 | 1753/TD | 01/08/2023 | 853 | SUSIL KUMAR HAZRA | 254.73 | 0 | 32
954 | Tamluk Division | Digha Sub-Division | Laying Balance distribution pipe line,with balance FHTC and allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000597/2024-2025 | 569/TD | 17/02/2025 | 25 | R CONSTRUCTION | 36.35 | 0 | 0
955 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (123 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000917/2022-2023 | 3554/TD | 29/03/2023 | 876 | SUBRATA KUMAR BERA | 39.9 | 31.5 | 100
956 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (42 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000918/2022-2023 | 3555/TD | 29/03/2023 | 889 | DEBABRATA DAS | 9.94 | 6.57 | 100
957 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (19 Nos) under JJM with allied work for Nij Maitana & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHED, Purba Medinipur (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000919/2022-2023 | 3556/TD | 29/03/2023 | 799 | DEBABRATA DAS | 11.2 | 9.64 | 100
958 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000157/2023-2024 | 134/TD | 05/01/2024 | 0 | Resource Division | 12.26 | 0 | 0
959 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000215/2022-2023 | 2693/TD | 06/02/2023 | 0 | Resource Division | 54.53 | 0 | 0
960 | Tamluk Division | Contai Sub-Division | Shifting of HTOH line at Palpara PWSS, OHR Site under Patashpur-I Dev. Block. Memo No: AMR/SHIFTING/HTOH/.....Date: 05.04.2024 Reference ID: 860297135 Application ID: 100000104915 Application Date: 05.04.2024 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00129/2024-2025 | BP-2024-25-66 | 26/04/2024 | 0 | WBSEDCL | 5.23 | 0 | 0
961 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000371/2023-2024 | 879/TD | 01/06/2023 | 961 | SANKHA ENTERPRISE | 1144 | 0 | 30
962 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000202/2022-2023 | 2446/TD | 16/01/2023 | 0 | Resource Division | 19.77 | 0 | 0
963 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at TW-II of Mahabishra ws scheme under MMD,PHE Dte, Block-Egra-I, EGRA CCC Application no-2004823398 Consumer ID-204358386 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00729/2024-2025 | BP-2024-25-380 | 29/08/2024 | 0 | WBSEDCL | 17.31 | 0 | 0
964 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Mahabisra PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000169/2024-2025 | 2081/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
965 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000133/2022-2023 | 2417/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0
966 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (2244 Nos.) under JJM in Uttar Dhalhara Zone-I Water Supply Scheme for Sahid Matangini Dev. Block in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000390/2022-2023 | 1423/TD | 26/09/2022 | 30 | SANKHA ENTERPRISE | 86.77 | 68.76 | 100
967 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000216/2023-2024 | 1115/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
968 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline for Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000664/2023-2024 | 2672/TD | 16/10/2023 | 602 | M/S. CHANDI CHARAN MISHRA & CO. | 51.03 | 0 | 1
969 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Baranalgeria Zone-I PWSS under Egra-II Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | ORD/000775/2022-2023 | 2859/TD | 17/02/2023 | 45 | DAS CONSTRUCTION | 80.73 | 54.34 | 70
970 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000290/2022-2023 | 2646/TD | 02/02/2023 | 0 | Resource Division | 14.41 | 0 | 0
971 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 11.46 | 100
972 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000016/2023-2024 | 361/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
973 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Rising main ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , OHR (Intze type with pile foundation) & Accommodate FHTC (5135 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dubda & Khagda PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000511/2023-2024 | 1733/TD | 31/07/2023 | 819 | MAHAVIR PUMPS MFG. PVT. LTD. | 1235.52 | 0 | 48
974 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000317/2022-2023 | 2972/TD | 27/02/2023 | 0 | Resource Division | 65.15 | 0 | 0
975 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at Replacement of 1st Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 4th Tube well Site of Mukutshila Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2022-2023 | 1223/TD | 07/09/2022 | 40 | KALPANA BUILDERS | 71.97 | 17.72 | 48
976 | Tamluk Division | Contai Sub-Division | Laying of Balance portion for Distribution pipe line by UPVC pipes with allied works for Sherkhanchak Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000356/2023-2024 | 924/TD | 01/06/2023 | 40 | S.D. CONSTRUCTION | 98.88 | 0 | 95
977 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000362/2021-2022 | 1477/TD | 03/01/2022 | 20 | SANTRA ENTERPRISE. | 4.97 | 4.97 | 100
978 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Sherkhanchak Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000398/2022-2023 | 1447/TD | 27/09/2022 | 1068 | TAPAS SANTRA | 896.61 | 598.68 | 70
979 | Tamluk Division | Contai Sub-Division | Replacement of Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well site of Sherkhanchak Zone-I Water Supply Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001211/2023-2024 | 977/TD | 13/03/2024 | 25 | B. K. ENTERPRISE | 19.16 | 0 | 100
980 | Tamluk Division | Contai Sub-Division | i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) construction of Boundary Wall (as per Departmental Design & Drawing) at 4th TW site for Augmentation of Sherkhanchak Zone-I PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-342) iv) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Sherkhanchak Zone-I W/S Scheme within Khejuri - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) ( Location:-Mouza-Baratala, J.L No-29, Plot No-2543) v) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-I W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000439/2023-2024 | 1422/TD | 12/07/2023 | 622 | M/S. NEW DINDA ENTERPRISE | 41.06 | 0 | 75
981 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000053/2022-2023 | 1200/TD | 06/09/2022 | 0 | Resource Division | 292.79 | 0 | 0
982 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000062/2022-2023 | 1199/TD | 06/09/2022 | 0 | Resource Division | 44.01 | 0 | 0
983 | Tamluk Division | Contai Sub-Division | Bill or Damage of road flank / hard shoulder due to cutting of hard shoulder and road flank on Egra-Bajkul Road from 5.30 Km. To 7.00 Km. For laying water pipe line of Kekai PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00988/2024-2025 | BP-2024-25-492 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.03 | 0 | 0
984 | Tamluk Division | Contai Sub-Division | Charges for WBSEDCL for Shifting of Rail Pole of 33 KV OH Line at Kekai, Junpukur under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/01216/2024-2025 | BP-2024-25-633 | 30/11/2024 | 0 | WBSEDCL | 0.87 | 0 | 0
985 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kekai PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000157/2024-2025 | 2069/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
986 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000047/2024-2025 | 1654/TD | 29/04/2024 | 0 | Resource Division | 11.04 | 0 | 0
987 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000149/2022-2023 | 2453/TD | 16/01/2023 | 0 | Resource Division | 37.57 | 0 | 0
988 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1588 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Rukminipur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000232/2023-2024 | 460/TD | 04/05/2023 | 1063 | FIROZ KHAN | 483.49 | 0 | 70
989 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000253/2022-2023 | 2716/TD | 06/02/2023 | 0 | Resource Division | 34.45 | 0 | 0
990 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000400/2023-2024 | 1068/TD | 08/06/2023 | 934 | TAPAS SANTRA | 1110.29 | 286.43 | 85
991 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000123/2023-2024 | 83/TD | 05/01/2024 | 0 | Resource Division | 9.34 | 0 | 0
992 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000279/2022-2023 | 2688/TD | 06/02/2023 | 0 | Resource Division | 24.43 | 0 | 0
993 | Tamluk Division | Haldia Electrical Sub-Division | Continuation for Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2025 to 31.12.2025 i.e. 06 (Six) months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000423/2025-2026 | 169/RWS/TSD | 26/06/2025 | 184 | SADHAN CHANDRA SAMANTA | 0.87 | 0 | 0
994 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gojina PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000878/2023-2024 | 200/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
995 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000006/2024-2025 | 1564/TD | 23/04/2024 | 0 | Resource Division | 15.01 | 0 | 0
996 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000174/2022-2023 | 2435/TD | 16/01/2023 | 0 | Resource Division | 46.71 | 0 | 0
997 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000089/2024-2025 | 2965/TD | 12/09/2024 | 0 | Resource Division | 4.72 | 0 | 0
998 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000335/2022-2023 | 2980/TD | 27/02/2023 | 0 | Resource Division | 17.68 | 0 | 0
999 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Potapukuria PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000176/2024-2025 | 2066/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1000 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000078/2024-2025 | 2972/TD | 12/09/2024 | 0 | Resource Division | 6.04 | 0 | 0
1001 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000175/2022-2023 | 2397/TD | 16/01/2023 | 0 | Resource Division | 22.13 | 0 | 0
1002 | Tamluk Division | Digha Sub-Division | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (248nos) under JJM with allied work of BADALPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000300/2023-2024 | 603/TD | 17/05/2023 | 685 | AYSAN KHAN | 63.14 | 0 | 60
1003 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (635 nos) including 02(two) Years Operation & Maintenance under JJM with allied work of Badalpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000351/2023-2024 | 853/TD | 31/05/2023 | 1031 | GHOSH CONSTRUCTION | 320.45 | 66.83 | 52
1004 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000114/2023-2024 | 78/TD | 05/01/2024 | 0 | Resource Division | 3.91 | 0 | 0
1005 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000260/2022-2023 | 2686/TD | 06/02/2023 | 0 | Resource Division | 8.88 | 0 | 0
1006 | Tamluk Division | Contai Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied works under Murisai & its adjoining moujas Water Supply Scheme within Contai-III Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000512/2023-2024 | 1741/TD | 01/08/2023 | 180 | ANUSKA ENTERPRISE | 130.06 | 0 | 0
1007 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-I] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000453/2022-2023 | .1853/TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.2 | 100
1008 | Tamluk Division | Contai Sub-Division | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1807 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-I PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000852/2023-2024 | 897/TD | 11/03/2024 | 180 | SRIMANTA KUMAR MAITY | 428.55 | 0 | 0
1009 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000055/2023-2024 | 2093/TD | 29/08/2023 | 0 | Resource Division | 69.1 | 0 | 0
1010 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (1718 nos.) under JJM in Baranalgeria Zone -II PWSS Block - EGRA -II in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000042/2022-2023 | 173/TD | 25/04/2022 | 30 | FIROZ KHAN | 82.65 | 68.87 | 100
1011 | Tamluk Division | Digha Sub-Division | Laying ( Left out ) HDPE pipe lineto accommodated FHTC under JJM in Baranalgeria (Zone-II) PWSS within Egra-II Block( to Support Phase -I FHTC ( part -B ) under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000201/2023-2024 | 402/TD | 27/04/2023 | 30 | DEBDUT CONSTRUCTION | 32.43 | 0 | 100
1012 | Tamluk Division | Digha Sub-Division | Land development at 1st tube well site of Baranalgeria ( Zone-II ) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000426/2022-2023 | 1595/TD | 18/10/2022 | 20 | PULAK KUMAR SAMANTA | 3.51 | 3.5 | 100
1013 | Tamluk Division | Digha Sub-Division | TRIAL RUN work of distribution system and rising main pipe line etc. of Baranalgeriya (Zone - II) W/S Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. For the period of 90 (Ninety) Days. (01/04/2022 to 29/06/2022 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000660/2021-2022 | 778/DSD | 31/03/2022 | 90 | BIBEKANANDA DAS | 0.72 | 0 | 100
1014 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -VIII (Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000103/2021-2022 | 729/TD | 15/09/2021 | 180 | ARABINDA GHOSH | 342.78 | 471.5 | 100
1015 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Surface Water Based W/S Scheme for Zone - VIII under Tamluk Division, PHE Dte. in the district of Purba Medinipur. |  |  | VCH/000375/2021-2022 | BP-2021-22-125 | 07/10/2021 | 0 | ARABINDA GHOSH | 106.46 | 0 | 0
1016 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte.[PART-II] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000454/2022-2023 | .1854/TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.09 | 3.49 | 100
1017 | Tamluk Division | Contai Sub-Division | Sinking of Tubewell, 250 cum OHR (Intze type with pile foundation), Laying distribution pipe line, Soil investigation, Pump House, Boundary wall, Rising Main & Accommodate FHTC (1636 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-II PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000680/2023-2024 | 2709/TD | 30/10/2023 | 540 | TAPAS SANTRA | 480.26 | 0 | 0
1018 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000056/2023-2024 | 2094/TD | 29/08/2023 | 0 | Resource Division | 15.65 | 0 | 0
1019 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000103/2023-2024 | 3006/TD | 29/11/2023 | 0 | Resource Division | 10.08 | 0 | 0
1020 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (851 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-XII Block - Kolaghat in the District of Purba Medinipur.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000122/2023-2024 | 253/TD | 19/04/2023 | 30 | CHANDIMATA CONSTRUCTION | 56.02 | 50.36 | 100
1021 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of DI Specials for Zone-XII under Surface Water based Water Supply Scheme of Panskura-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000825/2023-2024 | 1528/TSD | 10/11/2023 | 10 | KRISHNENDU SEKHAR DAS | 0.73 | 0 | 100
1022 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Purba Teghari & its adjoining Moujas New PWSS in Deshpran Block & Augmentation of Contai Saline Area Zone-I (Phase-A) & Augmentation of Contai Saline Area Zone-I (Phase-B) PWSS in Contai-III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000565/2024-2025 | 2442/CSD | 22/10/2024 | 7 | AMIT PAYRA | 0.62 | 0 | 100
1023 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000072/2024-2025 | 2975/TD | 12/09/2024 | 0 | Resource Division | 1.4 | 0 | 0
1024 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000349/2022-2023 | 3013/TD | 27/02/2023 | 0 | Resource Division | 14.09 | 0 | 0
1025 | Tamluk Division | Contai Sub-Division | Payment of WBSEDCL for Quotation money for New Service Connection at Tube Well No. - II of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00336/2024-2025 | BP-2024-25-113 | 10/05/2024 | 0 | WBSEDCL | 6.61 | 0 | 0
1026 | Tamluk Division | Contai Sub-Division | Quotation bill of WBSEDCL for New Service Connection at Tube Well No.-1 of Garbar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/02147/2023-2024 | BP-2023-24-995 | 20/03/2024 | 0 | WBSEDCL | 5.56 | 0 | 0
1027 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (40 Nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000126/2023-2024 | 262/TD | 19/04/2023 | 15 | PARTHA CONSTRUCTION | 9.59 | 0 | 70
1028 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (40 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000259/2023-2024 | 540/TD | 12/05/2023 | 750 | CHANDA AGENCIES | 19.28 | 0 | 60
1029 | Tamluk Division | Contai Sub-Division | Pump House ,50 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (20 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000527/2023-2024 | 1776/TD | 02/08/2023 | 180 | SUSIL KUMAR HAZRA | 68.66 | 0 | 35
1030 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line & Accommodate FHTC (50 nos) under JJM with allied work of GARA BAR PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000839/2022-2023 | 3183/TD | 10/03/2023 | 180 | BADAL CHANDRA GOLE | 18.58 | 6.64 | 70
1031 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000187/2023-2024 | 636/W | 20/02/2024 | 0 | Resource Division | 0.92 | 0 | 0
1032 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000345/2022-2023 | 3010/TD | 27/02/2023 | 0 | Resource Division | 16.31 | 0 | 0
1033 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 162 Nos) under JJM with allied work for Chirulia-Chatla (Zone-I) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000408/2023-2024 | 1088/TD | 08/06/2023 | 1028 | AJIT KUMAR SOM | 269.22 | 0 | 60
1034 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000965/2022-2023 | 1055/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 4.01 | 4.01 | 100
1035 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000033/2023-2024 | 2062/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
1036 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000090/2023-2024 | 2993/TD | 29/11/2023 | 0 | Resource Division | 1 | 0 | 0
1037 | Tamluk Division | Haldia Electrical Sub-Division | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 0 | 51
1038 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line, Rising main pipe line with allied works of Pratapdighi & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000531/2023-2024 | 1826/TD | 07/08/2023 | 509 | GIRI CONSTRUCTION | 55.97 | 0 | 45
1039 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 0 | 100
1040 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Pratapdighi Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000779/2025-2026 | 3042/TD | 18/12/2025 | 60 | MAHARAJ NAYAK | 3.61 | 0 | 0
1041 | Tamluk Division | Haldia Electrical Sub-Division | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 0 | 51
1042 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000089/2023-2024 | 2902/TD | 21/11/2023 | 0 | Resource Division | 2.26 | 0 | 0
1043 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-F ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000072/2023-2024 | 174/TD | 11/04/2023 | 15 | AURGHA BHATTACHARYA | 9.97 | 0 | 100
1044 | Tamluk Division | Digha Sub-Division | Land development of 2nd T/W Site at Dakshin Shitala & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000247/2024-2025 | 872/DSD | 27/08/2024 | 7 | ABHIJIT BERA | 0.91 | 0 | 100
1045 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000370/2023-2024 | 1006/TD | 05/06/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 9.96 | 0 | 96
1046 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, & Accommodate FHTC ( 500Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000410/2023-2024 | 1096/TD | 08/06/2023 | 992 | ABHIJIT BERA | 119.92 | 0 | 48
1047 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, soil investigation, 150 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 392 Nos) under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000629/2023-2024 | 2437/TD | 19/09/2023 | 540 | EVEREST INFRATECH INC | 119.98 | 0 | 30
1048 | Tamluk Division | Digha Sub-Division | Laying of Balance Distribution HDPE Pipe Line(180 mm dia) for Dakshin Shitala Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000707/2023-2024 | 2873/TD | 17/11/2023 | 20 | HYDROTECH ASSOCIATES | 11.34 | 0 | 99
1049 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 128Nos) under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000855/2022-2023 | 3173/TD | 10/03/2023 | 1148 | DHANANJOY DAS | 39.79 | 0 | 60
1050 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000857/2022-2023 | 3174/TD | 10/03/2023 | 1074 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.84 | 0 | 97
1051 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Sitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000858/2022-2023 | 3175/TD | 10/03/2023 | 1074 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.83 | 0 | 97
1052 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-H ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000859/2022-2023 | 3176/TD | 10/03/2023 | 15 | CHARUBALA ENTERPRISE | 9.93 | 0 | 0
1053 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-I ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000860/2022-2023 | 3177/TD | 10/03/2023 | 15 | DAS ENTERPRISE. | 9.58 | 0 | 0
1054 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, to Accommodate FHTC under JJM with allied work for Dakshin Shitala & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-J ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000863/2022-2023 | 3178/TD | 10/03/2023 | 15 | M/S SOURAV MAHAPATRA | 2.72 | 0 | 0
1055 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000127/2023-2024 | 92/TD | 05/01/2024 | 0 | Resource Division | 6.28 | 0 | 0
1056 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000156/2022-2023 | 2463/TD | 16/01/2023 | 0 | Resource Division | 60.63 | 0 | 0
1057 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000681/2023-2024 | 2710/TD | 30/10/2023 | 790 | TAPAS SANTRA | 866.03 | 0 | 85
1058 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000158/2023-2024 | 100/TD | 05/01/2024 | 0 | Resource Division | 3.57 | 0 | 0
1059 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000277/2022-2023 | 2696/TD | 06/02/2023 | 0 | Resource Division | 16.55 | 0 | 0
1060 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000499/2023-2024 | 1670/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 0 | 60
1061 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000022/2023-2024 | 351/TD | 26/04/2023 | 0 | Resource Division | 14.49 | 0 | 0
1062 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000037/2024-2025 | 1663/TD | 29/04/2024 | 0 | Resource Division | 16.25 | 0 | 0
1063 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Kotbar(CT),J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000107/2020-2021 | 2463/TD | 18/12/2020 | 30 | RAJ KUMAR SINGHA | 43.46 | 0 | 100
1064 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Kulapara,J.L. No-9 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000108/2020-2021 | 2464/TD | 18/12/2020 | 25 | RAJ KUMAR SINGHA | 22.74 | 0 | 100
1065 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Kotbar(CT) of Kotbar Purba & Paschim Para,J.L. No-18 under JJM in Kotbar PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000109/2020-2021 | 2465/TD | 18/12/2020 | 25 | RAJ KUMAR SINGHA | 24.58 | 0 | 100
1066 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000289/2021-2022 | 217/W | 27/08/2021 | 0 | RAJ KUMAR SINGHA | 0.41 | 0 | 0
1067 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000383/2021-2022 | 222/W | 01/09/2021 | 0 | RAJ KUMAR SINGHA | 1.23 | 0 | 0
1068 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000402/2021-2022 | 223/W | 01/09/2021 | 0 | RAJ KUMAR SINGHA | 1.16 | 0 | 0
1069 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kulapara under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000589/2020-2021 | 683/W | 27/01/2021 | 0 | RAJ KUMAR SINGHA | 21.58 | 0 | 0
1070 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000613/2020-2021 | 682/W | 27/01/2021 | 0 | RAJ KUMAR SINGHA | 42.23 | 0 | 0
1071 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Kotbar (CT) of Kotbar Purba and Paschim Para under JJM Kotbar W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/001042/2020-2021 | 726/W | 18/02/2021 | 0 | RAJ KUMAR SINGHA | 24.17 | 0 | 0
1072 | Tamluk Division |  | Functional Household Tap Connection to the 311 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Payrakola (609) ii) Bargolia (610) iii) Hajrakola (611) iv) Bhogpur (624) v) Kalichar (626) vi) Kalidasbar (627). |  |  | ORD/000095/2020-2021 | 2451/TD | 18/12/2020 | 20 | AHINDRA BARIK | 15.31 | 0 | 100
1073 | Tamluk Division |  | Functional Household Tap Connection to the 232 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bankipur(629) ii ) Tiakola (630). |  |  | ORD/000096/2020-2021 | 2452/TD | 18/12/2020 | 20 | JASODA ENTERPRISE | 11.46 | 0 | 100
1074 | Tamluk Division |  | Functional Household Tap Connection to the 202 nos. Household of Bankiput Water Supply Scheme within Contai-II (Deshapran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Bhupatichak (628) ii ) Kaluraybar (631) iii) Kanaichatta (632). |  |  | ORD/000097/2020-2021 | 2453/TD | 18/12/2020 | 20 | SUBHENDU HAZRA | 10 | 0 | 100
1075 | Tamluk Division |  | Construction of 3.60 mtr. x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well of Source Augmentation of Bankiput W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte. |  |  | ORD/000355/2023-2024 | 1001/TD | 05/06/2023 | 60 | GITA ENTERPRISE | 3.97 | 0 | 0
1076 | Tamluk Division |  | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bankiput & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000369/2023-2024 | 1000/TD | 05/06/2023 | 30 | GITA ENTERPRISE | 3.39 | 0 | 0
1077 | Tamluk Division |  | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. |  |  | VCH/000818/2021-2022 | BP-2021-22-279 | 25/02/2022 | 0 | JASODA ENTERPRISE | 0.66 | 0 | 0
1078 | Tamluk Division |  | Retrofitting to accommodate FHTC 19 Nos. at different School under JJM in Bankiput PWSS Block-Contai - I under Tamluk Division, PHE Dte. |  |  | VCH/000868/2021-2022 | 603/W | 24/02/2022 | 0 | JASODA ENTERPRISE | 0.85 | 0 | 0
1079 | Tamluk Division |  | Retrofitting to accomodate for 232 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001044/2020-2021 | 729/W | 18/02/2021 | 0 | JASODA ENTERPRISE | 11.46 | 0 | 0
1080 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001049/2020-2021 | 802/W | 24/02/2021 | 0 | SUBHENDU HAZRA | 9.68 | 0 | 0
1081 | Tamluk Division |  | Retrofitting to accomodate for 311 Nos. FHTC connection under JJM in Bankiput W/S Scheme within Contai - II Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001200/2020-2021 | 861/W | 16/03/2021 | 0 | AHINDRA BARIK | 15.01 | 0 | 0
1082 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Lakshya PWSS Block- Mahishadal in the District of Purba Medinipur. |  |  | ORD/000222/2020-2021 | 2844/TD | 08/02/2021 | 70 | HARIPADA PATTANAYAK | 160.74 | 138.8 | 100
1083 | Tamluk Division |  | Retrofitting to accomodate FHTC of Lakshya W/S Scheme within Mahishadal under Tamluk Division, PHE Dte. |  |  | VCH/000129/2021-2022 | BP-2021-22-39 | 23/07/2021 | 0 | HARIPADA PATTANAYAK | 60.72 | 0 | 0
1084 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 1783 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District.[Mouza-Mahammadpur(07) - Part] Part-A. | Assistant Engineer | Junior Engineer | ORD/000015/2021-2022 | 108/TD | 17/05/2021 | 60 | DAS CONSTRUCTION | 83.89 | 70.62 | 100
1085 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 588 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Mahammadpur (07) - Part, Durbba Chakri (14),Manoharpur (10) - Part] Part-B. | Assistant Engineer | Junior Engineer | ORD/000016/2021-2022 | 109/TD | 17/05/2021 | 25 | JASODA ENTERPRISE | 27.79 | 27.79 | 100
1086 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 510 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Manoharpur (10) - Part, Tiraipur (11),Chapal Ghata (13) - Part] Part-C. | Assistant Engineer | Junior Engineer | ORD/000017/2021-2022 | 110/TD | 17/05/2021 | 25 | MRINAL KANTI PRADHAN | 24.1 | 20.98 | 100
1087 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 411 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Chapal Ghata (13) - Part, Parial Chak (15),Benauda (16) - Part] Part-D. | Assistant Engineer | Junior Engineer | ORD/000023/2021-2022 | 111/TD | 17/05/2021 | 20 | M/S. NEW DINDA ENTERPRISE | 19.33 | 18.1 | 100
1088 | Tamluk Division | Contai Sub-Division | Functional Household Tap Connection to the 370 nos. Household of Mahammadpur W/S Scheme within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. [Mouza-Benauda (16) - Part,Mabarakpur (20)] Part-E. | Assistant Engineer | Junior Engineer | ORD/000024/2021-2022 | 112/TD | 17/05/2021 | 20 | SUBHENDU HAZRA | 17.49 | 15.92 | 100
1089 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate FHTC (741 nos) under JJM in Mahammadpur PWSS within Mahammadpur JL No.-185- (Uttar Mahammadpur) in Nandigram-I dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000210/2020-2021 | 2822/TD | 05/02/2021 | 30 | NARAYAN CHANDRA DAS | 35.29 | 0 | 100
1090 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Haldia PWSS Block - Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000136/2020-2021 | 2662/TD | 11/01/2021 | 60 | SANKHA ENTERPRISE | 96.1 | 10.96 | 100
1091 | Tamluk Division |  | Laying of Distribution pipe line by UPVC pipes with allied works for jointing of Existing line( N.P-55A-55B, N.P-56A-56B, 58A-58B) under Haldia & its adjoining mouzas W/S Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. |  |  | ORD/000975/2023-2024 | 986/DSD | 17/01/2024 | 7 | LOKENATH ENTERPRISES | 0.97 | 0 | 100
1092 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Haldia PWSS within Ramnagar ¿I Block under Tamluk Division, PHE Dte. |  |  | VCH/001132/2020-2021 | 1113/W | 30/03/2021 | 0 | SANKHA ENTERPRISE | 3.98 | 0 | 0
1093 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Haldia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001240/2020-2021 | 966/W | 25/03/2021 | 0 | SANKHA ENTERPRISE | 80 | 0 | 0
1094 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS, Block- Nandakumar under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. |  |  | ORD/000112/2020-2021 | 2468/TD | 18/12/2020 | 25 | MAA ANANDAMAYEE | 20.9 | 0 | 0
1095 | Tamluk Division |  | Construction of approach road at head work site of Kolsar PWSS under Tamluk Sub-division of Tamluk Division PHE Dte.( 20.0 mtr) |  |  | ORD/000400/2025-2026 | 2733/TSD | 13/08/2025 | 15 | M/S MONDAL CONSTRUCTION & CO. | 1.2 | 0 | 0
1096 | Tamluk Division |  | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Engineer-In-Chief, Govt. of West Bengal, PHE Dte. for the month of May, 2022, June, 2022 and July, 2022 |  |  | VCH/000791/2022-2023 | BP-2022-23-578 | 30/12/2022 | 0 | KRISHNA MONDAL | 1.2 | 0 | 0
1097 | Tamluk Division |  | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division, PHE Dte. for the period from November, 2021 to March, 2022. |  |  | VCH/000793/2022-2023 | BP-2022-23-452 | 25/11/2022 | 0 | TAPAS SANTRA | 1.97 | 0 | 0
1098 | Tamluk Division |  | Hiring of One No. Diesel Motor Cabs & Maxi Cab with contract carriage permit from RTA for the office of Assistant Engineer, Tamluk Sub-Division, PHE Dte. for the period from June, 2022 to August, 2022. |  |  | VCH/000794/2022-2023 | BP-2022-23-455 | 01/12/2022 | 0 | DEBNATH MAITY | 1.2 | 0 | 0
1099 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Kolsar PWSS, Block- Nandakumar under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. |  |  | VCH/000991/2021-2022 | BP-2021-22-385 | 31/03/2022 | 0 | MAA ANANDAMAYEE | 3.38 | 0 | 0
1100 | Tamluk Division |  | Functional Household Tap connection to the 750 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Shirui, JL-74.)PART- A. |  |  | ORD/000215/2020-2021 | 2827/TD | 05/02/2021 | 30 | DILIP KUMAR GHOSH | 35.45 | 6.34 | 100
1101 | Tamluk Division |  | unctional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- B |  |  | ORD/000216/2020-2021 | 2828/TD | 05/02/2021 | 20 | DEBDUT CONSTRUCTION | 9.69 | 0.44 | 100
1102 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Alinan, JL-39.)PART- C |  |  | ORD/000217/2020-2021 | 2829/TD | 05/02/2021 | 20 | S.D. CONSTRUCTION | 9.69 | 0 | 100
1103 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division,PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- D |  |  | ORD/000218/2020-2021 | 2830/TD | 05/02/2021 | 20 | S.D. CONSTRUCTION | 9.7 | 0 | 100
1104 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Saira, JL-38.)PART- E. |  |  | ORD/000219/2020-2021 | 2831/TD | 05/02/2021 | 20 | J.M. CONSTRUCTION | 9.7 | 0.32 | 100
1105 | Tamluk Division |  | Functional Household Tap connection to the 205 nos Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri, JL-76.)PART-F |  |  | ORD/000220/2020-2021 | 2832/TD | 05/02/2021 | 20 | SHAKEEL KHAN | 9.71 | 0 | 100
1106 | Tamluk Division |  | Functional Household Tap connection to the 205 nos(Barsuri-28 nos + Belun-140nos,Soyadighi-37) Household of Alinan Zone-II W/S scheme within Sahid Matangini Dev, Block under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District (Mouza-Barsuri , Belun & Soyadighi, JL-76 , 75 & 36.) PART-G. |  |  | ORD/000221/2020-2021 | 2833/TD | 05/02/2021 | 20 | TARUN KOLEY | 9.71 | 0 | 100
1107 | Tamluk Division |  | Left out of ( 90 mm & 75 mm) OD pvc laying distribution system of pipe line and its allied works for Alinan zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000300/2022-2023 | 1150/TD | 31/08/2022 | 15 | TARUN KOLEY | 3.39 | 3.39 | 100
1108 | Tamluk Division |  | Left out of 110 mm OD pvc laying distribution system of pipe line and its allied works for Alinan Zone-II Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000301/2022-2023 | 1151/TD | 31/08/2022 | 15 | TARUN KOLEY | 4.52 | 0.41 | 100
1109 | Tamluk Division |  | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 2.28 | 100
1110 | Tamluk Division |  | Retrofitting to accomodate FHTC 205 Nos. connection under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000106/2021-2022 | BP-2021-22-54 | 05/08/2021 | 0 | DEBDUT CONSTRUCTION | 9.25 | 0 | 0
1111 | Tamluk Division |  | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. |  |  | VCH/001064/2020-2021 | 1111/W | 30/03/2021 | 0 | J.M. CONSTRUCTION | 9.37 | 0 | 0
1112 | Tamluk Division |  | Functional Household Tap Connection for Alinan Zone - II W/S Scheme within Sahid Matangini Block Tamluk Division, PHE Dte. |  |  | VCH/001065/2020-2021 | 1107/W | 30/03/2021 | 0 | SHAKEEL KHAN | 9.41 | 0 | 0
1113 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001100/2020-2021 | 1110/W | 30/03/2021 | 0 | TARUN KOLEY | 9.48 | 0 | 0
1114 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001101/2020-2021 | 1109/W | 30/03/2021 | 0 | S.D. CONSTRUCTION | 9.26 | 0 | 0
1115 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme under Tamluk Division, PHE Dte. |  |  | VCH/001102/2020-2021 | 1099/W | 30/03/2021 | 0 | S.D. CONSTRUCTION | 9.36 | 0 | 0
1116 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Alinan Zone - II W/S Scheme within Sahid Matangini Block under Tamluk Division, PHE Dte. |  |  | VCH/001140/2020-2021 | 1117/W | 30/03/2021 | 0 | DILIP KUMAR GHOSH | 29.1 | 0 | 0
1117 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 206 nos] under JJM in Barasubarnanagar PWSS [Prakash Kultalia 1st Part(500,part),Chaitanyapur(501, part),Bara Subarnanagar(502, part),Rupnagar(503, part),Krishnalal Chak(504, part),Sikdar Chak(505,part),DahaShonamui(506,part),Bamunia Nankar(510,part),Purba Bhagabanpur(517, part)] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | VCH/000075/2021-2022 |  | 08/06/2021 | 0 | NARAYAN MANDAL | 30.18 | 0 | 0
1118 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Barasubarnagar W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000241/2021-2022 | BP-2021-22-35 | 23/07/2021 | 0 | NARAYAN MANDAL | 30.18 | 0 | 0
1119 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur. (PART- A) |  |  | ORD/000137/2021-2022 | 1019/TD | 02/11/2021 | 20 | ABHIJIT BERA | 21.29 | 21.29 | 100
1120 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Mandarmani PWSS (PHASE-II) Block - Ramnagar-II in the District of Purba Medinipur ( PART - B ) |  |  | ORD/000138/2021-2022 | 1020/TD | 02/11/2021 | 30 | UNIQUE AGENCY | 52.71 | 52.71 | 100
1121 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- A) |  |  | ORD/000133/2021-2022 | 1015/TD | 02/11/2021 | 20 | MAA KALI CONSTRUCTION | 20.35 | 20.34 | 100
1122 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- B) |  |  | ORD/000134/2021-2022 | 1016/TD | 02/11/2021 | 20 | LOKENATH ENTERPRISES | 20.29 | 20.28 | 100
1123 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- C) |  |  | ORD/000135/2021-2022 | 1017/TD | 02/11/2021 | 20 | SHAKEEL KHAN | 22.37 | 22.37 | 100
1124 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in PANCHROL PWSS Block - Egra-I in the District of Purba Medinipur. (PART- D) |  |  | ORD/000136/2021-2022 | 1018/TD | 02/11/2021 | 20 | NARAYAN CHANDRA DAS | 22.37 | 22.37 | 100
1125 | Tamluk Division |  | Laying ( Left out ) UPVC pipe line to accommodate FHTC under JJM in PANCHROL PWSS within EGRA -I BLOCK ( to Support phase I FHTC ) (part -B )under Digha Sub Division of Tamluk Division PHE Dte. |  |  | ORD/000285/2021-2022 | 1541/TD | 11/01/2022 | 15 | LOKENATH ENTERPRISES | 4.76 | 0 | 100
1126 | Tamluk Division |  | Laying distribution pipe line to accommodate FHTC of Panchrol Water Supply Scheme within Egra - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. Within (Panchrol West part ). |  |  | ORD/000348/2021-2022 | 1781/TD | 08/02/2022 | 20 | SHAKEEL KHAN | 11.26 | 0 | 100
1127 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in DULALPUR PWSS Block - Egra-II in the District of Purba Medinipur |  |  | ORD/000130/2021-2022 | 1012/TD | 02/11/2021 | 30 | BIDHAN MONDAL | 57.42 | 57.41 | 100
1128 | Tamluk Division |  | Balance Work for Retrofitting to accommodate FHTC (907 Nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipeline at different nodal point under JJM in Surface Water based water supply scheme for Zone-VII ,Block-Kolaghat in the District of Purba Medinipur under tamluk Division. (Phase-II) |  |  | ORD/000142/2021-2022 | 1069/TD | 08/11/2021 | 60 | TARUN KOLEY | 119.62 | 115.86 | 100
1129 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-II & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000119/2022-2023 | 622/TD | 22/06/2022 | 1193 | TARUN KOLEY | 570.24 | 337.16 | 85
1130 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - II) Water Supply under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000169/2021-2022 | 1178/TD | 02/12/2021 | 20 | HORIZEN | 6.26 | 6.26 | 100
1131 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site for Mohisda (Zone-II) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000851/2022-2023 | 3205/TD | 14/03/2023 | 30 | TARUN KOLEY | 16.19 | 0 | 100
1132 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2021 to 30.11.2022 i.e. 01 (One) year for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001000/2021-2022 | 309/RWS/TSD | 01/12/2021 | 365 | SRIMANTA PANJA | 1.48 | 2.35 | 100
1133 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000036/2022-2023 | 652/TD | 27/06/2022 | 0 | Resource Division | 10.05 | 0 | 0
1134 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000050/2021-2022 | 641/TD | 27/06/2022 | 0 | Resource Division | 23.01 | 0 | 0
1135 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000214/2023-2024 | 1114/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1136 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000035/2022-2023 | 134/TD | 19/04/2022 | 21 | MENAKA ENTERPRISE | 13.26 | 0 | 0
1137 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Golaranji Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000322/2021-2022 | 1615/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.46 | 3.04 | 100
1138 | Tamluk Division | Contai Sub-Division | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site and 2nd Tube Well site at Golaranij Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000355/2024-2025 | 3318/TD | 22/10/2024 | 30 | BADAL CHANDRA GOLE | 4.92 | 0 | 100
1139 | Tamluk Division | Contai Sub-Division | Augmentation of ground water based Golaranij Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Potashpur-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000381/2022-2023 | 1370/TD | 23/09/2022 | 795 | KISHORE GHOSH | 392.47 | 150.4 | 70
1140 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Golaranij Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000534/2023-2024 | 1835/TD | 08/08/2023 | 20 | RAMESH & SHANTI ENGINEERING WORKS | 4.2 | 4.2 | 100
1141 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Golaranij W/S Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000714/2022-2023 | 1212/TD | 06/09/2022 | 60 | BADAL CHANDRA GOLE | 3.81 | 0 | 100
1142 | Tamluk Division | Contai Sub-Division | Laying Distribution Pipe Line With allied Works of Left Out Area for Augmentation Of Golaranij Water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte., Purba Medinipur District. (PHASE-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001201/2023-2024 | 738/TD | 28/02/2024 | 275 | KISHORE GHOSH | 44.24 | 0 | 100
1143 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000024/2021-2022 | 1249/TD | 13/12/2021 | 0 | Resource Division | 10.87 | 0 | 0
1144 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000060/2021-2022 | 1273/TD | 12/09/2022 | 0 | Resource Division | 18.08 | 0 | 0
1145 | Tamluk Division |  | Retrofitting to accommodate FHTC (410 Nos.) under JJM in Keshabpur Jalpai PWSS (Balance Part : Phase-II) Block - Mahisadal in the District of Purba Medinipur |  |  | ORD/000546/2021-2022 | 2006/TD | 08/03/2022 | 25 | RAJ KUMAR SINGHA | 23.33 | 19.06 | 100
1146 | Tamluk Division | Tamluk Sadar Sub-Division | Laying damage portion of different dia. UPVC pipes within Surface Water Based Water Supply Scheme for Zone- VIII of Kolaghat Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000019/2022-2023 | 63/TD | 05/04/2022 | 20 | CONCORD ENGINEERING | 12.59 | 12.58 | 100
1147 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC(Balance work) (200 nos.) and laying of left-out portion with uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone- VIII, Block-Kolaghat in the District of Purba Medinipur(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000124/2022-2023 | 616/TD | 21/06/2022 | 20 | ARABINDA GHOSH | 78.41 | 67.03 | 100
1148 | Tamluk Division | Digha Sub-Division | Providing FHTC under JJM in Negua PWSS within Egra-I Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000300/2021-2022 | 1641/TD | 19/01/2022 | 120 | M/S CARE | 137.35 | 84.49 | 85
1149 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (Phase-II) of Negua PWSS, Egra - I Block under Digha Sub-Division PHE Dte. of Tamluk Division PHE Dte. in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000307/2023-2024 | 621/TD | 17/05/2023 | 25 | SOM CONSTRUCTION | 15.44 | 15.44 | 100
1150 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000074/2021-2022 | 1748/TD | 08/02/2022 | 0 | Resource Division | 15.3 | 0 | 0
1151 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money for Thenkuachak PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00394/2022-2023 | BP-2022-23-755 | 28/02/2023 | 0 | WBSEDCL | 4.07 | 0 | 0
1152 | Tamluk Division | Haldia Electrical Sub-Division | Additional laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000071/2022-2023 | 292/TD | 06/05/2022 | 15 | MALLICK CONSTRUCTION | 3.91 | 3.91 | 100
1153 | Tamluk Division | Haldia Electrical Sub-Division | Laying of DI (K7) ( Nodal point 167 to 627) ,UPVC pipe (Nodal 167-623) & Supply of of DI (Specials) under Thekuachak Zone-I Water Supply Scheme under Tamluk Division, Purba Medinipur, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000111/2024-2025 | 1905/TD | 07/06/2024 | 20 | GHOSH ENTERPRISE | 12.87 | 0 | 100
1154 | Tamluk Division | Haldia Electrical Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-II PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000175/2023-2024 | 332/TD | 25/04/2023 | 60 | GHOSH ENTERPRISE | 17.82 | 0 | 70
1155 | Tamluk Division | Haldia Electrical Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Thekuachak zone-I PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000176/2023-2024 | 333/TD | 25/04/2023 | 480 | GHOSH ENTERPRISE | 15.05 | 0 | 70
1156 | Tamluk Division | Haldia Electrical Sub-Division | Laying distribution pipe line & other allied works for water supplying arrangement to Dakhin Damodarpur PHC through Thakuachak PWSS under Tamluk Sub- Division of Tamluk Division, PHE Dte.with in Purba Mednipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000196/2021-2022 | 1228/TD | 08/12/2021 | 40 | ANUSKA ENTERPRISE | 17.87 | 17.85 | 100
1157 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Thenkuachak Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000242/2022-2023 | 1021/TD | 08/08/2022 | 988 | ARABINDA GHOSH | 1009.34 | 461.5 | 70
1158 | Tamluk Division | Haldia Electrical Sub-Division | Pilling work & casing pipe (GI/MS)over khal and Road crossing of various junction of Thekuachak Zone-II water supply scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000341/2023-2024 | 806/TD | 30/05/2023 | 30 | GHOSH ENTERPRISE | 14.63 | 5.86 | 50
1159 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Thenkuachak (Zone - I & II) Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000391/2021-2022 | 1607/TD | 14/01/2022 | 20 | INDRANIL DUTTA & ASSOCIATES | 8.64 | 8.59 | 100
1160 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & Renovation of Construction of Pump house ,Boundary wall & allied works at 1st Tube well site for Thekuachak Zone-II Water Supply Scheme in Nandakumar Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000464/2024-2025 | 3724/TD | 04/12/2024 | 120 | GHOSH ENTERPRISE | 7.83 | 0 | 100
1161 | Tamluk Division | Haldia Electrical Sub-Division | Additional works of Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur .( Low Land ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000466/2023-2024 | 1446/TD | 13/07/2023 | 40 | TARUN KHATUA | 1.86 | 1.83 | 100
1162 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Concrete road for Kharar Pool ( Mansa Mandir) (Nodal Point -38) to Head work site of Thekuachak Zone -I(Nodal point 1158 )( Length - 350 mtr, width 2.10 mte , Depth of cincrete 150 mm ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000734/2023-2024 | 2988/TD | 29/11/2023 | 30 | KRISHNENDU SEKHAR DAS | 9.63 | 0 | 100
1163 | Tamluk Division | Haldia Electrical Sub-Division | Cannel crossing for DI and uPVC pipes of Thekua chak Zone-II PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. (Nodal Point 139-140, 410-528, 165-164, 636-448, 675-381, 783-789, 665-214 and 55-221= 8 nos) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000736/2023-2024 | 2986/TD | 29/11/2023 | 30 | GHOSH ENTERPRISE | 33.58 | 0 | 100
1164 | Tamluk Division | Haldia Electrical Sub-Division | Canel crossing for DI and uPVC pipes of Thekua chak Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. ( Nodal 167-112, 585-327,33-98,337-401 and 213-109 )= 5 nos | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000737/2023-2024 | 2985/TD | 29/11/2023 | 30 | GHOSH ENTERPRISE | 20.97 | 0 | 100
1165 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000831/2022-2023 | 3171/TD | 10/03/2023 | 60 | ANIRBAN MONDAL | 4.59 | 4.57 | 100
1166 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Thekuachak Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000832/2022-2023 | 3172/TD | 10/03/2023 | 60 | TARUN KHATUA | 5.11 | 5.11 | 100
1167 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2023 to 14/07/2024 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001289/2023-2024 | 1489/TD | 14/07/2023 | 366 | THREE MAA ENTERPRISE | 1.24 | 0 | 0
1168 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000025/2022-2023 | 413/TD | 25/05/2022 | 0 | Resource Division | 121.31 | 0 | 0
1169 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000026/2022-2023 | 414/TD | 25/05/2022 | 0 | Resource Division | 46.43 | 0 | 0
1170 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000074/2022-2023 | 1267/TD | 12/09/2022 | 0 | Resource Division | 59.51 | 0 | 0
1171 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000194/2023-2024 | 670/W | 22/02/2024 | 0 | Resource Division | 16.44 | 0 | 0
1172 | Tamluk Division | Tamluk Sadar Sub-Division | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Mohisda Zone-I PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/01193/2023-2024 | BP-2023-24-566 | 07/11/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.6 | 0 | 0
1173 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000067/2022-2023 | 338/TD | 12/05/2022 | 1080 | TAPAS SANTRA | 331.77 | 315.84 | 95
1174 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 700 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Mohisda Zone-I & its adjoining mouzas Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000075/2022-2023 | 337/TD | 12/05/2022 | 1054 | TAPAS SANTRA | 417.56 | 274.52 | 70
1175 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well at OHR Site of Mahisda Zone-I Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000103/2022-2023 | 479/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.39 | 15.97 | 100
1176 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mohisda (Demarihat) PWSS (Zone - I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000168/2021-2022 | 1177/TD | 02/12/2021 | 20 | HORIZEN | 7.73 | 7.73 | 100
1177 | Tamluk Division | Tamluk Sadar Sub-Division | Laying Distribution system of Left-out portion of pipe line and its allied works to accommodate FHTC at Mahisda Zone-I Water Supply Scheme in Sahid Matangini Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000249/2023-2024 | 513/TD | 11/05/2023 | 30 | TAPAS SANTRA | 58.58 | 55.7 | 90
1178 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia DI(K-9) & 200 mm dia DI (K-9) rising main from 1st.,2nd. & 3rd. T/W to OHR at Mohisda Zone-I PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000454/2023-2024 | 1494/TD | 17/07/2023 | 20 | TAPAS SANTRA | 3.84 | 0 | 0
1179 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of Retaining wall and approach concrete road at OHR site at Mohisda Zone-I Water Supply scheme of Sahid Matangini Dev. Block under Tamluk Sub-Division of Tamlul Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000617/2023-2024 | 2282/TD | 07/09/2023 | 420 | TAPAS SANTRA | 27.97 | 0 | 100
1180 | Tamluk Division | Tamluk Sadar Sub-Division | Hire charges of Bharat Stage-IV Diesel Motor Cabs (Luxury Taxi)/Swift Desire/Ambassador Non AC) having Contract Carriage Permit from the Reginal Transport Authority valid for the State of West Bengal on monthly Hire rate basis for the period from 15/07/2022 to 14/07/2023 (12 months) to be used by the Assistant Engineer, Head Quarters, Tamluk Division, PHE Dte. The cost inclusive of all charges due to the wages of Driver, Taxies, Insurance, Fees etc. as applicable Fuel :- a) Diesel - 12 Km./Ltr. b) Mobile Oil 500 Km./Ltr. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000703/2022-2023 | 821/TD | 15/07/2022 | 365 | THREE MAA ENTERPRISE | 1.24 | 0 | 100
1181 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of construction of switch room cum Chlorine room at 1 st.T.W. Site and Construction of switch room cum Chlorine room with water supply & sanitary arrangement at 3 rd. Tube Well Site and Repairing & renovation of existing Boundary Wall at 1 st.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000852/2022-2023 | 3206/TD | 14/03/2023 | 30 | TAPAS SANTRA | 17.08 | 16.83 | 100
1182 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at OHR Site and Repairing & renovation of construction of switch room cum Chlorine room and Boundary Wall at 2 nd Tube Well Site and Construction of Pump House at 3 rd Tube Well site &New construction of Boundary Wall at 3 rd.T.W. site for Mohisda (Zone-I) Water Supply Scheme within Sahid Matangini Dev.Block under Tamluk Sub Division,PHE Dte | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000853/2022-2023 | 3207/TD | 14/03/2023 | 30 | TAPAS SANTRA | 19.48 | 0 | 100
1183 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000035/2022-2023 | 651/TD | 27/06/2022 | 0 | Resource Division | 22.79 | 0 | 0
1184 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000072/2021-2022 | 640/TD | 27/06/2022 | 0 | Resource Division | 31.83 | 0 | 0
1185 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000215/2023-2024 | 1113/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1186 | Tamluk Division | Haldia Sub-Division | Electric Quotation Bill for Rangibasan PWSS | Assistant Engineer | Junior Engineer | BILL/00226/2022-2023 | BP-2022-23-637 | 20/01/2023 | 0 | WBSEDCL | 0.59 | 0 | 0
1187 | Tamluk Division | Haldia Sub-Division | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Mahishadal-Geonkhali road from Ch.0.20 km to 1.10 km under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer | Junior Engineer | BILL/00235/2023-2024 | BP-2023-24-120 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.98 | 0 | 0
1188 | Tamluk Division | Haldia Sub-Division | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000143/2024-2025 | 2013/TD | 14/06/2024 | 313 | A. R. CONSTRUCTION | 56.76 | 0 | 20
1189 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rangibasan Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2021-2022 | 1180/TD | 02/12/2021 | 20 | HORIZEN | 5.56 | 5.56 | 100
1190 | Tamluk Division | Haldia Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District (PART-A) | Assistant Engineer | Junior Engineer | ORD/000388/2023-2024 | 1052/TD | 07/06/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.9 | 5.9 | 100
1191 | Tamluk Division | Haldia Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Rangibasan Water Supply Scheme under Haldia Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000389/2023-2024 | 1053/TD | 07/06/2023 | 20 | MA SARADA ENTERPRISE | 0.73 | 0.73 | 100
1192 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Rangibasan Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000459/2023-2024 | 1496/TD | 17/07/2023 | 45 | PULAK KUMAR SAMANTA | 4.81 | 0 | 60
1193 | Tamluk Division | Haldia Sub-Division | Laying of supply & delivery of different dia D.I specials for Rising main line and inter connection at Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000463/2023-2024 | 1493/TD | 17/07/2023 | 895 | S.D. CONSTRUCTION | 7.32 | 0 | 10
1194 | Tamluk Division | Haldia Sub-Division | Repairing & Renovation of Switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube Well site of Rangibasan Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000655/2023-2024 | 2620/TD | 11/10/2023 | 30 | PULAK KUMAR SAMANTA | 5.98 | 0 | 3
1195 | Tamluk Division | Haldia Sub-Division | Sinking of 300 mm x 200 mm dia x 280 mtr. deep tube well by direct rotary rig method at 3rd Tubewell site of Rangibasan Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000846/2023-2024 | 51/TD | 04/01/2024 | 45 | AQUATECH ENGINEER | 20.68 | 0 | 100
1196 | Tamluk Division | Haldia Sub-Division | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | Assistant Engineer | Junior Engineer | ORD/001006/2021-2022 | 476/HSD, | 27/12/2021 | 365 | SANTANU PATTANAYAK | 1.5 | 1.91 | 100
1197 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000016/2021-2022 | 1258/TD | 13/12/2021 | 0 | Resource Division | 11.32 | 0 | 0
1198 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000048/2021-2022 | 1867/TD | 17/02/2022 | 0 | Resource Division | 19.09 | 0 | 0
1199 | Tamluk Division | Contai Sub-Division | payment Wayleave plan & survey charges SER-KGP-2024-WL-103 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00486/2024-2025 | BP-2024-25-189 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.1 | 0 | 0
1200 | Tamluk Division | Contai Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-103) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00694/2024-2025 | BP-2024-25-301 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.75 | 0 | 0
1201 | Tamluk Division | Contai Sub-Division | Way Leave permission from South Eastern Railway for Mukutshilla Zone-I PWSS for Application ID-SER-KGP-2023-WL-57 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01830/2023-2024 | BP-2023-24-824 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.27 | 0 | 0
1202 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000411/2022-2023 | 1575/TD | 14/10/2022 | 868 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 92.06 | 50
1203 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion HDPE Pipe line of Distribution pipe line by HDPE pipes with allied works of Mukutshila Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000519/2024-2025 | 113/TD | 09/01/2025 | 25 | GEE BEE NIRMAN CO PVT LTD. | 36.64 | 0 | 0
1204 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Mukutshila Zone-II Piped Water Supply Scheme in Khejuri-I Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (PART-B) In between OHE MAST NO 34/2 & 34/3, Nodal Point 253 to 182. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000554/2024-2025 | 136/CSD | 16/01/2025 | 20 | BIBEKANANDA DAS | 1.16 | 0 | 100
1205 | Tamluk Division | Contai Sub-Division | Rising main and other allied works Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000589/2023-2024 | 2190/TD | 01/09/2023 | 720 | GRAND CONSTRUCTION | 11.85 | 0 | 0
1206 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Mukutshila Zone-I PWSS within Khejuri-I Block under Contai Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. (Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000615/2023-2024 | 2277/TD | 07/09/2023 | 796 | SAMIT KUMAR MONDAL | 8.63 | 0 | 100
1207 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x 3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Mukutshila Zone-I water supply scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Normal Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000724/2023-2024 | 2968/TD | 28/11/2023 | 60 | ABHIJIT BERA | 3.72 | 0 | 100
1208 | Tamluk Division | Contai Sub-Division | Temporary water supply arrangement through pipe line & PVC tank connection from distribution pipe line of Mukutshila Zone-I W/S Scheme for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-A), Date of Mela :- 20.03.2023 to 23.03.2023, (4 days) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000998/2022-2023 | 394/CSD | 16/03/2023 | 3 | M/S. NEW DINDA ENTERPRISE | 0.7 | 0 | 100
1209 | Tamluk Division | Contai Sub-Division | Construction of Temporary 25(twenty five) nos. Latrine & Urinal for Krishnanagar Matrisakti Aradhana Mela at Krishnanagar within Khejuri-I Block in the year 2023, under Contai sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PART-B) Date of Mela :- 20.03.2023 to 23.03.2023,(4 days) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000999/2022-2023 | 395/CSD | 16/03/2023 | 3 | M/S. NEW DINDA ENTERPRISE | 0.62 | 0 | 100
1210 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000068/2022-2023 | 1194/TD | 06/09/2022 | 0 | Resource Division | 108.25 | 0 | 0
1211 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Chirulia PWSS Block Egra-II in the District of Purba Medinipur. |  |  | ORD/000190/2020-2021 | 2768/TD | 28/01/2021 | 60 | FIROZ KHAN | 56.35 | 6.8 | 100
1212 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000153/2021-2022 | 62/W | 08/06/2021 | 0 | FIROZ KHAN | 24.5 | 0 | 0
1213 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001236/2020-2021 | 977/W | 25/03/2021 | 0 | FIROZ KHAN | 21.3 | 0 | 0
1214 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
1215 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 2892/TD | 21/11/2023 | 0 | Resource Division | 19.46 | 0 | 0
1216 | Tamluk Division |  | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Jagati(244 ) part,] |  |  | ORD/000171/2020-2021 | 2721/TD | 21/01/2021 | 20 | M/S. NEW DINDA ENTERPRISE | 10.43 | 0 | 100
1217 | Tamluk Division |  | Functional Household Tap Connection to the 225 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Jagati(244 ) part,] |  |  | ORD/000172/2020-2021 | 2722/TD | 21/01/2021 | 20 | GIRI ENTERPRISE | 10.43 | 0 | 100
1218 | Tamluk Division |  | Functional Household Tap Connection to the 1400 nos. Household of Pratapdighi W/S Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [Pratap Dighi (245), Mangalpur (249)] |  |  | ORD/000173/2020-2021 | 2809/TD | 04/02/2021 | 50 | GIRI CONSTRUCTION | 64.82 | 0 | 100
1219 | Tamluk Division |  | Renovation of existing pump house at head works & 2nd tube well site of Pratapdighi W/S Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000193/2022-2023 | 409 / CSD | 12/07/2022 | 30 | GIRI CONSTRUCTION | 1.36 | 1.35 | 100
1220 | Tamluk Division |  | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000283/2021-2022 | 159/W | 02/08/2021 | 0 | GIRI CONSTRUCTION | 13.24 | 0 | 0
1221 | Tamluk Division |  | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/000387/2021-2022 | 225/W | 01/09/2021 | 0 | M/S. NEW DINDA ENTERPRISE | 0.63 | 0 | 0
1222 | Tamluk Division |  | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000469/2021-2022 | 315/W | 08/10/2021 | 0 | GIRI ENTERPRISE | 0.38 | 0 | 0
1223 | Tamluk Division |  | Retrofitting to accomodate for 225 Nos. FHTC connection under JJM in Pratapdighi W/S Scheme within Potashpur - II Dev. Block Block under Tamluk Division, PHE Dte. (Part-C) |  |  | VCH/001052/2020-2021 | 815/W | 24/02/2021 | 0 | M/S. NEW DINDA ENTERPRISE | 9.64 | 0 | 0
1224 | Tamluk Division |  | Retrofitting to accomodate FHTC 225 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001222/2020-2021 | 980/W | 23/03/2021 | 0 | GIRI ENTERPRISE | 9.77 | 0 | 0
1225 | Tamluk Division |  | Retrofitting to accomodate FHTC 1400 Nos. connection under JJM Pratapdighi W/S Scheme within Patashpur - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001237/2020-2021 | 972/W | 25/03/2021 | 0 | GIRI CONSTRUCTION | 21.89 | 0 | 0
1226 | Tamluk Division | Haldia Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01480/2023-2024 | BP-2023-24-665 | 15/12/2023 | 0 | WBSEDCL | 5.18 | 0 | 0
1227 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000136/2023-2024 | 277/TD | 20/04/2023 | 25 | TARUN KHATUA | 19.88 | 11.59 | 60
1228 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (240 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-G+H+I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000137/2023-2024 | 278/TD | 20/04/2023 | 45 | BHOLANATH DEY | 90.98 | 76.65 | 76
1229 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J+K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000138/2023-2024 | 279/TD | 20/04/2023 | 30 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.8 | 25.84 | 80
1230 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (480 nos.) work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000411/2023-2024 | 1097/TD | 08/06/2023 | 180 | SUSIL KUMAR HAZRA | 104.34 | 0 | 10
1231 | Tamluk Division | Haldia Sub-Division | Canal Crossing Structure for Laying Distribution (Nodal Point -161-163, 378-382, R1 - 1, 12-16) Pipe line of Bamanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000649/2023-2024 | 2615/TD | 11/10/2023 | 30 | TARUN KHATUA | 8.77 | 0 | 100
1232 | Tamluk Division | Haldia Sub-Division | Ground water based Bamanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (425 nos.)work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D+E+F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000665/2023-2024 | 2678/TD | 16/10/2023 | 649 | SK. SARFARAJ | 93.13 | 0 | 10
1233 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000898/2022-2023 | 3348/TD | 22/03/2023 | 638 | M/S SYCHROTECH INDUSTRY | 62.36 | 0 | 100
1234 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000117/2023-2024 | 81/TD | 05/01/2024 | 0 | Resource Division | 8.39 | 0 | 0
1235 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000330/2022-2023 | 2986/TD | 27/02/2023 | 0 | Resource Division | 15.66 | 0 | 0
1236 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH line at Moyna Zone-I Water Supply Scheme | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01475/2023-2024 | BP-2023-24-663 | 15/12/2023 | 0 | WBSEDCL | 3.97 | 0 | 0
1237 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (4679 nos) with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Moyna Zone-I Water Supply Scheme within Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000442/2022-2023 | 1652/TD | 02/11/2022 | 903 | ARABINDA GHOSH | 612.74 | 246.39 | 85
1238 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000597/2023-2024 | 2211/TD | 01/09/2023 | 40 | PRASANTA MONDAL | 5.1 | 0 | 10
1239 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Moyna Zone-I Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000598/2023-2024 | 2212/TD | 01/09/2023 | 40 | PRASANTA MONDAL | 5.1 | 0 | 70
1240 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of 300/250/200/150 mm dia DI (K9) rising main in between OHR to T/W-I, T/W-2, T/W-3 and T/W-4 including canel crossing and dram Sheet Walling and DI specials of Moyna Zone-I PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte.,Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000653/2023-2024 | 2618/TD | 11/10/2023 | 420 | KRISHNENDU SEKHAR DAS | 24.68 | 0 | 100
1241 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Moyna Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000859/2021-2022 | 1470/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.08 | 3.93 | 100
1242 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor cabs (Luxury Taxi) (Standard non air conditioned) Bharat stage-IV, (Vehicle No. WB-29B-2278) on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit for state of West Bengal for the office of Assistant Engineer, Tamluk Sub Division, PHE Dte under Tamluk Division for the period from 01.01.2024 to 31.03.2024. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001226/2023-2024 | 1756/TSD | 29/12/2023 | 50 | DEBNATH MAITY | 0.24 | 0 | 100
1243 | Tamluk Division | Tamluk Sadar Sub-Division | Continuation work order for Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001259/2023-2024 | 1468/TSD | 31/10/2023 | 239 | TAPAS SANTRA | 1.14 | 0 | 0
1244 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000032/2023-2024 | 1922/TD | 14/08/2023 | 0 | Resource Division | 9.63 | 0 | 0
1245 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000050/2022-2023 | 1209/TD | 06/09/2022 | 0 | Resource Division | 131.09 | 0 | 0
1246 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000058/2022-2023 | 1205/TD | 06/09/2022 | 0 | Resource Division | 7.03 | 0 | 0
1247 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000200/2023-2024 | 1099/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1248 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kshetrapal PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000158/2024-2025 | 2070/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1249 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000050/2024-2025 | 1657/TD | 29/04/2024 | 0 | Resource Division | 11.58 | 0 | 0
1250 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000150/2022-2023 | 2456/TD | 16/01/2023 | 0 | Resource Division | 19.2 | 0 | 0
1251 | Tamluk Division |  | Retrofitting to accommodate FHTC [180 nos.] under JJM in Uttar Charaikhia PWSS Block - Contai-I in the District of Purba Medinipur. Mouza- Saheb Khankeranibar(101),Kanchra Gerya(122),Dakshin Charai Khia(124),Uttar Charai Khia(125) (Phase-II) |  |  | ORD/000127/2021-2022 | 1007/TD | 02/11/2021 | 20 | M/S SREE DURGA ENTERPRISE | 17.26 | 17.26 | 100
1252 | Tamluk Division | Haldia Sub-Division | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Rautari to Terapara Jalpai road from Ch.8.5 KM to 9.85 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer | Junior Engineer | BILL/00237/2023-2024 | BP-2023-24-122 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.76 | 0 | 0
1253 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000106/2022-2023 | 514/TD | 07/06/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.81 | 4.81 | 100
1254 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve for Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000107/2022-2023 | 515/TD | 07/06/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.7 | 3.7 | 100
1255 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Rajarampur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000161/2021-2022 | 1165/TD | 01/12/2021 | 7 | HORIZEN | 5.74 | 5.61 | 100
1256 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.28 | 100
1257 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Rajarampur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000256/2022-2023 | 1069/TD | 22/08/2022 | 45 | TAPAN BERA | 3.96 | 3.93 | 100
1258 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Rajarampur Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.. | Assistant Engineer | Junior Engineer | ORD/000528/2021-2022 | 2021/TD | 08/03/2022 | 1334 | SANKHA ENTERPRISE | 549.46 | 437.5 | 90
1259 | Tamluk Division | Haldia Sub-Division | Laying Rising main, laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Rajarampur Water Supply Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2022-2023 | 2167/TD | 19/12/2022 | 1170 | SANKHA ENTERPRISE | 78.54 | 23.06 | 35
1260 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Rajarampur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000819/2023-2024 | 3289/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 8.69 | 0 | 25
1261 | Tamluk Division | Haldia Sub-Division | Work Order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2022 to 31/12/2022. (12 Months) | Assistant Engineer | Junior Engineer | ORD/001005/2021-2022 | 476/HSD | 27/12/2021 | 365 | SUSANTA PATTANAYAK | 1.5 | 0 | 100
1262 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000011/2021-2022 | 1253/TD | 13/12/2021 | 0 | Resource Division | 40.29 | 0 | 0
1263 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2022-2023 | 465/W | 02/06/2022 | 0 | Resource Division | 55.01 | 0 | 0
1264 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000042/2021-2022 | 2344/TD | 31/03/2022 | 0 | Resource Division | 16.03 | 0 | 0
1265 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000136/2023-2024 | 104/TD | 05/01/2024 | 0 | Resource Division | 5.61 | 0 | 0
1266 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000278/2022-2023 | 2682/TD | 06/02/2023 | 0 | Resource Division | 14.87 | 0 | 0
1267 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000140/2023-2024 | 90/TD | 05/01/2024 | 0 | Resource Division | 12.69 | 0 | 0
1268 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000207/2022-2023 | 2465/TD | 16/01/2023 | 0 | Resource Division | 18.6 | 0 | 0
1269 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at T/W-I of Barada under MMD,PHE DTE, Block-Egra-I, Chorpalia CCC Application no-2004811995 CON ID-204352240 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00635/2024-2025 | BP-2024-25-312 | 02/08/2024 | 0 | WBSEDCL | 20.24 | 0 | 0
1270 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Barda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000170/2024-2025 | 2082/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1271 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000135/2022-2023 | 2419/TD | 16/01/2023 | 0 | Resource Division | 27.14 | 0 | 0
1272 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 0 | 30
1273 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000029/2024-2025 | 1651/TD | 29/04/2024 | 0 | Resource Division | 7.38 | 0 | 0
1274 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000200/2022-2023 | 2462/TD | 16/01/2023 | 0 | Resource Division | 17.76 | 0 | 0
1275 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Basanta Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000877/2023-2024 | 199/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1276 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000002/2024-2025 | 1560/TD | 23/04/2024 | 0 | Resource Division | 12.76 | 0 | 0
1277 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000182/2022-2023 | 2431/TD | 16/01/2023 | 0 | Resource Division | 21.73 | 0 | 0
1278 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Radhaballabh Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000875/2023-2024 | 197/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1279 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000011/2024-2025 | 1569/TD | 23/04/2024 | 0 | Resource Division | 12.48 | 0 | 0
1280 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000184/2022-2023 | 2428/TD | 16/01/2023 | 0 | Resource Division | 32.13 | 0 | 0
1281 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Telami PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000161/2024-2025 | 2073/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1282 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000125/2022-2023 | 2409/TD | 16/01/2023 | 0 | Resource Division | 35.73 | 0 | 0
1283 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000437/2022-2023 | 1650/TD | 02/11/2022 | 180 | TARUN KOLEY | 942.75 | 0 | 85
1284 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shilaberia-Janka Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000441/2021-2022 | 1647/TD | 19/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.95 | 100
1285 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000095/2022-2023 | 1376/TD | 23/09/2022 | 0 | Resource Division | 13.06 | 0 | 0
1286 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000103/2022-2023 | 1659/TD | 03/11/2022 | 0 | Resource Division | 186.64 | 0 | 0
1287 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 860 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000249/2022-2023 | 1040/TD | 16/08/2022 | 1088 | M/S SREE DURGA ENTERPRISE | 110.9 | 78.87 | 96
1288 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 814 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. ( Part -C ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000259/2022-2023 | 1077/TD | 23/08/2022 | 45 | J. K. BUILDERS | 109.37 | 70.92 | 95
1289 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000439/2021-2022 | 1542/TD | 11/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.71 | 4.44 | 100
1290 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000444/2022-2023 | 1654/TD | 02/11/2022 | 180 | SIBSANKAR CHOWDHURY | 449.19 | 50.81 | 40
1291 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for the work of Hiring of one Diesel Motor cabs & Maxi cabs with Engine capacity More than 2000 C.C. with ( Air Condition) on monthly Hiring (Per day) ( including Govt. Holidays as and when required ) having contract carriage permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. Govt. of West Bengal. For the Period from 01/07/2023 to 30/06/2024 i.e.12 Months. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000560/2023-2024 | 1204/A/CSD | 21/06/2023 | 366 | SABITA PRADHAN | 1.49 | 0 | 0
1292 | Tamluk Division | Haldia Electrical Sub-Division | Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2021 to 30/06/2022. (12 Months) Vehicle No-WB-31/6974 | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000979/2021-2022 | 157/CSD | 29/06/2021 | 12 | SABITA PRADHA | 1.49 | 4.53 | 100
1293 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000076/2022-2023 | 1259/TD | 12/09/2022 | 0 | Resource Division | 24.85 | 0 | 0
1294 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000127/2022-2023 | 2411/TD | 16/01/2023 | 0 | Resource Division | 12.32 | 0 | 0
1295 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 13.07 | 98
1296 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Barasubarnanagar W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000210/2023-2024 | 472/TD | 10/05/2023 | 60 | JASODA ENTERPRISE | 3.83 | 3.58 | 100
1297 | Tamluk Division | Contai Sub-Division | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 1st Tube Well & 1(One) no. Boosting Tube Well of Barasubarnanagar & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000234/2023-2024 | 471/TD | 10/05/2023 | 30 | JASODA ENTERPRISE | 4.01 | 0 | 100
1298 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 13.05 | 100
1299 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000015/2023-2024 | 345/TD | 26/04/2023 | 0 | Resource Division | 9.11 | 0 | 0
1300 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Ramnagar Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000638/2022-2023 | 741/TD | 04/07/2022 | 20 | SANTRA ENTERPRISE. | 4.52 | 0 | 100
1301 | Tamluk Division | Digha Sub-Division | Laying of Distribution System to accomodate FHTC(2941 Nos), Construction of Boundary Wall,Pump House ,R.C.C. Overhead Reservoir of Capacity 350 Cum and staging height 20 meter for Augmentation of Ramnagar Water Supply Scheme (Zone-II) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000743/2022-2023 | 2532/TD | 19/01/2023 | 803 | BASANTA KUMAR MAITY | 476.59 | 123.61 | 66
1302 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000237/2022-2023 | 2614/TD | 02/02/2023 | 0 | Resource Division | 65.04 | 0 | 0
1303 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000287/2022-2023 | 2640/TD | 02/02/2023 | 0 | Resource Division | 18.12 | 0 | 0
1304 | Tamluk Division | Contai Sub-Division | Payment of WBSEDCL for Quotation of Shifting of LTOH line at Haludbari Water Supply Scheme for Construction of New OHR. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01889/2023-2024 | BP-2023-24-844 | 07/02/2024 | 0 | WBSEDCL | 1.52 | 0 | 0
1305 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000228/2022-2023 | 2708/TD | 06/02/2023 | 0 | Resource Division | 20.18 | 0 | 0
1306 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 0 | 30
1307 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000272/2022-2023 | 2703/TD | 06/02/2023 | 0 | Resource Division | 15.41 | 0 | 0
1308 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3181 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of PASCHIM BAR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000220/2023-2024 | 447/TD | 04/05/2023 | 942 | TAPAS SANTRA | 872.64 | 210.78 | 40
1309 | Tamluk Division | Contai Sub-Division | Laying Distribution System (Nodal-1-2,2-4,4-19,19-20,20-50,50-84,84-109,109-167 & 167-89) of pipe line and its allied works for PASCHIM BAR Water Supply Scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001258/2023-2024 | 1072/TD | 16/03/2024 | 25 | MISHRA ENTERPRISE | 23.45 | 0 | 80
1310 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000163/2023-2024 | 128/TD | 05/01/2024 | 0 | Resource Division | 19.59 | 0 | 0
1311 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000246/2022-2023 | 2720/TD | 06/02/2023 | 0 | Resource Division | 33.64 | 0 | 0
1312 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kasba Patashpur PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000153/2024-2025 | 2064/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1313 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000045/2024-2025 | 1652/TD | 29/04/2024 | 0 | Resource Division | 11.55 | 0 | 0
1314 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000148/2022-2023 | 2451/TD | 16/01/2023 | 0 | Resource Division | 32.56 | 0 | 0
1315 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000226/2022-2023 | 2706/TD | 06/02/2023 | 0 | Resource Division | 24.84 | 0 | 0
1316 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sherkhanchak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000363/2021-2022 | 1511/TD | 06/01/2022 | 20 | SANTRA ENTERPRISE. | 3.71 | 3.33 | 100
1317 | Tamluk Division | Contai Sub-Division | Name of Work: i) Laying Rising main and other allied works Augmentation of Sherkhanchak Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000871/2022-2023 | 3222/TD | 14/03/2023 | 650 | SRIMANTA KUMAR MAITY | 7.4 | 0 | 100
1318 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line, Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site under Sherkhanchak Zone-II Water Supply Scheme (Augmentation) in Khejuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001218/2023-2024 | 982/TD | 13/03/2024 | 430 | BIPLAB GUHA | 86.79 | 0 | 60
1319 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000054/2022-2023 | 1198/TD | 06/09/2022 | 0 | Resource Division | 15.39 | 0 | 0
1320 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000063/2022-2023 | 1210/TD | 06/09/2022 | 0 | Resource Division | 15.91 | 0 | 0
1321 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gabardhanpur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000191/2024-2025 | 2201/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1322 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000044/2024-2025 | 1650/TD | 29/04/2024 | 0 | Resource Division | 10.35 | 0 | 0
1323 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000185/2022-2023 | 2455/TD | 16/01/2023 | 0 | Resource Division | 15.86 | 0 | 0
1324 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 79 Nos) under JJM with allied work for SANKARPUR (Zone-II) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000145/2023-2024 | 287/TD | 20/04/2023 | 20 | BUNBA CONSTRUCTION | 16.35 | 0 | 90
1325 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000329/2023-2024 | 739/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.46 | 3.41 | 100
1326 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 0 | 75
1327 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai- II ( Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000111/2023-2024 | 241/TD | 19/04/2023 | 30 | GITA ENTERPRISE | 7.54 | 0 | 0
1328 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Bamunia & its adjoining mouzas Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000368/2023-2024 | 999/TD | 05/06/2023 | 30 | GIRI CONSTRUCTION | 3.39 | 0 | 0
1329 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000012/2023-2024 | 340/TD | 26/04/2023 | 0 | Resource Division | 5.21 | 0 | 0
1330 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 0 | 75
1331 | Tamluk Division | Contai Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well of Source Augmentation of Silampur & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000213/2023-2024 | 480/TD | 10/05/2023 | 30 | JASODA ENTERPRISE | 3.27 | 0 | 100
1332 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Source Augmentation of Silampur W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000214/2023-2024 | 481/TD | 10/05/2023 | 60 | THE GODFATHER TRADING COMPANY | 3.67 | 0 | 100
1333 | Tamluk Division | Contai Sub-Division | Constrution of Boundary wall (as per Departmental Desigh & Drawing) And,Augmentation of Silampur Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000303/2023-2024 | 600/TD | 17/05/2023 | 30 | M/S SOURAV MAHAPATRA | 7.01 | 0 | 100
1334 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Silampur, Uttar Khasda, Barchunfali, Uttar Charaikhia Retrofitting PWSS in Contai - I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001176/2023-2024 | 2331/CSD | 29/12/2023 | 15 | SAURAV HAZRA | 0.83 | 0 | 100
1335 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000013/2023-2024 | 341/TD | 26/04/2023 | 0 | Resource Division | 4.77 | 0 | 0
1336 | Tamluk Division | Digha Sub-Division | Land Development at HeadWorks site of Baincha Water Supply Scheme within Egra - II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000208/2025-2026 | 1575/TD | 13/06/2025 | 7 | M/S JOY | 4.75 | 0 | 0
1337 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (880nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Baincha PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000481/2023-2024 | 1566/TD | 19/07/2023 | 709 | M/S JOY | 322.5 | 0 | 45
1338 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000255/2022-2023 | 2712/TD | 06/02/2023 | 0 | Resource Division | 32.92 | 0 | 0
1339 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Katnadighi PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000187/2024-2025 | 2197/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1340 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000046/2024-2025 | 1653/TD | 29/04/2024 | 0 | Resource Division | 3.51 | 0 | 0
1341 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000155/2022-2023 | 2461/TD | 16/01/2023 | 0 | Resource Division | 21.8 | 0 | 0
1342 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000019/2023-2024 | 117/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 37.12 | 16.48 | 100
1343 | Tamluk Division | Tamluk Sadar Sub-Division | 3(Three) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Gobindanagar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000133/2023-2024 | 269/TD | 20/04/2023 | 600 | M/S. S. A. CONSTRUCTION | 49.64 | 0 | 100
1344 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Gobindanagar PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000728/2022-2023 | 2558/TD | 24/01/2023 | 60 | TARUN KOLEY | 73.36 | 0 | 100
1345 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000010/2023-2024 | 344/TD | 26/04/2023 | 0 | Resource Division | 13.24 | 0 | 0
1346 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000344/2022-2023 | 3018/TD | 27/02/2023 | 0 | Resource Division | 24.12 | 0 | 0
1347 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000496/2022-2023 | 1932./TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 2.89 | 100
1348 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 173 Nos) under JJM with allied work for Chirulia-Chatla (Zone-IV) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000523/2023-2024 | 1759/TD | 01/08/2023 | 180 | SUSIL KUMAR HAZRA | 262.49 | 0 | 0
1349 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000051/2023-2024 | 2076/TD | 28/08/2023 | 0 | Resource Division | 15.05 | 0 | 0
1350 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000093/2023-2024 | 2996/TD | 29/11/2023 | 0 | Resource Division | 1.07 | 0 | 0
1351 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000463/2022-2023 | 1866/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.98 | 100
1352 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (48 nos) under JJM with allied work for Bathuari (Zone-IV) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000526/2023-2024 | 1762/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 278.74 | 0 | 20
1353 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000050/2023-2024 | 2073/TD | 28/08/2023 | 0 | Resource Division | 15.35 | 0 | 0
1354 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000099/2023-2024 | 3002/TD | 29/11/2023 | 0 | Resource Division | 0.3 | 0 | 0
1355 | Tamluk Division | Contai Sub-Division | Quotation for new service connection at Dekhali w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004783456, Ref ID 204336497) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00590/2024-2025 | BP-2024-25-288 | 29/07/2024 | 0 | WBSEDCL | 12.1 | 0 | 0
1356 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000227/2022-2023 | 2707/TD | 06/02/2023 | 0 | Resource Division | 20.88 | 0 | 0
1357 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100
1358 | Tamluk Division | Haldia Sub-Division | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Tajpur W/S Scheme within Nandigram-I Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000174/2023-2024 | 331/TD | 25/04/2023 | 617 | M/S SOURAV MAHAPATRA | 12.42 | 0 | 100
1359 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000002/2023-2024 | 354/TD | 26/04/2023 | 0 | Resource Division | 1.14 | 0 | 0
1360 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Badalpur PWSS at Ramnagar - II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000889/2023-2024 | 208/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1361 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000069/2024-2025 | 2947/TD | 12/09/2024 | 0 | Resource Division | 1.53 | 0 | 0
1362 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000346/2022-2023 | 3011/TD | 27/02/2023 | 0 | Resource Division | 6.62 | 0 | 0
1363 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100
1364 | Tamluk Division | Haldia Sub-Division | Construction of Pump House, Laying Rising Main & Construction of Boundary Wall at Boosting Tube well Site of Jalpai Part-II W/S Scheme within Nandigram-II Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000172/2023-2024 | 329/TD | 25/04/2023 | 608 | M/S SOURAV MAHAPATRA | 13.12 | 0 | 100
1365 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000006/2023-2024 | 360/TD | 26/04/2023 | 0 | Resource Division | 0.35 | 0 | 0
1366 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 17.82 | 100
1367 | Tamluk Division | Tamluk Sadar Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Saripur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000442/2023-2024 | 1425/TD | 12/07/2023 | 60 | SK. NUR ISLAM | 13.01 | 0 | 100
1368 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (42 nos) under JJM within Saripur PWSS (Balance work) within Chandipur Block under Tamluk Sub Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000546/2024-2025 | 147/TSD | 20/01/2025 | 126 | NARAYAN MANDAL | 2.48 | 0 | 100
1369 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000005/2023-2024 | 350/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
1370 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate under JJM with allied work for Dariapur PWSS within Contai-II (Deshpran) Block including supply of all labour & materials under Contai Sub-Division of Tamluk Division, PHE Dte. Part-A | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000143/2023-2024 | 286/TD | 20/04/2023 | 60 | BUNBA CONSTRUCTION | 28.63 | 0 | 0
1371 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Haipur, Damodarpur Retrofitting PWSS in Contai - I Block, Dariapur & Bankiput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001167/2023-2024 | 2332/CSD | 29/12/2023 | 15 | JASODA ENTERPRISE | 0.83 | 0 | 100
1372 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000014/2023-2024 | 343/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
1373 | Tamluk Division | Digha Sub-Division | Drum sheet piling work, Canal Crossing Structure for Distribution pipe line, Supply and delivery of different dia D.I. specials, Repairing & renovation of OHR (350 CUM), Repairing & renovation of existing H/W site Pump House & 2nd TW site Pump house with allied works under JJM for Augmentation of Astichak Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000640/2024-2025 | 852/TD | 19/03/2025 | 40 | ONKAR ENTERPRISE | 78.51 | 0 | 100
1374 | Tamluk Division | Digha Sub-Division | Proposed Rising main and interconnection with OHR of ASTICHAK (Z-II ) & its adjoining moujas Water Supply Scheme within Egra-II Dev. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000834/2023-2024 | 3326/TD | 27/12/2023 | 789 | ONKAR ENTERPRISE | 515.99 | 0 | 98
1375 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Astichak Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000858/2021-2022 | 1471/TD | 03/01/2022 | 20 | APEX ENGINEERING | 4.75 | 4.75 | 100
1376 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000041/2023-2024 | 2079/TD | 28/08/2023 | 0 | Resource Division | 49.99 | 0 | 0
1377 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000104/2023-2024 | 3007/TD | 29/11/2023 | 0 | Resource Division | 13.53 | 0 | 0
1378 | Tamluk Division | Contai Sub-Division | Quotation bill for Kanthi Bari Water supply scheme PH-II, new service connection (Central Drilling) Khejuri CCC Block- Khejuri-I Quotation Bill Date. -02-05-2024 Application no.-2004711606 Reference ID.-204294517 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00448/2024-2025 | BP-2024-25-169 | 10/06/2024 | 0 | WBSEDCL | 10.12 | 0 | 0
1379 | Tamluk Division | Contai Sub-Division | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert,CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (1582 nos) under JJM with allied work for Kanthi Bari & its adjoining moujas PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000475/2023-2024 | 1516/TD | 17/07/2023 | 987 | TAPAS SANTRA | 565.57 | 266.44 | 70
1380 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000094/2024-2025 | 2962/TD | 12/09/2024 | 0 | Resource Division | 7.86 | 0 | 0
1381 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000338/2022-2023 | 2977/TD | 27/02/2023 | 0 | Resource Division | 33.32 | 0 | 0
1382 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 911 | JAYANTA KUMAR MONDAL | 1264.74 | 0 | 30
1383 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000073/2024-2025 | 2974/TD | 12/09/2024 | 0 | Resource Division | 10.48 | 0 | 0
1384 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000203/2022-2023 | 2405/TD | 16/01/2023 | 0 | Resource Division | 20.41 | 0 | 0
1385 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
1386 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000088/2024-2025 | 2966/TD | 12/09/2024 | 0 | Resource Division | 2.62 | 0 | 0
1387 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000213/2022-2023 | 2408/TD | 16/01/2023 | 0 | Resource Division | 13.74 | 0 | 0
1388 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Basudevpur ( Phase-II ) PWSS Block-Egra-II in the District Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000131/2021-2022 | 1013/TD | 02/11/2021 | 30 | SNEHESH SEN | 69.11 | 67.16 | 100
1389 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gobradan PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000874/2023-2024 | 196/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1390 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000005/2024-2025 | 1563/TD | 23/04/2024 | 0 | Resource Division | 8.75 | 0 | 0
1391 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000181/2022-2023 | 2426/TD | 16/01/2023 | 0 | Resource Division | 21.84 | 0 | 0
1392 | Tamluk Division | Haldia Electrical Sub-Division | Route survey and all releated field works for preparation and submission of zone wise Geo tagged reference drawing with desinged pipe network system at Chandipur Development Block and Nandakumar Development Block within Purba Medinipur District Under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000344/2023-2024 | 844/TD | 31/05/2023 | 40 | ENVIROTECH SOLUTIONS | 85.01 | 68.61 | 100
1393 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-II (Bhagaban Khali) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000392/2025-2026 | 2132/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1394 | Tamluk Division | Haldia Electrical Sub-Division | Laying UPVC pipe line 90 ( OD ) for left out portion at village Bhandarberia Jalpai under Jalpai PWSS Tamluk Sub-Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000402/2025-2026 | 2148/TD | 18/08/2025 | 30 | FARID UDDIN AHMED | 4.18 | 0 | 90
1395 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-III (Jaukti Basan) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000407/2025-2026 | 2133/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1396 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-IV (Barneturia) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000408/2025-2026 | 2134/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1397 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VI (Balibar) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000409/2025-2026 | 2135/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1398 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XI (Bamunara) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000410/2025-2026 | 2136/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1399 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XIV (Barabanki) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000411/2025-2026 | 2137/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0
1400 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XV (Usmanpur) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000412/2025-2026 | 2138/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1401 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XVI (Rasik Chak) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000413/2025-2026 | 2139/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0
1402 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XVII (Kulbari) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000414/2025-2026 | 2140/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1403 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XX (Dibakarpur) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000415/2025-2026 | 2141/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0
1404 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-XXI (Baraghuni) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000416/2025-2026 | 2142/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1405 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XXII (Khagda) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000417/2025-2026 | 2143/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 0
1406 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Zone-XXIII (Jalpai Part - II) Nandakumar-Chandipur Surface Water Based Water Supply Scheme at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000418/2025-2026 | 2144/TD | 18/08/2025 | 10 | ENGINEERS CONSULTANT (INDIA) | 0.8 | 0 | 100
1407 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board (20 nos) at different work site for P.H.E. Dept. Land within Nandakumar Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (Part-C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000477/2025-2026 | 2438/TD | 18/09/2025 | 14 | GLOBAL TRADE | 3.33 | 0 | 100
1408 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board (29 nos) at different work site within Sahid Matangini Block for P.H.E. Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000479/2025-2026 | 2440/TD | 18/09/2025 | 14 | GLOBAL TRADE | 4.83 | 0 | 100
1409 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE- I) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000483/2025-2026 | 2359/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 100
1410 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000484/2025-2026 | 2360/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 100
1411 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District .(PHASE-III) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000485/2025-2026 | 2361/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.83 | 0 | 100
1412 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at different work( ZONE-XI,XXII) site of Chandipur Block, under Tamluk Division, PHE Dte. Purba Medinipur District.(PHASE-IV) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000486/2025-2026 | 2362/TD | 10/09/2025 | 10 | TECHNO ENTERPRISE. | 0.42 | 0 | 100
1413 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Zone-XII (Kulup) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000620/2024-2025 | 668/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
1414 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-VIII (Atattar) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000621/2024-2025 | 669/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
1415 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-V (Narandanri) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000622/2024-2025 | 670/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
1416 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Zone-IX (Baroj) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000623/2024-2025 | 671/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
1417 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Zone-XIII (Sultanpur) at Chandipur Block under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division-I,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/000624/2024-2025 | 672/TD | 03/03/2025 | 10 | D N SARKAR & SONS | 0.95 | 0 | 100
1418 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Gholepukuria PWSS(Zone-II) Block -Nandigram-II in the District of Purba Medinipur. |  |  | ORD/000127/2020-2021 | 2635/TD | 05/01/2021 | 60 | SWADHIN KUMAR CHAKRABORTY | 76.69 | 0 | 100
1419 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000260/2021-2022 | BP-2021-22-77 | 17/09/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 6.78 | 0 | 0
1420 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000395/2021-2022 | 245/W | 13/09/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 9 | 0 | 0
1421 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001185/2020-2021 | 825/W | 02/03/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 35.94 | 0 | 0
1422 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Gholpukuria Zone - II W/S Scheme within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001210/2020-2021 | 933/W | 18/03/2021 | 0 | SWADHIN KUMAR CHAKRABORTY | 24.96 | 0 | 0
1423 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Habichak PWSS Block Chandipur in the District of Purba Medinipur. |  |  | ORD/000035/2020-2021 | 2112/TD | 05/11/2020 | 180 | TAPAS SANTRA | 96.73 | 0 | 100
1424 | Tamluk Division |  | Left out portion for laying distribution system of pipe line and its allied works for Habichak & its adjoining mouzas Water Supply Scheme at Chandipur Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. |  |  | ORD/000108/2021-2022 | 790/TD | 28/09/2021 | 20 | TAPAS SANTRA | 6.59 | 0 | 0
1425 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000227/2021-2022 | 142/W | 22/07/2021 | 0 | TAPAS SANTRA | 1.52 | 0 | 0
1426 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000593/2020-2021 | 638/W | 14/01/2021 | 0 | TAPAS SANTRA | 48.82 | 0 | 0
1427 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Habichak W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/001045/2020-2021 | 698/W | 02/02/2021 | 0 | TAPAS SANTRA | 46.39 | 0 | 0
1428 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Jagatpur PWSS Block Panskura-I in the District of Purba Medinipur. |  |  | ORD/000034/2020-2021 | 2111/TD | 05/11/2020 | 180 | ARUP KUMAR DEY | 88.18 | 12.62 | 100
1429 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Jagatpur W/S Scheme within Panskura - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001033/2020-2021 | 711/W | 09/02/2021 | 0 | ARUP KUMAR DEY | 74.34 | 0 | 0
1430 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Mandarmani PWSS Block - Ramnagar-II in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000138/2020-2021 | 2688/TD | 20/01/2021 | 60 | UNIQUE AGENCY | 60.84 | 60.84 | 100
1431 | Tamluk Division |  | Laying (Left Out) UPVC pipe line to accommodate FHTC under JJM in Kudi PWSS within Egra-I Block (to support phase-1 FHTC) under Digha Sub-Division of Tamluk Division, PHE Dte. (Mouza- Naraharipur, Usma, Kudi) |  |  | ORD/000023/2022-2023 | 76/TD | 08/04/2022 | 25 | MONDAL PRECISION PRIVATE LIMITED | 16.72 | 0 | 0
1432 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kudi PWSS Block-Egra-I in the District of Purba Medinipur. |  |  | ORD/000137/2020-2021 | 2667/TD | 14/01/2021 | 60 | MONDAL PRECISION PRIVATE LIMITED | 70.47 | 0 | 75
1433 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kudi W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000399/2021-2022 | 246/W | 14/09/2021 | 0 | MONDAL PRECISION PRIVATE LIMITED | 10.18 | 0 | 0
1434 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kudi W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001233/2020-2021 | 983/W | 25/03/2021 | 0 | MONDAL PRECISION PRIVATE LIMITED | 37.11 | 0 | 0
1435 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Argoal PWSS Block -Potashpur-II in the District of Purba Medinipur. |  |  | ORD/000202/2020-2021 | 2803/TD | 04/02/2021 | 45 | DAS ENTERPRISE | 125.99 | 38.39 | 100
1436 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Argoal W/S Scheme within Potashpur - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000259/2021-2022 |  | 06/09/2021 | 0 | DAS ENTERPRISE | 47.57 | 0 | 0
1437 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Argoal W/S Scheme within Potashpur - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000314/2021-2022 | BP-2021-22-79 | 17/09/2021 | 0 | DAS ENTERPRISE | 47.57 | 0 | 0
1438 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Argoal Piped Water Supply Scheme |  |  | VCH/001113/2020-2021 | 1091/W | 30/03/2021 | 0 | DAS ENTERPRISE | 40.02 | 0 | 0
1439 | Tamluk Division |  | Retrofitting to accomodate FHTC (700 nos.) under JJM IN Silampur PWSS under CONTAI-I BLOCK of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) |  |  | ORD/000008/2021-2022 | 686/TD | 10/09/2021 | 30 | BASANTA KUMAR MAITY | 58.45 | 48.98 | 90
1440 | Tamluk Division |  | Laying of different dia UPVC pipe line to accommodate 86 nos FHTC to make Betgerya,Eryafetepur, Khalisabhanga,, Betbani, Paryadwip, Silampur, Sitalpur & Sujulpur Mouza as Swajal Gram of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  |  | ORD/000522/2022-2023 | 2094 /TD | 13/12/2022 | 20 | ROY & ROY CONSTRUCTION. | 5.73 | 0 | 100
1441 | Tamluk Division |  | Re-laying of 140 mm dia UPVC pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  |  | ORD/000576/2022-2023 | 877 / CSD | 22/11/2022 | 21 | JASODA ENTERPRISE | 0.84 | 0.84 | 100
1442 | Tamluk Division |  | Re-laying of 125 mm dia UPVC & 100 mm dia DI (K-7) pipe line due to Construction of Drain under Dulalpur GP at Silampur Mouza of Silampur W/S Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. |  |  | ORD/000577/2022-2023 | 885 / CSD | 23/11/2022 | 21 | PAL ENTERPRISE. | 0.82 | 0.81 | 100
1443 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block- Contai-I in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000279/2020-2021 | 2997/TD | 25/02/2021 | 60 | SRIMANTA KUMAR MAITY | 197.96 | 119.39 | 100
1444 | Tamluk Division |  | Repair and Renovation of Pump House with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site at Haipur Water Supply Scheme in Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000338/2024-2025 | 3336/TD | 22/10/2024 | 30 | SUBHRANGSHU SEKHAR GIRI | 3.06 | 0 | 0
1445 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Haipur PWSS Block Contai - I in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000377/2021-2022 | BP-2021-22-132 | 18/10/2021 | 0 | SRIMANTA KUMAR MAITY | 78.57 | 0 | 0
1446 | Tamluk Division |  | Retrofitting to accommodate FHTC 310 Nos. under JJM at Santeswarpur J.L No-8(Part), Purushottampur J.L. No-11(Part), Kholaberia J.L. No-36(part), Ranisai J.L. No-40(Part) in Ranisai PWSS within Block - Ramnagar under Digha Sub-Division of Tamluk Division, P.H.E. Dte. in the District of Purba Medinipur. ( PHASE-II) |  |  | ORD/000269/2020-2021 | 2922/TD | 22/02/2021 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.9 | 0 | 100
1447 | Tamluk Division |  | Retrofitting to accommodate FHTC 310 Nos. under JJM in Ranisai PWSS Block Ramnagar - I in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  |  | VCH/000379/2021-2022 |  | 04/10/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.68 | 0 | 0
1448 | Tamluk Division |  | Retrofitting to accommodate FHTC 310 Nos. under JJM in Ranisai PWSS Block Ramnagar - I in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  |  | VCH/000424/2021-2022 | BP-2021-22-136 | 18/10/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 34.68 | 0 | 0
1449 | Tamluk Division |  | Retrofitting to accomodate FHTC (1050 nos.) under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance work) Block- Kolaghat in the District of Purba Medinipur under Tamluk Sub Division of Tamluk Division,PHE Dte . (Phase-II) |  |  | ORD/000128/2021-2022 | 1008/TD | 02/11/2021 | 45 | M/S A.R. ENTERPRISE | 60.36 | 59.87 | 100
1450 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bar Basudevpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000189/2021-2022 | 1198/TD | 02/12/2021 | 20 | RADIANT | 4.28 | 4.21 | 100
1451 | Tamluk Division | Haldia Sub-Division | Additional Laying Distribution System of 200 mm dia upvc pipe line and Cannel Crossing by G.I. pipes with cement concrete and M.S. structure on 110 mm dia(sec 2-14) and 180 mm dia(sec-20-23) of pipe line of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000307/2022-2023 | 1147/TD | 31/08/2022 | 20 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.88 | 24.11 | 100
1452 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (646 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000335/2021-2022 | 1769/TD | 08/02/2022 | 680 | ZENITH CONSTRUCTION | 84.54 | 50.24 | 75
1453 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (446 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2021-2022 | 1770/TD | 08/02/2022 | 40 | SHAKEEL KHAN | 53.9 | 17.85 | 55
1454 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line and inter connection at Barbasudevpur Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2023-2024 | 802/TD | 30/05/2023 | 20 | PULAK KUMAR SAMANTA | 6.22 | 0 | 100
1455 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part- III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000338/2021-2022 | 1771/TD | 08/02/2022 | 30 | MAA KALI CONSTRUCTION | 47.34 | 28.76 | 100
1456 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barbasudevpur Water Supply Scheme to accommodate FHTC (346 nos.) in Haldia Block of Purba Medinipur District under Tamluk Division, PHE Dte. (Part-IV) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000339/2021-2022 | 1772/TD | 08/02/2022 | 30 | FARID UDDIN AHMED | 47.43 | 43.13 | 80
1457 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Barbasudevpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000382/2022-2023 | 1383/TD | 23/09/2022 | 45 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 4.13 | 3.88 | 100
1458 | Tamluk Division | Haldia Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Barbasudebpur Water Supply Scheme,with in Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000484/2022-2023 | 1886/TD | 24/11/2022 | 828 | MAA ANANDAMAYEE | 104.61 | 42.72 | 96
1459 | Tamluk Division | Haldia Sub-Division | Laying of additional 90mm dia. distribution pipe line and cannel crossing by M.S. structure for 140mm dia. distribution pipe laying of Barbasudevpur Water Supply Scheme of Haldia Sub-Division under Tamluk Division P.H.E. Dte. (Phase - II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000663/2022-2023 | 2348/TD | 10/01/2023 | 20 | MAA KALI CONSTRUCTION | 13.75 | 13.66 | 0
1460 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (for Barbasudevpur PWSS, Lakshya PWSS, Chaitanyapur Zone-II PWSS, Manoharpur PWSS) (Phase-VI) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001171/2023-2024 | 767/HSD | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0 | 100
1461 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000027/2021-2022 | 1300/TD | 20/12/2021 | 0 | Resource Division | 19.51 | 0 | 0
1462 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000056/2021-2022 | 1834/TD | 15/02/2022 | 0 | Resource Division | 9.79 | 0 | 0
1463 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 200 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Baghaput Water Supply Scheme within Deshpran ( Contai- II)Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000188/2022-2023 | 813/TD | 12/07/2022 | 1147 | G. B. CONSTRUCTION & CO. | 378.59 | 240.73 | 70
1464 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Baghaput Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000314/2021-2022 | 1548/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.62 | 3.26 | 100
1465 | Tamluk Division | Contai Sub-Division | Repairing Of Boundary Wall of Head Work site and Pump House No - II under Augmentation of Baghaput Water Supply Scheme within Deshpran (Contai-II) Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000424/2023-2024 | 493/TD | 10/05/2023 | 30 | SUBHENDU HAZRA | 3.73 | 0 | 0
1466 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Baghaput Water Supply Scheme in Contai II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000488/2022-2023 | 1928/TD | 28/11/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 5.35 | 5.35 | 100
1467 | Tamluk Division | Contai Sub-Division | Repair and Renovation of 136 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Baghaput Water Supply Scheme within Contai-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000733/2022-2023 | 2563/TD | 24/01/2023 | 60 | NARAYAN CHANDRA DAS | 11.29 | 7.54 | 0
1468 | Tamluk Division | Contai Sub-Division | Repair And renovation Of Pump House No. I & II under Augmentation of Baghaput Water Supply Scheme within Deshpran( Contai- II) Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000958/2022-2023 | 421/CSD | 17/03/2023 | 30 | THE GODFATHER TRADING COMPANY | 2.24 | 0 | 100
1469 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000018/2022-2023 | 406/TD | 25/05/2022 | 0 | Resource Division | 22.79 | 0 | 0
1470 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000089/2022-2023 | 1269/TD | 12/09/2022 | 0 | Resource Division | 11.27 | 0 | 0
1471 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Durmut Water Supply Scheme within Despran & Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000082/2022-2023 | 394/TD | 23/05/2022 | 1306 | MAHAVIR PUMPS MFG. PVT. LTD. | 430.39 | 305.68 | 81
1472 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Durmut Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000319/2021-2022 | 1612/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.09 | 3.09 | 100
1473 | Tamluk Division | Haldia Electrical Sub-Division | Repairing and Renovation of over head reservoir in Durmuth Water Supply Scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000491/2024-2025 | 3771/TD | 10/12/2024 | 294 | BISWA NIRMAN ENTERPRISE. | 7.05 | 0 | 100
1474 | Tamluk Division | Haldia Electrical Sub-Division | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 150 mm dia MS Carrier Pipe in between Mast NO 54/9 TO Mast NO 54/8 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =45 M) Section 482 TO 486. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000514/2023-2024 | 1744/TD | 01/08/2023 | 30 | ROY CONSTRUCTION | 72.22 | 0 | 64
1475 | Tamluk Division | Haldia Electrical Sub-Division | Jack Pushing of Railway Track in between Station Nachinda and Kanthi of Augmentation of Durmuth Piped Water Supply Scheme of 600 mm dia MS Casing Pipe and 100 mm dia MS Carrier Pipe in between Mast NO 55/17 TO Mast NO 55/16 With in Contai Sub Division under Tamluk Division P.H.E DTE. (TOTAL LENGTH =127M) Section 209 TO 231. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000515/2023-2024 | 1745/TD | 01/08/2023 | 30 | ROY CONSTRUCTION | 75.01 | 0 | 71
1476 | Tamluk Division | Haldia Electrical Sub-Division | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 4.26 | 100
1477 | Tamluk Division | Haldia Electrical Sub-Division | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000744/2023-2024 | 3133/TD | 07/12/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.6 | 0 | 100
1478 | Tamluk Division | Haldia Electrical Sub-Division | Augmentation of Durmut Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000746/2023-2024 | 3134/TD | 07/12/2023 | 20 | ABHIJIT BERA | 3.85 | 0 | 100
1479 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Hade work site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000901/2023-2024 | 248/TD | 11/01/2024 | 450 | ANIRBAN MONDAL | 11.93 | 0 | 100
1480 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Tube Well (2nd Tube Well) site for Durmuth Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000904/2023-2024 | 249/TD | 11/01/2024 | 30 | BISWA NIRMAN ENTERPRISE. | 5.73 | 0 | 100
1481 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Pump House , Tube well , Boundary Wall, Rising main for Durmuth PWSS in Deshpran & Contai III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001109/2023-2024 | 559/TD | 15/02/2024 | 40 | DEVEN ENTERPRISES | 33.8 | 0 | 0
1482 | Tamluk Division | Haldia Electrical Sub-Division | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 0 | 100
1483 | Tamluk Division | Haldia Electrical Sub-Division | Repairing and Renovation of pump house 1 and boundary wall in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001372/2023-2024 | 240/CSD | 07/02/2024 | 45 | BISWA NIRMAN ENTERPRISE. | 0.71 | 0 | 100
1484 | Tamluk Division | Haldia Electrical Sub-Division | Repairing and Renovation of pump house 2 in Durmuth water supply scheme in Contai-II and Contai-III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001373/2023-2024 | 241/CSD | 07/02/2024 | 180 | RABINDRANATH DAS | 0.92 | 0 | 100
1485 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000013/2022-2023 | 91/TD | 11/04/2022 | 0 | Resource Division | 210.65 | 0 | 0
1486 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000084/2022-2023 | 1271/TD | 12/09/2022 | 0 | Resource Division | 23.95 | 0 | 0
1487 | Tamluk Division | Haldia Electrical Sub-Division | Payment for Railway Application Fees. for Durmut PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | VCH/000450/2022-2023 |  | 01/08/2022 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 17.19 | 0 | 0
1488 | Tamluk Division | Haldia Electrical Sub-Division | Charges for Way Leave Permission under railway track permission for Durmut PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | VCH/000520/2022-2023 | BP-2022-23-271 | 29/08/2022 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 3.15 | 0 | 0
1489 | Tamluk Division | Contai Sub-Division | Repairing of inlet, outlet, washout pipe and allied works of 180 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for PASHIM KAMARDA W/S Scheme in Contai- III Block Of Purba Medinipur District under Contai Sub Division within Tamluk division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000175/2022-2023 | 394 / CSD | 12/07/2022 | 30 | GIRI CONSTRUCTION | 2.26 | 2.22 | 100
1490 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC under JJM in PASCHIM KAMARDA PWSS ( Phase- II) Block - Contai-III in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000545/2021-2022 | 2005/TD | 08/03/2022 | 25 | RAJ KUMAR SINGHA | 39.32 | 0 | 100
1491 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valves for Paschim Kamarda Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000659/2021-2022 | 889 / CSD | 23/03/2022 | 15 | PARTHA CONSTRUCTION | 1.3 | 1.3 | 100
1492 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (345 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-A] | Assistant Engineer | Junior Engineer | ORD/000121/2022-2023 | 614/TD | 21/06/2022 | 20 | ARABINDA GHOSH | 30.95 | 30.93 | 100
1493 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for Retrofitting to accommodate FHTC (620 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-II, Block- Kolaghat in the District of Purba Medinipur. (Phase-III)[PART-B] | Assistant Engineer | Junior Engineer | ORD/000123/2022-2023 | 615/TD | 21/06/2022 | 25 | MAA ANANDAMAYEE | 65.39 | 65.43 | 100
1494 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000031/2022-2023 | 130/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 18.87 | 100
1495 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Gopalpur Water Supply Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000032/2022-2023 | 131/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100
1496 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Gopalpur Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000170/2021-2022 | 1179/TD | 02/12/2021 | 20 | HORIZEN | 9.54 | 9.54 | 100
1497 | Tamluk Division | Haldia Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 900 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000201/2022-2023 | 832/TD | 15/07/2022 | 1082 | RAJ KUMAR SINGHA | 838.35 | 675.56 | 62
1498 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room at Head work & 2nd tube well site respectively of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000302/2022-2023 | 1152/TD | 31/08/2022 | 45 | RAI CONSTRUCTION | 4.12 | 4.09 | 0
1499 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with Water Supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000316/2022-2023 | 1227/TD | 07/09/2022 | 60 | M/S SOURAV MAHAPATRA | 4.84 | 4.42 | 100
1500 | Tamluk Division | Haldia Sub-Division | Cannel crossing, Road crossing and Drum sheet pilling of Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000449/2023-2024 | 1470/TD | 13/07/2023 | 40 | RAJ KUMAR SINGHA | 71.38 | 0 | 60
1501 | Tamluk Division | Haldia Sub-Division | Boundery wall including land development at 4th tube well site of Gopalpur Pwss under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000462/2023-2024 | 1492/TD | 17/07/2023 | 30 | GUCHHAIT ENTERPRISE | 8.53 | 0 | 100
1502 | Tamluk Division | Haldia Sub-Division | Continuation work order for hiring of one no. Diesel motor cabs (Luxury Taxi commercial standard non air conditioned) Bharat Stage -IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of the Assistant Engineer, Haldia Sub-Division under Tamluk Division, PHE dte. within Purba Medinipur District. For the period from 01/01/2023 to 31/12/2023. (12 Months) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000563/2022-2023 | 815/HSD | 29/12/2022 | 365 | SANTANU PATTANAYAK | 1.5 | 2.78 | 100
1503 | Tamluk Division | Haldia Sub-Division | New Construction of boundary wall at 3rd T/W site (50mt) of Gopalpur Water Supply Scheme under Haldia Sub-Division PHE Dte.. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000641/2022-2023 | 2352/TD | 10/01/2023 | 45 | M/S SOURAV MAHAPATRA | 6.48 | 5.01 | 0
1504 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well site of Gopalpur Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000644/2022-2023 | 2353/TD | 10/01/2023 | 60 | GUCHHAIT ENTERPRISE | 4.63 | 3.67 | 100
1505 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line and inter connection at Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000740/2023-2024 | 3067/TD | 30/11/2023 | 481 | RAJ KUMAR SINGHA | 14.06 | 0 | 100
1506 | Tamluk Division | Haldia Sub-Division | Laying Distribution System of Leftout portion, Providing Functional Household Tap Connection (FHTC) and construction of new Boundary wall at Gopalpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001216/2023-2024 | 980/TD | 13/03/2024 | 456 | RAJ KUMAR SINGHA | 128.78 | 0 | 30
1507 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000092/2022-2023 | 1373/TD | 23/09/2022 | 0 | Resource Division | 37.63 | 0 | 0
1508 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000110/2022-2023 | 1674/TD | 03/11/2022 | 0 | Resource Division | 96.09 | 0 | 0
1509 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhanghara Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000167/2021-2022 | 1171/TD | 01/12/2021 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 10.76 | 10.07 | 100
1510 | Tamluk Division | Contai Sub-Division | Supply & Delivery 80 mm dia Sluice Valve for Dhanghara W/S Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur.(Phase-I) (Supply at Mukutshila Store) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000359/2022-2023 | 1298/TD | 13/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.9 | 3.9 | 100
1511 | Tamluk Division | Contai Sub-Division | Augmentation of Dhanghara Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block Of Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000472/2021-2022 | 1947/TD | 03/03/2022 | 150 | M/S S. S. ENTERPRISE | 547.65 | 439.13 | 90
1512 | Tamluk Division | Contai Sub-Division | Rising main 150mm dia DI(K9) Rising main pipeline with specials and other allied works at 3rd Tube Well Site for Augmentation of Dhanghara W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000472/2023-2024 | 1498/TD | 17/07/2023 | 622 | SUDIP MANNA | 5.27 | 0 | 100
1513 | Tamluk Division | Contai Sub-Division | Re-laying of Distribution pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Dhanghara PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000615/2024-2025 | 667/TD | 03/03/2025 | 40 | SRIMANTA KUMAR MAITY | 23.42 | 0 | 0
1514 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000772/2022-2023 | 105 / CSD | 19/01/2023 | 15 | BIBEKANANDA DAS | 0.95 | 0 | 0
1515 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Dhanghara Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000886/2022-2023 | 439 / CSD | 20/03/2023 | 15 | SAURAV HAZRA | 0.95 | 0.95 | 0
1516 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorine Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E .Dte. Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001152/2023-2024 | 560/TD | 15/02/2024 | 240 | GITA ENTERPRISE | 3.72 | 0 | 100
1517 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2021-2022 | 1250/TD | 13/12/2021 | 0 | Resource Division | 10.79 | 0 | 0
1518 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000035/2021-2022 | 1952/TD | 04/03/2022 | 0 | Resource Division | 18.66 | 0 | 0
1519 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (50 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000141/2022-2023 | 715/TD | 28/06/2022 | 20 | SANTANU PATTANAYAK | 4.27 | 4.21 | 100
1520 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (840 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000152/2022-2023 | 727/TD | 04/07/2022 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 70.64 | 64.02 | 95
1521 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (460 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000153/2022-2023 | 728/TD | 04/07/2022 | 25 | NARAYAN MANDAL | 80.94 | 55.3 | 100
1522 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (500 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000154/2022-2023 | 729/TD | 04/07/2022 | 25 | ZENITH CONSTRUCTION | 80.53 | 78.32 | 100
1523 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (370 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000156/2022-2023 | 731/TD | 04/07/2022 | 1101 | MAA KALI CONSTRUCTION | 39.79 | 23.31 | 75
1524 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000157/2022-2023 | 733/TD | 04/07/2022 | 885 | R CONSTRUCTION | 20.34 | 11.21 | 78
1525 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (200 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000158/2022-2023 | 734/TD | 04/07/2022 | 1072 | TAPAN BERA | 20.46 | 10.92 | 100
1526 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (210 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000159/2022-2023 | 735/TD | 04/07/2022 | 887 | SUDIP MANNA | 20.03 | 10.04 | 95
1527 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (96 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000160/2022-2023 | 736/TD | 04/07/2022 | 15 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 10 | 5.98 | 100
1528 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (82 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000161/2022-2023 | 737/TD | 04/07/2022 | 15 | MAHAPRABHU ENTERPRISE | 10.01 | 9.87 | 100
1529 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (104 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-N) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000162/2022-2023 | 738/TD | 04/07/2022 | 1312 | MODERN CONSTRUCTION | 10 | 5.04 | 100
1530 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (115 nos) work within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-O) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000163/2022-2023 | 739/TD | 04/07/2022 | 15 | CANVAS | 9.54 | 4.82 | 55
1531 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (110 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-P) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000164/2022-2023 | 740/TD | 04/07/2022 | 15 | TARUN KHATUA | 10.01 | 10 | 100
1532 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (350 nos)work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000165/2022-2023 | 732/TD | 04/07/2022 | 20 | SK MAIDUL ISLAM | 40.03 | 32.28 | 85
1533 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Chaitanyapur Zone-I Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (850 nos) work and Construction of R.C.C. Over Head Reservoir of capacity 700 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000244/2022-2023 | 1004/TD | 08/08/2022 | 1242 | HARIPADA PATTANAYAK | 212.75 | 0 | 80
1534 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head Work Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 2nd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-II Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Well Site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000337/2022-2023 | 1250/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 77.68 | 0 | 100
1535 | Tamluk Division | Haldia Sub-Division | Canal Crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I W/S Scheme under Haldia Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000359/2023-2024 | 927/TD | 01/06/2023 | 30 | NARAYAN MANDAL | 7.82 | 5.07 | 100
1536 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000409/2022-2023 | 1563/TD | 12/10/2022 | 720 | KRISHNENDU SEKHAR DAS | 4.78 | 0 | 100
1537 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Chaitanyapur Zone -I Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000410/2022-2023 | 1564/TD | 12/10/2022 | 45 | SAYAN MAITY | 3.95 | 3.93 | 0
1538 | Tamluk Division | Haldia Sub-Division | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase - 2) Name of Work site :- 1) Chaitanyapur Zone-I (Part-A) PWSS, 2) Chaitanyapur Zone-I (Part-B) PWSS, 3) Chaitanyapur Zone-I (Part-C) PWSS, 4) Chaitanyapur Zone-I (Part-D) PWSS, 5) Chaitanyapur Zone-I (Part-E) PWSS, 6) Chaitanyapur Zone-I (Part-F) PWSS, 7) Chaitanyapur Zone-I (Part-G) PWSS & 8) Chaitanyapur Zone-I (Part-H) PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000439/2022-2023 | 724/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100
1539 | Tamluk Division | Haldia Sub-Division | Installation of display Board of 8 nos work site within different PWSS under Haldia Sub-Division of Tamluk Division, PHE Dte. District Purba Medinipur. (Phase -3) Name of Work site :- 1) Chaitanyapur Zone-I (Part-I) PWSS, 2) Chaitanyapur Zone-I (Part-J) PWSS, 3) Chaitanyapur Zone-I (Part-K) PWSS, 4) Chaitanyapur Zone-I (Part-L) PWSS, 5) Chaitanyapur Zone-I (Part-M) PWSS, 6) Chaitanyapur Zone-I (Part-N) PWSS, 7) Chaitanyapur Zone-I (Part-O) PWSS & 8) Chaitanyapur Zone-I (Part-P) PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000440/2022-2023 | 725/HSD | 28/10/2022 | 3 | TAPAN BERA | 0.93 | 0.93 | 100
1540 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chaitanyapur (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000458/2021-2022 | 1662/TD | 21/01/2022 | 20 | RADIANT | 4.13 | 4.13 | 100
1541 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 4th tubewell site of Chaitanyapur Zone-I Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-13mtr) & (length of Approach road-20mtr). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000572/2023-2024 | 2163/TD | 31/08/2023 | 30 | TAPAN BERA | 13.62 | 0 | 100
1542 | Tamluk Division | Haldia Sub-Division | Laying Rising main work of ground water based Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000580/2023-2024 | 2202/TD | 01/09/2023 | 20 | ELECTIVA ENTERPRISE | 6.04 | 0 | 40
1543 | Tamluk Division | Haldia Sub-Division | Earth filling and Making approach road at OHR site at Chaitanyapur (Zone-I) Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -45mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000593/2023-2024 | 2208/TD | 01/09/2023 | 490 | BAGLAMUKHI SECURITY SERVICE | 8.55 | 0 | 0
1544 | Tamluk Division | Haldia Sub-Division | Construction of Damaged bitumen road from PHE office to Rampur more at Chaitanyapur (zone-1) W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of approach road -330mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000616/2023-2024 | 2281/TD | 07/09/2023 | 20 | RAI CONSTRUCTION | 9.04 | 0 | 100
1545 | Tamluk Division | Haldia Sub-Division | Laying left out pipe line and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur (Zone-I) Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000636/2023-2024 | 2448/TD | 20/09/2023 | 854 | S.D. CONSTRUCTION | 69.7 | 0 | 40
1546 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 4th Tube Well site of Chaitanyapur Zone-I Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000660/2022-2023 | 2345/TD | 10/01/2023 | 40 | TAPAN BERA | 5.08 | 5.06 | 100
1547 | Tamluk Division | Haldia Sub-Division | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000801/2022-2023 | 909/HSD | 23/02/2023 | 10 | RAI CONSTRUCTION | 0.95 | 0.92 | 0
1548 | Tamluk Division | Haldia Sub-Division | Construction of Boundary Wall at 1st tube well site of Chaitanyapur Zone-I water supply scheme, under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000802/2022-2023 | 910/HSD | 23/02/2023 | 10 | MODERN CONSTRUCTION | 0.95 | 0.92 | 100
1549 | Tamluk Division | Haldia Sub-Division | Canal crossing and supporting work with Drum Sheet walling and Earth filling in Chaitanyapur Zone-I Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte (PART - J). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000856/2022-2023 | 3209/TD | 14/03/2023 | 20 | TAPAN BERA | 8.74 | 8.72 | 100
1550 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000030/2022-2023 | 467/TD | 02/06/2022 | 0 | Resource Division | 10.8 | 0 | 0
1551 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000031/2022-2023 | 466/W | 02/06/2022 | 0 | Resource Division | 40.61 | 0 | 0
1552 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000032/2022-2023 | 468/W | 02/06/2022 | 0 | Resource Division | 30.41 | 0 | 0
1553 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000040/2022-2023 | 829/TD | 15/07/2022 | 0 | Resource Division | 55.98 | 0 | 0
1554 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Left-Out portion HDPE Pipe line of Distribution system by HDPE pipes with allied works of Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000288/2024-2025 | 3053/TD | 19/09/2024 | 180 | M/S. NEW DINDA ENTERPRISE | 48.21 | 0 | 5
1555 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 2nd TW site for Amarshikasba Zone-I PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000289/2023-2024 | 591/TD | 17/05/2023 | 40 | M/S SOURAV MAHAPATRA | 9.2 | 0 | 45
1556 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000321/2022-2023 | 591/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.71 | 100
1557 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3rd Pump House & Boundary wall of Amarshi Kasba Zone-I & its adjoining moujas PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000329/2025-2026 | 1716/TD | 30/06/2025 | 40 | GOUTAM DEY | 9.9 | 0 | 0
1558 | Tamluk Division | Haldia Electrical Sub-Division | Repair and Renovation of Pump House & Boundary Wall and others allied works for 1st Tube well site at Amarshi Kasba Zone-I Water Supply Scheme in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000359/2024-2025 | 3322/TD | 22/10/2024 | 30 | M/S. NEW DINDA ENTERPRISE | 2.76 | 0 | 0
1559 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000068/2023-2024 | 2644/TD | 13/10/2023 | 0 | Resource Division | 27.1 | 0 | 0
1560 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000117/2022-2023 | 1668/TD | 03/11/2022 | 0 | Resource Division | 90.44 | 0 | 0
1561 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshinchak Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000017/2022-2023 | 51/TD | 05/04/2022 | 20 | HORIZEN | 6.01 | 6 | 0
1562 | Tamluk Division | Haldia Sub-Division | Sinking of Tube well, Reparing & Renovation of 1st & 2nd Pump House, Construction of New 3rd Tube well site Pump House, Construction of 2 nos Pump House, Soil Investigation Test, Construction of Different Capacity OHR, Laying of Rising main, Laying of Distribution pipe line & FHTC(6512 Nos) works for Augmentation of Dakshinchak Zone- I and Dakshinchak Zone-II Water Supply Scheme under Haldia Sub-Division,of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000428/2023-2024 | 1411/TD | 12/07/2023 | 873 | M/S S. S. ENTERPRISE | 1432.04 | 0 | 6
1563 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-I Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000820/2023-2024 | 3288/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.38 | 0 | 30
1564 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Dakshinchak Zone-II Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000821/2023-2024 | 3287/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 10.9 | 0 | 30
1565 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000062/2023-2024 | 2638/TD | 13/10/2023 | 0 | Resource Division | 43.18 | 0 | 0
1566 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000233/2022-2023 | 2616/TD | 02/02/2023 | 0 | Resource Division | 349.36 | 0 | 0
1567 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000288/2022-2023 | 2641/TD | 02/02/2023 | 0 | Resource Division | 204.6 | 0 | 0
1568 | Tamluk Division | Contai Sub-Division | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division P.H.E. DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000112/2024-2025 | 1906/TD | 07/06/2024 | 361 | SK. NUR ISLAM | 45.39 | 0 | 35
1569 | Tamluk Division | Contai Sub-Division | Dismantling chlorinator room & Staff quater at Head Work Site/ Reserver site of Contai Saline Area Zone-II PWSS under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000232/2024-2025 | 2487/TD | 02/08/2024 | 105 | S R TRADING CORPORATION | 3.45 | 0 | 100
1570 | Tamluk Division | Contai Sub-Division | Renovation work of Spiral stair and related works for R.C.C. Over Head Reservoir of capacity 60000 Gallons at Keshurkunda mouza within Contai S.A. Zone-II W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur.( 2nd Part) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2021-2022 | 497 / CSD | 18/11/2021 | 21 | SRIMANTA KUMAR MAITY | 2.06 | 0 | 0
1571 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 63
1572 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000449/2021-2022 | 1684/TD | 28/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.86 | 4.85 | 100
1573 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-II Water Supply Scheme within Contai-I & III Dev. Block under Contai sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000500/2022-2023 | 1972/TD | 01/12/2022 | 1154 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 938.66 | 159.62 | 45
1574 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000027/2023-2024 | 612/TD | 17/05/2023 | 0 | Resource Division | 37.05 | 0 | 0
1575 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000106/2022-2023 | 1663/TD | 03/11/2022 | 0 | Resource Division | 315.36 | 0 | 0
1576 | Tamluk Division |  | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. |  |  | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 0 | 98
1577 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanpur PWSS Block- Ramnagar-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000278/2020-2021 | 2994/TD | 25/02/2021 | 60 | BASANTA KUMAR MAITY | 210.56 | 172.89 | 100
1578 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000196/2023-2024 | 306/TD | 24/04/2023 | 20 | RAMASISH ENTERPRISE | 11.41 | 11.41 | 100
1579 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Shilaberia Janka Zone-II Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000197/2023-2024 | 307/TD | 24/04/2023 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 0.3 | 0.3 | 100
1580 | Tamluk Division | Contai Sub-Division | Laying of left out pipe line by HDPE pipes with allied works of Shillaberia Jhanka Zone-II & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000238/2024-2025 | 2677/TD | 22/08/2024 | 156 | TARUN KOLEY | 79.64 | 0 | 95
1581 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000437/2022-2023 | 1650/TD | 02/11/2022 | 180 | TARUN KOLEY | 942.75 | 595.13 | 85
1582 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) with Approach road at 2nd TW site for Augmentation of Shillaberia Jhanka Zone-II PWSS within Khejuri -II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) | Assistant Engineer | Junior Engineer | ORD/000594/2024-2025 | 566/TD | 17/02/2025 | 40 | DAS ENTERPRISE | 9.15 | 0 | 0
1583 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i)300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at Head Works Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. ii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 2nd Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iii) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 4th Tube Well Site for Shillaberia Jhanka Zone-II PWSS in Khejuri-II Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000848/2022-2023 | 3145/TD | 09/03/2023 | 40 | B. K. ENTERPRISE | 70.37 | 53.19 | 75
1584 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) ii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 2nd TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iii) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) iv) Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 4th TW site for Augmentation of Shillaberia Jhanka Zone-II & its adjoining moujas PWSS in Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) v) Laying Rising main and other allied works Augmentation of Shillaberia Jhanka Zone-II W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000864/2022-2023 | 3219/TD | 14/03/2023 | 962 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.37 | 0 | 90
1585 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000181/2023-2024 | 630/W | 20/02/2024 | 0 | Resource Division | 6.3 | 0 | 0
1586 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000308/2022-2023 | 2965/TD | 27/02/2023 | 0 | Resource Division | 23.38 | 0 | 0
1587 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000167/2023-2024 | 114/TD | 05/01/2024 | 0 | Resource Division | 11.32 | 0 | 0
1588 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000212/2022-2023 | 2467/TD | 16/01/2023 | 0 | Resource Division | 19.42 | 0 | 0
1589 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Mayachar PWSS at Mahishadal Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000151/2024-2025 | 2062/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1590 | Tamluk Division | Haldia Sub-Division | Ground water based Mayachar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000630/2023-2024 | 2438/TD | 19/09/2023 | 180 | ANUSKA ENTERPRISE | 165.66 | 0 | 30
1591 | Tamluk Division | Haldia Sub-Division | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-III) [Chaitanyapur Zone-I PWSS, Dwariberia PWSS, Natshal Lakshya Zone-I PWSS & Mayachar PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000831/2023-2024 | 619/HSD, | 21/12/2023 | 7 | SANTANU PATTANAYAK | 0.83 | 0 | 100
1592 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000897/2022-2023 | 3347/TD | 22/03/2023 | 40 | PRANTIK DRILLING AGENCY | 61.77 | 0 | 50
1593 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000156/2023-2024 | 135/TD | 05/01/2024 | 0 | Resource Division | 8.04 | 0 | 0
1594 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000332/2022-2023 | 2983/TD | 27/02/2023 | 0 | Resource Division | 12.88 | 0 | 0
1595 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000190/2022-2023 | 2441/TD | 16/01/2023 | 0 | Resource Division | 33.17 | 0 | 0
1596 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Sofiabad W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000235/2023-2024 | 483/TD | 10/05/2023 | 60 | BABA LOKNATH CONSTRUCTION | 4.03 | 0 | 0
1597 | Tamluk Division | Contai Sub-Division | Laying of 150 mm dia & 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at Replacement of 2nd Tube Well & 1(One) no. Boosting Tube Well of Sofiabad & its adjoining mouzas Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000236/2023-2024 | 482/TD | 10/05/2023 | 600 | KAMAL KUMAR BERA | 3.92 | 0 | 0
1598 | Tamluk Division | Contai Sub-Division | Retrofitting to Accommodate 30 nos FHTC under JJM in Sofiabad PWSS Block- Contai-II ( Deshpran) of Tamluk Division, PHE Dte,in the districtof Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000394/2022-2023 | 1427/TD | 26/09/2022 | 15 | RELIABLE CONSTRUCTIONS | 1.28 | 0 | 100
1599 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Bamunia, Barasubarnagar, Sofiabad, Aladarput Retrofitting PWSS in Contai - II (Deshopran) Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001185/2023-2024 | 2333/CSD | 29/12/2023 | 15 | ABHIJIT BERA | 0.83 | 0 | 100
1600 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges(SER-KGP-2024-WL-49) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00137/2024-2025 | BP-2024-25-80 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.59 | 0 | 0
1601 | Tamluk Division | Contai Sub-Division | Payment of wayleave charges(SER-KGP-2024-WL-50) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00138/2024-2025 | BP-2024-25-81 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 9.38 | 0 | 0
1602 | Tamluk Division | Contai Sub-Division | payment of way leave facility cahrges(SER-KGP-2024-WL-51) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00139/2024-2025 | BP-2024-25-82 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.3 | 0 | 0
1603 | Tamluk Division | Contai Sub-Division | Payment of Wayleave facility charges (SER-KGP-2024-WL-52) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00140/2024-2025 | BP-2024-25-83 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.28 | 0 | 0
1604 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges(SER-KGP-2024-WL-53) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00141/2024-2025 | BP-2024-25-84 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0
1605 | Tamluk Division | Contai Sub-Division | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00570/2024-2025 | BP-2024-25-236 | 12/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.25 | 0 | 0
1606 | Tamluk Division | Contai Sub-Division | Way Leave Plan and Survey Charges under railway track permission for Application ID SER-KGP-2023-WL-136 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01940/2023-2024 | BP-2023-24-894 | 22/02/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.65 | 0 | 0
1607 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-KANTHI Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-B) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. (2nd Call) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000147/2024-2025 | 1735/CSD | 20/06/2024 | 20 | ABHIJIT BERA | 2.31 | 0 | 100
1608 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Contai Saline Area Zone-I(Phase-A) Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000149/2024-2025 | 1732/CSD | 20/06/2024 | 20 | GIRI CONSTRUCTION | 1.16 | 0 | 100
1609 | Tamluk Division | Contai Sub-Division | Construction Boundary Wall & Repairing and renovation of Pump House and others allied works for 2nd Tube well site under Contai Saline Area Zone-I (Phase-B) Water Supply scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000241/2024-2025 | 2680/TD | 22/08/2024 | 40 | BISWA NIRMAN ENTERPRISE. | 10.08 | 0 | 0
1610 | Tamluk Division | Contai Sub-Division | Dismantling chlorinator room & Staff quater at Head Work Site/ Reserver site of Contai S.A. Zone I (Phase B) PWSS under Contai Sub Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000282/2024-2025 | 3035/TD | 18/09/2024 | 21 | SUBHENDU HAZRA | 3.53 | 0 | 0
1611 | Tamluk Division | Contai Sub-Division | Construction of Pump House & Boundary Wall and others allied works for 1st Tube well site under Contai Saline Area Zone-I (Phase-A) Water Supply Scheme ( Augmentation) in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000294/2024-2025 | 3063/TD | 19/09/2024 | 40 | GUCHHAIT ENTERPRISE | 14.07 | 0 | 0
1612 | Tamluk Division | Contai Sub-Division | Repairing and Renovation of Boundary Wall, Construction of Pump house and allied works of Reservoir (OHR) Site under Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000334/2024-2025 | 3292/TD | 05/10/2024 | 280 | DEBANANDA CONSTRUCTION | 21.34 | 0 | 35
1613 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Contai Saline Area Zone-I (Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000634/2022-2023 | 2313/TD | 05/01/2023 | 966 | DAS CONSTRUCTION | 439.86 | 0 | 42
1614 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at Head Work Site of Solat Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 124 Plot No. 421, Mouza-Dakshin Caraikhia under Contai Saline Area Zone-II Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 157 Plot No. 146, Mouza- Kharipukuria under Contai Saline Area Zone-I (Part-A) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at J.L. No. 415 Plot No. 925(S), 397(N), Mouza- Bhaitghar under Contai Saline Area Zone-I (Part-B) Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000379/2022-2023 | 1361/TD | 22/09/2022 | 40 | B. K. ENTERPRISE | 72.46 | 15.29 | 63
1615 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Contai Saline Area Zone-I ( Phase - B) Water Supply Scheme within Contai- I & III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. (Part-II) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000697/2022-2023 | 2312/TD | 05/01/2023 | 739 | DAS CONSTRUCTION | 180.42 | 0 | 45
1616 | Tamluk Division | Contai Sub-Division | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- I within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001238/2023-2024 | 1086/TD | 16/03/2024 | 20 | RUPKUMAR KARMAKAR | 18.4 | 0 | 0
1617 | Tamluk Division | Contai Sub-Division | Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method with 200 dia UPVC Strainer of 30 M. length all complete including cost of materials for Contai Saline Area Zone-I Water Supply Scheme of Tube Well No.- II within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001239/2023-2024 | 1085/TD | 16/03/2024 | 20 | RUPKUMAR KARMAKAR | 18.24 | 0 | 0
1618 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000026/2023-2024 | 611/TD | 17/05/2023 | 0 | Resource Division | 31.42 | 0 | 0
1619 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000105/2022-2023 | 1661/TD | 03/11/2022 | 0 | Resource Division | 239.21 | 0 | 0
1620 | Tamluk Division | Contai Sub-Division | Drum Sheet Walling & allied works of Pachhari PWSS (PART-A) in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000319/2024-2025 | 3222/TD | 01/10/2024 | 25 | THREE MAA ENTERPRISE | 9.45 | 0 | 0
1621 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for PACHHARI PWSS (PART-B) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (PHASE-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000533/2024-2025 | 211/TD | 15/01/2025 | 376 | SAURAV HAZRA | 12.27 | 0 | 0
1622 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (357 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000634/2023-2024 | 2443/TD | 19/09/2023 | 682 | THREE MAA ENTERPRISE | 226.83 | 0 | 32
1623 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line & Accommodate FHTC (420 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000873/2022-2023 | 3210/TD | 14/03/2023 | 1106 | ABHIJIT BERA | 82.33 | 35.1 | 50
1624 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (170 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000875/2022-2023 | 3211/TD | 14/03/2023 | 1104 | KAMAL KUMAR BERA | 19.49 | 5.93 | 45
1625 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (75nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000876/2022-2023 | 3212/TD | 14/03/2023 | 20 | PARTHA CONSTRUCTION | 9.77 | 0 | 45
1626 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 430 nos) under JJM with allied work of PACHAHRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000912/2022-2023 | 3561/TD | 29/03/2023 | 785 | OM ENTERPRISE | 80.86 | 20.02 | 55
1627 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000183/2023-2024 | 632/W | 20/02/2024 | 0 | Resource Division | 8.94 | 0 | 0
1628 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000189/2022-2023 | 2388/TD | 16/01/2023 | 0 | Resource Division | 34.82 | 0 | 0
1629 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000208/2023-2024 | 417/TD | 02/05/2023 | 719 | ARABINDA GHOSH | 113.16 | 29.89 | 46
1630 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Boundary wall at 1st. & 2nd. Tube well site, Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room, interconnection with laying of 150 mm dia & 200 mm dia DI(K-9) Rising main and Accommodate FHTC (638 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000212/2023-2024 | 416/TD | 02/05/2023 | 660 | KRISHNENDU SEKHAR DAS | 140.04 | 68.65 | 74
1631 | Tamluk Division | Tamluk Sadar Sub-Division | Earth work in filling by carried earth and Construction of link Road for Naichanpur and its adjoining mouzas new Piped Water Supply Scheme within Moyna Block, under Tamluk Sub-Divn. of Tamluk Division. P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000654/2023-2024 | 2619/TD | 11/10/2023 | 25 | KRISHNENDU SEKHAR DAS | 9.57 | 0 | 69
1632 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Pump House & Accommodate FHTC (375 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000890/2022-2023 | 3244/TD | 15/03/2023 | 660 | GHOSH ENTERPRISE | 90.18 | 54.85 | 65
1633 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System & Accommodate FHTC (500 nos) with allied works under JJM for Naichhanpur and its Adjoining Mouzas PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000891/2022-2023 | 3245/TD | 15/03/2023 | 854 | ADHIKARY CONSTRUCTION | 64.64 | 32.51 | 60
1634 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000010/2024-2025 | 1568/TD | 23/04/2024 | 0 | Resource Division | 9.32 | 0 | 0
1635 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000327/2022-2023 | 2989/TD | 27/02/2023 | 0 | Resource Division | 16.3 | 0 | 0
1636 | Tamluk Division | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of SAHAJADAPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: PICHABANI C.C.C. Ref. Memo No- 2004772844/QUOT/03 DT. 14-06-2024 Application NO- 2004772844 Application type-New connection Consumer Id- 204329286 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00591/2024-2025 | BP-2024-25-289 | 29/07/2024 | 0 | WBSEDCL | 14.1 | 0 | 0
1637 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Sahajadapur PWSS at Contai-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000881/2023-2024 | 203/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0 | 0
1638 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000068/2024-2025 | 2977/TD | 12/09/2024 | 0 | Resource Division | 3.28 | 0 | 0
1639 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000166/2022-2023 | 2392/TD | 16/01/2023 | 0 | Resource Division | 34.34 | 0 | 0
1640 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Amtalia W/S Scheme within Contai- II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000437/2023-2024 | 1420/TD | 12/07/2023 | 30 | PARIA ENTERPRISE | 9.47 | 0 | 0
1641 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Dakshin Utaspur PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000166/2024-2025 | 2078/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1642 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000128/2023-2024 | 91/TD | 05/01/2024 | 0 | Resource Division | 8.11 | 0 | 0
1643 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000276/2022-2023 | 2681/TD | 06/02/2023 | 0 | Resource Division | 15.32 | 0 | 0
1644 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000191/2022-2023 | 2384/TD | 16/01/2023 | 0 | Resource Division | 19.89 | 0 | 0
1645 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 911 | JAYANTA KUMAR MONDAL | 1264.74 | 0 | 30
1646 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Purba Mahammadpur PWSS at Deshpran Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001275/2023-2024 | 1049/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1647 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000075/2024-2025 | 2973/TD | 12/09/2024 | 0 | Resource Division | 6.99 | 0 | 0
1648 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000205/2022-2023 | 2407/TD | 16/01/2023 | 0 | Resource Division | 18.82 | 0 | 0
1649 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000144/2022-2023 | 2447/TD | 16/01/2023 | 0 | Resource Division | 22.75 | 0 | 0
1650 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
1651 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000098/2024-2025 | 2960/TD | 12/09/2024 | 0 | Resource Division | 1.92 | 0 | 0
1652 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000214/2022-2023 | 2400/TD | 16/01/2023 | 0 | Resource Division | 30.7 | 0 | 0
1653 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Boundary Wall, Providing Functional Household Tap Connection (1277 Nos), including 2 years Operation & Maintenance For Satkalua, Uttar Sautanchak, Pipe Water Supply Scheme within TAMLUK Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000218/2023-2024 | 449/TD | 04/05/2023 | 698 | TARUN KOLEY | 549.23 | 0 | 75
1654 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000218/2022-2023 | 2673/TD | 06/02/2023 | 0 | Resource Division | 19.08 | 0 | 0
1655 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Barchunfali PWSS Block Contai-I in the District of Purba Medinipur. |  |  | ORD/000026/2020-2021 | 2102/TD | 05/11/2020 | 180 | DAS CONSTRUCTION | 96.5 | 1.82 | 100
1656 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000466/2021-2022 | 311/W | 08/10/2021 | 0 | DAS CONSTRUCTION | 16.22 | 0 | 0
1657 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000612/2020-2021 | 686/W | 27/01/2021 | 0 | DAS CONSTRUCTION | 59.4 | 0 | 0
1658 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Barchunfali W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001266/2020-2021 | 1040/W | 30/03/2021 | 0 | DAS CONSTRUCTION | 18.19 | 0 | 0
1659 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2843 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Chakbhabani PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000489/2023-2024 | 1564/TD | 19/07/2023 | 180 | TARUN KOLEY | 947.78 | 0 | 35
1660 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2024-2025 | 1649/TD | 29/04/2024 | 0 | Resource Division | 17.51 | 0 | 0
1661 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000343/2022-2023 | 2996/TD | 27/02/2023 | 0 | Resource Division | 22.46 | 0 | 0
1662 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at t/w no.-II of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753851 Con ID-204322327 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00593/2024-2025 | BP-2024-25-293 | 29/07/2024 | 0 | WBSEDCL | 4.56 | 0 | 0
1663 | Tamluk Division | Digha Sub-Division | Quotation for new service connection at TW-1 of Bhatsalia ws scheme under MMD,PHE Dte, Block-Egra-1, Chorpalia CCC Application no-2004753843 CON ID-204318364 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00595/2024-2025 | BP-2024-25-292 | 29/07/2024 | 0 | WBSEDCL | 5.37 | 0 | 0
1664 | Tamluk Division | Digha Sub-Division | Soil investigation, Construction of 50 cum OHR (tourch type with pile foundation) under JJM with allied work for Bhatsalia PWSS within Egra-I Block including Supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000417/2023-2024 | 1086/TD | 08/06/2023 | 180 | GOUTAM CONSTRUCTION | 38.57 | 0 | 30
1665 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC (337 nos) under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000445/2023-2024 | 1453/TD | 13/07/2023 | 643 | R CONSTRUCTION | 78.02 | 0 | 85
1666 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Boundary Wall under JJM with allied work for BHATSALIA PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000446/2023-2024 | 1454/TD | 13/07/2023 | 45 | MAHAPRABHU ENTERPRISE | 14.4 | 0 | 0
1667 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000351/2022-2023 | 3014/TD | 27/02/2023 | 0 | Resource Division | 9.41 | 0 | 0
1668 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (105 nos) under JJM with allied work for CHIRULIA PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000299/2023-2024 | 589/TD | 17/05/2023 | 743 | SK MAIDUL ISLAM | 53.24 | 0 | 30
1669 | Tamluk Division | Contai Sub-Division | Pump House ,Rising main, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (250 nos) under JJM with allied work of DESHHDUTTABARH PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000440/2023-2024 | 1424/TD | 12/07/2023 | 570 | JASODA ENTERPRISE | 64.31 | 0 | 70
1670 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000090/2024-2025 | 2956/TD | 12/09/2024 | 0 | Resource Division | 1.54 | 0 | 0
1671 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000348/2022-2023 | 3012/TD | 27/02/2023 | 0 | Resource Division | 19.16 | 0 | 0
1672 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block- Egra-II in the District of Purba Medinipur.(Phase-II) |  | Junior Engineer | ORD/000066/2021-2022 | 693/TD | 10/09/2021 | 60 | SATYABRATA BHAUMIK | 137.67 | 137.67 | 100
1673 | Tamluk Division | Digha Sub-Division | Continuation Work Order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Augmentation Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/001160/2023-2024 | 2566/TD | 06/10/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 0 | 100
1674 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division |  | Junior Engineer | RTOR000006/2021-2022 | 1235/TD | 09/12/2021 | 0 | Resource Division | 6.01 | 0 | 0
1675 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Jalpai Part-II W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Tajpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at Boosting Tubewell Site of Manikpur W/S Scheme within Nandigram-I Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000017/2023-2024 | 115/TD | 06/04/2023 | 40 | B. K. ENTERPRISE | 63.13 | 20.56 | 100
1676 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000001/2023-2024 | 353/TD | 26/04/2023 | 0 | Resource Division | 0.63 | 0 | 0
1677 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 0 | 100
1678 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000004/2023-2024 | 355/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
1679 | Tamluk Division | Haldia Electrical Sub-Division | Installation of display Board at 55 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000330/2024-2025 | 3289/TD | 05/10/2024 | 20 | MISHRA ENTERPRISE | 9.16 | 0 | 100
1680 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000292/2022-2023 | 2910/TD | 21/11/2023 | 0 | Resource Division | 10.62 | 0 | 0
1681 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000681/2023-2024 | 2710/TD | 30/10/2023 | 790 | TAPAS SANTRA | 866.03 | 0 | 85
1682 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000147/2023-2024 | 102/TD | 05/01/2024 | 0 | Resource Division | 13.76 | 0 | 0
1683 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000270/2022-2023 | 2698/TD | 06/02/2023 | 0 | Resource Division | 65.99 | 0 | 0
1684 | Tamluk Division | Tamluk Sadar Sub-Division | payment of Wayleave plan & survey charges SER-KGP-2024-WL-104 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00488/2024-2025 | BP-2024-25-190 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0
1685 | Tamluk Division | Tamluk Sadar Sub-Division | payment of Wayleave plan & survey charges SER-KGP-2024-WL-105 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00489/2024-2025 | BP-2024-25-191 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0
1686 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-105) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00692/2024-2025 | BP-2024-25-299 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.27 | 0 | 0
1687 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-104) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00693/2024-2025 | BP-2024-25-300 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.21 | 0 | 0
1688 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Sub-Soil investigation, Construction of OHR - 50 Cum, Laying of Distribution pipe line and FHTC work (477 nos) Including 2 years of Operation & Maintenance under JJM with alied work for ground water based Simulberya Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000352/2023-2024 | 881/TD | 01/06/2023 | 914 | BARH CONSTRUCTION | 177.2 | 0 | 30
1689 | Tamluk Division | Tamluk Sadar Sub-Division | Installation of 1 Nos. Display Board at Simulberya PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase -VIII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001173/2023-2024 | 769/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.21 | 0 | 100
1690 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000193/2023-2024 | 642/W | 20/02/2024 | 0 | Resource Division | 2.94 | 0 | 0
1691 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000302/2022-2023 | 3004/TD | 27/02/2023 | 0 | Resource Division | 5.27 | 0 | 0
1692 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Amtalia PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000028/2020-2021 | 2104/TD | 05/11/2020 | 180 | ARABINDA GHOSH | 96.58 | 40.55 | 100
1693 | Tamluk Division |  | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000748/2022-2023 | 1109 / CSD | 23/12/2022 | 30 | MRINAL KANTI PRADHAN | 2.85 | 0 | 90
1694 | Tamluk Division |  | Instalation of display Board at different work site of Amtalia PWSS (Retrofitting) in Deshpran Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/001189/2023-2024 | 2337/CSD | 29/12/2023 | 7 | AMIT PAYRA | 0.21 | 0 | 100
1695 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Amtalia W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000591/2020-2021 | 635/W | 13/01/2021 | 0 | ARABINDA GHOSH | 54.93 | 0 | 0
1696 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II Of BARTANA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004874714/QUOT/03/296 DT. 03-09-2024 Application NO- 2004874714 Application type-New connection Consumer Id- 204386343 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01002/2024-2025 | BP-2024-25-631 | 26/11/2024 | 0 | WBSEDCL | 14.38 | 0 | 0
1697 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barttana PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000162/2024-2025 | 2074/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1698 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000134/2022-2023 | 2418/TD | 16/01/2023 | 0 | Resource Division | 43.87 | 0 | 0
1699 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Puronda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000184/2024-2025 | 2194/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1700 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000130/2022-2023 | 2414/TD | 16/01/2023 | 0 | Resource Division | 25.18 | 0 | 0
1701 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3076 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Barttan PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000226/2023-2024 | 452/TD | 04/05/2023 | 876 | TARUN KOLEY | 782.24 | 152.65 | 45
1702 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000121/2023-2024 | 95/TD | 05/01/2024 | 0 | Resource Division | 18.95 | 0 | 0
1703 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000244/2022-2023 | 2724/TD | 06/02/2023 | 0 | Resource Division | 35.45 | 0 | 0
1704 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Sofiabad PWSS Block-Contai-II (Deshpran) in the District of Purba Medinipur. |  |  | ORD/000224/2020-2021 | 2792/TD | 01/02/2021 | 60 | RELIABLE CONSTRUCTIONS | 70.61 | 34.76 | 100
1705 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Sofiabad W/S Scheme within Deshapran Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001243/2020-2021 | 993/W | 26/03/2021 | 0 | RELIABLE CONSTRUCTIONS | 35.85 | 0 | 0
1706 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Chirulia-Chatla PWSS Block Egra-I in the District of Purba Medinipur. |  |  | ORD/000191/2020-2021 | 2770/TD | 28/01/2021 | 60 | FIROZ KHAN | 96.97 | 0 | 100
1707 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000077/2021-2022 | BP-2021-22-40 | 23/07/2021 | 0 | FIROZ KHAN | 3.74 | 0 | 0
1708 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000261/2021-2022 | BP-2021-22-80 | 17/09/2021 | 0 | FIROZ KHAN | 15.36 | 0 | 0
1709 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000393/2021-2022 | 229/W | 07/09/2021 | 0 | FIROZ KHAN | 35.28 | 0 | 0
1710 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chirulia - Chatla W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001229/2020-2021 | 970/W | 23/03/2021 | 0 | FIROZ KHAN | 44.72 | 0 | 0
1711 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Dariapur PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000032/2020-2021 | 2108/TD | 05/11/2020 | 180 | RAJ KUMAR SINGHA | 79.23 | 0 | 100
1712 | Tamluk Division |  | Land Development at Head Work Site of Dariapur PWSS within Desopran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. |  |  | ORD/000643/2023-2024 | 1584/CSD | 16/08/2023 | 15 | JASODA ENTERPRISE | 0.53 | 0 | 100
1713 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Dariapur W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000599/2020-2021 | 636/W | 13/01/2021 | 0 | RAJ KUMAR SINGHA | 76.24 | 0 | 0
1714 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Aladarput PWSS Block Contai-II in the District of Purba Medinipur. |  |  | ORD/000029/2020-2021 | 2105/TD | 05/11/2020 | 180 | TARUN KOLEY | 96.5 | 188.57 | 100
1715 | Tamluk Division |  | Providing FHTC with allied works of Aladarput and its adjoining mouzas water supply scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000748/2022-2023 | 1109 / CSD | 23/12/2022 | 30 | MRINAL KANTI PRADHAN | 2.85 | 0 | 90
1716 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Uttar Khasda PWSS Block Contai-I in the District of Purba Medinipur. |  |  | ORD/000027/2020-2021 | 2103/TD | 05/11/2020 | 180 | SRIMANTA KUMAR MAITY | 96.46 | 0 | 100
1717 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Uttar Khasda W/S Scheme within Contai - I Block under Tamluk Division, PHE Dte. |  |  | VCH/000609/2020-2021 | 649/W | 25/01/2021 | 0 | SRIMANTA KUMAR MAITY | 87.27 | 0 | 0
1718 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -IXA Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000121/2020-2021 | 2630/TD | 05/01/2021 | 60 | RAJ KUMAR SINGHA | 96.85 | 193.4 | 100
1719 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate FHTC under JJM in Baharchandberya PWSS Block -Contai-II (Deshpran) in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000206/2020-2021 | 2802/TD | 04/02/2021 | 45 | DIPAK KUMAR BAKLY | 111.16 | 20.05 | 70
1720 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Baharchandberya W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land) | Assistant Engineer | Junior Engineer | ORD/000314/2023-2024 | 484/TD | 10/05/2023 | 60 | END POINT STRUCTURAL DEPARTMENT | 3.58 | 0 | 0
1721 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC under JJM Baharchand Berya W/S Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | VCH/001141/2020-2021 | 1119/W | 30/03/2021 | 0 | DIPAK KUMAR BAKLY | 23.16 | 0 | 0
1722 | Tamluk Division |  | Retrofitting to accomodate FHTC (400 nos.) under JJM in Argoal PWSS Block - Potashpur-II under Contai Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase - II) |  |  | ORD/000004/2021-2022 | 682/TD | 10/09/2021 | 20 | DAS ENTERPRISE | 44.39 | 35.17 | 100
1723 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanaidighi PWSS Block- Contai-III in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000021/2021-2022 | 82/TD | 11/05/2021 | 30 | DAS ENTERPRISE | 96.02 | 59.46 | 100
1724 | Tamluk Division |  | Repair and Renovation of Pump House & R.C.C. Elevated Reservoir of capacity 350 cum with Sanitary and water supply arrangement and others allied works for Head works & 2nd Tube well site and Boundary Wall at 2nd TW Site at Kanaidighi Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. |  |  | ORD/000339/2024-2025 | 3337/TD | 22/10/2024 | 40 | PARTHA CONSTRUCTION | 10.87 | 0 | 0
1725 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanaidighi PWSS Block Contai - III in the district of Purba Medinipur under Tamluk Division, PHE Dte.(Phase-II) |  |  | VCH/000378/2021-2022 | BP-2021-22-131 | 18/10/2021 | 0 | DAS ENTERPRISE | 27.23 | 0 | 0
1726 | Tamluk Division |  | Laying left out pipe line and Retrofitting to accommodate FHTC (1600 Nos.) under JJM in Surface Water Based Water Supply Scheme for Zone-X (Balance work) Block- Kolaghat in the District of Purba Medinipur under Tamluk Sub Division of Tamluk Division,PHE Dte (Phase-III) . |  |  | ORD/000101/2021-2022 | 1066/TD | 08/11/2021 | 30 | JAYANTA KUMAR MONDAL | 84.04 | 84.01 | 100
1727 | Tamluk Division | Contai Sub-Division | Dismantling of existing OHR (Capacity 55000 Gallons) at Head work Site of Murisai Water Supply Scheme including carriage of old materials to store under Contai Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000067/2021-2022 | 453/TD | 06/08/2021 | 30 | M/S B. N. ENTERPRISES | 7.62 | 6.4 | 100
1728 | Tamluk Division | Contai Sub-Division | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000083/2022-2023 | 436-A/TD | 30/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 6.67 | 6.67 | 100
1729 | Tamluk Division | Contai Sub-Division | Supply and Delivery of 80 mm & 125 mm Sluice Valve for Murisai piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000093/2022-2023 | 450/TD | 31/05/2022 | 20 | RAMASISH ENTERPRISE | 0.31 | 0.31 | 100
1730 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000102/2022-2023 | 478/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 13.41 | 0 | 0
1731 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube Well (Head Work) of Mouza- Barasubarnanagar, JL No.- 502, Plot No.-297 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Ramnagar-II Block of Kanpur Water Supply Scheme under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for 2nd Tube Well of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000108/2022-2023 | 1050/TD | 18/08/2022 | 1017 | AQUATECH ENGINEERS | 45.52 | 0 | 98
1732 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Murisai PWSS at Contai-III Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000152/2024-2025 | 2063/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1733 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main under JJM with allied work for Augmentation of Murisai Water Supply Scheme in Contai III Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000269/2024-2025 | 2898/TD | 10/09/2024 | 319 | MRINAL KANTI PRADHAN | 53.73 | 0 | 40
1734 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Murisai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000317/2021-2022 | 1610/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.67 | 100
1735 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd Tube Well site for Augmentation of Murisai W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000347/2022-2023 | 1283/TD | 12/09/2022 | 827 | MRINAL KANTI PRADHAN | 3.82 | 0 | 100
1736 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 620 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000350/2021-2022 | 1790/TD | 08/02/2022 | 30 | MAITY CONSTRUCTION | 89.06 | 82.85 | 100
1737 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 570 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000351/2021-2022 | 1791/TD | 08/02/2022 | 30 | SNEHESH SEN | 86.32 | 64.26 | 100
1738 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 419 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000352/2021-2022 | 1792/TD | 08/02/2022 | 30 | LOKENATH ENTERPRISES | 64.86 | 61.94 | 100
1739 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 210 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000353/2021-2022 | 1793/TD | 08/02/2022 | 25 | MRINAL KANTI PRADHAN | 35.66 | 34.09 | 100
1740 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 260 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000354/2021-2022 | 1794/TD | 08/02/2022 | 25 | AHINDRA BARIK | 30.12 | 19.73 | 70
1741 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000355/2021-2022 | 1795/TD | 08/02/2022 | 25 | ABHIJIT BERA | 25.4 | 24.03 | 100
1742 | Tamluk Division | Contai Sub-Division | Canal crossing of Distribution pipe line for Augmentation of Murisai & its adjoining mouzas W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (N.P.-410-415 & N.P.-181-190) (Length = 2nos x15.00 Mtr.= 30.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000355/2022-2023 | 1282/TD | 12/09/2022 | 21 | AHINDRA BARIK | 3.63 | 0 | 0
1743 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 180 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000356/2021-2022 | 1796/TD | 08/02/2022 | 1335 | JASODA ENTERPRISE | 25.5 | 24.33 | 100
1744 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 155 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000357/2021-2022 | 1797/TD | 08/02/2022 | 1177 | PARIA ENTERPRISE | 22.19 | 21.33 | 100
1745 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 110 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000358/2021-2022 | 1798/TD | 08/02/2022 | 20 | S.A. ENTERPRISE | 11.89 | 9.44 | 100
1746 | Tamluk Division | Contai Sub-Division | Retrofitting to accommodate of 75 nos FHTC with laying of Distribution Pipe Line and allied Works For Augmentation Of Murisai Water Supply Scheme within contai - III Block under Contai Sub- Division of Tamluk Division, PHE.Dte.in the district of Purba Medinipur. (PART- J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000359/2021-2022 | 1799/TD | 08/02/2022 | 1323 | LAKSHMI NARAYAN ENTERPRISE | 9.86 | 7.96 | 100
1747 | Tamluk Division | Contai Sub-Division | Laying Distribution main for Augmentation of Murisai Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. N.P. 4-8, & 8-12 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000393/2022-2023 | 1426/TD | 26/09/2022 | 15 | CHANDA AGENCIES | 4.18 | 4.18 | 100
1748 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Murisai-3 nos., Junbani-1 no., Bhagwanpur Zone-I- 1 no.,Bhagwanpur Zone-II- 1 no., Contai Saline Area Zone-III (Phase-A)- 1no. & Contai Saline Area Zone-III (Phase-B)- 1no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000511/2022-2023 | 811 / CSD | 21/10/2022 | 15 | MRINAL KANTI PRADHAN | 0.93 | 0 | 100
1749 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000562/2023-2024 | 2048/TD | 25/08/2023 | 40 | KALPANA BUILDERS | 34.03 | 0 | 40
1750 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Baharchandberia Retrofitting PWSS in Contai - II (Deshopran) Block, Kanaidighi, Paschim Kamarda, Murisai Retrofitting PWSS in Contai - III Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001186/2023-2024 | 2334/CSD | 29/12/2023 | 15 | BISWA NIRMAN ENTERPRISE. | 0.83 | 0 | 100
1751 | Tamluk Division | Contai Sub-Division | Strengthening of existing approach road for Replacement of 2nd Tube Well at Murisai Water Supply Scheme within Contai-III Block within Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001280/2024-2025 | 2468/CSD | 25/10/2024 | 7 | GANAPATI CONSTRUCTION | 0.97 | 0 | 100
1752 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000029/2021-2022 | 1345/TD | 23/12/2021 | 0 | Resource Division | 20.82 | 0 | 0
1753 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000061/2021-2022 | 1835/TD | 15/02/2022 | 0 | Resource Division | 14.73 | 0 | 0
1754 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges(SER-KGP-2024-WL-46) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00134/2024-2025 | BP-2024-25-77 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.35 | 0 | 0
1755 | Tamluk Division | Contai Sub-Division | Draning out of washout & over flow water from 500 Cum Capacity Over Head Reservoir to the near by natural ditch of Augmentation of Kumirda Water Supply Scheme and its adjoining mouzas in Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000033/2025-2026 | 1162/TD | 22/04/2025 | 60 | SAURAV HAZRA | 4.34 | 0 | 0
1756 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line And FHTC ( Functional Household tap connection ) with allied works including all for Augmentation of Kumirda Water Supply Scheme within Contai- III under Contai sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000117/2022-2023 | 601/TD | 20/06/2022 | 1200 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 799.74 | 517.9 | 70
1757 | Tamluk Division | Contai Sub-Division | Jack Pushing of Railway Track from station henria and nachinda of augmentation of Kumirda Piped Water Supply scheme of 600 mm dia ms casing pipe and 150 mm dia ms carrier pipe in between mast no 44/15 to mast no 44/16 with in Contai Sub Division under Tamluk Division PHE Dte. (total length =53 m) (nodal point 508 to nodal point 525) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000120/2024-2025 | 1916/TD | 07/06/2024 | 179 | ROY CONSTRUCTION | 61.73 | 0 | 100
1758 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between HENRIA-NACHINDA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Kumirda Piped Water Supply Scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000150/2024-2025 | 1736/CSD | 20/06/2024 | 20 | M/S. NEW DINDA ENTERPRISE | 1.16 | 0 | 100
1759 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for Additional Tube well site J.L no. -155, Plot no. -1245, Mouza -Panichiary under Augmentation of Kumirda W/S Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000311/2023-2024 | 490/TD | 10/05/2023 | 60 | PARIA ENTERPRISE | 4.09 | 0 | 100
1760 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kumirda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000320/2021-2022 | 1613/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.66 | 5.64 | 100
1761 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kumirda Water Supply Scheme in Contai III Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000565/2022-2023 | 2262/TD | 30/12/2022 | 20 | CASTING CORPORATION OF INDIA | 8.5 | 8.5 | 100
1762 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir ( OHR) & 1st.Tube Well , 2nd , 3rd , Additional Tube Well Site, Mouza -kumirda under Augmentation of Kumirda Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 230.00 mtr. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000732/2022-2023 | 2562/TD | 24/01/2023 | 60 | M/S. PRADIP PRADHAN | 32.65 | 0 | 90
1763 | Tamluk Division | Contai Sub-Division | Repairing and Renovation Of Pump House No. I , II & III under Augmentation of Kumirda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000960/2022-2023 | 422/CSD | 17/03/2023 | 30 | PARIA ENTERPRISE | 2.89 | 0 | 0
1764 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000011/2022-2023 | 98/TD | 11/04/2022 | 0 | Resource Division | 40.13 | 0 | 0
1765 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000081/2022-2023 | 1274/TD | 12/09/2022 | 0 | Resource Division | 33.04 | 0 | 0
1766 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with Construction of R.C.C. Elevated Reservoir of Capacity 600 Cum and Staging Height of 20.0 Mtr. as per departmental drawing with allied works including supply of all labour & materials for Augmentation of Mukutshila Zone-I Water Supply Scheme within Khejuri-I Dev. Block under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000411/2022-2023 | 1575/TD | 14/10/2022 | 868 | GEE BEE NIRMAN CO PVT LTD. | 796.53 | 240.57 | 50
1767 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mukutshila Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000447/2021-2022 | 1678/TD | 27/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.72 | 4.71 | 100
1768 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000064/2022-2023 | 1196/TD | 06/09/2022 | 0 | Resource Division | 29.7 | 0 | 0
1769 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 0 | 100
1770 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money of Pump House No. - 4 of Khejurberia PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00002/2023-2024 | BP-2023-24-12 | 17/04/2023 | 0 | WBSEDCL | 3.87 | 0 | 0
1771 | Tamluk Division | Haldia Electrical Sub-Division | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00466/2023-2024 | BP-2023-24-238 | 09/08/2023 | 0 | CHIEF EXECUTIVE OFFICER, HDA | 5.94 | 0 | 0
1772 | Tamluk Division | Haldia Electrical Sub-Division | Payment to WBSEDCL for Quotation Money for Khejurberia PWSS under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00610/2022-2023 | BP-2022-23-818 | 24/03/2023 | 0 | WBSEDCL | 2.61 | 0 | 0
1773 | Tamluk Division | Haldia Electrical Sub-Division | Payment to Haldia Development Authority for underground LT power cable restoration work of LED Street lighting system (damaged due to laying of underground pipe line by PHE Deptt.) at Nandakumar Bazar area under Nandakumar Block. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00892/2024-2025 | BP-2024-25-454 | 24/09/2024 | 0 | CHIEF EXECUTIVE OFFICER, HDA | 1.31 | 0 | 0
1774 | Tamluk Division | Haldia Electrical Sub-Division | Amount payment to PWD Road for damaged of carriage way and road flank caused due to laying of water pipe line of Khejurberia PWSS | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01192/2023-2024 | BP-2023-24-565 | 07/11/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 0.37 | 0 | 0
1775 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejurberia Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000164/2021-2022 | 1168/TD | 01/12/2021 | 7 | RADIANT | 8.76 | 8.65 | 100
1776 | Tamluk Division | Haldia Electrical Sub-Division | Left out pipe line of Providing Functional Household Tap Connection of Khejurberia water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000308/2023-2024 | 622/TD | 17/05/2023 | 30 | TAPAS SANTRA | 77.24 | 77.23 | 100
1777 | Tamluk Division | Haldia Electrical Sub-Division | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000328/2024-2025 | 3268/TD | 04/10/2024 | 90 | MISHRA ENTERPRISE | 44.78 | 0 | 100
1778 | Tamluk Division | Haldia Electrical Sub-Division | Laying of Distribution pipe line to accommodate FHTC (8284 nos) with new construction of R.C.C. Elevated Reservoir of capacity 1000cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000335/2022-2023 | 1279/TD | 12/09/2022 | 1146 | TAPAS SANTRA | 956.75 | 768.82 | 90
1779 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Khejurberia Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000389/2022-2023 | 1428/TD | 26/09/2022 | 27 | PRANTIK DRILLING AGENCY | 49.66 | 29.84 | 80
1780 | Tamluk Division | Haldia Electrical Sub-Division | Restoration work at Panskura Durgachak road from Ch. 38.400 km to Ch. 38.404 Km (length-4.40 m) after laying pipe line by PHE. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000712/2023-2024 | 1280/TSD | 15/09/2023 | 20 | MIHIR SAMANTA | 2.99 | 0 | 100
1781 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 2nd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000724/2022-2023 | 2554/TD | 24/01/2023 | 60 | RAI CONSTRUCTION | 2.8 | 0 | 100
1782 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well site of Khejurberia Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000725/2022-2023 | 2555/TD | 24/01/2023 | 60 | PULAK KUMAR SAMANTA | 2.79 | 2.08 | 0
1783 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Khejurberia Water Supply Scheme under Tamluk-Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000726/2022-2023 | 2556/TD | 24/01/2023 | 60 | PULAK KUMAR SAMANTA | 5.09 | 5.09 | 0
1784 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well sites of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000735/2022-2023 | 2553/TD | 24/01/2023 | 60 | ANIRBAN MONDAL | 4.79 | 4.19 | 100
1785 | Tamluk Division | Haldia Electrical Sub-Division | Water supply & sanitary arrangement for Switch Room cum chlorine Room (pump House no-II) at Khejurberia PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000770/2023-2024 | 1688/TSD | 15/12/2023 | 24 | TECHNO ENTERPRISE. | 0.96 | 0 | 100
1786 | Tamluk Division | Haldia Electrical Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall & fencing work over boundary work with allied work for Khejurberia PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000850/2022-2023 | 3204/TD | 14/03/2023 | 630 | TAPAS SANTRA | 29.62 | 0 | 30
1787 | Tamluk Division | Haldia Electrical Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-41 of Khejurberia Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001181/2023-2024 | 740/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.48 | 0 | 0
1788 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000044/2022-2023 | 1015/TD | 08/08/2022 | 0 | Resource Division | 69.9 | 0 | 0
1789 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000070/2022-2023 | 1256/TD | 12/09/2022 | 0 | Resource Division | 50.95 | 0 | 0
1790 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
1791 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 2900/TD | 21/11/2023 | 0 | Resource Division | 5.49 | 0 | 0
1792 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
1793 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000082/2023-2024 | 2895/TD | 21/11/2023 | 0 | Resource Division | 1.9 | 0 | 0
1794 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
1795 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 2899/TD | 21/11/2023 | 0 | Resource Division | 12.28 | 0 | 0
1796 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Retaining wall cum Gurad Wall at Head work site under Dakshin Anukha and its Adjoning mouzas PWSS under Moyna Block Development Block under Tamluk Sub Division in Tamluk Division, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000139/2024-2025 | 1928/TD | 07/06/2024 | 30 | M J A ENTERPRISE | 3.33 | 0 | 100
1797 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000183/2023-2024 | 373/TD | 27/04/2023 | 20 | ACHINTA KUMAR HALDER | 9.86 | 0 | 71
1798 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000184/2023-2024 | 374/TD | 27/04/2023 | 20 | BAGLAMUKHI SECURITY SERVICE | 10 | 0 | 56
1799 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000185/2023-2024 | 375/TD | 27/04/2023 | 20 | MRITYUNJOY PARIA | 9.97 | 0 | 60
1800 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Boundary wall at 1st. Tube well site & Accommodate FHTC (385 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000250/2023-2024 | 514/TD | 11/05/2023 | 1078 | MAA KALI CONSTRUCTION | 77.96 | 0 | 3
1801 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Construction of Boundary Wall at 2nd. Tube well site , & Accommodate FHTC (500 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2023-2024 | 515/TD | 11/05/2023 | 60 | SHAKEEL KHAN | 89.3 | 0 | 31
1802 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, Switch Room cum Chlorine Room I & II , Accommodate FHTC (550 nos) & Rising Main under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000293/2023-2024 | 582/TD | 16/05/2023 | 896 | NARAYAN MANDAL | 138.66 | 0 | 80
1803 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000528/2023-2024 | 1777/TD | 02/08/2023 | 851 | NEW STAR CONSTRUCTION | 108.73 | 0 | 90
1804 | Tamluk Division | Tamluk Sadar Sub-Division | Development of low land and construction of Link Road by carried earth at H/W Site for Dakshin Anukha PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000698/2023-2024 | 2738/TD | 01/11/2023 | 890 | MAA KALI CONSTRUCTION | 6.92 | 0 | 25
1805 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000702/2023-2024 | 2813/TD | 07/11/2023 | 20 | CHANDA AGENCIES | 9.93 | 0 | 81
1806 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed retaining wall cum guard wall , approach road, earth filling at 2nd tube site under Dakshin Anukha and its adjoining mouzas PWSS under Moyna development block under Tamluk Sub-Division in Tamluk Division ,Dist-Pruba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000719/2023-2024 | 2941/TD | 23/11/2023 | 25 | NARAYAN MANDAL | 8.22 | 0 | 60
1807 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000004/2024-2025 | 1562/TD | 23/04/2024 | 0 | Resource Division | 10.07 | 0 | 0
1808 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000326/2022-2023 | 2990/TD | 27/02/2023 | 0 | Resource Division | 46.28 | 0 | 0
1809 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000127/2023-2024 | 258/TD | 19/04/2023 | 25 | MENAKA ENTERPRISE | 13.21 | 0 | 0
1810 | Tamluk Division | Digha Sub-Division | Soil investigation, 150 cum OHR (Torch type with pile foundation) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000254/2023-2024 | 522/TD | 11/05/2023 | 1056 | SASWATA CONSTRUCTION | 86.46 | 0 | 0
1811 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall , Laying rising main pipe line & Accommodate FHTC (835 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000518/2023-2024 | 1754/TD | 01/08/2023 | 708 | BARH CONSTRUCTION | 211.44 | 0 | 70
1812 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline for distribution pipeline due to revised drawing for Mirjapur PWSS under JJM within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001179/2023-2024 | 723/TD | 28/02/2024 | 718 | ELECTIVA ENTERPRISE | 6.28 | 0 | 0
1813 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000319/2022-2023 | 2973/TD | 27/02/2023 | 0 | Resource Division | 37.6 | 0 | 0
1814 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 600cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Shillaberia Jhanka Zone-I Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000441/2022-2023 | 1653/TD | 02/11/2022 | 1032 | TAPAS SANTRA | 997.19 | 598.73 | 70
1815 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000094/2022-2023 | 1372/TD | 23/09/2022 | 0 | Resource Division | 38.75 | 0 | 0
1816 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000101/2022-2023 | 1658/TD | 03/11/2022 | 0 | Resource Division | 180.08 | 0 | 0
1817 | Tamluk Division | Haldia Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01479/2023-2024 | BP-2023-24-666 | 15/12/2023 | 0 | WBSEDCL | 2.75 | 0 | 0
1818 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000070/2023-2024 | 140/TD | 10/04/2023 | 30 | THREE MAA ENTERPRISE | 69.26 | 51.44 | 75
1819 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000296/2023-2024 | 585/TD | 16/05/2023 | 180 | RAJ KUMAR SINGHA | 112.37 | 0 | 0
1820 | Tamluk Division | Haldia Sub-Division | Canal Crossing Structure for Laying Distribution (Nodal Point - 17 - 18) & Rising Main Pipeline of Madhya Hingly Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000651/2023-2024 | 2609/TD | 11/10/2023 | 30 | SOUVIK GHOSAL | 7.39 | 0 | 100
1821 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000818/2022-2023 | 3108//TD | 02/03/2023 | 969 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 67.57 | 33.89 | 55
1822 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000819/2022-2023 | 3109/TD | 02/03/2023 | 30 | SK SANAMAJ | 59.34 | 0 | 40
1823 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000820/2022-2023 | 3110/TD | 02/03/2023 | 30 | S. N. A. CONSTRUCTION | 58.38 | 0 | 35
1824 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000821/2022-2023 | 3111/TD | 02/03/2023 | 30 | SOUMYA ENTERPRISE | 49.53 | 38.52 | 80
1825 | Tamluk Division | Haldia Sub-Division | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000822/2022-2023 | 3112/TD | 02/02/2023 | 20 | PULAK KUMAR SAMANTA | 31.14 | 19.16 | 62
1826 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000138/2022-2023 | 2423/TD | 16/01/2023 | 0 | Resource Division | 34.51 | 0 | 0
1827 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000155/2023-2024 | 101/TD | 05/01/2024 | 0 | Resource Division | 10.82 | 0 | 0
1828 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000898/2022-2023 | 3348/TD | 22/03/2023 | 638 | M/S SYCHROTECH INDUSTRY | 62.36 | 0 | 100
1829 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Bakcha PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000879/2023-2024 | 201/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1830 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000001/2024-2025 | 1559/TD | 23/04/2024 | 0 | Resource Division | 12.6 | 0 | 0
1831 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000183/2022-2023 | 2430/TD | 16/01/2023 | 0 | Resource Division | 26.3 | 0 | 0
1832 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2305 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of MIRJAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000225/2023-2024 | 456/TD | 04/05/2023 | 900 | TAPAS SANTRA | 719.36 | 310.34 | 66
1833 | Tamluk Division | Contai Sub-Division | Construction boundary wall & Accommodate FHTC (200 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000444/2023-2024 | 1452/TD | 13/07/2023 | 30 | HYDROTECH ASSOCIATES | 13.65 | 0 | 0
1834 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000149/2023-2024 | 87/TD | 05/01/2024 | 0 | Resource Division | 14.2 | 0 | 0
1835 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000193/2022-2023 | 2380/TD | 16/01/2023 | 0 | Resource Division | 19.37 | 0 | 0
1836 | Tamluk Division | Contai Sub-Division | Sinking Tube well,Pump House , Construction of 350 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2138 nos), Including 2 years of operation maintance under JJM with allied work for Balgobindapur- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000613/2023-2024 | 2272/TD | 05/09/2023 | 875 | DAS ENTERPRISE | 693.39 | 0 | 40
1837 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000018/2024-2025 | 1648/TD | 29/04/2024 | 0 | Resource Division | 13.17 | 0 | 0
1838 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000261/2022-2023 | 2702/TD | 06/02/2023 | 0 | Resource Division | 14.6 | 0 | 0
1839 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,OHR of capacity 400 Cum & 150 Cum , Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation, Rigid Pavement & Accommodate FHTC (3874 nos) Including 2 years of Operation & maintenace , under JJM with allied work for Satshatamal PWSS ,Tania Bila PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000499/2023-2024 | 1670/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 1214.41 | 0 | 60
1840 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000021/2023-2024 | 349/TD | 26/04/2023 | 0 | Resource Division | 51.9 | 0 | 0
1841 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000042/2024-2025 | 1664/TD | 29/04/2024 | 0 | Resource Division | 7.61 | 0 | 0
1842 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1750 nos) under JJM with allied work for BIJAYNAGAR PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000480/2023-2024 | 1553/TD | 19/07/2023 | 652 | TARUN KOLEY | 555.04 | 0 | 70
1843 | Tamluk Division | Contai Sub-Division | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Contai-I, Deshpran(Contai-II), Contai-III, Bhagwanpur-I & Bhagwanpur-II ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001290/2023-2024 | 562/CSD | 14/03/2024 | 10 | BISWA NIRMAN ENTERPRISE. | 0.68 | 0 | 100
1844 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000180/2023-2024 | 629/W | 20/02/2024 | 0 | Resource Division | 10.78 | 0 | 0
1845 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000307/2022-2023 | 2964/TD | 27/02/2023 | 0 | Resource Division | 16.56 | 0 | 0
1846 | Tamluk Division | Contai Sub-Division | Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1594 nos) under JJM with allied work of GARBERHA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000074/2023-2024 | 131/TD | 10/04/2023 | 782 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 454.99 | 55.94 | 75
1847 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000133/2023-2024 | 120/TD | 05/01/2024 | 0 | Resource Division | 7.85 | 0 | 0
1848 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000195/2022-2023 | 2382/TD | 16/01/2023 | 0 | Resource Division | 23.95 | 0 | 0
1849 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (5507 Nos) For 4 nos Pipe water supply Scheme including two years Operation & Maintainance work for Ayambar Barya PWSS, Bara Bhagia PWSS, within Patashpur-I Block and Kalyanpur PWSS, Malikpur PWSS within Patashpur-II Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000678/2023-2024 | 2703/TD | 20/10/2023 | 860 | S & P ENTERPRISE | 1928.99 | 0 | 30
1850 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000199/2022-2023 | 2444/TD | 16/01/2023 | 0 | Resource Division | 33.17 | 0 | 0
1851 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1669 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NILKANTHAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000076/2023-2024 | 129/TD | 10/04/2023 | 966 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 486.76 | 0 | 25
1852 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000160/2023-2024 | 127/TD | 05/01/2024 | 0 | Resource Division | 10.28 | 0 | 0
1853 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000247/2022-2023 | 2721/TD | 06/02/2023 | 0 | Resource Division | 19.28 | 0 | 0
1854 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Shipur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000173/2024-2025 | 2085/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1855 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000132/2022-2023 | 2416/TD | 16/01/2023 | 0 | Resource Division | 19.96 | 0 | 0
1856 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Amdai PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000172/2024-2025 | 2084/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
1857 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000158/2022-2023 | 2421/TD | 16/01/2023 | 0 | Resource Division | 16.01 | 0 | 0
1858 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 02 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Paniparul Zone-I W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000169/2023-2024 | 296/TD | 20/04/2023 | 40 | SPG ENTERPRISES | 37.92 | 34.74 | 100
1859 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000323/2021-2022 | 1616/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 6.16 | 6.16 | 100
1860 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000408/2022-2023 | 1448/TD | 27/09/2022 | 1214 | SNEHESH SEN | 170.64 | 99.16 | 0
1861 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000521/2022-2023 | 2093/TD | 13/12/2022 | 1106 | LOKENATH ENTERPRISES | 79.14 | 47.5 | 95
1862 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000524/2022-2023 | 2096/TD | 13/12/2022 | 15 | M/S. PRADIP PRADHAN | 4.18 | 4.18 | 100
1863 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000525/2022-2023 | 2011/TD | 06/12/2022 | 25 | DHANANJOY DAS | 38.53 | 9.09 | 25
1864 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000526/2022-2023 | 2012/TD | 06/12/2022 | 25 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.56 | 3.16 | 0
1865 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Paniparul (Zone-I) Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000527/2022-2023 | 2013/TD | 06/12/2022 | 25 | CHARUBALA ENTERPRISE | 10.76 | 2.41 | 0
1866 | Tamluk Division | Digha Sub-Division | Repairing & renovation of Pump House, construction of boundary wall , Land development, Supply & delivery of different dia D.I. Specials with allied works under JJM for Paniparul (Z-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000601/2023-2024 | 2195/TD | 01/09/2023 | 571 | AJIT KUMAR SOM | 48.26 | 0 | 90
1867 | Tamluk Division | Digha Sub-Division | Site cleaning at Head work site of Paniparul (zone-I ) W/S Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000917/2023-2024 | 859/DSD | 01/12/2023 | 3 | SOM CONSTRUCTION | 0.36 | 0 | 100
1868 | Tamluk Division | Digha Sub-Division | Laying distribution of pipe line, Pump House at 2nd TW site, construction of boundary wall & FHTC -100nos. (Phase-II) with allied works under JJM for Paniparul( Z-I) PWSS within Egra- II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001145/2023-2024 | 565/TD | 15/02/2024 | 40 | AJIT KUMAR SOM | 39.83 | 0 | 100
1869 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000114/2022-2023 | 1667/TD | 03/11/2022 | 0 | Resource Division | 128.58 | 0 | 0
1870 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000281/2022-2023 | 2634/TD | 02/02/2023 | 0 | Resource Division | 24.04 | 0 | 0
1871 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, & Accommodate FHTC (270 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000840/2022-2023 | 3184/TD | 10/03/2023 | 25 | SUBHENDU HAZRA | 48.38 | 23.1 | 50
1872 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC ( 250 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000841/2022-2023 | 3185/TD | 10/03/2023 | 1110 | M/S. NEW DINDA ENTERPRISE | 48.13 | 0 | 50
1873 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (300nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000843/2022-2023 | 3186/TD | 10/03/2023 | 25 | BADAL CHANDRA GOLE | 37.34 | 0 | 48
1874 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000844/2022-2023 | 3187/TD | 10/03/2023 | 15 | SUSANTA KUMAR KAR | 9.8 | 0 | 45
1875 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Basudeb Berya PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001052/2023-2024 | 382/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1876 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of BASUDEVBERIA PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001148/2023-2024 | 568/TD | 15/02/2024 | 264 | PARTHA CONSTRUCTION | 6.83 | 0 | 90
1877 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000120/2022-2023 | 2389/TD | 16/01/2023 | 0 | Resource Division | 33.31 | 0 | 0
1878 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000185/2023-2024 | 634/W | 20/02/2024 | 0 | Resource Division | 6.55 | 0 | 0
1879 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) for OHR site at Nijkasba W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (for East side, North & South Side) | Assistant Engineer | Junior Engineer | ORD/000316/2023-2024 | 487/TD | 10/05/2023 | 45 | BIPLAB BAHNI GUCHHAIT | 4.5 | 0 | 100
1880 | Tamluk Division | Contai Sub-Division | Providing FHTC with allied works of Nijkasba & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000544/2022-2023 | 2163/TD | 19/12/2022 | 25 | HARIPADA PATTANAYAK | 35.25 | 33.89 | 70
1881 | Tamluk Division | Contai Sub-Division | Laying of left out pipe line by HDPE pipes with allied works of distribution system of Nijkasba W/S Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000765/2025-2026 | 2275/CSD | 09/10/2025 | 30 | SAVORIO REALITY LLP | 0.96 | 0 | 0
1882 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000030/2023-2024 | 609/TD | 17/05/2023 | 0 | Resource Division | 4.7 | 0 | 0
1883 | Tamluk Division | Contai Sub-Division | Sinking of 3 (three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube well of 1st Tubewell at Mouza- Baliarpur, JL. No. -358 for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia x 250 mtr. deep tube well by direct rotary rig method of Boosting Tube well of 3rd Tubewell at Mouza- Madhusudhanbar, JL. No. 365, Plot No. 237 - for Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell ( Boosting Tube well) at Mouza -Bhaitghar, JL No. - 415, Plot No. -287, Contai- III Block of Kanaidighi Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000252/2022-2023 | 1051/TD | 18/08/2022 | 40 | AQUATECH ENGINEER | 54.66 | 16.89 | 32
1884 | Tamluk Division | Contai Sub-Division | Laying Rising Main, Construction of Boundary wall at 3rd Tube Well Boosting Site of Damudarpur PWSS in Contai-I within Contai Sub-Division of Tamluk Division,PHE Dte. {Length-44.00 mtr.} (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000486/2023-2024 | 1576/TD | 19/07/2023 | 30 | M/S MONDAL CONSTRUCTION & CO. | 14.04 | 0 | 100
1885 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000019/2023-2024 | 356/TD | 26/04/2023 | 0 | Resource Division | 11.65 | 0 | 0
1886 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Raghusardarbar Jalpai PWSS at Contai-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000882/2023-2024 | 204/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.96 | 0 | 100
1887 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000070/2024-2025 | 2976/TD | 12/09/2024 | 0 | Resource Division | 5.96 | 0 | 0
1888 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000170/2022-2023 | 2394/TD | 16/01/2023 | 0 | Resource Division | 45.39 | 0 | 0
1889 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000225/2022-2023 | 2704/TD | 06/02/2023 | 0 | Resource Division | 22.02 | 0 | 0
1890 | Tamluk Division | Digha Sub-Division | Payment to WBSEDCL for Shifting of 11KV HT maithana feeder for Kalapunja PWSS | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01994/2023-2024 | BP-2023-24-938 | 06/03/2024 | 0 | WBSEDCL | 2.16 | 0 | 0
1891 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000422/2023-2024 | 1416/TD | 12/07/2023 | 746 | BASANTA KUMAR MAITY | 961.33 | 0 | 60
1892 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000150/2023-2024 | 119/TD | 05/01/2024 | 0 | Resource Division | 8.41 | 0 | 0
1893 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000263/2022-2023 | 2690/TD | 06/02/2023 | 0 | Resource Division | 39.36 | 0 | 0
1894 | Tamluk Division | Digha Sub-Division | Relaying the Distribution pipe line (Damaged during the construction of RIDF road from Dakshin Purushottampur Khal Parh to House of Jugal Giri House) of Ranisai PWSS, Ramnagar- I Block under Digha Sub-Division of Tamluk Division , PHE Dte. in the district of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000369/2022-2023 | 1336/TD | 16/09/2022 | 25 | SUKOMAL BERA | 27.06 | 27.05 | 0
1895 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Ranisai & its adjoining mouzas W/S Scheme within Ramnagar - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000378/2023-2024 | 1027/TD | 07/06/2023 | 842 | SWASTIK ENTERPRISE | 62.09 | 0 | 21
1896 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000036/2023-2024 | 2064/TD | 28/08/2023 | 0 | Resource Division | 17.51 | 0 | 0
1897 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000092/2023-2024 | 2995/TD | 29/11/2023 | 0 | Resource Division | 2.24 | 0 | 0
1898 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at PATNA PWSS at Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000376/2025-2026 | 1375/CSD | 03/06/2025 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
1899 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000429/2023-2024 | 1413/TD | 12/07/2023 | 720 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 82.63 | 60
1900 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Patna, Jahanabad & its adjoining Moujas New PWSS in Khejuri-I Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000567/2024-2025 | 2443/CSD | 22/10/2024 | 7 | M/S. NEW DINDA ENTERPRISE | 0.42 | 0 | 100
1901 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000079/2024-2025 | 2971/TD | 12/09/2024 | 0 | Resource Division | 18.05 | 0 | 0
1902 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000229/2022-2023 | 2710/TD | 06/02/2023 | 0 | Resource Division | 6.86 | 0 | 0
1903 | Tamluk Division | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of BAHADURPUR W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004768458/QUOT/03 DT. 11-06-2024 Application NO- 2004768458 Application type-New connection Consumer Id- 204327319 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00596/2024-2025 | BP-2024-25-294 | 29/07/2024 | 0 | WBSEDCL | 10.84 | 0 | 0
1904 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000390/2023-2024 | 1049/TD | 07/06/2023 | 694 | TARUN KOLEY | 266.16 | 0 | 65
1905 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (370 nos) under JJM with allied work of Bahadurpur PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000447/2023-2024 | 1466/TD | 13/07/2023 | 446 | R CONSTRUCTION | 69.75 | 0 | 60
1906 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works for Left Out Area due to Revised Drawing of BAHADURPUR PWSS within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000709/2023-2024 | 2875/TD | 17/11/2023 | 681 | M/S SREE DURGA ENTERPRISE | 33.75 | 0 | 97
1907 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000177/2023-2024 | 626/W | 20/02/2024 | 0 | Resource Division | 15.22 | 0 | 0
1908 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000298/2022-2023 | 2962/TD | 27/02/2023 | 0 | Resource Division | 65.74 | 0 | 0
1909 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Panchet PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000192/2024-2025 | 2202/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1910 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000053/2024-2025 | 1662/TD | 29/04/2024 | 0 | Resource Division | 11.82 | 0 | 0
1911 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000147/2022-2023 | 2452/TD | 16/01/2023 | 0 | Resource Division | 24.44 | 0 | 0
1912 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000139/2022-2023 | 2439/TD | 16/01/2023 | 0 | Resource Division | 27.79 | 0 | 0
1913 | Tamluk Division | Tamluk Sadar Sub-Division | Estimate for against damage of road flank/hard shoulder due to cutting of hard shoulder and road flank on Bhabanipur-Thekuabazar Road from 5.00 km to 7.00 km for laying of water pipe kline by PHE Department. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00232/2023-2024 | BP-2023-24-117 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 2.76 | 0 | 0
1914 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-57 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01499/2023-2024 | BP-2023-24-661 | 15/12/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.28 | 0 | 0
1915 | Tamluk Division | Tamluk Sadar Sub-Division | Way Leave permission from South Eastern Railway for Jalpai PWSS for Application ID-SER-KGP-2023-WL-59 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01829/2023-2024 | BP-2023-24-823 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 4.98 | 0 | 0
1916 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Jalpai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000018/2022-2023 | 52/TD | 05/04/2022 | 20 | HORIZEN | 5.57 | 5.56 | 100
1917 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 5th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000068/2023-2024 | 137/TD | 10/04/2023 | 40 | GRAND CONSTRUCTION | 5.1 | 0 | 0
1918 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai Sater Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000278/2022-2023 | 1114/TD | 29/08/2022 | 25 | SUDIPTA ROY | 75.72 | 48.16 | 65
1919 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000279/2022-2023 | 1115/TD | 29/08/2022 | 778 | CHANDIMATA CONSTRUCTION | 72.07 | 48.92 | 90
1920 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (350 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000280/2022-2023 | 1116/TD | 29/08/2022 | 25 | SHAKEEL KHAN | 74.47 | 43.52 | 80
1921 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(260 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000281/2022-2023 | 1117/TD | 29/08/2022 | 20 | ADHIKARY CONSTRUCTION | 42.21 | 23.02 | 60
1922 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000283/2022-2023 | 1118/TD | 29/08/2022 | 25 | NARAYAN CHANDRA DAS | 76.58 | 59.71 | 80
1923 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000284/2022-2023 | 1119/TD | 29/08/2022 | 25 | S.D. CONSTRUCTION | 70.82 | 43.92 | 70
1924 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(400 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000285/2022-2023 | 1120/TD | 29/08/2022 | 999 | FARID UDDIN AHMED | 65.7 | 41.04 | 91
1925 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(200 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000286/2022-2023 | 1121/TD | 29/08/2022 | 25 | KRISHNENDU SEKHAR DAS | 78.19 | 64.98 | 85
1926 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC (100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000287/2022-2023 | 1122/TD | 29/08/2022 | 20 | SK SANAMAJ | 56.8 | 48.44 | 100
1927 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-N) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000288/2022-2023 | 1123/TD | 29/08/2022 | 840 | BHOLANATH DEY | 57.72 | 52.02 | 96
1928 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-O) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000289/2022-2023 | 1124/TD | 29/08/2022 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.12 | 49.58 | 100
1929 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-Q) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000290/2022-2023 | 1125/TD | 29/08/2022 | 20 | S. N. A. CONSTRUCTION | 46.55 | 38.25 | 99
1930 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-R) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000291/2022-2023 | 1126/TD | 29/08/2022 | 15 | SAYAN MAITY | 9.94 | 7.85 | 80
1931 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(50 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. (PART-S) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000292/2022-2023 | 1127/TD | 29/08/2022 | 15 | OM UDYOG | 9.85 | 7.78 | 100
1932 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(100 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-P) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000293/2022-2023 | 1128/TD | 29/08/2022 | 20 | AQUATECH ENGINEERS | 45.31 | 32.97 | 85
1933 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(300 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000294/2022-2023 | 1129/TD | 29/08/2022 | 1306 | S.K. MONDAL | 72.41 | 53.12 | 75
1934 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC(330 nos) with allied works for Augmentation of Jalpai water supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000295/2022-2023 | 1130/TD | 29/08/2022 | 25 | RELIABLE CONSTRUCTIONS | 72.71 | 51.83 | 75
1935 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of Distribution pipe line to accommodate FHTC(3600 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Jalpai Water Supply Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000385/2022-2023 | 1386/TD | 23/09/2022 | 180 | M/S. CARE | 454 | 60.3 | 30
1936 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 2nd Tubewell Site of Natshal Lakshya Zone - I W/S Scheme within Mahishadal Block under Haldia Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 5th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 4th Tubewell Site of Jalpai W/S Scheme within Nandakumar Dev. Block under Tamluk Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000543/2023-2024 | 1905/TD | 10/08/2023 | 40 | AQUATECH ENGINEER | 58.34 | 0 | 45
1937 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000664/2022-2023 | 2349/TD | 10/01/2023 | 40 | RAI CONSTRUCTION | 5.06 | 0 | 10
1938 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 4th tube well sites of Jalpai Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000665/2022-2023 | 2350/TD | 10/01/2023 | 40 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 5.06 | 0 | 0
1939 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000091/2022-2023 | 1374/TD | 23/09/2022 | 0 | Resource Division | 48.52 | 0 | 0
1940 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000113/2022-2023 | 1672/TD | 03/11/2022 | 0 | Resource Division | 373.53 | 0 | 0
1941 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000205/2023-2024 | 1104/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
1942 | Tamluk Division | Tamluk Sadar Sub-Division | Soil investigation & Construction of RCC Over Head of capacity 200 cum and staging height 20.00 mtr as per Deptt. Drawing ( Intze type with pile foundation), under JJM with allied work for Nilkanthia_PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division,PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000140/2023-2024 | 281/TD | 20/04/2023 | 180 | HARIPADA PATTANAYAK | 93.35 | 0 | 0
1943 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system pipe line, accommodate FHTC (877 nos),Construction of switch room cum cholorine room , Laying of rising main, Construction of Boundary Wall under JJM with allied work for Nilkanthia PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000392/2023-2024 | 1065/TD | 08/06/2023 | 1012 | SUDIPTA ROY | 123.48 | 0 | 26
1944 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 250 x 150 mm Dia and 230m deep tubewell ( at 2nd tube well site) Drilling by Direct Rotary method with 150 dia. UPVC. Strainer of 30m.length all complete including cost of materials for Nilkunthia Water Supply Scheme under Tamluk Block under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000578/2024-2025 | 456/TD | 04/02/2025 | 20 | PRANTIK DRILLING AGENCY | 12.58 | 0 | 0
1945 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000300/2022-2023 | 3006/TD | 27/02/2023 | 0 | Resource Division | 16.01 | 0 | 0
1946 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mathura PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000190/2024-2025 | 2200/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1947 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000051/2024-2025 | 1659/TD | 29/04/2024 | 0 | Resource Division | 13.37 | 0 | 0
1948 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000154/2022-2023 | 2460/TD | 16/01/2023 | 0 | Resource Division | 41.71 | 0 | 0
1949 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 840 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000256/2023-2024 | 538/TD | 12/05/2023 | 1007 | GIRI CONSTRUCTION | 199.43 | 0 | 90
1950 | Tamluk Division | Digha Sub-Division | Land development of 2nd T/W Site at Kadua & Its Adjoining Mouzas water Supply Scheme within Ramnagar-II BLOCK under Digha Sub-Division of Tamluk Division , PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000307/2024-2025 | 892/DSD | 02/09/2024 | 7 | GIRI CONSTRUCTION | 1.85 | 0 | 0
1951 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 70 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part - E ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000483/2023-2024 | 1533/TD | 18/07/2023 | 20 | HYDROTECH ASSOCIATES | 9.99 | 0 | 60
1952 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 81 Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - D ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000624/2023-2024 | 2363/TD | 12/09/2023 | 463 | KESHOB ENTERPRISE | 19.96 | 0 | 100
1953 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( Intze type with pile foundation ) & Accommodate FHTC ( 900Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000628/2023-2024 | 2436/TD | 19/09/2023 | 1011 | BIDHAN MONDAL | 246.91 | 0 | 45
1954 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (261Nos) under JJM with allied work for Kadua & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000916/2022-2023 | 3553/TD | 29/03/2023 | 808 | MRINAL KANTI PRADHAN | 84.53 | 0 | 100
1955 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000146/2023-2024 | 125/TD | 05/01/2024 | 0 | Resource Division | 13.24 | 0 | 0
1956 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000216/2022-2023 | 2691/TD | 06/02/2023 | 0 | Resource Division | 33.64 | 0 | 0
1957 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line & Accommodate FHTC (7 Nos) under JJM with allied work for Chirulia-Chatla (Zone-II) PWSS within Egra-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000262/2023-2024 | 542/TD | 12/05/2023 | 60 | SUBHENDU HAZRA | 71.29 | 0 | 93
1958 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chirulia Chatla Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- II ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000966/2022-2023 | 1056/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 4.01 | 4.01 | 100
1959 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000143/2022-2023 | 2448/TD | 16/01/2023 | 0 | Resource Division | 26.2 | 0 | 0
1960 | Tamluk Division | Haldia Sub-Division | Land development of ditch and Approach Road with Box Culvert at 3rd T.W. site of Barsundra Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000104/2023-2024 | 214/TD | 17/04/2023 | 30 | BISWANATH BHUNIA | 16.31 | 0 | 0
1961 | Tamluk Division | Haldia Sub-Division | Laying of proposed Rising main line with inter connection ,Supply of DI Specials, at Head Work Site at Barsundara Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000234/2024-2025 | 2698/TD | 22/08/2024 | 25 | ANIRBAN BHOWMIK | 10.21 | 0 | 0
1962 | Tamluk Division | Haldia Sub-Division | Construction new Boundary Wall at Head Work Site of BARSUNDRA Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, P.H.E. Dte. (Length - 225.00 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000235/2024-2025 | 2697/TD | 22/08/2024 | 191 | ANIRBAN BHOWMIK | 19.92 | 0 | 50
1963 | Tamluk Division | Haldia Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-I Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 1st Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 320 mtr. Deep Tube well by direct rotary rig method at 3rd Tube Tube well Site of Barsundra Water Supply Scheme within Haldia Block under Haldia Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000334/2022-2023 | 1249/TD | 12/09/2022 | 40 | SIMPLEX DRILLING COMPANY | 83.68 | 20.27 | 75
1964 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Barsundra Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000437/2021-2022 | 1518/TD | 07/01/2022 | 20 | RADIANT | 4.5 | 4.5 | 100
1965 | Tamluk Division | Haldia Sub-Division | Repairing & Renovation of Pump House No. "1" & Pump House No.- "2" at Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000650/2023-2024 | 2616/TD | 11/10/2023 | 444 | GUCHHAIT ENTERPRISE | 6 | 0 | 80
1966 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Barsundra Water Supply Scheme by providing Laying of Distribution to accommodate FHTC (5920 Nos),construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. with allied works within Haldia Dev.Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000776/2022-2023 | 2860/TD | 17/02/2023 | 865 | TAPAS SANTRA | 900.87 | 475.39 | 73
1967 | Tamluk Division | Haldia Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 of Barsundra Water Supply Scheme within Haldia Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000823/2023-2024 | 3285/TD | 20/12/2023 | 20 | DONA ASSOCIATES | 9.93 | 0 | 30
1968 | Tamluk Division | Haldia Sub-Division | New Construction of boundary wall at 3rd T/W site (50mt) of Barsundra water supply scheme under Haldia Sub-Division PHE Dte.. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000829/2022-2023 | 3168/TD | 10/03/2023 | 749 | M/S SOURAV MAHAPATRA | 6.26 | 0 | 100
1969 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Barsundra PWSS, Betkundu PWSS, Baramrit Beria PWSS, Amritberya PWSS) (Phase-VII) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001172/2023-2024 | 768/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0 | 100
1970 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000067/2023-2024 | 2643/TD | 13/10/2023 | 0 | Resource Division | 36.47 | 0 | 0
1971 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000231/2022-2023 | 2611/TD | 02/02/2023 | 0 | Resource Division | 118.88 | 0 | 0
1972 | Tamluk Division | Contai Sub-Division | Payment of wayleave facility charges (SER-KGP-2024-WL-45) | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00133/2024-2025 | BP-2024-25-76 | 29/04/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.41 | 0 | 0
1973 | Tamluk Division | Contai Sub-Division | Quotation money for shifting of 11 KV OH Henria Feeder at Najir Bazar for Bajukl Zone-III PWSS under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01685/2023-2024 | BP-2023-24-743 | 04/01/2024 | 0 | WBSEDCL | 2.63 | 0 | 0
1974 | Tamluk Division | Contai Sub-Division | Supply of documents for way leave permission of Railway Track Between DESHPRAN-HENRIA Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Bajkul Zone-III Piped Water Supply Scheme in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, P.H.E DTE. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000148/2024-2025 | 1730/CSD | 20/06/2024 | 20 | BIBEKANANDA DAS | 1.16 | 0 | 100
1975 | Tamluk Division | Contai Sub-Division | Pump House, Boundary Wall and others allied works for 3rd Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000198/2024-2025 | 2322/TD | 23/07/2024 | 320 | M/S S M H CONSTRUCTION | 10.68 | 0 | 100
1976 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Bajkul Zone-III Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000240/2024-2025 | 2679/TD | 22/08/2024 | 160 | SWARUPANANDA DAS | 83.59 | 0 | 0
1977 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000318/2022-2023 | 598/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.72 | 4.71 | 100
1978 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 600 cum RCC OHR at Bajkul Zone-III PWSS at Bhagwanpur-I & II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001053/2023-2024 | 383/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1979 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 40 | PRANTIK DRILLING AGENCY | 61.68 | 0 | 90
1980 | Tamluk Division | Contai Sub-Division | Sinking of 300 mm x 200 mm dia x 225 mtr. deep tube well by direct rotary rig method for Replacement of 2nd Tube well of Bajkul Zone-III Water Supply Scheme within Bhagwanpur-I & II Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001157/2023-2024 | 608/TD | 16/02/2024 | 20 | B. K. ENTERPRISE | 17.8 | 0 | 0
1981 | Tamluk Division | Contai Sub-Division | Repair and renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001184/2023-2024 | 724/TD | 28/02/2024 | 40 | PARTHA CONSTRUCTION | 10.65 | 0 | 0
1982 | Tamluk Division | Contai Sub-Division | Repair and renovation and others allied works of Pump House, Boundary Wall for 2nd. Tube well site at mouza- Bajkul,J.L- No -156, under Bajkul - III Water Supply Scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001246/2023-2024 | 1077/TD | 16/03/2024 | 409 | M/S. S. A. CONSTRUCTION | 9.84 | 0 | 100
1983 | Tamluk Division | Contai Sub-Division | Pump House, Boundary Wall and others allied works for 4th Tube well site at moza- Bajkul,J.L- No -156, under Bajkul - III Water Supply scheme ( Augmentation) in Bhagabanpur-I & II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001248/2023-2024 | 1076/TD | 16/03/2024 | 396 | M/S. S. A. CONSTRUCTION | 11.22 | 0 | 90
1984 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000065/2023-2024 | 2641/TD | 13/10/2023 | 0 | Resource Division | 28.85 | 0 | 0
1985 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division.,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000234/2022-2023 | 2612/TD | 02/02/2023 | 0 | Resource Division | 210.83 | 0 | 0
1986 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 0 | 75
1987 | Tamluk Division | Contai Sub-Division | Re- Laying od different dia. UPVC Pipe and Constrution of Boundary wall (as per Departmental Design & Drawing),Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000112/2023-2024 | 242/TD | 19/04/2023 | 45 | SUBRATA KUMAR BERA | 30.48 | 0 | 60
1988 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Augmentation of Barchunfali W/S Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000215/2023-2024 | 479/TD | 10/05/2023 | 60 | SAURAV HAZRA | 3.6 | 0 | 0
1989 | Tamluk Division | Contai Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1(One) no. Boosting Tube Well for Augmentatuion of Barchunfali & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000216/2023-2024 | 478/TD | 10/05/2023 | 30 | SUBHRANGSHU SEKHAR GIRI | 3.38 | 0 | 0
1990 | Tamluk Division | Contai Sub-Division | Laying of different dia UPVC pipe line to accommodate 70 Nos FHTC to make Benipur Mouza, Chuaphali, Ghata, Hugli, Khikina & Subdi mouzas as Swajal Gram of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000523/2022-2023 | 2095/TD | 13/12/2022 | 20 | M/S UNIQUE. | 7.92 | 6.38 | 100
1991 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000011/2023-2024 | 342/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
1992 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line( for FHTC) & Accommodate FHTC (80 Nos) under JJM with allied work for Dakshin Kalyanpur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000423/2024-2025 | 3474/TD | 06/11/2024 | 30 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.7 | 0 | 0
1993 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 50 Cum OHR & Accommodate FHTC ( 236 Nos) under JJM with allied work for DAKSHIN KALYANPUR & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000521/2023-2024 | 1758/TD | 01/08/2023 | 1033 | PREMANANDA ROY BISWAS | 164.16 | 0 | 40
1994 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 50 cum RCC OHR at Dakshin Kalyanpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001049/2023-2024 | 379/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
1995 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000126/2023-2024 | 132/TD | 05/01/2024 | 0 | Resource Division | 1.45 | 0 | 0
1996 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000304/2022-2023 | 3001/TD | 27/02/2023 | 0 | Resource Division | 9.75 | 0 | 0
1997 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 98 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division ,PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000109/2024-2025 | 1903/TD | 07/06/2024 | 25 | SOUMYA ENTERPRISE | 53.79 | 0 | 65
1998 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000330/2023-2024 | 740/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.49 | 3.48 | 100
1999 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 267 Nos) under JJM with allied work for SANKARPUR (Zone-III) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000519/2023-2024 | 1756/TD | 01/08/2023 | 910 | SUSIL KUMAR HAZRA | 193.96 | 0 | 40
2000 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-III PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001044/2023-2024 | 374/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2001 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000045/2023-2024 | 2075/TD | 28/08/2023 | 0 | Resource Division | 14.02 | 0 | 0
2002 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000095/2023-2024 | 2998/TD | 29/11/2023 | 0 | Resource Division | 1.64 | 0 | 0
2003 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC(Balance work) (579 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-IV, Block-Kolaghat in the District of Purba Medinipur.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000021/2022-2023 | 62/TD | 05/04/2022 | 30 | CONCORD ENGINEERING | 91.47 | 65.2 | 100
2004 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (172 nos) under JJM with allied work for Panchrol PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000113/2023-2024 | 243/TD | 19/04/2023 | 808 | KRISHNENDU SEKHAR DAS | 61.6 | 28.15 | 50
2005 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (239 nos) under JJM with allied work for Bheribaranga PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000117/2023-2024 | 247/TD | 19/04/2023 | 808 | KRISHNENDU SEKHAR DAS | 66.11 | 0 | 75
2006 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC (Phase-II) under JJM in DULALPUR PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur (Part-A) | Assistant Engineer | Junior Engineer | ORD/000115/2023-2024 | 245/TD | 19/04/2023 | 30 | AYSAN KHAN | 25.68 | 25.66 | 100
2007 | Tamluk Division | Digha Sub-Division | Schedule for retrofitting to accommodate FHTC under JJM in DULALPUR PWSS within Egra-II Block under DighaSub-Division of Tamluk Division,P HE Dte. in the District of Purba Medinipur (Part-B) | Assistant Engineer | Junior Engineer | ORD/000116/2023-2024 | 246/TD | 19/04/2023 | 560 | AYSAN KHAN | 5.16 | 0 | 100
2008 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000462/2022-2023 | 1861./TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.89 | 100
2009 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (55 nos) under JJM with allied work for Bathuari (Zone-III) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000525/2023-2024 | 1761/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 261.16 | 0 | 80
2010 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000049/2023-2024 | 2072/TD | 28/08/2023 | 0 | Resource Division | 15.35 | 0 | 0
2011 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000100/2023-2024 | 3003/TD | 29/11/2023 | 0 | Resource Division | 0.34 | 0 | 0
2012 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone- IV) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000331/2023-2024 | 741/TD | 25/05/2023 | 20 | ASTER CONSULTANCY | 3.46 | 3.46 | 100
2013 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 294 Nos) under JJM with allied work for SANKARPUR (Zone-IV) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000510/2023-2024 | 1732/TD | 31/07/2023 | 970 | ONKAR ENTERPRISE | 216.84 | 0 | 55
2014 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Z-IV PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001281/2023-2024 | 1053/TD | 15/03/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2015 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000047/2023-2024 | 2070/TD | 28/08/2023 | 0 | Resource Division | 14.46 | 0 | 0
2016 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000096/2023-2024 | 2999/TD | 29/11/2023 | 0 | Resource Division | 1.81 | 0 | 0
2017 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 3 (Three) nos.Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Kotbar W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Saripur W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Paramanandapur W/S Scheme within Moyna Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000020/2023-2024 | 118/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 61.66 | 0 | 100
2018 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000008/2023-2024 | 359/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
2019 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,400 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2897 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GURGRAM PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000501/2023-2024 | 1689/TD | 26/07/2023 | 717 | TARUN KOLEY | 894.96 | 2.06 | 69
2020 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000139/2023-2024 | 121/TD | 05/01/2024 | 0 | Resource Division | 17.85 | 0 | 0
2021 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000192/2022-2023 | 2381/TD | 16/01/2023 | 0 | Resource Division | 75.63 | 0 | 0
2022 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000845/2022-2023 | 00/TD | 10/03/2023 | 180 | SRIMANTA KUMAR MAITY | 0 | 0 | 0
2023 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 480 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000846/2022-2023 | 3189/TD | 10/03/2023 | 997 | SRIMANTA KUMAR MAITY | 67.29 | 0 | 50
2024 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (83 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000847/2022-2023 | 3190/TD | 10/03/2023 | 1117 | KAMAL KUMAR BERA | 19.35 | 0 | 75
2025 | Tamluk Division | Contai Sub-Division | Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (500 nos) under JJM with allied work for URURI- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000853/2023-2024 | 139/TD | 05/01/2024 | 481 | SRIMANTA KUMAR MAITY | 242.35 | 0 | 45
2026 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line by HDPE pipes with allied works of URURI- PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District.(PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001147/2023-2024 | 567/TD | 15/02/2024 | 775 | KAMAL KUMAR BERA | 5.66 | 0 | 80
2027 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Ururi, Garabar, Itaberia & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001168/2023-2024 | 2328/CSD | 29/12/2023 | 10 | KAMAL KUMAR BERA | 0.62 | 0 | 100
2028 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000119/2022-2023 | 2387/TD | 16/01/2023 | 0 | Resource Division | 23.22 | 0 | 0
2029 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000179/2023-2024 | 628/W | 20/02/2024 | 0 | Resource Division | 13.76 | 0 | 0
2030 | Tamluk Division | Contai Sub-Division | Sinking Tube well,Pump House , Construction of 200 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1324 nos), Including 2 years of operation maintance under JJM with allied work for Taladiha PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000403/2023-2024 | 1093/TD | 08/06/2023 | 1056 | SUJATA CONSTRUCTION | 373.7 | 0 | 21
2031 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000258/2022-2023 | 2705/TD | 06/02/2023 | 0 | Resource Division | 51.54 | 0 | 0
2032 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Gopinathpur PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000224/2023-2024 | 457/TD | 04/05/2023 | 822 | TAPAS SANTRA | 588.58 | 240.18 | 85
2033 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000137/2023-2024 | 130/TD | 05/01/2024 | 0 | Resource Division | 11.4 | 0 | 0
2034 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000239/2022-2023 | 2728/TD | 06/02/2023 | 0 | Resource Division | 36.99 | 0 | 0
2035 | Tamluk Division | Contai Sub-Division | Sinking of Big dia Tube Well, Laying distribution System, Construction of Pump House, Construction of Boundary Wall, Soil investigation, R.C.C. Elevated Reservoir of capacity 200cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation), Accommodate FHTC (1656 nos) & Two years Operation & Maintenance with allied works under JJM for Dwarikapur & It's Adjoining Moujas PWSS in Bhagwanpur-I Block including supply of all labour & materials within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000075/2023-2024 | 128/TD | 10/04/2023 | 628 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 407.28 | 0 | 0
2036 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000131/2023-2024 | 85/TD | 05/01/2024 | 0 | Resource Division | 10.2 | 0 | 0
2037 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000194/2022-2023 | 2386/TD | 16/01/2023 | 0 | Resource Division | 13.74 | 0 | 0
2038 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line (Left out), Repair and Renovation Pump House, Boundary Wall , 450 Cum OHR & Accommodate Balance FHTC ( 65 Nos) under JJM with allied work for KANPUR (Zone-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000237/2024-2025 | 2676/TD | 22/08/2024 | 45 | MAITY CONSTRUCTION | 87.84 | 0 | 0
2039 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Accommodate FHTC ( 69 Nos) under JJM with allied work for KANPUR (Z-I) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000611/2023-2024 | 2255/TD | 05/09/2023 | 60 | BASANTA KUMAR MAITY | 85.65 | 0 | 60
2040 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme under Tamluk Division, PHE Dte. ( PART- I ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000967/2022-2023 | 1057/TD | 18/08/2022 | 20 | ASTER CONSULTANCY | 3.6 | 2.95 | 100
2041 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000039/2023-2024 | 2081/TD | 28/08/2023 | 0 | Resource Division | 13.54 | 0 | 0
2042 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000110/2023-2024 | 3013/TD | 29/11/2023 | 0 | Resource Division | 0.43 | 0 | 0
2043 | Tamluk Division | Kharagpur Sub-Division | Supplying, laying of 22 nos zone Distribution System including specials, valves & pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule (dept. supply), saddle piece etc. all complete, Construction of 25 Nos. various capacities of 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR, Construction of Switch room cum Chlorine Room Including Chlorination & Sanitary Arrangement, Boundary Wall, Service Road for 50 M length & Improvement of Land for each site, surface Drain, Campus lighting & other provisional works etc for Panskura Block on EPC turnkey basis in a single package as per detail scope of work / direction of the E-I-C including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Panskura Block, District Paschim & Purba Medinipur under Western Circle, PHE Dte. (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/000183/2024-2025 | 2258/TD | 16/07/2024 | 1826 | M/S ANAND SINGH | 18090.51 | 0 | 5
2044 | Tamluk Division | Kharagpur Sub-Division | Surveying, Designing, Engineering, Supplying, Construction, Erectioning, Testing, Commissioning of Raw Water Intake Jetty Structure (Fixed type) with Pump House connected by RCC carriageway with the river bank, 70 MLD capacity conventional type Water Treatment Plant, Raw Water Rising Mains, Bank protection, Substation Building for Intake and WTP, Clear Water Reservoir, High Lift Pump House, Clear Water Rising Mains, 1000 Cum capacity UGR cum Booster Pumping Station at Pingla block , Chlorine room & Guard room at UGR site with necessary sanitary arrangements including plinth protection work with surface drain, Administrative Building with centralized SCADA system, Bunglow & Staff Quarter including furniture at WTP & other necessary all Civil and Electro-Mechanical works [excluding substation equipments] etc on EPC turnkey basis as per direction of the EIC including 6(six) months Trial Run and Operation & Maintenance for 5(five) years for SURFACE WATER BASED PIPED WATER SUPPLY SCHEME for Pingla, Panskura Block, District Purba & Paschim Medinipur (Phase-I) | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla),JE1 Kharagpur Sub-division | ORD/001219/2023-2024 | 1012/TD | 14/03/2024 | 730 | G. B. CONSTRUCTION | 28900 | 0 | 12
2045 | Tamluk Division | Contai Sub-Division | Pump House, Laying distribution pipe line, Boundary Wall, & Accommodate FHTC (1165 nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000272/2023-2024 | 530/TD | 12/05/2023 | 80 | SWARUPANANDA DAS | 240.51 | 160.38 | 70
2046 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC ( 325nos) under JJM with allied work of KAYEMGIRI PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. (PART - C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000905/2022-2023 | 3460/TD | 27/03/2023 | 633 | GIRI ENTERPRISE | 37.99 | 16.12 | 45
2047 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000178/2023-2024 | 627/W | 20/02/2024 | 0 | Resource Division | 12.66 | 0 | 0
2048 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000306/2022-2023 | 2963/TD | 27/02/2023 | 0 | Resource Division | 35.87 | 0 | 0
2049 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [536 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-E) Jagannath Karbar(213)(Part) |  | Junior Engineer | ORD/000164/2020-2021 | 2714/TD | 21/01/2021 | 30 | PALCON | 25.95 | 0.39 | 70
2050 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-D) Jagannath Karbar(213)(Part) |  | Junior Engineer | ORD/000165/2020-2021 | 2715/TD | 21/01/2021 | 20 | ANUPAM CONSTRUCTION | 9.99 | 0 | 40
2051 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [206 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-C),Bamaniabar(228), Narubhunya Chak(229). |  | Junior Engineer | ORD/000166/2020-2021 | 2716/TD | 21/01/2021 | 20 | DHANANJOY DAS | 9.99 | 0 | 100
2052 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [740 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.( Part-A), Nalbar(227),Dhalgoda (231) part, .Uttar Padma(233), Kashmali(234), .Kumbha Dharbar(235), |  | Junior Engineer | ORD/000167/2020-2021 | 2717/TD | 21/01/2021 | 35 | LOKENATH ENTERPRISES | 35.86 | 0 | 100
2053 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [126 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 2B ]. |  | Junior Engineer | ORD/000271/2020-2021 | 2924/TD | 22/02/2021 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.1 | 0 | 0
2054 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC [181 nos.] under JJM in ASTICHAK PWSS within Egra-II Block under Digha Sub-Diviion of Tamluk Division, Purba Medinipur.(Part-B) Dakshin Choumukh(209, part), Gagana(211, part), Paik Bar(212, part), Dhalgoda (Part, 231) [ PART - 1B ]. |  | Junior Engineer | ORD/000272/2020-2021 | 2925/TD | 22/02/2021 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.77 | 0 | 0
2055 | Tamluk Division | Digha Sub-Division | Laying 150mm. dia. D.I. (K-9) Rising main pipe line in between 1st Tube Well to pump house & O.H.R. to Distribution Main including construction of masonry pillar and Thrust concrete block for Astichak Water supply Scheme under Digha Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur. |  | Junior Engineer | ORD/000370/2022-2023 | 834/TD | 18/07/2022 | 7 | ANUPAM CONSTRUCTION | 3.14 | 0 | 100
2056 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000232/2021-2022 | 160/W | 30/07/2021 | 0 | PALCON | 4.33 | 0 | 0
2057 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000233/2021-2022 | 97/W | 07/07/2021 | 0 | DHANANJOY DAS | 4.68 | 0 | 0
2058 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate for 206 Nos. FHTC connection under JJM in Astichak W/S Scheme within Egra - II Dev. Block Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000290/2021-2022 | 209/W | 18/08/2021 | 0 | DHANANJOY DAS | 5.2 | 0 | 0
2059 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000394/2021-2022 | 233/W | 07/09/2021 | 0 | LOKENATH ENTERPRISES | 25.14 | 0 | 0
2060 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC (206 Nos.) under JJM of Astichak W/S Scheme within Egra-II Block under Tamluk Division, PHE Dte. (Part-D) |  | Junior Engineer | VCH/000539/2021-2022 | 397/W | 25/11/2021 | 0 | ANUPAM CONSTRUCTION | 2.65 | 0 | 0
2061 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 536 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/001234/2020-2021 | 982/W | 25/03/2021 | 0 | PALCON | 10.68 | 0 | 0
2062 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC 740 Nos. connection under JJM Astichak W/S Scheme within Egra - I Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/001238/2020-2021 | 971/W | 25/03/2021 | 0 | LOKENATH ENTERPRISES | 10.64 | 0 | 0
2063 | Tamluk Division |  | Functional Household Tap Connection to the 275 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Damudarpur (357) ii) Hamirpur (545). |  |  | ORD/000098/2020-2021 | 2454/TD | 18/12/2020 | 20 | ABHIJIT BERA | 13.49 | 0 | 100
2064 | Tamluk Division |  | Functional Household Tap Connection to the 237 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Chandanpur (422) ii) Dakshin Rampur ( 539). |  |  | ORD/000099/2020-2021 | 2455/TD | 18/12/2020 | 20 | PARIA ENTERPRISE | 11.6 | 0 | 100
2065 | Tamluk Division |  | Functional Household Tap Connection to the 233 nos. Household of Damudarpur Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. i) Baliapur (358) ii) Jamna Madhusudhanbar (365). |  |  | ORD/000100/2020-2021 | 2456/TD | 18/12/2020 | 20 | BADAL CHANDRA GOLE | 11.46 | 0 | 100
2066 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000386/2021-2022 | 224/W | 01/09/2021 | 0 | ABHIJIT BERA | 1.3 | 0 | 0
2067 | Tamluk Division |  | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/000475/2021-2022 | 325/W | 08/10/2021 | 0 | BADAL CHANDRA GOLE | 0.81 | 0 | 0
2068 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001043/2020-2021 | 728/W | 18/02/2021 | 0 | ABHIJIT BERA | 11.81 | 0 | 0
2069 | Tamluk Division |  | Retrofitting to accomodate for 275 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001048/2020-2021 | 801/W | 24/02/2021 | 0 | PARIA ENTERPRISE | 11.27 | 0 | 0
2070 | Tamluk Division |  | Retrofitting to accomodate for 233 Nos. FHTC connection under JJM in Damudarpur W/S Scheme within Contai - I Dev. Block Block under Tamluk Division, PHE Dte. |  |  | VCH/001214/2020-2021 | 956/W | 19/03/2021 | 0 | BADAL CHANDRA GOLE | 10.24 | 0 | 0
2071 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM within Kanaidighi PWSS Block Contai-III in the District of Purba Medinipur. |  |  | ORD/000036/2020-2021 | 2109/TD | 05/11/2020 | 180 | DAS ENTERPRISE | 96.3 | 26.7 | 100
2072 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. |  |  | VCH/000594/2020-2021 | 640/W | 13/01/2021 | 0 | DAS ENTERPRISE | 52.63 | 0 | 0
2073 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Kanaidighi W/S Scheme within Contai - III Block under Tamluk Division, PHE Dte. |  |  | VCH/001208/2020-2021 | 935/W | 18/03/2021 | 0 | DAS ENTERPRISE | 16.93 | 0 | 0
2074 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone -XIII(Balance Work) Block Panskura-II in the District of Purba Medinipur. |  |  | ORD/000119/2020-2021 | 2632/TD | 05/01/2021 | 60 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 96.92 | 195.77 | 100
2075 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-XI (Balance Work) Block ¿ Panskura-II in the District of Purba Medinipur. |  |  | ORD/000208/2020-2021 | 2820/TD | 05/02/2021 | 70 | TAPAS SANTRA | 196.75 | 6.19 | 100
2076 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  |  | VCH/000295/2021-2022 |  | 09/09/2021 | 0 | TAPAS SANTRA | 134 | 0 | 0
2077 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Surfaces Water Based Water Supply Scheme for Zone - XI (Balance Work) under Tamluk Division, PHE Dte. |  |  | VCH/000313/2021-2022 | BP-2021-22-78 | 17/09/2021 | 0 | TAPAS SANTRA | 134 | 0 | 0
2078 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Zone ¿ XI (Balance Work) Piped Water Supply Scheme |  |  | VCH/001122/2020-2021 | 1081/W | 30/03/2021 | 0 | TAPAS SANTRA | 56.32 | 0 | 0
2079 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Alisuli,J.L. No-42 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. |  |  | ORD/000101/2020-2021 | 2457/TD | 18/12/2020 | 20 | KRISHNENDU SEKHAR DAS | 16.12 | 0.59 | 100
2080 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Bet Kalla,J.L. No-41 and Village-Dakshin Dhalhara,J.L No-39 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. |  |  | ORD/000102/2020-2021 | 2458/TD | 18/12/2020 | 30 | ARABINDA GHOSH | 33.51 | 1.43 | 100
2081 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village-Hariharpur,J.L. No-43 and Village-Uttar Rautori,J.L No-40 under JJM in Dakshin Dhalhara PWSS Block - Nandakumar in the District of Purba Medinipur. |  |  | ORD/000103/2020-2021 | 2459/TD | 18/12/2020 | 30 | ARABINDA GHOSH | 38.54 | 0.88 | 100
2082 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/000595/2020-2021 | 642/W | 13/01/2021 | 0 | ARABINDA GHOSH | 21.06 | 0 | 0
2083 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/000600/2020-2021 | 641/W | 13/01/2021 | 0 | ARABINDA GHOSH | 23.24 | 0 | 0
2084 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/000607/2020-2021 | 647/W | 25/01/2021 | 0 | KRISHNENDU SEKHAR DAS | 12.09 | 0 | 0
2085 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Alisuli under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/001253/2020-2021 | 1032/W | 27/03/2021 | 0 | KRISHNENDU SEKHAR DAS | 3.44 | 0 | 0
2086 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Betkalla under JJM Dakshin Dhalhara W/S Scheme within Nandakumar Block under Tamluk Division, PHE Dte. |  |  | VCH/001269/2020-2021 | 1034/W | 30/03/2021 | 0 | ARABINDA GHOSH | 11.02 | 0 | 0
2087 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Hariharpur under JJM Dakshin Dhalhara W/S Scheme within Conai - II Block under Tamluk Division, PHE Dte. |  |  | VCH/001270/2020-2021 | 1033/W | 30/03/2021 | 0 | ARABINDA GHOSH | 14.42 | 0 | 0
2088 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Uttar Charaikhia PWSS Block -Contai-l in the District of Purba Medinipur. |  |  | ORD/000204/2020-2021 | 2804/TD | 04/02/2021 | 25 | M/S SREE DURGA ENTERPRISE | 45.73 | 0 | 100
2089 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Uttar Charaikhia W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000256/2021-2022 | BP-2021-22-73 | 04/09/2021 | 0 | M/S SREE DURGA ENTERPRISE | 0.69 | 0 | 0
2090 | Tamluk Division |  | Functional Household Tap Connection for Uttar Charaikhia W/S Scheme within Contai - I Block Tamluk Division, PHE Dte. |  |  | VCH/001062/2020-2021 |  | 08/03/2021 | 0 | M/S SREE DURGA ENTERPRISE | 44.55 | 0 | 0
2091 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Uttar Charaikhia W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001262/2020-2021 | 1088/W | 30/03/2021 | 0 | M/S SREE DURGA ENTERPRISE | 44.55 | 0 | 0
2092 | Tamluk Division | Digha Sub-Division | Bill for damage of Road flank / hard shoulder due to cutting of hard shoulder and road flank on Alamgiri Birbara Khosbagola Road from 5.80 Km. to 6.20 Km., 6.40 Km. to 6.50 Km. & 6.80 Km. to 7.00 Km. for laying water pipe line of Kasbagola PWSS. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00990/2024-2025 | BP-2024-25-493 | 01/10/2024 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 1.24 | 0 | 0
2093 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kasbagola Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000191/2021-2022 | 1200/TD | 02/12/2021 | 20 | RADIANT | 3.78 | 3.78 | 100
2094 | Tamluk Division | Digha Sub-Division | Repairing of Pump house, Construction of Boundary Wall, Laying Rising main pipe line & Supply under JJM with allied work for Kasbagola PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000200/2023-2024 | 401/TD | 27/04/2023 | 789 | ANUSKA ENTERPRISE | 26.15 | 0 | 95
2095 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, of 3rd Tube Well site with allied works of Kasbagola & its adjoining mouzas W/S Scheme within Egra -I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000292/2023-2024 | 594/TD | 17/05/2023 | 60 | CHAKRABORTY CONSTRUCTION | 13.42 | 0 | 90
2096 | Tamluk Division | Digha Sub-Division | Augmentation of ground water based Kasbagola Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Egra-I Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000426/2021-2022 | 1910/TD | 23/02/2022 | 180 | KISHORE GHOSH | 287.79 | 81.08 | 70
2097 | Tamluk Division | Digha Sub-Division | Sinking of 300 mm. x 200 mm. dia. x 230 mtr. deep tube well by direct rotary rig method using UPVC pipe and UPVC Deep Well Screen (RDS) at Kasbagola PWSS, Block- EGRA-I under Digha Sub-Division of Tamluk Division Dist- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000575/2021-2022 | 2048/TD | 14/03/2022 | 21 | KISHORE GHOSH | 13.75 | 10.69 | 100
2098 | Tamluk Division | Digha Sub-Division | Supply of CIDF sluice valve for Augmentation of Kasbagola PWSS within Egra-I Block under Digha Sub Division of Tamluk division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000620/2023-2024 | 2334/TD | 08/09/2023 | 10 | KISHORE GHOSH | 3.38 | 0 | 100
2099 | Tamluk Division | Digha Sub-Division | Requirement of additional pipeline to accommodate FHTC under JJM for Augmentation of Kasbagola PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 3191/TD | 11/12/2023 | 25 | KISHORE GHOSH | 31.07 | 0 | 95
2100 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000053/2021-2022 | 1955/TD | 04/03/2022 | 0 | Resource Division | 11.7 | 0 | 0
2101 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000085/2021-2022 | 2189/TD | 21/03/2022 | 0 | Resource Division | 14.39 | 0 | 0
2102 | Tamluk Division |  | Retrofitting to accomodate FHTC (1575 nos.) under JJM in Palduhi PWSS Block - RAMNAGAR-II under Digha Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. (Phase- I) |  |  | ORD/000007/2021-2022 | 685/TD | 10/09/2021 | 45 | BASANTA KUMAR MAITY | 95.95 | 61.88 | 100
2103 | Tamluk Division |  | Retrofitting to accommodate FHTC 1575 Nos. under JJM in Palduhi PWSS Block Ramnagar - II in the district of Purba Medinipur under Tamluk Division, PHE Dte. |  |  | VCH/000382/2021-2022 | BP-2021-22-135 | 18/10/2021 | 0 | BASANTA KUMAR MAITY | 34.05 | 0 | 0
2104 | Tamluk Division |  | Retrofitting to accomodate FHTC (548 nos.) under JJM in Habichak PWSS(Balance Work) Block - Chandipur in the District of Purba Medinipur. (Phase- II) |  |  | ORD/000003/2021-2022 | 681/TD | 10/09/2021 | 50 | S.D. CONSTRUCTION | 24.29 | 0 | 100
2105 | Tamluk Division |  | Retrofitting to accomodate FHTC (548 Nos.) under JJM in Habichak PWSS (Balance Work) Block-Chandipur under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000351/2021-2022 | BP-2021-22-87 | 05/10/2021 | 0 | S.D. CONSTRUCTION | 24 | 0 | 0
2106 | Tamluk Division | Contai Sub-Division | Retrofitting to accomodate FHTC (220 nos.) under JJM IN Damudarpur PWSS under Contai-I Block of Contai Sub-Division under Tamluk Division, PHE Dte. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000009/2021-2022 | 687/TD | 10/09/2021 | 20 | MAA ANANDAMAYEE | 16.62 | 0 | 96
2107 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC under JJM in Chirulia PWSS Block - Egra-II in the District of Purba Medinipur. (PHASE- II) | Assistant Engineer | Junior Engineer | ORD/000132/2021-2022 | 1014/TD | 02/11/2021 | 30 | FIROZ KHAN | 44.75 | 43.55 | 100
2108 | Tamluk Division | Digha Sub-Division | Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000594/2023-2024 | 2209/TD | 01/09/2023 | 60 | MISHRA ENTERPRISE | 9.53 | 3 | 100
2109 | Tamluk Division |  | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless AWC under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Dakshin Badhia AWC, G.P- Badhia, Mouza - Badhia, J.L. No.- 06 |  |  | ORD/000129/2022-2023 | 135/RWS/TSD | 14/06/2022 | 7 | GRAND CONSTRUCTION | 2.98 | 2.59 | 100
2110 | Tamluk Division |  | Installation of 1.0 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at Sourceless School under Ramnagar-I Dev. Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: Ghersai SSK, G.P- Padima-II, Mouza - Ghersai, J.L. No.- 88 |  |  | ORD/000131/2022-2023 | 138/RWS/TSD | 14/06/2022 | 7 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 2.97 | 2.62 | 100
2111 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Benagolisa Tapas Mandal House (19345200609), G.P- Gobindanagar, (ii) Ratulia Jr. Basic School (19345200501), G.P- Gobindanagar, (iii) Paschim Arjunda Pry. (19345200502), G.P- Gobindanagar,, (iv) Paschim Nekra Pry. School (19345200505), G.P- Gobindanagar, (v) Joykrishnapur I.C.J.C.K. (19345200507),G.P- Gobindanagar, (vi) Dharmapore Asharam (19345200508), G.P- Gobindanagar, (vii) Manur Pry. School (19345200611), (viii) Golghat Pry. School (19345200613), G.P- Gobindanagar. |  |  | ORD/000225/2021-2022 | 1356/TD | 24/12/2021 | 45 | MADAN MOHAN MAITY | 22.79 | 22.56 | 100
2112 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Tamluk Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) HOUSE OF SADHAN KUILA,JASADUMBUR (19345281114). G.P- Bishnubarh-I, (ii) MAISALI MAHILA SAMITY HOUSE (19345281118), G.P- Bishnubarh-I, (iii) GHOLECHAK VIJOY PRY. SCH. (19345281119),G.P- Bishnubarh-I, (iv) AMGECHHIA SITALA AWC (19345280915),G.P- Bishnubarh-I, (v) BAHICHARD DAKSHIN PALLI AWC (19345280917),G.P- Bishnubarh-I. |  |  | ORD/000226/2021-2022 | 1357/TD | 24/12/2021 | 35 | BHOLANATH DEY | 14.22 | 14.09 | 100
2113 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Moyna Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Moyna Badurtala (19345140202), G.P- Moyna-II,(ii) Dakshin Moyna Dangisai (19345140215), G.P- Moyna-II, (iii) P D Moyna (19345140216), G.P- Moyna-II, (iv) Radhaballabh Chak (19345140509), G.P- Gokulnagar. |  |  | ORD/000227/2021-2022 | 1358/TD | 24/12/2021 | 30 | JAGANNATH MAKAR | 12.4 | 12.4 | 100
2114 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 270 mt.) along with stand post at different Sourceless AWC under Nandigram-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Amdabad Uttar AWC (19345160504), G.P- Amdabad-I, (ii) Amdabad Purba chara AWC (19345160618), G.P- Amdabad-I, (iii) Amdabad Madhya AWC (19345160502), G.P- Amdabad-I, (iv) Subdi N. State Plan AWC (19345160514), G.P- Amdabad-I, (v) Amdabad 2 N0.AWC (19345160516), G.P- Amdabad-I, (vi) Hanubhuiya Uttar AWC (19345160420),G.P- Birulia, (vii) Sibrampur AWC (19345160422), G.P- Birulia, (viii) Gholpukur Dakshin AWC (19345160409), G.P- Birulia. |  |  | ORD/000228/2021-2022 | 1359/TD | 24/12/2021 | 45 | NARAYAN CHANDRA DAS | 26.82 | 25.2 | 100
2115 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakkhin Amtalia Anathbandhu A.W.C. (19345050907), G.P- Amtalia, (ii) Kasafalia A.W.C. (19345050105), G.P- Amtalia, (iii) Aurai Kacharibari A.W.C. (19345050301), G.P- Aurai, (iv) Chhanberya A.W.C. (19345050121), G.P- Aurai, (v) Uttar Basudebberya Bramhanarayan A.W.C. (19345050307), G.P- Aurai, (vi) Namaldiha Mother Teresa A.W.C. (19345050302), G.P- Aurai, (vii) Uttar Karpura Keshabchandra A.W.C. (19345050315), G.P- Aurai, (viii) Sarsa A.W.C. (19345050610), G.P- Bamunia. |  |  | ORD/000229/2021-2022 | 1360/TD | 24/12/2021 | 45 | PARIA ENTERPRISE | 24.53 | 23.27 | 100
2116 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 250 mt.) along with stand post at different Sourceless AWC under Contai-III Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Khalsiberia AWC (19345060125), (ii) Marishda AWC (19345060524), G.P- Marishda, (iii) Dakhsin Sukunia (19345060310), (iv) Sukunia Uttar (19345060312), (v) Jagudasbar AWC (19345060413). |  |  | ORD/000230/2021-2022 | 1361/TD | 24/12/2021 | 35 | JASODA ENTERPRISE | 16.04 | 14.11 | 100
2117 | Tamluk Division |  | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bakshishpur AWC (19345250519), G.P- Maitana, (ii) Dakshin Tentultala AWC (19345250522), G.P- Maitana, (iii) Dakshin Maitana AWC (19345250525), G.P- Maitana, (iv) Satilapur AWC (19345250604), G.P- Sitalapur, (v) Purba Satilapur AWC (19345250605), G.P- Sitalapur, (vi) Purba Ghole AWC (19345250622), G.P- Sitalapur, (vii) Bararankua Harijan AWC (19345250716), G.P- Balisai. |  |  | ORD/000231/2021-2022 | 1362/TD | 24/12/2021 | 45 | MRINAL KANTI PRADHAN | 20.96 | 19.36 | 100
2118 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 17,Batashpur FP School 15 (19345070115), G.P- Barida, (ii) 10, Barida Banikishor Sangha 11, (19345070111), G.P- Barida, (iii) 11, Khalina ICJCK 17 (19345070117), G.P- Barida, (iv) 12,Khalina Own Awc 13 (19345070113), G.P- Barida, (v) 13, Madhabpur FP School 16 (19345070116), G.P- Barida, (vi) 194,Sekhpara,Jerthan 08 (19345070408), G.P- Jerthan, (vii) 2, Swarrang Narayan Das'House 06 (19345070106), G.P- Barida, (viii) 190,Sannihari Dhananjoy Patra 15 (19345070315). G.P- Chhatri. |  |  | ORD/000232/2021-2022 | 1364/TD | 24/12/2021 | 45 | S.D. CONSTRUCTION | 22.23 | 22.14 | 100
2119 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rasulpur A.W.C. (19345050911), G.P- Basantia, (ii) Tengorerya Ma Ballavi A.W.C. (19345051007), G.P- Basantia, (iii) Kultalia Paschimpara A.W.C. (19345050915), G.P- Basantia, (iv) Dakkhin Deulpota Subhashchandra A.W.C. (19345051009), G.P- Basantia, (v) Gokulnagar A.W.C. ( 19345050916), G.P- Basantia, (vi) Kalikakumari Vivekananda A.W.C. (19345051010), G.P- Basantia, (vii) Purba Mahammadpur Jana Para A.W.C. (19345051005), G.P- Basantia, (viii) Kultalia Purba Para A.W.C. (19345050914), G.P- Basantia. |  |  | ORD/000239/2021-2022 | 1394/TD | 28/12/2021 | 45 | M/S SREE DURGA ENTERPRISE | 24.51 | 24.23 | 100
2120 | Tamluk Division |  | Installation of 07 (Seven) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Kusbani A.W.C. (19345050919), G.P- Basantia, (ii) Baghaghole Vivekananda A.W.C. (19345050620), G.P- Chalti, (iii) Dakkhin Kalikapur A.W.C. (19345050619), G.P- Chalti, (iv) Nanker Gopinathpur A.W.C. ( 19345050804) G.P- Dariapur, (v) Chitanyapur A.W.C. (19345050818), G.P- Dariapur, (vi) Haripur A.W.C. (19345050812), G.P- Dariapur, (vii) Uttar Deulpota Padmabati A.W.C. (19345050202), G.P- Dhobaberya. |  |  | ORD/000240/2021-2022 | 1395/TD | 28/12/2021 | 45 | SUBRATA KUMAR BERA | 21.46 | 21.14 | 100
2121 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Block: (i) Sukrasoni (19345240211), G.P- Haldia-I, (ii) Dikshal (19345240216), G.P- Haldia-I, (iii) Khairanda-3 (19345240218), G.P- Haldia-I, (iv) Bandhmuri (19345240219), G.P- Haldia-I, (v) Gangra-1 (19345240312), G.P-Haldia-II, (vi) Gangra-2 (19345240315), G.P- Haldia-II, (vii) Ranisai-2 (19345240322), G.P- Haldia-II, (viii) Koniora-3 (19345240323), G.P- Haldia-II. |  |  | ORD/000241/2021-2022 | 1396/TD | 28/12/2021 | 45 | PALCON | 24.7 | 21.07 | 100
2122 | Tamluk Division |  | Installation of 03 (Three) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Gopalpur (19345240720), G.P- Talgachari-II, (ii) Nariha-2 (19345240802), G.P- Talgachari-I, (iii) Jamra (19345240819), G.P- Talgachari-II. |  |  | ORD/000242/2021-2022 | 1397/TD | 28/12/2021 | 25 | SAYAN MAITY | 9.31 | 8.34 | 100
2123 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Jinandapur AWC (19345250319), G.P- Badalpur, (ii) Balarampur AWC (19345250323), G.P- Maitana, (iii) Uttar Kalindi AWC (19345250401), G.P- Kalindi, (iv) Kalindi Basti AWC (19345250405), G.P- Kalindi, (v) Purbabarh Manodamoyee AWC (19345250406), G.P- Kalindi, (vi) Teghari ICDS Centre (19345250409), G.P- Kalindi, (vii) Demuria Paikbar AWC (19345250510), G.P- Maitana, (viii) Mandarpur Pry. School(OWN) (19345250516), G.P- Maitana. |  |  | ORD/000243/2021-2022 | 1398/TD | 28/12/2021 | 45 | MAITY CONSTRUCTION | 23.94 | 22.03 | 100
2124 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 39,Rasan Chakbandi FpSchool 23 (19345070323), G.P- Chhatri, (ii) 40,Rasan Own AWC 25 (19345070325), G.P-G.P- Chhatri. |  |  | ORD/000244/2021-2022 | 1400/TD | 28/12/2021 | 20 | GRAND CONSTRUCTION | 5.55 | 5.53 | 100
2125 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Rukminipur ICDS Centre (19345080302), G.P- Deshbandhu, (ii) Eranda Binapani Club (19345080306), G.P- Deshbandhu, (iii) Kirtipur Bhai Bhai Sangha (19345080307), G.P- Deshbandhu, (iv) Rajendrachak Matsya Jibi Yuva Kalyan Sangha (19345080501), G.P- Deshbandhu, (v) Urijalkar Martri Sakti Sangha (19345080310), G.P- Deshbandhu, (vi) Sarisa Jagrata Yuva Sangha (19345080203), G.P- Deshbandhu, (vii) Hurkuchia Sourav Club (19345080503), G.P- Deshbandhu, (viii) Eranda Haripriya Seba Sangha (19345080309), G.P- Deshbandhu. |  |  | ORD/000245/2021-2022 | 1401/TD | 28/12/2021 | 45 | ABHIJIT BERA | 23.38 | 23.29 | 100
2126 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Narubhuiachak ICDS (19345080410), G.P- Bathuary, (ii) Jaganathkarbar Sunrise ICDS ( 193450805414), G.P- Bathuary, (iii) Bhatda Haripur Youth Club (19345080101), G.P- Manjushree, (iv) Bhatda Palli Mongal ICDS (19345080102), G.P- Manjushree. |  |  | ORD/000246/2021-2022 | 1402/TD | 28/12/2021 | 30 | DEBABRATA DAS | 11.69 | 11.63 | 100
2127 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kaijuddin para-06 (19345220406), G.P- Amarshi 7/1, (ii) Amarshi Kasba-08 (19345220408), G.P- Amarshi 7/1, (iii) Amarshi(e)muslimpara-12 (19345220412), G.P- Amarshi 7/1, (iv) Barsankar-01 (19345220501), (v) Sanamginga-03 (19345220503), G.P- Amarshi 7/2, (vi) Bantitaka-06 (19345220506), (vii) Gumraveri-07 (19345220507), G.P- Amarshi 7/2, (viii) Taladiha-2-08 (19345220508), G.P- Amarshi 7/2. |  |  | ORD/000247/2021-2022 | 1403/TD | 28/12/2021 | 45 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.23 | 21 | 100
2128 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Muradpur AWC (19345230101), G.P- Khar, (ii) Manpur AWC (19345230102), G.P- Khar, (iii) Girisha AWC (19345230104), G.P- Khar, (iv) Gangasagar AWC (19345230105), G.P- Khar, (v) Mustafapur Dakshin AWC (19345230107), G.P- Khar, (vi) Bar Mustafapur AWC (19345230108), G.P- Khar, (vii) Panchet Uttar AWC (19345230206), G.P- Panchet-04, (viii) Panchet Daksin AWC (19345230207) |  |  | ORD/000248/2021-2022 | 1404/TD | 28/12/2021 | 45 | GIRI CONSTRUCTION | 25.08 | 24 | 100
2129 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Nimja AWC (19345230213), G.P- Panchet-04, (ii) Bamunda-II AWC (19345230307), G.P- Panchet-04, (iii) Etachana AWC (19345230309), G.P- Panchet-04, (iv) Motirampur AWC (19345230310), G.P- Patashpur-05. |  |  | ORD/000249/2021-2022 | 1405/TD | 28/12/2021 | 30 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.55 | 11.45 | 100
2130 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Uttar Tiraipur AWC (19345010201), G.P- Mahammadpur-II, (ii) Benauda 1 No. ICDS (19345010203), G.P- Mahammadpur-II, (iii) Goalapukur AWC (19345010208), G.P- Mahammadpur-II, (iv) Garbhera South ICDS (19345010214), G.P- Gurgram (v) Purba Gurgram-1 No. ICDS (19345010302), G.P- Gurgram, (vi) Dakshin Gurgram ICDS (19345010304), G.P- Gurgram, (vii) Fatepur ICDS (19345010312), G.P- Gurgram, (viii) Buraburi-2 No.ICDS (19345010313), G.P- Gurgram. |  |  | ORD/000250/2021-2022 | 1406/TD | 28/12/2021 | 45 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.23 | 23.51 | 100
2131 | Tamluk Division |  | Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2024 to 31.12.2024 i.e. 06 (Six) Months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. |  |  | ORD/000251/2024-2025 | 104/RWS/TSD | 28/06/2024 | 184 | HALADHAR SAMANTA | 0.87 | 0 | 50
2132 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Purba Gurgram-2 No. ICDS (19345010314), G.P- Gurgram, (ii) Amratala AWC (19345010213), G.P- Gurgram. |  |  | ORD/000252/2021-2022 | 1407/TD | 28/12/2021 | 20 | BADAL CHANDRA GOLE | 6.06 | 5.99 | 100
2133 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dhelua AWC (19345020309), G.P- Jukhia, (ii) Bani Mandir AWC (19345020312), G.P- Jukhia. |  |  | ORD/000256/2021-2022 | 1363/TD | 24/12/2021 | 20 | DHANANJOY DAS | 6.05 | 5.61 | 100
2134 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 64,Kiya Nonformal School 22 (19345070422), G.P- Jerthan, (ii) 66, Ashada 19 (19345070419), G.P- Jerthan, (iii) 59, Satkhanda FP School 02 (19345070402), G.P- Jerthan, (iv) 38,Chhatri Bhatgeria 06 (19345070306), G.P- Chhatri. |  |  | ORD/000257/2021-2022 | 1365/TD | 24/12/2021 | 30 | M/S. S. A. CONSTRUCTION | 11.1 | 11.07 | 100
2135 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 210 mt.) along with stand post at different Sourceless AWC under Egra-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Shilampur Swamiji Seba Sangha ( 19345080519), G.P- Vivekananda, (ii) Uttar Eranda Tapsili Sangha (19345080315), G.P- Deshbandhu, (iii) Nijdant Tarun Sangha (19345080316), G.P- Bathuary, (iv) Dakshin Chowmukh ICDS ( 19345080507), G.P- Bathuary, (v) Gangadharbar ICDS Center (19345080508), G.P- Bathuary. |  |  | ORD/000258/2021-2022 | 1366/TD | 24/12/2021 | 35 | ANUPAM CONSTRUCTION | 14.59 | 0 | 100
2136 | Tamluk Division |  | Installation of 05 (Five) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Mahapur Pry. School G.P. Gobindanagar. (ii) Bijaharpur Nabarun Sangha ( 19345200604), G.P- Gobindanagar, (iii) Rajnagar Pry. School (19345200605), G.P- Gobindanagar, (iv) Anupganj Pry. School (19345200606), G.P- Gobindanagar, (v) Gobindanagar Pry. School(19345200607), G.P- Gobindanagar. |  |  | ORD/000268/2021-2022 | 1502/TD | 06/01/2022 | 35 | BARH CONSTRUCTION | 14.25 | 13.5 | 100
2137 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Saiadpur (19345240701), G.P- Talgachari-I, (ii) Uttar Bagpura (19345240712), G.P- Talgachari-I, (iii) Bagpura-2 (19345240714), G.P- Talgachari-I, (iv) Ramnagar (19345240718), G.P- Talgachari-I. |  |  | ORD/000269/2021-2022 | 1503/TD | 06/01/2022 | 30 | SWADHIN KUMAR CHAKRABORTY | 12.43 | 11.57 | 100
2138 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250102), G.P- Paldhui, (ii) Kanwa ICDS (19345250105), G.P- Paldhui, (iii) Purba Paldhui AWC (19345250108), G.P- Paldhui, (iv) Uttar Sabitrapur AWC (19345250116), G.P- Paldhui. |  |  | ORD/000270/2021-2022 | 1504/TD | 06/01/2022 | 30 | SUDIP MANNA | 11.98 | 11.05 | 100
2139 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 220 mt.) along with stand post at different Sourceless AWC under Ramnagar-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Dakshin Veribaranga AWC (19345250122), G.P- Paldhui, (ii) Uttar Kanpur Awc (19345250206), G.P- Depal, (iii) Tajpur AWC (19345250307), G.P- Badalpur, (iv) Badalpur Tarun Sangha Awc (19345250313), G.P- Badalpur. |  |  | ORD/000271/2021-2022 | 1505/TD | 06/01/2022 | 30 | TAPAN BERA | 11.98 | 11.5 | 100
2140 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschimbarh-2 No. ICDS (19345010102), G.P- Mahammadpur-I, (ii) Paschimbarh-3 No. ICDS (19345010103), G.P- Mahammadpur-I, (iii) Uttarbarh-1 No ICDS (19345010104), G.P- Mahammadpur-I, (iv) Sekbarh ICDS (19345010105), G.P- Mahammadpur-I, (v) Mahammadpur-2 No. ICDS (19345010107), G.P- Mahammadpur-I, (vi) Sribachhipur-1 No. ICDS (19345010108), G.P- Mahammadpur-I, (vii) Nimakbarh-2 No. ICDS (19345010113),G.P- Mahammadpur-I, (viii) Uttarbarh-3 No. ICDS (19345010114), G.P- Mahammadpur-I. |  |  | ORD/000272/2021-2022 | 1506/TD | 06/01/2022 | 45 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.25 | 23.52 | 100
2141 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Egra-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) 28,Baranihari Ramkrishna Seba Sangha 05 (19345070305), G.P- Chhatri, (ii) 30,Ramkrishnapur AWC 03 (19345070303), G.P- Chhatri, (iii) 31, Sannihari Own AWC 14 (19345070314), G.P- Chhatri, (iv) 133, Arjuni ICJCK 21 (19345070821), G.P- Jumki, (v) 134, Hansaria AWC (19345070725), G.P- Jumki, (vi) 136, Chaulda AWC (19345070727), G.P- Jumki,, (vii) 137, Nischinta AWC 27 (19345070827), G.P- Jumki, (viii) 62, Benachakri Mandalpara 24 (19345070424), G.P- Jerthan. |  |  | ORD/000294/2021-2022 | 1399/TD | 28/12/2021 | 45 | AJIT KUMAR SOM | 22.24 | 22.15 | 100
2142 | Tamluk Division |  | Sinking of 1(One) nos. 100 mm X 50 mm dia. X 220.0 m(av.) depth Indian Mark-II tube well with PVC pipes including cost of all materials and construction of Platform (as per Departtl. approved drawing) at ''Tamralipta Mahavidyalaya'' due to scarcity of drinking water in a newly constructed three- storied building under Tamluk Sub Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. |  |  | ORD/000328/2023-2024 | 626/TD | 17/05/2023 | 15 | GLOBAL TRADE | 2.29 | 2.16 | 100
2143 | Tamluk Division |  | Installation of 02 (Two) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 190 mt.) along with stand post at different Sourceless AWC under Patashpur-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Panchuria-2-12 (19345220512), G.P- Amarshi-7/2, (ii) Taladiha-3-13 (19345220513), G.P- Amarshi-7/2. |  |  | ORD/000388/2021-2022 | 1848/TD | 16/02/2022 | 20 | SK. SAHALAM | 5.55 | 5.19 | 100
2144 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 240 mt.) along with stand post at different Sourceless AWC under Patashpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Kamalpur AWC (19345230311), G.P- Patashpur-05, (ii) Shikhoda AWC (19345230319), G.P- Patashpur-05, (iii) Morirampur Uttar Awc (19345230322), G.P- Patashpur-05, (iv) Tupchibarh- III AWC (19345230327), G.P- G.P- Patashpur-05. |  |  | ORD/000389/2021-2022 | 1849/TD | 16/02/2022 | 30 | ELECTIVA ENTERPRISE | 12.43 | 11.24 | 100
2145 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Bikra Khan Para (19345200216), G.P- Mysora, (ii) Sahalajpur (Chotto Bhim Para) (19345200218), G.P- Mysora, (iii) Mysora Paschim Muslim Para (19345200124), G.P- Mysora, (iv) Gobindanagar Kali Mandir (19345200603), G.P- Gobindanagar. |  |  | ORD/000404/2021-2022 | 1896/TD | 23/02/2022 | 30 | TARUN KHATUA | 11.39 | 11.29 | 100
2146 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Sikarput A.W.C. (19345050705), G.P- Bamunia, (ii) Choudhuribar A.W.C. (19345051011), G.P- Basantia, (iii) Mukundapur Paschim Para A.W.C. (19345051018), G.P- Basantia, (iv) Basantia Mago Mandir A.W.C. (19345051012), G.P- Basantia. |  |  | ORD/000405/2021-2022 | 1897/TD | 23/02/2022 | 30 | FARID UDDIN AHMED | 12.26 | 12.16 | 100
2147 | Tamluk Division |  | Installation of 04 (Four) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 230 mt.) along with stand post at different Sourceless AWC under Contai-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Charaput A.W.C. (19345050612), G.P- Bamunia, (ii) Murabenia Maktab A.W.C. (19345050617), G.P- Bamunia, (iii) Dakshin Kadua A.W.C. (19345050706), G.P- Bamunia (iv) Uttar Kadua Vivekananda A.W.C. (19345050708), G.P- Bamunia. |  |  | ORD/000406/2021-2022 | 1898/TD | 23/02/2022 | 30 | SUBHRANGSHU SEKHAR GIRI | 12.25 | 11.62 | 100
2148 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 200 mt.) along with stand post at different Sourceless AWC under Panskura Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Paschim Bakulda Dashibard AWC (19345200204), G.P- Mysora, (ii) Radhaballavpur P.L.C. (19345200208), G.P- Mysora, (iii) Bikra Pry. School (19345200209), G.P- Mysora, (iv) Rajshar AWC (19345200113), G.P- Mysora, (v) Paschim Shyampur (19345200115), G.P- Mysora, (vi) Purba Mysora Club (19345200117), G.P- Mysora, (vii) Balarampur S.S.K. (19345200211), G.P- Mysora, (viii) Gopal Hazra SSK (19345200213),G.P- Mysora. |  |  | ORD/000454/2021-2022 | 1937/TD | 02/03/2022 | 45 | BIDHAN MONDAL | 22.81 | 21.39 | 100
2149 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 235 mt.) along with stand post at different Sourceless AWC under Ramnagar-I Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Chandanpur-1 (19345240116), G.P- Badhia, (ii) South Badhia-3 (19345240121), G.P- Badhia, (iii) Dangri Patna (19345240125), G.P- Badhia, (iv) Damodarpur Paschim (19345240203), G.P- Badhia, (v) Sadi (19345240207), G.P- Haldia-I, (vi) Kholaberia (19345240208), G.P- Haldia-I, (vii) Nilkanthapur (19345240209), G.P- Haldia-I, (viii) Rania (19345240210), G.P- Haldia-I. |  |  | ORD/000455/2021-2022 | 1938/TD | 02/03/2022 | 45 | AYSAN KHAN | 24.8 | 21.96 | 100
2150 | Tamluk Division |  | Installation of 08 (Eight) Nos. 0.5 H.P. capacity Submerssible Pump Set within the Newly constructed Tube well (100 mm. x 50 mm. x 225 mt.) along with stand post at different Sourceless AWC under Bhagwanpur-II Block of Tamluk Division, PHE Dte. within Purba Medinipur district. Name of Site: (i) Porachingra AWC (19345020102), G.P- Garbari-I, (ii) Jhinuk-khali Madhyapally AWC (19345020117), G.P- Garbari-I, (iii) Paschim Garbari AWC (19345020216), G.P- Garbari-II, (iv) Kutubuddinpur AWC (19345020302), G.P- Jukhia, (v) Madhakhali Primary School (19345020303), G.P- Jukhia, (vi) Sitadighi Primary School (19345020305), G.P- Jukhia, (vii) Jukhia AWC (19345020307), G.P- Jukhia, (viii) Jukhia Sitadhighi Primary School (19345020308), G.P- Jukhia. |  |  | ORD/000456/2021-2022 | 1939/TD | 02/03/2022 | 45 | DAS ENTERPRISE | 24.24 | 23.02 | 100
2151 | Tamluk Division |  | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. |  |  | ORD/000529/2023-2024 | 1299/TD | 30/06/2023 | 184 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 0 | 100
2152 | Tamluk Division |  | Continuation work order for hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily rate basis (as and when required including Govt. Holiday) for the period from 01.06.2023 to 30.06.2023 i.e. 01 (one) month only, having contract carriage permit from Regional Transport Authority for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. (Ref:- Memo No.- 375/RWS/TSD Dated, 30/11/2022 |  |  | ORD/000703/2023-2024 | 54/RWS/TSD | 19/05/2023 | 30 | SRIMANTA PANJA | 0.14 | 0 | 100
2153 | Tamluk Division |  | Construction of M.S. Structure over drainage canal to support different dia DI(K-7) distribution pipe & 150 mm dia. DI(K-9) rising main pipe under Shyampur Water Supply Scheme at different Nodal Point within Moyna Block under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte. |  |  | ORD/000048/2022-2023 | 271/TD | 02/05/2022 | 30 | RAJ KUMAR SINGHA | 17.62 | 15.54 | 100
2154 | Tamluk Division |  | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 500 Cum and staging height 20.00 mtr. with allied work under Shyampur & its adjoining mouzas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. |  |  | ORD/000152/2021-2022 | 1092/TD | 17/11/2021 | 210 | RAJ KUMAR SINGHA | 521.85 | 405.18 | 100
2155 | Tamluk Division |  | Interconnection with laying of 150 mm dia DI (K-9) Rising main From 1st & 2nd Tube Well Site to O.H.R. and other allied works at Shyampur PWSS Water Supply Scheme within Moyna Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000392/2022-2023 | 1425/TD | 26/09/2022 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 3.91 | 0 | 100
2156 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Shyampur Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000520/2021-2022 | 1995/TD | 07/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.07 | 100
2157 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 1284/TD | 15/12/2021 | 0 | Resource Division | 33.3 | 0 | 0
2158 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000031/2021-2022 | 1474/TD | 03/01/2022 | 0 | Resource Division | 14.11 | 0 | 0
2159 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000033/2021-2022 | 1680/TD | 28/01/2022 | 0 | Resource Division | 3.98 | 0 | 0
2160 | Tamluk Division |  | Laying of Distribution pipe line , Construction of Pump House & Boundary Wall, Construction of RCC Over Head Reservoir of Capacity 450 Cum, Sub -Soil Investigation with allied works of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/000151/2021-2022 | 1091/TD | 17/11/2021 | 210 | TAPAS SANTRA | 526.12 | 429.67 | 95
2161 | Tamluk Division |  | Laying of 150 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials in between 1st Tube well to 2nd Tube Well of Baharampur & its adjoining mouzas Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000168/2023-2024 | 295/TD | 20/04/2023 | 30 | SUBHENDU HAZRA | 3.71 | 2.91 | 100
2162 | Tamluk Division |  | Supply & Delivery of 80 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000311/2021-2022 | 1687/TD | 31/01/2022 | 15 | SANTRA ENTERPRISE. | 4.01 | 4.01 | 100
2163 | Tamluk Division |  | Supply & Delivery of 125 mm, 150 mm,200 mm & 250 mm dia Sluice Valve for Baharampur piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000312/2021-2022 | 1688/TD | 31/01/2022 | 15 | SANTRA ENTERPRISE. | 3.81 | 3.81 | 100
2164 | Tamluk Division |  | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 1st TW / Head Work Site ( Mouza- Kalmichhabar ,J.L. No-317, Plot No- 599), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur,PHE Dte. |  |  | ORD/000372/2021-2022 | 1682/TD | 28/01/2022 | 45 | BIBEKANANDA DAS | 6.41 | 6.4 | 100
2165 | Tamluk Division |  | Construction of Culvert with Wing-wall & Toe wall for Approach Road at 2nd TW Site ( Mouza- Jethaibari ,J.L. No-307, Plot No- 106), for Baharampur Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur, PHE Dte. |  |  | ORD/000373/2021-2022 | 1683/TD | 28/01/2022 | 45 | BIBEKANANDA DAS | 6.41 | 6.4 | 100
2166 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Baharampur Water Supply Scheme within under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000513/2021-2022 | 1994/TD | 07/03/2022 | 21 | AQUATECH ENGINEERS | 14.76 | 10.39 | 100
2167 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Baharampur PWSS Block - Bhagwanpur-II in the District of Purba Medinipur. |  |  | ORD/000715/2023-2024 | 2959/TD | 24/11/2023 | 25 | S.D. CONSTRUCTION | 51.79 | 0 | 85
2168 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000001/2022-2023 | 81/TD | 08/04/2022 | 0 | Resource Division | 21.16 | 0 | 0
2169 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 1283/TD | 15/12/2021 | 0 | Resource Division | 3.37 | 0 | 0
2170 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000030/2021-2022 | 1475/TD | 03/01/2022 | 0 | Resource Division | 12.61 | 0 | 0
2171 | Tamluk Division | Contai Sub-Division | Quotation for new service connection at TW-III of Basudebberia ws scheme under MMD,PHE Dte, Block-Contai-III, Marishda CCC Application no-2004765941 Con ID-204324592 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00592/2024-2025 | BP-2024-25-290 | 29/07/2024 | 0 | WBSEDCL | 6.15 | 0 | 0
2172 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000101/2022-2023 | 477/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
2173 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia. Sluice Valve for Augmentation of Basudebberia Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000126/2022-2023 | 630/TD | 23/06/2022 | 15 | BIBEKANANDA DAS | 4.82 | 4.82 | 100
2174 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Basudebberya Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000176/2021-2022 | 1185/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.84 | 9.56 | 100
2175 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (60 nos) under JJM with allied work of BASUDEB BERYA PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte.(PART - E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000261/2023-2024 | 541/TD | 12/05/2023 | 508 | GRAND CONSTRUCTION | 9.36 | 0 | 60
2176 | Tamluk Division | Contai Sub-Division | Laying of Washout pipeline, Repairing of OHR, Pump House no 1, Pump House No. 2 and Head Works Boundary Wall under JJM with allied work of Basudebberiya PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000292/2024-2025 | 3057/TD | 19/09/2024 | 400 | ABHIJIT BERA | 19.56 | 0 | 100
2177 | Tamluk Division | Contai Sub-Division | Relaying of Existing Damaged Distribution Pipe Line With allied Works for Augmentation Of Basudebberiya Water Supply Scheme in Deshpran Block Of Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000333/2023-2024 | 807/TD | 30/05/2023 | 30 | A-PLUS | 20.92 | 0 | 100
2178 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line and providing of FHTC for Augmentation of Basudebberiya Water Supply Scheme In Deshpran Block in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000471/2021-2022 | 1946/TD | 03/03/2022 | 180 | M/S A.R. ENTERPRISE | 490.93 | 393.51 | 90
2179 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Basudebbrya, JL No. 428 Plot No. 2879) of Basudebberya Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tubewell Site (Mouza- Uttar Ektarpur, JL No. - 136, Plot No. 38) of Murisai Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000562/2023-2024 | 2048/TD | 25/08/2023 | 40 | KALPANA BUILDERS | 34.03 | 0 | 40
2180 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Basudebberiya Water Supply Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000636/2024-2025 | 849/TD | 19/03/2025 | 60 | SMMD | 3.59 | 0 | 0
2181 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Basudebberiya Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000887/2022-2023 | 440 / CSD | 20/03/2023 | 15 | GIRI ENTERPRISE | 0.91 | 0.91 | 0
2182 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000010/2021-2022 | 1252/TD | 13/12/2021 | 0 | Resource Division | 19.67 | 0 | 0
2183 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000037/2021-2022 | 1953/TD | 04/03/2022 | 0 | Resource Division | 16.73 | 0 | 0
2184 | Tamluk Division |  | Laying distribution pipe line, soil test & construction of R.C.C. Over Head Reservoir of capacity 400 Cum and staging height 20.00 mtr. with allied work under Narikeldaha & its adjoining moujas Water Supply Scheme within Moyna Dev. Block including supply of all labour & materials under Tamluk sub-division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. |  |  | ORD/000155/2021-2022 | 1154/TD | 30/11/2021 | 210 | ARABINDA GHOSH | 523.45 | 518.48 | 100
2185 | Tamluk Division |  | Land filling with earth at 2nd. T/W site at Narikeldaha W/S scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. |  |  | ORD/000166/2022-2023 | 712/TSD | 16/06/2022 | 7 | GHOSH ENTERPRISE | 1.43 | 1.43 | 100
2186 | Tamluk Division |  | Land filling with earth at H/W site at Narikeldaha Water Supply scheme of Moyna Dev. Block under Tamluk Sub-Division of Tamluk Division. PHE Dte. |  |  | ORD/000207/2022-2023 | 860/TD | 21/07/2022 | 7 | GHOSH ENTERPRISE | 4.79 | 4.79 | 100
2187 | Tamluk Division |  | Interconnection with laying of 150 mm dia DI (K-9) rising main from H/W site tube well to 2nd T/W site at Narikeldaha PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. |  |  | ORD/000231/2022-2023 | 972/TD | 03/08/2022 | 15 | GHOSH ENTERPRISE | 5.7 | 0 | 100
2188 | Tamluk Division |  | Additional work of Plinth protection, surface drain, septic tank, soak well, plumbing work, brick work,water arrangement of Toilet at 2nd T/W site for Narikeldaha Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000350/2022-2023 | 1172/TSD | 07/09/2022 | 25 | GHOSH ENTERPRISE | 2.27 | 2.27 | 100
2189 | Tamluk Division |  | Construction of M.S. Structure over irrigation canal to support 200 mm dia. DI (K-7) distribution pipe under Narikeldaha Water Supply Scheme at different Nodal Point under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte (L=40.00 Mtr ) |  |  | ORD/000395/2022-2023 | 1429/TD | 26/09/2022 | 25 | KRISHNENDU SEKHAR DAS | 4.48 | 4.48 | 100
2190 | Tamluk Division |  | Installation of display Board (80 nos.) at different work site for PHE Dept. Land under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/000445/2024-2025 | 3544/TD | 14/11/2024 | 25 | MISHRA ENTERPRISE | 13.33 | 0 | 100
2191 | Tamluk Division |  | Functional Household Tap Connection (FHTC=798 nos)at Narikeldaha water supply scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000467/2023-2024 | 1447/TD | 13/07/2023 | 30 | GHOSH ENTERPRISE | 31.51 | 31.45 | 100
2192 | Tamluk Division |  | Laying Distribution system of Left-out portion of pipe line at Narikeldaha Water Supply Scheme in Moyna Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. |  |  | ORD/000566/2023-2024 | 2046/TD | 25/08/2023 | 30 | GHOSH ENTERPRISE | 88.3 | 88.28 | 100
2193 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 1st Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000578/2021-2022 | 2049/TD | 14/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.32 | 100
2194 | Tamluk Division |  | Sinking of 300 mm. x 200 mm. dia. x 240 mtr. deep tube well by direct rotary rig method at of 2nd Tubewell Site of Narkeldaha Water Supply Scheme within under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000580/2021-2022 | 2050/TD | 14/03/2022 | 21 | AQUATECH ENGINEERS | 15.11 | 14.1 | 100
2195 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000032/2021-2022 | 1685/TD | 31/01/2022 | 0 | Resource Division | 12.47 | 0 | 0
2196 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000034/2021-2022 | 1681/TD | 28/01/2022 | 0 | Resource Division | 3.98 | 0 | 0
2197 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000076/2021-2022 | 1832/TD | 15/02/2022 | 0 | Resource Division | 36.27 | 0 | 0
2198 | Tamluk Division |  | Bill for WBSEDCL for Quotation charges of Narikeldaha PWSS under Moyna Block under Tamluk Division, PHE Dte. |  |  | VCH/000572/2022-2023 | BP-2022-23-272 | 29/08/2022 | 0 | WBSEDCL | 9.17 | 0 | 0
2199 | Tamluk Division |  | Retrofitting to accommodate .FHTC (152 nos.)(Balance work) and laying of left-out portion with uPVC pipeline due to uncovered area of Dona Zone-II Water Supply Scheme and its adjoining mouzas Water Supply Scheme at different nodal point under JJM within Moyna Block under Tamluk Sub-Division of Tamluk Division in the District of Purba Medinipur. (Phase-II) |  |  | ORD/000204/2021-2022 | 1267/TD | 13/12/2021 | 25 | TARUN KOLEY | 46.72 | 45.8 | 100
2200 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Sankarpur Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000125/2022-2023 | 628/TD | 23/06/2022 | 15 | BIBEKANANDA DAS | 4.21 | 4.21 | 100
2201 | Tamluk Division | Contai Sub-Division | Renovation work of spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum for Augmentation of Sankarpur Water Supply Scheme within Block Contai- III under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000172/2022-2023 | 392 / CSD | 12/07/2022 | 30 | LAKSHMI NARAYAN ENTERPRISE | 2.43 | 2.34 | 100
2202 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd Tube Well site for Shankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-44.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000201/2024-2025 | 2323/TD | 23/07/2024 | 120 | DIPANKAR MAITY | 4.96 | 0 | 100
2203 | Tamluk Division | Contai Sub-Division | Continuation work order for Hiring of one no. Diesel Motor cabs (Luxury Taxi Standered non air conditioned) Bharat Stage -IV , on daily rate basis (including Govt. Holidays as and when required ) Having contract carraige permit from RTA for the office of the Assistant Engineer, Contai Sub-Division under Tamluk Division, PHE Dte. Purba Medinipur. For the Period from 01/07/2022 to 30/06/2023. (12 Months) Vehicle No-WB-31/6974 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000222/2022-2023 | 357/CSD | 30/06/2022 | 365 | SABITA PRADHA | 1.49 | 0.76 | 100
2204 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Additional 3rd Tubewell of Augmentation of Shankarpur Water Supply Scheme (Mouza - Kukraul, JL No. - 468, Plot No. - 66) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000239/2022-2023 | 980/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 12.15 | 11.67 | 100
2205 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipeline to accommodate FHTC with allied works including supply of all labour & materials for Augmentation of Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,P.H.E. Dte., Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000313/2022-2023 | 1226/TD | 07/09/2022 | 45 | PATHIK PABAN NANDI | 359.47 | 342.92 | 99
2206 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Shankarpur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000316/2021-2022 | 1609/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 3.54 | 100
2207 | Tamluk Division | Contai Sub-Division | Laying of Left out Distribution pipe line by HDPE pipes with allied works for Augmentation of Shankarpur & adjoining mouzas Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000418/2024-2025 | 3476/TD | 06/11/2024 | 20 | KOUSHIK MALLICK | 7.56 | 0 | 100
2208 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary and water supply arrangements including Plinth Protection at 3rd TW site for Shankarpur Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur (For Normal Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000427/2023-2024 | 717/TD | 24/05/2023 | 60 | JASODA ENTERPRISE | 3.73 | 3.67 | 100
2209 | Tamluk Division | Contai Sub-Division | Rising main and other allied works Augmentation of Shankarpur W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000494/2023-2024 | 1092/CSD | 06/06/2023 | 30 | LAKSHMI NARAYAN ENTERPRISE | 2.58 | 0 | 100
2210 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Shankarpur PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-104.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001199/2023-2024 | 820/TD | 05/03/2024 | 180 | S R TRADING CORPORATION | 12.57 | 0 | 100
2211 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2022-2023 | 411/TD | 25/05/2022 | 0 | Resource Division | 18.52 | 0 | 0
2212 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000088/2022-2023 | 1265/TD | 12/09/2022 | 0 | Resource Division | 13.3 | 0 | 0
2213 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting of FHTC (200 nos.) and Laying of Left-Out portion HDPE Pipe line under Surface Water Based Water Supply Scheme at Zone-V due to uncovered area of this Zone and damaged pipe line at different Nodal Point under Tamluk Sub-Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000020/2022-2023 | 61/TD | 05/04/2022 | 20 | MRITYUNJOY PARIA | 17.51 | 16.09 | 100
2214 | Tamluk Division | Digha Sub-Division | Providing FHTC under JJM in Gobra PWSS within Ramnagar-II Dev. Block under Digha Sub-Division of Tamluk Division PHE Dte.in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000299/2021-2022 | 1640/TD | 19/01/2022 | 100 | M/S CARE | 122.42 | 92.17 | 80
2215 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000075/2021-2022 | 1749/TD | 08/02/2022 | 0 | Resource Division | 14.03 | 0 | 0
2216 | Tamluk Division |  | Providing 1412 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000143/2022-2023 | 719/TD | 29/06/2022 | 40 | S.D. CONSTRUCTION | 64.5 | 64.48 | 100
2217 | Tamluk Division |  | Providing 1450 Nos FHTC with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Contai Sub Division of Tamluk Division, PHE Dte. Purba Medinipur |  |  | ORD/000615/2021-2022 | 2203/TD | 21/03/2022 | 35 | TAPAS SANTRA | 78.78 | 78.78 | 100
2218 | Tamluk Division |  | Instalation of display Board at different work site of Paschimbetiya Retrofitting PWSS in Contai - III Block, Mahammadpur Retrofitting PWSS in Bhagwanpur - I Block, Baharampur, Arjunnagar Retrofitting PWSS in Bhagwanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/001187/2023-2024 | 2335/CSD | 29/12/2023 | 15 | SAURAV HAZRA | 0.83 | 0 | 100
2219 | Tamluk Division |  | Retrofitting to accommodate FHTC (2753 nos) and laying of left-out uPVC pipeline due to uncovered area of this zone at different nodal point under JJM in Uttar Dhalhara Zone-II Water Supply Scheme for Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in the District of Purba medinipur. |  |  | ORD/000298/2021-2022 | 1634/TD | 19/01/2022 | 120 | M/S CARE | 135.49 | 63.79 | 80
2220 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000073/2021-2022 | 2349/TD | 31/03/2022 | 0 | Resource Division | 15.14 | 0 | 0
2221 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000218/2023-2024 | 1116/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2222 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Chandibeniya Zone-I PWSS within Moyna Dev. Block .in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000297/2021-2022 | 1633/TD | 19/01/2022 | 90 | ARABINDA GHOSH | 105.61 | 104.47 | 100
2223 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000199/2023-2024 | 1100/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2224 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of sluice valve & delivery at Chapbasan Store for Dakshin Mechogram PWSS within Panskura-I Dev. Block and under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000091/2022-2023 | 442/TD | 31/05/2022 | 15 | SWADHIN KUMAR CHAKRABORTY | 3.34 | 3.34 | 100
2225 | Tamluk Division | Tamluk Sadar Sub-Division | 1(One) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Dakshin Mechogram Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000130/2023-2024 | 267/TD | 20/04/2023 | 45 | TARUN KHATUA | 13.06 | 0 | 96
2226 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dakshin Mechogram Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000181/2021-2022 | 1190/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 5.28 | 5.28 | 100
2227 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000306/2021-2022 | 1667/TD | 25/01/2022 | 120 | SWADHIN KUMAR CHAKRABORTY | 135.54 | 132.11 | 100
2228 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution system of pipe line and its allied works for Dakshin Mechogram & its adjoining mouzas Water Supply Scheme at Panskura-I Block under Tamluk Sub Division of Tamluk Division, P.H.E Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000306/2022-2023 | 1146/TD | 31/08/2022 | 20 | M/S. CHANDI CHARAN MISHRA & CO. | 14.56 | 14.4 | 100
2229 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation of Dakshin Mechogram Water Supply Scheme by Providing Laying Distribution System and FHTC in Panskura Block in the District of Purba Medinipur. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000307/2021-2022 | 1668/TD | 25/01/2022 | 120 | M/S. CHANDI CHARAN MISHRA & CO. | 134.86 | 96.8 | 100
2230 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation Of Ground Water Based Dakshin Mechogram PWSS to Accommodate FHTC in Panskura-I Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000734/2022-2023 | 2552/TD | 24/01/2023 | 60 | FARID UDDIN AHMED | 43.27 | 11.69 | 100
2231 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000014/2021-2022 | 1256/TD | 13/12/2021 | 0 | Resource Division | 0.59 | 0 | 0
2232 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000029/2022-2023 | 419/TD | 25/05/2022 | 0 | Resource Division | 1.16 | 0 | 0
2233 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000045/2021-2022 | 1730/TD | 02/02/2022 | 0 | Resource Division | 12.11 | 0 | 0
2234 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money of Uttar Sonamui PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00015/2023-2024 | BP-2023-24-1 | 13/04/2023 | 0 | WBSEDCL | 0.5 | 0 | 0
2235 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money for Uttar Sonamui PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00645/2022-2023 | BP-2022-23-934 | 30/03/2023 | 0 | WBSEDCL | 4.34 | 0 | 0
2236 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000158/2021-2022 | 1162/TD | 01/12/2021 | 7 | HORIZEN | 7.18 | 7.16 | 100
2237 | Tamluk Division | Tamluk Sadar Sub-Division | Leftout FHTC- 15 Nos. including supplying, laying, fitting, fixing of Pipe with all necessary specials, saddle piece etc. all complete including cost of all materials and labour for Uttar Sonamui Water Supply Scheme under Uttar Sonamui Gram Panchayat Area within Tamluk-II Dev. Block under Tamluk Sub-Division of Tamluk Division PHE Dte. in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000200/2024-2025 | 1061/TSD | 19/07/2024 | 84 | DIPANKAR MALAKAR | 0.97 | 0 | 100
2238 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000218/2022-2023 | 904/TD | 27/07/2022 | 21 | AQUATECH ENGINEER | 17.25 | 15.84 | 100
2239 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at 2nd Tube well Site of Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000219/2022-2023 | 905/TD | 27/07/2022 | 21 | AQUATECH ENGINEER | 17.25 | 15.53 | 100
2240 | Tamluk Division | Tamluk Sadar Sub-Division | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000229/2022-2023 | 970/TD | 03/08/2022 | 15 | NARAYAN MANDAL | 10.6 | 10.59 | 100
2241 | Tamluk Division | Tamluk Sadar Sub-Division | Left-out portion of uncovered area with uPVC pipe line and its allied works for Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000230/2022-2023 | 971/TD | 03/08/2022 | 15 | KRISHNENDU SEKHAR DAS | 8.3 | 8.29 | 100
2242 | Tamluk Division | Tamluk Sadar Sub-Division | Supply & Delivery of different dia DI Specials for Laying of Distribution Main (K-7) of Different works for providing functional house hold tap connection(FHTC) by Augmentation of Uttar Sonamui Water Supply Scheme. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000331/2022-2023 | 1175/TSD | 09/09/2022 | 15 | SK. NUR ISLAM | 1.92 | 1.77 | 100
2243 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 810 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-I) (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000340/2021-2022 | 1773/TD | 08/02/2022 | 1336 | NARAYAN MANDAL | 74.62 | 68.32 | 95
2244 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 388 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Uttar Sonamui,Part-II) (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000341/2021-2022 | 1774/TD | 08/02/2022 | 30 | ADHIKARY CONSTRUCTION | 42.02 | 31.98 | 95
2245 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 533 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Bhandarberya) (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000342/2021-2022 | 1775/TD | 08/02/2022 | 30 | S.D. CONSTRUCTION | 58 | 32.49 | 100
2246 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 510 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-I) (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000343/2021-2022 | 1776/TD | 08/02/2022 | 40 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 76.98 | 67.75 | 95
2247 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 858 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Chak Srikrishnapur &Uttar Narikelda) (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000344/2021-2022 | 1777/TD | 08/02/2022 | 40 | NARAYAN CHANDRA DAS | 86.75 | 81.26 | 100
2248 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 484 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme''(Mouza-Payrachali) (PART-J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000345/2021-2022 | 1778/TD | 08/02/2022 | 1467 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 43.68 | 39.07 | 100
2249 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 586 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Ganapatinagar) (PART-K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000346/2021-2022 | 1779/TD | 08/02/2022 | 40 | BHOLANATH DEY | 57.93 | 47 | 95
2250 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000556/2022-2023 | 2214/TD | 22/12/2022 | 25 | KRISHNENDU SEKHAR DAS | 4.56 | 0 | 0
2251 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Uttar Sonamui Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000557/2022-2023 | 2215/TD | 22/12/2022 | 25 | ADHIKARY CONSTRUCTION | 4.46 | 3.93 | 0
2252 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 204 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Nimtouri,P-II) (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000588/2021-2022 | 2061/TD | 15/03/2022 | 30 | J.M. CONSTRUCTION | 29.04 | 24.61 | 95
2253 | Tamluk Division | Tamluk Sadar Sub-Division | Different works for providing functional house hold tap connection (FHTC 374 nos.) by Augmentation of Uttar Sonamui Water Supply Scheme (Mouza-Kulberya) (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000589/2021-2022 | 2062/TD | 15/03/2022 | 30 | SK. NUR ISLAM | 51.1 | 47.12 | 100
2254 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of 3.60 Mtr. X 3.00 Mtr. Switch Room cum Chlorine Room for Water Supply (as per Deptt. drawing) at 2nd. Tube well site. of Uttar Sonamui Pipe Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte.in the District of Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000731/2023-2024 | 2982/TD | 29/11/2023 | 45 | KRISHNENDU SEKHAR DAS | 7.81 | 0 | 100
2255 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of R.C.C. Elevated Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work including supply of all labour & materials for Augmentation of Uttar Sonamui & its adjoining moujas Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District . (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000745/2022-2023 | 2550/TD | 24/01/2023 | 738 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 149.76 | 41.91 | 80
2256 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia DI(K-9) Rising main From 3 rd Tube Well & 2 nd Tube Well Site to O.H.R. Site and other allied works at Uttar Sonamui Water Supply Scheme within Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000842/2022-2023 | 3196/TD | 14/03/2023 | 15 | MAHAMAYA TIMBER AND CONSTRUCTION | 5.48 | 0 | 0
2257 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000054/2021-2022 | 1833/TD | 15/02/2022 | 0 | Resource Division | 26.06 | 0 | 0
2258 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000083/2021-2022 | 2191/TD | 21/03/2022 | 0 | Resource Division | 30.92 | 0 | 0
2259 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000222/2023-2024 | 1121/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2260 | Tamluk Division | Contai Sub-Division | Payment to WBSEDCL for Quotation Money of Ramchak PWSS from Sapai PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00016/2023-2024 | BP-2023-24-2 | 13/04/2023 | 0 | WBSEDCL | 0.28 | 0 | 0
2261 | Tamluk Division | Contai Sub-Division | Providing FHTC( Functional Household tap connection )For implementation of Har Ghar Jhal Gram / Sajal Gram under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000058/2023-2024 | 133/TD | 10/04/2023 | 20 | MRINAL KANTI PRADHAN | 10.72 | 0 | 60
2262 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sapai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000178/2021-2022 | 1187/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.13 | 4.11 | 100
2263 | Tamluk Division | Contai Sub-Division | Repairing Of Pump House and Boundary Wall of Pump House No-I & II under Augmentation of Sapai Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000313/2023-2024 | 486/TD | 10/05/2023 | 30 | SADDAM DIN | 4.19 | 0 | 100
2264 | Tamluk Division | Contai Sub-Division | Augmentation of Sapai Water Supply Scheme by Providing Laying Distribution System and FHTC in Conati-III Block of Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000334/2021-2022 | 1653/TD | 21/01/2022 | 90 | ARUP KUMAR DEY | 223.76 | 145.55 | 100
2265 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development for Additional Tube Well at J.L. No.-171, PLot no.-65/215, Mouza-Chandrikalapunja under Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000343/2022-2023 | 1294/TD | 13/09/2022 | 60 | GITA ENTERPRISE | 4.85 | 3.81 | 100
2266 | Tamluk Division | Contai Sub-Division | Rising main and other allied works for connecting Additional Tube well of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000346/2022-2023 | 1295/TD | 13/09/2022 | 30 | AMIT PAYRA | 4.57 | 0 | 100
2267 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional Tubewell Site (JL no. 171, Plot no. 65/215, Mouza-Chandrikalapunja) of Sapai Water Supply Scheme under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2021-2022 | 1993/TD | 07/03/2022 | 21 | PRANTIK DRILLING AGENCY | 12.08 | 8.76 | 100
2268 | Tamluk Division | Contai Sub-Division | Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method with 150 dia. uPVC Steiner of 30 m length for replacement of 1st Tube Well for Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000577/2024-2025 | 455/TD | 04/02/2025 | 40 | PRANTIK DRILLING AGENCY | 13.3 | 0 | 0
2269 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Reservoir (OHR)Site, Mouza -Sapai, J.L no - 176, under Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. Length 76.00 mtr. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000661/2022-2023 | 2346/TD | 10/01/2023 | 30 | JASODA ENTERPRISE | 10.32 | 8.76 | 100
2270 | Tamluk Division | Contai Sub-Division | Supply & Delivery of CIDF Sluice Valve for laying of distribution pipe line by UPVC pipes with allied works for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000662/2021-2022 | 2224/TD | 24/03/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.31 | 4.31 | 100
2271 | Tamluk Division | Contai Sub-Division | Repairing of 100 cum. capacity 20 mtr. staging height R.C.C. Over Head Reservoir for Augmentation of Sapai Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000662/2022-2023 | 2347/TD | 10/01/2023 | 60 | BARH CONSTRUCTION | 14.41 | 8.54 | 0
2272 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000009/2021-2022 | 1251/TD | 13/12/2021 | 0 | Resource Division | 0.35 | 0 | 0
2273 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000036/2021-2022 | 1866/TD | 17/02/2022 | 0 | Resource Division | 5.42 | 0 | 0
2274 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village- Saripur,J.L. No-92 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000110/2020-2021 | 2466/TD | 18/12/2020 | 25 | NARAYAN MANDAL | 27.85 | 0 | 100
2275 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village- Damodarpur,J.L. No-93 under JJM in Saripur PWSS Block - Chandipur in the District of Purba Medinipur. |  |  | ORD/000111/2020-2021 | 2467/TD | 18/12/2020 | 25 | NARAYAN MANDAL | 27.46 | 0 | 100
2276 | Tamluk Division |  | Retrofitting to accommodate FHTC (53 nos) under JJM within Saripur PWSS(Balance Work), Block- Chandipur in the District of Purba Medinipur |  |  | ORD/000222/2021-2022 | 639/TSD | 26/10/2021 | 20 | NARAYAN MANDAL | 2.52 | 1.69 | 100
2277 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000216/2021-2022 | 123/W | 07/07/2021 | 0 | NARAYAN MANDAL | 1.54 | 0 | 0
2278 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000217/2021-2022 | 124/W | 07/07/2021 | 0 | NARAYAN MANDAL | 2 | 0 | 0
2279 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Saripur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000597/2020-2021 | 644/W | 13/01/2021 | 0 | NARAYAN MANDAL | 26.31 | 0 | 0
2280 | Tamluk Division |  | Retrofitting to accomodate FHTC of Village - Damudarpur under JJM Saripur W/S Scheme within Chandipur Block under Tamluk Division, PHE Dte. |  |  | VCH/000608/2020-2021 | 648/W | 25/01/2021 | 0 | NARAYAN MANDAL | 25.46 | 0 | 0
2281 | Tamluk Division | Contai Sub-Division | Quotation Bill for New Service connection at T/W NO-I Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767136/QUOT/03 DT. 07-06-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204325528 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00594/2024-2025 | BP-2024-25-291 | 29/07/2024 | 0 | WBSEDCL | 21.24 | 0 | 0
2282 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Chalti PWSS at Deshpran Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001279/2023-2024 | 1052/TD | 15/03/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
2283 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000080/2024-2025 | 2952/TD | 12/09/2024 | 0 | Resource Division | 6.76 | 0 | 0
2284 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000123/2022-2023 | 2404/TD | 16/01/2023 | 0 | Resource Division | 49.91 | 0 | 0
2285 | Tamluk Division | Contai Sub-Division | Ancillary Work of Reinforcement for reinforced cement concrete work for Constrution of R.C.C Elevated Reservoir of Capacity 900 cum and staging height 20.00mtr. With allied work including supply of all labour & material of Augmentation of Contai Saline Area Zone-III (PHASE-A) & its adjoining maujas water supply scheme within Contai-I Block under Contai sub- Division of Tamluk Division, P.H.E.Dte. Dist.- Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000192/2023-2024 | 393/TD | 27/04/2023 | 40 | TAPAS SANTRA | 48.63 | 24.47 | 60
2286 | Tamluk Division | Contai Sub-Division | Laying of distribution pipe line to accommodate FHTC (7341 Nos) with construction of R.C.C. Elevated Reservoir of capacity 900cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Contai Saline Area Zone-III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000514/2022-2023 | 2062/TD | 09/12/2022 | 935 | TAPAS SANTRA | 1130.28 | 750.64 | 80
2287 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia HDPE Pipe Lines With allied works to accommodate Total 7341 nos FHTC of Augementation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000701/2023-2024 | 3115/TD | 05/12/2023 | 40 | TAPAS SANTRA | 115.73 | 0 | 100
2288 | Tamluk Division | Contai Sub-Division | Laying of 90 mm dia HDPE Pipe Lines With allied works to accommodate Total 7341 nos FHTC of Augmentation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000856/2023-2024 | 00/TD | 09/01/2024 | 40 | TAPAS SANTRA | 0 | 0 | 0
2289 | Tamluk Division | Contai Sub-Division | Boundary Wall, Raising Main, and Pump House, under JJM with allied work for Augmentation of Contai Saline area Zone-III( Phase-B) in Contai-I Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001153/2023-2024 | 561/TD | 15/02/2024 | 481 | PULAK KUMAR SAMANTA | 46.1 | 0 | 25
2290 | Tamluk Division | Contai Sub-Division | Replacement of Damaged Existing DI/CI pipe line with HPPE Pipe line With allied works to accommodate Total 7341 nos FHTC of Augementation of Contai Saline Area Zone -III (Phase-A) Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001198/2023-2024 | 849/TD | 06/03/2024 | 30 | TAPAS SANTRA | 52.89 | 0 | 100
2291 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000028/2023-2024 | 613/TD | 17/05/2023 | 0 | Resource Division | 45.22 | 0 | 0
2292 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000107/2022-2023 | 1662/TD | 03/11/2022 | 0 | Resource Division | 263.84 | 0 | 0
2293 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 14.62 | 100
2294 | Tamluk Division | Contai Sub-Division | Laying Rising Main DI(K-9) pipe line with interconnection, Construction of 3.60 mtr. X 3.00 mtr. Size Switch Room cum Chlorine Room & Boundary Wall at 3rd Boosting TW site (Mouza-Jabda, J.L No-225, Plot No-887) of Argoal PWSS in Patashpur-II within Contai Sub-Division of Tamluk Division,PHE Dte.(Length-50.00 mtr.) (for Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000487/2023-2024 | 1521/TD | 18/07/2023 | 30 | SK. SARFARAJ | 33.57 | 0 | 90
2295 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000018/2023-2024 | 357/TD | 26/04/2023 | 0 | Resource Division | 17.67 | 0 | 0
2296 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC (2244 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - II Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000494/2022-2023 | 1891/TD | 24/11/2022 | 1283 | MAA ANANDAMAYEE | 407.46 | 215.51 | 50
2297 | Tamluk Division | Contai Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 40 | PRANTIK DRILLING AGENCY | 61.68 | 23.98 | 90
2298 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-II Water Supply scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000577/2023-2024 | 2185/TD | 01/09/2023 | 830 | MAA ANANDAMAYEE | 84.88 | 0 | 60
2299 | Tamluk Division | Contai Sub-Division | Brick bats road due to smoothly carring Rig Machine and soil testing equipment for Head Works site at Mouza-Pora Chingra, J.L. NO.-155, under Bajkul Zone-II W/S Scheme (Augmentation) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000841/2023-2024 | 1705/CSD | 31/08/2023 | 15 | M/S MONDAL CONSTRUCTION & CO. | 0.8 | 0 | 100
2300 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000889/2021-2022 | 1803/TD | 08/02/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.32 | 100
2301 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000024/2023-2024 | 608/TD | 17/05/2023 | 0 | Resource Division | 13.82 | 0 | 0
2302 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000116/2022-2023 | 1671/TD | 03/11/2022 | 0 | Resource Division | 39.54 | 0 | 0
2303 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- D [Bamania Jangal(62) part, Chhota Sijua(64) part, Parihara(65), Panchberya(67) part, Dhandali Bar(139) part, Bhaja Chauli(140)]. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000054/2022-2023 | 322/TD | 11/05/2022 | 45 | SRIMANTA KUMAR MAITY | 287.16 | 230.63 | 92
2304 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART- B [Dhandi Bar (139) part]. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000080/2022-2023 | 385/TD | 20/05/2022 | 30 | SWARUPANANDA DAS | 120.93 | 117.93 | 100
2305 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART - A [ Bamania(74), Ugalpur(73), Kajli(70), Katmuri(69), Amratalia(68), Panchberya(67) part]. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000081/2022-2023 | 395/TD | 23/05/2022 | 30 | PRANAB KUMAR DAS | 118.3 | 93.84 | 65
2306 | Tamluk Division | Contai Sub-Division | Augmentation Of Bhajachauli Water Supply Scheme by Providing Laying Distribution System and FHTC in Contai-III Block in the District of Purba Medinipur. PART-C [Bamania Jangal (62) part, Sijua (63), Chhota Sijua (64) part.] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000086/2022-2023 | 433/TD | 27/05/2022 | 981 | SNEHESH SEN | 113.07 | 89.13 | 100
2307 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Bhajachauli Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Phase-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000128/2022-2023 | 629/TD | 23/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.44 | 4.44 | 100
2308 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bhajachauli Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000177/2021-2022 | 1186/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 12.34 | 9.91 | 100
2309 | Tamluk Division | Contai Sub-Division | Washout pipeline, Repairing of OHR, Pump House no 1 under JJM with allied work of Bhajachauli PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000291/2024-2025 | 3056/TD | 19/09/2024 | 186 | SUBHENDU HAZRA | 31.12 | 0 | 50
2310 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for Additional(4th) Tubewell of Augmentation of Bhagwanpur Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300 mm x 200 mm dia. x 250 mtr. deep tube well by direct rotary rig method at Additonal 3rd Tubewell of Augmentation of Bhajachauli Water Supply Scheme (Mouza - Khalsiberia, JL No. - 138, Plot No. - 162/387) within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000311/2022-2023 | 1224/TD | 07/09/2022 | 857 | B. K. ENTERPRISE | 34.31 | 16.53 | 0
2311 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr. x 3.00 mtr. size switch Room cum chlorine room without sanitary & water supply arrangements including plinth protection at 3rd TW site for Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000361/2023-2024 | 929/TD | 01/06/2023 | 25 | DEBABRATA DAS | 3.53 | 0 | 100
2312 | Tamluk Division | Contai Sub-Division | Rising main and other allied works of 3rd Tube Well for Augmentation of BHAJACHAULI W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000362/2023-2024 | 930/TD | 01/06/2023 | 25 | DEBABRATA DAS | 4.31 | 0 | 100
2313 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for BHAJACHAULI PWSS within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-160.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000363/2023-2024 | 931/TD | 01/06/2023 | 40 | DEBABRATA DAS | 22.69 | 0 | 100
2314 | Tamluk Division | Contai Sub-Division | Laying Distribution Pipe Line & Accommodate FHTC (146 nos) under JJM with allied work for Left out Areas of BHAJACHAULI- PWSS in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000576/2023-2024 | 2198/TD | 01/09/2023 | 30 | SUBHENDU HAZRA | 19.54 | 0 | 100
2315 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room at 2nd TW site at Bhajachauli Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000726/2023-2024 | 2971/TD | 28/11/2023 | 45 | SUBHENDU HAZRA | 3.53 | 0 | 100
2316 | Tamluk Division | Contai Sub-Division | Augmentation of Bhajachauli Water Supply Scheme for Supply and Delivery of Different dia Sluice Valves under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000843/2023-2024 | 2128/CSD | 24/11/2023 | 20 | SAURAV HAZRA | 1.22 | 0 | 100
2317 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000006/2022-2023 | 101/TD | 11/04/2022 | 0 | Resource Division | 21.75 | 0 | 0
2318 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000066/2021-2022 | 644/TD | 27/06/2022 | 0 | Resource Division | 23.79 | 0 | 0
2319 | Tamluk Division | Contai Sub-Division | Restoration of Hard shoulder at Heria-Mugberia and Itaberia-Mugberia Road after laying pipe line by PHE under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | BILL/00236/2023-2024 | BP-2023-24-121 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 5.16 | 0 | 0
2320 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000100/2022-2023 | 476/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
2321 | Tamluk Division | Contai Sub-Division | Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 1st Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1228) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000105/2022-2023 | 481/TD | 03/06/2022 | 21 | TAPAS KUMAR GIRI | 17.91 | 0 | 0
2322 | Tamluk Division | Contai Sub-Division | Left-out portion of uncovered area of different dia. uPVC pipeline within Suadighi Zone-II Water Supply Scheme and its adjoining mouzas at different Nodal Point in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000132/2024-2025 | 1910/TD | 07/06/2024 | 267 | SETH ENTERPRISE | 48.35 | 0 | 0
2323 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-I Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000189/2022-2023 | 815/TD | 12/07/2022 | 1085 | JAYANTA KUMAR MONDAL | 565.34 | 382.17 | 88
2324 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Suadighi Zone-II Water Supply Scheme within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000190/2022-2023 | 814/TD | 12/07/2022 | 963 | JAYANTA KUMAR MONDAL | 584.44 | 307.37 | 80
2325 | Tamluk Division | Contai Sub-Division | Boundary Wall Repair at 2nd TW Site and Construction of Toilet at 1st TW site of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000341/2024-2025 | 3339/TD | 22/10/2024 | 40 | BIBEKANANDA DAS | 7.03 | 0 | 0
2326 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-I Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000396/2022-2023 | 1435/TD | 27/09/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.34 | 7.34 | 100
2327 | Tamluk Division | Contai Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements at 1st TW (Head Work) site at Suadighi Zone-II Water Supply Scheme within Bhagwanpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000425/2022-2023 | 1594/TD | 18/10/2022 | 60 | M/S. NEW DINDA ENTERPRISE | 6.94 | 6.32 | 100
2328 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-I) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000450/2021-2022 | 1694/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.2 | 4.02 | 100
2329 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Suadighi (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000451/2021-2022 | 1695/TD | 31/01/2022 | 20 | CONCORD ENGINEERING | 4.47 | 4.47 | 100
2330 | Tamluk Division | Contai Sub-Division | Laying Rising Main, Earth work filling & Construction of Boundary wall at OHR (1st), 2nd & 3rd Tube Well Site Mouza- Bhupatinagar & Keshaidighi, J.L No.-253,262 for Augmentation of Suadighi Zone-II PWSS within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000490/2023-2024 | 1599/TD | 24/07/2023 | 570 | JAYANTA KUMAR MONDAL | 45.98 | 0 | 0
2331 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements at for 3rd Tube well J.L no. -257,Plot no. -240, Mouza -Kasba under Suadighi Zone-I Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000530/2022-2023 | 2097/TD | 13/12/2022 | 60 | SMMD | 3.4 | 3.16 | 100
2332 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 2nd Tube well site J.L no. -262,Plot no. -272, Mouza -Keshaidighi under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000531/2022-2023 | 2098/TD | 13/12/2022 | 60 | SMMD | 3.46 | 3.45 | 100
2333 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including land development at for 3rd Tube well site J.L no. -253,Plot no. -1498, Mouza -Bhupatinagar under Suadighi Zone-II Water Supply Scheme within Bhawanpur-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000532/2022-2023 | 2099/TD | 13/12/2022 | 712 | SMMD | 3.4 | 0 | 0
2334 | Tamluk Division | Contai Sub-Division | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Dhalua, JL No. 243 Plot No. 152) of Madhakhali Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site (Mouza- Bhupatinagar, JL No. 253 Plot No. 1498) of Suadighi Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000561/2023-2024 | 2047/TD | 25/08/2023 | 40 | PADMA ENGINEERING CO. | 38.21 | 0 | 44
2335 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000574/2022-2023 | 2261/TD | 30/12/2022 | 20 | SWASTIK ENTERPRISE | 6.18 | 6.18 | 100
2336 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Suadighi Zone-II Water Supply Scheme in Bhagabanpur II Block under Contai Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000575/2022-2023 | 2266/TD | 30/12/2022 | 20 | MAKALI ENGINEERING CORPORATION | 1.01 | 0 | 0
2337 | Tamluk Division | Contai Sub-Division | Rising main, Boundary Wall under JJM with allied work at 3rd TW site for Augmentation of SUADIGHI ZONE-I PWSS in Bhagwanpur-II Dev. Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000646/2023-2024 | 2598/TD | 10/10/2023 | 40 | A. R. CONSTRUCTION | 14.76 | 0 | 100
2338 | Tamluk Division | Contai Sub-Division | Left out Portion of uncovered area with upvc pipes with allied works of Suadighi Zone-I PWSS in Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001225/2023-2024 | 1038/TD | 15/03/2024 | 350 | S.D. CONSTRUCTION | 43.4 | 0 | 50
2339 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000009/2022-2023 | 95/TD | 11/04/2022 | 0 | Resource Division | 58.97 | 0 | 0
2340 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000070/2021-2022 | 648/TD | 27/06/2022 | 0 | Resource Division | 21.41 | 0 | 0
2341 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000071/2021-2022 | 649/TD | 27/06/2022 | 0 | Resource Division | 21.19 | 0 | 0
2342 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Biramput PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000155/2024-2025 | 2067/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2343 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000077/2024-2025 | 2951/TD | 12/09/2024 | 0 | Resource Division | 5.79 | 0 | 0
2344 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000167/2022-2023 | 2390/TD | 16/01/2023 | 0 | Resource Division | 43.89 | 0 | 0
2345 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2046 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of NARAYAN DANRI PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000849/2023-2024 | 72/TD | 05/01/2024 | 540 | SRIMANTA KUMAR MAITY | 519.29 | 0 | 25
2346 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000243/2022-2023 | 2723/TD | 06/02/2023 | 0 | Resource Division | 15.86 | 0 | 0
2347 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iv)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000255/2023-2024 | 521/TD | 11/05/2023 | 849 | PRASANTA MONDAL | 8.09 | 0 | 35
2348 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(i)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000347/2023-2024 | 876/TD | 01/06/2023 | 45 | TARUN KHATUA | 11.03 | 0 | 100
2349 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C(ii)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000348/2023-2024 | 877/TD | 01/06/2023 | 30 | TARUN KHATUA | 28.18 | 22.55 | 85
2350 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000414/2023-2024 | 1099/TD | 08/06/2023 | 1028 | MAA ANANDAMAYEE | 139.46 | 0 | 2
2351 | Tamluk Division | Haldia Sub-Division | Construction of Retaining wall, Approach road & Earth filling Work in Head work site of Kanchanpur Water Supply Scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(length of Retaining wall-120mtr) & (length of Approach road- 60 mtr). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000459/2024-2025 | 3705/TD | 03/12/2024 | 200 | TARUN KHATUA | 17.55 | 0 | 90
2352 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (280 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000877/2022-2023 | 3213/TD | 14/03/2023 | 654 | SK MAIDUL ISLAM | 39.57 | 0 | 60
2353 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (200 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000878/2022-2023 | 3214/TD | 14/03/2023 | 30 | G. S. CONSTRUCTION | 34.87 | 0 | 79
2354 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000880/2022-2023 | 3216/TD | 14/03/2023 | 60 | THREE MAA ENTERPRISE | 64.69 | 22.92 | 50
2355 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (115 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(i)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000881/2022-2023 | 3238/TD | 15/03/2023 | 45 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 9.62 | 4.57 | 100
2356 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(ii)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000882/2022-2023 | 3239/TD | 15/03/2023 | 45 | MAHAPRABHU ENTERPRISE | 9.86 | 0 | 21
2357 | Tamluk Division | Haldia Sub-Division | Ground water based Kanchanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC (100 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E(iii)) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000883/2022-2023 | 3240/TD | 15/03/2023 | 1086 | MODERN CONSTRUCTION | 9.69 | 2.71 | 43
2358 | Tamluk Division | Haldia Sub-Division | "G.I pipe column with M.S. Structure for laying of HDPE pipe line with Casing at Kanchanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. " (Total Length= 60.00 mtr, {i) NP-21 to 27= 30.00 mtr + ii) NP-44 to 50= 30.00 mtr .} | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001200/2023-2024 | 727/TD | 28/02/2024 | 30 | TARUN KHATUA | 8.88 | 0 | 100
2359 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000152/2023-2024 | 115/TD | 05/01/2024 | 0 | Resource Division | 10.5 | 0 | 0
2360 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000329/2022-2023 | 2987/TD | 27/02/2023 | 0 | Resource Division | 29.7 | 0 | 0
2361 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 911 | JAYANTA KUMAR MONDAL | 1264.74 | 0 | 30
2362 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000084/2024-2025 | 2954/TD | 12/09/2024 | 0 | Resource Division | 5.5 | 0 | 0
2363 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000204/2022-2023 | 2406/TD | 16/01/2023 | 0 | Resource Division | 18.29 | 0 | 0
2364 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (325 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000186/2023-2024 | 376/TD | 27/04/2023 | 60 | A. K. SIKDAR | 73.19 | 0 | 52
2365 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (322 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000187/2023-2024 | 377/TD | 27/04/2023 | 668 | SWARUPANANDA DAS | 73.44 | 0 | 50
2366 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (140 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000188/2023-2024 | 378/TD | 27/04/2023 | 30 | M/S. NEW DINDA ENTERPRISE | 38.62 | 22.81 | 65
2367 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (200 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000189/2023-2024 | 379/TD | 27/04/2023 | 30 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.51 | 0 | 60
2368 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (150 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000190/2023-2024 | 380/TD | 27/04/2023 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.52 | 0 | 58
2369 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (170 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000191/2023-2024 | 381/TD | 27/04/2023 | 25 | M/S. NEW DINDA ENTERPRISE | 19.14 | 7.88 | 45
2370 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (160 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000252/2023-2024 | 516/TD | 11/05/2023 | 60 | NEW STAR CONSTRUCTION | 84.23 | 0 | 73
2371 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Pump House & Accommodate FHTC (375 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000253/2023-2024 | 517/TD | 11/05/2023 | 818 | S.S.T ENGINEERING | 77.56 | 0 | 65
2372 | Tamluk Division | Contai Sub-Division | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (195 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000377/2023-2024 | 1016/TD | 06/06/2023 | 900 | DAS ENTERPRISE | 189.43 | 0 | 10
2373 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Panushi PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001051/2023-2024 | 381/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2374 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Pachahari, Basudevberya,Panusi & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001174/2023-2024 | 2329/CSD | 29/12/2023 | 10 | KAMAL KUMAR BERA | 0.62 | 0 | 100
2375 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000186/2023-2024 | 635/W | 20/02/2024 | 0 | Resource Division | 12.55 | 0 | 0
2376 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000312/2022-2023 | 2968TD | 27/02/2023 | 0 | Resource Division | 21.55 | 0 | 0
2377 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,Construction of 200 cum & 250 Cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3146 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Dhankar & Talchitkini its adjoining moujas PWSS in Patashpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2023-2024 | 1671/TD | 25/07/2023 | 1040 | HALDIA DEVELOPMENT CONSTRUCTION | 895.07 | 0 | 20
2378 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000325/2022-2023 | 2991/TD | 27/02/2023 | 0 | Resource Division | 14.06 | 0 | 0
2379 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Boosting Tube Well of Mouza- Rupnagar, JL No.- 503, Plot No.-320 of Barasubarnanagar Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement Tube Well of 2nd Tubewell at Mouza- Chanberya, JL No.- 425, Plot No.-416/1210 of Baharchandberya Water Supply Scheme within Contai-II(Deshpran) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 mm. x 200 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell site ( Boosting Tube well ) at Mouza -Argoal, JL No. - 233, Plot No. -514, Patashpur- II Block of Argoal Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 150 mm x 100 mm dia x 250 mtr. deep tube well by direct rotary rig method at Replacement of 2nd Tubewell site of Paschimbatya Water Supply Scheme at Mouza- Paschimbetya, JL No. 79, Plot No. 344 within Contai-III Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000251/2022-2023 | 1052/TD | 18/08/2022 | 40 | AQUATECH ENGINEERS | 55.36 | 0 | 100
2380 | Tamluk Division | Contai Sub-Division | Dismantling & Re-Construction of Boundary Wall and Land Filling at 2nd TW site for Site Preparation for Lowering of Replacement Tube Well at Paschimbetya PWSS for within Contai-III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000458/2023-2024 | 1495/TD | 17/07/2023 | 15 | PULAK KUMAR SAMANTA | 4.84 | 0 | 30
2381 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000017/2023-2024 | 347/TD | 26/04/2023 | 0 | Resource Division | 4.86 | 0 | 0
2382 | Tamluk Division | Digha Sub-Division | Laying of Distribution System to accomodate FHTC (3086 Nos) for Augmentation of Ramnagar Water Supply Scheme (Zone-I) within Ramnagar-I Block under Tamluk Division in the district of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000742/2022-2023 | 2533/TD | 19/01/2023 | 90 | BASANTA KUMAR MAITY | 287.99 | 125.94 | 45
2383 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, Laying of Rising main with distribution pipe line & Accommodate FHTC ( 500 Nos) under JJM with allied work for Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000858/2023-2024 | 169/TD | 09/01/2024 | 45 | BASANTA KUMAR MAITY | 104.58 | 0 | 41
2384 | Tamluk Division | Digha Sub-Division | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P-72-74(P)=18.0M, 53-72=298.0M, 34-53(P)=53.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001221/2023-2024 | 1032/TD | 15/03/2024 | 45 | APARNA CONSTRUCTION | 4.72 | 0 | 100
2385 | Tamluk Division | Digha Sub-Division | Laying of Distribution Pipe Line for Balance 180 mm dia HDPE pipe( N.P- 34-53(P)=233.0M, 26-34=136.0M) within Ramnagar Zone-I & Its Adjoining Mouzas Water Supply Scheme of Ramnagar-I Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001223/2023-2024 | 1033/TD | 15/03/2024 | 45 | BASANTI ENTERPRISE | 4.69 | 0 | 100
2386 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000236/2022-2023 | 2613/TD | 02/02/2023 | 0 | Resource Division | 75.91 | 0 | 0
2387 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000286/2022-2023 | 2639/TD | 02/02/2023 | 0 | Resource Division | 19.01 | 0 | 0
2388 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000223/2022-2023 | 2676/TD | 06/02/2023 | 0 | Resource Division | 35.6 | 0 | 0
2389 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1988 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of BETULYA CHAKLAPUR PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000206/2023-2024 | 413/TD | 02/05/2023 | 728 | DAS CONSTRUCTION | 517.7 | 0 | 7
2390 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Betula Chaklalpur Water Supply Scheme at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001276/2023-2024 | 1050/TD | 15/03/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2391 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000122/2023-2024 | 94/TD | 05/01/2024 | 0 | Resource Division | 12.25 | 0 | 0
2392 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000241/2022-2023 | 2726/TD | 06/02/2023 | 0 | Resource Division | 59.37 | 0 | 0
2393 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Chongra PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000880/2023-2024 | 202/TD | 10/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2394 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000003/2024-2025 | 1561/TD | 23/04/2024 | 0 | Resource Division | 11.88 | 0 | 0
2395 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000176/2022-2023 | 2434/TD | 16/01/2023 | 0 | Resource Division | 39.7 | 0 | 0
2396 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Chatra Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2021-2022 | 1189/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 3.53 | 3.53 | 100
2397 | Tamluk Division | Tamluk Sadar Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Rejuvenation of Chatra Water Supply Scheme in Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District | Assistant Engineer | Junior Engineer | ORD/000535/2023-2024 | 1836/TD | 08/08/2023 | 20 | RAMESH & SHANTI ENGINEERING WORKS | 3.13 | 3.13 | 100
2398 | Tamluk Division | Tamluk Sadar Sub-Division | Hiring of one no Diesel Motor Cabs(Luxary taxi) (Standerd non air conditioned) Bharat stage-IV, on daily rate basis (including Govt. Holidays as and when required) having contract carriage permit from RTA for the office of Executive Engineer, Tamluk Division ,PHE Dte. Under Tamluk Division for the period from 12 (Twelve) Months. | Assistant Engineer | Junior Engineer | ORD/000619/2022-2023 | 1345/TSD | 28/10/2022 | 239 | TAPAS SANTRA | 1.14 | 0 | 100
2399 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000041/2021-2022 | 1731/TD | 02/02/2022 | 0 | Resource Division | 8.76 | 0 | 0
2400 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000212/2023-2024 | 1112/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2401 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1914 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SOYA DIGHI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000205/2023-2024 | 412/TD | 02/05/2023 | 821 | JAYANTA KUMAR MONDAL | 418.27 | 0 | 40
2402 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000172/2023-2024 | 110/TD | 05/01/2024 | 0 | Resource Division | 11.79 | 0 | 0
2403 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000257/2022-2023 | 2680/TD | 06/02/2023 | 0 | Resource Division | 20.04 | 0 | 0
2404 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Construction of Pump House ,200 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1376 nos) under JJM with allied work including 02 (two) Years Operation & Maintenance of GULURI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000108/2023-2024 | 219/TD | 17/04/2023 | 900 | TAPAS SANTRA | 384.71 | 87.95 | 60
2405 | Tamluk Division | Tamluk Sadar Sub-Division | Land Development work at Headwork Site of Guluria Water Supply Scheme within Sahid Matangini Development Block under Tamluk Sadar Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000285/2024-2025 | 3050/TD | 19/09/2024 | 15 | S.D. CONSTRUCTION | 5.82 | 0 | 100
2406 | Tamluk Division | Tamluk Sadar Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116B of Guluri PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001183/2023-2024 | 742/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.53 | 0 | 0
2407 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000138/2023-2024 | 131/TD | 05/01/2024 | 0 | Resource Division | 8.48 | 0 | 0
2408 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000211/2022-2023 | 2470/TD | 16/01/2023 | 0 | Resource Division | 25.32 | 0 | 0
2409 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kia PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000171/2024-2025 | 2083/TD | 24/06/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2410 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000128/2022-2023 | 2412/TD | 16/01/2023 | 0 | Resource Division | 35.2 | 0 | 0
2411 | Tamluk Division | Contai Sub-Division | Sinking of Tube well, Pump House, 300 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, Soil investigation & Accommodate FHTC (1581 nos) under JJM with allied work including 02(Two) Years Operation & Maintenance for Basantia and Adjoining Moujas PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000421/2023-2024 | 1412/TD | 12/07/2023 | 180 | JAYANTA KUMAR MONDAL | 413.14 | 0 | 85
2412 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000074/2024-2025 | 2949/TD | 12/09/2024 | 0 | Resource Division | 9.74 | 0 | 0
2413 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000314/2022-2023 | 2970/TD | 27/02/2023 | 0 | Resource Division | 21.24 | 0 | 0
2414 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Central Zone) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000444/2021-2022 | 1665/TD | 24/01/2022 | 20 | HORIZEN | 3.52 | 3.46 | 100
2415 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2069 nos) under JJM with allied work for Digha Augmentation (Central Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000612/2023-2024 | 2271/TD | 05/09/2023 | 808 | ORIENT CONSTRUCTION | 477.25 | 0 | 22
2416 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000054/2023-2024 | 2077/TD | 28/08/2023 | 0 | Resource Division | 38.59 | 0 | 0
2417 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000066/2023-2024 | 2642/TD | 13/10/2023 | 0 | Resource Division | 12.75 | 0 | 0
2418 | Tamluk Division | Digha Sub-Division | Repairing & renovation of Switch Room , existing boundary wall, Store Room, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (125 Nos) under JJM with allied work for Digha Augmentation (Eastern Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000323/2024-2025 | 3219/TD | 01/10/2024 | 426 | M/S. NEW DINDA ENTERPRISE | 28.09 | 0 | 65
2419 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Eastern Zone) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000442/2021-2022 | .1651/TD | 20/01/2022 | 20 | HORIZEN | 4.21 | 4.15 | 100
2420 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2052 nos) under JJM with allied work for Digha Augmentation (Eastern Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000493/2023-2024 | 1591/TD | 21/07/2023 | 864 | ATCO ENTERPRISE | 642.85 | 0 | 40
2421 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000040/2023-2024 | 2066/TD | 28/08/2023 | 0 | Resource Division | 106.76 | 0 | 0
2422 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000064/2023-2024 | 2640/TD | 13/10/2023 | 0 | Resource Division | 13.39 | 0 | 0
2423 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at KASHIBHUIAN BAR PWSS at Contai-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000608/2024-2025 | 189/CSD | 27/01/2025 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0
2424 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000091/2024-2025 | 2964/TD | 12/09/2024 | 0 | Resource Division | 3.78 | 0 | 0
2425 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000177/2022-2023 | 2398/TD | 16/01/2023 | 0 | Resource Division | 34.37 | 0 | 0
2426 | Tamluk Division | Haldia Sub-Division | Ground water based Bakshichak Water Supply Scheme by providing Sinking of Tube Well, Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000149/2023-2024 | 276/TD | 20/04/2023 | 1046 | NARAYAN CHANDRA DAS | 84.8 | 0 | 39
2427 | Tamluk Division | Haldia Sub-Division | Ground water based Bakshichak Water Supply Scheme by Sub-Soil investigation, Construction of OHR - 50 Cum, within Mahishadal Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000384/2023-2024 | 1008/TD | 05/06/2023 | 900 | ZENITH CONSTRUCTION | 45.79 | 0 | 5
2428 | Tamluk Division | Haldia Sub-Division | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-II) [Bakshichak PWSS, Bamanpur PWSS, Kanchanpur PWSS & Madhyahingli PWSS] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000830/2023-2024 | 618/HSD | 21/12/2023 | 7 | SNEHASIS BERA | 0.83 | 0 | 100
2429 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000116/2023-2024 | 80/TD | 05/01/2024 | 0 | Resource Division | 1.53 | 0 | 0
2430 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000328/2022-2023 | 2988/TD | 27/02/2023 | 0 | Resource Division | 4.55 | 0 | 0
2431 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, road restoration for distribution pipe line ( for FHTC) & Accommodate FHTC (172 Nos) under JJM with allied work for KANPUR (Zone-III) PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000315/2024-2025 | 3182/TD | 30/09/2024 | 40 | MAITY CONSTRUCTION | 91.37 | 0 | 0
2432 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kanpur Water Supply Scheme (Zone-III) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000457/2022-2023 | 1856/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.22 | 100
2433 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000035/2023-2024 | 2083/TD | 28/08/2023 | 0 | Resource Division | 13.95 | 0 | 0
2434 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000107/2023-2024 | 3010/TD | 29/11/2023 | 0 | Resource Division | 0.61 | 0 | 0
2435 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 300 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000170/2022-2023 | 784/TD | 12/07/2022 | 25 | JASODA ENTERPRISE | 63.98 | 63.98 | 100
2436 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 220 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-D) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000173/2022-2023 | 785/TD | 12/07/2022 | 1171 | ABHIJIT BERA | 45.02 | 41.98 | 100
2437 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 67 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-E) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000174/2022-2023 | 786/TD | 12/07/2022 | 15 | KAMAL KUMAR BERA | 9.5 | 9.49 | 100
2438 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 217 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-F) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000176/2022-2023 | 787/TD | 12/07/2022 | 1071 | PARIA ENTERPRISE | 42.11 | 34.27 | 100
2439 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 112 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-G) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000177/2022-2023 | 788/TD | 12/07/2022 | 15 | LAKSHMI NARAYAN ENTERPRISE | 19.61 | 19.61 | 100
2440 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 198 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-H) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000178/2022-2023 | 789/TD | 12/07/2022 | 1104 | SUBHENDU HAZRA | 39.49 | 29.43 | 75
2441 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 85 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-J) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000179/2022-2023 | 790/TD | 12/07/2022 | 15 | GIRI ENTERPRISE | 20.05 | 16.08 | 70
2442 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 60 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-K) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000180/2022-2023 | 791/TD | 12/07/2022 | 15 | M/S BLUE BIRD | 10.57 | 7.28 | 80
2443 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 200 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-L) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000181/2022-2023 | 792/TD | 12/07/2022 | 20 | AHINDRA BARIK | 44.27 | 0 | 0
2444 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 69 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-N) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000182/2022-2023 | 793/TD | 12/07/2022 | 15 | GITA ENTERPRISE | 8.33 | 4.78 | 75
2445 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 68 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-O) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000183/2022-2023 | 794/TD | 12/07/2022 | 15 | S.A. ENTERPRISE | 9.73 | 0 | 0
2446 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-P) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000184/2022-2023 | 795/TD | 12/07/2022 | 998 | HYDROTECH ASSOCIATES | 9.05 | 4.57 | 98
2447 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 66 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-Q) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000185/2022-2023 | 796/TD | 12/07/2022 | 969 | SUSANTA KUMAR KAR | 9.24 | 6.88 | 99
2448 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 65 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Part-R) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000186/2022-2023 | 797/TD | 12/07/2022 | 1034 | DEBABRATA DAS | 9.59 | 6.14 | 100
2449 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 81 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-I) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000209/2022-2023 | 861/TD | 21/07/2022 | 15 | R K CONSTRUCTION | 11.52 | 6.6 | 75
2450 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 1410 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000261/2022-2023 | 1078/TD | 23/08/2022 | 45 | SWADHIN KUMAR CHAKRABORTY | 241.76 | 67.26 | 95
2451 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 70 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-T) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000273/2022-2023 | 1083/TD | 24/08/2022 | 15 | GITA ENTERPRISE | 8.99 | 4.96 | 80
2452 | Tamluk Division | Haldia Electrical Sub-Division | Retrofitting to accommodate of 99 nos FHTC with laying of Distribution pipe line by HDPE pipes with allied works of Khejuri Zone-I & its adjoining mouzas W/S Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(Part-U) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000274/2022-2023 | 1084/TD | 24/08/2022 | 15 | SUBHRANGSHU SEKHAR GIRI | 7.86 | 2.73 | 70
2453 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 150mm, 200mm & 250mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000361/2022-2023 | 1285/TD | 12/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.37 | 4.37 | 100
2454 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 80 mm dia Sluice Valve for Augmentation of Khejuri Zone-I Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-C) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000362/2022-2023 | 1286/TD | 12/09/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.79 | 3.79 | 100
2455 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 100 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-B) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000363/2022-2023 | 1296/TD | 13/09/2022 | 15 | NANDY UDYOG | 3.62 | 3.62 | 100
2456 | Tamluk Division | Haldia Electrical Sub-Division | Supply & Delivery 125 mm dia Sluice Valve for Augmentation of Khejuri Zone-I & Zone-II Piped W/S Scheme of Khejuri-II Block within Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. (Part-A) (Supply at Mukutshila Store) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000364/2022-2023 | 597 / CSD | 06/09/2022 | 15 | ABHIJIT BERA | 2.46 | 2.46 | 100
2457 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Khejuri Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000438/2021-2022 | 1519/TD | 07/01/2022 | 20 | ROY CHOWDHURY ASSOCIATES | 4.96 | 4.92 | 100
2458 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000041/2022-2023 | 827/TD | 15/07/2022 | 0 | Resource Division | 210.14 | 0 | 0
2459 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000075/2022-2023 | 1258/TD | 12/09/2022 | 0 | Resource Division | 31.77 | 0 | 0
2460 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, with allied works of MANDARMANI & its adjoining mouzas W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. (Phase-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000342/2023-2024 | 842/TD | 31/05/2023 | 40 | DILIP KUMAR GHOSH | 94.7 | 0 | 0
2461 | Tamluk Division | Digha Sub-Division | Pipe crossing for laying Distribution pipe line to provide FHTC (9 nos.) of Mondarmoni W/S Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (NP- 8 - 6, NP- 48 - 50, NP-50 - 52) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000373/2023-2024 | 1010/TD | 05/06/2023 | 20 | UNIQUE AGENCY | 7.52 | 7.52 | 100
2462 | Tamluk Division | Digha Sub-Division | Sinking of 250mm. X 150mm dia. X 250 mtr. Deep tube well by direct rotary rig method for 3rd Tubewell at Ramnagar-II Block of Mandarmoni Water Supply Scheme under Digha Sub-Division of Tamluk Division,PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000564/2023-2024 | 2050/TD | 25/08/2023 | 401 | PADMA ENGINEERING CO. | 14.21 | 0 | 100
2463 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, Laying rising main pipe line & Accommodate FHTC (176 nos) under JJM with allied work for Palduhi PWSS within Ramnagar -II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000302/2023-2024 | 599/TD | 17/05/2023 | 45 | BASANTA KUMAR MAITY | 61.68 | 0 | 45
2464 | Tamluk Division | Haldia Sub-Division | Way Leave permission from South Eastern Railway for Lakshya PWSS for Application ID-SER-KGP-2023-WL-66 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01827/2023-2024 | BP-2023-24-821 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.52 | 0 | 0
2465 | Tamluk Division | Haldia Sub-Division | Laying of Distribution pipe line for FHTC (920 nos), Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Lakshya & its adjoining mouzas Water Supply Scheme within Mahisadal Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000124/2023-2024 | 254/TD | 19/04/2023 | 30 | HARIPADA PATTANAYAK | 64.14 | 0 | 0
2466 | Tamluk Division | Tamluk Sadar Sub-Division | Balance work for retrofitting to accommodate FHTC (545 Nos) under JJM in Surface water Based Water Supply Scheme for Zone-VII Block - Kolaghat in the District of Purba Medinipur.(Phase-III) | Assistant Engineer | Junior Engineer | ORD/000120/2023-2024 | 251/TD | 19/04/2023 | 25 | MRITYUNJOY PARIA | 32.97 | 27.83 | 100
2467 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-V) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000498/2022-2023 | 1934/TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.3 | 100
2468 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 321 Nos) under JJM with allied work for SANKARPUR (Zone-V) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000507/2023-2024 | 1729/TD | 31/07/2023 | 936 | ONKAR ENTERPRISE | 194.4 | 0 | 55
2469 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-V PWSS at Ramnagar - I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000866/2023-2024 | 189/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2470 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000046/2023-2024 | 2069/TD | 28/08/2023 | 0 | Resource Division | 14.56 | 0 | 0
2471 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000097/2023-2024 | 3000/TD | 29/11/2023 | 0 | Resource Division | 1.98 | 0 | 0
2472 | Tamluk Division | Digha Sub-Division | Land Developing at Head Work site & 2nd Tube well site for Augmentation of Bathuary (Zone-II) Water Supply Scheme within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000297/2024-2025 | 3066/TD | 19/09/2024 | 20 | GHOSH ENTERPRISE | 9.46 | 0 | 100
2473 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000461/2022-2023 | 1860./TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 3.1 | 100
2474 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (24 nos) under JJM with allied work for Bathuari (Zone-II) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000524/2023-2024 | 1760/TD | 01/08/2023 | 853 | ARABINDA GHOSH | 294.32 | 0 | 50
2475 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000048/2023-2024 | 2071/TD | 28/08/2023 | 0 | Resource Division | 15.21 | 0 | 0
2476 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000101/2023-2024 | 3004/TD | 29/11/2023 | 0 | Resource Division | 0.07 | 0 | 0
2477 | Tamluk Division | Digha Sub-Division | Additional boundary wall, repairing & renovation of Switch Room, existing boundary wall, OHR 250 cum. capacity 20 m height, & Accommodate FHTC (105 Nos) under JJM with allied work for Digha Augmentation (Western Zone ) Water Supply Scheme under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000365/2024-2025 | 3355/TD | 23/10/2024 | 135 | SAHA CONSTRUCTION & CO | 31.05 | 0 | 100
2478 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Digha Water Supply Scheme (Western Zone) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000443/2021-2022 | .1652/TD | 20/01/2022 | 20 | HORIZEN | 3.2 | 3.15 | 100
2479 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (782 nos) under JJM with allied work for Digha Augmentation (Western Zone) PWSS within Ramnagar-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000484/2023-2024 | 1569/TD | 19/07/2023 | 1073 | GUHA CONSTRUCTION | 355.55 | 0 | 16
2480 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000038/2023-2024 | 2065/TD | 28/08/2023 | 0 | Resource Division | 29.47 | 0 | 0
2481 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000063/2023-2024 | 2639/TD | 13/10/2023 | 0 | Resource Division | 4.82 | 0 | 0
2482 | Tamluk Division | Contai Sub-Division | Withdrawing and Relaying of different dia D.I pipe line at Contai Saline Area Zone-IV PART-III Water Supply Scheme due to Widening and Strengthening along existing alignment of Contai-Rasulpur Road under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000114/2024-2025 | 1907/TD | 07/06/2024 | 25 | TARUN KHATUA | 43.11 | 0 | 0
2483 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1 and Head Works Boundary Wall under JJM with allied work of Contai Saline Area Zone-IV Part-III PWSS within Contai-II(Deshpran) Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000293/2024-2025 | 3058/TD | 19/09/2024 | 40 | SOUMEN KUMAR GHOSH | 29.17 | 0 | 100
2484 | Tamluk Division | Contai Sub-Division | Repairing of Switch Room cum Chlorin Room at 2nd TW site for Augmentation of Contai Saline Area Zoner-IV Part-III Water Supply Scheme within Deshpran Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000370/2024-2025 | 3399/TD | 28/10/2024 | 30 | SUBRATA KUMAR BERA | 1.8 | 0 | 0
2485 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (1427 nos) under JJM with allied work for Augmentation of Contai Saline Area Zone-IV PART-III PWSS in Deshapran Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000405/2023-2024 | 1091/TD | 08/06/2023 | 929 | SUJATA CONSTRUCTION | 214.81 | 0 | 50
2486 | Tamluk Division | Contai Sub-Division | Relaying of Damaged Distribution Pipe Line due to Paka Drain work by PWD with allied Works for Contai Saline Area Zone-IV Water Supply Scheme within Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000407/2024-2025 | 3468/TD | 06/11/2024 | 20 | FARID UDDIN AHMED | 3.19 | 0 | 100
2487 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Contai Saline Area Water Supply Scheme (Zone-IV) under Tamluk Division, PHE Dte. [PART-III] | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000455/2022-2023 | 1855./TD | 21/11/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.23 | 100
2488 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000057/2023-2024 | 2095/TD | 29/08/2023 | 0 | Resource Division | 156.45 | 0 | 0
2489 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division.,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000061/2023-2024 | 2637/TD | 13/10/2023 | 0 | Resource Division | 8.79 | 0 | 0
2490 | Tamluk Division | Digha Sub-Division | Payment of WBSEDCL for Quotation of Shifting of 11 KV line of Bagmari Water Supply Scheme within Egra-II Block | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/01476/2023-2024 | BP-2023-24-664 | 15/12/2023 | 0 | WBSEDCL | 4.64 | 0 | 0
2491 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 100cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bagmari Water Supply Scheme within Egra-I Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000237/2023-2024 | 459/TD | 04/05/2023 | 1061 | AJIT KUMAR SOM | 241.82 | 76.67 | 70
2492 | Tamluk Division | Digha Sub-Division | Renovation & Repairing of existing pump house H/W site and 2nd TW Site of Bagmari Water Supply Scheme within Egra-I Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000449/2024-2025 | 3616/TD | 27/11/2024 | 399 | SOM CONSTRUCTION | 11.36 | 0 | 0
2493 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bagmari Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000692/2021-2022 | 1741/TD | 03/02/2022 | 20 | HORIZEN | 3.67 | 3.14 | 0
2494 | Tamluk Division | Digha Sub-Division | Instalation of display Board at different work site of Kanakpur Retrofitting PWSS in Potashpur - I Block, Argoal, Bagmari, Pratapdighi Retrofitting PWSS in Potashpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001188/2023-2024 | 2336/CSD | 29/12/2023 | 15 | THE GODFATHER TRADING COMPANY | 0.83 | 0 | 100
2495 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000059/2023-2024 | 2635/TD | 13/10/2023 | 0 | Resource Division | 5.72 | 0 | 0
2496 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000105/2023-2024 | 3008/TD | 29/11/2023 | 0 | Resource Division | 5.72 | 0 | 0
2497 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site( Mouza- Bagmari ,J.L. No-116, Plot No- 189), for Bagmari Water Supply Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000067/2023-2024 | 138/TD | 10/04/2023 | 60 | GRAND CONSTRUCTION | 3.99 | 0 | 100
2498 | Tamluk Division | Contai Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 15.62 | 100
2499 | Tamluk Division | Contai Sub-Division | Laying of Distribution pipe line, Rising main pipe line with allied works of Bagmari & its adjoining mouzas Water Supply Scheme within Patashpur-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district.(PHASE-III) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000530/2023-2024 | 1825/TD | 07/08/2023 | 576 | DAS ENTERPRISE | 63.16 | 0 | 100
2500 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at SRIKANTHA PWSS at MOYNA Block under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000028/2025-2026 | 07/RWS/TSD | 04/04/2025 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2501 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000013/2024-2025 | 1571/TD | 23/04/2024 | 0 | Resource Division | 15.86 | 0 | 0
2502 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000172/2022-2023 | 2436/TD | 16/01/2023 | 0 | Resource Division | 23.09 | 0 | 0
2503 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3103 Nos) For 2 nos Pipe Water Supply Scheme including two years Operation & Maintainance for BHUINAJIBAR and DEULI within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000400/2023-2024 | 1068/TD | 08/06/2023 | 934 | TAPAS SANTRA | 1110.29 | 253.43 | 85
2504 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000130/2023-2024 | 84/TD | 05/01/2024 | 0 | Resource Division | 9.77 | 0 | 0
2505 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000262/2022-2023 | 2689/TD | 06/02/2023 | 0 | Resource Division | 43.3 | 0 | 0
2506 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Chandra Chak PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000872/2023-2024 | 194/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2507 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000015/2024-2025 | 1573/TD | 23/04/2024 | 0 | Resource Division | 12.71 | 0 | 0
2508 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000187/2022-2023 | 2427/TD | 16/01/2023 | 0 | Resource Division | 41.87 | 0 | 0
2509 | Tamluk Division |  | Functional Household Tap Connection to the 172 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-C [(Bara Rasulpur(635)] |  |  | ORD/000168/2020-2021 | 2718/TD | 21/01/2021 | 20 | SUKOMAL BERA | 8.15 | 1.3 | 100
2510 | Tamluk Division |  | Functional Household Tap Connection to the 355 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-B [(Aluan(78 ) part,Paschimbatya(79)] |  |  | ORD/000169/2020-2021 | 2719/TD | 21/01/2021 | 25 | MRINAL KANTI PRADHAN | 16.73 | 0.64 | 100
2511 | Tamluk Division |  | Functional Household Tap Connection to the 190 nos. Household of Paschimbetya W/S Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Within Purba Medinipur District. PART-A [(Balagerya(77 ) ,Aluan(78) ,Part)] |  |  | ORD/000170/2020-2021 | 2720/TD | 21/01/2021 | 20 | SUBRATA KUMAR BERA | 9 | 1.52 | 100
2512 | Tamluk Division |  | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000471/2021-2022 | 329/W | 08/10/2021 | 0 | MRINAL KANTI PRADHAN | 2.08 | 0 | 0
2513 | Tamluk Division |  | Retrofitting to accomodate FHTC 172 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001057/2020-2021 | 823/W | 26/02/2021 | 0 | SUKOMAL BERA | 6.61 | 0 | 0
2514 | Tamluk Division |  | Functional Household Tap Connection to the 190 Nos. Household of Paschimbetya W/S Scheme within Contai - III Block Tamluk Division, PHE Dte. (PART-A) |  |  | VCH/001194/2020-2021 | 843/W | 08/03/2021 | 0 | SUBRATA KUMAR BERA | 7.26 | 0 | 0
2515 | Tamluk Division |  | Retrofitting to accomodate FHTC 355 Nos. connection under JJM Paschim Betya W/S Scheme within Contai - III Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001218/2020-2021 | 967/W | 22/03/2021 | 0 | MRINAL KANTI PRADHAN | 14.01 | 0 | 0
2516 | Tamluk Division | Contai Sub-Division | Sinking Tube well ,Construction of Pump House ,150 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (958 nos), Including 2 years of Operation maintance under JJM with allied work of BATIPUR PWSS within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000404/2023-2024 | 1092/TD | 08/06/2023 | 1020 | SUJATA CONSTRUCTION | 368.76 | 0 | 30
2517 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000076/2024-2025 | 2950/TD | 12/09/2024 | 0 | Resource Division | 5.9 | 0 | 0
2518 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000249/2022-2023 | 2717/TD | 06/02/2023 | 0 | Resource Division | 42.25 | 0 | 0
2519 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Erenda PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000491/2023-2024 | 1592/TD | 21/07/2023 | 856 | MUKHERJEE CONSTRUCTION | 504.12 | 0 | 62
2520 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000254/2022-2023 | 2713/TD | 06/02/2023 | 0 | Resource Division | 29.89 | 0 | 0
2521 | Tamluk Division | Digha Sub-Division | Leftout pipeline & Drum Sheet Walling to accommodate FHTC under JJM of Tajpur Water Supply Scheme within Egra II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000068/2025-2026 | 1167/TD | 22/04/2025 | 40 | R CONSTRUCTION | 103.69 | 0 | 0
2522 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 400 cum RCC OHR at Tajpur PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000160/2024-2025 | 2072/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2523 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall soil investigation , 400 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2785 nos) under JJM with allied work for Tajpur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000423/2023-2024 | 1415/TD | 12/07/2023 | 994 | FIROZ KHAN | 607.63 | 0 | 70
2524 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000251/2022-2023 | 2715/TD | 06/02/2023 | 0 | Resource Division | 32.5 | 0 | 0
2525 | Tamluk Division | Tamluk Sadar Sub-Division | payment for Wayleave plan & survey charges SER-KGP-2024-WL-95 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00487/2024-2025 | BP-2024-25-188 | 14/06/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.11 | 0 | 0
2526 | Tamluk Division | Tamluk Sadar Sub-Division | Payment of Wayleave facility charges(Application ID-SER-KGP-2024-WL-95) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | BILL/00691/2024-2025 | BP-2024-25-298 | 30/07/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.08 | 0 | 0
2527 | Tamluk Division | Tamluk Sadar Sub-Division | M.S. Structure for canel crossing for laying 90 mm dia pipe of Harasankar Khamarchak PWSS of Tamluk Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Nodal Point 242-243, 314-315,356-343 & 88A-128 ) Canal Length- = 14.00 mtr. Number of crossing -4 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000331/2024-2025 | 3290/TD | 05/10/2024 | 30 | BAGLAMUKHI SECURITY SERVICE | 9.39 | 0 | 100
2528 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1435 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Harashankar Khamarchak PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000372/2023-2024 | 907/TD | 01/06/2023 | 970 | HARIPADA PATTANAYAK | 371.31 | 0 | 50
2529 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000299/2022-2023 | 3007/TD | 27/02/2023 | 0 | Resource Division | 18.84 | 0 | 0
2530 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Kiarana PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000870/2023-2024 | 192/TD | 10/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2531 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000009/2024-2025 | 1567/TD | 23/04/2024 | 0 | Resource Division | 8.77 | 0 | 0
2532 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000178/2022-2023 | 2433/TD | 16/01/2023 | 0 | Resource Division | 36.03 | 0 | 0
2533 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Bathuary PWSS Block-Egra-II in the District of Purba Medinipur. |  | Junior Engineer | ORD/000135/2020-2021 | 2661/TD | 11/01/2021 | 60 | SATYABRATA BHAUMIK | 96.25 | 53.35 | 100
2534 | Tamluk Division | Digha Sub-Division | Continuation work order for Charges for Entry of Household Data through JJM website of 33 (Thirty three) Nos. Aug. Piped Water Supply Scheme within different Sub-Division under Tamluk Division, PHE Dte. |  | Junior Engineer | ORD/001331/2023-2024 | 895/TD | 07/03/2024 | 300 | MISHRA ENTERPRISE | 9.53 | 0 | 65
2535 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC under JJM Bathuari W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/000226/2021-2022 | 141/W | 22/07/2021 | 0 | SATYABRATA BHAUMIK | 22.86 | 0 | 0
2536 | Tamluk Division | Digha Sub-Division | Retrofitting to accomodate FHTC under JJM Bathuari W/S Scheme within Egra - II Dev. Block under Tamluk Division, PHE Dte. |  | Junior Engineer | VCH/001235/2020-2021 | 981/W | 25/03/2021 | 0 | SATYABRATA BHAUMIK | 20.03 | 0 | 0
2537 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Badhia PWSS Block Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000126/2020-2021 | 2636/TD | 05/01/2021 | 60 | AJIT KUMAR SOM | 96.85 | 21.21 | 100
2538 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/000392/2021-2022 | 230/W | 07/09/2021 | 0 | AJIT KUMAR SOM | 21.1 | 0 | 0
2539 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Badhia W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001246/2020-2021 | 978/W | 26/03/2021 | 0 | AJIT KUMAR SOM | 54.53 | 0 | 0
2540 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-VII(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000195/2020-2021 | 2779/TD | 29/01/2021 | 120 | TARUN KOLEY | 253.33 | 506.67 | 100
2541 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-III(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000196/2020-2021 | 2780/TD | 29/01/2021 | 120 | JAYANTA KUMAR MONDAL | 259.53 | 512.89 | 100
2542 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-V(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000198/2020-2021 | 2785/TD | 01/02/2021 | 120 | M/S EL-CON | 241.65 | 450.27 | 100
2543 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface Water Based Water Supply Scheme for Zone-I (Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000209/2020-2021 | 2821/TD | 05/02/2021 | 100 | M/S A.R. ENTERPRISE | 216.86 | 433.43 | 100
2544 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC under JJM in Surface water Based Water Supply Scheme for Zone-IV(Balance Work) Block-Kolaghat in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000240/2020-2021 | 2845/TD | 08/02/2021 | 120 | CONCORD ENGINEERING | 267.73 | 375.13 | 100
2545 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Chandanpur PWSS Block Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000115/2020-2021 | 2481/TD | 21/12/2020 | 60 | TAPAS SANTRA | 96.74 | 2.45 | 100
2546 | Tamluk Division |  | Preparation and submission of Revised Detailed Project Report for Retrofitting to accommodate FHTC under JJM in CHANDANPUR piped water supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division,Purba Medinipur District. |  |  | ORD/000135/2025-2026 | 147/DSD | 14/05/2025 | 7 | ASTER CONSULTANCY | 2.66 | 0 | 0
2547 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Chandanpur W/S Scheme |  |  | VCH/000892/2020-2021 | 827/W | 03/03/2021 | 0 | TAPAS SANTRA | 16.22 | 0 | 0
2548 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Chandanpur W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001036/2020-2021 | 714/W | 09/02/2021 | 0 | TAPAS SANTRA | 78 | 0 | 0
2549 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Silampur PWSS Block -Contai-I in the District of Purba Medinipur. |  |  | ORD/000245/2020-2021 | 2876/TD | 11/02/2021 | 30 | BASANTA KUMAR MAITY | 77.79 | 21.22 | 100
2550 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Silampur PWSS within Contai ¿I Block under Tamluk Division, PHE Dte. |  |  | VCH/001131/2020-2021 |  | 17/03/2021 | 0 | BASANTA KUMAR MAITY | 55.45 | 0 | 0
2551 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Silampur W/S Scheme within Contai - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001260/2020-2021 | 1092/W | 30/03/2021 | 0 | BASANTA KUMAR MAITY | 55.45 | 0 | 0
2552 | Tamluk Division |  | Retrofitting to accommodate FHTC (520 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Baishnab Chak (JL-136) - (Baishnab Chak Uttar Paschim Para, Baishnab Chak Purba Dakshin Para &Gholepukuria [JL134(P)] - (Jaykhali Paschim Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur. ,PART-A |  |  | ORD/000187/2020-2021 | 2753/TD | 27/01/2021 | 25 | ZENITH CONSTRUCTION | 26.93 | 0 | 100
2553 | Tamluk Division |  | Retrofitting to accommodate FHTC (480 nos) under JJM in Gholepukuria PWSS (Zone-II) (Phase -II) within Gholepukuria [JL-134(P)] - (Purba Dakshin Para & Madhya Jana Para) Nandigram-II dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.PART-B |  |  | ORD/000188/2020-2021 | 2754/TD | 27/01/2021 | 25 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.38 | 0 | 100
2554 | Tamluk Division |  | Retrofitting to accomodate FHTC 520 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-A) |  |  | VCH/000097/2021-2022 | BP-2021-22-44 | 29/07/2021 | 0 | ZENITH CONSTRUCTION | 3.86 | 0 | 0
2555 | Tamluk Division |  | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/000200/2021-2022 | BP-2021-22-59 | 13/08/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.49 | 0 | 0
2556 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001105/2020-2021 | 1103/W | 30/03/2021 | 0 | ZENITH CONSTRUCTION | 23.02 | 0 | 0
2557 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Gholpukuria - II W/S Scheme under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/001107/2020-2021 |  | 12/03/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0
2558 | Tamluk Division |  | Retrofitting to accomodate FHTC 480 Nos. connection under JJM Gholpukuria Zone - II W/S Scheme (Phase - II) within Nandigram - II Dev. Block under Tamluk Division, PHE Dte. (Part-B) |  |  | VCH/001257/2020-2021 | 1104/W | 30/03/2021 | 0 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.88 | 0 | 0
2559 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Alinan Zone-I PWSS Block -Sahid Matangini in the District of Purba Medinipur. |  |  | ORD/000207/2020-2021 | 2819/TD | 05/02/2021 | 45 | TAPAS SANTRA | 97.45 | 193.36 | 100
2560 | Tamluk Division |  | Retrofitting to accommodate (175) nos FHTC under JJM of Balarampur & Joyrampur village in Alinan Zone-I PWSS Block- Sahid Matangini under Tamluk Sub Division of Tamluk Division, PHE Dte within Purba Medinipur District . |  |  | ORD/000332/2021-2022 | 1717/TD | 01/02/2022 | 20 | MUKHERJEE ENTERPRISE | 10.37 | 0 | 100
2561 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Kanakpur PWSS Block -Potashpur-I in the District of Purba Medinipur. |  |  | ORD/000203/2020-2021 | 2801/TD | 04/02/2021 | 45 | SRIMANTA KUMAR MAITY | 114.41 | 41.4 | 100
2562 | Tamluk Division |  | Providing Balance FHTC with allied works of Kanakpur mouzas under Kanakpur water supply scheme of Contai Sub Division under Tamluk Division, PHE Dte. Purba Medinipur. |  |  | ORD/000456/2022-2023 | 1301/TD | 13/09/2022 | 30 | THE GODFATHER TRADING COMPANY | 3.52 | 3.51 | 100
2563 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM in Kanakpur Piped Water Supply Scheme |  |  | VCH/001114/2020-2021 | 1085/W | 30/03/2021 | 0 | SRIMANTA KUMAR MAITY | 41.89 | 0 | 0
2564 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia. Sluice Valve for Augmentation of Anurai Water Supply Scheme under Contai Sub-Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000087/2022-2023 | 426/TD | 27/05/2022 | 15 | PARTHA CONSTRUCTION | 4.59 | 4.59 | 100
2565 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anurai Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000175/2021-2022 | 1184/TD | 02/12/2021 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 8.21 | 6.31 | 100
2566 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Additional Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000265/2022-2023 | 1088/TD | 25/08/2022 | 40 | ABHIJIT BERA | 5.47 | 5.31 | 100
2567 | Tamluk Division | Contai Sub-Division | Repairing of OHR, Pump House no 1, Pump House No. 2 under JJM with allied work of Anurai PWSS within Deshpran Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000278/2024-2025 | 2906/TD | 10/09/2024 | 40 | RAI CONSTRUCTION | 12.9 | 0 | 100
2568 | Tamluk Division | Contai Sub-Division | Augmentation of Anurai Water Supply Scheme by Providing Laying Distribution System and FHTC in In Contai-III & Deshpran Block Of in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000301/2021-2022 | 1639/TD | 19/01/2022 | 1415 | MAHAVIR PUMPS MFG. PVT. LTD. | 391.92 | 326.22 | 90
2569 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Additiona Tube Well (3rd Tube Well) site for Anurai Water Supply Scheme within Deshpran & Contai - III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000329/2022-2023 | 843/TD | 20/07/2022 | 30 | ABHIJIT BERA | 3.63 | 3.57 | 100
2570 | Tamluk Division | Contai Sub-Division | Supply & delivery D.I. Specials for Rising main and other allied works for Augmentation of Anurai W/S Scheme within Contai - II & Contai-III Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000401/2022-2023 | 690 / CSD | 22/09/2022 | 15 | SUBRATA KUMAR BERA | 0.76 | 0 | 100
2571 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head work site for Anurai W/S Scheme within Deshpran & Contai -III Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Lenght-136 Mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000477/2023-2024 | 1535/TD | 18/07/2023 | 410 | DEBABRATA DAS | 21.39 | 0 | 100
2572 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 1st Tube well Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1407) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000495/2021-2022 | 1991/TD | 07/03/2022 | 21 | AQUATECH ENGINEER | 12.17 | 11.65 | 100
2573 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method at 3rd Tube well (Additional) Site of Anurai Water Supply Scheme (Mouza - Anurai, JL No. - 439, Plot No. - 1289) within Contai-III & Deshpran Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000497/2021-2022 | 1992/TD | 07/03/2022 | 21 | AQUATECH ENGINEER | 12.17 | 11.85 | 100
2574 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Anurai- 1 no, Bhajachauli- 1 no, Dhanghara- 1 no, Basudebberiya- 1 no, Shankarpur- 1 no, Mukutshila Zone-II- 1 no. & Chandibhetti- 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000510/2022-2023 | 810 / CSD | 21/10/2022 | 15 | SAURAV HAZRA | 0.81 | 0.81 | 100
2575 | Tamluk Division | Contai Sub-Division | Renovation work of Spiral staircase and related works for R.C.C. Over Head Reservoir of capacity 250 Cum at Anurai Mouza within Anurai W/S Scheme under Contai Sub-Division of Tamluk Division, P.H.E.Dte. Dist. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000602/2021-2022 | 493 / CSD | 16/11/2021 | 21 | SUBRATA KUMAR BERA | 2.43 | 2.26 | 100
2576 | Tamluk Division | Contai Sub-Division | Supply and Delivery of Different dia Sluice Valves for Anurai Water Supply Scheme in the District of Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000888/2022-2023 | 441 / CSD | 20/03/2023 | 15 | KAMAL KUMAR BERA | 0.95 | 0.95 | 0
2577 | Tamluk Division | Contai Sub-Division | Land Filling & Construction of Approch Road for 3rd TW site of Anurai W/S Scheme within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000904/2022-2023 | 307/CSD | 27/02/2023 | 15 | ABHIJIT BERA | 1.25 | 1.23 | 0
2578 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000023/2021-2022 | 1265/TD | 13/12/2021 | 0 | Resource Division | 42.96 | 0 | 0
2579 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000058/2021-2022 | 1729/TD | 02/02/2022 | 0 | Resource Division | 13.95 | 0 | 0
2580 | Tamluk Division |  | Retrofitting to accomodate FHTC (1897 nos.) under JJM in Dona Zone-I PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) |  |  | ORD/000013/2021-2022 | 689/TD | 10/09/2021 | 60 | ARABINDA GHOSH | 88.68 | 0 | 100
2581 | Tamluk Division |  | Retrofitting to accomodate FHTC 1125 Nos. connection under JJM under Dona Zone - I W/S Scheme within Moyna Block under Tamluk Division, PHE Dte. (Phase - I) |  |  | VCH/000435/2021-2022 | BP-2021-22-148 | 09/11/2021 | 0 | ARABINDA GHOSH | 21.94 | 0 | 0
2582 | Tamluk Division |  | Retrofitting to accomodate FHTC (1897 nos.) under JJM in Dona Zone-I PWSS (Balance Work) Block - Moyna under Tamluk Sub-Division of Tamluk Division, PHE Dte. in the District of Purba Medinipur.(Phase- II) |  |  | VCH/000996/2021-2022 | BP-2021-22-391 | 31/03/2022 | 0 | ARABINDA GHOSH | 75.2 | 0 | 0
2583 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Bagmari PWSS Block- Potashpur-II in the District of Purba Medinipur.(Phase-II) |  |  | ORD/000020/2021-2022 | 83/TD | 11/05/2021 | 30 | DAS ENTERPRISE | 88.69 | 115.43 | 100
2584 | Tamluk Division |  | Retrofitting to accommodate FHTC under JJM in Ranisai PWSS Block Ramnagar-I in the District of Purba Medinipur. |  |  | ORD/000116/2020-2021 | 2480/TD | 21/12/2020 | 60 | TARUN KOLEY | 94.35 | 0 | 100
2585 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM of Ranisai W/S Scheme |  |  | VCH/000891/2020-2021 | 828/W | 02/03/2021 | 0 | TARUN KOLEY | 4.71 | 0 | 0
2586 | Tamluk Division |  | Retrofitting to accomodate FHTC under JJM Ranisai W/S Scheme within Ramnagar - I Dev. Block under Tamluk Division, PHE Dte. |  |  | VCH/001034/2020-2021 | 712/W | 09/02/2021 | 0 | TARUN KOLEY | 80 | 0 | 0
2587 | Tamluk Division | Contai Sub-Division | Providing FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-01) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000049/2022-2023 | 287/TD | 05/05/2022 | 60 | DAS CONSTRUCTION | 124.25 | 57.69 | 95
2588 | Tamluk Division | Contai Sub-Division | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000084/2022-2023 | 437-A/TD | 30/05/2022 | 20 | SSPR VALVE MANUFACTURING PVT. LTD. | 7.88 | 7.88 | 100
2589 | Tamluk Division | Contai Sub-Division | Supply and Delivery of different dia. Sluice Valve for Talda piped Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000094/2022-2023 | 451/TD | 31/05/2022 | 20 | RAMASISH ENTERPRISE | 0.24 | 0.24 | 100
2590 | Tamluk Division | Contai Sub-Division | Supply & Delivery of different dia Sluice Valve for Augmentation of Talda,Murisai & Anurai Water Supply Scheme under Contai Sub- Division, of Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000112/2022-2023 | 278 / CSD | 14/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT. LTD. | 2.34 | 2.34 | 100
2591 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 3rd Tubewell (Mouza - Gonara, JL No. - 187, Plot No. -41)of Talda Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000118/2022-2023 | 613/TD | 21/06/2022 | 21 | M/S BISWANATH CONSTRUCTION | 13.38 | 0 | 100
2592 | Tamluk Division | Contai Sub-Division | Construction of Pump House & Boundary Wall and others allied works for 3rd Tube well site under Talda Water Supply Scheme (Augmentation) in Contai III Block within Contai Sub Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000268/2024-2025 | 2897/TD | 10/09/2024 | 40 | BISWA NIRMAN ENTERPRISE. | 11.34 | 0 | 0
2593 | Tamluk Division | Contai Sub-Division | Repairing Of Pump House ( House No-I & II) and Boundary Wall of Pump House No- II under Augmentation of Talda Water Supply Scheme within Contai- III Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000280/2023-2024 | 485/TD | 10/05/2023 | 30 | M/S SREE DURGA ENTERPRISE | 3.65 | 0 | 100
2594 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Talda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000318/2021-2022 | 1611/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.3 | 3.97 | 100
2595 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000361/2021-2022 | 1816/TD | 11/02/2022 | 45 | M/S SREE DURGA ENTERPRISE | 95.89 | 89.58 | 100
2596 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000377/2021-2022 | 1817/TD | 11/02/2022 | 40 | AJIT KUMAR SOM | 77.52 | 75.76 | 100
2597 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000378/2021-2022 | 1818/TD | 11/02/2022 | 40 | GIRI CONSTRUCTION | 58.08 | 51.27 | 100
2598 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000379/2021-2022 | 1819/TD | 11/02/2022 | 20 | SUBHENDU HAZRA | 24.07 | 23.63 | 100
2599 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000380/2021-2022 | 1820/TD | 11/02/2022 | 20 | M/S. NEW DINDA ENTERPRISE | 23.24 | 23.09 | 100
2600 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. . (PART-G) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000381/2021-2022 | 1821/TD | 11/02/2022 | 20 | BADAL CHANDRA GOLE | 19.35 | 19.13 | 100
2601 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-H) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000382/2021-2022 | 1822/TD | 11/02/2022 | 20 | GIRI ENTERPRISE | 19.36 | 19.19 | 100
2602 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART-I) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000383/2021-2022 | 1823/TD | 11/02/2022 | 20 | SUBRATA KUMAR BERA | 18.89 | 18.64 | 100
2603 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- J) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000384/2021-2022 | 1824/TD | 11/02/2022 | 20 | DHANANJOY DAS | 19.35 | 16.86 | 100
2604 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- K) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000385/2021-2022 | 1825/TD | 11/02/2022 | 20 | SUKOMAL BERA | 14.52 | 14.44 | 100
2605 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District. (PART- L) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2021-2022 | 1826/TD | 11/02/2022 | 20 | ANUPAM CONSTRUCTION | 9.6 | 9.53 | 100
2606 | Tamluk Division | Contai Sub-Division | FHTC with connecting Distribution and allied works for Talda Water Supply Scheme in Contai- III Block of Purba Medinipur District.(PART- M) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000387/2021-2022 | 1827/TD | 11/02/2022 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.62 | 9.54 | 100
2607 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Talda- 1 no, Sapai- 1 no, Baghaput- 1 no & Kumirda - 1 no. PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000512/2022-2023 | 812 / CSD | 21/10/2022 | 15 | ABHIJIT BERA | 0.46 | 0.46 | 100
2608 | Tamluk Division | Contai Sub-Division | Laying Distribution System (Nodal-36-89,89-131 & 131-139A,Part) of pipe line and its allied works for Talda water supply scheme in Contai-III Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000741/2023-2024 | 3068/TD | 30/11/2023 | 25 | ACHINTA KUMAR HALDER | 10.08 | 0 | 80
2609 | Tamluk Division | Contai Sub-Division | Sinking of 250 mm x 150 mm dia x 250 mtr. deep tube well by direct rotary rig method for Replacement of 1st Tube well of Talda Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001156/2023-2024 | 607/TD | 16/02/2024 | 20 | KALPANA BUILDERS | 14.29 | 0 | 0
2610 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000062/2021-2022 | 1875/TD | 18/02/2022 | 0 | Resource Division | 17.42 | 0 | 0
2611 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000084/2021-2022 | 2190/TD | 21/03/2022 | 0 | Resource Division | 39.93 | 0 | 0
2612 | Tamluk Division | Contai Sub-Division | Supply and Delivery of CIDF Sluice Valve for laying of distribution pipe line and allied works for Augmentation of Kamarda Water Supply Scheme under Contai Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000195/2023-2024 | 305/TD | 24/04/2023 | 20 | RAMASISH ENTERPRISE | 4.15 | 4.15 | 100
2613 | Tamluk Division | Contai Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kamarda Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000321/2021-2022 | 1614/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.2 | 3.6 | 100
2614 | Tamluk Division | Contai Sub-Division | Instalation of display Board at different work site of Augmentation of Kamarda-1 no, Sherkhanchak Zone-I-1 no, Sherkhanchak Zone-II-1 no, Majna-1 no, Madhakhali Zone-I-1 no , Madhakhali Zone-I-1 no, Arjunnagar-1 no & Nijkasba-1 no PWSS within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000508/2022-2023 | 808 / CSD | 21/10/2022 | 15 | ABHIJIT BERA | 0.93 | 0.93 | 100
2615 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 0 | 100
2616 | Tamluk Division | Contai Sub-Division | Name of Work: i) Construction of Boundary Wall (as per Departmental Design & Drawing) at 3rd TW site for Augmentation of Kamarda PWSS within Khejuri -I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-60.00 mtr.) ii) Rising main and other allied works Augmentation of Kamarda W/S Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. iii) construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at 3rd TW site for Kamarda W/S Scheme within Khejuri - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. (For Low Land). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000867/2022-2023 | 3220/TD | 14/03/2023 | 880 | GIRI CONSTRUCTION | 20.1 | 0 | 70
2617 | Tamluk Division | Contai Sub-Division | Laying of Left-Out portion HDPE Pipe line of Distribution pipe line by HDPE pipes and FHTC works under Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001257/2023-2024 | 1071/TD | 16/03/2024 | 25 | TARUN KHATUA | 34.31 | 0 | 30
2618 | Tamluk Division | Contai Sub-Division | Land Development at 3rd Tube Well site of Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001294/2023-2024 | 162/CSD | 29/01/2024 | 15 | GIRI CONSTRUCTION | 0.97 | 0 | 100
2619 | Tamluk Division | Contai Sub-Division | Land Development at 3rd Tube Well site of Kamarda Water Supply Scheme within Khejuri-I Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001465/2023-2024 | 222/CSD | 06/02/2024 | 15 | GIRI CONSTRUCTION | 0.97 | 0 | 0
2620 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000019/2022-2023 | 407/TD | 25/05/2022 | 0 | Resource Division | 50.49 | 0 | 0
2621 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000079/2022-2023 | 1261/TD | 12/09/2022 | 0 | Resource Division | 19.4 | 0 | 0
2622 | Tamluk Division |  | Balance work for Retrofitting to accommodate FHTC (750 nos) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone at different nodal point under JJM in Surface water based water supply scheme for Zone-XI, Block-Kolaghat in the District of Purba Medinipur. (Phase-II) |  |  | ORD/000360/2021-2022 | 1800/TD | 08/02/2022 | 40 | TAPAS SANTRA | 92.64 | 92.89 | 100
2623 | Tamluk Division |  | Retrofitting to accommodate FHTC (Balance work) (951 nos.) and laying of left-out portion uPVC pipeline due to uncovered area of this Zone and damaged pipe line at different nodal point under JJM in Surface water based water supply scheme for Zone-III, Block-Kolaghat in the District of Purba Medinipur. (Phase-II) |  |  | ORD/000407/2021-2022 | 1907/TD | 23/02/2022 | 40 | JAYANTA KUMAR MONDAL | 82.25 | 77.04 | 100
2624 | Tamluk Division | Digha Sub-Division | Quotation money payment to WBSEDCL for Mandar Water Supply Scheme of Tube Well No. - III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | BILL/00468/2023-2024 | BP-2023-24-237 | 09/08/2023 | 0 | WBSEDCL | 3.54 | 0 | 0
2625 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line, Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Mandar & its adjoining mouzas Water Supply Scheme within RAMNAGAR -II Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000114/2023-2024 | 244/TD | 19/04/2023 | 45 | BASANTA KUMAR MAITY | 59.1 | 0 | 50
2626 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Mandar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000173/2021-2022 | 1182/TD | 02/12/2021 | 20 | HORIZEN | 2.94 | 2.94 | 100
2627 | Tamluk Division | Digha Sub-Division | Supply of C.I D.F Sluice valve for Augmentation of ground water based Mander W/S Scheme to accommodate FHTC within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000212/2022-2023 | 324/DSD | 15/07/2022 | 7 | BASANTA KUMAR MAITY | 2.86 | 2.86 | 100
2628 | Tamluk Division | Digha Sub-Division | Augmentation of ground water based Mandar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Ramnagar-II Dev. Block under Digha Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000376/2021-2022 | 1813/TD | 11/02/2022 | 180 | BASANTA KUMAR MAITY | 199.91 | 122.57 | 70
2629 | Tamluk Division | Digha Sub-Division | Valve operator (one no) in head work site at Mandar & its adjoining mouzas water supply scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division PHE Dte. (From 01.10.2024 to 03.04.2025 i.e. 185 days) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/000517/2024-2025 | 1026/DSD | 01/10/2024 | 185 | DAS ENTERPRISE. | 1.2 | 0 | 0
2630 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000019/2021-2022 | 1261/TD | 13/12/2021 | 0 | Resource Division | 5.63 | 0 | 0
2631 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | RTOR000052/2021-2022 | 1869/TD | 17/02/2022 | 0 | Resource Division | 5.31 | 0 | 0
2632 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Assistant Engineer | Junior Engineer | ORD/000006/2022-2023 | 58/TD | 05/04/2022 | 60 | BARH CONSTRUCTION | 130.82 | 119.91 | 100
2633 | Tamluk Division | Tamluk Sadar Sub-Division | Rejuvenation & Retrofitting of ground water based Paramanandapur PWSS to accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District (Part- B) | Assistant Engineer | Junior Engineer | ORD/000169/2022-2023 | 743/TD | 05/07/2022 | 60 | SATYABRATA BHAUMIK | 165 | 156.56 | 100
2634 | Tamluk Division | Tamluk Sadar Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room,Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Paramanandapur Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer | Junior Engineer | ORD/000173/2023-2024 | 330/TD | 25/04/2023 | 811 | SUDIP MANNA | 13.09 | 0 | 100
2635 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paramanandapur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2021-2022 | 1193/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 4.74 | 4.74 | 100
2636 | Tamluk Division | Tamluk Sadar Sub-Division | Augmentation of Ground Water Based Paramanandapur PWSS to Accommodate FHTC in Moyna Block under Tamluk Sub-Division of Tamluk Division in Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000727/2022-2023 | 2557/TD | 24/01/2023 | 60 | M/S. S. A. CONSTRUCTION | 41.95 | 41.3 | 100
2637 | Tamluk Division | Tamluk Sadar Sub-Division | Proposed Rejuvenation &Retrofitting of Laying Distribution System of proposed left out portion pipe line at Paramanandapur PWSS | Assistant Engineer | Junior Engineer | ORD/000830/2022-2023 | 3170/TD | 10/03/2023 | 20 | PURNA CHANDRA BARH | 7.63 | 7.46 | 100
2638 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01676/2023-2024 | BP-2023-24-737 | 29/12/2023 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 0.07 | 0 | 0
2639 | Tamluk Division | Tamluk Sadar Sub-Division | Way leave charges of South Eastern Railway Track for Application ID SER-KGP-2023-WL-58 of Erashole PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/01896/2023-2024 | BP-2023-24-853 | 08/02/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 5.38 | 0 | 0
2640 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Erasole Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000369/2021-2022 | 1646/TD | 19/01/2022 | 20 | HORIZEN | 5.37 | 5.37 | 100
2641 | Tamluk Division | Tamluk Sadar Sub-Division | Interconnection with laying of 150 mm dia,200 mm dia & 250 mm dia DI(K-9) rising main from 3rd & 4th. T/W to OHR at Erasole PWSS under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000452/2023-2024 | 1476/TD | 14/07/2023 | 843 | SAYAN MAITY | 10.15 | 0 | 100
2642 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Additional Tube well by direct rotary rig method at 4th Tube well Site of Erasol Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 230 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Kanktia Water Supply Scheme within Matangini Dev. Block under Tamluk Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site(Boosting T/W) of Bagmari Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000264/2022-2023 | 1094/TD | 25/08/2022 | 40 | AQUATECH ENGINEERS | 70.49 | 33.7 | 100
2643 | Tamluk Division | Tamluk Sadar Sub-Division | Jack Pushing of Railway Track Between NANDAKUMAR P.H. & LAVAN SATYAGARH SMARAK P.H. Railway Station on Tamluk-Digha Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of ERASOLE Piped Water Supply Scheme of 600 mm Dia MS Casing Pipe and 250 mm Dia DI (K7) Carrier Pipe within Tamluk Sub-Division under Tamluk Division, P.H.E DTE. (Total Length =48 Mtr) Nodal Point J393 to J338. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000720/2023-2024 | 2942/TD | 23/11/2023 | 20 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 68.57 | 0 | 100
2644 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & Renovation of Construction of switch Room cum Chlorine Room at OHR site and 2 nd.Tube Well site and Renovation of existing Boundary Wall at OHR site and 2 nd.Tube Well site and New construction of Boundary Wall at 3rd.& 4 th Tube Well site for Erasal Water Supply Scheme under Tamluk Sub Division,PHE Dte.. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000783/2022-2023 | 3019/TD | 27/02/2023 | 60 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.17 | 0 | 100
2645 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000021/2022-2023 | 409/TD | 25/05/2022 | 0 | Resource Division | 114.93 | 0 | 0
2646 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000086/2022-2023 | 1263/TD | 12/09/2022 | 0 | Resource Division | 44.05 | 0 | 0
2647 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Dhenkua Water Supply Scheme by Providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 400 cum and staging height 20.00 mtr. With allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000007/2022-2023 | 57/TD | 05/04/2022 | 180 | RAJ KUMAR SINGHA | 563.22 | 446.5 | 100
2648 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000069/2022-2023 | 346/TD | 13/05/2022 | 20 | TAPAS SANTRA | 4.49 | 4.49 | 100
2649 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice Valve for Dhenkua Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000070/2022-2023 | 347/TD | 13/05/2022 | 20 | TAPAS SANTRA | 3.67 | 3.67 | 100
2650 | Tamluk Division | Haldia Sub-Division | Laying of Left-out portion Distribution pipe line and Household Tap Connection (FHTC) for Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000134/2024-2025 | 3466/TD | 06/11/2024 | 96 | RAJ KUMAR SINGHA | 54.66 | 0 | 70
2651 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Dhenkua Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000160/2021-2022 | 1164/TD | 01/12/2021 | 7 | HORIZEN | 5.92 | 5.83 | 100
2652 | Tamluk Division | Haldia Sub-Division | G.I pipe column with M.S. Structure for laying of D.I pipe line & HDPE pipe line with Casing at Dhenkua Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. (Total Length= 65.00 mtr, {i) NP-116 to 46= 20mt + ii) NP-90 to 5= 2.5mt + iii) NP 10 to 11 = 2.5 Mtr. + iv) NP - 199 to 168 = 20.0mt + NP - 151 to 154 =20.0mtr.} | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000233/2022-2023 | 974/TD | 03/08/2022 | 20 | RAJ KUMAR SINGHA | 9.49 | 4.79 | 100
2653 | Tamluk Division | Haldia Sub-Division | Laying Rising main and supporting work with Drum Sheet walling and Earth filling in Dhenkua Water Supply Scheme within Sutahata Block under Haldia Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000234/2022-2023 | 975/TD | 03/08/2022 | 875 | RAJ KUMAR SINGHA | 87.92 | 78.8 | 100
2654 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Dhenkua Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000299/2022-2023 | 1133/TD | 30/08/2022 | 90 | DIPANKAR MALAKAR | 4.75 | 2.74 | 100
2655 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000013/2021-2022 | 1255/TD | 13/12/2021 | 0 | Resource Division | 12.45 | 0 | 0
2656 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000044/2021-2022 | 2345/TD | 31/03/2022 | 0 | Resource Division | 15.83 | 0 | 0
2657 | Tamluk Division | Haldia Sub-Division | Restoration work of the damaged flank portions caused for laying pipe line by PHE Dte.on Terapara Jalpai to Jaganathpur (Basulia Hospital to Horikhali) road from Ch.0.42 KM to 2.00 KM under Haldia Highway Sub Division within Tamluk Highway Divison in the District Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00238/2023-2024 | BP-2023-24-123 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.68 | 0 | 0
2658 | Tamluk Division | Haldia Sub-Division | Payment to WBSEDCL for Electric Quotation money of Begunberia Tube Well No. ¿ III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00378/2023-2024 | BP-2023-24-206 | 25/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
2659 | Tamluk Division | Haldia Sub-Division | Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Begunberia Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000033/2022-2023 | 132/TD | 19/04/2022 | 21 | SIMPLEX DRILLING COMPANY | 19.03 | 19.03 | 100
2660 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000072/2022-2023 | 355/TD | 13/05/2022 | 20 | SANTRA ENTERPRISE. | 4.85 | 4.85 | 100
2661 | Tamluk Division | Haldia Sub-Division | Supply & delivery of different dia CIDF Sluice valve of Begunberia Water Supply Scheme under Haldia Sub-Division of Tamluk Division PHE Dte. (Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000073/2022-2023 | 356/TD | 13/05/2022 | 20 | SANTRA ENTERPRISE. | 4.42 | 4.42 | 100
2662 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of Construction of 5.40 Mtr. X 3.60 Mtr. & 3.60 mt x 3.0 mt Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work & 2 nd tube well site of Begunberia Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000122/2021-2022 | 1000/TD | 01/11/2021 | 20 | SAYAN MAITY | 4.25 | 3.26 | 100
2663 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Begunberia Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000174/2021-2022 | 1183/TD | 02/12/2021 | 20 | HORIZEN | 7 | 7 | 100
2664 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall, Retaining wall, Approach road & Earth filling Work in 3rd tubewell site of Begunberia Water Supply scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) , (length of Retaining wall-16mtr) & (length of Approach road-10mtr). | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000573/2023-2024 | 2162/TD | 31/08/2023 | 30 | M/S SOURAV MAHAPATRA | 22.85 | 0 | 20
2665 | Tamluk Division | Haldia Sub-Division | Laying Left Out Distribution System, FHTC work & Pilling work with Drum sheet Augmentation of ground water based Begunberia Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000578/2023-2024 | 2200/TD | 01/09/2023 | 520 | TAPAS SANTRA | 97.5 | 0 | 50
2666 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Begunberia Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 600 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000636/2021-2022 | 2335/TD | 29/03/2022 | 1282 | TAPAS SANTRA | 681.46 | 590.71 | 92
2667 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000015/2021-2022 | 1257/TD | 13/12/2021 | 0 | Resource Division | 71.92 | 0 | 0
2668 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000047/2021-2022 | 2347/TD | 31/03/2022 | 0 | Resource Division | 25.41 | 0 | 0
2669 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
2670 | Tamluk Division |  | Installation of 150 mm.x100 mm.x 230 mtr.(av) depth Tube well(PVC) & Providing FHTC (364 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme ( maximum 100 nos household) at 09 nos Different Location Block within Purba Medinipur district under Tamluk Division, PHE Dte. |  |  | ORD/000419/2023-2024 | 1100/TD | 08/06/2023 | 907 | SWADHIN KUMAR CHAKRABORTY | 245.94 | 0 | 51
2671 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000081/2023-2024 | 2894/TD | 21/11/2023 | 0 | Resource Division | 2.04 | 0 | 0
2672 | Tamluk Division | Haldia Sub-Division | Payment to WBSEDCL for Electric Quotation money of Tabakhali Tube Well No. ¿ III | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00377/2023-2024 | BP-2023-24-205 | 25/07/2023 | 0 | WBSEDCL | 0.56 | 0 | 0
2673 | Tamluk Division | Haldia Sub-Division | Way Leave permission from South Eastern Railway for Tabakhali PWSS for Application ID-SER-KGP-2023-WL-67 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/01828/2023-2024 | BP-2023-24-822 | 22/01/2024 | 0 | FA & CAO, S.E. RAILWAY, GRC. | 6.17 | 0 | 0
2674 | Tamluk Division | Haldia Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Tabakhali Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000162/2021-2022 | 1166/TD | 01/12/2021 | 7 | HORIZEN | 7.85 | 7.74 | 100
2675 | Tamluk Division | Haldia Sub-Division | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at 1st Tube well Site of Kapaseria W/S Scheme within Mahisadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Replacement Tube well by direct rotary rig method at Head work Site of Rajarampur W/S Scheme within Mahishadal Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 280 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well Site of Tabakhali W/S Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000235/2022-2023 | 976/TD | 03/08/2022 | 21 | SIMPLEX DRILLING COMPANY | 58.06 | 19.26 | 100
2676 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd Tube Well site of Tabakhali Water Supply Scheme under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000341/2022-2023 | 1284/TD | 12/09/2022 | 60 | ELECTIVA ENTERPRISE | 4.77 | 3.37 | 100
2677 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 3rd tubewell site of Tabakhali W/S scheme under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000395/2023-2024 | 1084/TD | 08/06/2023 | 30 | M/S SOURAV MAHAPATRA | 5.91 | 3 | 100
2678 | Tamluk Division | Haldia Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 750 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Ground Water Based Tabakhali Water Supply Scheme within Sutahata Dev. Block under Haldia sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000416/2022-2023 | 1578/TD | 14/10/2022 | 180 | RAJ KUMAR SINGHA | 709.93 | 261.56 | 55
2679 | Tamluk Division | Haldia Sub-Division | Jack Pushing of Railway Track Between BASULYA - BARADA Railway Station on Tamluk-Haldia Section of Kharagpur S.E. Railway Division of Purba Medinipur for Augmentation of Tabakhali Piped Water Supply Scheme of 150 mm Dia G.I. Casing Pipe and 125 mm Dia HDPE (PE-100) Carrier Pipe in between OHE MAST NO H50/11 & H50/13, H50/12 & H50/14 within Haldia Sub-Division under Tamluk Division, P.H.E DTE. (Total Length = 80 Mtr) Nodal Point J38 - J40. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000722/2023-2024 | 2944/TD | 23/11/2023 | 20 | KRISHNENDU SEKHAR DAS | 72.62 | 0 | 100
2680 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000022/2022-2023 | 410/TD | 25/05/2022 | 0 | Resource Division | 205.42 | 0 | 0
2681 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000087/2022-2023 | 1264/TD | 12/09/2022 | 0 | Resource Division | 34 | 0 | 0
2682 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000319/2022-2023 | 599/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 3.61 | 100
2683 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Madhabpur (Balighai) Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000324/2021-2022 | 1617/TD | 14/01/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 5.71 | 5.71 | 100
2684 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied work for Madhabpur (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000380/2023-2024 | 1024/TD | 07/06/2023 | 60 | BASANTA KUMAR MAITY | 45.82 | 0 | 90
2685 | Tamluk Division | Digha Sub-Division | Laying of Distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Madhabpur Zone-II Water Supply Scheme within Egra-II. Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000418/2022-2023 | 1576/TD | 14/10/2022 | 991 | BASANTA KUMAR MAITY | 495.32 | 58.97 | 75
2686 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-I Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for Head Work site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 220 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well site Tube Well of Madhabpur Zone-II Water Supply Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000487/2022-2023 | 1909/TD | 25/11/2022 | 912 | OSMAN SEKH | 69.99 | 0 | 100
2687 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000112/2022-2023 | 1666/TD | 03/11/2022 | 0 | Resource Division | 141.02 | 0 | 0
2688 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000284/2022-2023 | 2637/TD | 02/02/2023 | 0 | Resource Division | 15.45 | 0 | 0
2689 | Tamluk Division |  | Payment balance 6% GST amount against GST No. 19AAKCB8479M1ZO for the work of Implementation of Mini Piped Water Supply Scheme for Installation of 150 mm.x100 mm.x 222 mtr.(av) depth Tube well(PVC) & Providing FHTC (16246 Nos) (Functional Household Tap Connection) of Ground water based mini piped water supply Scheme (maximum 100 nos household) at different locations of different Village (260 nos at different locations of different Village (260 nos.) under different Block within Purba Medinipur district under Tamluk Division, PHE Dte in connection with Jal Swapna. |  |  | BILL/00402/2024-2025 | BP-2024-25-143 | 27/05/2024 | 0 | BIRBHUM INFRAPARK PRIVATE LIMITED | 185.24 | 0 | 0
2690 | Tamluk Division |  | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 2897/TD | 21/11/2023 | 0 | Resource Division | 4.61 | 0 | 0
2691 | Tamluk Division | Haldia Electrical Sub-Division | Quotation money payment to WBSEDCL for Khejuri Zone-II Water Supply Scheme of Tube Well No. - III | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00536/2023-2024 | BP-2023-24-284 | 17/08/2023 | 0 | WBSEDCL | 1.41 | 0 | 0
2692 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low land at Head Work site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000117/2024-2025 | 1909/TD | 07/06/2024 | 7 | TECHNO ENTERPRISE. | 2.02 | 0 | 100
2693 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC with construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, P.H.E. Dte, Purba Medinipur.(Part-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000444/2022-2023 | 1654/TD | 02/11/2022 | 180 | SIBSANKAR CHOWDHURY | 449.19 | 0 | 40
2694 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 4 (four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-I Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 1st Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 2nd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at additional 3rd Tube well Site of Khejuri Zone-II Water Supply Scheme under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000312/2022-2023 | 1225/TD | 07/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 71.86 | 0 | 100
2695 | Tamluk Division | Haldia Electrical Sub-Division | Construction of boundary wall and construction of Switch Room with allied works including supply of all labour & materials for Augmentation of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000457/2023-2024 | 1502/TD | 17/07/2023 | 40 | RAI CONSTRUCTION | 9.19 | 0 | 100
2696 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-I) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000532/2023-2024 | 1858/TD | 09/08/2023 | 10 | TECHNO ENTERPRISE. | 0.96 | 0.96 | 100
2697 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-II) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000533/2023-2024 | 1859/TD | 09/08/2023 | 10 | TECHNO ENTERPRISE. | 0.95 | 0.94 | 100
2698 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Pump Houses and Laying Rising Main for water connection between 1st , 2nd and 3rd Tube Well at Khejuri Water Supply Scheme (Zone-II) within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000733/2023-2024 | 2984/TD | 29/11/2023 | 45 | M/S SOURAV MAHAPATRA | 22.43 | 0 | 70
2699 | Tamluk Division | Haldia Electrical Sub-Division | Earth Work in filling in Ditches, Low Land at Head Work Site of Khejuri Zone-II & its adjoining mouzas Water Supply Scheme within Khejuri-II Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. (PHASE-III) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000745/2023-2024 | 3147/TD | 07/12/2023 | 10 | TECHNO ENTERPRISE. | 0.91 | 0 | 100
2700 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000042/2022-2023 | 828/TD | 15/07/2022 | 0 | Resource Division | 60.29 | 0 | 0
2701 | Tamluk Division |  | Relaying of 125 mm dia GI Pipe & 150 mm dia GI pipe line for canal crossing with allied works due to damage of pipe line of N.P.-97-99 (part) for construction of culvert of Strengthening & Widening Contai Junput Road of Aladarput Water Supply Scheme under Contai Sub-Division of Tamluk Division, PHE Dte. |  |  | ORD/000264/2021-2022 | 569 / CSD | 08/12/2021 | 21 | MRINAL KANTI PRADHAN | 2.24 | 0 | 0
2702 | Tamluk Division |  | Retrofitting to accommodate FHTC [ 427 nos] under JJM in Aladarput PWSS [Sarsa(532, part),Uttar Dauki(549,part),Dakshin Paikbar(574,part),Faridpur(575, part),Biswanathpur(576, part),Aladarput(578, part),Hosenaput(579, part),Kalaminaput(580, part),Dakshin Murabanya(581, part),Bichina(584, part),Purba Chechuraput(585,part )] within Contai-II Block under Contai Sub-Division of Tamluk Division,Purba Medinipur (PHASE -II) |  |  | ORD/000266/2020-2021 | 2919/TD | 22/02/2021 | 20 | BARH CONSTRUCTION | 26.62 | 4.66 | 100
2703 | Tamluk Division |  | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000372/2021-2022 |  | 01/10/2021 | 0 | BARH CONSTRUCTION | 20.48 | 0 | 0
2704 | Tamluk Division |  | Retrofitting to accomodate FHTC 427 Nos. under JJM Aladarput W/S Scheme within Contai - II Dev. Block under Tamluk Division, PHE Dte. (Phase-II) |  |  | VCH/000420/2021-2022 | BP-2021-22-93 | 05/10/2021 | 0 | BARH CONSTRUCTION | 20.48 | 0 | 0
2705 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,100 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (618 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Purba Puroshattampur PWSS within Ramnagar-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000353/2023-2024 | 880/TD | 01/06/2023 | 180 | BARH CONSTRUCTION | 281.85 | 84.92 | 66
2706 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000166/2023-2024 | 98/TD | 05/01/2024 | 0 | Resource Division | 3.81 | 0 | 0
2707 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000265/2022-2023 | 2692/TD | 06/02/2023 | 0 | Resource Division | 14.58 | 0 | 0
2708 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000096/2024-2025 | 2961/TD | 12/09/2024 | 0 | Resource Division | 7.86 | 0 | 0
2709 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000124/2022-2023 | 2402/TD | 16/01/2023 | 0 | Resource Division | 11.28 | 0 | 0
2710 | Tamluk Division | Haldia Electrical Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head works site for Augmentation of Amarshikasba Zone-II PWSS within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Length-136.00 mtr.) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000290/2023-2024 | 592/TD | 17/05/2023 | 45 | ANUSKA ENTERPRISE | 21.29 | 0 | 40
2711 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 5.40 mtr x3.60mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) with sanitary & water supply arrangements including Plinth Protection at 1st TW(Head Work) site for Augmentation of Amarshikasba Zone-II & its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(For Low Land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000291/2023-2024 | 593/TD | 17/05/2023 | 60 | M/S SOURAV MAHAPATRA | 7.26 | 0 | 100
2712 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Amarshikashba Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000322/2022-2023 | 617/TD | 21/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 3.32 | 100
2713 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (2238 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Amarshikasba Zone-II water Supply Scheme within Patashpur-I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000750/2022-2023 | 2593/TD | 30/01/2023 | 878 | DAS ENTERPRISE | 372.65 | 129.3 | 100
2714 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 3.60 mtr x 3.00 mtr. Size Switch Room cum Chlorin Room (as per Departmental Design and Drawing) without sanitary and water supply arrangements including Plinth Protection at 2nd TW site for Augmentation of Amarshikasba Zone-II and its adjoining moujas PWSS in Patashpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (For Low land) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000845/2023-2024 | 18/TD | 03/01/2024 | 240 | GOUTAM DEY | 3.75 | 0 | 100
2715 | Tamluk Division | Haldia Electrical Sub-Division | Drum Sheet walling 1.40m. (av.) high on sal-bullah / Eucalyptus bullah pilling with allied works of Amarshi Kasba Zone-II & its adjoining moujas PWSS within Patashpur-I Block under Contai-Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001257/2024-2025 | 130/CSD | 16/01/2025 | 7 | GHOSH CONSTRUCTION (GST : 19AXMPG8403A1ZO) | 0.97 | 0 | 100
2716 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000069/2023-2024 | 2645/TD | 13/10/2023 | 0 | Resource Division | 14.4 | 0 | 0
2717 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000118/2022-2023 | 1669/TD | 03/11/2022 | 0 | Resource Division | 57.23 | 0 | 0
2718 | Tamluk Division |  | Rejuvenation to accommodate FHTC (450 nos.) under JJM of Chandanpur PWSS within Ramnagar I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. (Phase-II) |  |  | ORD/000005/2021-2022 | 683/TD | 10/09/2021 | 20 | TAPAS SANTRA | 63.43 | 124.51 | 100
2719 | Tamluk Division | Tamluk Sadar Sub-Division | Electric Quotation Bill under Nandakumar CCC at Bargodagodar PWSS under Tamluk Division, PHE Dte. within Purba Medinipur District. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00135/2022-2023 | BP-2022-23-511 | 22/12/2022 | 0 | WBSEDCL | 2.57 | 0 | 0
2720 | Tamluk Division | Tamluk Sadar Sub-Division | Restoration estimate with sand filling and jhama -metal consolidation of Thekuabazar- Pursaghat Road due to lcutting of hard shoulder for laying water pipelines by PHE Dte. within Tamluk Highway Sub-Division under Tamluk Highway Division in the district of Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00231/2023-2024 | BP-2023-24-116 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.12 | 0 | 0
2721 | Tamluk Division | Tamluk Sadar Sub-Division | Restoration estimate with Bituminous Surfacing ,sand filling and jhama -metal consolidation of Tamluk -Moyna road from 10 KM to 11.30 KM due to cutting of Hard shoulder for laying water pipe lines by PHE Dte. within Tamluk Highway Sub-Division in the district of Purba Medinipur during the year 2022-23 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00233/2023-2024 | BP-2023-24-118 | 14/06/2023 | 0 | EXECUTIVE ENGINEER, TAMLUK HIGHWAY DIVISION, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.09 | 0 | 0
2722 | Tamluk Division | Tamluk Sadar Sub-Division | Payment to WBSEDCL for Quotation Money for Bargodagodar PWSS under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00612/2022-2023 | BP-2022-23-820 | 24/03/2023 | 0 | WBSEDCL | 8.99 | 0 | 0
2723 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 300cum and staging height 20.00 mtr.and repairing & renovation of 450 cum OHR and staging height 20.00 mtr as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Bargodagodar Water Supply Scheme within Nandakumar Dev. Block under Tamluk sub-division of Tamluk Division, P.H.E. Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000187/2022-2023 | 812/TD | 12/07/2022 | 180 | CONCORD ENGINEERING | 774.2 | 542.52 | 76
2724 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bargodagodar Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000190/2021-2022 | 1199/TD | 02/12/2021 | 20 | RADIANT | 8.93 | 8.93 | 100
2725 | Tamluk Division | Tamluk Sadar Sub-Division | Left out pipe line of Providing Functional Household Tap Connection & construction of new drain of Khejurberia Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000328/2024-2025 | 3268/TD | 04/10/2024 | 90 | MISHRA ENTERPRISE | 44.78 | 0 | 100
2726 | Tamluk Division | Tamluk Sadar Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd tube well sites of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000397/2022-2023 | 1445/TD | 27/09/2022 | 30 | TARUN KHATUA | 4.85 | 4.85 | 100
2727 | Tamluk Division | Tamluk Sadar Sub-Division | Repairing & renovation of Construction of Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 1st tube well site of Bargodagodar Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000436/2022-2023 | 1208/TSD | 15/09/2022 | 30 | S.K. MONDAL | 2.66 | 2.3 | 0
2728 | Tamluk Division | Tamluk Sadar Sub-Division | Supply of 80 mm dia sluice valve and construction of chamber for 80 mm dia sluice valve at Nodal point J-307 to J-308, J-270 to J-271 and J-307 to J-321 J-168 to J-196 under Bargodagodar PWSS under Tamluk Sub-Division of Tamluk division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000566/2024-2025 | 196/TSD | 22/01/2025 | 15 | TARUN KHATUA | 0.82 | 0 | 100
2729 | Tamluk Division | Tamluk Sadar Sub-Division | Laying left out portion of 90 mm dia UPVC pipe lines with allied works to facilitate the FHTC connection for Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000586/2023-2024 | 2205/TD | 01/09/2023 | 900 | SK. NUR ISLAM | 27.66 | 0 | 60
2730 | Tamluk Division | Tamluk Sadar Sub-Division | Functional Household Tap Connection (FHTC-796 nos) of Bargodagodar water supply scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000588/2023-2024 | 2206/TD | 01/09/2023 | 900 | SK. NUR ISLAM | 27.14 | 0 | 60
2731 | Tamluk Division | Tamluk Sadar Sub-Division | New Construction of boundary wall (Length-50 m) with R.C.C structures including provision of M.S. gate at Head work site under Bargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000602/2023-2024 | 2214/TD | 01/09/2023 | 40 | BARH CONSTRUCTION | 6.22 | 0 | 0
2732 | Tamluk Division | Tamluk Sadar Sub-Division | Dismentling of existing damaged staff quarter and godown of Bargodagodar and its adjoining mouza Water Supply Scheme under Tamluk Sub Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000604/2024-2025 | 337/TSD | 17/02/2025 | 390 | SK. INJAMUL ALI | 2.81 | 0 | 100
2733 | Tamluk Division | Tamluk Sadar Sub-Division | Land filling work at 3rd tube well site of Bargodagodar water supply scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000738/2022-2023 | 74/TSD | 11/01/2023 | 15 | TARUN KHATUA | 0.95 | 0.95 | 100
2734 | Tamluk Division | Tamluk Sadar Sub-Division | Jungle cutting at Head work site in connection repair & renovation of Boundary of Boargodagodar W/S Scheme under Tamluk Sub-Division of Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000755/2023-2024 | 1659/TSD | 11/12/2023 | 7 | PURNA CHANDRA BARH | 0.24 | 0 | 0
2735 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of rising main, Construction of Boundary Wall and Repairing & Renovation of Construction of Boundary wall with allied work for Bargodagodar PWSS in Nandakumar Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000828/2022-2023 | 3167/TD | 10/03/2023 | 632 | BARH CONSTRUCTION | 33.83 | 13.27 | 80
2736 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 300 mm x 200 mm dia x 240 mtr. deep tube well by direct rotary rig method for Replacement of head work site Tube well of Bargodagudar Water Supply Scheme within Nandakumar Block under Tamluk Sub-Division of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001240/2023-2024 | 1084/TD | 16/03/2024 | 20 | MANNA COMPUTER | 17.87 | 0 | 100
2737 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000007/2022-2023 | 97/TD | 11/04/2022 | 0 | Resource Division | 41.98 | 0 | 0
2738 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000067/2021-2022 | 645/TD | 27/06/2022 | 0 | Resource Division | 37.93 | 0 | 0
2739 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000203/2023-2024 | 1102/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2740 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- B) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000004/2022-2023 | 60/TD | 05/04/2022 | 60 | TAPAS SANTRA | 154.84 | 129.6 | 100
2741 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part-D) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000008/2022-2023 | 55/TD | 05/04/2022 | 90 | MAA ANANDAMAYEE | 251.38 | 220.76 | 100
2742 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District.(Part- A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000009/2022-2023 | 54/TD | 05/04/2022 | 90 | HARIPADA PATTANAYAK | 273.36 | 272.86 | 100
2743 | Tamluk Division | Haldia Electrical Sub-Division | Rejuvenation & Retrofitting of ground water based Kulbari PWSS to accommodate FHTC in Chandipur Block under Tamluk Sub Division of Tamluk Division in Purba Medinipur District. (Part- C) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000039/2022-2023 | 138/TD | 19/04/2022 | 1009 | BIDHAN MONDAL | 184.94 | 90.33 | 55
2744 | Tamluk Division | Haldia Electrical Sub-Division | 2(Two) nos Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room, Laying of proposed Rising main line with interconnection and new construction of boundary wall (Length-50 m) at Boosting Tube Well Site for Kulbari Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000132/2023-2024 | 268/TD | 20/04/2023 | 855 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.15 | 0 | 100
2745 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Kulbari Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000186/2021-2022 | 1195/TD | 02/12/2021 | 20 | INDRANIL DUTTA & ASSOCIATES | 10.5 | 10.5 | 100
2746 | Tamluk Division | Haldia Electrical Sub-Division | Sinking of 1 (One) no Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at OHR Site of Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000236/2022-2023 | 977/TD | 03/08/2022 | 15 | PRANTIK DRILLING AGENCY | 17.17 | 16.45 | 100
2747 | Tamluk Division | Haldia Electrical Sub-Division | Supply of DI Specials for Proposed Rejuvenation & Retrofitting of Laying Distribution System of KULBARI PWSS under tamluk Sub-Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000328/2022-2023 | 1229/TD | 07/09/2022 | 15 | BAGLAMUKHI SECURITY SERVICE | 4.81 | 4.81 | 100
2748 | Tamluk Division | Haldia Electrical Sub-Division | Repairing & renovation of Pump House at OHR site & 2nd Pump house and boundary wall at 2nd TW site and new construction of boundary wall at OHR site and renovation works of OHR for Kulbari Water Supply Scheme within Chandipur Block under Tamluk Sub Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000357/2023-2024 | 925/TD | 01/06/2023 | 575 | HARIPADA PATTANAYAK | 44.56 | 0 | 100
2749 | Tamluk Division | Haldia Electrical Sub-Division | Sal-bullah /Eucalyptus bullah piling of pipe line and its allied works to accommodate FHTC at Kulbari water supply scheme in Chandipur Block within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur(PART-A) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000358/2023-2024 | 926/TD | 01/06/2023 | 20 | LITTLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 12.86 | 0 | 100
2750 | Tamluk Division | Haldia Electrical Sub-Division | Construction of 2(Two) nos M.S. Structure over irrigation canal to support 90 mm dia. UPVC distribution pipe under Kulbari Water Supply Scheme at NP 71-893 & NP 72-475 under Tamluk Sub-Division of Tamluk Division, Purba Medinipur,PHE Dte.(Each length=15.00 Mtr ) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000432/2024-2025 | 3553/TD | 19/11/2024 | 24 | MAA ANANDAMAYEE | 4.46 | 0 | 100
2751 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000004/2022-2023 | 96/TD | 11/04/2022 | 0 | Resource Division | 43.14 | 0 | 0
2752 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000028/2022-2023 | 418/TD | 25/05/2022 | 0 | Resource Division | 4.92 | 0 | 0
2753 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000064/2021-2022 | 642/TD | 27/06/2022 | 0 | Resource Division | 27.12 | 0 | 0
2754 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000197/2023-2024 | 1097/TD | 19/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2755 | Tamluk Division | Digha Sub-Division | Sinking of 250mm x 150mm dia Tube well of 210 mtr deep tubewell Drilling by Direct Rotary method with 150 dia.uPVC. Strainer of 30m.length all complete including cost of materials for Replacement of 2nd Tubewell at Bagmari & its adjoining mouzas Water Supply Scheme within Egra- I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000116/2024-2025 | 1913/TD | 07/06/2024 | 20 | MAITY CONSTRUCTION | 12.06 | 0 | 100
2756 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 200 Cum Capacity OHR ( Intze type with pile foundatio ) & Accommodate FHTC ( 1230 Nos) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000180/2023-2024 | 294/TD | 20/04/2023 | 180 | BASANTA KUMAR MAITY | 401.59 | 121.06 | 63
2757 | Tamluk Division | Digha Sub-Division | Laying of balance distribution pipe line to provide Balance FHTC with allied works for Bagmari & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHE Dte, Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000596/2024-2025 | 568/TD | 17/02/2025 | 50 | MAITY CONSTRUCTION | 23.23 | 0 | 0
2758 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000115/2023-2024 | 79/TD | 05/01/2024 | 0 | Resource Division | 7.58 | 0 | 0
2759 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000267/2022-2023 | 2700/TD | 06/02/2023 | 0 | Resource Division | 46.45 | 0 | 0
2760 | Tamluk Division | Tamluk Sadar Sub-Division | Crossing permission of laying HDPE pipeline along and across of NH-116 (from Mecheda bus stop to Hakola Bus stop) of Santipur Water Supply Scheme within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/001182/2023-2024 | 741/TD | 28/02/2024 | 20 | DONA ASSOCIATES | 9.24 | 0 | 0
2761 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000168/2023-2024 | 117/TD | 05/01/2024 | 0 | Resource Division | 14.4 | 0 | 0
2762 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000208/2022-2023 | 2466/TD | 16/01/2023 | 0 | Resource Division | 21.59 | 0 | 0
2763 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at 3rd. T/W Site. of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000398/2023-2024 | 1082/TD | 08/06/2023 | 45 | TARUN KHATUA | 5.1 | 5.1 | 100
2764 | Tamluk Division | Haldia Electrical Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Anantapur (Zone-II) Water Supply Scheme under Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000463/2021-2022 | 1740/TD | 03/02/2022 | 20 | RADIANT | 3.89 | 3.86 | 100
2765 | Tamluk Division | Haldia Electrical Sub-Division | Laying of distribution pipe line to accommodate FHTC (5686 nos) with new construction of R.C.C. Elevated Reservoir of capacity 750cum and staging height 20.00 mtr.and as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Anantapur Zone-II Water Supply Scheme within Tamluk Dev. Block under Tamluk Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000481/2022-2023 | 1885/TD | 24/11/2022 | 859 | TAPAS SANTRA | 609.95 | 307.59 | 75
2766 | Tamluk Division | Haldia Electrical Sub-Division | Laying of 200 /250/300mm dia DI(K-9) for Rising main line from T/W-1 , T/W-2 ,T/W-3 and interconnection betn. T/W-1 to OHR including supply of DI specials , Construction of approach road at 3rd tube well site under Anantapur Zone- II PWSS with in Tamluk Dev. Block in Purba Medinipur District under Tamluk Sub Division of Tamluk Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000579/2023-2024 | 2201/TD | 01/09/2023 | 20 | TARUN KHATUA | 8.66 | 0 | 80
2767 | Tamluk Division | Haldia Electrical Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement (as per Deptt. drawing) at Head work Site of Anantapur Zone-II Water Supply Scheme under Tamluk Sub Division of Tamluk Division, PHE Dte. Purba Medinipur . | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000600/2023-2024 | 2213/TD | 01/09/2023 | 40 | TARUN KHATUA | 5.14 | 0 | 100
2768 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000048/2022-2023 | 1018/TD | 08/08/2022 | 0 | Resource Division | 88.34 | 0 | 0
2769 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000057/2022-2023 | 1207/TD | 06/09/2022 | 0 | Resource Division | 2.44 | 0 | 0
2770 | Tamluk Division | Haldia Electrical Sub-Division | Material Requisition To Resource Division | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000223/2023-2024 | 1122/TD | 18/03/2024 | 0 | Resource Division | 0.19 | 0 | 0
2771 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Mustaphapur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000189/2024-2025 | 2199/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2772 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000052/2024-2025 | 1660/TD | 29/04/2024 | 0 | Resource Division | 11.12 | 0 | 0
2773 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000151/2022-2023 | 2457/TD | 16/01/2023 | 0 | Resource Division | 24.12 | 0 | 0
2774 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
2775 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000083/2024-2025 | 2969/TD | 12/09/2024 | 0 | Resource Division | 12.36 | 0 | 0
2776 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000248/2022-2023 | 2718/TD | 06/02/2023 | 0 | Resource Division | 38.35 | 0 | 0
2777 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Laying distribution system pipe line, accommodate FHTC(1309 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of 200 Cum. capacity RCC over Head Reservoir and staging height20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall and 2 yeras Operation & Maintenance under JJM with allied work for Kurpai PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000231/2023-2024 | 461/TD | 04/05/2023 | 1062 | MAA ANANDAMAYEE | 396.25 | 0 | 75
2778 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000219/2022-2023 | 2679/TD | 06/02/2023 | 0 | Resource Division | 19.42 | 0 | 0
2779 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000140/2022-2023 | 2440/TD | 16/01/2023 | 0 | Resource Division | 30.48 | 0 | 0
2780 | Tamluk Division | Digha Sub-Division | Additional Quotation for Additional Service connection Charges against APP NO: 2004521731 IRO DEPAL W/S Scheme T/W no-I AT DEPAL Under Jal Jeevan Mission under MMD, PHE, Dte. Block- RAMNAGAR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No-DGA/776 DT. 05-08-2024 Application NO- 100000115575 DT. 05-08-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860310305 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00761/2024-2025 | BP-2024-25-381 | 29/08/2024 | 0 | WBSEDCL | 11.8 | 0 | 0
2781 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (3154 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance for DEPAL and KALAPUNJA within Ramnagar-II Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000422/2023-2024 | 1416/TD | 12/07/2023 | 746 | BASANTA KUMAR MAITY | 961.33 | 0 | 60
2782 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000129/2023-2024 | 108/TD | 05/01/2024 | 0 | Resource Division | 11.02 | 0 | 0
2783 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000309/2022-2023 | 2999/TD | 27/02/2023 | 0 | Resource Division | 22.33 | 0 | 0
2784 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000081/2024-2025 | 2953/TD | 12/09/2024 | 0 | Resource Division | 14.49 | 0 | 0
2785 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000336/2022-2023 | 2979/TD | 27/02/2023 | 0 | Resource Division | 17 | 0 | 0
2786 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Baispur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000185/2024-2025 | 2195/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2787 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000126/2022-2023 | 2410/TD | 16/01/2023 | 0 | Resource Division | 21.35 | 0 | 0
2788 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1648 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Uttar Daidpur PWSS within Egra-II Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000482/2023-2024 | 1568/TD | 19/07/2023 | 180 | M/S JOY MAA DURGA ENTERPRISE | 488.61 | 0 | 60
2789 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000252/2022-2023 | 2714/TD | 06/02/2023 | 0 | Resource Division | 61 | 0 | 0
2790 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well ,Construction of 250 Cu.m. Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2852 Nos) For 2 nos Pipe Water Supply Scheme including (Santra & Purba Mukundapur) including two years Operation & Maintainance within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000682/2023-2024 | 2711/TD | 30/10/2023 | 790 | TAPAS SANTRA | 938.36 | 0 | 40
2791 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000169/2023-2024 | 113/TD | 05/01/2024 | 0 | Resource Division | 9.76 | 0 | 0
2792 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000264/2022-2023 | 2701/TD | 06/02/2023 | 0 | Resource Division | 27.23 | 0 | 0
2793 | Tamluk Division | Contai Sub-Division | Construction of Boundary Wall (as per Departmental Design & Drawing) at Boosting Tube Well for Uttar Khasda W/S Scheme within Contai- I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000436/2023-2024 | 1419/TD | 12/07/2023 | 30 | PULAK KUMAR SAMANTA | 8.31 | 0 | 100
2794 | Tamluk Division | Contai Sub-Division | Laying of 100 mm dia DI(K9) Rising Main pipe line with CIDF pipe & specials at 1 (One) no. Boosting Tube Well of Uttar Khasda & its adjoining mouzas Water Supply Scheme within Contai-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000864/2023-2024 | 234/TD | 10/01/2024 | 390 | THE GODFATHER TRADING COMPANY | 3.44 | 0 | 100
2795 | Tamluk Division | Contai Sub-Division | Construction of 3.60 mtr x3.00mtr. Size Switch Room cum Chlorin Room (as per Departmental Design & Drawing) without sanitary & water supply arrangements including Plinth Protection at Boosting Tube Well for Uttar Khasda Water Supply Scheme within Contai - I Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000865/2023-2024 | 233/TD | 10/01/2024 | 60 | KAMAL KUMAR BERA | 4.02 | 0 | 100
2796 | Tamluk Division | Haldia Sub-Division | Quotation bill for new service connection at TW-II of Mohanpur w/s scheme,Block-Sutahata under MMD, PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818907 Application type-new connection Reference ID-204355767 Quotation Date-12/07/2024 Quotation Due Date-14/07/2025 Contract Demand-6479 W | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | BILL/00682/2024-2025 | BP-2024-25-311 | 02/08/2024 | 0 | WBSEDCL | 3.21 | 0 | 0
2797 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000207/2023-2024 | 418/TD | 02/05/2023 | 1027 | NARAYAN CHANDRA DAS | 135.23 | 41.38 | 30
2798 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (300nos) and Construction of R.C.C. Over Head Reservoir of capacity 300 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000246/2023-2024 | 525/TD | 11/05/2023 | 966 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 175.05 | 32.44 | 25
2799 | Tamluk Division | Haldia Sub-Division | Box Culvert at HW site ,Land Development work & Construction of Retaining wall of ground water based Mohanpur Water Supply Scheme within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000730/2023-2024 | 2981/TD | 29/11/2023 | 540 | M/S SOURAV MAHAPATRA | 14.92 | 0 | 30
2800 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (400 nos) work within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000793/2022-2023 | 3044/TD | 27/02/2023 | 60 | NARAYAN CHANDRA DAS | 135.23 | 0 | 0
2801 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000794/2022-2023 | 3045/TD | 27/02/2023 | 30 | FARID UDDIN AHMED | 89.21 | 0 | 30
2802 | Tamluk Division | Haldia Sub-Division | Ground water based Mohanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (591 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/000795/2022-2023 | 3046/TD | 27/02/2023 | 30 | ANUSKA ENTERPRISE | 71.82 | 0 | 0
2803 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000161/2022-2023 | 2474/TD | 16/01/2023 | 0 | Resource Division | 27.14 | 0 | 0
2804 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | RTOR000191/2023-2024 | 640/W | 20/02/2024 | 0 | Resource Division | 12.26 | 0 | 0
2805 | Tamluk Division | Tamluk Sadar Sub-Division | Land development at Head work site and 2nd Tube well site of Mamudpur Water Supply Scheme within Tamluk Block under Tamluk Sub-Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000141/2024-2025 | 1921/TD | 07/06/2024 | 161 | SAYAN CONSTRUCTION | 7.12 | 0 | 95
2806 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Big dia Tube Well ,Laying distribution system pipe line, accommodate FHTC(1127 nos),Construction of switch room cum cholorine room , Laying of rising main, soil investigation,Construction of RCC over Head Reservoir of capacity 200 cum and staging height 20.00 mtr as per Deptt. drawing ( Intze type with pile foundation), Construction of Boundary Wall ,Instalation of display Board and 2 yeras Operation & Maintenance under JJM with allied work for Mamudpur PWSS in Tamluk Dev. Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000402/2023-2024 | 1094/TD | 08/06/2023 | 1028 | SUJATA CONSTRUCTION | 315 | 0 | 20
2807 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000297/2022-2023 | 3008/TD | 27/02/2023 | 0 | Resource Division | 20.18 | 0 | 0
2808 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000066/2024-2025 | 2946/TD | 12/09/2024 | 0 | Resource Division | 11.38 | 0 | 0
2809 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000339/2022-2023 | 2976/TD | 27/02/2023 | 0 | Resource Division | 32.62 | 0 | 0
2810 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kharat Katbar PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000188/2024-2025 | 2198/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2811 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000049/2024-2025 | 1656/TD | 29/04/2024 | 0 | Resource Division | 11.67 | 0 | 0
2812 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000146/2022-2023 | 2450/TD | 16/01/2023 | 0 | Resource Division | 31.66 | 0 | 0
2813 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in Sarrang PWSS under Egra-I Block within Digha Sub-Division of Tamluk Division. | Assistant Engineer | Junior Engineer | ORD/000485/2022-2023 | 1890/TD | 24/11/2022 | 60 | H. SAMANTA | 123.68 | 0 | 53
2814 | Tamluk Division | Digha Sub-Division | Construction of approach road at H/W site & 2nd T/W site of Sarrang Water Supply Scheme within Egra-I Block under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2024-2025 | 209/TD | 15/01/2025 | 30 | ASEMA ENTERPRISE | 1.95 | 0 | 0
2815 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000289/2022-2023 | 2645/TD | 02/02/2023 | 0 | Resource Division | 16.37 | 0 | 0
2816 | Tamluk Division | Tamluk Sadar Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 100 cum RCC OHR at Agar PWSS at Sahid Matangini Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000163/2024-2025 | 2075/TD | 24/06/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2817 | Tamluk Division | Tamluk Sadar Sub-Division | Laying distribution pipe line, Pump House , Boundary Wall ,Rising main , O&M and accommodate FHTC (832 nos) under JJM with allied work for AGAR PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000346/2023-2024 | 850/TD | 31/05/2023 | 915 | JAGANNATH MAKAR | 196.83 | 0 | 60
2818 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000112/2023-2024 | 76/TD | 05/01/2024 | 0 | Resource Division | 5.13 | 0 | 0
2819 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000315/2022-2023 | 3003/TD | 27/02/2023 | 0 | Resource Division | 20.51 | 0 | 0
2820 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Khar at Patashpur - II Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000586/2024-2025 | 462/TD | 04/02/2025 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2821 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000048/2024-2025 | 1655/TD | 29/04/2024 | 0 | Resource Division | 17.55 | 0 | 0
2822 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000153/2022-2023 | 2459/TD | 16/01/2023 | 0 | Resource Division | 53.73 | 0 | 0
2823 | Tamluk Division | Haldia Sub-Division | Quotation for new service connection at Bar Amritbera w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App No. 2004755767, Ref ID 204319519) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | BILL/00605/2024-2025 | BP-2024-25-295 | 29/07/2024 | 0 | WBSEDCL | 24.37 | 0 | 0
2824 | Tamluk Division | Haldia Sub-Division | Ground water based Bar Amrit Bere Water Supply Scheme by providing Sinking of Tube well, Construction of Pump House, Boundary Wall, Sub-soil Investigation, Construction of OHR (200 Cum), Laying Rising main, Laying of Distribution pipe line, FHTC work and 'Operation & Maintenance' within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000386/2023-2024 | 1048/TD | 07/06/2023 | 629 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 412.67 | 0 | 45
2825 | Tamluk Division | Haldia Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Bar Amrit Bere PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001054/2023-2024 | 384/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2826 | Tamluk Division | Haldia Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Mayachar Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Baramritbera Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000897/2022-2023 | 3347/TD | 22/03/2023 | 40 | PRANTIK DRILLING AGENCY | 61.77 | 0 | 50
2827 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000119/2023-2024 | 96/TD | 05/01/2024 | 0 | Resource Division | 9.24 | 0 | 0
2828 | Tamluk Division | Haldia Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000341/2022-2023 | 2985/TD | 27/02/2023 | 0 | Resource Division | 18.82 | 0 | 0
2829 | Tamluk Division | Contai Sub-Division | Sinking of Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Soil investigation & Accommodate FHTC (1527 nos) under JJM with allied work for BARMUNDA- PWSS in Patashpur- II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000498/2023-2024 | 1672/TD | 25/07/2023 | 887 | HALDIA DEVELOPMENT CONSTRUCTION | 584.47 | 0 | 48
2830 | Tamluk Division | Contai Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Barmunda PWSS at Patashpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001050/2023-2024 | 380/TD | 29/01/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2831 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000021/2024-2025 | 1647/TD | 29/04/2024 | 0 | Resource Division | 9.41 | 0 | 0
2832 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000318/2022-2023 | 2995/TD | 27/02/2023 | 0 | Resource Division | 26.96 | 0 | 0
2833 | Tamluk Division | Digha Sub-Division | Name of Work: Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 2nd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at 3rd Tube well site of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Additional Tube well by direct rotary rig method at Head Work site Tube well of Paniparul Zone-II W/S Scheme within Egra-II Block under Digha Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000022/2023-2024 | 120/TD | 06/04/2023 | 40 | KALPANA BUILDERS | 57.98 | 33.76 | 100
2834 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Paniparul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000320/2022-2023 | 590/TD | 17/06/2022 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.77 | 3.77 | 100
2835 | Tamluk Division | Digha Sub-Division | Construction of Pump House, Boundary Wall, Laying Rising main pipe line & Land development under JJM with allied works for Paniparul (Z-II ) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000599/2023-2024 | 2194/TD | 01/09/2023 | 60 | BASANTA KUMAR MAITY | 55.17 | 0 | 75
2836 | Tamluk Division | Digha Sub-Division | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 500cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of Paniparul Zone-II Water Supply Scheme within Egra-II. Block under Digha sub-division of Tamluk Division, P.H.E.Dte, Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000723/2022-2023 | 2534/TD | 19/01/2023 | 894 | BASANTA KUMAR MAITY | 644.68 | 204.29 | 78
2837 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000232/2022-2023 | 2615/TD | 02/02/2023 | 0 | Resource Division | 122.45 | 0 | 0
2838 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000282/2022-2023 | 2635/TD | 02/02/2023 | 0 | Resource Division | 23.91 | 0 | 0
2839 | Tamluk Division | Contai Sub-Division | Bill for payment to WBSEDCL for Shifting of Electric Line for Mukundapur Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/02049/2023-2024 | BP-2023-24-961 | 14/03/2024 | 0 | WBSEDCL | 2.93 | 0 | 0
2840 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000085/2024-2025 | 2968/TD | 12/09/2024 | 0 | Resource Division | 8.17 | 0 | 0
2841 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000165/2022-2023 | 2393/TD | 16/01/2023 | 0 | Resource Division | 30.99 | 0 | 0
2842 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bathuary Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000460/2022-2023 | 1859/TD | 21/11/2022 | 20 | ASTER CONSULTANCY | 3.3 | 2.95 | 100
2843 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Repair of Pump House , Repair Boundary Wall , land development for approch road & Accommodate FHTC (70 nos) under JJM with allied work for Bathuari (Zone-I) PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000648/2023-2024 | 2600/TD | 10/10/2023 | 813 | DILIP KUMAR GHOSH | 110.33 | 0 | 82
2844 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000052/2023-2024 | 2080/TD | 28/08/2023 | 0 | Resource Division | 14.36 | 0 | 0
2845 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000109/2023-2024 | 3012/TD | 29/11/2023 | 0 | Resource Division | 0.14 | 0 | 0
2846 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, & Accommodate FHTC (430 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-B) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000282/2023-2024 | 565/TD | 12/05/2023 | 927 | JASODA ENTERPRISE | 125.59 | 86.85 | 75
2847 | Tamluk Division | Contai Sub-Division | 250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line,Pump House , Boundary Wall, Soil investigation & Accommodate FHTC (460 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur Block within Contai Sub-Division under Tamluk Division, PHE Dte.(PART-A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000599/2024-2025 | 578/TD | 19/02/2025 | 180 | ARABINDA GHOSH | 217.97 | 0 | 0
2848 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (120 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000906/2022-2023 | 3461/TD | 27/03/2023 | 1078 | JASODA ENTERPRISE | 62.76 | 0 | 85
2849 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (320 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000908/2022-2023 | 3463/TD | 27/03/2023 | 849 | PARIA ENTERPRISE | 82.41 | 50.9 | 65
2850 | Tamluk Division | Contai Sub-Division | Laying distribution pipe line & Accommodate FHTC (74 nos) under JJM with allied work for Ita Baria- PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (PART-F) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000909/2022-2023 | 3464/TD | 27/03/2023 | 1030 | LAKSHMI NARAYAN ENTERPRISE | 19.34 | 0 | 70
2851 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000182/2023-2024 | 631/W | 20/02/2024 | 0 | Resource Division | 12.74 | 0 | 0
2852 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000310/2022-2023 | 2966/TD | 27/02/2023 | 0 | Resource Division | 171.72 | 0 | 0
2853 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 695 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000260/2023-2024 | 534/TD | 12/05/2023 | 973 | M/S SREE DURGA ENTERPRISE | 199.79 | 140.37 | 75
2854 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC ( 288 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- C) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000264/2023-2024 | 533/TD | 12/05/2023 | 984 | M/S SREE DURGA ENTERPRISE | 111.4 | 0 | 82
2855 | Tamluk Division | Digha Sub-Division | Drum Sheet walling, left out pipe line, road restoration, Accommodate FHTC (27 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - B ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000298/2024-2025 | 3067/TD | 19/09/2024 | 30 | DHANANJOY DAS | 34.51 | 0 | 0
2856 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundation ) & Accommodate FHTC ( 534 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part - A) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000409/2023-2024 | 1095/TD | 08/06/2023 | 1017 | RELIABLE CONSTRUCTIONS | 253.87 | 60.93 | 25
2857 | Tamluk Division | Digha Sub-Division | Drum Sheet walling , pipe line(for FHTC), road restoration, Accommodate FHTC (60 Nos) and others allied works under JJM for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part ¿ A ) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000534/2024-2025 | 210/TD | 15/01/2025 | 30 | RELIABLE CONSTRUCTIONS | 23.37 | 0 | 0
2858 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (275 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- D) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000920/2022-2023 | 3557/TD | 29/03/2023 | 30 | BUNBA CONSTRUCTION | 39.82 | 23.93 | 65
2859 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line, & Accommodate FHTC (116 Nos) under JJM with allied work for Uttar Gopalpur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part- E) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000921/2022-2023 | 3558/TD | 29/03/2023 | 20 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.49 | 0 | 60
2860 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Uttar Gopalpur PWSS at Ramnagar-II Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001047/2023-2024 | 377/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2861 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000173/2023-2024 | 109/TD | 05/01/2024 | 0 | Resource Division | 11.75 | 0 | 0
2862 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000217/2022-2023 | 2687/TD | 06/02/2023 | 0 | Resource Division | 21.28 | 0 | 0
2863 | Tamluk Division | Contai Sub-Division | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 860 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 0 | 30
2864 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000086/2024-2025 | 2967/TD | 12/09/2024 | 0 | Resource Division | 2.47 | 0 | 0
2865 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | RTOR000206/2022-2023 | 2399/TD | 16/01/2023 | 0 | Resource Division | 3.44 | 0 | 0
2866 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 450 cum RCC OHR at Ailan PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000186/2024-2025 | 2196/TD | 09/07/2024 | 10 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 100
2867 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000131/2022-2023 | 2415/TD | 16/01/2023 | 0 | Resource Division | 25.14 | 0 | 0
2868 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the New Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Tamluk Dev. Block (Av. depth 205 mtr.) = 03 Unit, Sahid Matangini Dev. Block (Av. depth 205mtr.) = 01 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 06 Unit. Name of Site : i) G.P.- Anantapur-I, Mouza- Maisali, J.L. No.-127, Plot No.- 16 under Tamluk Dev. Block, ii) G.P.- Municipality, Mouza- Daharpur, J.L. No.- 276, Plot No.- 442 under Tamluk Dev. Block, iii) G.P.- Pipulberia-I, Mouza - Gaurangapur, J.L. No.-150, Plot No.- 373 under Tamluk Dev. Block, iv) G.P.- Balluk-I, Mouza - Janubasan RH, J.L. No.- 44, Plot No.- 40 under Sahid Matangini Dev. Block, v) G.P.- Sarbodaya, Mouza- Naskarpur, J.L. No.-262, Plot No.- 120 under Egra-II Dev. Block & vi) G.P.- Basudevpur, Mouza- Shyamharibar, J.L. No.- 266, Plot No.- 3611 under Egra-II Dev. Block. |  |  | ORD/000045/2022-2023 | 175/TD | 25/04/2022 | 45 | CHANDA AGENCIES | 62.48 | 59.93 | 100
2869 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Khejuri-II Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 01Unit. Name of Site : i) G.P.- Nijkasba, Mouza- Thanaberia, J.L. No.- 98, Plot No.- 328 under Khejuri-II Dev. Block. |  |  | ORD/000051/2022-2023 | 296/TD | 06/05/2022 | 25 | SK. NUR ISLAM | 11.05 | 10.88 | 100
2870 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Ramnagar-I Dev. Block (Av. depth 230mtr.) = 01 Unit, Ramnagar-II Dev. Block (Av. depth 205mtr.) = 02 Unit & Egra-II Dev. Block (Av. depth 205mtr.) = 02 Unit ] Total 05 Unit. Name of Site : i) G.P.- Talgachari-I, Mouza- Talgachari, J.L. No.-108, Plot No.- 633 under Ramnagar-I Dev. Block, ii) G.P.- Balisai, Mouza- Bararankua, J.L. No.-200, Plot No.-307 under Ramnagar-II Dev. Block, iii) G.P.-Maithana, Mouza - Demuria Paikbar, J.L. No.-142, Plot No.-275 under Ramnagar-II Dev. Block, iv) G.P.- Paniparul, Mouza -Paniparul, J.L. No.-203, Plot No.-3329 under Egra-II Dev. Block & v) G.P.- Dubda, Mouza- Dubda, J.L. No.-191, Plot No.-38 under Egra-II Dev. Block. |  |  | ORD/000277/2021-2022 | 1526/TD | 11/01/2022 | 45 | BASANTA KUMAR MAITY | 53.79 | 53.72 | 100
2871 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Contai-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Contai-III Dev. Block (Av. depth 260 mtr.) = 01 Unit ] Total 02 Unit. Name of Site : i) G.P.- Sabajpur, Mouza- Sabajpur, J.L. No.- 296, Plot No.- 503 under Contai-I Dev. Block, & ii) G.P.- Debendra, Mouza- Balageria, J.L. No.- 79, Plot No.- 250 under Contai-III Dev. Block, |  |  | ORD/000278/2021-2022 | 1527/TD | 11/01/2022 | 30 | SRIMANTA KUMAR MAITY | 22.46 | 10.79 | 100
2872 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Deshpran Dev. Block (Av. depth 230 mtr.) = 01 Unit ] Total 01 Unit. Name of Site : i) G.P.- Basntia, Mouza- Purba Mukundapur, J.L. No.- 488, Plot No.- 120 under Deshpran Dev. Block |  |  | ORD/000279/2021-2022 | 1528/TD | 11/01/2022 | 20 | SUBRATA KUMAR BERA | 11.09 | 11.03 | 100
2873 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Nandakumar Dev. Block (Av. depth 260 mtr.) = 02 Unit, Mahishadal Dev. Block (Av. depth 260mtr.) = 01 Unit, Sutahata Dev. Block (Av. depth 260 mtr.) = 02 Unit & Kolaghat Dev. Block (Av. depth 205 mtr.) = 01 Unit ] Total 06 Unit. |  |  | ORD/000280/2021-2022 | 1529/TD | 11/01/2022 | 45 | ARABINDA GHOSH | 69.7 | 65.53 | 100
2874 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-II Dev. Block (Av. depth 230 mtr.) = 07 Unit ] Total 07 Unit. |  |  | ORD/000281/2021-2022 | 1530/TD | 11/01/2022 | 50 | MIDNAPUR PIPE CONCERN | 66.72 | 65.61 | 100
2875 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Chandipur Dev. Block (Av. depth 230 mtr.) = 02 Unit, Haldia Dev. Block (Av. depth 260mtr.) = 01 Unit, Panskura-I Dev. Block (Av. depth 205 mtr.) = 01 Unit & Patashpur-II Dev. Block (Av. depth 230 mtr.) = 02 Unit ] Total 06 Unit. |  |  | ORD/000282/2021-2022 | 1531/TD | 11/01/2022 | 45 | EQUIPMENTS AND SPARES AGENCIES | 64.74 | 63.36 | 100
2876 | Tamluk Division |  | Installation of 01 (one) no. 2.00 H.P. capacity Solar Photovoltiaic Submerssible Pump Set (900 watt) within the Newly constructed Tube well Size (150mm.x80mm.x diff.depth.) along with 900 watt peak capacity Solar Photovoltatic array panels on structure including Supply & Delivery of approved quality materials with all allied work at different Block of Tamluk Division, PHE Dte. within Purba Medinipur Zilla Parishad. [ Bhagwanpur-I Dev. Block (Av. depth 230 mtr.) = 03 Unit & Khejuri-II Dev. Block (Av. depth 260 mtr.) = 02 Unit ] Total 05 Unit. |  |  | ORD/000283/2021-2022 | 1532/TD | 11/01/2022 | 45 | MIDNAPUR PIPE CONCERN | 50.45 | 48.67 | 100
2877 | Tamluk Division |  | Installation of display Board at 54 nos. different work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. |  |  | ORD/000329/2024-2025 | 3288/TD | 05/10/2024 | 20 | MISHRA ENTERPRISE | 9 | 0 | 100
2878 | Tamluk Division |  | Diesel Motor Cab/Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage IV) on daily rate basis for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. from 01.07.2023 to 31.12.2023 (Six) Months. |  |  | ORD/000529/2023-2024 | 1299/TD | 30/06/2023 | 184 | JOY MAA TARA TRAVELS & TRANSPORT | 0.87 | 0.37 | 100
2879 | Tamluk Division |  | Continuation Work Order for Hiring of Diesel Motor Cab/ Luxury Taxy (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.12.2022 to 31.05.2023 i.e. 06 b(Six) months for the use of the office of the Assistant Engineer, RWS Tamluk Sub-Division, PHE Dte. |  |  | ORD/000939/2022-2023 | 375/RWS/TSD | 30/11/2022 | 156 | SRIMANTA PANJA | 0.74 | 1.95 | 100
2880 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 50 cum OHR & Accommodate FHTC (131 nos) under JJM with allied work for PANCHBERRYA PWSS in Sahid Matangini Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000513/2023-2024 | 1742/TD | 01/08/2023 | 719 | S.D. CONSTRUCTION | 141.9 | 0 | 0
2881 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000162/2023-2024 | 116/TD | 05/01/2024 | 0 | Resource Division | 0.81 | 0 | 0
2882 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000347/2022-2023 | 3017/TD | 27/02/2023 | 0 | Resource Division | 7.21 | 0 | 0
2883 | Tamluk Division | Tamluk Sadar Sub-Division | Laying of Left-Out portion uPVC Pipe line due to uncovered area under Dona Zone-I Water Supply Scheme under Tamluk Sub-Division of Tamluk Division, PHE Dte.(Phase-II) | Assistant Engineer | Junior Engineer | ORD/000118/2023-2024 | 249/TD | 19/04/2023 | 30 | GHOSH ENTERPRISE | 85.84 | 79.22 | 95
2884 | Tamluk Division | Tamluk Sadar Sub-Division | Retrofitting to accommodate FHTC (610 nos.) under JJM in Dona Zone-I Water Supply Scheme within Moyan Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. (Phase-II) | Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 250/TD | 19/04/2023 | 25 | GHOSH ENTERPRISE | 23.24 | 0 | 0
2885 | Tamluk Division | Contai Sub-Division | Providing 1321 Nos FHTC (Functional Household Tap Connection) with allied works of Arjunnagar & its adjoining mouzas Water Supply Scheme under Bhagawanpur-II Block under Contai Sub Division of Tamluk Division, PHE DTe.Purba Medinipur (Phase -II) | Assistant Engineer | Junior Engineer | ORD/000401/2023-2024 | 1069/TD | 08/06/2023 | 45 | TAPAS SANTRA | 91.09 | 0 | 0
2886 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000058/2023-2024 | 2096/TD | 29/08/2023 | 0 | Resource Division | 26.91 | 0 | 0
2887 | Tamluk Division | Contai Sub-Division | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000060/2023-2024 | 2636/TD | 13/10/2023 | 0 | Resource Division | 8.14 | 0 | 0
2888 | Tamluk Division | Digha Sub-Division | Retrofitting to accommodate FHTC under JJM in PAYA ( MAHAPRABHU) PWSS ( Phase-II) Block - Ramnagar-I in the District of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 240/TD | 19/04/2023 | 30 | MAITY CONSTRUCTION | 67.92 | 57.26 | 100
2889 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000125/2023-2024 | 93//TD | 05/01/2024 | 0 | Resource Division | 1.66 | 0 | 0
2890 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000271/2022-2023 | 2672/TD | 06/02/2023 | 0 | Resource Division | 10.22 | 0 | 0
2891 | Tamluk Division | Contai Sub-Division | Laying of different dia HDPE Pipe line to accommodate remaining FHTC under Augmentation of Amtalia PWSS within Contai-II (Deshpran) Block under Contai Sub-Division of Tamluk Division,PHE Dte., in the District of Purba Medinipur | Assistant Engineer | Junior Engineer | ORD/000142/2023-2024 | 285/TD | 20/04/2023 | 40 | GHOSH ENTERPRISE | 56.31 | 0 | 100
2892 | Tamluk Division | Contai Sub-Division | Laying Distribution Pipe Line With allied Works for Augmentation Of Dhanghara Water Supply Scheme within Contai-III Block under Contai Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur District. (PHASE-II) | Assistant Engineer | Junior Engineer | ORD/000319/2023-2024 | 665/TD | 19/05/2023 | 30 | M/S S. S. ENTERPRISE | 58.98 | 0 | 100
2893 | Tamluk Division | Contai Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) 1 (One) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method for Replacement of 2nd Tube Well for Dhanghara W/S Scheme within Contai - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 250 mtr. Deep Tube well by direct rotary rig method at 3rd Tubewell Site (Boosting T/W) of Pratapdighi W/S Scheme within Patashpur - II Block under Contai Sub-Division of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Mukutshila Zone - I PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. iv) Sinking of 300 x 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with 200 dia.uPVC. Strainer of 30m.length all complete including cost of materials at 3rd Tube Well Site for Kamarda PWSS in Khejuri- I Block including supply of all labour & materials within Contai Sub-Division under East Midnapore Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000541/2023-2024 | 1904/TD | 10/08/2023 | 529 | B. K. ENTERPRISE | 74.56 | 0 | 100
2894 | Tamluk Division | Tamluk Sadar Sub-Division | Name of Work: Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Gobindanagar W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Tube well by direct rotary rig method at Boosting Tubewell Site of Dakshin Mechogram W/S Scheme within Panskura-I Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/000019/2023-2024 | 117/TD | 06/04/2023 | 40 | AQUATECH ENGINEER | 37.12 | 16.48 | 100
2895 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000009/2023-2024 | 346/TD | 26/04/2023 | 0 | Resource Division | 4.41 | 0 | 0
2896 | Tamluk Division | Tamluk Sadar Sub-Division | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Habichak W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 240 mtr. Deep Replacement of Tube well by direct rotary rig method at Boosting Tubewell Site of Kulbari W/S Scheme within Chandipur Block under Tamluk Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000018/2023-2024 | 116/TD | 06/04/2023 | 40 | AQUATECH ENGINEERS | 74.22 | 0 | 100
2897 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | RTOR000007/2023-2024 | 348/TD | 26/04/2023 | 0 | Resource Division | 8.83 | 0 | 0
2898 | Tamluk Division | Haldia Sub-Division | Construction of boundary wall in 3rd tubewell site of Natshal Lakshya Zone II under Haldia Sub-Division of Tamluk Division, P.H.E. Dte.(Length of Boundary wall-50mtr) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000396/2023-2024 | 1080/TD | 08/06/2023 | 30 | M/S SOURAV MAHAPATRA | 5.91 | 5.27 | 100
2899 | Tamluk Division | Haldia Sub-Division | Repairing & renovation of switch Room cum Chlorine Room at 1st Tube Well site & 2nd Tube well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000464/2022-2023 | 1876/TD | 22/11/2022 | 30 | PRASANTA MONDAL | 4.13 | 4 | 0
2900 | Tamluk Division | Haldia Sub-Division | Construction of (3.60 Mtr. X 3.00 Mtr.) Switch Room cum Chlorine Room with water supply & sanitary arrangement including Plinth Protection at 3rt Tube Well site of Natshal Lakshya Zone-II Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000493/2022-2023 | 1879/TD | 22/11/2022 | 60 | DIPANKAR MALAKAR | 5.11 | 5.09 | 100
2901 | Tamluk Division | Haldia Sub-Division | Canal crossing , laying Rising main, Construction of boundary wall of Head work site & 2nd TW site & Drum Sheet walling of Natshal Lakshya (Zone-II) Water Supply Scheme within Mahisadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000590/2023-2024 | 2207/TD | 01/09/2023 | 502 | RAJ KUMAR SINGHA | 91.71 | 0 | 30
2902 | Tamluk Division | Haldia Sub-Division | Augmentation of ground water based Natshal Lakshya Zone-II Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 1000 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000747/2022-2023 | 2594/TD | 30/01/2023 | 180 | RAJ KUMAR SINGHA | 986.55 | 0 | 65
2903 | Tamluk Division | Haldia Sub-Division | Supply and delivery of 3 nos office Table/Executive Desk (Godrej - 120cm X 60cm X 72.80cm, RH) 2 nos Chairs (without arms rest) and 2 nos stainless steel rack (72inch X 36inch X 15 inch) with 5nos selves) (all articles are should be of Godrej interio Brand) under office of the Assistant Engineer, Haldia Sub-Division, PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001012/2023-2024 | 688/HSD, | 31/01/2024 | 343 | MALLIK TRADERS | 0.99 | 0 | 100
2904 | Tamluk Division | Haldia Sub-Division | Installation of 4 Nos. Display Board at different PWSS works sites under Haldia Sub-Division of Tamluk Division, PHE Dte.(for Tabakhali PWSS, Dakshinchak Zone-1 PWSS, Dakshinchak Zone-II PWSS, Natshal lakshya Zone-II PWSS) (Phase-V) | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001170/2023-2024 | 766/HSD, | 27/02/2024 | 7 | SNEHASIS BERA | 0.83 | 0 | 100
2905 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000141/2023-2024 | 122/TD | 05/01/2024 | 0 | Resource Division | 16.51 | 0 | 0
2906 | Tamluk Division | Tamluk Sadar Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | RTOR000259/2022-2023 | 2683/TD | 06/02/2023 | 0 | Resource Division | 16.55 | 0 | 0
2907 | Tamluk Division |  | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Barchunfali Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Silampur Water Supply Scheme within Contai-I Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150 mm. dia. x 230 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bankiput Water Supply Scheme within Contai-II (DESOPRAN) Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150 mm. dia. x 250 mtr. deep tube well by direct rotary rig method for 1(One) no. Boosting Tube Well for Source Augmentation of Bamunia Water Supply Scheme within Contai-II Block under Contai Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. |  |  | ORD/000021/2023-2024 | 119/TD | 06/04/2023 | 703 | B. K. ENTERPRISE | 53.77 | 0 | 75
2908 | Tamluk Division | Digha Sub-Division | Quotation Bill for New Service connection at T/W NO-II, ZONE-I Of SANKARPUR W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004721008/QUOT/03 DT. 07-05-2024 Application NO- 2004721008 Application type-New connection Consumer Id- 204298882 | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | BILL/00442/2024-2025 | BP-2024-25-170 | 10/06/2024 | 0 | WBSEDCL | 31.79 | 0 | 0
2909 | Tamluk Division | Digha Sub-Division | Laying distribution pipe line due to Re-design, & Accommodate Balance FHTC ( 155 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur. (Part Work Order 1/2) | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000195/2024-2025 | 315/TD | 22/01/2025 | 30 | PRANAB KUMAR DAS | 49.33 | 0 | 0
2910 | Tamluk Division | Digha Sub-Division | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Sankarpur Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000497/2022-2023 | 1933/TD | 28/11/2022 | 20 | ASTER CONSULTANCY | 3.46 | 3.37 | 100
2911 | Tamluk Division | Digha Sub-Division | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 250 Cum OHR & Accommodate FHTC ( 355 Nos) under JJM with allied work for SANKARPUR (Zone-I) PWSS within Ramnagar-I Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/000520/2023-2024 | 1757/TD | 01/08/2023 | 909 | SUSIL KUMAR HAZRA | 193.96 | 0 | 55
2912 | Tamluk Division | Digha Sub-Division | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Sankarpur Zone-I PWSS at Ramnagar-I Block under Tamluk Division,PHE Dte. | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | ORD/001045/2023-2024 | 375/TD | 29/01/2024 | 10 | ASTER CONSULTANCY | 0.95 | 0 | 100
2913 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000053/2023-2024 | 2074/TD | 28/08/2023 | 0 | Resource Division | 13.25 | 0 | 0
2914 | Tamluk Division | Digha Sub-Division | Material Requisition To Resource Division | Assistant Engineer,Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Division. | Junior Engineer,Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division. | RTOR000098/2023-2024 | 3001/TD | 29/11/2023 | 0 | Resource Division | 2.99 | 0 | 0
Total | [10 empty] | 253976.61 | 53103.18