## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | RCFA Division -I | Asansol Mechanical Division | Separate connection for Hazrabera under Prayagpur OHR Kanksa Zone-II (Part-B) under Augmentation of Tilakchandrapur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001061/2023-2024 | 707/RCD-I | 29/02/2024 | 15 | MALLICK CONSTRUCTION | 0.91 | 0 | 100
2 | RCFA Division -I | Asansol Mechanical Division | Restoration of damaged road surface due to the cause of earthwork in connection with placement of under ground water pipe line in stretches at Pandabeswar-Natundanga Road from Chainage 0.000 km to 2.00 Km 2.500 to 3.000 Km 5.500 to 5.800 km, 7.900 km to 8.141 km in the district of Paschim Bardhaman under Asansol Division PWD | Assistant Engineer-II | Junior Engineer-5 | BILL/01547/2023-2024 | 629/23-24 | 15/03/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 33.26 | 0 | 0
3 | RCFA Division -I | Asansol Mechanical Division | Permission for laying of water pipeline along NH-02 from Duburdih (km. 441+780) to Kalla More (Km. 462+080) and 1 no. crossing acros NH-2 in the state of West Bengal unde RCFA Divn-I PHE Dte - Submission of Bank Guarantee reg. | Assistant Engineer-I | Junior Engineer-4 | BILL/00053/2024-2025 | 268/24-25 | 05/09/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 104.25 | 0 | 0
4 | RCFA Division -I | Asansol Mechanical Division | Restoreation and repairing work from Ch. 13415 to 14300 of Neamatpur - Rupnarayanpur Road (FR-10) under Asansol Division, PWD for laying of distribution system of Zone - VII under JJM work in the district of Paschim Bardhaman during the year 2024-2025 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | BILL/00307/2024-2025 | 168/24-25 | 23/07/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 14.85 | 0 | 0
5 | RCFA Division -I | Asansol Mechanical Division | Execution of agreement with Damodar Valley Corporation for drawl of 15.757 (Fifteen point seven five seven) MGD raw water for RCFA Part-II piped water supply scheme under RCFA Public Health Engineering Directorate, Asansol from Maithon Reservoir | Assistant Engineer-I | Junior Engineer-4 | BILL/00769/2023-2024 | 371/23-24 | 21/11/2023 | 0 | DAMODAR VALLEY CORPORATION | 13.08 | 0 | 0
6 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-55 for Asansol East Cabin - Asansol East Hump under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00834/2023-2024 | 404/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 149.35 | 0 | 0
7 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-57 for Kalipahari - Nimcha under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00837/2023-2024 | 410/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 5.28 | 0 | 0
8 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-56 for Damodar under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00839/2023-2024 | 405/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 19.69 | 0 | 0
9 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-61 for Baktarnagar - Raniganj under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00842/2023-2024 | 409/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 9.91 | 0 | 0
10 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-53 for Salanpur - Sitarampur link Cabin under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00848/2023-2024 | 403/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 15.82 | 0 | 0
11 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-52 for Damagoria under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00850/2023-2024 | 407/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 15.2 | 0 | 0
12 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-58 for Sonachara - Topsi under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00855/2023-2024 | 412/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 10.27 | 0 | 0
13 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-59 for Pandabeswar - Ukhra under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00859/2023-2024 | 408/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 8.26 | 0 | 0
14 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-60 for Topsi - Sripur under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00861/2023-2024 | 411/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 4.67 | 0 | 0
15 | RCFA Division -I | Asansol Mechanical Division | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-54 for Chinchuria - Sitarampur under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/00865/2023-2024 | 406/23-24 | 08/12/2023 | 0 | EASTERN RAILWAY | 4.78 | 0 | 0
16 | RCFA Division -I | Asansol Mechanical Division | Permission for laying of water pipeline along NH-02 from Duburdih (km 441.780) to Kalla More (k. 462.080) and 1 no crossing across NH-2 in th state of West Bengal under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. RCFA Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/01344/2023-2024 | 545/23-24 | 08/02/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 169.62 | 0 | 0
17 | RCFA Division -I | Asansol Mechanical Division | Restoration work of damaged road flank caused by PHE for laying water pipe line at kajora Haripur from 0.00 km to 10.74 km at Ukhra Madhaigand road rom 0.00 to 12.13 km at Galigram - Kutruki - Chandipur road between 9 km to 12 km , Raghunathpur - Kantaberia road at 19th km near kantabaria Raghunathpur Kantaberia road from 0.00 kmp to 3.50 near Jamdoba village under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I (Intake, RWRM, WTP, CWRMs & GLRs) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | BILL/01345/2023-2024 | 544/23-24 | 08/02/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 32.25 | 0 | 0
18 | RCFA Division -I | Asansol Mechanical Division | Damage of "PMGSY" and "Pathashree" Roads due to laying of PHED pipeline and tentative estimates for restoration | Assistant Engineer-I | Junior Engineer-4 | BILL/01354/2023-2024 | 549/23-24 | 12/02/2024 | 0 | WEST BENGAL STATE RURAL DEVELOPMENT AGENCY | 46.78 | 0 | 0
19 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying pipe line for Chapui, Kumardihi village under Ratibati Gram Panchayet, Raniganj Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000017/2024-2025 | 1520/RCD-I | 14/06/2024 | 45 | M/S U.G. ENTERPRISE | 11.77 | 0 | 100
20 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional laying of different dia HDPE pipe line at Madhudanga village and adjacent area within Jamuria Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000021/2024-2025 | 1524/RCD-I | 14/06/2024 | 45 | MD AAMIR KHAN | 20.3 | 0 | 100
21 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000024/2024-2025 | 1517/RCD-I | 14/06/2024 | 15 | INDIA PIPE FITTING CO | 96.97 | 0 | 100
22 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying & Pushing by adopting trench less technology (e.g. jack Pushing Method etc) additional for Distribution Network of Augmentation of RCFA Part-II PWSS within command area of Vol-I (Segment-V) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000028/2024-2025 | 1581/RCD-I | 27/06/2024 | 30 | DIP CONSTRUCTION | 37.13 | 0 | 0
23 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Stack Yard (including filling of low land), Jungle cutting, Surface dressing, Dismantling related to RCFA Part-II WTP Site at Kalyaneswari Town ship under RCFA Division-I PHE Dte. Improvement of RCFA Part-II Vol-I | Assistant Engineer-I | Junior Engineer-4 | ORD/000029/2024-2025 | 1582/RCD-I | 27/06/2024 | 45 | UNITED CONSTRUCTION | 18.67 | 0 | 100
24 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of CWR 150 cum at Shyamla for Kendra Khottamdihi of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000033/2024-2025 | 1587/RCD-I | 27/06/2024 | 90 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 28.76 | 0 | 90
25 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block including FHTC & allied work Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-I | Junior Engineer-4 | ORD/000034/2024-2025 | 1588/RCD-I | 27/06/2024 | 45 | SIMA ENTERPRISE | 27.22 | 0 | 100
26 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for laying pipe line and allied works from Kelejora Health Center towards Domohani Bazar within Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000035/2024-2025 | 1589/RCD-I | 27/06/2024 | 45 | R B ENTERPRISE | 34.16 | 0 | 100
27 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Extension and renovation work of Annex Building including other allied works inside the premises of RCFA Division-I Office Campus under Augmentation of RCFA Part-II, Volume-I PWSS under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000048/2024-2025 | 1698/RCD-I | 11/07/2024 | 180 | M/S KALYANI ENTERPRISE | 28.95 | 0 | 100
28 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for providing FHTC within command area of Zone-I (Dendua OHR Site) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte.(Part-B) | Assistant Engineer-I | Junior Engineer-4 | ORD/000052/2024-2025 | 1742/RCD-I | 18/07/2024 | 355 | TARA CONSTRUCTION | 66.88 | 0 | 100
29 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Providing of different dia water regulating apparatus (cast iron and Ductile iron) of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000072/2024-2025 | 1938/RCD-I | 07/08/2024 | 15 | MAKALI ENGINEERING CORPORATION | 96.16 | 0 | 100
30 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Providing of different dia water regulating apparatus (cast iron and Ductile iron) of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000073/2024-2025 | 1937/RCD-I | 07/08/2024 | 15 | MAKALI ENGINEERING CORPORATION | 92.83 | 0 | 100
31 | RCFA Division -I | Asansol Mechanical Division | Supply & erection of Govt. Land Boards (51 nos) having M.S. Channel/Angle posts& 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Raniganj, Andal, Pandabeswar, Kanksa & Durgapur-Faridpur Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000134/2024-2025 | Camp-02-Raniganj/AE/2024- | 20/08/2024 | 15 | MUKHERJEE TRADERS | 9.91 | 0 | 100
32 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply & erection on Information Boards (51 nos) having M.S. Channel/Angle posts & 1.5 mm thick M.S Synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur, Barabani & Jamuria Block for Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000136/2024-2025 | 2231/RCD-¦ | 10/09/2024 | 15 | SHARMA ENGINEERING WORKS | 9.9 | 0 | 100
33 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting and regulating apparatus for distribution system and rising main under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000138/2024-2025 | 2232/RCD-i | 10/09/2024 | 30 | MAKALI ENGINEERING CORPORATION | 94.06 | 0 | 100
34 | RCFA Division -I | Asansol Mechanical Division | Supply & erection of Govt. Land Boards ( 102 nos) having M.S. Channel/Angle posts& 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000139/2024-2025 | Camp-02-Jamuria-AE/2024-2 | 20/08/2024 | 15 | UNITED CONSTRUCTION | 20.45 | 0 | 100
35 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing between Chinchuria (CCR) and Sitarampur (STN) at KM 34/8-9 (Sitarampur end of LC No. 12/A/E) in Asansol Division under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000424/2023-2024 | 2622/RCD-I | 13/09/2023 | 15 | M/S MONDAL ENTERPRISE | 31.21 | 0 | 100
36 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-70 mtr) and drain (Length-160 mtr) at Bansketia OHR site of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-I under Salanpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000432/2023-2024 | 2663/RCD-I | 26/09/2023 | 30 | AMAR CONSTRUCTION | 39.04 | 0 | 100
37 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for 450 mm dia pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc) Ch. 222.05 near Damlia OCP for IOCL crossing of rising main (Part-A) under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000517/2024-2025 | 117/RCD-I | 08/01/2025 | 236 | MD AAMIR KHAN | 29.48 | 0 | 100
38 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Interconnection at Kalyaneswari WTP Site, Banskatia OHR and bypass line, Kadvita More branch line, Dendua OHR, Rupnarayanpur OHR and construction of valve chamber etc under RCFA Part-II Vol-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000518/2024-2025 | 118/RCD-I | 08/01/2025 | 45 | MAK CONSTRUCTION CO | 46.44 | 0 | 100
39 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply and delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000550/2023-2024 | 3044/RCD-I | 17/10/2023 | 20 | INDIA PIPE FITTING CO | 94.09 | 0 | 100
40 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Zone VII (Part E) water Supply scheme within command area of Zone VII under RCFA Div-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000633/2023-2024 | 3444/RCD-I | 24/11/2023 | 557 | TARA CONSTRUCTION | 2.64 | 0 | 100
41 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for Supply and laying of MS water Carrier pipe of dia 600 mm, 450 mm, 350 mm, 250 mm and allied works in connection of Rising Main (Part-A) to Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000635/2023-2024 | 3417/RCD-1 | 24/11/2023 | 30 | MD AAMIR KHAN | 70.38 | 0 | 100
42 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying E.R.M.S. Black pipe of approved quality including carring, stacking at works for crossing of 12 nos culvert/cannel of by the side of PWD road under Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/000651/2023-2024 | 3426/RCD-1 | 24/11/2023 | 20 | SWATI CORPORATION | 7.09 | 0 | 100
43 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Bolkunda and surrounding villages within Filberia-Bolkunda Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000652/2023-2024 | 3449/RCD-I | 24/11/2023 | 15 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.52 | 0 | 100
44 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balanced work at Shyamsundarpur Zone-13 of Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000926/2024-2025 | 2802_RCD-1 | 29/11/2024 | 244 | MD AAMIR KHAN | 95.62 | 0 | 100
45 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for concrete dismantling restoration of concrete for 350 mm D.I. and 315 mm HDPE pipe line repair damaged PVC and GI pipe line and other allied works for Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I within command area of Zone-VIII under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-4 | ORD/000945/2023-2024 | 490/RCD-I | 12/02/2024 | 30 | TARA CONSTRUCTION | 11.01 | 0 | 100
46 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Distribution Network for Laying distribution system including FHTC for 5 (Two) nos uncoverd village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001134/2023-2024 | 807/RCD-I | 14/03/2024 | 505 | UMA ENTERPRISE | 107.86 | 0 | 30
47 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for Shifting of Rising main for extension of Bonjemary Colliery and ECL Railway siding near Dalmia OCP under ECL Deposite Scheme under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001173/2023-2024 | 1013/RCD-I | 16/03/2024 | 15 | R B ENTERPRISE | 30.24 | 0 | 100
48 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc), additional for Rising main and culvert crossing near Semlya Head Work Site under Jamuria Block under Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Division I PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001207/2023-2024 | 1010/RCD-I | 16/03/2024 | 15 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.72 | 0 | 100
49 | RCFA Division -I | Asansol Mechanical Division | Additional works for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) and MS water carrier pipe under I.O.C.L pipe line at Basudevpur village of distribution network for RCFA Part-I within command area of Zone-I (Part B) Augmentation of RCFA Part II Piped Water Supply Scheme Volume -I under RCFA Div-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-4 | ORD/001246/2023-2024 | Camp-02_Basudebpur/AE/23- | 15/03/2024 | 30 | SWATI CORPORATION | 10.13 | 0 | 100
50 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000039/2023-2024 | 2980/RCD-I | 12/10/2023 | 0 | Resource Division | 5756.61 | 0 | 0
51 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000041/2023-2024 | 3662/RCD-I | 28/12/2023 | 0 | Resource Division | 35.15 | 0 | 0
52 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-4 | RTOR000042/2023-2024 | 106/RCD-I | 10/01/2024 | 0 | Resource Division | 308 | 0 | 0
53 | RCFA Division -I | RCFA Division I | PAYMENT OF WALEAVE PLAN & SURVEY CHARGES ER-ASN-2024-WL-10 | Assistant Engineer 2 |  | BILL/00002/2024-2025 | 03/24-25 | 18/04/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
54 | RCFA Division -I | RCFA Division I | Payment of Way leave Plan & Survey charges for track crossing proposal with Application ID ER-ASN2024-WL-18 dt 15.04.2024 | Assistant Engineer 2 |  | BILL/00012/2024-2025 | 11/24-25 | 24/04/2024 | 0 | EASTERN RAILWAY | 0.25 | 0 | 0
55 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network & allied work at Ondal Block of RCFA Part-II (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000028/2023-2024 | 1618/RCD I | 25/04/2023 | 372 | M/S UNIT CONSTRUCTION | 231.44 | 112.93 | 100
56 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for supplying & laying M.S pipe, Supplying specials for Interconnection work for Improvement of RCFA Part-I for Augmentation of RCFA Part-II (Zone-2) PWSS within command area of Zone-VIII under RCFA Div-I, PHE Dte. | Assistant Engineer 2 |  | ORD/000085/2024-2025 | 2110/RCD-I | 27/08/2024 | 25 | TARA CONSTRUCTION | 13.73 | 0 | 100
57 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works for Laying & pushing of 600mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g Jack pushing method) , MS water carrier pipe and other allied works at different location (Node point:- 226-232, 289-292, 441-442, 69-76, 63-64, 256-272 ) of distribution network for Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Div-I, PHE Dte. | Assistant Engineer 2 |  | ORD/000089/2024-2025 | 2114/RCD-I | 27/08/2024 | 60 | SWATI CORPORATION | 35.82 | 0 | 100
58 | RCFA Division -I | RCFA Division I | Formal Work order for construction of 900 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-2) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000098/2023-2024 | 1846/RCD-I | 31/05/2023 | 366 | M/S CHANDI CHARAN ROY | 199.25 | 99.63 | 90
59 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of important roads (2 nos location at zone-4A) of Augmentation PWSS of RCFA Part-II (Zone-2) under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 2 |  | ORD/000110/2024-2025 | 2132/RCD-I | 27/08/2024 | 30 | UNITED CONSTRUCTION | 39.74 | 0 | 100
60 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000157/2023-2024 | 1902/RCD-I | 09/06/2023 | 245 | M/S SANTANU PALIT & CO. | 182.7 | 0 | 70
61 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 01 (One) location on Salanpur ¿ Khuidica road and supplying and laying MS pipe near culvert and gas line including ancillary work within command area of Zone-I (Dendua OHR Site) Part-C under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000220/2023-2024 | 2225/RCD-I | 17/07/2023 | 259 | DAS & CHAKRABORTY | 15.47 | 12.05 | 100
62 | RCFA Division -I | RCFA Division I | Formal Work Order for Additional supplying laying 280 mm & 225 mm dia HDPE pipe line for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000311/2023-2024 | 2384/RCD-I | 07/08/2023 | 60 | SWATI CORPORATION | 124.64 | 0 | 80
63 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution of pipe line from Alinagar OHR to Khattardihi Village via Minsa Das Para including Laying & Pushing by adopting trench less technology (e.g, Jack Pushing Method etc) & other allied work under Shyamla GP under Augmentation PWSS of RCFA Part-II (Zone-2) Block - Andal, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000515/2024-2025 | 115/RCD-I | 08/01/2025 | 45 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 47.67 | 0 | 80
64 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line towards Teli Para (Sansad -XIV) under Ukhra area Block- Andal & Pandabswar of Augmentation of RCFA Part-II (Zone-2) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000559/2023-2024 | 3188/RCD-I | 01/11/2023 | 15 | NILIMA CONSTRUCTION | 2.49 | 0 | 100
65 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-2) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000564/2022-2023 | 3358/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 100
66 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, aligning & Laying of different dia HDPE pipe line and allied works for dedicated line to Chotkara village and Satta under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000579/2023-2024 | 2989-RCD-I | 12/10/2023 | 15 | SHREE DURGA ENTERPRISE | 5.85 | 0 | 100
67 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of damaged collecting main in river Damodar rising main to D.P Colony OHR and allied works of DP colony W/S scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 |  | ORD/000611/2023-2024 | 3370/RCD-1 | 21/11/2023 | 15 | DURGA DAS MONDAL | 4.98 | 0 | 100
68 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara Block Anda & Pandabeswar of Ukhra under Augmentation of RCFA Part-II (Zone-2) PWSS under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 |  | ORD/000680/2022-2023 | 367/RCDI | 30/01/2023 | 30 | JAI MAHARAJ ENTERPRISE | 5.62 | 0 | 100
69 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE Pipe Line including concrete cutting, mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Ukhra under Additional works under Ukhra & its adjoining mouzas water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000693/2022-2023 | 382/RCD I | 30/01/2023 | 15 | B.T.M CONCERN | 20.71 | 16.81 | 100
70 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000017/2023-2024 | 2958/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
71 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-72 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00788/2023-2024 | 382/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
72 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-71 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00790/2023-2024 | 378/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.11 | 0 | 0
73 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-70 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00791/2023-2024 | 379/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.11 | 0 | 0
74 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-69 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00792/2023-2024 | 380/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
75 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-68 for Nimcha - J.K.Nagar under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00793/2023-2024 | 381/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
76 | RCFA Division -I | RCFA Division I | Way leave / track crossing proposal with Application ID ER-ASN-2023-WL-67 for Nimcha - Kalipahari under AUGMENTATION OF PWSS OF RCFA PART-II (ZONE-3) under RCFA Division-I, PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00794/2023-2024 | 383/23-24 | 22/11/2023 | 0 | EASTERN RAILWAY | 0.14 | 0 | 0
77 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) in Asansol Division under JJM under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000423/2023-2024 | 2621/RCD-I | 13/09/2023 | 15 | MAK CONSTRUCTION CO. | 62.81 | 0 | 100
78 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, Aligning, laying HDPE pipe & Supply Sluice Valve & construction of sluice valve chamber including providing FHTC and other allied works at Ratibati village Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000469/2023-2024 | 2874/RCD-1 | 06/10/2023 | 30 | NIYATI CONSTRUCTION | 7.87 | 0 | 100
79 | RCFA Division -I | RCFA Division I | Acceptance cum work order for 2nos of Emergency repairing work of 450 mm dia rising main at Upper Jamdoba and Nichu Para under RCFA Part-II W7S scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000483/2023-2024 | 2890/RCD-I | 06/10/2023 | 15 | KHEPI MAA TRADERS | 2.29 | 0 | 100
80 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 90mm dia HDPE pipe and allied works at Bauri para of Khandra area of Block-Ondal under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000487/2023-2024 | 2893/RCD-I | 06/10/2023 | 15 | KHEPI MAA TRADERS | 2.33 | 0 | 100
81 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Parasia Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000507/2023-2024 | 2969/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
82 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHADURPUR Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000508/2023-2024 | 2970/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
83 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for HARIPUR Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000509/2023-2024 | 2971/RCD-I | 11/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 0 | 100
84 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for RATIBATI Water Supply Scheme for Implementation of JJM at Jamuria Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000510/2023-2024 | 2972/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
85 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for BAHULA Water Supply Scheme for Implementation of JJM at Pandabeswar Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000511/2023-2024 | 2973/RCD-I | 11/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 0 | 100
86 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Panchgachia & Majiara Water Supply Scheme for Implementation of JJM at Barabani Block under RCFA DIVISION-I, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000512/2023-2024 | 2974/RCD-I | 11/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
87 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur in between KM 227/31-33 and Salanpur (SLS) ¿ Rupnarayanpur (RNPR) Station in Asansol Division of JJM under Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000518/2023-2024 | 2870/RCD-I | 06/10/2023 | 30 | SWATI CORPORATION | 67.3 | 0 | 100
88 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of HDPE pipeline and MS work and interconnection of Raniganj Chati,Baliapur and adjacent area of Zone-IX for Augmentation of PWSS of RCFA Part-II (Zone-3) under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000525/2024-2025 | 126/RCD-I | 08/01/2025 | 30 | DAWN CONSTRUCTION | 16.98 | 0 | 100
89 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency work for Withdrawing and Relaying of collecting main and other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar water supply scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000608/2023-2024 | 3368/RCD-1 | 21/11/2023 | 15 | M/S KALYAN ENTERPRISE | 2.78 | 0 | 100
90 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000620/2023-2024 | 3383/RCD-I | 21/11/2023 | 15 | MD. JAWED KHAN | 4.27 | 0 | 100
91 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying aligning, Laying of PVC pipe, HDPE pipe sluice valve, Sluice valve chamber and other allied works at Oriapara, Chapui Vaskadaora 7 nos pit to Rangadanga Talbagan under Ratibati Gram Panchayet under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000637/2023-2024 | 3419/RCD-1 | 24/11/2023 | 30 | M/S KALYAN ENTERPRISE | 7.78 | 0 | 100
92 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Withdrawing, supplying, aligning Relaying of 80 mm dia PVC pipe line, repairing of street stand post and other allied works at Goylapara under Tirat Gram Panchyat under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000639/2023-2024 | 3420/RCD-1 | 24/11/2023 | 30 | M/S KALYAN ENTERPRISE | 6.24 | 0 | 100
93 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-3)(Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000821/2022-2023 | 1002/RCDI | 22/03/2023 | 120 | SINGHA ROY & CO. | 392.43 | 265.75 | 86
94 | RCFA Division -I | RCFA Division I | Emergent Sinking of one no.200 x 165 mm Rig box tubewell at ADM Bunglow, Asansol, Paschim Bardhaman, Under R.C.F.A Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000888/2023-2024 | SpotNITCamp-02/ADMBunglow | 09/01/2024 | 7 | M/S CHANDI CHARAN ROY | 7.5 | 0 | 100
95 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying Aligning & laying HDPE pipe supplying sluice valve and others allied works of different places under Nutun Egara under Narayankuri W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000933/2023-2024 | 496/RCD-1 | 12/02/2024 | 45 | DIP CONSTRUCTION | 8.67 | 0 | 100
96 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Road Crossing by adopting trenchless technology at 3 (Three) nos locations near ECL stack yard including restoration of road from Dabor more to Amdanga more in connection to rising main Part-A under Improvement of RCFA Part-I in Connection of Rising Main (Part-A) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000957/2023-2024 | 482/RCD-I | 12/02/2024 | 45 | MD AAMIR KHAN | 44.01 | 0 | 100
97 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Laying MS pipe over bridge / culvert including adopting trench less technology (e.g. Jack Pushing Method etc) at 4 (Four) nos location within laying distribution system of Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000959/2023-2024 | 483/RCD-I | 12/02/2024 | 45 | TARAPRASAD SARKAR | 25.18 | 0 | 100
98 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of dismantling & concrete works, laterite and sand filling at distribution system network for RCFA Part-II (Zone-3) PWSS including FHTC & allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000977/2023-2024 | 493/RCD-I | 12/02/2024 | 35 | SINGHA ROY & CO. | 77.52 | 0 | 100
99 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Replacing existing UPVC pipe line with HDPE at Marickkota and different village under Salanpur Block under RCFA Part-I PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000981/2023-2024 | 509/RCD-I | 12/02/2024 | 45 | SUKHENDU MAJUMDAR | 6.37 | 0 | 0
100 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of sinking of 3 (Three) nos. 200 mm dia river bed tube well including collecting main in the river Damodar at Gourbazar H/W Site for Hourbazar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000982/2023-2024 | 510/RCD-I | 12/02/2024 | 25 | R B ENTERPRISE | 12.96 | 0 | 100
101 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work of 50 cum/hr capacity I.E. Plant at Churulia and Madanpur Head Works Site Augmentation of RCFA Part-II (Zone-3) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000989/2023-2024 | 475/RCD-I | 12/02/2024 | 120 | TARAPRASAD SARKAR | 31.29 | 0 | 100
102 | RCFA Division -I | RCFA Division I | Continuation of work order for Conducting route survey, design rising main network and preparation & submission of source Augmentation DPR for Ukhra OHR of RCFA (Part-I) PWSS. | Assistant Engineer 2 | Junior Engineer | ORD/001008/2023-2024 | 3523-A/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
103 | RCFA Division -I | RCFA Division I | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Improvement of Collector well by infiltration gallery at Kalajharia Part-II W/S Scheme | Assistant Engineer 2 | Junior Engineer | ORD/001011/2023-2024 | 3523-B/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
104 | RCFA Division -I | RCFA Division I | Continuation work order for Conducting route survey, design rising main network and preparation & submission of source augmentation DPR for Madanpur OHR of RCFA (Part-I) PWSS under RCFA DIVISION-I , P.H.E Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001012/2023-2024 | 3523-C/RCD-I | 04/12/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.97 | 0 | 100
105 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional repairing and maintenance work of RCC Elevated reservoir, Boundary Wall and other allied works at Mangalpur of 25000 gallon capacity under Augmentation of RCFA Part-II (Zone-3) Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001186/2023-2024 | 938/RCD-I | 15/03/2024 | 15 | M/S SUBHRADEEP | 16.89 | 0 | 100
106 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional providing FHTC of retrofitting at kumardiha Village (left out portion) of Kumardiha Mouza, GP-Ratibati Block Raniganj of Ratibati Water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001206/2023-2024 | 1023/RCD-I | 16/03/2024 | 30 | SAYAN CONSTRUCTION | 5.65 | 0 | 0
107 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000013/2023-2024 | 2933/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
108 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-I) Pipe Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000037/2023-2024 | 1609/RCD I | 25/04/2023 | 90 | GITA CONSTRUCTION | 245.36 | 0 | 65
109 | RCFA Division -I | RCFA Division I | Formal Work Order for Construction of Sub-station, CWR and Pump House including toilet at Ethora under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000173/2023-2024 | 2009/RCD-I | 26/06/2023 | 120 | D.S. ENTERPRISE | 122.25 | 0 | 40
110 | RCFA Division -I | RCFA Division I | Urgent Basis rapairing of 50 sqmm x 4 core Al Armoured Damaged cable line street Light Providing of FHTC Pipe line near Andal More to Culvert (Bridge) under Dignala OHR dite under Andal W/s scheme under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000560/2023-2024 | SpotNit_Camp_02/AndalMore | 09/10/2023 | 10 | T R ENTERPRISE | 6.17 | 0 | 100
111 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Jagrdih, Gopal area ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000601/2023-2024 | 3283/RCD-I | 08/11/2023 | 15 | SIMA ENTERPRISE | 6.12 | 0 | 100
112 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) 02 (Two) Nos. Near Dakshin Khanda Dharmaraj Tala and Khandra BPHC under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000656/2023-2024 | 3428/RCD-1 | 24/11/2023 | 15 | UNITED CONSTRUCTION | 18.39 | 0 | 100
113 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Shifting of 450 mm dia Rising main for ECL Railway siding near Dalmia OCP for extension of Bonjemari Colliery under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001108/2023-2024 | 913/RCD-I | 15/03/2024 | 45 | MD AAMIR KHAN | 43.51 | 0 | 100
114 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Laying of Rising main including allied works of for extension of Bonjemary Colliery and ECL Railway siding under Improvement of RCFA Part-II Zone-8 under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001109/2023-2024 | 914/RCD-I | 15/03/2024 | 45 | MD AAMIR KHAN | 38.46 | 0 | 100
115 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for concrete cutting, restoration of road and allied works Dakshin Khanda area under RCFA Part-II W/S Scheme PHE Dte. [Zone-1A] | Assistant Engineer 2 | Junior Engineer | ORD/001111/2023-2024 | 917/RCD-I | 15/03/2024 | 30 | UNITED CONSTRUCTION | 17.04 | 0 | 100
116 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Construction of pillar, MS pipe, specials, GI Pipe and allied works within Zone-I near Dendua under Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001118/2023-2024 | 924/RCD-I | 15/03/2024 | 45 | SWATI CORPORATION | 25.03 | 0 | 100
117 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work Distribution Network for Augmentation of RCFA Part-II (Zone-1) Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/001123/2023-2024 | 929/RCD-I | 15/03/2024 | 45 | UNITED CONSTRUCTION | 32.03 | 0 | 100
118 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Dedicated pipe line beyond Patal Lakhi Mandir including FHTC connections and allied works for Augmentation PWSS of RCFA Part-II (Zone-I) under RCFA Division - I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001131/2023-2024 | 916/RCD-I | 15/03/2024 | 30 | RAJAT BARAN CHAND | 17.3 | 0 | 100
119 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional supplying laying 90 mm dia, HDPE pipe line at Tentul Tala and Damalia Village including repairing different dia pipe line in different places in Tirat Mouza within Amritnagar Distribution Zone under Augmentation Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001139/2023-2024 | 937/RCD-I | 15/03/2024 | 15 | RUBY CONSTRUCTION | 6.88 | 0 | 100
120 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for concrete cutting and concreting and distribution network for RCFA Part-II PWSS including FHTC and allied work under RCFA Division-I PHE Dte. Zone-12B (Segement 2) | Assistant Engineer 2 | Junior Engineer | ORD/001170/2023-2024 | 1009/RCD-I | 16/03/2024 | 15 | M/S SINGH & KONAR CONSTRUCTION | 31.75 | 0 | 0
121 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying pipeline and allied works from Kelejora Health Centre Crossing towards Barabani Village (ICML Road) withthin Zone XIII of Augmentation RCFA Part-II (Zone-I) PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/001171/2023-2024 | 1011/RCD-I | 16/03/2024 | 168 | PINKI ENTERPRISE | 31.63 | 0 | 100
122 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of laying of rising main at Surjanagar Head Work Site to High lift site and interconnection of collecting main to CWR in the river of Damodar under Augmentation of RCFA Part-II (Zone-I) PWSS under RCFA Division-I. PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001175/2023-2024 | 1014/RCD-I | 16/03/2024 | 45 | MAK CONSTRUCTION CO | 40.81 | 0 | 100
123 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000015/2023-2024 | 2935/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
124 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-91 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00114/2024-2025 | 47/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 5.45 | 0 | 0
125 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-90 at Pandabeswar under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00116/2024-2025 | 49/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 5.45 | 0 | 0
126 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-18 under Augmentation of RCFA Part-II (Zone-11) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00156/2024-2025 | 69/24-25 | 30/05/2024 | 0 | EASTERN RAILWAY | 14.3 | 0 | 0
127 | RCFA Division -I | RCFA Division I | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-56 Payment of wayleave facility charges. | Assistant Engineer 2 | Junior Engineer | BILL/00545/2024-2025 | 272/24-25 | 05/09/2024 | 0 | EASTERN RAILWAY | 6.27 | 0 | 0
128 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped Water Supply including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-11) | Assistant Engineer 2 | Junior Engineer | ORD/000003/2023-2024 | 1390/RCD I | 11/04/2023 | 90 | M/S SRI MAHADEO ENTERPRISES | 294.95 | 239.31 | 85
129 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000092/2023-2024 | 1755/RCD-I | 12/05/2023 | 90 | MAA DURGA ENTERPRISE | 4.6 | 0 | 0
130 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Raniganj Block (Zone-11) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000097/2023-2024 | 1841/RCD-I | 31/05/2023 | 366 | DAS & CHAKRABORTY | 115.95 | 0 | 90
131 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala more to towards Amnala village surrounding area (Zone-IX) under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000226/2023-2024 | 2228/RCD-I | 17/07/2023 | 30 | KHEPI MAA TRADERS | 13.09 | 13.09 | 100
132 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional work repairing old plaster surface, color washing, painting and R.B.T. (Reinforced Barbed Tape) Concertina fencing on wall and allied works at Kalyaneswari Inspection Bungalow under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000399/2023-2024 | 2581/RCD-I | 07/09/2023 | 15 | JYOGOMAYA ENTERPRISE | 5.71 | 0 | 100
133 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Ethora (779 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000535/2023-2024 | 3016/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.93 | 0 | 100
134 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Pariharpur (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000536/2023-2024 | 3023/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 0 | 100
135 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Amritnagar (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000543/2023-2024 | 3026/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 0 | 100
136 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-11) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000556/2022-2023 | 3350/RCDI | 23/12/2022 | 770 | MOYTEC | 0.49 | 0 | 100
137 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 3 (Three) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at D.P Colony H/W Site for D P Colony Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2023-2024 | 3423/RCD-1 | 24/11/2023 | 15 | DURGA DAS MONDAL | 9.53 | 0 | 100
138 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional supplying, aligning, laying HDPE & PVC pipe line, construction of sluice valve chamber and other allied works under Tirat Mouza (Taldanga, Pathan Dhaora & Shyamdanga) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000648/2023-2024 | 3425/RCD-1 | 24/11/2023 | 30 | RUBY CONSTRUCTION | 6.78 | 0 | 100
139 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Trial Run for Barabani Kashidanga under Improvement of RCFA Part-I (Zone-XI) Piped W/S Scheme under RCFA Division-I PHE Dte. (180 days) | Assistant Engineer 2 | Junior Engineer | ORD/000665/2023-2024 | 3455/RCD-I | 24/11/2023 | 180 | UNITED CONSTRUCTION | 1.08 | 0 | 0
140 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying distribution main over concrete pillar including supply of rubber gusket within Zone-XI Part-I under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000676/2023-2024 | 3475/RCD-I | 28/11/2023 | 15 | R B ENTERPRISE | 4.89 | 0 | 100
141 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of Dismantling & concrete works, Supplying, Aligning & Laying HDPE Pipe and other allied works at distribution system Network for Shyamlya in Chatrisganda Mouza under Shyamlya Gram Panchayat under Jamuria Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000701/2023-2024 | 3499/RCD-1 | 30/11/2023 | 30 | DAWN CONSTRUCTION | 45.48 | 0 | 100
142 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying collecting and other allied works at DP Colony PWSS under RCFA Division-I PHE Dte. Augmentation PWSS of RCFA Part-II (Zone-11) | Assistant Engineer 2 | Junior Engineer | ORD/000947/2023-2024 | 505/RCD-I | 12/02/2024 | 30 | DURGA DAS MONDAL | 7.01 | 0 | 100
143 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work for Enamel paint, painting, weather coat at treatment plant, bridge, CWR and other places for Amritnagar Zone-I under Augmentation of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000964/2023-2024 | 507/RCD-I | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 16.92 | 0 | 100
144 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work concrete cutting, restoration of road and allied works within command area of Zone-11 (Part-6 Distribution Segment) of under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000983/2023-2024 | 467/RCD-1 | 12/02/2024 | 20 | M/S SUBHRADEEP | 17.08 | 0 | 100
145 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Extension of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001120/2023-2024 | 926/RCD-I | 15/03/2024 | 20 | SIMA ENTERPRISE | 7.02 | 0 | 100
146 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area Zone-VII of Augmentation of RCFA Part-II (Zone-11) PWSS under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/001215/2023-2024 | 935_RCD_I | 15/03/2024 | 15 | KONAR CONSTRUCTION | 23.57 | 0 | 100
147 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000027/2023-2024 | 2947/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
148 | RCFA Division -I | RCFA Division I | Way leave permission of 250 mm dia waer pipeline (Jal Jeevan Mision) near LC Gate No. 9/Spl/T near Pandabeswar Station in Asansol Divison of Eastern Railway by RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00987/2024-2025 | 415/24-25 | 05/12/2024 | 0 | EASTERN RAILWAY | 68.95 | 0 | 0
149 | RCFA Division -I | RCFA Division I | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line and extension of HDPE pipe to adjacent village of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000030/2023-2024 | 1615/RCD I | 25/04/2023 | 90 | DAS & CHAKRABORTY | 115.96 | 107.47 | 100
150 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA part-II Piped Water Supply Scheme (Zone-7) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000155/2023-2024 | 1900/RCD-I | 09/06/2023 | 365 | TARAPRASAD SARKAR | 150.41 | 0 | 25
151 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-7) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000560/2022-2023 | 3354/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
152 | RCFA Division -I | RCFA Division I | Additional extra cutting Laterrate / sandstone of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Div-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000573/2023-2024 | 2694/RCD-I | 27/09/2023 | 15 | TARA CONSTRUCTION | 0.94 | 0 | 100
153 | RCFA Division -I | RCFA Division I | Acceptance Cum work order for Additional work for distribution network for Improvement of RCFA Part-II Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000675/2022-2023 | 358/RCD I | 30/01/2023 | 336 | UNITED CONSTRUCTION | 62.01 | 5.82 | 100
154 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-1 | Assistant Engineer 2 | Junior Engineer | ORD/000850/2022-2023 | 1098/ RCD-I | 23/03/2023 | 90 | MAK CONSTRUCTION CO. | 97.63 | 0 | 15
155 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-2 | Assistant Engineer 2 | Junior Engineer | ORD/000853/2022-2023 | 1100/RCD I | 23/03/2023 | 90 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 89.86 | 0 | 50
156 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-3 (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000856/2022-2023 | 1102/RCD I | 23/03/2023 | 90 | RUBY CONSTRUCTION | 94.47 | 0 | 70
157 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-4 | Assistant Engineer 2 | Junior Engineer | ORD/000858/2022-2023 | 1104/RCD I | 23/03/2023 | 90 | M/S MONI TRADERS | 93.11 | 0 | 45
158 | RCFA Division -I | RCFA Division I | Acceptance cum work order for distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | ORD/000863/2022-2023 | 1106/RCD I | 23/03/2023 | 90 | B.T.M CONCERN | 94.6 | 0 | 65
159 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional supplying, Laying & Aligning of HDPE pipe, including providing FHTC retrofitting (left out portion) at Ratibati village under Augmentation PWSS of RCFA Part-II (Zone-7) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001023/2023-2024 | 622/RCD-I | 27/02/2024 | 15 | M/S KALYAN ENTERPRISE | 4.09 | 0 | 100
160 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000021/2023-2024 | 2950/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
161 | RCFA Division -I | RCFA Division I | Formal work order for Supplying laying different HDPE Pipe line for Improvement of RCFA Part-I Water Supply Scheme within Command area of Zone-VIII with LDS work under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000031/2023-2024 | 1614/RCD I | 25/04/2023 | 90 | SWATI CORPORATION | 128.33 | 22.19 | 80
162 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 450 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-5) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil Investigation and chlorine Room (4.50 x 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000042/2023-2024 | 1608/RCD I | 25/04/2023 | 366 | HIRANMAY GHOSH | 137.5 | 0 | 50
163 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000422/2023-2024 | 2620/RCD-I | 13/09/2023 | 15 | MD AAMIR KHAN | 38.07 | 0 | 100
164 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work for bridge with foundation at Chalbalpur under Amritnagar Zone-II for Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000513/2023-2024 | 2864/RCD-I | 06/10/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 87.54 | 86.59 | 100
165 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of new boundary wall, Land developing and Pathway and other allied works at Nimsa mouza RCC over Head Site at Shyamla under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Length 188 Mtr) | Assistant Engineer 2 | Junior Engineer | ORD/000519/2023-2024 | 2873/RCD-I | 06/10/2023 | 90 | M/S CHANDI CHARAN ROY | 21.97 | 0 | 100
166 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying and pushing MS pipe through RCC pipe in different dia and different including cutting welding for barricading jointing for Augmentation of RCFA Part-II (Zone-5) PWSS under Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000523/2023-2024 | 2881/RCD-I | 06/10/2023 | 178 | MRITYUNJOY MUKHERJEE & CO. | 16.98 | 0 | 100
167 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying. Aligning and laying MS pipe (Node no. 45-47, 61-62, 5-16, 44-45) construction of Guard wall, concrete dismantling with re concreting and other allied works for Shyamla & Bhuri Mouzas, Block-Jamuria, Dist-Paschim Bardhaman under Augmentation of RCFA Part-II (Zone-5) under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2 | Junior Engineer | ORD/000524/2023-2024 | 2882/RCD-I | 06/10/2023 | 30 | TARA CONSTRUCTION | 13.8 | 0 | 100
168 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-5) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000565/2022-2023 | 3359/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 100
169 | RCFA Division -I | RCFA Division I | Formal work order for distribution network including FHTC & allied work at Ondal Block of RCFA Part-II(zone -5) pipe water supply under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000811/2022-2023 | 954/RCDI | 20/03/2023 | 926 | M/S PIONEER CONSTRUCTION | 475.88 | 0 | 80
170 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000019/2023-2024 | 2954/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
171 | RCFA Division -I | RCFA Division I | Repairing and renovation of staff quarter (Group A Type) and other allied works at Kalyaneswari Township under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000019/2022-2023 | 1078/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 4.86 | 0 | 100
172 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying Rising Main of Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000055/2024-2025 | 1745/RCD-I | 18/07/2024 | 260 | M/S MONDAL ENTERPRISE | 28.19 | 0 | 60
173 | RCFA Division -I | RCFA Division I | Balance work of Supplying,laying and aligning of Distribution system includind FHTC for Shyamla W/S Scheme in Shyamla and Bhuri Mouza, Block jamuria, Dist-Paschim Bardhaman under Augmentation of Sarshatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000082/2024-2025 | Camp-02_Shyamla_AE-II/24- | 06/08/2024 | 30 | TARA CONSTRUCTION | 12.5 | 0 | 100
174 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000108/2022-2023 | 1277/RCD-I | 02/06/2022 | 579 | JAYANTA DATTA | 32.82 | 18.31 | 85
175 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000109/2022-2023 | 1278/RCD-I | 02/06/2022 | 90 | MD. JAWED KHAN | 38.01 | 29.87 | 0
176 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Sarisatali Piped Water Supply Scheme including FHTC Work Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte.(Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000111/2022-2023 | 1279/RCD I | 02/06/2022 | 90 | M/S B.K. CONSTRUCTION | 59.35 | 38.85 | 80
177 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No 07) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000113/2022-2023 | 1281/RCD I | 02/06/2022 | 30 | MAA ENTERPRISE. | 11.06 | 10.81 | 0
178 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Sarisathali OHR site of Augmentation of Sarsathali Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000206/2023-2024 | 2219/RCD-I | 17/07/2023 | 30 | M/S CHANDI CHARAN ROY | 29.79 | 0 | 65
179 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for laying of distribution system including adopting trench less technology for one location near Khosnagar Health Centre and allied works under Augmentation of Sarishatali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000285/2023-2024 | 2334/RCD-I | 01/08/2023 | 15 | M/S B.K. CONSTRUCTION | 11.2 | 9.4 | 100
180 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying rising main including Guard room with Toilet including 12 (Twelve) nos Tube Well and Collecting main at River Ajoy under due to open cast mining activity of ECL Salanpur area for Sarisatali and Majiara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000290/2023-2024 | 2339/RCD-I | 01/08/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 87.93 | 0 | 20
181 | RCFA Division -I | RCFA Division I | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at District Magistrate bungalow, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000417/2023-2024 | Camp_2_DM_Office_AE_II_20 | 01/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.87 | 7.74 | 100
182 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of OHR (Capacity 300 cum, staging Height 20 mtrs) for Augmentation of Sarisathali Piped Water Supply Scheme under RCFA Division-I PHE Dte. Block-Barabani, Dist - Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000458/2022-2023 | 2933/RCD-I | 17/11/2022 | 12 | M/S CHANDI CHARAN ROY | 85.83 | 77.25 | 100
183 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 2 (Two) nos 200 mm dia river bed tube well including collecting main in the river of Ajoy for Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000467/2023-2024 | 2859/RCD-I | 06/10/2023 | 15 | MAA ENTERPRISE | 7.67 | 0 | 100
184 | RCFA Division -I | RCFA Division I | Preparation of DPR for Augumentation of Sarshatali Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(Sl No 04) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000480/2021-2022 | 2348/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 0
185 | RCFA Division -I | RCFA Division I | Formal work order for Distribution network for augmentation of Sarisathali piped Water Supply scheme including FHTC work, Block-Baraboni, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000534/2022-2023 | 3231//RCDI | 19/12/2022 | 987 | SRI KRISHNA ENTERPRISE | 133.36 | 14.98 | 100
186 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying aligning & laying 225 mm dia HDPE pipe line in related to distribution Network for Augmentation of Sarisatali Piped W/S Scheme under RCFA Division-I PHE Dte. ( Sl No. 18) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/000848/2022-2023 | 1085/RCD I | 23/03/2023 | 90 | JAYANTA DATTA | 19.21 | 18.02 | 100
187 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Chlorine room of size 4 mtr x 4 mtr x3.5 mtr (Ht) at Sarsatali under Augmentation of Sarsatali PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-4 | ORD/001085/2023-2024 | 875/RCD-I | 15/03/2024 | 60 | JAI MAHARAJ ENTERPRISE | 3.99 | 0 | 100
188 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional supplying laying and aligning of distribution system including FHTC for Shyamla in Chatrisganda Mouza, Block Jamuria Paschim Bardhaman under Augmentation of Madantore PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000114/2024-2025 | 2137/RCD-I | 27/08/2024 | 45 | DAWN CONSTRUCTION | 38 | 0 | 100
189 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-4 Segment) for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000157/2022-2023 | 1708/RCD-I | 15/07/2022 | 881 | DAWN CONSTRUCTION | 48.67 | 0 | 100
190 | RCFA Division -I | RCFA Division I | Laying of distribution system including FHTC work for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000293/2022-2023 | 2450/RCD-I | 13/10/2022 | 180 | JOY HIND TUBEWELLS | 246.41 | 70.1 | 100
191 | RCFA Division -I | RCFA Division I | Detailed Route Survey, Design Drawing & DPR Preparation for Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 4) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000539/2021-2022 | 503/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 0
192 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of Capacity 250 cum at Madantore under Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000557/2023-2024 | 3186/RCD-I | 01/11/2023 | 270 | A.K.CONSTRUCTION | 10.95 | 0 | 100
193 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repair and renovation works of Clear Water Reservoir of Capacity 150 cum for Augmentation of Madantore Piped water Supply scheme under RCFA division-I PHE dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000558/2023-2024 | 3187/RCD-I | 01/11/2023 | 180 | A.K.CONSTRUCTION | 10.86 | 0 | 0
194 | RCFA Division -I | RCFA Division I | Construction of Pump House at Churulia under Madantore Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000572/2022-2023 | 3281/RCDI | 20/12/2022 | 90 | M/S MONDAL ENTERPRISE | 30.24 | 0 | 100
195 | RCFA Division -I | RCFA Division I | Acceptance work order for Construction of Chlorine Room of Size (4.50 x 3.50 m) at Churulia for Augmentation of Madantore Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000644/2022-2023 | 342/RCDI | 30/01/2023 | 15 | ANAMIKA CONSTRUCTION | 4.6 | 4.42 | 100
196 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 1 (One) no. 200 mm dia river bed tube well in the river Ajoy including 01 (One) no collecting main of Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 22) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000886/2022-2023 | 1165/RCD I | 24/03/2023 | 60 | R B ENTERPRISE | 5.77 | 5.68 | 0
197 | RCFA Division -I | RCFA Division I | Acceptance cum work order for repair and renovation works of GLR of capacity 90 cum for Augmentation of Madantor Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 23) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000889/2022-2023 | 1166/RCD I | 24/03/2023 | 180 | A.K.CONSTRUCTION | 6.48 | 0 | 5
198 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repairing & shifting work of DI pipes and allied repairing at Madanpur under Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000928/2022-2023 | 1261/ RCD I | 27/03/2023 | 15 | MAK CONSTRUCTION CO. | 3.22 | 0 | 100
199 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of Dismantling and concrete works supplying aligning and laying HDPE pipe and other allied works at distribution system network for Bagdiha (Part-D) Augmentation of Madantor Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000973/2023-2024 | 491/RCD-I | 12/02/2024 | 45 | TARA MA ENTERPRISE | 18.79 | 0 | 75
200 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply & Delivery of GI pipe including loading, unloading and carriage to Searsole Store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/001034/2023-2024 | 713/RCD-I | 29/02/2024 | 20 | NEZONE TUBES LIMITED | 95.53 | 0 | 100
201 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000011/2022-2023 | 2351/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
202 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000023/2022-2023 | 3130 | 09/12/2022 | 0 | Resource Division | 12.9 | 0 | 0
203 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of road at Runakuraghat H/W site including earth filling,treeguard making including repairing and restoration of rising main including collecting main under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000006/2024-2025 | 1432/RCD-I | 06/06/2024 | 45 | SRI KRISHNA ENTERPRISE | 58.57 | 0 | 100
204 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000013/2022-2023 | 1038/RCD-I | 10/05/2022 | 1179 | ASHA CONSTRUCTION | 147.65 | 26.38 | 100
205 | RCFA Division -I | RCFA Division I | Plumbing works, sanitary fitting, flooring and other allied works of staff Quarter (Group A Type) and other allied works at Kalyaneswari township under RCFA Division-I PHE Dte.(Sl no 03) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000018/2022-2023 | 1077/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 3.89 | 0 | 100
206 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000125/2022-2023 | 1611/RCD-I | 06/07/2022 | 1365 | UNITED CONSTRUCTION | 55.84 | 10.08 | 75
207 | RCFA Division -I | RCFA Division I | acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Tematha Panuria Bazar, Gourandi Bazar, Aliganj Road including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000222/2023-2024 | 2226/RCD-I | 17/07/2023 | 30 | A. CONSTRUCTION CO. | 30.14 | 29.86 | 100
208 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Bhtas more, ardanga more on Asansol Runakuraghat Road, including supply of MS pipe and left out laying of HDPE pipe at Gourandi Bazar and allied works under Augmentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000224/2023-2024 | 2227/RCD-I | 17/07/2023 | 30 | GITA CONSTRUCTION | 43.42 | 39.5 | 91
209 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work at Baradanga, Alipur and Kanta Pahari Villages under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000240/2022-2023 | 2015/RCD-I | 26/08/2022 | 45 | GITA CONSTRUCTION | 44.01 | 0 | 40
210 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution System surrounding OHR near Panuria under Agumentation of Panuria PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000242/2022-2023 | 2151/RCD-I | 02/09/2022 | 30 | A. CONSTRUCTION CO. | 28.88 | 19.6 | 100
211 | RCFA Division -I | RCFA Division I | Acceptance cum work order Providing FHTC work at Panuria (Part) and adjacent Habitation under Augmentation of Panuria Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000295/2022-2023 | 2468/RCDI | 14/10/2022 | 45 | A. CONSTRUCTION CO. | 69.99 | 0 | 100
212 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Laying of different dia distribution pipe line and etc. work at Tanti para, Camp para, Sasan para etc. under Khandra area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000405/2023-2024 | 2587/RCD-I | 07/09/2023 | 15 | D.S.ENTERPRISE | 7.48 | 7.42 | 100
213 | RCFA Division -I | RCFA Division I | Preparation of DPR for Augmentation of Panuria Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000449/2021-2022 | 2345/RCD-I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 3.02 | 3.02 | 0
214 | RCFA Division -I | RCFA Division I | Acceptance cum work order for new pipe line of 200 mm, 90 mm and 75 mm dia at Panuria Bazar under Panuria GP under Augmentation of Panuria Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000576/2022-2023 | 3285/RCD I | 20/12/2022 | 60 | SRI KRISHNA ENTERPRISE | 12.15 | 12.08 | 0
215 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution System at Katapahari, Alipur, Baradanga village and surrounding area (Part-B) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000585/2021-2022 | 598/RCD-I | 07/03/2022 | 60 | GITA CONSTRUCTION | 78.27 | 70.11 | 91
216 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution System at Panuria village at surrounding area (Part-C) under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000586/2021-2022 | 599/RCD-I | 07/03/2022 | 60 | A. CONSTRUCTION CO. | 76.15 | 72.59 | 100
217 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of C.W.R. (Clear water Reservoir) of capacity 200 Cu.m & allied Work at Panuria under Augmentation of Panuria Piped Water Supply Scheme under RCFA Divn.-I. P.H.E. Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000594/2022-2023 | 3276/RCDI | 20/12/2022 | 90 | SAMIR KUMAR ROY CHOWDHURY | 22.05 | 20.65 | 70
218 | RCFA Division -I | RCFA Division I | Formal work order for construction of 350 cum capacity 20 mtr staging height RCC over Head Reservoir (Piped connection and cost of pipes, specials at Gourandi H/W site for Augmentation of Panuria Piped Water Supply Scheme under RCFA Div-I, PHE dte in the District of Pachim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000618/2022-2023 | 102/RCD I | 20/01/2023 | 212 | A. CONSTRUCTION CO. | 115.99 | 104.39 | 100
219 | RCFA Division -I | RCFA Division I | Acceptance cum work order Proposed Pump House including Toilet of Augmentation Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000836/2022-2023 | 1064/RCD-I | 23/03/2023 | 180 | RUBY CONSTRUCTION | 31.13 | 0 | 100
220 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and renovation of existing culvert, Pump House, Staff Quarter under Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000891/2022-2023 | 1167/RCD I | 24/03/2023 | 90 | R B ENTERPRISE | 5.94 | 5.88 | 0
221 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000002/2024-2025 | 1179/RCD-I | 03/04/2024 | 0 | Resource Division | 37.47 | 0 | 0
222 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000007/2022-2023 | 2347/RCD-I | 28/09/2022 | 0 | Resource Division | 21.56 | 0 | 0
223 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000013/2021-2022 | 696/RCD-I | 23/03/2022 | 0 | Resource Division | 92.44 | 0 | 0
224 | RCFA Division -I | RCFA Division I | Color Xerox repairing and supply of color xerox toner | Assistant Engineer 2 | Junior Engineer | BILL/00292/2024-2025 | 131/24-25 | 11/07/2024 | 0 | MUKHERJEE TRADERS | 0.17 | 0 | 0
225 | RCFA Division -I | RCFA Division I | Bill for GST Return Oct 2023 to Feb 2024 24 Q 1 & Q 2 2023-2024 and 16 A 26 Q 23-24 | Assistant Engineer 2 | Junior Engineer | BILL/00348/2024-2025 | 172/24-25 | 25/07/2024 | 0 | SHRESTHA & ASSOCIATES | 0.44 | 0 | 0
226 | RCFA Division -I | RCFA Division I | Arrangement of Stationary items , Flex and Tea snacks for Krmashree meeting held on 12.07.2024 at RTC Hall Asansol | Assistant Engineer 2 | Junior Engineer | BILL/00358/2024-2025 | 171/24-25 | 26/07/2024 | 0 | BLESSING ENTERPRISE | 0.14 | 0 | 0
227 | RCFA Division -I | RCFA Division I | Hire charges and fuel bill 16.05.2023 to 15.08.2023 | Assistant Engineer 2 | Junior Engineer | BILL/00635/2023-2024 | 264/23-24 | 27/09/2023 | 0 | PRAMIT CHATTERJEE | 1.2 | 0 | 0
228 | RCFA Division -I | RCFA Division I | Hire charges for the month of August 2023 | Assistant Engineer 2 | Junior Engineer | BILL/00636/2023-2024 | 262/23-24 | 27/09/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
229 | RCFA Division -I | RCFA Division I | Fuel bill of WB 37D 0482 | Assistant Engineer 2 | Junior Engineer | BILL/00637/2023-2024 | 263/23-24 | 27/09/2023 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
230 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Maira area Dakshin Khnada (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000246/2022-2023 | 2212/RCD-I | 14/09/2022 | 30 | UNITED CONSTRUCTION | 44.65 | 9.74 | 0
231 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B1) | Assistant Engineer 2 | Junior Engineer | ORD/000305/2021-2022 | 2130/RCD-I | 29/11/2021 | 30 | D.S. ENTERPRISE | 18.12 | 12.86 | 0
232 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B2) | Assistant Engineer 2 | Junior Engineer | ORD/000306/2021-2022 | 2131/RCD-I | 29/11/2021 | 30 | M/S B.K. CONSTRUCTION | 18.13 | 18.13 | 0
233 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C1) | Assistant Engineer 2 | Junior Engineer | ORD/000307/2021-2022 | 2132/RCD-I | 29/11/2021 | 30 | KHEPI MAA TRADERS | 17.52 | 17.52 | 0
234 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khandra CT (Jl No. 32) Block ¿ Pandabeswar of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C2) | Assistant Engineer 2 | Junior Engineer | ORD/000308/2021-2022 | 2133/RCD-I | 29/11/2021 | 30 | MRITYUNJOY MUKHERJEE & CO. | 18.7 | 12.53 | 0
235 | RCFA Division -I | RCFA Division I | Formal work order for Providing FHTC through Retrofitting at Khandra (CT) (JL no. 32, Block - Andal) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000318/2021-2022 | 2145/RCD-I | 29/11/2021 | 488 | DAS & CHAKRABORTY | 78.91 | 68.92 | 100
236 | RCFA Division -I | RCFA Division I | Laying of different dia HDPE pipe line including repairing work of UPVC pipe line and etc. allied works under Khandra Zone distribution pipe line under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 2 | Junior Engineer | ORD/000508/2021-2022 | 222/RCD I | 01/02/2022 | 15 | UNITED CONSTRUCTION | 4.79 | 4.79 | 0
237 | RCFA Division -I | RCFA Division I | Supply, fitting fixing of street stand posts and crossing of distribution water branch main through Khandra main road and etc. including interconnection work under Khandra Zone under RCFA Part-II W/S Scheme. (Sl No. 11) | Assistant Engineer 2 | Junior Engineer | ORD/000509/2021-2022 | 223/RCD I | 01/02/2022 | 12 | UNITED CONSTRUCTION | 2.61 | 2.61 | 0
238 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of different dia distribution pipe line and allied works etc at Bisseswari Muslimpara and adjacent area of Khandra area under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000636/2022-2023 | 334/RCD I | 30/01/2023 | 15 | M/S B.K. CONSTRUCTION | 7.68 | 0.73 | 100
239 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line towards Bisserari, Anandapally and etc. adjacent area under Khandra area Block Andal & Pandabeswar of Improvement of RCFA Part-II Water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000684/2022-2023 | 372/RCD I | 30/01/2023 | 15 | M/S B.K. CONSTRUCTION | 6.87 | 1.11 | 100
240 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different 140 mm dia HDPE pipe line including interconnection and fitting, fixing sluice valves and etc allied works at Maira Dipu area under Khandra Zone under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000923/2022-2023 | 1259/ RCD I | 27/03/2023 | 15 | TARA CONSTRUCTION | 2.32 | 2.16 | 0
241 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia HDPE pipe line towards Ruidas Para and Baouripara under Dakshin Khanda (Jl No. 36) area Block - Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000938/2022-2023 | 1272/ RCD I | 27/03/2023 | 15 | DURGADAS MONDAL | 3.71 | 3.68 | 0
242 | RCFA Division -I | RCFA Division I | Acceptance cum work order Interconnection work of 200 distribution main at Ukhra Zone and emergency repairing of 400 mm dia rising main at Khandra Zone under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000947/2022-2023 | 1285/ RCD I | 27/03/2023 | 15 | RANJIB GHATAK | 4.28 | 4.26 | 100
243 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000003/2021-2022 | 2283 | 12/12/2021 | 0 | Resource Division | 18.59 | 0 | 0
244 | RCFA Division -I | RCFA Division I | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000160/2024-2025 | 2164_RCD-I | 30/08/2024 | 182 | SHYAMAL MAJI | 0.9 | 0 | 33
245 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Supply and laying MS water carrier pipe and allied works of Improvement of RCFA Part-I in connection of Rising Main (Part-A) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000209/2023-2024 | 2209/RCD-I | 17/07/2023 | 30 | MD AAMIR KHAN | 37.26 | 36.13 | 100
246 | RCFA Division -I | RCFA Division I | Acceptance cum Providing FHTC of retrofitting at Kumardihi village (left out portion) of kumardihi Mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Sceme under RCFA Division -I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000775/2022-2023 | 806/RCD-I | 06/03/2023 | 20 | M/S MONDAL CONSTRUCTION | 13.78 | 12.41 | 100
247 | RCFA Division -I | RCFA Division I | acceptance cum work order Repairing of 450 mm dia DI pipe line at Baidyanathpur, Barachak, Jagaridih area of ASTA rising main of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000946/2022-2023 | 1282/RCD-I | 27/03/2023 | 15 | SIMA ENTERPRISE | 2.66 | 2.66 | 0
248 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for railway crossing in between Jamuria (JMA) and Barabani (BBI) at KM 25/2-3 in Asansol Division under JJM of Retrofitting of Bagdiha & adjoining mouzas for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001124/2023-2024 | 931/RCD-I | 15/03/2024 | 30 | SOMNATH SAMANTA | 23.15 | 0 | 100
249 | RCFA Division -I | RCFA Division I | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and barabani (BBI) station of Asansol Division, Eastern Railway | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00011/2023-2024 | 30/23-24 | 03/05/2023 | 0 | EASTERN RAILWAY | 0.53 | 0 | 0
250 | RCFA Division -I | RCFA Division I | DEPOSITION OF WAY LEAVE FEE (ER-ASN-2023-WL-17) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00017/2023-2024 | 41/23-24 | 10/05/2023 | 0 | EASTERN RAILWAY | 5.37 | 0 | 0
251 | RCFA Division -I | RCFA Division I | June 2022 to Novemeber & December 2022 to Feburary 2023 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00030/2023-2024 | 19/23-24 | 18/04/2023 | 0 | PRASENJIT DEY | 3.6 | 0 | 0
252 | RCFA Division -I | RCFA Division I | Restoration amount for unauthorised execavation and damaged at Ethora Nuni Road [Road connecting FR 10 and FR 19 (FR 13) under Asansol highwa | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00039/2022-2023 | Asn-Highway-PWD | 11/01/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 10.45 | 0 | 0
253 | RCFA Division -I | RCFA Division I | Deposition of way leave fee for pipeline crossing of Railway track in between Jamuria (JMA) and Barabani stan (BBI) km post 25/02-25/03 of Asansol Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00058/2023-2024 | 65/23-24 | 25/05/2023 | 0 | EASTERN RAILWAY | 4.63 | 0 | 0
254 | RCFA Division -I | RCFA Division I | Deposition of way leave fee for pipeline crossing of Railway track in between Salanpur (SLS) and Rupnarayanpur (RNPR) km post 23/15-17 to 231/16-18 of Asansol Division, Eastern Railway | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00059/2023-2024 | 64/23-24 | 25/05/2023 | 0 | EASTERN RAILWAY | 5.12 | 0 | 0
255 | RCFA Division -I | RCFA Division I | Desposition of way leave Fees for Railway crossing for pipeline. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00147/2022-2023 | 947/22-23 | 09/03/2023 | 0 | EASTERN RAILWAY | 5.04 | 0 | 0
256 | RCFA Division -I | RCFA Division I | Deposition of way leave Fees for Railway crossing for pipeline. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00150/2022-2023 | 946/22-23 | 09/03/2023 | 0 | EASTERN RAILWAY | 6.08 | 0 | 0
257 | RCFA Division -I | RCFA Division I | ER-ASN-2023-WL-28 (Salanpur SLS to Rupnarayanpur RNPR) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00278/2023-2024 | 130/23-24 | 10/07/2023 | 0 | EASTERN RAILWAY | 5.7 | 0 | 0
258 | RCFA Division -I | RCFA Division I | fuel bill For WB 37D 0482 Nov 2022 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00432/2022-2023 | 821/22-23 | 20/01/2023 | 0 | RANAJIT AUTO | 0.27 | 0 | 0
259 | RCFA Division -I | RCFA Division I | Hiring of Maxi Cab (Non Air-conditioned) Bharat Stage-II/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. for the Office use of the Assistant Engineer, RCFA Division-I, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.07.2022 to 30.06.2023)(sl no 01) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00703/2022-2023 | 1210/22-23 | 31/03/2023 | 0 | NIRMALA TRADERS | 2.8 | 0 | 0
260 | RCFA Division -I | RCFA Division I | Vehicle bill | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00704/2022-2023 | 1166/22-23 | 31/03/2023 | 0 | KHEPI MAA TRADERS | 2.21 | 0 | 0
261 | RCFA Division -I | RCFA Division I | VEHICLE BILL | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00705/2022-2023 | 1165/22-23 | 30/03/2023 | 0 | PRAMIT CHATTERJEE | 1.2 | 0 | 0
262 | RCFA Division -I | RCFA Division I | IT GST FILLING | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00706/2022-2023 | 1206/22-23 | 30/03/2023 | 0 | SHRESTHA & ASSOCIATES | 0.5 | 0 | 0
263 | RCFA Division -I | RCFA Division I | VEHICLE BILL | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00707/2022-2023 | 1113/22-23 | 30/03/2023 | 0 | SHYAMAL MAJI | 0.19 | 0 | 0
264 | RCFA Division -I | RCFA Division I | Supply of computer for Assistant Enginner-II | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00708/2022-2023 | 944/22-23 | 30/03/2023 | 0 | MUKHERJEE TRADERS | 0.42 | 0 | 0
265 | RCFA Division -I | RCFA Division I | Engagement of 01 (One) no person under control of 2 (Two) nos AE/RCFA Div-I day to day report and return of FHTC as per scheme wise panchayet wise and updation of JJm | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | BILL/00761/2023-2024 | 320/23-24 | 16/10/2023 | 0 | MUKHERJEE TRADERS | 0.49 | 0 | 0
266 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Div-I PHE Dte. (Part B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000001/2022-2023 | 931/RCD-I | 26/04/2022 | 736 | M/S MONDAL ENTERPRISE | 82.94 | 61.98 | 100
267 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000002/2022-2023 | 932/RCD-I | 26/04/2022 | 615 | DIP CONSTRUCTION | 61.83 | 51.53 | 100
268 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000003/2022-2023 | 933/RCD-I | 26/04/2022 | 90 | M/S K & KONAR CONSTRUCTION | 75.35 | 69.5 | 90
269 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000004/2022-2023 | 934/RCD-I | 26/04/2022 | 90 | SRI KRISHNA ENTERPRISE | 86.98 | 30.45 | 65
270 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-IX under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000005/2022-2023 | 935/RCD-I | 26/04/2022 | 90 | KHEPI MAA TRADERS | 71.89 | 67.45 | 75
271 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000006/2022-2023 | 936/RCD-I | 26/04/2022 | 90 | M/S MONI TRADERS | 75.17 | 40.2 | 70
272 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600mm dia ms water Carrer pipe and road Crossing by adopting trenchless technology at Dendua more to Kalyaneswri road of improvement of RCFA Part-I in connection of rasing main (part-A) under RCFA Division-I PHE Dte.(Sl No. 07) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000007/2023-2024 | 1405/RCD-1 | 12/04/2023 | 357 | MD AAMIR KHAN | 90.31 | 68.18 | 100
273 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-B) (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000010/2022-2023 | 1006/RCD-I | 05/05/2022 | 60 | M/S SANTANU PALIT & CO. | 93.2 | 0 | 70
274 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-D) (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000011/2022-2023 | 1007/RCD-I | 05/05/2022 | 90 | GITASREE FABRICATION | 77.41 | 66.72 | 85
275 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000012/2022-2023 | 1020/RCD-I | 06/05/2022 | 180 | SWATI CORPORATION | 149.9 | 63.87 | 85
276 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000013/2022-2023 | 1038/RCD-I | 10/05/2022 | 1179 | ASHA CONSTRUCTION | 147.65 | 58.28 | 100
277 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - I (Dendua OHR Site) under RCFA Division-I PHE Dte. (Part - C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000014/2022-2023 | 1039/RCD-I | 10/05/2022 | 1179 | DAS & CHAKRABORTY | 130.86 | 56.55 | 100
278 | RCFA Division -I | RCFA Division I | Formal Work order for Rising Main for Improvement RCFA Part-I Water Supply Scheme for Salanpur and Barabani Block under RCFA Division-I PHE Dte. (Part ¿ A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000016/2022-2023 | 1073/RCD-I | 13/05/2022 | 719 | MD AAMIR KHAN | 115.25 | 75.01 | 90
279 | RCFA Division -I | RCFA Division I | Formal work order for 200 mm, 160 mm & 90 mm dia HDPE PE-80 distribution network of RCFA Part-I Water Supply Scheme command area of Zone-IX under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000034/2023-2024 | 1612/RCD I | 25/04/2023 | 90 | KHEPI MAA TRADERS | 149.55 | 53.69 | 90
280 | RCFA Division -I | RCFA Division I | Formal work order for Supplying aligning and laying of different dia HDPE pipe line instead of DI pipe line within distribution network within command are of Zone-I (Dendua OHR Site) of Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000036/2023-2024 | 1610/RCD I | 25/04/2023 | 90 | SWATI CORPORATION | 114.21 | 98.16 | 86
281 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-IX under RCFA Division-I PHE Dte. (Part C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000095/2022-2023 | 1213/RCD-I | 30/05/2022 | 1281 | T M CONCRETE CREATION PRIVATE LIMITED | 131.44 | 108.9 | 65
282 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000096/2022-2023 | 1214/RCD-I | 30/05/2022 | 90 | RANJIB GHATAK | 100.72 | 90.61 | 90
283 | RCFA Division -I | RCFA Division I | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII with LDS & FHTC Work | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000105/2022-2023 | 1329/RCD-I | 09/06/2022 | 180 | SWATI CORPORATION | 399.2 | 235.1 | 100
284 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of drain at Dabor mouzas under RCFA Part-I W/S Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000106/2023-2024 | 1865/RCD-1 | 01/06/2023 | 60 | TARA CONSTRUCTION | 10.11 | 10 | 85
285 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 1 (One) no. Chlorine Room including Plinth protection, drain for 900 cum and 250 cum OHR at Baliapur under Improvement of RCFA (Part-I) Piped Water Supply Scheme. under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000115/2024-2025 | 2138/RCD-I | 27/08/2024 | 60 | AMAR CONSTRUCTION | 9.01 | 0 | 100
286 | RCFA Division -I | RCFA Division I | Formal Work Order for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000117/2022-2023 | 1379/RCD-I | 17/06/2022 | 180 | MRITYUNJOY MUKHERJEE & CO. | 466.46 | 346.89 | 80
287 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XIII under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000119/2022-2023 | 1605/RCD-I | 06/07/2022 | 90 | PINKI ENTERPRISE | 78.73 | 37.76 | 80
288 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000124/2022-2023 | 1610/RCD-I | 06/07/2022 | 990 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 64.62 | 18.73 | 100
289 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000125/2022-2023 | 1611/RCD-I | 06/07/2022 | 1365 | UNITED CONSTRUCTION | 55.84 | 16.36 | 75
290 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000126/2022-2023 | 1612/RCD-I | 06/07/2022 | 90 | PINKI ENTERPRISE | 60.85 | 21.88 | 65
291 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000127/2022-2023 | 1613/RCD-I | 06/07/2022 | 90 | KONAR CONSTRUCTION | 64.73 | 23.94 | 75
292 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000128/2022-2023 | 1614/RCD-I | 06/07/2022 | 90 | TARA CONSTRUCTION | 88.3 | 43.84 | 70
293 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-7 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000130/2022-2023 | 1702/RCD-I | 14/07/2022 | 45 | UNITED CONSTRUCTION | 20.25 | 19.99 | 5
294 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-9 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000131/2022-2023 | 1703/RCD-I | 14/07/2022 | 45 | SOMNATH SAMANTA | 28.67 | 0 | 5
295 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000143/2022-2023 | 1437/RCD I | 27/06/2022 | 45 | VISUVIOUS | 2.75 | 2.35 | 0
296 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-5 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000158/2022-2023 | 1707/RCD-I | 14/07/2022 | 45 | M/S B.K. CONSTRUCTION | 32.05 | 20.27 | 100
297 | RCFA Division -I | RCFA Division I | Continuation work order for Laying & Pushing of 600 mm dia MS Water Carrier pipe and road Crossing by adopting trench less technology at Dendua more to Kalyaneswari road of Improvement of RCFA Part-I in connection of rising main (Part-A) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000158/2023-2024 | 1883/1/RCD-I | 07/06/2023 | 15 | MD AAMIR KHAN | 66.19 | 66.19 | 0
298 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and renovation of Rupnarayanpur OHR of Capacity 1135 cum staging height 20 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000163/2021-2022 | 1588/RCD-I | 07/09/2021 | 30 | BKB INFRA PROJECTS PVT LTD | 37.48 | 37.45 | 0
299 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-8 Segment) for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000163/2022-2023 | 1712/RCD-I | 15/07/2022 | 45 | SIMA ENTERPRISE | 24.13 | 0 | 5
300 | RCFA Division -I | RCFA Division I | Continuation work order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 Nos. location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000164/2023-2024 | 1911/RCD-I | 14/06/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 19.62 | 15.26 | 80
301 | RCFA Division -I | RCFA Division I | Hiring of maxi cab (Non-airconditioned)Bharat stage-II/BS-II purchased on or after 01.05.2008 with diesel/LPG/CNG engine for the office use of the Assistant Engineer, RCFA Div-I, PHE dte, Govt of West Bengal (w.e.f 01.09.2021 to 31.08.2022) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000194/2021-2022 | 1541/RCD I | 31/08/2021 | 365 | KHEPI MAA TRADERS | 1.73 | 1.14 | 0
302 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-VI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000205/2022-2023 | 1874/RCD-I | 04/08/2022 | 12 | KAMIRUL SK & CO | 76.6 | 68.94 | 100
303 | RCFA Division -I | RCFA Division I | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman (Sl No. 01) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000207/2022-2023 | 1908/RCD-I | 12/08/2022 | 7 | SHARMA ENGINEERING WORKS | 1.3 | 1.3 | 0
304 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000207/2023-2024 | 2208/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 12.78 | 11.55 | 100
305 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000217/2023-2024 | 2211/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 19.71 | 11.22 | 60
306 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines and Supplying Aligning Laying MS pipe (including carring loading & unloading at work site) Head Works Site (node point R1-1) and Lalganj Hat of Improvement RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000223/2023-2024 | 2246/RCD-1 | 17/07/2023 | 30 | TARA CONSTRUCTION | 17.17 | 15.58 | 100
307 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000225/2023-2024 | 2247/RCD-1 | 17/07/2023 | 30 | TARA CONSTRUCTION | 10.06 | 9.8 | 100
308 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work laying of 180 mm dia HDPE pipe line at Alladi More to Jemnari Bus Stand and Railway crossing at Rupnarayanpur village in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of (Zone-V) with LDS & FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000227/2023-2024 | 2212/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 54.74 | 10.58 | 100
309 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of Dismantling & concrete works & extra cutting Laterate/sandstone at distribution network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000229/2023-2024 | 2248/RCD-1 | 17/07/2023 | 30 | SWATI CORPORATION | 12.73 | 9.93 | 80
310 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 3 (Three) nos. location at Lalganj Domohani Road under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000234/2023-2024 | 2230/RCD-I | 17/07/2023 | 30 | R B ENTERPRISE | 42.66 | 26.2 | 65
311 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000236/2023-2024 | 2216/RCD-I | 17/07/2023 | 30 | SIMA ENTERPRISE | 16.68 | 15.96 | 100
312 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Gowalabathan More towards Jamuria Road, Gowala para more towards Domohani Village, Goshala More towards Domohani village under Improvement of RCFA Part-I (Zone-11, Part-5) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000239/2023-2024 | 2232/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 19.77 | 19.76 | 100
313 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Kelejhora Health Centre More under Improvement of RCFA Part-I (Zone-11) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000242/2023-2024 | 2233/RCD-I | 17/07/2023 | 30 | SNEHA ELECTRIC | 29.11 | 16.38 | 55
314 | RCFA Division -I | RCFA Division I | Acceptation cum work order for Additional work for allied work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000246/2023-2024 | 2254/RCD-I | 17/07/2023 | 30 | MACHINO TECHNO | 99.31 | 71.44 | 100
315 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for laying of 200 mm dia Rising Main under Lalganj Bridge by concrete conduit and allied MS work including adopting trench less technology (e.g. Jack Pushing Method etc) of 04 (Four) nos. location at Barabani & near Kelejora Health Centre in connection to rising main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000248/2023-2024 | 2235/RCD-I | 17/07/2023 | 30 | M/S MONDAL ENTERPRISE | 50.86 | 50.09 | 100
316 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dabor More (250 mm dia Water Carrier 02 nos) and Dendua road to Chittaranjan road 01 no 450 mm dia Water Carrier and 02 nos 450 mm dia Water Carrier Pipe on Bonjemary Road of Salanpur Block under Improvement of RCFA Part-I (Part-A Rising Main) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000249/2023-2024 | 2236/RCD-I | 17/07/2023 | 30 | MD AAMIR KHAN | 51.47 | 51.44 | 100
317 | RCFA Division -I | RCFA Division I | Acceptance cum work order Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000250/2023-2024 | 2239/RCD-I | 17/07/2023 | 259 | MRITYUNJOY MUKHERJEE & CO. | 88.68 | 0 | 100
318 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000252/2023-2024 | 2238/RCD-I | 17/07/2023 | 30 | M/S B.K. CONSTRUCTION | 39.57 | 24.47 | 100
319 | RCFA Division -I | RCFA Division I | Construction of 450 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at Barabani (Zone-XIII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman [Rf Drwaing no. PC-I/OHR/04/2012(Sheet 1& 2) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000291/2022-2023 | 2448/RCD-I | 13/10/2022 | 365 | JOY HIND TUBEWELLS | 122.44 | 122.44 | 0
320 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Urgent basis repairing work of Churulia OHR of capacity 100000 gallons and 20 mtr staging height under Churulia Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000293/2021-2022 | 2025/RCD-I | 24/11/2021 | 30 | ASHA CONSTRUCTION | 15.47 | 15.33 | 0
321 | RCFA Division -I | RCFA Division I | Distribution Network for Improvement of RCFA Part-II Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000294/2022-2023 | 2451/RCD-I | 13/10/2022 | 180 | SINGHA ROY & CO. | 270.57 | 65.85 | 0
322 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of DI pipe, MS work, making valve chamber and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000295/2023-2024 | 2366/RCD-I | 04/08/2023 | 30 | SNEHA ELECTRIC | 51.75 | 50.2 | 98
323 | RCFA Division -I | RCFA Division I | Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone VII) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000298/2022-2023 | 2453/RCD-I | 13/10/2022 | 365 | SINGHA ROY & CO. | 181.16 | 163.04 | 100
324 | RCFA Division -I | RCFA Division I | Acceptance cum work order of Construction of CWR (Clear Water Reservoir) of Capacity 500 cum and allied work at Dendua under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000302/2022-2023 | 2484/RCD I | 18/10/2022 | 120 | D.S. ENTERPRISE | 61.78 | 43.72 | 96
325 | RCFA Division -I | RCFA Division I | Formal Work Order for Construction of 350 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-IX) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000324/2022-2023 | 2403/RCD-I | 30/09/2022 | 365 | MALLICK ENTERPRISE | 107.64 | 96.87 | 95
326 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-F) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000327/2022-2023 | 2404/RCD-I | 30/09/2022 | 180 | GITA CONSTRUCTION | 201.57 | 131.66 | 67
327 | RCFA Division -I | RCFA Division I | Formal Work Oder for Construction of 900 cum capacity 20 Mtr staging height RCC Over Head Reservoir (Pipe connection and cost of pipes, specials at (Zone-XI) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000380/2022-2023 | 2005/RCD-I | 25/08/2022 | 365 | AMAR CONSTRUCTION | 181 | 162.9 | 100
328 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (Length-160 mtr) at Malbahal OHR site of Improvement of RCFA Part-I Piped Water Supply Scheme under Salanpur Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000431/2023-2024 | 2662/RCD-I | 26/09/2023 | 583 | AMAR CONSTRUCTION | 35.5 | 0 | 100
329 | RCFA Division -I | RCFA Division I | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022) (Sl no 03) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000453/2021-2022 | 2456/RCD I | 31/12/2021 | 365 | MUKHERJEE TRADERS | 1.73 | 0.87 | 0
330 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000490/2021-2022 | 376/RCD-I | 15/02/2022 | 30 | MD AAMIR KHAN | 22.72 | 0 | 100
331 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000530/2022-2023 | 3143/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 100
332 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000531/2021-2022 | 491/RCD-I | 24/02/2022 | 90 | R B ENTERPRISE | 27.59 | 26.92 | 85
333 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-2 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000532/2021-2022 | 492/RCD-I | 24/02/2022 | 90 | SNEHA ELECTRIC | 25.78 | 25.39 | 75
334 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-3 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000533/2021-2022 | 493/RCD-I | 24/02/2022 | 401 | VISUVIOUS | 25.41 | 23.7 | 100
335 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000536/2021-2022 | 494/RCD-I | 24/02/2022 | 1042 | DAWN CONSTRUCTION | 68.87 | 65.56 | 100
336 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-5 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000538/2021-2022 | 495/RCD-I | 24/02/2022 | 1101 | M/S B.K. CONSTRUCTION | 44.11 | 37.17 | 100
337 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-6 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000541/2021-2022 | 496/RCD-I | 24/02/2022 | 1087 | UMA ENTERPRISE | 63.83 | 50.69 | 70
338 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000542/2021-2022 | 497/RCD-I | 24/02/2022 | 90 | UNITED CONSTRUCTION | 23.75 | 23.72 | 80
339 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-8 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000543/2021-2022 | 498/RCD-I | 24/02/2022 | 90 | SIMA ENTERPRISE | 30.98 | 29.26 | 81
340 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone - XI (Part-9 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000544/2021-2022 | 499/RCD-I | 24/02/2022 | 90 | SOMNATH SAMANTA | 39.28 | 38.73 | 98
341 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) of Water Pipe Lines including supplying and laying of 400 mm dia MS Pipe line at Alladi More on Sitarampur Chittaranjan Road in connection to rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000580/2022-2023 | 3288/RCD I | 20/12/2022 | 15 | MAK CONSTRUCTION CO. | 16.45 | 16.38 | 0
342 | RCFA Division -I | RCFA Division I | Laying of Rising Main (Part-B) at Mohismura Culvat crossing by constructing concrete piller, MS work and allied works under Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000581/2022-2023 | 3289/RCD I | 20/12/2022 | 17 | M/S MONDAL ENTERPRISE | 10.26 | 8.52 | 100
343 | RCFA Division -I | RCFA Division I | Acceptance cum work order for dedicated bypass line from Prantapally Durga Mandir to Kalyan Gram under Jitpur Uttarrampur GP under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000584/2022-2023 | 3292/RCD I | 20/12/2022 | 15 | ASHA CONSTRUCTION | 11.77 | 11.48 | 0
344 | RCFA Division -I | RCFA Division I | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000595/2022-2023 | SpotNIQ.Camp-02/Office/AE | 31/05/2022 | 183 | PRASENJIT DEY | 0.9 | 0 | 0
345 | RCFA Division -I | RCFA Division I | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Executive Engineer, RCFA Div-I, PHE Dte Govt. of West Bengal (w.e.f 01.06.2022 to 30.11.2022) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000596/2022-2023 | Spot/NIQ/Camp-02/Office/A | 31/05/2022 | 6 | PRASENJIT DEY | 0.9 | 0 | 0
346 | RCFA Division -I | RCFA Division I | Repalcing of old and damaged C.I. spiral stairs and other allied minor repairing works at Panchgachia OHR (Capacity 55000 gallon staging height 10 mtr under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte.(Sl no 06) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000612/2021-2022 | 635/RCD 1 | 09/03/2022 | 15 | RUBY CONSTRUCTION | 3.87 | 3.83 | 0
347 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Urgent basis repairing work of D P Colony (OHR) at D P Colony W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000618/2021-2022 | 712/RCD-I | 24/03/2022 | 30 | RUBY CONSTRUCTION | 15.72 | 15.13 | 0
348 | RCFA Division -I | RCFA Division I | Acceptance work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 450 mm dia MS pipe line at Mohismura More on NH Madhaichak Road in connection to rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000643/2022-2023 | 341/RCD I | 30/01/2023 | 15 | M/S MONDAL ENTERPRISE | 8.69 | 8.51 | 0
349 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Samdi and surrounding villages within Samdi Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000653/2023-2024 | 3450/RCD-I | 24/11/2023 | 15 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 3.39 | 0 | 100
350 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VI) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000658/2022-2023 | 357/RCDI | 30/01/2023 | 15 | DAS & SARKAR ENTERPRISE | 4.6 | 0 | 100
351 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 450 mm dia MS Pipe Line at Hunuman Mandir on Mohismura Ethora Road near Ethora OHR inconnection to rising main (Part-B) under Augmentation of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000676/2022-2023 | 360/RCD I | 30/01/2023 | 15 | M/S MONDAL ENTERPRISE | 11.17 | 11.09 | 0
352 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Different dia HDPE pipe line including extra cutting Laterate /sandstone and concrete cutting of distribution of pipe line Zone-I (Part-B) at Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000682/2022-2023 | 370/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 25.76 | 11.14 | 95
353 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000686/2022-2023 | 374/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 3.75 | 3.69 | 0
354 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000687/2022-2023 | 375/RCD I | 30/01/2023 | 15 | SWATI CORPORATION | 3.12 | 3.07 | 0
355 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and delivery of CI sluice valve and C.I/D.I specials under improvement of RCFA part-I piped water supply scheme under RCFA div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000701/2022-2023 | 613/RCD I | 23/02/2023 | 10 | MAKALI ENGINEERING CORPORATION | 28.49 | 28.49 | 0
356 | RCFA Division -I | RCFA Division I | Accepatance cum work order for construction of chlorine room of size (4.50 X 3.50m) at (Zone-IX) of Baraboni Block for Improvement of RCFA Part-I piped water supply scheme under RCFA Div-I, PHE Dte., in the District Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000737/2022-2023 | 676/RCDI | 24/02/2023 | 15 | ZEROTH CONTROL SYSTEM | 4.61 | 2.91 | 100
357 | RCFA Division -I | RCFA Division I | Additional extra cutting laterate/sandstone of distribution network for improvement of Part-I W/S Scheme within command area of Zone VII under RCFA Div-I, PHE Dte(Part-E) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000747/2022-2023 | 695/RCD I | 02/03/2023 | 7 | TARA CONSTRUCTION | 0.83 | 0.79 | 0
358 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying aligning and laying of HDPE Pipe line for restoration of pipe line towards MSPL at Kalyaneswari Dendua Road and supplying CI/DI specials in connection to aligning of rising main Part-A for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000762/2022-2023 | 389/RCD I | 30/01/2023 | 10 | MD AAMIR KHAN | 21.01 | 20.7 | 0
359 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and renovation of Panchagachia OHR of Capacity 1000 cum staging height 15 mtr under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000777/2022-2023 | 399/RCD I | 30/01/2023 | 90 | RUBY CONSTRUCTION | 20.33 | 11.62 | 100
360 | RCFA Division -I | RCFA Division I | Acceptance cum work order for additional work for laying of distribution network for Improvement RCFA Part-I Piped Water Supply Scheme within command area of Zone-XI (Part-9 Distribution Segment) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000831/2022-2023 | 1035/RCDI | 23/03/2023 | 376 | SOMNATH SAMANTA | 42.19 | 20.02 | 100
361 | RCFA Division -I | RCFA Division I | Acceptance cum work order for the additional work for the laying of different dia (315 mm , 280 mm, 225 mm ) dia HDPE pipe instead of different dia (300 mm , 250 mm, 200 mm) dia DJ pipe of distribution network for improvement RCA Part-I Water Supply Scheme within command area of Zone VI under RCFA Div-I, PHE Dte (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000832/2022-2023 | 1051/RCD I | 23/03/2023 | 30 | DIP CONSTRUCTION | 98.08 | 89.82 | 100
362 | RCFA Division -I | RCFA Division I | Acceptance cum work order for additional dedicated line to Sen Raleigh (Block-B) under Panchgachiya Distribution zone including laying of UPVC pipe line and allied works under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000833/2022-2023 | 1054/RCD I | 23/03/2023 | 15 | RUBY CONSTRUCTION | 11.13 | 11.11 | 0
363 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 500 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines including supplying and laying of 200 mm dia 250 mm dia MS pipe line at different location on Asansol Chittanrajan Road, Kalyaneswari Dendua road within command area of rising main (Part-A) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000834/2022-2023 | 1060/RCD-I | 23/03/2023 | 15 | MAK CONSTRUCTION CO. | 40.5 | 39.62 | 100
364 | RCFA Division -I | RCFA Division I | Acceptance cum work order Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) at 7 nos location at Zone-V area Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000837/2022-2023 | 1065/RCD-I | 23/03/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 45.79 | 45.79 | 50
365 | RCFA Division -I | RCFA Division I | Engagement of 01 (One) person under control of 02 (Two) nos Assistant Engineers of RCFA Division-I for day to day report and return of FHTC as per scheme wise, Panchayet wise and updation of JJM and verification of FHTC connection of School Aganawadi and Heath Centre and monitoring of report return of training of Asha Karmi under Health Department as per direction of EIC. under RCFA Division-I PHE Dte. (w.e.f. 01.01.2022 to 31.12.2022)(Sl no 03) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000838/2021-2022 | 2456/RCD- 1 | 31/12/2021 | 365 | MUKHERJEE TRADERS | 1.73 | 0.87 | 0
366 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Dismanting of existing Drain and reconstruction the same, Construction of RCC pipe carring structur and other allied work at Alladih more and Rupnarayanpur Railway Station Site of improvement of RCFA Part -I in Connection of Rising main Part-A under RCFA Division-I PHE Dte.(Sl No. 06) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000838/2022-2023 | 1066/RCD I | 23/03/2023 | 30 | MAK CONSTRUCTION CO. | 31.64 | 29.75 | 100
367 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of drain at Ethora and its adjoining mouzas under Improvement of RCFA Part-I W/S Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000849/2022-2023 | 1086/RCD-I | 23/03/2023 | 60 | SWATI CORPORATION | 23.95 | 23.94 | 0
368 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of water pipe lines at Sandi More (Node point 137) Sandi Masimura More (Node point 85) and Lalganj Domhani Road (Node point 5-26) under Augmentation of RCFA Part-I PWSS within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000857/2022-2023 | 1093/RCD-I | 23/03/2023 | 30 | SWATI CORPORATION | 19.65 | 19.65 | 0
369 | RCFA Division -I | RCFA Division I | Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines including supplying and laying of 500 mm dia and 150 mm dia MS pipe line at different location on Asansol Chittaranjan Road within command area of Zone-I (Dendua OHR) Distribution system (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000861/2022-2023 | 1095/RCD-I | 23/03/2023 | 30 | SWATI CORPORATION | 25.75 | 25.59 | 0
370 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Laying & Pushing of 400 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. jack Pushing Method etc) of Water Pipe Lines at Dabor More (Node point 334) Youth club (Node point 398) and Jaya hotel (Node point 228) Augmentation of RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. (Part-E) (Sl No. 28) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000862/2022-2023 | 1094 / RCD-I | 23/03/2023 | 30 | TARA CONSTRUCTION | 23.59 | 23.59 | 0
371 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply within command area of Zone-VI under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000874/2022-2023 | 1134/RCD-I | 24/03/2023 | 30 | M/S K & KONAR CONSTRUCTION | 30.49 | 19 | 100
372 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-4 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000875/2022-2023 | 1136/RCD-I | 24/03/2023 | 30 | DAWN CONSTRUCTION | 56.15 | 31.27 | 90
373 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-7 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000878/2022-2023 | 1138/RCD-I | 24/03/2023 | 30 | UNITED CONSTRUCTION | 24.64 | 17.12 | 90
374 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Lalganj more and Nuni more in related to laying of rising main (Part-B) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000883/2022-2023 | 1127/ RCD I | 24/03/2023 | 15 | M/S MONDAL ENTERPRISE | 23.75 | 23.62 | 0
375 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VI under RCAF Division-I PHE Dte. (Part-C) (Sl. No. 17) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000893/2022-2023 | 1143/ RCD I | 24/03/2023 | 30 | RANJIB GHATAK | 26.19 | 12.65 | 90
376 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) under RCAF Division-I PHE Dte. (SL No. 16) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000895/2022-2023 | 1142/ RCD I | 24/03/2023 | 283 | UMA ENTERPRISE | 76.17 | 32.7 | 100
377 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Road crossing by open cut near to Nuni more including construction of drain, laterite cutting, concrete and bitumen road cutting and allied works at Ethora and adjacent area for laying of Rising Main (Part-B) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 08) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000898/2022-2023 | 1152/RCD-1 | 24/03/2023 | 15 | M/S MONDAL ENTERPRISE | 5.09 | 4.7 | 100
378 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Dismantling of existing guard room and store room for construction of 500 cum CWR at Dendua Boosting station of Improvement of RCFA Part-I under RCFA Division-I PHE Dte. (Sl No. 09) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000901/2022-2023 | 1153/RCD-1 | 24/03/2023 | 10 | D.S. ENTERPRISE | 1.02 | 1.02 | 0
379 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (90 cum) at Surjanagar Head Works Site to replace existing damaged CWR under Improvement of RCFA (Part-I) Piped Water Supply Scheme. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000939/2021-2022 | 376_RCD_I | 15/02/2022 | 30 | MD AAMIR KHAN | 0 | 0 | 0
380 | RCFA Division -I | RCFA Division I | Continuation work order for Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-VI/BS-VI purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine, for the office Use of the Executive Engineer, RCFA Division-I PHE Dte. (w.e.f. 01.12.2022 to 31.05.2023) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/000955/2022-2023 | 3057/RCD-I | 30/11/2022 | 182 | PRASENJIT DEY | 0.9 | 0 | 0
381 | RCFA Division -I | RCFA Division I | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/001164/2023-2024 | Camp-02-Wall-Writing-AE-I | 18/01/2024 | 30 | MUKHERJEE TRADERS | 6.61 | 0 | 100
382 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of RCC column and M.S Structural Bridge for laying of 200 m dia MS pipe and other allied work for distribution network for Improvement of RCFA Part-I water supply scheme within command area of Zone-VII under RCFA Division ¿I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | ORD/001172/2023-2024 | 1012/RCD-I | 16/03/2024 | 30 | UNITED CONSTRUCTION | 6.54 | 0 | 100
383 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000002/2023-2024 | 1637/RCD-I | 27/04/2023 | 0 | Resource Division | 127.23 | 0 | 0
384 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000005/2021-2022 | 301/RCD-I | 02/02/2022 | 0 | Resource Division | 676.57 | 0 | 0
385 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000006/2021-2022 | 392/RCD-I | 16/02/2022 | 0 | Resource Division | 2340.25 | 0 | 0
386 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000008/2022-2023 | 2352/RCD-I | 28/09/2022 | 0 | Resource Division | 92.4 | 0 | 0
387 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000011/2021-2022 | 677/RCD-I | 21/03/2022 | 0 | Resource Division | 57.29 | 0 | 0
388 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000013/2022-2023 | 2644/RCD-I | 28/10/2022 | 0 | Resource Division | 64.5 | 0 | 0
389 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000015/2022-2023 | 2626/RCD-I | 17/11/2022 | 0 | Resource Division | 27.66 | 0 | 0
390 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000028/2022-2023 | 19/RCD-I | 05/01/2023 | 0 | Resource Division | 121.92 | 0 | 0
391 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | RTOR000030/2022-2023 | 54/RCD-I | 11/01/2023 | 0 | Resource Division | 180.92 | 0 | 0
392 | RCFA Division -I | RCFA Division I | Payment for sample PT test bill no 376/21-22 dt. 25.06.2021 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000011/2022-2023 | 545/22-23 | 01/11/2022 | 0 | GREEN ECONOMY INITIATIVES PRIVATE LIMITED | 0.01 | 0 | 0
393 | RCFA Division -I | RCFA Division I | Hire charges bill for vehicle no WB 37 D 0482 for the month of March 2022 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000121/2022-2023 | 518/22-23 | 29/09/2022 | 0 | SHYAMAL MAJI | 0.19 | 0 | 0
394 | RCFA Division -I | RCFA Division I | Submission of Quarterly regular return for non-salary 26Q3 & 26Q4 Regular Return for Salary 24Q3 & 24Q4 for the F.Y 2021-2022 and creation of Form 16 Part A & B 26Q2 for the F.Y 202021-22 Revised return for non salary return for the quarter 26Q3 & 26Q4 for the financial 2021-22 includes GST return for the month of April 2021 to March 2022 and April 2022 to May 2022 | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000366/2022-2023 | 383/22-23 | 17/08/2022 | 0 | SHRESTHA & ASSOCIATES | 0.58 | 0 | 0
395 | RCFA Division -I | RCFA Division I | Payment for furniture | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3,Junior Engineer-5 | VCH/000668/2022-2023 | 433/22-23 | 21/09/2022 | 0 | VYAS & CO. | 2.35 | 0 | 0
396 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000015/2021-2022 | 952/RCD-I | 07/06/2021 | 30 | DIP CONSTRUCTION | 23.01 | 4.1 | 0
397 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000016/2021-2022 | 953/RCD-I | 07/06/2021 | 30 | TARA MA ENTERPRISE | 23.02 | 45.17 | 0
398 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] | Assistant Engineer 1 | Junior Engineer | ORD/000017/2021-2022 | 954/RCD-I | 07/06/2021 | 30 | PINKI ENTERPRISE | 23.02 | 39.98 | 0
399 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-I), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000018/2021-2022 | 955/RCD-I | 07/06/2021 | 30 | MD AAMIR KHAN | 22.98 | 45.44 | 0
400 | RCFA Division -I | RCFA Division I | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC to Manahora, Kanskuli (Part) and Kalisanko villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1 | Junior Engineer | ORD/000139/2022-2023 | 1433/RCD I | 27/06/2022 | 45 | GITASREE FABRICATION | 1.97 | 1.76 | 0
401 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kalya (part) and Siakulberia and Chotkara (Part) village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 12) | Assistant Engineer 1 | Junior Engineer | ORD/000573/2021-2022 | 255/RCD-I | 01/02/2022 | 20 | JAYANTA DATTA | 4.99 | 4.64 | 0
402 | RCFA Division -I | RCFA Division I | Extension of HDPE pipe line (Parallel to main distribution) at village Kirtansala and Dharaspur village (Part) for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 1 | Junior Engineer | ORD/000578/2021-2022 | 260/RCD-I | 01/02/2022 | 20 | DIP CONSTRUCTION | 4.98 | 4.64 | 0
403 | RCFA Division -I | RCFA Division I | Extension of UPVC pipe line (Parallel to main distribution) at village Ghiadoba and Kusumdanali West side for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | Assistant Engineer 1 | Junior Engineer | ORD/000580/2021-2022 | 262/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 3.58 | 2.79 | 0
404 | RCFA Division -I | RCFA Division I | Arrangement of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conference hall | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01309/2023-2024 | 494/23-24 | 25/01/2024 | 0 | SHARMA ENGINEERING WORKS | 0.1 | 0 | 0
405 | RCFA Division -I | RCFA Division I | Arrangemen of breakfast and lunch box for DWSM meeting held on 13.01.2024 at ADDA Conferenc hall | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01310/2023-2024 | 495/23-24 | 25/01/2024 | 0 | SHARMA ENGINEERING WORKS | 0.09 | 0 | 0
406 | RCFA Division -I | RCFA Division I | Supply of it peripherals | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01741/2023-2024 | 497/23-24 | 25/01/2024 | 0 | MUKHERJEE TRADERS | 0.43 | 0 | 0
407 | RCFA Division -I | RCFA Division I | Supply of computer desktop | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01742/2023-2024 | 498/23-24 | 25/01/2024 | 0 | MUKHERJEE TRADERS | 0.42 | 0 | 0
408 | RCFA Division -I | RCFA Division I | AMC for xerox machine | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01743/2023-2024 | 455/23-24 | 04/01/2024 | 0 | WORK CHARGE BILL | 0.21 | 0 | 0
409 | RCFA Division -I | RCFA Division I | Repair & maintenance on contract basis of computers and local area network under SERCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01745/2023-2024 | 499/23-24 | 01/02/2024 | 0 | KALPANA ENTERPRISE | 0.46 | 0 | 0
410 | RCFA Division -I | RCFA Division I | Hiring charge of Maxi cab (non conditioned) stage II / BS III for ofice use Veh WB 37 D 9526 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01746/2023-2024 | 553/23-24 | 27/02/2024 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
411 | RCFA Division -I | RCFA Division I | Hirig of maxi cab state II/BS III for the office use of the Assistant Engineer | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01747/2023-2024 | 554/23-24 | 27/02/2024 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
412 | RCFA Division -I | RCFA Division I | Hire charges bill for vehicle no WB 37 D0482 for the month of January | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01748/2023-2024 | 570/23-24 | 27/02/2024 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
413 | RCFA Division -I | RCFA Division I | Fuel bill of Ranajit Auto vehicle no WB 37 D 0482 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01749/2023-2024 | 571/23-24 | 27/02/2024 | 0 | RANAJIT AUTO | 0.19 | 0 | 0
414 | RCFA Division -I | RCFA Division I | Vehicle bill for the month of Dec 2023 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01750/2023-2024 | 529/23-24 | 06/02/2024 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
415 | RCFA Division -I | RCFA Division I | Fuel bill for shyamal Maji for the month of Dec 23 | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | BILL/01751/2023-2024 | 530/23-24 | 08/02/2024 | 0 | RANAJIT AUTO | 0.17 | 0 | 0
416 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for sinking 3 nos 200 mm dia river bed tube wells and allied repairing work in river Damodar including surging of tube wells at Damalia H/W site under Tirat Mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 11) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000002/2023-2024 | 1387/RCD-I | 11/04/2023 | 12 | D.S.C. CONCERN | 6.88 | 6.87 | 0
417 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency supplying aligning and laying of different dia HDPE pipe line for by pass water supply arrangement to Roypara, Singhapara and adjacent areas under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000007/2022-2023 | 937/RCD-I | 26/04/2022 | 30 | M/S MONDAL ENTERPRISE | 24.23 | 24.17 | 0
418 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through retrofitting at Saheb Bangla & allied areas at Khottamdihi Block Pandabeswar of Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000039/2021-2022 | 978/RCD-I | 17/06/2021 | 1550 | A.K. SIKDAR | 19.13 | 26.36 | 100
419 | RCFA Division -I | RCFA Division I | Acceptance cum work order Providing FHTC of retrofitting at Kumardihi village (Left out portion) of kumardiha Mouza, GP-Ratibati, Block Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000057/2023-2024 | 1742/RCD I | 11/05/2023 | 15 | D.S.C. CONCERN | 7.9 | 7.51 | 0
420 | RCFA Division -I | RCFA Division I | Continuation work order for Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000098/2021-2022 | 816/RCD-I | 19/04/2021 | 45 | GITA CONSTRUCTION | 11.84 | 9.17 | 0
421 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000102/2020-2021 | 1156 /RCD I | 23/12/2020 | 20 | A.K.CONSTRUCTION | 4.43 | 6.18 | 0
422 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000103/2020-2021 | 1157/RCD I | 23/12/2020 | 20 | DHRUBA ENTERPRISE | 4.45 | 6.13 | 0
423 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000104/2020-2021 | 1158/RCD I | 23/12/2020 | 20 | M/S MONDAL CONSTRUCTION | 4.44 | 6.17 | 0
424 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000105/2020-2021 | 1159/RCD I | 23/12/2020 | 20 | VISUVIOUS | 4.47 | 6.17 | 0
425 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Metaldhaora, Booth No. 05, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000106/2020-2021 | 1160/RCD I | 23/12/2020 | 20 | MS KALYAN ENTERPRISE | 4.45 | 6.37 | 0
426 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Providing FHTC through Retrofitting at Chelod Mouza, G.P.-Tirat, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000108/2020-2021 | 1167/RCD-I | 23/12/2020 | 30 | MRITYUNJOY MUKHERJEE & CO. | 37.97 | 31.34 | 0
427 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000110/2020-2021 | 1185/RCD-I | 24/12/2020 | 30 | SWATI CORPORATION | 39.19 | 58.25 | 0
428 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Providing FHTC through Retrofitting at Kumardiha Mouza, G.P.-Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000111/2020-2021 | 1186/RCD-I | 24/12/2020 | 30 | M/S B.K. CONSTRUCTION | 19.63 | 35.64 | 0
429 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Seora Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 05) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000112/2020-2021 | 1187/RCD-I | 24/12/2020 | 30 | A. CONSTRUCTION CO. | 20.48 | 39.53 | 0
430 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ratibati (Part-II), G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No. 06) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000113/2020-2021 | 1188/RCD-I | 24/12/2020 | 30 | SOMNATH SAMANTA | 22.88 | 40 | 0
431 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 2 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000114/2020-2021 | 1189/RCD-I | 24/12/2020 | 30 | GITASHREE FABRICATION | 12.68 | 19.38 | 0
432 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Mines Quarter Booth No. 3, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000115/2020-2021 | 1190/RCD-I | 24/12/2020 | 30 | SIMA ENTERPRISE | 9.93 | 12.38 | 0
433 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dom Para Both No. 4, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000116/2020-2021 | 1191/RCD-I | 24/12/2020 | 30 | DAWN CONSTRUCTION | 18.7 | 7.57 | 0
434 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Khottamdih Village, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 04) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000117/2020-2021 | 1192/RCD-I | 24/12/2020 | 30 | M/S MONI TRADERS | 14.1 | 19.45 | 0
435 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at ECL 3 Nos Colliery area, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000118/2020-2021 | 1193/RCD-I | 24/12/2020 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 16.09 | 22.19 | 0
436 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) (Sl No. 06) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000119/2020-2021 | 1194/RCD-I | 24/12/2020 | 30 | DURGADAS MONDAL | 9.08 | 10.62 | 0
437 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Kendra Mouza, Booth No. 1 (Kendra Gram), Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 07) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000120/2020-2021 | 1195/RCD-I | 24/12/2020 | 30 | UNITED CONSTRUCTION | 9.15 | 13.54 | 0
438 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Chatadhawra, Booth No. 02, Vill - Kendra, Block - Pandabeswar of Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000122/2020-2021 | 1155/RCD I | 23/12/2020 | 20 | ZEROTH CONTROL SYSTEM | 4.4 | 5.68 | 0
439 | RCFA Division -I | RCFA Division I | Laying of HDPE pipe line and other repairing work of distribution at Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000152/2022-2023 | 1446/RCD I | 27/06/2022 | 45 | M/S MONDAL ENTERPRISE | 2.54 | 2.49 | 0
440 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, aligning and laying of DI & HDPE pipe line for water supply arrangement to Kumardiha village under Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000156/2021-2022 | 1584/RCD-I | 07/09/2021 | 30 | M/S MONDAL ENTERPRISE | 20.03 | 19.9 | 0
441 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia UPVC/HDPE pipe line for extension of distribution system regarding FHTC work at Kumardiha mouza of Ratibati water supply scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000160/2021-2022 | 1585/RCD-I | 07/09/2021 | 30 | M/S B.K. CONSTRUCTION | 14.42 | 13.73 | 0
442 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, Aligning and laying of HDPE pipe line for FHTC work at Chapui mouzas of Ratibati W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000162/2021-2022 | 1587/RCD-I | 07/09/2021 | 30 | SWATI CORPORATION | 25.46 | 17.1 | 0
443 | RCFA Division -I | RCFA Division I | Providing FHTC through Retrofitting at Salanpur Mouza, Vill-Salanpur, Block-Salanpur of Salanpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000215/2020-2021 | 432 /RCD-I | 04/03/2021 | 45 | GITA CONSTRUCTION | 46.13 | 75.61 | 0
444 | RCFA Division -I | RCFA Division I | Sinking of 3 (Three) nos 200 mm dia River Bed Tube Wells including repairing work of 100 mm dia Collecting Mains which were damaged due to flood in the month of July - August & etc. allied works at River Damodar under Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. (sl no 05) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000278/2021-2022 | 1937/RCD I | 09/11/2021 | 20 | M/S PIONEER CONSTRUCTION | 3.17 | 2.92 | 0
445 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari Bauri Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000294/2021-2022 | 2026/RCD-I | 24/11/2021 | 30 | RANJIB GHATAK | 26.95 | 22.7 | 0
446 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying, laying and aligning distribution branch main from distribution main including providing FHTC work at Bilpahari General Para (Re-habilitated village) under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000295/2021-2022 | 2027/RCD-I | 24/11/2021 | 30 | SWATI CORPORATION | 39.08 | 31.16 | 0
447 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and laying of 16 sqmm x 4 core Al armored PVC power cable and 10 HP Submersible Pump at Ratibati river bed pump house site damaged due to spreading of fire of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000298/2021-2022 | 2030/RCD-I | 24/11/2021 | 10 | M/S PIONEER CONSTRUCTION | 11.72 | 11.72 | 0
448 | RCFA Division -I | RCFA Division I | Annual Maintenance Contract (AMC) for Computers, Prnters, UPS & other related peripherals installed at office chamber of the Assistant Engineer, Junior Engineers, DPMU, IEC under of the Executive Engineer, RCFA Division-I PHE Dte. (Period from 01.07.2023 to 31.12.2023) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000308/2023-2024 | 2039/RCD-I | 30/06/2023 | 184 | SHARMA ENGINEERING WORKS | 0.9 | 0 | 100
449 | RCFA Division -I | RCFA Division I | Laying of 50 mm dia PVC pipe line and construction of different dia valve chamber, FHTC work and etc. allied works at Kendra area under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000326/2021-2022 | 2175/RCD I | 06/12/2021 | 10 | MS KALYAN ENTERPRISE | 4.57 | 4.47 | 0
450 | RCFA Division -I | RCFA Division I | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chapui (CT) Mouza, G.P.- Ratibati, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte. (Sl No 17) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000339/2020-2021 | 363/RCD I | 26/02/2021 | 7 | SWATI CORPORATION | 4.68 | 9.36 | 0
451 | RCFA Division -I | RCFA Division I | Supply of 10 mm NB Gun-metal ferrule for Providing FHTC through Retrofitting at Chelod Mouza, G.P.- Tirat, Block- Raniganj of Ratibati Water supply scheme under RCFA Division-I, P.H.E. Dte.(SL NO 18) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000341/2020-2021 | 364/RCD I | 26/02/2021 | 7 | MRITYUNJOY MUKHERJEE & CO. | 4.66 | 9.33 | 0
452 | RCFA Division -I | RCFA Division I | Hiring of Maxi Cab (Non Air- conditioned ) bharatstage - III/BS-III purchased on after 01.05.2008 with Diesel / LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal ( w.e.f 16.08.2023 to 15.02.2024) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000354/2023-2024 | 2420/RCD-I | 11/08/2023 | 184 | PRAMIT CHATTERJEE | 0.9 | 0 | 100
453 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dhandardihi Mouza, Vill-Madanpur, Block-Andal of Dhandardihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000357/2020-2021 | 1032/RCD-I | 05/11/2020 | 30 | MACHINO TECHNO | 43.84 | 13.66 | 0
454 | RCFA Division -I | RCFA Division I | Supply, fitting fixing railling, grill, painting of pump house, CWR, chlorine room etc and allied works at Ratibati H/W and Tirat Colliery H/W site under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000359/2021-2022 | 2203/RCD I | 06/12/2021 | 21 | SOMNATH SAMANTA | 3.53 | 2.97 | 0
455 | RCFA Division -I | RCFA Division I | Laying UPVC pipeline for FHTC work for Dhandadihi W/S Scheme under RCFA Div-I, PHE Dte.(Sl no 01) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000456/2021-2022 | 2458/RCD I | 31/12/2021 | 10 | MACHINO TECHNO | 3.83 | 3.82 | 0
456 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Kumardiha village area of Chold mouza, GP -Ratibati Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 08) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000462/2021-2022 | 2465/RCD I | 31/12/2021 | 7 | D.S.C. CONCERN | 4.81 | 4.81 | 0
457 | RCFA Division -I | RCFA Division I | Additional laying of different dia UPVC pipeline for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 09) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000463/2021-2022 | 2466/RCD I | 31/12/2021 | 15 | MACHINO TECHNO | 4.78 | 4.55 | 0
458 | RCFA Division -I | RCFA Division I | Hard rock cutting, laying of different dia UPVC pipe line for extension of distribution system regarding FHTC work at Chelod mouza of Ratibati W/S Scheme under RCFA Div-I PHE Dte.(Sl no 10) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000464/2021-2022 | 2467/RCD I | 31/12/2021 | 15 | MACHINO TECHNO | 3.06 | 2.82 | 0
459 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Damra rural and adjacent area of Chelod mouza, G.P, Tirat , GP Block Raniganj of Ratibati water supply scheme under RCFA Division-I PHE Dte.(Sl no 11) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000465/2021-2022 | 2468/RCD I | 31/12/2021 | 10 | GOPAL CONSTRUCTION | 4.68 | 4.68 | 0
460 | RCFA Division -I | RCFA Division I | Laying of different dia UPVC pipeline for extension system regarding FHTC work at Chelod village of Ratibati W/S Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000488/2021-2022 | 2464/RCD-I | 31/12/2021 | 15 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.81 | 2.35 | 0
461 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia PVC/HDPE pipe line for extension of distribution system regarding FHTC work at Ratibati Mouza of Ratibati Water Supply Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000558/2021-2022 | 581/RCD-I | 02/03/2022 | 15 | SOMNATH SAMANTA | 9.58 | 9.55 | 0
462 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Chelod village area (Part-A) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000601/2021-2022 | 278/RCD-I | 01/02/2022 | 30 | M/S MONDAL CONSTRUCTION | 4.84 | 4.55 | 0
463 | RCFA Division -I | RCFA Division I | Laying of Different dia UPVC /PVC pipeline for extention of distribution system regarding FHTC work at Saora Mouza of Ratibati Water supply Scheme under RCFA Div-I PHE Dte. (Sl No 17) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000602/2021-2022 | 280/RCD-I | 01/02/2022 | 30 | A. CONSTRUCTION CO. | 4.81 | 4.81 | 0
464 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Chelod village area (Part-B) of Chelod mouza, GP Ratibati, Block-Raniganj of Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000606/2021-2022 | 279/RCD-I | 01/02/2022 | 30 | M/S U.G. ENTERPRISE | 4.84 | 4.84 | 100
465 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of HDPE pipe line for byepass water supply arrangement to Chapui village under Ratibati Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A)(Sl no 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000608/2021-2022 | 631/RCD-1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.75 | 4.75 | 0
466 | RCFA Division -I | RCFA Division I | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-B)(Sl no 3) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000609/2021-2022 | 632/RCD 1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.76 | 4.72 | 0
467 | RCFA Division -I | RCFA Division I | Emergency supplying. Aligning and laying of HDPE pipe line for bypass water supply arrangement to Chapui village under Ratibati water supply scheme under RCFA Division-I PHE Dte. (Part-C)(Sl no 04) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000610/2021-2022 | 633/RCD 1 | 09/03/2022 | 15 | SWATI CORPORATION | 4.84 | 4.82 | 0
468 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Interconnection work including Augurboring, supply of value, construction of valve, construction of valve chamber within command under Dabor OHR under Retrofitting of 4 Nos. PWSS for providing FHTC under RCFA Division-I PHE Dte (sl. no-6). | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000772/2022-2023 | 804/RCD-I | 06/03/2023 | 10 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 12.51 | 12.28 | 0
469 | RCFA Division -I | RCFA Division I | Acceptance cum work order Emergency repairing of damaged collecting main in river Damodar and allied works at Surjanagar H/W site of Surjanagar W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000924/2022-2023 | 1257/RCD-I | 27/03/2023 | 15 | MD. JAWED KHAN | 4.31 | 4.15 | 0
470 | RCFA Division -I | RCFA Division I | Acceptance cum work order Supplying Laying 90 mm dia HDPE pipe line, sluice valve chamber, Street Stand Post and other allied works within Amritnagar Rising Main & Distribution of Tirat Colliery W/S Scheme Zone under Improvement Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000943/2022-2023 | 1279/RCD-I | 27/03/2023 | 15 | MS KALYAN ENTERPRISE | 4.81 | 4.8 | 0
471 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Street Stand Post, Sluice Valve Chamber and Aligning Laying HDPE pipe in different places (Nimcha, Damra, Chelod Bouripara, Tirat Hospital Etc.) under Tirat Colliery W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000944/2022-2023 | 1281/RCD-I | 27/03/2023 | 15 | MS KALYAN ENTERPRISE | 4.57 | 4.57 | 80
472 | RCFA Division -I | RCFA Division I | Acceptance cum work order 300 mm dia MS Bye pass line and interconnection work at Khandra OHR site and allied works of Dakhin Khandra and Mahira adjacent area under Retrofitting of 4 Nos. Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | ORD/000957/2022-2023 | 1056/RCD-I | 23/03/2023 | 15 | UNITED CONSTRUCTION | 15.47 | 15.47 | 0
473 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | RTOR000009/2021-2022 | 439/RCD-I | 21/02/2022 | 0 | Resource Division | 11 | 0 | 0
474 | RCFA Division -I | RCFA Division I | Repairing of 6 (Six) nos panel board, panel board wiring, Supply and installation of 10 HP submersible pump & motor & cable laying & other allied works at Ratibati river bed pump house site of Ratibati W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | VCH/000069/2022-2023 | 172/22-23 | 13/06/2022 | 0 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 0
475 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting at Dhandardihi Mouza, vill-Madanpur, Block -Andal of Dhandadihi Water supply scheme under RCFA Div-I PHE Dte. | Assistant Engineer 1,Assistant Engineer 2 | Junior Engineer | VCH/000832/2020-2021 | 45/21-22 | 15/07/2021 | 0 | MACHINO TECHNO | 25.79 | 0 | 0
476 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional work of supplying ,laying and aligning of HDPE Distribution pipeline & allied works including functional household tap connection (FHTC) at Pathanpara command area for Augmentation of Ground Water Based Water Supply Scheme for Telipara under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000385/2025-2026 | 1759/RCDI | 18/06/2025 | 166 | MAK CONSTRUCTION CO | 76.14 | 0 | 50
477 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied work of laying distribution system, New FHTC and re connection of FHTC at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000455/2025-2026 | 2010/RCD-I | 11/07/2025 | 30 | M/S KALYANI ENTERPRISE | 18.97 | 0 | 0
478 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Switch Room (5.4 m x 3.6 m) at Shibpur of Augmentation of Telipara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000615/2025-2026 | 2011/RCD-I | 11/07/2025 | 90 | MOUMITA ENTERPRISE | 6.73 | 0 | 0
479 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of RCC Conduit for crossing of HDPE Rising Main across the Kunur river at Jemua Augmentation of Ground Water Based Water Supply Scheme for Napara under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000223/2024-2025 | 2542/RCD-I | 29/10/2024 | 90 | ASHA CONSTRUCTION | 64.49 | 0 | 50
480 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Sukna with Boundary wall, Pump House & other allied works of Augmentation of ground water based water supply scheme for Napara under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000295/2024-2025 | 2625/RCD-I | 14/11/2024 | 137 | UNITED CONSTRUCTION | 27.73 | 0 | 60
481 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Dhobaghata with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Napara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000357/2024-2025 | 2848/RCD-I | 04/12/2024 | 309 | UNITED CONSTRUCTION | 54.09 | 0 | 60
482 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 500 cum & allied work at Pansuili Head Works Site under Augmentation of Ground Water Based Water Supply Scheme for Napara W/S Scheme under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-3 | ORD/000359/2024-2025 | 2851/RCD-I | 04/12/2024 | 362 | BABA LOKNATH ENTERPRISE | 63.91 | 0 | 40
483 | RCFA Division -I | Asansol Mechanical Division | Formal work order for creating separate zone for Adibasipara near WTP Panagarh, supplying, laying of 160 mm dia HDPE distribution pipe line and other allied works at Anandapur, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), at Bistupur and Dannay. Mohal & Sinking of 2 Nos 300 X 200 MM dia RBT tube well at Silampur under Augmentation of Kanksha (Zone-I & II), Augmentation of RCFA Part-III (Zone-II), Augmentation of ground water based water supply scheme Napara under RCFA Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/001024/2023-2024 | 662/RCD-I | 29/02/2024 | 90 | SARASWATI ENTERPRISE | 119.89 | 0 | 100
484 | RCFA Division -I | Asansol Mechanical Division | Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Telipara PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer-I | Junior Engineer-3 | ORD/001028/2023-2024 | 684_RCD-1 | 29/02/2024 | 184 | MALLICK ENTERPRISE | 1.64 | 0 | 0
485 | RCFA Division -I | Asansol Mechanical Division | Addition work for Laying of HDPE pipeine and Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission at of Arra Mouza JL No 89 Under command area of Augumentation of Napara piped W/S Scheme,under D.W.S.D., P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/001039/2022-2023 | 327/DWSD | 20/02/2023 | 35 | DARPAN DAS & CO | 70.42 | 0 | 75
486 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum formal order for the work of Additional pipe line work with concrete cutting at Shilampur mouza for providing FHTC in connection with Jal Jeevan mission for Shilampur Mouza(JL90) under Augmentation of Napara Piped W/s Scheme at Kanksa block under DWSD, PHE Dte (SL-18) | Assistant Engineer-I | Junior Engineer-3 | ORD/001189/2023-2024 | 1014/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 96.46 | 0 | 0
487 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum formal order for the work of construction of pump house cum chlorine room at Silampur pump house No-I H/W site for of Kanksa (Zone-I) Under Augmentation of Napara P piped W/s Scheme under DWSD,PHE Dt | Assistant Engineer-I | Junior Engineer-3 | ORD/001236/2023-2024 | 1279_DWSD | 07/08/2023 | 45 | MUKHERJEE ENTERPRISE | 6.41 | 0 | 100
488 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 900 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000157/2023-2024 | 1902/RCD-I | 09/06/2023 | 245 | M/S SANTANU PALIT & CO. | 182.7 | 0 | 70
489 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 4 (Four) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Amritnagar Water Supply Scheme (Phase-I & II) under RCFA Division-I PHE Dte. 2nd Call | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000367/2022-2023 | 2875/RCD-I | 07/11/2022 | 30 | NIYATI CONSTRUCTION | 24.5 | 17.68 | 0
490 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency Sinking of 04 (Four) nos. 200 mm dia river bed tube well including collecting main for in the river Damodar of Amritnagar Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000389/2023-2024 | 2575/RCD-I | 07/09/2023 | 323 | M/S UNITED CONSTRUCTION | 6.75 | 6.13 | 100
491 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Dismantling & reconstruction of flooring of pump house, CWR and other allied works at H/W site of Tirat Colliery under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000402/2023-2024 | 2584/RCD-I | 07/09/2023 | 15 | MS KALYAN ENTERPRISE | 5.16 | 5.1 | 100
492 | RCFA Division -I | RCFA Division I | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. (sL no. 01) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000534/2021-2022 | 500/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.04 | 4.04 | 0
493 | RCFA Division -I | RCFA Division I | Formal work order for laying of distribution system to accommodate FHTC and providing FHTC including supplying, laying, fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe with all necessary specials, saddle piece etc. all complete at Egara, Amkula and part of Nimcha Mouza Part-B) for Augmnentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Division I, PHE Dte.under RCFA Division I,PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000603/2022-2023 | 37/RCD I | 11/01/2023 | 760 | TARAPRASAD SARKAR | 164.7 | 43.33 | 50
494 | RCFA Division -I | RCFA Division I | Formal work order for laying of distribution system to accommodate FHTC and proving FHTC including supplying, laying,fitting, fixing of 15 mm NB PVC (schedule 80)/20 mm OD HDPE (PE100,PN6) pipe wth all necessary specials, saddle piece etc all complete at Murgasole mouza for augmentation of Sub surface Water Based Piped Water Supply Scheme for Amritnagar Zone-I under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000605/2022-2023 | 35/RCD I | 11/01/2023 | 90 | DAS & CHAKRABORTY | 113.18 | 45.55 | 0
495 | RCFA Division -I | RCFA Division I | Laying of distribution system to accommodation FHTC and providing FHTC including supplying, laying, fitting fixing of 15mm NB PVC (schedule 80) /20 mm OD HDPE (PE ,PN6) pipe with all necessary specials.saddle piece etc all complete at Egara, Amkula and part of Nimcha mouza for Improvement of RCFA Part-II Water Supply Scheme under RCFA Div-I, PHE Dte. under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000607/2022-2023 | 36/RCD I | 11/01/2023 | 45 | M/S SINGH & KONAR CONSTRUCTION | 167.84 | 31.26 | 55
496 | RCFA Division -I | RCFA Division I | Acceptance work order for sinking of 6 nos river bed 200 dia tube well including laying of collecting main for augmentation of sub surface water based piped water supply scheme for Amritnagar Zone-I within RCFA Part-II area under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000614/2022-2023 | 3272/RCDI | 20/12/2022 | 30 | M/S MONDAL CONSTRUCTION | 13.37 | 13.37 | 100
497 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for adopting trench less technology (e.g. Jack Pushing Method etc) at i) Opposite Amritnagar OHR, ii) near Nimcha Kata More, iii) near Mincha Rail gate and allied MS work, supply of valves, specials etc at Murgathole Mouza under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000641/2023-2024 | 3421/RCD-1 | 24/11/2023 | 147 | DAS & CHAKRABORTY | 33.99 | 0 | 100
498 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work for Laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000951/2023-2024 | 478/RCD-I | 12/02/2024 | 45 | TARAPRASAD SARKAR | 44.86 | 0 | 80
499 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for supply and laying HDPE pipe instead of DI pipe for the work of laying distribution system under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000952/2023-2024 | 501/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 30.11 | 0 | 50
500 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Pipe line crossing adopting trench less Technology (e.g. Jack Pushing method etc.) near Deshbandhu Park, Chittaranjan Road, Joadbari Rupnarayanpur from node no 921 to 924 RCFA Part-I PWSS within command area of Zone-VII under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000979/2023-2024 | 494/RCD-I | 12/02/2024 | 15 | KONAR CONSTRUCTION | 6.55 | 0 | 100
501 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying of DI pipe under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000985/2023-2024 | 473/RCD-I | 12/02/2024 | 15 | M/S SINGH & KONAR CONSTRUCTION | 8.65 | 0 | 80
502 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000991/2023-2024 | 481/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 0 | 80
503 | RCFA Division -I | RCFA Division I | Formal work order for Laying of Distribution System to Accommodate FHTC and Providing FHTC including Supplying laying, fitting, fixing of 15 mm NB PVC (Schedule 80) 20 mm OD HDPE (PE 100, PN 6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001036/2022-2023 | 2455./RCD-I | 02/11/2022 | 180 | MACHINO TECHNO | 130.76 | 104.24 | 90
504 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | RTOR000021/2022-2023 | 3126 | 09/12/2022 | 0 | Resource Division | 86.94 | 0 | 0
505 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I Phe Dte. (Zone-9A) | Assistant Engineer 2 |  | ORD/000073/2023-2024 | 1760/RCD I | 16/05/2023 | 839 | ASHA CONSTRUCTION | 345.86 | 0 | 80
506 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work and crossing road by trenchless technology in different site connection with distribution network including FHTC & allied work at Andal Block of Augmentation PWSS RCFA Part-II (Zone-9A) under RCFA Division-I PHE, Dte | Assistant Engineer 2 |  | ORD/000193/2024-2025 | 2420/RCD-I | 26/09/2024 | 45 | MACHINO TECHNO | 69.72 | 0 | 100
507 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Repairing of Boundary Wall for 45 mtr at Chora OHR Site of RCFA Part-II (Zone- 9, 9A and 9B) PWSS Block-Pandabeswar under RCFA Division-I PHE Dte. (Sl No. 01) | Assistant Engineer 2 |  | ORD/000916/2022-2023 | 1144/RCD-1 | 24/03/2023 | 15 | N.R. CONSTRUCTION | 4.61 | 0 | 100
508 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for distribution network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-9A(Segment-III) under RCFA Division-I. PHE Dte. | Assistant Engineer 2 |  | ORD/001176/2023-2024 | 1016/RCD-I | 16/03/2024 | 45 | UNITED CONSTRUCTION | 35.76 | 0 | 70
509 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000024/2023-2024 | 2951/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
510 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-08 at Andal under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00112/2024-2025 | 46/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.81 | 0 | 0
511 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-10 under Augmentation of RCFA Part-II (Zone-9) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00155/2024-2025 | 68/24-25 | 30/05/2024 | 0 | EASTERN RAILWAY | 4.73 | 0 | 0
512 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under RCFA Part-II PWSS (Zone-9) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000014/2024-2025 | 1516/RCD-I | 14/06/2024 | 15 | MAKALI ENGINEERING CORPORATION | 99.5 | 0 | 100
513 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply of different dia Sluice valve, including C.I. / D.I. Specials to the Searsole Store of RCFA Part-II (Zone-9) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000015/2024-2025 | 1518/RCD-I | 14/06/2024 | 15 | MAKALI ENGINEERING CORPORATION | 77.57 | 0 | 100
514 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for RCFA Prt-II Pipe Water Supply scheme including FHTC & allied ork under RCFA Division-I PHE Dte. (Zone-9) Parshkol (Part-A) | Assistant Engineer 2 |  | ORD/000038/2023-2024 | 1607/RCD I | 25/04/2023 | 90 | MD AAMIR KHAN | 107.46 | 0 | 70
515 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work related to shifting Rising main, laying of distribution network, Road restoration and other allied work for Ondal Block of Augmentation PWSS of RCFA Part-II (Zone - 9) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000199/2024-2025 | 2457/RCD-I | 01/10/2024 | 30 | M/S UNIT CONSTRUCTION | 45.22 | 0 | 100
516 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Dedicated line towards Paharpur village, Kallya village and necessary repairing including supply of valve construction of valve chamber etc. within Distribution Network of Dabor OHR under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000395/2023-2024 | 2577/RCD-I | 07/09/2023 | 15 | DHRUBA ENTERPRISE | 9.05 | 0 | 100
517 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of laying dia HDPE Pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-9 for Augmentation of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000517/2023-2024 | 2868/RCD-I | 06/10/2023 | 453 | MACHINO TECHNO | 89.05 | 0 | 50
518 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line at Pure Jambad Hattala Zone, Real Jambad under Bahula (CT) (Jl No. 30, Block-Pandabeswar under Improvement of RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000593/2022-2023 | 3299/RCD I | 20/12/2022 | 60 | GITA CONSTRUCTION | 78.64 | 21.9 | 90
519 | RCFA Division -I | RCFA Division I | Acceptance cum work order for 2 nos Emergency repairing work of 450mm dia rising main at Basu Vata and Jamdoba under RCFA Part-II water supply scheme under RCFA Div-I, PHE Dte | Assistant Engineer 2 |  | ORD/000610/2023-2024 | 3376/RCD-I | 21/11/2023 | 15 | KHEPI MAA TRADERS | 2.16 | 0 | 100
520 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 |  | ORD/000663/2023-2024 | 3432/RCD-1 | 24/11/2023 | 30 | JAI MAHARAJ ENTERPRISE | 6.86 | 0 | 100
521 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Pump House at Dendua for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000696/2022-2023 | 487/RCDI | 03/02/2023 | 90 | D.S. ENTERPRISE | 30.3 | 0 | 77
522 | RCFA Division -I | RCFA Division I | Emergency repairing work 750 mm dia Rising main at Kalyaneswari Dendua road under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000736/2023-2024 | Camp_02_Kalyaneswari_AE_I | 06/10/2023 | 15 | MD AAMIR KHAN | 2.75 | 0 | 100
523 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repair and renovation works of one no RCC Elevated Reservoir of capacity 1362 cum at Chora for RCFA Part-II (Zone-9, 9A & 9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 |  | ORD/000844/2022-2023 | 1078/RCD I | 23/03/2023 | 270 | ASHA CONSTRUCTION | 17.06 | 0 | 100
524 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied works under RCFA Division-I PHE Dte.(Zone-9) Parshkol (Part-B)(Sl No. 16) | Assistant Engineer 2 |  | ORD/000846/2022-2023 | 1081/RCD I | 23/03/2023 | 90 | ALOKESH BANERJEE | 40.44 | 13.78 | 35
525 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Store Room at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 25) | Assistant Engineer 2 |  | ORD/000894/2022-2023 | 1168/RCD I | 24/03/2023 | 90 | M/S S.K. ENTERPRISE | 4.61 | 0 | 0
526 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at Chora of Pandabeswar Block for Augmentation of RCFA Part-II (Zone-9) Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (2nd Call) | Assistant Engineer 2 |  | ORD/000915/2023-2024 | 212/RCD-I | 29/01/2024 | 90 | KALYAN DAWN | 4.57 | 0 | 100
527 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-XI) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000973/2022-2023 | 3148/RCD-I | 12/12/2022 | 7 | AMAR CONSTRUCTION | 0.98 | 0 | 100
528 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000023/2023-2024 | 2949/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
529 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-92 at Ukhra under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | BILL/00115/2024-2025 | 48/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 16.46 | 0 | 0
530 | RCFA Division -I | RCFA Division I | Way leave track crossing proposal with application ID - ER-ASN-2024-WL-57 Payment of wayleave facility charges. | Assistant Engineer 2 | Junior Engineer | BILL/00546/2024-2025 | 273/24-25 | 05/09/2024 | 0 | EASTERN RAILWAY | 9.09 | 0 | 0
531 | RCFA Division -I | RCFA Division I | Restoration work for laying of 450 mm D.I. K9 pipeline under JJM work within the paved carriageway from Ch. 0.000 km to Ch. kmp at Right Side, Ch 03.006 km to Ch. 3.206 kmp at left side & ch. 4.570 km to Ch. 5.000 kmp at left side of Ukhra-Haripur Road under Asansol Division, PWD in the district of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00880/2024-2025 | 401/24-25 | 11/11/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 24.61 | 0 | 0
532 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Pipe Water Supply Scheme (Zone-15) with Construction of 450 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000101/2023-2024 | 1843/RCD-I | 31/05/2023 | 365 | GITA CONSTRUCTION | 150.65 | 0 | 0
533 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-15) | Assistant Engineer 2 | Junior Engineer | ORD/000254/2023-2024 | 2299/RCD-I | 24/07/2023 | 892 | SWATI CORPORATION | 516.27 | 0 | 100
534 | RCFA Division -I | RCFA Division I | Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000321/2023-2024 | Camp-02-Sign-Board-AE-II | 30/06/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 15.83 | 70
535 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work for bridge at Chalbalpur in connection with the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000514/2023-2024 | 2865/RCD-I | 06/10/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 70.4 | 52.84 | 100
536 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 100 cum & allied work at Bagdiha under Augmentation of RCFA Part-II (Zone-15) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000520/2023-2024 | 2877/RCD-I | 06/10/2023 | 90 | M/S KALYANI ENTERPRISE | 18.69 | 0 | 0
537 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-15) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000563/2022-2023 | 3357/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 0
538 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000034/2023-2024 | 2940/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
539 | RCFA Division -I | RCFA Division I | Restoration work for laying of under ground water supply line (400 mm dia) Ch. 0.100 kmp to ch 1.350 on Ukhra Haripur (0-5) road in the district of Pachim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00463/2023-2024 | 235/23-24 | 29/08/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 32.64 | 0 | 0
540 | RCFA Division -I | RCFA Division I | Formal work order Distribution Network including FHTC & alied work at Ondal Block of RCFA Part-II (Zone-12A) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000065/2023-2024 | 1764/RCD I | 16/05/2023 | 962 | MRITYUNJOY MUKHERJEE & CO. | 610.49 | 195.98 | 70
541 | RCFA Division -I | RCFA Division I | Formal work for Construction of 1000 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connetion and cost of pipes,specials at Ondal Block (Zone-12A) for Augmentation of RCFA Part-II Piped Water Supply Scheme including Soil investigation and chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. in District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000096/2023-2024 | 1847/RCD-I | 31/05/2023 | 366 | M/S PIONEER CONSTRUCTION | 203.2 | 101.6 | 100
542 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Pancgachia (240 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000537/2023-2024 | 3017/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 0 | 100
543 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 1000 cum capacity RCC Over Head Reservoir at (Zone-12A) of Ondal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000578/2022-2023 | 3366/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
544 | RCFA Division -I | RCFA Division I | Formal work order for distributionn network for RCFA Part-II piped Water Supply Including FHTC & allied works under RCFA Div-I, PHE Dte. (Zone-12B)(Segment-1) | Assistant Engineer 2 | Junior Engineer | ORD/000805/2022-2023 | 931/RCDI | 14/03/2023 | 60 | ARISTOCON ENGINEER'S CO-OP. SOCIETY LTD. | 157.79 | 67.99 | 82
545 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000028/2023-2024 | 2946/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
546 | RCFA Division -I | RCFA Division I | 100 mm dia water pipe line with 600 mm dia MS Casing pipe line (Jal Jeevan Mission) by R.C.F.A Division-1, PHE DTE, Asansol in between Parasia Siding ¿ New Jambad Siding at Km. CB-2/15-16 in Asansol Division of Eastern Railway under AUGMENTATION PWSS OF RCFA PART-II (ZONE-12B) UNDER RCFA DIVISION-I PHE DTE. | Assistant Engineer 2 | Junior Engineer | BILL/00863/2024-2025 | 396/24-25 | 28/10/2024 | 0 | EASTERN RAILWAY | 4.58 | 0 | 0
547 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work of allied items at Andal OHR Site under Phase-II/B under RCFA Division-I PHE Dte. AUGMENTATION PWSS OF RCFA PART-II (Zone-12B) | Assistant Engineer 2 | Junior Engineer | ORD/000063/2024-2025 | 1647/RCD-I | 04/07/2024 | 15 | AMAR CONSTRUCTION | 5.25 | 0 | 100
548 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Barabani (910 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000539/2023-2024 | 3018/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.95 | 0 | 100
549 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Shankarpur under Pandabeswar H/W Site within Pandabeswar Block for Augmentation of PWSS of RCFA Part-II (Zone-12B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000558/2024-2025 | 162/RCD-I | 08/01/2025 | 90 | DIP CONSTRUCTION | 34.75 | 0 | 0
550 | RCFA Division -I | RCFA Division I | Formal Work Order for Distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-12B)(Segment-2). | Assistant Engineer 2 | Junior Engineer | ORD/000631/2022-2023 | 485/RCDI | 03/02/2023 | 60 | M/S SINGH & KONAR CONSTRUCTION | 155.21 | 31.62 | 80
551 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of Distribution Network including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-12 A) Piped Water Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000669/2023-2024 | 3436/RCD-1 | 24/11/2023 | 60 | MRITYUNJOY MUKHERJEE & CO. | 81.28 | 0 | 65
552 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work Balance work of Road restoration in connection with laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 mm NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000941/2023-2024 | 500/RCD-I | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 54.54 | 0 | 100
553 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied works of laying distribution system of balance work of supply & laying of HDPE pipe under Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000942/2023-2024 | 498/RCD-I | 12/02/2024 | 45 | MACHINO TECHNO | 78.67 | 0 | 100
554 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of restoration approach road in Amritnagar Zone-I for Augmentation of RCFA Part-II under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000948/2023-2024 | 499/RCDI | 12/02/2024 | 30 | MACHINO TECHNO | 24.72 | 0 | 100
555 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000029/2023-2024 | 2945/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
556 | RCFA Division -I | RCFA Division I | Way leave permission for water supply poipe line for JJM carrier pipe dia 250 mm at Pandabeswar under Augmentation of RCFA PART-II (ZONE-8) under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00864/2024-2025 | 398/24-25 | 29/10/2024 | 0 | EASTERN RAILWAY | 1.19 | 0 | 0
557 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-8) with Construction of 250 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman, (Sl No. 07). | Assistant Engineer 2 | Junior Engineer | ORD/000005/2023-2024 | 1402 RCD I | 12/04/2023 | 365 | PINKI ENTERPRISE | 95.85 | 38.92 | 65
558 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 04 nos location (Bus stand/Taxi stand Domohani Bazar, Rural more, Near Domohani Electric Supply Office, BDO Office More) of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-6) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000231/2023-2024 | 2229/RCD-I | 17/07/2023 | 30 | UMA ENTERPRISE | 30.82 | 0 | 0
559 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-1 Distribution Segment) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000296/2023-2024 | 2367/RCD-I | 04/08/2023 | 30 | R B ENTERPRISE | 47.39 | 40.66 | 86
560 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of MS pipe carrier bridge, additional (Extra line) supplying, aligning & laying HDPE pipe line and other works of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000297/2023-2024 | 2368/RCD-I | 04/08/2023 | 60 | SWATI CORPORATION | 28.11 | 26.64 | 100
561 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional (Extra line Node no. 550-550A, 555-548, 554-547, 527-321, 378-296, 397-423, 423-441) supplying, aligning & laying HDPE pipe line of RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000406/2023-2024 | 2588/RCD-I | 07/09/2023 | 15 | TARA CONSTRUCTION | 7.55 | 7.46 | 100
562 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional extra cutting Laterate/sandstone of distribution of pipe line at Augmentation of RCFA Part-II (Zione-8) within command area under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000522/2023-2024 | 2880/RCD-I | 06/10/2023 | 90 | SWATI CORPORATION | 10.6 | 0 | 100
563 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 250 cum capacity RCC Over Head Reservoir at (Zone-8) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000561/2022-2023 | 3355/RCDI | 23/12/2022 | 777 | MOYTEC | 0.49 | 0 | 100
564 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for crossing of 07 nos (Node Point :139-140,153-3,42-43,86-87,60-61, and 38-40 culvert/canal of by the side of PWD road under Improvement RCFA Part-I water Supply scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000720/2023-2024 | 3614/RCD-I | 20/12/2023 | 15 | TARA CONSTRUCTION | 3.32 | 0 | 0
565 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying E.R.M.S Black pipe of approved quality including carring, stacking at works site and other allied works for Improvement RCFA Part-I Water Supply Scheme within command area of Zone VIII under RCFA Div-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000723/2023-2024 | 3612/RCD-1 | 20/12/2023 | 15 | SWATI CORPORATION | 2.78 | 0 | 0
566 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Pump Houses (Size 14 mtr x 10 mtr x 8 mtr) under at Madanpur H/W Site under AUGMENTATION PWSS OF RCFA PART-II (ZONE-8) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000724/2023-2024 | 3611/RCD-1 | 20/12/2023 | 567 | D.S.C. CONCERN | 35.91 | 0 | 50
567 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work for laying of different dia HDPE pipe line (left out portion) and other allied works at Amritnagar (Part-A) under Augmentation of Amritnagar Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000955/2023-2024 | 2455/RCD-I | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 45.53 | 0 | 0
568 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Emergent dismantling of RCC Elevated Reservoir capacity 682 cum staging height 20 meter at Mohishila OHR within Asansol Municipal Corporation area of Augmentation PWSS of RCFA Part-II (Zone-8) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001018/2023-2024 | 519/RCD-I | 16/02/2024 | 45 | GITA CONSTRUCTION | 17.37 | 0 | 100
569 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply & Delivery of GI pipe including loading , unloading and carriage to Searsole store under RCFA Part-II PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001022/2023-2024 | 626/RCD-I | 27/02/2024 | 20 | MAKALI ENGINEERING CORPORATION | 93.69 | 0 | 100
570 | RCFA Division -I | RCFA Division I | Formal work order for Laying distribution system including FHTC for 5 (Two) nos uncovered village viz. Namokeshia and Jorbari within Salanpur Block under Augmentation of RCFA Part-II (zone-10) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001074/2023-2024 | 806/RCD-I | 13/03/2024 | 90 | UMA ENTERPRISE | 107.86 | 0 | 0
571 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000022/2023-2024 | 2948/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
572 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-IV) under RCFA Division-I PHE Division-I PHE Dte. (Sl No. 08). | Assistant Engineer 2 | Junior Engineer | ORD/000053/2023-2024 | 1706/ RCD I | 03/05/2023 | 90 | DURGADAS MONDAL | 85.16 | 36.77 | 55
573 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-10) with Construction of 350 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District-Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000099/2023-2024 | 1845/RCD-I | 31/05/2023 | 365 | RUBY CONSTRUCTION | 126.43 | 0 | 20
574 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of DP Colony (450 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000533/2023-2024 | 3022/RCD-1 | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.93 | 0 | 100
575 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Rupnarayanpur (1182 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000534/2023-2024 | 3015/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 0 | 100
576 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Chora (1135Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000540/2023-2024 | 3025/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 0 | 100
577 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir at (Zone-10) of Jamuria Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000562/2022-2023 | 3356/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
578 | RCFA Division -I | RCFA Division I | Sub Soil investigation for 350 cum capacity RCC Over Head Reservoir at (zone-IX) of Barabani Block for Improvement of RCFA Part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. In the District Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000580/2023-2024 | 2695/RCD-I | 27/09/2023 | 7 | MALLICK ENTERPRISE | 0.98 | 0 | 0
579 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-XIII) of Barabani Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. In the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000582/2023-2024 | 2696/RCD-I | 27/09/2023 | 7 | JOY HIND TUBEWELLS | 0.98 | 0 | 0
580 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Wall arrangement to project 450 mm dia the Rising Main at Bidyanandapur of ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000612/2023-2024 | 3377/RCD-I | 21/11/2023 | 15 | SIMA ENTERPRISE | 4.03 | 0 | 100
581 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Jitpur Uttarrampur and surrounding villages within Jitpur Uttarrampur Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000654/2023-2024 | 3451/RCD-I | 24/11/2023 | 15 | DIP ENTERPRISE | 4.49 | 0 | 100
582 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying and distribution system for Improvement of RCFA Part-I Water Supply Scheme under Command area of Zone-VII under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000683/2023-2024 | 3472/RCD-I | 28/11/2023 | 30 | GITA CONSTRUCTION | 95.09 | 0 | 100
583 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia HDPE pipe line (left out portion) including adopting trench less technologies and other allied works at Moul Danga village under Barabani Block of Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000685/2023-2024 | 3284/RCD-1 | 08/11/2023 | 30 | SRI KRISHNA ENTERPRISE | 19.21 | 0 | 100
584 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-III) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000851/2022-2023 | 1112/ RCD I | 23/03/2023 | 90 | UNITED CONSTRUCTION | 86.38 | 53.43 | 75
585 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-II) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000855/2022-2023 | 1113/ RCD I | 23/03/2023 | 1174 | M/S KONAR CONSTRUCTION | 84.65 | 0 | 50
586 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-I) under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000860/2022-2023 | 1115/ RCD I | 23/03/2023 | 90 | M/S B.K. CONSTRUCTION | 86.29 | 0 | 38
587 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-VI) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000866/2022-2023 | 1108/RCD-I | 23/03/2023 | 90 | VISUVIOUS | 54.47 | 34.82 | 90
588 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme within command area of Zone-10 (Segment-V) under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 2 | Junior Engineer | ORD/000867/2022-2023 | 1110/RCD-I | 23/03/2023 | 90 | DIP CONSTRUCTION | 90.17 | 31.53 | 35
589 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance Work of different work to Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000962/2023-2024 | 506/RCD-I | 12/02/2024 | 30 | MACHINO TECHNO | 82.78 | 0 | 100
590 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000026/2023-2024 | 2955/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
591 | RCFA Division -I | RCFA Division I | Construction of Pumping Station at Itapara new H/W Site of Itapara Water Supply Scheme under RCFA Division-I PHE Dte.(Sl no 01) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000127/2020-2021 | 14 / RCD I | 08/01/2021 | 45 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 2.75 | 0 | 0
592 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC work for the Command area of Zone-XI (Part-6 Segment) for augmentation of Itapara piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000161/2022-2023 | 1699/RCD-I | 13/07/2022 | 923 | UMA ENTERPRISE | 44.47 | 0 | 45
593 | RCFA Division -I | RCFA Division I | Preparation of DPR for Augumentation of Itapara Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000482/2021-2022 | 2346/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.82 | 2.82 | 0
594 | RCFA Division -I | RCFA Division I | Rising Main for Augmentation of Itapara Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000566/2022-2023 | 3277/RCD I | 20/12/2022 | 529 | DURGADAS MONDAL | 34.74 | 19.21 | 80
595 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of approach road, land development, CWR painting, Cable trench slab, drainage system at Runakuraghat H/W campus under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 24) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000859/2022-2023 | 1090/RCD-I | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 37.83 | 17.38 | 100
596 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Room with toilet at Malladihi OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000967/2023-2024 | 717-A/RCD-I | 01/03/2024 | 90 | PINKI ENTERPRISE | 5.97 | 0 | 0
597 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Room with toilet at Dabor OHR site under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000970/2023-2024 | 460/RCD-1 | 12/02/2024 | 90 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 5.97 | 0 | 0
598 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply of valves, construction of valve chamber, supplying laying HDPE/UPVC/GI pipe line and allied works at Putulia, Hosenpur and adjacent area under Augmentation of Itapara W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000972/2023-2024 | 461/RCD-1 | 12/02/2024 | 30 | R B ENTERPRISE | 7.72 | 0 | 100
599 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of spout, repairing and restoration of pipe line, FHTC connection and allied land development works within distribution system under Malladihi OHR under Augmentation of Itapara PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000986/2023-2024 | 469/RCD-1 | 12/02/2024 | 15 | ASHA CONSTRUCTION | 7.18 | 0 | 100
600 | RCFA Division -I | RCFA Division I | Continuation of work order for Conducting route survey , design rising main network and preparation & submission of source augmentation DPR for Itapara PWSS for Impementation of JJM at Barabani block under RCFA DIVISION-I P.H.E. Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001009/2023-2024 | 74/A/RCD-I | 02/01/2024 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.97 | 0 | 100
601 | RCFA Division -I | RCFA Division I | Continuation work order for Renovation of filter bed, changing of Media and allied works at Salanpur Dalmia OCP Project under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001070/2023-2024 | 101_A_RCD-I | 09/01/2024 | 15 | R B ENTERPRISE | 7.46 | 0 | 0
602 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for raising height of tube well to encounter flood including surging of tube well, repairing work of collecting main at river Ajoy at Churulia under Augmentation of Itapara Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001087/2023-2024 | 876/RCD-I | 15/03/2024 | 15 | MD AAMIR KHAN | 4.09 | 0 | 100
603 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000011/2023-2024 | 2207/RCD-I | 17/07/2023 | 0 | Resource Division | 160.38 | 0 | 0
604 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000029/2022-2023 | 28/RCD-I | 10/01/2023 | 0 | Resource Division | 92.01 | 0 | 0
605 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000032/2022-2023 | 121/RCD-I | 24/01/2023 | 0 | Resource Division | 222.41 | 0 | 0
606 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work for laying DI pipe at Shilampur under Augmentation of ground water based piped W/s scheme for Kanksa (Zone-II/Part-A) to accommodate FHTC of Gopalpur PWSS under RCFA Division-I PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000064/2024-2025 | 1794/RCD-I | 24/07/2024 | 161 | MD AAMIR KHAN | 8.7 | 0 | 100
607 | RCFA Division -I | Asansol Mechanical Division | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | Assistant Engineer-II | Junior Engineer-3 | ORD/000727/2023-2024 | 3514/RCD-I | 30/11/2023 | 182 | SUBHA TOUR & TRAVELS | 0.89 | 0 | 35
608 | RCFA Division -I | RCFA Division I | Installation of Jio Fiber connection for Six months under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | BILL/00329/2024-2025 | 153/24-25 | 19/07/2024 | 0 | MUKHERJEE TRADERS | 0.07 | 0 | 0
609 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Gourbazar, Bindudihi, Hosenpara villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl NO. 05) | Assistant Engineer 1 | Junior Engineer | ORD/000142/2022-2023 | 1436/RCD I | 27/06/2022 | 45 | M/S S.K. ENTERPRISE | 4.97 | 4.48 | 0
610 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Putulia (Part), Kharboni, Jamjuri and allied villages under Gourbazar W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 1 | Junior Engineer | ORD/000143/2022-2023 | 1437/RCD I | 27/06/2022 | 45 | VISUVIOUS | 2.75 | 0 | 0
611 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Gourbazar Village, Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000191/2021-2022 | 1865/RCD-I | 28/10/2021 | 30 | M/S S.K. ENTERPRISE | 13.17 | 12.21 | 0
612 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Putulia (Part), Block-Barabani under Gourbazar Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000192/2021-2022 | 1866/RCD-I | 28/10/2021 | 30 | VISUVIOUS | 12.85 | 10.95 | 0
613 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000008/2021-2022 | 437/RCD-I | 21/02/2022 | 0 | Resource Division | 2.75 | 0 | 0
614 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional Work for distribution main pipe line Panagarh Gram Shibtola of Kanksa Zone-II Part-B of Augmentation of Kanchanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000378/2024-2025 | 3106/RCD-I | 13/12/2024 | 60 | MD AAMIR KHAN | 37.68 | 0 | 100
615 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for additional work of construction of IEP, drain and platform and other allied works at Kanchanpur under Augmentation of Kanchanpur Piped water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000395/2025-2026 | 1761/RCDI | 18/06/2025 | 30 | RUPALI ELECTRONICS | 15.48 | 0 | 0
616 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of Concrete dismantling, Concrete restoration, Bolder cutting and other allied works at distribution network of Augmentation PWSS of RCFA Part-II (Zone-2A) under RCFA Div-I,PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000053/2024-2025 | 1743/RCD-I | 18/07/2024 | 255 | SWATI CORPORATION | 67.64 | 0 | 30
617 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Left out part at Banbahal village distribution pipe line Zone-4A under Pandabeswar Block for smooth running of water supply near Shankarpur area of Augmentation PWSS of RCFA Part-II (Zone-2A) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000238/2025-2026 | 1460/RCD-I | 15/05/2025 | 30 | BABA LOKNATH ENTERPRISE | 18.07 | 0 | 80
618 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing by adopting trench less technology (e.g. Jack Pushing Method etc0 at Bagdiha to Sidhapur Road and Bagdiha OHR to Bahadurpur under Jamuria Block under Augmentation of Bagdiha PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000600/2023-2024 | 3282/RCD-I | 08/11/2023 | 15 | SIMA ENTERPRISE | 6.34 | 0 | 100
619 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000670/2023-2024 | 3437/RCD-1 | 24/11/2023 | 15 | M/S UNIT CONSTRUCTION | 9.31 | 0 | 100
620 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of chlorine room of size (4.50 X 3.50 m) at (Zone-XIII) of Baraboni block for Improvement of RCFA Pt-I piped Water Supply under RCFA Div-I, PHE Dte. in the district of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000738/2022-2023 | 677/RCDI | 24/02/2023 | 15 | ZEROTH CONTROL SYSTEM | 4.61 | 0 | 100
621 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network and allied work for Ukhra area of RCFA Part-II Piped Water Supply Scheme allied work under RCFA Division-I PHE Dte. (Zone-2A)(Sl. No. 13) | Assistant Engineer 2 | Junior Engineer | ORD/000845/2022-2023 | 1080/RCD-I | 23/03/2023 | 90 | GITASREE FABRICATION | 97.2 | 0 | 80
622 | RCFA Division -I | RCFA Division I | Acceptance cum work order Concrete road cutting and mending work for laying distribution pipe line at Das Para (Sansad-XIX) at Ukhra area Block ¿ Andal and Pandabeswar under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 17) | Assistant Engineer 2 | Junior Engineer | ORD/000903/2022-2023 | 1161/RCD-I | 24/03/2023 | 15 | JYOGOMAYA ENTERPRISE | 2.01 | 1.94 | 100
623 | RCFA Division -I | RCFA Division I | Formal work order for Additional work for allied work in connection with in connection supply, laying fitting, fixing of 15 mm NB PVC (Schedule 80) / 2020 mm OD HDPE (PE 80, PN 6) pipe with all necessary specials piece etc. all complete for Augmentation of Sub-Station Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000904/2023-2024 | 158/RCD-I | 22/01/2024 | 435 | MRITYUNJOY MUKHERJEE & CO. | 213.03 | 0 | 85
624 | RCFA Division -I | RCFA Division I | Acceptance cum work order Concrete road cutting mending works for laying of distribution pipe line at Kankardanga Part (Sansad-VIII) at Ukhra area Block-Andal and Pandabeswar under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 19) | Assistant Engineer 2 | Junior Engineer | ORD/000909/2022-2023 | 1163/RCD-I | 24/03/2023 | 15 | MS KALYAN ENTERPRISE | 2.77 | 2.71 | 100
625 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000018/2023-2024 | 2956/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
626 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme Including FHTC & allied work under RCFA Division-I PHE Dte. (Zone 9B) (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000001/2023-2024 | 1348/RCD-I | 04/04/2023 | 30 | M/S SANTANU PALIT & CO. | 156.13 | 33.23 | 30
627 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of making spout and Platform with other allied work at Amritnagar Zone -1 under Augmentation PWSS of RCFA Part-II (Zone - 9 B) under RCFA Division 1 PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000194/2024-2025 | 2421/RCD-I | 26/09/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 41.77 | 0 | 100
628 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 06 (Six) nos. river bed tube wells including collecting main, sluice valve chamber & other allied works at Shyamlya H/W site at Ajoy river under Shyamla Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000208/2023-2024 | 2241/RCD-1 | 17/07/2023 | 30 | MAA ENTERPRISE. | 33.68 | 0 | 100
629 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repair and renovation works of One no RCC Elevated Reservoir of Capacity 1362 cum at Khandra for Augmentation RCFA Part-II (Zone-9B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000247/2023-2024 | 2234/RCD-I | 17/07/2023 | 30 | UNITED CONSTRUCTION | 16.43 | 0 | 100
630 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte. (Zone-9B)(Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000630/2022-2023 | 486/RCDI | 03/02/2023 | 30 | M/S MONDAL ENTERPRISE | 156.13 | 49.8 | 70
631 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000025/2023-2024 | 2953/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
632 | RCFA Division -I | RCFA Division I | Formal work word for Distribution Network for RCFA Part-II Pipe Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-16). | Assistant Engineer 2 | Junior Engineer | ORD/000039/2023-2024 | 1606/RCD I | 25/04/2023 | 251 | JOY HIND TUBEWELLS | 488.35 | 417.76 | 100
633 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 600 cum capacity 20 mtr. Staging height RCC Over head Reservoir (pipe connection and cost of pipes, special at Raniganj Block (Zone-16) for Augmentation of RCFA Division-II piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000156/2023-2024 | 1899/RCD-I | 09/06/2023 | 366 | ASHA CONSTRUCTION | 154.85 | 0 | 45
634 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 600 mm dia MS pipes under the Railway track by jack pushing technology at different spots and pushing diff. dia M.S pipes throgh 600 mm dia MS pipes in connection with the work for the laying distribution system for Augmentation of Sub - Surface water based piped water supply scheme for Amritnagar Zone -II for Augmentation of PWSS RCFA Part-II (Zone-16) Under RCFA Division -I PHE. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000192/2024-2025 | 2419/RCD-I | 26/09/2024 | 187 | MRITYUNJOY MUKHERJEE & CO. | 40.11 | 0 | 70
635 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Distribution Network for Improvement RCFA Part-II Water Supply Scheme within command area of Zone-16 including FHTC work (Part-A) under RCFA Div-I PHE Dte. (Mouza-Sahebganj) | Assistant Engineer 2 | Junior Engineer | ORD/000532/2022-2023 | 3160/RCD-I | 13/12/2022 | 30 | KRISHNA KUMAR TODI HUF | 88.68 | 79.11 | 100
636 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000559/2022-2023 | 3353/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 100
637 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for laying of HDPE pipeline and PVC pipeline and allied works at Nabagram, Ukhra (Sansad-VI) Chatterjee para and Bahula Colony under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000660/2023-2024 | 3453/RCD-I | 24/11/2023 | 15 | MD AAMIR KHAN | 4.36 | 0 | 100
638 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-16) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 31) | Assistant Engineer 2 | Junior Engineer | ORD/000911/2022-2023 | 1175/RCD I | 24/03/2023 | 90 | N.R. CONSTRUCTION | 4.61 | 0 | 0
639 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Supplying aligning laying HDPE pipe Mechanical fitting supplying sluice valve and other allied works at (Mouza-Sahenganj) under Zone-16 Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001019/2023-2024 | 572/RCD-I | 23/02/2024 | 30 | KRISHNA KUMAR TODI HUF | 36.45 | 0 | 100
640 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000035/2023-2024 | 2939/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
641 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Road crossing of 250 mm dia Rising Main for under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under Raniganj Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000102/2024-2025 | 2122/RCD-I | 27/08/2024 | 30 | MD. JAWED KHAN | 8.41 | 0 | 100
642 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Dhunabaid of Dendua for distribution system within command area of Zone-I (Dendua OHR Site) under Augmentation of sub surface water supply scheme for Amritnagar Zone-II under RCFA, Division-1,P.H.E.Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000104/2024-2025 | 2124/RCD-I | 27/08/2024 | 30 | DAS & CHAKRABORTY | 12.7 | 0 | 100
643 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Pathan Dahwra of Murgasole Mouza under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA, Division-1, P.H.E. Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000106/2024-2025 | 2126/RCD-I | 27/08/2024 | 25 | DAS & CHAKRABORTY | 7.38 | 0 | 100
644 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of Sinking of 6 (Six) nos. river bed tube wells including collecting main & other allied works at Damalia H/W under RCFA part II at Damodar river under Amritnagar Zone II water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000116/2024-2025 | 2136/RCD-I | 27/08/2024 | 216 | M/S MONDAL CONSTRUCTION | 12.6 | 0 | 30
645 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of OHR and Construction of new boundary wall, Land developing and Path way and other allied works at Saora mouza, Plot No:2787 at R.C.C over Head Site of Augmentation of Amritnagar Zone-II Piped Water Supply Scheme within RCFA Part-II Area under Raniganj Block under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000215/2024-2025 | 2550/RCD-I | 29/10/2024 | 154 | DAS & CHAKRABORTY | 26.19 | 0 | 80
646 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of laying distribution system for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000244/2023-2024 | 2253/RCD-1 | 17/07/2023 | 30 | MRITYUNJOY MUKHERJEE & CO. | 62.23 | 62.13 | 100
647 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of laying distribution system to Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000245/2023-2024 | 2255/RCD-1 | 17/07/2023 | 30 | MACHINO TECHNO | 28.24 | 28.13 | 100
648 | RCFA Division -I | RCFA Division I | Laying of Distribution System to Accommodate FHTC and Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN6) pipe with all necessary specials, saddle piece etc. all complete for Augmentation of Sub-Surface Water Based Piped Water Supply Scheme for Amritnagar Zone-II under RCFA Division I, PHE Dte.under RCFA Division I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000301/2022-2023 | 2455/RCD-I | 13/10/2022 | 536 | MACHINO TECHNO | 366.55 | 235.84 | 100
649 | RCFA Division -I | RCFA Division I | Acceptance cum work order of rising main for Amritnagar Zone-II Water Supply Scheme for Ranoganj Block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000303/2022-2023 | 2513/RCD I | 20/10/2022 | 30 | MD. JAWED KHAN | 38.5 | 26.97 | 100
650 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional Work for crossing Nunia River through the riverbed and allied works of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000398/2023-2024 | 2580/RCD-I | 07/09/2023 | 15 | MD. JAWED KHAN | 7.58 | 7.43 | 100
651 | RCFA Division -I | RCFA Division I | Detailed Route Survey, Design Drawing & DPR Preparation for Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 2 | Junior Engineer | ORD/000540/2021-2022 | 504/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.23 | 4.23 | 0
652 | RCFA Division -I | RCFA Division I | Acceptance cum wor order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Amritnagar under Augmentation of Sub Surface Water Supply Scheme of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000574/2022-2023 | 3283/RCDI | 20/12/2022 | 90 | SOMNATH SAMANTA | 22.04 | 0 | 100
653 | RCFA Division -I | RCFA Division I | Acceptance cum work order for supplying 90 mm dia HDPE pipe line at Murgathol Adibasipara and Old Egera Including repairing different dia pipe line in different places within Amritnagar Distribution Zone under Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division- IPHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000792/2022-2023 | 410/RCD-I | 30/01/2023 | 20 | DAS & CHAKRABORTY | 9.23 | 9.18 | 0
654 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Special Repair & Renovation of existing High Lift Pump House, Boundary Wall, Guard Room, CWR, Switch Room etc. and allied works at H/W Site of Amritnagar Piped Water Supply Scheme. | Assistant Engineer 2 | Junior Engineer | ORD/000880/2022-2023 | 1145/RCD-1 | 24/03/2023 | 30 | RUBY CONSTRUCTION | 9.83 | 9.59 | 0
655 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Boundary Wall with Gate at OHR Site (Length-80 mtrs) at Amritnagar H/W Site (Damalia village) of Raniganj Block for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 03) | Assistant Engineer 2 | Junior Engineer | ORD/000884/2022-2023 | 1147/RCD-1 | 24/03/2023 | 892 | M/S MONDAL CONSTRUCTION | 7.04 | 0 | 100
656 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Amritnagar Zone-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No.- 05) | Assistant Engineer 2 | Junior Engineer | ORD/000892/2022-2023 | 1149/RCD-1 | 24/03/2023 | 948 | ZEROTH CONTROL SYSTEM | 6.5 | 0 | 40
657 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000014/2022-2023 | 2925/RCD-I | 17/11/2022 | 0 | Resource Division | 356.25 | 0 | 0
658 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000022/2022-2023 | 3129 | 09/12/2022 | 0 | Resource Division | 60.34 | 0 | 0
659 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Separate connection for Ijjatgunj OHR Kanksa Zone-II (Part-C) under RCFA Division - I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000141/2024-2025 | 2245/RCD-I | 11/09/2024 | 30 | COMPUTER MEDIA | 6.62 | 0 | 70
660 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Trial run and special Maintenance of Rising main and Distribution system with operating of valve within command area under Augmentation of Kanksa Zone-II (Part-D) PWSS, JJM under RCFA Division-I PHE Dte. 6 (Six) Months | Assistant Engineer-II | Junior Engineer-3 | ORD/001033/2023-2024 | 688/RCD-1 | 29/02/2024 | 184 | AMARANJALI CONSTRUCTION | 1.79 | 0 | 0
661 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and delivery of C.I. Sluice valve and D.I Specials under Improvement of RCFA part-I Piped water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000055/2023-2024 | 1729/RCD-1 | 08/05/2023 | 10 | SSPR VALVE MANUFACTURING PVT LTD | 45.31 | 45.31 | 100
662 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Requirement of different type water regulating apparatus including water leakage protection apparatus etc. for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000056/2023-2024 | 1730/RCD-1 | 08/05/2023 | 10 | MAKALI ENGINEERING CORPORATION | 45.99 | 45.99 | 0
663 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for laying & pushing of 600 to 1000 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) and MS pipe including supply of collar and allied work at Ethora Nuni more Panchgachiya and Lalganj more in connection to rising main Part-B under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000218/2023-2024 | 2224/RCD-I | 17/07/2023 | 30 | M/S MONDAL ENTERPRISE | 30.17 | 25.6 | 100
664 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying of 450 mm dia distribution main under Lalganj Bridge by concrete conduit and allied MS work in connection to distribution network of Zone-XI (Part-1) for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000251/2023-2024 | 2237/RCD-1 | 17/07/2023 | 30 | R B ENTERPRISE | 16.06 | 13.45 | 100
665 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Route Survey and Preparation of DPR for Augmentation of Churulia Piped Water Supply Scheme, Retrofitting of Churulia PWSS for providing FHTC within Jamuria Block., District-Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000716/2023-2024 | 3373/RCD-1 | 21/11/2023 | 15 | APEX ENGINEERING | 3.61 | 0 | 100
666 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of stand post on emergency basis at Rupnarayanpur, Rangamati area of Rupnarayanpur Zone under 4 Nos. retrofitting PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000987/2022-2023 | 1266/RCD-1 | 27/03/2023 | 15 | B.B. CONSTRUCTION | 2.8 | 2.78 | 0
667 | RCFA Division -I | RCFA Division I | Car bill may 23 and june 23 | Assistant Engineer 1 | Junior Engineer | BILL/00518/2023-2024 | 234/2/23-24 | 05/09/2023 | 0 | NIRMALA TRADERS | 0.78 | 0 | 0
668 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-B) under Roshna W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000138/2022-2023 | 1432/RCD I | 27/06/2022 | 45 | MD SARFARAZ ALAM | 4.98 | 4.65 | 0
669 | RCFA Division -I | RCFA Division I | Supplying, aligning & Laying of different dia HDPE pipe line for providing FHTC at Parulberia and allied villages (Part-A) under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 1 | Junior Engineer | ORD/000140/2022-2023 | 1434/RCD I | 27/06/2022 | 45 | MD AAMIR KHAN | 5 | 4 | 0
670 | RCFA Division -I | RCFA Division I | Extension of different dia HDPE pipe line for providing FHTC at Roshna & Baspahari villages under Roshna W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000144/2022-2023 | 1438/RCD I | 27/06/2022 | 45 | SHREE DURGA ENTERPRISE | 3.22 | 3.1 | 0
671 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Daskeary Village Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000188/2021-2022 | 1862/RCD-I | 28/10/2021 | 30 | M/S MONI TRADERS | 39.47 | 35.31 | 0
672 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Roshna (Part) Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000189/2021-2022 | 1863/RCD-I | 28/10/2021 | 30 | SRI KRISHNA ENTERPRISE | 12.81 | 9.39 | 0
673 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Parulberia Mouza Block-Barabani under Roshna Water supply scheme under RCFA Division-I, P.H.E. Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000190/2021-2022 | 1864/RCD-I | 28/10/2021 | 30 | MAK CONSTRUCTION CO. | 20.28 | 17.74 | 0
674 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Distribution Network including supply of Hume pipe, G.I. pipe Sluice Valve and allied works for Augmentation of Roshna PWS (Part-D) under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000237/2023-2024 | 2251/RCD-1 | 17/07/2023 | 30 | JYOGOMAYA ENTERPRISE | 10.86 | 5.29 | 100
675 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1 | Junior Engineer | RTOR000007/2021-2022 | 438/RCD-I | 21/02/2022 | 0 | Resource Division | 8.25 | 0 | 0
676 | RCFA Division -I | Asansol Mechanical Division | Emergent sinking of one no 200 x 165 mm dia rig bore tube well at ESI Hospital near staff quarter Kali Mandir, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000001/2024-2025 | Camp_02_ESI_Hospital_AE_I | 16/04/2024 | 7 | M/S CHANDI CHARAN ROY | 8.1 | 0 | 100
677 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balanced work Sinking of 03 (Three) nos. 200 mm dia river bed tube well in the river of Ajoy (Pandabeswar H/W Site) for Source Augmentation of RCFA Part-II W/S Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000083/2024-2025 | 2108/RCD-I | 27/08/2024 | 278 | B.T.M. CONCERN | 23.41 | 0 | 70
678 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 6 (Six) nos. 200 mm dia river bed tube well including 3 nos. collecting main in the river Ajoy at Runakuraghat H/W site for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000103/2024-2025 | 2123/RCD-I | 27/08/2024 | 25 | MAA ENTERPRISE | 13.24 | 0 | 100
679 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Hydro-Geological study of Sub-Surface Water Flow with Sinking of Tube Well in Damodar & Ajay River bed and Bank Position of Source Augmentation of RCFA Part-II Water Supply Scheme by installing River bed tube well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000178/2024-2025 | 2435/RCD-I | 26/09/2024 | 15 | ENVIROTECH SOLUTIONS | 95 | 0 | 100
680 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia river bed tube wells in the river Ajoy at Baidyanathpur for Baidyanathpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000287/2023-2024 | 2336/RCD-I | 01/08/2023 | 530 | MD AAMIR KHAN | 43.86 | 0 | 50
681 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube wells in the river Ajoy at Kendra Khottamdihi for Kendra Khottamdihi Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000288/2023-2024 | 2337/RCD-I | 01/08/2023 | 30 | M/S MONI TRADERS | 42.45 | 0 | 55
682 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work of Emergent laying of Collecting Main for sinking of 4 nos river bed tube well and making of manifold with in addition of connecting of 10 nos tube well in River Ajoy at Bhaburia Head Works Site under RBT Type Sarpi, Jamgora Jagannathpur and Gourbazar-Ichapur Water Supply Scheme for Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000371/2024-2025 | 3099/RCD-I | 13/12/2024 | 45 | MD AAMIR KHAN | 46.32 | 0 | 100
683 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Flow control of Rising main and different dia distribution system by different regulating apparatus of Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000602/2024-2025 | 267/RCD-I | 04/02/2025 | 30 | MAKALI ENGINEERING CORPORATION | 87.75 | 0 | 100
684 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in the river Damodar at Madanpur Head Works Site for Madanpur Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000937/2023-2024 | 477/RCD-I | 12/02/2024 | 30 | NIYATI CONSTRUCTION | 29.98 | 0 | 100
685 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000953/2023-2024 | 479/RCD-I | 12/02/2024 | 30 | M/S MONDAL ENTERPRISE | 15.54 | 0 | 100
686 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 5 (Five) nos 200 mm dia river bed tube well including collecting main in the river Damodar at Surjanagar H/W site for ASTA of Source Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000954/2023-2024 | 480/RCD-I | 12/02/2024 | 30 | MD. JAWED KHAN | 15.82 | 0 | 100
687 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000969/2023-2024 | 485/RCD-I | 12/02/2024 | 25 | SOMNATH SAMANTA | 19.46 | 0 | 100
688 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 4 (Four) nos river bed tube wells including collecting main and other allied works at Damodar river under (Part-II) Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000974/2023-2024 | 492/RCD-I | 12/02/2024 | 30 | TARA MA ENTERPRISE | 13.02 | 0 | 100
689 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well including collecting main in the river of Damodar at Surjanagar under Source Augmentation of RCFA Part-II Water Supply Scheme by installing Riverbed Tube-well under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/000994/2023-2024 | 295/A/RCD-I | 06/02/2024 | 30 | MAK CONSTRUCTION CO | 22.57 | 0 | 100
690 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 1 (One) no river bed tube wells including collecting main & other allied works at Damalia Damodar river under Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/001105/2023-2024 | 894/RCD-I | 15/03/2024 | 15 | MAA ENTERPRISE | 3.05 | 0 | 100
691 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Sinking of 2 (Two) nos river bed tube wells including collecting main & other allied works at Damodar river under Tirat Colliery Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | Junior Engineer-1,Junior Engineer-3,Junior Engineer-4,Junior Engineer-5 | ORD/001106/2023-2024 | 895/RCD-I | 15/03/2024 | 15 | MAA ENTERPRISE | 4.51 | 0 | 100
692 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied works of Gopalpur site office including construction of pump house, premises development under Augmentation of Shyambazar water supply scheme of RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000086/2024-2025 | 2111/RCD-I | 27/08/2024 | 181 | BASANTI TRADERS | 33.72 | 0 | 65
693 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum formal order for the work of Supplying, laying and aligning of HDPE distribution pipe line and other allied works providing FHTC under command area Shyambazar under Augmentation Shyambazar piped water supply scheme , Block-Durgapur-Faridpur,Dist-Paschim Bardhhaman (SL-14) | Assistant Engineer-II | Junior Engineer-3 | ORD/001210/2023-2024 | 795/DWSD | 12/09/2023 | 30 | MAJI DEVELOPERS | 98.7 | 0 | 100
694 | RCFA Division -I | Asansol Mechanical Division | License Fees for five (05) years for 6-lanning of Barwa Adda - Panagarh section of NH-2 from km 398.240 to km 521.120 including Panagarh Bypass in the state of Jharkhand & West Bengal under NHDP Phase -V on BOT (Toll) on DBFOT pattern - Permission for laying of water pipeline along NH-2 from Kalla more (km 462+080) to Harishpur (km+918) and 7 nos crossing across NH-2 in the state of West Bengal under Augmentatin of RCFA Pt II Volume -II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/00522/2024-2025 | 282/24-25 | 09/09/2024 | 0 | NATIONAL HIGHWAY AUTHORITY OF INDIA | 164.48 | 0 | 0
695 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01359/2023-2024 | 559/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 16.52 | 0 | 0
696 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-67 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01361/2023-2024 | 560/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 10.41 | 0 | 0
697 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-69 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01362/2023-2024 | 561/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0
698 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-71 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01363/2023-2024 | 562/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 7.84 | 0 | 0
699 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01364/2023-2024 | 563/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 17.21 | 0 | 0
700 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-70 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01365/2023-2024 | 564/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 7.84 | 0 | 0
701 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-68 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01366/2023-2024 | 565/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0
702 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-72 dt 09.02.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01367/2023-2024 | 566/23-24 | 20/02/2024 | 0 | EASTERN RAILWAY | 6.97 | 0 | 0
703 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-93 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01538/2023-2024 | 623/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
704 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-91 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01539/2023-2024 | 624/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
705 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-08 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01540/2023-2024 | 625/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
706 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-90 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01541/2023-2024 | 626/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.09 | 0 | 0
707 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-92 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01542/2023-2024 | 627/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.28 | 0 | 0
708 | RCFA Division -I | Asansol Mechanical Division | Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-95 dt 07.03.2024 under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Booster Stations & Allied Works) under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | BILL/01543/2023-2024 | 628/23-24 | 14/03/2024 | 0 | EASTERN RAILWAY | 0.08 | 0 | 0
709 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for approach concrete road, room and toilet repairing, materials shifting and stacking and etc allied works at Searsole Stack yard under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000022/2024-2025 | 1525/RCD-I | 14/06/2024 | 45 | M/S MONDAL ENTERPRISE | 16.4 | 0 | 100
710 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of laying 250 mm dia HDPE pipe line and PWD road crossing from Semalya to Kendra Khottamdihi intake pump house site under Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II | Assistant Engineer-I | Junior Engineer-3 | ORD/000041/2024-2025 | 1642/RCD-I | 04/07/2024 | 497 | UMA ENTERPRISE | 71.29 | 0 | 100
711 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000050/2024-2025 | 1750/RCD-I | 18/07/2024 | 20 | MAKALI ENGINEERING CORPORATION | 94.91 | 0 | 100
712 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional for Distribution Network for Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II (Part-4) Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000051/2024-2025 | 1741/RCD-I | 18/07/2024 | 45 | UNITED CONSTRUCTION | 30.14 | 0 | 85
713 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supply and erection of Information Boards (31 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Salanpur ,Barabani, Andal ,Pandabeswar ,Raniganj and Durgapur Faridpur Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000056/2024-2025 | 1746/RCD-I | 18/07/2024 | 15 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 6.1 | 0 | 100
714 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supply and erection of Information Boards (49 nos) having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Kanksa Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000057/2024-2025 | 1747/RCD-I | 18/07/2024 | 15 | UTTAR DINAJPUR ANKUR GRAM UNNAYAN SOCIETY | 9.69 | 0 | 100
715 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supply and erection of Information Boards(43 nos)having M.S Channel/Angle posts and 1.5 mm thick M.S synthetic enamel paint over a coat of red oxide primer including lettering complete at different places under Jamuria Block Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000058/2024-2025 | 1748/RCD-I | 18/07/2024 | 15 | UNITED CONSTRUCTION | 8.48 | 0 | 100
716 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Protecting apparatus of collecting main including other allied works under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000059/2024-2025 | 1751/RCD-I | 18/07/2024 | 20 | INDIA PIPE FITTING CO | 93.63 | 0 | 100
717 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Realtime Water Quality Monitoring including 1 year maintenance for the OHR as hereunder RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000079/2024-2025 | 2033/RCD-I | 21/08/2024 | 455 | MAXBRIDGE SOLUTIONS LLP | 33.46 | 0 | 55
718 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Visiter room and driver rest room at office premises Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000120/2024-2025 | 2155/RCD-I | 29/08/2024 | 90 | G. CONSTRUCTION | 18.48 | 0 | 100
719 | RCFA Division -I | Asansol Mechanical Division | Emergency repairing work of 110 mm dia HDPE distribution main and G.I. line of Health World Hospital of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000165/2024-2025 | Camp-02_Health-World/AE/2 | 22/08/2024 | 10 | M/S CHANDI CHARAN ROY | 4.2 | 0 | 100
720 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-A) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000196/2024-2025 | 2451/RCD-I | 30/09/2024 | 15 | MAKALI ENGINEERING CORPORATION | 78.04 | 0 | 100
721 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Providing of different dia of water regulating apparatus and other allied works (Part-B) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte | Assistant Engineer-I | Junior Engineer-3 | ORD/000197/2024-2025 | 2452/RCD-I | 30/09/2024 | 15 | MAKALI ENGINEERING CORPORATION | 81.71 | 0 | 100
722 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for construction work and Interior Decoration of Office Building in Asansol under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000209/2024-2025 | 2513/RCD-I | 04/10/2024 | 45 | M/S KALYANI ENTERPRISE | 41.78 | 0 | 100
723 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Laying of different dia HDPE pipe line and allied works at Raghunathchak, Raniganj Chati, Baliapur and adjacent area under Zone-IX for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000305/2023-2024 | 2383/RCD-I | 07/08/2023 | 90 | DAWN CONSTRUCTION | 105.48 | 0 | 100
724 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in Salanpur at KM SLS/1136 and SLS/1138 on Bemjomary siding Railway line in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000604/2023-2024 | 3297/RCD-I | 10/11/2023 | 15 | MD AAMIR KHAN | 24.44 | 0 | 100
725 | RCFA Division -I | Asansol Mechanical Division | Continuation work order for Laying 450 mm dia MS water pipe line with 700 mm dia MS casing pipe for Railway crossing in between KM 227/27-29 and between Salanpur (SLS) Rupnarayanpur (RNPR) inAsansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000606/2023-2024 | 3298/RCD-1 | 10/11/2023 | 15 | MAK CONSTRUCTION CO | 45.92 | 0 | 100
726 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Renovation work at Kalyaneswari Inspection Bungalow & WTP under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000721/2023-2024 | 3610/RCD-1 | 20/12/2023 | 540 | M/S KALYANI ENTERPRISE | 81.82 | 0 | 100
727 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency repairing of 50 sqmm x 4 core Al Armoured damaged cable line and other allied Electrical works at Executive Engineer office building, SE office building, rest room & B type quarter under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000722/2023-2024 | 3573_RCD/1 | 12/12/2023 | 15 | T R ENTERPRISE | 6.82 | 0 | 100
728 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Operation and regulatiing of different dia S/V of Distribution system and rising main for FHTC work for Mdira, Dighalpahari, Chotkara and Kanskuli villages under administrative contingency of JJM under RCFA Division -I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000820/2023-2024 | 101/RCD-1 | 09/01/2024 | 239 | SRI KRISHNA ENTERPRISE | 2.91 | 0 | 100
729 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of different dia Sluice Valve, Air Valve, NRV including C.I./D.I Specials to the Searsole Store of Augmentation of RCFA Part-II (Zone-18) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000910/2023-2024 | 215/RCD-I | 29/01/2024 | 20 | SSPR VALVE MANUFACTURING PVT LTD | 49.92 | 0 | 100
730 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-15) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000912/2023-2024 | 216/RCD-I | 29/01/2024 | 20 | INDIA PIPE FITTING CO | 89.25 | 0 | 100
731 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supply of GI pipes to Searsole Store under Augmentation of RCFA Part-II (Zone-17) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000914/2023-2024 | 217/RCD-I | 29/01/2024 | 20 | MAKALI ENGINEERING CORPORATION | 90.4 | 0 | 100
732 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying of rising main at Surjanagar Head Works Site to High lift site under ASTA Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000935/2023-2024 | 476/RCD-I | 12/02/2024 | 45 | MAK CONSTRUCTION CO | 58.51 | 0 | 100
733 | RCFA Division -I | Asansol Mechanical Division | Allied work of laying distribution system of Improvement of RCFA Part-I Commanded area of Zone-V with LDS FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000936/2023-2024 | 451/RCD-1 | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 25.84 | 0 | 100
734 | RCFA Division -I | Asansol Mechanical Division | Allied work Balance Work of Road restoration in connection with formal work order Distribution network including FHTC and allied work at Ondal Block of Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000938/2023-2024 | 452/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 43.94 | 0 | 100
735 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional work of Laying and pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) with 400 mm dia and 300 mm dia MS water carrier pipe line at Node point (82-83) and (74-75) for Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-VIII under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000939/2023-2024 | 487/RCD-I | 12/02/2024 | 25 | SWATI CORPORATION | 17.43 | 0 | 100
736 | RCFA Division -I | Asansol Mechanical Division | Construction of restoration approach road in Chalbalpur at Amritnagar Zone-I under RCFA Part-II under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000943/2023-2024 | 453/RCD-1 | 12/02/2024 | 30 | MRITYUNJOY MUKHERJEE & CO. | 20.62 | 0 | 100
737 | RCFA Division -I | Asansol Mechanical Division | Balance work in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS and FHTC work under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000950/2023-2024 | 455/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 21.29 | 0 | 100
738 | RCFA Division -I | Asansol Mechanical Division | Laying 300 mm dia MS water pipe line with 600 mm dia MS cashing pipe for Railway crossing in Salanpur in between KM 231/16-18 and Salanpur (SLS) Rupnarayanpur (RNPR) Station in Asansol Diviion under JJM under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000956/2023-2024 | 456/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 37.06 | 0 | 100
739 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Emergency repairing work of CI rising main (500 mm dia, 200 mm dia & 150 mm dia ) at Chotdola more, Dhasal more and new Kenda and Searsole H/W site near Pump House under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000958/2023-2024 | 504/RCD-I | 12/02/2024 | 30 | DAWN CONSTRUCTION | 8.84 | 0 | 0
740 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Adopting trench less technology (e.g. Jack Pushing Method etc.) at 3 (Three) nos location within laying distribution system of Amritnagar (Part-B) under Augmentation of Amritnagar Zone-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000963/2023-2024 | 457/RCD-1 | 12/02/2024 | 45 | M/S SINGH & KONAR CONSTRUCTION | 23.02 | 0 | 100
741 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of pipe line from Domhani Asansol main Road near BDO Office to Domohani PHC and construction of stand post at different places at Domohani Bazar under Barabani Development Block under RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-I | Junior Engineer-3 | ORD/000966/2023-2024 | 458/RCD-1 | 12/02/2024 | 20 | UNITED CONSTRUCTION | 6.71 | 0 | 62
742 | RCFA Division -I | Asansol Mechanical Division | Laying of 110 mm dia HDPE pipeline including pushing of 600 mm dia RCC (NP3) hume pipe by adopting trench less technology at Health World Hospital, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. Extension work. | Assistant Engineer-I | Junior Engineer-3 | ORD/001020/2023-2024 | Camp-02_Health_World_AE-I | 21/02/2024 | 20 | M/S CHANDI CHARAN ROY | 18.54 | 0 | 100
743 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Supplying of different pipe specials for Ondal (Phase-I) under Augmentation of RCFA Part II Piped Water Supply Scheme Volume-II for providing FHTC under Andal Block | Assistant Engineer-I | Junior Engineer-3 | ORD/001168/2023-2024 | 1006/RCD-I | 16/03/2024 | 15 | M/S UNIT CONSTRUCTION | 12.5 | 0 | 100
744 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Modification, Improvement of storage, documents with seating arrangement of entire Central Circle, PHE Dte. at Purta Bhawan in the District of Purba Bardhhaman. | Assistant Engineer-I | Junior Engineer-3 | ORD/001183/2023-2024 | 932/RCD-I | 15/03/2024 | 196 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.53 | 0 | 100
745 | RCFA Division -I | Asansol Mechanical Division | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-3 | RTOR000001/2024-2025 | 1178/RCD-I | 03/04/2024 | 0 | Resource Division | 337.92 | 0 | 0
746 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of Jamuri (Rural) (Zone-I) RCFA Part-II Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part-A). | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000032/2023-2024 | 1613/RCD I | 25/04/2023 | 30 | M/S B.K. CONSTRUCTION | 132.16 | 51.78 | 65
747 | RCFA Division -I | RCFA Division I | Formal Work Order for Construction of Water sample collection cum Laboratory cum ISA & DPMU activity center as well as training hall etc. in the premises of RCFA office building under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000172/2023-2024 | 2008/RCD-I | 26/06/2023 | 564 | M/S CHANDI CHARAN ROY | 241.14 | 0 | 67
748 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at 03 (Three) nos. location at Lalganj Domohani Road, Kelejhora Health Centre More to Puchra Road, Puchra to Natudihi Road under Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000240/2023-2024 | 2217/RCD-I | 17/07/2023 | 30 | VISUVIOUS | 30.35 | 0 | 100
749 | RCFA Division -I | RCFA Division I | Preparation of DPR & Route Survey for augumentation of Jamuria (Rural) (Zone-I) piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. (Sl No. 32) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000251/2022-2023 | 2247/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.43 | 3.43 | 0
750 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying 200 mm dia MS water pipe line with 600 mm dia MS casing pipe for Railway crossing in between KM 27/21-23 and between Barabani (BBI) and Jamuria (JMA) Station in Asansol Division under JJM under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000286/2023-2024 | 2335/RCD-I | 01/08/2023 | 15 | M/S MONDAL ENTERPRISE | 36.29 | 34.64 | 100
751 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Additional Supplying, Laying and Aligning HDPE pipe line, construction of street stand post and allied works under Ballavpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000403/2023-2024 | 2585/RCD-I | 07/09/2023 | 15 | TARA CONSTRUCTION | 6.32 | 6.15 | 100
752 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 200 mm dia rising main for the proposed of Shyamla for Augmentation of Jamuria (Rural) (Zone-I) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000686/2023-2024 | 3285/RCD-1 | 08/11/2023 | 30 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 12.63 | 0 | 85
753 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Jamuria under Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000732/2023-2024 | 3656/RCD-1 | 28/12/2023 | 330 | MD SARFARAZ ALAM | 23.33 | 0 | 70
754 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for augmentation of Jamuria (Rural)(Zone-I) pipe water Supply Scheme including FHTC allied work wthin Jamuria Block under RCFA Div-I PHE Dte.(Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000782/2022-2023 | 813/RCD I | 10/03/2023 | 30 | DIP CONSTRUCTION | 151.47 | 43.68 | 20
755 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 03 (Three) Nos river bed tube wells including collecting main, Sluice Valve chamber & other allied work at Darbardanga H/W at Ajoy River under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000843/2022-2023 | 1076/RCD-I | 23/03/2023 | 90 | MAA ENTERPRISE. | 19.58 | 0 | 100
756 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional estimate for concrete conduit for water body crossing at 4 (Four) nos location including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work, Supply of valve, hard rock cutting, valve chamber and allied works related to distribution network at Churulia, Rakhakura, Joynagar, Chinchurbil etc villages under Augmentation of Jamuria Rural (Zone-1) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000984/2023-2024 | 468/RCD-1 | 12/02/2024 | 45 | ASHA CONSTRUCTION | 39.4 | 0 | 100
757 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. jack Pushing Method etc) for crossing of NH-60 near Pandabeswar H/W Site to carry 350 mm dia distribution & 250 mm dia rising main pipe line under RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000018/2024-2025 | 1521/RCD-I | 14/06/2024 | 45 | HIRANMAY GHOSH | 14.09 | 0 | 0
758 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 (Four) nos 200 mm dia Horizontal River Bed Tube Well with fitting of 200 mm dia Strainer (12.2 mtr) in river Ajay & Collecting line under RCFA Part-III Zone-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000020/2024-2025 | 1523/RCD-I | 14/06/2024 | 45 | T M CONCRETE CREATION PVT.LTD | 14.42 | 0 | 100
759 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Allied work of Replacement of A.C pipe of Main Distribution pipeline from Madhaiganj OHR to RANGAMATI Village including ROAD Restoration of Rangamati Village Of Augmentation of RCFA part III Zone I under RCFA Div- I, PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000217/2024-2025 | 2547/RCD-I | 29/10/2024 | 154 | BASANTI TRADERS | 32.79 | 0 | 40
760 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying of Rising main and other allied works from Panshuili H/W Site to Natundanga OHR of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000224/2024-2025 | 2556/RCD-I | 29/10/2024 | 180 | UNITED CONSTRUCTION | 36.87 | 0 | 70
761 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Improvement & Overhauling of 5 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Bhaburia H/W Site under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA W/S Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000241/2024-2025 | 2615/RCD-I | 13/11/2024 | 30 | SREE ENTREPRENEUR | 24.71 | 0 | 100
762 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for HDPE distribution pipe line laying for Gourbazar and Bhabanandapur village and other allied works under Augmentation of RCFA Part-III (Zone-I) PWSS under RCFA Davison-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000263/2025-2026 | 1485/RCD-I | 15/05/2025 | 120 | SILPO UDYOG ENGINEERING CONSTRUCTIONS | 34.41 | 0 | 80
763 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional pipe line with of HDPE pipe with at Pratappur and Kalikapur with re-connection of existing FHTC and other allied works of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000291/2024-2025 | 2628/RCD-I | 14/11/2024 | 182 | SIMA ENTERPRISE | 57.5 | 0 | 80
764 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) for crossing of Railway Track near Fulbagan more DVC para to carry 250 mm dia distribution line of Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme (Complying JJM) under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000298/2024-2025 | 2635/RCD-I | 14/11/2024 | 60 | RUBY CONSTRUCTION | 19.07 | 0 | 100
765 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPaschim Para at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-I under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000325/2025-2026 | 1511/RCD-I | 20/05/2025 | 87 | UNITED CONSTRUCTION | 22.25 | 0 | 60
766 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Sub-Station Building at Ramnagar H/W Site within Pandabeswar Block under RCFA Part-III (Zone-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000373/2024-2025 | 3101/RCD-I | 13/12/2024 | 292 | RANJIB GHATAK | 36.86 | 0 | 90
767 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Balance work of distribution pipe line including allied works at Sarpi village under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000380/2024-2025 | 3108/RCD-I | 13/12/2024 | 45 | UNITED CONSTRUCTION | 30.42 | 0 | 100
768 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology(e.g. Jack Pushing Method etc)of 03(Three) nos. location at Sarpi Maji para, Shyamsundarpur More and Kumardihi gram near stadium under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/000534/2024-2025 | 137/RCD-I | 08/01/2025 | 30 | MAK CONSTRUCTION CO | 22.97 | 0 | 100
769 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of Laudoha OHR site at Laudoha under RCFA Part-III Water Supply Scheme within Durgapur Faridpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/001209/2023-2024 | 1021/RCD-I | 16/03/2024 | 45 | M/S A G CONSTRUCTION | 8.87 | 0 | 100
770 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Repairing and renovation of Pansiuli OHR site under Augmentation of RCFA (PART-lll) Zone-l Piped water supply scheme within Durgapur Faridpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-2 | ORD/001222/2023-2024 | 1022/RCD-I | 16/03/2024 | 564 | SHWET BARANI | 13.3 | 0 | 100
771 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 200 cum capacity 20 mtr. Staging height RCC Over Head Reservoir (pipe connection and cost of pipes, speciials at jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000006/2023-2024 | 1403 RCD I | 12/04/2023 | 366 | SRI KRISHNA ENTERPRISE | 72.48 | 36.24 | 99
772 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000097/2022-2023 | 1270/RCD-I | 02/06/2022 | 90 | M/S S.K. ENTERPRISE | 24.81 | 21.56 | 100
773 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000098/2022-2023 | 1271/RCD-I | 02/06/2022 | 90 | ALOKESH BANERJEE | 23.92 | 21.24 | 80
774 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000099/2022-2023 | 1272/RCD-I | 02/06/2022 | 90 | B.T.M CONCERN | 55.19 | 49.18 | 100
775 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for Distribution Network including adopting trench less technology at two places under Augmentation of Jamgram Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000216/2023-2024 | 2223/RCD-I | 17/07/2023 | 30 | B.T.M CONCERN | 39.15 | 35.84 | 92
776 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Jamgram OHR site of Augmentation of Jamgram Piped Water Supply Scheme under Barabani Block under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000346/2023-2024 | 2479/RCD-I | 23/08/2023 | 30 | SRI KRISHNA ENTERPRISE | 36.83 | 0 | 5
777 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 4 (Four) nos river bed tube wells including collecting main & other allied works at Unionpara H/W under RCFA Part-II at Damodar river under Unionpara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000349/2023-2024 | 2483/RCD-I | 23/08/2023 | 30 | T.R. ENTERPRISE | 11.42 | 11.08 | 100
778 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000404/2022-2023 | 2519/RCDI | 20/10/2022 | 712 | MAA ENTERPRISE | 22.6 | 0 | 60
779 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-I) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000405/2022-2023 | 2520/RCDI | 20/10/2022 | 30 | B.T.M CONCERN | 50.77 | 0 | 65
780 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency Repairing of 750 mm dia Rising main with supply of leak repairing clamp and allied works related to supply of CI/DI specials etc, under Augmentation of Itapara Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000412/2023-2024 | 2612/RCD-I | 12/09/2023 | 20 | MAKALI ENGINEERING CORPORATION | 98.81 | 98.81 | 100
781 | RCFA Division -I | RCFA Division I | Preparation of DPR for Augumentation of Jamgram Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte.(sl no 03) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000481/2021-2022 | 2347/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 2.88 | 2.88 | 0
782 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000525/2022-2023 | 3138/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 100
783 | RCFA Division -I | RCFA Division I | Acceptance cum work order for rising Main for Augmentation of Jamgram Piped Water Supply Scheme at Baraboni Block Under RCFA - Div - I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000569/2022-2023 | 3278/RCD I | 20/12/2022 | 21 | DEBI PRASAD MAJI | 15.63 | 6.18 | 100
784 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Pump House at Jamgram for Augmentation of Jamgarm Piped Water Supply Scheme under RCFA, Division-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000570/2022-2023 | 3279/RCDI | 20/12/2022 | 468 | R B ENTERPRISE | 20.73 | 9.49 | 100
785 | RCFA Division -I | RCFA Division I | Providing FHTC through retrofitting under Augmentation of Jamgram PWSS (Part-III) under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000606/2022-2023 | 3274/RCDI | 20/12/2022 | 623 | M/S S.K. ENTERPRISE | 22.96 | 0 | 50
786 | RCFA Division -I | RCFA Division I | Additional work like Horizonal Augar boring, dismantaling concrete and allied works in releted to part-B of Augmentation of jamgram PWSS under RCFA division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000642/2023-2024 | 3394/RCD-I | 23/11/2023 | 7 | M/S S.K. ENTERPRISE | 0.8 | 0 | 100
787 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of HDPE Pipe line from Panuria Bazar to Shirikhad Para under Jamgram Panuria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000646/2022-2023 | 344/RCD I | 30/01/2023 | 15 | SHREE DURGA ENTERPRISE | 1.35 | 1.34 | 0
788 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying 110 mm dia HDPE pipe with construction of piller for crossing a water body within Jamgram PWSS Part-C under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000674/2023-2024 | 3458/RCD-1 | 24/11/2023 | 15 | ALOKESH BANERJEE | 3.39 | 0 | 100
789 | RCFA Division -I | RCFA Division I | Acceptance cum work order Ground Level Reservoir of capacity 105 cum for Augmentation Jamgram & its Adjoining Mouza Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000835/2022-2023 | 1062/RCD-I | 23/03/2023 | 375 | SUBHADEEP DAS | 12.25 | 11.43 | 100
790 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of Jamgram Piped Water Supply Scheme including FHTC work Block Barabani, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000960/2022-2023 | 1053/RCD-I | 23/03/2023 | 30 | SRI KRISHNA ENTERPRISE | 90.22 | 34.13 | 55
791 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional by constructing pillar for water body crossing including adopting trench less technology (e.g. Jack Pushing Method etc) at Three nos location including MS work and allied works related to rising main of Itapara and adjoining mouzas under Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001062/2023-2024 | 502/RCD-I | 12/02/2024 | 232 | DURGA DAS MONDAL | 38.11 | 0 | 100
792 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Switch room and balance work of approach road towards Gourbazar Head Works Site under Augmentation of Jamgram PWSS under RCFA Division-I PHE Dte | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001115/2023-2024 | 921/RCD-I | 15/03/2024 | 60 | R B ENTERPRISE | 8.42 | 0 | 100
793 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work of Laying distribution system within distribution network for Augmentation of Jamgram PWSS under RCFA Div- I, PHE Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001121/2023-2024 | 927/RCD-I | 15/03/2024 | 45 | B.T.M. CONCERN | 35.23 | 0 | 89
794 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | RTOR000010/2022-2023 | 2350/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
795 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000019/2021-2022 | 956/RCD-I | 07/06/2021 | 30 | SUMIT BANERJEE | 23.02 | 38.36 | 0
796 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000020/2021-2022 | 957/RCD-I | 07/06/2021 | 30 | BABA LOKNATH ENTERPRISE | 23.01 | 43.71 | 0
797 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000021/2021-2022 | 958/RCD-I | 07/06/2021 | 30 | KHEPI MAA TRADERS | 22.98 | 5.31 | 0
798 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-II), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000061/2021-2022 | 1147/RCD-I | 22/07/2021 | 30 | GITASHREE FABRICATION | 21.97 | 21.9 | 0
799 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of Morum cutting, concrete cutting, Hard rock cutting, Bituminus Road cutting different dia DI (K-7) & HDPE pipe line with other allied works from Dabor OHR Zone-II (Pahargara, Mohanpur, Partabpur, Bolkundi etc) distribution under Retrofitting Chotkara-Kanskuli W/S Scheme Zone II under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000161/2021-2022 | 1586/RCD-I | 07/09/2021 | 30 | DAS & CHAKRABORTY | 11.29 | 10.88 | 0
800 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Chotkara (Part) for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 16) | Assistant Engineer 1 | Junior Engineer | ORD/000576/2021-2022 | 258/RCD-I | 01/02/2022 | 15 | JAYANTA DATTA | 2.59 | 2.48 | 0
801 | RCFA Division -I |  | Acceptance cum work order for Re-connection of FHTC & additional Functional Household Tap Connection (FHTC) for Retrofitting of Ijjatganj and Kanksa mouza for providing FHTC for new pipe line laying under RCFA Division-I PHE Dte. |  |  | ORD/000289/2024-2025 | 2630/RCD-I | 14/11/2024 | 135 | SHWET BARANI | 23.56 | 0 | 100
802 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Creating separate zone with pipe line & additional FHTC including Water sources at Sibpur Ruidaspara under Augmentation of Krishnapur Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000366/2024-2025 | 3066/RCD-I | 10/12/2024 | 90 | HIRANMAY GHOSH | 26.47 | 0 | 100
803 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of Boundary wall and allied works at Krishnapur tube well No-02 under Augmentation of Krishnapur Piped water Supply scheme under Kanksa Block under RCFA Division-I,PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/001188/2023-2024 | 1007/RCD-I | 16/03/2024 | 30 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 7.12 | 0 | 80
804 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block including FHTC & allied work under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000029/2023-2024 | 1616/RCD I | 25/04/2023 | 180 | SIMA ENTERPRISE | 115.57 | 67.26 | 75
805 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Pump House at River side H/W for Augmentation Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000110/2023-2024 | 1867/RCD-1 | 01/06/2023 | 180 | M/S KALYANI ENTERPRISE | 19.55 | 0 | 0
806 | RCFA Division -I | RCFA Division I | Continuation work order for Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.09.2024 to 28.02.2025) (Sl No. 02) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000160/2024-2025 | 2164_RCD-I | 30/08/2024 | 182 | SHYAMAL MAJI | 0.9 | 0 | 33
807 | RCFA Division -I | RCFA Division I | Formal Work Order for Construction of 350 cum capacity 20 mtr. staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Bagdiha for Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/12/2012 (Sheet No. 1 & 2) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000184/2023-2024 | 2042/RCD-I | 04/07/2023 | 366 | DHANANJOY DUTTA | 108 | 0 | 50
808 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 03 (Three) nos. river bed tube wells including collecting main, sluice valve chamber, reinforcement & other allied works at Bagdiha H/W site at Ajoy river under Augmentation of Bagdiha Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000205/2023-2024 | 2240/RCD-I | 17/07/2023 | 30 | M/S KALYANI ENTERPRISE | 24.44 | 0 | 0
809 | RCFA Division -I | RCFA Division I | Acceptance Cum work order Laying of different dia distribution pipe line and concrete road cutting and mending works at Bagdi para, Dangal Para, Telipara etc adjacent area Dakshin Khanda area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000212/2023-2024 | 2221/RCD-I | 17/07/2023 | 30 | M/S KALYANI ENTERPRISE | 10.09 | 8.45 | 100
810 | RCFA Division -I | RCFA Division I | Preparation of DPR & Route Survey for augumentation of Bagdiha piped water supply scheme block-Jamuria, dist- Paschim Barddhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000279/2022-2023 | 2246/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.43 | 3.43 | 0
811 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing by adopting trench less technology (e.g. Jack Pushing Method etc) and allied works at Bagdiha to Sidhapur Road and Bagdiha OHR to Bahadurpur under Jamuria Block under Augmentation of Bagdiha PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000284/2023-2024 | 2333/RCD-I | 01/08/2023 | 15 | SIMA ENTERPRISE | 46.6 | 17.22 | 77
812 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 3 (Three) nos 200 mm dia river bed tube wells including collecting main in the river Ajoy at Bagdiha under Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000350/2023-2024 | 2484/RCD-I | 23/08/2023 | 30 | M/S KALYANI ENTERPRISE | 24.12 | 0 | 0
813 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Bye pass connection including supplying, aligning, laying of HDPE pipe and other allied works at Bagdiha Head Works Site to Bagdiha Siddapur High School under Bagdiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000767/2022-2023 | 393/RCDI | 30/01/2023 | 30 | BABA LOKNATH ENTERPRISE | 30.27 | 17.57 | 100
814 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000839/2022-2023 | 1069/RCD-I | 23/03/2023 | 90 | M/S S.K. ENTERPRISE | 61.35 | 21.2 | 35
815 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Rising Main for Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000840/2022-2023 | 1067/RCD I | 23/03/2023 | 1105 | D.S.C. CONCERN | 12.64 | 0 | 100
816 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000841/2022-2023 | 1071/RCD-I | 23/03/2023 | 90 | TARA MA ENTERPRISE | 54.95 | 15.27 | 0
817 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Bagdiha Piped Water Supply Scheme at Jamuria Block Including FHTC & allied work under RCFA Division-I PHE Dte. (Part-E)( Sl No. 10) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000865/2022-2023 | 1072/RCD-I | 23/03/2023 | 90 | R B ENTERPRISE | 68.85 | 28.7 | 50
818 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of boundary wall Gate at OHR Site (Length-60 mtrs) at Bagdiha of Jamuria Block for Augmentation of Bagdiha Piped Water Supply Scheme under RCFA Division-I PHE Dte. in District Paschim Bardhaman (Sl No. 20) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000913/2022-2023 | 1164/ RCD I | 24/03/2023 | 60 | M/S KALYANI ENTERPRISE | 5.31 | 0 | 0
819 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Plastering, painting works of Boundary Wall, Pump House, Chlorine Room CWR and other allied works and other allied works under Bagdiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | ORD/000950/2022-2023 | 1280/RCD-I | 27/03/2023 | 15 | M/S KALYANI ENTERPRISE | 5.04 | 5.04 | 0
820 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-4 | RTOR000009/2023-2024 | 2029/RCD-I | 30/06/2023 | 0 | Resource Division | 127.95 | 0 | 0
821 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & Aallied work under RCFA Division-I PHE Dte. (Zone-19) (Part-B). | Assistant Engineer 2 |  | ORD/000035/2023-2024 | 1611/RCD I | 25/04/2023 | 180 | UMA ENTERPRISE | 195.63 | 0 | 65
822 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied Work under RCFA Division-I PHE Dte. (Zone-19)(Part-A) | Assistant Engineer 2 |  | ORD/000040/2023-2024 | 1605/RCD I | 25/04/2023 | 180 | A. CONSTRUCTION CO. | 233.19 | 67.77 | 70
823 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Distribution Network for Augmentation of RCFA Part-II (Zone-19) (Part-A) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000043/2024-2025 | 1644/RCD-I | 04/07/2024 | 20 | A CONSTRUCTION CO | 9.41 | 0 | 100
824 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-19) with Construction of 600 cumcapacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District -Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000094/2023-2024 | 1830/RCD-I | 29/05/2023 | 365 | SWATI CORPORATION | 181.97 | 0 | 40
825 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of Construction of Rigid Pavement for the approach road from the main road towards Head Work Site and Laying of Pipe line for Pandebeswar Block of Augmentation PWSS of RCFA Part-II (Zone-19) under RCFA Division-I P.H.E Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000096/2024-2025 | 2127/RCD-I | 27/08/2024 | 30 | SWATI CORPORATION | 10.61 | 0 | 100
826 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 600 cum capacity RCC Over Head Reservoir at (Zone-19) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000555/2022-2023 | 3349/RCDI | 23/12/2022 | 782 | MOYTEC | 0.49 | 0 | 100
827 | RCFA Division -I | RCFA Division I | Formal work order of laying of 200 mm dia HDPE pipe line from Semalya to kendra Khottamdihi intake pump house site under Kendra Khottamdihi Water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 |  | ORD/000601/2022-2023 | 14/RCDI | 05/01/2023 | 452 | UMA ENTERPRISE | 157.45 | 156.69 | 100
828 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including Adopting trench less technology (e.g. Jack Pushing Method etc) of 03 ( Three) Nos. location at Bankola Rail gate, Bankola Siding ECL & Bankola Water Supply Gate under Augmentation of RCFA Part-II Zone 19 PWSS under RCFA,Division-I,P.H.E.Dte. | Assistant Engineer 2 |  | ORD/001113/2023-2024 | 919/RCD-I | 15/03/2024 | 30 | A CONSTRUCTION CO | 42.4 | 0 | 100
829 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Interconnection at Baliapur OHR Site (02 nos. OHR), Barabani OHR and Barabani Railway crossing of RCFA Part-II Zone-19 PWSS under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/001119/2023-2024 | 925/RCD-I | 15/03/2024 | 30 | M/S MONDAL ENTERPRISE | 22.75 | 0 | 100
830 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000038/2023-2024 | 2957/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
831 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14B) | Assistant Engineer 2 |  | ORD/000071/2023-2024 | 1761/RCD I | 16/05/2023 | 961 | MD AAMIR KHAN | 409.77 | 0 | 15
832 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for distribution network including supply of Hume pipe, G.I. pipe and adopting trench less technologies at 02 (Two) locations in connection to Zone-I Part-A Dendua OHR for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000294/2023-2024 | 2365/RCD-I | 04/08/2023 | 30 | ASHA CONSTRUCTION | 15.08 | 0 | 100
833 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance and other allied works for construction of store room at work site for(Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II (Zone-14B) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000542/2024-2025 | 145/RCD-I | 08/01/2025 | 90 | RANJIB GHATAK | 20.29 | 0 | 70
834 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Shifting of existing rising main for construction of new Pump House at Dendua OHR Campus under Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000599/2023-2024 | 3281/RCD-I | 08/11/2023 | 90 | D.S.ENTERPRISE | 12.45 | 0 | 100
835 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of concrete road due to FHTC work at Kallya and surrounding villages within Kallya Gram Panchayat under Improvement of RCFA Part-I water Supply scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000658/2023-2024 | 3452/RCD-I | 24/11/2023 | 15 | JAI MAHARAJ ENTERPRISE | 3.71 | 0 | 100
836 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) of Water Pipe Lines at Railway Gate (Node No 116 to 128) under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | ORD/000661/2023-2024 | 3431/RCD-1 | 24/11/2023 | 90 | SINGHA ROY & CO. | 44.79 | 0 | 100
837 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied work at Baidyanathpur under AUGMENTATION PWSS OF RCFA PART-II (ZONE-14B) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000681/2023-2024 | 3473/RCD-I | 28/11/2023 | 551 | MAA ENTERPRISE | 23.33 | 0 | 25
838 | RCFA Division -I | RCFA Division I | Acceptance cum work order of additional works of Dismantling & concrete works, Jack Pushing Supplying, Aligning and laying and other allied works at distribution system Networks for Shyamlya in Nimsa mouza under Shyamlya Gram Panchayat under Jamuria Block of Augmentation of PWSS RCFA Part-II (Zone-14B) under R.C.F.A Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000713/2023-2024 | 2883/RCD-I | 06/10/2023 | 543 | A CONSTRUCTION CO | 37.4 | 0 | 100
839 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 03 (Three) nos. 200 mm dia river bed tube well including laying of 250 mm dia HDPE pipe line in the river of Ajoy for Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000717/2023-2024 | 3546/RCD-1 | 07/12/2023 | 30 | B.T.M. CONCERN | 21.19 | 0 | 10
840 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000032/2023-2024 | 2942/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
841 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 250 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Samlya for Samlya Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Ref Drawing No. PC-I/OHR/10/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000459/2022-2023 | 2934/RCD-I | 17/11/2022 | 12 | M/S CHANDI CHARAN ROY | 80.02 | 24.01 | 100
842 | RCFA Division -I | RCFA Division I | Formal Work Order for Supplying, laying and aligning of distribution system including FHTC for Shyamla W/S Scheme in Syamla and Bhuri Mouza, Block ¿ Jamuria, Dist ¿ Bardhaman under Shyamla W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 2 | Junior Engineer | ORD/000479/2022-2023 | 2029/RCD-I | 30/08/2022 | 1030 | SWATI CORPORATION | 337.77 | 207.8 | 85
843 | RCFA Division -I | RCFA Division I | Continuation work order for Supplying, laying and aligning of distribution system for Part of Kendra Khottamdihi Mouza (JL No. 001), Bajari (Jl No. 023) & Sonpur (Jl No. 022) for Kendra Khottamdihi W/S Scheme (Zone-I) , Block:-Pandabeswar under RCFA Division-I PHE Dte. (Part-A) under JJM (RCFA Part-II) | Assistant Engineer 2 | Junior Engineer | ORD/000824/2022-2023 | 800/RCD-I | 06/03/2023 | 90 | MRITYUNJOY MUKHERJEE & CO. | 95.19 | 83.15 | 100
844 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000005/2023-2024 | 1854/RCD-I | 31/05/2023 | 0 | Resource Division | 7.25 | 0 | 0
845 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for pushing 300 mm dia MS Rising main through 600 mm Dia RCC pipe road crossing trenchless method under NH-19 at front topline more under OCP based Kajora site Augmentation of sub surface water supply scheme ondal phase-II/A under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000179/2024-2025 | 2427/RCD-I | 26/09/2024 | 30 | T M CONCRETE CREATION PVT.LTD | 12.98 | 0 | 100
846 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-2) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000228/2023-2024 | 2213/RCD-I | 17/07/2023 | 30 | SOMNATH SAMANTA | 11.57 | 0 | 100
847 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-3) Block Andal, Dist-Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000230/2023-2024 | 2214/RCD-I | 17/07/2023 | 30 | UNITED CONSTRUCTION | 56.6 | 24.99 | 50
848 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Ondal (Phase ¿ II/A) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part - 3) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000245/2022-2023 | 2211/RCD-I | 14/09/2022 | 45 | UNITED CONSTRUCTION | 88.03 | 74.93 | 90
849 | RCFA Division -I | RCFA Division I | Acceptance cum work order of distribution network for augmentation of Ondal (Phase II/A) piped water supply scheme including FHTC & allied work within Ondal Block under RCFA Div-I, PHE Dte. (Part-I) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000296/2022-2023 | 2482/RCD I | 17/10/2022 | 45 | SIMA ENTERPRISE | 89.81 | 71.28 | 90
850 | RCFA Division -I | RCFA Division I | Acceptance cum work order of distribution network for augmentation Of Ondal (Phase-II/A) piped Water Supply scheme including FHTC & allied works Ondal Block under RCFA Div-I PHE Dte.(Part-2) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000299/2022-2023 | 2483/RCD I | 17/10/2022 | 45 | SOMNATH SAMANTA | 89.8 | 49.6 | 90
851 | RCFA Division -I | RCFA Division I | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 03) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000537/2021-2022 | 502/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.54 | 4.54 | 0
852 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 200 cum & allied work at Ramprasadpur H/W Site under Augmentation of Sub Surface Water Supply Scheme of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000575/2022-2023 | 3284/RCDI | 20/12/2022 | 90 | SOMNATH SAMANTA | 22.05 | 0 | 70
853 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repair and renovation works of One no. RCC Elevated Reservoir of capacity 550 cum at Dignala for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000873/2022-2023 | 1124/ RCD I | 24/03/2023 | 90 | M/S SUBHRADEEP | 11 | 0 | 100
854 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-II/A) Piped Water Supply Scheme (Part-1) Block- Andal Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 08) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000885/2022-2023 | 1129/ RCD I | 24/03/2023 | 30 | SIMA ENTERPRISE | 13.76 | 9.36 | 80
855 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | RTOR000018/2022-2023 | 3131 | 09/12/2022 | 0 | Resource Division | 106.94 | 0 | 0
856 | RCFA Division -I | RCFA Division I | Fuel bill in favor of Ranjit Auto for the month of March 2024 for 1 no. Vehicle for Office of the Deputy Superintending Engineer, RCFA W/S Circle, PHE Dte, Govt. of West Bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00221/2024-2025 | 109/24-25 | 21/06/2024 | 0 | RANAJIT AUTO | 0.2 | 0 | 0
857 | RCFA Division -I | RCFA Division I | Fuel bill in favor of Ranjit Auto for the month of April 2024 for 1 no. Vehicle for Office of the Deputy Superintending Engineer, RCFA W/S Circle, PHE Dte, Govt. of West Bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00222/2024-2025 | 110/24-25 | 21/06/2024 | 0 | RANAJIT AUTO | 0.19 | 0 | 0
858 | RCFA Division -I | RCFA Division I | fuel bill infavor of Ranjit Auto for one no vechile for affiliated of the Deputy superintending Engineer RCFA W/S circle PHE Dte Govt of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00487/2024-2025 | 255/24-25 | 28/08/2024 | 0 | RANAJIT AUTO | 0.24 | 0 | 0
859 | RCFA Division -I | RCFA Division I | fuel bill infavor of Ranjit Auto for one no vechile for affiliated of the Deputy superintending Engineer RCFA W/S circle PHE Dte Govt of west bengal | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | BILL/00489/2024-2025 | 257/24-25 | 28/08/2024 | 0 | RANAJIT AUTO | 0.25 | 0 | 0
860 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work of construction of CWR at Runakuraghat for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000062/2024-2025 | 1590/RCD-I | 27/06/2024 | 45 | SAMIR KUMAR ROY CHOWDHURY | 9.92 | 0 | 100
861 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-B) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000100/2022-2023 | 1273/RCD-I | 02/06/2022 | 90 | SRI KRISHNA ENTERPRISE | 75.81 | 49.8 | 100
862 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-C) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000101/2022-2023 | 1274/RCD-I | 02/06/2022 | 670 | RUBY CONSTRUCTION | 41.7 | 37.77 | 80
863 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme Block Barabani, Dist- Paschim Bardhaman under RCFA Div-I PHE,Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000102/2022-2023 | 1275/RCD-I | 02/06/2022 | 90 | JYOGOMAYA ENTERPRISE | 28.02 | 26.65 | 100
864 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL No 08) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000115/2022-2023 | 1282/RCDI | 02/06/2022 | 30 | SRI KRISHNA ENTERPRISE | 21.96 | 10.24 | 100
865 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Roshna Piped Water Supply Scheme including FHTC Work and Construction of 300 cum capacity 20 Mtr staging height RCC Over Head Reservoir Block Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000121/2022-2023 | 1607/RCD-I | 06/07/2022 | 180 | SRI KRISHNA ENTERPRISE | 163.56 | 130.54 | 100
866 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of Boundary wall, dismantling & reconstruction of flooring of Pump House, CWR and other allied work at H/W site of Ballavpur Hospital under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000267/2023-2024 | 2324/RCD-I | 01/08/2023 | 21 | SUBHADEEP DAS | 7.46 | 0 | 100
867 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Extension of pipe line for providing 60 nos FHTC at different area of Kendra for Kendra Khottamdihi Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000470/2023-2024 | 2861/RCD-I | 06/10/2023 | 30 | TARA CONSTRUCTION | 26.79 | 0 | 100
868 | RCFA Division -I | RCFA Division I | Preparation of DPR for Augumentation of Roshna Piped Water Supply Scheme Block - Barabani, Dist - Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 05) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000479/2021-2022 | 2349/RCD I | 17/12/2021 | 15 | STEELCONC AND ASSOCIATES | 3.03 | 3.03 | 0
869 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000527/2022-2023 | 3140/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 50
870 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of 200 mm dia rising main for Roshna OHR from Gourandi CWR under Augmentation of Roshna Piped water Supply Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000830/2022-2023 | 1034/RCDI | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 11.44 | 0 | 60
871 | RCFA Division -I | RCFA Division I | Acceptance cum work order forLaying of different dia HDPE pipe line including concrete cutting and mending work at Khyerbaid, Amdiha area Zone-IX under Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. (Sl. No. 26) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000864/2022-2023 | 1092/RCD-I | 23/03/2023 | 60 | SRI KRISHNA ENTERPRISE | 24.69 | 0 | 80
872 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing, Renovation, renewing & overhauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Works Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 Nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75cum/hr ¿ 2nos) at Madantore Head works site for Madantore W/S Scheme under RCFA Division-I PHE Dte. (Part-B) iii) for 4 nos. Iron removal Plant (Pressure type) each capacity 20 cum/hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. Iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Works Site under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000879/2023-2024 | 1391_I_RCD_I | 11/04/2023 | 60 | TARAPRASAD SARKAR | 52.19 | 0 | 70
873 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional work for the laying of 315 mm dia HDPE pipe instead of 300 mm dia D.I. pipe of Distribution Network for Improvement RCFA Part-I Water Supply Scheme within command area of Zone-XI (Part-6 Distribution Segment) Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000882/2022-2023 | 1140/RCD-I | 24/03/2023 | 30 | UMA ENTERPRISE | 71.96 | 0 | 30
874 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 1.5 mtrs Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 3 layer Barbed Wire around Roshna Head Works Site under Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl. No. 09) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000887/2022-2023 | 1131/ RCD I | 24/03/2023 | 30 | SRI KRISHNA ENTERPRISE | 27.16 | 0 | 95
875 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional laying of 90 mm dia HDPE pipe of distribution network at Aliganj and surrounding area for Augmentation of Roshna Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000897/2022-2023 | 1151/RCD-1 | 24/03/2023 | 30 | RUBY CONSTRUCTION | 5.99 | 4.63 | 50
876 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Laying of 200 mm dia rising main for the Augmentation of Roshna Piped Water Supply Scheme . under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000975/2023-2024 | 462/RCD-1 | 12/02/2024 | 30 | T R ENTERPRISE | 12.98 | 0 | 100
877 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying and pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Aliganj within distribution system Part-C of Roshna under Augmentation of Roshna PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/000992/2023-2024 | 472/RCD-1 | 12/02/2024 | 25 | RUBY CONSTRUCTION | 11.75 | 0 | 100
878 | RCFA Division -I | RCFA Division I | Formal work order for construction of CWR 150 cum, sub station building of H/W site, pump house, chlorine room and other allied work (Bank of Ajoy river) under Semalya Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001037/2022-2023 | 1216_1_RCD-I | 24/03/2023 | 120 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 72.59 | 0 | 0
879 | RCFA Division -I | RCFA Division I | Hiring of SUV (A.C) (Non Airconditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. for the Office Use of the Deputy Superintending Engineer, RCFA W/S Circle, Public Health Engineering Directorate, Govt. of West Bengal (w.e.f. 01.03.2024 to 31.08.2024) (Sl No. 02) | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001128/2023-2024 | 718C/RCD-I | 01/03/2024 | 184 | SHYAMAL MAJI | 0.9 | 0 | 10
880 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Additional work including Adopting Trench less technology (e.g. Jack Pushing Method etc) at 04(Four) nos. location at (i)Churulia Main Road, (ii)Nazrul Academy Road Crossing (iii)Likapur Road Crossing (iv)Madhudanga OHR and allied MS work including open cut at pump house and existing OHR site including supply of Hume pipe in related to rising main of Churulia and Madantore under Augmentation of Roshna PWSS under RCFA Division ¿I PHE Dte | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | ORD/001179/2023-2024 | 1020/RCD-I | 16/03/2024 | 30 | T R ENTERPRISE | 40.55 | 0 | 100
881 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000003/2023-2024 | 1638/RCD-I | 27/04/2023 | 0 | Resource Division | 30.48 | 0 | 0
882 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-I | Junior Engineer,Junior Engineer-3 | RTOR000009/2022-2023 | 2349/RCD-I | 28/09/2022 | 0 | Resource Division | 12.32 | 0 | 0
883 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000033/2023-2024 | 1631/RCD-I | 26/04/2023 | 366 | UNITED CONSTRUCTION | 69.15 | 13.83 | 100
884 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- I) under Jamuria Block in the district of Paschim Bardhaman Under RCFA Division - I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000100/2024-2025 | 2120/RCD-I | 27/08/2024 | 60 | SIMA ENTERPRISE | 46.06 | 0 | 40
885 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work of Distribution Network for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme including FHTC & allied work within Jamuria Block under RCFA Division-I PHE Dte. (Part- A) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000111/2024-2025 | 2133/RCD-I | 27/08/2024 | 146 | M/S B.K. CONSTRUCTION | 20.94 | 0 | 65
886 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution network for Augmentation of Jamuria Rural- II Piped Water Supply Scheme including FHTC work (Segment- II) under Jamuria Block in the district of Paschim Bardhaman under RCFA Division - I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000118/2024-2025 | 2117/RCD-I | 27/08/2024 | 804 | MS SAMANTA CONSTRUCTION | 48.54 | 0 | 100
887 | RCFA Division -I | RCFA Division I | Preparation of DPR & Route Survey for Augmentation of Jamuria (Rural) (Zone-II) Piped Water Supply Scheme Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000250/2022-2023 | 2230/RCD I | 15/09/2022 | 15 | APEX ENGINEERING | 3.58 | 3.58 | 0
888 | RCFA Division -I | RCFA Division I | Distribution network for Augmentation of Jamuria Rural-II Piped Water Scheme including FHTC work Block Jamuria, Dist Paschim Bardhaman under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000292/2022-2023 | 2449/RCD-I | 13/10/2022 | 180 | JOY HIND TUBEWELLS | 236.71 | 0 | 100
889 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Jamuria Rural-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000524/2022-2023 | 3137/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0 | 0
890 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of High Lift Pump House at Riverside H/W site under Augmentation of Jamuria Rural (Zone I & II) Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000573/2022-2023 | 3282/RCDI | 20/12/2022 | 90 | GLOBAL CONSTRUCTION | 31.24 | 0 | 90
891 | RCFA Division -I | RCFA Division I | Formal work order for augmentation of Jamuria (Rural)(zone-I) piped water supply scheme including FHTC & allied work within Jamuria Block under RCFA Div-I, PHE Dte.(Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000599/2022-2023 | 16/RCD I | 05/01/2023 | 30 | DIP CONSTRUCTION | 0 | 0 | 0
892 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Rising Main of Augmentation of Jamuria Rural (Zone-I & II) under RCFA Division-I PHE Dte (sl.no-14) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000773/2022-2023 | 805/RCD-I | 06/03/2023 | 60 | M/S MONDAL ENTERPRISE | 22.77 | 0 | 40
893 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | RTOR000005/2022-2023 | 2345/RCD-I | 28/09/2022 | 0 | Resource Division | 9.24 | 0 | 0
894 | RCFA Division -I | RCFA Division I | Arrangement of breakfast (Tea with snacks) for DWSM meeting held on 27.07.2024 at ADDA Conference hall, Asansol Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00935/2024-2025 | 240/24-25 | 23/08/2024 | 0 | BLESSING ENTERPRISE | 0.08 | 0 | 0
895 | RCFA Division -I | RCFA Division I | Arrangeme of tiffin packets for DWSM meeting held on 27.07.2024 at ADDA Conferene hall, Asansol, Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00936/2024-2025 | 241/24-25 | 23/08/2024 | 0 | BLESSING ENTERPRISE | 0.09 | 0 | 0
896 | RCFA Division -I | RCFA Division I | Installation of quick Heal Anti Viru for 3 years under RCFA Diivison-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00937/2024-2025 | 245/24-25 | 27/08/2024 | 0 | MUKHERJEE TRADERS | 0.09 | 0 | 0
897 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ A) | Assistant Engineer 2 | Junior Engineer | ORD/000299/2021-2022 | 2124/RCD-I | 29/11/2021 | 30 | A.K.CONSTRUCTION | 14.4 | 14.4 | 0
898 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ B) | Assistant Engineer 2 | Junior Engineer | ORD/000300/2021-2022 | 2125/RCD-I | 29/11/2021 | 30 | UNITED CONSTRUCTION | 14.36 | 14.36 | 0
899 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ C) | Assistant Engineer 2 | Junior Engineer | ORD/000301/2021-2022 | 2126/RCD-I | 29/11/2021 | 30 | DURGADAS MONDAL | 14.37 | 14.26 | 0
900 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ D) | Assistant Engineer 2 | Junior Engineer | ORD/000302/2021-2022 | 2127/RCD-I | 29/11/2021 | 30 | SIMA ENTERPRISE | 14.42 | 14.42 | 0
901 | RCFA Division -I | RCFA Division I | Acceptance cum work for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ E) | Assistant Engineer 2 | Junior Engineer | ORD/000303/2021-2022 | 2128/RCD-I | 29/11/2021 | 30 | M/S KALYANI ENTERPRISE | 14.45 | 14.44 | 0
902 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dakshin Khanda (Jl No. 36) Block ¿ Andal of RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. (Part ¿ F) | Assistant Engineer 2 | Junior Engineer | ORD/000304/2021-2022 | 2129/RCD-I | 29/11/2021 | 30 | M/S SUBHRADEEP | 16.51 | 16.51 | 0
903 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying and interconnection work of different dia HDPE pipe line unde Dakshin Khanda area Khandra Zone under RCFA Pt-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000489/2021-2022 | 118/RCD-I | 20/01/2022 | 30 | UNITED CONSTRUCTION | 13.96 | 10.91 | 0
904 | RCFA Division -I | RCFA Division I | Laying of 25 mm dia PVC pipe line at Ukhra Adarsha Hindi High School and installation of Street stand post and etc. allied works at Dakshin Khanda area under RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 | Junior Engineer | ORD/000510/2021-2022 | 224/RCD I | 01/02/2022 | 15 | UNITED CONSTRUCTION | 4.63 | 4.63 | 0
905 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Jamgram Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000526/2022-2023 | 3139/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
906 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 300 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Sarisatali Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000528/2022-2023 | 3141/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
907 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 350 cum capacity RCC Over Head Reservoir of Barabani Block for Augmentation of Panuria Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000529/2022-2023 | 3142/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
908 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 200 cum capacity RCC Over Head Reservoir of Jamuria Block for Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000531/2022-2023 | 3144/RCDI | 12/12/2022 | 7 | P.K TEWARY DRILLING CO. | 0.55 | 0.55 | 100
909 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000002/2021-2022 | 2281/RCD-I | 12/12/2021 | 0 | Resource Division | 10.17 | 0 | 0
910 | RCFA Division -I | RCFA Division I | Acceptance cum formal order for the work of Construction of boundary wall at OHR site approach road ,drain blower room and plantation and other allied works of Jemua W/S Scheme under Augmentation of Gopalpur W/s Scheme of Durgapur-Faridpur Block under DWSD, PHE Dte | Assistant Engineer 2 |  | ORD/001235/2023-2024 | 587/DWSD | 11/04/2023 | 45 | GITA CONSTRUCTION | 61.45 | 0 | 100
911 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional works for distribution main pipe line including Road Restoration under Augmentation of Jatgoria Water Supply Scheme Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000235/2024-2025 | 2607/RCD-I | 12/11/2024 | 90 | SUPERSKILL | 84.46 | 0 | 0
912 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Guard Room at Jatgoria Head Works Site under Augmentation of Jatgoria Water Supply Distribution System of Jatgoria W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000314/2024-2025 | 2730/RCD-I | 26/11/2024 | 90 | IMPULSE INTERNATIONAL | 5.53 | 0 | 40
913 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for balance work for Construction of site office at Panagarh of RCFA Division-I PHE Dte. under Augmentation of Jatgoria W/S Scheme JJm Fund. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000911/2023-2024 | 211/RCD-I | 29/01/2024 | 60 | BASANTI TRADERS | 32.98 | 0 | 100
914 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Laying & pushing of 600 mm dia RCC hume pipe (NP3) by adopting trench less technology (e.g. Jack Pushing Method) MS water carrier pipe and other allied works under command area of Tetikhola (Part-E) under Tetikhola Piped Water Supply Scheme, Block Durgapur-Faridpur, Dist-Paschim Bardhaman | Assistant Engineer-II | Junior Engineer-5 | ORD/001141/2023-2024 | 940/RCD-I | 15/03/2024 | 15 | TARA CONSTRUCTION | 9.51 | 0 | 100
915 | RCFA Division -I | RCFA Division I | Restoration and repairing work form Ch. 6.889 km to Ch 12.7 mm km of Chinchuria-Bhuri road under Asansol Division, PWD for laying pipe line under JJM | Assistant Engineer 2 |  | BILL/00464/2023-2024 | 236/23-24 | 29/08/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 68.17 | 0 | 0
916 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14A) | Assistant Engineer 2 |  | ORD/000027/2023-2024 | 1617/RCD I | 25/04/2023 | 180 | KONAR CONSTRUCTION | 365.88 | 65.47 | 35
917 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (Zone-14A) with Construction of 1250 cum capacity RCC OHR with staging height including Boundary Walls with gates and land Development, Drain and internal pathway at OHR site under Jamuria Block, District Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000102/2023-2024 | 1842/RCD-I | 31/05/2023 | 365 | A. CONSTRUCTION CO. | 277.09 | 87.51 | 40
918 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Majiara (250 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000542/2023-2024 | 3020/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 0 | 100
919 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 1250 cum capacity RCC Over Head Reservoir at (Zone-14A) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000554/2022-2023 | 3348/RCDI | 23/12/2022 | 782 | G. MITRA & ASSOCIATES | 0.5 | 0 | 100
920 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of in connection with Improvement of RCFA Part-I Water Supply Scheme within command area of Zone-V with LDS & FHTC work | Assistant Engineer 2 |  | ORD/000655/2023-2024 | 3427/RCD-1 | 24/11/2023 | 160 | MACHINO TECHNO | 58.12 | 0 | 100
921 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying MS pipe and allied works including adopting trench less technology (e.g. Jack Pushing Method etc) at Amnala irrigation Damp within command area of Zone-IX Part-I distribution system under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000672/2023-2024 | 3439/RCD-1 | 24/11/2023 | 15 | KHEPI MAA TRADERS | 22.98 | 0 | 100
922 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of different dia MS & HDPE Pipe line and mending works at Chanchani (Sansad-XII) of Ukhra area under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 |  | ORD/000771/2022-2023 | 397/RCDI | 30/01/2023 | 30 | M/S B.K. CONSTRUCTION | 11.94 | 0 | 100
923 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000031/2023-2024 | 2943/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
924 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-95 at Sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00117/2024-2025 | 50/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.58 | 0 | 0
925 | RCFA Division -I | RCFA Division I | Way leave / Track crossing proposal with application ID : ER-ASN-2024-WL-93 at sonachara under Augmentation of RCFA Part-II (Zone-13) under RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00118/2024-2025 | 51/24-25 | 20/05/2024 | 0 | EASTERN RAILWAY | 4.9 | 0 | 0
926 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of RCFA Part-II Piped Water Supply Scheme (zone-13) with Construction of 400 cum capacity RCC OHR with 20 mtr with staging height including Boundary Walls with gates and land Development, Drain ad internal pathway at OHR site under Jamuria Block, District- Paschim Bardhaman. | Assistant Engineer 2 |  | ORD/000100/2023-2024 | 1844/RCD-I | 31/05/2023 | 365 | JAYANTA DATTA | 129.69 | 0 | 65
927 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying & Pushing of 600 mm dia RCC (NP3) Hume Pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Charanpur Bus Stand and Faridpur of Barabani Block under Improvement of RCFA Part-I (Zone-11, Part-9) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000238/2023-2024 | 2231/RCD-I | 17/07/2023 | 30 | SOMNATH SAMANTA | 14.44 | 0 | 100
928 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Boundary Wall with gate (length 200 mtr.) land development with approach road including internal drain at H/W site & construction of guard room with toilet at Baliapur under Barabani Block in Improvement of RCFA Part-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000273/2023-2024 | 2330/RCD-I | 01/08/2023 | 90 | AMAR CONSTRUCTION | 31.48 | 0 | 100
929 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 6 (Six) nos 200 mm dia river bed tube wells including collecting main for river Damodar at Kalajharia of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000348/2023-2024 | 2482/RCD-I | 23/08/2023 | 30 | A. CONSTRUCTION CO. | 13.15 | 0 | 100
930 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 5 (Five) nos 200 mm dia river bed tube well in the river of Damodar at Kalajharia H/W site for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000489/2023-2024 | 2884/RCD-1 | 06/10/2023 | 45 | A CONSTRUCTION CO | 9.8 | 0 | 100
931 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Churulia (200 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000541/2023-2024 | 3019/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.92 | 0 | 100
932 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Kendra (750Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000545/2023-2024 | 3027/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.92 | 0 | 100
933 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 400 cum capacity RCC Over Head Reservoir at (Zone-13) of Pandabeswar Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000553/2022-2023 | 3347/RCDI | 23/12/2022 | 782 | MOYTEC | 0.46 | 0 | 100
934 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply and delivery of Centrifugal Pump Motor Set for Nimsha Village (High Lift) at Shemalya under AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) Block - Jamuria, Dist - Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000699/2023-2024 | 3502/RCD-1 | 30/11/2023 | 10 | M/S SWAPAN BANERJEE | 21.05 | 0 | 100
935 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of CWR (Clear Water Reservoir) of capacity 150 cum & allied works at Churulia under Augmentation of Churulia Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000705/2023-2024 | 3501/RCD-1 | 30/11/2023 | 90 | SIMA ENTERPRISE | 23.68 | 0 | 100
936 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Boundary wall including land development, approach road (Length-65 mtr) and drain (length-160 mtr) at Churulia OHR site of AUGMENTATION PWSS OF RCFA PART-II (ZONE-13) under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000706/2023-2024 | 3500/RCD-1 | 30/11/2023 | 30 | ASHA CONSTRUCTION | 28.18 | 0 | 100
937 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Room with toilet under Mangalpur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000922/2023-2024 | 300/RCD-I | 07/02/2024 | 15 | M/S SUBHRADEEP | 5.63 | 0 | 0
938 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of Boundary Wall at Khandra Bisswari OHR Site under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000923/2023-2024 | 299/RCD-I | 07/02/2024 | 45 | NATIONAL CONSTRUCTION | 11.15 | 0 | 100
939 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for distribution network & allied work at Ondal Block of RCFA Part-II (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000968/2023-2024 | 717/RCD-I | 01/03/2024 | 30 | M/S UNIT CONSTRUCTION | 92.71 | 0 | 100
940 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000030/2023-2024 | 2944/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
941 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work along with Construction of Guard room with Toilet for Construction of 150 cum capacity RCC OHR with 20 Mtr staging height RCC Over Head Reservoir Piped connection and cost of pipes, specials at Augmentation of PWSS of RCFA Part-II (Zone-14C) Piped Water Supply Scheme under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000054/2024-2025 | 1744/RCD-I | 18/07/2024 | 256 | NATIONAL CONSTRUCTION | 12.73 | 0 | 85
942 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Additional works of Pump House and other allied works at Damalia H/W Site for Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA, Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000094/2024-2025 | 2128/RCD-I | 27/08/2024 | 45 | B.T.M. CONCERN | 15.28 | 0 | 100
943 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance Work of Road Restoration In Connection With Improvement of RCFA _Part-I Water Supply Scheme for Amritnagar Zone-II of Augmentation PWSS of RCFA Part-II (Zone-14C) under RCFA Division PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000108/2024-2025 | 2130/RCD-I | 27/08/2024 | 30 | T M CONCRETE CREATION PVT.LTD | 48.27 | 0 | 100
944 | RCFA Division -I | RCFA Division I | Acceptence cum work order for Supplying aligning & laying 90 mm dia HDPE pipe line bye pass at Kallya, Dharashpur & Pahargara under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000401/2023-2024 | 2583/RCD-I | 07/09/2023 | 15 | ASHA CONSTRUCTION | 8.67 | 0 | 100
945 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g. Jack Pushing Method etc.) 03 nos. location at Haripur (Zone-14C) within Pandabeswar Block of Augmentation of PWSS RCFA Part-II (Zone-14C) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000537/2024-2025 | 140/RCD-I | 08/01/2025 | 90 | MD AAMIR KHAN | 85.12 | 0 | 60
946 | RCFA Division -I | RCFA Division I | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000589/2023-2024 | 2263/RCD-I | 19/07/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 0 | 60
947 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-14C) | Assistant Engineer 2 | Junior Engineer | ORD/000604/2022-2023 | 38/RCD-I | 11/01/2023 | 90 | PRADIP KUMAR DEB | 378.29 | 104.54 | 100
948 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work supplying, laying and pushing of 600 mm dia MS cashing pipe for Railway crossing by Jack Pushing method with 150 mm dia MS water carrier pipe in Rupnarayanpur in between 232/16-18 (SLS-RNPR) in Asansol Division under distribution network Improvement RCFA Part-I Water Supply Scheme within command area of Zone-VII (Part-E) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000659/2023-2024 | 3430/RCD-1 | 24/11/2023 | 45 | TARA CONSTRUCTION | 55.01 | 0 | 100
949 | RCFA Division -I | RCFA Division I | Continuation work order for Supplying, fitting, fixing and fabrication of sign board including printing and carriage to different area with necessary allied works in connection with Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001080/2023-2024 | 2382_A_RCD_I | 07/08/2023 | 20 | UNITED CONSTRUCTION | 17.51 | 0 | 100
950 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000033/2023-2024 | 2941/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
951 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Carriage DI pipe & specials from Searsole to Andal for rising main pipeline work at Andal block of Augmentation of sub surface water supply scheme for Andal Phase-II/B RCFA Division-I ,PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000180/2024-2025 | 2428/RCD-I | 26/09/2024 | 15 | MRITYUNJOY MUKHERJEE & CO. | 5.04 | 0 | 10
952 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work of the pushing 300 mm Dia MS rising main through 600 mm Dia pipe under Hinglow River for the work Of OCP based Kajora site of Augmentation of sub surface water supply scheme for Ondal Phase-II/B Under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000182/2024-2025 | 2430/RCD-I | 26/09/2024 | 60 | T M CONCRETE CREATION PVT.LTD | 48.99 | 0 | 100
953 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work of 600 mm Dia RCC pipe road crossing trenchless method jack pushing under NH-19 at Railway Kajora more to Andal Police station under OCP based KAJORA of Augmentation sub surface water supply scheme Ondal Phase-II/B under RCFA Division-I PHE, Dte | Assistant Engineer 2 | Junior Engineer | ORD/000183/2024-2025 | 2431/RCD-I | 26/09/2024 | 60 | T M CONCRETE CREATION PVT.LTD | 73.64 | 0 | 100
954 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for cutting hard rock at Kajora OHR Site for Ghanashyampur abandoned Kajora of Augmentation of sub surface water based PWSS for Andal Phase-II/B under RCFA Division-I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000190/2024-2025 | 2426/RCD-I | 26/09/2024 | 45 | MACHINO TECHNO | 14.71 | 0 | 100
955 | RCFA Division -I | RCFA Division I | Distribution network for Augmentation of Ondal (Phase-II/B) Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-1) | Assistant Engineer 2 | Junior Engineer | ORD/000331/2022-2023 | 2836/RCDI | 28/10/2022 | 885 | M/S KALYANI ENTERPRISE | 88.58 | 22.06 | 60
956 | RCFA Division -I | RCFA Division I | Supply & erection of Swajal Village Boards (102 nos) having M.S. Channel/Angle Posts & 1.5 mm thick M.S. synthetic enamel paint over a coat of red oxied primer including lettering complete at different places under Augmentation of sub surface water based for PWSS Ondal Phase-II/B under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000349/2024-2025 | Camp-02_Swajal/AE/24-25 | 03/10/2024 | 120 | SHARMA ENGINEERING WORKS | 20.55 | 0 | 50
957 | RCFA Division -I | RCFA Division I | Formal work order for construction of 450 cum capacity 20 mtr staging height RCC over head reservoir pipe connection and cost of pipes, specials at Andal village for Augmentation of Ondal Phase-II/B piped water supply scheme under RCFA Div-I, PHE Dte. in the District of Paschim Bardhaman. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2022-2023 | 18 /RCD I | 05/01/2023 | 9 | AMAR CONSTRUCTION | 129.3 | 116.37 | 100
958 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for augmentation of Ondal (Phase-II/B) piped Water Supply Scheme including FHTC & allied works within Ondal Block under RCFA Div-I, PHE Dte.(Part-3) | Assistant Engineer 2 | Junior Engineer | ORD/000600/2022-2023 | 15/RCDI | 05/01/2023 | 30 | DAS & CHAKRABORTY | 178.26 | 60.64 | 85
959 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of 200 mm dia rising main from Dignala OHR ste to proposed OHR site at Andal BL & LRO office for the proposed Augmentation work of Andal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000645/2022-2023 | 343/RCDI | 30/01/2023 | 822 | D.S.C. CONCERN | 7.65 | 0 | 65
960 | RCFA Division -I | RCFA Division I | Formal order for distribution network for augmentation of Ondal (Phase -II/B) piped Water Supply scheme including FHTC & allied work within ondal block under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000780/2022-2023 | 819/RCDI | 10/03/2023 | 30 | M/S MONI TRADERS | 108.27 | 34.49 | 60
961 | RCFA Division -I | RCFA Division I | Acceptance cum work order forConstruction of Boundary Wall with Gate at OHR Site (Length-160 mtrs) at Ondal Block for Augmentation of Ondal Phase- II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000879/2022-2023 | 1126/ RCD I | 24/03/2023 | 30 | AMAR CONSTRUCTION | 13.43 | 0 | 100
962 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Land development with approach road including internal drain at Head Works Site for Augmentation of Ondal Phase II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 04) | Assistant Engineer 2 | Junior Engineer | ORD/000888/2022-2023 | 1148/RCD-1 | 24/03/2023 | 30 | AMAR CONSTRUCTION | 6.5 | 0 | 100
963 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Guard room with toilet under Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 06) | Assistant Engineer 2 | Junior Engineer | ORD/000896/2022-2023 | 1150/RCD-1 | 24/03/2023 | 60 | SUBHADEEP DAS | 5.64 | 0 | 100
964 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at OHR Site for Augmentation of Ondal Phase-II/B Piped Water Supply Scheme under RCFA Division-I PHE Dte.(Sl No. 34) | Assistant Engineer 2 | Junior Engineer | ORD/000915/2022-2023 | 1177/RCD-1 | 24/03/2023 | 90 | SUBHADEEP DAS | 4.61 | 0 | 100
965 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000012/2023-2024 | 2206/RCD-I | 17/07/2023 | 0 | Resource Division | 24.19 | 0 | 0
966 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000016/2022-2023 | 2927/RCD-I | 17/11/2022 | 0 | Resource Division | 85.11 | 0 | 0
967 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000019/2022-2023 | 3125 | 09/12/2022 | 0 | Resource Division | 220.25 | 0 | 0
968 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Special repair and renovation of existing high lift Pump house, boundary Walls, Guard rooms, CWR, Switch Room etc, and allied works at H/W site of Ondal Phase-I Piped water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 03) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000008/2023-2024 | 1404 RCD I | 12/04/2023 | 60 | NATIONAL CONSTRUCTION | 13.75 | 6.55 | 100
969 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 5 (five) nos. 200 mm dia river bed tube well in river Damodar including laying of collecting main (HDPE & MS) of Augmentation of Ondal (Phase-I & Phase-II) piped Water Supply Scheme under RCFA Division-I PHE Dte.(SL NO 6) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000112/2022-2023 | 1287/RCD I | 03/06/2022 | 30 | DAS & CHAKRABORTY | 75.11 | 36.68 | 100
970 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000122/2022-2023 | 1608/RCD-I | 06/07/2022 | 1057 | AMAR CONSTRUCTION | 53.68 | 31.3 | 100
971 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000123/2022-2023 | 1609/RCD-I | 06/07/2022 | 90 | UMA ENTERPRISE | 67.49 | 54.82 | 100
972 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction additional length of Boundary wall including land development and Pathway at Khas Kajora OHR site at Andal Block for Augmentation of Ondal (Phase-I) Water Supply Scheme under RCFA Division-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000201/2024-2025 | 2467/RCD-I | 01/10/2024 | 45 | M/S UNIT CONSTRUCTION | 21.86 | 0 | 100
973 | RCFA Division -I | RCFA Division I | Acceptance cum work order Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-A) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000214/2023-2024 | 2222/RCD-I | 17/07/2023 | 30 | M/S SUBHRADEEP | 16.33 | 15.89 | 100
974 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work for collecting main of River bed tube well in Damodar River for Augmentation of Ondal (Phase-I) Water Supply Scheme under JJM at Andal H/W Site under Andal Block under RCFA Division-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000222/2024-2025 | 2543/RCD-I | 29/10/2024 | 30 | MAA ENTERPRISE | 10.75 | 0 | 100
975 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for Distribution Network for Augmentation of Ondal (Phase-I) Piped Water Supply Scheme (Part-C) Block Andal, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000233/2023-2024 | 2215/RCD-I | 17/07/2023 | 30 | M/S UNIT CONSTRUCTION | 30.8 | 0 | 100
976 | RCFA Division -I | RCFA Division I | Distribution Network for Augmentation of Ondal Phase-1 Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-C) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000297/2022-2023 | 2452/RCD-I | 13/10/2022 | 180 | M/S PIONEER CONSTRUCTION | 307.62 | 149.82 | 100
977 | RCFA Division -I | RCFA Division I | Acceptance cum work order for additional work cutting hard rock,boulder concrete and others work including filling earth, removal rubbish of Augmentation of Ondal Phase-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000307/2023-2024 | 2382/RCD-I | 07/08/2023 | 30 | M/S UNIT CONSTRUCTION | 89.75 | 0 | 100
978 | RCFA Division -I | RCFA Division I | Supply fitting fixing different dia valve and allied works in connection with laying distribution system including FHTC of Ondal Phase-I Water Supply Scheme (Part-B) under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000338/2023-2024 | 2465/RCD-I | 18/08/2023 | 30 | AMAR CONSTRUCTION | 0.62 | 0 | 100
979 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency Repairing of 50 sqmm x 4 core Al Armoured damaged cable line provided of FHTC Pipe line near Dignala OHR Site under Andal W/S Scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000480/2023-2024 | 2887/RCD-I | 06/10/2023 | 15 | T R ENTERPRISE | 3.72 | 3.72 | 100
980 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of rising main for Augmentation of Andal Phase-I (Dignala OHR) from Andal H/W Site under RCFA Div-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000505/2024-2025 | 131/RCD-I | 08/01/2025 | 45 | UNITED CONSTRUCTION | 16.84 | 0 | 100
981 | RCFA Division -I | RCFA Division I | Detailed Route Survey, Design Drawing & DPR Preparation for Ondal (Phase-I) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000535/2021-2022 | 501/RCD-I | 24/02/2022 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.91 | 3.91 | 0
982 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional for supplying, aligning and laying HDPE pipe, dismantling & concerting, supplying sluice valve and other allied works for Distribution Network for Augmentation of Ondal Phase-I Piped Water Supply Scheme including FHTC & allied work within Ondal Block under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000647/2023-2024 | 3424/RCD-1 | 24/11/2023 | 30 | M/S SUBHRADEEP | 34.89 | 0 | 100
983 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Emergency repairing and maintenance work of damaged RCC Elevated Reservoir including of capacity 700cum at Ramprasadpur of Augmentation of Ondal Phase-I W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | ORD/000763/2022-2023 | 390/RCD I | 30/01/2023 | 60 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 12.78 | 12.62 | 100
984 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | RTOR000006/2022-2023 | 2346/RCD-I | 28/09/2022 | 0 | Resource Division | 30.8 | 0 | 0
985 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-2 | RTOR000017/2022-2023 | 3132 | 09/12/2022 | 0 | Resource Division | 40.44 | 0 | 0
986 | RCFA Division -I | RCFA Division I | Supply of it periphersls under sub district laboratory | Assistant Engineer 2 | Junior Engineer | BILL/00211/2024-2025 | 92/24-25 | 13/06/2024 | 0 | SHARMA ENGINEERING WORKS | 0.02 | 0 | 0
987 | RCFA Division -I | RCFA Division I | Fuel and vehicle bill for Feb 2023 to June 23 | Assistant Engineer 2 | Junior Engineer | BILL/00511/2023-2024 | 234/23-24 | 04/09/2023 | 0 | NIRMALA TRADERS | 1.19 | 0 | 0
988 | RCFA Division -I | RCFA Division I | Spiral Binding | Assistant Engineer 2 | Junior Engineer | BILL/00610/2023-2024 | 185/23-24 | 10/08/2023 | 0 | MUKHERJEE TRADERS | 0.68 | 0 | 0
989 | RCFA Division -I | RCFA Division I | Transporting loading and unloading of jackets Banners etc for pump operator and valve operation at sites under JJM | Assistant Engineer 2 | Junior Engineer | BILL/00611/2023-2024 | 179/23-24 | 08/08/2023 | 0 | SHARMA ENGINEERING WORKS | 0.18 | 0 | 0
990 | RCFA Division -I | RCFA Division I | hire charges & fuel bill of Ranajit Auto | Assistant Engineer 2 | Junior Engineer | BILL/00612/2023-2024 | 220/23-24 | 22/08/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
991 | RCFA Division -I | RCFA Division I | fuel bill shyamal maji jyly 2023 | Assistant Engineer 2 | Junior Engineer | BILL/00613/2023-2024 | 220/23-24 | 24/08/2023 | 0 | RANAJIT AUTO | 0.16 | 0 | 0
992 | RCFA Division -I | RCFA Division I | Khepi Maa Traders | Assistant Engineer 2 | Junior Engineer | BILL/00614/2023-2024 | 215/23-24 | 22/08/2023 | 0 | KHEPI MAA TRADERS | 1.16 | 0 | 0
993 | RCFA Division -I | RCFA Division I | Hire charge and fuel bill for the month o June 2023 to August 2023 | Assistant Engineer 2 | Junior Engineer | BILL/00759/2023-2024 | 323/23-24 | 17/10/2023 | 0 | KHEPI MAA TRADERS | 1.19 | 0 | 0
994 | RCFA Division -I | RCFA Division I | Submissin of quarterly revised return for non salary return Bill no 7236 to 7339 | Assistant Engineer 2 | Junior Engineer | BILL/00774/2023-2024 | 367/23-24 | 10/11/2023 | 0 | SHRESTHA & ASSOCIATES | 0.36 | 0 | 0
995 | RCFA Division -I | RCFA Division I | Vehicle bill for 37 D 0482 Oct 2023 and nov 2023 | Assistant Engineer 2 | Junior Engineer | BILL/01144/2023-2024 | 429/23-24 | 20/12/2023 | 0 | SHYAMAL MAJI | 0.3 | 0 | 0
996 | RCFA Division -I | RCFA Division I | Fuel bill for WB 37 D 0482 for Oct 23 and Nov 23 | Assistant Engineer 2 | Junior Engineer | BILL/01145/2023-2024 | 430/23-24 | 20/12/2023 | 0 | RANAJIT AUTO | 0.29 | 0 | 0
997 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of 150 cum capacity 20 mtr staging height RCC Over Head Reservoir (pipe connection and cost of pipes, specials at Augmentation of Jamuria Rural (Zone-II) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 | Junior Engineer | ORD/000033/2023-2024 | 1631/RCD-I | 26/04/2023 | 366 | UNITED CONSTRUCTION | 69.15 | 20.75 | 100
998 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000211/2023-2024 | 2242/RCD-I | 17/07/2023 | 30 | MS KALYAN ENTERPRISE | 12.81 | 11.11 | 100
999 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Subhas Para & Chunari Para (Sansad-III) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000258/2021-2022 | 1867/RCD-I | 28/10/2021 | 30 | DAS & CHAKRABORTY | 18.1 | 18.09 | 0
1000 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 30 | DAWN CONSTRUCTION | 26.54 | 20.57 | 0
1001 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 30 | UMA ENTERPRISE | 21.3 | 6.08 | 0
1002 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Suri Para, Bisakhalakhi Tala (Sansad-VI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000261/2021-2022 | 1870/RCD-I | 28/10/2021 | 30 | JAYANTA DATTA | 18.06 | 18.06 | 0
1003 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Puratan Mushlim Para & Dhibarpara (Sansad-VII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000262/2021-2022 | 1871/RCD-I | 28/10/2021 | 30 | RUBY CONSTRUCTION | 15.67 | 15.67 | 0
1004 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Kankardanga (Sansad-VIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000263/2021-2022 | 1872/RCD-I | 28/10/2021 | 30 | MS KALYAN ENTERPRISE | 10.6 | 10.6 | 0
1005 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Dangal Para (Sansad-XI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000264/2021-2022 | 1873/RCD-I | 28/10/2021 | 30 | SNEHA ELECTRIC | 13.31 | 13.3 | 0
1006 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Mulimpara & Ruidaspara (Sansad-XIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000265/2021-2022 | 1874/RCD-I | 28/10/2021 | 30 | MD. JAWED KHAN | 18.16 | 18.15 | 0
1007 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Asthalpara (Sansad-XIV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000266/2021-2022 | 1875/RCD-I | 28/10/2021 | 30 | UNITED CONSTRUCTION | 13.32 | 13.32 | 0
1008 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Pathakpara (Sansad-XV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000267/2021-2022 | 1876/RCD-I | 28/10/2021 | 30 | B.T.M CONCERN | 15.25 | 15.25 | 0
1009 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Mukherjeepara & Khad Para (Sansad-XVII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000268/2021-2022 | 1877/RCD-I | 28/10/2021 | 30 | SIMA ENTERPRISE | 15.72 | 15.71 | 0
1010 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 30 | M/S K & KONAR CONSTRUCTION | 17.13 | 11.64 | 0
1011 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Sukho Para (Sansad-XX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000270/2021-2022 | 1879/RCD-I | 28/10/2021 | 30 | SOMNATH SAMANTA | 15.63 | 15.63 | 0
1012 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 30 | TARAPRASAD SARKAR | 14.37 | 2.26 | 100
1013 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia HDPE pipe line and allied works at Kankardanga Part (Sansad-VIII) at Ukhra area under Augmentation of RCFA Part-II (Zone-2A) PWSS under RCFA Division-I PHE Dte. (Sl No. 18) | Assistant Engineer 2 | Junior Engineer | ORD/000906/2022-2023 | 1162/RCD-I | 24/03/2023 | 15 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 1.42 | 1.29 | 100
1014 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia distribution pipe line at Sukopara (Part), Bauripara (Part) etc adjacent area at Ukhra Gram Panchayet (Sansad-XX) Augmentation of RCFA Part-II (Zone-2A) W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000939/2022-2023 | 1275/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 3.25 | 2.95 | 0
1015 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Providing FHTC of retrofitting at Kumardiha village (left out portion) of Kumardiha Mouza, Retrofitting of Madantore PWSS for providing FHTC under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000281/2024-2025 | 2619/RCD-I | 14/11/2024 | 20 | D.S.C. CONCERN | 6.57 | 0 | 0
1016 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and restoration of pipe line including supply of valve, construction of valve chamber, restoration of FHTC etc. at Bathan Bari, Sidhabari, Kalyaneswari and adjoining area Retrofitting of Madantore PWSS for providing FHTC within Jamuria Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000516/2024-2025 | 116/RCD-I | 08/01/2025 | 45 | DIP CONSTRUCTION | 13.76 | 0 | 100
1017 | RCFA Division -I | RCFA Division I | Acceptance cum work order for supplying, aligning, laying of PVC & HDPE Pipeline, Construction of Sluice valve chamber and supplying, aligning, laying of G.I Pipe under Retrofitting of Madantore PWSS scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000784/2022-2023 | 405/RCD-I | 30/01/2023 | 15 | M/S S.K. ENTERPRISE | 5.17 | 5.17 | 0
1018 | RCFA Division -I | RCFA Division I | Acceptance cum work order Sinking of 5 (Five nos. 200mm dia river bed tube wells including collecting main instead of defunct tube well at river Damodar (intake well Site ) Kalajharia Under Omprovement of RCFS part-II W/S Scheme under RCFA Division-I PHE Dte. (Part-G). | Assistant Engineer 2 | Junior Engineer | ORD/000789/2022-2023 | 402/RCDI | 30/01/2023 | 15 | DURGADAS MONDAL | 8.43 | 7.68 | 0
1019 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repairing & shifting work of DI pipes, repairing of 350 mm dia MS pipe and allied repairing at Madanpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000940/2022-2023 | 1278/ RCD I | 27/03/2023 | 15 | MD. JAWED KHAN | 4.78 | 4.69 | 100
1020 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000006/2023-2024 | 1857/RCD-I | 31/05/2023 | 0 | Resource Division | 1.76 | 0 | 0
1021 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000025/2021-2022 | 962/RCD-I | 07/06/2021 | 30 | ASHA CONSTRUCTION | 45.95 | 83.29 | 0
1022 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-IV), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000026/2021-2022 | 963/RCD-I | 07/06/2021 | 30 | DAS & CHAKRABORTY | 45.92 | 10.12 | 0
1023 | RCFA Division -I | RCFA Division I | Sinking of 4 (Four) nos river bed tube wells including collecting main at Runakuraghat for Flood damaged at river Ajoy under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl No. 14) | Assistant Engineer 1 | Junior Engineer | ORD/000034/2022-2023 | 1093/RCD I | 13/05/2022 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 4.99 | 4.73 | 100
1024 | RCFA Division -I | RCFA Division I | Additional work of supplying, aligning and laying of 160 mm dia HDPE pipe line for distribution line at Bolkundi village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 07) | Assistant Engineer 1 | Junior Engineer | ORD/000551/2021-2022 | 250/RCD-I | 01/02/2022 | 15 | DAS & CHAKRABORTY | 2.05 | 2.05 | 0
1025 | RCFA Division -I | RCFA Division I | Additional work for laying of different dia DI (K7) & HDPE pipe line with other allied work from Dabor OHR Zone-II (Lohat, Phulberiya, Patal, Sadhana, Madhaichak, Shyamdihi etc.) distribution Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) (Sl No. 08) | Assistant Engineer 1 | Junior Engineer | ORD/000552/2021-2022 | 251/RCD-I | 01/02/2022 | 15 | ASHA CONSTRUCTION | 2.18 | 1.96 | 0
1026 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of HDPE line (Parallel to main distribution) for Ghidoba village & Kushum Danali West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 09) | Assistant Engineer 1 | Junior Engineer | ORD/000553/2021-2022 | 252/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 4.98 | 4.71 | 0
1027 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba West side for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 10) | Assistant Engineer 1 | Junior Engineer | ORD/000554/2021-2022 | 253/RCD-I | 01/02/2022 | 20 | GITA CONSTRUCTION | 4.99 | 4.71 | 0
1028 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kushum Danali more towords Ghidoba East side under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 15) | Assistant Engineer 1 | Junior Engineer | ORD/000575/2021-2022 | 257/RCD-I | 01/02/2022 | 20 | B.T.M CONCERN | 4.98 | 4.75 | 0
1029 | RCFA Division -I | RCFA Division I | Extension of UPVC Pipe line at Uttarrampur and Part of Kalisanko including connection to different ICDS & FP Schools for providing FHTC under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl no 01) | Assistant Engineer 1 | Junior Engineer | ORD/000607/2021-2022 | 630/ RCD I | 09/03/2022 | 15 | KHEPI MAA TRADERS | 4.18 | 2.74 | 0
1030 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of HDPE line (parallel to main distribution) at Ghidoba, Kushum Danali and extension of pipe line at Ghiadoba village for providing FHTC under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte.(Sl no 07) | Assistant Engineer 1 | Junior Engineer | ORD/000613/2021-2022 | 636/RCD 1 | 09/03/2022 | 15 | DAS & CHAKRABORTY | 3.01 | 2.45 | 0
1031 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of UPVC line (parallel to main distribution) at Malladihi Hospital para towards Chayanpur for providing FHTC work under Chotkara Kanskuli water supply scheme under RCFA Division-I PHE Dte. (Sl no 09) | Assistant Engineer 1 | Junior Engineer | ORD/000615/2021-2022 | 638/RCD 1 | 09/03/2022 | 15 | MD AAMIR KHAN | 2.82 | 0 | 0
1032 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000013/2021-2022 | 950/RCD-I | 07/06/2021 | 30 | UMA ENTERPRISE | 30.02 | 30.7 | 0
1033 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Barabani Zone PWSS, Block- Barabani of Improvement of Barabani Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000014/2021-2022 | 951/RCD-I | 07/06/2021 | 30 | TARAPRASAD SARKAR | 30.12 | 24.47 | 0
1034 | RCFA Division -I | RCFA Division I | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission and its components at Barabani, Salanpur, Jamuria, Pandabeswar, Raniganj, Andal, Kansha & Durgapur Faridpur Block in the Districts of Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000718/2023-2024 | Camp_02_8_Nos_Block_AE_II | 26/09/2023 | 30 | MUKHERJEE TRADERS | 3.79 | 0 | 100
1035 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 4 nos 200 mm dia River bed tube wells in the river Ajoy at Bhaburia Head Work Site under Augmentation of ground water based water supply scheme for Basudha Piped Water Supply Scheme (JJM) under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer-II | Junior Engineer-3 | ORD/000191/2024-2025 | 2443/RCD-I | 30/09/2024 | 166 | MACHINO TECHNO | 12.11 | 0 | 100
1036 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Improvement & Overhauling of 2 nos Iron Removal Plant (pressure type), each capacity 50 cum/Hr at Basusha H/W site & at Krishnapur of Augmentation of Ground Water Based Water Supply Scheme for Basudha under RCFA W/S Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000251/2024-2025 | 2614/RCD-I | 13/11/2024 | 30 | RUPALI ELECTRONICS | 12.85 | 0 | 100
1037 | RCFA Division -I | Asansol Mechanical Division | Formal work order for sinking of 02(two) nos TW. FHTC,laying Rising main & laying distribution system(LDS) construction of boundary wall, pump house and restoration of road & and other allied works for Augmentation of ground water based W/S scheme for Basudha under RCFA Division-I, PHE Dte. Block-Kanksa, Dist- Paschim Bardhaman, | Assistant Engineer-II | Junior Engineer-3 | ORD/001015/2023-2024 | 559/RCD-I | 21/02/2024 | 130 | MRITYUNJOY MUKHERJEE & CO. | 209.86 | 0 | 90
1038 | RCFA Division -I | Asansol Mechanical Division | Shifting of office of the Executive Engineer, Durgapur W/s Division, PHE Dte, ADDA Administrative Building, EPIP Complex, Banskopa, Durgapur-12 to Nababhat, PHE Complex, Purba Bandhaman under Augmentation of Kataberia PWSS, Augmentation of Telipara under RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/001150/2023-2024 | 3516/RCD-I | 01/12/2023 | 15 | AMARANJALI CONSTRUCTION | 3.83 | 0 | 100
1039 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Additional works for distribution network for RBTW water based water supply scheme for Sarpi and its joining mouza (Part-C) at Arati village including FHTC & allied works AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II Durgapur-Faridpur Block under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000065/2024-2025 | 1795/RCD-I | 24/07/2024 | 45 | M/S BADAL GHOSH | 44.53 | 0 | 100
1040 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional pipe line from Madhaiganj to Jamdoba Adibasi Para including re-connection of FHTC under Augmentation of Amlajora Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000290/2024-2025 | 2629/RCD-I | 14/11/2024 | 90 | M/S BADAL GHOSH | 37.59 | 0 | 100
1041 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of laying distribution system, rising main, construction of 250 cum reservoir with 20 mtr staging height including soil investigation, construction of pump house (5.40 m x 3.60 m) with sanitary & W/S arrangement & construction of pump house (3.60 m x 3.00 m) for Amlajora W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000320/2025-2026 | 1424/RCD-I | 15/05/2025 | 90 | RANADHIR SINHA | 59.19 | 0 | 70
1042 | RCFA Division -I | Asansol Mechanical Division | Formal work order for Additional work for covering isolated area beyond the NH2 by creating a 2 (Two) nos separate zone under command area of Amlajora PWSS at the embankment of Durgapur Panagarh DVC branch canal situated in between DVC branch canal to Kol-Del Railway track and Biharpur Gram with sinking of 2 nos tube well 300 x 200 mm dia, Construction of Pump House cum/Switch room 5.4 m x 3.6 and laying of LDS with necessary inter connection including all others works of Amlajora PWSS under Augmentation of Amlajora Piped W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000390/2024-2025 | 3191/RCD-I | 23/12/2024 | 90 | RANADHIR SINHA | 156.64 | 0 | 40
1043 | RCFA Division -I | Asansol Mechanical Division | Addition work for Laying of HDPE pipeine and Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission at of Arra Mouza JL No 89 Under command area of AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | Assistant Engineer-II | Junior Engineer-3 | ORD/001040/2022-2023 | 326/DWSD | 20/02/2023 | 30 | BISHAL ENTERPRISE | 81.29 | 0 | 100
1044 | RCFA Division -I | Asansol Mechanical Division | Implememntation of Har Ghar Jal for Providing FHTC in connection with JJM for Pratapur, Nachan mouza ,Dhabani mouza (JL-48) underAUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR AMLAJORA PART - II, UNDER DURGAPUR W/S DIVISION , BLOCK : KANKSA, DISTRICT : PASCHIM BARDDHAMAN | Assistant Engineer-II | Junior Engineer-3 | ORD/001237/2023-2024 | 1074/DWSD | 12/07/2023 | 20 | MUKHERJEE ENTERPRISE | 18.4 | 0 | 0
1045 | RCFA Division -I | RCFA Division I | Restoration of Concrete road of Gopalpur & surrounding area under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000144/2024-2025 | Camp-02-Gopalpur-AE-2024- | 02/09/2024 | 10 | M/S CHANDI CHARAN ROY | 9.5 | 0 | 100
1046 | RCFA Division -I | RCFA Division I | Formal work order for Creating at 3 (Three) nos Separate Zone of Bamunara PWSS at Banskopa Toll Plaza to Rajbundh Railway Station, Rajbundh Choti, EPIP area of Banskopa mouza and Gopalpur mouza part (40%) situated between NH2 to Kolkata ¿ Delhi Railway track with sinking of 2 nos 300 x 200 mm dia, 01 no 150 x 150 mm dia Tubewell, Construction of Pump House cum Switch Room 5.40 x 3.60 mtr and LDS with necessary interconnection including all others works of Bamunara PWSS under Augmentation of Bamunara Piped Water Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000391/2024-2025 | 3190/RCD-I | 23/12/2024 | 180 | HANNAN BUILDERS PVT. LTD. | 216.57 | 0 | 45
1047 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Construction of 350 cum OHR at Arrah Sibtala, Block-Kanksa Dist - Paschim Bardhaman under Augmentation of Bamunara W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/000916/2023-2024 | 210/RCD-I | 29/01/2024 | 60 | AMARANJALI CONSTRUCTION | 39.01 | 0 | 65
1048 | RCFA Division -I | RCFA Division I | Formal work order for Acceptance order for Sinking of 02 (Two) no.s TW, FHTC, Laying Rising main & laying distribution system(LDS) construction of boundary wall, Pump House and restoration of road & other allied works for Augmentation of ground water based Bamunara PWSS under RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/001079/2023-2024 | 809/RCD-I | 14/03/2024 | 413 | RANJIB GHATAK | 91.37 | 0 | 90
1049 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction of CWR (200 cum capacity) and allied work at Madhaiganj OHR site under Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte | Assistant Engineer-II | Junior Engineer-3 | ORD/000023/2024-2025 | 1538/RCD-I | 19/06/2024 | 286 | B.T.M. CONCERN | 37.18 | 0 | 100
1050 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of Laying distribution system within distribution network for Rangamati of Augmentation of Ground Water Based Water Supply Scheme for Bistupur under Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000044/2024-2025 | 1645/RCD-I | 04/07/2024 | 45 | BASANTI TRADERS | 18.35 | 0 | 50
1051 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Separate distribution pipe with interconnection for Gopalpur Bazar (Left Side) of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000188/2025-2026 | 1363-RCD-I | 15/05/2025 | 78 | DAWN CONSTRUCTION | 40.06 | 0 | 100
1052 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Right including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based water supply scheme of Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000189/2025-2026 | 1362-RCD-I | 15/05/2025 | 60 | UNITED CONSTRUCTION | 61.57 | 0 | 100
1053 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Kuldiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000218/2024-2025 | 2551/RCD-I | 28/10/2024 | 240 | TARA CONSTRUCTION | 50.54 | 0 | 25
1054 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of Supplying, laying and aligning of HDPE distribution pipe line / rising main & allied works at Bistupur Head Works Site and Saraswatingunj command area of Bistupr PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000246/2025-2026 | 1468/RCD-I | 15/05/2025 | 170 | MRITYUNJOY MUKHERJEE & CO. | 79.35 | 0 | 70
1055 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional 1 no sinking of 300 x 200 mm dia& distribution pipe line with interconnection for GopalpurNamoparaAdibasipara at ChatallidangaGosaidanga, Dangapara, Dhoadanga for Augmentation of Ground Water Based Water Supply Scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000256/2025-2026 | 1478/RCD-I | 15/05/2025 | 60 | RANJIB GHATAK | 73.79 | 0 | 0
1056 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work of supplying laying and aligning of HDPE distribution pipe line & allied works including Function House Hold Tap Connection (FHTC) and re concoction at Ghatakdanga, Akandara and Saraswatigunj under command area of Bistupur under Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000266/2025-2026 | 1488/RCD-I | 15/05/2025 | 170 | MACHINO TECHNO | 44.86 | 0 | 50
1057 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Rakshitpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000293/2024-2025 | 2627/RCD-I | 14/11/2024 | 352 | MACHINO TECHNO | 70.46 | 0 | 20
1058 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Creating separate zone with pipe & additional FHTC including Water sources at Chua Adhibasipara under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000296/2024-2025 | 2639/RCD-I | 14/11/2024 | 352 | MRITYUNJOY MUKHERJEE & CO. | 20.41 | 0 | 50
1059 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for separate distribution pipe line with inter connection for Gopalpur Left including Paschim Para Bauripara General para of Gopalpur W/S Scheme for Augmentation of ground water based supply scheme for Bistupur under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000330/2025-2026 | 1516/RCD-I | 20/05/2025 | 60 | UNITED CONSTRUCTION | 70.8 | 0 | 100
1060 | RCFA Division -I | Asansol Mechanical Division | Construction of Separate Zone at Pathardiha with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000369/2024-2025 | 3097/RCD-I | 13/12/2024 | 313 | T M CONCRETE CREATION PVT.LTD | 45.89 | 0 | 40
1061 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum Work Order for Construction Boundary Wall at Bistupur H/W Site Pump House no 1 Tube well No. 1 under Augmentation of Bistupur Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000376/2024-2025 | 3104/RCD-I | 13/12/2024 | 60 | RANA ENTERPRISE | 15.43 | 0 | 0
1062 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Construction of Separate Zone at Keshabpur with Boundary wall, Pump House, Tubewell & other allied works of Augmentation of Bistupur PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000632/2024-2025 | 318/RCD-I | 12/02/2025 | 262 | MRITYUNJOY MUKHERJEE & CO. | 22.9 | 0 | 80
1063 | RCFA Division -I | Asansol Mechanical Division | Formal work order for creating separate zone for Amlajora, supplying, laying of HDPE distribution pipeline and other allied works at Sarpi, Repairing of existing cement concrete road restoration and other allied works (Part- A & B), construction of 5.40 X 3.6 meter switch room including additional concreting of exition dismantled road after extension of pipeline and retrofitting of existing distribution system under RBT Sarpi PWSS, Augmentation of Gopalpur & Bistupur PWSS and Amlajora PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001013/2023-2024 | 548/RCD-I | 20/02/2024 | 599 | HIRANMAY GHOSH | 200.38 | 0 | 40
1064 | RCFA Division -I | Asansol Mechanical Division | Formal Work Order for Construction of 450 cum OHR, Laying, Aligning of DI (K9) Rising main (22 km) Pipe line and interconnection between rising main with OHR 2 nos House at Madhaiganj and Bhaburia H/W site and other allied works of RBTW water based water supply scheme for Sharpi and its adjoining areas to accommodate FHTC under Augmentation of Bistupur PWSS in Durgapur-Faridpur Block, Dist-Paschim Bardhaman under Durgapur W/S Division PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001232/2023-2024 | 126_RCD_I | 16/01/2024 | 834 | GITA CONSTRUCTION | 305.57 | 0 | 100
1065 | RCFA Division -I | Asansol Mechanical Division | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part B under Augmentation of Bistupur Piped W/S Scheme. | Assistant Engineer-II | Junior Engineer-3 | ORD/001233/2023-2024 | 1292/DWSD | 07/08/2023 | 45 | PRAKRITI CONSTRUCTION | 6.02 | 0 | 100
1066 | RCFA Division -I | RCFA Division I | Restoration work for laying D.I pipeline along the Hard Shoulder from Ch. 3.67 Km to Ch. 8.50 kmp at left side and from ch. 3.00 to Ch. 4.50 kmp (ICDS more to Maira colliary ) at right side of Andal - Ukhra Road under Asansol Division, PWD in the district of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | BILL/00217/2024-2025 | 112/24-25 | 21/06/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL DIVISION, PWD | 20.4 | 0 | 0
1067 | RCFA Division -I | RCFA Division I | Formal work order for Augmentation of construction of 500 cum capacity 20 mtr. staging height RCC Over Head Reservoir (piped connection and cost of pipes, specials at Raniganj Block (Zone-17) for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/2012 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000095/2023-2024 | 1829/RDC-i | 29/05/2023 | 366 | SWATI CORPORATION | 131.06 | 39.32 | 100
1068 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 800 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc.) at Amdiha more towards Itapara village Surrounding area (Zone-IX) under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000283/2023-2024 | 2332/RCD-I | 01/08/2023 | 15 | SRI KRISHNA ENTERPRISE | 19.97 | 0 | 100
1069 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000465/2023-2024 | 2871/RCD-1 | 06/10/2023 | 90 | TARA CONSTRUCTION | 24.96 | 0 | 100
1070 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of concrete dismantling & re-concreting with other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000472/2023-2024 | 2876/RCD-1 | 06/10/2023 | 30 | TARA CONSTRUCTION | 76.37 | 0 | 100
1071 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000474/2023-2024 | 2863/RCD-I | 06/10/2023 | 573 | TARA CONSTRUCTION | 38.14 | 0 | 90
1072 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone-17) under RCFA Division-I PHE Dte. (Part-A). | Assistant Engineer 2 | Junior Engineer | ORD/000515/2023-2024 | 2866/RCD-I | 06/10/2023 | 30 | MACHINO TECHNO | 88.08 | 0 | 100
1073 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard room with toilet at Shyamla Over Head site under Augmentation of RCFA Part-II (Zone-17) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000521/2023-2024 | 2879/RCD-I | 06/10/2023 | 90 | G. CONSTRUCTION | 5.48 | 0 | 100
1074 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 500 cum capacity RCC Over Head Reservoir at (Zone-17) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000558/2022-2023 | 3352/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 100
1075 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Pump House at Damalia H/W site for Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000571/2022-2023 | 3280/RCDI | 20/12/2022 | 45 | B.T.M CONCERN | 30.19 | 0 | 70
1076 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing and providing FHTC painting of H/W site for Dhandardihi Piped water supply Scheme Block-Andal, Dist-Paschim Bardhaman under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000609/2023-2024 | 3369/RCD-1 | 21/11/2023 | 15 | MD. JAWED KHAN | 3.12 | 0 | 100
1077 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Repairing of UPVC pipe line supply fitting and fixing of valves and allied works under Dhandardihi water supply scheme under RCFA Division -I PHE Dte | Assistant Engineer 2 | Junior Engineer | ORD/000622/2023-2024 | 3375/RCD-I | 21/11/2023 | 15 | MD. JAWED KHAN | 3.61 | 0 | 100
1078 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard Room, extension of Boundary Wall, Land Development, approached road and allied works under Augmentation of RCFA Part-II (Zone-17) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000626/2023-2024 | 3416/RCD-1 | 24/11/2023 | 60 | DIP CONSTRUCTION | 25.93 | 0 | 100
1079 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 110 mm dia and 90 mm dia HDPE pipe line including chokage cleaning and other allied works of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000664/2023-2024 | 3433/RCD-1 | 24/11/2023 | 30 | JAI MAHARAJ ENTERPRISE | 6.6 | 0 | 100
1080 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000815/2022-2023 | 997/RCDI | 22/03/2023 | 855 | TARA CONSTRUCTION | 342.78 | 59.15 | 75
1081 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-17) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman (Sl No. 30) | Assistant Engineer 2 | Junior Engineer | ORD/000910/2022-2023 | 1174/RCD I | 24/03/2023 | 739 | N.R. CONSTRUCTION | 4.61 | 0 | 100
1082 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/000940/2023-2024 | 488/RCD-I | 12/02/2024 | 45 | TARA CONSTRUCTION | 9.16 | 0 | 100
1083 | RCFA Division -I | RCFA Division I | Additional work for supply and delivery of CI/DI specials including hard rock cutting, restoration of drain and supply of MS pipe (500 mm dia) and allied works within Zone-I Part-B under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000960/2023-2024 | 464/RCD-1 | 12/02/2024 | 20 | SWATI CORPORATION | 18.11 | 0 | 100
1084 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works for construction of boundary wall with gate at OHR site (length 150 mtr) and land development with approach road including internal drain at Head Work Site for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-17) | Assistant Engineer 2 | Junior Engineer | ORD/001136/2023-2024 | 934/RCD-I | 15/03/2024 | 15 | SWATI CORPORATION | 20.16 | 0 | 100
1085 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000036/2023-2024 | 2938/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1086 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-A). | Assistant Engineer 2 |  | ORD/000041/2023-2024 | 1604/RCD I | 25/04/2023 | 180 | PINKI ENTERPRISE | 115.02 | 28.43 | 85
1087 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-D) (Sl No. 14) | Assistant Engineer 2 |  | ORD/000054/2023-2024 | 1707/ RCD I | 03/05/2023 | 90 | MD. JAWED KHAN | 69.87 | 17.89 | 80
1088 | RCFA Division -I | RCFA Division I | Laying of distribution system at Khottamdihi village including FHTC works under Kendra Khottamdihi W/S Scheme under RCFA Div-I, PHE dte. | Assistant Engineer 2 |  | ORD/000399/2022-2023 | 2643/RCDI | 28/10/2022 | 225 | JAYANTA DATTA | 100 | 0 | 100
1089 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of ASTA (1135 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000531/2023-2024 | 3021/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 0 | 100
1090 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Dendua(1135Cum) and ancillary structure sconducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000532/2023-2024 | 3014/RCD-I | 16/10/2023 | 15 | SIRCON ENGINEERING SERVICES | 4.98 | 0 | 100
1091 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Health assessment of existing OHR of Searsole (900 Cum) and ancillary structures conducting Non-Destructive Test and thorough visual observation under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000538/2023-2024 | 3024/RCD-1 | 16/10/2023 | 15 | RISHAN ENGINEERING CONSULTANCY | 4.95 | 0 | 100
1092 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction for Additional works of MS manifold including interconnection in beetween CWR and pump house and etc allied works at Samlya H/W under Samlya W/S Scheme under RCFA Division-I PHe Dte. | Assistant Engineer 2 |  | ORD/000571/2023-2024 | 2869/RCD-I | 06/10/2023 | 15 | MAA ENTERPRISE | 6.41 | 0 | 100
1093 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of Chlorine Room of Size (4.50 x 3.50 m) at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000657/2022-2023 | 356/RCDI | 30/01/2023 | 15 | DAS & SARKAR ENTERPRISE | 4.6 | 0 | 100
1094 | RCFA Division -I | RCFA Division I | Continuation work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. under JJM (RCFA Part-II) | Assistant Engineer 2 |  | ORD/000825/2022-2023 | 801/RCD-I | 06/03/2023 | 30 | MACHINO TECHNO | 67.77 | 65.09 | 100
1095 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-C) | Assistant Engineer 2 |  | ORD/000868/2022-2023 | 1118/RCD-I | 23/03/2023 | 90 | UNITED CONSTRUCTION | 81.57 | 50.21 | 90
1096 | RCFA Division -I | RCFA Division I | Acceptance cum work order Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-E) | Assistant Engineer 2 |  | ORD/000869/2022-2023 | 1120/RCD-I | 23/03/2023 | 800 | JAYANTA DATTA | 91.65 | 0 | 70
1097 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme including FHTC & allied work under RCFA Division-I PHE Dte. (Zone-4A) (Part-B)(Sl No. 12) | Assistant Engineer 2 |  | ORD/000870/2022-2023 | 1116/RCD-I | 23/03/2023 | 90 | BABA LOKNATH ENTERPRISE | 71.02 | 31.1 | 80
1098 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Store Room at Head Works Site for (Zone-4A) of Pandabeswar and Andal Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 29) | Assistant Engineer 2 |  | ORD/000902/2022-2023 | 1173/RCD I | 24/03/2023 | 90 | RANJIB GHATAK | 4.61 | 0 | 0
1099 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Chlorine Room (Size 4.1 m x 3.5 m out to out) at Shankarpur OHR Site for Augmentation of RCFA part-II (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 27) | Assistant Engineer 2 |  | ORD/000904/2022-2023 | 1171/RCD I | 24/03/2023 | 277 | RANJIB GHATAK | 4.61 | 0 | 100
1100 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Approach road and others necessary allied works at Front Gate to village road for Shankarpur OHR Site (Zone-4A and 4B) Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No 28) | Assistant Engineer 2 |  | ORD/000908/2022-2023 | 1172/RCD I | 24/03/2023 | 60 | RANJIB GHATAK | 3.78 | 0 | 100
1101 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying MS pipe and allied works including adopting trench less technology b(e.g. Jack Pushing Method etc) of 02 (Two) nos location at Sankarpur (near Footbal ground ) and Shankarpur GP office under Augmentation of RCFA Part-II (Zone-4A) PWSS (Part-C ) under RCFA Division-I PHE Dte. (2nd Call) | Assistant Engineer 2 |  | ORD/000913/2023-2024 | 213/RCD-I | 29/01/2024 | 15 | UNITED CONSTRUCTION | 13.08 | 0 | 100
1102 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Allied work for bridge, road and other allied work at Amritnagar Zone-I under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000965/2023-2024 | 508/RCD-I | 12/02/2024 | 30 | MACHINO TECHNO | 81.93 | 0 | 100
1103 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000014/2023-2024 | 2934/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1104 | RCFA Division -I | RCFA Division I | Formal work order for Distribution Network Including FHTC & allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme Under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000066/2023-2024 | 1763/RCD I | 16/05/2023 | 962 | MACHINO TECHNO | 541.2 | 167.23 | 30
1105 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & Pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology at 4 nos location (Dabor more, Achhra Road, Rupnarayanpur Phari, Rupnarayanpur Chittaranjan Road) of Salanpur Block under Improvement of RCFA Part-I (Zone-7, Part-F) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000289/2023-2024 | 2338/RCD-I | 01/08/2023 | 15 | GITA CONSTRUCTION | 67.97 | 0 | 100
1106 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 600 mm dia MS Pipes under the Railway track by jack pushing technology at different spots and pushing different dia MS Pipes through 600 mm dia MS pipes in connection with the work of estimates for the laying distribution system for Amritnagar Zone-II under Augmentation of RCFA Part-II (Zone- under RCFA Division-I PHE Dte. (Part-B). | Assistant Engineer 2 | Junior Engineer | ORD/000516/2023-2024 | 2867/RCD-I | 06/10/2023 | 15 | MACHINO TECHNO | 41.98 | 0 | 100
1107 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Guard room with toilet at Dendua under Salanpur Block for Improvement of RCFA Part-I Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000598/2023-2024 | 3280/RCD-I | 08/11/2023 | 90 | D.S.ENTERPRISE | 7.61 | 0 | 100
1108 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC (NP3) Hume pipe by adopting trench less technology (e.g. Jack Pushing Method etc) at Srirampur Workshop road near Railway Workshop under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000791/2023-2024 | 3437_RCD_I | 24/11/2023 | 15 | M/S UNIT CONSTRUCTION | 9.31 | 0 | 0
1109 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Supply fitting and allining of 250 mm dia non return valve and 80 mm dia air valve and etc allied works at Bilpahari OCP area on distribution main under Kendra Khottamdihi water supply scheme under RCFA Div-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000797/2023-2024 | 2896_RCD-I | 06/10/2023 | 30 | M/S UNIT CONSTRUCTION | 2.42 | 0 | 0
1110 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Allied work Balance Work of Road restoration in connection with Distribution Network including FHTC and allied work at Ondal Block of RCFA Part-II (Zone-6) Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000946/2023-2024 | 454/RCD-1 | 12/02/2024 | 45 | MRITYUNJOY MUKHERJEE & CO. | 45.34 | 0 | 50
1111 | RCFA Division -I | RCFA Division I | Formal work order for construction of 600 cum capacity 20 mtrs staging height RCC Over Reservoir (Pipe connection and cost of pipes, specials at Ondal Block (Zone-6) for Augmentation of RCFA Part_II Piped Water Supply Scheme including Soil investigation and Chlorine Room (4.50 X 3.50 m) under RCFA Division-I PHE Dte. In District Paschim Bardhaman.(2nd Call). | Assistant Engineer 2 | Junior Engineer | ORD/001016/2023-2024 | 558/RCD-I | 21/02/2024 | 366 | MRITYUNJOY MUKHERJEE & CO. | 151 | 0 | 42
1112 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying and Pushing by adopting trench less technology(e.g.Jack Pushing Method etc) at Kunustoria for Distribution Network for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I.PHE Dte.(Zone-7) Segment-5 | Assistant Engineer 2 | Junior Engineer | ORD/001165/2023-2024 | 1017/RCD-I | 16/03/2024 | 15 | B.T.M. CONCERN | 22.8 | 0 | 100
1113 | RCFA Division -I | RCFA Division I | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA div-I PHE Dte (w.e.f 01.08.2023 to 31.01.2024) | Assistant Engineer 2 | Junior Engineer | ORD/001166/2023-2024 | 2319_RCD-I | 31/07/2023 | 184 | M/S KALYANI ENTERPRISE | 4.49 | 0 | 0
1114 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for laying distribution pipe line of providing FHTC at Harispur Taldanga under Madanpur Gram Panchayat of Andal Block of JJM work AUGMENTATION PWSS OF RCFA PART-II (ZONE-6) under RCFA Division-I.PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001169/2023-2024 | 1008/RCD-I | 16/03/2024 | 15 | M/S MONDAL ENTERPRISE | 5.56 | 0 | 100
1115 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000020/2023-2024 | 2952/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1116 | RCFA Division -I | Asansol Mechanical Division | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. | Assistant Engineer-II | Junior Engineer-3 | BILL/00105/2024-2025 | 53/24-25 | 20/05/2024 | 0 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.8 | 0 | 0
1117 | RCFA Division -I | Asansol Mechanical Division | Proposal for diversion of forest land for consytruction of OHR Capacity 350 cum of Augmentation of Roopganj Piped water supply scheme (JJM Work) under Durgapur W/S Division, PHE Directoreate - Demand note for payment of NPV, CA, Boundary demarcation witll pillar fencing etc. :- Cost of Boundary demarcation with pillar | Assistant Engineer-II | Junior Engineer-3 | BILL/00146/2024-2025 | 66/24-25 | 28/05/2024 | 0 | DIVISIONAL FOREST OFFICER, BURDWAN DIVISION | 0.3 | 0 | 0
1118 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of Rising Main from Tube Well to OHR at Roopganj Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000045/2024-2025 | 1646/RCD-I | 04/07/2024 | 242 | M/S KALYANI ENTERPRISE | 12.36 | 0 | 100
1119 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Sinking of 2 nos of 300 x 200 mm dia tube well 210 mtr deep by D.R. Rig method using UPVC pipe (CD) and UPVC deep well screen (RDS) at Bandra village and Roopganj of Augmentation of Roopganj PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/000456/2025-2026 | 2009/RCD-I | 11/07/2025 | 20 | M/S KALYANI ENTERPRISE | 27.78 | 0 | 100
1120 | RCFA Division -I | Asansol Mechanical Division | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at kanchanpur of kanksa block under Augmentation of Roopganj Piped W/S Scheme under DWSD PHE Dte. | Assistant Engineer-II | Junior Engineer-3 | ORD/001227/2023-2024 | 1293/DWSD | 07/08/2023 | 45 | MAJI DEVELOPERS | 6.09 | 0 | 100
1121 | RCFA Division -I | Asansol Mechanical Division | Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Kanksa Zone II/Part C under Augmentation of Roopganj Piped W/S Scheme. | Assistant Engineer-II | Junior Engineer-3 | ORD/001234/2023-2024 | 1277_DWSD | 07/08/2023 | 45 | PRADIP CHOUDHARY | 5.83 | 0 | 100
1122 | RCFA Division -I | RCFA Division I | Arrangement of brakfast and lunch box, etc. for DWSM meeting held on 22.06.2024 at ADDA conference hall | Assistant Engineer 2 |  | BILL/00256/2024-2025 | 121/24-25 | 03/07/2024 | 0 | MUKHERJEE TRADERS | 0.28 | 0 | 0
1123 | RCFA Division -I | RCFA Division I | Fuel bill of Ranajit auto against vehicle no WB 37D 0482 for the month of May | Assistant Engineer 2 |  | BILL/00265/2023-2024 | 116/1/23-24 | 03/07/2023 | 0 | RANAJIT AUTO | 0.23 | 0 | 0
1124 | RCFA Division -I | RCFA Division I |  | Assistant Engineer 2 |  | BILL/00327/2023-2024 | 149/1/23-24 | 21/07/2023 | 0 | RANAJIT AUTO | 0.17 | 0 | 0
1125 | RCFA Division -I | RCFA Division I | April 2023 | Assistant Engineer 2 |  | BILL/00559/2023-2024 | 77/23-24 | 06/06/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
1126 | RCFA Division -I | RCFA Division I | fuel bill april 2023 shyamal maji | Assistant Engineer 2 |  | BILL/00560/2023-2024 | 77/1/23-24 | 06/06/2023 | 0 | RANAJIT AUTO | 0.2 | 0 | 0
1127 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Bhaluka & Sonepur Bazari under Kendra Khottamdih Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | BILL/00619/2023-2024 | 204/23-24 | 18/08/2023 | 0 | MACHINO TECHNO | 19.87 | 0 | 0
1128 | RCFA Division -I | RCFA Division I | Hire charge and fuel bill for the month of July 2023 to September 2023 | Assistant Engineer 2 |  | BILL/00754/2023-2024 | 339/23-24 | 17/10/2023 | 0 | SHYAMAL MAJI | 0.15 | 0 | 0
1129 | RCFA Division -I | RCFA Division I | Fuel bill for WB37D0482 for the month of Sept 2023 | Assistant Engineer 2 |  | BILL/00755/2023-2024 | 339/1/23-24 | 17/10/2023 | 0 | RANAJIT AUTO | 0.22 | 0 | 0
1130 | RCFA Division -I | RCFA Division I | Hire charges and fuel bill for the month of July 2023 to Sept 2023 | Assistant Engineer 2 |  | BILL/00756/2023-2024 | 338/23-24 | 17/10/2023 | 0 | NIRMALA TRADERS | 1.2 | 0 | 0
1131 | RCFA Division -I | RCFA Division I | Hire charges and fuel bill for Executive Engineer RCFA Division-I PHE Dte | Assistant Engineer 2 |  | BILL/00823/2023-2024 | 291/23-24 | 10/10/2023 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
1132 | RCFA Division -I | RCFA Division I | Acceptance cum work order Repairing laying PVC pipe line and allied work at Asansol District Hospital under RCFA Division-I PHE Dte. (Sl. No. 34) | Assistant Engineer 2 |  | ORD/000060/2023-2024 | 1751/RCD I | 12/05/2023 | 15 | UNITED CONSTRUCTION | 3.23 | 3.23 | 0
1133 | RCFA Division -I | RCFA Division I | Construction of guard wall on emergency basis near Kalyaneswari I.B. gate under Retrofitting Bahula mouza RCFA Division-I PHE Dte. (Sl No. 12) | Assistant Engineer 2 |  | ORD/000064/2022-2023 | 1111/RCDI | 13/05/2022 | 30 | R B ENTERPRISE | 4.7 | 4.47 | 100
1134 | RCFA Division -I | RCFA Division I | Emergency basis construction of culvert near Kalyaneswari I.B. gate under Retrofitting Bahula mouza W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 17) | Assistant Engineer 2 |  | ORD/000069/2022-2023 | 1116/RCDI | 13/05/2022 | 45 | R B ENTERPRISE | 4.93 | 4.92 | 100
1135 | RCFA Division -I | RCFA Division I | Hiring of Maxi Cab (Non Air-conditioned)(Bharat stage-III/BS-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine. as when required basis for supervision of FHTC related works under JJM) of RCFA Div-I, PHE Dte Govt, of West Bengal (w.e.f 16.08.2022 to 15.08.2023) | Assistant Engineer 2 |  | ORD/000204/2022-2023 | 1907/RCDI | 12/08/2022 | 12 | PRAMIT CHATTERJEE | 1.8 | 0.79 | 0
1136 | RCFA Division -I | RCFA Division I | Supply of Computer and accessories for Office use under RCFA Division-I PHE Dte. District - Paschim Bardhaman | Assistant Engineer 2 |  | ORD/000309/2023-2024 | 2040/RCD-I | 30/06/2023 | 7 | MUKHERJEE TRADERS | 0.86 | 0.86 | 100
1137 | RCFA Division -I | RCFA Division I | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-A) | Assistant Engineer 2 |  | ORD/000316/2021-2022 | 2143/RCD-I | 29/11/2021 | 120 | GITA CONSTRUCTION | 81.14 | 61.82 | 0
1138 | RCFA Division -I | RCFA Division I | Formal work order for Providing FHTC through Retrofitting at Bahula (CT) (JL no. 30, Block - Pandabeswar) of RCFA Pt-II W/S Scheme under RCFA Division-I, PHE Dte. (Part-B) | Assistant Engineer 2 |  | ORD/000317/2021-2022 | 2144/RCD-I | 29/11/2021 | 120 | MD AAMIR KHAN | 81 | 59.89 | 0
1139 | RCFA Division -I | RCFA Division I | Acceptance cum work order Cleaning compound premises of Ballavpur Hospital & Unionpara Head Works Site under RCFA Part-II W/S Scheme under RCFA Div-I PHE Dte. | Assistant Engineer 2 |  | ORD/000330/2023-2024 | 2452/RCD-I | 18/08/2023 | 15 | SWATI CORPORATION | 0.97 | 0.96 | 100
1140 | RCFA Division -I | RCFA Division I | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at Health World Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000440/2023-2024 | Camp-02-Health-World-Hosp | 27/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.77 | 7.65 | 100
1141 | RCFA Division -I | RCFA Division I | Emergent sinking of one no 200 X 165 mm dia rig bore tube well at ESI Hospital, Asansole, Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000441/2023-2024 | Camp-2-ESI-Hospital-AE-II | 27/09/2023 | 3 | M/S CHANDI CHARAN ROY | 7.84 | 7.68 | 100
1142 | RCFA Division -I | RCFA Division I | Cleaning compound premises, painting works and preparing approched road with sand and stone dust and other allied works at Kalyaneswari Inspection bunglow under Bahual Retrofitting under RCFA Division-I PHE Dte. (Sl No. 13) | Assistant Engineer 2 |  | ORD/000511/2021-2022 | 225/RCDI | 01/02/2022 | 7 | JYOGOMAYA ENTERPRISE | 1.81 | 1.81 | 100
1143 | RCFA Division -I | RCFA Division I | Hiring of SUV (A.C) (Non-Air conditioned) Bharat Stage-IV/BS-IV purchased on or after 01.01.2022 with Diesel/LPG/CNG Engine. For the office Use of the Deputy Superintending Engineer Engineer, RCFA W/S Circle, PHE Dte Govt. of West Bengal (w.e.f 01.02.2023 to 31.07.2023) | Assistant Engineer 2 |  | ORD/000872/2022-2023 | 455/RCDI | 31/01/2023 | 181 | SHYAMAL MAJI | 0.9 | 0.3 | 80
1144 | RCFA Division -I | RCFA Division I | Acceptance cum work order Supply and installation of sluice valve, shifting of household connection instead of old AC pipe line to distribution branch and etc allied works at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000926/2022-2023 | 1258/ RCD I | 27/03/2023 | 15 | SOMNATH SAMANTA | 2.5 | 2.49 | 0
1145 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of 90 mm dia HDPE pipe line and etc allied works at Baidyanathpur Namopara, Bouripara under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000929/2022-2023 | 1264/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 2.72 | 2.59 | 0
1146 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying of different dia distribution pipe line at Baidyanathpur Namopara, Bouripara and adjacent area under Baidyanathpur W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 |  | ORD/000942/2022-2023 | 1276/RCD-I | 27/03/2023 | 15 | SOMNATH SAMANTA | 3.61 | 3.48 | 0
1147 | RCFA Division -I | RCFA Division I | Continuation work order for Probable Office expenditure of office of the Executive Engineer to meet up day to day various office & site expenses under RCFA Div-I PHE Dte (w.e.f 01.02.2023 to 31.07.2023) | Assistant Engineer 2 |  | ORD/000969/2022-2023 | 3439/RCD-I | 30/12/2022 | 182 | M/S KALYANI ENTERPRISE | 4.51 | 4.51 | 100
1148 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 |  | RTOR000001/2021-2022 | 2280/RCD-I | 12/12/2021 | 0 | Resource Division | 20.23 | 0 | 0
1149 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-A] | Assistant Engineer 1 | Junior Engineer | ORD/000022/2021-2022 | 959/RCD-I | 07/06/2021 | 30 | JAYANTA DATTA | 23.01 | 4.02 | 0
1150 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-B] | Assistant Engineer 1 | Junior Engineer | ORD/000023/2021-2022 | 960/RCD-I | 07/06/2021 | 30 | M/S MONDAL ENTERPRISE | 23 | 40.38 | 0
1151 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-D] | Assistant Engineer 1 | Junior Engineer | ORD/000024/2021-2022 | 961/RCD-I | 07/06/2021 | 30 | S. CHAKRABORTY & CO. | 22.97 | 45.64 | 0
1152 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chotkara Kanskuli PWSS (Zone-III), Block- Salanpur & Barabani of Chotkara- Kanskuli Water supply scheme under RCFA Division-I, P.H.E. Dte. [Part-C] (3rd Call) | Assistant Engineer 1 | Junior Engineer | ORD/000062/2021-2022 | 1148/RCD-I | 22/07/2021 | 30 | GITA CONSTRUCTION | 22.58 | 45.26 | 0
1153 | RCFA Division -I | RCFA Division I | Formal Work Order for Pipe line crossing by adopting trench less technology (e.g. Jack Pushing Method etc) near Kanskuli DAM for dedicated pipe line towards Kanskuli village under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1 | Junior Engineer | ORD/000078/2023-2024 | 1772/RCD-I | 18/05/2023 | 15 | SRI KRISHNA ENTERPRISE | 4.37 | 4.37 | 0
1154 | RCFA Division -I | RCFA Division I | Emergency for providing balance FHTC through retrofitting at Shamdi G.P. area and Chayanpur and adjacent villages under Chotkara Kanskuli W/S Scheme under RCFA Division-I PHE Dte.(Sl no 03) | Assistant Engineer 1 | Junior Engineer | ORD/000211/2022-2023 | 1980/RCD I | 24/08/2022 | 15 | KHEPI MAA TRADERS | 4.54 | 4.04 | 0
1155 | RCFA Division -I | RCFA Division I | Supplying, aligning and laying of 90 mm dia HDPE pipe line (Parallel to main distribution) at village Kirtansala (part) and Dharaspur village for providing FHTC work under Chotkara Kanskuli Water Supply Scheme under RCFA Division-I PHE Dte. (Sl 11) | Assistant Engineer 1 | Junior Engineer | ORD/000572/2021-2022 | 254/RCD-I | 01/02/2022 | 20 | DIP CONSTRUCTION | 4.95 | 4.76 | 0
1156 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Balance work of distribution pipe line of Kanska Zone-II (Part-B)from OHR to Pathanpara under Augmentation of Birudiha W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | ORD/001178/2023-2024 | 1019/RCD-I | 16/03/2024 | 45 | MD AAMIR KHAN | 35.4 | 0 | 100
1157 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 1,Assistant Engineer-II | Junior Engineer 15,Junior Engineer-3 | RTOR000043/2023-2024 | 134/RCD-I | 18/01/2024 | 0 | Resource Division | 130.63 | 0 | 0
1158 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Boundary Wall at OCP Based Treatment Plant at Kajora under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000036/2024-2025 | 1591/RCD-I | 27/06/2024 | 414 | MACHINO TECHNO | 25.99 | 0 | 100
1159 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for retaining wall construction and with allied work for Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of steel Truss Bridge, Guard room, CWR, Boundary wall, Laying of raising main, Land development Etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000097/2024-2025 | 2116/RCD-I | 27/08/2024 | 353 | MRITYUNJOY MUKHERJEE & CO. | 46.19 | 0 | 100
1160 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional Work For Concrete , MS Girder In connection With source Augmentation of OCP Based PWSS of Kajora (Ghanashampur OCP ) including intake arrangement construction of steel Truss Bridge , Guard room ,CWR, Boundary wall, Laying of raising main, Land development etc, and other allied works of OCP Kajora PWSS under RCFA Division 1 PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000098/2024-2025 | 2118/RCD-I | 27/08/2024 | 445 | MACHINO TECHNO | 82.14 | 0 | 100
1161 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for Laying 300 mm dia Raising Main through 600 mm dia MS pipe by trenchless technique under railway / NH / SH for the OCP base PWSS of Kajora (Ghanashampur OCP) of OCP Kajora PWSS under RCFA Division -1 PHE Dte. . | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000101/2024-2025 | 2121/RCD-I | 27/08/2024 | 45 | T M CONCRETE CREATION PVT.LTD | 57.67 | 0 | 100
1162 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work for laying 300 mm Dia rising main through 600 mm Dia Ms pipe by trenchless technique under railway /NH/SH FOR THE OCP base PWSS OF Kajora (Ghanashyampur OCP) of OCP Kajora PWSS under RCFA Division-I PHE, Dte | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000181/2024-2025 | 2429/RCD-I | 26/09/2024 | 60 | MRITYUNJOY MUKHERJEE & CO. | 54.06 | 0 | 100
1163 | RCFA Division -I | RCFA Division I | Formal work order for Source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including, Intake Arrangement, Construction of Steel Truss Bridge, Guardroom, CWR, Boundary Wall, Laying of Rising Main, Land Development etc. & other allied works of OCP Kajora PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000192/2023-2024 | 2148/RCD-I | 12/07/2023 | 275 | MRITYUNJOY MUKHERJEE & CO. | 120.71 | 18.58 | 16
1164 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Crossing 250 mm Dia MS pipe under the canal in connection with source Augmentation of OCP based PWSS of Kajora (Ghanashampur OCP) including intake arrangement construction of Steel Truss Bridge, Guard Room, CWR Boundary wall, Laying of rising main, land Development etc. and other allied works of OCP Kajora PWSS under RCFA Division-I PHE, Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000318/2024-2025 | 2760/RCD-I | 28/11/2024 | 260 | MRITYUNJOY MUKHERJEE & CO. | 14.7 | 0 | 100
1165 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Route Survey & Preparation of DPR for Augmentation of Kajora Piped Water Supply Scheme. Augmentation of Kajora Piped Water Supply Scheme including Providing FHTC Block : Andal District- Paschim Bardhaman. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/000617/2023-2024 | 3381/RCD-I | 21/11/2023 | 15 | APEX ENGINEERING | 2.54 | 0 | 100
1166 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Pump House under at Kajora under Kajora OCP based PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-II | Junior Engineer,Junior Engineer-5 | ORD/001122/2023-2024 | 928/RCD-I | 15/03/2024 | 90 | MACHINO TECHNO | 35.86 | 0 | 100
1167 | RCFA Division -I | RCFA Division I | Formal work order for Construction of 450 cum capacity 20 mtr. staging height RCC Over Head Reservoir (Pipe connection and cost of pipes. specials at Raniganj Block (Zone-18) for Augmentation of RCFA Part-II piped Water Supply Scheme under RCFA Division-I PHe Dte. in the District of Paschim Bardhaman. Ref Drawing No. PC-I/OHR/04/2022 (Sheet No. 1 & 2) | Assistant Engineer 2 | Junior Engineer | ORD/000154/2023-2024 | 1901/RCD-I | 09/06/2023 | 366 | SRI KRISHNA ENTERPRISE | 130.86 | 0 | 20
1168 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 900 cum capacity RCC Over Head Reservoir at (Zone-VII) of Salanpur Block for Improvement of RCFA Part-I Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000380/2023-2024 | 2553/RCD-I | 31/08/2023 | 7 | SINGHA ROY & CO. | 0.98 | 0.98 | 100
1169 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of extra cutting Laterate/sand stone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000466/2023-2024 | 2872/RCD-1 | 06/10/2023 | 90 | SWATI CORPORATION | 21.83 | 0 | 100
1170 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying & pushing of 600 mm dia RCC Hume pipe (NP3) by adopting trench less technology (e.g. Jack pushing method), MS water carrier pipe and other allied works at distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000473/2023-2024 | 2862/RCD-I | 06/10/2023 | 544 | SWATI CORPORATION | 44.91 | 0 | 100
1171 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional works of concrete dismantling & re concreting with other allied works at distribution networks including additional laying of pipe line for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000493/2023-2024 | 2885/RCD-1 | 06/10/2023 | 30 | SWATI CORPORATION | 73.24 | 0 | 100
1172 | RCFA Division -I | RCFA Division I | Sub Soil Investigation for 450 cum capacity RCC Over Head Reservoir at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman | Assistant Engineer 2 | Junior Engineer | ORD/000557/2022-2023 | 3351/RCDI | 23/12/2022 | 7 | MOYTEC | 0.49 | 0 | 100
1173 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II Piped water Supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte.(Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000816/2022-2023 | 998/RCDI | 22/03/2023 | 1016 | SWATI CORPORATION | 454.37 | 194.95 | 100
1174 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Construction of Chlorine Room of size (4.50 x 3.50 M) at (Zone-18) of Raniganj Block for Augmentation of RCFA Part-II Piped Water Supply Scheme under RCFA Division-I PHE Dte. in the District of Paschim Bardhaman. (Sl No. 32) | Assistant Engineer 2 | Junior Engineer | ORD/000914/2022-2023 | 1176/RCD-1 | 24/03/2023 | 90 | GOPAL CONSTRUCTION | 4.61 | 0 | 0
1175 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional works of extra cutting laterate / sandstone of distribution network for RCFA Part-II Piped Water Supply Scheme under RCFA Div-I PHE Dte. (Zone-18) | Assistant Engineer 2 | Junior Engineer | ORD/000944/2023-2024 | 489/RCD-I | 12/02/2024 | 45 | TARA CONSTRUCTION | 9.36 | 0 | 100
1176 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Carring, stacking of different dia (80 mm to 700 mm dia) C.I./D.I. specials, valves grannual chlorine etc including surface dressing, road base at Searsole Stack yard under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000976/2023-2024 | 463/RCD-1 | 12/02/2024 | 20 | M/S MONDAL ENTERPRISE | 10.95 | 0 | 100
1177 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work related to Rising Main Part-A for concrete cutting and road restoration at Ethora village including interconnection and Barabani OHR including Bituminous road cutting etc allied works under Improvement of RCFA Part-I PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000978/2023-2024 | 465/RCD-1 | 12/02/2024 | 30 | M/S MONDAL ENTERPRISE | 25.64 | 0 | 100
1178 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of Godown for stacking of Cholorine at Searsole Head Work site of Augmentation PWSS Of RCFA Part-II (Zone-18) under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000980/2023-2024 | 466/RCD-1 | 12/02/2024 | 90 | M/S MONDAL ENTERPRISE | 9.5 | 0 | 100
1179 | RCFA Division -I | RCFA Division I | Formal work order for Acceptance order for Construction of 700 cum capacity 20 mtr staging height RCC Over Head Reservior (pipe connection and cost of pipes, specials and land devlopment with approached road including internal drain at Mohishila OHR within Asansol Municipal Corporation area under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/001078/2023-2024 | 805/RCD-I | 13/03/2024 | 180 | GITA CONSTRUCTION | 180.36 | 0 | 82
1180 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000037/2023-2024 | 2937/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1181 | RCFA Division -I | RCFA Division I | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-65 dt 22.11.2023 in Indian railway from Andal to Bhaktarnagar under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00821/2023-2024 | 390/23-24 | 29/11/2023 | 0 | EASTERN RAILWAY | 0.25 | 0 | 0
1182 | RCFA Division -I | RCFA Division I | Survey Charges for Way leave / Track crossing proposal with Application ID : ER-ASN-2023-WL-66 dt 22.11.2023 in Indian railway from Andal to Andal Junction Cabin under Augmentation of RCFA Pt-II (Zone-1A) under RCFA Division-I, PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/00822/2023-2024 | test | 30/11/2023 | 0 | EASTERN RAILWAY | 0.24 | 0 | 0
1183 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work laying of different dia HDPE & MS pipe including installation of sluice valve and chamber in different location of Dakshin Khanda & Khandra GP under Ondal Block under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000468/2023-2024 | 2860/RCD-I | 06/10/2023 | 30 | UNITED CONSTRUCTION | 25.34 | 0 | 90
1184 | RCFA Division -I | RCFA Division I | Laying of different dia distribution pipe line at Ghosalpara, Dharmarajtala, Sabarpara, Dagalpara, Ghosalpara, Kamarpara, MajhiPara etc area of Dakshin Khanda area under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000586/2022-2023 | 3294/RCD I | 20/12/2022 | 45 | UNITED CONSTRUCTION | 52.8 | 52.4 | 0
1185 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Additional work 300 mm dia MS pipe line for Singharani Bridge crossing and Kajora at Madanpur under RCFA Part-II W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000636/2023-2024 | 3418/RCD-1 | 24/11/2023 | 30 | MD. JAWED KHAN | 11.59 | 0 | 100
1186 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Construction of FHTC Platform in different household at Dakshin Khanda (Jl No. 36) Block ¿ Andal under Augmentation of RCFA Part-II (Zone-1A) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000759/2022-2023 | 385/RCD I | 30/01/2023 | 45 | UNITED CONSTRUCTION | 34.42 | 28.04 | 100
1187 | RCFA Division -I | RCFA Division I | Formal work order for distribution network for RCFA Part-II piped water supply Scheme including FHTC & allied work under RCFA Div-I, PHE Dte (Zone-1A) (Ukhra) | Assistant Engineer 2 | Junior Engineer | ORD/000781/2022-2023 | 818/RCDI | 10/03/2023 | 905 | ASHA CONSTRUCTION | 249.09 | 0 | 70
1188 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work line concrete cutting and allied works for Augmentation of Nutondanga RCFA Part-II (Zone-1A) piped W/S Scheme of durgapur sub-Division under RCFA division-I PHE dte. | Assistant Engineer 2 | Junior Engineer | ORD/000909/2023-2024 | 214/RCD-I | 29/01/2024 | 30 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 35.52 | 0 | 70
1189 | RCFA Division -I | RCFA Division I | Acceptance cum work order Laying 160 mm dia HDPE pipe line along Domahani Jamuria Road under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000921/2022-2023 | 1254/RCD-I | 27/03/2023 | 15 | NATIONAL CONSTRUCTION | 3.85 | 0 | 100
1190 | RCFA Division -I | RCFA Division I | Allied work of laying distribution system of Balance Work of laying distribution system to Accommodate FHTC and providing FHTC including supplying laying fittings fixing of 15 NB PVC pipe with all necessary work specials saddle piece etc. all complete for Augmentation of sub-surface water based PWSS for Amritnagar Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000934/2023-2024 | 497/RCD-I | 12/02/2024 | 45 | MACHINO TECHNO | 73.78 | 0 | 100
1191 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Additional work for Electrical wiring of C and D type quarter building, PHE Housing Complex and Installation of street including arrangement and fedar box and other allied works under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000961/2023-2024 | 484/RCD-I | 12/02/2024 | 15 | T R ENTERPRISE | 13.35 | 0 | 100
1192 | RCFA Division -I | RCFA Division I | Acceptance cum Work Order for Sinking of 3 (Three) nos river bed tube wells including collecting main manifold sluice valve chamber reinforcement and other allied works at Damalia H/W under RCFA Part-II at Damodar river under Augmentation of Amritnagar Zone-II Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000971/2023-2024 | 486/RCD-I | 12/02/2024 | 25 | M/S KALYAN ENTERPRISE | 10.68 | 0 | 100
1193 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Balance work for distribution network for Augmentation of Ondal Phase-II/A Piped Water Supply Scheme including FHTC and allied works within Ondal Block under RCFA Division-I PHE Dte. (Part-I) | Assistant Engineer 2 | Junior Engineer | ORD/000988/2023-2024 | 470/RCD-1 | 12/02/2024 | 30 | SIMA ENTERPRISE | 5.59 | 0 | 100
1194 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 90 mm HDPE pipe line inter connection stand post and other allied works at Dakshin Khanda, Moira and adjacent area under RCFA Part-II Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000990/2023-2024 | 471/RCD-1 | 12/02/2024 | 30 | UNITED CONSTRUCTION | 9.57 | 0 | 100
1195 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2 | Junior Engineer | RTOR000016/2023-2024 | 2936/RCD-I | 11/10/2023 | 0 | Resource Division | 6.78 | 0 | 0
1196 | RCFA Division -I | Asansol Mechanical Division | Road restoration of work 03 nes location (Reghunathpur Kantaberia via Molandihi, Muchipara Shibpur, Reghunathpur Kantaberna via Molandihi) | Assistant Engineer-II | Junior Engineer-5 | BILL/00544/2024-2025 | 275/24-25 | 06/09/2024 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, PW (ROADS) DIRECTT. | 26.8 | 0 | 0
1197 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Additional work for Jemua Water Supply Scheme at Gopalpur within Durgapur Faridpur Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000019/2024-2025 | 1522/RCD-I | 14/06/2024 | 292 | ASHA CONSTRUCTION | 22.23 | 0 | 100
1198 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Supplying laying HDPE distribution pipe line at JhanjraPurbapara at Durgapur Faridpur Block under Augmentation of RCFA Part-III Zone-II under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000323/2025-2026 | 1509/RCD-I | 20/05/2025 | 73 | DAWN CONSTRUCTION | 23.41 | 0 | 40
1199 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Laying and pushing by adopting trenchless technology (jack pushing method) additional for distribution network for Augmentation of RCFA part-III (Zone-II) PWSS including FHTC and allied works under RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000339/2024-2025 | 2779/RCD-I | 28/11/2024 | 180 | MAK CONSTRUCTION CO | 35.16 | 0 | 68
1200 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Balance work of dismantling of concrete, restoration of road including pipe crossing by adopting trenchless technologies (e.g Jack Pushing Method etc.) 03 nos. location at Bahula(Zone-9) within Pandabeswar Block for Augmentation of RCFA Part-III (Zone-II) PWSS under RCFA Division-I PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/000536/2024-2025 | 139/RCD-I | 08/01/2025 | 45 | MD AAMIR KHAN | 40.95 | 0 | 100
1201 | RCFA Division -I | Asansol Mechanical Division | Hiring of Maxi Cab (Non Air Conditional ) Bharat Stage-iii/BS-ii purchased on or after 01.05.2008 with Diesel /LPG /CNG Engine for the supervision work of Durgapur W/S Division for office use of Assitant Engineer, RCFA Division-I Public Helth Engineering Directorate, Govt of West Bengal ( w.e.f 01.12.2023. to 31.05.2024) Consumption of Diesel,12 km per litre, Mobil 05 litre per 2500 km. | Assistant Engineer-II | Junior Engineer-5 | ORD/000727/2023-2024 | 3514/RCD-I | 30/11/2023 | 182 | SUBHA TOUR & TRAVELS | 0.89 | 0 | 35
1202 | RCFA Division -I | Asansol Mechanical Division | Acceptance cum work order for Detailed study of Households/Habitations of Barabani, Faridpur-Durgapur, Jamuria, Kanksa, Ondal, Pandabeswar, Raniganj and Salanpur blocks under Paschim Barddhaman District under the jurisdiction of RCFA Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-5 | ORD/001073/2023-2024 | 803/RCD-I | 13/03/2024 | 2224 | HORIZEN | 67.79 | 0 | 80
1203 | RCFA Division -I | RCFA Division I | Acceptance cum work Order for Repairing, Renovation, renewing & oversauling & obsolete i) for 2 nos. Iron Removal Plant (Pressure type) each capacity 45 cum/Hr at Churulia Head Work Site for Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Part-A) ii) for 3 nos. Iron Removal Plant (Pressure type of capacity 50 cum/hr 1no. & 75 cum/hr-2nos) at Madantore Head Works site for Madantore W/S Scheme under RCFA Division-I PHE Dte (Part-B) iii) for 4 nos. iron removal Plant (Pressure type) each capacity 20 cum /hr at Pandabeswar Head Works Site for Pandabeswar W/S Scheme under RCFA Division-I PHE Dte. (Part-C) iv) for 2 nos. iron Removal Plant (Pressure type) each capacity 50 cum/hr at Madanpur Head Work Site under RCFA Division-I PHE Dte. (Part-D). | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000009/2023-2024 | 1391/RCD I | 11/04/2023 | 356 | TARAPRASAD SARKAR | 97.93 | 45.74 | 100
1204 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Distribution Network including providing FHTC Work under Augmentation of Churulia and its adjoining mouzas (Zone-II) PWSS Block- Jamuira, Dist- Paschim Bardhaman under RCFA Div-I Phe,Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000103/2022-2023 | 1276/RCD-I | 02/06/2022 | 90 | MD AAMIR KHAN | 70.29 | 48.29 | 100
1205 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 2 (Two) no. 200 mm dia river bed tube well in the river Ajoy of Augmentation of Churulia and its Adjoining Mouzas PWSS under RCFA Division-I PHE Dte.(SL NO 09) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000114/2022-2023 | 1283/RCD I | 02/06/2022 | 30 | R B ENTERPRISE | 13 | 8.2 | 80
1206 | RCFA Division -I | RCFA Division I | Formal Work Order for Augmentation of Churulia and its adjoining mouzas (Zone-I) PWSS by construction of OHR of capacity 100 cum with 20 mtr staging height LDS with necessary interconnection & FHTC work Block-Jamuria, Dist-Paschim Bardhaman under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000118/2022-2023 | 1372/RCD-I | 16/06/2022 | 1172 | ASHA CONSTRUCTION | 306.57 | 156.81 | 100
1207 | RCFA Division -I | RCFA Division I | Acceptance cum work order for construction of 200 cum capacity 20 mtr staging height RCC over Head Reservoir, pipe connection and cost of pipes specials of Churulia piped Water Supply Scheme under RCFA Div-I PHE Dte in the District of Paschim Bardhaman. Ref PC-I/OHR/09/2021 | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000543/2022-2023 | 3245/RCD I | 20/12/2022 | 274 | ASHA CONSTRUCTION | 71.55 | 64.4 | 100
1208 | RCFA Division -I | RCFA Division I | Acceptance cum work order for laying of 150 mm and 200 mm dia rising main for the proposed augmentation work of Churulia and its adjoining mouzas piped water supply scheme under RCFA Div-I, PHE Dte | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000613/2022-2023 | 3273/RCD I | 20/12/2022 | 621 | T.R. ENTERPRISE | 21.17 | 10.65 | 70
1209 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 6 (Six) nos 200 mm dia river bed tube well in river Ajoy of Augmentation of Churulia PWSS under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000761/2022-2023 | 388/RCDI | 30/01/2023 | 45 | ASHA CONSTRUCTION | 41.46 | 22.21 | 100
1210 | RCFA Division -I | RCFA Division I | Acceptance cum work order Construction of Concrete retaining wall with land development Churulia Ajoy River Bed Site under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000852/2022-2023 | 1088/RCD-I | 23/03/2023 | 90 | S. CHAKRABORTY & CO. | 44.66 | 40.55 | 100
1211 | RCFA Division -I | RCFA Division I | Acceptance come work order for Balance work for distribution network of Churulia Madhudanga and its adjoining mouzas (Zone-II) under Augmentation of Churulia W/S Scheme under RCFA Division-I PHE Dte. (Sl No. 20) | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | ORD/000854/2022-2023 | 1087/RCD-I | 23/03/2023 | 90 | MD AAMIR KHAN | 16.38 | 16.32 | 100
1212 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000004/2023-2024 | 1639/RCD-I | 27/04/2023 | 0 | Resource Division | 45.72 | 0 | 0
1213 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000024/2022-2023 | 3127 | 09/12/2022 | 0 | Resource Division | 178.46 | 0 | 0
1214 | RCFA Division -I | RCFA Division I | Material Requisition To Resource Division | Assistant Engineer 2,Assistant Engineer-I | Junior Engineer,Junior Engineer-5 | RTOR000031/2022-2023 | 106/RCD-I | 20/01/2023 | 0 | Resource Division | 159.09 | 0 | 0
1215 | RCFA Division -I | RCFA Division I | Suuply of UPS laboratory antivirus toner 12 for Asansol Laboratory | Assistant Engineer 2 | Junior Engineer | BILL/00210/2024-2025 | 91/24-25 | 13/06/2024 | 0 | SHARMA ENGINEERING WORKS | 0.08 | 0 | 0
1216 | RCFA Division -I | RCFA Division I | Supply of chair for SE/RCFA Circle | Assistant Engineer 2 | Junior Engineer | BILL/00330/2023-2024 | 151/23-24 | 25/07/2023 | 0 | GLOBAL LOGISTIC CO | 0.23 | 0 | 0
1217 | RCFA Division -I | RCFA Division I | hirting of maxi cab for date 27.7.2023 to 28.07.2023 us of AE RCFA Div WB37D 9526 | Assistant Engineer 2 | Junior Engineer | BILL/00532/2023-2024 | 256/23-24 | 11/09/2023 | 0 | NIRMALA TRADERS | 0.06 | 0 | 0
1218 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Laying of 110 mm dia HDPE Pipe line including concrete cutting mending etc allied works towards Pathakpara (Sansad-XV) Block Andal & Pandabeswar of Improvement of Ukhra Piped Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | BILL/01008/2023-2024 | 372/23-24 | 21/11/2023 | 0 | B.T.M. CONCERN | 2.14 | 0 | 0
1219 | RCFA Division -I | RCFA Division I | Supply of 10 mm into female 15 mm outer male reducer Brass Bush at Searsole Store to provide interconnection work in between maniflod and ferrule under Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Sl No. 02) | Assistant Engineer 2 | Junior Engineer | ORD/000208/2022-2023 | 1909/RCD-I | 12/08/2022 | 7 | SNEHA ELECTRIC | 4.69 | 4.69 | 0
1220 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Sinking of 02 (Two) nos. river bed tube wells including collecting main and other allied works at Narayankuri H/W site at Damodar river under Narayankuri Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000215/2023-2024 | 2243/RCD-1 | 17/07/2023 | 30 | MS KALYAN ENTERPRISE | 13.23 | 11.39 | 100
1221 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Hanuman Danga & Saradapally (Sansad-IV) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000259/2021-2022 | 1868/RCD-I | 28/10/2021 | 30 | DAWN CONSTRUCTION | 26.54 | 5.97 | 0
1222 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Bazar Area (Sansad-V) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000260/2021-2022 | 1869/RCD-I | 28/10/2021 | 30 | UMA ENTERPRISE | 21.3 | 15.22 | 0
1223 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Teli Para (Sansad-XVIII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000269/2021-2022 | 1878/RCD-I | 28/10/2021 | 30 | M/S K & KONAR CONSTRUCTION | 17.13 | 5.48 | 0
1224 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Guzarbagh (Sansad-XXI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000271/2021-2022 | 1880/RCD-I | 28/10/2021 | 30 | R B ENTERPRISE | 13.3 | 13.3 | 0
1225 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Safique Nagar (Sansad-XXII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000272/2021-2022 | 1881/RCD-I | 28/10/2021 | 30 | A. CONSTRUCTION CO. | 18.11 | 18.11 | 0
1226 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Bibirbandh Para and Santipara (Sansad-I) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000365/2021-2022 | 2323/RCD-I | 16/12/2021 | 30 | GITASHREE FABRICATION | 18.16 | 18.16 | 0
1227 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Huchukpara (Sansad-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000366/2021-2022 | 2324/RCD-I | 16/12/2021 | 30 | A. CONSTRUCTION CO. | 15.53 | 15.53 | 0
1228 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Das Para (Sansad-XIX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000367/2021-2022 | 2325/RCD-I | 16/12/2021 | 30 | JYOGOMAYA ENTERPRISE | 12.46 | 10.43 | 0
1229 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-XII) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000368/2021-2022 | 2326/RCD-I | 16/12/2021 | 30 | M/S B.K. CONSTRUCTION | 25.7 | 17.19 | 100
1230 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Chanchani (Sansad-X) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000369/2021-2022 | 2327/RCD-I | 16/12/2021 | 30 | ASHA CONSTRUCTION | 27.72 | 18.23 | 0
1231 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-A) | Assistant Engineer 2 | Junior Engineer | ORD/000370/2021-2022 | 2328/RCD-I | 16/12/2021 | 30 | MD AAMIR KHAN | 14.42 | 14.42 | 0
1232 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-B) | Assistant Engineer 2 | Junior Engineer | ORD/000371/2021-2022 | 2329/RCD-I | 16/12/2021 | 30 | SHILPA UDDOYG ENGINEERING CO-OP SOCIETY LTD. | 14.4 | 10.71 | 0
1233 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000372/2021-2022 | 2332/RCD-I | 17/12/2021 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 7.14 | 0
1234 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-E) | Assistant Engineer 2 | Junior Engineer | ORD/000373/2021-2022 | 2333/RCD-I | 17/12/2021 | 30 | TARAPRASAD SARKAR | 14.37 | 10.48 | 100
1235 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-C) 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000491/2021-2022 | 120/RCD-I | 20/01/2022 | 30 | GLOBAL CONSTRUCTION | 14.23 | 13.36 | 0
1236 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Sanyasi Kalitala (Sansad-XVI) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. | Assistant Engineer 2 | Junior Engineer | ORD/000496/2021-2022 | 2491/RCD-I | 31/12/2021 | 30 | TARA CONSTRUCTION | 11.24 | 10.92 | 0
1237 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Asthana (Sansad-IX) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. 2nd Call | Assistant Engineer 2 | Junior Engineer | ORD/000498/2021-2022 | 198/RCD-I | 28/01/2022 | 30 | B M SARKAR | 13.04 | 10.18 | 0
1238 | RCFA Division -I | RCFA Division I | Acceptance cum work order for Providing FHTC through Retrofitting at Ukhra Area (Phase-II) Block-Andal & Pandabeswar of Ukhra Water Supply Scheme under RCFA Division-I PHE Dte. (Part-D) | Assistant Engineer 2 | Junior Engineer | ORD/000851/2021-2022 | 2332/RCD-1 | 17/12/2021 | 30 | RELIABLE ENGINEERS CO-OP CONSTRUCTION SOCIETY LTD. | 14.44 | 4.03 | 0
Total | [10 empty] | 58888.84 | 14215.27