## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 02) Tender No.- 211/NAD-I/2020-2021. |  |  | ORD/000178/2020-2021 | 282/NAD-I | 03/02/2021 | 90 | MONDAL ENTERPRISE | 93.33 | 92.26 | 100
2 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000004/2021-2022 | 768/NAD-I | 04/05/2021 | 60 | MALI CONSTRUCTION | 34.25 | 33.8 | 100
3 | Nadia Arsenic Division I |  | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis of mass emission standard like Bharat Stage - III and Higher and purchased on or after 01.05.2008 with diesel / LPG / CNG Engine, non-air-conditioned for official use of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. [For the period of 6 (six) Months] |  |  | ORD/000062/2023-2024 | 0262/AE-I/NAD-I | 31/05/2023 | 183 | MUKHERJEE CONSTRUCTION | 0.88 | 0 | 100
4 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Subarnapur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 4) tender No. - 215/NAD-I/2020-2021. |  |  | ORD/000177/2020-2021 | 284/NAD-I | 03/02/2021 | 90 | SINGHA ROY & CO. | 97.07 | 95.86 | 100
5 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No.- 202/NAD-I/2020-2021. |  |  | ORD/000171/2020-2021 | 156/NAD-I | 25/01/2021 | 60 | TAPU SAHA | 84.28 | 82.73 | 100
6 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-V, (Purba Bishnupur) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 04) Tender No. 218/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2020-2021 | 311/NAD-I | 08/02/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 97.1 | 70.89 | 100
7 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Purba Bishnupur Zone -V of Surface Water Based PWSS for Chakdah Part Water Supply Scheme under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte.( Sl.no. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000283/2022-2023 | 1473/NAD-I | 22/08/2022 | 60 | APURBA MANDAL | 1.77 | 0 | 0
8 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur, Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000063/2021-2022 | 1421/NAD-I | 08/11/2021 | 60 | M/S ASHA CONSTRUCTION | 77.3 | 0 | 100
9 | Nadia Arsenic Division I |  | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Muragachha Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000176/2021-2022 | 497/NAD-I | 22/03/2022 | 60 | DIVINE | 144.2 | 0 | 100
10 | Nadia Arsenic Division I |  | Laying of additional; pipelines at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000035/2024-2025 | 183/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.92 | 0 | 100
11 | Nadia Arsenic Division I |  | Laying of additional pipelines and reconnection of damages FHTC at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000036/2024-2025 | 184/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.93 | 0 | 100
12 | Nadia Arsenic Division I |  | Laying of additional pipelines at Node Point 27 to 32 at Garapota W/S Scheme under JJM within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte |  |  | ORD/000037/2024-2025 | 185/AE-II/NAD-I | 09/08/2024 | 7 | M/S ADIL CONSTRUCTION | 0.92 | 0 | 100
13 | Nadia Arsenic Division I |  | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) |  |  | ORD/000051/2024-2025 | 1501/NAD-I | 18/09/2024 | 45 | B.S. ENTERPRISE | 19.54 | 0 | 100
14 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Garapota, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000053/2021-2022 | 1410/NAD-I | 08/11/2021 | 60 | B.M. ENGINEERING & CONSTRUCTION | 86.04 | 0 | 100
15 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 140/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
16 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IV, (Uttar Duttapara), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000124/2021-2022 | 49/NAD-I | 11/01/2022 | 90 | KINGS AND CO | 223.23 | 0 | 100
17 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XI,(Chanduria) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000122/2021-2022 | 15/NAD-I | 05/01/2022 | 90 | MADE AND TRADE CO. | 441.26 | 0 | 100
18 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Brambhapara, Manasapota (Nirmalpally, Sahapara) Brambhapara, Chanduria (Sahapara) area under Chakdah Block by Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia District Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.20) | Assistant Engineer-II | Junior Engineer-III | ORD/000193/2023-2024 | 2190/NAD-I | 13/09/2023 | 15 | PRADIP KUMAR BANIK | 14.14 | 0 | 100
19 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection from node point 105 to node point 16 for augmentation work at Koutakpur, Jibannagar and Kajibagan under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte (sl.7) | Assistant Engineer-II | Junior Engineer-III | ORD/000258/2022-2023 | 457/ NAD-I | 06/03/2023 | 21 | ABDUL ALIM MONDAL | 32.03 | 0 | 0
20 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Itaberia Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Itaberia W/S Scheme under JJM (sl.no.11) | Assistant Engineer-II | Junior Engineer-IV | ORD/000016/2023-2024 | 1122 /NAD-I | 27/04/2023 | 15 | B.S. ENTERPRISE | 13.04 | 0 | 100
21 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000025/2024-2025 | 1118/NAD-I | 19/07/2024 | 180 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0
22 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Gobindapur W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000039/2022-2023 | 1589/NAD-I | 05/09/2022 | 45 | APURBA MANDAL | 14.41 | 0 | 40
23 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at ITABERIA W/S Scheme & Betna W/S Scheme at Hanskhali Block under Nadia Arsenic Division-I , P.H.E.Dte. (Sl.no. 10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000043/2022-2023 | 1583/NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 28.26 | 0 | 100
24 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet , Pathway and other allied work at Gobindapur (Hanskhali) W/S Scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.(Sl.no. 02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000048/2022-2023 | 1588 / NAD-I | 06/09/2022 | 45 | GOPAL KIRTYANIYA | 11.82 | 0 | 100
25 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, pathway and other allied work at Joypur W/S scheme within Hanskhali Block under Nadia Arsenic Division -I, P.H.E.Dte.( Sl.no.01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000052/2022-2023 | 1590 / NAD-I | 06/09/2022 | 45 | M/S DREAM INFRASTRUCTURE | 12.41 | 0 | 100
26 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and all repair works at Itaberia W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000055/2022-2023 | 1638 / NAD-I | 06/09/2022 | 45 | APURBA MANDAL | 12.04 | 0 | 100
27 | Nadia Arsenic Division I | Nadia Arsenic Division I | 'Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E [he. in connection with Augmentation of Gobindapur W/S Scheme under JIM (SL No. 10)". | Assistant Engineer-II | Junior Engineer-IV | ORD/000068/2023-2024 | 1071/NAD-I | 24/04/2023 | 733 | APURBA MANDAL | 13.03 | 0 | 100
28 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir, Painting of Boundary Wall of Head Work Site, Pump House and AIRP at Joypur W/S Scheme in Hanskhali Block under Nadia Arsenic Division - I P. H.E. Dte (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000074/2023-2024 | 1258/NAD-I | 04/05/2023 | 15 | GHOSH CONSTRUCTION | 21.34 | 0 | 100
29 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Itaberia WS Scheme in Hanskhali Block under NAD I PHE Dte (Sl.no.12) | Assistant Engineer-II | Junior Engineer-IV | ORD/000109/2022-2023 | 2058 / NAD-I | 21/10/2022 | 45 | M/S D.C. RAKSHIT & COMPANY | 19.77 | 0 | 100
30 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Itaberia PWSS Hanskhali Block (Part-I) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000157/2022-2023 | 3489/NAD-I | 02/01/2023 | 21 | BUDDHADEV MONDAL | 19.22 | 0 | 99
31 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Gobindapur PWSS Hanskhali Block (Part-II) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia under Nadia Arsenic Division-I, PHE Dte (sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000161/2022-2023 | 3513/NAD-I | 09/01/2023 | 21 | M/S DIPAK ENTERPRISE | 19.75 | 0 | 100
32 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Joypur PWSS Hanskhali Block (Part-III) by Augmentation of Itaberia, Gobindapur & Joypur at Hanskhali Block, Dist- Nadia Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000162/2022-2023 | 3514/NAD-I | 09/01/2023 | 21 | SUBIR KUMAR DEY | 19.99 | 0 | 100
33 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Joypur Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000165/2021-2022 | 433/NAD-I | 07/03/2022 | 60 | M/S GHOSH CONSTRUCTION | 60.4 | 0 | 100
34 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 500 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House at Digha Zone-XIII under Surface W/S Scheme of Haringhata-Chakdah Part under NAD-I PHE Dte (Sl.no.06) | Assistant Engineer-I | Junior Engineer-II | ORD/000072/2022-2023 | 1691/NAD-I | 08/09/2022 | 60 | CHOWDHURY & CO. | 28.14 | 0 | 100
35 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Subarnapur Zone XI under Surface WS Scheme of Haringhata Chakdah Part under NAD -I PHE Dte (sl.no.07) | Assistant Engineer-I | Junior Engineer-II | ORD/000131/2022-2023 | 3035 /NAD-I | 09/11/2022 | 60 | DIVINE | 33.26 | 0 | 100
36 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Birohi Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I | Junior Engineer-II | ORD/000141/2022-2023 | 3157/NAD-I | 25/11/2022 | 60 | ONKAR ENTERPRISE | 24.53 | 0 | 100
37 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XIII (Digha) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 11) | Assistant Engineer-I | Junior Engineer-II | ORD/000160/2021-2022 | 427/NAD-I | 07/03/2022 | 60 | SANJIB DEY | 81.56 | 0 | 100
38 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-X (Subarnapur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No. 15) | Assistant Engineer-I | Junior Engineer-II | ORD/000161/2021-2022 | 428/NAD-I | 07/03/2022 | 60 | IJABUL SEKH | 95.12 | 0 | 100
39 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-XI (Birohi) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata Zone-X, (Subarnapur), Zone-XI (Birohi) and Zone-XIII (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000173/2022-2023 | 38/AE-I/NAD-I | 07/01/2023 | 15 | J & T ENTERPRISE | 4.83 | 0 | 100
40 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Birohi) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | Assistant Engineer-I | Junior Engineer-II | ORD/000174/2021-2022 | 465/NAD-I | 10/03/2022 | 60 | GHOSH CONSTRUCTION | 91.98 | 0 | 100
41 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-X (Subarnapur) at Haringhata Block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X, (Subarnapur), Zone-XI, (Birohi) and Zone-XIII, (Digha) Part-III under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000174/2022-2023 | 39/AE-I/NAD-I | 07/01/2023 | 15 | M/S DIPAK ENTERPRISE | 4.83 | 0 | 100
42 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Pipeline at Ayeshpur More (Near Petrol Pump) at NH-34 and other allied works under JalJeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI, Birohi under JJM underNadia Arsenic Division-I, PHE Dte. (SL.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000246/2022-2023 | 512 / NAD-I | 10/03/2023 | 30 | M/S DIPAK ENTERPRISE | 64.25 | 0 | 35
43 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Pipeline at Birohi More(Underpass) at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-XI at Birohi at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XI,Birohi under JJM under Nadia Arsenic Division-I, PHE Dte. (SL.09) | Assistant Engineer-I | Junior Engineer-II | ORD/000247/2022-2023 | 513 /NAD-I | 10/03/2023 | 30 | M/S DIPAK ENTERPRISE | 66.19 | 0 | 100
44 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Zone-XIII, (Digha), Part-III at Haringhata Block by augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.22) | Assistant Engineer-I | Junior Engineer-II | ORD/000261/2022-2023 | 828/NAD-I | 31/03/2023 | 21 | NISHITH BANERJEE | 14.03 | 0 | 100
45 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000127/2020-2021 | 90/NAD-I | 22/01/2021 | 60 | APURBA MANDAL | 70.37 | 70.02 | 100
46 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. (Sl no.-02) Tender No. 229/NAD-I/2020-2021. |  |  | ORD/000186/2020-2021 | 291/NAD-I | 04/02/2021 | 45 | CHANDAN ROY | 42.81 | 2.44 | 0
47 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Augmentation of pipeline and FHTC including repair of Boundary wall at Saguna, Aluipara & Hijuli Mouzas and Parbatipur & Gopalpur Mouzas under Parbatipur Piped Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000011/2025-2026 | 123/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 85.69 | 0 | 0
48 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Interconnection of pipeline from manifold to different direction of distrtibution pipeline including laying of balance pipeline and FHTC along with allied works at Nrisinghapur (Chandkuri) under Parbatipur Piped Water Supply Scheme at Parbatipur & Gopalpur Mouzas under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | Assistant Engineer | Junior Engineer | ORD/000052/2025-2026 | 529/NAD-I | 03/07/2025 | 90 | CHOWDHURY & CO. | 192.83 | 0 | 0
49 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil Investigation for the work of construction of 400 cum OHR staging height 20 mtr. Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and construction of Pump House, Boundary Wall, Service Road and other allied Works at Head Work & 2nd site under Jal Jeevan Mission for Parbatipur Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl. NO. 06) | Assistant Engineer | Junior Engineer | ORD/000094/2023-2024 | 1740/NAD-I | 19/07/2023 | 1095 | H I ENTERPRISE | 628.88 | 0 | 61
50 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Laying of Rising Main, Laying distribution system and Providing FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 400 cum OHR staging height 20 mtr., Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house, Boundary Wall, Service Road and other allied Works at Head work & 2nd site under Jal Jeevan Mission for Parbatipur Zone- I Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 1743/NAD-I | 19/07/2023 | 730 | M/S TARAK CHANDRA PAUL | 633.23 | 0 | 54
51 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Laying of pipeline for functionally of FHTC including new FHTC connection at Phuliapara, Durlav para, Narasinghanagar, Chapatala & Beharia Mouza under Fulia G.P. & Gopalpur & Parbatipur mouza under Parbatipur PWSS under Nadia Arsenic Division-I, P.H.E. Dte. (2nd Call) [Sl. No. 04] | Assistant Engineer | Junior Engineer | ORD/000101/2025-2026 | 664/NAD-I | 21/07/2025 | 120 | BUDDHADEV MONDAL | 87.35 | 0 | 0
52 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Parbatipur Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(SL.05) | Assistant Engineer | Junior Engineer | ORD/000181/2022-2023 | 66 / NAD-I | 20/01/2023 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 10.97 | 0 | 100
53 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000003/2024-2025 | 847/NAD-I | 04/06/2024 | 0 | Resource Division | 37.63 | 0 | 0
54 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000005/2024-2025 | 1750/NAD-I | 25/10/2024 | 0 | Resource Division | 39 | 0 | 0
55 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000020/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 33.39 | 0 | 0
56 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna, Zone-I, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000005/2021-2022 | 769/NAD-I | 04/05/2021 | 60 | MALLICK ENTERPRISE | 97.12 | 88.67 | 100
57 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000015/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
58 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node point 1 to node point 105 in connection with augmentation work at Priyanagar under Zone-XI, Chanduria W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(SL.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000010/2023-2024 | 535 /NAD-I | 13/04/2023 | 21 | ABDUL ALIM MONDAL | 33.72 | 0 | 0
59 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of rising main and distribution pipeline in revised alignment along NH-34 for Simurali (Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) in connection with providing FHTC for Simurali(Zone-X), Chanduria (Zone-XII), Joykrishnapur (Zone-II) under JJM by Augmentation of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, P.H.E.Dte. (sl.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000030/2023-2024 | 1254/ NAD-I | 04/05/2023 | 21 | BUDDHADEV MONDAL | 42.85 | 0 | 0
60 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jack Pushing of Clearwater Rising Main Pipeline at Chakdah Chowmataha Crossing along NH-12 and other allied works under Jal Jeevan Mission (JJM) for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) at Chakdah Block under Surface Water based PWSS for Chakdah Water Supply Scheme in connection with Providing FHTC for Joykrishnapur (Zone-II), Chanduria (Zone-XI), Simurali (Zone-X), Ghetugachi (Zone-IX), Baraberia (Zone-VIII), Rukminidanga (Zone-IV) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.13) | Assistant Engineer-II | Junior Engineer-III | ORD/000036/2023-2024 | 1276 / NAD-I | 08/05/2023 | 21 | GBC INFRASTRUCTURE PRIVATE LIMITED | 58.64 | 0 | 0
61 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Simurali Zone-XI under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000054/2022-2023 | 1433 / NAD-I | 16/08/2022 | 45 | ONKAR ENTERPRISE | 29.88 | 0 | 100
62 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Sanyalchar bablatala to Sanyalchar High School under Chanduria(Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E Dte (sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000057/2023-2024 | 1459/NAD-I | 29/05/2023 | 21 | SHYAMAL SHIL | 13.29 | 0 | 100
63 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection from Node point 178 to node point 188 for Augmentation work at Tetulberia, Khorgachi,mollabelia village under Joykrishna ( Zone- II ) Water supply scheme under Jal Jeevan Mission for Chakdah Water bsaed PWSS within Chakdah Block ( Part ) under Nadia Arsenic Division-I, PHE Dte.(SL.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000069/2023-2024 | 1383/NAD-I | 16/05/2023 | 21 | M/S A.K. CONSTRUCTION | 25.14 | 0 | 100
64 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000076/2023-2024 | 1400/NAD-I | 16/05/2023 | 25 | CHANDAN ROY | 47.15 | 0 | 100
65 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000079/2023-2024 | 1412/NAD-I | 18/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 0 | 100
66 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway and Room at Head work site of Joykrishnapur OHR Site (Zone-II), Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Jeeva Mission for Zone-II (Joykrishnapur) Part-II, Providing FHTC under Jal Jeevan Mission (JJM) Zone -VIII (Barberia) Part-IV, Providing FHTC under Jal Jeevan Mission (JJM) Zone-X (Simurali) Part-IV and Providing FHTC under Jal Jeevan Mission (JJM) Zone-IV (Rukminidanga) Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000106/2023-2024 | 1709/NAD-I | 14/07/2023 | 892 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 608.25 | 0 | 75
67 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work Kajir baganunder Chanduria (Zone-XI) W/S Scheme in connection with augmentation of Chanduria W/S Scheme under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000149/2023-2024 | 377/AE-II/NAD-I | 29/08/2023 | 7 | ASHIM ENTERPRISE | 1.17 | 0 | 100
68 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Pathway from Madnapur PWD road to Tantipara and allied works in connection with Augmentation of Surface Water Based W/S Scheme for Arsenic affected areas of Chakdah (Part Block) of Nadia district Zone-X (Chanduria) under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000150/2023-2024 | 378/AE-II/NAD-I | 29/08/2023 | 7 | GREEN VIEW PROJECT INDIA | 2.5 | 0 | 100
69 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Inayetpur and Ektarpur under Simurali (Zone-IX) W/S Scheme under Surface based Chakdah (Part) Water Supply Scheme under JJM under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000155/2023-2024 | 2114/NAD-I | 01/09/2023 | 15 | BIDYUT KUMAR | 30.26 | 0 | 100
70 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node 6 to node 382, node 340 to node 355 and providing FHTC (Functional Household Tap Connection) for augmentation work at Suturgachi, Simurali Railgate and Santipally in connection with augmentation of Simurali Zone-X W/S Scheme under Chakdah (Part) W/S Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl.no.17) | Assistant Engineer-II | Junior Engineer-III | ORD/000159/2023-2024 | 2117/NAD-I | 04/09/2023 | 21 | BUDDHADEV MONDAL | 74.38 | 0 | 100
71 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of approach road at the Head Work site of Goruimari W/S Scheme under Chakdah Surface PWSS under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000176/2024-2025 | 2111/NAD-I | 18/12/2024 | 236 | M/S LAXMI ENTERPRISE | 18.35 | 0 | 100
72 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between Inlet and outlet pipe and OHR and bypass arrangement at Joykrishnapur ( Zone- II ) under Chakdah surface water supply scheme inconnection with augmentation of Joykrishnapur W/S Scheme under JJM under Nadia Arsenic Division- I P.H.E Dte(Sl.no.15) | Assistant Engineer-II | Junior Engineer-III | ORD/000185/2023-2024 | 2156/NAD-I | 08/09/2023 | 21 | TARUN KUMAR BHATTACHARYA | 13.76 | 0 | 100
73 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between Washout/Overflowpipe and delivery pipe at Baeberia H/W site under Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of surface water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000257/2023-2024 | 516/AE-II/NAD-I | 05/12/2023 | 7 | BUDDHADEV MONDAL | 2.53 | 0 | 100
74 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of at Manosapota and Malichaghar at Chanduria under Chanduria (Zone-XI) W/S Scheme under Surface based Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000263/2023-2024 | 2725/NAD-I | 06/12/2023 | 21 | SUMAN CHAKRABORTY | 18.82 | 0 | 100
75 | Nadia Arsenic Division I | Nadia Arsenic Division I | Replacement of pipeline and allied works under Jal Jeevan Mission (JJM) for Chanduria area under Chakdah Block by augmentation of Surface Water Based W/S Scheme for arsenic affected areas of Chakdah (Part Block) of Nadia Dist. Zone-XI (Chanduria) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000280/2023-2024 | 10/AE-II/NAD-I | 04/01/2024 | 7 | PRADIP KUMAR BANIK | 2.68 | 0 | 100
76 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XI, Chanduria, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000008/2021-2022 | 772/NAD-I | 04/05/2021 | 60 | M/S NIBHAS SINHA | 95.81 | 62.04 | 100
77 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) |  |  | ORD/000211/2020-2021 | 283/NAD-I | 03/02/2021 | 90 | KINGS AND CO | 93.82 | 90.53 | 100
78 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-VI (Balia), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000096/2021-2022 | 1565/NAD-I | 13/12/2021 | 90 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 214.98 | 0 | 100
79 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV, Balia (Part-II) at Chak Amdanga, Silinda, Balia, Balarampur village at Chakdah Block retrofitting of Surface Water Based PWSS FOR Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.NO.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000145/2022-2023 | 3216/NAD-I | 30/11/2022 | 30 | BIDYUT KUMAR | 31.54 | 0 | 100
80 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline and retrofitting work at different loations i.e; Halalpur Krishnapur ,Madanpur,Goalpur,Beharia and Nabla Mouzas for smooth water supply in coneection with Retrofitting under JJM of Ground Water Based PWSS of Halalpur Krishnapur Zone-I W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E Dte.(sl.no.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000014/2023-2024 | 11118 / NAD-I | 27/04/2023 | 21 | CHOWDHURY & CO. | 23.38 | 0 | 0
81 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000080/2021-2022 | 1448/NAD-I | 12/11/2021 | 90 | DIVINE | 151.18 | 0 | 100
82 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing and renovation of Rising main and allied works at Halalpur Krishnapur Zone-I under Ranaghat-II, Block under Halalpur Krishnapur Zone-I Water Supply Scheme in the District of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000110/2022-2023 | 253/AE-I/NAD-I | 21/10/2022 | 15 | BUDDHADEV MONDAL | 0.93 | 0 | 100
83 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipe line at Jaffarnagar ,near Headwork Site under Raghunathpur Hijuli-I Gram Panchayet under Halalpur Zone-I Water Supply Scheme under Ranahghat -II Block under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000113/2022-2023 | 254/AE-I/NAD-I | 21/10/2022 | 15 | BUDDHADEV MONDAL | 0.96 | 0 | 100
84 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, pathway and other allied works at Head Work Tubewell site of Ground water based piped supply scheme of Halalpur-Krishnapur Zone-I Piped Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 138 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000134/2021-2022 | 76/NAD-I | 17/01/2022 | 20 | MONDAL ENTERPRISE | 9.94 | 0 | 100
85 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II form Puratan Chapra Primary School to Kharida Chapra Primary School at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2022-2023 | 57/AE-I/NAD-I | 17/01/2023 | 15 | BANERJEE ENTERPRISE | 3.88 | 0 | 99
86 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Pragati Sangha Club to Purba Para Kalimandir at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000264/2022-2023 | 142/AE-I/NAD-I | 29/03/2023 | 15 | CONSTRUCTURE | 3.63 | 0 | 100
87 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Purba Para Kalimandir to Paschim Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000265/2022-2023 | 143/AE-I/NAD-I | 29/03/2023 | 15 | CONSTRUCTURE | 3.38 | 0 | 100
88 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000013/2021-2022 | 147/NAD-I | 28/01/2022 | 0 | Resource Division | 1.99 | 0 | 0
89 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Zone-IX at North, South Chandmari, Muratipur at Kanchrapara G.P. by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-IX, Chandmari, Part-II under Nadia Arsenic Division-I , PHE Dte.(SL.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2023-2024 | 1465/NAD-I | 30/05/2023 | 21 | BUDDHADEV MONDAL | 22.58 | 0 | 0
90 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IX (Chandmari) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000111/2021-2022 | 1613/NAD-I | 28/12/2021 | 90 | SATYABRATA CHAKRABORTY | 248.68 | 0 | 100
91 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-III (Mosra), Part-II at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000091/2021-2022 | 1539/NAD-I | 06/12/2021 | 90 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 214.03 | 0 | 100
92 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur, Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000059/2021-2022 | 1417/NAD-I | 08/11/2021 | 60 | M/S R.K. ENTERPRISE | 65.48 | 0 | 100
93 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of Over Head Reservoir Painting at Gayeshpur Zone II WS Scheme in Santipur Block under NAD- I PHE Dte. (SL. NO. 04) | Assistant Engineer-I | Junior Engineer-II | ORD/000121/2022-2023 | 3024 / NAD-I | 07/11/2022 | 45 | BIDYUT KUMAR | 15.46 | 0 | 100
94 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara/JalSwapna for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000074/2021-2022 | 1434/NAD-I | 09/11/2021 | 90 | APURBA MANDAL | 117.48 | 0 | 100
95 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Rabonbor mouza near Shyamal Biswas house and near Sailen Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000189/2022-2023 | 86/AE-I/NAD-I | 06/02/2023 | 15 | BISWAS CONSTRUCTION | 4.64 | 0 | 100
96 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) at Nandighat, Sardarpara & Baganpara under Anulia G.P. under Parniamatpur Phase-II at Ranaghat-I Block by retrofitting Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.06) | Assistant Engineer-I | Junior Engineer-I | ORD/000191/2023-2024 | 2206/NAD-I | 13/09/2023 | 15 | SAORSA | 42.45 | 0 | 100
97 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Nandighat mouza (Jl No 126) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-I | Junior Engineer-I | ORD/000194/2023-2024 | 2240/NAD-I | 21/09/2023 | 21 | GANGULY ENTERPRISE | 11.86 | 0 | 100
98 | Nadia Arsenic Division I | Nadia Arsenic Division I | Charges of entry of household date in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(sl.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000250/2022-2023 | 241 / AE-I / NAD-I | 29/09/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 0 | 100
99 | Nadia Arsenic Division I | Nadia Arsenic Division I | Charges of entry of household date in JJM website along with Household Aadhar details and Geo tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl No.-03) | Assistant Engineer-I | Junior Engineer-I | ORD/000282/2022-2023 | 309 / AE-I / NAD-I | 30/12/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 0 | 0
100 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division- I, P.H.E. Dte. for the period from 15.07.2021 to 14.07.2022 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-I | ORD/000321/2021-2022 | 129 /AE-I/NAD-I | 14/07/2021 | 365 | SUMAN CHAKRABORTY | 4.27 | 0 | 100
101 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl.No. 03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000013/2022-2023 | 965/NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 78.62 | 0 | 40
102 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House Darrappur Z-VIA under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no. 06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000038/2022-2023 | 1531/ NAD-I | 30/08/2022 | 45 | MAA LAXMI ENTERPRISE | 17.21 | 0 | 100
103 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir, Boundary Wall, Switch Room and other allied works at Balia (Zone-VI) under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division ? I, P. H..E. Dte (SL NO. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000066/2023-2024 | 1367/NAD-I | 12/05/2023 | 30 | M/S COSMOPOLITAN TRADERS | 23.55 | 0 | 100
104 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Ballavpur Zone- VII under Surface (Sl.no.07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000098/2022-2023 | 1964 / NAD-I | 14/10/2022 | 45 | D.C. RAKSHIT & SONS INDIA PVT LTD | 29.25 | 0 | 100
105 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VI (BALIA) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000163/2021-2022 | 429/NAD-I | 07/03/2022 | 60 | BIDYUT KUMAR | 87.82 | 0 | 100
106 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballavpur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000177/2021-2022 | 514/NAD-I | 28/03/2022 | 60 | MANGES INDUSTRIAL CORPORATION | 125 | 0 | 100
107 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Lakshmipur and Srinagar under Ballavpur W/S Scheme in connection with augmentation of Ballavpur W/S Scheme under Chakdah (Part) W/S Scheme under JJM under NadiaArsenic Division-I, PHE Dte. (sl.no.18) | Assistant Engineer-II | Junior Engineer-IV | ORD/000200/2023-2024 | 2243/NAD-I | 21/09/2023 | 15 | MANGES INDUSTRIAL CORPORATION | 9.54 | 0 | 100
108 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000009/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 14.93 | 0 | 0
109 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation Work of Zone-IV (Uttar Duttapara) Part-III under JJM in connection with Surface Water based PWSS for Haringhata and Chakdah (Part) in Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte(sl.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000029/2023-2024 | 1253 / NAD-I | 04/05/2023 | 30 | CHOWDHURY & CO. | 95.64 | 0 | 0
110 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Balance Portion of Zone-XI (Birohi) and Zone-III (Jalkar Bhomra) in connection with Augmentation of Zone-III (Jalkar Bhomra) Part-III at Haringhata Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.1) | Assistant Engineer-I | Junior Engineer-I | ORD/000039/2023-2024 | 237 /AE-I/NAD-I | 18/05/2023 | 7 | BUDDHADEV MONDAL | 4.81 | 0 | 0
111 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting and Laying of D.I. (K9) Pipes at Kalyani More along (NH-34) in connection with Augmenation of Zone-IV (Uttar Duttapara) Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000040/2023-2024 | 238 /AE-I/NAD-I | 18/05/2023 | 7 | BUDDHADEV MONDAL | 4.56 | 0 | 0
112 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 900 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Jalkar Bhomra, Zone-III under Surface W/S Scheme of Haringhata-Chakdah Part under NAD I PHE Dte (Sl.no.09) | Assistant Engineer-I | Junior Engineer-I | ORD/000071/2022-2023 | 1702 / NAD-I | 09/09/2022 | 60 | GHOSH CONSTRUCTION | 33.26 | 0 | 100
113 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC Pipeline at different locations of Jalkar Bhomra(Zone-III),Madanpur(Zone-XII) and Birohi(Zone-XI) under Kastodanga-I & II, Madanpur-I & II and Birohi-I G.P. respectively under Haringhata & Chakdah (Part) Surface Water Supply scheme Under Nadia Arsenic Division-I,PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000077/2022-2023 | 89/ AE-I/NAD-I | 28/04/2022 | 15 | AVINABA ENGINEERING CONCERN | 4.82 | 0 | 100
114 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-III (Jalkar Bhomra) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte ( Sl No. 08) | Assistant Engineer-I | Junior Engineer-I | ORD/000157/2021-2022 | 424/NAD-I | 07/03/2022 | 60 | MONDAL ENTERPRISE | 90.02 | 0 | 100
115 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-IV (Uttar Duttapara) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. NO. 09) | Assistant Engineer-I | Junior Engineer-I | ORD/000158/2021-2022 | 425/NAD-I | 07/03/2022 | 60 | SARKAR AGENCY | 91.65 | 0 | 100
116 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofiting of work in Kastodanga -II, G.P. at Jalkar Bhomra (Zone-III) under Surface Water based PWSS for arsenic affected areas of Haringhata and Chakdah (Part) Block under Nadia Arsenic Division -I P.H.E. Dte. (Sl No.-06) | Assistant Engineer-I | Junior Engineer-I | ORD/000170/2022-2023 | 166 /AE-I/ NAD-I | 04/07/2022 | 15 | MONDAL ENTERPRISE | 4.84 | 0 | 100
117 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) and Recoonection at Ayeshpur,Sonakhali at Birohi-I G.P & Dakshin Rajapur at Birohi-II G.P under Jal Jeevan Mission (JJM) for Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Birohi under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000203/2023-2024 | 463/AE-I/NAD-I | 05/10/2023 | 30 | MANAJIT BISWAS | 3.99 | 0 | 100
118 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 600 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Uttar Duttapara, Zone-IV under Surface W/S Scheme of Haringhata-Chakdah (Part) under JJM under Nadia Arsenic Division - I P. H.E. Dte (sl.21) | Assistant Engineer-I | Junior Engineer-I | ORD/000266/2022-2023 | 830/NAD-I | 31/03/2023 | 21 | MS MAA BHABANI ENTERPRISE | 24.42 | 0 | 100
119 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 900 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Tarinipur, Zone-VIII under Surface W/S Scheme of Haringhata- Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no.08) | Assistant Engineer-II | Junior Engineer-III | ORD/000058/2022-2023 | 1639 / NAD-I | 06/09/2022 | 60 | REAL TIME | 33.3 | 0 | 100
120 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Kumarpur, Zone-VII under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I P.H.E Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III | ORD/000103/2022-2023 | 2064/NAD-I | 28/10/2022 | 45 | GANGULY ENTERPRISE | 13.95 | 0 | 100
121 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting of different dia D.I pipe and HDPE Pipe from the Office Premises of Nadia Arsenic Division -I to nearest Zone-VIII (Tarinipur) OHR site under Haringhata and Chakdah (Part) Surface Based W/S Scheme at Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000135/2022-2023 | 267/AE-I/NAD-I | 09/11/2022 | 15 | BUDDHADEV MONDAL | 3.46 | 0 | 100
122 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-VIII (Tarinipur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000155/2021-2022 | 422/NAD-I | 07/03/2022 | 60 | M/S K.P. CONSTRUCTION | 73.17 | 0 | 100
123 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone- VII, Kumarpur Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 15) | Assistant Engineer-II | Junior Engineer-III | ORD/000172/2021-2022 | 439/NAD-I | 07/03/2022 | 45 | MALI CONSTRUCTION | 39.65 | 0 | 100
124 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Zone-VIII (Tarinipur) under Augmentation work of Zone-VII (Kumarpur) and Zone-VIII (Tarinipur), Part-III at Santipur Block under Surface Water Based PWSS for Haringhata & Chakdah(Part) under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000197/2023-2024 | 2242/NAD-I | 21/09/2023 | 15 | NISHITH BANERJEE | 12.9 | 0 | 100
125 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC Pipeline and other allied works under JJM at Khalderpara, Babudangapara for Kumarpur Zone-VII at Haringhata Block by retrofitting work of Surface based W/S Scheme Water PWSS of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000242/2023-2024 | 529/AE-I/NAD-I | 24/11/2023 | 30 | M/S K..M. ENTERPRISE | 4.36 | 0 | 100
126 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) incluidng restoration of road for Tarinipur at Sarati G.P. at Kalyani under Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000243/2023-2024 | 530/AE-I/NAD-I | 24/11/2023 | 30 | M/S S.K ENTERPRISE | 4.85 | 0 | 100
127 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Nokari- Aishmali Road from CH. 2.95 Km. to CH. 6.20 Km. Restoration work arising out of damage of black top for laying of pipe line for "Integrated surface water besed PWSS for Ranaghat -I and Ranaghat -II, Block by Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00199/2024-2025 | 221/PFMS | 12/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 62.96 | 0 | 0
128 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Duttaphulia-Aranghata Road from CH. 35.00 Km. to CH. 40.00 Km. Restoration estimate due to excavations for underground Water Supply pipeline by Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00200/2024-2025 | 222/PFMS | 12/09/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 60.83 | 0 | 0
129 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Duttaphulia-Aranghata Road from CH. 40.00 Km. to CH. 44.766 Km. Restoration estimate due to the cause of excavations for underground Water Supply pipeline layout Proposal of PHE along the R/S of Quality Control sub-Division-I, under Nadia Highway Division-I, in the District Nadia during 2023-2024. | Assistant Engineer | Junior Engineer | BILL/00409/2024-2025 |  | 18/12/2024 | 0 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO.-II, PW (ROADS) DIRECTORATE. | 64.84 | 0 | 0
130 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work for revamping / upgradation of the hydraulic parameters of distribution network in reference to Raynagar and Joypur W/S Scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 75/NAD-I | 16/04/2025 | 153 | S B CONSTRUCTION | 57.7 | 0 | 75
131 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 127/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 96.3 | 0 | 0
132 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance Work for revamping / upgradation of the hydraulic parameters of distribution network towards Badkulla in reference to Raynagar and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 03) | Assistant Engineer | Junior Engineer | ORD/000020/2025-2026 | 138/NAD-I | 23/04/2025 | 60 | BUDDHADEV MONDAL | 95.86 | 0 | 0
133 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000025/2025-2026 | 154/NAD-I | 28/04/2025 | 60 | TAPU SAHA | 86.49 | 0 | 0
134 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing, Laying of Rising Main, Laying Distribution system and FHTC (Functional Household Tap Connection), Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr. Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials and construction of Pump house, Boundary Wall, Service and allied Works at head work & 2nd site at Raynagar Zone-II under Jal Jeevan Mission for Raynagar Zone-II Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000109/2023-2024 | 1765/NAD-I | 24/07/2023 | 366 | MINTU CHAKRABORTY | 337.06 | 0 | 0
135 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance Work to complete revamping/upgradation of the hydraulic parameters at distribution network at the part of Betna Mouza and Raynagar Mouza in reference to Raynagar PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (2nd Call) (Sl. NO. 02) | Assistant Engineer | Junior Engineer | ORD/000138/2025-2026 | 1043/NAD-I | 25/09/2025 | 120 | M/S A.K. CONSTRUCTION | 61.71 | 0 | 0
136 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Raynagar Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.06) | Assistant Engineer | Junior Engineer | ORD/000168/2022-2023 | 3288 / NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 8.5 | 0 | 100
137 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | "Providing Laying of Rising Main ,Laying distribution system and FHTC Soil investigation for the work of construction of 200 cum OHR staging heigjt 20 mtr , Construction of 200 cum capacity 20 mtr . staging hieght RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials and Construction of Pump house , Boundary Wall , Service and Allied Works at head work & 2nd site under Jal Jivan Mission for Raynagar Zone -II Water Supply Scheme within Ranaghat -I Block under Nadia Arsenic Division -I P.H.E.Dte." (Sl.no.02) | Assistant Engineer | Junior Engineer | ORD/000209/2023-2024 | 2292/NAD-I | 27/09/2023 | 730 | TAPU SAHA | 386.21 | 0 | 70
138 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | Assistant Engineer | Junior Engineer | ORD/000254/2024-2025 | 17/AE-1/NAD-I | 31/01/2025 | 181 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0
139 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000021/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 8.49 | 0 | 0
140 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Bill for Restoration work due to laying of pipe line on PMGSY road for HARADHAN GORAGACHA under WBSRDA Nadia division (Length 4.00 km.) under office of the Executive Engineer, Nadia Arsenic Division - I, PHE Dte. | Assistant Engineer | Junior Engineer | BILL/00232/2024-2025 | 277/PFMS | 30/09/2024 | 0 | EXECUTIVE ENGINEER, WBSRDA NADIA DIVISION | 25.08 | 0 | 0
141 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Repair of different type road different Water Supply Scheme under Shantipur block and Habibpur G.P. under Dakshin Bishnupur PWSS under Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 124/NAD-I | 22/04/2025 | 30 | RAKESH ENTERPRISE | 20.44 | 0 | 0
142 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation Work for Hiring of additional vehicle for supervision of JJM works including identification of land for JJM projects under Nadia Arsenic Division-I, P.H.E. Dte. W.e.f. 01/08/2025 to 31/01/2026. | Assistant Engineer | Junior Engineer | ORD/000108/2025-2026 | 110/AE-I/NAD-I | 31/07/2025 | 184 | OM TRANSPORT | 0.86 | 0 | 0
143 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE-100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle peice etc. all complete with Rising Main System incluidng specials & Valves & Laying of Distribution System including Specials, Valves & Pipe Supporting Structure, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials, Construction of Boundary Wall [H/W Site (160.0 m length), 2nd T/W Site (45.0 m length)], Pump House for H/W Site (4.88 M X 3.60 M), 2nd T/W Site (3.60 M X 3.0 M), Land Development and allied works with Approach Road (105.0 m Length and 3.0 m Wide), Restoration Work for Bituminous Road and Soil Investigation for the work of Construction of RCC Elevated Reservoir of capacity 300 m3 Staging Height 20 Mtr. at Ground Water Based PWSS for Dakshin Bishnupur in Ranaghat-I Block of Nadia District under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000108/2023-2024 | 1764/NAD-I | 24/07/2023 | 1096 | SUPRITI ENTERPRISE | 566.66 | 0 | 60
144 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Dakshin Bishnupur Water Supply Scheme atRanaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (sl.02) | Assistant Engineer | Junior Engineer | ORD/000172/2022-2023 | 47/ NAD-I | 09/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 5.28 | 0 | 100
145 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Augmentation for providing FHTC (Functional Household Tap Connection) at Narasinghanagar, Chapatala & Beharia Mouzas in Beharia PWSS and different Mouzas under Dakshin Bishnupur PWSS under Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000177/2024-2025 | 2173/NAD-1 | 30/12/2024 | 60 | SUMAN CHAKRABORTY | 96.23 | 0 | 0
146 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Collection of Household Details at prescribed Format through Mobile App/Hard Copy including Geo- Reference as directed by EIC and submission of same to PHE Dte in soft copy at different piped water supply scheme under Nadia Arsenic Division-I, PHED. Name of PWSS:- 1) Haringhata (Zone-I & II) 2) Gobindapur 3) Haringhata Zone-V Part-IV 4) CHakdah Zone-XII 5) Arranghata 6) Haringhata Zone-I, II & III 7) Par Naimatpur (Phase-I) 8) Par Naimatpur (Phase-II) 9) Par Naimatpur (Phase-III) 10) Ramnagar 11) Chakdah Zone-VI & VI A & VII 13) Sabdalpur 14) Haringhata Zone-II 15) Chakdah Zone-X 17) Haringhata Zone-I & Zone- II 18) Chakdah Zone-II & IV VII & VIII & X 19) Halalpur-Krishnapur 20) Dakshin Bishnupur. | Assistant Engineer | Junior Engineer | ORD/000178/2023-2024 | 380/AE-I/NAD-I | 31/08/2023 | 90 | TECH VISION | 4.89 | 0 | 100
147 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Culvert crossing including restoration of damaged pipeline including laying of dedicated pipeline towords Bagdia, Barajiakur & Bhatangachi Village (Babla GP, Dakshin Majdia) and allied works at Dakshin Bishnupur PWSS under Nadia Arsenic Division, PHE Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000196/2024-2025 | 2321/NAD-I | 15/01/2025 | 90 | CHOWDHURY & CO. | 24.28 | 0 | 100
148 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Supply of vehicle on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division-I, P.H.E. Dte. (Period from 15/01/2025 to 14/07/2025). | Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 05/AE-I/NAD-I | 14/01/2025 | 181 | SUMAN CHAKRABORTY | 0.86 | 0 | 0
149 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2022 to 14.07.2023 i.e. for 1(one) year. | Assistant Engineer | Junior Engineer | ORD/000255/2022-2023 | 172 / AE-I / NAD -I | 14/07/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 0 | 75
150 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Supply and installation of sign board related to JJM Matters at different piped water supply schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 07/AE-I/NAD-I | 04/01/2024 | 30 | BIBHAS PAL | 0.88 | 0 | 100
151 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation Work Order 1(One) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer, Nadia Arsenic Division-I, P.H.E. Dte. for the period from 15.07.2023 to 14.01.2024 i.e, for 6 months. | Assistant Engineer | Junior Engineer | ORD/000294/2023-2024 | 292/AE-I/NAD-I | 14/07/2023 | 184 | SUMAN CHAKRABORTY | 0.98 | 0 | 0
152 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000015/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 13.77 | 0 | 0
153 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000018/2023-2024 | 2106/NAD-I | 01/09/2023 | 0 | Resource Division | 72.02 | 0 | 0
154 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000051/2021-2022 | 1408/NAD-I | 08/11/2021 | 60 | SANDIP BISWAS | 68.26 | 0 | 100
155 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dhantala Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000108/2021-2022 | 1610/NAD-I | 28/12/2021 | 90 | UMWELT ENGINEER PVT. LTD. | 164.47 | 0 | 100
156 | Nadia Arsenic Division I | Nadia Arsenic Division I | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0
157 | Nadia Arsenic Division I | Nadia Arsenic Division I | Inter-Connection with M.S Pipeline to Distribution Pipeline of Surface Water Based Piped Water Supply Scheme for arsenic affected areas of Haringhata & Chakdah (Part) (Hapania Zone-II) under Haringhata Block under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Tender No.-04/NAD-I/2021-2022. | Assistant Engineer-I | Junior Engineer-II | ORD/000041/2021-2022 | 87/AE-I/NAD-I | 05/05/2021 | 30 | SATYABRATA CHAKRABORTY | 4.17 | 4.17 | 0
158 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying work of Upvc pipeline at Hapania,Singa, Thansara and other Mouzas under Nagarukhra -II G.P. under Zone-II (Hapania) under Surface Based Haringhata & Chakdah (Part) W/S Scheme under Haringhata Block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000078/2022-2023 | 88 /AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 100
159 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | Assistant Engineer-I | Junior Engineer-II | ORD/000205/2020-2021 | 154/NAD-I | 25/01/2021 | 60 | SATYABRATA CHAKRABORTY | 95.8 | 95.63 | 100
160 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ramnagar, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Ramnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000050/2021-2022 | 1407/NAD-I | 08/11/2021 | 60 | M/S PRADIP KUMAR PAL | 69.04 | 0 | 100
161 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Ramnagar Ground Based Water Supply Scheme under Hnaskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Ramnagar (Part-I) under JJM (Sl.no.08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000111/2023-2024 | 1773/NAD-I | 26/07/2023 | 15 | SUMAN CHAKRABORTY | 13.01 | 0 | 90
162 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey, Design Drawing & DPR Preparation for Augmentation of RAMNAGAR Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-1, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000122/2023-2024 | 318/AE-II/NAD-I | 14/07/2023 | 7 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT. LTD. | 4.4 | 0 | 100
163 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000014/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
164 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara, Zone-I, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000048/2021-2022 | 1405/NAD-I | 08/11/2021 | 60 | M/S UMA CONSTRUCTION | 63.86 | 0 | 100
165 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing, painting of Boundary wall, Pump House and other llied work at Ukhilnara Zone-II (2nd T/W Site) Water supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000075/2023-2024 | 291/AE-I/NAD-I | 12/07/2023 | 7 | GANGULY ENTERPRISE | 4.7 | 0 | 100
166 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-I | RTOR000006/2021-2022 | 139/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
167 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Chakdah Zone-I (Palagachha) at Chakdah Block by retrofitting of Ground Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000092/2021-2022 | 1540/NAD-I | 06/12/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 164.35 | 0 | 100
168 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting and repairing of clear water rising main and distribution pipeline from Palagacha more to Singher Bagan more along NH-34 of Surface based ChakdahW/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (sl.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000235/2022-2023 | 500 / NAD-I | 10/03/2023 | 21 | BUDDHADEV MONDAL | 32.9 | 0 | 100
169 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Madanpur) at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000118/2021-2022 | 11/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 378.71 | 0 | 100
170 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | Assistant Engineer-I | Junior Engineer-II | ORD/000022/2023-2024 | 1158 / NAD-I | 28/04/2023 | 21 | CHOWDHURY & CO. | 92.76 | 0 | 100
171 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Distribution Pipeline at Buddhapark Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-II | ORD/000080/2023-2024 | 1701/NAD-I | 13/07/2023 | 25 | M/S DIPAK ENTERPRISE | 93.64 | 0 | 100
172 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I | Junior Engineer-II | ORD/000081/2023-2024 | 1702/NAD-I | 13/07/2023 | 21 | M/S DIPAK ENTERPRISE | 89.84 | 0 | 100
173 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-X (Subarnapur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000112/2021-2022 | 1614/NAD-I | 28/12/2021 | 90 | GHOSH BROTHERS | 356.08 | 0 | 90
174 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Zone-IX (Chandmari) at Kanchrapara G.P. and Zone-X (Subarnapur) under Jal Jeevan Mission (JJM) by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) for Zone-X (Subarnapur) Part-II under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (SL.03) | Assistant Engineer-I | Junior Engineer-II | ORD/000236/2022-2023 | 501 / NAD-I | 10/03/2023 | 21 | BUDDHADEV MONDAL | 30.99 | 0 | 100
175 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD andallied works at OHR site under Matikumra Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Matikumra (Phase-I) Piped W/S Scheme (Sl.no.20) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000050/2023-2024 | 1449/NAD-I | 26/05/2023 | 15 | M/S DIPAK ENTERPRISE | 13.02 | 0 | 100
176 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of FHTC and Laying of balanced Pipeline at the command areas of Gayeshpur, Panpara (Part) and Matikumra Mouza under Matikumra Water Supply scheme Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000070/2025-2026 | 531/NAD-I | 03/07/2025 | 60 | M/S DIPAK ENTERPRISE | 49.93 | 0 | 0
177 | Nadia Arsenic Division I | Nadia Arsenic Division I | FHTC under Jaldhara/Jalswapna for Matikumra Phasa -I at Ranaghat -II Block by augmentation of Ground Water Based PWSS Matikumra Ws scheme under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000091/2022-2023 | 1938/NAD-I | 12/10/2022 | 90 | SATYABRATA CHAKRABORTY | 416.57 | 0 | 100
178 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000144/2024-2025 | 1882/NAD-I | 11/11/2024 | 180 | BALAJI UDDYOG | 129.1 | 0 | 0
179 | Nadia Arsenic Division I | Nadia Arsenic Division I | Reconnection at Ukhilnara Chowmatha, laying of pipeline from Ukhilnara Zone-I headwork site to Ukhilnara Chowmatha at Payrandanga G.P in Ukhilnara Zone-I PWSS & Reparing and laying of pipeline at Golabazar ,Matikumra Bazar and 2nd T/W site at Nokari G.P under Jal Jeevan Mission (JJM) for Ranaghat-I & Ranaghat-II Block by retrofitting of Ground Water based PWSS for Matikumra Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000299/2023-2024 | 90/AE-I/NAD-I | 22/02/2024 | 30 | GANGULY ENTERPRISE | 3.88 | 0 | 100
180 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHtC (Functional Household Tap Connection) under Jaldhara/jalswapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I ,PHE Dte | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | BILL/00189/2024-2025 | 213/PFMS | 26/09/2024 | 0 | GHOSH ENTERPRISE | 13.73 | 0 | 0
181 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Debagram ii)Dhantala iii)Dubli Zone-I iv)Dubli Zone-II v)Zone-IX (Chandmari) vi)Zone-XII (Madanpur) vii)Nabla | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000006/2023-2024 | 168/AE-I/NAD-I | 12/04/2023 | 15 | TECH VISION | 4.84 | 0 | 41
182 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000029/2025-2026 | 155/NAD-I | 28/04/2025 | 60 | GOUTAM DEY | 34.34 | 0 | 0
183 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 90 | GHOSH ENTERPRISE | 320.01 | 0 | 100
184 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of additional pipelines and FHTC at south west part of Betna W/S Scheme under JJM at Betna W/S Scheme inconnection with Betna and Debogram water supply scheme under Ranaghat - II block within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000059/2024-2025 | 1621/NAD-I | 27/09/2024 | 182 | M/S A.K. CONSTRUCTION | 68.67 | 0 | 75
185 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of existing pipelines at Debagram, Ranaghat-II Block in connection with providing FHTC undr JJM under Debagram W/S Scheme under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000072/2023-2024 | 1385/NAD-I | 16/05/2023 | 21 | GHOSH ENTERPRISE | 23.15 | 0 | 0
186 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well situated at the 3rd Tube Well site at Debogram Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000080/2024-2025 | 205/AE-II/NAD-I | 24/09/2024 | 7 | SUMAN CHAKRABORTY | 0.64 | 0 | 0
187 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000080/2025-2026 | 581/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 96.78 | 0 | 0
188 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting works at Debogramunder Debogram W/S Schemeunder JJM under Ranaghat- II Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000147/2023-2024 | 375/AE-II/NAD-I | 29/08/2023 | 7 | JYOTIRMOY ENTERPRISE | 3.76 | 0 | 100
189 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of Debagram, Ranaghat-II Block in connection with providing FHTC under Debagram W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000151/2023-2024 | 2096/NAD-I | 31/08/2023 | 15 | UMWELT ENGINEER PVT. LTD. | 23.14 | 0 | 100
190 | Nadia Arsenic Division I | Nadia Arsenic Division I | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000199/2024-2025 | 18/AE-I/NAD-I | 31/01/2025 | 89 | SUMAN CHAKRABORTY | 4.85 | 0 | 0
191 | Nadia Arsenic Division I | Nadia Arsenic Division I | Field Level Survey of different School/Anganwadi Centre (AWC) by GPs enabled Mobile Application for uploading of data at IMIS website in Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000220/2023-2024 | 467/AE-I/NAD-I | 09/10/2023 | 630 | TECH VISION | 1.15 | 0 | 100
192 | Nadia Arsenic Division I | Nadia Arsenic Division I | Renovation of IEP (155m3/hr.) at Debogram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000227/2023-2024 | 2298/NAD-I | 29/09/2023 | 491 | M/S DIPAK ENTERPRISE | 15.81 | 0 | 100
193 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Debagram Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Debagram W/S Scheme (Phase-I) under JJM(Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000297/2022-2023 | 719/NAD-I | 27/03/2023 | 15 | CHANDAN ROY | 12.95 | 0 | 100
194 | Nadia Arsenic Division I | Nadia Arsenic Division I | Continuation Work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000354/2023-2024 | 448/AE-I/NAD-I | 29/09/2023 | 91 | SUMAN CHAKRABORTY | 4.85 | 0 | 100
195 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000010/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 22.55 | 0 | 0
196 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I Part-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000073/2022-2023 | 1784/NAD-I | 22/09/2022 | 90 | MANGES INDUSTRIAL CORPORATION | 424.43 | 0 | 100
197 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Bhatbhanha, Kulgachi chak, Daluabari, Andipur Chak, Uttar Rameswarpur, Kalipur, Andipur, Kalinanagar, Kulgacchi Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- II ) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I , PHE Dte. (sl.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000263/2022-2023 | 831 / NAD-I | 31/03/2023 | 45 | MANGES INDUSTRIAL CORPORATION | 41.26 | 0 | 38
198 | Nadia Arsenic Division I | Nadia Arsenic Division I | Continuation Work order for ¿Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department in different Blocks of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.¿ | Assistant Engineer-II | Junior Engineer-III | ORD/000281/2022-2023 | 144/AE-I/NAD-I | 31/03/2023 | 90 | SUMAN CHAKRABORTY | 4.85 | 0 | 100
199 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/ Jal Swapna for matikumra Phase -II at Ranaghat -II Block by augmentation of Ground Water bassed PWSS for Matikumra Water Supply Sch. under Nadia Arsenic Division -I , P.H.E.Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000082/2022-2023 | 1769 / NAD-I | 20/09/2022 | 90 | KINGS AND CO | 436.53 | 0 | 65
200 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission for Madanpur at Madanpur-I G.P by retrofitting of Surface Water based Piped Water Supply Scheme for Haringhata- Chakdah(Part) in connection with retrofitting work ofZone-X (Subarnapur),Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.13) | Assistant Engineer-II | Junior Engineer-III | ORD/000022/2023-2024 | 1158 / NAD-I | 28/04/2023 | 21 | CHOWDHURY & CO. | 92.76 | 0 | 100
201 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration under for Madanpur-I and Madanpur-II GP at Kalyani Block under providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-IX (Chandmari) and Zone-XII, (Madanpur), Part-III at Chakdah Block by Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000032/2025-2026 | 166/NAD-I | 29/04/2025 | 30 | MANAJIT BISWAS | 31.06 | 0 | 100
202 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 410 cum Over Head Reservoir (Two Nos) Painting and repairing of H/W Boundary Wall, Pump House at Madanpur Zone-XII under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000070/2022-2023 | 1692 / NAD-I | 08/09/2022 | 45 | CHOWDHURY & CO. | 36.08 | 0 | 100
203 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Clear Water Rising Main at Majher Char Crossing at WBHDCL Road and other allied works under Jal Jeevan Mission (JJM) for Zone-X, (Subarnapur) at Subarnapur Mouza at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-X, (Subarnapur) Part-II under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000081/2023-2024 | 1702/NAD-I | 13/07/2023 | 21 | M/S DIPAK ENTERPRISE | 89.84 | 0 | 100
204 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Chandmari Zone-XI under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte | Assistant Engineer-II | Junior Engineer-III | ORD/000143/2022-2023 | 3154 / NAD-I | 25/11/2022 | 60 | NEERMAN | 25.87 | 0 | 99
205 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-XII (Madanpur) at Madanpur G.P at Chakdah block under Jal Jeevan Mission (JJM) by Augmentation of Surface Water Based PWSS for Haringhata-Chakdah (Part) for Zone-XII (Madanpur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL no-01) | Assistant Engineer-II | Junior Engineer-III | ORD/000171/2022-2023 | 37/AE-I/NAD-I | 07/01/2023 | 15 | BUDDHADEV MONDAL | 4.84 | 0 | 100
206 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII (Madanpur) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000173/2021-2022 | 464/NAD-I | 10/03/2022 | 60 | H I ENTERPRISE | 93.56 | 0 | 100
207 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chandmari) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 14) | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2021-2022 | 466/NAD-I | 10/03/2022 | 60 | CALCON CONSTRUCTION | 91.89 | 0 | 100
208 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XII at Madanpur I & II G.P at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-XII, Madanpur,Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III | ORD/000176/2022-2023 | 34/NAD-I | 17/01/2023 | 60 | CHOWDHURY & CO. | 96.1 | 0 | 90
209 | Nadia Arsenic Division I | Nadia Arsenic Division I | Grouting and Renovation of 700 cum capacity OverHead Reservoir at Chandmari,Zone-IX under Surface water supply scheme of Haringhata-Chakdah(Part) under Nadia Arsenic Division - I P. H.E. Dte (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000198/2023-2024 | 469/AE-I/NAD-I | 09/10/2023 | 30 | NEERMAN | 4.79 | 0 | 100
210 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, PrimarySchool, SSk & MSK under Jal Jeevan Mission (JJM) atHaringhata Block under Zone-IX (Chandmari) underAugmentation of Zone-IV (Chandmari) & Zone-XIIMadanpur, Part-III at Surface Water Based Water Suupply Scheme of Haringhata & Chakdah (Part)Water Supply Scheme of Haringhata & Chakdah (Part)under Nadia Arsenic Division-I, PHE Dte. (SL.NO.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000207/2022-2023 | 178/ NAD-I | 09/02/2023 | 21 | M/S KALIMATA ENTERPRISE | 20.46 | 0 | 100
211 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing domestic Water Supply to the 36 nos. temporary dwelling units constructed near Buddha Park, Kalyani for rehabilitation of families of Majher Char area including W/S at Sahidpally and Majherchar at Kanchrapara GP at Kalyani block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) W/S Scheme for Zone-XI Chandmari under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000232/2023-2024 | 2300/NAD-I | 29/09/2023 | 21 | M/S DIPAK ENTERPRISE | 12.7 | 0 | 100
212 | Nadia Arsenic Division I | Nadia Arsenic Division I | Structural stability report for repair/reconstruction of existing overhead reservoir at Baganchara Water Supply Scheme. | Assistant Engineer-I | Junior Engineer-II | BILL/00483/2023-2024 | 379/PFMS | 06/12/2023 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0
213 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000024/2024-2025 | 1079/NAD-I | 15/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 65
214 | Nadia Arsenic Division I | Nadia Arsenic Division I | DI Rising main line at Baganchara PWSS under Santipur Block in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000030/2024-2025 | 232/AE-I/NAD-I | 25/07/2024 | 623 | MANARAMA ENTERPRISE | 3.96 | 0 | 85
215 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Baganchra under Ground Water Based PWSS for Baganchra Water Supply Scheme at Santipur Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000036/2022-2023 | 221/AE-I/NAD-I | 02/09/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 0 | 100
216 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site for Baganchara Piped Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000040/2024-2025 | 1314/NAD-I | 22/08/2024 | 60 | K K MARKETING | 13.01 | 0 | 0
217 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE(PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall, Chlorine Room, and Approach Road (60.0m Length and 3.0m Wide) and Toilet at Head Work Site and 2nd T/W Site and Repair of 450 cum capacity Over Head Reservoir, Painting and Pump House at Ground Water Based Piped Water Supply Scheme for Baganchara in Santipur Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-I | Junior Engineer-II | ORD/000128/2023-2024 | 1896/NAD-I | 14/08/2023 | 731 | KINGS AND CO | 706.54 | 0 | 22
218 | Nadia Arsenic Division I | Nadia Arsenic Division I | MS pipeline connection with rising main, Over head reservoir including making provision for AIRP connection under Baganchhara PWSS, Shantipur block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000142/2024-2025 | 316/AE-I/NAD-I | 06/12/2024 | 30 | MANARAMA ENTERPRISE | 1.82 | 0 | 100
219 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well Situated at Head Site of Baganchara Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000304/2023-2024 | 69/AE-I/NAD-I | 12/02/2024 | 15 | PROGRESSIVE ENGINEERING & CONSTRUCTION | 0.64 | 0 | 100
220 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000026/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 30.8 | 0 | 0
221 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Muragachha Zone-II Ground Based Water Supply Scheme under Hanskhali Block under Nadia Arsenic Division-I,P.H.E Dte. in connection with Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Muragachha Zone-I & Zone-II Part-III at Hanskhali Block by Augmentation of Ground Water based PWSS for Muragachha Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000023/2024-2025 | 1135/NAD-I | 24/07/2024 | 60 | GHOSH & CO | 17.57 | 0 | 100
222 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Murgachha Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under 1304536.00 26091.00 Initially Nil, Rs. 1005/- per copy of tender document including 2911(ii) to be purchased by the successful bidder at 15 Days Page 3Muragachha Zone-I & II (Part-III) Piped W/S Scheme (sl.16) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000024/2023-2024 | 1160 / NAD-I | 28/04/2023 | 734 | SANJIB DEY | 13.05 | 0 | 100
223 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (104m3/hr) in connection with augmentation of Ground Water Based PWSS for Chupria Zone-I under Jal Jeevan Mission at Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000025/2024-2025 | 1118/NAD-I | 19/07/2024 | 180 | HARBAUER INDIA PRIVATE LIMITED | 265.04 | 0 | 0
224 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jalswapna / Jaldhara for Muragachha Z-I & II ( Part -III) at Hanskhali Block by Augmentation of Ground Water based pipe PWSS for Muragachha W/S Scheme. under Nadia Arsenic Division -I, P.H.E. Dte. (Sl .no. 06) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000124/2022-2023 | 2050 / NAD-I | 21/10/2022 | 831 | MONDAL PRECISION PRIVATE LIMITED | 282.77 | 0 | 100
225 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Muragachha Zone-II W/S Scheme under Hanskhali Block of capacity 75 cum/hr. under augmentation of Muragachha Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000142/2023-2024 | 2043/NAD-I | 24/08/2023 | 542 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 144.1 | 0 | 100
226 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Muragachha, Zone-I W/S Scheme under Hanskahli Block of capacity 65 cum/hr. under augmentation of Muragachha, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte (Sl.no.07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000145/2023-2024 | 2046/NAD-I | 24/08/2023 | 542 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 132.46 | 0 | 100
227 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-I, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000233/2023-2024 | 497/AE-I/NAD-I | 31/10/2023 | 7 | DAYANIDHI CONSTRUCTIONS | 0.97 | 0 | 100
228 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of damages pipeline and other allied work at 2nd site of Muragachha Zone-II, water supply scheme, Block- Hanskhali under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000234/2023-2024 | 498/AE-I/NAD-I | 31/10/2023 | 7 | M/S T.S. ENTERPRISE | 0.95 | 0 | 100
229 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (121cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-II, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte (Sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000141/2023-2024 | 2029/NAD-I | 23/08/2023 | 569 | MONDAL PRECISION PRIVATE LIMITED | 173.98 | 0 | 35
230 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (71cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Ramnagar, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.10) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000120/2023-2024 | 1795/NAD-I | 31/07/2023 | 30 | ASIT PRAMANIK | 93.55 | 0 | 0
231 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Contact Tank for Conversion of IEP to AIRP at Goalpur PWSS under Shantipur Block under Nadia Arasenic Division-I, P.H.E.Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000031/2024-2025 | 233/AE-I/NAD-I | 25/07/2024 | 189 | SATYABRATA CHAKRABORTY | 3.37 | 0 | 100
232 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Goalpur Zone-II, Ground Based Water Supply Scheme under Santipur under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte.in connection with Augmentation under JJM under Goalpur Zone-II, Part-III, Piped Water Supply Scheme (Sl.No.-35) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000110/2023-2024 | 1772/NAD-I | 26/07/2023 | 15 | MANISHIKA CONSTRUCTION | 13.04 | 0 | 100
233 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP of Ground Water Based Piped Water Supply Scheme for Goalpur Zone-II, (30 cum/hr) including augmentation of Matikumra Water Supply Scheme under Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000144/2024-2025 | 1882/NAD-I | 11/11/2024 | 180 | BALAJI UDDYOG | 129.1 | 0 | 0
234 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation Work at Umapur and Goalpur Mouzas at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Goalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000157/2023-2024 | 2115/NAD-I | 04/09/2023 | 15 | BUDDHADEV MONDAL | 50.03 | 0 | 100
235 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection inbetween new pump to rising main line , Pathway & delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-II water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000201/2023-2024 | 450/AE-I/NAD-I | 29/09/2023 | 30 | CONSTRUCTURE | 4.83 | 0 | 100
236 | Nadia Arsenic Division I | Nadia Arsenic Division I | Dedicated line at Dhakuria and delivery line from manifold to distribution line at Shantipur Block of ground water based PWSS for Goalpur Zone-I water supply scheme in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000202/2023-2024 | 451/AE-I/NAD-I | 29/09/2023 | 30 | M/S G.M ASSOCIATES | 4.82 | 0 | 100
237 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP at Goalpur Zone-I Water Supply Scheme under Shantipur Block of capacity 15 Cu.m/hr inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000237/2023-2024 | 2344/NAD-I | 03/10/2023 | 1062 | SATYABRATA CHAKRABORTY | 67.28 | 0 | 100
238 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (30cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nabla, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000127/2023-2024 | 1885/NAD-I | 11/08/2023 | 984 | APURBA MANDAL | 89.6 | 0 | 38
239 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000046/2023-2024 | 1364/NAD-I | 12/05/2023 | 15 | DEBASISH DEY | 12.2 | 0 | 100
240 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (119cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Beharia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000136/2023-2024 | 1880/NAD-I | 10/08/2023 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 158.74 | 0 | 100
241 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Muratipur at Kanchrapara G.P. and Hapania at Nagrukhra-II G.P. by retrofitting of surface water based PWSS Water Supply Scheme for Haringhata-Chakdah (Part) in connection with retrofitting work of Zone-II, Hapania Part-II under Nadia Arsenic Division-I, PHE Dte. (sl.02) | Assistant Engineer-I | Junior Engineer-II | ORD/000031/2023-2024 | 1255 /NAD-I | 04/05/2023 | 30 | BUDDHADEV MONDAL | 37.15 | 0 | 0
242 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-II (Hapania) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000109/2021-2022 | 1611/NAD-I | 28/12/2021 | 90 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 404.05 | 0 | 100
243 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying UPVC pipeline at different location of Z-II ( Hapania ) under Nagarukhra -I & II G.P. under Surface Based Haringhata & Chakdah (Part) Surface Water Supply scheme under Nadia Arsenic -I, P.H.E. Dte. (01) | Assistant Engineer-I | Junior Engineer-II | ORD/000112/2022-2023 | 88 / AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 100
244 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | Assistant Engineer-I | Junior Engineer-II | ORD/000221/2022-2023 | 303 /NAD-I | 27/02/2023 | 60 | MONDAL ENTERPRISE | 96.62 | 0 | 74
245 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, Shimurali, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000022/2021-2022 | 865/NAD-I | 15/06/2021 | 60 | ALOK ENTERPRISE | 80.87 | 0 | 100
246 | Nadia Arsenic Division I |  | Hiring of 1 (One) no Diesel Luxury Taxi/Maxi Cab/Motor Cab on Daily basis for monitoring of JJM works and progress of JJM works (Such as identification of land etc) under the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000182/2023-2024 | 383/AE-I/NAD-I | 01/09/2023 | 182 | ANURADHA DHARA | 2.4 | 0 | 20
247 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 40.97 | 100
248 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukilnara Zone - II at Ranaghat - I Block by retrofitting of Ground Water based PWSS for Ukilnara - Zone - II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl. No.-08) Tender No. 234/NAD-I/2020-2021. |  |  | ORD/000189/2020-2021 | 292/NAD-I | 04/02/2021 | 45 | M/S UMA CONSTRUCTION | 43.74 | 0 | 100
249 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. -01) Tender no.- 230/NAD-I/2020-2021. |  |  | ORD/000192/2020-2021 | 290/NAD-I | 04/02/2021 | 45 | CHANDAN ROY | 43.9 | 0 | 100
250 | Nadia Arsenic Division I |  | Supply of 1(one )no. Motor Cab ( Luxury Taxi) on hire basis for official use of the Executive Engineer , Nadia Arsenic Division -I, P.H.E.Dte. for the period from ( 15.07.22 to 14.07.23i.e. for 1(one) year .(sl.01) |  |  | ORD/000304/2021-2022 | 173 / AE-I/NAD-I | 14/07/2021 | 365 | AVINABA ENGINEERING CONCERN | 5.34 | 0 | 100
251 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I, Ukhilnara -II, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000391/2020-2021 | 292 / NAD-I | 04/02/2021 | 45 | M/S UMA CONSTRUCTION | 43.74 | 0 | 60
252 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara Jal Swapna for Zone IX Ghetugachi Part II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte |  |  | ORD/000018/2021-2022 | 783/NAD-I | 05/05/2021 | 60 | TAPU SAHA | 68.94 | 62.74 | 100
253 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, Balagarichar, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000010/2021-2022 | 774/NAD-I | 04/05/2021 | 60 | PALCON | 39.63 | 37.17 | 100
254 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XII, Balagarichar, Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000011/2021-2022 | 775/NAD-I | 04/05/2021 | 60 | PRIYA CONSTRUCTION | 66.11 | 58.7 | 100
255 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000023/2021-2022 | 954/NAD-I | 09/07/2021 | 90 | TARUN KUMAR BHATTACHARYA | 182.15 | 57.19 | 100
256 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (Darrappur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No.- 217/NAD-I/2020-2021. |  |  | ORD/000168/2020-2021 | 277/NAD-I | 03/02/2021 | 90 | H I ENTERPRISE | 90.31 | 88.74 | 100
257 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway and Toilet at 2nd, 3rd and 4th Tubewell site of Aranghata and 3rd site of Debogram water supply Scheme in Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. Under JJM. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000029/2025-2026 | 155/NAD-I | 28/04/2025 | 60 | GOUTAM DEY | 34.34 | 0 | 0
258 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-I Phase-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000093/2021-2022 | 1541/NAD-I | 06/12/2021 | 90 | JOY HIND TUBE WELLS | 123.89 | 0 | 100
259 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Head work site to Shibnarayanpur and allied works in reference to Aranghata Zone-I water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (2nd Call) [Sl. No. 04] | Assistant Engineer-II | Junior Engineer-III | ORD/000106/2025-2026 | 720/NAD-I | 29/07/2025 | 60 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 49.04 | 0 | 0
260 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) at Patkabari, Hatibanda and Uttor Bishnupur under Jaldhara Jal Swapna from Arranghata Zone-I PWSS Part-III at Ranaghat-II Block by retrofitting under under Nadia Arsenic Division- I, P.H.E Dte. (Sl. No. 14) | Assistant Engineer-II | Junior Engineer-III | ORD/000130/2022-2023 | 3044/NAD-I | 09/11/2022 | 30 | M/S R.K. ENTERPRISE | 32.39 | 0 | 100
261 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway OHR Repair and other allied work in connection with Augmentation of Arranghata Zone-I water supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I,P.H.E. Dte. (sl.no.16) | Assistant Engineer-II | Junior Engineer-III | ORD/000244/2022-2023 | 569/NAD-I | 16/03/2023 | 60 | REAL TIME | 59.28 | 0 | 100
262 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Bhayna Zone-I Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000117/2021-2022 | 10/NAD-I | 05/01/2022 | 90 | TARUN KUMAR BHATTACHARYA | 202.09 | 0 | 100
263 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Bhayna Zone-I water supply scheme in Hanskhali Block in Nadia District under JJM under Nadia Arsenic Division-I , PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2023-2024 | 427/AE-I/NAD-I | 20/09/2023 | 30 | PALCON | 1.5 | 0 | 100
264 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000017/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
265 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of exisiting Tube Well Situated at 2nd Tube Well Site of Saguna Water Supply Scheme in connection with Jal Jeevan Mission under Santipur Block to increase the yield of the tube well under Nadia Arsenic Division-I P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000012/2024-2025 | 192/AE-I/NAD-I | 21/06/2024 | 15 | APURBA MANDAL | 0.64 | 0 | 0
266 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000056/2021-2022 | 1413/NAD-I | 08/11/2021 | 60 | M/S TARAK CHANDRA PAUL | 79.19 | 0 | 100
267 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Boalia at Santipur Block by retrofitting of Ground Water based PWSS for Boalia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000090/2021-2022 | 1538/NAD-I | 06/12/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 430.7 | 0 | 100
268 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000016/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
269 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Itaberia at Hanskhali Block by retrofitting of Ground Water based PWSS for Itaberia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000052/2021-2022 | 1409/NAD-I | 08/11/2021 | 60 | CHANDAN ROY | 89.54 | 0 | 100
270 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey, Design Drawing for Augmentation of ITABERIA Water Supply Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000266/2023-2024 | 494/AE-II/NAD-I | 24/11/2023 | 7 | SUMAN CHAKRABORTY | 2.83 | 0 | 100
271 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 50
272 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000057/2021-2022 | 1415/NAD-I | 08/11/2021 | 60 | M/S S.CHOUDHURY | 84.96 | 0 | 100
273 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Ghetugachi G.P for Surface water based P.W.S.S for Chakdah ( Part ) in connection with providing FHTC at Barberia ( Zone- VIII ) Part- II under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000091/2023-2024 | 1685/NAD-I | 12/07/2023 | 21 | TAPAS GHOSH | 22.22 | 0 | 100
274 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000119/2021-2022 | 12/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 299.45 | 0 | 98
275 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 800 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Barberia Zone-VIII under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000123/2022-2023 | 1385/NAD-I | 12/08/2022 | 45 | TARUN KUMAR BHATTACHARYA | 32.36 | 0 | 100
276 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Mukundupur of Balagarichar W/S Scheme and Dakshin Panchpota, Kadambagachi of Barberia W/S Scheme in connection with providing FHTC Zone-VIII (Barberia) Part-II under Barberia W/S Scheme under Jal Jeevan Mission under Chakdah (Part) W/S Scheme under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.10) | Assistant Engineer-II | Junior Engineer-III | ORD/000189/2023-2024 | 2154/NAD-I | 08/09/2023 | 764 | SUMAN CHAKRABORTY | 91.29 | 0 | 100
277 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection in between outlet pipe of OHR and delivery main at different H/W site in Chakdah SurfaceWater Based PWSS at Chakdah Block under JJM under Nadia Arsenic Division-I,PHE Dte. (sl.15) | Assistant Engineer-II | Junior Engineer-III | ORD/000259/2022-2023 | 826/NAD-I | 31/03/2023 | 45 | BIPLAB GUHA | 39.73 | 0 | 58
278 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Paschim Sambhupur mouza (JI No 133) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2023-2024 | 163/AE-I/NAD-I | 10/04/2023 | 15 | GANGULY ENTERPRISE | 0.97 | 0 | 0
279 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Sibpur mouza (JI No 134) under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000002/2023-2024 | 164/AE-I/NAD-I | 10/04/2023 | 15 | MS ENTERPRISE | 0.97 | 0 | 100
280 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Dakshin Haradham mouza (JI No 137) under Jal Jeevan Mission (JJM) for parniamatpur Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000003/2023-2024 | 165/AE-I/NAD-I | 11/04/2023 | 15 | MS ENTERPRISE | 0.97 | 0 | 0
281 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Parniamatpur, Phase-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Parniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000064/2021-2022 | 1418/NAD-I | 08/11/2021 | 60 | TAPU SAHA | 69.94 | 0 | 99
282 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Rabonbor mouza near Sampa Biswas house and near Abodh Halder house under Parniamatpur Water Supply Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-II under Nadia Arsenic Division-I, P.H.E. Dte. (SL No-2) | Assistant Engineer-I | Junior Engineer-I | ORD/000188/2022-2023 | 85/AE-1/NAD-I | 06/02/2023 | 15 | GANGULY ENTERPRISE | 4.83 | 0 | 100
283 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Haradham village under Parniamatpur W/S Scheme under Ranaghat-I Block under Providing FHTC under Jal Jeevan Mission (JJM) for Parniamatpur Phase-I under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000192/2022-2023 | 84/AE-1/NAD-I | 03/02/2023 | 15 | AURGHA BHATTACHARYA | 2.05 | 0 | 100
284 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-I | RTOR000010/2021-2022 | 143/NAD-I | 28/01/2022 | 0 | Resource Division | 0.8 | 0 | 0
285 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping/upgradation of the hydraulic parameters at Hatisala and Goalsalua mouzas in reference to Goalsalua mouzas in reference to Goalsalua W/S Scheme under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000036/2025-2026 | 170/NAD-I | 29/04/2025 | 60 | PAPAN ROY | 44.03 | 0 | 0
286 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Goalsalua Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Goalsalua Zone-I under JJM.(sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000041/2023-2024 | 1123 / NAD-I | 27/04/2023 | 15 | MANAJIT BISWAS | 13.03 | 0 | 100
287 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua, Zone-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000046/2021-2022 | 1403/NAD-I | 08/11/2021 | 45 | BIDYUT KUMAR | 53.89 | 0 | 100
288 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall at H/W site of Goalsalua, Zone-I Water Supply Scheme under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 208 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000131/2021-2022 | 72/NAD-I | 17/01/2022 | 30 | NISHITH BANERJEE | 19.68 | 0 | 100
289 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing & other allied works near Bankim Nagar station (BNCA to PNCB) in between Mast No - 77/24 and 77/26 in the district of Nadia to provide FHTC at Kesaipur under Goalsalua PWSS under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (2nd Call) [Sl. No. 03] | Assistant Engineer-II | Junior Engineer-III | ORD/000141/2025-2026 | 1042/NAD-I | 25/09/2025 | 90 | SUMAN CHAKRABORTY | 39.44 | 0 | 0
290 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of additional pipeline for providing FHTC (Functional Household Tap Connection)at Salua Gatepara & pipeline connection with Manifold under JJM at Ranaghat-II Block of Ground Water Based PWSS for Goalsalua Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000165/2024-2025 | 327/AE-II/NAD-I | 09/12/2024 | 15 | GOUTAM DEY | 4 | 0 | 0
291 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Pathway and all repair works at 2nd T/W Site and all repair works at H/W site of Saguna under Nadia Arsenic Division-I, PHE Dte. ( Sl.no 11) | Assistant Engineer-I | Junior Engineer-I | ORD/000053/2022-2023 | 1592 / NAD-I | 06/09/2022 | 45 | PAPAN ROY | 11.31 | 0 | 85
292 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting pipeline works for providing FHTC (Functional Household Tap Connection) at Aluipara & Srirampur para under JJM at Shantipur Block of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-I | Junior Engineer-I | ORD/000057/2024-2025 | 1543/NAD-I | 23/09/2024 | 405 | TAPAS GHOSH | 10.69 | 0 | 80
293 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir and other allied works at Paschim Noapara W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte.(Sl.no.07) | Assistant Engineer-I | Junior Engineer-I | ORD/000069/2022-2023 | 1443/NAD-I | 17/09/2022 | 45 | MONDAL ENTERPRISE | 12.83 | 0 | 100
294 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir and other allied works at Saguna WS Scheme in Santipur Block under NAD I PHE Dte (Sl.no.04) | Assistant Engineer-I | Junior Engineer-I | ORD/000105/2022-2023 | 2049 / NAD-I | 21/10/2022 | 45 | M/S ARATI ENTERPRISE | 14.01 | 0 | 100
295 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Pathway and all repair works at 2nd T/W site and all repair works at H/W site of Paschim Noapara W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.02) | Assistant Engineer-I | Junior Engineer-I | ORD/000111/2022-2023 | 2009/NAD-I | 19/10/2022 | 30 | J & T ENTERPRISE | 6.93 | 0 | 100
296 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Saguna Part-III at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-I | Junior Engineer-I | ORD/000169/2021-2022 | 437/NAD-I | 07/03/2022 | 60 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD. | 63.41 | 0 | 100
297 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Paschim Noapara, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000180/2021-2022 | 517/NAD-I | 28/03/2022 | 60 | GHOSH BROTHERS | 171.71 | 0 | 100
298 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Hijuli, Ghoshpara, Aluipara & adjacent areas of Shantipur Block by retrofitting of Ground Water Based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000273/2023-2024 | 2744/NAD-I | 08/12/2023 | 705 | DEBASIS SAMADDAR | 57.4 | 0 | 70
299 | Nadia Arsenic Division I | Nadia Arsenic Division I | Pipeline connection with Manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block under Ground Water based PWSS for Saguna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000302/2023-2024 | 95/AE-I/NAD-I | 27/02/2024 | 15 | ROY ASSOCIATES | 2.89 | 0 | 100
300 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Chupria Zone-I ii)Garapota iii)Itaberia iv)Muragachha Zone-I v)Muragachha Zone-II vi)Zone-I (Palagachha) vii)Zone-II (joykrishnapur) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000007/2023-2024 | 169/AE-I/NAD-I | 12/04/2023 | 1275 | TECH VISION | 4.84 | 0 | 100
301 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-I Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-I W/S Scheme under JJM (SL.NO.12) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000015/2023-2024 | 1116 / NAD-I | 27/04/2023 | 15 | SAHA CONSTRUCTION &CO | 13.05 | 0 | 100
302 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Chupria (Zone -I) Part -I at Hanskhali Block by retrofitting of Grond Water based PWSS for CHUPRIA Water Supply Sceme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000066/2022-2023 | 1673 / NAD-I | 07/09/2022 | 539 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 565.67 | 0 | 85
303 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and other allied work at H/W Site (Length-135.0 m) and 2nd T/W Site (Length-55.0m) in Chupria Zone-I water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. (SL.NO.17) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000183/2022-2023 | 104 / NAD-I | 31/01/2023 | 45 | GOPAL KIRTYANIA | 24.03 | 0 | 40
304 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Chupria Zone-I under Jal Jeevan Mission (JJM) for Chupria Zone-I W/S Scheme at Hanskhali Block in connection with augmentation of Ground Water based W/S Scheme for Chupria Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.19) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000184/2023-2024 | 2155/NAD-I | 08/09/2023 | 21 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 71.93 | 0 | 80
305 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-I under Surface W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, P. H.E. Dte (Sl. No.16) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000190/2022-2023 | 153/NAD-I | 07/02/2023 | 30 | PAPAN ROY | 13.66 | 0 | 100
306 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-IV, (Rukminidanga), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000003/2022-2023 | 644/NAD-I | 29/04/2022 | 336 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT LTD. | 359.23 | 0 | 100
307 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Rukminidanga ZoneV at under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000060/2022-2023 | 1596/NAD-I | 06/09/2022 | 60 | SAHA ENGINEERS | 28.04 | 0 | 100
308 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000005/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 26.12 | 0 | 0
309 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Kamargaria & Debogram Village in connection with Debagram Water Supply Scheme within Nadia Arsenic Division-I, PHE Dte under Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000027/2025-2026 | 157/NAD-I | 28/04/2025 | 60 | M/S A.K. CONSTRUCTION | 82.68 | 0 | 0
310 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/JalSwapna for Debogram Phase-II at Ranaghat-II Block by augmentation of Ground Water based PWSS for Debogram Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000049/2022-2023 | 1688/NAD-I | 08/09/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 399.59 | 0 | 99
311 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Sijdia, Dakhin Rameswarpur,Anatapur, Mithapur & aismali Village in connection with Debagram Water Supply Scheme under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000080/2025-2026 | 581/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 96.78 | 0 | 0
312 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of additional pipelines under JJM at Garapota W/S Scheme in connection with Debagram W/ Scheme under Ranaghat-II block within Hanskhali Block Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000306/2024-2025 | 229/AE-II/NAD-I | 12/11/2024 | 15 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 4.85 | 0 | 0
313 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of AIRP capacity (111m3/hr) in connection with augmentation of Ground Water Based PWSS for Baganchara under Jal Jeevan Mission at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000024/2024-2025 | 1079/NAD-I | 15/07/2024 | 180 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 278.95 | 0 | 65
314 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Nabla Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Nabla Part-III Piped W/S Scheme (sl.no.21) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000026/2023-2024 | 1162 / NAD-I | 28/04/2023 | 15 | CHOWDHURY & CO. | 13.07 | 0 | 100
315 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site for Gayeshpur Zone-I & Gobindapur Zone-I PWSS at Shantipur Block providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for PWSS for Boalia, Nabla, Gayeshpur W/S Schemes under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000042/2024-2025 | 1338/NAD-I | 23/08/2024 | 300 | B.S. ENTERPRISE | 26.73 | 0 | 65
316 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline including providing FHTC at Goalpur and Boalia W/S Scheme, Shnatipur Block under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 05) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000058/2024-2025 | 1566/NAD-I | 26/09/2024 | 495 | CONSTRUCTURE | 13.85 | 0 | 78
317 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000065/2022-2023 | 1672 / NAD-I | 07/09/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 0 | 70
318 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000131/2023-2024 | 1899/NAD-I | 14/08/2023 | 691 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 70
319 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Boalia, Part-III at Santipur Block bY Augmentation of Ground Water Based PWSS for Boalia W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-I, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Providing FHTC under Jal Jeevan Mission (JJM) for Gayeshpur Zone-II, Part-III at Santipur Block by Augmentation of Ground Water Based PWSS for Gayeshpur W/S Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Boalia Water Supply Scheme within Santipur Block, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-I Water Supply Scheme, Construction of Boundary wall, Toilet, Pathway and other allied work at Gayeshpur Zone-II Water Supply Scheme, Repair of 550 cum capacity Over Head Reservoir and other allied works at Boalia water supply scheme AND Repair of 250 cum capacity Over Head Reservoir and other allied works at Gayeshpur Zone-I water supply scheme underNadia Arsenic Division-I , PHE Dte. (Sl.no. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000102/2023-2024 | 1697/NAD-I | 13/07/2023 | 1095 | JAL PRAVHAHIKA PVT. LTD., | 493.44 | 0 | 45
320 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of Manifold and allied works at OHR site under for Goalpur Zone-I PWSS including augmentation works under Gayeshpur Zone-I PWSS at Shantipur Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000137/2024-2025 | 1968/NAD-I | 28/11/2024 | 300 | M/S DREAM INFRASTRUCTURE | 16.83 | 0 | 80
321 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000012/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 6.22 | 0 | 0
322 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000027/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 4.31 | 0 | 0
323 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of Pipeline for FHTC works under Surface Water Based PWSS Saguna Zone-VI (Part-II) for arsenic affected areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000020/2024-2025 | 1117/NAD-I | 19/07/2024 | 300 | APURBA MANDAL | 95.96 | 0 | 85
324 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying Of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction Of Boundary Wall (675m Length), Chlorine Room, Drain (I300 m Length) and Approach Road (60.0m Length and 3.0m Wide),Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials and Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 600 m3 Staging Height 20Mtr. at Surface Water Based Piped Water Supply Scheme for Saguna ZONE-VI (PART-II) in Chakdah Block of Nadia Districtunder Nadia Arsenic Division-I, PHE Dte. (Sl.no.09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000105/2023-2024 | 1690/NAD-I | 13/07/2023 | 1095 | APURBA MANDAL | 529.72 | 0 | 30
325 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Zone-VI (Saguna) Part -II of Surface Water Based PWSS for Haringhata and Chakdah (Part) at Chakdah Block at Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(Sl.No.-02) | Assistant Engineer-II | Junior Engineer-IV | ORD/000243/2022-2023 | 169 / AE-I/NAD-I | 08/07/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.81 | 0 | 100
326 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000019/2023-2024 | 02/NAD-I | 02/01/2024 | 0 | Resource Division | 128.4 | 0 | 0
327 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000025/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 18.48 | 0 | 0
328 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Goalsalua Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Goalsalua Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000129/2021-2022 | 77/NAD-I | 17/01/2022 | 90 | M/S NIBHAS SINHA | 110.34 | 0 | 100
329 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, pathway and others allied works at Head Work site of Goalsalua, Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 156 metre. | Assistant Engineer-II | Junior Engineer-III | ORD/000133/2021-2022 | 73/NAD-I | 17/01/2022 | 30 | D.K. CONSTRUCTION | 17.59 | 0 | 95
330 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying Dedicated Pipe line to supply water for Pachberia Coloni Area under Goalsalua Zone II Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 06) | Assistant Engineer-II | Junior Engineer-III | ORD/000168/2024-2025 | 1949/NAD-I | 27/11/2024 | 480 | BIPLAB GUHA | 70.82 | 0 | 52
331 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentaton of Distribution pipeline at Rajapur , Kesaipur village under Goalsalua Zone II water supply scheme at Ranaghat-II Block by providing FHTCs & dedicated pipeline from common manifold under Nadia Arsenic Division-I, PHE Dte as a part of JJM. (Sl. NO. 05) | Assistant Engineer-II | Junior Engineer-III | ORD/000170/2024-2025 | 2057/NAD-I | 09/12/2024 | 60 | SUMIT GHOSH | 91.9 | 0 | 0
332 | Nadia Arsenic Division I |  | SHIFTING OF POLE AT GANGNAPUR PHE |  |  | BILL/00124/2024-2025 | 100/PFMS | 11/07/2024 | 0 | W.B.S.E.D.C.L (GANGNAPURC.C.C) | 0.41 | 0 | 0
333 | Nadia Arsenic Division I |  | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-32 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00131/2023-2024 | 147/PFMS | 04/07/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.91 | 0 | 0
334 | Nadia Arsenic Division I |  | Bill for Wayleave/Track crossing proposal with Application ID ER-SDAH-2023-WL-31 in IR-RBCS has been approved in-principle subject to the payment of Wayleave facility. |  |  | BILL/00132/2023-2024 | 146/PFMS | 04/07/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 6.15 | 0 | 0
335 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-49 in IR-RBCS is pending for payment. |  |  | BILL/00191/2023-2024 | 179/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.15 | 0 | 0
336 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-50 in IR-RBCS is pending for payment. |  |  | BILL/00192/2023-2024 | 178/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.22 | 0 | 0
337 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-51 in IR-RBCS is pending for payment. |  |  | BILL/00193/2023-2024 | 180/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.3 | 0 | 0
338 | Nadia Arsenic Division I |  | Your Wayleave/Track crossing proposal with application ID ER-SDAH-2023-WL-52 in IR-RBCS is pending for payment. |  |  | BILL/00194/2023-2024 | 177/PFMS | 04/08/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
339 | Nadia Arsenic Division I |  | Bill for Taherpur flag to Badkulla station railway crossing for JJM works under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00273/2023-2024 | 220/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.25 | 0 | 0
340 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-49 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00278/2023-2024 | 221/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 9.96 | 0 | 0
341 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-50 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00279/2023-2024 | 240/PFMS | 20/09/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 14.94 | 0 | 0
342 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-51 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00381/2023-2024 | 340/PFMS | 13/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 19.06 | 0 | 0
343 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00438/2023-2024 | 345/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
344 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00439/2023-2024 | 346/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
345 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00440/2023-2024 | 347/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
346 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00441/2023-2024 | 348/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.07 | 0 | 0
347 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 in IR-RBCS has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00442/2023-2024 | 349/PFMS | 23/11/2023 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 0.32 | 0 | 0
348 | Nadia Arsenic Division I |  | Shifting of Electric Pole from the proposed GLR Site inside the Campus of water Management Research Station, Begopara (Patuli) Ranaghat-II Block, under Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00506/2023-2024 | 396/PFMS | 18/12/2023 | 0 | WBSEDCL | 0.06 | 0 | 0
349 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-71 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00561/2023-2024 | 437/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.35 | 0 | 0
350 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-72 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00562/2023-2024 | 438/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0
351 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-73 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00563/2023-2024 | 439/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 5.27 | 0 | 0
352 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-74 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00564/2023-2024 | 441/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 4.93 | 0 | 0
353 | Nadia Arsenic Division I |  | Your wayleave / Track crossing Proposal with Application ID ER-SDAH-2023-WL-75 has been approved in wayleave facility charges under office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. |  |  | BILL/00565/2023-2024 | 442/PFMS | 12/01/2024 | 0 | FA & CAO, EASTERN RAILWAY, KOLKATA | 20.56 | 0 | 0
354 | Nadia Arsenic Division I |  | Carriage of DI pipes including Pipe carrying structure, road restoration, repair of damaged UPVC pipeline, crossing of pipeline by jack pushing, pathway and allied works related to Integrated Surface Water Based Water Supply Scheme under Ranaghat-I & II Blocks under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) |  |  | ORD/000111/2025-2026 | 786/NAD-I | 12/08/2025 | 120 | AMAL DUTTA ROY | 559.99 | 0 | 0
355 | Nadia Arsenic Division I |  | Supply of documents for way leave permission from the Eastern Railways authority at 2 nos of locations on Ranaghat-Krishnagar, Ranaghat -Shantipur&Ranaghat-Bongaon Railway track under Intregrated surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. Intersection Name: 1) AV24- AV28 Birnagar Rail Gate) 2) AV61- AV64 Taherpur Rail Gate) |  |  | ORD/000114/2023-2024 | 309/AE-I/NAD-I | 28/07/2023 | 90 | SUMAN CHAKRABORTY | 3.84 | 0 | 100
356 | Nadia Arsenic Division I |  | Preparation of Detailed Project Report (DPR) for Integrated Surface Water Based PWSS for Ranaghat-I & Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.03) |  |  | ORD/000116/2023-2024 | 1610/NAD-I | 22/06/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 57.65 | 0 | 100
357 | Nadia Arsenic Division I |  | Laying of DI Rising Main of Ranaghat I & II Block, Construction of 4 Nos. 100 Cum GLR, 1 No 50 Cum GLR, Construction of 900, 500, 150& 2 Nos. 1500 M3 OHR at Different Location, 6 Nos. Chlorine Room & 5 Nos. Pump House of Integrated Surface Water Based PWSS for Ranaghat-I and Ranaghat-II Block under Nadia Arsenis Division-I P.H.E. Dte (Sl.no.01) |  |  | ORD/000135/2023-2024 | 1897/NAD-I | 14/08/2023 | 1095 | AMAL DUTTA ROY | 3770.77 | 0 | 90
358 | Nadia Arsenic Division I |  | Laying and repairing of damaged UPVC pipeline of different existing piped water supply schemes under PHED at Ranaghat-I & II Block due to laying of DI Secondary Rising main under Integrated Surface Water Based PWSS For Ranaghat-I & Ranaghat-II Block, including restoration of village roads by Jhama Metal, Rail/National Way Crossing of pipeline, Pipe Carriage and allied works Under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000174/2024-2025 | 1748/NAD-I | 24/10/2024 | 270 | AMAL DUTTA ROY | 474.38 | 0 | 80
359 | Nadia Arsenic Division I |  | Name of Work: Supply of documents for way leave permission from the Eastern Railways authority at 9 nos of locations on Ranaghat- Krishnagar, Ranaghat- Shantipur & Ranaghat-Bongaon Railway track under Intregrated Surface Water Based PWSS for Ranaghat-I & II Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000236/2023-2024 | 2343/NAD-I | 03/10/2023 | 25 | SATYABRATA CHAKRABORTY | 17.28 | 0 | 100
360 | Nadia Arsenic Division I |  | Pond side earth protection with Eucalyptus bullah piling at Kamgachi GLR Site within Ranaght-II Block under Nadia Arsenic Division-I,P.H.E. Dte. |  |  | ORD/000303/2023-2024 | 96/AE-I/NAD-I | 27/02/2024 | 15 | R R ENTERPRISE | 4.38 | 0 | 100
361 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 1085/NAD-I | 25/04/2023 | 0 | Resource Division | 1599.91 | 0 | 0
362 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 1874/NAD-I | 10/08/2023 | 0 | Resource Division | 1012.08 | 0 | 0
363 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 1887/NAD-I | 11/08/2023 | 0 | Resource Division | 1117.16 | 0 | 0
364 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000007/2025-2026 | 76/NAD-1 | 16/04/2025 | 240 | JOYGOPAL GUPTI | 96.49 | 0 | 57
365 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000028/2025-2026 | 158/NAD-I | 28/04/2025 | 60 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0
366 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-I Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-I (Phase-I) under JJM (Sl.no.10) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000044/2023-2024 | 1365 /NAD-I | 12/05/2023 | 15 | M/S ARATI ENTERPRISE | 13.04 | 0 | 100
367 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-I (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000094/2022-2023 | 1941/NAD-I | 13/10/2022 | 90 | MONDAL ENTERPRISE | 323.87 | 0 | 95
368 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for DUTTAPULIA ZONE-I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000207/2021-2022 | 68/AE-II/N.A.D.-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.74 | 0 | 100
369 | Nadia Arsenic Division I | Nadia Arsenic Division I | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - I Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000224/2021-2022 | 69/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 3.5 | 0 | 100
370 | Nadia Arsenic Division I | Nadia Arsenic Division I | Renovation of IEP (110m3/hr.) at Duttaphulia Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000229/2023-2024 | 2297/NAD-I | 29/09/2023 | 491 | SATYABRATA CHAKRABORTY | 14.82 | 0 | 100
371 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at .Barberia Colony Paschimpara, Dakshinpara, Kushberia, Paschim para Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone- I Ground water based piped water supply scheme (Phase- I) Block- Ranaghat -II under JJM Dist- Nadia under Nadia Arsenic Division-I, PHE Dte. (sl.no10) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000245/2022-2023 | 570/NAD-I | 16/03/2023 | 21 | MONDAL ENTERPRISE | 34.86 | 0 | 0
372 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000012/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 14.67 | 0 | 0
373 | Nadia Arsenic Division I |  | Restoration of damages pipelines at PWD Bridge at Raninagar village in Balagorichar (Zone-XII) under augmentation of surface water based PWSS for Chakdah Part at Chakdah Block under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000005/2024-2025 | 143/AE-II/NAD-I | 07/06/2024 | 330 | MESSRS FREEDOM CONSTRUCTION | 4.05 | 0 | 100
374 | Nadia Arsenic Division I |  | Construction of pathway and allied works for WTP Chakdah in connection with Augmentation of Chakdah WTP under JJM within Chakdah Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000064/2024-2025 | 1709/NAD-I | 21/10/2024 | 21 | MALI CONSTRUCTION | 39.68 | 0 | 0
375 | Nadia Arsenic Division I |  | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS for Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) |  |  | ORD/000123/2023-2024 | 1829/NAD-I | 07/08/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 74.61 | 0 | 100
376 | Nadia Arsenic Division I |  | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 29 Nos. distribution zone for Chakdah (Part) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte (Sl.no 01) |  |  | ORD/000166/2023-2024 | 2110/NAD-I | 01/09/2023 | 547 | GBC INFRASTRUCTURE PRIVATE LIMITED | 8630 | 0 | 10
377 | Nadia Arsenic Division I |  | Continuation work order of Casual hiring of vehicle on an as and when required basis for Jal-Jeevan Mission site inspection under Nadia arsenic Division-I, PHE Dte. |  |  | ORD/000255/2024-2025 | 500/AE-II/NAD-I | 28/03/2025 | 184 | BUDDHADEV MONDAL | 0.86 | 0 | 0
378 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1952/NAD-I | 28/11/2024 | 0 | Resource Division | 38.55 | 0 | 0
379 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1884/NAD-I | 11/08/2023 | 0 | Resource Division | 3612.51 | 0 | 0
380 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIA, Darappur, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000007/2021-2022 | 771/NAD-I | 04/05/2021 | 60 | M/S DIPAK ENTERPRISE | 96.96 | 94.41 | 100
381 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000002/2021-2022 | 766/NAD-I | 04/05/2021 | 60 | CALCON CONSTRUCTION | 63.98 | 14.53 | 100
382 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-VIII, (Barberia), Part-I at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) |  |  | ORD/000207/2020-2021 | 312/NAD-I | 08/02/2021 | 90 | MONDAL PRECESION PVT. LTD. | 95.18 | 30.32 | 100
383 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Masunda village at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000065/2021-2022 | 1419/NAD-I | 08/11/2021 | 60 | PRIYA CONSTRUCTION | 77.38 | 0 | 100
384 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Paschim Noapara at Ranaghat-I Block by augmentation of Ground Water Based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte . (Sl.no.12) | Assistant Engineer-I | Junior Engineer-I | ORD/000221/2023-2024 | 2409/NAD-I | 10/10/2023 | 30 | JOYGOPAL GUPTI | 86.45 | 0 | 100
385 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000019/2025-2026 | 137/NAD-I | 23/04/2025 | 60 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0
386 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functioanal Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Dubli, Zone-I at Ranaghat-II Block by retrofitting of GRound Water based PWSS for Dubli, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000105/2021-2022 | 1587/NAD-I | 22/12/2021 | 90 | SUPRITI ENTERPRISE | 205.54 | 0 | 100
387 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dubli, Zone-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dubli Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000075/2021-2022 | 1435/NAD-I | 09/11/2021 | 90 | MONDAL ENTERPRISE | 147.05 | 0 | 100
388 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000012/2021-2022 | 145/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
389 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000073/2021-2022 | 1414/NAD-I | 08/11/2021 | 45 | JOY HIND TUBE WELLS | 44.57 | 0 | 100
390 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between 1st and 2nd Tubewell Rising Main at Chupria Zone-II W/S Scheme in Hanskhali block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000214/2023-2024 | 2371/NAD-I | 06/10/2023 | 21 | BISWAS CONSTRUCTION | 14.67 | 0 | 100
391 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000009/2021-2022 | 142/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
392 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Joypur Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Joypur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000058/2021-2022 | 1416/NAD-I | 08/11/2021 | 60 | GHOSH ENTERPRISE | 86.93 | 0 | 100
393 | Nadia Arsenic Division I | Nadia Arsenic Division I | Wall writing on smooth wall surface (Preferably on Govt. premises / Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and two coat best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Nadia all completed as per direction of EIC. | Assistant Engineer-II | Junior Engineer-IV | ORD/000331/2023-2024 | 466/NAD-I | 15/03/2024 | 92 | IMAGIN | 11.2 | 0 | 100
394 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping / upgradation of the hydraulic parameters at Kalipara,Gobindapur, Jhinukghata and Raynagar mouzas in reference to Gobindapur PWSS and Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000018/2025-2026 | 127/NAD-I | 22/04/2025 | 60 | CHOWDHURY & CO. | 96.3 | 0 | 0
395 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000051/2025-2026 | 231/NAD-I | 13/05/2025 | 60 | TARUN GHOSH | 89.24 | 0 | 0
396 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Part-I (Gobindapur) at Hanskhali Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000125/2021-2022 | 50/NAD-I | 11/01/2022 | 90 | M/S DIPAK ENTERPRISE | 128.71 | 0 | 100
397 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Land Development, Construction of Pathway & other allied works at Headwork site of Gobindapur (Hanskhali) under Hanskhali Dev. Block water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. Length of Boundary wall - 145 mtr. metre. | Assistant Engineer-II | Junior Engineer-IV | ORD/000130/2021-2022 | 74/NAD-I | 17/01/2022 | 30 | NISHITH BANERJEE | 16.71 | 0 | 70
398 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Hanskhali BDO, BL&LRO, Ration Deptt, Animal Husbandary,Health etc, at Hanskhali Block by retrofitting of Ground Water based PWSS for Gobindapur (Hanskhali) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000134/2022-2023 | 266/AE-I/NAD-I | 09/11/2022 | 15 | BUDDHADEV MONDAL | 4.66 | 0 | 100
399 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-I Water Supply Scheme under Nadia Arsenic-I Division, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000410/2020-2021 | 59/AE-I/N.A.D.-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 4.6 | 0 | 100
400 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for GOBINDAPUR ZONE-II Water Supply Scheme of Nadia District under Nadia Arsenic-I Division, PHE Dte. (Sl. No.-04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000411/2020-2021 | 61/AE-I/N.A.D.-I | 24/02/2021 | 30 | UMWELT ENGINEER PVT. LTD. | 3.68 | 0 | 100
401 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chupria Zone-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000123/2021-2022 | 48/NAD-I | 11/01/2022 | 90 | M/S MALLICK ENTERPRISE | 126.06 | 0 | 100
402 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-I Water Supply Scheme, Phase-I at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000004/2022-2023 | 645/NAD-I | 29/04/2022 | 90 | M/S R.K. ENTERPRISE | 260.46 | 0 | 100
403 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000008/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 19.86 | 0 | 0
404 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Mamjoani mouzas in reference to Mamjoani water supply scheme & Duttaphulia water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000007/2025-2026 | 76/NAD-1 | 16/04/2025 | 240 | JOYGOPAL GUPTI | 96.49 | 0 | 57
405 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase -II FHTC under Jaldhara/ Jal Swapna for Ramnagar at Hanskhali Block by retrofitting of Ground Water Based PWSS for Ramnagar Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000015/2022-2023 | 962 / NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 81.96 | 0 | 100
406 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall Pathway Toilet and all repair works at 2 nd TW Site and all repair works at HW site of Ramnagar WS Scheme under NAD I PHE Dte (Sl.no.03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000063/2022-2023 | 1595 / NAD-I | 06/09/2022 | 45 | SANJIB DEY | 10.06 | 0 | 93
407 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet Pathway and all repair works at 2nd T W allied site and all repair works at HW site of Mamjoani under NAD I PHE Dte (Sl.no.08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000097/2022-2023 | 1963 / NAD-I | 14/10/2022 | 60 | D.K. CONSTRUCTION | 13.16 | 0 | 0
408 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Mamjoani Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 13) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000171/2021-2022 | 438/NAD-I | 07/03/2022 | 600 | SHYAMAL SHIL | 88.34 | 0 | 100
409 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Chupria Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Chupria Zone-II W/S Scheme under JJM (SL.NO.13) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000013/2023-2024 | 1117 / NAD-I | 27/04/2023 | 715 | MONDAL ENTERPRISE | 12.96 | 0 | 100
410 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara / Jalswapna for Garapota P-III at Hanskhali block by retrofitting of Ground Water Based PWSS W/S Scheme under Nadia Arsenic Division -I , P.H.E. Dte. (Sl. No. 12) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000032/2022-2023 | 1512 / NAD-I | 26/08/2022 | 21 | SAHA ENGINEERS | 43.43 | 0 | 100
411 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Kautaknagar, Ramdulalpur, under Mayurhat-I G.P. for Ground Water Based PWSS at Hanskhali Block in connection with augmenttaion of Garapota W/S Scheme under Jal Jeevna Mission (JJM) under Nadia Arsenic Division-I , PHE Dte. (Sl.no.09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000048/2023-2024 | 1457 /NAD-I | 29/05/2023 | 21 | TAPU SAHA | 21.99 | 0 | 100
412 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied work at Chupria Zone II WS Scheme within Hanskhali Block under NAD- I PHE Dte (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000062/2022-2023 | 1594 /NAD-I | 06/09/2022 | 45 | SUBIR KUMAR DEY | 12.65 | 0 | 100
413 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Garapota Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Garapota W/S Scheme under JJM (Sl.no 08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000082/2023-2024 | 1072/NAD-I | 24/04/2023 | 738 | SWAPAN KUMAR BISWAS | 12 | 0 | 100
414 | Nadia Arsenic Division I | Nadia Arsenic Division I | Operation & Maintenance of Distribution System and Rising Main Pipeline (CI/DI/UPVC) and Iron Elimination Plant of Different Ground Based Piped Water Supply Scheme for arsenic affected areas of Joypur, Itaberia, Chupria Z-I, Chupria Z-II, Gobindapur ( Hanskhali ) and Garapota & adjoining mouzas for the period of 1 year under Nadia Arsenic Division - I, P.H. Engineering Dte. (Sl.no. 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000083/2022-2023 | 1920 / NAD-I | 30/09/2022 | 365 | APURBA MANDAL | 28.6 | 0 | 0
415 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir, Painting of Pump House in connection with Augmentation of Garapota W/S Scheme in Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.23) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000097/2023-2024 | 892/NAD-I | 04/04/2023 | 30 | S B CONSTRUCTION | 26.31 | 0 | 75
416 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Garapota W/S Scheme under Hanskhali Block of capacity 120 cum/hr. under augmentation of Garapota W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000133/2023-2024 | 1901/NAD-I | 14/08/2023 | 592 | HARBAUER INDIA PRIVATE LIMITED | 166.14 | 0 | 56
417 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Chupria Zone-II Part-III at Hanskhali Block by retrofitting of Ground Water based PWSS for Chupria Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000166/2021-2022 | 434/NAD-I | 07/03/2022 | 60 | M/S SHIL AND CO. | 45.66 | 0 | 100
418 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir ,Painting and Pump House at Chupria, Zone-II underSurface W/S Scheme in Hanskhali Block under NadiaArsenic Division - I P. H.E. Dte (Sl.no.14) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000191/2022-2023 | 154 /NAD-I | 07/02/2023 | 30 | APURBA MANDAL | 22.4 | 0 | 45
419 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connectionwith Augmentation of Chupria Zone-II water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I, P.H.E. Dte. (SL.19) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000248/2022-2023 | 579/NAD-I | 17/03/2023 | 15 | DIPANKAR DUTTA | 18.87 | 0 | 48
420 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work T/W site in connection with Augmentation of Garapota water supply Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. ( sl.no.12) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000249/2022-2023 | 580/NAD-I | 17/03/2023 | 21 | ONKAR ENTERPRISE | 19.03 | 0 | 100
421 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Garapota Bazar to H/O Chayan Biswas, Boro Chupria & Paschim Garapota to H/O Sanjiban Biswas, Boro Chupria at Hanskhali Block by retrofitting of Ground Water Based PWSS for Chupria W/S Scheme underNadia Arsenic Division-I, P.H.E. Dte. (Sl.20) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000267/2022-2023 | 827 / NAD-I | 31/03/2023 | 30 | JAGADANADAPUR CO-OPT LABOUR CONTTRACT AND CONSTRUTION SOCITY LTD. | 32.85 | 0 | 0
422 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply and installation of Butterfly Valve at Back Wash OHR at Palagachha under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000045/2023-2024 | 246/AE-II/NAD-I | 18/05/2023 | 7 | SATYABRATA CHAKRABORTY | 2.76 | 0 | 100
423 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Palagacha Zone-I under Chakdah Surface W/S Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.10) | Assistant Engineer-II | Junior Engineer-IV | ORD/000064/2022-2023 | 1597/NAD-I | 06/09/2022 | 45 | M/S PRADIP KUMAR PAL | 12.72 | 0 | 100
424 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for clear water rising main & distribution main at Palagachha Zone-I W/S Scheme in connection with Augmentation of Palagachha (Zone-I) & Masra (Zone-III) under JJM under Nadia Arsenic Division-I , PHE Dte. (Sl. No. 12)" | Assistant Engineer-II | Junior Engineer-IV | ORD/000077/2023-2024 | 1411/NAD-I | 18/05/2023 | 21 | THE TOWER CONSTRUCTION | 36.38 | 0 | 75
425 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting works at Balir math and Palagachha (Zone-I) W/S Scheme under Surface Water Based PWSS for Chakdah (Part) water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000126/2022-2023 | 3042/NAD-I | 09/11/2022 | 60 | BUDDHADEV MONDAL | 9.28 | 0 | 100
426 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting of UPVC distribution main pipe line from Palagacha more to WTP of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme under Nadia Arsenic Division-I PHE Dte.(sl.no.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000127/2022-2023 | 1424 / NAD-I | 12/08/2022 | 30 | G.B. CONSTRUCTION | 29.6 | 0 | 0
427 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Masra (Zone- III) under Chakdah Surface WS Scheme in Chakdah Block under NAD I PHE Dte (Sl.no.09) | Assistant Engineer-II | Junior Engineer-IV | ORD/000136/2022-2023 | 1969 / NAD-I | 14/10/2022 | 60 | RAM KRISHNA CHAKRABORTY | 26.49 | 0 | 100
428 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Node Point 180 to 180 at Lalpur of Palagacha (Zone-I) W/S Scheme under Chakdah Surface W/S Scheme at Chakdah Block under Jal Jeevan Mission under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-II | Junior Engineer-IV | ORD/000148/2023-2024 | 376/AE-II/NAD-I | 29/08/2023 | 7 | M/S K..M. ENTERPRISE | 4.71 | 0 | 100
429 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Masra (Zone-III), (Part-II) Water Supply Scheme under Chakdah (Part) Surface Water Based W/S Scheme under Nadia Arsenic Division-I, PHE Dte. Sl. No.- 11 | Assistant Engineer-II | Junior Engineer-IV | ORD/000151/2022-2023 | 3329/NAD-I | 15/12/2022 | 45 | KESHOB ENTERPRISE | 28.27 | 0 | 0
430 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III (Masra), at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 08) | Assistant Engineer-II | Junior Engineer-IV | ORD/000152/2022-2023 | 3446/NAD-I | 21/12/2022 | 30 | SUMIT GHOSH | 39.83 | 0 | 100
431 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofittng work at Mahanala due to construction of N.H.-34 road under Palagacha (Zone-I ) within Chakdah Surface W/S Scheme under JJM under Nadia Arsenic Division-I ,PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-IV | ORD/000154/2023-2024 | 2113/NAD-I | 01/09/2023 | 15 | K K MARKETING | 6.82 | 0 | 100
432 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at RanjanPally, Lalpur and Singher Bagan under Palagacha W/S Scheme under JJM within Chakdah Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.05) | Assistant Engineer-II | Junior Engineer-IV | ORD/000160/2023-2024 | 2118/NAD-I | 04/09/2023 | 15 | MANAJIT BISWAS | 13.58 | 0 | 100
433 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, Primary School, SSk & MSK under Jal Jeevan Mission (JJM) at Palagachha Zone-I Chakdah Block Palagachha (Zone-I) & Mosra (Zone-III) at Chakdah Block, Dist- Nadia of Surface Water Based PWSS for Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000177/2022-2023 | 33/NAD-I | 17/01/2023 | 15 | SUNIL KUMAR DATTA | 11.95 | 0 | 100
434 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I, (Palagachha), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000179/2021-2022 | 516/NAD-I | 28/03/2022 | 60 | SHYAMAL SHIL | 134.14 | 0 | 100
435 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atMosra (Zone-III) Kalyani Block under Palagachha (Zone-I) & Mosra (Zone-III) Dist.-Nadia of Surface Water Based PWSS for Chakdah (Part) Surface Water Based Water Supply Scheme of Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (sl.no. 07) | Assistant Engineer-II | Junior Engineer-IV | ORD/000215/2022-2023 | 242 / NAD-I | 17/02/2023 | 15 | M/S S.K ENTERPRISE | 10.79 | 0 | 60
436 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at DD Brick Field at Palagacha in connection with augmentation of Zone-I, Palagacha W/S Scheme under Surface Water Based PWSS for Chakdah (Part) under Jal Jeevan Mission under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte.(sl.03) | Assistant Engineer-II | Junior Engineer-IV | ORD/000275/2022-2023 | 170//AE-II/NAD-I | 27/03/2023 | 21 | K K MARKETING | 4.48 | 0 | 0
437 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply, delivery and storage at site of automatically controlled diapharm type Chlorinatore dosing pump. Under Augmentation of Ground Water Based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000003/2024-2025 | 141/AE-II/NAD-I | 07/06/2024 | 30 | MANARAMA ENTERPRISE | 2.89 | 0 | 100
438 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-II Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Bhayna Zone-I & Zone-II (Part-III) Piped W/S Scheme (Sl.no.29) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000042/2023-2024 | 1361 /NAD-I | 12/05/2023 | 15 | NISHITH BANERJEE | 13.04 | 0 | 100
439 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet , Pathway and other allied works at Bhayana Z-I W/S Scheme within Hanshkhali Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.No. 20) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000046/2022-2023 | 1586 / NAD-I | 06/09/2022 | 45 | CHANDAN ROY | 13.37 | 0 | 100
440 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Bhayna Zone-I GroundWater Supply Scheme under Hanskhali under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation in connection with JJM under Bhayna Zone-I & Zone-II Part-III Piped W/S Scheme (Sl.no28) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000047/2023-2024 | 1451/NAD-I | 26/05/2023 | 15 | PALCON | 12.98 | 0 | 100
441 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between Common Manifold and distribution main at Bhayna Zone-I W/S Scheme under JJM in connection with Garapota and Bhayna W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I, PHE Dte. (Sl. no. 03) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000051/2024-2025 | 1501/NAD-I | 18/09/2024 | 45 | B.S. ENTERPRISE | 19.54 | 0 | 100
442 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Bhayna Zone-I & II Part-III at Hanskhali block by Augmentation of Ground water based PWSS for Bhayna W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000095/2023-2024 | 1686/NAD-I | 12/07/2023 | 790 | TAPU SAHA | 390.82 | 0 | 80
443 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Bhayna Zone-I W/S Scheme under Hanskhali Block of capacity 125 cum/hr. under augmentation of Bhayna Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000143/2023-2024 | 2044/NAD-I | 24/08/2023 | 548 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 165.95 | 0 | 94
444 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | RTOR000010/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 12.32 | 0 | 0
445 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | RTOR000029/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 8.62 | 0 | 0
446 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Halalpur-Krishnapur Zone-I & II (Part-III) Piped W/S Scheme (sl.19) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000025/2023-2024 | 1161 / NAD-I | 28/04/2023 | 15 | B.S. ENTERPRISE | 13.04 | 0 | 100
447 | Nadia Arsenic Division I | Nadia Arsenic Division I | Balance work for revamping / upgradation of the hydraulic parameters at Gayesh, Daluigram & Jafar-nagar mouzas in reference to Halalpur-Krisnapur PWSS & Raynagar PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000025/2025-2026 | 154/NAD-I | 28/04/2025 | 60 | TAPU SAHA | 86.49 | 0 | 0
448 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection of M.S pipeline with Manifold at Halalpur Krishnapur Z-1 Water Supply Scheme including fixing of Sign Board for dematcation of Land at different location under the judisdiction of Nadia Arsenic Division-I ,PHE Dte. under JJM. (Sl. No. 08) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000034/2025-2026 | 168/NAD-I | 29/04/2025 | 60 | BUDDHADEV MONDAL | 9.81 | 0 | 60
449 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Halalpur-Krishnapur Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Muragachha Zone-I & II (Part-III) Piped W/S Scheme (Sl.no.18) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000051/2023-2024 | 1430/NAD-I | 24/05/2023 | 15 | D.K. CONSTRUCTION | 12.98 | 0 | 100
450 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM), Construction of Boundary wall, Toilet, Pathway and other allied work at Head Work Site & 2nd T/W Site, Repair of 350 cum capacity Over Head Reservoir, Painting and Pump House at Halalpur Krishnapur Zone-I & Repair of 180 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House at Halapur Zone-II for Halalpur Krishnapur Zone-I & II at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000098/2023-2024 | 1742/NAD-I | 19/07/2023 | 90 | SATYABRATA CHAKRABORTY | 377.65 | 0 | 40
451 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Halalpur Krishnapur Zone-I & Zone-II from Kharida Chapra Primary School to Purba Sangha at Ranaghat-II Block under Jal Jeevan Mission (JJM) by Retrofitting of Ground Water Based PWSS for Halalpur Krishnapur Water Supply Scheme under Retrofitting of Ground Water Based PWSS of Halalpur- Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000218/2022-2023 | 100/AE-I/NAD-i | 20/02/2023 | 15 | MONDAL ENTERPRISE | 3.56 | 0 | 0
452 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000016/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 15.4 | 0 | 0
453 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply, delivery and installation commissioning of Domestic Ultrasonic (153 RWM) type water meter with Software for data communication at Patkabari, Hatibhanda, Madna, Jaganath, Sahapur & Dhakuria village under augmentation of ground watwer based PWSS for Itaberia W/S Scheme Part-III under Jal Jeevan Mission (JJM) at Hanskhali Block, Nadia under Nadia Arsenic Division-I, PHE Dte. (Sl.04) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000015/2025-2026 | 131/NAD-I | 22/04/2025 | 60 | SHANTA COLIBRI (INDIA) PVT. LTD. | 5.43 | 0 | 0
454 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (60cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Itaberia, under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.06) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000138/2023-2024 | 1969/NAD-I | 21/08/2023 | 30 | B.M. ENGINEERING & CONSTRUCTION | 112.08 | 0 | 0
455 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VII, (Ballabhpur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000120/2021-2022 | 13/NAD-I | 05/01/2022 | 90 | H I ENTERPRISE | 243.49 | 0 | 100
456 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000001/2021-2022 | 765/NAD-I | 04/05/2021 | 60 | UNICON INDIA | 93.41 | 39.9 | 100
457 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000012/2021-2022 | 777/NAD-I | 05/05/2021 | 60 | J.D.J. ENTERPRISE | 97.11 | 0 | 50
458 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Mouza-Beharia at Santipur Block by augmentation of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division-I, PHE Dte (SL.NO.03) |  |  | ORD/000148/2022-2023 | 3326 / NAD-I | 16/12/2022 | 45 | CHOWDHURY & CO. | 67.83 | 0 | 100
459 | Nadia Arsenic Division I |  | Pipeline connection with manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block by retrofitting o Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. ¿ 01) |  |  | ORD/000290/2023-2024 | 28/AE-I/NAD-I | 19/01/2024 | 15 | DEBASHISH DEY | 0.96 | 0 | 100
460 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 29.69 | 100
461 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VII, (Kumarpur), Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) Tender No. - 208/NAD-I/2020-2021. |  |  | ORD/000128/2020-2021 | 91/NAD-I | 13/01/2021 | 45 | APURBA MANDAL | 46.77 | 9.54 | 100
462 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000002/2022-2023 | 643/NAD-I | 29/04/2022 | 90 | UNICON INDIA | 335.39 | 0 | 10
463 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenatioin under Jal Jeevan Mission Aranghata Zone- II W/S Scheme, Part - II at Ranaghat- II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000104/2023-2024 | 1696/NAD-I | 13/07/2023 | 982 | ORIENT CONSTRUCTION | 311.77 | 0 | 90
464 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000355/2023-2024 | 461/NAD-I | 15/03/2024 | 382 | DIVINE | 329.47 | 0 | 75
465 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000014/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 24.52 | 0 | 0
466 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 950 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at Chanduria Zone-XI under Surface W/S Scheme of Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte.( Sl.no . 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000056/2022-2023 | 1636/NAD-I | 06/09/2022 | 45 | M/S R.K. ENTERPRISE | 37.67 | 0 | 100
467 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of Chanduria Zone XI at Priyanagar New Kautukpur Kautukpur Jibannagar village under Chakdah Block of PWSS for Chakdah Surface water supply scheme under NAD I PHE Dte ( Sl.no. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000095/2022-2023 | 1960 / NAD-I | 12/10/2022 | 60 | MADE AND TRADE CO. | 15.76 | 0 | 100
468 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-VIII, (Barberia) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000119/2021-2022 | 12/NAD-I | 05/01/2022 | 90 | UMWELT ENGINEER PVT. LTD. | 299.45 | 0 | 98
469 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000162/2021-2022 | 431/NAD-I | 07/03/2022 | 60 | CHAKRABORTTI ENTERPRISE | 67.64 | 0 | 100
470 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-XI (Chanduria) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-II | Junior Engineer-III | ORD/000164/2021-2022 | 432/NAD-I | 07/03/2022 | 60 | SANJOY BAKSHI | 78.61 | 0 | 100
471 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of Barberia, Zone-VIII, at Chakdah Block of PWSS for Chakdah Surface Water Supply Scheme under Nadia arsenic Division-I, P.H.E. Dte. (Sl No.-01) | Assistant Engineer-II | Junior Engineer-III | ORD/000169/2022-2023 | 87/ AE-II/ NAD-I | 30/06/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 3.89 | 0 | 100
472 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VIII (Barberia) Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000170/2021-2022 | 430/NAD-I | 07/03/2022 | 60 | SANDIP BISWAS | 85.12 | 0 | 100
473 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000003/2021-2022 | 767/NAD-I | 04/05/2021 | 60 | IJABUL SEKH | 94.5 | 93.55 | 100
474 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Matikumra ii)Duttaphulia Zone-I iii)Duttaphulia Zone-II | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000004/2023-2024 | 166/AE-I/NAD-I | 12/04/2023 | 15 | TECH VISION | 4.84 | 0 | 40
475 | Nadia Arsenic Division I | Nadia Arsenic Division I | Restoration of damages pipelines from Duttaphulia more to BSF camp in Ranaghat- II, Block under Nadia Arsenic Division-I,PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000004/2024-2025 | 142/AE-II/NAD-I | 07/06/2024 | 30 | BUDDHADEV MONDAL | 4.19 | 0 | 100
476 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Gangsara & Duttaphulia Village in connection Duttapulia Zone-II Ground Water Based Piped Water Supply Scheme , Under Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. (Sl.05) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000006/2025-2026 | 74/NAD-I | 16/04/2025 | 60 | SHYAMAL SHIL | 94.18 | 0 | 0
477 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall and pathway Head work site of Duttaphulia Zone- II and Dubli Zone- I water supply Scheme in Ranaghat-II Block in connection with Duttaphulia Zone-I W/S Scheme under JJM under Nadia Arsenic Division-I,P.H.E. Dte. (sl.02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000019/2025-2026 | 137/NAD-I | 23/04/2025 | 60 | CFS MANAGEMENT PRIVATE LIMITED | 38.99 | 0 | 0
478 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Duttaphulia Zone-II (Part-I) at Ranaghat-II Block by Augmentation of Ground Water based PWSS for Duttaphulia Zone-I Water SUpply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000030/2022-2023 | 1463/NAD-I | 18/08/2022 | 1123 | APURBA MANDAL | 321.95 | 0 | 85
479 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Duttaphulia Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Duttaphulia Zone-II (Phase-I) under JJM (Sl.no.09) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000037/2023-2024 | 1362 / NAD-I | 12/05/2023 | 15 | DULAL MAJUMDER | 13.03 | 0 | 100
480 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Duttaphulia Mouza inconnection with Augmentation to accomodate FHTC under JJM for Duttaphulia Zone- II Ground water based piped watrer supply scheme ( Phase- I ) Block- Ranaghat -II Dist- Nadia under Nadia Arsenic Division-I , P.H.E Dte.(Sl.No. 08)" | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000078/2023-2024 | 1384/NAD-I | 16/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 72.08 | 0 | 100
481 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well situated at thr 2nd Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000078/2024-2025 | 201/AE-II/NAD-I | 24/09/2024 | 7 | BUDDHADEV MONDAL | 0.64 | 0 | 100
482 | Nadia Arsenic Division I | Nadia Arsenic Division I | Surging of existing Tube Well situated at the 5th Tube Well site at Duttaphulia Zone-II Water Supply Scheme in Connection with Jal Jeevan Mission under Hanskhali Block to increase the yield of the Tube Well under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000079/2024-2025 | 204/AE-II/NAD-I | 24/09/2024 | 7 | M/S DIPAK ENTERPRISE | 0.64 | 0 | 100
483 | Nadia Arsenic Division I | Nadia Arsenic Division I | Work for revamping / upgradation of the hydraulic parameters at Sahapur Battala, Patikabari, Hatibanda, Uttor Bhayna mouzas in reference to Duttaphulia Zone - II and Bhayna Zone - I water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (SL.01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000216/2024-2025 | 2434/NAD-I | 06/02/2025 | 186 | B.S. ENTERPRISE | 113.05 | 0 | 100
484 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000225/2021-2022 | 70/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.67 | 0 | 100
485 | Nadia Arsenic Division I | Nadia Arsenic Division I | Distribution Design for preparation of DPR for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Duttapulia Zone - II Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000226/2021-2022 | 71/AE-II/NAD-I | 24/02/2022 | 30 | UMWELT ENGINEER PVT. LTD. | 4.8 | 0 | 100
486 | Nadia Arsenic Division I | Nadia Arsenic Division I | Renovation of I E P (225m3/hr.) at Duttaphulia Zone II W/S Scheme under Nadia Arsenic Division - I , PHE Dte. | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | ORD/000230/2023-2024 | 2299/NAD-I | 29/09/2023 | 491 | SATYABRATA CHAKRABORTY | 19.29 | 0 | 100
487 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000007/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 20.94 | 0 | 0
488 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-III | RTOR000030/2023-2024 | 68/NAD-I | 16/01/2024 | 0 | Resource Division | 3.72 | 0 | 0
489 | Nadia Arsenic Division I |  | Providing Functional Household Tap Connection (FHTC) under Jaldhara/Jal Swapna for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Garapota Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000104/2021-2022 | 1586/NAD-I | 22/12/2021 | 90 | TAPU SAHA | 116 | 0 | 100
490 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 50
491 | Nadia Arsenic Division I | Nadia Arsenic Division I | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000005/2025-2026 | 40/NAD-I | 07/04/2025 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0
492 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (86cum/hr ) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Joypur under Jal Jeevan Mission at Hanskhali Block, under Nadia Arsenic Division -I, PHE Dte.(Sl.no.07) | Assistant Engineer,Assistant Engineer-II | Junior Engineer,Junior Engineer-IV | ORD/000129/2023-2024 | 1886/NAD-I | 11/08/2023 | 30 | APURBA MANDAL | 139.79 | 0 | 32
493 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | "Work for revamping / upgradation of the hydraulic parameters in distribution network from OHR towards Joypur Pry School in reference to Hijuli and Joypur water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission.(SI. No. 02) | Assistant Engineer | Junior Engineer | ORD/000005/2025-2026 | 40/NAD-I | 07/04/2025 | 60 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD | 93.13 | 0 | 0
494 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance work for revamping / upgradation of the hydraulic parameters at Gobindapur Colony and Hijuli mauza in reference to Gobindapur PWSS and Hijuli PWSS under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission (Sl. NO. 08) | Assistant Engineer | Junior Engineer | ORD/000051/2025-2026 | 231/NAD-I | 13/05/2025 | 60 | TARUN GHOSH | 89.24 | 0 | 0
495 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 359/NAD-I | 09/06/2025 | 90 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0
496 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Shifting of Manifold and interconnection between old and new OHR and revamping /upgradation of hydraulic parameter in the distribution network at bhayna (P) paschim harin danga and hijuli part In connection with hijuli PWSS under Nadia Arsenic Division I, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2025-2026 | 721/NAD-I | 29/07/2025 | 60 | TAPU SAHA | 51.24 | 0 | 0
497 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer | Junior Engineer | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0
498 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Balance Work for revamping/upgradation of the hydraulic parameters at distribution network at the part of Satpota and Hijuli (P) in connection with Hijuli PWSS under Nadia Arsenic Division-I, PHE Dte. As a part of Jal Jeevan Mission. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/000142/2025-2026 | 1044/NAD-I | 25/09/2025 | 90 | NISHITH BANERJEE | 36.07 | 0 | 0
499 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Hijuli Water Supply Scheme at Ranaghat-II Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.04) | Assistant Engineer | Junior Engineer | ORD/000180/2022-2023 | 39 /NAD-I | 17/01/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 14.36 | 0 | 100
500 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/08/2025 to 30/09/2025) | Assistant Engineer | Junior Engineer | ORD/000197/2025-2026 | 144 | 30/07/2025 | 61 | M/S DIPAK ENTERPRISE | 0.29 | 0 | 0
501 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/08/2024 to 31/01/2025) | Assistant Engineer | Junior Engineer | ORD/000249/2024-2025 | 228/AE-I/NAD-I | 24/07/2024 | 184 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0
502 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300/100/200/200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials , Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 300/100/200/200 m3 Staging Height 20 Mtr, CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length), 2nd T/W Site(50.0 m length)], Pump House for H/W Site(5.4 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) , Land Development and aliied works with Approach Road (105.0m Length and 3.0m Wide), RESTORATION WORK FOR BITUMINOUS ROAD, Hijuli (Zone-I,II,III & IV) Ground Water Based Piped Water Supply Scheme in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000225/2023-2024 | 2351/NAD-I | 03/10/2023 | 730 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 1541.25 | 0 | 3
503 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Continuation work order for Hiring of 1 (One) no inspection vehicle (Diesel Luxury Taxi/Maxi Cab/Motor Cab) on Daily basis for monitoring of JJM works by the Junior Engineers at the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. (Period- 01/02/2025 to 31/07/2025) | Assistant Engineer | Junior Engineer | ORD/000287/2024-2025 | 14/AE-I/NAD-I | 30/01/2025 | 181 | M/S DIPAK ENTERPRISE | 0.86 | 0 | 0
504 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000023/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 31.88 | 0 | 0
505 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara /Jal Swapna for Zone-I, (Palagachha) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. Tender No. 219/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000172/2020-2021 | 313/NAD-I | 08/02/2021 | 90 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 97.1 | 82.41 | 100
506 | Nadia Arsenic Division I |  | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Muragachha Zone I Part II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division I PHE Dte. |  |  | ORD/000016/2021-2022 | 781/NAD-I | 05/05/2021 | 60 | MONDAL ENTERPRISE | 89.68 | 43.9 | 100
507 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000013/2021-2022 | 778/NAD-I | 05/05/2021 | 60 | M/S R.K. ENTERPRISE | 97.1 | 92.92 | 100
508 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Gayeshpur Zone I at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division I PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000017/2021-2022 | 782/NAD-I | 05/05/2021 | 60 | APURBA MANDAL | 96.99 | 90.79 | 100
509 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 60 | H I ENTERPRISE | 95.74 | 0 | 100
510 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (Tarinipur), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.¿ (Sl. No. 02) |  |  | ORD/000129/2020-2021 | 96/NAD-I | 13/01/2021 | 60 | GHOSH ENTERPRISE | 79.67 | 78.15 | 100
511 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Balance Portion of Zone-XI, (Birohi), at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000126/2020-2021 | 95/NAD-I/20-21 | 13/01/2021 | 60 | TAPU SAHA | 75.09 | 68.84 | 100
512 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Tarapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM of Tarapur (Part-I) Piped W/S Scheme (sl.no.14) | Assistant Engineer-I | Junior Engineer-I | ORD/000052/2023-2024 | 1429/NAD-I | 24/05/2023 | 15 | SAORSA | 13.03 | 0 | 100
513 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Tarapur Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Tarapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000066/2021-2022 | 1420/NAD-I | 08/11/2021 | 60 | CHAKRABORTTI ENTERPRISE | 68.76 | 0 | 100
514 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall & other allied works at 2nd Tubewell site of Ground water based piped supply scheme of Tarapur under Nadia Arsenic Division-I,P.H.E. Dte. Length of Boundary wall - 57 metre. | Assistant Engineer-I | Junior Engineer-I | ORD/000132/2021-2022 | 75/NAD-I | 17/01/2022 | 20 | M/S S.K ENTERPRISE | 6.9 | 0 | 100
515 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-I | RTOR000011/2021-2022 | 144/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
516 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukhilnara, Zone-I Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Ukhilnara, Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000047/2021-2022 | 1404NAD-I | 08/11/2021 | 60 | UNICON INDIA | 77.99 | 0 | 100
517 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Water Sample form different water supply scheme for testing at laboratory through collection to be engaged through agency under Nadia Arsenic Division- I PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000268/2022-2023 | 191/AE-I/NAD-I | 29/07/2022 | 365 | M/S ARATI ENTERPRISE | 4.78 | 0 | 100
518 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Haringhata & Chakdah Zone-XIII (Digha), Part-II at Haringhata Block by retrofitting of Ground Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000097/2021-2022 | 1566/NAD-I | 13/12/2021 | 90 | SATYABRATA CHAKRABORTY | 132.3 | 0 | 100
519 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2022 to 14.07.2023 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-II | ORD/000255/2022-2023 | 172 / AE-I / NAD -I | 14/07/2022 | 365 | SUMAN CHAKRABORTY | 4.8 | 0 | 75
520 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of Existing structure and other allied works under Zone-XIII (Digha) Part-II under Surface Based PWSS for Haringhata & Chakdah(Part) under JJM under Nadia Arsenic Division-I, P.H.E. Dte. (sl.01) | Assistant Engineer-I | Junior Engineer-II | ORD/000262/2022-2023 | 829 / NAD-I | 31/03/2023 | 15 | TARUN KUMAR BHATTACHARYA | 13.23 | 0 | 90
521 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis for official use of the Assistant Engineer-I, Nadia Arsenic Division - I, P.H.E. Dte. for the period from 15.07.2020 to 14.07.2021 i.e. for 1(one) year. | Assistant Engineer-I | Junior Engineer-II | ORD/000446/2020-2021 | 155 / AE-I / NAD-I | 14/07/2020 | 365 | SUMAN CHAKRABORTY | 2.25 | 0 | 100
522 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II (Joykrishnapur) at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000127/2021-2022 | 52/NAD-I | 11/01/2022 | 90 | GHOSH ENTERPRISE | 270 | 0 | 100
523 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000003/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 25.02 | 0 | 0
524 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase -II FHTC under Jaldhara/ Jal Swapna for Dubli Z-I & II at Ranaghat -II Block by retrofitting of Ground Water Based PWSS for Dubli Water Supply scheme under Nadia Arsenic Division -I, P.H.E. Dte. (Sl. no -08) | Assistant Engineer-II | Junior Engineer-III | ORD/000010/2022-2023 | 960 / NAD-I | 07/07/2022 | 60 | BIPLAB GUHA | 55.81 | 0 | 85
525 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of M.S. Manifold of 1000mm thickness for improvement of Water Supply at Head Work Site under Ukhilnara Zone-I Ground Water Based Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation of Ukhilnara Zone-I W/S Scheme underJJM (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000017/2023-2024 | 1153 /NAD-I | 28/04/2023 | 15 | GANGULY ENTERPRISE | 13.05 | 0 | 0
526 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Ukhilnara Zone-II Ground Based Water Supply Scheme under Ranaghat- I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Ukhilnara Zone-II W/S Scheme under JJM (sl.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000019/2023-2024 | 1156 /NAD-I | 28/04/2023 | 735 | K K MARKETING | 13.04 | 0 | 100
527 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 100 cum capacity and other allied works at Ukhilnara Zone-II W/S Scheme in Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E.Dte. (Sl no. 17) | Assistant Engineer-II | Junior Engineer-III | ORD/000026/2022-2023 | 1320 / NAD -I | 04/08/2022 | 45 | INVENT ENGINEER'S CO - OPERATIVE SOCIETY LTD. | 11.32 | 0 | 100
528 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairs and Renovation work of Arsenic cum Iron Removal Plant having Capacity 16 m3/hr including Civil Structures of Ukhilnara Zone-II W/S Sch. within Ranaghat -I Block under Nadia Arsenic Division -I , P.H.E. Dte. (SL.No. 22) | Assistant Engineer-II | Junior Engineer-III | ORD/000033/2022-2023 | 1513 / NAD-I | 26/08/2022 | 45 | SUNIL KUMAR DATTA | 7.1 | 0 | 100
529 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet , Pathway and all repair works at nd T/W site and other allied works at Ukhilnara Z-I W/S Scheme at Ranaghat -I Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl. No. 23) | Assistant Engineer-II | Junior Engineer-III | ORD/000034/2022-2023 | 1514 / NAD-I | 26/08/2022 | 45 | NISHITH BANERJEE | 22.91 | 0 | 100
530 | Nadia Arsenic Division I | Nadia Arsenic Division I | CONSTRUCTION OF BOUNDARY WALL,TOILET ,PATHWAY AND ALL REPAIR WORKS AT 2nd T/W AND OTHER ALLIE WORKS AT DUBLI Z-II W/S SCHEME AT RANAGHAT -II BLOCK , UNDER NADIA ARSENIC DIVISION -I , P.H.E.DTE. ( SL NO.21) | Assistant Engineer-II | Junior Engineer-III | ORD/000035/2022-2023 | 1515 / NAD-I | 26/08/2022 | 45 | DAS CONSTRUCTION | 16.36 | 0 | 100
531 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity over head reservoir and painting of all structures with repair Works & other allied works at Dubli Z-I W/S scheme in Ranaghat -II Block under Nadia Arsenic Division -I (Sl.no. 24) | Assistant Engineer-II | Junior Engineer-III | ORD/000044/2022-2023 | 1584 / NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 15.84 | 0 | 100
532 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir and Painting of all structures with repair works & other allied works at Dubli Zone -II W/S Scheme within Ranaghat -Ii Block under Nadia Arsenic Division -I, P.H.E.DTE. (Sl.no. 26) | Assistant Engineer-II | Junior Engineer-III | ORD/000047/2022-2023 | 1587 / NAD-I | 06/09/2022 | 45 | SATYABRATA CHAKRABORTY | 17.14 | 0 | 0
533 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 180 cum capacity Over Head Reservoir and painting of all structures with repair works and other allied works at Ukhilnara Zone-I W/S Scheme in Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000068/2022-2023 | 1442/NAD-I | 17/09/2022 | 45 | MONDAL ENTERPRISE | 14.98 | 0 | 100
534 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied works at 2nd and 3rd TW site of Dubli Zone I WS Scheme within Ranaghat II Block under NADI PHE Dte (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000150/2022-2023 | 3328/NAD-I | 15/12/2022 | 45 | B.M. ENTERPRISE | 20.53 | 0 | 100
535 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation & Retrofitting work under Jal Jeevan Mission (JJM) for UKILNARA ZONE-I at Ranaghat-I Block of Ground Water based PWSS for Ukilnara Zone-I Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000167/2024-2025 | 1897/NAD-I | 18/11/2024 | 300 | GANGULY ENTERPRISE | 29.52 | 0 | 0
536 | Nadia Arsenic Division I | Nadia Arsenic Division I | Improvement of AIRP for Dubli Zone-I (105 cum/hr.) W/S Scheme in connection with Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dubli Zone-I, under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.14) | Assistant Engineer-II | Junior Engineer-III | ORD/000188/2023-2024 | 2151/NAD-I | 08/09/2023 | 21 | SATYABRATA CHAKRABORTY | 63.28 | 0 | 100
537 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting in Uzirpukuria North at Dubli Zone-I W/S Scheme under Ground Water Based PWSS for arsenic affected areas of Dubli W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000200/2022-2023 | 28/AE-II/NAD-I | 10/02/2023 | 15 | BUDDHADEV MONDAL | 4.8 | 0 | 100
538 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting of pipeline From Headwork site to Ukhilnara More due to widening of PWD Road under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000223/2022-2023 | 106/AE-II/ NAD-I | 02/03/2023 | 15 | GANGULY ENTERPRISE | 1.86 | 0 | 50
539 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work from Ukhilnara More towards Payradanga Station under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte. (Sl.no. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000224/2022-2023 | 107/ AE-II/NAD-I | 02/03/2023 | 15 | GANGULY ENTERPRISE | 2.64 | 0 | 0
540 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC Pipeline under JJM for Ukhilnara Zone-II at Payradanga G.P. at Ranaghat-I Block of Ground Water Based PWSS for Ukhilnara Zone-II W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000270/2023-2024 | 2752/NAD-I | 11/12/2023 | 315 | GANGULY ENTERPRISE | 9.32 | 0 | 90
541 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Mistripara under Ukhilnara Zone-I Water Supply Scheme under Ranaghat-I Block under Nadia Arsenic Division-I,P.H.E. Dte (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000274/2022-2023 | 169 / AE-II/NAD-I | 27/03/2023 | 21 | MALI CONSTRUCTION | 2.79 | 0 | 100
542 | Nadia Arsenic Division I | Nadia Arsenic Division I | FHTC under Jaldhara / Jalswapna for Duttaphulia Z-II Part -II at Ranaghat-II Block by augmentation of Ground water Based PWSS for Duttaphulia Z-II W/S scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.no. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000092/2022-2023 | 1939 /NAD-I | 12/10/2022 | 90 | M/S TARAK CHANDRA PAUL | 557.43 | 0 | 100
543 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Ramnagar and Duttaphulia at Hanskhali Block under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-III | ORD/000186/2023-2024 | 2160/NAD-I | 11/09/2023 | 21 | MESSRS FREEDOM CONSTRUCTION | 75.74 | 0 | 100
544 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Baranbria, Srirampur, Kalupur, Kani Bamni, Bagdia Mouza inconnection with Augmentation to accommodate FHTC under JJM for Duttaphulia Zone-II Ground water based PWSS (Phase-II) Block ¿ Ranaghat-II, Dist (sl.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000241/2022-2023 | 537 / NAD-I | 13/03/2023 | 21 | M/S TARAK CHANDRA PAUL | 31.77 | 0 | 0
545 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000011/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 38.85 | 0 | 0
546 | Nadia Arsenic Division I |  | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IV Rukminidanga Part I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte |  |  | ORD/000020/2021-2022 | 785/NAD-I | 05/05/2021 | 60 | CHANDAN ROY | 97.05 | 86.31 | 100
547 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-XIII, (Digha), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. Tender No. 204/NAD-I/2020-2021. |  |  | ORD/000169/2020-2021 | 152/NAD-I | 25/01/2021 | 60 | M/S NIBHAS SINHA | 89.4 | 87.76 | 100
548 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair, Renovation of Haringhata WTP (including 500 cum Back Wash OHR) and Intake with different units and Boundary Wall of WTP under Surface W/S Scheme Haringhata-Chakdah (Part) under Nadia Arsenic Division-I PHE Dte (Sl.no. 02) | Assistant Engineer-I | Junior Engineer-I | ORD/000122/2022-2023 | 1908 / NAD-I | 29/09/2022 | 60 | TARUN KUMAR BHATTACHARYA | 55.33 | 0 | 100
549 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Darrappur, Zone-V under Surface W/S Scheme of Haringhata-Chakdah (Part) under NAD I PHE Dte (Sl.no. 13) | Assistant Engineer-I | Junior Engineer-I | ORD/000146/2022-2023 | 3217/ NAD-I | 30/11/2022 | 45 | CHANDAN ROY | 14.38 | 0 | 100
550 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-V (Darrappur) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 10) | Assistant Engineer-I | Junior Engineer-I | ORD/000159/2021-2022 | 426/NAD-I | 07/03/2022 | 60 | NATIONAL CONSTRUCTION | 93.56 | 0 | 100
551 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-I W/S Scheme under JJM (sl.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000018/2023-2024 | 1154 / NAD-I | 28/04/2023 | 15 | BUDDHADEV MONDAL | 13.02 | 0 | 100
552 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-II Ground Based Water Supply Scheme under Ranaghat- II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone- II (Phase-I) under JJM (sl.06) | Assistant Engineer-II | Junior Engineer-III | ORD/000020/2023-2024 | 1157/NAD-I | 28/04/2023 | 728 | BISWAS CONSTRUCTION | 13.01 | 0 | 100
553 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Dubli Zone-II Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dubli Zone-II W/S Scheme under JJM (sl.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2023-2024 | 1155 / NAD-I | 28/04/2023 | 15 | BISWAS ENTERPRISE | 13.04 | 0 | 100
554 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2025-2026 | 133/NAD-I | 22/04/2025 | 60 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0
555 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Debagram Phase-I at Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Debagram W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000031/2022-2023 | 1475/NAD-I | 22/08/2022 | 90 | GHOSH ENTERPRISE | 320.01 | 0 | 100
556 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC and laying dedicated pipeline for Uzirpukuria, Humaniapota, Purba Simulia Village under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dubli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-II | Junior Engineer-III | ORD/000037/2025-2026 | 248/NAD-I | 15/05/2025 | 60 | SUMAN CHAKRABORTY | 58.02 | 0 | 0
557 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Approach Road and allied work at site of Arranghata Z-I W/S scheme within Ranaghat -II Block under Nadia Arsenic Division -I ( Sl.no. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000045/2022-2023 | 1585 / NAD-I | 06/09/2022 | 45 | B.K. ENGINEERING | 12.4 | 0 | 100
558 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Arranghata Zone-I Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Arranghata Zone-I (Phase-II) W/S Scheme under JJM (Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000054/2023-2024 | 1425/NAD-I | 23/05/2023 | 15 | M/S BISWAS BROTHERS | 12.98 | 0 | 100
559 | Nadia Arsenic Division I | Nadia Arsenic Division I | Culvert crossing and restoration of pipeline including jointing with manifold and other allied works under Paschim Noapara Water Supply Scheme , Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000055/2024-2025 | 1555/NAD-I | 25/09/2024 | 45 | JOYGOPAL GUPTI | 6.11 | 0 | 100
560 | Nadia Arsenic Division I | Nadia Arsenic Division I | "Augmentation of Garapota PWSS by providing dedicated pipeline for Shibchandrapur and Kutaknagar mouza under Nadia Arsenic Division-I,P.H.E. Dte. as a part of Jal Jeevan Mission.(SL. No. 07)" | Assistant Engineer-II | Junior Engineer-III | ORD/000140/2024-2025 | 2007/NAD-I | 29/11/2024 | 132 | BUDDHADEV MONDAL | 57.81 | 0 | 80
561 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Chandpur More area under Ranaghat-II block Augmentation of Ground Water Based PWSS for Dhantala W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000146/2023-2024 | 369/AE-II/NAD-I | 24/08/2023 | 7 | REKHA ENTERPRISE | 2.31 | 0 | 60
562 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Gourisail area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS forDubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.22) | Assistant Engineer-II | Junior Engineer-III | ORD/000192/2023-2024 | 2207/NAD-I | 13/09/2023 | 30 | GHOSH ENTERPRISE | 95.24 | 0 | 100
563 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work including FHTC (Functional Household Tap Connection) of Garapota and Duttaphulia at Block Hanskhali under Jal Jeevna Mission in connection with augmentation of Duttaphulia Zone-II W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000215/2023-2024 | 2253/NAD-I | 22/09/2023 | 21 | M/S A.K. CONSTRUCTION | 78.25 | 0 | 100
564 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work under Jal Jeevan Mission (JJM) for Humanipota & Kamargaria area under Ranaghat-II Block by Augmentation of Ground Water Based PWSS for Dubli Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000267/2023-2024 | 2689/NAD-I | 05/12/2023 | 427 | TARUN GHOSH | 56.47 | 0 | 70
565 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Paschim Noapara Ground Based Water Supply Scheme under Ranaghat-I, under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Paschim Noapara Water Supply Scheme under JJM (Sl.No.-04) | Assistant Engineer-II | Junior Engineer-III | ORD/000294/2022-2023 | 720/NAD-I | 27/03/2023 | 15 | DAS CONSTRUCTION | 13.04 | 0 | 100
566 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) at Jugolkishore G.P. under Jal Jeevan Mission (JJM) for Ranaghat-II Block of Goalsalua Zone-I Ground Water based PWSS under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000298/2023-2024 | 167/NAD-I | 07/02/2024 | 15 | GOUTAM DEY | 4.91 | 0 | 0
567 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara / Jal Swapna for Aranghata Zone-II Part -III under Jal Jeevan Mission at Ranaghat -II Block by retrofitting of ground Water based PWSS for Aranghata Zone-II Water Supply Scheme under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000355/2023-2024 | 461/NAD-I | 15/03/2024 | 382 | DIVINE | 329.47 | 0 | 75
568 | Nadia Arsenic Division I | Nadia Arsenic Division I | Supplying, ,installation and commissioning of different equipments at the Conference Room under Haringhata WTP to make it compatible for video conferencing facility including supply & installation of surveillance system under Office of the Executive Engineer , Nadia Arsenic Division - I , PHE Dte. under Public Health Engineering Department, Govt. of West Bengal | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2022-2023 | 601/NAD-I | 20/04/2022 | 45 | ALTAVISTA TECH SOLUTIONS | 24.44 | 0 | 43
569 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 450 cum capacity Over Head Reservoir, for Chakdah WTP under Chakdah Surface W/S Scheme in Chakdah Block under Nadia Arsenic Division-I, P.H.E Dte. (Sl.no. 08) | Assistant Engineer-I | Junior Engineer-I | ORD/000057/2022-2023 | 1637 / NAD-I | 06/09/2022 | 45 | M/S R.K. ENTERPRISE | 13.75 | 0 | 55
570 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration under Jal Jeevan Mission (JJM) for Birohi-I and Fatepur G.P. and Haringhata Block under Providing FHTC (Functional Househod Tap Connection) under Jaldhara/Jalswapna for Zone-III (Jalkar Bhomra), Part-II at Haringhata Block by retrofitting of Surface Water Based PWSS for Haringhata & Chakdah (Part) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000081/2025-2026 | 582/NAD-I | 10/07/2025 | 60 | SUMAN CHAKRABORTY | 10.33 | 0 | 100
571 | Nadia Arsenic Division I | Nadia Arsenic Division I | Charges of entry of household data in JJM with Household Aadhar details ......... Geo Tagging ..... in different Block of Nadia District under Nadia Arsenic Division -I, P.H.E.Dte. (Sl.no.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000107/2022-2023 | 163 / AE-I/NAD-I | 04/07/2022 | 90 | SUMAN CHAKRABORTY | 4.85 | 0 | 100
572 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC Functional Household Tap Connection under Jal Jeevan Mission JJM Zone -V Darrappur Part -IV at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata and Chakdah Part W/S Scheme under Nadia Arsenic Division- I P.H.E Dte. (Sl. No. 17) | Assistant Engineer-I | Junior Engineer-I | ORD/000128/2022-2023 | 3041/NAD-I | 09/11/2022 | 45 | M/S DIPAK ENTERPRISE | 71.77 | 0 | 80
573 | Nadia Arsenic Division I |  | Augmentation of WTP & Intake in all respect along with ancillary works to make all the units, SCADA compatible all complete at Chakdah WTP under Augmentation of Chakdah Part & Haringhata & Chakdah (Part) under Nadia Arsenic Division I, PHE Dte. (Sl. NO. 01) |  |  | ORD/000022/2025-2026 | 97/NAD-I | 17/04/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 855.87 | 0 | 0
574 | Nadia Arsenic Division I |  | Replacing of old filter media from filter bed and supply, placing by new filter media of different size, Replacing the control chamber of the filter bed , construction of shed over filter bed & installation of SCADA system and ancillary works at HARINGHATA WTP under Augmentation of HARINGHATA & CHAKDAH(Part) under Nadia Arsenic Division I, PHE Dte. (sl.02) |  |  | ORD/000023/2025-2026 | 96/NAD-I | 17/04/2025 | 120 | GBC INFRASTRUCTURE PRIVATE LIMITED | 839.8 | 0 | 0
575 | Nadia Arsenic Division I |  | Emergency restoration of UPVC pipeline for functionally of FHTC connections, damaged due to restoration of roads at Nagar Ukhra ¿I & II G.P. at Haringhata Block of Surface Water Based PWSS for Zone-II (Hapania) W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.06) |  |  | ORD/000063/2024-2025 | 1494/NAD-I | 18/09/2024 | 225 | MONDAL ENTERPRISE | 25.84 | 0 | 100
576 | Nadia Arsenic Division I |  | Interconnection between outlet pipe of OHR and delivery main at different H/W sites in Haringhata and Chakdah (Part) surface water based PWSS at Haringhata block in connection with JJM under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) |  |  | ORD/000067/2024-2025 | 1710/NAD-I | 21/10/2024 | 21 | TARUN KUMAR BHATTACHARYA | 36.87 | 0 | 0
577 | Nadia Arsenic Division I |  | Preparation of Detailed Project Report (DPR) for Augmentation of Surface Water Based PWSS fo Haringhata & Chakdah (Part) Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(Sl.no.02) |  |  | ORD/000246/2023-2024 | 2614/NAD-I | 22/11/2023 | 15 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 92.86 | 0 | 100
578 | Nadia Arsenic Division I |  | Shifting and relaying of distribution pipeline under Haringhata-Chakdah(P) Zone-III from pond side to inner location for preventing bacteriological contamination of distribution water and providing secondary chlorination system and including internal electrification and yard lighting at all the 13 (thirteen) nos of existing zones of Surface Water based water supply schemes for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 02) |  |  | ORD/000248/2024-2025 | 2804/NAD-I | 25/03/2025 | 45 | TARUN KUMAR BHATTACHARYA | 35.7 | 0 | 0
579 | Nadia Arsenic Division I |  | Augmentation work of Clariflocculator-I of Haringhata & Chakdah (Part) WTP (33.39) MLD under JJM in connection with Augmentation of Surface Water Based PWSS for Haringhata & Chakdah (Part) at Chakdah & Haringhata block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. |  |  | ORD/000261/2023-2024 | 2699/NAD-I | 05/12/2023 | 21 | G.B. CONSTRUCTION | 95.48 | 0 | 100
580 | Nadia Arsenic Division I |  | Augmentation of different units in connection with augmentation of Surface Based PWSS for Haringhata & Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (sl.03) |  |  | ORD/000269/2023-2024 | 2610/NAD-I | 22/11/2023 | 30 | CHOWDHURY & CO. | 95.73 | 0 | 100
581 | Nadia Arsenic Division I |  | Augmentation of Water Treatment Plant, Intake & Rising Main for Surface Water Based Piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR including Soil Test, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 26 Nos. distribution zone for Haringhata & Chakdah (Part) in Haringhata & Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte |  |  | ORD/000279/2023-2024 | 2730/NAD-I | 07/12/2023 | 548 | G.B. CONSTRUCTION & UMWELT JV | 10913.55 | 0 | 3
582 | Nadia Arsenic Division I |  | Augmentation work of Filter Bed & different units of Haringhata & Chakdah (Part) WTP (33.39 MLD) under JJM in connection with augementation of Surface Water Based W/S Scheme for Haringhata &Chakdah (Part) at Chakdah & Haringhata Block in the didtrict of Nadia under Nadia Arsenic Division - I P. H.E. Dte |  |  | ORD/000282/2023-2024 | 08/NAD-I | 03/01/2024 | 25 | TARUN KUMAR BHATTACHARYA | 24.29 | 0 | 100
583 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1167/NAD-I | 29/07/2024 | 0 | Resource Division | 438.24 | 0 | 0
584 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000007/2024-2025 | 2054/NAD-I | 09/12/2024 | 0 | Resource Division | 112.27 | 0 | 0
585 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 2090/NAD-I | 16/12/2024 | 0 | Resource Division | 207.24 | 0 | 0
586 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 276/NAD-I | 23/02/2024 | 0 | Resource Division | 250.42 | 0 | 0
587 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Gosair Char Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.03) | Assistant Engineer | Junior Engineer | ORD/000166/2022-2023 | 3286 /NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 2.92 | 0 | 100
588 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing, Laying of Rising Main, Laying distribution system and FHTC (Functional Household Tap Connection) under Jal Jivam Mission, Soil investigation for the work of construction of 100 cum OHR staging height 20 mtr, Construction of 100 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including Raft foundation), pipe connection and cost of pipes, specials, Construction of Pump house, Boundary Wall, Service and Allied Works at head work & 2nd site for Gosair Char Water Supply Scheme within Ranaghat-I Block under Nadia Arsenic Division-I , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000217/2023-2024 | 2370/NAD-I | 06/10/2023 | 779 | SANJOY BAKSHI | 294.57 | 0 | 60
589 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000001/2024-2025 | 845/NAD-I | 04/06/2024 | 0 | Resource Division | 1.87 | 0 | 0
590 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000024/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 3.09 | 0 | 0
591 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of pipeline at Nirsinghapur Utterpara including water connection at Nirsinghapur High School and allied works under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000053/2024-2025 | 247/AE-I/NAD-I | 20/09/2024 | 30 | TUHIN CONSTRUCTION | 0.97 | 0 | 100
592 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of pipeline including FHTC connections near Nirsinghapur Health Centre at Nirsinghapur Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. ¿ 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000054/2024-2025 | 248/AE-I/NAD-I | 20/09/2024 | 30 | TUHIN CONSTRUCTION | 0.96 | 0 | 100
593 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (216cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Nrisinghapur, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.09) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000131/2023-2024 | 1899/NAD-I | 14/08/2023 | 691 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 167.06 | 0 | 70
594 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000259/2023-2024 | 2595/NAD-I | 17/11/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 0 | 100
595 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (16cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Gayeshpur Zone-II, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000137/2023-2024 | 1881/NAD-I | 10/08/2023 | 517 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 142.26 | 0 | 100
596 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site of Joypur and Mamjoani Water Supply Scheme in connection with Duttaphulia Zone-I under Nadia Arsenic Division-I, PHE Dte. as a part of JJM (Sl. No. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000004/2025-2026 | 39/NAD-I | 07/04/2025 | 242 | REAL TIME | 39.28 | 0 | 50
597 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000128/2021-2022 | 53/NAD-I | 11/01/2022 | 90 | TIRUPATI ENTERPRISES | 163.2 | 0 | 100
598 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Mamjoani (Part-I) W/S Scheme within Hanskhali Block under Nadia Arsenic Division-I,P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000156/2022-2023 | 225/AE-II/NAD-I | 07/12/2022 | 15 | PURNIMA ELECTRICS & DECORATORS | 2.59 | 0 | 100
599 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Sabdalpur Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Sabdalpur W/S Scheme under JJM (SL.NO.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000012/2023-2024 | 1115 / NAD-I | 27/04/2023 | 15 | ASIT PRAMANIK | 13.01 | 0 | 100
600 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying dedicated pipeline to supply water for Sabdalpur and Hosenpur under Jal Jeevan Mission (JJM) at Ranaghat-II Block of Sabdalpur Ground Water Based PWSS for under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2025-2026 | 133/NAD-I | 22/04/2025 | 60 | MANISHIKA CONSTRUCTION | 52.42 | 0 | 0
601 | Nadia Arsenic Division I | Nadia Arsenic Division I | Pipeline connection from Manifold to Distribution Main (Left Part) and Rejoining with Existing Distribution Line (Right Part) under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water Based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000032/2024-2025 | 1197/NAD-I | 01/08/2024 | 60 | MANAJIT BISWAS | 9.81 | 0 | 100
602 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting Work for Provoiding FHTC at Bholadanga under Jal Jeevan Mission (JJM) at Ranaghat-II Block under Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000033/2024-2025 | 1198/NAD-I | 01/08/2024 | 60 | M/S K..M. ENTERPRISE | 9.49 | 0 | 0
603 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Dhantala W/S Scheme within Ranaghat -II Block under Nadia Arsenic Division -I, P.H.E.Dte. ( Sl.no. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000040/2022-2023 | 1582 /NAD-I | 06/09/2022 | 45 | GHOSH CONSTRUCTION | 24.96 | 0 | 100
604 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Dhantala Ground Based Water Supply Scheme under Ranaghat-II under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation of Dhantala W/S Scheme under JJM. (Sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000099/2023-2024 | 1688/NAD-I | 12/07/2023 | 15 | SANJIB DEY | 13.04 | 0 | 100
605 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir Painting and repairing of H W Boundary Wall Pump House and AIRP at Sabdalpur W/S Scheme at Ranaghat-II Block under Nadia Arsenic Division-I P.H.E Dte (Sl.No.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000132/2022-2023 | 3045/NAD-I | 09/11/2022 | 45 | MONDAL CONSTRUCTION | 31.43 | 0 | 100
606 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied work at Sabdalpur W S Scheme within Ranaghat II Block under NAD I PHE Dte. (sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000133/2022-2023 | 3034/NAD-I | 09/11/2022 | 45 | M/S LAXMI ENTERPRISE | 12.78 | 0 | 100
607 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Dhantala WS Scheme atRanaghat II Block under NAD I PHE Dte(sl.no.02) | Assistant Engineer-II | Junior Engineer-III | ORD/000138/2022-2023 | 3037/NAD-I | 09/11/2022 | 45 | TAPU SAHA | 25.33 | 0 | 100
608 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Dhantala at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no.01) | Assistant Engineer-II | Junior Engineer-III | ORD/000238/2022-2023 | 963 / NAD-I | 07/07/2022 | 60 | M/S K.P. CONSTRUCTION | 75.57 | 0 | 60
609 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-II FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Sabdalpur, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Sabdalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (sl.no. 04) | Assistant Engineer-II | Junior Engineer-III | ORD/000239/2022-2023 | 966 / NAD-I | 07/07/2022 | 1998 | M/S K.P. CONSTRUCTION | 65.89 | 0 | 70
610 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Goalsalua Zone-I, Dhantala and Betna in connection with Augmentation of Ground Water based PWSS under Jaldhara/JalSwapna by retrofitting of Sabdalpur & Dhantala under Ranaghat-II Block district Nadia to accomodate FHTC, REpair of OHR construction of Boundary Wall and allied works. | Assistant Engineer-II | Junior Engineer-III | ORD/000283/2023-2024 | 09/NAD-I | 03/01/2024 | 21 | CHANDAN ROY | 7.89 | 0 | 100
611 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP for Ground Water Based Piped Water Supply Scheme for Dhantala (125 Cum) under Jal Jeevan Mission at Ranaghat-II Block, under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000284/2023-2024 | 2779/NAD-I | 18/12/2023 | 21 | APURBA MANDAL | 10.62 | 0 | 100
612 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (123cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Boalia, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000130/2023-2024 | 1898/NAD-I | 14/08/2023 | 928 | M/S R.K. ENTERPRISE | 170.25 | 0 | 75
613 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD including UPVC pipeline and allied works at OHR site under Boalia Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission(JJM) for Boalia, Nabla, Gayeshpur Zone-I and Gayeshpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Boalia, Nabla, Gayeshpur Water Supply Schemes under Nadia Arsenic Division-I, PHE Dte. " | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000272/2023-2024 | 2745/NAD-I | 08/12/2023 | 445 | MS MAA BHABANI ENTERPRISE | 20.18 | 0 | 100
614 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Par Niamatpur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Parniamatpur Part-III Piped W/S Scheme (Sl.no.26) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000049/2023-2024 | 1450/NAD-I | 26/05/2023 | 15 | SAORSA | 13.01 | 0 | 100
615 | Nadia Arsenic Division I | Nadia Arsenic Division I | Dedicated pipeline connection from Manifold to different directions of Parniamatpur Piped Water Supply Scheme at each part of the command areas at Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000072/2024-2025 | 1531/NAD-I | 23/09/2024 | 135 | SAORSA | 5.89 | 0 | 100
616 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of FHTC and Laying of balanced Pipeline at Gazipur, Tarapur, Girish Nagar, Jhau Mahal, Suresh Nagar under Tarapur GP at Ranaghat-I Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000079/2025-2026 | 580/NAD-I | 10/07/2025 | 60 | BISWAS CONSTRUCTION | 27.98 | 0 | 0
617 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Radhakantapur Ground Based Water Supply Scheme under Ranaghat-I under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM under Radhakantapur Part-III Piped W/S Scheme (Sl.no.25) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000100/2023-2024 | 1689/NAD-I | 12/07/2023 | 15 | KESHOB ENTERPRISE | 13.04 | 0 | 100
618 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Part-III at Ranaghat-I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata, Radhakantapur, Parniamatpur, Birnagar Water Supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Tarapur water supply scheme. Repair of Pump House & other units of AIRP and other allied works at Kalaighata water supply scheme Construction of Boundary wall, Toilet, Pathway and other allied work at Kalaighata Water supply Scheme, Repair of Pump House and construction of Boundary Wall and other allied works at Radhakantapur water supply scheme, Repair of Over Head Reservoir and other allied works at Radhakantapur water supply scheme, Construction of Boundary wall, Toilet, Pathway andother allied work at Parniamatpur Water supply Scheme, Repair of 250 cum capacity Over Head Reservoir and other allied works at Parniamatpur water supply scheme, Repairing,Painting of Boundary wall,Toilet,Pathway and other allied works at Birnagar water supply scheme, Repair of 250 cum capacity Over Head Reservoir, Painting and repairing of H/W Boudary wall, Pump House and AIRP at Birnagar water supply scheme, under Nadia Arsenic Division-I, PHEDte. (Sl.no.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000101/2023-2024 | 1698/NAD-I | 13/07/2023 | 365 | M/S DIPAK ENTERPRISE | 481.09 | 0 | 100
619 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Radhakantapur Mouza at Ranaghat-I Block by augmentation of Ground Water based PWSS of Radhakantapur water supply scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000106/2022-2023 | 2053/NAD-I | 21/10/2022 | 45 | M/S DIPAK ENTERPRISE | 61.28 | 0 | 100
620 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of distribution pipeline at Gazipur & Tarapur Mouzas including balance FHTC connections at Tarapur PWSS at Ranaghat-I Block under Arsenic Division-I,P.H.E. Dte (Sl. No. 10) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000122/2024-2025 | 1924/NAD-I | 22/11/2024 | 320 | BISWAS CONSTRUCTION | 19.11 | 0 | 80
621 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of distribution pipeline at Khrishma, Arshikhra & Birnagar villages for balance FHTC connections under Radhakantapur PWSS at Ranaghat-I Block under Arsenic Division-I,P.H.E. Dte (Sl. No. 09) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000123/2024-2025 | 1925/NAD-I | 22/11/2024 | 300 | CHOWDHURY & CO. | 41.2 | 0 | 100
622 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting works at Paharpur Mouza at Ranaghat-I Block by augmentation of Ground Water Based PWSS of Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000125/2022-2023 | 3038/NAD-I | 09/11/2022 | 45 | BISWAS CONSTRUCTION | 9.17 | 0 | 100
623 | Nadia Arsenic Division I | Nadia Arsenic Division I | Shifting and Laying of Pipeline under Jal Jeevan Mission (JJM) for Ganguly Para, Chatterjee Para and Augmentation works of Parniamatpur by Augmentation of Ground Water based PWSS for Parniamatpur Water Supply Scheme, Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.07) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000158/2023-2024 | 2116/NAD-I | 04/09/2023 | 21 | BUDDHADEV MONDAL | 17.56 | 0 | 100
624 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of pipeline at Sahidpally and different Augmentation work of Radhakantapur, Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by Augmentation of Ground Water Based Piped Water Supply Scheme for Radhakantapur W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl.n.08) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000161/2023-2024 | 2119/NAD-I | 04/09/2023 | 21 | M/S DIPAK ENTERPRISE | 65.68 | 0 | 100
625 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of pipeline between Majherchar and Sahidpally and different Augmentation works of Tarapur and Kalaighata Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I Block by augmentation of Ground Water based PWSS for Tarapur & Kalaighata under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.13) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000164/2023-2024 | 2122/NAD-I | 04/09/2023 | 21 | M/S DIPAK ENTERPRISE | 96.43 | 0 | 100
626 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline and other allied works near House of Richa Master at Uttarpara Tarapur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000169/2023-2024 | 423/AE-I/NAD-I | 20/09/2023 | 30 | ASHIM ENTERPRISE | 3.72 | 0 | 100
627 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works near House of Saroda Nath at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000171/2023-2024 | 419/AE-I/NAD-I | 20/09/2023 | 30 | MRINAL DASGUPTA | 4.76 | 0 | 100
628 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying and restoration of pipeline for functionalities of FHTC connection at Nandighat Village under Perniamatpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000171/2024-2025 | 2026/NAD-I | 03/12/2024 | 120 | JYOTIRMOY ENTERPRISE | 4.99 | 0 | 100
629 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works from Kalaighata Kheyaghat to Mathpara Kali Mandir at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000173/2023-2024 | 421/AE-I/NAD-I | 20/09/2023 | 30 | MANARAMA ENTERPRISE | 4.66 | 0 | 100
630 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works at Parniamatpur Mouza under JJM by Augmentation of Ground Water Based PWSS of Parniamatpur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000174/2023-2024 | 422/AE-I/NAD-I | 20/09/2023 | 30 | M/S RANA ENTERPRISE | 3.16 | 0 | 100
631 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipelineat Uttarpara Tarapur Mouza by retrofitting of GRound Water Based PWSS under JJM at Ranaghat-I block by augmentation of Tarpur Part-III W/S Scheme under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000175/2023-2024 | 424/AE-I/NAD-I | 20/09/2023 | 30 | KUHELI ENTERPRISE | 4.82 | 0 | 100
632 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline at Gazipur Mouza by retrofitting of Ground Water Based PWSS under Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Ranaghat-l Block Under Nadia Arsenic Division-I,P.H.E Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000176/2023-2024 | 425/AE-I/NAD-I | 20/09/2023 | 30 | DAFADAR ENTERPRISE | 4.84 | 0 | 100
633 | Nadia Arsenic Division I | Nadia Arsenic Division I | Lyaing of UPVC Pipeline at Sureshnagar, Tarapur Mouza by retrofitting of Ground Water Based PWSS under JJM at Ranaghat-I Block by Augmentation of Tarapur Part-III W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000177/2023-2024 | 426/AE-I/NAD-I | 20/09/2023 | 30 | SAGAR ENTERPRISE | 4.81 | 0 | 100
634 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work of laying of UPVC pipeline and other allied works near Colony Para Bridge at Kalaighata Mouza under JJM by Augmentation of Ground Water Based PWSS of Kalaighata Part-III W/S Scheme under Ranaghat-I Block under Nadia Arsenic | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000180/2023-2024 | 420/AE-I/NAD-I | 20/09/2023 | 30 | M/S PHANINDRA NATH ROY | 4.32 | 0 | 100
635 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation Work under Jal Jeevan Mission(JJM) for Tarapur, Kalaighata and Parniamatpur PWSS Part- III at Ranaghat -I Block by Augmentation of Ground Water based PWSS for Tarapur, Kalaighata and Parniamatpur Water Supply Schemes under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000190/2023-2024 | 2205/NAD-I | 13/09/2023 | 25 | M/S R.K. ENTERPRISE | 7.09 | 0 | 100
636 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangement in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atRanaghat-I Block underRdahakantapur PWSS underAugmentation of Ground Water Based Water SupplyScheme of Tarapur, Kalaighata, Radhakantapur, Praniamatpur & Birnagar Part-III at Ranaghat-I Block (sl.06) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000212/2022-2023 | 204 /NAD-I | 15/02/2023 | 21 | SATYABRATA CHAKRABORTY | 33.07 | 0 | 35
637 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | RTOR000028/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 9.86 | 0 | 0
638 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone VII Ballavapur Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | Assistant Engineer-II | Junior Engineer-III | ORD/000021/2021-2022 | 786/NAD-I | 05/05/2021 | 60 | H I ENTERPRISE | 97 | 82.26 | 100
639 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha, Zone-I, Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000006/2021-2022 | 770/NAD-I | 04/05/2021 | 60 | MONDAL ENTERPRISE | 68.28 | 31.89 | 100
640 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Radhakantapur, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Radhakantapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000015/2021-2022 | 780/NAD-I | 05/05/2021 | 60 | TAPU SAHA | 88.27 | 82.83 | 0
641 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000014/2021-2022 | 779/NAD-I | 05/05/2021 | 60 | GHOSH CONSTRUCTION | 97.11 | 0 | 100
642 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Chandmari), Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 01) Tender No.- 205/NAD-I/2020-2021. |  |  | ORD/000179/2020-2021 | 157/NAD-I | 25/01/2021 | 60 | GHOSH ENTERPRISE | 97.08 | 97.07 | 100
643 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 03) |  |  | ORD/000185/2020-2021 | 159/NAD-I | 25/01/2021 | 60 | TARUN KUMAR BHATTACHARYA | 96.53 | 94.81 | 100
644 | Nadia Arsenic Division I |  | Reconnection of Functional household tap connection including additional restoration and renovation work of pump house, boundary wall and path way at Zone-I,Fatepur under Surface based Water Supply PWSS of Haringhata & Chakdah (Part) under Haringhata Block under Nadia Arsenic Division-I,P.H.E Dte |  |  | ORD/000288/2023-2024 | 31/AE-I/NAD-I | 19/01/2024 | 30 | SHYAMAL SHIL | 3.2 | 0 | 100
645 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Jalkar Bhomra), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 04) Tender No. 196/NAD-I/2020-2021. | Assistant Engineer-I | Junior Engineer-II | ORD/000180/2020-2021 | 155/NAD-I | 25/01/2021 | 60 | UNICON INDIA | 97.03 | 95.19 | 100
646 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-VI, (Balia) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 02) Tender No. - 225/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000176/2020-2021 | 314/NAD-I | 08/02/2021 | 90 | UMWELT ENGINEER PVT. LTD. | 97.05 | 59.01 | 100
647 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Saguna Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with providing FHTC for Saguna (Part-I) under JJM(Sl.no.12) | Assistant Engineer-I | Junior Engineer-II | ORD/000053/2023-2024 | 1426/NAD-I | 23/05/2023 | 15 | ROY ASSOCIATES | 13.04 | 0 | 100
648 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Saguna, Part-I at Santipur Block by retrofitting of Ground Water based PWSS for Saguna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000055/2021-2022 | 1412/NAD-I | 08/11/2021 | 60 | H I ENTERPRISE | 87.11 | 0 | 100
649 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-II W/S Scheme, Phase-II at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000002/2022-2023 | 643/NAD-I | 29/04/2022 | 90 | UNICON INDIA | 335.39 | 0 | 10
650 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) by retrofitting/rejuvenation under Jaldhara/Jal Swapna for Arranghata Zone-I Water Supply Scheme, Phase-I at Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000004/2022-2023 | 645/NAD-I | 29/04/2022 | 90 | M/S R.K. ENTERPRISE | 260.46 | 0 | 100
651 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing Functional Household Tap Connection (FHTC) under Jaldhara / Jal Swapna for Arranghata Zone-II Phase-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Arranghata Zone-II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000087/2021-2022 | 1480/NAD-I | 24/11/2021 | 90 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 167.42 | 0 | 100
652 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000014/2021-2022 | 146/NAD-I | 28/01/2022 | 0 | Resource Division | 0.6 | 0 | 0
653 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X (Shimurali) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000126/2021-2022 | 51/NAD-I | 11/01/2022 | 90 | APURBA MANDAL | 203.19 | 0 | 100
654 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection under Jaldhara/Jal Swapna for Dhantala Part-I at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Dhantala Water Supply Scheme under Nadia Arsenic Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000045/2021-2022 | 1402/NAD-I | 08/11/2021 | 60 | M/S DIPAK ENTERPRISE | 85.84 | 0 | 100
655 | Nadia Arsenic Division I | Nadia Arsenic Division I | Revamping / upgardation of hydraulic parameter of distribution network and providing FHTC for Doula, Debipur Chandpur Biraberia Dhantala & Notungram and Hizuli (Part) Village and under Jal Jeevan Mission (JJM) Under Ranaghat-II Block in connection with Dhantala PWSS & Hizuli Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-III | ORD/000112/2025-2026 | 800/NAD-I | 18/08/2025 | 90 | BIDYUT KUMAR | 182.15 | 0 | 0
656 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000005/2021-2022 | 138/NAD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0
657 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-III (Jalkar Bhomra) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000110/2021-2022 | 1612/NAD-I | 28/12/2021 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 304.75 | 0 | 100
658 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000021/2022-2023 | 3502/NAD-I | 05/01/2023 | 0 | Resource Division | 15.41 | 0 | 0
659 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-I (Fatepur) Part-II at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000113/2021-2022 | 1615/NAD-I | 28/12/2021 | 90 | BKB INFRA PROJECTS PRIVATE LIMITED | 244.09 | 0 | 100
660 | Nadia Arsenic Division I |  | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Paschim Noapara, Part-I at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Paschim Noapara Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. |  |  | ORD/000049/2021-2022 | 1406/NAD-I | 08/11/2021 | 60 | IJABUL SEKH | 83.14 | 0 | 100
661 | Nadia Arsenic Division I |  | Material Requisition To Resource Division |  |  | RTOR000018/2022-2023 | 3005/NAD-I | 04/11/2022 | 0 | Resource Division | 1.73 | 0 | 0
662 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Mamjoani, Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Mamjoani Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000054/2021-2022 | 1411/NAD-I | 08/11/2021 | 60 | SANJOY BAKSHI | 73.62 | 0 | 100
663 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Betna Ground Based Water Supply Scheme under Hanskhali under Nadia Arsenic Division-I, P.H.E Dte. in connection with Augmentation of Betna W/S Scheme under JJM (Sl.No.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000067/2023-2024 | 1378/NAD-I | 15/05/2023 | 25 | TAPAS GHOSH | 12.52 | 0 | 90
664 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other work at Goalsalua Zone II WS Scheme within Ranaghat II Block under NAD-I PHE Dte ( Sl.no.05) | Assistant Engineer-II | Junior Engineer-III | ORD/000093/2022-2023 | 1940 / NAD-I | 12/10/2022 | 60 | BUDDHADEV MONDAL | 12.94 | 0 | 50
665 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall Toilet Pathway and other allied work at Betna WS Scheme within Hanskhali Block under NAD I PHE Dte(Sl.no.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000096/2022-2023 | 1961/ NAD-I | 12/10/2022 | 45 | BANERJEE ENTERPRISE | 11.54 | 0 | 0
666 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and Pump House at Goalsalua Zone II WS Scheme in Ranaghat II Block under NAD I PHE Dte (Sl.no.07) | Assistant Engineer-II | Junior Engineer-III | ORD/000137/2022-2023 | 3036 /NAD-I | 09/11/2022 | 60 | TAPU SAHA | 20.13 | 0 | 100
667 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Betna W/S Scheme under Hanskhali Block of capacity 50 cum/hr. under Nadia under augmentation of Betna W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (SL.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000144/2023-2024 | 2045/NAD-I | 24/08/2023 | 542 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 130.98 | 0 | 100
668 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Goalsalua Zone-I Water Supply Scheme within Ranaghat-II Block under Nadia Arsenic Division-I, PHE Dte. ( SL.NO.13) | Assistant Engineer-II | Junior Engineer-III | ORD/000149/2022-2023 | 3327/NAD-I | 15/12/2022 | 45 | M/S AKSHAY HALDER | 11.93 | 0 | 100
669 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Goalsalua Part-II at Hanskhali Block by retrofitting of Ground Water based PWSS for Goalsalua Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000167/2021-2022 | 435/NAD-I | 07/03/2022 | 30 | MANISHIKA CONSTRUCTION | 23.94 | 0 | 100
670 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Betna Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 10) | Assistant Engineer-II | Junior Engineer-III | ORD/000168/2021-2022 | 436/NAD-I | 07/03/2022 | 30 | B.M. ENTERPRISE | 25.11 | 0 | 100
671 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Chak Dakshinpara & Fulbari villages at Hanskhali Block by retrofitting of Ground Water based PWSS for Betna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl No. - 11) Tender No.- 224/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-III | ORD/000175/2020-2021 | 294/NAD-I | 04/02/2021 | 45 | K.P. CONSTRUCTION | 43.55 | 0 | 0
672 | Nadia Arsenic Division I | Nadia Arsenic Division I | Water Supply Arrangment in High School, PrimarySchool, SSK & MSK under Jal Jeevan Mission (JJM) atGoalsalua (Zone-I) PWSS, Ranaghat-II Block by Augmentation of Goalsalua Zone-I &II underRanaghat-II Block & Betnaunder Hanskhali Block under Nadia Arsenic Division-I, PHE Dte (sl.10) | Assistant Engineer-II | Junior Engineer-III | ORD/000213/2022-2023 | 205 /NAD-I | 15/02/2023 | 689 | M/S ASOKE GHOSH & BROTHERS | 90.79 | 0 | 30
673 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-III FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX Ghetugachi, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. ( Sl. no. 02) | Assistant Engineer-II | Junior Engineer-III | ORD/000012/2022-2023 | 964/NAD-I | 07/07/2022 | 60 | B.S. ENTERPRISE | 65.97 | 0 | 100
674 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline at different location of Zone-II (Hapania) under Nagarukhra-I & II G.P. under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000017/2022-2023 | 88/AE-I/NAD-I | 28/04/2022 | 15 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 90
675 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of UPVC pipeline at different location of Jalkar Bhomra (Zone-III) Madanpur (Zone-XII) Birohi (Zone-XI) under Kastodanga-I & II Madanpur-I & II Birohi-I G.P. respectively under 'surface water based piped water supply scheme of HARINGHATA & CHAKDAHA under Office of the Executive Engineer, Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000018/2022-2023 | 89/AE-I/NAD-I | 28/04/2022 | 15 | AVINABA ENGINEERING CONCERN | 4.82 | 0 | 85
676 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 800 cum capacity Over Head Reservoir Boundary Wall Switch Room and other allied works at Purba Bishnupur Zone-V under Chakdah Surface WS Scheme in Chakdah Block under NAD-I PHE Dte (Sl.no.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000059/2022-2023 | 1670/ NAD-I | 07/09/2022 | 60 | TAPU SAHA | 33.13 | 0 | 100
677 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work at Tangra & Bagdob for augmentation of Surface water based PWSS for providing FHTC at Purba Bishnupur ( Zone V) of Surfac water based piped water supply scheme for Chakdah ( Part ) under JJM within Chakdah Block under Nadia Arsenic Division-I , PHE Dte. (SL.No.11) | Assistant Engineer-II | Junior Engineer-III | ORD/000076/2023-2024 | 1400/NAD-I | 16/05/2023 | 25 | CHANDAN ROY | 47.15 | 0 | 100
678 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 350 cum capacity Over Head Reservoir Two Nos Painting and repairing of HW Boundary Wall, Pump House at Ghetugachi Zone IX under urface WS Scheme of Chakdah Part under NAD I PHE Dte (Sl.no.12) | Assistant Engineer-II | Junior Engineer-III | ORD/000102/2022-2023 | 1985 / NAD-I | 18/10/2022 | 45 | U TURN CONSTRUCTION | 22.32 | 0 | 100
679 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work along Simurali-Kalibazar Road of Ghetugachi (Zone-IX) Water Supply Scheme under Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-II | Junior Engineer-III | ORD/000126/2023-2024 | 1839/NAD-I | 07/08/2023 | 15 | PURNIMA ELECTRICS & DECORATORS | 9.19 | 0 | 100
680 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V, (Purba Bishnupur), Part-III at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000178/2021-2022 | 515/NAD-I | 28/03/2022 | 60 | APURBA MANDAL | 156.91 | 0 | 100
681 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-III | RTOR000004/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 20.28 | 0 | 0
682 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing of existing structure of WTP and it's different units and other allied works under Zone-I (Fatepur) & Zone-II (Hapania) under Surface Based PWSS for Harinnghata & Chakdah (Part) under JJM under Zone-I & Zone-II, Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.10 | Assistant Engineer-I | Junior Engineer-II | ORD/000033/2023-2024 | 998 /NAD-I | 17/04/2023 | 25 | SUMAN CHAKRABORTY | 45.59 | 0 | 0
683 | Nadia Arsenic Division I | Nadia Arsenic Division I | Jackpushing of Clear Water Rising Main at Kalyani More Crossing at NH-34 and other allied works under Jal Jeevan Mission (JJM) for Zone-I Fatepur at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme for Zone-I, (Fatepur), Part-III under Nadia Arsenic Division-I, PHE Dte. (Sl.no.08) | Assistant Engineer-I | Junior Engineer-II | ORD/000035/2023-2024 | 1283 /NAD-I | 08/05/2023 | 30 | GBC INFRASTRUCTURE PRIVATE LIMITED | 55.87 | 0 | 0
684 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Bhabanipur Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000058/2023-2024 | 268/AE-I/NAD-I | 05/06/2023 | 7 | MALI CONSTRUCTION | 0.9 | 0 | 100
685 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Satyapole Mouza under JJM in connection with Augmenation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte | Assistant Engineer-I | Junior Engineer-II | ORD/000059/2023-2024 | 269/AE-I/NAD-I | 05/06/2023 | 7 | M/S ARATI ENTERPRISE | 0.89 | 0 | 100
686 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Panchkahania Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000060/2023-2024 | 266/AE-I/NAD-I | 05/06/2023 | 7 | M/S ARATI ENTERPRISE | 0.93 | 0 | 100
687 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at Behara Mouza under JJM in connection with Augmentation of Zone-I (Fatepur) Part-III at Haringhata Block by Augmentation Surface Water Based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000061/2023-2024 | 267/AE-I/NAD-I | 05/06/2023 | 7 | MALI CONSTRUCTION | 0.91 | 0 | 100
688 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House at Fatepur ZoneI under Surface WS Scheme of Haringhata Chakdah Part under NAD I PHE Dte (Sl.no.05) | Assistant Engineer-I | Junior Engineer-II | ORD/000081/2022-2023 | 1817/ NAD-I | 26/09/2022 | 60 | SHYAMAL SHIL | 25.68 | 0 | 100
689 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 1100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Hapania Zone-II under Surface W/S Scheme of Haringhata-Chakdah (Part) under Nadia Arsenic Division-I, PHE Dte.(Sl. No. 04) | Assistant Engineer-I | Junior Engineer-II | ORD/000153/2022-2023 | 3447/NAD-I | 21/12/2022 | 45 | B.S. ENTERPRISE | 37.53 | 0 | 100
690 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II (Hapania) Part-III at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 07) | Assistant Engineer-I | Junior Engineer-II | ORD/000156/2021-2022 | 423/NAD-I | 07/03/2022 | 60 | SUMAN CHAKRABORTY | 85.3 | 0 | 100
691 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-I (Fatepur) at Haringhta Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-I, Fatepur,Part-III under Nadia Arsenic Division-I, PHE Dte. (sl.no.15) | Assistant Engineer-I | Junior Engineer-II | ORD/000163/2022-2023 | 3515 / NAD-I | 09/01/2023 | 60 | MALI CONSTRUCTION | 97.06 | 0 | 70
692 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repairing of existing structure of WTP and other alliedworks under Zone-I (Fatepur) & Zone-II (Hapania)under Surface Water Based PWSS for Haringhata&Chakdah(Part) under Zone-I (Fatepur) & Zone-II(Hapania), Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (sl.11) | Assistant Engineer-I | Junior Engineer-II | ORD/000211/2022-2023 | 200 / NAD-I | 15/02/2023 | 60 | SUMAN CHAKRABORTY | 63.13 | 0 | 55
693 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work for Zone-I (Fatepur) G.P. at Haringhata Block under Jal Jeevna Mission (JJM) by Augmentation of Surface Water Based PWSS forHaringhata & Chakdah (Part) for Zone-I (Fatepur) Part-III under Nadia Arsenic Division-I, PHE Dte. (SL.09) | Assistant Engineer-I | Junior Engineer-II | ORD/000219/2022-2023 | 259/NAD-I | 20/02/2023 | 60 | BKB INFRA PROJECTS PRIVATE LIMITED | 40.51 | 0 | 100
694 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Zone-II , Hapania at Nagarukhra G.P at Haringhata Block by Augmentation of Surface Water based PWSS for Haringhata & Chakdah(Part) Water Supply Scheme for Zone-II, Hapania, Part-III under Nadia Arsenic Division-I, PHE Dte. (sl. 18) | Assistant Engineer-I | Junior Engineer-II | ORD/000221/2022-2023 | 303 /NAD-I | 27/02/2023 | 60 | MONDAL ENTERPRISE | 96.62 | 0 | 74
695 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Nabla, Part-IV at Santipur block by retrofitting/augmentation of Ground Water Based PWSS for Nabla W/S scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 18) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000025/2022-2023 | 1319/NAD-I | 04/08/2022 | 30 | CHOWDHURY & CO. | 55.7 | 0 | 100
696 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD andallied works at OHR site under Behria Ground Based Water Supply Scheme under Santipur under Office of Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. in connection with Augmentation under JJM under Beharia Part-III, Piped Water Supply Scheme (Sl.no.33) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000046/2023-2024 | 1364/NAD-I | 12/05/2023 | 15 | DEBASISH DEY | 12.2 | 0 | 100
697 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 100 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House at Goalpur, Zone-I W/S Scheme of Santipur Block under NAD- I, PHE Dte ( Sl.no.18) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000067/2022-2023 | 1725 / NAD-I | 13/09/2022 | 45 | MONDAL ENTERPRISE | 11.12 | 0 | 100
698 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall Toilet Pathway and other allied work at Goalpur Zone I WS Scheme within Santipur Block under Nadia Arsenic Division-I, PHE Dte ( Sl.No.02) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000074/2022-2023 | 1798 / NAD-I | 26/09/2022 | 45 | N.H. ENTERPRISE | 14.18 | 0 | 100
699 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 136 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall Pump House and AIRP at Nabla W/S Scheme Santipur Block under NAD- I PHE Dte (Sl.no.03) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000075/2022-2023 | 1799 /NAD-I | 26/09/2022 | 45 | M/S S & P CONSTRUCTION | 15.29 | 0 | 100
700 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir Painting and repairing of HW Boundary Wall Pump House and AIRP at Beharia WS Scheme Santipur Block under NAD PHE Dte (Sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000076/2022-2023 | 1831 / NAD-I | 27/09/2022 | 45 | PALCON | 24.15 | 0 | 100
701 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary wall , Toilet, Pathway and other allied work at Goalpur Z-II WAter Supply scheme within Santipur block under Nadia Arsenic Division -I , P.H.E.Dte. ( Sl.no. 01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000080/2022-2023 | 219 / AE-I/NAD-I | 02/09/2022 | 30 | BUDDHADEB MONDAL | 0.97 | 0 | 100
702 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Beharia W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no.16) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000119/2022-2023 | 2010 / NAD-I | 19/10/2022 | 45 | S S CONSUTANCYAND CONSTRUCTION | 13.08 | 0 | 100
703 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Boundary Wall, Toilet, Pathway and other allied work at Nabla W/S Scheme within Santipur Block under NAD I PHE Dte (sl.no. 15) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000140/2022-2023 | 3093/NAD-I | 21/11/2022 | 45 | G S CONSTRUCTION AND CO. | 14.24 | 0 | 100
704 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 700 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House and AIRP at Goalpur Zone-II under Nadia Arsenic Division -I, P.H.E.DTE. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000142/2022-2023 | 3157 / NAD-I | 25/11/2022 | 60 | DAS CONSTRUCTION | 11.08 | 0 | 100
705 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Beharia, Nabla, Goalpur Zone-I and Goalpur Zone-II Part-III at Santipur Block by Augmentation of Ground Water based PWSS for Beharia, Nabla, Goalpur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 05) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000154/2021-2022 | 421/NAD-I | 07/03/2022 | 60 | CHOWDHURY & CO. | 95.27 | 0 | 100
706 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Malipota. Phulia Para at Santipur block by retrofitting of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division- I, PHE Dte (Sl.no.12) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000163/2023-2024 | 2121/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 12.91 | 0 | 100
707 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP at Goalpur Zone-I Water Supply Scheme under Shantipur Block of capacity 15 Cu.m/hr inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division -I, PHE Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000237/2023-2024 | 2344/NAD-I | 03/10/2023 | 1062 | SATYABRATA CHAKRABORTY | 67.28 | 0 | 100
708 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work of laying of UPVC and M.S. pipeline and other allied works at Goalpur mouza under Jal Jeevan Mission (JJM) under Goalpur Zone-II, Part-III at Santipur Block under Ground Water Based PWSS for Goalpur Zone-II under Nadia Arsenic Division-I, P.H.E. Dte. (sl.17) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000240/2022-2023 | 536 / NAD-I | 13/03/2023 | 21 | CHOWDHURY & CO. | 14.94 | 0 | 30
709 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction of Back Wash Water Holding Tank and Land development and allied works at Head work site of Goalpur Zone-I PWSS under Shantipur Block under Nadia Arsenic Division- I P.H.E Dte | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I,Junior Engineer-II | ORD/000289/2023-2024 | 32/AE-I/NAD-I | 19/01/2024 | 601 | SATYABRATA CHAKRABORTY | 4.82 | 0 | 100
710 | Nadia Arsenic Division I | Nadia Arsenic Division I | Collection of Household data through mobile app for FHTC Connection at Following schemes under Nadia Arsenic Division-I PHE Dte. Schemes:- i)Nrisinghapur ii)Gobindapur Zone-I iii)Gobindapur Zone-II | Assistant Engineer-I | Junior Engineer-II | ORD/000005/2023-2024 | 167/AE-I/NAD-I | 12/04/2023 | 15 | HORIZEN | 4.84 | 0 | 44
711 | Nadia Arsenic Division I | Nadia Arsenic Division I | Reconnection at Beledanga, Uttarpara, Chandkuri, Harinadi, Sahebdanga laying of pipeline and rising main at Beledanga, Uttarpara, Chandkuri, Harinadi, Sahebdanga under Harinadi G.P. & supply of Sluice Valve with construction of chamber at H/W site and 2nd, 3rd, 4th Pump House under Jal Jeevan Mission (JJM) for Santipur Block by retrofitting of Ground Water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-I | Junior Engineer-II | ORD/000017/2024-2025 | 1039/NAD-I | 08/07/2024 | 300 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 7.72 | 0 | 100
712 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Nrisinghapur Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Augmentation under JJM of Nrisinghapur Piped W/S Scheme (sl.15) | Assistant Engineer-I | Junior Engineer-II | ORD/000023/2023-2024 | 1159 /NAD-I | 28/04/2023 | 15 | CHOWDHURY & CO. | 13.02 | 0 | 0
713 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jal Swapna for Nrisinghapur at Santipur Block by augmentation of Ground water Based PWSS for Nrisinghapur W/S Scheme under Nadia Arsenic Division -I ,P.H.E.Dte.(Sl.No.05) | Assistant Engineer-I | Junior Engineer-II | ORD/000050/2022-2023 | 1689 / NAD-I | 08/09/2022 | 45 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 864.56 | 0 | 75
714 | Nadia Arsenic Division I | Nadia Arsenic Division I | Road Restoration Work along PMGSY Road under Nrisinghapur Ground Water Supply Scheme at Santipur Block under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000259/2023-2024 | 2595/NAD-I | 17/11/2023 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 48.14 | 0 | 100
715 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000019/2022-2023 | 3155/NAD_I | 25/11/2022 | 0 | Resource Division | 57.42 | 0 | 0
716 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC under Jaldhara/Jalswapna for Gobindapur Z-I Santipur Bolck by Augmentation of Ground Water Based PWSS for Gobindapur Z-I W/S scheme under Nadia Arsenic Division-I , P.H.E.Dte (Sl.no.04) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000065/2022-2023 | 1672 / NAD-I | 07/09/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 534.08 | 0 | 70
717 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work at villages Panchpota, Koehua Para, Bagdia, Beale Danda, Promoth Nagar in connection with Augmentation of Ground Water Based Piped Water Supply Scheme for Gobindapur Zone-I at Santipur Block under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No.05) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000070/2023-2024 | 1379/NAD-I | 15/05/2023 | 30 | ALOK ENTERPRISE | 49.8 | 0 | 80
718 | Nadia Arsenic Division I | Nadia Arsenic Division I | Conversion of IEP to AIRP (Pressure Type) at Gobindapur, Zone-I W/S Scheme under Santipur Block of capacity 110 cum/hr. under augmentation of Gobindapur, Zone-I W/S Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl.no.06) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000134/2023-2024 | 1902/NAD-I | 14/08/2023 | 818 | MULTITEX ENGINEERING INDUSTRIES | 159.34 | 0 | 60
719 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of Rising main line at Gobindapur zone-I in connection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, PHE Dte. (sL.NO.16) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000238/2023-2024 | 2301/NAD-I | 29/09/2023 | 15 | M/S DIPAK ENTERPRISE | 18.43 | 0 | 100
720 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting Pipeline work for providing FHTC (Functional Household Tap Connection) and dedicated line from manifold at Shantipur Block of Ground Water Based PWSS for Gobindapur (Zne-I & II) W/S Scheme inconnection with Jal Jeevan Mission (JJM) under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000271/2023-2024 | 2751/NAD-I | 11/12/2023 | 983 | SAHA ENGINEERS | 15.75 | 0 | 85
721 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000020/2022-2023 | 3155/NAD_I | 25/11/2022 | 0 | Resource Division | 52.05 | 0 | 0
722 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | RTOR000022/2022-2023 | 108/NAD-I | 31/01/2023 | 0 | Resource Division | 92.4 | 0 | 0
723 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair Renovation of Chakdah WTP and intake with different units and Boundary Wall of WTP under Surface W/S Scheme of Chakdah (Part) block under Nadia Arsenic Division-I PHE Dte (Sl. NO. 09) | Assistant Engineer-II | Junior Engineer-III | ORD/000037/2022-2023 | 1533/NAD-I | 31/08/2022 | 60 | PALCON | 52.63 | 0 | 95
724 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 250 cum capacity Over Head Reservoir Painting and repairing of H/W Boundary Wall, Pump House at BalagariChar Zone-XII under Surface W/S Scheme of Chakdah (Part) under Nadia Arsenic Division-I, P.H.E Dte (Sl.no.03) | Assistant Engineer-II | Junior Engineer-III | ORD/000079/2022-2023 | 1763 / NAD-I | 19/09/2022 | 45 | BISHALAXMI ENTERPRISE | 20.08 | 0 | 100
725 | Nadia Arsenic Division I | Nadia Arsenic Division I | Interconnection between node point 3 and 76 of Balagarichar W/S Scheme for augmentation work at Uttar Ghughia village under Chakdah (Part) Water supply scheme under Nadia Arsenic Division-I, PHE Dte. (Sl.no.04) | Assistant Engineer-II | Junior Engineer-III | ORD/000079/2023-2024 | 1412/NAD-I | 18/05/2023 | 30 | MESSRS FREEDOM CONSTRUCTION | 62.36 | 0 | 100
726 | Nadia Arsenic Division I | Nadia Arsenic Division I | Phase-III FHTC ((Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-XII, (Balagarichar) at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply under Nadia Arsenic Division-I, PHE Dte. (Sl. No. 12) | Assistant Engineer-II | Junior Engineer-III | ORD/000129/2022-2023 | 3043/NAD-I | 09/11/2022 | 45 | M/S A.K. CONSTRUCTION | 33.39 | 0 | 100
727 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Gobindapur Zone-II at Santipur Block by retrofitting of Ground Water based PWSS for Gobindapur W/S Scheme under Nadia Arsenic Division-I, P.H.E Dte. (Sl. No. 02) | Assistant Engineer-I | Junior Engineer-II | ORD/000008/2022-2023 | 765/NAD-I | 07/06/2022 | 90 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 637.9 | 0 | 100
728 | Nadia Arsenic Division I | Nadia Arsenic Division I | Construction and installation of MANIFOLD and allied works at OHR site under Gobindapur Zone-II Ground Based Water Supply Scheme under Santipur under Nadia Arsenic Division-I,P.H.E Dte. in connection with Retrofitting under JJM under Gobindapur Zone-II Piped W/S Scheme (Sl.no.32) | Assistant Engineer-I | Junior Engineer-II | ORD/000043/2023-2024 | 1363/ NAD-I | 12/05/2023 | 15 | SANDIP ROY | 12.75 | 0 | 100
729 | Nadia Arsenic Division I | Nadia Arsenic Division I | Repair of 550 cum capacity Over Head Reservoir, Painting and repairing of H/W Boundary Wall, Pump House repair, Construction of Rigid Pavement and Boundary Wall for 2nd & 3rd T/W site at Gobindapur Zone-II Water Supply Scheme in Santipur Block under Nadia Arsenic Division-I, PHE Dte. (sl.no.14) | Assistant Engineer-I | Junior Engineer-II | ORD/000154/2022-2023 | 3448 / NAD-I | 21/12/2022 | 1572 | THE CALCUTTA CONSTRUCTION | 38.03 | 0 | 100
730 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000006/2022-2023 | 1781/NAD-I | 22/09/2022 | 0 | Resource Division | 28.78 | 0 | 0
731 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I | Junior Engineer-II | RTOR000011/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 12.69 | 0 | 0
732 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation of AIRP capacity (78cum/hr) in connection with augmentation of Ground Water Based Piped Water Supply Scheme for Saguna, under Jal Jeevan Mission at Santipur Block, under Nadia Arsenic Division -I, PHE Dte. (Sl.no.11) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-II | ORD/000140/2023-2024 | 1903/NAD-I | 14/08/2023 | 30 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD. | 141.34 | 0 | 100
733 | Nadia Arsenic Division I | Nadia Arsenic Division I | Dedicated pipeline towards Durgapur Mouza and adjacent areas including allied works for Birnagar PWSS at Ranaghat-I Block of Ground Water Based PWSS for Birnagar W/S Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.No. 01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000135/2024-2025 | 1966/NAD-I | 28/11/2024 | 60 | M/S DIPAK ENTERPRISE | 82.96 | 0 | 100
734 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for at Madanpur-I & II G.P. and different augmentation works of Radhakantapur and Birnagar Part-III under Jal Jeevan Mission (JJM) at Ranaghat-I block by augmentation of Ground Water Based PWSS for Radhakantapur and Birnagar under Nadia Arsenic Division-I, PHE Dte. (Sl.no.11) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000162/2023-2024 | 2120/NAD-I | 04/09/2023 | 714 | CHOWDHURY & CO. | 96.13 | 0 | 70
735 | Nadia Arsenic Division I | Nadia Arsenic Division I | Augmentation work of 2 no Gobindanagar near Indira More & Birnagar at Ranaghat-I Block under augmentation of Ground Water Based PWSS of Birnagar Part-III under Nadia Arsenic Division-I, P.H.E. Dte. (Sl.no.16) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000165/2023-2024 | 2123/NAD-I | 04/09/2023 | 21 | CHOWDHURY & CO. | 75.32 | 0 | 100
736 | Nadia Arsenic Division I | Nadia Arsenic Division I | Preparation of Detailed Project Report (DPR) for Birnagar (Part) Water Supply Scheme at Ranaghat-I Block at Nadia District under Nadia Arsenic Division-I, P.H.E. Dte.(sl.no.01) | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | ORD/000167/2022-2023 | 3287 / NAD-I | 08/12/2022 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 3.74 | 0 | 100
737 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-I ,Assistant Engineer | Junior Engineer,Junior Engineer-I | RTOR000002/2024-2025 | 846/NAD-I | 04/06/2024 | 0 | Resource Division | 1.52 | 0 | 0
738 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work for revamping / upgradation of the hydraulic parameters at Kamdanga and Nasra Mouza in reference to Nasra and Aranghata water supply scheme under Nadia Arsenic Division-I,P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. No. 05) | Assistant Engineer | Junior Engineer | ORD/000028/2025-2026 | 158/NAD-I | 28/04/2025 | 60 | SAFTI PRIVATE LIMITED | 77.16 | 0 | 0
739 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Work revamping / upgradation of the hydraulic parameters at distribution network at the part of Malsadaha, Ulasi, Silberia, Nasra (P) and Hijuli (P) Mouzas in reference to Hijuli and Nasra PWSS under Nadia Arsenic Division-I, P.H.E. Dte as a part of Jal Jeevan Mission. (Sl. NO. 02) | Assistant Engineer | Junior Engineer | ORD/000060/2025-2026 | 359/NAD-I | 09/06/2025 | 90 | M/S DIPAK ENTERPRISE | 246.94 | 0 | 0
740 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Preparation of Detailed Project Report (DPR) for Nasra Water Supply Scheme at Ranaghat-II Block atNadia District under Nadia Arsenic Division-I,P.H.E. Dte. (sl.04) | Assistant Engineer | Junior Engineer | ORD/000182/2022-2023 | 38/ NAD-I | 16/01/2023 | 7 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 6.74 | 0 | 100
741 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Rising Main System including specials & valves. & LAYING OF DISTRIBUTION SYSTEM INCLUDING SPECIALS, VALVES & PIPE SUPPORTING STRUCTURE, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I), Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-II), CONSTRUCTION OF BOUNDARY WALL [ H/W Site(160.0 m length),2nd T/W Site(45.0 m length),3rd T/W(45.0 m length),4th T/W(45.0 m length)],Pump House for H/W Site(4.88 M X 3.60 M),2nd T/W Site(3.60 M X 3.0 M) ,Land Development,Restoration of Bituminous Road and aliied works with Approach Road (195.0m Length and 3.0m Wide), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 300 m3 of Height 20 Mtr. for Nasra (Zone-I), Soil investigation for the work of construction of R.C.C. Elevated Reserviour of Capacity 200 m3 of Height 20 Mtr. for Nasra (Zone-II) and RESTORATION WORK FOR BITUMINOUS ROAD at Ground Water Based Piped Water Supply Scheme for Nasra (Zone-I&II) in Ranaghat-II Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000239/2023-2024 | 2381/NAD-I | 06/10/2023 | 1095 | BIDYUT KUMAR | 804.39 | 0 | 70
742 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000022/2023-2024 | 59/NAD-I | 16/01/2024 | 0 | Resource Division | 19.27 | 0 | 0
743 | Nadia Arsenic Division I | Eastern Mechanical Sub Division-II | Material Requisition To Resource Division | Assistant Engineer | Junior Engineer | RTOR000033/2023-2024 | 294/NAD-I | 28/02/2024 | 0 | Resource Division | 16.87 | 0 | 0
744 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jal Swapna for Zone-V,(Purba Bishnupur) Part-II at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000121/2021-2022 | 14/NAD-I | 05/01/2022 | 90 | M/S TARAK CHANDRA PAUL | 277.36 | 0 | 100
745 | Nadia Arsenic Division I | Nadia Arsenic Division I | Retrofitting work for Purba Bishnupur Zone V of Surface Water based PWSS for Chakdah Part water supply scheme under NAD - I PHE Dte (SL.06) | Assistant Engineer-II | Junior Engineer-IV | ORD/000256/2022-2023 | 1473 / NAD-I | 22/08/2022 | 60 | APURBA MANDAL | 32.4 | 0 | 100
746 | Nadia Arsenic Division I |  | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IX Ghetugachi Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte |  |  | ORD/000019/2021-2022 | 784/NAD-I | 05/05/2021 | 60 | GHOSH ENTERPRISE | 92.92 | 81.07 | 100
747 | Nadia Arsenic Division I | Nadia Arsenic Division I | Laying of Pipeline for FHTC works under Surface Water Based PWSS Saguna Zone-VI (Part-II) for arsenic affected areas of Nadia District to accommodate FHTC under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000020/2024-2025 | 1117/NAD-I | 19/07/2024 | 300 | APURBA MANDAL | 95.96 | 0 | 85
748 | Nadia Arsenic Division I | Nadia Arsenic Division I | Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete with Laying of Distribution System Including Specials, Valves & Pipe Supporting Structure, Construction of Boundary Wall (675m Length), Chlorine Room, Drain (I300 m Length) and Approach Road (60.0m Length and 3.0m Wide), Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials and Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 900 m3 Staging Height 20Mtr. at Surface Water Based Piped Water Supply Scheme for Saguna ZONE-VI(PART-I) in Chakdah Block of Nadia District under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000103/2023-2024 | 1708/NAD-I | 14/07/2023 | 366 | MONDAL ENTERPRISE | 676.94 | 0 | 0
749 | Nadia Arsenic Division I | Nadia Arsenic Division I | Route Survey for providing FHTC (Functional Household Tap Connection) under JJM (Jal Jeevan Mission) by Augmentation of Zone-VI (Saguna) Part -I of Surface Water Based PWSS for Haringhata and Chakdah (PArt) at Chakdah Block at Nadia District under Nadia Arsenic Division -I, P.H.E. Dte.(Sl.No.-01) | Assistant Engineer-II | Junior Engineer-IV | ORD/000242/2022-2023 | 168 / AE-I / NAD-I | 08/07/2022 | 30 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 4.78 | 0 | 100
750 | Nadia Arsenic Division I | Nadia Arsenic Division I | Material Requisition To Resource Division | Assistant Engineer-II | Junior Engineer-IV | RTOR000013/2023-2024 | 1961/NAD-I | 18/08/2023 | 0 | Resource Division | 31.72 | 0 | 0
Total | [10 empty] | 87231.89 | 2701.68