## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Supply Based Piped Water Supply Scheme For Uttar Khariop PWSS under Amta-II Block under Howrah Division, PHE Dte.(No of FHTC to be provided (Approx:- 1711) | AE/Ulu | JE/USD | ORD/000012/2021-2022 | 1198/HD | 31/05/2021 | 60 | N. G ENGINEERING | 112.54 | 0 | 0
2 | Howrah Division | Ulberia Sub-Division | Survey & collection of house hold details through mobile app and geo tagging the same of water tap connection in each house hold from existing distribution system within scheme juridiction in Nakubar, Amragori, Joypur & Uttar Khorip and others Pipe Water Supply Scheme of Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | VCH/000284/2022-2023 | BP-2022-23-44 | 11/05/2022 | 0 | M/S ASHIRBAD (INDIA) | 4.87 | 0 | 0
3 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-G) (for Sarda Mouza(part) |  |  | ORD/000103/2020-2021 | 1315/HD | 12/10/2020 | 30 | B.M ENTERPRISE | 29.28 | 8 | 0
4 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-H) (for Sarda Mouza(part) |  |  | ORD/000104/2020-2021 | 1316/HD | 12/10/2020 | 30 | MITHU BUILDERS | 25.87 | 0 | 0
5 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-I) (for Sarda Mouza(part) |  |  | ORD/000105/2020-2021 | 1317/HD | 12/10/2020 | 30 | MAA TARA CONSTRUCTION | 7.07 | 0 | 0
6 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme |  |  | VCH/000728/2020-2021 | 84433 | 09/02/2021 | 0 | JAHANGIR ALAM | 25.63 | 0 | 0
7 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme |  |  | VCH/000759/2020-2021 | 84438 | 09/02/2021 | 0 | USHA CONCERN | 26.17 | 0 | 0
8 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme |  |  | VCH/000858/2020-2021 | 844347 | 22/03/2021 | 0 | M/S SARADA UDYOG | 25.7 | 0 | 0
9 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Tajpur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) (Phase-II) | AE/Ulu | JE/USD | ORD/000055/2022-2023 | 1049/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 3.76 | 0 | 0
10 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) [Tajpur Mouza part] | AE/Ulu | JE/USD | ORD/000268/2020-2021 | 1801/HD | 27/11/2020 | 30 | MITHU BUILDERS | 30.95 | 21.85 | 0
11 | Howrah Division | Ulberia Sub-Division | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at tube well site of Vill Bansbagan of Tajpur PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (SM/07009) | AE/Ulu | JE/USD | ORD/000352/2024-2025 | 1168/AE/USD | 25/11/2024 | 45 | ALI ENTERPRISE | 4.84 | 0 | 100
12 | Howrah Division | Ulberia Sub-Division | Cons of Balance work for boundary wall at HW Site and interconnection between OHR to LDS and rising main of Tajpur | AE/Ulu | JE/USD | VCH/000880/2021-2022 | 844332 | 30/03/2022 | 0 | KANIKA CONSTRUCTION | 2.16 | 0 | 0
13 | Howrah Division | Ulberia Sub-Division | Cons of approach road of Tajpur W/S Scheme. | AE/Ulu | JE/USD | VCH/000902/2021-2022 | 844330 | 29/03/2022 | 0 | PIKASU BOSE | 2.46 | 0 | 0
14 | Howrah Division | Ulberia Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. for 2697 nos. | AE/Ulu |  | ORD/000003/2022-2023 | 789/HD | 06/04/2022 | 91 | SAMIRON GHOSH | 139.78 | 0 | 100
15 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Dakhinpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000702/2023-2024 | 3247/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
16 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Uttarpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000703/2023-2024 | 3248/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
17 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Panpur Ghoshpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000704/2023-2024 | 3249/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
18 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Purbapara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000705/2023-2024 | 3250/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
19 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Hazrapara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000706/2023-2024 | 3251/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
20 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dakhin Ramchandrapur Chatterjeepara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000707/2023-2024 | 3252/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
21 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection (FHTC) from existing distribution system in Dadpur Bamunpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000708/2023-2024 | 3253/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
22 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dadpur Majhipara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000710/2023-2024 | 3254/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
23 | Howrah Division | Ulberia Sub-Division | Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system in Dadpur Paschimpara at Dakhin Harishpur W/S scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000711/2023-2024 | 3255/AE/USD | 12/03/2024 | 21 | MMS CONSTRUCTIONS PVT. LTD. | 0.97 | 0 | 100
24 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of HDPE pipe for Providing Functional Household Tap Connection(FHTC) from existing distribution system at Dakhin Harishpur Piped Water Supply Scheme under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu |  | ORD/000727/2022-2023 | 517/HD | 09/02/2023 | 30 | SAMIRON GHOSH | 40.57 | 0 | 100
25 | Howrah Division | Howrah Sadar Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-C) | AE/SADAR | JE Sadar | ORD/000138/2020-2021 | 1550/HD | 05/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 18.96 | 0 | 0
26 | Howrah Division | Howrah Sadar Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-A) | AE/SADAR | JE Sadar | ORD/000139/2020-2021 | 1551/HD | 05/11/2020 | 30 | N. G ENGINEERING | 18.82 | 0 | 0
27 | Howrah Division | Howrah Sadar Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Maju Khetra piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-B) | AE/SADAR | JE Sadar | ORD/000142/2020-2021 | 1554/HD | 05/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 18.8 | 0 | 0
28 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. and Laying of additional UPVC pipe line of 63 mm & 75 mm dia. Total 1500 mtr. Length within the Command area of Majukhtra PWSS under Howrah Sadar Sub Division of Howrah Division , PHE Dte. (Phase-II) | AE/SADAR | JE Sadar | ORD/000429/2021-2022 | 343/HD | 17/02/2022 | 30 | KRISH CONSTRUCTION | 4.53 | 0 | 0
29 | Howrah Division | Howrah Sadar Sub-Division | Construction of Septic tank chamber with soak well at Head work site in Maju Khetra w/s scheme under Howrah Sadar Sub-Division, PHE Dte. | AE/SADAR | JE Sadar | VCH/000690/2021-2022 | 844347 | 22/02/2022 | 0 | ABONTICA ENTERPRISE | 0.59 | 0 | 0
30 | Howrah Division | Howrah Sadar Sub-Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | AE/SADAR | JE Sadar | VCH/000727/2020-2021 | 84432 | 09/02/2021 | 0 | N. G ENGINEERING | 16.5 | 0 | 0
31 | Howrah Division | Howrah Sadar Sub-Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | AE/SADAR | JE Sadar | VCH/000730/2020-2021 | 84435 | 09/02/2021 | 0 | M/S ASHIRBAD (INDIA) | 16.65 | 0 | 0
32 | Howrah Division | Howrah Sadar Sub-Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Maju Khetra PWSS | AE/SADAR | JE Sadar | VCH/000731/2020-2021 | 84436 | 09/02/2021 | 0 | M/S ASHIRBAD (INDIA) | 16.38 | 0 | 0
33 | Howrah Division | Howrah Sadar Sub-Division | Ground Water Based Piped Water Supply Scheme For Majhu Khetra | AE/SADAR | JE Sadar | VCH/000995/2020-2021 | 844339 | 19/03/2021 | 0 | DEV DAS SHAW | 5.64 | 0 | 0
34 | Howrah Division | RWS Howrah Sub-Division | NDT of OHR of of Khila PWSSS | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | BILL/00328/2024-2025 | BP-2024-25-197 | 22/07/2024 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0
35 | Howrah Division | RWS Howrah Sub-Division | Construction of 600 cum capacity 20 mtr. Staging height RCC Elevated Reservoir as per Departmental Design Drawing including Soil Investigation, Design of Pile foundation & all pipe connections for KHILA PWSS of Udaynarayanpur Block under Howrah Division, P.H.E. Dte. (SM/12270) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000105/2025-2026 | 3083/HD | 08/07/2025 | 365 | ABDUL HAI | 158.66 | 0 | 0
36 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Approach Road, Land Development and Pump house at HEAD WORK Site, 2nd Tube Well Site and 3rd Tube Well Site of KHILA Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.[SM/12270] | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000154/2024-2025 | 4130/HD | 23/09/2024 | 525 | JAHANGIR ALAM | 102.93 | 0 | 50
37 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for new piped water supply scheme of Khila PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000255/2022-2023 | 329/AE/USD | 16/08/2022 | 45 | STEELCONC AND ASSOCIATES | 4.01 | 0 | 0
38 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
39 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khila PWSS of RWS Howrah Sub-Division under Howrah Division, P. H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000558/2022-2023 | 2488/HD | 30/11/2022 | 60 | M/S SYCHROTECH INDUSTRY | 54.33 | 0 | 100
40 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 3rd TW site Khila W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000623/2022-2023 | 2803/HD | 21/12/2022 | 60 | MAITY CONSTRUCTIONS | 7.7 | 0 | 60
41 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection(FHTC) of KHILA Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B). | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000819/2022-2023 | 1104/HD | 17/03/2023 | 863 | JAHANGIR ALAM | 113 | 0 | 35
42 | Howrah Division | RWS Howrah Sub-Division | Acceptance cum Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of KHILA Piped Water Supply Scheme under Udaynaryanpur block under Uluberia Sub- Division, PHE Dte.(Part-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000884/2022-2023 | 1450/HD | 30/03/2023 | 908 | M/S EL-CON | 620.6 | 0 | 50
43 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000042/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 29.79 | 0 | 0
44 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000053/2023-2024 | 3217/HD | 05/09/2023 | 0 | Resource Division | 38.86 | 0 | 0
45 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | je/blk/ulu1,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000070/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 8.77 | 0 | 0
46 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
47 | Howrah Division | RWS Howrah Sub-Division | Raising main & Inter Connection with both tube wells of Khodra Etarai PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000343/2023-2024 | 4636/HD | 21/12/2023 | 15 | UNIVERSAL CONSTRUCTION | 6.87 | 0 | 100
48 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Khorda Etarai PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000452/2021-2022 | 253/HD | 07/02/2022 | 15 | APEX ENGINEERING | 2.91 | 0 | 0
49 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khordah Etarai PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000560/2022-2023 | 2490/HD | 30/11/2022 | 45 | DEV DAS SHAW | 27.37 | 0 | 100
50 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 100 cum Capacity 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (733 nos) for KHORDA ETARAI PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000618/2022-2023 | 2784/HD | 20/12/2022 | 900 | AJAY MONDAL | 191.45 | 0 | 55
51 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000626/2022-2023 | 2806/HD | 21/12/2022 | 60 | JAHANGIR ALAM | 8.42 | 0 | 98
52 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Khorda Etarai W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | ORD/000628/2022-2023 | 2809/HD | 21/12/2022 | 60 | SR TRADING CORPORATION | 8.5 | 0 | 100
53 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | RTOR000033/2023-2024 | 2716/HD | 25/07/2023 | 0 | Resource Division | 13.78 | 0 | 0
54 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | RTOR000041/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 4.52 | 0 | 0
55 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | RTOR000065/2023-2024 | 28/HD | 03/01/2024 | 0 | Resource Division | 0.87 | 0 | 0
56 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,JE/RWS/Uluberia I,Junior Engineer2 | RTOR000069/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 2.18 | 0 | 0
57 | Howrah Division | Howrah Sadar Sub-Division | Concrete Approach Road at 1st Tubewell Site at Domjur (Zone-III) Khashmora PWSS under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000020/2024-2025 | 2725/HD | 11/06/2024 | 45 | SUJATA CONSTRUCTION | 9.63 | 0 | 100
58 | Howrah Division | Howrah Sadar Sub-Division | Work Order for 3 nos Construction of Pump House (5.40m x 3.60 m) at 1st , 2nd &3rd Tube Well Site ,Construction of Boundary Wall at 1st Tube Well Site,Construction of 2 nos Boundary Wall at 2nd & 3rd Tube Well Site,Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Domjur (Zone-III) Khasmara PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000029/2023-2024 | 1698/HD | 21/04/2023 | 925 | SUJATA CONSTRUCTION | 452.67 | 0 | 45
59 | Howrah Division | Howrah Sadar Sub-Division | Emergency Restoration of CI/DI Pipeline along with damaged main road due to laying of pipe line From Node No. 149 to 292 of Domjur (Zome-3) Khasmora PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000097/2025-2026 | 2942/HD | 25/06/2025 | 120 | SUJATA CONSTRUCTION | 59.8 | 0 | 0
60 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Khasmara (Zone-III) PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000205/2022-2023 | 78/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.42 | 0 | 0
61 | Howrah Division | Howrah Sadar Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Domjur Block) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000230/2025-2026 | 4128/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
62 | Howrah Division | Howrah Sadar Sub-Division | Pipe Carrying Structure for Crossing of Keto Pol at Khasmora PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000482/2024-2025 | 1014/HD | 21/02/2025 | 60 | GUPTA ENTERPRISE | 37.95 | 0 | 0
63 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (ZoneIII) Khasmara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000663/2022-2023 | 174/HD | 13/01/2023 | 45 | BALAJI UDDYOG | 38.37 | 0 | 100
64 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000013/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 130.95 | 0 | 0
65 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000076/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 14.79 | 0 | 0
66 | Howrah Division | Ulberia Sub-Division | Land Development and Approach Road at HW site of Tulsiberia PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000004/2025-2026 | 1826/HD | 09/04/2025 | 30 | MUKHERJEE CONSTRUCTION | 9.01 | 0 | 0
67 | Howrah Division | Ulberia Sub-Division | Construction of Pump House (3.60m x 3.30m) with water supply arrangement at Head Work site of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000009/2025-2026 | 1811/HD | 08/04/2025 | 45 | ARUP NANDY | 6.47 | 0 | 15
68 | Howrah Division | Ulberia Sub-Division | Construction of 1.8 mtrs. Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 4 layer barbed wire fencing around head work site including land development & approach road of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub Division under Howrah Division, PHE. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000011/2025-2026 | 1812/HD | 08/04/2025 | 60 | ARUP NANDY | 24.85 | 0 | 10
69 | Howrah Division | Ulberia Sub-Division | Work order for Interconnection between Tube wells & OHR at Tulsiberia Water Supply scheme at Uluberia-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000099/2023-2024 | 1948/HD | 10/05/2023 | 60 | SUNIL ENTERPRISE | 10.42 | 0 | 100
70 | Howrah Division | Ulberia Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-II & Uluberia-II Block) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000222/2025-2026 | 4120/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
71 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for new piped water supply scheme of Tulshiberia PWSS, Uluberia-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000361/2022-2023 | 456/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 3.13 | 0 | 0
72 | Howrah Division | Ulberia Sub-Division | Land Development & Approach Road at 2nd TW site of Tulsiberia PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000416/2024-2025 | 1491/AE/USD | 16/01/2025 | 20 | MM ENTERPRISE | 1.19 | 0 | 0
73 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall at HW Site of Tulsiberia W/S scheme within Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000453/2024-2025 | 988/HD | 20/02/2025 | 60 | SANJOY GHOSH | 27.81 | 0 | 0
74 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Tulsiberia PWSS of Uluberia-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000599/2022-2023 | 2715/HD | 14/12/2022 | 45 | ACME CONSTRUCTION | 36.15 | 0 | 0
75 | Howrah Division | Ulberia Sub-Division | Construction of 2.50 mtrs. Height Boundary Wall with double column after 15 mtrs interval along with 750 mm Height 4 layer barbed wire fencing around 2nd. TW site including with land development & approach road of Kamina adjacent to Tulshiberia PWSS at Uluberia-II Block under Uluberia Sub-Division under Howrah Division, PHE. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000734/2024-2025 | 1353/HD | 11/03/2025 | 268 | A.A ENTERPRISE | 9.3 | 0 | 85
76 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000006/2023-2024 | 1698/HD | 21/04/2023 | 0 | Resource Division | 5.48 | 0 | 0
77 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000024/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 20.18 | 0 | 0
78 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000102/2023-2024 | 530/HD | 06/02/2024 | 0 | Resource Division | 11.09 | 0 | 0
79 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline (PART-2) & Providing FHTC (PART-2) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000021/2023-2024 | 1674/HD | 19/04/2023 | 60 | PIKASU BOSE | 149.08 | 0 | 60
80 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Ichhapur PWSS (Mouza-Ichhapur, Ranmahal & Tripurapur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000073/2022-2023 | 1016/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 3.04 | 0 | 0
81 | Howrah Division | Howrah Sadar Sub-Division | Continuation order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000314/2023-2024 | 4254/HD | 28/11/2023 | 30 | AUXILIARY TUBEWELL DRILLERS | 25.64 | 0 | 100
82 | Howrah Division | Howrah Sadar Sub-Division | Restoration of road and Ancillary work for Ichapur PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000527/2024-2025 | 1068/HD | 27/02/2025 | 120 | MAITY CONSTRUCTION | 20.84 | 0 | 0
83 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ichapur PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000694/2022-2023 | 312/HD | 20/01/2023 | 30 | ALLIED TUBEWELLS PRIVATE LIMITED | 25.64 | 0 | 0
84 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 2 nos Pump House ( 5.40m x 3.60 m), 2nos Construction of Boundary Walls, Rising Main Pipeline Work, Laying Distribution Pipeline (Part-1) & Providing FHTC(Part-1) of Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division,PHE DTE (PART-I) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000796/2022-2023 | 977/HD | 10/03/2023 | 900 | D D CONSTRUCTION | 110.53 | 0 | 10
85 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection For Ichapur PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000870/2022-2023 | 1347/HD | 27/03/2023 | 300 | RANI CONSTRUCTION | 91.61 | 0 | 10
86 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000011/2024-2025 | 4348/HD | 30/09/2024 | 0 | Resource Division | 24.66 | 0 | 0
87 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000051/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 12.32 | 0 | 0
88 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000077/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 12.27 | 0 | 0
89 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000116/2023-2024 | 1317/HD | 14/03/2024 | 0 | Resource Division | 17.52 | 0 | 0
90 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
91 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000664/2022-2023 | 175/HD | 13/01/2023 | 1017 | B K ENTERPRISE | 77.78 | 0 | 50
92 | Howrah Division | Howrah Sadar Sub-Division | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P.H.E. DTE | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000774/2022-2023 | 795/HD | 27/02/2023 | 90 | UNIVERSAL CORPORATION | 143.99 | 0 | 50
93 | Howrah Division | Howrah Sadar Sub-Division | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-I) in DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000814/2022-2023 | 981/HD | 13/03/2023 | 180 | MA MANASA CONSTRUCTION | 148.59 | 0 | 48
94 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000014/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 47.46 | 0 | 0
95 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000077/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 19.07 | 0 | 0
96 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Additional laying distribution Pipeline work of Gabberia Mallickbagan PWSS at Panchla Block,of Howrah Sadar Sub Division under Howrah Division , PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000069/2023-2024 | 1930/HD | 10/05/2023 | 723 | ADITYA HAZRA | 52.7 | 0 | 30
97 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Gabberia PWSS (Mouza-Gabberia(CT) & Mallik Bagan (CT) of Panchla Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000079/2022-2023 | 1022/HD | 05/05/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.04 | 0 | 0
98 | Howrah Division | Howrah Sadar Sub-Division | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000148/2023-2024 | 2866/HD | 08/08/2023 | 910 | SAMIRON GHOSH | 1986.19 | 0 | 30
99 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000081/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 21.47 | 0 | 0
100 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000083/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 59.98 | 0 | 0
101 | Howrah Division | Howrah Sadar Sub-Division | Additional Laying Distribution Pipeline & approach road with land development at OHR site & allied works of Paschim Panchla PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (SM/13768) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000026/2024-2025 | 2828/HD | 20/06/2024 | 420 | SAMIRON GHOSH | 130.84 | 0 | 20
102 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Paschim Panchla PWSS (Mouza-Paschim Panchla(CT) & Dakshin Panchla) of Panchla Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000078/2022-2023 | 1021/HD | 05/05/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 0 | 100
103 | Howrah Division | Howrah Sadar Sub-Division | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000148/2023-2024 | 2866/HD | 08/08/2023 | 910 | SAMIRON GHOSH | 1986.19 | 0 | 30
104 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
105 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000083/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 12.18 | 0 | 0
106 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000105/2023-2024 | 843/HD | 22/02/2024 | 0 | Resource Division | 22.18 | 0 | 0
107 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000112/2023-2024 | 1094/HD | 05/03/2024 | 0 | Resource Division | 29.4 | 0 | 0
108 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000113/2023-2024 | 1094/HD | 05/03/2024 | 0 | Resource Division | 45.31 | 0 | 0
109 | Howrah Division | Howrah Sadar Sub-Division | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS | AE/SADAR | JE Sadar | BILL/00063/2024-2025 | BP-2024-25-19 | 26/04/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.3 | 0 | 0
110 | Howrah Division | Howrah Sadar Sub-Division | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS, | AE/SADAR | JE Sadar | BILL/00065/2024-2025 | BP-2024-25-20 | 23/04/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.12 | 0 | 0
111 | Howrah Division | Howrah Sadar Sub-Division | Payment of Way Leave Plan and Survey charges Bargachia Zone-II PWSS, | AE/SADAR | JE Sadar | BILL/00067/2024-2025 | BP-2024-25-21 | 23/04/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.11 | 0 | 0
112 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for payment of wayleave facility charges for Application ID : SER-KGP-2024-WL-34, Bargachia Zone-v | AE/SADAR | JE Sadar | BILL/00110/2024-2025 | BP-2024-25-50 | 07/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 7.37 | 0 | 0
113 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave Plan & Survey Charges | AE/SADAR | JE Sadar | BILL/00126/2024-2025 | BP-2024-25-68 | 16/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.03 | 0 | 0
114 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave facility charges | AE/SADAR | JE Sadar | BILL/00160/2024-2025 | BP-2024-25-99 | 28/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 6.22 | 0 | 0
115 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave facility charges | AE/SADAR | JE Sadar | BILL/00161/2024-2025 | BP-2024-25-100 | 28/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 17.55 | 0 | 0
116 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave facility charges | AE/SADAR | JE Sadar | BILL/00234/2024-2025 | BP-2024-25-121 | 11/06/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 8.37 | 0 | 0
117 | Howrah Division | Howrah Sadar Sub-Division | Payment for WBSEDCL Augmentation of Bargachia Water Supply Scheme (Zone-IV) Pump house no -I | AE/SADAR | JE Sadar | BILL/00241/2023-2024 | BP-2023-24-74 | 13/06/2023 | 0 | WBSEDCL | 3.91 | 0 | 0
118 | Howrah Division | Howrah Sadar Sub-Division | Payment for WBSEDCL Augmentation of Bargachia Water Supply Scheme (Zone-IV) Pump house no -II | AE/SADAR | JE Sadar | BILL/00242/2023-2024 | BP-2023-24-74 | 13/06/2023 | 0 | WBSEDCL | 3.37 | 0 | 0
119 | Howrah Division | Howrah Sadar Sub-Division | Restoration Work of Bituminous Road and Shoulder with allied work Bargachia Boharia Road from 2.30 kmp to 6.30 kmp (Due to cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-2025. | AE/SADAR | JE Sadar | BILL/00827/2024-2025 | BP-2024-25-495 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 34.15 | 0 | 0
120 | Howrah Division | Howrah Sadar Sub-Division | Post 5 years maintenance works for the road Begpara - Godaripara T06 at Jagatballavpur Block, Howrah under W.B.S.R.D.A. Howrah Division-I, Package No. WB/09/105. | AE/SADAR | JE Sadar | BILL/00853/2024-2025 | BP-2024-25-504 | 09/12/2024 | 0 | WBSRDA | 9.5 | 0 | 0
121 | Howrah Division | Howrah Sadar Sub-Division | Payment for Way Leave and Survey Charges Bargachia PWSS | AE/SADAR | JE Sadar | BILL/01656/2023-2024 | BP-2023-24-735 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.13 | 0 | 0
122 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall, 300, 400 & 500 cum capacity OHR, Rising Main Laying Distribution System & Providing FHTC for Augmentation of Bargachia (Zone-I, II, III, IV-A, IV-B) Piped Water Supply Scheme at Jagatballavpur Block under Howrah Division, PHE Dte in connection with JJM. | AE/SADAR | JE Sadar | ORD/000009/2023-2024 | 1559/HD | 06/04/2023 | 814 | GREEN ROYAL INFRA CON PRIVATE LIMITED | 2577.67 | 0 | 25
123 | Howrah Division | Howrah Sadar Sub-Division | Road Restoration, Supply and Fabrication of 700 mm Dia, 7.10 mm thick MS Casing Pipe and Pushing of Casing Pipe by Hydraulic Jack Pushing Method, Construction of RCC Retaining Wall, Land Development, Construction of 1 No. Culvert and ancillary works at Bargachia PWSS (Zone-VII, VIII & IX) of J.B. Pur Block under Howrah Sadar Sub-Division, Howrah Division, P.H.E. Dte.(SM/14095) | AE/SADAR | JE Sadar | ORD/000103/2025-2026 | 3057/HD | 08/07/2025 | 75 | REALIENCE CONSTRUCTION | 413.83 | 0 | 0
124 | Howrah Division | Howrah Sadar Sub-Division | Hiring of 1 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer Howrah Sadar Sub-Division, PHE Dte. Government of West Bengal. (for the period of 1 year)(for 365 days) | AE/SADAR | JE Sadar | ORD/000104/2024-2025 | 809/HSSD | 06/08/2024 | 365 | MD KADIR | 4.73 | 0 | 8
125 | Howrah Division | Howrah Sadar Sub-Division | Road restoration work, approach road and Land development at Over Head Reservoir Site, Construction of 1no Hume pipe culvert, RCC Retaining Wall & Jack Pushing of 700 mm dia M.S pipe as Casing Pipe to Cross Water carrier pipe (Between Node Point 81-82 of LDS drawing) at Bargachia zone-V & VI PWSS under Howrah Sadar Sub-Division of Howrah Division P.H.E.Dte. (SM/14095) | AE/SADAR | JE Sadar | ORD/000114/2024-2025 | 3871/HD | 04/09/2024 | 270 | S.P. CONSTRUCTION | 227.58 | 0 | 30
126 | Howrah Division | Howrah Sadar Sub-Division | Construction of R.C.C. Culvert at OHR site, Approach Road and Land Development at OHR Site, Retaining Wall at OHR site of Bargachia PWSS(Zone-VII) in J.B. Pur Block of Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | AE/SADAR | JE Sadar | ORD/000163/2024-2025 | 4195/HD | 26/09/2024 | 120 | COSMO ENTERPRISE | 65.1 | 0 | 0
127 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR | JE Sadar | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 390 | HORIZEN | 10.11 | 0 | 44
128 | Howrah Division | Howrah Sadar Sub-Division | Construction of Pump House, Boundary Wall, 400 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (2554 nos) For Augmentation of Bargachia PWSS (Zone-VII) in Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000486/2023-2024 | 454/HD | 01/02/2024 | 180 | M/S ASHA CONSTRUCTION | 442.08 | 0 | 12
129 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall, 500 cum Capacity OHR (2 nos), Rising Main, Laying Distribution Pipeline & Providing FHTC For AUGMENTATION OF Bargachia (ZONE-V and ZONE-VI) PWSS in Jagatballavpur Block under Howrah Sadar Sub-Division of HOWRAH DIVISION, P. H. E. DTE.. | AE/SADAR | JE Sadar | ORD/000634/2022-2023 | 05/HD | 02/01/2023 | 1080 | S.P. CONSTRUCTION | 1271.27 | 0 | 80
130 | Howrah Division | Howrah Sadar Sub-Division | Construction of 1 no. Slab culvert,Construction of RCC Retaining Wall, construction of approch road and land Devlopment at Over Head Reservoir Site at Bargachia (Zone -VIII) PWSS Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR | JE Sadar | ORD/000657/2023-2024 | 1246/HD | 12/03/2024 | 480 | REALIENCE CONSTRUCTION | 36.2 | 0 | 11
131 | Howrah Division | Howrah Sadar Sub-Division | Additional work related to Augmentation of Bargachia PWSS (For Zone-X) under JJM for land development for Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000660/2023-2024 | 193/HSSD | 23/02/2024 | 360 | S.B ENTERPRISE | 4.38 | 0 | 0
132 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone III (TW-1 &TW-II), Zone-IVA (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000686/2022-2023 | 305/HD | 20/01/2023 | 917 | B K ENTERPRISE | 69.42 | 0 | 50
133 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone VI (TW-1 &TW-II), Zone-VII (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000687/2022-2023 | 307/HD | 20/01/2023 | 120 | B K ENTERPRISE | 69.42 | 0 | 50
134 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone 1 (TW-1 &TW-II), Zone-II TW I&II at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000688/2022-2023 | 304/HD | 20/01/2023 | 60 | CARBON SERVICES INDIA | 68.08 | 0 | 50
135 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone IVB (TW-1 &TW-II), Zone-V (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000689/2022-2023 | 306/HD | 20/01/2023 | 817 | CARBON SERVICES INDIA | 68.08 | 0 | 100
136 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS Zone VIII (TW-1 &TW-II), Zone-IX (TW I&II) at Jagat ballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000690/2022-2023 | 308/HD | 20/01/2023 | 60 | WATER TECH | 68.83 | 0 | 50
137 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (One) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bargachia PWSS ZONE -X (TW I,II) of Jagatballavpur Block under Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000691/2022-2023 | 309/HD | 20/01/2023 | 30 | NADIA TUBEWELLS | 34.37 | 0 | 100
138 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall, 450 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (3187 nos) For Augmentation of Bargachia PWSS (Zone-VIII) in Jagatballavpur Block under Howrah Sadar sub Division of Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000708/2022-2023 | 336/HD | 24/01/2023 | 1170 | MONDAL PRECISION PVT. LTD. | 566.01 | 0 | 35
139 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall, 400 cum Capacity OHR, Rising Main, Laying Distribution Pipeline & Providing FHTC (2554 nos) For AUGMENTATION OF Bargachia PWSS (ZONE-IX) in Jagatballavpur Block under Howrah Sadar Sub-Division of HOWRAH DIVISION, P.H.E. DTE. | AE/SADAR | JE Sadar | ORD/000723/2022-2023 | 379/HD | 01/02/2023 | 900 | G.B. CONSTRUCTION AND CO | 462.97 | 0 | 15
140 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall, 400 cum Capacity OHR , Rising Main , Laying Distribution Pipeline & Providing FHTC (1615 nos) For Augmentation of Bargachia PWSS (Zone-X) In Jagatballavpur Block under Howrah Sadar sub Division of Howrah Division, P. H. E. Dte. | AE/SADAR | JE Sadar | ORD/000748/2022-2023 | 682/HD | 20/02/2023 | 1157 | B.B.C ENTERPRISE | 339 | 0 | 20
141 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR | JE Sadar | RTOR000001/2024-2025 | 1956/HD | 16/04/2024 | 0 | Resource Division | 17.78 | 0 | 0
142 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR | JE Sadar | RTOR000017/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 282.87 | 0 | 0
143 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR | JE Sadar | RTOR000072/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 176.2 | 0 | 0
144 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR | JE Sadar | RTOR000104/2023-2024 | 843/HD | 22/02/2024 | 0 | Resource Division | 31.83 | 0 | 0
145 | Howrah Division | Howrah Mechanical Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
146 | Howrah Division | Ulberia Sub-Division | Original quotation of WBSEDCL for Kamina Water Supply Scheme | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | BILL/00836/2023-2024 | BP-2023-24-485 | 23/11/2023 | 0 | WBSEDCL | 22.69 | 0 | 0
147 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials for in Kamina PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. in the District of Howrah. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000010/2023-2024 | 1593/HD | 12/04/2023 | 1200 | ARUP NANDY | 138.34 | 0 | 90
148 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000025/2023-2024 | 1690/HD | 20/04/2023 | 721 | JAHANGIR ALAM | 263.67 | 0 | 100
149 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
150 | Howrah Division | Ulberia Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Kamina PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000445/2021-2022 | 246/HD | 07/02/2022 | 15 | DULAL MAJUMDER | 3.44 | 0 | 100
151 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000858/2022-2023 | 1190/HD | 23/03/2023 | 45 | M/S ANUBHAB CONSTRUCTION | 92.63 | 0 | 100
152 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Kamina PWSS of Uluberia-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-C) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000859/2022-2023 | 1191/HD | 23/03/2023 | 758 | SUSHANTA MONDAL | 27.98 | 0 | 100
153 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000881/2022-2023 | 1195/HD | 23/03/2023 | 847 | ACME CONSTRUCTION | 90.87 | 0 | 85
154 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000026/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 44.93 | 0 | 0
155 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000055/2023-2024 | 3396/HD | 21/09/2023 | 0 | Resource Division | 48.32 | 0 | 0
156 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000058/2023-2024 | 4414/HD | 07/12/2023 | 0 | Resource Division | 45.12 | 0 | 0
157 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000094/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 6.16 | 0 | 0
158 | Howrah Division | Ulberia Sub-Division | Sinking of 2 nos Tube Well, Laying Distribution System & Construction of 100 cum RCC OHR & Interconnection between Tubewells & OHR for SHIBGACHHIA PWSS OF AMTA-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000130/2023-2024 | 2646/HD | 18/07/2023 | 1006 | MITHU BUILDERS | 262.08 | 0 | 70
159 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
160 | Howrah Division | Ulberia Sub-Division | Construction of 2nos switch room (5.40m x 3.60m) with water supply & sanitary arrangement at Head Work site & 2nd TW site of Shibgachia PWSS [SM/18193] of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000309/2023-2024 | 4340/HD | 04/12/2023 | 660 | KALIDAS ENTERPRISE | 12.56 | 0 | 100
161 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for new piped water supply scheme of Shibgachia PWSS, Amta-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000360/2022-2023 | 455/AE/USD | 15/09/2022 | 45 | VOYAGER | 3.2 | 0 | 0
162 | Howrah Division | Ulberia Sub-Division | Display Board at different PWSS at Amta-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000645/2023-2024 | 3220/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.76 | 0 | 100
163 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | RTOR000057/2023-2024 | 4184/HD | 22/11/2023 | 0 | Resource Division | 23.18 | 0 | 0
164 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | RTOR000090/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 2.4 | 0 | 0
165 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Sahapur piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) |  |  | ORD/000423/2021-2022 | 337/HD | 17/02/2022 | 30 | UNIVERSAL CONSTRUCTION | 2.98 | 0 | 100
166 | Howrah Division |  | Connection with distribution system and reconnection of FHTC & allied works, construction of 1 (One) no.pump house (5.40m x 3.60m),construction of 1 (One) no. boundary wall at Sahapur piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000602/2023-2024 | 1067/HD | 04/03/2024 | 60 | ADITYA HAZRA | 50.59 | 0 | 30
167 | Howrah Division |  | Additional construction of 1nos switch room (5.4x 3.6) at 4th TW site and laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. |  |  | ORD/000056/2024-2025 | 2858/HD | 24/06/2024 | 210 | RANI CONSTRUCTION | 6.28 | 0 | 100
168 | Howrah Division |  | Additional laying distribution pipeline with FHTC at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. |  |  | ORD/000074/2024-2025 | 3164/HD | 12/07/2024 | 420 | RANA ENTERPRISE | 34.95 | 0 | 100
169 | Howrah Division |  | Additional Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Balichack PWSS SM/18885 of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000666/2023-2024 | 1305/HD | 14/03/2024 | 60 | ACME CONSTRUCTION | 29.98 | 0 | 100
170 | Howrah Division | Ulberia Sub-Division | Work Order for Additional Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte.(Part-G) (Phase-I) | AE/Ulu | JE/USD | ORD/000097/2022-2023 | 111/AE/USD | 15/06/2022 | 45 | MAITY CONSTRUCTIONS | 4.89 | 0 | 100
171 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Kasra Mouza (Part) | AE/Ulu | JE/USD | ORD/000108/2020-2021 | 1503/HD | 04/11/2020 | 30 | PRADIP KUMAR JATI | 28.98 | 0 | 0
172 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kasra Mouza (Part) | AE/Ulu | JE/USD | ORD/000109/2020-2021 | 1504/HD | 04/11/2020 | 30 | DEV DAS SHOW | 18.74 | 0 | 0
173 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Bara Mahara Mouza) | AE/Ulu | JE/USD | ORD/000120/2020-2021 | 1515/HD | 04/11/2020 | 30 | PRADIP KUMAR JATI | 30.15 | 0 | 0
174 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-3) | AE/Ulu | JE/USD | ORD/000300/2021-2022 | 2231/HD | 09/12/2021 | 30 | PRADIP KUMAR JATI | 4.07 | 0 | 0
175 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | AE/Ulu | JE/USD | VCH/000777/2020-2021 | 84434 | 01/03/2021 | 0 | DEV DAS SHAW | 27.09 | 0 | 0
176 | Howrah Division | Ulberia Sub-Division | Retrofitting Khosalpur Water Supply Scheme | AE/Ulu | JE/USD | VCH/000869/2020-2021 | 84435 | 01/03/2021 | 0 | PRADIP KUMAR JATI | 24.12 | 0 | 0
177 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | AE/Ulu | JE/USD | VCH/000871/2020-2021 | 844327 | 17/03/2021 | 0 | JAHANGIR ALAM | 26.44 | 0 | 0
178 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme | AE/Ulu | JE/USD | VCH/000873/2020-2021 | 844330 | 17/03/2021 | 0 | M/S ASHIRBAD (INDIA) | 27.58 | 0 | 0
179 | Howrah Division | Ulberia Sub-Division | Additional Retrofitting Khoshalpur | AE/Ulu | JE/USD | VCH/000927/2021-2022 | BP-2021-22-387 | 07/03/2022 | 0 | JAHANGIR ALAM | 3.45 | 0 | 0
180 | Howrah Division | Ulberia Sub-Division | Additional Retrofitting Khoshalpur | AE/Ulu | JE/USD | VCH/000931/2021-2022 | BP-2021-22-385 | 08/03/2022 | 0 | JAHANGIR ALAM | 3.44 | 0 | 0
181 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme. | AE/Ulu | JE/USD | VCH/000952/2020-2021 | 8443106 | 30/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 21.16 | 0 | 0
182 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (Phase-1) | AE/Ulu | JE/USD | VCH/001021/2021-2022 | BP-2021-22-451 | 25/03/2022 | 0 | N. G ENGINEERING | 3.11 | 0 | 0
183 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | VCH/001027/2021-2022 | BP-2021-22-449 | 30/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 4.52 | 0 | 0
184 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-I) |  |  | ORD/000494/2020-2021 | 424/HD | 11/02/2021 | 30 | UNIVERSAL CORPORATION | 93.25 | 23.86 | 0
185 | Howrah Division |  | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) |  |  | VCH/000525/2021-2022 | 84437 | 12/11/2021 | 0 | UNIVERSAL CORPORATION | 7.85 | 0 | 0
186 | Howrah Division |  | Mass Awarness generation and IEC activities. |  |  | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0
187 | Howrah Division |  | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) |  |  | VCH/000644/2021-2022 | 844317 | 20/01/2022 | 0 | UNIVERSAL CORPORATION | 4.67 | 0 | 0
188 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) |  |  | VCH/000851/2021-2022 | 844325 | 24/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0
189 | Howrah Division |  | Retrofitting works for providing Functional Household Tap Connection FHTC under Bikihakola PWSS within Panchla Block (Phase-1) |  |  | VCH/000938/2020-2021 | 8443104 | 30/03/2021 | 0 | UNIVERSAL CORPORATION | 15.35 | 0 | 0
190 | Howrah Division | Ulberia Sub-Division | Work Order for Additional pipeline work for providing Functional Household Tap Connection(FHTC) from existing distribution system (Hazari para, Beg para, Molla para, Chandrapur primary school) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (Part-I) (Phase-B) | AE/Ulu | JE/USD | ORD/000135/2022-2023 | 132/AE/USD | 20/06/2022 | 45 | DDD CONSTRUCTION | 4.78 | 0 | 0
191 | Howrah Division | Ulberia Sub-Division | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Chandrapur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E. Dte.(Location-Chatra) | AE/Ulu | JE/USD | ORD/000380/2024-2025 | 784/HD | 04/02/2025 | 20 | AUXILIARY TUBEWELL DRILLERS | 14.4 | 0 | 0
192 | Howrah Division | Ulberia Sub-Division | Work Order for Additional pipe line work for providing Functional Household Tap Connection(FHTC) from existing distribution system (moksed para, Hazra para, molla para) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (Part-I) | AE/Ulu | JE/USD | ORD/000381/2021-2022 | 2378/HD | 24/12/2021 | 30 | MAA TARA CONSTRUCTION | 4.82 | 0 | 0
193 | Howrah Division | Ulberia Sub-Division | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) all complete at Chandrapur PWSS at Amta-I Block under Uluberia Sub Division within Howrah Division, P.H.E. Dte.(Location-Maheshguha) | AE/Ulu | JE/USD | ORD/000381/2024-2025 | 785/HD | 04/02/2025 | 20 | AUXILIARY TUBEWELL DRILLERS | 14.4 | 0 | 0
194 | Howrah Division | Ulberia Sub-Division | Work Order for Additional pipe line work for providing Functional Household Tap Connection(FHTC) from existing distribution system ( Mirpara, Bodok para, Khapara, Adolpara) at CHANDRAPUR W/S scheme under AMTA-I Block under Howrah Division, PHE Dte. (part-II) | AE/Ulu | JE/USD | ORD/000382/2021-2022 | 2379/HD | 24/12/2021 | 30 | QUICK CONCRETE PROJECT | 4.82 | 0 | 0
195 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur PipedWater Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-B) [CHANDRAPUR GP PART] | AE/Ulu | JE/USD | VCH/000814/2021-2022 | BP-2021-22-370 | 28/02/2022 | 0 | QUICK CONCRETE PROJECT | 35.83 | 0 | 0
196 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-A) [MAHISHGOHA GP] | AE/Ulu | JE/USD | VCH/000926/2021-2022 | BP-2021-22-388 | 08/03/2022 | 0 | PRADIP KUMAR JATI | 38.13 | 0 | 0
197 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chandrapur Piped Water Supply Scheme under Amta-I Block under Howrah Division, PHE Dte. (PART-D) [CHANDRAPUR GP PART] | AE/Ulu | JE/USD | VCH/000971/2021-2022 | BP-2021-22-417 | 14/03/2022 | 0 | MAA TARA CONSTRUCTION | 24.68 | 0 | 0
198 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site (2nd TW site) at Uttar & Dakhin Bhatora Zone-I of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000056/2023-2024 | 1848/HD | 02/05/2023 | 60 | SUNIL ENTERPRISE | 3.76 | 0 | 100
199 | Howrah Division | Ulberia Sub-Division | Additional laying distribution pipeline and Road restoration at Village-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu |  | ORD/000076/2025-2026 | 2762/HD | 12/06/2025 | 60 | RANA ENTERPRISE | 56.75 | 0 | 0
200 | Howrah Division | Ulberia Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Zone-I) 1505 nos | AE/Ulu |  | ORD/000412/2021-2022 | 318/HD | 16/02/2022 | 45 | GHOSH CONCERN | 58.39 | 0 | 0
201 | Howrah Division | RWS Howrah Sub-Division | Payment against requirement of fund for restoration of PMGSY Road WB-09-250 (T032- Malick Pukur ) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | BILL/00315/2023-2024 | BP-2023-24-115 | 27/06/2023 | 0 | WBSRDA | 10.14 | 0 | 0
202 | Howrah Division | RWS Howrah Sub-Division | Payment against requestion of fund for restoration of PMGSY road Package No- WB-09-250 (TO-32- Mallick Pukur) of Augmentation of Kalyanpur and Birampur Water Supply Scheme | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | BILL/00548/2023-2024 | BP-2023-24-259 | 31/08/2023 | 0 | WBSRDA | 10.14 | 0 | 0
203 | Howrah Division | RWS Howrah Sub-Division | Work Order for Augmentation of Kalyanpur Birampur Water Supply Schemem with LDS, Rising Main, FHTC work, at Bagnan-I Block of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000022/2022-2023 | 966/HD | 29/04/2022 | 8 | M/S EL-CON | 714.88 | 0 | 100
204 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Kalyanpur-Birampur W/S scheme at Bagnan-I Block in Uluberia SubDivision P.H.E. Dte. Under Howrah Division, P.H.E Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000028/2022-2023 | 1009/HD | 05/05/2022 | 30 | AQUATECH ENGINEERS | 35.2 | 0 | 0
205 | Howrah Division | RWS Howrah Sub-Division | Work order for Additional laying of pipeline at Augmentation of Kalyanpur Birampur Water Supply Scheme at Bagnan-I Block under Uluberia Sub-Division PHE Dte of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000089/2023-2024 | 1987/HD | 15/05/2023 | 120 | M/S EL-CON | 247.87 | 0 | 100
206 | Howrah Division | RWS Howrah Sub-Division | Work Order for Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 700m3 Staging Height 20 mtr. for Kalyanpur Birampur W/S Scheme under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000415/2021-2022 | 386/HD | 22/02/2022 | 20 | PROSENJIT DAS | 0.65 | 0 | 0
207 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000019/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 18.99 | 0 | 0
208 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000041/2022-2023 | 2639/HD | 09/12/2022 | 0 | Resource Division | 12.08 | 0 | 0
209 | Howrah Division | RWS Howrah Sub-Division | WBSRDA PAYMENT | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | VCH/000564/2022-2023 |  | 07/09/2022 | 0 | WBSRDA | 13.77 | 0 | 0
210 | Howrah Division | RWS Howrah Sub-Division | Indent of Material | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
211 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Kalyanpur Birampur, Bagnan-I under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | VCH/000961/2021-2022 | BP-2021-22-408 | 14/03/2022 | 0 | RADIANT | 3.68 | 0 | 0
212 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Land Development at HEAD WORK Site, Additional Laying of Distribution Pipe Lines at UTTAR MANASRI Piped Water Supply Scheme and Additional Laying of Distribution Pipe Lines at KHALATPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000012/2025-2026 | 1855/HD | 16/04/2025 | 300 | SAMIRON GHOSH | 96.34 | 0 | 40
213 | Howrah Division | RWS Howrah Sub-Division | Land Development and Additional Laying of Distribution Pipe Lines with providing FHTC for leftout area for Augmentation of Khalatpur Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.(SM/11271) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000040/2024-2025 | 2862/HD | 24/06/2024 | 360 | BISWAJIT BAG | 113.86 | 0 | 50
214 | Howrah Division | RWS Howrah Sub-Division | Continuous work order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/05/2025 to 30/06/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000043/2025-2026 | 123/RWS | 22/04/2025 | 61 | REKHA GUCHAIT | 0.79 | 0 | 0
215 | Howrah Division | RWS Howrah Sub-Division | Hiring of 1 no. Inspection Vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. for different PWSS in Udayanaryanpur Dev. Block, PHE Dte. Government of West Bengal (for the period from 01/07/2024 to 31/08/2024) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000053/2024-2025 | 347/RWS | 28/06/2024 | 62 | REKHA GUCHAIT | 0.79 | 0 | 0
216 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around 2nd Pump House site of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte.. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000076/2023-2024 | 1774/HD | 27/04/2023 | 45 | BINOY KOLEY | 5.16 | 0 | 100
217 | Howrah Division | RWS Howrah Sub-Division | Work Order for Constrcution of 1.5 mtrs. Height Boundary Wall along with 750mm Height 3 layer barbed wire around head work site of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000077/2023-2024 | 1775/HD | 27/04/2023 | 502 | MAITY CONSTRUCTIONS | 13.8 | 0 | 90
218 | Howrah Division | RWS Howrah Sub-Division | Work Order for Repairing of OHR & 2 nos Pump House(H/W & 2nd TW site) of KHALATPUR PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000079/2023-2024 | 1777/HD | 27/04/2023 | 45 | CHANDRANI ENTERPRISE | 6.64 | 0 | 100
219 | Howrah Division | RWS Howrah Sub-Division | Work order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/06/2025 to 31/07/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000079/2025-2026 | 178/A/RWS | 27/05/2025 | 61 | SANJIB BARMAN | 0.79 | 0 | 0
220 | Howrah Division | RWS Howrah Sub-Division | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/07/2025 to 31/08/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000106/2025-2026 | 215/RWS | 30/06/2025 | 62 | REKHA GUCHAIT | 0.79 | 0 | 0
221 | Howrah Division | RWS Howrah Sub-Division | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/09/2024 to 31/10/2024) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000112/2024-2025 | 423/RWS | 30/08/2024 | 61 | REKHA GUCHAIT | 0.79 | 0 | 0
222 | Howrah Division | RWS Howrah Sub-Division | Continuous work order for hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/09/2025 to 31/10/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000154/2025-2026 | 276/RWS | 21/08/2025 | 61 | REKHA GUCHAIT | 0.79 | 0 | 0
223 | Howrah Division | RWS Howrah Sub-Division | Continuous work order for hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2024 to 31/03/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000181/2024-2025 | 470/RWS | 30/09/2024 | 183 | M/S STAR CONSTRUCTION | 2.36 | 0 | 0
224 | Howrah Division | RWS Howrah Sub-Division | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/11/2024 to 31/12/2024) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000241/2024-2025 | 493/RWS | 30/10/2024 | 61 | REKHA GUCHAIT | 0.79 | 0 | 0
225 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Khalatpur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000265/2021-2022 | 2147/HD | 01/12/2021 | 15 | APEX ENGINEERING | 3.65 | 0 | 0
226 | Howrah Division | RWS Howrah Sub-Division | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/10/2023 to 30/11/2023) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000275/2023-2024 | 392/RWS | 29/09/2023 | 61 | DEB KUMAR DAS | 0.79 | 0 | 50
227 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000306/2022-2023 | 1752/HD | 30/08/2022 | 30 | BISWAJIT SAMANTA | 13.32 | 0 | 30
228 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000308/2022-2023 | 1753/HD | 30/08/2022 | 30 | LAKSHMI IRON | 28.41 | 0 | 10
229 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000309/2022-2023 | 1754/HD | 30/08/2022 | 30 | ARINDAM ENTERPRISE | 21.71 | 0 | 30
230 | Howrah Division | RWS Howrah Sub-Division | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/12/2023 to 31/01/2024) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000335/2023-2024 | 493/RWS | 30/11/2023 | 62 | DEB KUMAR DAS | 0.79 | 0 | 50
231 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000342/2022-2023 | 1854/HD | 09/09/2022 | 60 | M/S CARE | 155.84 | 0 | 50
232 | Howrah Division | RWS Howrah Sub-Division | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/01/2025 to 28/02/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000353/2024-2025 | 550/RWS | 31/12/2024 | 59 | REKHA GUCHAIT | 0.78 | 0 | 0
233 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Khalatpur Water Supply Scheme in Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000439/2022-2023 | 2101/HD | 12/10/2022 | 45 | A.K. SIKDAR | 111.19 | 0 | 30
234 | Howrah Division | RWS Howrah Sub-Division | Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/02/2024 to 31/03/2024) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000487/2023-2024 | 69/RWS | 31/01/2024 | 60 | DEB KUMAR DAS | 0.79 | 0 | 100
235 | Howrah Division | RWS Howrah Sub-Division | Continuation order for Hiring of 1 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage Permit from Regional Transport Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/03/2025 to 30/04/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000646/2024-2025 | 57/RWS | 27/02/2025 | 61 | REKHA GUCHAIT | 0.79 | 0 | 0
236 | Howrah Division | RWS Howrah Sub-Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Udaynarayanpur Block of Uluberia Sub Division under Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000651/2023-2024 | 1210/HD | 11/03/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.39 | 0 | 100
237 | Howrah Division | RWS Howrah Sub-Division | Hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/04/2024 to 30/09/2024) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000720/2023-2024 | 225/RWS | 28/03/2024 | 183 | M/S STAR CONSTRUCTION | 2.37 | 0 | 0
238 | Howrah Division | RWS Howrah Sub-Division | Hiring of 01 No. Diesel vehicle in good condition (traffic worthy) having licensed contract carriage permit from Regional Authority for the office of the Assistant Engineer, RWS Howrah Sub-Division, PHE Dte. Government of West Bengal (for the period from 01/04/2025 to 31/05/2025) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000919/2024-2025 | 103/RWS | 28/03/2025 | 61 | SANJIB BARMAN | 0.79 | 0 | 0
239 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000001/2023-2024 | 1552/HD | 05/04/2023 | 0 | Resource Division | 6.78 | 0 | 0
240 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000005/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 1.85 | 0 | 0
241 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000037/2022-2023 | 2113/HD | 09/11/2022 | 0 | Resource Division | 16.9 | 0 | 0
242 | Howrah Division |  | Bill for Power Connect in Bhurshit Bamunpara Water Supply Scheme |  |  | BILL/00481/2022-2023 | W/887 | 29/03/2023 | 0 | WBSEDCL | 11.77 | 0 | 0
243 | Howrah Division |  | Laskarpur |  |  | BILL/00497/2022-2023 | W/791 | 02/03/2023 | 0 | WBSEDCL | 2.68 | 0 | 0
244 | Howrah Division |  | Laskarpur |  |  | BILL/00507/2022-2023 |  | 03/03/2023 | 0 | WBSEDCL | 2.68 | 0 | 0
245 | Howrah Division |  | Supply Delivery & Installation of 250 mm dia valve with valve Chamber and Retrofitting work for existing Laskarpur Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000316/2022-2023 | 1795/HD | 05/09/2022 | 30 | ADRIJA ENTERPRISE | 2 | 0 | 0
246 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000924/2020-2021 | 647/21/2022 | 15/08/2020 | 0 | N. G ENGINEERING | 3.16 | 3.16 | 0
247 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000189/2021-2022 | W/173 | 06/08/2021 | 0 | DEV DAS SHAW | 8.08 | 0 | 0
248 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000190/2021-2022 | W/180 | 06/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 8.42 | 0 | 0
249 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000191/2021-2022 | W/181 | 06/08/2021 | 0 | N. G ENGINEERING | 4.29 | 0 | 0
250 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000198/2021-2022 | W/224 | 13/08/2021 | 0 | N. G ENGINEERING | 8.24 | 0 | 0
251 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000200/2021-2022 | W/172 | 14/08/2021 | 0 | DEV DAS SHAW | 16.14 | 0 | 0
252 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000370/2021-2022 | 844342 | 28/09/2021 | 0 | PRADIP KUMAR JATI | 10.19 | 0 | 0
253 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000419/2021-2022 | W/315 | 01/10/2021 | 0 | DEV DAS SHAW | 11.97 | 0 | 0
254 | Howrah Division |  | Laying additional UPVC pipe line for FHTC Laskarpur Water Supply Scheme |  |  | VCH/000514/2021-2022 | 84432 | 01/11/2021 | 0 | M/S ASHIRBAD (INDIA) | 3.45 | 0 | 0
255 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000591/2021-2022 | W/592 | 21/12/2021 | 0 | MONIRUL ISLAM | 3.32 | 0 | 0
256 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000647/2021-2022 | 844320 | 20/01/2022 | 0 | MONIRUL ISLAM | 3.87 | 0 | 0
257 | Howrah Division |  | Survey and Collection of hous hold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/001008/2020-2021 | 844374 | 25/03/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0
258 | Howrah Division | Howrah Sadar Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | AE/SADAR |  | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
259 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m),Construction of Boundary Wall at Head work Site, Others site Boundary Wall, Construction of 200 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/2/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Estimate of Providing FHTC (Functional Household Tap Connection) For Sankhali PWSS at Panchla Block of Howrah District under Howrah Division, P. H. E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000015/2023-2024 | 1595/HD | 12/04/2023 | 894 | REALIENCE CONSTRUCTION | 236.2 | 0 | 20
260 | Howrah Division | Howrah Mechanical Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
261 | Howrah Division | Howrah Mechanical Sub-Division | Additional Laying Distribution Pipe line for providing (FHTC), Land development and allied works of Shankhali PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000593/2023-2024 | 999/HD | 01/03/2024 | 270 | REALIENCE CONSTRUCTION | 41.91 | 0 | 100
262 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shankhali PWSS of Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000799/2022-2023 | 999/HD | 13/03/2023 | 45 | SPG ENTERPRISES | 25.7 | 0 | 100
263 | Howrah Division | Howrah Mechanical Sub-Division | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Shankhali PWSS of Panchla Block under Howrah Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000977/2022-2023 | 1456/HD | 13/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.63 | 0 | 100
264 | Howrah Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000082/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 6.52 | 0 | 0
265 | Howrah Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000084/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 4.34 | 0 | 0
266 | Howrah Division | Howrah Mechanical Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
267 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall (120 m Length) at 1st Tubewell Site, (66 m Length) at 2nd Tubewell Site & (52 m Length) at 3rd Tubewell Site, Construction of Approach Road with Paver Block from existing road to Head Work Site, Land Development of 3rd TW Site, construction of 1 nos switch room (3.6m x 3.00m) with water supply & sanitary arrangement at 3rd Tubewell site and Interconnection work with 3rd T. well of Jhikra PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000094/2025-2026 | 2885/HD | 23/06/2025 | 90 | K.P. CONSTRUCTION | 75.36 | 0 | 0
268 | Howrah Division | RWS Howrah Sub-Division | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 60 | PRANTIK DRILLING AGENCY | 77.89 | 0 | 100
269 | Howrah Division | RWS Howrah Sub-Division | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Jagadishpur G.P Area) Zone-14 Length= 536.00mtr.(PART-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000246/2020-2021 | 1194/HD | 30/09/2020 | 30 | ADITYA HAZRA | 3.12 | 0 | 0
270 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
271 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Jikira PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000441/2021-2022 | 242/HD | 07/02/2022 | 15 | VOYAGER | 3.36 | 0 | 0
272 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation,Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site, Laying Distribution Pipeline & Providing FHTC (3205 nos) for Jhikira Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000563/2022-2023 | 2501/HD | 30/11/2022 | 900 | K.P. CONSTRUCTION | 616.01 | 0 | 62
273 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | RTOR000029/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 21.53 | 0 | 0
274 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | RTOR000089/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 8.13 | 0 | 0
275 | Howrah Division |  | Work Order for Sinking of 1 (one) no PVC big dia additional Tube well 250 mm x 150 mm dia of 240 mtr deep at Nakubar W/S scheme at Amta-II Block in Uluberia Sub-Division under Howrah Division P.H.E Dte. |  |  | ORD/000188/2022-2023 | 1513/HD | 22/07/2022 | 20 | NADIA TUBEWELLS | 12.71 | 0 | 100
276 | Howrah Division |  | Work Order for Construction of switch room (3.60 m x 3.0 m) with water supply & sanitary arrangement at 3rd tube well site of Nakubar PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) |  |  | ORD/000583/2022-2023 | 2600/HD | 07/12/2022 | 781 | S.M. CONSTRUCTION | 4.7 | 0 | 100
277 | Howrah Division |  | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 250m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ajangachhi PWSS (SM/18561) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E.Dte. |  |  | ORD/000135/2024-2025 | 4061/HD | 18/09/2024 | 60 | LOKENATH ENTERPRISES | 12.81 | 0 | 100
278 | Howrah Division |  | Laying Distribution System & Providing House Hold Tap Connection (FHTC) & 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of AJANGACHI PWSS in AMTA-II Block of Howrah District under Howrah Division, P.H.E. Dte. |  |  | ORD/000180/2023-2024 | 2949/HD | 16/08/2023 | 730 | GEE BEE NIRMAN CO PVT LTD | 817.6 | 0 | 60
279 | Howrah Division |  | Preparation of DPR for new piped W/S scheme of Ajangachi PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000221/2022-2023 | 315/AE/USD | 16/08/2022 | 45 | VOYAGER | 3.85 | 0 | 0
280 | Howrah Division |  | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 60 | PRANTIK DRILLING AGENCY | 77.89 | 0 | 100
281 | Howrah Division |  | Additional laying distribution pipeline with DI(K-7) and HDPE(PE-100,PN6) at Ajangachi PWSS of Amta-II Block in Uluberia Sub Division, under Howrah Division, P.H.E. Dte. |  |  | ORD/000280/2025-2026 | 4414/HD | 25/11/2025 | 60 | GEE BEE NIRMAN COMPANY PVT. LTD. | 65.24 | 0 | 0
282 | Howrah Division |  | Sinking of 1(One) No. additional T.Well size (250 X 150mm) Dia and 230m deep, Drilling by Direct Rotary method with UPVC Pipes all complete at Ajangachi PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Location: Solbaga) |  |  | ORD/000358/2024-2025 | 270/HD | 15/01/2025 | 90 | PRANTIK DRILLING AGENCY | 14.6 | 0 | 100
283 | Howrah Division |  | Construction of approach Road including restoration of CC road with Bullah piling and shifting of DI(K-7/K-9) pipes near TantiparaHazrapara of Ajangachi PWSS of Amta-II Block under Uluberia Sub Division under Howrah Divison PHE Dte. |  |  | ORD/000912/2024-2025 | 1763/AE/USD | 05/03/2025 | 30 | S R TRADING CORPORATION | 4.61 | 0 | 0
284 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 5.54 | 0 | 0
285 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000114/2023-2024 | 1286/HD | 13/03/2024 | 0 | Resource Division | 58.29 | 0 | 0
286 | Howrah Division |  | Additional laying distribution pipeline with FHTC at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000045/2024-2025 | 2901/HD | 26/06/2024 | 525 | S.S. ENTERPRISE | 43.21 | 0 | 45
287 | Howrah Division |  | Additional construction of 1nos switch room (5.4x 3.6) at TW site at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub Division, under Howrah Division, P.H.E. Dte. |  |  | ORD/000057/2024-2025 | 2911/HD | 26/06/2024 | 30 | RANI CONSTRUCTION | 6.28 | 0 | 0
288 | Howrah Division |  | Sinking of 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sarda PWSS SM/18884 of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000669/2023-2024 | 1308/HD | 14/03/2024 | 376 | WESTERN WATER SUPPLY AGENCY | 14.64 | 0 | 100
289 | Howrah Division |  | Preparation of DPR for Source Strengthning at Sarda PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000682/2023-2024 | 517/AE/USD | 05/10/2023 | 30 | APEX TECHNOLOGIES | 0.78 | 0 | 100
290 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Islampur, JagatBallavpur under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/000279/2021-2022 | 2152/HD | 01/12/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.03 | 0 | 0
291 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Islampur PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/000335/2022-2023 | 1834/HD | 08/09/2022 | 40 | B K ENTERPRISE | 35.33 | 0 | 0
292 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall, 450 cum Capacity OHR, Rising Main , Laying Distribution Pipeline & Providing FHTC (4480 nos) For AUGMENTATION OF Islampur PWSS at Jagatballavpur Block under Howrah Sadar Sub Division of HOWRAH DIVISION, P. H. E. DTE.. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | ORD/000507/2022-2023 | 2256/HD | 04/11/2022 | 180 | SUBHASH BOSE | 571.07 | 0 | 25
293 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | RTOR000013/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 95.73 | 0 | 0
294 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | RTOR000053/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 27.6 | 0 | 0
295 | Howrah Division | Howrah Sadar Sub-Division | Indent of Material | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
296 | Howrah Division |  | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Sherpur PWSS (4th Tube well) of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000032/2025-2026 | 2102/HD | 29/04/2025 | 45 | MANAS MALICK | 5.95 | 0 | 0
297 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 12.32 | 0 | 0
298 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000108/2023-2024 | 964/HD | 28/02/2024 | 0 | Resource Division | 65.52 | 0 | 0
299 | Howrah Division | Ulberia Sub-Division | Work order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design & Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site HIjlak PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000105/2023-2024 | 2696/HD | 24/07/2023 | 1096 | PRADIP KUMAR JATI | 293.89 | 0 | 1
300 | Howrah Division | Ulberia Sub-Division | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Hizlok Head Work Site and 2nd TW Site at Hizlok PWSS of Bagnan-I Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/13747) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000133/2024-2025 | 4034/HD | 17/09/2024 | 90 | AQUATECH ENGINEER | 28.95 | 0 | 45
301 | Howrah Division | Ulberia Sub-Division | Additional laying distribution pipeline with FHTC at Bagur & Paschim Bainan Mouza part of Paschim Bainan PWSS adjoining to Hizlak PWSS of Bagnan-I Block in Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000204/2024-2025 | 4514/HD | 04/10/2024 | 45 | JOY CHANDI CONSTRUCTION | 48.54 | 0 | 100
302 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Hijlok PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000366/2022-2023 | 461/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 2.97 | 0 | 100
303 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000030/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 1.54 | 0 | 0
304 | Howrah Division | Ulberia Sub-Division | Work Order for Riverine effect over Construction of 400 m3 capacity and 20 mtr staging height RCC Over Head Reservoir including pile foundation & delivery inlet & outlet and overflow pipe connection and allied works as per departmental drawing (DRG No. ¿ PC-I/OHR/11/2012) at Chitnan water supply scheme under Uluberia Sub-Division, under Howrah Division PHE Dte | AE/Ulu | JE/USD | ORD/000395/2021-2022 | 160/HD | 25/01/2022 | 45 | S.N ENTERPRISE | 4.55 | 0 | 0
305 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) [Beral Mouza] [Number of FHTC to be provided (Approx) : 387] | AE/Ulu | JE/USD | ORD/000396/2020-2021 | 45/HD | 05/01/2021 | 30 | MS ASOKE GHOSH AND BROTHERS | 22.44 | 0 | 0
306 | Howrah Division | Ulberia Sub-Division | Retrofitting Chitnan Water Supply Scheme | AE/Ulu | JE/USD | VCH/000005/2021-2022 |  | 19/04/2021 | 0 | JAHANGIR ALAM | 23.87 | 0 | 0
307 | Howrah Division | Ulberia Sub-Division | Retrofitting Chitnan Water Supply Scheme | AE/Ulu | JE/USD | VCH/000006/2021-2022 | W/120 | 20/07/2021 | 0 | ASHOKE GHOSH AND BROTHERS | 15.46 | 0 | 0
308 | Howrah Division | Ulberia Sub-Division | Retrofitting Chitnan Water Supply scheme | AE/Ulu | JE/USD | VCH/000023/2021-2022 | W/170 | 09/08/2021 | 0 | PRASANTA SANA | 19.78 | 0 | 0
309 | Howrah Division | Ulberia Sub-Division | Retrofitting Chitnan | AE/Ulu | JE/USD | VCH/000038/2021-2022 | W/171 | 09/08/2021 | 0 | BOSE AND CO. | 26.83 | 0 | 0
310 | Howrah Division | Ulberia Sub-Division | Retrofitting Chitnan | AE/Ulu | JE/USD | VCH/000039/2021-2022 |  | 03/06/2021 | 0 | S.N ENTERPRISE | 26.88 | 0 | 0
311 | Howrah Division | Ulberia Sub-Division | Work Order for Riverine effect over Construction of 400 m3 capacity and 20 mtr staging height RCC Over Head Reservoir including pile foundation & delivery inlet & outlet and overflow pipe connection and allied works as per departmental drawing (DRG No. ¿ PC-I/OHR/11/2012) at Chitnan water supply scheme under Uluberia Sub-Division, under Howrah Division PHE Dte | AE/Ulu | JE/USD | VCH/000348/2022-2023 |  | 20/07/2022 | 0 | S.N ENTERPRISE | 3.52 | 0 | 0
312 | Howrah Division | Ulberia Sub-Division | Construction of Bounadry wall Chitnan Water supply scheme | AE/Ulu | JE/USD | VCH/000405/2022-2023 | BP-2022-23-71 | 14/06/2022 | 0 | M/S SARADA UDYOG | 2.14 | 0 | 0
313 | Howrah Division | Ulberia Sub-Division | Construction of 28 nos stand post at in various place of Chitnan Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-II) | AE/Ulu | JE/USD | VCH/000802/2021-2022 | BP-2021-22-338 | 17/02/2022 | 0 | ANUP PAUL | 2.63 | 0 | 0
314 | Howrah Division | Ulberia Sub-Division | Construction of 35 nos stand post at in various place of Chitnan Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-I) | AE/Ulu | JE/USD | VCH/000803/2021-2022 | BP-2021-22-339 | 17/02/2022 | 0 | ANUP PAUL | 3.28 | 0 | 0
315 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitnan Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) [Mirgram Mouza] [Number of FHTC to be provided (Approx) : 415] | AE/Ulu | JE/USD | VCH/001010/2021-2022 | BP-2021-22-472 | 30/03/2022 | 0 | PRASANTA SANA | 4.79 | 0 | 0
316 | Howrah Division | RWS Howrah Sub-Division | Work Order for Augmentation of Kanupat Water Supply scheme by laying distribution system, providing functional house hold tap connection (FHTC) work with geo tagging by using Jal Swapna app, construction of RCC elevated reservior of capacity 200 m3 of staging height 20 mtr including soil investigation under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000130/2022-2023 | 1339/HD | 27/06/2022 | 548 | JAHANGIR ALAM | 216.52 | 0 | 90
317 | Howrah Division | RWS Howrah Sub-Division | Shifting and stacking of serviceable DI pipes and specials within the campus at Kanupat Store under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000152/2024-2025 | 737/AE/USD | 30/08/2024 | 25 | BISWAJIT BAG | 2.43 | 0 | 100
318 | Howrah Division | RWS Howrah Sub-Division | Construction of approach road cum internal pathway at HW site of Kanupat PWSS Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000157/2024-2025 | 4133/HD | 23/09/2024 | 15 | BISWAJIT BAG | 6.64 | 0 | 0
319 | Howrah Division | RWS Howrah Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Udaynarayanpur Block) (PART-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000225/2025-2026 | 4123/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0
320 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Kanupat PWSS, Udaynarayanpur Block Under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000250/2021-2022 | 2109/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.05 | 0 | 0
321 | Howrah Division | RWS Howrah Sub-Division | Display Board at different PWSS at Uluberia-II Udaynarayanpur Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000643/2023-2024 | 3218/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.26 | 0 | 100
322 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000020/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 11.87 | 0 | 0
323 | Howrah Division | RWS Howrah Sub-Division | Indent of Material | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
324 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Kasmali Mouza (part) |  |  | ORD/000152/2020-2021 | 1607/HD | 09/11/2020 | 30 | CONSTRUCTION CORNER | 28.68 | 0 | 100
325 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (for Kasmali Mouza(part) |  |  | ORD/000153/2020-2021 | 1608/HD | 09/11/2020 | 30 | CONSTRUCTION CORNER | 28.67 | 0 | 100
326 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) (for Kasmali Mouza(part) |  |  | ORD/000154/2020-2021 | 1617/HD | 09/11/2020 | 30 | S RAHA ENTERPRISE | 16.6 | 0 | 0
327 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) & School, AWC from existing distribution system at Kharigeria mouza of Kasmali W/S scheme under Amta-II Block under Howrah Division, PHE Dte. |  |  | ORD/000271/2022-2023 | 353/AE/USD | 22/08/2022 | 45 | BANERJEE ENTERPRISE | 1.85 | 0 | 0
328 | Howrah Division |  | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-3). |  |  | ORD/000351/2022-2023 | 435/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.78 | 0 | 0
329 | Howrah Division |  | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-6). |  |  | ORD/000354/2022-2023 | 438/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.81 | 0 | 0
330 | Howrah Division |  | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-7). |  |  | ORD/000355/2022-2023 | 439/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.77 | 0 | 0
331 | Howrah Division |  | Construction of balance portion of boundary wall at 2nd TW site of Kasmali W/S scheme in Uluberia Sub-division, under Howrah Division P.H.E Dte. |  |  | ORD/000389/2022-2023 | 477/AE/USD | 16/09/2022 | 45 | M/S HOWRAH CONSTRUCTION | 3.34 | 0 | 0
332 | Howrah Division |  | Additional work for Retrofitting of providing Functional Household Tap Connection (FHTC) from existing distribution system of Kasmali pipe water supply scheme under Amta-II Block under Howrah Division, PHE Dte. |  |  | VCH/000847/2021-2022 | 844320 | 24/03/2022 | 0 | S RAHA ENTERPRISE | 1.51 | 0 | 0
333 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme |  |  | VCH/000883/2020-2021 | 844363 | 25/03/2021 | 0 | BANERJEE ENTERPRISE | 8.99 | 0 | 0
334 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kasmali Mouza of Kasmali piped water supply scheme |  |  | VCH/000895/2020-2021 | 844386 | 26/03/2021 | 0 | S RAHA ENTERPRISE | 15.64 | 0 | 0
335 | Howrah Division |  | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/001009/2020-2021 | 844375 | 25/03/2021 | 0 | STEELCONC AND ASSOCIATES | 2.17 | 0 | 0
336 | Howrah Division | Ulberia Sub-Division | Work Order for Replacement of distribution network with higher dia pipes at the closed vicinity of the Head work site of Uttar Khoriop Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000063/2022-2023 | 1057/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 4.83 | 0 | 0
337 | Howrah Division | Ulberia Sub-Division | Work Order for construction of outlet drawing system with 160 mm dia HDPE pipe including interconnection of overflow & washout of newly constructed OHR of Uttar Khoriop w/s Scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000064/2022-2023 | 1058/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 3.04 | 0 | 0
338 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Nignan Mouza(Part) | AE/Ulu | JE/USD | ORD/000155/2020-2021 | 1618/HD | 09/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 29.09 | 0 | 100
339 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (for Khari Geria Mouza part) | AE/Ulu | JE/USD | ORD/000156/2020-2021 | 1619/HD | 09/11/2020 | 30 | N. G ENGINEERING | 29.1 | 0 | 100
340 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kasmali piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-F) (for Khari Geria Mouza part) | AE/Ulu | JE/USD | ORD/000157/2020-2021 | 1620/HD | 09/11/2020 | 30 | BANERJEE ENTERPRISE | 9.49 | 0 | 0
341 | Howrah Division | Ulberia Sub-Division | Development of land, plinth protection of boundary wall construction of pathway and other allied works of Chitanan W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000243/2021-2022 | 2173/HD | 01/12/2021 | 30 | S.N ENTERPRISE | 4.13 | 0 | 0
342 | Howrah Division | Ulberia Sub-Division | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000348/2024-2025 | 4832/HD | 20/11/2024 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
343 | Howrah Division | Ulberia Sub-Division | Mass Awarness generation and IEC activities. | AE/Ulu | JE/USD | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0
344 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 73-74-75-76-70-73-67-70-71-67-47-71 under Uluberia-II block under Howrah Division, PHE Dte. (Part-M) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000013/2022-2023 | 837/HD | 11/04/2022 | 30 | NAUTANDAS & CO. | 4.8 | 0 | 0
345 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 1-2-3-4-5-6-7-8, 2-22-23-24-25 under Uluberia-II block under Howrah Division, PHE Dte. (Part-H) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000016/2022-2023 | 832/HD | 11/04/2022 | 30 | S.S ENTERPRISE | 4.83 | 0 | 0
346 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 24-27-28, 27-43-51-52-53, 51-56 under Uluberia-II block under Howrah Division, PHE Dte. (Part-I) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000017/2022-2023 | 833/HD | 11/04/2022 | 30 | NAG ENTERPRISE | 4.73 | 0 | 0
347 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 43-46-50 under Uluberia-II block under Howrah Division, PHE Dte. (Part-J) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000018/2022-2023 | 834/HD | 11/04/2022 | 30 | JOY GURU TRADING | 4.54 | 0 | 0
348 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 56-57-54-52, 54-55, 57-62-64, 56-58-59-60-61-65-62, 65-66 under Uluberia-II block under Howrah Division, PHE Dte. (Part-K) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000019/2022-2023 | 835/HD | 11/04/2022 | 30 | SHIV SHAKTI CONSTRUCTION | 4.75 | 0 | 0
349 | Howrah Division | Ulberia Sub-Division | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Augumentation of Surikhali Water Supply scheme (Zone-I) in Uluberia-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000020/2022-2023 | 838/HD | 11/04/2022 | 30 | MONIRUL ISLAM | 3.45 | 0 | 100
350 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section62-68-69-72-75-76-77-78, 61-63, under Uluberia-II block under Howrah Division, PHE Dte. (Part-L) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000021/2022-2023 | 836/HD | 11/04/2022 | 30 | CONSTRUCTION UDOUG | 4.67 | 0 | 0
351 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 87-88-89-91-90-, 85-87, 83-85-86, 83-84, 79-83under Uluberia-II block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000035/2022-2023 | 825/HD | 11/04/2022 | 30 | DEBABRATA CHAKRABORTY | 4.37 | 0 | 0
352 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 92-93-94-95-96-97-98, 96-99-100-101-102-103 under Uluberia-II block under Howrah Division, PHE Dte. (Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000036/2022-2023 | 826/HD | 11/04/2022 | 30 | ARINDAM ENTERPRISE | 4.77 | 0 | 0
353 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 79-80-81-82-92, 79-49-29 under Uluberia-II block under Howrah Division, PHE Dte. (Part-C) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000037/2022-2023 | 827/HD | 11/04/2022 | 30 | A.N ROY & CO | 4.72 | 0 | 0
354 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 11-23-25-29-30 under Uluberia-II block under Howrah Division, PHE Dte. (Part-D) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000038/2022-2023 | 828/HD | 11/04/2022 | 30 | BINOY KOLEY | 4.83 | 0 | 0
355 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 8-9-10-11-12-13-14-15-16-17, 9-21-18-19-20 under Uluberia-II block under Howrah Division, PHE Dte. (Part-E) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000039/2022-2023 | 829/HD | 11/04/2022 | 30 | SUNIL ENTERPRISE | 4.71 | 0 | 0
356 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 21-26-31-32-33-34, 13-18 under Uluberia-II block under Howrah Division, PHE Dte. (Part-F) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000040/2022-2023 | 830/HD | 11/04/2022 | 30 | MONIRUL ISLAM | 4.82 | 0 | 0
357 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline at Augumentation of Surikhali Water Supply Scheme (Zone-II) section 34-35-36-37-38-39, 38-40-41-42-44-45-47-48 under Uluberia-II block under Howrah Division, PHE Dte. (Part-G) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000041/2022-2023 | 831/HD | 11/04/2022 | 30 | A.B. ENTERPRISE | 4.81 | 0 | 0
358 | Howrah Division | Ulberia Sub-Division | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000044/2022-2023 | 839/HD | 11/04/2022 | 30 | APEX ENGINEERING | 4.97 | 0 | 0
359 | Howrah Division | Ulberia Sub-Division | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000045/2022-2023 | 840/HD | 11/04/2022 | 30 | S.M. CONSTRUCTION | 4.97 | 0 | 0
360 | Howrah Division | Ulberia Sub-Division | Work Order for providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-II) at under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000046/2022-2023 | 841/HD | 11/04/2022 | 30 | SK ANISUR | 4.98 | 0 | 0
361 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 3 (three) nos PVC big dia Tube well 250 mm x 150 mm dia of 250 mtr deep for Augmentation of Surikhali W/S scheme at Uluberia-II Block in Uluberia Sub-Division under Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000190/2022-2023 | 1515/HD | 22/07/2022 | 30 | NADIA TUBEWELLS | 39.12 | 0 | 0
362 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Surikhali Water Supply Scheme (Zone-I) at section (103-106-109-113-126-129-130-137-140-143-148-153-107-104) under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte.(Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000520/2021-2022 | 564/HD | 14/03/2022 | 30 | JOY GURU TRADING | 12.27 | 0 | 100
363 | Howrah Division | Ulberia Sub-Division | Work Order for Laying UPVC & DI pipeline & providing Functional Household Tap Connection (FHTC) at Augmentation of Surikhali Water Supply Scheme (Zone-I) under Uluberia-II block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000521/2021-2022 | 563/HD | 14/03/2022 | 45 | MODERN CONSTRUCTION | 84.8 | 0 | 100
364 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000024/2021-2022 | 407/HD | 24/02/2022 | 0 | Resource Division | 7.99 | 0 | 0
365 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Surikhali PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | VCH/000829/2021-2022 | BP-2021-22-364 | 28/02/2022 | 0 | APEX ENGINEERING | 3.47 | 0 | 0
366 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
367 | Howrah Division | Ulberia Sub-Division | Manku Bakshihat Road from 0.00 Km to 1.50 Km (in streches) Restoration of Head Crust due to laying of water Pipelines from PHE dte end for Augmentation of Mankur Deulgram piped water supply scheme under Highway Division P.W Roads Dte in the district Howrah during the year 2023-2024 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | BILL/00233/2024-2025 | BP-2024-25-124 | 11/06/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 2.08 | 0 | 0
368 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Mankur & Deulgram PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000252/2021-2022 | 2121/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.58 | 0 | 0
369 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Mankur Deulgram PWSS at Bagnan-I Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000334/2022-2023 | 1833/HD | 08/09/2022 | 40 | AUXILIARY TUBEWELL DRILLERS | 35.39 | 0 | 100
370 | Howrah Division | Ulberia Sub-Division | Temporary Approach road towards Head works site for Augmentation of Makur Deulgram PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Divison PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000529/2023-2024 | 2037/AE/USD | 13/02/2024 | 60 | NOBLE ENTERPRISE | 2 | 0 | 100
371 | Howrah Division | Ulberia Sub-Division | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 3rd tube well site of Mankur Deulgram PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000533/2023-2024 | 2036/AE/USD | 13/02/2024 | 60 | JSZ GLOBAL | 4.85 | 0 | 100
372 | Howrah Division | Ulberia Sub-Division | Work Order for alternative laying of damaged UPVC pipe,construction of RCC stand post, valve chamber and other allied work at Mankur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000538/2021-2022 | 670/HD | 23/03/2022 | 30 | S.S ENTERPRISE | 4.9 | 0 | 0
373 | Howrah Division | Ulberia Sub-Division | Construction of 750 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation at Mankur Deulgram PWSS at Bagnan-I Block under Uluberia Sub-Division PHE Dte under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000553/2023-2024 | 895/HD | 27/02/2024 | 720 | KALPANA TRADERS | 192.53 | 0 | 20
374 | Howrah Division | Ulberia Sub-Division | Work Order for Laying of Distribution Pipe Lines(UPVC & DI) with allied works and Providing Functional Household Tap Connection(FHTC). Interconnection between Tube wells and construction of switch room (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site for Augmentation of MANKUR-DEULGRAM Water Supply Scheme In Bagnan-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000633/2022-2023 | 2746/HD | 15/12/2022 | 961 | S.P. CONSTRUCTION | 674.25 | 0 | 60
375 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000036/2023-2024 | 2753/HD | 28/07/2023 | 0 | Resource Division | 15.4 | 0 | 0
376 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000059/2023-2024 | 4695/HD | 26/12/2023 | 0 | Resource Division | 48.28 | 0 | 0
377 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
378 | Howrah Division | Howrah Sadar Sub-Division | Construction of R.C.C Slab Culvert, Construction of 1(one) no. Pump House (5.40m x 3.60m), construction of 2(Two) nos. boundary wall, construction of approach road and land Development at 2nd tubewell site and allied pipe laying work (DI) for connecting tubewell with the distribution main at Maju PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000032/2024-2025 | 2836/HD | 20/06/2024 | 180 | SAMIRON GHOSH | 51.95 | 0 | 50
379 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Additional Laying Distribution Pipeline & allied works of Maju PWSS at J.Bpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000042/2023-2024 | 1785/HD | 28/04/2023 | 479 | SAMIRON GHOSH | 322.25 | 0 | 100
380 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 390 | HORIZEN | 10.11 | 0 | 44
381 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Maju PWSS at Jagatballavpur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000336/2022-2023 | 1835/HD | 08/09/2022 | 40 | B K ENTERPRISE | 35.32 | 0 | 0
382 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction Of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work & Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) with Boundary Wall and Pump House and 2 nos. Canal Crossing of Augmentation of Maju PWSS Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000419/2022-2023 | 2095/HD | 12/10/2022 | 910 | SAMIRON GHOSH | 838.17 | 0 | 50
383 | Howrah Division | Howrah Sadar Sub-Division | Sinking 2 nos. 250 X 150 mm dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30 m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Maju PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000670/2023-2024 | 1309/HD | 14/03/2024 | 60 | ACME CONSTRUCTION | 29.18 | 0 | 100
384 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000015/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 62.17 | 0 | 0
385 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000052/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 35.16 | 0 | 0
386 | Howrah Division | Howrah Sadar Sub-Division | Indent of Material | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
387 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Maju PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000960/2021-2022 | BP-2021-22-407 | 14/03/2022 | 0 | STEELCONC AND ASSOCIATES | 4.28 | 0 | 0
388 | Howrah Division | Ulberia Sub-Division | 1 no Kiosk (Size inside 2.44 x 1.52m) and additional laying distribution pipeline with FHTC at Kanpur Zone-II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000046/2024-2025 | 2904/HD | 26/06/2024 | 420 | MAITY CONSTRUCTION | 22.06 | 0 | 100
389 | Howrah Division | Ulberia Sub-Division | Work Order for Interconnection between tube wells & OHR at Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000051/2023-2024 | 1843/HD | 02/05/2023 | 60 | PRADIP KUMAR JATI | 9.35 | 0 | 100
390 | Howrah Division | Ulberia Sub-Division | Balance laying distribution pipeline at Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(Basantapur part) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000090/2025-2026 | 2807/HD | 17/06/2025 | 90 | PRADIP KUMAR JATI | 96.92 | 0 | 0
391 | Howrah Division | Ulberia Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) Mouza-Bhetkepara | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000238/2022-2023 | 1712/HD | 24/08/2022 | 45 | BISWAJIT BAG | 50.4 | 0 | 100
392 | Howrah Division | Ulberia Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) Mouza-PearapurHowrah. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000239/2022-2023 | 1713/HD | 24/08/2022 | 45 | SUNIRMAN ENTERPRISE | 38.67 | 0 | 100
393 | Howrah Division | Ulberia Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) Mouza-Habla | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000240/2022-2023 | 1714/HD | 24/08/2022 | 45 | USHA CONCERN | 33.16 | 0 | 20
394 | Howrah Division | Ulberia Sub-Division | Work Order for Laying HDPE pipeline & Providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) Mouza-Basantapur. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000343/2022-2023 | 1855/HD | 09/09/2022 | 60 | M/S EL-CON | 225.77 | 0 | 100
395 | Howrah Division | Ulberia Sub-Division | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Pearapur & Habla Mouza) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000347/2024-2025 | 5290/HD | 17/12/2024 | 45 | SUNIRMAN ENTERPRISE | 13.41 | 0 | 0
396 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 500 cum Capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. Drawing No.PC-I/OHR/09/2012 (Sheet No.1&2) & Laying HDPE & DI pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Kanpur Piped Water Supply Scheme (Zone-II) under Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000357/2022-2023 | 1908/HD | 15/09/2022 | 180 | PRADIP KUMAR JATI | 155.22 | 0 | 100
397 | Howrah Division | Ulberia Sub-Division | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Basantapur part mouza). | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000357/2023-2024 | 683/AE/USD | 06/11/2023 | 60 | PRADIP KUMAR JATI | 3.51 | 0 | 0
398 | Howrah Division | Ulberia Sub-Division | Emergent Road restoration work at Basantapur Mouza of Kanpur Zone II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/10021) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000412/2024-2025 | 1483/AE/USD | 16/01/2025 | 20 | BISWAJIT BAG | 4.83 | 0 | 0
399 | Howrah Division | Ulberia Sub-Division | Additional Laying of pipeline Augmentation of Kanpur Zone-II PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Bhetkepara mouza) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000445/2023-2024 | 216/HD | 17/01/2024 | 60 | BISWAJIT BAG | 13.11 | 0 | 100
400 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall at HW Site and additional pipeline at Basantupur Mouza of Augmentation of Kanpur Zone-II PWSS under Amta-I in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000456/2023-2024 | 246/HD | 18/01/2024 | 60 | PRADIP KUMAR JATI | 52.5 | 0 | 70
401 | Howrah Division | Ulberia Sub-Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. on smooth durable wall surface preferably of Govt. premises boundary wall under Amta-I and Amta-II Block of Uluberia Sub Division under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000549/2023-2024 | 847/HD | 22/02/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 4.1 | 0 | 100
402 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of switch room (3.60m x 3.0m) with water supply & sanitary arrangement at 3rd tube well site of Augmentation of Kanpur(Zone-II) PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000578/2022-2023 | 2595/HD | 07/12/2022 | 60 | A.N ROY & CO | 4.79 | 0 | 100
403 | Howrah Division | Ulberia Sub-Division | Sinking of additonal 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kanpur Zone-II PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | ORD/000668/2023-2024 | 1307/HD | 14/03/2024 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.71 | 0 | 100
404 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | RTOR000038/2023-2024 | 2753/HD | 28/07/2023 | 0 | Resource Division | 18.48 | 0 | 0
405 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | RTOR000043/2022-2023 | 2639/HD | 09/12/2022 | 0 | Resource Division | 33.45 | 0 | 0
406 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Kanpur PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | VCH/000828/2021-2022 | BP-2021-22-367 | 28/02/2022 | 0 | STEELCONC AND ASSOCIATES | 3.86 | 0 | 0
407 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer6 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
408 | Howrah Division | Howrah Sadar Sub-Division | Restoration work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 2.1 kmp to 3.5 kmp( due to Cutting for PHE water line) under Howrah Division in the dist of Howrah during the year 2024-2025 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00826/2024-2025 | BP-2024-25-494 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 5.33 | 0 | 0
409 | Howrah Division | Howrah Sadar Sub-Division | 2Nos Construction of Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Site, Reparing of 2 nos ExistingPump House 3rd & 4th TW site (3.60m x 3.00 m), Construction of Boundary Wall at 1st Tube Well Site (30 m X 20 m), 3 nos Boundary Wall at 2nd, 3rd & 4th Tube Well Site (12 m X 12 m), Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 4th Pump House, 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) Augmentation of Bipra Noapara at PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000134/2023-2024 | 2713/HD | 25/07/2023 | 1095 | B.B.C ENTERPRISE | 556.42 | 0 | 82
410 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Bipro Noapara PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000220/2022-2023 | 79/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.89 | 0 | 0
411 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
412 | Howrah Division | Howrah Sadar Sub-Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Jagatballavpur and Domjur Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000550/2023-2024 | 846/HD | 22/02/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 4.85 | 0 | 100
413 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bipra Noapara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000661/2022-2023 | 171/HD | 13/01/2023 | 45 | M DHARA AND BROTHERS | 51.16 | 0 | 25
414 | Howrah Division | Howrah Sadar Sub-Division | Laying of additional distribution pipeline and road restoration at Bipro Naopara PWSS at Domjur Block under Howrah Sadar Sub Division of Howrah Division, PHE Dte. (SM/11711) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000720/2024-2025 | 1322/HD | 10/03/2025 | 60 | B.B.C ENTERPRISE | 106.17 | 0 | 30
415 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000002/2024-2025 | 3589/HD | 13/08/2024 | 0 | Resource Division | 6.33 | 0 | 0
416 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000008/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 43.47 | 0 | 0
417 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000027/2024-2025 | 4769/HD | 14/11/2024 | 0 | Resource Division | 33.74 | 0 | 0
418 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000059/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 21.49 | 0 | 0
419 | Howrah Division | RWS Howrah Sub-Division | Construction of Kiosk (Two nos.) at Saoria PWSS of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Size inside 3.0 x 2.4m). | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000256/2024-2025 | 1109/AE/USD | 05/11/2024 | 15 | MAA TARA ENTERPRISE | 2.18 | 0 | 100
420 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
421 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Saoria PWSS at Amta-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000337/2022-2023 | 1836/HD | 08/09/2022 | 40 | DIBAKAR SHAW | 26.67 | 0 | 100
422 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying of Distribution System(UPVC & DI), Providing Functional Household Tap Connection (FHTC), Interconnection between tube wells, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials at HW site and construction of Two storied switch room ( 5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown at Head Work site & 2nd Tube well site of SAORIA PWSS of Amta-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000426/2022-2023 | 2085/HD | 11/10/2022 | 1319 | KAMIRUL SK AND CO. | 370.75 | 0 | 63
423 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Saoria PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000443/2021-2022 | 244/HD | 07/02/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.86 | 0 | 0
424 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | RTOR000025/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 24.23 | 0 | 0
425 | Howrah Division | Ulberia Sub-Division | Laying Distribution Pipe Lines(UPVC & DI) With Allied Works and Providing Household Functional Tap Connection & Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection and cost of pipes, specials including foundation design for NAYACHAK PWSS OF ULUBERIA-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000141/2023-2024 | 2808/HD | 03/08/2023 | 730 | GUPTA ENTERPRISE | 775.72 | 0 | 60
426 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nayachak PWSS of Uluberia-II block of Uluberia Sub Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | ORD/000601/2022-2023 | 2717/HD | 14/12/2022 | 841 | AQUATECH ENGINEERS | 54.31 | 0 | 100
427 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000026/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 160.85 | 0 | 0
428 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000027/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 159.48 | 0 | 0
429 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,Junior Engineer5 | RTOR000036/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 7.39 | 0 | 0
430 | Howrah Division | Howrah Mechanical Sub-Division | Sinking 1 no. 300 X 200 mm dia and 240 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 60 mtr. long PVC housing pipe & 200 mm dia. 150 mtr. long well pipe alongwith 3m blank pipe all complete including cost of materials under Jaynagar PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000071/2025-2026 | 2681/HD | 05/06/2025 | 150 | AQUATECH ENGINEERS | 19.16 | 0 | 0
431 | Howrah Division | Howrah Mechanical Sub-Division | Construction of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Foundation Design & All pipe Connection, 2(Two) Nos. Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Construction of Boundary Wall of 2nd Tube well site, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection-3079) for Jaynagar PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000214/2023-2024 | 3278/HD | 13/09/2023 | 335 | REALIENCE CONSTRUCTION | 529.89 | 0 | 0
432 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jaynagar PWSS(2 nos) & Banharishpur PWSS(2 nos) of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000800/2022-2023 | 1000/HD | 13/03/2023 | 977 | PRANTIK DRILLING AGENCY | 68.83 | 0 | 25
433 | Howrah Division | Howrah Mechanical Sub-Division | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Joynagar PWSS of Panchla Block under Howrah Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000978/2022-2023 | 1459/HD | 14/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 0 | 100
434 | Howrah Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000064/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 18.97 | 0 | 0
435 | Howrah Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000085/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 54.61 | 0 | 0
436 | Howrah Division | Howrah Mechanical Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer3 | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
437 | Howrah Division |  | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. |  |  | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
438 | Howrah Division | Ulberia Sub-Division | Work order for Ground Water Based Water Supply Scheme for Village CHAKUR of Bagnan I Block under Uluberia Sub-Division of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000372/2021-2022 | 69/HD | 11/01/2022 | 1201 | JAHANGIR ALAM | 162.65 | 0 | 83
439 | Howrah Division | Ulberia Sub-Division | Balance work in connection with water supply & sanitary arrangement of Pump House at Head Work site of Chakur Pipes water supply scheme of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000638/2023-2024 | 366/AE/USD | 21/08/2023 | 30 | M.K.ENTERPRISE | 0.4 | 0 | 100
440 | Howrah Division | Ulberia Sub-Division | Development of 2nd Tube well at Chakur PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000871/2022-2023 | 942/AE/USD | 22/03/2023 | 30 | LOKENATH ENTERPRISES | 0.71 | 0 | 100
441 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000007/2022-2023 | 1222/HD | 09/06/2022 | 0 | Resource Division | 1.35 | 0 | 0
442 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000023/2021-2022 | 408/HD | 24/02/2022 | 0 | Resource Division | 11.59 | 0 | 0
443 | Howrah Division | Ulberia Sub-Division | WBSRDA PAYMENT | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/000565/2022-2023 |  | 07/09/2022 | 0 | WBSRDA | 17.22 | 0 | 0
444 | Howrah Division | Ulberia Sub-Division | WBSRDA | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/000570/2022-2023 |  | 07/09/2022 | 0 | WBSRDA | 17.22 | 0 | 0
445 | Howrah Division | Ulberia Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold= 110 nos. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/000813/2021-2022 | BP-2021-22-365 | 28/02/2022 | 0 | APEX ENGINEERING | 2.77 | 0 | 0
446 | Howrah Division | Ulberia Sub-Division | Chakur W/S Scheme. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/000911/2021-2022 | BP-2021-22-482 | 30/03/2022 | 0 | JAHANGIR ALAM | 58.28 | 0 | 0
447 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Keshabpur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR |  | ORD/000003/2023-2024 | 1529/HD | 04/04/2023 | 765 | GARHBETA-I UNEMPLOYED YOUTH ENGINEERS CO OP | 25.31 | 0 | 100
448 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Boundary Wall, Repairing of Pump House (3.60 m x 3.00 m), Laying of Distribution Pipeline & Providing FHTC (1413 nos) for Augmentation of Keshabpur PWSS of Domjur Block under Howrah Division, PHE Dte. (Part-II) | AE/SADAR |  | ORD/000016/2023-2024 | 1547/HD | 04/04/2023 | 60 | MA MANASA CONSTRUCTION | 152.7 | 0 | 20
449 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Keshabpur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR |  | ORD/000231/2022-2023 | 84/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.64 | 0 | 100
450 | Howrah Division | Howrah Sadar Sub-Division | Construction of Pump House (5.40m x 3.60m) at 1st Tube Well Site, Laying of Rising main from Tube well including Road restoration & specials, Laying of Distribution system & providing Functional Household Tap Connection (FHTC) for Augmentation of KESHABPUR PWSS at Domjur Block under Howrah Division P.H.E Dte. (PART-1) [No. of FHTC = 1413] | AE/SADAR |  | ORD/000454/2023-2024 | 217/HD | 17/01/2024 | 540 | UNIQUE AGENCY | 194 | 0 | 10
451 | Howrah Division | Howrah Sadar Sub-Division | Laying of additional distribution pipe line and Road restoration at Keshabpur PWSS at Domjur Block under Howrah Sadar Sub-Division of Howrah Division PHE. | AE/SADAR |  | ORD/000645/2024-2025 | 1250/HD | 06/03/2025 | 60 | MA MANASA CONSTRUCTION | 27.71 | 0 | 0
452 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR |  | RTOR000058/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 8.7 | 0 | 0
453 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR |  | RTOR000063/2023-2024 | 4718/HD | 27/12/2023 | 0 | Resource Division | 88.18 | 0 | 0
454 | Howrah Division |  | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & Construction of 4 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement and 400 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design of HAROP (ZONE-II) PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. |  |  | ORD/000147/2023-2024 | 2846/HD | 07/08/2023 | 968 | SUBHASH BOSE | 506.25 | 0 | 35
455 | Howrah Division |  | Preparation of DPR for Augmentation of Harop PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000223/2022-2023 | 316/AE/USD | 16/08/2022 | 45 | MS SOBHA AND CO | 3.48 | 0 | 90
456 | Howrah Division |  | Sinking of 5 (Five) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Harop PWSS Zone -I (1 no) & Zone-II (2 nos) & Matinala PWSS (2 nos) of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000249/2023-2024 | 3533/HD | 04/10/2023 | 60 | AQUATECH ENGINEERS | 64.95 | 0 | 40
457 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 6.16 | 0 | 0
458 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 11.4 | 0 | 0
459 | Howrah Division |  | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells, construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at TW Sites and 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design for UDANG (ZONE-II) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. |  |  | ORD/000145/2023-2024 | 2839/HD | 07/08/2023 | 846 | NATURAL RESOURCES CONSORTIUM | 501.82 | 0 | 45
460 | Howrah Division |  | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells UDONG (ZONE-I) PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. |  |  | ORD/000159/2023-2024 | 2977/HD | 17/08/2023 | 600 | TAPU SAHA | 410.47 | 0 | 100
461 | Howrah Division |  | Sinking of 3(Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udang Zone-I & Zone-II 2 nos under Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000191/2023-2024 | 3133/HD | 29/08/2023 | 564 | NADIA TUBEWELLS | 38.94 | 0 | 68
462 | Howrah Division |  | Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 4th tube well (Replaced) site of Udang Zone-I PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) |  |  | ORD/000194/2024-2025 | 786/AE/USD | 09/09/2024 | 181 | DEBANANDA CONSTRUCTION | 4.72 | 0 | 100
463 | Howrah Division |  | Work for Preparation of DPR for Augmentation of Udong PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000219/2022-2023 | 314/AE/USD | 16/08/2022 | 45 | MS SOBHA AND CO | 3.83 | 0 | 100
464 | Howrah Division |  | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. |  |  | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
465 | Howrah Division |  | Construction of boundary wall at 2nd T/W Site of Udong Zone-II W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. |  |  | ORD/000369/2024-2025 | 705/HD | 30/01/2025 | 225 | TIYASA ENTERPRISE | 7.68 | 0 | 0
466 | Howrah Division |  | Land Development & Approach Road at 2nd TW site of Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. |  |  | ORD/000411/2024-2025 | 1482/AE/USD | 15/01/2025 | 20 | NOBLE ENTERPRISE | 1.24 | 0 | 0
467 | Howrah Division |  | Construction of boundary wall at HW Site of Udong Zone-II W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. |  |  | ORD/000448/2024-2025 | 964/HD | 19/02/2025 | 60 | NATURAL RESOURCES CONSORTIUM | 20.46 | 0 | 0
468 | Howrah Division |  | Road restoration work with Bullah piling at Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Division PHED. |  |  | ORD/000450/2024-2025 | 986/HD | 20/02/2025 | 45 | NATURAL RESOURCES CONSORTIUM | 20.08 | 0 | 0
469 | Howrah Division |  | Land Development and Approach Road at HW site of Udong Zone-II PWSS of Amta-I Block under Uluberia Sub Division under Howrah Division PHED. |  |  | ORD/000451/2024-2025 | 987/HD | 20/02/2025 | 30 | NATURAL RESOURCES CONSORTIUM | 12.13 | 0 | 0
470 | Howrah Division |  | Providing Additional Pipeline and repairing/ reconnection of existing FHTCs at Vill: Ranapara & Deorah of Udong-II G.P of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000456/2024-2025 | 989/HD | 20/02/2025 | 60 | ADITYA HAZRA | 29.76 | 0 | 0
471 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 9.24 | 0 | 0
472 | Howrah Division |  | Construction of 2nos switch room (5.4x 3.6) at TW site at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/18883) |  |  | ORD/000070/2024-2025 | 3120/HD | 09/07/2024 | 300 | S S CONSTRUCTION | 12.56 | 0 | 100
473 | Howrah Division |  | Laying distribution pipeline with FHTC at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/18883) |  |  | ORD/000079/2024-2025 | 3323/HD | 24/07/2024 | 420 | MODERN CONSTRUCTION | 136.25 | 0 | 75
474 | Howrah Division |  | Preparation of DPR for Source Strengthening at Amragori PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000460/2023-2024 | 826/AE/USD | 08/12/2023 | 30 | APEX ENGINEERING | 2.76 | 0 | 0
475 | Howrah Division |  | Construction of boundary wall with approach road at 3rd Site of Amragori PWSS in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000659/2023-2024 | 1299/HD | 13/03/2024 | 420 | MANAS MALICK | 8.25 | 0 | 100
476 | Howrah Division |  | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Amragori PWSS of Amta-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (SM/18883) |  |  | ORD/000674/2023-2024 | 1311/HD | 14/03/2024 | 60 | DEV DAS SHAW | 29.68 | 0 | 100
477 | Howrah Division |  | Construction of Remaining of 550 cum capacity, 20 mtr. staging height Over Head Reservoir including all allied works as per Departmental drawing at Amragori W/S Scheme under Howrah Division, P.H.E. Dte. |  |  | ORD/001295/2020-2021 | 542/HD | 15/06/2020 | 90 | UNIQUE AGENCY | 31.5 | 0 | 0
478 | Howrah Division |  | Additional work in connection with commissioning of Water Treatment Plant under SANKRAIL SURFACE WATER BASED WATER SUPPLY PROJECT of Howrah District under Howrah Division, P.H.E. Dte. (TSM/019257) |  |  | ORD/000067/2024-2025 | 3105/HD | 08/07/2024 | 540 | GBC INFRASTRUCTURE PRIVATE LIMITED | 405.4 | 0 | 10
479 | Howrah Division |  | Design, Construction, supply, erection and commissioning of additional fixed type intake jetty of Raw Water pipe carrying RCC walkway with all necessary components from 35 Mtr chainage of carriageway to connecting metal road of RAW WATER INTAKE near Manikpur ferry ghat on Hooghly river along with other allied works of Augmentation of surface water based Sankrail Piped Water Supply Scheme of SANKRAIL BLOCK (including Sankrail Food Park) and part of Domjur, Panchla & Uluberia-II Blocks of Howrah District under Howrah Division, PHE Dte. (SM/19187) |  |  | ORD/000119/2024-2025 | 3925/HD | 09/09/2024 | 90 | GBC INFRASTRUCTURE PRIVATE LIMITED | 2185.5 | 0 | 10
480 | Howrah Division |  | Surveying, designing, laying, commissioning of two separate rising mains for conveyance of treated water from CWR at Sankrail WTP premises to 14 nos. OHRs (12 nos. new, 02 no. existing) falling under jurisdiction of PHE Dte. at Sankrail, Domjur (Part), Panchla (Part), Uluberia-II (Part) block and 09 nos. overhead reservoirs falling under jurisdiction of KMDA (erstwhile KMW&SA) at Sankrail (Part) and Domjur (Part) block and to 01 no. GLR at Sankrail Food Park. Design of foundation, construction and commissioning of foundation and superstructure of 12 nos. OHRs of different capacity, 1No. GLR, minor repair, maintenance and painting of 02 nos. existing OHRs, and other allied works along with Trial run of 3 months and 6 (six) months operation and maintenance of the entire system. |  |  | ORD/000606/2023-2024 | 1288/HD | 13/03/2024 | 365 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 10463 | 0 | 2
481 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-1 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 7417] |  |  | ORD/000607/2023-2024 | 1185/HD | 09/03/2024 | 663 | THE UNICON ENGINEERS | 1192.14 | 0 | 45
482 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-2 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5396] |  |  | ORD/000608/2023-2024 | 1186/HD | 09/03/2024 | 663 | LIMRA CONSTRUCTION AND INDUSTRIAL DEVELOPMENT | 907.2 | 0 | 30
483 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-3 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3325] |  |  | ORD/000609/2023-2024 | 1187/HD | 09/03/2024 | 663 | M/S SARADA CONSTRUCTION | 1010.66 | 0 | 10
484 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-5 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 8336] |  |  | ORD/000610/2023-2024 | 1170/HD | 07/03/2024 | 665 | SAMIRON GHOSH | 1396.13 | 0 | 30
485 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-6A for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3997] |  |  | ORD/000611/2023-2024 | 1188/HD | 09/03/2024 | 753 | M/S. GHOSH CONSTRUCTION | 750.92 | 0 | 80
486 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-6B for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 3997] |  |  | ORD/000612/2023-2024 | 1171/HD | 07/03/2024 | 665 | GUPTA ENTERPRISE | 589.74 | 0 | 30
487 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-9A for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5719] |  |  | ORD/000614/2023-2024 | 1190/HD | 09/03/2024 | 659 | MONDAL PRECISION PRIVATE LIMITED | 617.29 | 0 | 10
488 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-9B for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 5717] |  |  | ORD/000615/2023-2024 | 1174/HD | 07/03/2024 | 574 | MONDAL ENTERPISE | 947 | 0 | 30
489 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-10 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 7772] |  |  | ORD/000616/2023-2024 | 1192/HD | 09/03/2024 | 662 | DEBAPRIYA DUTTA | 981.48 | 0 | 50
490 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-11 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 8889] |  |  | ORD/000617/2023-2024 | 1165/HD | 07/03/2024 | 665 | M/S R.S. CONSTRUCTION | 1341.84 | 0 | 10
491 | Howrah Division |  | Laying Distribution Pipeline and providing FHTC at Zone-7 for Augmentation of Sankrail Surface Water Based Project of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC = 6811] |  |  | ORD/000619/2023-2024 | 1189/HD | 09/03/2024 | 663 | MAHI ENTERPRISE | 825.27 | 0 | 20
492 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 233.2 | 0 | 0
493 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 113.45 | 0 | 0
494 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 177.21 | 0 | 0
495 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 93.64 | 0 | 0
496 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 255.11 | 0 | 0
497 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 33.48 | 0 | 0
498 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 98.37 | 0 | 0
499 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000021/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 93.99 | 0 | 0
500 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 329.84 | 0 | 0
501 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000023/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 56.03 | 0 | 0
502 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 120.02 | 0 | 0
503 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 160.35 | 0 | 0
504 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 4718/HD | 12/11/2024 | 0 | Resource Division | 240.65 | 0 | 0
505 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000041/2024-2025 | 5224/HD | 13/12/2024 | 0 | Resource Division | 3852.02 | 0 | 0
506 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000042/2024-2025 | 5380/HD | 26/12/2024 | 0 | Resource Division | 124.66 | 0 | 0
507 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-D) (for Banuchak mouza) | AE/Ulu | JE/USD | ORD/000161/2020-2021 | 1624/HD | 09/11/2020 | 30 | M/S. CHANDIMATA CONSTRUCTION | 18.4 | 0 | 0
508 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) for Balichak mouza part) | AE/Ulu | JE/USD | ORD/000162/2020-2021 | 1625/HD | 09/11/2020 | 30 | P B ENTERPRISE | 26.26 | 0 | 0
509 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) for Balichak mouza part) | AE/Ulu | JE/USD | ORD/000163/2020-2021 | 1626/HD | 09/11/2020 | 30 | P B ENTERPRISE | 27.61 | 0 | 0
510 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu | JE/USD | RTOR000031/2021-2022 | 495/HD | 07/03/2022 | 0 | Resource Division | 8.01 | 0 | 0
511 | Howrah Division | Ulberia Sub-Division | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme | AE/Ulu | JE/USD | VCH/000077/2021-2022 | W/39 | 11/06/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0
512 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply | AE/Ulu | JE/USD | VCH/000592/2021-2022 | W/594 | 21/12/2021 | 0 | RANA ENTERPRISE | 7.58 | 0 | 0
513 | Howrah Division | Ulberia Sub-Division | Retrofitting BalichakWater Supply Scheme | AE/Ulu | JE/USD | VCH/000891/2020-2021 | 844383 | 26/03/2021 | 0 | N. G ENGINEERING | 21.63 | 0 | 0
514 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. | AE/Ulu | JE/USD | VCH/000953/2020-2021 | 8443107 | 30/03/2021 | 0 | P B ENTERPRISE | 23.52 | 0 | 0
515 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. | AE/Ulu | JE/USD | VCH/000973/2020-2021 | 8443120 | 30/03/2021 | 0 | GHOSH CONCERN | 27.96 | 0 | 0
516 | Howrah Division | Ulberia Sub-Division | Additional laying distribution pipeline with repairing/ Refixing of FHTC at Kanpur Rejuvenation PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000641/2024-2025 | 1234/HD | 05/03/2025 | 270 | S.S. ENTERPRISE | 12.46 | 0 | 80
517 | Howrah Division | Ulberia Sub-Division | Mass Awarness generation and IEC activities. | AE/Ulu | JE/USD | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0
518 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000841/2020-2021 | 844333 | 17/03/2021 | 0 | MAA LAXMI ENTERPRISE | 8.15 | 0 | 0
519 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000874/2020-2021 | 844342 | 17/03/2021 | 0 | MAA LAXMI ENTERPRISE | 21.27 | 0 | 0
520 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000879/2021-2022 | 844328 | 29/03/2022 | 0 | PIKASU BOSE | 3.17 | 0 | 0
521 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000900/2020-2021 | 844391 | 26/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 18.79 | 0 | 0
522 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000901/2020-2021 | 844392 | 26/03/2021 | 0 | PIKASU BOSE | 25.48 | 0 | 0
523 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-A) |  |  | ORD/000123/2020-2021 | 1533/HD | 05/11/2020 | 30 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0
524 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-B) |  |  | ORD/000124/2020-2021 | 1534/HD | 05/11/2020 | 30 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0
525 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-C) |  |  | ORD/000125/2020-2021 | 1535/HD | 05/11/2020 | 30 | ALOK ENTERPRISE A UNIT OF SAKET TREXIM PVT. LTD. | 18.84 | 0 | 0
526 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000925/2020-2021 | 627/21/2022 | 15/08/2020 | 0 | RAKESH ENTERPRISE | 4.35 | 2.9 | 0
527 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000211/2021-2022 | W/217 | 18/08/2021 | 0 | ALOK ENTERPRISE | 16.11 | 0 | 0
528 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000371/2021-2022 | 844343 | 28/09/2021 | 0 | RAKESH ENTERPRISE | 4.11 | 0 | 0
529 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000373/2021-2022 | 844345 | 28/09/2021 | 0 | UNIQUE AGENCY | 9.35 | 0 | 0
530 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000774/2020-2021 | 84431 | 01/03/2021 | 0 | UNIQUE AGENCY | 16.13 | 0 | 0
531 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000775/2020-2021 | 84432 | 01/03/2021 | 0 | UNIQUE AGENCY | 16.15 | 0 | 0
532 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000876/2020-2021 | 844356 | 23/03/2021 | 0 | BUILT INDIA | 15.55 | 0 | 0
533 | Howrah Division | Ulberia Sub-Division | Work Order for Interconnection between tube wells & OHR at Mellock Bramhan Dkhakuria PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000052/2023-2024 | 1844/HD | 02/05/2023 | 60 | GLOBUS CONSULTANCY | 7.34 | 0 | 100
534 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Mellock Brahman Dhakuria PWSS, Bagnan-II Block Under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000253/2021-2022 | 2122/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.32 | 0 | 0
535 | Howrah Division | Ulberia Sub-Division | Work Order for Laying of Distribution System with providing FHTC for Augmentation of Mellock Brahman Dakuria PWSS of Bagnan-I & Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. [Mouza-Masiyara, Sondail, Bramhan Dhakuria- House Hold- 950 nos] (Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000396/2022-2023 | 1996/HD | 26/09/2022 | 45 | CREATION CONSTRUCTION | 107.55 | 0 | 100
536 | Howrah Division | Ulberia Sub-Division | Work Order for Laying of Distribution System with providing FHTC and Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), for Augumentation of Mellock Brahman Dakuria PWSS of Bagnan-I & Bagnan-II Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. in the District of Howrah.[Mouza-Subsit, House Hold- 1454] (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000485/2022-2023 | 2170/HD | 21/10/2022 | 893 | GHOSH CONCERN | 310.35 | 0 | 70
537 | Howrah Division | Ulberia Sub-Division | Additional Laying of pipeline Mellock Brahman Dhakuria PWSS of Bagnan-I & II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Sondail & Masiyara) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000527/2023-2024 | 2033/AE/USD | 13/02/2024 | 60 | DUNCON INDIA | 16.52 | 0 | 100
538 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of switch room (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Augumentation of Mellock Brahman Dakuria PWSS of Bagnan-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000579/2022-2023 | 2596/HD | 07/12/2022 | 60 | LOKENATH ENTERPRISES | 6.24 | 0 | 100
539 | Howrah Division | Ulberia Sub-Division | Development of 2nd Tube well at Mellock Bramhan Dkhakuria PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000869/2022-2023 | 941/AE/USD | 22/03/2023 | 30 | LOKENATH ENTERPRISES | 0.71 | 0 | 100
540 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000037/2023-2024 | 2753/HD | 28/07/2023 | 0 | Resource Division | 12.32 | 0 | 0
541 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000091/2022-2023 | 775/HD | 24/02/2023 | 0 | Resource Division | 46.08 | 0 | 0
542 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
543 | Howrah Division | Ulberia Sub-Division | Quotation money depostion for new service connection at Nischintapur Water Supply Scheme | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/01743/2023-2024 | BP-2023-24-775 | 29/03/2024 | 0 | WBSEDCL | 15.58 | 0 | 0
544 | Howrah Division | Ulberia Sub-Division | Additional LDS work to reduce water scanty problem from 3rd TW to Ghoshpara at Mouza Sheoraberia of Nischintapur PWSS under Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000114/2025-2026 | 3145/HD | 15/07/2025 | 45 | KALIDAS ENTERPRISE | 21.67 | 0 | 80
545 | Howrah Division | Ulberia Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-II Block) (PART-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000219/2025-2026 | 4117/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
546 | Howrah Division | Ulberia Sub-Division | Additional LDS work to reduce water scanty problem from 4th TW to Nischintapur at Mouza Nischintapur of Nischintapur PWSS under Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000279/2025-2026 | 4413/HD | 25/11/2025 | 45 | A. R. CONSTRUCTION | 22.93 | 0 | 0
547 | Howrah Division | Ulberia Sub-Division | Interconnection between 3rd TW with LDS for Augmentation of Nischintapur Piped Water Supply scheme in Amta-II Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000313/2024-2025 | 4858/HD | 22/11/2024 | 20 | DEV DAS SHAW | 15.37 | 0 | 100
548 | Howrah Division | Ulberia Sub-Division | Construction of Two storied switch room (3.6 x3.0)with water supply & sanitary arrangement at 3rd Tube well site of Nischintapur W/S scheme (SM/09720) of Amta-II Block under Uluberia Sub-Division under the Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000317/2024-2025 | 4859/HD | 22/11/2024 | 60 | DEV DAS SHAW | 7.79 | 0 | 100
549 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution system, & FHTC (3145 nos) for Augmentation of Nischintapur PWSS under Amta-II Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000387/2021-2022 | 184/HD | 31/01/2022 | 120 | VISHAL CONSTRUCTION CO. | 348.97 | 0 | 100
550 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Nischintapur PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000608/2022-2023 | 2724/HD | 14/12/2022 | 30 | DEV DAS SHAW | 13.64 | 0 | 100
551 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000006/2022-2023 | 1222/HD | 09/06/2022 | 0 | Resource Division | 6.21 | 0 | 0
552 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000019/2021-2022 | 204/HD | 01/02/2022 | 0 | Resource Division | 19.32 | 0 | 0
553 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Nischintapur PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | VCH/000827/2021-2022 | BP-2021-22-366 | 28/02/2022 | 0 | STEELCONC AND ASSOCIATES | 3.86 | 0 | 0
554 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
555 | Howrah Division | Ulberia Sub-Division | Connection with 5th Tube well site to distribution line with providing FHTC at Paschim Bainan PWSS under Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000022/2024-2025 | 248/AE/USD | 12/06/2024 | 30 | S R TRADING CORPORATION | 4.71 | 0 | 100
556 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 3 (Three) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Paschim Bainan W/S scheme at Bagnan-I Block in Uluberia SubDivision P.H.E. Dte. under Howrah Division, P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000030/2022-2023 | 1010/HD | 05/05/2022 | 30 | AUXILIARY TUBEWELL DRILLERS | 49.48 | 0 | 0
557 | Howrah Division | Ulberia Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-I Block) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000229/2025-2026 | 4127/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
558 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Paschim Bainan PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000264/2021-2022 | 2146/HD | 01/12/2021 | 15 | RADIANT | 3.89 | 0 | 0
559 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
560 | Howrah Division | Ulberia Sub-Division | Work Order for Soil Investigation for the work of Construction of R.C.C Elevated Reservoir of Capacity 1000m3 Staging Height 20 mtr. For Paschim Bainan W/S Scheme under Uluberia Sub-Division, under Howrah Division, P.H.E.Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000394/2021-2022 | 221/HD | 03/02/2022 | 20 | PROSENJIT DAS | 0.65 | 0 | 0
561 | Howrah Division | Ulberia Sub-Division | Construction of switch room (5.40m X 3.60m) with water supply & sanitary arrangement at Head Work site of Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E Dte. (As per approved drawing of Howrah Division, PHE Dte). | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000420/2022-2023 | 509/AE/USD | 27/09/2022 | 45 | S.P. CONSTRUCTION | 4.99 | 0 | 100
562 | Howrah Division | Ulberia Sub-Division | Construction of switch room (3.60m X 3.0m) with water supply & sanitary arrangement at 4th tube well site of Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E Dte. (As per approved drawing of Howrah Division, PHE Dte). | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000438/2022-2023 | 510/AE/USD | 27/09/2022 | 45 | K.N ENTERPRISE | 4.45 | 0 | 0
563 | Howrah Division | Ulberia Sub-Division | Construction of 1000 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection at Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000525/2023-2024 | 607/HD | 09/02/2024 | 720 | PIKASU BOSE | 239.3 | 0 | 24
564 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Paschim Bainan Water Supply scheme with LDS, Laying of Rising main & FHTC work at Bagnan-I Block of Howrah District under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000528/2021-2022 | 592/HD | 15/03/2022 | 306 | S.P. CONSTRUCTION | 1002.85 | 0 | 100
565 | Howrah Division | Ulberia Sub-Division | Development of 5th Tube well at Augmentation of Paschim Bainan PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000872/2022-2023 | 943/AE/USD | 22/03/2023 | 30 | LOKENATH ENTERPRISES | 0.71 | 0 | 100
566 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000011/2022-2023 | 1402/HD | 07/07/2022 | 0 | Resource Division | 87.96 | 0 | 0
567 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000034/2022-2023 | 1955/HD | 21/09/2022 | 0 | Resource Division | 0.05 | 0 | 0
568 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
569 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC), Interconnection for 2nd TW and 1st Tube well (HW site) & Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref: Dept. Super Struc. DRG. No. PC I/OHR/11/2012) Including All pipe Connection including foundation design for ULANPARA PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000017/2023-2024 | 1651/HD | 18/04/2023 | 365 | SUDHAMAY MAJUMDAR | 361.15 | 0 | 0
570 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Ulanpara PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000449/2021-2022 | 250/HD | 07/02/2022 | 15 | DULAL MAJUMDER | 2.69 | 0 | 100
571 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ulanpara PWSS of Bagnan I Block Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000598/2022-2023 | 2714/HD | 14/12/2022 | 45 | AUXILIARY TUBEWELL DRILLERS | 36.22 | 0 | 0
572 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000018/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 42.67 | 0 | 0
573 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000027/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 48.67 | 0 | 0
574 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 2 nos (5.40Mx 3.60M) Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 2nos T/well sites of Banharishpur PWSS at Panchla Block of Howrah District under Howrah Division, PHE Dte.. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000075/2023-2024 | 1773/HD | 27/04/2023 | 60 | ADRIJA ENTERPRISE | 13.25 | 0 | 50
575 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
576 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipe Lines With Functional Household Tap Connection(FHTC) for Augmentation of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, PHE Dte.(Part-B) From Node Point-8-22 to Node Point-54-61. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000508/2022-2023 | 2257/HD | 04/11/2022 | 815 | MITHU BUILDERS | 129.62 | 0 | 100
577 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR with Route Survey for new piped water supply scheme of Banharishpur PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000518/2022-2023 | 1929/HD | 19/09/2022 | 30 | STEELCONC AND ASSOCIATES | 2.91 | 0 | 0
578 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying of Distribution Pipeline with Functional Household Tap Connection (FHTC) of Banharishpur PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.(Part-C) From Node Point-22-31 to Node Point- 64-65. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000537/2022-2023 | 2419/HD | 23/11/2022 | 45 | MANAS CHATTERJEE | 129.55 | 0 | 80
579 | Howrah Division | Howrah Sadar Sub-Division | Additional laying distribution pipe line and allied works at Banharishpur PWSS under Shyamchak mouza at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000594/2023-2024 | 998/HD | 01/03/2024 | 75 | S RAHA ENTERPRISE | 74.68 | 0 | 60
580 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Jaynagar PWSS(2 nos) & Banharishpur PWSS(2 nos) of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000800/2022-2023 | 1000/HD | 13/03/2023 | 977 | PRANTIK DRILLING AGENCY | 68.83 | 0 | 25
581 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000080/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 33.65 | 0 | 0
582 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000080/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 27.73 | 0 | 0
583 | Howrah Division | Ulberia Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Water Supply Scheme under Amta-I block under Uluberia SubDivision under Howrah Division, PHE Dte. (Part-B) Mouza-BARUE | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000006/2022-2023 | 805/HD | 07/04/2022 | 45 | BISWAJIT BAG | 65.21 | 0 | 100
584 | Howrah Division | Ulberia Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) at Augumentation of Mato Water Supply Scheme under Amta-I block under Uluberia SubDivision under Howrah Division, PHE Dte. (Part-C) Mouza-GHORADAHA | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000007/2022-2023 | 806/HD | 07/04/2022 | 45 | JOY CHANDI CONSTRUCTION | 64.62 | 0 | 100
585 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Mato PWSS, Amta-I Block Under Uluberia SubDivision of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000268/2021-2022 | 2150/HD | 01/12/2021 | 15 | RADIANT | 3.07 | 0 | 0
586 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-1) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000441/2022-2023 | 524/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.99 | 0 | 0
587 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-2) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000442/2022-2023 | 525/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.99 | 0 | 0
588 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-3) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000443/2022-2023 | 526/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.8 | 0 | 0
589 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-4) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000444/2022-2023 | 527/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.98 | 0 | 0
590 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-5) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000446/2022-2023 | 528/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 5 | 0 | 0
591 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-B) (Phase-6) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000447/2022-2023 | 529/AE/USD | 27/09/2022 | 45 | BISWAJIT BAG | 4.98 | 0 | 0
592 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-1) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000448/2022-2023 | 530/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.99 | 0 | 0
593 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-2) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000449/2022-2023 | 531/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.94 | 0 | 0
594 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-3) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000450/2022-2023 | 532/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.92 | 0 | 0
595 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-4) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000451/2022-2023 | 533/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.97 | 0 | 0
596 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-5) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000452/2022-2023 | 534/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.97 | 0 | 0
597 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-6) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000453/2022-2023 | 535/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.98 | 0 | 0
598 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E Dte.(Part-C) (Phase-7) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000454/2022-2023 | 536/AE/USD | 27/09/2022 | 45 | JOY CHANDI CONSTRUCTION | 4.99 | 0 | 0
599 | Howrah Division | Ulberia Sub-Division | Sinking of 1 (one) Nos. replaced & 1 (one) Nos new (4th) Tube Well 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Mato PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000628/2023-2024 | 1214/HD | 11/03/2024 | 60 | LOKENATH ENTERPRISES | 30.28 | 0 | 100
600 | Howrah Division | Ulberia Sub-Division | Additional laying distribution pipeline with FHTC at Mato PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Location: Ghoradaha, Barui & Mato part) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000631/2024-2025 | 1226/HD | 05/03/2025 | 45 | MA DURGA ENTERPRISE | 26.57 | 0 | 0
601 | Howrah Division | Ulberia Sub-Division | Work Order for Dismantling, Demolition and Disposal of Rubbish, reinforcement, broken pipes & specials, Debris and filling the site upto existing ground level and clearing properly including complete in all respect of 136 cum capacity & 20.0 m staging height dilapidated RCC Over head Reservoir of Mato water supply scheme of Amta-I Blockunder Uluberia Sub-Division of Howrah Divsion PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000697/2022-2023 | 328/HD | 24/01/2023 | 60 | BISWAJIT BAG | 3.89 | 0 | 0
602 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
603 | Howrah Division | Ulberia Sub-Division | Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation & foundation design, Laying Distribution Pipeline & Providing FHTC (3243 nos) for Nawapara Water Supply Scheme In Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000176/2023-2024 | 2947/HD | 14/08/2023 | 1005 | ORIENT CONSTRUCTION | 675.07 | 0 | 60
604 | Howrah Division | Ulberia Sub-Division | Construction of switch room SLOPE ROOF (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Nawpara PWSS (H/W) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000228/2024-2025 | 4557/HD | 22/10/2024 | 120 | RAJ ENTERPRISE | 6.91 | 0 | 100
605 | Howrah Division | Ulberia Sub-Division | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement at Nawpara PWSS (2nd Tube well) of Amta-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000229/2024-2025 | 4558/HD | 22/10/2024 | 120 | RAJ ENTERPRISE | 5.8 | 0 | 100
606 | Howrah Division | Ulberia Sub-Division | Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nawapara PWSS (2nos) & Ajangachi PWSS (2nos) & Jhikira PWSS (2nos) of Amta-II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000238/2023-2024 | 3440/HD | 26/09/2023 | 60 | PRANTIK DRILLING AGENCY | 77.89 | 0 | 100
607 | Howrah Division | Ulberia Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Nawapara PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000444/2021-2022 | 245/HD | 07/02/2022 | 15 | VOYAGER | 3.2 | 0 | 0
608 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall & Land Development at 2nd TW Site Nawpara PWSS scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/11793) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000546/2024-2025 | 1072/HD | 27/02/2025 | 225 | M/S KANIKA ROY ENTERPRISE | 12.37 | 0 | 80
609 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall & Land Development at HW Site Nawpara PWSS scheme under Amta-II Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (SM/11793) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000783/2024-2025 | 1510/HD | 21/03/2025 | 60 | APEX ENGINEERING | 21.55 | 0 | 0
610 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000092/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 10.04 | 0 | 0
611 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000115/2023-2024 | 1286/HD | 13/03/2024 | 0 | Resource Division | 22.35 | 0 | 0
612 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site along with restoration work of damaged pipeline of SONATOLA Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000036/2025-2026 | 2276/HD | 07/05/2025 | 60 | GUPTA ENTERPRISE | 63.76 | 0 | 0
613 | Howrah Division | RWS Howrah Sub-Division | Rising Main & Inter Connection with both tube wells of SONATOLA Pipe Water Supply Scheme (SM/14949) at Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000038/2025-2026 | 2280/HD | 07/05/2025 | 45 | GUPTA ENTERPRISE | 18.62 | 0 | 0
614 | Howrah Division | RWS Howrah Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Udaynarayanpur Block) (PART-B) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000226/2025-2026 | 4124/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
615 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
616 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sonatala PWSS of Udaynarayanpur Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000746/2022-2023 | 664/HD | 17/02/2023 | 30 | LOKENATH ENTERPRISES | 26.22 | 0 | 100
617 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000006/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 2.77 | 0 | 0
618 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000040/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 14.77 | 0 | 0
619 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000051/2023-2024 | 3217/HD | 05/09/2023 | 0 | Resource Division | 29.9 | 0 | 0
620 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/amta2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000068/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 7.84 | 0 | 0
621 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Dakshin Panchla PWSS of Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000002/2023-2024 | 1528/HD | 04/04/2023 | 855 | ZEOLITE FRESH INDIA | 25.71 | 0 | 100
622 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 100 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Foundation Design & All pipe Connection, Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work ,Providing FHTC (Functional Household Tap Connection) for Dakshin Panchla PWSS at Panchla Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000031/2023-2024 | 1735/HD | 25/04/2023 | 335 | BISWAJIT BAG | 180.62 | 0 | 0
623 | Howrah Division | Howrah Sadar Sub-Division | Continuation order for Preparation of DPR for augmentation of existing piped water supply scheme of Dakshin Panchla PWSS, Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000979/2022-2023 | 1460/HD | 14/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.63 | 0 | 100
624 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000069/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 4.98 | 0 | 0
625 | Howrah Division |  | NDT for OHR of Augmentation Udaynaraynpur Zone-I & II Water Supply Scheme |  |  | BILL/00329/2024-2025 | BP-2024-25-216 | 26/07/2024 | 0 | JADAVPUR UNIVERSITY | 1.77 | 0 | 0
626 | Howrah Division |  | Permanent restoration work of probable damage stretches of Udaynarayanpur-Pancharul road, from ch. 0.00 km to 0.50 km & Amta-Rajapur-Dihibhurshut road from 15.50 km to 16.20 km, due to laying of water supply pipe line by P.H.E. i.c.w. rejuvenation of Udaynarayanpur water supply project under Howrah highway division, P.W.(Roads) Dte. in the district of Howrah. |  |  | BILL/00396/2024-2025 | BP-2024-25-241 | 06/08/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 6.65 | 0 | 0
627 | Howrah Division |  | Construction of Boundary Wall, Construction of Approach Road and Land Development and Additional Laying of Distribution Pipe Lines with providing FHTC for leftout area for UDAYNARAYANPUR ZONE-I of UDAYNARAYANPUR ZONE-I & II Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. (SM/18398) |  |  | ORD/000039/2024-2025 | 2861/HD | 24/06/2024 | 60 | M/S B.S.P. ENTERPRISES | 171.67 | 0 | 40
628 | Howrah Division |  | Additional Laying of Distribution Pipe Lines for leftout area of UDAYNARAYANPUR ZONE-II Piped Water Supply Scheme, Rising Main & Inter Connection with PH-1 & PH-5 of UDAYNARAYANPUR ZONE-I & II PWSS, Rising Main & Inter Connection with both PH-3 & PH-4 and Repairing of Pump House & Construction of W/C at H/W Site of UDAYNARAYANPUR ZONE-I & II PWSS at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. [SM/18398] |  |  | ORD/000115/2024-2025 | 3872/HD | 04/09/2024 | 450 | GHOSH CONCERN | 197.8 | 0 | 40
629 | Howrah Division |  | Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) and construction of 2 nos Pump House (H/W Site & 2nd T/W Site) for UDAYNARAYANPUR Agumentation Zone-I Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. |  |  | ORD/000129/2023-2024 | 2645/HD | 18/07/2023 | 978 | M/S B.S.P. ENTERPRISES | 378.71 | 0 | 75
630 | Howrah Division |  | Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) & construction of 750 cum capacity 20mtr staging height RCC Over head Reservoir (including pile foundation), pipe connection & cost of pipes & soil investigation with design for pile foundation & construction of 1no Pump house at HW site for Udaynarayanpur Augmentation Zone-II Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. |  |  | ORD/000138/2023-2024 | 2759/HD | 31/07/2023 | 899 | GHOSH CONCERN | 723.52 | 0 | 30
631 | Howrah Division |  | Preparation of DPR for Augmentation of Udaynarayanpur (Zone-I) PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000252/2022-2023 | 326/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.2 | 0 | 100
632 | Howrah Division |  | Preparation of DPR for Augmentation of Udaynarayanpur (Zone-II) PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000253/2022-2023 | 327/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.18 | 0 | 100
633 | Howrah Division |  | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Udaynarayanpur PWSS Zone -I (2 nos) and Zone-II (1 no) of Augmentation Udaynarayanpur Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000260/2023-2024 | 3618/HD | 09/10/2023 | 45 | MUNSHI ENTERPRISE | 52.12 | 0 | 90
634 | Howrah Division |  | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. |  |  | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
635 | Howrah Division |  | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(part-A) |  |  | ORD/000749/2023-2024 | 82/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.91 | 0 | 80
636 | Howrah Division |  | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(Part-B) |  |  | ORD/000750/2023-2024 | 83/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.91 | 0 | 80
637 | Howrah Division |  | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) |  |  | ORD/000751/2023-2024 | 84/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.91 | 0 | 80
638 | Howrah Division |  | Supplying,fitting,fixing and erecting of Display Board at different PWSS of Udaynarayanpur Block under Howrah R.W.S Sub-Division, under Howrah Division, P.H.E. Dte.(Part-D) |  |  | ORD/000752/2023-2024 | 85/RWS | 08/02/2024 | 15 | ABONTICA ENTERPRISE | 0.57 | 0 | 80
639 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 49.53 | 0 | 0
640 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 70.86 | 0 | 0
641 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1049/HD | 04/03/2024 | 0 | Resource Division | 132.58 | 0 | 0
642 | Howrah Division |  | Construction of Boundary Wall at Head work Site of Size-(50.00 m x 40.00 m), Reconnection of FHTC & distribution pipe line and Allied Works at Majhu Khetra PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000630/2023-2024 | 1215/HD | 11/03/2024 | 420 | ENVOTECH INFRA SOLUTION | 56.71 | 0 | 80
643 | Howrah Division |  | Reconnection of FHTC& Allied Works at Maju khetra PWSS at Jagatballavpur Block under Howrah sadar Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000718/2023-2024 | 160/HSSD | 12/02/2024 | 60 | KUNAL BANERJEE | 0.9 | 0 | 100
644 | Howrah Division |  | Sinking 1No. 250 X 150 mm Dia and 240 m deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Beldubi PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000589/2023-2024 | 997/HD | 01/03/2024 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.59 | 0 | 100
645 | Howrah Division |  | Reconnection of FHTC & distribution pipe line and allied works, Construction of 1 (One) no.pump house (5.40m x 3.60 m), Construction of 1 (One) no. Boundary wall at Beldubi piped water supply scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000620/2023-2024 | 1139/HD | 06/03/2024 | 361 | BISWAJIT BAG | 50.57 | 0 | 40
646 | Howrah Division |  | Work Order for Connection between 3rd TW with distribution pipeline to built up pressure for Bauria w/s scheme under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000049/2023-2024 | 1842/HD | 02/05/2023 | 60 | PRADIP KUMAR JATI | 48.41 | 0 | 100
647 | Howrah Division |  | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at at 3rd tube well site of Bauria PWSS of Uluberia-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) |  |  | ORD/000050/2023-2024 | 1841/HD | 02/05/2023 | 90 | CREATION | 6.95 | 0 | 100
648 | Howrah Division |  | Preparation of DPR for Source Strengthning at Bauria PWSS, Uluberia-I Block under Uluberia Sub-Division of Howrah Division PHE Dte |  |  | ORD/000641/2023-2024 | 495/AE/USD | 29/09/2023 | 30 | APEX ENGINEERING | 0.78 | 0 | 100
649 | Howrah Division |  | Work Order for construction of Guard wall cum boundary wall, Land Development, Barbed wire protection at HW site Site & allied works of Bauria W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000733/2022-2023 | 570/HD | 13/02/2023 | 45 | MJA ENTERPRISE | 37.38 | 0 | 60
650 | Howrah Division | Ulberia Sub-Division | Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete, 4no 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around head work site, Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site, land development of Head work site and other Tube well sites, Laying distribution system (HDPE & DI) & Providing Household Connection, Interconnection between Tube wells & 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design For Baniban Piped Water Supply Scheme (Zone-I) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/Ulu | JE-USD | ORD/000153/2023-2024 | 2963/HD | 16/08/2023 | 900 | SAMIRON GHOSH | 1019.91 | 0 | 0
651 | Howrah Division |  | Construction of Boundary Wall, Land Development at HEAD WORK Site, Additional Laying of Distribution Pipe Lines at UTTAR MANASRI Piped Water Supply Scheme and Additional Laying of Distribution Pipe Lines at KHALATPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P. H. E. Dte. |  |  | ORD/000012/2025-2026 | 1855/HD | 16/04/2025 | 300 | SAMIRON GHOSH | 96.34 | 0 | 40
652 | Howrah Division |  | Construction of 600 cum capacity RCC OHR with 20.0 mtr. staging height including soil investigation, Sinking of 2 nos. 300 mm X 200 mm dia X 230 m deep Tubewell, Construction of 2 nos Switch Room with sanitary arrangement, Laying Distribution System, providing Functional Household Tap Connection (FHTC) for UTTAR MANASRI Piped Water Supply Scheme under Udaynarayanpur block under Howrah Division, PHE Dte. [No. of FHTC=3307] |  |  | ORD/000261/2023-2024 | 3825/HD | 16/10/2023 | 900 | SAMIRON GHOSH | 825.77 | 0 | 25
653 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 9.98 | 0 | 0
654 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 4024/HD | 07/11/2023 | 0 | Resource Division | 116.49 | 0 | 0
655 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 1049/HD | 04/03/2024 | 0 | Resource Division | 36.78 | 0 | 0
656 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikihakola piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) Part- A |  |  | ORD/000435/2021-2022 | 349/HD | 17/02/2022 | 30 | UNIVERSAL CORPORATION | 4.3 | 0 | 0
657 | Howrah Division |  | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-A) No of House Hold= 100 nos. |  |  | ORD/000545/2021-2022 | 661/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.82 | 0 | 100
658 | Howrah Division |  | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-B)No of House Hold= 100 nos. |  |  | ORD/000546/2021-2022 | 662/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.67 | 0 | 100
659 | Howrah Division |  | Trial Run and Operation & maintenance of pipe lines (LDS & Risingmain) sluice valve & street stand post etc. including operation of sluice valves at Bikihakola w/s scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (90 days from issue of Work Order) |  |  | VCH/000603/2021-2022 | W/598 | 24/12/2021 | 0 | UNIVERSAL CORPORATION | 1.15 | 0 | 0
660 | Howrah Division |  | Interconnection of Pump1 and 2 with proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte. |  |  | VCH/000604/2021-2022 | W/597 | 28/12/2021 | 0 | UNIVERSAL CORPORATION | 23.22 | 0 | 0
661 | Howrah Division |  | FHTC of Bikihakola W/SScheme under Panchla Block under Howrah Sadar Sub-Division PHE Dte. (Phase-IV) |  |  | VCH/000850/2021-2022 | 844323 | 24/03/2022 | 0 | G.B. CONSTRUCTION AND CO | 62.79 | 0 | 0
662 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) |  |  | VCH/000851/2021-2022 | 844325 | 24/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0
663 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) |  |  | VCH/000855/2021-2022 | 844326 | 24/03/2022 | 0 | PRADIP KUMAR JATI | 89.17 | 0 | 0
664 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) |  |  | ORD/000493/2020-2021 | 400/HD | 10/02/2021 | 30 | PRADIP KUMAR JATI | 92.36 | 0 | 0
665 | Howrah Division |  | FHTC of Bikihakola W/SScheme under Panchla Block under Howrah Sadar Sub-Division PHE Dte. (Phase-IV) |  |  | VCH/000850/2021-2022 | 844323 | 24/03/2022 | 0 | G.B. CONSTRUCTION AND CO | 62.79 | 0 | 0
666 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) |  |  | VCH/000851/2021-2022 | 844325 | 24/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 55.24 | 0 | 0
667 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-III) |  |  | VCH/000855/2021-2022 | 844326 | 24/03/2022 | 0 | PRADIP KUMAR JATI | 89.17 | 0 | 0
668 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-J) |  |  | ORD/000130/2020-2021 | 1542/HD | 05/11/2020 | 30 | A P POWER & CONCRETE | 18.83 | 0 | 0
669 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-K) |  |  | ORD/000131/2020-2021 | 1543/HD | 05/11/2020 | 30 | GHOSH CONCERN | 18.88 | 0 | 0
670 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-L) |  |  | ORD/000132/2020-2021 | 1544/HD | 05/11/2020 | 30 | GHOSH CONCERN | 18.86 | 0 | 0
671 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Gobindapur piped water supply scheme under Jagatballavpur Blockunder Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Part-M) |  |  | ORD/000226/2020-2021 | 1406/HD | 16/10/2020 | 30 | MONIRUL ISLAM | 4.79 | 0 | 0
672 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) |  |  | ORD/000421/2021-2022 | 335/HD | 17/02/2022 | 30 | MS ARPAN ENTERPRISE | 2.97 | 0 | 0
673 | Howrah Division |  | Work Order for Laying of 90 mm dia 490 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-V) (Part-B) |  |  | ORD/000430/2021-2022 | 344/HD | 17/02/2022 | 30 | A.P. POWER & CONCRETE | 2.13 | 0 | 0
674 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-V)Part C |  |  | ORD/000431/2021-2022 | 345/HD | 17/02/2022 | 30 | M/S ASHIRBAD (INDIA) | 4.01 | 0 | 0
675 | Howrah Division |  | Work Order for Laying of 75 mm dia at node piont 41-27 and 20-15 node point for. 110mm dia,Total 1265 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-IV) |  |  | ORD/000516/2021-2022 | 504/HD | 08/03/2022 | 20 | A.P. POWER & CONCRETE | 4.92 | 0 | 0
676 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000208/2021-2022 | W/183 | 18/08/2021 | 0 | A.P. POWER & CONCRETE | 16.29 | 0 | 0
677 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000210/2021-2022 | W/218 | 18/08/2021 | 0 | ALOK ENTERPRISE | 11.75 | 0 | 0
678 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000211/2021-2022 | W/217 | 18/08/2021 | 0 | ALOK ENTERPRISE | 16.11 | 0 | 0
679 | Howrah Division |  | Laying of 90mm dia 490 mtr lenght additional UPVC pipe line for retrofitting work for FHTC of Gobindapur PWSS. |  |  | VCH/000784/2022-2023 | 84439 | 22/09/2022 | 0 | A P POWER & CONCRETE | 2.12 | 0 | 0
680 | Howrah Division |  | Consumption of Laying of 75 mm dia at node point 41-15 and 20-15 node point for 110 mm dia total 1265 mtr length additional UPVC pipe line for FHTC within the command area of Gobindapur PWSS (Phase-IV) |  |  | VCH/000790/2022-2023 | 84438 | 22/09/2022 | 0 | A P POWER & CONCRETE | 4.91 | 0 | 0
681 | Howrah Division |  | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. |  |  | VCH/000815/2022-2023 | 844310 | 22/09/2022 | 0 | MONIRUL ISLAM | 4.62 | 0 | 0
682 | Howrah Division |  | Relaying of pipe line of 110 mm dia 75 mm at node point for Retrofitting Gobindapur W/S Scheme under HSSD. |  |  | VCH/000821/2022-2023 | 844313 | 26/09/2022 | 0 | BUILT INDIA | 3.42 | 0 | 0
683 | Howrah Division |  | Retrofitting Gobindapur W/S Scheme. |  |  | VCH/000876/2021-2022 | 844334 | 30/03/2022 | 0 | ALOK ENTERPRISE | 15.52 | 0 | 0
684 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000881/2021-2022 | 844333 | 30/03/2022 | 0 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 13.74 | 0 | 0
685 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000106/2020-2021 | 1340/HD | 13/10/2020 | 30 | NATURAL RESOURCES CONSORTIUM | 28.42 | 0 | 0
686 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000107/2020-2021 | 1341/HD | 13/10/2020 | 30 | NATURAL RESOURCES CONSORTIUM | 28.2 | 0 | 0
687 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000419/2020-2021 | 93/HD | 14/01/2021 | 30 | PIKASU BOSE | 21.97 | 0 | 0
688 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000420/2020-2021 | 94/HD | 14/01/2021 | 30 | MAA LAXMI ENTERPRISE | 28.63 | 0 | 0
689 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kanpur Mouza (part) | AE/Ulu | JE/USD | ORD/000421/2020-2021 | 95/HD | 14/01/2021 | 30 | PIKASU BOSE | 28.49 | 0 | 0
690 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Kanpur Rejuvenation piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-G) | AE/Ulu | JE/USD | ORD/000422/2020-2021 | 96/HD | 14/01/2021 | 30 | PIKASU BOSE | 26.97 | 0 | 0
691 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000339/2021-2022 | W/255 | 03/09/2021 | 0 | PIKASU BOSE | 25.21 | 0 | 0
692 | Howrah Division | Ulberia Sub-Division | Retrofitting of Kanpur Reju Water Supply Scheme | AE/Ulu | JE/USD | VCH/000797/2020-2021 | 844321 | 12/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 24.79 | 0 | 0
693 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000874/2020-2021 | 844342 | 17/03/2021 | 0 | MAA LAXMI ENTERPRISE | 21.27 | 0 | 0
694 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kanpur Mouza of kanpur Rejuvenation piped water supply scheme | AE/Ulu | JE/USD | VCH/000879/2021-2022 | 844328 | 29/03/2022 | 0 | PIKASU BOSE | 3.17 | 0 | 0
695 | Howrah Division | Ulberia Sub-Division | Alternative relaying pipeline at Reju of Kanpur PWSS. | AE/Ulu | JE/USD | VCH/000900/2021-2022 | 844329 | 29/03/2022 | 0 | PIKASU BOSE | 2.87 | 0 | 0
696 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte.(Part-I) (for Kurit Mouza(Part) |  |  | ORD/000115/2020-2021 | 1510/HD | 04/11/2020 | 30 | DEV DAS SHOW | 29.1 | 0 | 0
697 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-J) (for Kurit Mouza(Part) |  |  | ORD/000116/2020-2021 | 1511/HD | 04/11/2020 | 30 | DEV DAS SHOW | 28.89 | 0 | 0
698 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-K) (for Darapur Mouza) |  |  | ORD/000117/2020-2021 | 1512/HD | 04/11/2020 | 30 | JAHANGIR ALAM | 16.23 | 0 | 0
699 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000344/2021-2022 | W/279 | 06/09/2021 | 0 | N. G ENGINEERING | 28.67 | 0 | 0
700 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000347/2021-2022 | W/276 | 06/09/2021 | 0 | JAHANGIR ALAM | 25.62 | 0 | 0
701 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kotalpara Mouza & Khosalpur Mouza(Part) |  |  | VCH/000606/2021-2022 | W/602 | 28/12/2021 | 0 | MONDAL PRECISION PVT. LTD. | 5.16 | 0 | 0
702 | Howrah Division |  | Mass Awarness generation and IEC activities. |  |  | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0
703 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-J) (for Kurit Mouza(Part) |  |  | VCH/000856/2021-2022 | 844311 | 14/03/2022 | 0 | DEV DAS SHAW | 29.01 | 0 | 0
704 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000954/2020-2021 | 8443108 | 30/03/2021 | 0 | PRADIP KUMAR JATI | 25.73 | 0 | 0
705 | Howrah Division | Ulberia Sub-Division | Supplying, fitting, fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000348/2024-2025 | 4832/HD | 20/11/2024 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
706 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) | AE/Ulu | JE/USD | VCH/000246/2021-2022 | W/347 | 07/10/2021 | 0 | USHA CONCERN | 3.52 | 0 | 0
707 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at SARDA W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | VCH/000812/2021-2022 | BP-2021-22-362 | 28/02/2022 | 0 | BISWAJIT BAG | 4.76 | 0 | 0
708 | Howrah Division | Ulberia Sub-Division | Additional Retrofitting Sarda | AE/Ulu | JE/USD | VCH/000974/2021-2022 | BP-2021-22-423 | 21/03/2022 | 0 | SUMANA ENTERPRISE | 2.17 | 0 | 0
709 | Howrah Division | RWS Howrah Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 1744 nos. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000004/2022-2023 | 790/HD | 06/04/2022 | 91 | GHOSH ENTERPRISE. | 95.49 | 0 | 0
710 | Howrah Division | RWS Howrah Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Joka Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 1744 nos. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000092/2022-2023 | 1244/HD | 14/06/2022 | 92 | GHOSH ENTERPRISE. | 95.49 | 0 | 0
711 | Howrah Division | Ulberia Sub-Division | Withdrawing and re-laying of UPVC pipeline damaged due to irrigation embarkment protection work at section 118-117-115-114-113-147-145-148 in Sehagori Water Supply Scheme(Part-B) under Amta-II block under Howrah Division , PHE Dte. (SL NO.-2 ) | AE/Ulu | JE/USD | ORD/000312/2022-2023 | 373/AE/USD | 30/08/2022 | 45 | PRADIP KUMAR JATI | 4.85 | 0 | 100
712 | Howrah Division | Ulberia Sub-Division | Work order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sehagari Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. for 2721 | AE/Ulu | JE/USD | ORD/000375/2021-2022 | 87/HD | 14/01/2022 | 45 | PRADIP KUMAR JATI | 114.31 | 0 | 0
713 | Howrah Division | Ulberia Sub-Division | Work order for Additional pipeline laying for left out portion (naba santra, ganesh santra, judhistir khanra, sourav khanra's house, Vai Vai milan sangha, kabir roy, avijit roy, Ashoke roy, kashinath middey) in Sehagori Water Supply Scheme (Part-A&B) under Amtra-II block under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000533/2021-2022 | 217/HD | 03/02/2022 | 45 | PRADIP KUMAR JATI | 4.84 | 0 | 0
714 | Howrah Division | Ulberia Sub-Division | Work Order for Additional pipeline laying for left out portion (Sibu house to burning ghat, Sk sifuddin to Sabir mollah, Sala Mudi shop to Moti mallick, Sk Faire to Sk Faiul, Das's Badh to Saidul mir, , indian petrol pump, dey builder, sikha dey, rajkumar mondal, porimal santra) in Sehagori Water Supply Scheme (Part-B) under Amtra-II block under Howrah Division, PHE Dte. (Phase-I) | AE/Ulu | JE/USD | ORD/000534/2021-2022 | 229/HD | 03/02/2022 | 45 | PRADIP KUMAR JATI | 4.82 | 0 | 0
715 | Howrah Division | Ulberia Sub-Division | Work order for Additional pipeline laying for left out portion (Tarun Sangha to Sanat roy, umbrella factory, sk para masjid to sk billu, sala modi shop, sova dolui, Bharat Petrolium, biswa mondal, haru dey, joydev dye, ibrahim mir, moonlight club) in Sehagori Water Supply Scheme (Part-B) under Amtra-II block under Howrah Division, PHE Dte. (Phase-II) | AE/Ulu | JE/USD | ORD/000535/2021-2022 | 230/HD | 03/02/2022 | 45 | PRADIP KUMAR JATI | 4.84 | 0 | 0
716 | Howrah Division | Ulberia Sub-Division | Work Order for Additional FHTC & pipeline work in-connection with providing Functional Household Tap Connection(FHTC) from existing distribution system at Sehagori W/S scheme under Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000770/2022-2023 | 737/HD | 23/02/2023 | 60 | JHARNA ENTERPRISE | 19.04 | 0 | 40
717 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu | JE/USD | RTOR000033/2021-2022 | 495/HD | 07/03/2022 | 0 | Resource Division | 3.08 | 0 | 0
718 | Howrah Division | Ulberia Sub-Division | Work order for Additional pipeline laying for left out portion (naba santra, ganesh santra, judhistir khanra, sourav khanra's house, Vai Vai milan sangha, kabir roy, avijit roy, Ashoke roy, kashinath middey) in Sehagori Water Supply Scheme (Part-A&B) under Amtra-II block under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | VCH/000841/2022-2023 | BP-2022-23-263 | 28/09/2022 | 0 | PRADIP KUMAR JATI | 4.06 | 0 | 0
719 | Howrah Division | RWS Howrah Sub-Division | Construction of boundary wall & Land Development at HW Site Garbhabanipur PWSS scheme under Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000504/2024-2025 | 1035/HD | 24/02/2025 | 120 | BINOY KOLEY | 14.11 | 0 | 100
720 | Howrah Division | RWS Howrah Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Garbhabanipur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2275 nos. | AE/RWS | JE/RWS/Udaynaryanpur | ORD/000567/2021-2022 | 733/HD | 31/03/2022 | 91 | MITHU BUILDERS | 96.62 | 0 | 0
721 | Howrah Division |  | Laying of 75mm & 140 mm dia.,Total 300 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Laskarpur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) |  |  | ORD/000091/2021-2022 | 1443/HD | 13/07/2021 | 30 | MONIRUL ISLAM | 1.67 | 0 | 0
722 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Laskarpur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) (PartA) |  |  | ORD/000147/2020-2021 | 1604/HD | 09/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 18.83 | 0 | 0
723 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Laskarpur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) (Part-B) |  |  | ORD/000148/2020-2021 | 1605/HD | 09/11/2020 | 30 | PRADIP KUMAR JATI | 18.84 | 0 | 0
724 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Laskarpur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) (PartC) |  |  | ORD/000149/2020-2021 | 1606/HD | 09/11/2020 | 30 | DEV DAS SHOW | 18.9 | 0 | 0
725 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000200/2021-2022 | W/172 | 14/08/2021 | 0 | DEV DAS SHAW | 16.14 | 0 | 0
726 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-B) |  |  | VCH/000436/2020-2021 | W/458 | 29/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0
727 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-C) |  |  | VCH/000437/2020-2021 | W/460 | 28/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.49 | 0 | 0
728 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-D) |  |  | VCH/000438/2020-2021 | W/459 | 28/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0
729 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-E) |  |  | VCH/000439/2020-2021 | W/461 | 06/01/2021 | 0 | M/S ASHIRBAD (INDIA) | 4.49 | 0 | 0
730 | Howrah Division |  | Continuation order for survey & collection of hopuse hold details through mobile app and geo-tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme juridiction in different pipe water supply scheme of Uluberia Sub-Division under Howrah Division, PHE Dte. |  |  | VCH/000511/2020-2021 |  | 15/12/2020 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0
731 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I) |  |  | VCH/000582/2020-2021 | W/466 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.49 | 0 | 0
732 | Howrah Division |  | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/000641/2020-2021 | W/508 | 18/01/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0
733 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000861/2020-2021 | 844353 | 22/03/2021 | 0 | M/S ASHIRBAD (INDIA) | 15.24 | 0 | 0
734 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000889/2020-2021 | 844381 | 26/03/2021 | 0 | STEELCONC AND ASSOCIATES | 15.18 | 0 | 0
735 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000890/2020-2021 | 844381 | 26/03/2021 | 0 | KRISH CONSTRUCTION | 19.99 | 0 | 0
736 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000898/2020-2021 | 844389 | 26/03/2021 | 0 | PRADIP KUMAR JATI | 15.2 | 0 | 0
737 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC)(Mouza-Chandrapur (58) & Interconnection for 2nd TW and 1st Tube well (HW site)& Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials (Drawing No.PC-I/OHR/07/2012 (Sheet No.1&2) with Soil test & Design for Chandrapur PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000043/2023-2024 | 1746/HD | 25/04/2023 | 1200 | K.M. ENTERPRISE | 300.94 | 0 | 0
738 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Chandrapur PWSS of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000603/2022-2023 | 2719/HD | 14/12/2022 | 45 | SPG ENTERPRISES | 27.49 | 0 | 50
739 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000021/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 29.1 | 0 | 0
740 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000028/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 31.28 | 0 | 0
741 | Howrah Division | RWS Howrah Sub-Division | Construction of Two storied switch room (5.4 x 3.6) & (3.6 x3.0) with water supply & sanitary arrangement cum godown & 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1707 nos) for Ghoraberia PWSS of Amta-II Block under Uluberia Sub-Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000114/2023-2024 | 2698/HD | 24/07/2023 | 1025 | SUJATA CONSTRUCTION | 435.07 | 0 | 52
742 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Ghoraberia PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000442/2021-2022 | 243/HD | 07/02/2022 | 15 | VOYAGER | 4.25 | 0 | 0
743 | Howrah Division | RWS Howrah Sub-Division | Display Board at different PWSS at Amta-I Amta-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000646/2023-2024 | 3221/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.26 | 0 | 100
744 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Ghoraberia PWSS of Amta - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | ORD/000744/2022-2023 | 662/HD | 17/02/2023 | 30 | LOKENATH ENTERPRISES | 28.39 | 0 | 100
745 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | RTOR000030/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 10.2 | 0 | 0
746 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Amta II,Junior Engineer3 | RTOR000091/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 3.7 | 0 | 0
747 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-I) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000233/2022-2023 | 86/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.04 | 0 | 100
748 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-IV) Dakshin Jhapardaha (Zone-II) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000234/2022-2023 | 87/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.7 | 0 | 100
749 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-II) PWSS (Mouza-Mollar Chak, Chak Narna, Parbatipur, Uttar Jhapardaha (CT) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000235/2022-2023 | 88/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.86 | 0 | 100
750 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
751 | Howrah Division | Howrah Sadar Sub-Division | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Dakshin Jhapardaha (Zone-4) PWSS (Zone-II) at 2nd & 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000627/2023-2024 | 1213/HD | 11/03/2024 | 45 | CHANDIMATA CONSTRUCTION | 15.45 | 0 | 100
752 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 6 (Six) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-IV) Dakshin Jhapordaha (Zone-I) & (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000664/2022-2023 | 175/HD | 13/01/2023 | 1017 | B K ENTERPRISE | 77.78 | 0 | 50
753 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 350 to 530) [PART-3]. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000669/2022-2023 | 161/HD | 13/01/2023 | 60 | BUILT INDIA | 77.96 | 0 | 50
754 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 557, 562 to 667) [PART-4]. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000670/2022-2023 | 162/HD | 13/01/2023 | 60 | CHAKRABORTY ENTERPRISE | 50.34 | 0 | 15
755 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline of DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. (Pipe Dia. 90mm Node No. 530 to 561) [PART-5]. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000682/2022-2023 | 270/HD | 19/01/2023 | 60 | PBA INFRASTRUCTURE | 15.34 | 0 | 35
756 | Howrah Division | Howrah Sadar Sub-Division | Work Order for LDS (Part-2) & FHTC (Part-2) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000765/2022-2023 | 722/HD | 23/02/2023 | 90 | FAITH ENTERPRISE | 135.21 | 0 | 50
757 | Howrah Division | Howrah Sadar Sub-Division | Work Order for CONSTRUCTION FOR 3 NOS. PUMP HOUSE, 3 NOS. BOUNDARY WALL, RISING MAIN, LDS (Part-1) & FHTC (Part-1) OF AUGMENTATION OF DOMJUR (ZONE-IV) DAKSHIN JHAPARDAHA (ZONE-II) In DOMJUR BLOCK OF HOWRAH DISTRICT UNDER HOWRAH DIVISION, P. H. E. DTE. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000775/2022-2023 | 812/HD | 28/02/2023 | 726 | M/S CHANDIMATA CONSTRUCTION | 151.7 | 0 | 40
758 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000015/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 87.43 | 0 | 0
759 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000078/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 22.21 | 0 | 0
760 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells (Part-A) & Construction of Swtich Room with Sanitary and water Supply arrangement at Head Work Site and Construction of 250 cum. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No:PC-I/OHR/10/2012) including Pipe connection & soil investigation and design at PATINAN PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000008/2023-2024 | 1553/HD | 05/04/2023 | 976 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 217.39 | 0 | 32
761 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
762 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Patinan PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000365/2022-2023 | 460/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 2.98 | 0 | 100
763 | Howrah Division | Ulberia Sub-Division | Display Board at different PWSS at Bagnan-I Bagnan-II Block under uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000644/2023-2024 | 3219/AE/USD | 12/03/2024 | 30 | ABONTICA ENTERPRISE | 4.76 | 0 | 100
764 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells at Patinan PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000724/2022-2023 | 513/HD | 09/02/2023 | 817 | MENOKA ENGINEERING WORKS | 58.94 | 0 | 75
765 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gopalpur PWSS 2nos & Patinan PWSS 2 Nos of Bagnan - I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000745/2022-2023 | 663/HD | 17/02/2023 | 45 | AQUATECH ENGINEER | 52.06 | 0 | 100
766 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000023/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 22.05 | 0 | 0
767 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000061/2023-2024 | 4695/HD | 26/12/2023 | 0 | Resource Division | 16.37 | 0 | 0
768 | Howrah Division | Ulberia Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
769 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Augmentation of Joargori PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | ORD/000242/2022-2023 | 319/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.83 | 0 | 100
770 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | RTOR000025/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 74.81 | 0 | 0
771 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE-USD,JE/USD,Junior Engineer5 | RTOR000037/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 6.16 | 0 | 0
772 | Howrah Division | Howrah Mechanical Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
773 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Additional Laying Distribution Pipeline & allied works of Pulgustia PWSS at J.Bpur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000065/2023-2024 | 1926/HD | 10/05/2023 | 60 | GHOSH CONCERN | 65.53 | 0 | 50
774 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution System, Rising main , FHTC (4559 nos), Construction of Pump House at OHR site (5.4mX3.6m ) with water supply & sanitary arrangement, 2 (Two) nos Construction of Pump House(3.6 mX3.0m) with water supply & sanitary arrangement, 2(Two) nos Boundary Wall (OHR & Other tubewell site), Construction of of 450 Cum OHR with 20 mtr Staging Height with pile foundation for Augumention of PULGUSTIA Water Supply Scheme of JAGABALLAVPUR Block under Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000183/2022-2023 | 1437/HD | 12/07/2022 | 549 | GHOSH CONCERN | 474.21 | 0 | 30
775 | Howrah Division | Howrah Sadar Sub-Division | Sinking 1No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with 150 mm. dia. PVC. Strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Pulgustia PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000587/2023-2024 | 995/HD | 01/03/2024 | 30 | ACME CONSTRUCTION | 14.58 | 0 | 100
776 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2(Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Polgustia PWSS of Jagatballavpur Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000657/2022-2023 | 168/HD | 13/01/2023 | 45 | B K ENTERPRISE | 34.7 | 0 | 0
777 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000014/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 34.87 | 0 | 0
778 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000055/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 28.08 | 0 | 0
779 | Howrah Division | Howrah Sadar Sub-Division | Indent of Material | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
780 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Palgustia PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000959/2021-2022 | BP-2021-22-406 | 14/03/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 0 | 0
781 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia SubDivision, under Howrah Division P.H.E. Dte. (MouzaAdra (Jl-44)) (Part-A) and Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pipe connection and cost of pipes, specials with Soil test & Design for Augmentation of Bangalpur Piped Water Supply scheme of Bagnan-I Block under Howrah Division P.H.E. Dte. in the District of Howrah | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000012/2023-2024 | 1592/HD | 12/04/2023 | 1097 | SUBHAS TRADING CO. | 368.95 | 0 | 46
782 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Bangalpur PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000446/2021-2022 | 247/HD | 07/02/2022 | 15 | DULAL MAJUMDER | 3.1 | 0 | 100
783 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bangalpur PWSS of Bagnan I Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000811/2022-2023 | 1091/HD | 16/03/2023 | 760 | ZEOLITE FRESH INDIA | 52.14 | 0 | 30
784 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Adra (Jl-44) (Part-A) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000812/2022-2023 | 1093/HD | 16/03/2023 | 30 | SAIKAT ENTERPRISE | 11.88 | 0 | 0
785 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Joka(Jl-42) (Part-B) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000813/2022-2023 | 1094/HD | 16/03/2023 | 30 | BHOLA NATH CONSTRUCTION | 11.78 | 0 | 0
786 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-C) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000815/2022-2023 | 1095/HD | 16/03/2023 | 30 | M/S BANERJEE ENGINEERING SYSTEM | 11.7 | 0 | 0
787 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-D) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000816/2022-2023 | 1096/HD | 16/03/2023 | 30 | AYUSH ENTERPRISE | 16.14 | 0 | 0
788 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Bangalpur(Jl-43) (Part-E) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000817/2022-2023 | 1097/HD | 16/03/2023 | 30 | JYOTY SOLAR POWER | 16.21 | 0 | 0
789 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Bangalpur Piped Water Supply scheme in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000818/2022-2023 | 1098/HD | 16/03/2023 | 977 | SUNIL ENTERPRISE | 10.66 | 0 | 0
790 | Howrah Division | Howrah Mechanical Sub-Division | Work Order for Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Bangalpur PWSS of Bagnan-I Block under Uluberia SubDivision, under Howrah Division P.H.E. Dte. (Mouza Bangalpur(Jl-43) (Part-B) | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000883/2022-2023 | 1449/HD | 30/03/2023 | 789 | DEV DAS SHAW | 192.05 | 0 | 19
791 | Howrah Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000022/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 45.94 | 0 | 0
792 | Howrah Division | Howrah Mechanical Sub-Division | Material Requisition To Resource Division | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000029/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 7.39 | 0 | 0
793 | Howrah Division | Ulberia Sub-Division | Permanent restoration work of portable damage stretches of Ranihati-Haridaspur Amta Road from 15.40 Km to 16.70 Km due to laying of Water Supply Pipe Line by PHE i.c.w Rejuvenation of Amta Water Supply Scheme (Zone-II) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | BILL/00033/2024-2025 | BP-2024-25-9 | 08/04/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 20.73 | 0 | 0
794 | Howrah Division | Ulberia Sub-Division | Additional FHTC at Rejuvenation of Amta PWSS (Zone-I) of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte.(SM/08966) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000121/2024-2025 | 3958/HD | 10/09/2024 | 180 | ADITYA HAZRA | 54.31 | 0 | 100
795 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of Big dia Rig Bored Tube well 4 nos (300 x 250 mm x 250 mtr)for Zone-I, II & III, Land development of Head work site and 2nd Tube well site , Construction of boundary wall at 2nd Tube well Site (Zone-I), HW Site (Zone-I & III), Laying Distribution System Zone-I, Zone-II and Zone-III , FHTC Zone-I(3227), Zone-II(4732), Zone-III(2022), Construction of Two storied switch room ( 5.4 x 3.6) with water supply & sanitary arrangement cum godown at Head Work site of Zone-I,& Zone-III,Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 2nd tube well Zone-I, Construction of 600 Cum OHR 20 mtr Staging Height (Zone-I) with pile foundation including soil test &design of piles, Constructionof 400 Cum OHR 20 mtr Staging Height (Zone-III) with pile foundation including soil test & design of piles, Interconnection 2nd Tube Well and First Tube Well ( Zone-I and Zone-III)of Rejuvenation of Amta Water Supply Scheme of Amta- I Block under Howrah Division, PHE Dte | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000196/2022-2023 | 1637/HD | 10/08/2022 | 549 | SAMIRON GHOSH | 1572.76 | 0 | 50
796 | Howrah Division | Ulberia Sub-Division | Work Order for 1 (One) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at 3rd TW site, Additional laying of pipeline and ancilary works for Zone-I, II, III and Construction of 2nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Augmentation of Rejuvenation of Amta PWSS Zone-II & III 3rd TW site FOR ADDITIONAL WORK AT REJUVENATION OF AMTA PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000868/2022-2023 | 1352/HD | 27/03/2023 | 120 | SAMIRON GHOSH | 399.6 | 0 | 100
797 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000040/2022-2023 | 2639/HD | 09/12/2022 | 0 | Resource Division | 68.93 | 0 | 0
798 | Howrah Division | Ulberia Sub-Division | Indent of Material | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
799 | Howrah Division |  | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep additional tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Chitnan PWSS of Amta-II Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000611/2022-2023 | 2750/HD | 16/12/2022 | 30 | LOKENATH ENTERPRISES | 15.12 | 0 | 100
800 | Howrah Division |  | Preparation of DPR for Source Strengthning at Chitnan PWSS, Amta-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000640/2023-2024 | 494/AE/USD | 29/09/2023 | 30 | APEX ENGINEERING | 0.78 | 0 | 100
801 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Construction of Approach Road and Land Development at 2nd TW Site and Estimate for Additional Laying of Distribution Pipe Lines for leftout area of PER RADHANAGAR (Part-B) Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000148/2024-2025 | 4118/HD | 23/09/2024 | 120 | GHOSH ENTERPRISE | 72.21 | 0 | 100
802 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for Augmentation of Par-Radhanagar PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000256/2022-2023 | 330/AE/USD | 16/08/2022 | 45 | STEELCONC AND ASSOCIATES | 3.29 | 0 | 0
803 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
804 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying HDPE pipeline & providing Functional Household Tap Connection (FHTC) of PER RADHANAGAR Piped Water Supply Scheme under Udaynaryanpur block under Howrah Division, PHE Dte. (Part-B) Mouza-Peruhareshpur | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000432/2022-2023 | 2108/HD | 13/10/2022 | 901 | GHOSH ENTERPRISE. | 149.58 | 0 | 65
805 | Howrah Division | RWS Howrah Sub-Division | Rising main & Inter Connection with both tube wells of Per Radhanagar PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000558/2023-2024 | 904/HD | 27/02/2024 | 89 | KUNAL BANERJEE | 6.28 | 0 | 100
806 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at PerRadhanagar PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000561/2022-2023 | 2491/HD | 30/11/2022 | 45 | WATER TECH | 36.22 | 0 | 100
807 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Per-radhanagar W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000622/2022-2023 | 2802/HD | 21/12/2022 | 60 | BINOY KOLEY | 7.83 | 0 | 98
808 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60m) with water supply & sanitary arrangement at HW site Per Radhanagar W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000625/2022-2023 | 2805/HD | 21/12/2022 | 60 | M/S M.K. MONDAL | 7.83 | 0 | 95
809 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000009/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 1.13 | 0 | 0
810 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000034/2023-2024 | 2716/HD | 25/07/2023 | 0 | Resource Division | 13.78 | 0 | 0
811 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000045/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 19.05 | 0 | 0
812 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000064/2023-2024 | 29/HD | 03/01/2024 | 0 | Resource Division | 0.87 | 0 | 0
813 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/BLK/AMTA2,JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000073/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 14.26 | 0 | 0
814 | Howrah Division |  | Construction of boundary wall at Kamardaha (Zone No. 37) of Bagnan-II block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000014/2025-2026 | 1880/HD | 17/04/2025 | 60 | S.S CONSTRUCTION | 26.72 | 0 | 0
815 | Howrah Division |  | Construction of Pump House cum Guard room (5.5m x 3.6m) with Water Supply & Sanitary arrangement for Kalinagar PWSS at Purba Kalinagar (Janapara New Park) at Uluberia-I Block Of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000018/2024-2025 | 2692/HD | 10/06/2024 | 90 | SUBRATA MONDAL | 7.65 | 0 | 0
816 | Howrah Division |  | Supply & Delivery of different types of DI Specials for Surface Based W/S Scheme of Shyampur-I & II, Part of Bagnan-I & II & Uluberia-I Block Under Howrah Division, PHE Dte. |  |  | ORD/000023/2024-2025 | 2689/HD | 07/06/2024 | 15 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 86.34 | 0 | 100
817 | Howrah Division |  | Construction of boundary wall, Bank Protection at Dalsalap (Zone No. 03) (J.L No. 45) & Interconnection between Tubewell & Distribution Pipeline of Belari PWSS at Choto Jaynagar of Shyampur I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000029/2024-2025 | 2841/HD | 21/06/2024 | 60 | K.N ENTERPRISE | 40.28 | 0 | 100
818 | Howrah Division |  | Construction of Approach Road (PHASE-1) at Nakol of surface based water supply scheme of Shyampur-I & II , Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000042/2024-2025 | 2891/HD | 26/06/2024 | 30 | KALIDAS ENTERPRISE | 4.61 | 0 | 100
819 | Howrah Division |  | Construction of Approach Road (PHASE-2) at Nakol of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000051/2024-2025 | 2903/HD | 26/06/2024 | 15 | KALIDAS ENTERPRISE | 5.72 | 0 | 100
820 | Howrah Division |  | Construction of boundary wall at Choto Joynagar tubewell site under Belari PWSS( Zone 13) of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000052/2024-2025 | 2902/HD | 26/06/2024 | 45 | KALIDAS ENTERPRISE | 9.71 | 0 | 100
821 | Howrah Division |  | Construction of Temporary Approach Road at Kamardaha (Zone- 37) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000063/2024-2025 | 3094/HD | 08/07/2024 | 150 | K.N ENTERPRISE | 5.1 | 0 | 100
822 | Howrah Division |  | Construction of Approach Road for Second H/W site of Baikhai PWSS under Uluberia-I block of Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000065/2024-2025 | 3095/HD | 08/07/2024 | 15 | K.N ENTERPRISE | 2.57 | 0 | 100
823 | Howrah Division |  | Boundary wall at Moubeshia tubewell site under Baikhali PWSS(Zone-7) of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000066/2024-2025 | 3097/HD | 08/07/2024 | 30 | K.N ENTERPRISE | 9.7 | 0 | 100
824 | Howrah Division |  | Construction of Chlorine Room (5.5 m x 4.5 m) at Kulgachia (Zone -5) at Uluberia¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000069/2025-2026 | 2575/HD | 02/06/2025 | 60 | S S CONSTRUCTION | 9.77 | 0 | 75
825 | Howrah Division |  | Approach Way at the premises of Camp Office Building of the Executive Engineer, Howrah Division of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000071/2024-2025 | 3096/HD | 08/07/2024 | 30 | K.N ENTERPRISE | 2.68 | 0 | 100
826 | Howrah Division |  | Construction of Rest Shed & Other Allied Works at Ghanashyampur (Zone 11) beside OHR site under Shyampur-II Block of Surface Based Water Supply Scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000080/2024-2025 | 3324/HD | 24/07/2024 | 30 | S R TRADING CORPORATION | 3.71 | 0 | 100
827 | Howrah Division |  | Construction of18 mtr boundary wall from the Bandh road (chainage 0 mtr to 18 mtr) upto the mid point of Right side of the Substation building at Kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000081/2024-2025 | 3364/HD | 30/07/2024 | 45 | RINKU SAU | 4.84 | 0 | 100
828 | Howrah Division |  | Construction of 18 mtr boundary wall (chainage 18 mtr to 36 mtr) from the midpoint & upto the end point of Right side of the Substation building at Kajiakhali of Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000082/2024-2025 | 3380/HD | 30/07/2024 | 45 | RINKU SAU | 4.84 | 0 | 100
829 | Howrah Division |  | Construction of boundary wall at Barunda H/W site (Zone 38) of Bagnan-II block of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000084/2025-2026 | 2663/HD | 05/06/2025 | 60 | K.N ENTERPRISE | 24.86 | 0 | 75
830 | Howrah Division |  | Construction of Chlorine Room (5.5 m x 4.5 m) at Hallyan (Zone -29) at Bagnan¿II Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000087/2025-2026 | 2801/HD | 17/06/2025 | 60 | SIDDHARTH ENTERPRISE | 7.73 | 0 | 0
831 | Howrah Division |  | Construction of Chlorine Room (5.5 m x 4.5 m) at Ramchandrapur (Zone-40) at Bagnan¿I Block Of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000088/2025-2026 | 2802/HD | 17/06/2025 | 180 | K.N ENTERPRISE | 7.73 | 0 | 80
832 | Howrah Division |  | Interconnection between Tubewell & Distribution Pipeline of Kalinagar PWSS at Alipukur & Fencing at the front side of entry of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000101/2024-2025 | 3542/HD | 09/08/2024 | 7 | SIDDHARTH ENTERPRISE | 0.83 | 0 | 100
833 | Howrah Division |  | Construction of drain beside Dhoramanna khal (Zone No. 35) of Bagnan-II block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000102/2024-2025 | 3543/HD | 09/08/2024 | 7 | SIDDHARTH ENTERPRISE | 0.97 | 0 | 100
834 | Howrah Division |  | Construction of Approach Road for alternate entrance of Camp office under Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000103/2024-2025 | 3544/HD | 09/08/2024 | 7 | SIDDHARTH ENTERPRISE | 0.97 | 0 | 100
835 | Howrah Division |  | Construction of Kiosk (one no)(Size inside 3.0 x 1.8m) for Kalinagar PWSS at Janapara & temporary approach way of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. (Size inside 3.0 x 1.8m) |  |  | ORD/000118/2024-2025 | 3786/HD | 02/09/2024 | 15 | ZUNAID ENTERPRISE | 2.03 | 0 | 100
836 | Howrah Division |  | Construction of Approach Road for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000139/2024-2025 | 4113/HD | 23/09/2024 | 7 | ZUNAID ENTERPRISE | 0.92 | 0 | 100
837 | Howrah Division |  | Construction of Temporary Approach Road at Ghatampur (Zone- 4) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000140/2024-2025 | 4114/HD | 23/09/2024 | 7 | RINKU SAU | 0.94 | 0 | 100
838 | Howrah Division |  | Construction of Slab Culvert for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000141/2024-2025 | 4115/HD | 23/09/2024 | 7 | ZUNAID ENTERPRISE | 0.97 | 0 | 100
839 | Howrah Division |  | Construction of Kiosk (one no) for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte |  |  | ORD/000142/2024-2025 | 4116/HD | 23/09/2024 | 7 | ZUNAID ENTERPRISE | 0.89 | 0 | 100
840 | Howrah Division |  | Construction of counterfort retaining wall at backend & left side of Substation building at Kajiakhali under Uluberia-I block of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000173/2024-2025 | 4364/HD | 30/09/2024 | 300 | S R TRADING CORPORATION | 32.44 | 0 | 5
841 | Howrah Division |  | Construction of boundary wall at Nakol H/W site of Shyampur-II block under Surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000188/2024-2025 | 4462/HD | 03/10/2024 | 120 | KALIDAS ENTERPRISE | 21.69 | 0 | 80
842 | Howrah Division |  | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Shyampur-I & II Block) |  |  | ORD/000221/2025-2026 | 4119/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0
843 | Howrah Division |  | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Uluberia-I Block) (PART-B) |  |  | ORD/000224/2025-2026 | 4122/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
844 | Howrah Division |  | Hiring of 1 (One) no. Inspection vehicle no-1 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal (for the period from 13.10.2024 to 12.10.2025). |  |  | ORD/000258/2024-2025 | 4444/HD | 03/10/2024 | 365 | M/S ANIMESH ENTERPRISE | 4.78 | 0 | 15
845 | Howrah Division |  | Hiring of 1(One) no. Inspection vehicle no-2 (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Surface Based Water Supply Scheme for "Shyampur", PHE Dte. Government of West Bengal(for the period from 13.10.2024 to 12.10.2025). |  |  | ORD/000259/2024-2025 | 4445/HD | 03/10/2024 | 365 | MR SAP ENTERPRISE | 4.78 | 0 | 0
846 | Howrah Division |  | Construction of boundary wall, land development & other alied work for Kalinagar PWSS at Alipukur of surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000331/2024-2025 | 4876/HD | 25/11/2024 | 135 | S.S CONSTRUCTION | 7.55 | 0 | 100
847 | Howrah Division |  | Additional Work of Laying Distribution system (LDS) & Road Restoration Work at Uluberia-1 & Shyampur-1 Block of Surface Based W/S scheme for Shyampur-I & II, Uluberia I and Part of Bagnan I & II Block under Howrah Division, PHE Dte. (SM/06386 & SM/19186) |  |  | ORD/000454/2024-2025 | 994/HD | 20/02/2025 | 304 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 1950.12 | 0 | 50
848 | Howrah Division |  | Extension of boundary wall and land development at Mugkalyan H/W site (OHR 32 & 32A) under Bagnan-II block of Surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000459/2024-2025 | 991/HD | 20/02/2025 | 300 | S R TRADING CORPORATION | 42.84 | 0 | 70
849 | Howrah Division |  | Construction of boundary wall at Manikpur H/W site (OHR 5A H/S) of Uluberia-I block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000537/2023-2024 | 739/HD | 16/02/2024 | 60 | S R TRADING CORPORATION | 23.75 | 0 | 100
850 | Howrah Division |  | Construction of boundary wall, land development and other allied works at Amritashal (Zone No. 09) (J.L No. 38) of Uluberia I block of surface-based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000551/2024-2025 | 1073/HD | 27/02/2025 | 120 | SK. MOMTAJUR RAHAMAN | 26.59 | 0 | 78
851 | Howrah Division |  | Construction of drain using 1000 mm dia hume pipe and other allied works at Ichapur (Zone-12) of surface based water supply scheme of Shyampur-I & II, Part of Bagnan-I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000632/2023-2024 | 1176/HD | 07/03/2024 | 15 | SKYLINE ENTERPRISE | 0.96 | 0 | 0
852 | Howrah Division |  | Bullah piling for bank protection of canal to the right side of Ghat at Ichapur (Zone 12) for Surface Based W/S Scheme of Shyampur-I & II, Bagnan-I & II & Uluberia -I Block under of Howrah Division, PHE Dte. |  |  | ORD/000633/2023-2024 | 1177/HD | 07/03/2024 | 15 | SKYLINE CONSTRUCTION | 0.96 | 0 | 100
853 | Howrah Division |  | Bullah piling for bank protection of canal to the left side of Ghat at Ichapur (Zone 12) for Surface Based W/S Scheme of Shyampur-I & II, Bagnan-I & II & Uluberia-I Block under of Howrah Division, PHE Dte. |  |  | ORD/000634/2023-2024 | 1178/HD | 07/03/2024 | 15 | SKYLINE CONSTRUCTION | 0.96 | 0 | 100
854 | Howrah Division |  | Construction of boundary wall and land development at Khalore H/W site (OHR 40A) under Bagnan-I block of Surface based water supply scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block under Howrah Division, PHE Dte. |  |  | ORD/000643/2024-2025 | 1248/HD | 06/03/2025 | 60 | K.N ENTERPRISE | 16.57 | 0 | 75
855 | Howrah Division |  | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Shyampur-I & II Block of Uluberia Sub-Division under Howrah Division PHE Dte. |  |  | ORD/000650/2023-2024 | 1209/HD | 11/03/2024 | 15 | KULTIKARI MOTHER TERESA SOCIAL WELLFARE SOCIETY | 2.45 | 0 | 100
856 | Howrah Division |  | Proposed Surface Based Water Supply Scheme for Part of Malancha Beria, Rauta, Harinarayanpur and Kaijuri of Uluberia I Block under "Surface Based Water Supply Scheme of Shyampur I & II, Part of Bagnan I & II and Uluberia-I Block" [No. of FHTC=1723] (SM/19186) |  |  | ORD/000779/2024-2025 | 1488/HD | 20/03/2025 | 300 | APRJ CONSTRUCTIONS | 707.58 | 0 | 0
857 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 4561/HD | 23/10/2024 | 0 | Resource Division | 1803.32 | 0 | 0
858 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 4673/HD | 06/11/2024 | 0 | Resource Division | 39.57 | 0 | 0
859 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000039/2024-2025 | 5140/HD | 11/12/2024 | 0 | Resource Division | 4159.12 | 0 | 0
860 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Nakubar Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000378/2021-2022 | 2368/HD | 23/12/2021 | 30 | M/S ASHIRBAD (INDIA) | 4.57 | 0 | 0
861 | Howrah Division | Ulberia Sub-Division | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. At different places of Boalia mouza | AE/Ulu | JE/USD | ORD/000866/2022-2023 | 939/AE/USD | 22/03/2023 | 30 | M/S ASHIRBAD (INDIA) | 0.97 | 0 | 100
862 | Howrah Division | Ulberia Sub-Division | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. Near Manuchack Zilla parisad pole | AE/Ulu | JE/USD | ORD/000877/2022-2023 | 949/AE/USD | 22/03/2023 | 30 | M/S ASHIRBAD (INDIA) | 0.97 | 0 | 100
863 | Howrah Division | Ulberia Sub-Division | Alternative laying of distribution pipe line damaged due to improvement of road work by WBSRDA Howrah under PMGSY programme for restoration of FHTC's at Nakubar W/S scheme under Amta-II Block under Howrah Division, PHE Dte. near Kalimata Club and various places. | AE/Ulu | JE/USD | ORD/000878/2022-2023 | 950/AE/USD | 22/03/2023 | 30 | M/S ASHIRBAD (INDIA) | 0.96 | 0 | 100
864 | Howrah Division | Ulberia Sub-Division | Retrofitting Nakubar | AE/Ulu | JE/USD | VCH/000051/2021-2022 | W/155 | 06/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 20.86 | 0 | 0
865 | Howrah Division | Ulberia Sub-Division | Retrofitting for Nakubar W/S Scheme. | AE/Ulu | JE/USD | VCH/000136/2021-2022 |  | 24/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 38.07 | 0 | 0
866 | Howrah Division | Ulberia Sub-Division | Retrofitting for Nakubar W/S Scheme. | AE/Ulu | JE/USD | VCH/000137/2021-2022 | W/263 | 03/09/2021 | 0 | N. G ENGINEERING | 35.84 | 0 | 0
867 | Howrah Division | Ulberia Sub-Division | Retrofitting of Nakubar. | AE/Ulu | JE/USD | VCH/000771/2020-2021 | W/93 | 19/07/2021 | 0 | SWASTIK ENTERPRISE | 14.6 | 0 | 0
868 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Ground Water Based Piped Water Supply Scheme For Nakubar under Amta-II Block under Howrah Division, PHE Dte. (PART-D) [Ranjoybar MOUZA PART & Nakubar MOUZA PART] | AE/Ulu | JE/USD | VCH/000922/2021-2022 | W/797 | 03/03/2022 | 0 | N. G ENGINEERING | 34.83 | 0 | 0
869 | Howrah Division | Howrah Sadar Sub-Division | Payment for WBSEDCL of Bhurshit Bamunpara Water Supply Scheme Pump House No-IV | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00368/2023-2024 | BP-2023-24-171 | 24/07/2023 | 0 | WBSEDCL | 5 | 0 | 0
870 | Howrah Division | Howrah Sadar Sub-Division | Additional Quotation money deposition for Bhurshit Bamunpara PWSS Pump House No- III | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00481/2023-2024 | BP-2023-24-237 | 23/08/2023 | 0 | WBSEDCL | 21.59 | 0 | 0
871 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Bhursit Bamunpara PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000283/2021-2022 | 2156/HD | 01/12/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 0 | 0
872 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 390 | HORIZEN | 10.11 | 0 | 44
873 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Bhurshit Bamunpara W/S Scheme In Jagatballavpur Block Of Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000393/2022-2023 | 1884/HD | 14/09/2022 | 180 | SUDHAMAY MAJUMDAR | 123.64 | 0 | 90
874 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte (Part-A) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000523/2021-2022 | 586/HD | 15/03/2022 | 45 | B.B.C ENTERPRISE | 65.18 | 0 | 40
875 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (Part-B) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000524/2021-2022 | 587/HD | 15/03/2022 | 45 | DEV DAS SHAW | 75.85 | 0 | 60
876 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah sadar Sub-division under Howrah Division, PHE Dte. (start node- 188 to 274) (Part-C) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000525/2021-2022 | 588/HD | 15/03/2022 | 1023 | N. G ENGINEERING | 93.7 | 0 | 100
877 | Howrah Division | Howrah Sadar Sub-Division | Work Oder for laying distribution system With FHTC Work of Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, PHE Dte. (start node- 276 to 373) (Part-D) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000526/2021-2022 | 589/HD | 15/03/2022 | 1113 | M/S. CHANDIMATA CONSTRUCTION | 71.69 | 0 | 100
878 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhursit Bamunpara PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000597/2022-2023 | 2713/HD | 14/12/2022 | 45 | BALAJI UDDYOG | 27.45 | 0 | 100
879 | Howrah Division | Howrah Sadar Sub-Division | Additional Laying of Distribution system at Dhasa mouza under Pipe water supply from Augmentation of Bhursit Bamanpara water supply scheme under Howrah Sadar Sub-division under Howrah Division, Phe Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000662/2023-2024 | 1300/HD | 13/03/2024 | 45 | M/S ASHIRBAD (INDIA) | 13.41 | 0 | 100
880 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 2 NOS 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 3RD & 4TH Tube well SiteS of Bhusit Bamun para PWSS at J.B.PUR Block of Howrah District under Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000825/2022-2023 | 1054/HD | 15/03/2023 | 90 | BASU CONSTRUCTION | 13.5 | 0 | 100
881 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000017/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 73.96 | 0 | 0
882 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000049/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 23.41 | 0 | 0
883 | Howrah Division | Howrah Sadar Sub-Division | Indent of Material | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
884 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Bargazipur Mouza) | AE/Ulu | JE/USD | ORD/000090/2020-2021 | 1302/HD | 12/10/2020 | 30 | ARINDAM ENTERPRISE | 9.05 | 0 | 0
885 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (for Paschim Gazipur mouza part) | AE/Ulu | JE/USD | ORD/000091/2020-2021 | 1303/HD | 12/10/2020 | 30 | CONSTRUCTION CORNER | 27.51 | 0 | 0
886 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) (for Paschim Gazipur mouza part) | AE/Ulu | JE/USD | ORD/000092/2020-2021 | 1304/HD | 12/10/2020 | 30 | NIRMAL UDYOG | 27.33 | 0 | 0
887 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Paschim Gazipur piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Paschim Gazipur mouza part) | AE/Ulu | JE/USD | ORD/000093/2020-2021 | 1305/HD | 12/10/2020 | 30 | MENOKA ENGINEERING WORKS | 27.03 | 0 | 0
888 | Howrah Division | Ulberia Sub-Division | Retrofitting Paschim Gazipur Water Supply Scheme | AE/Ulu | JE/USD | VCH/000638/2020-2021 | W/518 | 15/01/2021 | 0 | ARINDAM ENTERPRISE | 8.92 | 0 | 0
889 | Howrah Division | Ulberia Sub-Division | Retrofitting of Paschim Gazipur Water Supply Scheme | AE/Ulu | JE/USD | VCH/000795/2020-2021 | 844319 | 11/03/2021 | 0 | MENOKA ENGINEERING WORKS | 22.15 | 0 | 0
890 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water SUPPLY SCHEME. | AE/Ulu | JE/USD | VCH/000853/2020-2021 | 844344 | 20/03/2021 | 0 | NIRMAL UDYOG | 25.48 | 0 | 0
891 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Bargazipur & Paschim Gazipur Mouza of Paschim Gazipur piped water sup | AE/Ulu | JE/USD | VCH/001010/2020-2021 | 844384 | 26/03/2021 | 0 | CONSTRUCTION CORNER | 22.55 | 0 | 0
892 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte. (Part-A) (for Uttar Pirpur (CT)(Part) | AE/Ulu | JE-USD | ORD/000094/2020-2021 | 1306/HD | 12/10/2020 | 30 | JAHANGIR ALAM | 26.59 | 0 | 0
893 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte. (Part-B) (for Uttar Pirpur (CT)(Part) | AE/Ulu | JE-USD | ORD/000095/2020-2021 | 1307/HD | 12/10/2020 | 30 | MANAS CHATTERJEE | 27.1 | 0 | 0
894 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte. (Part-C) (for Uttar Pirpur (CT)(Part) | AE/Ulu | JE-USD | ORD/000096/2020-2021 | 1308/HD | 12/10/2020 | 30 | TANMOY ROY CHOUDHURY | 24.01 | 0 | 0
895 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Uttar Pirpur piped water supply scheme under Uluberia-II Block under Howrah Division, PHE Dte.(Part-D) (for Uttar Pirpur (CT)(Part) | AE/Ulu | JE-USD | ORD/000097/2020-2021 | 1309/HD | 12/10/2020 | 30 | S.S ENTERPRISE | 9.71 | 0 | 0
896 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | AE/Ulu | JE-USD | ORD/000852/2020-2021 | 387/21/2022 | 15/08/2020 | 0 | MANAS CHATTERJEE | 2.8 | 2.8 | 0
897 | Howrah Division | Ulberia Sub-Division | Retrofitting work of providing Functional house hold tap connection(FHTC) under Uttar Pirpur PWSS | AE/Ulu | JE-USD | VCH/000732/2020-2021 | 84437 | 09/02/2021 | 0 | TANMOY ROY CHOUDHURY | 18.74 | 0 | 0
898 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | AE/Ulu | JE-USD | VCH/000757/2020-2021 | 844335 | 25/02/2021 | 0 | JAHANGIR ALAM | 26.02 | 0 | 0
899 | Howrah Division | Ulberia Sub-Division | Retrofitting of Uttar Pirpur Water Supply Scheme. | AE/Ulu | JE-USD | VCH/000785/2020-2021 | 844315 | 09/03/2021 | 0 | S.S ENTERPRISE | 9.53 | 0 | 0
900 | Howrah Division | Ulberia Sub-Division | Const of 300 m3 RCC Over head Reservoir of Uttar Pirpur W/S Scheme. | AE/Ulu | JE-USD | VCH/000877/2021-2022 | 844335 | 30/03/2022 | 0 | JAHANGIR ALAM | 12.27 | 0 | 0
901 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar Pirpur (CT) of Uttar Pirpur piped water supply scheme | AE/Ulu | JE-USD | VCH/000951/2020-2021 | 8443105 | 30/03/2021 | 0 | MANAS CHATTERJEE | 16.39 | 0 | 0
902 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) (for Sarda Mouza(part) |  |  | ORD/000098/2020-2021 | 1310/HD | 12/10/2020 | 30 | JAHANGIR ALAM | 28.16 | 0 | 0
903 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) |  |  | ORD/000099/2020-2021 | 1311/HD | 12/10/2020 | 30 | BISWAJIT BAG | 28.88 | 0 | 0
904 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) |  |  | ORD/000100/2020-2021 | 1312/HD | 12/10/2020 | 30 | M/S SARADA UDYOG | 28.69 | 0 | 0
905 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (for Sarda Mouza(part) |  |  | ORD/000101/2020-2021 | 1313/HD | 12/10/2020 | 30 | USHA CONCERN | 28.61 | 0 | 0
906 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Sarda piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (for Sarda Mouza(part) |  |  | ORD/000102/2020-2021 | 1314/HD | 12/10/2020 | 30 | S. NAG CHOWDHURY | 28.6 | 0 | 0
907 | Howrah Division |  | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) |  |  | ORD/000308/2021-2022 | 2240/HD | 09/12/2021 | 30 | SUMANA ENTERPRISE | 2.17 | 0 | 0
908 | Howrah Division |  | Mass Awarness generation and IEC activities. |  |  | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0
909 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Sarda Mouza of Sarda piped water supply scheme |  |  | VCH/000729/2020-2021 | 84434 | 09/02/2021 | 0 | BISWAJIT BAG | 28.46 | 0 | 0
910 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme |  |  | VCH/000759/2020-2021 | 84438 | 09/02/2021 | 0 | USHA CONCERN | 26.17 | 0 | 0
911 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme |  |  | VCH/000760/2020-2021 | 84439 | 09/02/2021 | 0 | S. NAG CHOWDHURY | 28.56 | 0 | 0
912 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Kusberia Mouza of Sarda piped water supply scheme |  |  | VCH/000781/2020-2021 | 84439 | 03/03/2021 | 0 | MAA TARA CONSTRUCTION | 6.38 | 0 | 0
913 | Howrah Division | Ulberia Sub-Division | Inter Connection work for 3rd & 4th TW with delivery pipeline at village Selnepara & Kalasdihi within the command area of Jhamtia PWSS under Amta-II Block under Uluberia Sub-Division Under Howrah Division. PHE Dte. | AE/Ulu | JE/USD | ORD/000125/2024-2025 | 4014/HD | 13/09/2024 | 120 | LOKENATH ENTERPRISES | 14.73 | 0 | 100
914 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Phase-1) | AE/Ulu | JE/USD | ORD/000144/2022-2023 | 165/AE/USD | 28/06/2022 | 45 | MA MANASA CONSTRUCTION | 4.84 | 0 | 0
915 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Phase-2) | AE/Ulu | JE/USD | ORD/000145/2022-2023 | 166/AE/USD | 28/06/2022 | 45 | MA MANASA CONSTRUCTION | 4.78 | 0 | 0
916 | Howrah Division | Ulberia Sub-Division | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-1). | AE/Ulu | JE/USD | ORD/000349/2022-2023 | 433/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.85 | 0 | 0
917 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-4). | AE/Ulu | JE/USD | ORD/000352/2022-2023 | 436/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.8 | 0 | 0
918 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline for providing Functional Household Tap Connection (FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, P.H.E Dte.(Phase-5). | AE/Ulu | JE/USD | ORD/000353/2022-2023 | 437/AE/USD | 13/09/2022 | 45 | MA MANASA CONSTRUCTION | 4.79 | 0 | 0
919 | Howrah Division | Ulberia Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Jhamtia Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. 2184 nos | AE/Ulu | JE/USD | ORD/000376/2021-2022 | 93/HD | 17/01/2022 | 45 | MA MANASA CONSTRUCTION | 84.61 | 0 | 0
920 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall at HW site of Jhamtia W/S scheme in Uluberia Sub-division, under Howrah Division P.H.E Dte. ( Phase-1 ) | AE/Ulu | JE/USD | ORD/000385/2022-2023 | 472/AE/USD | 16/09/2022 | 45 | TIYASA ENTERPRISE | 4.82 | 0 | 50
921 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu | JE/USD | RTOR000017/2021-2022 | 114/HD | 20/01/2022 | 0 | Resource Division | 15.98 | 0 | 0
922 | Howrah Division | Ulberia Sub-Division | Additional Tube well of 250 X 150 mm Dia and 230 m deep by Direct Rotary method with UPVC Pipes all complete at vill-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000068/2025-2026 | 2557/HD | 30/05/2025 | 30 | PRANTIK DRILLING AGENCY | 14.71 | 0 | 0
923 | Howrah Division | Ulberia Sub-Division | Additional laying distribution pipeline and Road restoration at Village-Moyrachack of Amta-II Block under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000076/2025-2026 | 2762/HD | 12/06/2025 | 60 | RANA ENTERPRISE | 56.75 | 0 | 0
924 | Howrah Division | Ulberia Sub-Division | Construction of 1 no switch room (3.6m x 3.00 m ) with water supply & sanitary arrangement at TW sites of Moyrachack village under Uttar & Dakhin Bhatora PWSS under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000077/2025-2026 | 2763/HD | 12/06/2025 | 60 | RANA ENTERPRISE | 6.86 | 0 | 0
925 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline and internal pathway at Uttar & Dakhin Bhatora (Zone-II) Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000354/2021-2022 | 2440/HD | 29/12/2021 | 30 | P B ENTERPRISE | 4.84 | 0 | 0
926 | Howrah Division | Ulberia Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Uttar & Dakshin Bhatora Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Zone-II) 2203 nos | AE/Ulu | JE/USD | ORD/000377/2021-2022 | 96/HD | 17/01/2022 | 45 | DEV DAS SHAW | 82.22 | 0 | 0
927 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall at 2nd TW site of Uttar & Dakhin Bhatora Zone-II w/s scheme in Uluberia Sub-Division under Howrah Division, P.H.E Dte. | AE/Ulu | JE/USD | ORD/000436/2022-2023 | 522/AE/USD | 27/09/2022 | 45 | P B ENTERPRISE | 4.84 | 0 | 0
928 | Howrah Division | Howrah Sadar Sub-Division | Road Restoration work due to road cutting by PHE for laying water pipeline at Howrah Amta Road from 32.50 Km to 35.70 Km (Both side) Under Howrah Division, P.W.D. during the year 2024-25. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00828/2024-2025 | BP-2024-25-493 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 13.23 | 0 | 0
929 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline At Sekrahati Mouza Node No. 220 to 366 (Part-2) of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000005/2022-2023 | 803/HD | 07/04/2022 | 45 | SWASTIK ENTERPRISE | 56.88 | 0 | 100
930 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Providing FHTC (Functional Household Tap Connection) At Narendrapur Mouza (Part-3) of Shekrahati Water Supply Scheme In Jagatballavpur Block Of Howrah District. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000012/2022-2023 | 804/HD | 07/04/2022 | 45 | KAMIRUL SK AND CO. | 56.29 | 0 | 98
931 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House ( 5.40m x 3.60 m) at 3rd Tube Well Site of Sekrahati PWSS at J.B.Pur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000059/2023-2024 | 1851/HD | 02/05/2023 | 90 | M.K ENTERPRISE | 6.19 | 0 | 100
932 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Pipeline Work From 3rd Tubewell to Delivery line (Node No 326 to 312) at Sekrahati PWSS at J.B.Pur Block under Howrah Sadar Suv-Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000061/2023-2024 | 1853/HD | 02/05/2023 | 30 | DEBABRATA CHAKRABORTY | 4.33 | 0 | 100
933 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Boundary Wall at 3rd Tube Well Site of Sekrahati PWSS at J.B.Pur Block of Howrah District under Howrah Division, P. H. E. Dte. (12 m X 12 m) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000070/2023-2024 | 1931/HD | 10/05/2023 | 60 | M/S RAJBALLOVI CONSTRUCTION | 4.13 | 0 | 100
934 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction Of 400 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref :Dept. Super Struc. DRG. No. PCI/OHR/11/2012) Including All pipe Connection, Design od piles and soil test, Laying Distribution Pipeline At Krishnandapur Mouza Node No. 1 to 219 (Part-1) and Providing FHTC (Functional Household Tap Connection) at Krishnandapur Mouza (Part-1) for Augmentation Of SEKRAHATI Water Supply Scheme In Jagatballavpur Block Of Howrah Division PHED. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000131/2022-2023 | 1340/HD | 27/06/2022 | 1374 | JAHANGIR ALAM | 204.08 | 0 | 80
935 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Providing FHTC (Functional Household Tap Connection) At Sekrahati Mouza (Part-2) of Shekrahati Water Supply Scheme isn Jagatballavpur Block Of Howrah District (PART-B) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000531/2021-2022 | 628/HD | 22/03/2022 | 45 | SUSHANTA MONDAL | 26.5 | 0 | 100
936 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline At Narendrapur Mouza Node No. 367 to 450 (Part-3) of Shekrahati Water Supply Scheme in Jagatballavpur Block Of Howrah District. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000532/2021-2022 | 629/HD | 22/03/2022 | 45 | BUILT INDIA | 37.92 | 0 | 0
937 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep additional tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Shekrahati PWSS of Jagat Ballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000658/2022-2023 | 169/HD | 13/01/2023 | 45 | MUNSHI ENTERPRISE | 12.98 | 0 | 100
938 | Howrah Division | Howrah Sadar Sub-Division | Restoration of damaged concrete branch roads due to laying of pipe line at Sekrahati Mouza of Sekrahati PWSS under Howrah Divnision PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000663/2023-2024 | 208/HSSD | 29/02/2024 | 30 | SWASTIK ENTERPRISE | 3.69 | 0 | 100
939 | Howrah Division | Howrah Sadar Sub-Division | Laying Distribution Pipeline at Uncovered Area Near 3rd Tubewell (Node 326 to 309, 312 to 315 & 313 to 331) For Providing FHTC of Sekrahati Water Supply Scheme under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000664/2023-2024 | 209/HSSD | 29/02/2024 | 30 | MA-DURGA ENTERPRISE | 1.61 | 0 | 100
940 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Restoration of damaged concrete branch roads due to laying of pipe line at Narendrapur Mouza (Node No. 367 to 450) of Sekrahati PWSS under Howrah Divnision PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000685/2022-2023 | 273/HD | 19/01/2023 | 45 | BUILT INDIA | 10.4 | 0 | 0
941 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000018/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 20.07 | 0 | 0
942 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000048/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 23.04 | 0 | 0
943 | Howrah Division | Howrah Sadar Sub-Division | Indent of Material | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
944 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Sekrahati PWSS, Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | VCH/000955/2021-2022 | BP-2021-22-403 | 14/03/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.18 | 0 | 0
945 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of switch room ( 3.60 m x 3.0 m) with water supply & sanitary arrangement at 4th tube well site of Balichack PWSS of Amta-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu | JE/USD | ORD/000581/2022-2023 | 2598/HD | 07/12/2022 | 60 | BINOY KOLEY | 4.7 | 0 | 100
946 | Howrah Division | RWS Howrah Sub-Division | Restoration of Road at Murgaberia under Murgaberia PWSS under Uluberia Sub-Division of Howrah Division,PHEDte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000017/2024-2025 | 239/AE/USD | 10/06/2024 | 45 | BISWAJIT BAG | 19.58 | 0 | 100
947 | Howrah Division | RWS Howrah Sub-Division | Additional Laying distribution system at Chakmanohar mouza under Murgaberia PWSS of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000117/2024-2025 | 3883/HD | 05/09/2024 | 135 | MANIRUL ISLAM | 17.29 | 0 | 100
948 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
949 | Howrah Division | RWS Howrah Sub-Division | Laying Distribution System(UPVC & DI) & providing Functional Household Tap Connection (FHTC) of Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte.(Mouza-Chak monohar(54) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000330/2023-2024 | 4469/HD | 12/12/2023 | 75 | M/S. GHOSH CONSTRUCTION | 74.17 | 0 | 100
950 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Murgaberia PWSS at Bagnan-I Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000395/2022-2023 | 1971/HD | 22/09/2022 | 40 | ACME CONSTRUCTION | 35.36 | 0 | 0
951 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Murgaberia PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000448/2021-2022 | 249/HD | 07/02/2022 | 15 | STEELCONC AND ASSOCIATES | 3.11 | 0 | 0
952 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1350 nos ) for Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-I) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000589/2022-2023 | 2649/HD | 09/12/2022 | 1088 | B.B.C ENTERPRISE | 338.67 | 0 | 60
953 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000824/2022-2023 | 1053/HD | 15/03/2023 | 90 | KALIDAS ENTERPRISE | 7.18 | 0 | 100
954 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Murgaberia PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | ORD/000827/2022-2023 | 1056/HD | 15/03/2023 | 90 | GRAVITA ENTERPRISE | 7.17 | 0 | 100
955 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000022/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 36.79 | 0 | 0
956 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000045/2022-2023 | 2639/HD | 09/12/2022 | 0 | Resource Division | 32.55 | 0 | 0
957 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Bagnan I,Junior Engineer2 | RTOR000084/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 5.73 | 0 | 0
958 | Howrah Division | Howrah Sadar Sub-Division | Sinking 2nos. 300 X 200 mm dia and 230 m deep tube well drilling by direct rotary method with 200 mm. dia. PVC. strainer of 30m. length having 300 mm dia. 45m. long PVC housing pipe & 200 mm dia. 155m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Samanti PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000067/2025-2026 | 2574/HD | 02/06/2025 | 180 | G.T.AGRO CENTRE | 36.04 | 0 | 0
959 | Howrah Division | Howrah Sadar Sub-Division | Additional Laying Distribution Pipeline & Adopting 2 nos Jack Pushing of 700 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 198-200 & 53-200 of LDS drawing) on Ranihati-Amta Road of Samanti PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. (SM/12562) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000068/2024-2025 | 3106/HD | 08/07/2024 | 450 | M/S S.S. ENTERPRISE | 459.55 | 0 | 65
960 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
961 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR with Route Survey for new piped water supply scheme of Samanti PWSS Under Panchla Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000520/2022-2023 | 1947/HD | 20/09/2022 | 30 | STEELCONC AND ASSOCIATES | 3.98 | 0 | 0
962 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall,700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/6/2012) including Soil Investigation, Rising Main , Laying Distribution Pipeline & Provinding FHTC (6865 nos) For Samanti PWSS at Panchla Block under Howrah Sadar sub Division of Howrah Division, P. H. E. DTE. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000562/2022-2023 | 2500/HD | 30/11/2022 | 1085 | M/S S.S. ENTERPRISE | 789.11 | 0 | 40
963 | Howrah Division | Howrah Sadar Sub-Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Panchla Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000639/2023-2024 | 1207/HD | 11/03/2024 | 15 | M/S SUPROVAT GHOSH | 1.54 | 0 | 100
964 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Samanti PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000693/2022-2023 | 311/HD | 20/01/2023 | 30 | ZEOLITE FRESH INDIA | 34.42 | 0 | 100
965 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000079/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 307.14 | 0 | 0
966 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000079/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 42.29 | 0 | 0
967 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Baniara PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000228/2022-2023 | 81/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.86 | 0 | 100
968 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House, Boundary Wall,450 cum Capacity of 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Rising Main, Laying Distribution Pipeline & Providing FHTC (2221 nos) For Augmentation of Baniara PWSS at Domjur Block under Howrah Sadar sub Division of Howrah Division , P. H. E. DTE. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000588/2022-2023 | 2630/HD | 08/12/2022 | 1260 | UNIQUE AGENCY | 563.14 | 0 | 50
969 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 3 (Three) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Baniara PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000659/2022-2023 | 170/HD | 13/01/2023 | 630 | ACME CONSTRUCTION | 38.56 | 0 | 60
970 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | RTOR000009/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 28.1 | 0 | 0
971 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | RTOR000073/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 13.68 | 0 | 0
972 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site of SITAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000037/2024-2025 | 2853/HD | 21/06/2024 | 456 | K.N ENTERPRISE | 78.61 | 0 | 15
973 | Howrah Division | RWS Howrah Sub-Division | Rising Main & Inter Connection with both tube wells of SITAPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000037/2025-2026 | 2279/HD | 07/05/2025 | 30 | GUPTA ENTERPRISE | 9.41 | 0 | 0
974 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
975 | Howrah Division | RWS Howrah Sub-Division | Additional Laying of Distribution Pipe Lines & Functional Household Tap Connection(FHTC) for leftout area of SITAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000401/2024-2025 | 860/HD | 07/02/2025 | 75 | GUPTA ENTERPRISE | 92.73 | 0 | 0
976 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sitapur PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000564/2022-2023 | 2548/HD | 02/12/2022 | 45 | MUNSHI ENTERPRISE | 36.53 | 0 | 90
977 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Sitapur W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000627/2022-2023 | 2808/HD | 21/12/2022 | 840 | APEX ENGINEERING | 8.51 | 0 | 100
978 | Howrah Division | RWS Howrah Sub-Division | Work order for construction of Pump House ( 5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Sitapur W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000674/2022-2023 | 166/HD | 13/01/2023 | 840 | APEX ENGINEERING | 8.52 | 0 | 100
979 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Design including Soil Investigation, Laying Distribution Pipeline & Providing FHTC (1759 nos) for Sitapur PWSS of Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000710/2022-2023 | 380/HD | 01/02/2023 | 905 | GUPTA ENTERPRISE | 566.63 | 0 | 35
980 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000046/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 21.67 | 0 | 0
981 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000052/2023-2024 | 3217/HD | 05/09/2023 | 0 | Resource Division | 25.95 | 0 | 0
982 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000074/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 1.84 | 0 | 0
983 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Additional Distribution Pipe Lines With Allied Works of leftout area for RAMPUR Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte.(Part-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000062/2023-2024 | 1867/HD | 03/05/2023 | 60 | DEV DAS SHAW | 26.22 | 0 | 100
984 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Additional Distribution Pipe Lines With Allied Works of leftout area for RAMPUR Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte.(Part-B) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000072/2023-2024 | 1933/HD | 10/05/2023 | 60 | CONSTRUCTION CORNER | 29.82 | 0 | 50
985 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000237/2022-2023 | 1711/HD | 24/08/2022 | 30 | NANDY UDYOG | 9.36 | 0 | 50
986 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Rampur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000266/2021-2022 | 2148/HD | 01/12/2021 | 15 | APEX ENGINEERING | 3.17 | 0 | 0
987 | Howrah Division | RWS Howrah Sub-Division | Repairing of Pump house and Store room and ancillary work of HW site and 2nd TW site at Rampur w/s scheme at Udaynarayanpur Block under Uluberia Sub-Division, of Howrah Division P.H.E Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000274/2022-2023 | 347/AE/USD | 22/08/2022 | 45 | S RAHA ENTERPRISE | 3.5 | 0 | 0
988 | Howrah Division | RWS Howrah Sub-Division | Work order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-D) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000288/2022-2023 | 225/RWS | 01/09/2022 | 30 | MAITY CONSTRUCTIONS | 4.75 | 0 | 100
989 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Rampur Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-E) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000289/2022-2023 | 226 / RWS | 01/09/2022 | 30 | MAITY CONSTRUCTIONS | 4.75 | 0 | 100
990 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Rampur Water Supply Scheme in Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-A) (Section-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000341/2022-2023 | 1853/HD | 09/09/2022 | 60 | DEV DAS SHAW | 144.42 | 0 | 40
991 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Augmentation of Rampur Water Supply Scheme In Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte.(Part-B) (Section-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000358/2022-2023 | 1909/HD | 15/09/2022 | 45 | CONSTRUCTION CORNER | 114.82 | 0 | 35
992 | Howrah Division | RWS Howrah Sub-Division | Work Order for Repairing of OHR including land development of Rampur PWSS scheme in Udayanarayanpur Block, under Howrah Division P.H.E. Dte. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000773/2022-2023 | 790/H.D | 27/02/2023 | 30 | MAITY CONSTRUCTIONS | 6.6 | 0 | 100
993 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000004/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 7.39 | 0 | 0
994 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000036/2022-2023 | 2113/HD | 09/11/2022 | 0 | Resource Division | 10.38 | 0 | 0
995 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kotalpara Mouza & Khosalpur Mouza(Part) |  |  | ORD/000112/2020-2021 | 1507/HD | 04/11/2020 | 30 | MONDAL PRECISION PVT. LTD. | 28.5 | 0 | 0
996 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-G) (for Khosalpur Mouza(Part) |  |  | ORD/000113/2020-2021 | 1508/HD | 04/11/2020 | 30 | N. G ENGINEERING | 29.1 | 0 | 0
997 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-H) (for Khosalpur Mouza(Part) |  |  | ORD/000114/2020-2021 | 1509/HD | 04/11/2020 | 30 | N. G ENGINEERING | 29.1 | 0 | 0
998 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000345/2021-2022 | W/278 | 06/09/2021 | 0 | M/S ASHIRBAD (INDIA) | 27.77 | 0 | 0
999 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000346/2021-2022 | W/277 | 06/09/2021 | 0 | JAHANGIR ALAM | 16.09 | 0 | 0
1000 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-F) (for Kotalpara Mouza & Khosalpur Mouza(Part) |  |  | VCH/000606/2021-2022 | W/602 | 28/12/2021 | 0 | MONDAL PRECISION PVT. LTD. | 5.16 | 0 | 0
1001 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000806/2020-2021 | 844328 | 17/03/2021 | 0 | N. G ENGINEERING | 28.31 | 0 | 0
1002 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000873/2020-2021 | 844330 | 17/03/2021 | 0 | M/S ASHIRBAD (INDIA) | 27.58 | 0 | 0
1003 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline & Providing Functional Household Tap Connection((part-2), 550 nos of Sealdanga PWSS at J.B.PUR Blockof Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000013/2023-2024 | 1545/HD | 04/04/2023 | 1080 | M/S ASHIRBAD (INDIA) | 86.98 | 0 | 15
1004 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline of Sealdanga PWSS at J.B.PUR Block of Howrah District under Howrah Division, P. H. E. Dte.(part-3) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000014/2023-2024 | 1546/HD | 04/04/2023 | 120 | BUILT INDIA | 93.16 | 0 | 35
1005 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection, soil investigation & foundation design of Sealdanga PWSS at J.B.PUR Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000033/2023-2024 | 1736/HD | 25/04/2023 | 335 | BISWAJIT BAG | 110.36 | 0 | 0
1006 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Sial Danga PWSS (Mouza-Sial Danga, Kumarpur, & Chak Patmura) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000075/2022-2023 | 1018/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 3.04 | 0 | 0
1007 | Howrah Division | Howrah Sadar Sub-Division | Construction of approach road and land Development at OHR site for Sealdanga PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000111/2025-2026 | 3131/HD | 14/07/2025 | 60 | M/S SRIKANTA PATRA | 77.22 | 0 | 0
1008 | Howrah Division | Howrah Sadar Sub-Division | Construction of 2 nos 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at Head Work Site& other tubewell site, Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) (550 Nos) For Sealdanga PWSS at J.B.PUR Blockof Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000135/2023-2024 | 2736/HD | 26/07/2023 | 1066 | SWASTIK ENTERPRISE | 123.64 | 0 | 20
1009 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sealdanga PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000801/2022-2023 | 1001/H.D | 13/03/2023 | 780 | R CONSTRUCTION | 25.64 | 0 | 100
1010 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000050/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 10.53 | 0 | 0
1011 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000076/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 14.14 | 0 | 0
1012 | Howrah Division | Howrah Mechanical Sub-Division | Implementation of Mini Piped Water Supply Scheme in 13(thirteen) no villages under different blocks having less than 100 households under Howrah District in connection with Jal Swapna. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000125/2023-2024 | 2155/H.D | 07/06/2023 | 961 | MONDAL PRECISION PVT. LTD. | 330.32 | 0 | 80
1013 | Howrah Division | Howrah Sadar Sub-Division | Restoration Work of Bituminous Road and Shoulder with allied work of Makardah Bazar to Begri Road from 0.00 Kmp to 1.90 Kmp (Due to Cutting for PHE water line) under Howrah Division in th e dist of Howrah during the year 2024-25. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00829/2024-2025 | BP-2024-25-496 | 27/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 9.52 | 0 | 0
1014 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Bhandardaha PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000741/2022-2023 | 603/HD | 16/02/2023 | 45 | M DHARA AND BROTHERS | 38.37 | 0 | 100
1015 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying distribution pipe line, Providing FHTC , Repairing of RCC Over Head Reservoir of capacity 350cum with allied work including supply of all labour & materials for Augmentation Of BHANDARDAH Water Supply Scheme at Domjur Block under Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000798/2022-2023 | 998/HD | 13/03/2023 | 1020 | P B ENTERPRISE | 754.4 | 0 | 80
1016 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000056/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 21.73 | 0 | 0
1017 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000088/2022-2023 | 593/HD | 13/02/2023 | 0 | Resource Division | 88.98 | 0 | 0
1018 | Howrah Division | Ulberia Sub-Division | Special maintenance of pipeline at Amragori Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Phase-I) | AE/Ulu | JE/USD | ORD/000210/2021-2022 | 1820/HD | 17/09/2021 | 30 | UNIQUE AGENCY | 2.27 | 0 | 0
1019 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) to Schools, AWC's & Public Institution of Amragori, Nakubar, Sarda, Tajpur, Joypur, Narit, Kanpur, Paschim Gazipur, Balichack, Uttar Pirpur W/S scheme under under Howrah Division, PHE Dte. | AE/Ulu | JE/USD | ORD/000245/2021-2022 | 2175/HD | 01/12/2021 | 30 | JOY CHANDI CONSTRUCTION | 4.28 | 0 | 0
1020 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-B) [Amragari MOUZA PART & Rautara MOUZA PART] | AE/Ulu | JE/USD | ORD/000434/2020-2021 | 156/HD | 19/01/2021 | 30 | UNIQUE AGENCY | 28.9 | 21.75 | 0
1021 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-C) [Rautara MOUZA PART] | AE/Ulu | JE/USD | ORD/000435/2020-2021 | 157/HD | 19/01/2021 | 30 | GHOSH ENTERPRISE. | 42.22 | 5.52 | 0
1022 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-E) [Kakrol MOUZA PART] | AE/Ulu | JE/USD | ORD/000437/2020-2021 | 159/HD | 19/01/2021 | 30 | TANMOY ROY CHOUDHURY | 38.98 | 40.46 | 0
1023 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-F) [Kakrol MOUZA PART] | AE/Ulu | JE/USD | ORD/000438/2020-2021 | 160/HD | 19/01/2021 | 30 | DEV DAS SHAW | 39.02 | 36.37 | 0
1024 | Howrah Division | Ulberia Sub-Division | Retrofitting of providing Functional Household Tap Connection from existing distribution system of Amragori & adj Mouzas piped water supply scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) | AE/Ulu | JE/USD | VCH/000247/2021-2022 | BP-2021-22-164 | 07/10/2021 | 0 | TANMOY ROY CHOUDHURY | 11.83 | 0 | 0
1025 | Howrah Division | Ulberia Sub-Division | WBSEDCL | AE/Ulu | JE/USD | VCH/000585/2022-2023 |  | 13/09/2022 | 0 | WBSEDCL | 3.02 | 0 | 0
1026 | Howrah Division | Ulberia Sub-Division | Retrofitting of Amragori. | AE/Ulu | JE/USD | VCH/000766/2020-2021 |  | 24/03/2021 | 0 | TANMOY ROY CHOUDHURY | 22.54 | 0 | 0
1027 | Howrah Division | Ulberia Sub-Division | Retrofitting of Amragori. | AE/Ulu | JE/USD | VCH/000767/2020-2021 | W/386 | 19/07/2021 | 0 | GHOSH ENTERPRISE. | 30.3 | 0 | 0
1028 | Howrah Division | Ulberia Sub-Division | Retrofitting of Amragori. | AE/Ulu | JE/USD | VCH/000768/2020-2021 | W/95 | 19/07/2021 | 0 | MAA TARA CONSTRUCTION | 17.11 | 0 | 0
1029 | Howrah Division | Ulberia Sub-Division | Retrofitting of Amragori. | AE/Ulu | JE/USD | VCH/000769/2020-2021 | W/97 | 19/07/2021 | 0 | TANMOY ROY CHOUDHURY | 21.4 | 0 | 0
1030 | Howrah Division | Ulberia Sub-Division | Retrofitting of Amragori. | AE/Ulu | JE/USD | VCH/000770/2020-2021 |  | 24/03/2021 | 0 | UNIQUE AGENCY | 21.75 | 0 | 0
1031 | Howrah Division | Ulberia Sub-Division | Retrofitting of Amragori. | AE/Ulu | JE/USD | VCH/000772/2020-2021 | W/95 | 19/07/2021 | 0 | RANA ENTERPRISE | 10.33 | 0 | 0
1032 | Howrah Division | Ulberia Sub-Division | Alternative laying of pipeline due to construction of PMGSY road for Amragori w/s scheme (from Danda's Misti's shop to Chacksalika Vimtala) at section (100-101-101B-101C-103-105-107-111-113-118-120-121-127-128-128B-135-136-141) under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE/USD | VCH/000798/2021-2022 | BP-2021-22-322 | 18/02/2022 | 0 | UNIQUE AGENCY | 3.38 | 0 | 0
1033 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Piped Water Supply Scheme For Amragari & Adj. Mouzas. under Amta-II Block under Howrah Division, PHE Dte. (PART-B) [Amragari MOUZA PART & Rautara MOUZA PART] | AE/Ulu | JE/USD | VCH/000799/2021-2022 | BP-2021-22-321 | 18/02/2022 | 0 | UNIQUE AGENCY | 4.01 | 0 | 0
1034 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) | AE/Ulu | JE/USD | VCH/000975/2021-2022 | BP-2021-22-421 | 21/03/2022 | 0 | MAA TARA CONSTRUCTION | 2.05 | 0 | 0
1035 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | VCH/000976/2021-2022 | BP-2021-22-422 | 06/04/2022 | 0 | RANA ENTERPRISE | 2.3 | 0 | 0
1036 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Amragori W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu | JE/USD | VCH/001033/2021-2022 | BP-2021-22-422 | 23/03/2022 | 0 | RANA ENTERPRISE | 2.3 | 0 | 0
1037 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000001/2023-2024 | 1530/HD | 04/04/2023 | 45 | BALAJI UDDYOG | 89.53 | 0 | 70
1038 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 4 Nos Pump House (5.40m x 3.60m) at 1st 2nd,3rd &4th Tube Well Site, Construction of Boundary Wall at 1st Tube Well Site, 3 nos Boundary Wall at 2nd , 3rd & 4th Tube Well SiteConstruction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution of Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-II) Uttar Jhapardaha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000044/2023-2024 | 1831/HD | 02/05/2023 | 784 | PRAVAT SARKAR | 607.14 | 0 | 10
1039 | Howrah Division | Howrah Sadar Sub-Division | Land Development Works of Uttar Jhapardaha (Zone-2) PWSS 1st, 2nd, 3rd & 4th Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000447/2024-2025 | 975/HD | 19/02/2025 | 45 | SONAR BANGLA ENTERPRISE | 15.11 | 0 | 0
1040 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000012/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 163.76 | 0 | 0
1041 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000060/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 22.24 | 0 | 0
1042 | Howrah Division |  | Connection with 4th Tubewell to existing Laying Distribution Pipeline & Allied work for Laskarpur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division,P. H. E. Dte. |  |  | ORD/000034/2024-2025 | 643/HSSD | 26/06/2024 | 30 | ADRIJA ENTERPRISE | 4.9 | 0 | 100
1043 | Howrah Division |  | Construction of approach road and land Development of 4th tubewell site, Construction of 1(one) nos. boundary wall, Construction of 4th Pump House (5.40m x 3.60m) for Laskarpur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000429/2024-2025 | 892/HD | 11/02/2025 | 45 | ADRIJA ENTERPRISE | 13.66 | 0 | 0
1044 | Howrah Division |  | Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method, connection with distribution system and Reconnection of FHTC & Allied Works, Construction of 2 (Two) Nos.Pump House (5.40m x 3.60m), Construction of 2 (Two) nos. Boundary Wall at Laskarpur Piped Water Supply Scheme Under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000576/2023-2024 | 966/HD | 28/02/2024 | 540 | M/S SUMAN SHIL | 102.48 | 0 | 80
1045 | Howrah Division |  | Additional Pipline & connection with 3rd Tubewell to existing Laying Distribution Pipeline & Allied work for Gobindapur PWSS at JBpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000036/2024-2025 | 644/HSSD | 26/06/2024 | 30 | ADRIJA ENTERPRISE | 5.42 | 0 | 100
1046 | Howrah Division |  | Sinking 1 no. 250 X 150 mm dia and 240 m Replacement deep tube well drilling by direct rotary method with 150 mm. dia. PVC. strainer of 30 m. length having 250 mm dia. 60 m. long PVC housing pipe & 150 mm dia. 150 m. long well pipe alongwith 3m blank pipe all complete including cost of materials for Gobindapur PWSS at Jagatballavpur Block under Howrah Sadar Sub-Division under Howrah Division, P.H.E. Dte.. |  |  | ORD/000072/2025-2026 | 2682/HD | 05/06/2025 | 150 | AQUATECH ENGINEERS | 14.53 | 0 | 0
1047 | Howrah Division |  | Construction of approach road and land Development of 3rd tubewell site, Construction of 1(one) nos. boundary wall, Construction of 3rd Pump House (5.40m x 3.60m) for Gobindapur PWSS at Jagatballavpur at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000430/2024-2025 | 893/HD | 11/02/2025 | 45 | ADRIJA ENTERPRISE | 13.76 | 0 | 0
1048 | Howrah Division |  | Sinking 1No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with 150mm. dia. PVC. Strainer of 30m. length having 250 mm dia. 60 m. long PVC housing pipe & 150mm dia. 150m. long well pipe alongwith 3m blank pipe all complete including cost of materials at Gobindapur PWSS at Jagatballavpur Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000588/2023-2024 | 996/HD | 01/03/2024 | 30 | ACME CONSTRUCTION | 14.58 | 0 | 100
1049 | Howrah Division |  | Connection with distribution system and Reconnection of FHTC & allied Works, Construction of 1(One) No Pump House (5.40m x 3.60 m), Construction of 1(One) no Boundary Wall at Gobindapur Piped Water Supply Scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000595/2023-2024 | 1000/HD | 01/03/2024 | 300 | LAKSHMI IRON | 59.38 | 0 | 10
1050 | Howrah Division |  | Sinking of additional 3 (three) Nos. 250 X 150 mm Dia and 250 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete for Kulgachi PWSS of Uluberia-I Block of Howrah Division, P.H.E. Dte. |  |  | ORD/000038/2024-2025 | 2860/HD | 24/06/2024 | 60 | G.T.AGRO CENTRE | 46.21 | 0 | 100
1051 | Howrah Division |  | Additional Laying of pipeline in addition to providing FHTC Kulgachi PWSS of Uluberia-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000531/2023-2024 | 2039/AE/USD | 13/02/2024 | 30 | MA DURGA ENTERPRISE | 6.05 | 0 | 100
1052 | Howrah Division |  | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Uluberia-I block of Uluberia Sub Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000652/2023-2024 | 1211/HD | 11/03/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.85 | 0 | 100
1053 | Howrah Division |  | Re-Laying distribution system (HDPE & DI) & Shifting HouseHold Connection(FHTC) at Kulgachi PWSS of Uluberia -I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000685/2023-2024 | 3240/AE/USD | 12/03/2024 | 45 | PRADIP KUMAR JATI | 28.64 | 0 | 100
1054 | Howrah Division |  | Preparation of DPR for new piped water supply scheme of Brindabanpur PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.(Baniban, Zone-IV) |  |  | ORD/000249/2022-2023 | 323/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 3.8 | 0 | 100
1055 | Howrah Division |  | BANIBAN (Zone-II & IV) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Uluberia-II Block, District:- Howrah [NEW SCHEME] |  |  | ORD/000336/2023-2024 | 4553/HD | 18/12/2023 | 365 | LUKE ENGICON | 1736.09 | 0 | 35
1056 | Howrah Division |  | Hiring of 1 (One) no. Luxury Taxi/Maxi cab/Motor cab on daily basis under monthly hiring category for the Assistant Engineer,Uluberia Sub- Division , PHE Dte of the Government of West Bengal (for Twelve months) under Howrah Division,PHEdte. (Period of 365 Days) |  |  | ORD/000459/2023-2024 | 791/AE/USD | 29/11/2023 | 366 | NOBLE ENTERPRISE | 4.81 | 0 | 40
1057 | Howrah Division |  | Continuation order for Hiring of 01 (One) no. (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer, Uluberia Sub-Division, PHE Dte. (for the period from 01.01.2024 to 31.12.2024). Car No.:-WB-135078 In continuation to the order under reference and your application dated 26/12/2023, you are requested to continue the above mentioned 'work in consultation with the Assistant Engineer, Uluberia Sub-Division, PHE Dte. |  |  | ORD/000623/2023-2024 | 4785/HD | 29/12/2023 | 366 | PUTUL TRAVELS | 4.79 | 0 | 25
1058 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000038/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 7.39 | 0 | 0
1059 | Howrah Division |  | Preparation of DPR for new piped water supply scheme of Kantaberia PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.(Baniban, Zone-II) |  |  | ORD/000248/2022-2023 | 322/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 3.55 | 0 | 100
1060 | Howrah Division |  | BANIBAN (Zone-II & IV) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Uluberia-II Block, District:- Howrah [NEW SCHEME] |  |  | ORD/000336/2023-2024 | 4553/HD | 18/12/2023 | 365 | LUKE ENGICON | 1736.09 | 0 | 35
1061 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A)[Dakshin Jaypur Mouza] [Number of FHTC to be provided (Approx) : 227] | AE/Ulu | JE/USD | ORD/000391/2020-2021 | 46/HD | 05/01/2021 | 30 | MAHARAJ CONSTRUCTION CO | 14.33 | 0 | 0
1062 | Howrah Division | Ulberia Sub-Division | Construction of Pump House of additional Tube well site of Joypur PWSS at Amta-II Development Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000754/2024-2025 | 1410/HD | 17/03/2025 | 60 | JSZ GLOBAL | 7.93 | 0 | 0
1063 | Howrah Division | Ulberia Sub-Division | Retrofitting Joypur | AE/Ulu | JE/USD | VCH/000050/2021-2022 | W/154 | 09/08/2021 | 0 | N. G ENGINEERING | 37.09 | 0 | 0
1064 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Joypur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-C) [Jaypur Mouza part] [Number of FHTC to be provided (Approx) : 650] | AE/Ulu | JE/USD | VCH/000923/2021-2022 | BP-2021-22-378 | 03/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 39.42 | 0 | 0
1065 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-A) (for Purba Bajepratap Mouza) |  |  | ORD/000158/2020-2021 | 1621/HD | 09/11/2020 | 30 | GHOSH CONCERN | 25.92 | 0 | 0
1066 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-B) (for Dhurkhali Mouza part) |  |  | ORD/000159/2020-2021 | 1622/HD | 09/11/2020 | 30 | GHOSH CONCERN | 28.9 | 0 | 0
1067 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Balichak piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Dhurkhali Mouza part) |  |  | ORD/000160/2020-2021 | 1623/HD | 09/11/2020 | 30 | N. G ENGINEERING | 22.81 | 0 | 0
1068 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. |  |  | VCH/000756/2020-2021 | 844334 | 25/02/2021 | 0 | GHOSH CONCERN | 25.85 | 0 | 0
1069 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply Scheme. |  |  | VCH/000776/2020-2021 | 84433 | 01/03/2021 | 0 | P B ENTERPRISE | 27.61 | 0 | 0
1070 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply Scheme. |  |  | VCH/000872/2020-2021 | 844329 | 17/03/2021 | 0 | M/S CHANDIMATA CONSTRUCTION | 18.39 | 0 | 0
1071 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Purba Bajepratap and Dhurkhali Mouza of Balichak piped water supply scheme. |  |  | VCH/000953/2020-2021 | 8443107 | 30/03/2021 | 0 | P B ENTERPRISE | 23.52 | 0 | 0
1072 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-D) (for Chaltakhali (Part) & Jotsadar Mouza) |  |  | ORD/000110/2020-2021 | 1505/HD | 04/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 29.03 | 0 | 0
1073 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-E) for Chaltakhali Mouza (Part) |  |  | ORD/000111/2020-2021 | 1506/HD | 04/11/2020 | 30 | M/S ASHIRBAD (INDIA) | 28.82 | 0 | 0
1074 | Howrah Division |  | Retrofitting Khosalpur Water Supply Scheme |  |  | VCH/000869/2020-2021 | 84435 | 01/03/2021 | 0 | PRADIP KUMAR JATI | 24.12 | 0 | 0
1075 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000871/2020-2021 | 844327 | 17/03/2021 | 0 | JAHANGIR ALAM | 26.44 | 0 | 0
1076 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme. |  |  | VCH/000952/2020-2021 | 8443106 | 30/03/2021 | 0 | NATURAL RESOURCES CONSORTIUM | 21.16 | 0 | 0
1077 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chaltakhali & Jotsadar Mouza of Khosalpur piped water supply scheme |  |  | VCH/000954/2020-2021 | 8443108 | 30/03/2021 | 0 | PRADIP KUMAR JATI | 25.73 | 0 | 0
1078 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-A) [Narit Mouza part] | AE/Ulu |  | ORD/000269/2020-2021 | 1802/HD | 27/11/2020 | 30 | M/S MANABESH ROY | 22.53 | 0 | 0
1079 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-B) [Narit Mouza part] | AE/Ulu |  | ORD/000270/2020-2021 | 1803/HD | 27/11/2020 | 30 | SUNIRMAN ENTERPRISE | 19.47 | 16.2 | 0
1080 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-C) [Narit Mouza part] | AE/Ulu |  | ORD/000271/2020-2021 | 1804/HD | 27/11/2020 | 30 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.53 | 0 | 0
1081 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte.on, PHE Dte. (Part-D) [Sirol Mouza] | AE/Ulu |  | ORD/000272/2020-2021 | 1805/HD | 27/11/2020 | 30 | JAHANGIR ALAM | 36.58 | 0 | 0
1082 | Howrah Division | Ulberia Sub-Division | Hiring of Vehicle | AE/Ulu |  | VCH/000601/2021-2022 | W/579 | 16/12/2021 | 0 | DIPANKAR GHOSH | 3.71 | 0 | 0
1083 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | AE/Ulu |  | VCH/000657/2020-2021 | W/538 | 30/01/2021 | 0 | JAHANGIR ALAM | 36.57 | 0 | 0
1084 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | AE/Ulu |  | VCH/000852/2020-2021 | 844343 | 20/03/2021 | 0 | M/S MANABESH ROY | 15.07 | 0 | 0
1085 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Narit Piped Water Supply Scheme under Amta-II Block | AE/Ulu |  | VCH/000998/2020-2021 | 844352 | 22/03/2021 | 0 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.34 | 0 | 0
1086 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-L) |  |  | ORD/000081/2021-2022 | 1433/HD | 13/07/2021 | 30 | A.P. POWER & CONCRETE | 4.79 | 0 | 0
1087 | Howrah Division |  | Laying of 50 mm & 75 mm dia.,Total 1948 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-M) |  |  | ORD/000082/2021-2022 | 1434/HD | 13/07/2021 | 30 | A.P. POWER & CONCRETE | 4.8 | 0 | 0
1088 | Howrah Division |  | Laying of 63 mm dia. 1615 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-N) |  |  | ORD/000083/2021-2022 | 1435HD | 13/07/2021 | 30 | A.P. POWER & CONCRETE | 4.31 | 0 | 0
1089 | Howrah Division |  | Laying of 90 mm dia 470 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-O) |  |  | ORD/000084/2021-2022 | 1436HD | 13/07/2021 | 30 | BUILT INDIA | 2.41 | 0 | 0
1090 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-V) |  |  | ORD/000085/2021-2022 | 1437HD | 13/07/2021 | 30 | MONIRUL ISLAM | 4.27 | 0 | 0
1091 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-X) |  |  | ORD/000086/2021-2022 | 1438/HD | 13/07/2021 | 30 | BUILT INDIA | 4.34 | 0 | 0
1092 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-W) |  |  | ORD/000087/2021-2022 | 1439/HD | 13/07/2021 | 30 | BUILT INDIA | 2.61 | 0 | 0
1093 | Howrah Division |  | Laying of 50 mm ,63 mm & 75 mm dia. 110mm dia 125mm dia,Total 1034 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Gobindapur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-II) (Part-S) |  |  | ORD/000088/2021-2022 | 1440/HD | 13/07/2021 | 30 | BUILT INDIA | 3.34 | 0 | 0
1094 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS at Howrah Sub Division under Howrah Division , PHE Dte. |  |  | ORD/000089/2021-2022 | 1441/HD | 13/07/2021 | 30 | MONIRUL ISLAM | 4.76 | 0 | 0
1095 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-D) |  |  | ORD/000126/2020-2021 | 1536/HD | 05/11/2020 | 30 | JDJ ENTERPRISE A UNIT OF JDJ TRADERS PRIVATE LIMITED | 18.83 | 0 | 0
1096 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte.(Part-E) |  |  | ORD/000127/2020-2021 | 1537/HD | 05/11/2020 | 30 | BUILT INDIA | 18.06 | 0 | 0
1097 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-F |  |  | ORD/000128/2020-2021 | 1538/HD | 05/11/2020 | 30 | BUILT INDIA | 18.12 | 0 | 0
1098 | Howrah Division |  | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Gobindapur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. |  |  | ORD/000426/2021-2022 | 340/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 4.77 | 0 | 0
1099 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000916/2020-2021 | 645/21/2022 | 15/08/2020 | 0 | BUILT INDIA | 11.53 | 11.53 | 0
1100 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000925/2020-2021 | 627/21/2022 | 15/08/2020 | 0 | RAKESH ENTERPRISE | 4.35 | 1.45 | 0
1101 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | ORD/000926/2020-2021 | 27/21/2022 | 15/08/2020 | 0 | BUILT INDIA | 1.77 | 1.77 | 0
1102 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000473/2021-2022 | W/427 | 08/10/2021 | 0 | A.P. POWER & CONCRETE | 8.92 | 0 | 0
1103 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000480/2021-2022 | W/428 | 08/10/2021 | 0 | A.P. POWER & CONCRETE | 4 | 0 | 0
1104 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000527/2021-2022 | 84439 | 16/11/2021 | 0 | A.P. POWER & CONCRETE | 1.43 | 0 | 0
1105 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000645/2021-2022 | 844318 | 20/01/2022 | 0 | MS ARPAN ENTERPRISE | 4.26 | 0 | 0
1106 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-W) |  |  | VCH/000852/2021-2022 | 844315 | 17/03/2022 | 0 | BUILT INDIA | 2.57 | 0 | 0
1107 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000864/2020-2021 | 844357 | 23/03/2021 | 0 | BUILT INDIA | 15.66 | 0 | 0
1108 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000876/2020-2021 | 844356 | 23/03/2021 | 0 | BUILT INDIA | 15.55 | 0 | 0
1109 | Howrah Division |  | Retrofitting Gobindapur W/S Scheme. |  |  | VCH/000876/2021-2022 | 844334 | 30/03/2022 | 0 | ALOK ENTERPRISE | 15.52 | 0 | 0
1110 | Howrah Division |  | Bally Jagacha Phase -I |  |  | BILL/00155/2022-2023 |  | 20/01/2023 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 15.58 | 0 | 0
1111 | Howrah Division |  | Sample Test |  |  | BILL/00350/2022-2023 |  | 24/03/2023 | 0 | NATIONAL TEST HOUSE | 0.09 | 0 | 0
1112 | Howrah Division |  | National Test House |  |  | BILL/00461/2022-2023 | BP-2022-23-691 | 16/03/2023 | 0 | NATIONAL TEST HOUSE | 0.09 | 0 | 0
1113 | Howrah Division |  | Railway Permission |  |  | BILL/00464/2022-2023 | BP-2022-23-624 | 30/03/2023 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 11.93 | 0 | 0
1114 | Howrah Division |  | Eastern Railway, Howrah Division |  |  | BILL/00465/2022-2023 | BP-2021-22-623 | 30/03/2023 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 1.11 | 0 | 0
1115 | Howrah Division |  | Work Order for Remaining part of laying distribution system of Pipe water supply at Zone-III/IV.(pal para,mondal para, kote para, Rupnagar)for Surface water based water supply project for Bally-Jagacha(PH-II), under Howrah Division, PHE Dte.(Part-B). |  |  | ORD/000009/2022-2023 | 817/HD | 08/04/2022 | 30 | M/S MOINAK POREL | 19.5 | 0 | 100
1116 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/05/2024 to 31/07/2024) under Howrah Division, PHE Dte. |  |  | ORD/000009/2024-2025 | 2219/HD | 30/04/2024 | 92 | SUMANTA DEY | 1 | 0 | 0
1117 | Howrah Division |  | Work Order for Withdrawing & relaying distribution system pipe line from Makaltala to Bally station (N.P.- 155 to 4) in the uncovered areas of Surface water based water supply project for Bally Jagacha block, under Howrah Division PHE Dte.(D.A-1 G.P Area) Zone-5 Length= 1.05km.nos. |  |  | ORD/000010/2022-2023 | 818/HD | 08/04/2022 | 30 | BISWAJIT SAMANTA | 7.94 | 0 | 100
1118 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/06/2024 to 31/07/2024) |  |  | ORD/000011/2024-2025 | 2566/HD | 30/05/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1119 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Nischinda Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-A) No. of House Hold(Approx)=4500 nos. |  |  | ORD/000031/2021-2022 | 1310/HD | 24/06/2021 | 45 | JDJ ENTERPRISE A UNIT OF JDJ TRADERS PRIVATE LIMITED | 198.75 | 0 | 0
1120 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. |  |  | ORD/000032/2021-2022 | 1311/HD | 24/06/2021 | 45 | JAYANTA KUMAR MONDAL | 239.97 | 0 | 0
1121 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. |  |  | ORD/000033/2021-2022 | 1312/HD | 24/06/2021 | 45 | GHOSH CONCERN | 176.91 | 0 | 0
1122 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-2. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold(Approx)= 4500 nos |  |  | ORD/000034/2021-2022 | 1313/HD | 24/06/2021 | 45 | ALOK ENTERPRISE | 232 | 0 | 0
1123 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chakpara Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold(Approx)=5000 nos. |  |  | ORD/000035/2021-2022 | 1314/HD | 24/06/2021 | 45 | MAHAVIR PUMPS MFG.PVT.LTD | 220.68 | 47.15 | 100
1124 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface Based Water Supply Project for Bally-Jagacha Block, under HowrahDivision,PHEDte. (D.A-1G.PArea) Zone-5 |  |  | ORD/000035/2023-2024 | 1707/HD | 24/04/2023 | 10 | S.B. ENTERPRISE | 0.88 | 0 | 100
1125 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Jagadispur Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-G) No. of House Hold(Approx)= 3500 nos. |  |  | ORD/000036/2021-2022 | 1315/HD | 24/06/2021 | 45 | VISHAL CONSTRUCTION CO. | 176.21 | 107.28 | 0
1126 | Howrah Division |  | Work Order for Carrying charges office CE Office (HQ) NS Building to Bally WTP Site & WTP Site to Howrah Division office under Howrah Division, PHE Dte. |  |  | ORD/000036/2023-2024 | 1708/HD | 24/04/2023 | 7 | MENOKA ENGINEERING WORKS | 0.82 | 0 | 100
1127 | Howrah Division |  | Laying Distribution Pipeline For Uncovered area at Zone-IV of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. |  |  | ORD/000043/2024-2025 | 2892/HD | 26/06/2024 | 240 | S.B ENTERPRISE | 18.4 | 0 | 100
1128 | Howrah Division |  | Restoration of road in uncovered areas in Zone-1 & 2. under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. Howrah Length- 750m. (Part-I) |  |  | ORD/000054/2021-2022 | 1368/HD | 29/06/2021 | 30 | SK ENTERPRISE | 4.33 | 0 | 0
1129 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/07/2024 to 30/09/2024) under Howrah Division, PHE Dte. |  |  | ORD/000060/2024-2025 | 2924/HD | 27/06/2024 | 92 | MD KADIR | 1 | 0 | 0
1130 | Howrah Division |  | Work Order for Dismantling of concrete road for laying of pipe line in Zone-4 under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division, PHE Dte. (Part-A) |  |  | ORD/000081/2022-2023 | 1139/HD | 27/05/2022 | 20 | A.G.S ENTERPRISE | 3.93 | 0 | 0
1131 | Howrah Division |  | Work Order for Dismantling of concrete road for laying of pipe line in Zone-4 under Bally Jagacha (Phase-II) Surface based water supply Project under Howrah Division, PHE Dte. (Part-B) |  |  | ORD/000082/2022-2023 | 1140/HD | 27/05/2022 | 20 | A.G.S ENTERPRISE | 3.75 | 0 | 0
1132 | Howrah Division |  | Work Order for Adopting Jack Pushing of 813 mm Dia 10 mm thick M.S pipe as Casing to Cross Water carrier Pipe on Tentulkuli rail crossing work of Bally Jagacha (PH-II) Surface Water Supply Scheme under Howrah Division P.H.E. Dte. |  |  | ORD/000082/2023-2024 | 1963/HD | 11/05/2023 | 45 | SUBHASH BOSE | 95.69 | 0 | 100
1133 | Howrah Division |  | Construction of Retaining Wall at Narna Zone-V OHR Site under Bally Jagacha(phase-II) surface Based water supply project under Howrah Division, P.H.E. Dte. |  |  | ORD/000085/2024-2025 | 3463/HD | 02/08/2024 | 30 | GUPTA ENTERPRISE | 4.76 | 0 | 0
1134 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/05/2025 to 31/07/2025) under Howrah Division, PHE Dte. |  |  | ORD/000085/2025-2026 | 2103/HD | 29/04/2025 | 92 | SUMANTA DEY | 0.99 | 0 | 0
1135 | Howrah Division |  | Construction of partition wall and Earth filling in passage at Narna Zone-V OHR Site under Bally Jagacha(phase-II) surface Based water supply project under Howrah Division, P.H.E. Dte. |  |  | ORD/000086/2024-2025 | 3464/HD | 02/08/2024 | 30 | GUPTA ENTERPRISE | 4.48 | 0 | 0
1136 | Howrah Division |  | Special repairing for Distribution system and brusting of rising main at Lakshmanpur, Jotgiri & Narna of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. |  |  | ORD/000087/2024-2025 | 3465/HD | 02/08/2024 | 15 | COSMO ENTERPRISE | 3.91 | 0 | 100
1137 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/08/2024 to 30/09/2024) |  |  | ORD/000088/2024-2025 | 3362/HD | 30/07/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1138 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/08/2024 to 31/10/2024) under Howrah Division, PHE Dte. |  |  | ORD/000089/2024-2025 | 3379/HD | 30/07/2024 | 92 | SUMANTA DEY | 1 | 0 | 0
1139 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/07/2025 to 30/09/2025) under Howrah Division, PHE Dte. |  |  | ORD/000121/2025-2026 | 2952/HD | 26/06/2025 | 92 | MD KADIR | 1 | 0 | 0
1140 | Howrah Division |  | 1. Clear water rising main from GLR to different Zonal OHR, 2. Laying distribution system of piped water supply at (Zone-VI) and 3. Construction of Administrative Building, Store & Stack Yard at Domjur Boosting Station for surface water based water supply scheme for Bally-Jagacha (Phase-II) under Howrah Division, P.H.E. Dte. |  |  | ORD/000151/2020-2021 | 1597/HD | 09/11/2020 | 546 | SUBHASH BOSE | 267 | 0 | 50
1141 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/10/2024 to 30/11/2024) |  |  | ORD/000159/2024-2025 | 4188/HD | 26/09/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1142 | Howrah Division |  | Special repairing works in different location( at Lock down period) in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Nischinda G.P Area) Zone-6A, 6B. |  |  | ORD/000181/2020-2021 | 1172/HD | 30/09/2020 | 30 | MENOKA ENGINEERING WORKS | 1.77 | 0 | 0
1143 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara Basukati G.P Area) Zone-7,8 Length= 736.00mtr.(PART-J) |  |  | ORD/000188/2020-2021 | 1179/HD | 30/09/2020 | 30 | NIRMAL UDYOG | 4.5 | 0 | 0
1144 | Howrah Division |  | Work Order for Sinking of 2 (two) nos PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep near i)Bally Ghosh Para OHR Site Zone-6A & ii)Jagadishpur OHR Site Zone-14 under BallyJagacha Surface Based W/S scheme (Phase-I) under Howrah Division P.H.E Dte. |  |  | ORD/000191/2022-2023 | 1596/HD | 01/08/2022 | 30 | MUNSHI ENTERPRISE | 32.38 | 0 | 30
1145 | Howrah Division |  | Work Order for Sinking of 2 (two) nos PVC big dia Tube well 300 mm x 200 mm dia of 240 mtr deep near i)Chamrail OHR Site Zone-13 & ii) Bally Jagacha Block Office OHR Site Zone-12 under Bally-Jagacha Surface Based W/S scheme(Phase-I) under Howrah Division P.H.E Dte. |  |  | ORD/000192/2022-2023 | 1597/HD | 01/08/2022 | 30 | MUNSHI ENTERPRISE | 32.38 | 0 | 0
1146 | Howrah Division |  | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bally Jagacha & Panchla Block) |  |  | ORD/000220/2025-2026 | 4118/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0
1147 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/10/2024 to 31/12/2024) under Howrah Division, PHE Dte. |  |  | ORD/000225/2024-2025 | 4365/HD | 30/09/2024 | 92 | MD KADIR | 1 | 0 | 0
1148 | Howrah Division |  | Development of Road at Pakuria OHR in Zone-VI under Bally Jagacha (PH-II) Surface water supply scheme under Howrah Division, PHE Dte. |  |  | ORD/000228/2023-2024 | 2818/HD | 03/08/2023 | 15 | M/S HOWRAH CONSTRUCTION | 0.88 | 0 | 100
1149 | Howrah Division |  | Land Development for Approach to OHR Site at Narna Zone-V of Surface water supply scheme Bally Jagacha (Phase-II) under Howrah Division, PHE Dte. |  |  | ORD/000229/2023-2024 | 2819/HD | 03/08/2023 | 15 | GUPTA ENTERPRISE | 0.79 | 0 | 100
1150 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for two months from 01/09/2023 to 31/10/2023) under Howrah Division, PHE Dte.. |  |  | ORD/000231/2023-2024 | 3134/HD | 29/08/2023 | 61 | INDRAJIT GHOSAL | 0.8 | 0 | 30
1151 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface Water Based Project for Bally-Jagacha block under Howrah Division, PHE Dte (Chakpara, G.P. Area) Zone-10 Length=900.00mtr. |  |  | ORD/000288/2021-2022 | 2272/HD | 10/12/2021 | 30 | USHA CONCERN | 4.13 | 0 | 0
1152 | Howrah Division |  | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. |  |  | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
1153 | Howrah Division |  | Working area Development for Administrative Building (At Salap Zone-VII) for Surface Water Based Water Supply Scheme Bally Jagacha (Phase-II) under Howrah Division, PHE Dte. |  |  | ORD/000292/2021-2022 | 2276/HD | 10/12/2021 | 21 | KRISHNA CONSTRUCTION | 3.14 | 0 | 0
1154 | Howrah Division |  | Continuation Order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme Government of West Bengal (for two months from 01/11/2023 to 31/12/2023) under Howrah Division, PHE Dte.. |  |  | ORD/000296/2023-2024 | 3902/HD | 30/10/2023 | 61 | INDRAJIT GHOSAL | 0.8 | 0 | 50
1155 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte.(Part-A) No. of House Hold= 110 nos. |  |  | ORD/000313/2021-2022 | 2280/HD | 10/12/2021 | 30 | N. G ENGINEERING | 4.76 | 0 | 0
1156 | Howrah Division |  | Laying of Distribution system at uncovered areas of Pipli & Gayespur mouza under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. |  |  | ORD/000313/2023-2024 | 4363/HD | 05/12/2023 | 135 | SAIKAT ENTERPRISE | 14.52 | 0 | 100
1157 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold= 110 nos. |  |  | ORD/000314/2021-2022 | 2281/HD | 10/12/2021 | 30 | M/S ASHIRBAD (INDIA) | 4.76 | 0 | 0
1158 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold= 110 nos. |  |  | ORD/000315/2021-2022 | 2282/HD | 10/12/2021 | 30 | S.B. ENTERPRISE | 4.74 | 0 | 0
1159 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold= 110 nos. |  |  | ORD/000316/2021-2022 | 2283/HD | 10/12/2021 | 30 | APEX ENGINEERING | 4.74 | 0 | 0
1160 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-E) No. of House Hold= 110 nos. |  |  | ORD/000317/2021-2022 | 2284/HD | 10/12/2021 | 30 | DEBABRATA CHAKRABORTY | 4.74 | 0 | 0
1161 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold= 110 nos. |  |  | ORD/000318/2021-2022 | 2285/HD | 10/12/2021 | 30 | SUNIL ENTERPRISE | 4.74 | 0 | 0
1162 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Chamrail Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. (Part-G) No. of House Hold= 110 nos. |  |  | ORD/000319/2021-2022 | 2286/HD | 10/12/2021 | 30 | GHOSH ENTERPRISE. | 4.78 | 0 | 0
1163 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/11/2024 to 31/01/2025) under Howrah Division, PHE Dte. |  |  | ORD/000319/2024-2025 | 4627/HD | 30/10/2024 | 92 | SUMANTA DEY | 1 | 0 | 0
1164 | Howrah Division |  | Laying of Distribution system at uncovered areas of Daffarpur mouza(part no-18/19) under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. |  |  | ORD/000321/2023-2024 | 4437/HD | 08/12/2023 | 30 | USHA CONCERN | 12.51 | 0 | 100
1165 | Howrah Division |  | Laying of Distribution system at Narna mouza under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. |  |  | ORD/000329/2023-2024 | 4468/HD | 12/12/2023 | 30 | PBA INFRASTRUCTURE | 11.44 | 0 | 100
1166 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/12/2024 to 31/01/2025) |  |  | ORD/000337/2024-2025 | 4960/HD | 29/11/2024 | 62 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1167 | Howrah Division |  | Laying of Distribution system for uncovered areas at Boluhati mouza(Booth no-7,8,9), under Bally Jagacha (Ph-II) Surface based Water Supply Scheme at Domjur Block under Howrah Division, P.H.E. Dte. |  |  | ORD/000341/2023-2024 | 4577/HD | 18/12/2023 | 30 | CONSTRUCTION CORNER | 10.25 | 0 | 0
1168 | Howrah Division |  | Construction of Chlorination Room (5.5m x 4.5m) at Narna Zone-V OHR Site under Bally Jagacha(Phase-2) Surface Based water supply project under Howrah Division, P.H.E. Dte. |  |  | ORD/000349/2024-2025 | 4833/HD | 20/11/2024 | 45 | GUPTA ENTERPRISE | 4.85 | 0 | 0
1169 | Howrah Division |  | Construction of Guard Room with WC (4.35m X 3.60m) at Narna Zone-V OHR Site under Bally Jagacha(Ph-II) Surface Based water supply project under Howrah Division, P.H.E. Dte. |  |  | ORD/000350/2024-2025 | 4834/HD | 20/11/2024 | 45 | GUPTA ENTERPRISE | 4.85 | 0 | 0
1170 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Jagadispur Gram panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No of House hold-1600 Nos |  |  | ORD/000351/2021-2022 | 2429/HD | 29/12/2021 | 45 | N. G ENGINEERING | 54.6 | 0 | 0
1171 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/01/2025 to 31/03/2025) under Howrah Division, PHE Dte. |  |  | ORD/000355/2024-2025 | 5417/HD | 30/12/2024 | 90 | MD KADIR | 1 | 0 | 0
1172 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Nischinda Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-A) No of Household (Approx)= 4500 nos |  |  | ORD/000357/2021-2022 | 2384/HD | 27/12/2021 | 30 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 2.24 | 0 | 0
1173 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Sapuipara Basukati Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-B) No of Household (Approx)= 5500 nos |  |  | ORD/000358/2021-2022 | 2385/HD | 27/12/2021 | 30 | JAYANTA KUMAR MONDAL | 2.73 | 0 | 0
1174 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Duegapur-Abhoynagar-I Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-C) No of Household (Approx)= 4000 nos |  |  | ORD/000359/2021-2022 | 2386/HD | 27/12/2021 | 30 | GHOSH CONCERN | 1.98 | 0 | 100
1175 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Duegapur-Abhoynagar-II Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-D) No of Household (Approx)= 4500 nos |  |  | ORD/000360/2021-2022 | 2387/HD | 27/12/2021 | 30 | ALOK ENTERPRISE | 2.24 | 0 | 0
1176 | Howrah Division |  | Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for the period from 01/10/2023 to 30/11/2023) |  |  | ORD/000360/2023-2024 | 3482/HD | 29/09/2023 | 61 | SUMANTA DEY | 0.79 | 0 | 100
1177 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Bally Gram Panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No. of House Hold= 5000 nos. |  |  | ORD/000361/2021-2022 | 57/HD | 10/01/2022 | 150 | N. G ENGINEERING | 167.83 | 0 | 0
1178 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chakpara Anandanagar Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-F) No of Household (Approx)= 5000 nos |  |  | ORD/000362/2021-2022 | 2388/HD | 27/12/2021 | 30 | MAHAVIR PUMPS MFG.PVT.LTD | 2.48 | 0 | 0
1179 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Jagadishpur Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-G) No of Household (Approx)= 3500 nos |  |  | ORD/000363/2021-2022 | 2389/HD | 27/12/2021 | 30 | VISHAL CONSTRUCTION CO. | 1.74 | 0 | 0
1180 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-1) No of Household (Approx)= 850 nos |  |  | ORD/000364/2021-2022 | 2390/HD | 27/12/2021 | 30 | M/S ASHIRBAD (INDIA) | 0.42 | 0 | 0
1181 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-2) No of Household (Approx)= 850 nos |  |  | ORD/000365/2021-2022 | 2391/HD | 27/12/2021 | 30 | S.B. ENTERPRISE | 0.42 | 0 | 0
1182 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/02/2025 to 31/03/2025) |  |  | ORD/000365/2024-2025 | 640/HD | 28/01/2025 | 59 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1183 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-3) No of Household (Approx)= 850 nos |  |  | ORD/000366/2021-2022 | 2392/HD | 27/12/2021 | 30 | N. G ENGINEERING | 0.42 | 0 | 0
1184 | Howrah Division |  | Survey & collection of household details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system at Chamrail Gram Panchayet under Bally Jagacha Block under Howrah Division PHE Dte (Part-4) No of Household (Approx)= 950 nos |  |  | ORD/000367/2021-2022 | 2393/HD | 27/12/2021 | 30 | GHOSH ENTERPRISE. | 0.47 | 0 | 0
1185 | Howrah Division |  | Work Order for Excavation of Pipe Trenches in different location for Testing of Rising main pipe line under Bally Jagacha (PH-I) Water supply Project in Bally Jagacha Block under Howrah Sadar Sub- Division, P.H.E. Dte. |  |  | ORD/000368/2022-2023 | 1869/HD | 12/09/2022 | 10 | S.B. ENTERPRISE | 2.39 | 0 | 0
1186 | Howrah Division |  | Work Order for Restoration of road damaged for providing FHTC Works in Nischinda G.P in Bally Jagacha Block under Howrah Division, PHE Dte. (Part-C) |  |  | ORD/000371/2022-2023 | 1891/HD | 15/09/2022 | 10 | M/S HOWRAH CONSTRUCTION | 4.53 | 0 | 0
1187 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara. G.P Area) Zone-10 Length= 539.00mtr.(PART-C) |  |  | ORD/000377/2020-2021 | 1104/HD | 25/09/2020 | 30 | PRADIP KUMAR JATI | 4.04 | 0 | 0
1188 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(D.A -2. G.P Area) Zone-1. Length= 55.00 mtr. |  |  | ORD/000379/2022-2023 | 1867/H.D | 12/09/2022 | 10 | SKYLINE CONSTRUCTION | 0.48 | 0 | 0
1189 | Howrah Division |  | Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (from 01/01/2024 to 31/03/2024) under Howrah Division, PHE Dte. |  |  | ORD/000412/2023-2024 | 4765/HD | 29/12/2023 | 91 | INDRAJIT GHOSAL | 0.98 | 0 | 50
1190 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for the period from 01/12/2023 to 31/01/2024) |  |  | ORD/000455/2023-2024 | 4303/HD | 30/11/2023 | 62 | SUMANTA DEY | 0.79 | 0 | 100
1191 | Howrah Division |  | Work Order for Construction of MS Pipe Line at Lakshmanpur Boosting Station Site under Bally Jagacha Surface Based Water Supply Project (Phase-II) under Howrah Division, PHE Dte. |  |  | ORD/000466/2021-2022 | 306/HD | 15/02/2022 | 20 | GHOSH ENTERPRISE. | 3.05 | 0 | 0
1192 | Howrah Division |  | Work Order for Detail study of existing Bally Jagacha Surface Based Water Supply Scheme (Phase-1) to develop Innovative Sustainable Solutions which are field relevant and address the challenges faced by the consumer, under Howrah Division, PHE Dte. |  |  | ORD/000480/2022-2023 | 2211/HD | 02/11/2022 | 90 | AJIVAM WATER PRIVATE | 34.09 | 0 | 100
1193 | Howrah Division |  | Work Order for Withdrawing & relaying in the damaged part of pipeline for extension of Saorapotakhal(From Anandanagar sitala tala to Jhautala more) at Chakpara Anandanagar G.P. areas of Surface water based water supply project for Bally-Jagacha block,(Phase-1) under Howrah Division PHE Dte. Zone-9( N.P-197 to 15) Length= 1600.00mtr. |  |  | ORD/000481/2021-2022 | 476/HD | 04/03/2022 | 45 | S.B. ENTERPRISE | 15.39 | 0 | 0
1194 | Howrah Division |  | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-I of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1300 m) (Part-6) |  |  | ORD/000515/2020-2021 | 334/HD | 05/02/2021 | 10 | SK ENTERPRISE | 4.26 | 0 | 0
1195 | Howrah Division |  | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-II of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1300 Mtr) (Part-3) |  |  | ORD/000522/2020-2021 | 341/HD | 05/02/2021 | 10 | SK ENTERPRISE | 4.21 | 0 | 0
1196 | Howrah Division |  | Cutting of concrete road with restoration of concrete road for laying of UPVC Pipe (90 mm dia) Zone-II of surface water based water supply Project (Phase-II) for Bally Jagacha Block under Howrah Division PHE Dte. (Length of Road = 1250Mtr) (Part-4) |  |  | ORD/000523/2020-2021 | 342/HD | 05/02/2021 | 10 | SK ENTERPRISE | 4.05 | 0 | 0
1197 | Howrah Division |  | Work Order for Supply of Materials at Lakshmanpur Boosting Station Site under Bally Jagacha Surface based water supply project (Phase-II) under Howrah Division, PHE Dte. |  |  | ORD/000547/2021-2022 | 698/HD | 24/03/2022 | 15 | SK ENTERPRISE | 1.69 | 0 | 0
1198 | Howrah Division |  | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Bally Jagacha Block of Howrah Sadar Sub Division under Howrah Division PHE Dte. |  |  | ORD/000551/2023-2024 | 845/HD | 22/02/2024 | 15 | M&M GRAPHICS | 2.04 | 0 | 100
1199 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 440.00mtr.(PART-5)(Near Chakpara Market & Khal par) |  |  | ORD/000552/2021-2022 | 652/HD | 23/03/2022 | 30 | BISWAJIT SAMANTA | 2.49 | 0 | 0
1200 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 809.00mtr.(PART-1)(Near Burma colony) |  |  | ORD/000553/2021-2022 | 653/HD | 23/03/2022 | 30 | PRADIP KUMAR JATI | 3.05 | 0 | 0
1201 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 792.00mtr.(PART-2)(Near Chakpara Milony club) |  |  | ORD/000554/2021-2022 | 654/HD | 23/03/2022 | 30 | PRADIP KUMAR JATI | 3.18 | 0 | 0
1202 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 796.00mtr.(PART-3)(Near Anandanagar khal par) |  |  | ORD/000555/2021-2022 | 655/HD | 23/03/2022 | 30 | MAA TARA CONSTRUCTION | 3.15 | 0 | 0
1203 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chakpara Anandanagar G.P Area) Zone-9/10 Length= 913.00mtr. (PART-4) |  |  | ORD/000556/2021-2022 | 656/HD | 23/03/2022 | 30 | MAA TARA CONSTRUCTION | 2.94 | 0 | 0
1204 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A & 7 Length= 715.00mtr.(PART-3)(Location Bally near 7no pole) |  |  | ORD/000557/2021-2022 | 657/HD | 23/03/2022 | 30 | SAIKAT ENTERPRISE | 3.32 | 0 | 0
1205 | Howrah Division |  | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. (Part-A) |  |  | ORD/000558/2020-2021 | 415/HD | 11/02/2021 | 15 | MA TARA CONSTRUCTION | 4.68 | 2.42 | 0
1206 | Howrah Division |  | Work Order for Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A & 7 Length= 385.00mtr.(PART-4)(Location Bally Ghosh para) |  |  | ORD/000558/2021-2022 | 658/HD | 23/03/2022 | 30 | SAIKAT ENTERPRISE | 2.08 | 0 | 0
1207 | Howrah Division |  | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. (Part-B) |  |  | ORD/000559/2020-2021 | 416/HD | 11/02/2021 | 15 | GHOSH ENTERPRISE. | 4.5 | 2.64 | 0
1208 | Howrah Division |  | Supply of different types of Specials for conveyance of Treated Water from Off Take Point (Phase-I) to GLR (Phase-II) and LDS at Zone-1&2 under Bally-Jagacha (Phase-II) Surface based water supply Project under Howrah Division PHE Dte. |  |  | ORD/000561/2020-2021 | 418/HD | 11/02/2021 | 15 | GHOSH ENTERPRISE. | 1.16 | 0 | 0
1209 | Howrah Division |  | Barbed wire fencing with angle for Boundary wall & 450mm dia Sluice valve chamber at Lakhanpur CWR site & Raghabpur site of Bally jagacha (phase-II) Surface based water supply scheme under Howrah Division P.H.E. Dte. |  |  | ORD/000570/2020-2021 | 541/HD | 25/02/2021 | 30 | SK ENTERPRISE | 3.56 | 0 | 0
1210 | Howrah Division |  | Work Order for Measuring water flow of pipe under the ground level by portable flow meter (Endress & Hauser make) after thorough cleaning the outer surface of the pipe line and installing the measuring device as per manufacturer¿s procedure including mobilization of portable flow meter by hired vehicle at point to point engaging skilled technician and labours for pipe line size up to 400mm diameter. |  |  | ORD/000573/2022-2023 | 2009/HD | 27/09/2022 | 15 | EASTERN INDIA SALES & SERVICE | 1.26 | 0 | 0
1211 | Howrah Division |  | Work Order for Measuring water flow of pipe under the ground level by portable flow meter (Endress & Hauser make) after thorough cleaning the outer surface of the pipe line and installing the measuring device as per manufacturer¿s procedure including mobilization of portable flow meter by hired vehicle at point to point engaging skilled technician and labours for pipe line size up to 450mm to 900mm diameter. |  |  | ORD/000574/2022-2023 | 2054/HD | 28/09/2022 | 15 | EASTERN INDIA SALES & SERVICE | 0.28 | 0 | 0
1212 | Howrah Division |  | Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/02/2024 to 30/04/2024).¿ under Howrah Division, PHE Dte. |  |  | ORD/000597/2023-2024 | 421/HD | 31/01/2024 | 90 | SUMANTA DEY | 1 | 0 | 20
1213 | Howrah Division |  | Laying Distribution Pipeline For Uncovered area at Lakshmanpur (Zone-I) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. |  |  | ORD/000621/2023-2024 | 1154/HD | 07/03/2024 | 226 | SAIKAT ENTERPRISE | 31.53 | 0 | 100
1214 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 660.00mtr.(PART-4) |  |  | ORD/000654/2020-2021 | 513/HD | 25/02/2021 | 30 | MENOKA ENGINEERING WORKS | 3.65 | 0 | 0
1215 | Howrah Division |  | Laying Distribution Pipeline For Uncovered area at Jotgiri (Zone-I) of Bally-Jagaccha Surface based Water Supply Scheme (Phase-II) under Howrah Division PHE Dte. |  |  | ORD/000654/2023-2024 | 1244/HD | 12/03/2024 | 450 | COSMO ENTERPRISE | 28.36 | 0 | 100
1216 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 649.00mtr.(PART-5) |  |  | ORD/000655/2020-2021 | 514/HD | 25/02/2021 | 30 | MENOKA ENGINEERING WORKS | 3.51 | 0 | 0
1217 | Howrah Division |  | Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/02/2024 to 31/03/2024) |  |  | ORD/000655/2023-2024 | 420/HD | 31/01/2024 | 60 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1218 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 732.00mtr.(PART-6) |  |  | ORD/000656/2020-2021 | 515/HD | 25/02/2021 | 30 | MENOKA ENGINEERING WORKS | 4.22 | 0 | 0
1219 | Howrah Division |  | Restoration of damaged concrete roads due to laying of pipe line at Salap 1 & 2 GP of Bally-Jagacha surface based water supply scheme Phase-II under Howrah Division PHE Dte. (Part-B). |  |  | ORD/000665/2023-2024 | 1316/HD | 14/03/2024 | 60 | BISWAJIT SAMANTA | 11.22 | 0 | 100
1220 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer (HQ), Howrah Division, PHE Dte. Government of West Bengal (for three months from 01/02/2025 to 30/04/2025) under Howrah Division, PHE Dte. |  |  | ORD/000707/2024-2025 | 699/HD | 30/01/2025 | 90 | SUMANTA DEY | 0.99 | 0 | 0
1221 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/04/2024 to 31/05/2024) |  |  | ORD/000724/2023-2024 | 1672/HD | 28/03/2024 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1222 | Howrah Division |  | Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/04/2024 to 30/06/2024) under Howrah Division, PHE Dte. |  |  | ORD/000725/2023-2024 | 1363/HD | 15/03/2024 | 91 | MD KADIR | 0.99 | 0 | 0
1223 | Howrah Division |  | Work Order for Interconnection from Existing Tube well to Distribution line at Baigachi (Zone-14) in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. |  |  | ORD/000726/2022-2023 | 516/HD | 09/02/2023 | 30 | SUNIL ENTERPRISE | 2.71 | 0 | 100
1224 | Howrah Division |  | Work Order for Construction of Clorination Room ( 5.40m x 3.60 m) at Bhaskur Zone-III OHR Site under Bally jagacha(phase-2) surface Based water supply project under Howrah Division, P.H.E. Dte. at Lakhanpur CWR Site under Bally jagacha(phase-2) surface Based water supply project under Howrah Division, P.H.E. Dte. |  |  | ORD/000728/2022-2023 | 515/HD | 09/02/2023 | 60 | KUNDU CONSTRUCTION | 6.16 | 0 | 100
1225 | Howrah Division |  | Work Order for Construction of Boundary Wall at Tube Well Site of Chakpara Anandanagar Football Ground under Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte.(12M X12M) |  |  | ORD/000732/2022-2023 | 569/HD | 13/02/2023 | 30 | FUTURE CONSTRUCTION | 3.98 | 0 | 0
1226 | Howrah Division |  | Work Order for Construction of Pump House (5.40m x 3.60 m) at Tube Well Site of Chakpara Anandanagar Football Ground under Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. |  |  | ORD/000734/2022-2023 | 571/HD | 13/02/2023 | 60 | MAITY CONSTRUCTIONS | 6.12 | 0 | 100
1227 | Howrah Division |  | Work Order for Interconnection from Tube well to Bally jagacha OHR in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. |  |  | ORD/000735/2022-2023 | 572/HD | 13/02/2023 | 30 | MA-DURGA ENTERPRISE | 1.78 | 0 | 100
1228 | Howrah Division |  | Work Order for Interconnection from Tube well to Distribution line at Chakpara site in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. |  |  | ORD/000736/2022-2023 | 573/HD | 13/02/2023 | 30 | S.B. ENTERPRISE | 1.68 | 0 | 0
1229 | Howrah Division |  | Work Order for Interconnection from Tube well to Jagadispur OHR in Bally Jagacha surface based Water Supply scheme(Phase-1) under Howrah Division, P.H.E. Dte. |  |  | ORD/000737/2022-2023 | 574/HD | 13/02/2023 | 30 | S.B. ENTERPRISE | 2.2 | 0 | 100
1230 | Howrah Division |  | Continuation order for Hiring of 1 (One) no. Diesel cab having contact permit from regional transport authority for office use of the Executive Engineer, Howrah Division, Government of West Bengal (for two months from 01/04/2025 to 31/05/2025) |  |  | ORD/000809/2024-2025 | 1626/HD | 26/03/2025 | 61 | AVINABA ENGINEERING CONCERN | 0.79 | 0 | 0
1231 | Howrah Division |  | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system at uncovered areas of Durgapur Abhoynagar-1 & 2 Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte.(Part-1) |  |  | ORD/000821/2022-2023 | 1050/HD | 15/03/2023 | 90 | M/S SUPROVAT GHOSH | 6.79 | 0 | 100
1232 | Howrah Division |  | Work Order for providing Functional Household Tap Connection(FHTC) from existing distribution system at uncovered areas of Durgapur Abhoynagar-1 & 2 Gram Panchyet under bally Jagachha Block under Howrah Division, PHE Dte.(Part-2) |  |  | ORD/000822/2022-2023 | 1051/HD | 15/03/2023 | 60 | SONAR BANGLA ENTERPRISE | 6.71 | 0 | 70
1233 | Howrah Division |  | Continuation order for Hiring of 1(One) no. Inspection vehicle (BS-III/IV) (Commercial) car under the disposal of the Assistant Engineer for Bally-Jagacha Surface Based Piped Water Supply Scheme. Government of West Bengal (for three months from 01/04/2025 to 30/06/2025) under Howrah Division, PHE Dte. |  |  | ORD/000897/2024-2025 | 1627/HD | 26/03/2025 | 91 | MD KADIR | 1 | 0 | 0
1234 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 3594/HD | 13/08/2024 | 0 | Resource Division | 5.64 | 0 | 0
1235 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000013/2021-2022 | 2375/HD | 24/12/2021 | 0 | Resource Division | 16.5 | 0 | 0
1236 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000025/2021-2022 | 435/HD | 28/02/2022 | 0 | Resource Division | 21.45 | 0 | 0
1237 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2113/HD | 09/11/2022 | 0 | Resource Division | 61.6 | 0 | 0
1238 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 134/HD | 10/01/2024 | 0 | Resource Division | 12.94 | 0 | 0
1239 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000098/2023-2024 | 467/HD | 02/02/2024 | 0 | Resource Division | 5.18 | 0 | 0
1240 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 467/HD | 02/02/2024 | 0 | Resource Division | 2.19 | 0 | 0
1241 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 467/HD | 02/02/2024 | 0 | Resource Division | 1.49 | 0 | 0
1242 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000003/2021-2022 | W/104 | 19/07/2021 | 0 | SAIKAT ENTERPRISE | 3.49 | 0 | 0
1243 | Howrah Division |  | LDS in the uncovered araes of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000004/2021-2022 | W/106 | 19/07/2021 | 0 | SAIKAT ENTERPRISE | 3.84 | 0 | 0
1244 | Howrah Division |  | LDS of uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000007/2021-2022 | W/99-103 | 19/07/2021 | 0 | MITHU BUILDERS | 16.75 | 0 | 0
1245 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Scheme Bally Jagacha Block |  |  | VCH/000012/2021-2022 | 107-111 113-117 | 20/07/2021 | 0 | ADITYA HAZRA | 25.5 | 0 | 0
1246 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000013/2021-2022 | W/112 | 20/07/2021 | 0 | UNIVERSAL CONSTRUCTION | 3.89 | 0 | 0
1247 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000014/2021-2022 | W/105 | 19/07/2021 | 0 | S.M. CONSTRUCTION | 3.39 | 0 | 0
1248 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project for Bally Jagacha Block |  |  | VCH/000015/2021-2022 | W/118, 119 | 19/07/2021 | 0 | N. G ENGINEERING | 5.52 | 0 | 0
1249 | Howrah Division |  | LDS in the uncovered area of Surface Water Based Water supply project for Bally Jagacha Block |  |  | VCH/000021/2021-2022 | W/133-136 | 09/08/2021 | 0 | NIRMAL UDYOG | 13.94 | 0 | 0
1250 | Howrah Division |  | LDS Uncovered area Surface Water Based Water supply Project Bally Jagacha Block |  |  | VCH/000027/2021-2022 | W/164 | 09/08/2021 | 0 | PRAGATI CONSTRUCTION & CO | 18.44 | 0 | 0
1251 | Howrah Division |  | LDS Uncovered Bally Jagacha Surface Water Based Water Supply Project Bally Jagacha block |  |  | VCH/000035/2021-2022 | W/149-153 | 09/08/2021 | 0 | S.B. ENTERPRISE | 12.29 | 0 | 0
1252 | Howrah Division |  | LDS Uncovered Bally Jagacha |  |  | VCH/000036/2021-2022 |  | 03/06/2021 | 0 | MAA TARA CONSTRUCTION | 16.77 | 0 | 0
1253 | Howrah Division |  | LDS uncovered Bally Jagacha |  |  | VCH/000037/2021-2022 | W/137-142 | 09/08/2021 | 0 | USHA CONCERN | 20.51 | 0 | 0
1254 | Howrah Division |  | Retrofitting Bally Jagacha |  |  | VCH/000052/2021-2022 |  | 28/06/2021 | 0 | S.B. ENTERPRISE | 12.29 | 0 | 0
1255 | Howrah Division |  | LDS Uncovered Bally Jagacha |  |  | VCH/000054/2021-2022 | W/143 | 09/08/2021 | 0 | PRADIP KUMAR JATI | 29.38 | 0 | 0
1256 | Howrah Division |  | Uncoverd Bally jagacha |  |  | VCH/000095/2021-2022 | W/250 | 19/08/2021 | 0 | ABONTICA ENTERPRISE | 3.22 | 0 | 0
1257 | Howrah Division |  | Uncovered bally jagcha |  |  | VCH/000096/2021-2022 | W/249 | 19/08/2021 | 0 | ABONTICA ENTERPRISE | 1.94 | 0 | 0
1258 | Howrah Division |  | Uncovered bally jagcha |  |  | VCH/000097/2021-2022 | W/251 | 19/08/2021 | 0 | ABONTICA ENTERPRISE | 1.59 | 0 | 0
1259 | Howrah Division |  | Uncovered bally jagcha |  |  | VCH/000098/2021-2022 | W/252 | 19/08/2021 | 0 | SUSHANTA MONDAL | 1.03 | 0 | 0
1260 | Howrah Division |  | Uncoverd Bally Jagcha |  |  | VCH/000233/2021-2022 | W/228 | 19/08/2021 | 0 | ASHOKE ENGINEERING WORKS | 4.47 | 0 | 0
1261 | Howrah Division |  | Uncoverd Bally Jagcha |  |  | VCH/000234/2021-2022 | W/229-233 | 19/08/2021 | 0 | SUSHANTA MONDAL | 7.82 | 0 | 0
1262 | Howrah Division |  | Uncovered Bally Jagach |  |  | VCH/000235/2021-2022 | W/159-160 | 19/08/2021 | 0 | MAA TARA CONSTRUCTION | 16.77 | 0 | 0
1263 | Howrah Division |  | LDS in the uncovered areas of Surface Based Water Supply Project Bally Jagach Block |  |  | VCH/000255/2021-2022 | W/400 | 11/10/2021 | 0 | M/S. SREE HARI CONSTRUCTION | 3.33 | 0 | 0
1264 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000256/2021-2022 | BP-2021-22-217 | 11/10/2021 | 0 | N.N. CONSTRUCTION | 3.54 | 0 | 0
1265 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000257/2021-2022 | BP-2021-22-187 | 07/10/2021 | 0 | SAIKAT ENTERPRISE | 4.48 | 0 | 0
1266 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000261/2021-2022 | W/362 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.8 | 0 | 0
1267 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000262/2021-2022 | W/363 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.37 | 0 | 0
1268 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000263/2021-2022 | W/364 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.83 | 0 | 0
1269 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000264/2021-2022 | W/365 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.78 | 0 | 0
1270 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000265/2021-2022 | W/366 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.81 | 0 | 0
1271 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000266/2021-2022 | BP-2021-22-182 | 07/10/2021 | 0 | GHOSH ENTERPRISE. | 4.14 | 0 | 0
1272 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000267/2021-2022 | W/368 | 07/10/2021 | 0 | MA TARA CONSTRUCTION | 4.81 | 0 | 0
1273 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000268/2021-2022 | W/370 | 07/10/2021 | 0 | MA TARA CONSTRUCTION | 4.66 | 0 | 0
1274 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000269/2021-2022 | BP-2021-22-184 | 07/10/2021 | 0 | SK ENTERPRISE | 2.21 | 0 | 0
1275 | Howrah Division |  | LDS in the uncovered areas of Surface Water Based Water Supply Project Bally Jagacha Block |  |  | VCH/000270/2021-2022 | BP-2021-22-186 | 07/10/2021 | 0 | SK ENTERPRISE | 4.84 | 0 | 0
1276 | Howrah Division |  | Special repairing works in different location( at Lock down period) in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Bally G.P Area) Zone-6A, 6B.Length=66m. |  |  | VCH/000289/2022-2023 | BP-2022-23-31 | 11/05/2022 | 0 | CONSCORP | 0.48 | 0 | 0
1277 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyetunder Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. |  |  | VCH/000293/2022-2023 | BP-2022-23-28 | 11/05/2022 | 0 | JAYANTA KUMAR MONDAL | 2.73 | 0 | 0
1278 | Howrah Division |  | Railway permission |  |  | VCH/000419/2022-2023 | BP-2022-23-84 | 23/06/2022 | 0 | EASTERN RAILWAY, HOWRAH DIVISION | 9.05 | 0 | 0
1279 | Howrah Division |  | Indent of materials |  |  | VCH/000594/2021-2022 | BP-2021-22-309 | 02/02/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 36.59 | 0 | 0
1280 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. |  |  | VCH/000791/2021-2022 | BP-2021-22-323 | 18/02/2022 | 0 | GHOSH CONCERN | 116.13 | 0 | 0
1281 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 743.00mtr.(PART-3) |  |  | VCH/000804/2021-2022 | BP-2021-22-344 | 28/02/2022 | 0 | N. G ENGINEERING | 3.23 | 0 | 0
1282 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 737.00mtr.(PART-2) |  |  | VCH/000805/2021-2022 | BP-2021-22-345 | 28/02/2022 | 0 | N. G ENGINEERING | 3.26 | 0 | 0
1283 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-1) No. of House Hold= 850 nos. |  |  | VCH/000807/2021-2022 | BP-2021-22-348 | 28/02/2022 | 0 | MENOKA ENGINEERING WORKS | 34.94 | 0 | 0
1284 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 743.00mtr.(PART-8) |  |  | VCH/000809/2021-2022 | BP-2021-22-342 | 28/02/2022 | 0 | M/S ASHIRBAD (INDIA) | 3.21 | 0 | 0
1285 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 738.00mtr.(PART-9) |  |  | VCH/000810/2021-2022 | BP-2021-22-341 | 28/02/2022 | 0 | M/S ASHIRBAD (INDIA) | 3.52 | 0 | 0
1286 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-4) No. of House Hold= 950 nos. |  |  | VCH/000811/2021-2022 | BP-2021-22-351 | 28/02/2022 | 0 | GHOSH ENTERPRISE. | 13.09 | 0 | 0
1287 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-3) No. of House Hold= 850 nos |  |  | VCH/000822/2021-2022 | BP-2021-22-349 | 28/02/2022 | 0 | N. G ENGINEERING | 34.98 | 0 | 0
1288 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-2. Grampanchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-D) No. of House Hold(Approx)= 4500 nos |  |  | VCH/000823/2021-2022 | BP-2021-22-350 | 28/02/2022 | 0 | ALOK ENTERPRISE | 76.01 | 0 | 0
1289 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Nischinda Gram panchyet under BallyJagachha Block under Howrah Division, PHE Dte. (Part-A) No. of House Hold(Approx)=4500 nos. |  |  | VCH/000824/2021-2022 | BP-2021-22-360 | 28/02/2022 | 0 | JDJ ENTERPRISE (A UNIT OF JDJ TRADERS PRIVATE LIMITED) | 104.97 | 0 | 0
1290 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chamrail Gram panchyet under ballyjagachha Block under Howrah Division, PHE Dte. (Part-2) No. of House Hold= 850 nos. |  |  | VCH/000830/2021-2022 | BP-2021-22-347 | 28/02/2022 | 0 | M/S ASHIRBAD (INDIA) | 34.95 | 0 | 0
1291 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Sapuipara Basukati Gram panchyetunder Bally Jagachha Block under Howrah Division, PHE Dte. (Part-B) No. of House Hold(Approx)= 5500 nos. |  |  | VCH/000906/2021-2022 | W/796 | 03/03/2022 | 0 | JAYANTA KUMAR MONDAL | 24.79 | 0 | 0
1292 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chakpara Gram panchyet under BallyJagachha Block under Howrah Division, PHE Dte. (Part-F) No. of House Hold(Approx)=5000 nos. |  |  | VCH/000909/2021-2022 | BP-2021-22-485 | 30/03/2022 | 0 | MAHAVIR PUMPS MFG.PVT.LTD | 10.99 | 0 | 0
1293 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Chamrail G.P Area) Zone-12 &13 Length= 732.00mtr. (PART-1) |  |  | VCH/000925/2021-2022 | BP-2021-22-346 | 03/03/2022 | 0 | N. G ENGINEERING | 3.43 | 0 | 0
1294 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara G.P Area) Zone-7/8 Length= 1100.00mtr.(PART-2) |  |  | VCH/000942/2021-2022 | BP-2021-22-456 | 26/03/2022 | 0 | CHOWDHUARY & CO | 3.48 | 0 | 0
1295 | Howrah Division |  | Laying distribution system in the uncovered areas of Surface water based water supply project for Bally-Jagacha block, under Howrah Division PHE Dte.(Sapuipara G.P Area) Zone-7/8 Length= 1100.00mtr.(PART-1) |  |  | VCH/000951/2021-2022 | BP-2021-22-455 | 26/03/2022 | 0 | CHOWDHUARY & CO | 3.51 | 0 | 0
1296 | Howrah Division |  | Providing Functional Household Tap Connection(FHTC) from existing distribution system at Durgapur Abhoy Nagar-1. Gram panchyet under bally jagachha Block under Howrah Division, PHE Dte. (Part-C) No. of House Hold(Approx)= 4000 nos. |  |  | VCH/000978/2021-2022 | BP-2021-22-419 | 21/03/2022 | 0 | GHOSH CONCERN | 39.01 | 0 | 0
1297 | Howrah Division |  | Providing Functional Household Tap Connection (FHTC) from existing distribution system at Bally Gram Panchyet under Bally Jagachha Block under Howrah Division, PHE Dte. No. of House Hold= 5000 nos. |  |  | VCH/001009/2021-2022 | BP-2021-22-478 | 27/03/2022 | 0 | N. G ENGINEERING | 96.53 | 0 | 0
1298 | Howrah Division | Ulberia Sub-Division | Construction of 450 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation), pipe connection, Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC) for HATURIA KANDARPUR PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Haturia Kandarpur (Jl-49) & Khanpur (Jl-50)) [No. of FHTC = 2433] | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000194/2023-2024 | 3197/HD | 04/09/2023 | 880 | B.M. ENTERPRISE | 481.61 | 0 | 65
1299 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
1300 | Howrah Division | Ulberia Sub-Division | Additional Laying Distribution system (HDPE & DI) & providing Functional Household Tap connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000312/2023-2024 | 4341/HD | 04/12/2023 | 60 | MAA TARA CONSTRUCTION | 18.77 | 0 | 100
1301 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza- JOTE BIRESWAR(Jl-51) (Part-C) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000414/2022-2023 | 2057/HD | 29/09/2022 | 812 | NIRMAL UDYOG | 74.66 | 0 | 100
1302 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Natibpur (Jl-52) (Part-D) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000415/2022-2023 | 2058/HD | 29/09/2022 | 45 | MAA TARA CONSTRUCTION | 61.1 | 0 | 100
1303 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of Haturia Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Singara (Jl-53) (Part-E) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000416/2022-2023 | 2059/HD | 29/09/2022 | 45 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 39.47 | 0 | 100
1304 | Howrah Division | Ulberia Sub-Division | Work Order for Interconnection for 2nd TW and 1st Tube well (HW site) at Haturia Kandarpopur Piped Water Supply scheme in Bagnan-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000417/2022-2023 | 2060/HD | 29/09/2022 | 30 | ASHOKE ENGINEERING WORKS | 15.63 | 0 | 95
1305 | Howrah Division | Ulberia Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Haturie Kandarpur PWSS, Bagnan-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000447/2021-2022 | 248/HD | 07/02/2022 | 15 | STEELCONC AND ASSOCIATES | 3.61 | 0 | 0
1306 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Haturia Kandarpur PWSS of Bagnan-I Block Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000602/2022-2023 | 2718/HD | 14/12/2022 | 60 | LOKENATH ENTERPRISES | 54.06 | 0 | 100
1307 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Additional Distribution System(HDPE & DI) & providing Functional Household Tap Connections (FHTC) of Haturia Kandarpur PWSS within Mouza-Singara(53) of Haturia-I GP under Bagnan-I block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000820/2022-2023 | 1049/HD | 15/03/2023 | 90 | SADHURHAT CO OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 11.44 | 0 | 100
1308 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000823/2022-2023 | 1052/HD | 15/03/2023 | 90 | M/S M.R ENTERPRISE | 7.14 | 0 | 100
1309 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000826/2022-2023 | 1055/HD | 15/03/2023 | 90 | SR TRADING CORPORATION | 7.18 | 0 | 100
1310 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 3rd TW site at Haturie Kandarpur PWSS of Bagnan-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000828/2022-2023 | 1057/HD | 15/03/2023 | 90 | MARUTI CONSTRUCTION | 7.19 | 0 | 100
1311 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000023/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 45.57 | 0 | 0
1312 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000046/2022-2023 | 2639/HD | 09/12/2022 | 0 | Resource Division | 46.12 | 0 | 0
1313 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000085/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 10.47 | 0 | 0
1314 | Howrah Division | Howrah Sadar Sub-Division | Shifting of LT Cable from transformer to Makardaha pwss P.H.No.-I, on full deposite scheme , Dist.-Howrah under PHE Dte. Application No- 100000106104 Reference ID- 860298084 SM Code- 11159 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00106/2024-2025 | BP-2024-25-46 | 07/05/2024 | 0 | WBSEDCL | 20.94 | 0 | 0
1315 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave facility charges | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00114/2024-2025 | BP-2024-25-56 | 10/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 8.04 | 0 | 0
1316 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave Plan & Survey charges | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00159/2024-2025 | BP-2024-25-98 | 28/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0
1317 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave facility charges | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00276/2024-2025 | BP-2024-25-154 | 08/07/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.01 | 0 | 0
1318 | Howrah Division | Howrah Sadar Sub-Division | Augmentation of Makardaha | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/00278/2022-2023 | BP-2022-23-534 | 09/03/2023 | 0 | WBSEDCL | 0.66 | 0 | 0
1319 | Howrah Division | Howrah Sadar Sub-Division | Payment for Way Leave Plan and Survey Charges Makardaha PWSS | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | BILL/01654/2023-2024 | BP-2023-24-737 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.14 | 0 | 0
1320 | Howrah Division | Howrah Sadar Sub-Division | Emergency Restoration of damaged concrete road due to laying of pipe line at Ankurhati stadium of Makardaha PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000031/2024-2025 | 639/HSSD | 25/06/2024 | 30 | UNIVERSAL CORPORATION | 2.16 | 0 | 100
1321 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Land Development work at Makardaha Head Work Site For Makardaha PWSS under Howrah Divnision PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000066/2023-2024 | 1927/HD | 10/05/2023 | 60 | NATURAL RESOURCES CONSORTIUM | 2.97 | 0 | 100
1322 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Makardah PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000230/2022-2023 | 83/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 4.15 | 0 | 0
1323 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
1324 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Makardha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000399/2022-2023 | 1999/HD | 26/09/2022 | 40 | M/S SYCHROTECH INDUSTRY | 26.39 | 0 | 100
1325 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 3 (Three) Nos. of Pump House for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000403/2022-2023 | 1990/HD | 26/09/2022 | 45 | S.B. ENTERPRISE | 17.72 | 0 | 100
1326 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 3 (three) nos of Boundary Wall for Augmentation of Makardah PWSS at Domjur Block under Howrah Division PHE Dte | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000404/2022-2023 | 1991/HD | 26/09/2022 | 796 | JOY GURU TRADING | 17.93 | 0 | 60
1327 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying of Distribution Pipeline (Node No. 663 To 944) & FHTC work [Mouza: Ankurhati (CT) : PART-3] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division, P. H. E. Dte. (Part-7) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000427/2022-2023 | 2100/HD | 12/10/2022 | 813 | UNIVERSAL CORPORATION | 153.73 | 0 | 15
1328 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 450 cum Capacity OHR, Rising Main Pipe line, Laying of Distribution Pipeline (Node No. R-1 To 231) & FHTC work [Mouza: Makardah (CT)] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division, P. H. E. Dte. (Part-3) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000431/2022-2023 | 2099/HD | 12/10/2022 | 964 | NATURAL RESOURCES CONSORTIUM | 349.1 | 0 | 50
1329 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution System Pipeleine (Node No. 358 to 502 & 545) & FHTC work [Mouza: Ankurhati (CT) : PART-1] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000510/2022-2023 | 2319/HD | 11/11/2022 | 30 | MENOKA ENGINEERING WORKS | 82.16 | 0 | 70
1330 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution System Pipeleine (Node No. 503 to 662 & 669) & FHTC work [Mouza: Ankurhati (CT) : PART-2] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000511/2022-2023 | 2382/HD | 18/11/2022 | 30 | ANUSKA ENTERPRISE | 86.39 | 0 | 90
1331 | Howrah Division | Howrah Sadar Sub-Division | Sinking of 01 (One) No. 250 X 150 mm Dia and 240 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Makardha PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000545/2023-2024 | 805/HD | 20/02/2024 | 30 | AUXILIARY TUBEWELL DRILLERS | 14.12 | 0 | 100
1332 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution System Pipeleine (Node No. 232 to 357) & FHTC work [Mouza: Jhaluarber] for Augmentation of Makardah PWSS at Domjur Block under Howrah Division P.H.E Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000631/2022-2023 | 2991/HD | 29/12/2022 | 30 | QUICK CONCRETE PROJECT | 66.11 | 0 | 95
1333 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000057/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 20.31 | 0 | 0
1334 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000089/2022-2023 | 593/HD | 13/02/2023 | 0 | Resource Division | 53.91 | 0 | 0
1335 | Howrah Division | RWS Howrah Sub-Division | Work Order for Raising main & Inter Connection with both tube wells of Kumirmora PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000102/2023-2024 | 1922/HD | 08/05/2023 | 566 | LOKENATH ENTERPRISES | 5.34 | 0 | 70
1336 | Howrah Division | RWS Howrah Sub-Division | Additional Laying of Distribution Pipe Lines and Providing Functional Household Tap Connection(FHTC) for leftout area of KUMIRMORA Piped Water Supply Scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000248/2024-2025 | 4723/HD | 12/11/2024 | 217 | MISHRA ENTERPRISE | 48.16 | 0 | 85
1337 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
1338 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-C) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000401/2022-2023 | 1989/HD | 26/09/2022 | 871 | FARID UDDIN AHMED | 93.98 | 0 | 5
1339 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works and Providing Functional Household Tap Connection(FHTC) for Kumirmora Water Supply Scheme In Udaynarayanpur Block under Howrah Division, PHE Dte. (Part-B) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000402/2022-2023 | 1988/HD | 26/09/2022 | 45 | TANMOY ROY CHOUDHURY | 88.86 | 0 | 60
1340 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for piped water supply scheme of Kumirmora PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000454/2021-2022 | 255/HD | 07/02/2022 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.61 | 0 | 0
1341 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (including pile foundation) along with part Laying of Distribution and Providing Functional Household Tap Connection(FHTC)for Kumirmora Piped Water Supply scheme of Udayanarayanpur Block under Howrah Division P.H.E. Dte. in the District of Howrah. (Part-A) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000477/2022-2023 | 2164/HD | 21/10/2022 | 810 | PRAVAT SARKAR | 194.98 | 0 | 60
1342 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Kumirmora PWSS of Udaynarayanpur Block of Howrah RWS Sub- Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000559/2022-2023 | 2489/HD | 30/11/2022 | 45 | JYOTY SOLAR POWER | 27.45 | 0 | 0
1343 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000629/2022-2023 | 2810/HD | 21/12/2022 | 60 | SAMANTA BUILDERS | 8.5 | 0 | 100
1344 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Kumirmora W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000630/2022-2023 | 2807/HD | 21/12/2022 | 60 | CHINMOY SAMANTA | 8.5 | 0 | 100
1345 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000004/2023-2024 | 1552/HD | 05/04/2023 | 0 | Resource Division | 0.69 | 0 | 0
1346 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000008/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 0.32 | 0 | 0
1347 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000031/2023-2024 | 2234/HD | 14/06/2023 | 0 | Resource Division | 10.36 | 0 | 0
1348 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000044/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 9.79 | 0 | 0
1349 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000067/2023-2024 | 30/HD | 03/01/2024 | 0 | Resource Division | 1.75 | 0 | 0
1350 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000072/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 0.69 | 0 | 0
1351 | Howrah Division | RWS Howrah Sub-Division | Additional Laying of Distribution Pipe Lines for leftout area of GOURANGACHAK Piped Water Supply Scheme in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000017/2025-2026 | 1938/HD | 22/04/2025 | 60 | PRADIP KUMAR JATI | 61.73 | 0 | 0
1352 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site and Additional Laying of Distribution Pipe Lines with providing FHTC at GOURANGACHAK Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte.(SM/11573) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000041/2024-2025 | 2884/HD | 25/06/2024 | 479 | PRADIP KUMAR JATI | 149.89 | 0 | 40
1353 | Howrah Division | RWS Howrah Sub-Division | Work Order for Raising main & Inter Connection with both tube wells of Gauranga Chak PWSS In Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000101/2023-2024 | 1921/HD | 08/05/2023 | 30 | SONAR BANGLA ENTERPRISE | 5.19 | 0 | 100
1354 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for new piped water supply scheme of Gourangachak PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000257/2022-2023 | 331/AE/USD | 16/08/2022 | 45 | STEELCONC AND ASSOCIATES | 3.29 | 0 | 0
1355 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
1356 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gaurangachak PWSS of RWS Howrah Sub-Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000557/2022-2023 | 2487/HD | 30/11/2022 | 45 | PRANTIK DRILLING AGENCY | 36.08 | 0 | 0
1357 | Howrah Division | RWS Howrah Sub-Division | Work Order Construction of Pump House ( 5.40m x 3.60 m) with water supply & sanitary arrangement at 2nd TW site Gourangachak W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000621/2022-2023 | 2801/HD | 21/12/2022 | 60 | SAIKAT ENTERPRISE | 7.84 | 0 | 100
1358 | Howrah Division | RWS Howrah Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) with water supply & sanitary arrangement at HW site Gourangachak W/S scheme at Udaynarayanpur Block under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000624/2022-2023 | 2804/HD | 21/12/2022 | 60 | SONAR BANGLA ENTERPRISE | 7.6 | 0 | 100
1359 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000003/2023-2024 | 1552/HD | 05/04/2023 | 0 | Resource Division | 3.11 | 0 | 0
1360 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000007/2024-2025 | 3884/HD | 05/09/2024 | 0 | Resource Division | 3.7 | 0 | 0
1361 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000030/2023-2024 | 2234/HD | 14/06/2023 | 0 | Resource Division | 8.22 | 0 | 0
1362 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000043/2023-2024 | 2830/HD | 04/08/2023 | 0 | Resource Division | 15.87 | 0 | 0
1363 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000066/2023-2024 | 27/HD | 03/01/2024 | 0 | Resource Division | 0.52 | 0 | 0
1364 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000071/2022-2023 | 421/HD | 03/02/2023 | 0 | Resource Division | 2.38 | 0 | 0
1365 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No- PC I/O.H.R/7/2012)with necessary soil investigation with foundation design as per soil test report for Barramnagar Piped Water Supply Scheme in Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000026/2023-2024 | 1691/HD | 20/04/2023 | 1095 | PRADIP KUMAR JATI | 316.16 | 0 | 38
1366 | Howrah Division | Ulberia Sub-Division | Construction of 2nos switch room (5.4x 3.6) at HW & 2nd TW site and boundary wall at HW Site and Interconnection between TW's of Barramnagar PWSS under Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000318/2023-2024 | 4397/HD | 06/12/2023 | 425 | A. R. CONSTRUCTION | 39.66 | 0 | 100
1367 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Barram Nagar PWSS, Uluberia-II Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000362/2022-2023 | 457/AE/USD | 15/09/2022 | 45 | APEX ENGINEERING | 3.29 | 0 | 100
1368 | Howrah Division | Ulberia Sub-Division | Construction of Culvert over the Drainage Chanal at Head Work site of Barramnagar PWSS of Uluberia-II Block under Uluberia Sub Division under Howrah Division PHED. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000730/2024-2025 | 1350/HD | 11/03/2025 | 45 | PRADIP KUMAR JATI | 29.62 | 0 | 0
1369 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000881/2022-2023 | 1195/HD | 23/03/2023 | 847 | ACME CONSTRUCTION | 90.87 | 0 | 85
1370 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000028/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 21.56 | 0 | 0
1371 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000060/2023-2024 | 4695/HD | 26/12/2023 | 0 | Resource Division | 12.29 | 0 | 0
1372 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000095/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 3.14 | 0 | 0
1373 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2nos 250 X 150mm dia Tube Well 230 mtr,Construction of 2nos Pump House cum switch room with sanitary arrangement, Laying Distribution system (LDS) with necessaery inter-connections with OHR and bypass arrangemnet etc. all complete, Functional Household Tap Connection (FHTC) works, Construction of 200 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Drawing No-PC-I/O.H.R/9/2012) with necessary soil investigation with foundation design as per soil test report For SIBPUR PWSS at Udaynarayanpur Block under uluberia Sub Division under Howrah Division, P. H. E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000020/2023-2024 | 1652/HD | 18/04/2023 | 1095 | SANJOY GHOSH | 328.49 | 0 | 55
1374 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site of SHIBPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000044/2024-2025 | 2888/HD | 25/06/2024 | 480 | SANJOY GHOSH | 62.98 | 0 | 22
1375 | Howrah Division | RWS Howrah Sub-Division | Rising Main & Inter Connection with both tube wells of SIBPUR PWSS in Udaynarayanpur Block under Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000076/2024-2025 | 3166/HD | 12/07/2024 | 180 | TIYASA ENTERPRISE | 5.17 | 0 | 100
1376 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
1377 | Howrah Division | RWS Howrah Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Sibpur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000451/2021-2022 | 252/HD | 07/02/2022 | 15 | APEX ENGINEERING | 2.7 | 0 | 100
1378 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000050/2023-2024 | 3217/HD | 05/09/2023 | 0 | Resource Division | 14.7 | 0 | 0
1379 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000109/2023-2024 | 1049/HD | 04/03/2024 | 0 | Resource Division | 0.83 | 0 | 0
1380 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction Of 300 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/11/2012) Including All pipe Connection For Augmentation Of Nimabalia PWSS at Jagatballavpur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000028/2023-2024 | 1697/HD | 21/04/2023 | 900 | RAYCON CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 121.92 | 0 | 10
1381 | Howrah Division | Howrah Sadar Sub-Division | Land Development at OHR site & allied works at Nimabalia PWSS of J.B.Pur Block under Howrah Sadar Sub-Division under Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000033/2024-2025 | 640/HSSD | 25/06/2024 | 30 | TRADE GREEN | 4.8 | 0 | 100
1382 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Culvert & Approach Road at Nimabalia OHR Site under Nimabalia PWSS in J.B Pur Block under Howrah Division PHE Dte. Howrah. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000071/2023-2024 | 1932/HD | 10/05/2023 | 60 | TRADE GREEN | 7.11 | 0 | 100
1383 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Nimabalia PWSS (Mouza-Moulagachhi, Finga Gachhi, Marghurali & Nimabalia) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000074/2022-2023 | 1017/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 3.31 | 0 | 100
1384 | Howrah Division | Howrah Sadar Sub-Division | Construction of 2 Nos. Pump House (5.40m x 3.60 m) at 1st & 2nd Tube Well Sites Construction of Boundary Wall at 1st Tube Well Site, Construction of Boundary Wall at 2nd Tube Well Site, Laying Distribution Pipeline, providing Functional Household Tap Connection(FHTC) & Rising Main Pipeline Work From 2nd Pump House to 1st Pump House & OHR for NIMABALIA PWSS at J.B. PUR Block of Howrah District under Howrah Division, P. H. E. Dte. [No. of FHTC=850] | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000200/2023-2024 | 3257/HD | 11/09/2023 | 180 | GHOSH ENTERPRISE. | 175.9 | 0 | 60
1385 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Jagatballavpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000283/2024-2025 | 4814/HD | 19/11/2024 | 390 | HORIZEN | 10.11 | 0 | 44
1386 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Nimabalia PWSS of Jagatballavpur Block of Howrah Sadar Sub Division Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000695/2022-2023 | 313/HD | 20/01/2023 | 30 | R CONSTRUCTION | 25.64 | 0 | 100
1387 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000071/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 15.21 | 0 | 0
1388 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000078/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 18.43 | 0 | 0
1389 | Howrah Division | Ulberia Sub-Division | Work Order for Renovation of 2nd Pump House along with Land Development work for Khadinan piped water supply scheme of Bagnan-I Block under Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000078/2023-2024 | 1776/HD | 27/04/2023 | 45 | LOKENATH ENTERPRISES | 4.2 | 0 | 100
1390 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir (Drawing No- PC-I/O.H.R/7/2012) including Pipe connection & soil investigation with foundation design as per soil test report for Khadinan PWSS of Bagnan-I Block under Uluberia Sub Division under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000110/2023-2024 | 2074/HD | 24/05/2023 | 1043 | D D CONSTRUCTION | 384.72 | 0 | 65
1391 | Howrah Division | Ulberia Sub-Division | Sinking of 1 (One) No. 250 X 150 mm Dia and 230 m deep Replace HW site tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Khadian PWSS of Bagnan-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000136/2024-2025 | 4062/HD | 18/09/2024 | 75 | LOKENATH ENTERPRISES | 14.58 | 0 | 100
1392 | Howrah Division | Ulberia Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-I Block) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000229/2025-2026 | 4127/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
1393 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Khadinan PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000363/2022-2023 | 458/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 3.16 | 0 | 100
1394 | Howrah Division | Ulberia Sub-Division | Shifting and stacking of serviceable and unserviceable pipes and specials within the campus ofUluberia Sub-Division office campus including construction of wall racks and shelves almirah for keeping the office records in safe position in connection with "Khadinan PWSS" of Bagnan-I Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000649/2023-2024 | 3223/AE/USD | 12/03/2024 | 30 | S R TRADING CORPORATION | 2.16 | 0 | 100
1395 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000020/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 13.49 | 0 | 0
1396 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000087/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 7.95 | 0 | 0
1397 | Howrah Division | Ulberia Sub-Division | Site preparation and partial land Development at HW site of Matinala PWSS of Bagnan-II Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000175/2024-2025 | 797/AE/USD | 09/09/2024 | 30 | ADITYA HAZRA | 4.8 | 0 | 100
1398 | Howrah Division | Ulberia Sub-Division | Construction of switch room ( 3.60 m x 3.0 m) with water supply sanitary arrangement at 2nd tube well site of Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. (As per approved drawing of Howrah Division, PHE Dte.) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000185/2024-2025 | 769/AE/USD | 05/09/2024 | 45 | D.C. CONSTRUCTION | 4.68 | 0 | 100
1399 | Howrah Division | Ulberia Sub-Division | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bagnan-II & Uluberia-II Block) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000222/2025-2026 | 4120/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
1400 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Augmentation of Matinala (Mellock Zone-I) PWSS, Bagnan-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000225/2022-2023 | 317/AE/USD | 16/08/2022 | 45 | MS SOBHA AND CO | 3.61 | 0 | 100
1401 | Howrah Division | Ulberia Sub-Division | Sinking of 5 (Five) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Harop PWSS Zone -I (1 no) & Zone-II (2 nos) & Matinala PWSS (2 nos) of Bagnan-I Block of Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000249/2023-2024 | 3533/HD | 04/10/2023 | 60 | AQUATECH ENGINEERS | 64.95 | 0 | 40
1402 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
1403 | Howrah Division | Ulberia Sub-Division | Balance Laying of distribution pipeline Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Mellock) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000585/2023-2024 | 3104/AE/USD | 29/02/2024 | 45 | BISWAJIT BAG | 13 | 0 | 100
1404 | Howrah Division | Ulberia Sub-Division | Balance Laying of distribution pipeline Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Mouza-Matinala) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000687/2023-2024 | 3242/AE/USD | 12/03/2024 | 45 | SUNIRMAN ENTERPRISE | 11.92 | 0 | 100
1405 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) of MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-C) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000763/2022-2023 | 705/HD | 22/02/2023 | 721 | SUNIRMAN ENTERPRISE | 66.28 | 0 | 90
1406 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-D) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000764/2022-2023 | 706/HD | 22/02/2023 | 781 | USHA CONCERN | 73.23 | 0 | 100
1407 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube well & Construction of 450 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation for MATINALA PWSS OF BAGNAN-II BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. (PART-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000840/2022-2023 | 1141/HD | 21/03/2023 | 720 | ADITYA HAZRA | 218.71 | 0 | 100
1408 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) at Matinala PWSS of Bagnan-II Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000882/2022-2023 | 1436/HD | 29/03/2023 | 120 | BISWAJIT BAG | 163 | 0 | 100
1409 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000024/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 27.35 | 0 | 0
1410 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000048/2023-2024 | 2979/HD | 17/08/2023 | 0 | Resource Division | 26.58 | 0 | 0
1411 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | RTOR000096/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 10.29 | 0 | 0
1412 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Phase-D) | AE/RWS | JE/USD | ORD/000073/2023-2024 | 1934/HD | 10/05/2023 | 45 | S.M. CONSTRUCTION | 4.96 | 0 | 100
1413 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-1) | AE/RWS | JE/USD | ORD/000260/2022-2023 | 344/AE/USD | 22/08/2022 | 45 | SK ENTERPRISE | 4.8 | 0 | 0
1414 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-2) | AE/RWS | JE/USD | ORD/000261/2022-2023 | 345/AE/USD | 22/08/2022 | 45 | SK ENTERPRISE | 4.83 | 0 | 0
1415 | Howrah Division | Ulberia Sub-Division | Additional laying of pipeline for providing Functional Household Tap Connection(FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. (Phase-3) | AE/RWS | JE/USD | ORD/000272/2022-2023 | 354/AE/USD | 22/08/2022 | 45 | SK ENTERPRISE | 3.33 | 0 | 0
1416 | Howrah Division | Ulberia Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2452 nos. | AE/RWS | JE/USD | ORD/000459/2021-2022 | 443/HD | 02/03/2022 | 92 | SAMIRON GHOSH | 126.42 | 0 | 0
1417 | Howrah Division | Ulberia Sub-Division | Work Order for Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system at Chitrasenpur Piped Water Supply Scheme under Udaynarayanpur Block under Howrah Division, PHE Dte. for 2452 nos. | AE/RWS | JE/USD | VCH/000409/2022-2023 | BP-2022-23-100 | 29/06/2022 | 0 | SAMIRON GHOSH | 126.96 | 0 | 0
1418 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
1419 | Howrah Division | Ulberia Sub-Division | Continuation order for r Preparation of DPR for new piped water supply scheme of Ghutegari PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/001022/2022-2023 | 1508/HD | 21/07/2022 | 15 | APEX ENGINEERING | 3.17 | 0 | 0
1420 | Howrah Division |  | Road Restoration work due to road cutting by PHED for laying water pipe line at Howrah Amta Road from 37.40 Km to 41.30 Km under Howrah Division, PWD during the year 2024-2025 |  |  | BILL/00804/2024-2025 | BP-2024-25-479 | 06/11/2024 | 0 | EXECUTIVE ENGINEER HOWRAH DIVISION, PWD. | 11.45 | 0 | 0
1421 | Howrah Division |  | Sinking of 1 (one) No. Additional 250 X 150 mm Dia and 250 m deep Drilling by Direct Rotary method with UPVC Pipes all complete at Debandi PWSS of Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. (Location: Darapur) |  |  | ORD/000130/2025-2026 | 3232/HD | 23/07/2025 | 30 | AUXILIARY TUBEWELL DRILLERS | 15.45 | 0 | 0
1422 | Howrah Division |  | Construction of Boundary Wall (284 m Length), Land development, approach road etc at Head Work Site including alternative laying of DI(K-9) & DI (K-7) pipeline etc of 2nd T.Well & 3rd T.Well site of Debandi W/S scheme at Amta-I Block in Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000131/2025-2026 | 3233/HD | 23/07/2025 | 60 | MAA TARA CONSTRUCTION | 53.51 | 0 | 0
1423 | Howrah Division |  | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC 690 nos) DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-B-Sarpota & Chalunia |  |  | ORD/000165/2023-2024 | 2999/HD | 18/08/2023 | 690 | M/S SARADA UDYOG | 138.83 | 0 | 60
1424 | Howrah Division |  | Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC-1030 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-C-Debandi |  |  | ORD/000175/2023-2024 | 2948/HD | 14/08/2023 | 360 | JOY CHANDI CONSTRUCTION | 166.89 | 0 | 50
1425 | Howrah Division |  | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Debandi PWSS of Amta-I Block Uluberia Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000189/2023-2024 | 3126/HD | 29/08/2023 | 45 | SPG ENTERPRISES | 52.15 | 0 | 100
1426 | Howrah Division |  | Laying Distribution System(HDPE & DI) & Providing Functional Household Tap Connection (FHTC-1450 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-D-Uttar Ramchandrapur & Anule |  |  | ORD/000192/2023-2024 | 3194/HD | 04/09/2023 | 575 | A P POWER & CONCRETE | 182.91 | 0 | 30
1427 | Howrah Division |  | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Amta-I Block) (PART-B) |  |  | ORD/000228/2025-2026 | 4126/HD | 14/10/2025 | 30 | ABONTICA ENTERPRISE | 4.79 | 0 | 0
1428 | Howrah Division |  | Laying Distribution System (HDPE & DI) & providing Functional Household Tap Connection (FHTC-470 nos) FOR DEBANDI PWSS OF AMTA-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. Part-E-Kandua |  |  | ORD/000247/2023-2024 | 3531/HD | 04/10/2023 | 720 | M/S. BHOWMICK ENTERPRISE | 68.87 | 0 | 0
1429 | Howrah Division |  | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. |  |  | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
1430 | Howrah Division |  | Work Order for Preparation of DPR for new piped water supply scheme of Debandi PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000439/2021-2022 | 240/HD | 07/02/2022 | 15 | RADIANT | 4.4 | 0 | 100
1431 | Howrah Division |  | Construction of Kiosk (one no) at Debandi PWSS under uluberia Sub-Division, under Howrah DivisionP.H.E.Dte.(Size in side 3.0x1.8m)at 2nd TW Site at Baneswarpur Mouza. |  |  | ORD/000671/2023-2024 | 3234/AE/USD | 12/03/2024 | 30 | NOBLE ENTERPRISE | 1.13 | 0 | 100
1432 | Howrah Division |  | Construction of Kiosk (one no) at Debandi PWSS under uluberia Sub-Division, under Howrah Division P.H.E.Dte.(Size in side 3.0x1.8m) at 3rd TW Site at Debandi Mouza |  |  | ORD/000690/2023-2024 | 3232/AE/USD | 12/03/2024 | 30 | PRADIP KUMAR HAJRA | 1.13 | 0 | 100
1433 | Howrah Division |  | Construction of Kiosk (one no) at Debandi PWSS underuluberia Sub-Division, under Howrah Division P.H.E Dte.(Size in side 3.0x1.8m) at HW Site at Sarpota Mouza |  |  | ORD/000691/2023-2024 | 3233/AE/USD | 12/03/2024 | 30 | MAA TARA ENTERPRISE | 1.13 | 0 | 100
1434 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 12.87 | 0 | 0
1435 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 447/HD | 01/02/2024 | 0 | Resource Division | 52.51 | 0 | 0
1436 | Howrah Division | RWS Howrah Sub-Division | Construction of Boundary Wall, Construction of Approach Road and Land Development at HEAD WORK Site and 2nd Tube Well Site along with restoration work of damaged pipeline of BEDHICHANDRAPUR Piped Water Supply Scheme at Udaynarayanpur Block Under Howrah Division, P.H.E. Dte. | AE/RWS | JE/BLK/amta2 | ORD/000018/2025-2026 | 1939/HD | 22/04/2025 | 45 | JAHANGIR ALAM | 47.81 | 0 | 0
1437 | Howrah Division | RWS Howrah Sub-Division | Sinking of 2nos 250 X 150mm dia Tube Well 230 mtr,Construction of 2nos Pump House cum switch room with sanitary arrangement, Laying Distribution system (LDS) with necessary inter-connections with OHR and bypass arrangement etc. all complete, Functional Household Tap Connection (FHTC) works, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Drawing No- PC-I/O.H.R/7/2012)with necessary soil investigation with foundation design as per soil test report for BEDHI CHANDRAPUR PWSS at Udaynarayanpur Block under Uluberia Sub-Division under, Howrah Division, P. H. E. Dte. | AE/RWS | JE/BLK/amta2 | ORD/000137/2023-2024 | 2758/HD | 31/07/2023 | 1097 | JAHANGIR ALAM | 335.32 | 0 | 42
1438 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for new piped water supply scheme of Bedhichandrapur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS | JE/BLK/amta2 | ORD/000254/2022-2023 | 328/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 2.81 | 0 | 100
1439 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS | JE/BLK/amta2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
1440 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS | JE/BLK/amta2 | RTOR000049/2023-2024 | 3217/HD | 05/09/2023 | 0 | Resource Division | 16.59 | 0 | 0
1441 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of pipeline for retrofitting work for providing Functional Household Tap Connection(FHTC) at Tajpur Water Supply scheme in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Part-C) (Phase-I) | AE/Ulu | JE/USD | ORD/000054/2022-2023 | 1048/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 4.33 | 0 | 0
1442 | Howrah Division | Ulberia Sub-Division | Work order for interconnection between Replaced new Tube Well and existing OHR at Udong W/s scheme of Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu | JE/USD | ORD/000065/2022-2023 | 1059/HD | 06/05/2022 | 30 | JAHANGIR ALAM | 0.91 | 0 | 0
1443 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) [Tajpur Mouza part] | AE/Ulu | JE/USD | ORD/000267/2020-2021 | 1800/HD | 27/11/2020 | 30 | AYUSH ENTERPRISE | 12.97 | 0 | 0
1444 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | AE/Ulu | JE/USD | VCH/000188/2021-2022 | W/176 | 06/08/2021 | 0 | JAHANGIR ALAM | 29.23 | 0 | 0
1445 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | AE/Ulu | JE/USD | VCH/000640/2021-2022 | 84437 | 04/01/2022 | 0 | JOY CHANDI CONSTRUCTION | 5.88 | 0 | 0
1446 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) | AE/Ulu | JE/USD | VCH/000687/2021-2022 | 844330 | 21/02/2022 | 0 | AYUSH ENTERPRISE | 2.24 | 0 | 0
1447 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | AE/Ulu | JE/USD | VCH/000851/2020-2021 | 844341 | 20/03/2021 | 0 | AYUSH ENTERPRISE | 12.66 | 0 | 0
1448 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Tajpur Piped Water Supply Scheme (Phase-1) | AE/Ulu | JE/USD | VCH/000944/2020-2021 | 8443110 | 30/03/2021 | 0 | JOY CHANDI CONSTRUCTION | 30.29 | 0 | 0
1449 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-G) |  |  | ORD/000121/2020-2021 | 1539/HD | 05/11/2020 | 30 | UNIQUE AGENCY | 18.89 | 0 | 0
1450 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-H) |  |  | ORD/000122/2020-2021 | 1540/HD | 05/11/2020 | 30 | UNIQUE AGENCY | 18.88 | 0 | 0
1451 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Part-I) |  |  | ORD/000129/2020-2021 | 1541/HD | 05/11/2020 | 30 | A P POWER & CONCRETE | 18.85 | 0 | 0
1452 | Howrah Division |  | Work Order for Laying of additional UPVC pipe line of 75 mm & 110mm dia,Total 450 mtr. Length for Retrofitting work for providing Functional Household Tap Connection (FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. within the Command area of Gobindapur PWSS under Howrah Sadar Sub Division of Howrah Division , PHE Dte. (Phase-III) |  |  | ORD/000424/2021-2022 | 338/HD | 17/02/2022 | 30 | BUILT INDIA | 2.52 | 0 | 0
1453 | Howrah Division |  | Mass Awarness generation and IEC activities. |  |  | VCH/000611/2021-2022 | 844313 | 23/12/2021 | 0 | PRADIP KUMAR JATI | 42 | 0 | 0
1454 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000645/2021-2022 | 844318 | 20/01/2022 | 0 | MS ARPAN ENTERPRISE | 4.26 | 0 | 0
1455 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000648/2021-2022 | 844321 | 20/01/2022 | 0 | MONIRUL ISLAM | 4.31 | 0 | 0
1456 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Gobindapur piped water supply scheme under J.B.Pur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-II) (Part-X) |  |  | VCH/000853/2021-2022 | 844317 | 21/03/2022 | 0 | BUILT INDIA | 4.07 | 0 | 0
1457 | Howrah Division |  | Retrofitting Gobindapur W/S Scheme. |  |  | VCH/000876/2021-2022 | 844334 | 30/03/2022 | 0 | ALOK ENTERPRISE | 15.52 | 0 | 0
1458 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000932/2020-2021 | 8443103 | 30/03/2021 | 0 | A.P. POWER & CONCRETE | 16.16 | 0 | 0
1459 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Gobindapur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000949/2020-2021 | 8443116 | 30/03/2021 | 0 | MONIRUL ISLAM | 4.71 | 0 | 0
1460 | Howrah Division | Ulberia Sub-Division | Work Order for Additional Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte.(Part-G) (Phase-II) | AE/Ulu |  | ORD/000098/2022-2023 | 112/AE/USD | 15/06/2022 | 45 | BUNBA CONSTRUCTION | 4.9 | 0 | 0
1461 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-L) (for Kashtasangara(Part) | AE/Ulu |  | ORD/000118/2020-2021 | 1513/HD | 04/11/2020 | 30 | JAHANGIR ALAM | 27.43 | 0 | 0
1462 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-M) (for Ratanpota & Kashtasangara(Part) Mouza) | AE/Ulu |  | ORD/000119/2020-2021 | 1514/HD | 04/11/2020 | 30 | JAHANGIR ALAM | 25.61 | 0 | 0
1463 | Howrah Division | Ulberia Sub-Division | Work Order for Additional laying of pipeline work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system (Majipara, Khosalpur, Kastosangra, Ratanpota) at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-F1) | AE/Ulu |  | ORD/000136/2022-2023 | 133/AE/USD | 20/06/2022 | 45 | JAHANGIR ALAM | 4.71 | 0 | 0
1464 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-1) | AE/Ulu |  | ORD/000298/2021-2022 | 2229/HD | 09/12/2021 | 30 | PRADIP KUMAR JATI | 4.07 | 0 | 0
1465 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-D) (Phase-2) | AE/Ulu |  | ORD/000299/2021-2022 | 2230/HD | 09/12/2021 | 30 | PRADIP KUMAR JATI | 4.07 | 0 | 0
1466 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-1) | AE/Ulu |  | ORD/000301/2021-2022 | 2232/HD | 09/12/2021 | 30 | DEV DAS SHAW | 3.49 | 0 | 0
1467 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-2) | AE/Ulu |  | ORD/000302/2021-2022 | 2233/HD | 09/12/2021 | 30 | DEV DAS SHAW | 3.49 | 0 | 0
1468 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-E) (Phase-3) | AE/Ulu |  | ORD/000312/2021-2022 | 2243/HD | 09/12/2021 | 30 | DEV DAS SHAW | 3.49 | 0 | 0
1469 | Howrah Division | Ulberia Sub-Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distribution system of Khosalpur piped water supply scheme under Amta-I Block under Howrah Division, PHE Dte. (Part-C) (for Kasra Mouza (Part) | AE/Ulu |  | VCH/000932/2021-2022 | BP-2021-22-383 | 07/03/2022 | 0 | DEV DAS SHAW | 18.73 | 0 | 0
1470 | Howrah Division | Ulberia Sub-Division | Construction of delivery spouts for filling movable water tanker in connection with flood prepardeness measure alongwith lying of tube well wash out with HDPE pipe of 4 nos Tube Wells of Khoshalpur Water Supply Scheme | AE/Ulu |  | VCH/000933/2021-2022 | BP-2021-22-384 | 07/03/2022 | 0 | JAHANGIR ALAM | 1.08 | 0 | 0
1471 | Howrah Division | Ulberia Sub-Division | Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-B) (Phase-2) | AE/Ulu |  | VCH/001026/2021-2022 | BP-2021-22-451 | 25/03/2022 | 0 | N. G ENGINEERING | 3.1 | 0 | 0
1472 | Howrah Division | Ulberia Sub-Division | Additional work for Retrofitting of providing Functional Household Tap Connection(FHTC) from existing distribution system at Khosalpur W/S scheme under Amta-II Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu |  | VCH/001027/2021-2022 | BP-2021-22-449 | 30/03/2022 | 0 | M/S ASHIRBAD (INDIA) | 4.52 | 0 | 0
1473 | Howrah Division | Ulberia Sub-Division | Cons of OHR Khoshalpur | AE/Ulu |  | VCH/001030/2021-2022 | BP-2021-22-324 | 16/02/2022 | 0 | NATURAL RESOURCES CONSORTIUM | 8.49 | 0 | 0
1474 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-A) |  |  | ORD/000011/2020-2021 | 839/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0
1475 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-B) |  |  | ORD/000012/2020-2021 | 840/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0
1476 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-C) |  |  | ORD/000013/2020-2021 | 841/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0
1477 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-D) |  |  | ORD/000014/2020-2021 | 842/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0
1478 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-E) |  |  | ORD/000015/2020-2021 | 843/HD | 25/08/2020 | 30 | M/S ASHIRBAD (INDIA) | 4.56 | 0 | 0
1479 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-F) |  |  | ORD/000016/2020-2021 | 844/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0
1480 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-G) |  |  | ORD/000017/2020-2021 | 845/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0
1481 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-H) |  |  | ORD/000018/2020-2021 | 846/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0
1482 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-I) |  |  | ORD/000019/2020-2021 | 847/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0
1483 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-J) |  |  | ORD/000020/2020-2021 | 848/HD | 25/08/2020 | 30 | N. G ENGINEERING | 4.56 | 0 | 0
1484 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-K) |  |  | ORD/000021/2020-2021 | 849/HD | 25/08/2020 | 30 | TIYASA ENTERPRISE | 4.56 | 0 | 0
1485 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-L) |  |  | ORD/000022/2020-2021 | 850/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0
1486 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-M) |  |  | ORD/000023/2020-2021 | 851/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0
1487 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-N) |  |  | ORD/000024/2020-2021 | 852/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0
1488 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-O) |  |  | ORD/000025/2020-2021 | 853/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0
1489 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-P) |  |  | ORD/000026/2020-2021 | 854/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0
1490 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Q) |  |  | ORD/000027/2020-2021 | 855/HD | 25/08/2020 | 30 | DEV DAS SHOW | 4.56 | 0 | 0
1491 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-R) |  |  | ORD/000028/2020-2021 | 856/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0
1492 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-S) |  |  | ORD/000029/2020-2021 | 857/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0
1493 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-T) |  |  | ORD/000030/2020-2021 | 858/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0
1494 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-U) |  |  | ORD/000031/2020-2021 | 859/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0
1495 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-V) |  |  | ORD/000032/2020-2021 | 860/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0
1496 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-W) |  |  | ORD/000033/2020-2021 | 861/HD | 25/08/2020 | 30 | PRADIP KUMAR JATI | 4.56 | 0 | 0
1497 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-X) |  |  | ORD/000034/2020-2021 | 862/HD | 25/08/2020 | 30 | TIYASA ENTERPRISE | 4.56 | 0 | 0
1498 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Y) |  |  | ORD/000035/2020-2021 | 863/HD | 25/08/2020 | 30 | S.B. ENTERPRISE | 4.56 | 0 | 0
1499 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-I) (Part-Z) |  |  | ORD/000036/2020-2021 | 864/HD | 25/08/2020 | 30 | S.B. ENTERPRISE | 4.56 | 0 | 0
1500 | Howrah Division |  | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. |  |  | ORD/000427/2021-2022 | 341/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 4.47 | 0 | 0
1501 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P |  |  | VCH/000414/2020-2021 | W/453 | 28/12/2020 | 0 | DEV DAS SHOW | 4.49 | 0 | 0
1502 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-O |  |  | VCH/000415/2020-2021 | W/455 | 28/12/2020 | 0 | DEV DAS SHOW | 4.49 | 0 | 0
1503 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-N |  |  | VCH/000416/2020-2021 | W/454 | 28/12/2020 | 0 | DEV DAS SHOW | 4.49 | 0 | 0
1504 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-M |  |  | VCH/000417/2020-2021 | W/452/2 | 28/12/2020 | 0 | DEV DAS SHOW | 4.47 | 0 | 0
1505 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-L |  |  | VCH/000418/2020-2021 | W/452 | 28/12/2020 | 0 | DEV DAS SHOW | 4.43 | 0 | 0
1506 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-Q |  |  | VCH/000419/2020-2021 | W/456 | 28/12/2020 | 0 | DEV DAS SHOW | 4.46 | 0 | 0
1507 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-W |  |  | VCH/000420/2020-2021 | W/466 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.47 | 0 | 0
1508 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-V |  |  | VCH/000421/2020-2021 | W/466/2 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.46 | 0 | 0
1509 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-U |  |  | VCH/000422/2020-2021 | W/466/3 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.48 | 0 | 0
1510 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-T |  |  | VCH/000423/2020-2021 | W/466/4 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.47 | 0 | 0
1511 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-S |  |  | VCH/000424/2020-2021 |  | 02/12/2020 | 0 | PRADIP KUMAR JATI | 4.49 | 0 | 0
1512 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-R |  |  | VCH/000425/2020-2021 | W/466 | 30/12/2020 | 0 | PRADIP KUMAR JATI | 4.47 | 0 | 0
1513 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)Part-K |  |  | VCH/000426/2020-2021 | W/462 | 28/12/2020 | 0 | TIYASA ENTERPRISE | 4.46 | 0 | 0
1514 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000427/2020-2021 | W/463 | 28/12/2020 | 0 | TIYASA ENTERPRISE | 4.45 | 0 | 0
1515 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) (Part-Z) |  |  | VCH/000428/2020-2021 | W/451 | 29/12/2020 | 0 | S.B. ENTERPRISE | 4.46 | 0 | 0
1516 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-Y) |  |  | VCH/000429/2020-2021 | W/451/1 | 29/12/2020 | 0 | S.B. ENTERPRISE | 4.44 | 0 | 0
1517 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F) |  |  | VCH/000430/2020-2021 | W/464 | 30/12/2020 | 0 | N. G ENGINEERING | 4.45 | 0 | 0
1518 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-G) |  |  | VCH/000431/2020-2021 | W/464/2 | 30/12/2020 | 0 | N. G ENGINEERING | 4.5 | 0 | 0
1519 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-H) |  |  | VCH/000432/2020-2021 | W/464/3 | 30/12/2020 | 0 | N. G ENGINEERING | 4.49 | 0 | 0
1520 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-I) |  |  | VCH/000433/2020-2021 | W/464/4 | 30/12/2020 | 0 | N. G ENGINEERING | 4.47 | 0 | 0
1521 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-J) |  |  | VCH/000434/2020-2021 | W/465 | 29/12/2020 | 0 | N. G ENGINEERING | 4.47 | 0 | 0
1522 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte (Phase-I)Part-P, (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-F), (1) Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I)(Part-A) |  |  | VCH/000435/2020-2021 | W/457 | 28/12/2020 | 0 | M/S ASHIRBAD (INDIA) | 4.5 | 0 | 0
1523 | Howrah Division |  | Survey and Collection of houshold details through mobile app and geo tagging the same including IMIS entry of water tap connection in each house hold from existing distribution system within scheme jurisdiction in different pipe water supply scheme |  |  | VCH/000641/2020-2021 | W/508 | 18/01/2021 | 0 | STEELCONC AND ASSOCIATES | 4.73 | 0 | 0
1524 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-A) |  |  | ORD/000208/2020-2021 | 1390/HD | 16/10/2020 | 30 | DEV DAS SHOW | 4.57 | 0 | 0
1525 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-B) |  |  | ORD/000209/2020-2021 | 1391/HD | 16/10/2020 | 30 | DEV DAS SHOW | 4.5 | 0 | 0
1526 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-C) |  |  | ORD/000210/2020-2021 | 1392/HD | 16/10/2020 | 30 | PRADIP KUMAR JATI | 4.31 | 0 | 0
1527 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-D) |  |  | ORD/000211/2020-2021 | 1393/HD | 16/10/2020 | 30 | PRADIP KUMAR JATI | 4.27 | 0 | 0
1528 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-E) |  |  | ORD/000212/2020-2021 | 1394/HD | 16/10/2020 | 30 | PRADIP KUMAR JATI | 2.81 | 0 | 0
1529 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-F) |  |  | ORD/000213/2020-2021 | 1395/HD | 16/10/2020 | 30 | N. G ENGINEERING | 4.65 | 0 | 0
1530 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-G) |  |  | ORD/000214/2020-2021 | 1396/HD | 16/10/2020 | 30 | N. G ENGINEERING | 4.65 | 0 | 0
1531 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-H) |  |  | ORD/000215/2020-2021 | 1397/HD | 16/10/2020 | 30 | N. G ENGINEERING | 3.97 | 0 | 0
1532 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-I) |  |  | ORD/000216/2020-2021 | 1398/HD | 16/10/2020 | 30 | M/S ASHIRBAD (INDIA) | 3.97 | 0 | 0
1533 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-J) |  |  | ORD/000217/2020-2021 | 1399/HD | 16/10/2020 | 30 | M/S ASHIRBAD (INDIA) | 3.78 | 0 | 0
1534 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-K) |  |  | ORD/000218/2020-2021 | 1400/HD | 16/10/2020 | 30 | S.B. ENTERPRISE | 2.3 | 0 | 0
1535 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-L) |  |  | ORD/000219/2020-2021 | 1401/HD | 16/10/2020 | 30 | S.B. ENTERPRISE | 1.56 | 0 | 0
1536 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) |  |  | ORD/000422/2021-2022 | 336/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 3.96 | 0 | 0
1537 | Howrah Division |  | Work Order for Laying of 90mm dia,Node point 53-55, 55-57, 57-101, Total 940 mtr. Length additional UPVC pipe line for Retrofitting work for providing Functional Household Tap Connection (FHTC) within the Command area of Laskarpur PWSS at Howrah Sadar Sub Division under howrah Division , PHE Dte. (Phase-V) Part ¿A |  |  | ORD/000433/2021-2022 | 347/HD | 17/02/2022 | 30 | MONIRUL ISLAM | 4.07 | 0 | 0
1538 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) including school, anganwari & other establishments like temple, mosque, govt. premises, mela ground, public toilets etc. from existing distributin system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-V) (Part-B) |  |  | ORD/000434/2021-2022 | 348/HD | 17/02/2022 | 30 | KRISH CONSTRUCTION | 2.53 | 0 | 0
1539 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000200/2021-2022 | W/172 | 14/08/2021 | 0 | DEV DAS SHAW | 16.14 | 0 | 0
1540 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000201/2021-2022 | W/178 | 14/08/2021 | 0 | S.B. ENTERPRISE | 11.99 | 0 | 0
1541 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000202/2021-2022 | W/177 | 14/08/2021 | 0 | PRADIP KUMAR JATI | 12.13 | 0 | 0
1542 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000203/2021-2022 | W/179 | 14/08/2021 | 0 | M/S ASHIRBAD (INDIA) | 21.8 | 0 | 0
1543 | Howrah Division |  | Retrofitting work of providing Functional house hold tap connection(FHTC) under Laskarpur PWSS within Jagatballavpur Block (Phase-I) |  |  | VCH/000591/2021-2022 | W/592 | 21/12/2021 | 0 | MONIRUL ISLAM | 3.32 | 0 | 0
1544 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributing system of Laskarpur piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. ( Phase-IV) (Part-K) |  |  | VCH/000789/2022-2023 | 844323 | 29/09/2022 | 0 | S.B. ENTERPRISE | 3.63 | 0 | 0
1545 | Howrah Division |  | Work Order for Retrofitting work for Supply, delivery & installation of CIDF Sluice Valve in different Node point and construction of Sluice Valve chamber for providing Functional Household Tap Connection (FHTC) from existing distribution system of Laskarpur PWSS under Howrah Sub Division of Howrah Division , PHE Dte. |  |  | VCH/000791/2022-2023 | 84438 | 22/09/2022 | 0 | MONIRUL ISLAM | 8.49 | 0 | 0
1546 | Howrah Division |  | Development Internal pathway and allied work at H/W of Laskarpur PWSS. |  |  | VCH/000818/2022-2023 | 844318 | 27/09/2022 | 0 | RAJLAKSHMI ENTERPRISE | 3.44 | 0 | 0
1547 | Howrah Division | RWS Howrah Sub-Division | Additional Laying of distribution pipeline with FHTC at Mouza-Kakraipota for Augmentation of Pancharul PWSS of Udaynarayanpur Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000013/2024-2025 | 2646/HD | 07/06/2024 | 60 | ADITYA HAZRA | 50.3 | 0 | 100
1548 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Pancharul Mouza for (1567 nos) from existing distribution system at Augmentation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. Pancharul Mouza for 1567 nos (Part-C) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000033/2022-2023 | 1002/HD | 02/05/2022 | 45 | CREATION CONSTRUCTION | 121.95 | 0 | 100
1549 | Howrah Division | RWS Howrah Sub-Division | Work Order for Sinking of 2 (Two) nos PVC big dia Tube well 300 mm x 200 mm dia of 250 mtr deep for Augmentation of Pancharul W/S scheme at Udaynarayanpur Block in Uluberia Sub-Division P.H.E. Dte. under Howrah Division, P.H.E Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000108/2022-2023 | 1268/HD | 17/06/2022 | 30 | M/S SYCHROTECH INDUSTRY | 34.92 | 0 | 0
1550 | Howrah Division | RWS Howrah Sub-Division | Work Order for "Augmentation of Pancharul Water Supply scheme by Laying Distribution System, providing Functional Household Tap Connection(FHTC) work with GEO tagging of using Jal Swapna App, Construction of R.C.C Elevated Reservoir of Capacity 500 m3 of Staging Height 20 mtr including Soil Investigation, interconnection & Rising main between 2nd TW, 1st Tube well (HW site) & OHR under Howrah Division, P.H.E. Dte. (Part-A)" | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000129/2022-2023 | 1338/HD | 27/06/2022 | 947 | JAHANGIR ALAM | 232.99 | 0 | 100
1551 | Howrah Division | RWS Howrah Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Pancharul PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000251/2021-2022 | 2110/HD | 24/11/2021 | 15 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.16 | 0 | 0
1552 | Howrah Division | RWS Howrah Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Udaynarayanpur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000282/2024-2025 | 4813/HD | 19/11/2024 | 390 | HORIZEN | 13.59 | 0 | 60
1553 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Subal Chack Mouza for (372 nos) from existing distribution system at Augmentation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. (Part-D) | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000529/2021-2022 | 626/HD | 22/03/2022 | 45 | MODERN CONSTRUCTION | 59.54 | 0 | 100
1554 | Howrah Division | RWS Howrah Sub-Division | Work Order for Laying Distribution System & providing Functional Household Tap Connection(FHTC) Kakraipota Mouza (570 nos) from existing distribution system at Augementation of Pancharul Piped Water Supply Scheme under Udaynaraunpur Block under Howrah Division, PHE Dte. (Part-B). | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | ORD/000530/2021-2022 | 627/HD | 22/03/2022 | 45 | ADITYA HAZRA | 95.54 | 0 | 0
1555 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000021/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 21.34 | 0 | 0
1556 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000035/2023-2024 | 2753/HD | 28/07/2023 | 0 | Resource Division | 12.32 | 0 | 0
1557 | Howrah Division | RWS Howrah Sub-Division | Material Requisition To Resource Division | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | RTOR000042/2022-2023 | 2639/HD | 09/12/2022 | 0 | Resource Division | 21.34 | 0 | 0
1558 | Howrah Division | RWS Howrah Sub-Division | Indent of Material | AE/RWS,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Udaynaryanpur,Junior Engineer2 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
1559 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction Of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/06/2012) Including All pipe Connection Of Rudrapur PWSS In Domjur Block Of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000032/2023-2024 | 1740/HD | 25/04/2023 | 707 | N. G ENGINEERING | 147.33 | 0 | 21
1560 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Rudrapur PWSS Under Domjur Block of Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000226/2022-2023 | 80/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.29 | 0 | 100
1561 | Howrah Division | Howrah Sadar Sub-Division | Emergency Restoration of CI/DI Pipeline (Node No. 2 to 101) along with damaged main road due to laying of pipe line of Rudrapur PWSS under Howrah Sadar Sub-Divnision PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000425/2024-2025 | 891/HD | 11/02/2025 | 150 | REALIENCE CONSTRUCTION | 96.76 | 0 | 70
1562 | Howrah Division | Howrah Sadar Sub-Division | Restoration of damaged concrete roads due to laying of pipe line at Rudrapur PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000437/2024-2025 | 923/HD | 17/02/2025 | 225 | PRADIP KUMAR JATI | 70.93 | 0 | 0
1563 | Howrah Division | Howrah Sadar Sub-Division | Additional carriage of OHR materials & allied works of Rurdrapur PWSS at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000637/2023-2024 | 1239/HD | 12/03/2024 | 45 | N. G ENGINEERING | 6.67 | 0 | 100
1564 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Rudrapur PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000665/2022-2023 | 176/HD | 13/01/2023 | 45 | DEV DAS SHAW | 37.79 | 0 | 100
1565 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction for 3(Three) Nos.Pump House (5.40m x 3.60 m), Boundary Wall at Head work Site, 2(Two) nos. Boundary Walls (other sites), Rising Main Pipeline Work & Laying Distribution Pipeline work with Functional Household Tap Connection of Rudrapur PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000772/2022-2023 | 723/HD | 23/02/2023 | 904 | PRADIP KUMAR JATI | 290 | 0 | 70
1566 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000010/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 53.99 | 0 | 0
1567 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000074/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 17.01 | 0 | 0
1568 | Howrah Division | Ulberia Sub-Division | Construction of boundary wall at HW Site of Sonamoi W/S scheme within Amta-I Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000006/2025-2026 | 1810/HD | 08/04/2025 | 60 | M/S JOY | 29.15 | 0 | 0
1569 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site at Sonamui PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000096/2023-2024 | 1945/HD | 10/05/2023 | 60 | M/S KANIKA ROY ENTERPRISE | 7.18 | 0 | 100
1570 | Howrah Division | Ulberia Sub-Division | Work order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at 2nd TW site at Sonamui PWSS of Amta-I Block under Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000097/2023-2024 | 1946/HD | 10/05/2023 | 60 | KALIDAS ENTERPRISE | 7.18 | 0 | 100
1571 | Howrah Division | Ulberia Sub-Division | Work order for Interconnection between Tube wells & OHR at Sonamui Water Supply scheme at Amta-I Block under Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000098/2023-2024 | 1947/HD | 10/05/2023 | 60 | BHOLA NATH CONSTRUCTION | 13.13 | 0 | 100
1572 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
1573 | Howrah Division | Ulberia Sub-Division | Land Development & Approach Road at 2nd TW site of Sonamoi PWSS of Amta-I Block under Uluberia Sub Division under Howrah Divison PHED. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000386/2024-2025 | 1294/AE/USD | 17/12/2024 | 100 | APST TASTIC DEVELOPERS PRIVATE LIMITED | 0.86 | 0 | 100
1574 | Howrah Division | Ulberia Sub-Division | Work Order for Preparation of DPR for new piped water supply scheme of Sonamui PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000437/2021-2022 | 238/HD | 07/02/2022 | 15 | RADIANT | 3.61 | 0 | 0
1575 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-2) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000493/2022-2023 | 2245/HD | 04/11/2022 | 30 | AMIT CONSTRUCTION | 32.09 | 0 | 100
1576 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-3) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000494/2022-2023 | 2246/HD | 04/11/2022 | 638 | N. G ENGINEERING | 32.94 | 0 | 100
1577 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-4) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000495/2022-2023 | 2247/HD | 04/11/2022 | 720 | M/S ASHIRBAD (INDIA) | 32.95 | 0 | 100
1578 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme in Amta-I Block under Howrah Division, PHE Dte.(Part-5) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000496/2022-2023 | 2248/HD | 04/11/2022 | 30 | M/S B.S.P. ENTERPRISES | 33.03 | 0 | 100
1579 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-6) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000497/2022-2023 | 2249/HD | 04/11/2022 | 30 | S.S ENTERPRISE | 20.52 | 0 | 100
1580 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-7) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000500/2022-2023 | 2250/HD | 04/11/2022 | 30 | ABONTICA ENTERPRISE | 20.72 | 0 | 100
1581 | Howrah Division | Ulberia Sub-Division | Work Oder for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-8) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000501/2022-2023 | 2251/HD | 04/11/2022 | 30 | MS ARPAN ENTERPRISE | 20.64 | 0 | 100
1582 | Howrah Division | Ulberia Sub-Division | Work Oder for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-9) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000502/2022-2023 | 2252/HD | 04/11/2022 | 30 | ABONTICA ENTERPRISE | 20.76 | 0 | 100
1583 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-10) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000503/2022-2023 | 2253/HD | 04/11/2022 | 30 | UNIVERSAL CONSTRUCTION | 20.72 | 0 | 100
1584 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-11) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000506/2022-2023 | 2254/HD | 04/11/2022 | 30 | ABONTICA ENTERPRISE | 20.83 | 0 | 100
1585 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-B) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000521/2022-2023 | 2366/HD | 18/11/2022 | 45 | S RAHA ENTERPRISE | 82.51 | 0 | 100
1586 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-C) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000522/2022-2023 | 2367/HD | 18/11/2022 | 45 | BISWAJIT BAG | 86.2 | 0 | 100
1587 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-D) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000523/2022-2023 | 2368/HD | 18/11/2022 | 45 | M/S MOINAK POREL | 90 | 0 | 100
1588 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution Pipe Lines With Allied Works For Sonamoui Water Supply Scheme In Amta-I Block under Uluberia Sub-Division under Howrah Division, PHE Dte. (Part-E) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000524/2022-2023 | 2369/HD | 18/11/2022 | 45 | JAI BHARAT COMMERCIAL CORPORATION | 79.6 | 0 | 100
1589 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-12) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000525/2022-2023 | 2370/HD | 18/11/2022 | 30 | S.M. CONSTRUCTION | 10.15 | 0 | 100
1590 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-13) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000526/2022-2023 | 2371/HD | 18/11/2022 | 30 | BINOY KOLEY | 10.13 | 0 | 100
1591 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-14) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000527/2022-2023 | 2372/HD | 18/11/2022 | 30 | M/S AHAMED CONSTRUCTION | 10.06 | 0 | 100
1592 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-15) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000528/2022-2023 | 2373/HD | 18/11/2022 | 30 | MONIRUL ISLAM | 10.01 | 0 | 100
1593 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-16) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000529/2022-2023 | 2374/HD | 18/11/2022 | 30 | MAITY CONSTRUCTIONS | 9.7 | 0 | 100
1594 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-17) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000530/2022-2023 | 2375/HD | 18/11/2022 | 30 | APEX ENGINEERING | 10.12 | 0 | 95
1595 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-18) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000531/2022-2023 | 2376/HD | 18/11/2022 | 30 | ADRIJA ENTERPRISE | 10.09 | 0 | 100
1596 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-19) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000532/2022-2023 | 2377/HD | 18/11/2022 | 30 | KRISH CONSTRUCTION | 10.16 | 0 | 100
1597 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-20) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000533/2022-2023 | 2378/HD | 18/11/2022 | 30 | DEBABRATA CHAKRABORTY | 10.16 | 0 | 100
1598 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-21) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000534/2022-2023 | 2379/HD | 18/11/2022 | 30 | A.N ROY & CO | 10.15 | 0 | 100
1599 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 2 (Two) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Sonamui PWSS of Amta-I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000600/2022-2023 | 2716/HD | 14/12/2022 | 45 | AQUATECH ENGINEERS | 36.21 | 0 | 0
1600 | Howrah Division | Ulberia Sub-Division | Work Order for Construction of 450 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir as Per Departmental Design including Soil Investigation, Laying Distribution Pipeline for Sonamui PWSS of Amta-I Block under Howrah Division, PHE Dte. (Part-A) | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000612/2022-2023 | 2676/HD | 12/12/2022 | 720 | M/S JOY | 244.66 | 0 | 100
1601 | Howrah Division | Ulberia Sub-Division | Work Order for Providing Functional Household Tap Connection(FHTC) at Sonamui Water Supply Scheme In Amta-I Block under Howrah Division, PHE Dte. (Part-1)Number of FHTC to be provided (Approx):320 | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | ORD/000632/2022-2023 | 2990/HD | 29/12/2022 | 30 | RANA ENTERPRISE | 34.79 | 0 | 100
1602 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000005/2023-2024 | 1698/HD | 21/04/2023 | 0 | Resource Division | 3.22 | 0 | 0
1603 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000031/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 56.07 | 0 | 0
1604 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer3 | RTOR000039/2023-2024 | 2753/HD | 28/07/2023 | 0 | Resource Division | 15.4 | 0 | 0
1605 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 7 (Seven) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone 1) Mahisnala PWSS & Domjur (Zone-II)PWSS of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000001/2023-2024 | 1530/HD | 04/04/2023 | 45 | BALAJI UDDYOG | 89.53 | 0 | 70
1606 | Howrah Division | Howrah Sadar Sub-Division | Emergency Restoration of CI/DI Pipeline along with damaged at Node No. 22 to 270 main road due to laying of pipe line of Domjur (Zone-1) Mahishnala PWSS under Howrah Sadar Sub-Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000109/2025-2026 | 3130/HD | 14/07/2025 | 45 | MONDAL ENTERPISE | 42.03 | 0 | 0
1607 | Howrah Division | Howrah Sadar Sub-Division | 3 Nos Construction of Pump House (5.40m x 3.60 m), 3 nos Construction of Boundary Wall at 1st, 2nd &3rd Tube Well Sites, Construction of 350 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/4/2012) including Soil Investigation, Foundation Design & All pipe Connection, Rising Main Pipeline Work From 3rd Pump House, 2nd Pump House to 1st Pump House & OHR, Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) for Augmentation of Domjur (Zone-I) Mahisnala PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000127/2023-2024 | 2622/HD | 17/07/2023 | 1085 | MONDAL PRECISION PVT. LTD. | 411.41 | 0 | 40
1608 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-I) PWSS (Mouza-Mahisgote, Chak Mahisjol, Chal Hari, Mahisnala, Nanakundu & Chak Kadamtala) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000236/2022-2023 | 89/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.19 | 0 | 0
1609 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
1610 | Howrah Division | Howrah Sadar Sub-Division | Pipe Carrying Structure for Crossing at Node No. 104 to 109 of Mahishnala PWSS Under Howrah Sadar Sub-Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000424/2024-2025 | 867/HD | 10/02/2025 | 60 | GUPTA ENTERPRISE | 36.93 | 0 | 0
1611 | Howrah Division | Howrah Sadar Sub-Division | Land Development Works (1st, 2nd & 3rd T/W Site) & RCC Retaining Wall of Mahishnala (Zone-1) PWSS at 3rd Tubewell Site at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/000626/2023-2024 | 1135/HD | 06/03/2024 | 187 | KALIDAS ENTERPRISE | 12.66 | 0 | 50
1612 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000011/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 50.64 | 0 | 0
1613 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | RTOR000075/2023-2024 | 135/HD | 10/01/2024 | 0 | Resource Division | 12.09 | 0 | 0
1614 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System(HDPE & DI) & providing Functional Household Tap Connection (FHTC) & Interconnection between tube wells & 300 cu.m. capacity 20mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including pile design & Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement at Head Work Site GOPALPUR PWSS OF BAGNAN-I BLOCK UNDER THE ULUBERIA SUB-DIVISION UNDER HOWRAH DIVISION, P.H.E. DTE. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000063/2023-2024 | 1917/HD | 08/05/2023 | 599 | PRAVAT SARKAR | 335.59 | 0 | 16
1615 | Howrah Division | Ulberia Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Amta-I, Amta-II, Bagnan-I, Bagnan-II, Shyampur-I and Shyampur-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000286/2024-2025 | 4815/HD | 19/11/2024 | 90 | TECH VISION | 12.67 | 0 | 100
1616 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Gopalpur PWSS, Bagnan-I Block under Uluberia Sub-division of Howrah Division P.H.E Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000364/2022-2023 | 459/AE/USD | 15/09/2022 | 45 | DULAL MAJUMDER | 3.14 | 0 | 100
1617 | Howrah Division | Ulberia Sub-Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Bagnan-I & II Block of Uluberia Sub-Division under Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000636/2023-2024 | 1206/HD | 11/03/2024 | 15 | KULTIKARI MOTHER TERESA SOCIAL WELLFARE SOCIETY | 2.01 | 0 | 100
1618 | Howrah Division | Ulberia Sub-Division | Site clearence of HW site of Gopalpur & Patinan PWSS under Uluberia Sub Division under Howrah Division, PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000693/2023-2024 | 3244/AE/USD | 12/03/2024 | 30 | S R TRADING CORPORATION | 0.96 | 0 | 100
1619 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 4 (Four) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Gopalpur PWSS 2nos & Patinan PWSS 2 Nos of Bagnan - I Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | ORD/000745/2022-2023 | 663/HD | 17/02/2023 | 45 | AQUATECH ENGINEER | 52.06 | 0 | 100
1620 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000019/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 36.34 | 0 | 0
1621 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer2 | RTOR000086/2023-2024 | 170/HD | 15/01/2024 | 0 | Resource Division | 4.87 | 0 | 0
1622 | Howrah Division | Howrah Sadar Sub-Division | Work order for Laying Additional DI Pipe line LDS Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000067/2023-2024 | 1928/HD | 10/05/2023 | 60 | MONIRUL ISLAM | 4.11 | 0 | 100
1623 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Rising Main Pipeline Work of Shyampur PWSS at J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000068/2023-2024 | 1929/HD | 10/05/2023 | 60 | KUNAL BANERJEE | 3.96 | 0 | 100
1624 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000076/2022-2023 | 1019/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0
1625 | Howrah Division | Howrah Sadar Sub-Division | Construction of approach road and land Development at 1st tubewell site for Shyampur PWSS at J.B.PUR Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000107/2025-2026 | 3086/HD | 08/07/2025 | 30 | ADRIJA ENTERPRISE | 5.55 | 0 | 0
1626 | Howrah Division | Howrah Sadar Sub-Division | Construction of 2 nos. Boundary Wall at pump house of Shyampur PWSS at J.B Pur Block of Howrah District under Howrah Division, P. H. E. Dte. Size-(25.00 m x 20.00 m) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000306/2023-2024 | 4318/HD | 01/12/2023 | 60 | ADRIJA ENTERPRISE | 15.43 | 0 | 100
1627 | Howrah Division | Howrah Sadar Sub-Division | Laying distribution pipe line (DI) between node point J34 to J46 of Shyampur PWSS at Jagatballavpur Block of Howrah District under Howrah sadar sub division of Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000423/2024-2025 | 1186/HSSD | 20/11/2024 | 60 | MANIRUL ISLAM | 0.96 | 0 | 100
1628 | Howrah Division | Howrah Sadar Sub-Division | Work order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte.From Section R-1 - J-1 to Section J-134 - J-136 (Part-3) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000504/2022-2023 | 2259/HD | 04/11/2022 | 45 | AQUATECH ENGINEERS | 30.98 | 0 | 100
1629 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-9- J-10 to Section J-140 - J-141 (Part-2) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000505/2022-2023 | 2260/HD | 04/11/2022 | 45 | BUILT INDIA | 18.8 | 0 | 100
1630 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) at 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000586/2022-2023 | 2603/HD | 07/12/2022 | 60 | NAG ENTERPRISE | 6.17 | 0 | 100
1631 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of Pump House (5.40m x 3.60 m) At 2nd T/Well site at Shyampur PWSS In J.B pur Block Of Howrah District under Howrah Division, P. H. E. Dte. (Part-4) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000587/2022-2023 | 2617/HD | 08/12/2022 | 60 | MONIRUL ISLAM | 6.14 | 0 | 100
1632 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline With FHTC of Shyampur PWSS at Jagatballavpur Block of Howrah Sadar Sub Division within Howrah Division, P. H. E. Dte. From Section J-16- J-17 to Section J-157-J-158 (Part-1) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000590/2022-2023 | 2604/HD | 07/12/2022 | 45 | MA DURGA ENTERPRISE | 15.61 | 0 | 50
1633 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 2 (Two) No. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Shyampur PWSS of Jagatballavpur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | ORD/000666/2022-2023 | 177/HD | 13/01/2023 | 45 | MUNSHI ENTERPRISE | 25.96 | 0 | 100
1634 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | RTOR000054/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 4.58 | 0 | 0
1635 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Shyampur PWSS (Mouza-Shyampur) of Jagatballavpur Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Jagatballavpur,Junior Engineer4,Junior Engineer5 | VCH/000776/2022-2023 |  | 20/10/2022 | 0 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0
1636 | Howrah Division | Ulberia Sub-Division | Work Order for Laying Distribution System & Providing House Hold Tap Connection (FHTC) & AugmeConstruction of 500cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation including foundation design of Bamunhati Piped Water Supply Scheme (Part A :- Bamunhati Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000011/2023-2024 | 1594/HD | 12/04/2023 | 960 | M/S SRIKANTA PATRA | 219.51 | 0 | 30
1637 | Howrah Division | Ulberia Sub-Division | Laying Distribution System & Providing Household Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part D :-LDS & FHTC of Mahishrekha Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000106/2023-2024 | 2697/HD | 24/07/2023 | 960 | CONSTRUCTION CORNER | 104.49 | 0 | 60
1638 | Howrah Division | Ulberia Sub-Division | Laying Distribution System & Providing House Hold Tap Connection (FHTC) for Augmentation of Bamunhati Piped Water Supply Scheme (Part C :- LDS & FHTC of Srirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000136/2023-2024 | 2749/HD | 28/07/2023 | 600 | CREATION CONSTRUCTION | 176.47 | 0 | 0
1639 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for Augmentation of Bamunhati PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000244/2022-2023 | 321/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 4.04 | 0 | 100
1640 | Howrah Division | Ulberia Sub-Division | Interconnection with existing distribution pipeline and newly sunk replaced T.Well at old Head works site of Bamunhati PWSS of Uluberia-II Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000318/2024-2025 | 1075/AE/USD | 22/10/2024 | 160 | KALIDAS ENTERPRISE | 4.14 | 0 | 100
1641 | Howrah Division | Ulberia Sub-Division | Construction of switch room SLOPE ROOF (5.40m x 3.60 m) with water supply & sanitary arrangement at Head Work site of Bamunhati PWSS of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000621/2024-2025 | 1207/HD | 04/03/2025 | 45 | M/S SRIKANTA PATRA | 7.05 | 0 | 0
1642 | Howrah Division | Ulberia Sub-Division | Renovation of boundary wall at old Headwork Site of Bamunhati W/S scheme in uluberia Sub-Division, under Howrah Division P.H.E.Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000672/2023-2024 | 3235/AE/USD | 12/03/2024 | 30 | A.A ENTERPRISE | 3.07 | 0 | 100
1643 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part O:-LDS & FHTC of Part-IX of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000749/2022-2023 | 648/HD | 17/02/2023 | 854 | JHARNA ENTERPRISE | 11.08 | 0 | 100
1644 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part E :- LDS & FHTC of Norther Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000750/2022-2023 | 650/HD | 17/02/2023 | 763 | B.M ENTERPRISE | 63.69 | 0 | 0
1645 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part B :- LDS & FHTC of Barbangalpur Village) in Uluberia-II Block of Howrah District under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000751/2022-2023 | 649/HD | 17/02/2023 | 1080 | S. R. ENTERPRISE | 76.95 | 0 | 60
1646 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part F :- LDS & FHTC of Southern Part of Palera Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000752/2022-2023 | 651/HD | 17/02/2023 | 45 | M/S MITRA CONSTRUCTION | 35.66 | 0 | 0
1647 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part G :- LDS & FHTC of Part I of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000753/2022-2023 | 652/HD | 17/02/2023 | 958 | JOY GURU TRADING | 38.68 | 0 | 75
1648 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part H :- LDS & FHTC of Part II of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000754/2022-2023 | 653/HD | 17/02/2023 | 45 | SUPRIYA MAHANTI MISRA | 22.76 | 0 | 0
1649 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part I :- LDS & FHTC of Part III of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000755/2022-2023 | 654/HD | 17/02/2023 | 1034 | ASHOKE ENGINEERING WORKS | 11.31 | 0 | 0
1650 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part J :- LDS & FHTC of Part IV of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000756/2022-2023 | 655/HD | 17/02/2023 | 868 | ABONTICA ENTERPRISE | 27.96 | 0 | 100
1651 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part K :- LDS & FHTC of Part V of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000757/2022-2023 | 656/HD | 17/02/2023 | 778 | LOKENATH ENTERPRISES | 13.99 | 0 | 100
1652 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part L :- LDS & FHTC of Part VI of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000758/2022-2023 | 657/HD | 17/02/2023 | 45 | BISWAJIT SAMANTA | 15.72 | 0 | 0
1653 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part M :- LDS & FHTC of Part VII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000759/2022-2023 | 658/HD | 17/02/2023 | 765 | ARINDAM ENTERPRISE | 22.22 | 0 | 100
1654 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part N:- LDS & FHTC of Part VIII of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000760/2022-2023 | 659/HD | 17/02/2023 | 855 | S.B ENTERPRISE | 10.66 | 0 | 100
1655 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part P:- LDS & FHTC of Part X of Abhirampur Village) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000761/2022-2023 | 660/HD | 17/02/2023 | 960 | KALIDAS ENTERPRISE | 3.99 | 0 | 100
1656 | Howrah Division | Ulberia Sub-Division | Work Order for Augmentation of Bamunhati Piped Water Supply Scheme (Part Q:- FHTC of Part XI ) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000762/2022-2023 | 661/HD | 17/02/2023 | 855 | SR TRADING CORPORATION | 3.98 | 0 | 0
1657 | Howrah Division | Ulberia Sub-Division | Construction of switch room SLOPE ROOF (3.60m x 3.00m) with water supply & sanitary arrangement of Bamunhati PWSS (2nd Tube well) of Uluberia-II Block under Uluberia Sub-Division under Howrah Division, P.H.E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000778/2024-2025 | 1464/HD | 19/03/2025 | 45 | NOBLE ENTERPRISE | 5.9 | 0 | 0
1658 | Howrah Division | Ulberia Sub-Division | Work Order for Sinking of 7 (Seven) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Bamunhati PWSS (3 nos) & Kamina PWSS (2 nos) & Barramnagar PWSS (2 nos) of Uluberia - II Block of Uluberia Sub-Division under Howrah Division, P. H. E. Dte. | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | ORD/000881/2022-2023 | 1195/HD | 23/03/2023 | 847 | ACME CONSTRUCTION | 90.87 | 0 | 85
1659 | Howrah Division | Ulberia Sub-Division | Material Requisition To Resource Division | AE/Ulu,Assistant Engineer Howrah mechanical Sub Division | JE/USD,Junior Engineer5 | RTOR000029/2023-2024 | 1754/HD | 26/04/2023 | 0 | Resource Division | 120.09 | 0 | 0
1660 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for Payment of Wayleave facility charges for Application ID: SER-KGP-2024-WL-36,Domjur CT Bill Id-WL0051767 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/00108/2024-2025 | BP-2024-25-49 | 07/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.28 | 0 | 0
1661 | Howrah Division | Howrah Sadar Sub-Division | Bill Document for payment of Wayleave facility charges for Application id: SER-KGP-2024-WL-37,Domjur-CT | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/00109/2024-2025 | BP-2024-25-48 | 07/05/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 5.2 | 0 | 0
1662 | Howrah Division | Howrah Sadar Sub-Division | Payment for Way Leave and Survey Charges Domjur Zone-VIII | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/01655/2023-2024 | BP-2023-24-734 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0
1663 | Howrah Division | Howrah Sadar Sub-Division | Payment for Way Leave and Survey Charges Domjur Zone-VIII | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | BILL/01657/2023-2024 | BP-2023-24-736 | 27/03/2024 | 0 | SOUTH EASTERN RAILWAY, KHARAGPUR DIVISION | 0.09 | 0 | 0
1664 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 600 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection For Domjur Zone-VIII, Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000034/2023-2024 | 1741/HD | 25/04/2023 | 1173 | M/S ASHIRBAD (INDIA) | 174.05 | 0 | 60
1665 | Howrah Division | Howrah Sadar Sub-Division | Supplying fabrication of 600 mm dia 10 mm thick MS casing pipe and Pushing of casing pipe by Hydraulic Jack pushing method to Cross Water carrier Pipe (Between Node Point 127 to 135 of LDS drawing) From Domjur station to Makardha station, KM/(TP/OHE) 11/03-11/04 (WL-37) of Domjur CT (Zone-8) Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000073/2025-2026 | 2756/HD | 12/06/2025 | 60 | B. D. ENTERPRISE | 40.52 | 0 | 0
1666 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection) 2493 nos for Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P. H. E. Dte.(Part-II) For Node Section (135-136) to Node Section (800-801) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000093/2023-2024 | 1997/HD | 16/05/2023 | 892 | ZAKIR HOSSIN MONDAL | 212.69 | 0 | 100
1667 | Howrah Division | Howrah Sadar Sub-Division | Construction of 3 (Three) Nos.Pump House (5.40m x 3.60 m), Construction of Boundary Wall at Head work Site, Domjur Zone-VIII, Construction of 2(Two) nos. Boundary Wall, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work, Providing FHTC (Functional Household Tap Connection) 2494 nos for Domjur (CT) PWSS at Domjur Block of Howrah District under Howrah Division, P.H.E. Dte. (Part-I) For Node Section (R-1- 1) to Node Section (565-566) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000188/2023-2024 | 3041/HD | 22/08/2023 | 817 | TUSHAR KANTI GHOSH | 284.71 | 0 | 95
1668 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Domjur (Zone-VIII) Domjur (CT) of Domjur Block of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000232/2022-2023 | 85/HSSD | 12/08/2022 | 15 | APEX ENGINEERING | 3.88 | 0 | 100
1669 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Bally Jagachha and Domjur Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000288/2024-2025 | 4817/HD | 19/11/2024 | 390 | TECH VISION | 8.36 | 0 | 79
1670 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 3 (Three) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Domjur (Zone-VIII) of Domjur Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | ORD/000656/2022-2023 | 167/HD | 13/01/2023 | 45 | AUXILIARY TUBEWELL DRILLERS | 38.56 | 0 | 40
1671 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | RTOR000016/2023-2024 | 1748/HD | 25/04/2023 | 0 | Resource Division | 99.73 | 0 | 0
1672 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | RTOR000028/2024-2025 | 4768/HD | 14/11/2024 | 0 | Resource Division | 13.96 | 0 | 0
1673 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE/RWS/Domjur,Junior Engineer5 | RTOR000061/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 22.21 | 0 | 0
1674 | Howrah Division | Howrah Sadar Sub-Division | Joynagar bazar to deulpur H.C Road from 2.730km to 3.00 km, Restoration work of PHE Cutting for laying pipe line under Howrah Highway Division in the District of Howrah.under deulpur gangadharpur Zone-II water supply scheme for Panchla Block. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | BILL/00761/2024-2025 | BP-2024-25-442 | 04/10/2024 | 0 | EXECUTIVE ENGINEER HIGHWAY DIVISION P W ROADS HOWRAH | 2.05 | 0 | 0
1675 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 255-287 to Node Section 90-91 From Node Section 287-304 to Node Section 448-450 (P-2,&4) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000005/2023-2024 | 1532/HD | 04/04/2023 | 1233 | N. G ENGINEERING | 91.11 | 0 | 85
1676 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-405 NOS) For Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 456-457 to Node Section 522-530 Part 9 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000006/2023-2024 | 1533/HD | 04/04/2023 | 726 | JHARNA ENTERPRISE | 41.43 | 0 | 100
1677 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte. From Node Section R1-1 to Node Section 280-281, Part 1 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000027/2023-2024 | 1696/HD | 21/04/2023 | 916 | PRAVAT SARKAR | 351.82 | 0 | 30
1678 | Howrah Division | Howrah Sadar Sub-Division | Construction of 1(One) no. Boundary Wall at OHR site for Deulpur Gangadharpur (Zone-II) PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000110/2025-2026 | 3132/HD | 14/07/2025 | 270 | M/S ASHIRBAD (INDIA) | 9.06 | 0 | 0
1679 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for new piped water supply scheme of Deulpur PWSS, Panchla Block under Uluberia Sub-Division of Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000241/2022-2023 | 318/AE/USD | 16/08/2022 | 45 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.25 | 0 | 100
1680 | Howrah Division | Howrah Sadar Sub-Division | Construction of 1 (one) no.Pump House (5.40m x 3.60m) at 4th tube well site,Construction of 1(One) no. boundary wall at 4th Tube well site, Construction of approch road and land Devlopment at 4th tubewell site and allied pipe laying work (DI) for Connecting 4th tubewell with the distribution main for Deulpur Gangadharpur Zone II PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000409/2024-2025 | 861/HD | 07/02/2025 | 420 | MANIRUL ISLAM | 20.91 | 0 | 0
1681 | Howrah Division | Howrah Sadar Sub-Division | Construction of 1 (one) no.Pump House (5.40m x 3.60m) at 3rd tube well site,Construction of 1(One) no. boundary wall at 3 rd Tube well site, Construction of land Development and approach road at 3rd tubewell site and allied pipe laying work (DI and UPVC) for connecting 3 rd tubewell with the distribution main at Deulpur Gangadharpur Zone-II PWSS under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000543/2024-2025 | 1070/HD | 27/02/2025 | 300 | S.S ENTERPRISE | 21.99 | 0 | 0
1682 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-II) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H.E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000660/2022-2023 | 172/HD | 13/01/2023 | 956 | PRANTIK DRILLING AGENCY | 50.26 | 0 | 35
1683 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 88-94 to Node Section 97-98 Part 3 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000791/2022-2023 | 855/HD | 01/03/2023 | 576 | DEBABRATA CHAKRABORTY | 16.89 | 0 | 58
1684 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Node Section 97-127 to Node Section 423-425 Part 5 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000792/2022-2023 | 856/HD | 01/03/2023 | 701 | S.S ENTERPRISE | 23.46 | 0 | 100
1685 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution System for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 217-230 to Node Section 352-361 Part 7 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000793/2022-2023 | 857/HD | 01/03/2023 | 904 | DULAL MAJUMDER | 67.69 | 0 | 75
1686 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 352- 405 to Node Section 532-534 Part 8 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000794/2022-2023 | 875/H.D | 02/03/2023 | 120 | M/S MSS RISING ENTERPRISE | 74.39 | 0 | 30
1687 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) for Augmentation of Deulpur Gangadharpur Zone-II PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 130-152 to Node Section 201-217 Part 6 | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000795/2022-2023 | 876/HD | 02/03/2023 | 749 | K.B ENTERPRISE | 69.39 | 0 | 80
1688 | Howrah Division | Howrah Sadar Sub-Division | Continuation order for Preparation of DPR with Route Survey for new piped water supply scheme of Deulpur Gangadharpur Zone-II PWSS of Panchla Block under Howrah Division PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000980/2022-2023 | 1507/HD | 21/07/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.13 | 0 | 100
1689 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000066/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 33.91 | 0 | 0
1690 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000087/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 307.95 | 0 | 0
1691 | Howrah Division |  | Construction of Approach road 3.00 mtr wide at Pump House -I of Bikihakola PWSS at Howrah Sadar Sub- Division under Howrah Division , P.H.E Dte |  |  | ORD/000097/2021-2022 | 1449/HD | 13/07/2021 | 30 | S.M. CONSTRUCTION | 4.3 | 0 | 0
1692 | Howrah Division |  | Work Order for Adopting Jack Pushing of 600 mm Dia M.S pipe as Casing to Cross Water carrier Pipe(Between Node Point 200-203 of LDS drawing) on Ranihati- Amta Road and adjoining work of Biki hakola Water Supply Scheme of Howrah Sadar Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000413/2021-2022 | 377/HD | 21/02/2022 | 30 | SAMIRON GHOSH | 26.38 | 0 | 0
1693 | Howrah Division |  | Work Order for Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikihakola piped water supply scheme under Jagatballavpur Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) Part- A |  |  | ORD/000435/2021-2022 | 349/HD | 17/02/2022 | 30 | UNIVERSAL CORPORATION | 4.3 | 0 | 0
1694 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) |  |  | ORD/000495/2020-2021 | 425/HD | 11/02/2021 | 30 | G.B. CONSTRUCTION AND CO | 92.5 | 0 | 100
1695 | Howrah Division |  | Work Order Retrofitting work of Laying Pipeline From Node Point 4-162, 162-220 for Bikihakola PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000596/2022-2023 | 2606/HD | 07/12/2022 | 45 | UNIVERSAL CORPORATION | 11.28 | 0 | 40
1696 | Howrah Division |  | Work Order for Laying of Delivery Main Proposal 700 cum reservoir for BikihaKola Water Supply Scheme at Panchla Block under Howrah Division, PHE Dte. (Part-IV) |  |  | VCH/000263/2022-2023 | BP-2022-23-49 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 1.55 | 0 | 0
1697 | Howrah Division |  | Work Order for Laying of Delivery Main Proposal 700 cum reservoir for BikihaKola Water Supply Scheme at Panchla Block under Howrah Division, PHE Dte. (Part-III) |  |  | VCH/000281/2022-2023 | BP-2022-23-50 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 3.19 | 0 | 0
1698 | Howrah Division |  | Work order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-B) |  |  | VCH/000303/2022-2023 | BP-2022-23-45 | 11/05/2022 | 0 | PRADIP KUMAR JATI | 0.73 | 0 | 0
1699 | Howrah Division |  | Work Order for laying of Delivery Main proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte.( Part -II) |  |  | VCH/000304/2022-2023 | BP-2022-23-51 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 4.44 | 0 | 0
1700 | Howrah Division |  | Work Order for laying of Delivery Main proposed 700 cum reservoir for Bikihakola Water Supply scheme at Panchla Block under Howrah Division, P.H.E. Dte. |  |  | VCH/000305/2022-2023 | BP-2022-23-52 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 4.85 | 0 | 0
1701 | Howrah Division |  | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. |  |  | VCH/000312/2022-2023 | BP-2022-23-53 | 11/05/2022 | 0 | UNIVERSAL CORPORATION | 0.73 | 0 | 0
1702 | Howrah Division |  | O & M of distribution system and rising main pipe line (CI/DI/AC/UPVC) of Bikihakhola w/s scheme under Howrah Division, PHE Dte. Period for O & M (01.09.2021 to 31.12.2021) |  |  | VCH/000989/2021-2022 | BP-2021-22-434 | 23/03/2022 | 0 | UNIVERSAL CORPORATION | 0.99 | 0 | 0
1703 | Howrah Division |  | Continuation order for Trial Run and Operation & maintenance of pipe lines (LDS & Risingmain) sluice valve & street stand post etc. including operation of sluice valves at Bikihakola w/s scheme under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. (09/05/2021 to 31/08/2021)In continuation to the order under reference, and your application dated 06-05-2021, you are requested to continue the above mentioned work in consultation with the Assistant Engineer, Howrah Sadar Sub-Division, PHE Dte. |  |  | VCH/000993/2021-2022 | BP-2021-22-435 | 23/03/2022 | 0 | UNIVERSAL CORPORATION | 1.53 | 0 | 0
1704 | Howrah Division |  | Construction of Pump House, Boundary Wall & Land development, approach road including alternative laying of DI (K-9) & DI (K-7) pipes at 3rd tube well site of Raspur Piped Water Supply Scheme at Amta-I Block in Uluberia Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000108/2025-2026 | 3084/HD | 08/07/2025 | 60 | M/S MJA ENTERPRISE | 22.43 | 0 | 0
1705 | Howrah Division |  | Sinking of 3rd T.well Size (250 X 150 mm Dia) and 250 m deep Drilling by Direct Rotary method with UPVC Pipes all complete at Raspur Piped Water Supply Scheme of Amta-I Block in Uluberia Sub-Division, under Howrah Division, P.H.E. Dte. (Location: Kotalpara/Putkhali) |  |  | ORD/000118/2025-2026 | 3165/HD | 16/07/2025 | 30 | WATER TECH | 15.58 | 0 | 0
1706 | Howrah Division |  | Sinking of big dia Tube wells, Construction of Switch rooms(5.4x3.6) for HW site and other TW sites, Boundary walls, Land Developments, Laying distribution system (HDPE & DI) & Providing House Hold Connection(FHTC), Interconnection between tube wells and OHR and Construction of OHR 350 cum capacity (DRG. NO.- PC-I/OHR/12/2012) 20.0mtr staging height along with pipe connection, soil investigation & design etc for Raspur PWSS in Amta-I Block under Uluberia Sub Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000223/2023-2024 | 3294/HD | 14/09/2023 | 300 | GEE BEE NIRMAN CO PVT LTD | 831.69 | 0 | 20
1707 | Howrah Division |  | Work Order for Preparation of DPR for new piped water supply scheme of Raspur PWSS, Amta-I Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000438/2021-2022 | 239/HD | 07/02/2022 | 15 | RADIANT | 3.87 | 0 | 100
1708 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 4864/HD | 22/11/2024 | 0 | Resource Division | 6.16 | 0 | 0
1709 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 964/HD | 28/02/2024 | 0 | Resource Division | 75.31 | 0 | 0
1710 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection (FHTC) from existing distributin system of Bikihakola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-II) |  |  | ORD/000492/2020-2021 | 399/HD | 10/02/2021 | 30 | M/S ASHIRBAD (INDIA) | 92.07 | 0 | 100
1711 | Howrah Division |  | Retrofitting work for providing Functional Household Tap Connection(FHTC) from existing distributin system of Bikiha kola piped water supply scheme under Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. (Phase-IV) |  |  | ORD/000495/2020-2021 | 425/HD | 11/02/2021 | 30 | G.B. CONSTRUCTION AND CO | 92.5 | 0 | 100
1712 | Howrah Division |  | Work Order for Survey & Collection of house hold details through mobile app and geo tagging (JJM entry) of the same of water tap connection in each household from existing distribution system in Bikihakola Piped Water Supply Scheme under Howrah District. (Part-C) |  |  | ORD/000519/2021-2022 | 508/HD | 08/03/2022 | 15 | G.B. CONSTRUCTION AND CO | 0.68 | 0 | 100
1713 | Howrah Division |  | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-A) No of House Hold= 100 nos. |  |  | ORD/000545/2021-2022 | 661/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.82 | 0 | 100
1714 | Howrah Division |  | Work Order for Retrofitting work for Functional Household Tap Connection(FHTC) from existing distribution system of Bikihakola PWSS under Panchla Block of Howrah Sadar Sub Division under Howrah Division, PHE Dte.(Phase-II) (Part-B)No of House Hold= 100 nos. |  |  | ORD/000546/2021-2022 | 662/HD | 23/03/2022 | 20 | UNIQUE CONSTRUCTION | 3.67 | 0 | 100
1715 | Howrah Division |  | Work Order Retrofitting work of Laying Pipeline From Node Point 4-162, 162-220 for Bikihakola PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. |  |  | ORD/000596/2022-2023 | 2606/HD | 07/12/2022 | 45 | UNIVERSAL CORPORATION | 11.28 | 0 | 40
1716 | Howrah Division |  | Additional laying distribution pipeline with FHTC at Garbhabanipur PWSS SM/18849 of Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000072/2024-2025 | 3121/HD | 09/07/2024 | 300 | TAPU SAHA | 62.11 | 0 | 70
1717 | Howrah Division |  | Preparation of DPR for Source Strengthning at Garhbhabanipur PWSS, Udaynarayanpur Block under Uluberia Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000642/2023-2024 | 496/AE/USD | 29/09/2023 | 30 | APEX ENGINEERING | 0.78 | 0 | 100
1718 | Howrah Division |  | Sinking of additonal 1 (One) Nos. 250 X 150 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Garbhabanipur PWSS SM/18849 of Udaynarayanpur Block in Uluberia Sub-Division, under Howrah Division P.H.E. Dte. |  |  | ORD/000667/2023-2024 | 1306/HD | 14/03/2024 | 30 | WESTERN WATER SUPPLY AGENCY | 14.87 | 0 | 100
1719 | Howrah Division |  | Construction of 700 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir As Per Departmental Type Design (Ref : Dept. Super Struc. DRG. No. PC-I/OHR/8/2012) including Soil Investigation, Foundation Design & All pipe Connection, Laying Rising Main Pipeline Work, Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection)For Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah District under Howrah Division, P.H.E. Dte.,Part 1 From Node Section R1-1 to Node Section 21-22 to Section 202-204 |  |  | ORD/000144/2023-2024 | 2838/HD | 07/08/2023 | 600 | SUJATA CONSTRUCTION | 373.91 | 0 | 24
1720 | Howrah Division |  | Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection-1818 NOS) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 7-34 to Node Section 74-77, From Node Section 101-248 to Node Section 356-358, From Node Section 72-84 to Node Section 241-256, From Node Section 256-257 to Node Section 449-450 (P-5,6,7 & 8) |  |  | ORD/000151/2023-2024 | 2956/HD | 16/08/2023 | 1080 | M/S ASHIRBAD (INDIA) | 179.05 | 0 | 85
1721 | Howrah Division |  | Laying of additional distribution pipe line and allied works in Kusadanga mouza at Deulpur Gangadharpur Zone-I PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division, PHE Dte. |  |  | ORD/000161/2024-2025 | 4187/HD | 26/09/2024 | 240 | MAA TARA CONSTRUCTION | 53.88 | 0 | 80
1722 | Howrah Division |  | Laying Distribution Pipeline work with Providing FHTC (1300 nos) (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P.H.E. Dte. From Node Section 55-82 to Node Section 147-148 & From Node Section 82-170 to Node Section 409-410 (P-2&3) |  |  | ORD/000193/2023-2024 | 3195/HD | 04/09/2023 | 516 | SANJUKTA ENGINEERS | 121.57 | 0 | 55
1723 | Howrah Division |  | Laying Distribution Pipeline work with Providing FHTC (Functional Household Tap Connection) For Augmentation of Deulpur Gangadharpur Zone-I PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Node Section 174-242 to Node Section 411-414, Part 4 |  |  | ORD/000215/2023-2024 | 3279/HD | 13/09/2023 | 120 | MAA TARA CONSTRUCTION | 98.18 | 0 | 70
1724 | Howrah Division |  | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. |  |  | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
1725 | Howrah Division |  | Sinking of 3 (Three) Nos. 300 X 200 mm Dia and 230m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Deulpur Gangadharpur (Zone-I) PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P.H.E. Dte. |  |  | ORD/000340/2023-2024 | 4597/HD | 20/12/2023 | 45 | WATER TECH | 50.26 | 0 | 100
1726 | Howrah Division |  | Laying of additional distribution pipe line & allied works at Deulpur Gangadharpur Zone-I PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. |  |  | ORD/000399/2024-2025 | 859/HD | 07/02/2025 | 450 | M/S ASHIRBAD (INDIA) | 87.3 | 0 | 40
1727 | Howrah Division |  | Special repairing work for restoration of damage pavement caused by laying of pipe line from start Node point 36 to End Node point 256 of existing LDS at Deulpur Board Girls primary School to Deulpur Bandher Bazar for the 2.0 km (PMGSY/PWD) road at Deulpur Gangadharpur Zone-I PWSS Under Panchla Block under Howrah Sadar Sub Division of Howrah Howrah Division, P.H.E. Dte. |  |  | ORD/000710/2024-2025 | 1313/HD | 10/03/2025 | 120 | ASSOCIATE CONSTRUCTION | 28.9 | 0 | 0
1728 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 36.76 | 0 | 0
1729 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 86.28 | 0 | 0
1730 | Howrah Division |  | Additional Laying Distribution Pipeline & approach road with land development at OHR site & allied works of Panchla PWSS at Panchla Block of Howrah District under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000030/2024-2025 | 2835/HD | 20/06/2024 | 600 | SAMIRON GHOSH | 66.05 | 0 | 20
1731 | Howrah Division |  | Work Order for Preparation of DPR with Route Survey for new piped water supply scheme of Panchla PWSS (Mouza-Panchla (CT) of Panchla Block under Howrah Division PHE Dte. |  |  | ORD/000077/2022-2023 | 1020/HD | 05/05/2022 | 15 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 100
1732 | Howrah Division |  | Special repairing work for restoration of damage pavement caused by laying of pipe line from Start Node Section 359 to End Node section 873 of existing LDS at MEJUTI BRIDGE TO PANCHLA BAZAR for the 2.7 km (WBSRDA) road at Panchla PWSS in Panchla Block under Howrah Sadar Sub-Division of Howrah Division, P.H.E. Dte. |  |  | ORD/000112/2025-2026 | 3144/HD | 15/07/2025 | 60 | LAKSHMI IRON | 37.39 | 0 | 0
1733 | Howrah Division |  | Different Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, and Construction of different capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Panchla Block, District:-Howrah [NEW SCHEME][Name of Schemes:-1)Paschim Panchla PWSS 2) Panchla PWSS 3) Gabberia-Mallik Bagan PWSS]. |  |  | ORD/000148/2023-2024 | 2866/HD | 08/08/2023 | 910 | SAMIRON GHOSH | 1986.19 | 0 | 30
1734 | Howrah Division |  | Supplying,fitting,fixing and erecting of Swajal Gram (Har Ghar Jal Village) Board at different PWSS of different schemes under Howrah Division P.H.E. Dte. (For, Bally Jagacha & Panchla Block) |  |  | ORD/000220/2025-2026 | 4118/HD | 14/10/2025 | 30 | JHARNA ENTERPRISE | 4.79 | 0 | 0
1735 | Howrah Division |  | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. |  |  | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
1736 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 38.2 | 0 | 0
1737 | Howrah Division |  | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 446/HD | 06/02/2023 | 0 | Resource Division | 62.61 | 0 | 0
1738 | Howrah Division | Ulberia Sub-Division | Restoration of Bituminous Road along with alterntive laying of DI & HDPE (PE 100, PN6) pipes from 1) Basudebpur Lalpool to Basudebpur G.P. Office via. H/W site to Jhuri Battala(PWD), 2) Basudebpur Battala to Basudebpur Shibtala, 3) Nurullapara Battala to Katra Bazar via. Katra Auto Stand, 4) Katra Auto stand to Basudebpur Lalpool, 5) Basudebpur Bazar to Tehatta Mollickpara via. Tehatta Sishu Niketan to Tehatta Balika Vidyalaya, 6) Uttar Magurkhali to Dakshin Magurkhali, 7) Adharmanik IOCL crossing to Adharmanik Pry. School via. Adharmanik HKKS Pry. School & Pramanick para under Baniban Zone-III PWSS under Uluberia Sub-Division of Howrah Division, PHE Dte. | AE/Ulu | JE-USD | ORD/000147/2025-2026 | 3467/HD | 12/08/2025 | 60 | INDICON ENGINEERS CO-OP SOCIETY LTD | 83.93 | 0 | 0
1739 | Howrah Division | Ulberia Sub-Division | Sinking of 3 (Three) Nos. 250 X 150 mm Dia tubewell Drilling by Direct Rotary method with UPVC Pipes all complete, Construction of 3no 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 1000mm) with Sanitary and water Supply arrangement, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around head work site, Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site land development of Head work site and other Tube well sites, Laying distribution system (HDPE & DI) & Providing Household Connection (3191nos), Interconnection between Tube wells & OHR and Construction of 700 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation Baniban with foundation design Baniban Piped Water Supply Scheme (Zone-III) in Uluberia-II Block of Howrah District under Howrah Division, P. H. E. Dte. | AE/Ulu | JE-USD | ORD/000152/2023-2024 | 2960/HD | 16/08/2023 | 1026 | SAMIRON GHOSH | 1022.24 | 0 | 55
1740 | Howrah Division | Ulberia Sub-Division | Preparation of DPR for new piped water supply scheme of Basudebpur PWSS, Uluberia-II Block under Uluberia Sub-Division of Howrah Division PHE Dte.( Banibon, Zone-III) | AE/Ulu | JE-USD | ORD/000251/2022-2023 | 325/AE/USD | 16/08/2022 | 45 | APEX ENGINEERING | 3.76 | 0 | 100
1741 | Howrah Division | Ulberia Sub-Division | Wall writing IEC message along with logo picture etc. of multiple colour as will be supplied by the PHE Dte. On smooth durable wall surface preferably of Govt. premises boundary wall under Uluberia - II block of Uluberia Sub Division under Howrah Division, P.H.E. Dte. | AE/Ulu | JE-USD | ORD/000653/2023-2024 | 1212/HD | 11/03/2024 | 15 | TRIMARV SOLUTIONS PRIVATE LIMITED | 1.85 | 0 | 100
1742 | Howrah Division | Howrah Sadar Sub-Division | Additional distribution pipe line with Rider line and allied works at Jujarsaha PWSS at Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte. (SM/10146) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000064/2024-2025 | 3099/HD | 08/07/2024 | 420 | MA MANASA CONSTRUCTION | 176.73 | 0 | 60
1743 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction of 5.40Mx 3.60M Swtich Room with Plinth Height (600mm to 2000mm) with Sanitary and water Supply arrangement at 4th T/well site of Jujarsah PWSS at Panchla Block of Howrah District under Howrah Division, PHE Dte.. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000074/2023-2024 | 1760/HD | 27/04/2023 | 60 | GRAFTON TARMAC ENGINEERING AND CIVIL | 26.45 | 0 | 0
1744 | Howrah Division | Howrah Sadar Sub-Division | Field level data validation of FHTC for error free database in different Pipe Water Supply Scheme under Panchla and Uluberia-II Block in the District of Howrah under the jurisdiction of Howrah Division, PHE Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000287/2024-2025 | 4816/HD | 19/11/2024 | 390 | TECH VISION | 12.48 | 0 | 62
1745 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Section Node 678-679 to Section Node 804-806 (Part-E) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000339/2022-2023 | 1851/HD | 09/09/2022 | 931 | ADITYA HAZRA | 204.49 | 0 | 30
1746 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. From Section Node 110-123 to Section Node 611-613 (Part-C) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000340/2022-2023 | 1852/HD | 09/09/2022 | 60 | UNIVERSAL CORPORATION | 158.4 | 0 | 60
1747 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Section Node 248-265 to Section Node 449-453 (Part-D) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000359/2022-2023 | 1819/HD | 06/09/2022 | 1330 | N. G ENGINEERING | 183.13 | 0 | 30
1748 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Laying Distribution Pipeline With FHTC of Jujarsah PWSS at Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. From Section 263-307 to Section 526-533 (Part-B) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000367/2022-2023 | 1827/HD | 07/09/2022 | 1310 | M/S ASHIRBAD (INDIA) | 149.32 | 0 | 40
1749 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Construction Of 1250 cum Capacity, 20mtr. Staging Height RCC Elevated Reservoir with Rising Main Pipeline Work & Laying Distribution Pipeline & Providing FHTC (Functional Household Tap Connection) of Augmentation of Jujarsah PWSS Panchla Block of Howrah Sadar Sub Division under Howrah Division, P. H. E. Dte. (Part-A) | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000392/2022-2023 | 1842/HD | 08/09/2022 | 1021 | G.B. CONSTRUCTION AND CO | 356.33 | 0 | 30
1750 | Howrah Division | Howrah Sadar Sub-Division | Work Order for Sinking of 4 (Four) Nos. 300 X 200 mm Dia and 230 m deep tubewell Drilling by Direct Rotary method with UPVC Pipes all complete at Augmentation of Jujarshah PWSS of Panchla Block Howrah Sadar Sub-Division under Howrah Division, P. H. E. Dte. | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | ORD/000692/2022-2023 | 310/HD | 20/01/2023 | 661 | SPG ENTERPRISES | 68.81 | 0 | 0
1751 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000016/2022-2023 | 1624/HD | 05/08/2022 | 0 | Resource Division | 258.1 | 0 | 0
1752 | Howrah Division | Howrah Sadar Sub-Division | Material Requisition To Resource Division | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | RTOR000062/2022-2023 | 2839/HD | 23/12/2022 | 0 | Resource Division | 56.12 | 0 | 0
1753 | Howrah Division | Howrah Sadar Sub-Division | Indent of Material | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000953/2021-2022 | BP-2021-22-402 | 14/03/2022 | 0 | EXECUTIVE ENGINNER RESOURCES DIVISION | 513.19 | 0 | 0
1754 | Howrah Division | Howrah Sadar Sub-Division | Preparation of DPR for augmentation of existing piped water supply scheme of Jujarsha PWSS, Panchla Block under Howrah Sadar Sub-Division of Howrah Division PHE Dte | AE/SADAR,Assistant Engineer Howrah mechanical Sub Division | JE Sadar,Junior Engineer5 | VCH/000957/2021-2022 | BP-2021-22-405 | 14/03/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.36 | 0 | 0
Total | [10 empty] | 139066.67 | 357.12