## Work order List (Rs. in Lakh)
Work order List (Rs. in Lakh)
Sl No. | Division | Sub Division | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Physical Progress %
1 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.07.2024 upto 14.01.2025). | Assistant Engineer RSD |  | ORD/000053/2024-2025 | 2159/RD/PHE | 15/07/2024 | 184 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0
2 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Nalbithi Madhabpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD |  | ORD/000178/2020-2021 | 1238/RD/PHE | 16/10/2020 | 40 | M/S LOKENATH CONST | 91.32 | 0 | 0
3 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | Assistant Engineer RSD |  | ORD/000807/2024-2025 | 296/RD/PHE | 15/01/2025 | 181 | DEBASISH GHOSH | 2.4 | 0 | 0
4 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Barabilla and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000179/2020-2021 | 1241/RD/PHE | 16/10/2020 | 40 | BHOLA PAUL | 62.49 | 23.59 | 0
5 | Raiganj Division | Islampur Sub-Division | FHTC OF BARABILLA PWSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000451/2020-2021 | 1505/RD/PHE | 23/12/2020 | 30 | M/S LUCKY CONSTRUCTION | 11.66 | 0 | 0
6 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002096/2021-2022 | 771/W | 11/03/2022 | 0 | M/S DUTTA ENTERPRISE | 0.07 | 0 | 0
7 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002104/2021-2022 | 767/W | 11/03/2022 | 0 | DIGITEK SOLUTIONS | 0.1 | 0 | 0
8 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of KOTAR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000419/2021-2022 | 2122/RD/PHE | 03/11/2021 | 30 | APEX ENTERPRISES | 8.31 | 0 | 1
9 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Kunore Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000377/2021-2022 | 2072/RD/PHE | 02/11/2021 | 30 | M/S BHOWMIK ENTERPRISE | 8.79 | 0 | 1
10 | Raiganj Division | Raiganj Sub-Division | Route Survey & Preparation of DPR of KUNORE PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000758/2021-2022 | 156/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 4.14 | 0 | 0
11 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000004/2021-2022 | 28/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.06 | 0 | 0
12 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000016/2022-2023 | 1802/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.31 | 0 | 0
13 | Raiganj Division | Islampur Sub-Division | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000040/2022-2023 | 992/RD/PHED | 05/05/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 1
14 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Chopra PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000237/2025-2026 | 1041/RD/PHE | 02/04/2025 | 60 | ASHIM CHANDA | 0.49 | 0 | 0
15 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Chopra Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Chopra Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000276/2021-2022 | 1829/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 3.7 | 0
16 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Chopra Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000387/2021-2022 | 2082/RD/PHE | 02/11/2021 | 30 | M/S LUCKY CONSTRUCTION | 18.64 | 0 | 1
17 | Raiganj Division | Islampur Sub-Division | Retrofitting Of Functional Household Tap Connections(FHTC) under Chopra Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000747/2021-2022 | 486/RD/PHE | 25/02/2022 | 30 | M/S LUCKY CONSTRUCTION | 11.46 | 0 | 0
18 | Raiganj Division | Islampur Sub-Division | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000764/2021-2022 | 598/RD/PHE | 11/03/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 1
19 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000018/2021-2022 | 42/RD/PHE | 06/01/2022 | 0 | Resource Division | 0.29 | 0 | 0
20 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000022/2022-2023 | 1815/RD/PHE | 26/09/2022 | 0 | Resource Division | 3.26 | 0 | 0
21 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Sitlagaon Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Chopra Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000277/2021-2022 | 1813/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.87 | 2.85 | 0
22 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Sitlagaon Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000445/2021-2022 | 2381/RD/PHE | 24/12/2021 | 30 | M/S LUCKY CONSTRUCTION | 9.24 | 0 | 0
23 | Raiganj Division | Islampur Sub-Division | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000760/2021-2022 | 553/RD/PHE | 04/03/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 1
24 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000017/2021-2022 | 41/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.9 | 0 | 0
25 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000024/2022-2023 | 1816/RD/PHE | 28/09/2022 | 0 | Resource Division | 1.23 | 0 | 0
26 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of POALTAIR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000401/2021-2022 | 2104/RD/PHE | 03/11/2021 | 30 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 15.91 | 0 | 1
27 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Choprabari Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000369/2021-2022 | 2150/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 1.38 | 0 | 1
28 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of BARUNA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000399/2021-2022 | 2102/RD/PHE | 03/11/2021 | 30 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 5.16 | 0 | 1
29 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of BAMAIR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000400/2021-2022 | 2103/RD/PHE | 03/11/2021 | 30 | SANKAR DAS | 8.81 | 0 | 1
30 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting ofF PHULATTI Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000402/2021-2022 | 2105/RD/PHE | 03/11/2021 | 30 | RAHUL ENTERPRISE | 6.57 | 0 | 1
31 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of CHOTPARUA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000404/2021-2022 | 2107/RD/PHE | 03/11/2021 | 30 | NIMAI DAS | 9.36 | 0 | 1
32 | Raiganj Division | Raiganj Sub-Division | Preliminary Route Survey for finding feasibility of providing FHTC in different PWSS (Which excluded design year) Preparation of DPR of No.1. Goalpukhur PWSS 2. Lakhipur PWSS 3. Khanta PWSS 4. Hemtabad PWSS 5. Dharampur PWSS Zone-II under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000001/2022-2023 | 896/RD/PHED | 20/04/2022 | 7 | M/S DUTTA ENTERPRISE | 4.46 | 0 | 100
33 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Chandanpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000355/2021-2022 | 2136/RD/PHE | 12/11/2021 | 30 | UTTAM SAHA | 3.94 | 0 | 1
34 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Chandanpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000356/2021-2022 | 2137/RD/PHE | 12/11/2021 | 30 | UTTAM SAHA | 3.94 | 0 | 1
35 | Raiganj Division | Raiganj Sub-Division | office accessories bill | Assistant Engineer RSD | Junior Engineer, RSD | VCH/000320/2022-2023 | BP-2022-23-29 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.06 | 0 | 0
36 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Deona Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000362/2021-2022 | 2143/RD/PHE | 12/11/2021 | 30 | SWAGATA | 4.42 | 0 | 1
37 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Deona Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000430/2021-2022 | 2192/RD/PHE | 17/11/2021 | 30 | HAQUE CONSTRUCTION | 6.19 | 0 | 0
38 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Gunabari Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000432/2021-2022 | 2194/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 6.52 | 0 | 0
39 | Raiganj Division | Islampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Sherpur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Raiganj,Capacity- 90 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000003/2021-2022 | 1208/RD/PHE | 18/06/2021 | 90 | M/S LOKENATH CONSTRUCTION | 37.36 | 0 | 0
40 | Raiganj Division | Islampur Sub-Division | Supplying, Laying, Fixing and Jointing of UPVC Pipe including Dismantling PCC & Ordinary Cement Concrete [1:2:4] in connection with retrofitting of FHTC under TUNGAIL BILLPARA & Adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division ,P.H.E Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000108/2020-2021 | 475/RD/PHE | 26/02/2021 | 30 | M/S.SADHANA ENTERPRISE | 6.36 | 0 | 0
41 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Puria and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000126/2020-2021 | 362/RD/PHE | 04/02/2021 | 40 | UTTAM SAHA | 91.12 | 0 | 1
42 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Gutin and adjoining Mouzas Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000135/2020-2021 | 1528/RD/PHE | 23/12/2020 | 45 | M/S LOKENATH CONST | 101.7 | 0 | 0
43 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at under Baruna and adjoining Mouza Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000137/2020-2021 | 1527/RD/PHE | 23/12/2020 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 104.88 | 0 | 0
44 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Tungail Bilpara and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000139/2020-2021 | 1524/RD/PHE | 23/12/2020 | 45 | SANYAL ENTERPRISE | 110.26 | 0 | 0
45 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Gopalpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000140/2020-2021 | 1533/RD/PHE | 23/12/2020 | 45 | M/S LOKENATH CONST | 110.89 | 0 | 0
46 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Dakhin Jibakata and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000141/2020-2021 | 1540/RD/PHE | 23/12/2020 | 45 | CALCON CONSTRUCTION | 126.63 | 0 | 100
47 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Sitgram and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000143/2020-2021 | 1537/RD/PHE | 23/12/2020 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 103.65 | 0 | 15
48 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Bamair and adjoining Mouzas Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000144/2020-2021 | 1531/RD/PHE | 23/12/2020 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 116.81 | 0 | 0
49 | Raiganj Division | Islampur Sub-Division | FHTC OF MAHINAGAR WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000159/2020-2021 | 1504/RD | 23/12/2020 | 25 | M/S ARVI CONSTRUCTION | 3.06 | 0 | 0
50 | Raiganj Division | Islampur Sub-Division | FHTC OF GOPALPUR WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000160/2020-2021 | 1502/RD | 23/12/2020 | 25 | KARTICK BISWAS | 1.8 | 0 | 0
51 | Raiganj Division | Islampur Sub-Division | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Pokheria and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000165/2020-2021 | 374/RD/PHE | 05/02/2021 | 25 | SARNALI ENTERPRISE | 3.36 | 0 | 1
52 | Raiganj Division | Islampur Sub-Division | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Sridharpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000166/2020-2021 | 375/RD/PHE | 05/02/2021 | 25 | GOPES SAHA | 3.33 | 0 | 1
53 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kaliganj and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000172/2020-2021 | 1544/RD/PHE | 23/12/2020 | 40 | NEOGI ENTERPRISE | 98.37 | 0 | 0
54 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Sridharpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000173/2020-2021 | 1526/RD/PHE | 23/12/2020 | 45 | AJIT PARMANIK | 126.43 | 0 | 0
55 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Bindol and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000174/2020-2021 | 1529/RD/PHE | 23/12/2020 | 45 | AJIT PARMANIK | 125.64 | 0 | 0
56 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Mahinagar and adjoining Mouzas Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000175/2020-2021 | 1543/RD/PHE | 23/12/2020 | 40 | SANYAL ENTERPRISE | 96.95 | 0 | 0
57 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Deona and adjoining Mouzas Water Supply Scheme in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000177/2020-2021 | 1542/RD/PHE | 23/12/2020 | 40 | MAMATA USHA ENTERPRISE | 94.51 | 0 | 0
58 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for improving FHTC nos. of Jaingaon Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000186/2022-2023 | 2256/RD/PHE | 22/12/2022 | 30 | APEX ENTERPRISES RUPESH.RNJ@GMAIL.COM | 5.75 | 0 | 0
59 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Gunabari and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000203/2020-2021 | 1534 /RD/PHE | 23/12/2020 | 45 | M/S LOKENATH CONSTRUCTION | 122.2 | 0 | 0
60 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Jaingaon and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000204/2020-2021 | 1538/RD/PHE | 23/12/2020 | 45 | M/S SOMNATH KUNDU | 104.31 | 0 | 90
61 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Pokheria and adjoining Mouzas Water Supply Scheme in Goalpoklher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000205/2020-2021 | 1530/RD/PHE | 23/12/2020 | 45 | AJIT PARMANIK | 134.73 | 0 | 50
62 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) under Poaltair and adjoining Mouzas water supply scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000209/2020-2021 | 1539/RD/PHE | 23/12/2020 | 45 | SANYAL ENTERPRISE | 106.28 | 0 | 0
63 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Phulatti and adjoining mouzas Water Supply Scheme in Kaliaganj Block in under Raiganj Division.(Part-III) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000236/2020-2021 | 476/RD/PHE | 26/02/2021 | 45 | SUBHAS CHOWDHURY | 4.1 | 0 | 0
64 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at under Bheur and adjoining Mouza Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000277/2020-2021 | 1557/RD/PHE | 24/12/2020 | 60 | UTTAM SAHA | 124.33 | 0 | 100
65 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER PAHARAJPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN ITAHAR BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000278/2020-2021 | 1560/RD/PHE | 24/12/2020 | 60 | J.D.J. ENTERPRISE | 133.31 | 0 | 0
66 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER BHAGABATI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN CHOPRA BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000279/2020-2021 | 1564/RD/PHE | 24/12/2020 | 60 | M/S LOKENATH CONSTRUCTION | 194.09 | 0 | 0
67 | Raiganj Division | Islampur Sub-Division | Providing Functional House Hold Connection (FHTC) for the purpose of Bheur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000279/2022-2023 | 493/RD/PHE | 17/02/2023 | 45 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 6.22 | 0 | 0
68 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Providing Functional Household Tap Connection for Sridharpur(Paharajpur) Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000286/2022-2023 | 500/RD/PHE | 17/02/2023 | 45 | SANDIP SARKAR | 7.18 | 0 | 0
69 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING FIXING AND JOINTING UPVC PIPE INCLUDING DISMANTLING PCC FHTC OF GUTIN PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000367/2020-2021 | 1514/RD | 23/12/2020 | 30 | M/S.BANGARAJ | 9.92 | 0 | 0
70 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Jaingaon for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000434/2021-2022 | 2196/RD/PHE | 17/11/2021 | 30 | M/S SARKAR ENTERPRISE | 44.62 | 0 | 0
71 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING FIXING OF FHTC OF JAINGAON PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000440/2020-2021 | 1498/RD | 23/12/2020 | 25 | DULAL MAJUMDER | 3.82 | 0 | 0
72 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING FIXING OF FHTC OF GUNABARI PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000441/2020-2021 | 1499/RD | 23/12/2020 | 25 | M/S GHOSH CONSTRUCTION | 2.5 | 0 | 0
73 | Raiganj Division | Islampur Sub-Division | SUPPLYING FITTING UPVC PIPE FOR KALIGANJ PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000447/2020-2021 | 1503/RD | 23/12/2020 | 25 | ALI ENTERPRISE | 2.75 | 0 | 0
74 | Raiganj Division | Islampur Sub-Division | Restoration of damaged Pipe Line work required for FHTC work at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000452/2021-2022 | 2428/RD/PHE | 31/12/2021 | 30 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.87 | 0 | 100
75 | Raiganj Division | Islampur Sub-Division | supply, laying, fitting , fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1;2:4) for FHTC under Bhagabati and adjoining mouzas water supply scheme in chopra block under Raiganj Division, P.h.e.dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000463/2020-2021 | 1509/RD/PHE | 23/12/2020 | 30 | PRINCE BUILDERS | 8.31 | 0 | 0
76 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING FIXING AND JOINTING OF UPVC PIPE INCLUDING DISMANTLING PCC OF FHTC OF DEONA PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000464/2020-2021 | 1507/RD | 23/12/2020 | 30 | M/S LUCKY CONSTRUCTION | 11.66 | 0 | 0
77 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING FIXING AND JOINTING UPVC PIPE INCLUDING DISMANTLING PCC FHTC OF BAMAIR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000465/2020-2021 | 1508/RD/PHE | 23/12/2020 | 30 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.91 | 0 | 0
78 | Raiganj Division | Islampur Sub-Division | office accessories bill | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/000312/2022-2023 | BP-2022-23-36 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.13 | 0 | 0
79 | Raiganj Division | Islampur Sub-Division | office accessories bill | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/000325/2022-2023 | BP-2022-23-28 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
80 | Raiganj Division | Islampur Sub-Division | office accessories bill | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/000327/2022-2023 | BP-2022-23-26 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0
81 | Raiganj Division | Islampur Sub-Division | Supply of urgent office article against laying of additional pipeline Siripur | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/001438/2022-2023 | BP-2022-23-158 | 28/09/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
82 | Raiganj Division | Islampur Sub-Division | Supply of urgent office article against laying of additional pipeline Siripur | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/001440/2022-2023 | BP-2022-23-159 | 28/09/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
83 | Raiganj Division | Islampur Sub-Division | hire charge of vehicle | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/001732/2022-2023 | BP-2022-23-137 | 12/09/2022 | 0 | DIGENDRANATH DAS | 0.04 | 0 | 0
84 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Faridpur Piped Water Supply Scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000137/2022-2023 | 1915/RD/PHE | 28/10/2022 | 901 | M/S P.S. ENTERPRISE | 39.95 | 0 | 70
85 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000120/2023-2024 | 16/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
86 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Dopaharu Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000310/2025-2026 | 1978/RD/PHE | 03/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.74 | 0 | 0
87 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
88 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at BARA DOPAHARU PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000385/2025-2026 | 2097/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 43.32 | 0 | 0
89 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Bara Dopaharu Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000389/2025-2026 | 2174/RD/PHE | 25/07/2025 | 90 | M/S SHIB ENTERPRISE | 5.4 | 0 | 0
90 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000004/2023-2024 | 1036/RD/PHE | 04/04/2023 | 0 | Resource Division | 25.91 | 0 | 0
91 | Raiganj Division | Islampur Sub-Division | Augmentation of PANJIPARA (Zone-I)Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000104/2022-2023 | 1551/RD/PHE | 26/08/2022 | 90 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 162.49 | 0 | 0
92 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, & 3rd Tube-Well Site under Augmentation of Panjipara PWSS at Goalpukhur-I Block under Raiganj Division, PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000160/2024-2025 | 2892/RD/PHE | 25/09/2024 | 180 | HAQUE CONSTRUCTION | 26.07 | 0 | 60
93 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Panjipara Zone-I Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000164/2022-2023 | 2024/RD/PHE | 17/11/2022 | 992 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 82.85 | 0 | 40
94 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000243/2022-2023 | 374/RD/PHE | 07/02/2023 | 45 | M/S PAYEL CONSTRUCTION HIMADRI.RNJ@GMAIL.COM | 5.01 | 0 | 100
95 | Raiganj Division | Islampur Sub-Division | Repair Pump House 2nd Tube well & 3rd Tubewell Site in connection with Augmentation of Panjipara Zone-I piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000247/2022-2023 | 377/RD/PHE | 07/02/2023 | 540 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 2.1 | 0 | 100
96 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-400 Cum) of PANJIPARA (Zone-I) Pipe Water Supply Scheme in connection with Augmentation at Goalpokher-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000379/2022-2023 | 734/RD/PHE | 15/03/2023 | 636 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 143.15 | 0 | 80
97 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panjipara Zone-I Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000410/2025-2026 | 2509/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 32.36 | 0 | 0
98 | Raiganj Division | Islampur Sub-Division | Providing FHTC at Panjipara Santinagar of Panjipara Zone-I PWSS in connection with Augmentation of Panjipara Zone-I PWSS in Goalpukhur-I Block of Uttar Dinajpur under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000415/2023-2024 | 2787/RD/PHE | 11/10/2023 | 30 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 2.87 | 0 | 100
99 | Raiganj Division | Islampur Sub-Division | Balance pipeline with dismantling of concrete road in connection with Augmentation Of Panjipara Zone-I PWSS at Goalpukhur-I Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000513/2024-2025 | 44/RD/PHE | 03/01/2025 | 45 | M/S J.M.M. CONSTRUCTION | 22.75 | 0 | 0
100 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC for Augmentation of Panjipara Zone-I Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division., P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000515/2024-2025 | 3801/RD/PHE | 20/12/2024 | 180 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 28.73 | 0 | 0
101 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000568/2022-2023 | 1031/RD/PHE | 31/03/2023 | 504 | M/S PAYEL CONSTRUCTION HIMADRI.RNJ@GMAIL.COM | 4.1 | 0 | 100
102 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
103 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000045/2022-2023 | 1972/RD/PHE | 08/11/2022 | 0 | Resource Division | 142.48 | 0 | 0
104 | Raiganj Division | Raiganj Sub-Division | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of North East Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00178/2024-2025 | BP-2024-25-106 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 0.12 | 0 | 0
105 | Raiganj Division | Raiganj Sub-Division | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of Northeast Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00271/2024-2025 | BP-2024-25-177 | 29/08/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.81 | 0 | 0
106 | Raiganj Division | Raiganj Sub-Division | Implementation of CHAKDILAL and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000241/2022-2023 | 292/RD/PHE | 01/02/2023 | 1065 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 620.92 | 0 | 58
107 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chakdilal PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000425/2024-2025 | 3737/RD/PHE | 18/12/2024 | 135 | AJIT PRAMANIK | 68.07 | 0 | 0
108 | Raiganj Division | Raiganj Sub-Division | Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAKDILAL Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000527/2023-2024 | 580/RD/PHE | 05/03/2024 | 148 | M C CONSTRUCTION | 11.27 | 0 | 100
109 | Raiganj Division | Raiganj Sub-Division | Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAKDILAL Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000528/2023-2024 | 595/RD/PHE | 05/03/2024 | 148 | M/S. ROY & CO. | 11.27 | 0 | 100
110 | Raiganj Division | Raiganj Sub-Division | Trial Run For Chakdilal PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000673/2024-2025 | 519/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0
111 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000063/2022-2023 | 2180/RD/PHE | 12/12/2022 | 0 | Resource Division | 39.53 | 0 | 0
112 | Raiganj Division | Raiganj Sub-Division | Implementation of UTTAR LAKSHMIPUR andit's adjoining mouzas Pipe Water Supply Scheme at KALIYAGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000200/2022-2023 | 69/RD/PHE | 16/01/2023 | 665 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 232.09 | 0 | 70
113 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
114 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000093/2022-2023 | 30/RD/PHE | 06/01/2023 | 0 | Resource Division | 24.11 | 0 | 0
115 | Raiganj Division | Raiganj Sub-Division | DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/01224/2023-2024 | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 5.18 | 0 | 0
116 | Raiganj Division | Raiganj Sub-Division | Laying distribution of rising main and Balance Pipeline for Implementation of ADIAR and its adjoining mouzas Piped Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. (Phase-1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000063/2024-2025 | 2226/RD/PHE | 23/07/2024 | 60 | M/S SOMNATH KUNDU | 32.67 | 0 | 63
117 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Adiar Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000290/2025-2026 | 1816/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 19.35 | 0 | 0
118 | Raiganj Division | Raiganj Sub-Division | Implementation of ADAIR and its adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte(2nd Call). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000325/2022-2023 | 621/RD/PHE | 28/02/2023 | 455 | M/S SOMNATH KUNDU | 338.34 | 0 | 60
119 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000409/2024-2025 | 3045/RD/PHE | 04/10/2024 | 90 | ARNAB DUTTA | 1.2 | 0 | 0
120 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Adiar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000443/2024-2025 | 3755/RD/PHED | 18/12/2024 | 45 | M/S SOMNATH KUNDU | 30.08 | 0 | 0
121 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ADIAR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000463/2023-2024 | 571/RD/PHE | 05/03/2024 | 135 | BHOLA PAUL | 22.57 | 0 | 100
122 | Raiganj Division | Raiganj Sub-Division | Trial Run For Adiar PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000698/2024-2025 | 539/RD/PHE | 12/02/2025 | 90 | M/S SOMNATH KUNDU | 0.88 | 0 | 0
123 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000082/2022-2023 | 2200/RD/PHE | 14/12/2022 | 0 | Resource Division | 28.55 | 0 | 0
124 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kamalpur Water Supply Scheme at Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 20 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000291/2025-2026 | 1818/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 15.38 | 0 | 0
125 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000016/2023-2024 | 1123/RD/PHE | 24/04/2023 | 0 | Resource Division | 23.6 | 0 | 0
126 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
127 | Raiganj Division | Raiganj Sub-Division | Providing functional house hold tap connection at village-Dakhshin Bishnupur of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000100/2023-2024 | 2047/RD/PHE | 19/07/2023 | 622 | SANDIP SARKAR | 16.32 | 0 | 0
128 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000290/2022-2023 | 539/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 65
129 | Raiganj Division | Raiganj Sub-Division | Laying of pipe line at Village-Amritakhanda of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000409/2022-2023 | 764/RD/PHE | 17/03/2023 | 60 | M/S PIONEER ENTERPRISE | 40.84 | 0 | 20
130 | Raiganj Division | Raiganj Sub-Division | Construction of boundary wall and Pump house at 2nd tube-well of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000414/2022-2023 | 769/RD/PHE | 17/03/2023 | 540 | DULAL DUTTA | 11.28 | 0 | 100
131 | Raiganj Division | Raiganj Sub-Division | Providing functional house hold tap connection at Village-Amritkhanda of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000419/2022-2023 | 774/RD/PHE | 17/03/2023 | 60 | M/S BHOWMIK CONSTRUCTION | 16 | 0 | 0
132 | Raiganj Division | Raiganj Sub-Division | Laying distribution of Pipe line of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000473/2022-2023 | 820/RD/PHE | 22/03/2023 | 45 | M/S P.S. ENTERPRISE | 47.35 | 0 | 20
133 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bishahar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000483/2024-2025 | 16/RD/PHE | 02/01/2025 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 24.95 | 0 | 0
134 | Raiganj Division | Raiganj Sub-Division | Construction of Pump house and boundary wall at Head Work Site of Bishahar PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000487/2022-2023 | 826/RD/PHE | 22/03/2023 | 60 | DISCOVERY CO. OPERATIVE LABOUR CONT AND CONST SOC. LTD. | 24.86 | 0 | 0
135 | Raiganj Division | Raiganj Sub-Division | Construction of OHR (Capacity-250Cum) of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur district under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000510/2022-2023 | 853/RD/PHE | 24/03/2023 | 275 | DIPAK SAHA | 95.39 | 0 | 0
136 | Raiganj Division | Raiganj Sub-Division | Laying, Rising-Main of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000515/2022-2023 | 858/RD/PHE | 24/03/2023 | 60 | M/S MANDAL ENTERPRISE TUMPASONU05@YAHOO.COM | 4.52 | 0 | 0
137 | Raiganj Division | Raiganj Sub-Division | Laying of Pipe Line at village-Birahimkhanda & Ital of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000520/2022-2023 | 874/RD/PHE | 27/03/2023 | 60 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 41.03 | 0 | 20
138 | Raiganj Division | Raiganj Sub-Division | Providing functional House hold tap connection at village-Birhimkhanda & Ital of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000529/2022-2023 | 879/RD/PHE | 27/03/2023 | 735 | SANDIP SARKAR | 15.22 | 0 | 15
139 | Raiganj Division | Raiganj Sub-Division | Laying pipe line at Dakhshin Bishnupur of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000537/2022-2023 | 949/RD/PHED | 29/03/2023 | 60 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 40.88 | 0 | 15
140 | Raiganj Division | Raiganj Sub-Division | Laying Pipe line at Village-Bishahar of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000547/2022-2023 | 959/RD/PHE | 29/03/2023 | 60 | MAA SHEETALA ENTERPRISE | 40.95 | 0 | 35
141 | Raiganj Division | Raiganj Sub-Division | Providing Functional House Hold Tap Connection at village- Bishahar of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000548/2022-2023 | 960/RD/PHE | 29/03/2023 | 60 | DAS CONSTRUCTION COMPANY | 15.45 | 0 | 0
142 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000058/2023-2024 | 1679/RD/PHE | 19/06/2023 | 0 | Resource Division | 39.44 | 0 | 0
143 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PRATAPPUR PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000270/2025-2026 | 2087/RD/PHE | 14/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 38.64 | 0 | 0
144 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pratappur Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000341/2025-2026 | 1803/RD/PHE | 24/06/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 29.55 | 0 | 0
145 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000026/2023-2024 | 1201/RD/PHE | 28/04/2023 | 0 | Resource Division | 37.78 | 0 | 0
146 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Damodarkhuri Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000005/2025-2026 | 1172/RD/PHE | 23/04/2025 | 30 | ANILA CONSTRUCTION | 10.08 | 0 | 0
147 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Damodarkhuri Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000350/2025-2026 | 2496/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.58 | 0 | 0
148 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
149 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000147/2022-2023 | 848/RD/PHE | 24/03/2023 | 0 | Resource Division | 30.26 | 0 | 0
150 | Raiganj Division | Islampur Sub-Division | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of Islampur- Amaljhari- Sonamoti Road under Uttar Dinajpur division, PWD. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00506/2023-2024 | BILL/00506/2023 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 7.97 | 0 | 0
151 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PANDITPOTA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000052/2024-2025 | 1711/RD/PHE | 10/06/2024 | 270 | BHAGYA LAXMI ENTERPRISE | 22.59 | 0 | 0
152 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panditpota Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000296/2025-2026 | 1924/RD/PHE | 30/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.74 | 0 | 0
153 | Raiganj Division | Islampur Sub-Division | Implementation of PANDITPOTA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000307/2022-2023 | 569/RD/PHE | 23/02/2023 | 1038 | SANYAL ENTERPRISE | 320.79 | 0 | 81
154 | Raiganj Division | Islampur Sub-Division | Construction Of Single Row 1200 Mm Dia Np3 Hume Pipe Culvert In Front Of Panditpota Head Works Site For Approach Road Under Raiganj Division, Phe Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000414/2024-2025 | 3578/RD/PHE | 05/12/2024 | 15 | UTTAM SAHA | 3.13 | 0 | 0
155 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipeline ,FHTC with Land development and Path way for PANDITPOTA Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000417/2024-2025 | 3581/RD/PHE | 05/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 65.94 | 0 | 0
156 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Panditpota Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000509/2024-2025 | 54/RD/PHE | 03/01/2025 | 45 | SANYAL ENTERPRISE | 10.39 | 0 | 0
157 | Raiganj Division | Islampur Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
158 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000106/2022-2023 | 599/RD/PHE | 27/02/2023 | 0 | Resource Division | 24.54 | 0 | 0
159 | Raiganj Division | RWS Raiganj Sub-Divisin | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
160 | Raiganj Division | RWS Raiganj Sub-Divisin | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000295/2022-2023 | 541/RD/PHE | 22/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 60
161 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for LAHUTARA Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000367/2024-2025 | 3486/RD/PHE | 02/12/2024 | 30 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16.66 | 0 | 0
162 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of Additional pipeline with other ancillary works at different mouzas of LAHUTARA PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000379/2024-2025 | 3498/RD/PHE | 02/12/2024 | 270 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 48.12 | 0 | 30
163 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying pipe line at village- Dhangaon of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000407/2022-2023 | 762/RD/PHE | 17/03/2023 | 60 | CHAITANYA SAMAL | 48.9 | 0 | 0
164 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of Boundary Wall and Pump House at 2nd Tube-well site of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000412/2022-2023 | 767/RD/PHE | 17/03/2023 | 60 | M/S UNIQUE 13 | 11.28 | 0 | 0
165 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village- Dhangaon of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000417/2022-2023 | 772/RD/PHE | 17/03/2023 | 60 | M/S P.S. ENTERPRISE | 17.95 | 0 | 0
166 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying distribution of pipe line of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000469/2022-2023 | 818/RD/PHE | 22/03/2023 | 730 | BHOWMICK ENTERPRISE | 50.31 | 0 | 70
167 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of OHR(Capacity-300Cum) of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte.. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000508/2022-2023 | 851/RD/PHE | 24/03/2023 | 709 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 96.67 | 0 | 0
168 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of Rising Main of LAHUTARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000513/2022-2023 | 856/RD/PHE | 24/03/2023 | 60 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 5.25 | 0 | 0
169 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of Pipe line of village-Bhagdarin of LAHUTARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000518/2022-2023 | 872/RD/PHE | 27/03/2023 | 608 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 47.52 | 0 | 75
170 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village- Bhagdoarin of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000527/2022-2023 | 877/RD/PHE | 27/03/2023 | 60 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 17.08 | 0 | 0
171 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of pipe line at village -Lahutara & Gurul Bhasa of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000535/2022-2023 | 947/RD/PHED | 29/03/2023 | 60 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 48.48 | 0 | 0
172 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village- Lahutara & Gurulbhasa of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000540/2022-2023 | 952/RD/PHE | 29/03/2023 | 60 | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 19.57 | 0 | 0
173 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village-Lahutara of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RWS SD | Junior Engineer, RWS | ORD/000545/2022-2023 | 957/RD/PHE | 29/03/2023 | 481 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16.29 | 0 | 0
174 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer RWS SD | Junior Engineer, RWS | RTOR000041/2023-2024 | 1321/RD/PHE | 12/05/2023 | 0 | Resource Division | 44.41 | 0 | 0
175 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
176 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Chitaura piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000404/2025-2026 | 2362/RD/PHE | 25/08/2025 | 45 | MILAN GHOSH | 61.51 | 0 | 0
177 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000159/2022-2023 | 902/RD/PHE | 28/03/2023 | 0 | Resource Division | 60.85 | 0 | 0
178 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Barobilla Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000188/2022-2023 | 56/RD/PHE | 16/01/2023 | 45 | SUSANTA GOBINDA DEB GOPALDEB9475@GMAIL.COM | 28.53 | 0 | 60
179 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000098/2023-2024 | 2388/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
180 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000290/2022-2023 | 539/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 65
181 | Raiganj Division | Raiganj Sub-Division | Laying Pipeline at village-Aulabari of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000408/2022-2023 | 763/RD/PHE | 17/03/2023 | 60 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 50.29 | 0 | 65
182 | Raiganj Division | Raiganj Sub-Division | Construction of boundary wall and pump house at 2nd tube-well site of DHOABISHUA PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000413/2022-2023 | 768/RD/PHE | 17/03/2023 | 60 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 11 | 0 | 80
183 | Raiganj Division | Raiganj Sub-Division | Providing Functional House hold tap connection at village- Aulabari of DHOABISHUA Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000418/2022-2023 | 773/RD/PHE | 17/03/2023 | 775 | BITTU ENTERPRISE BISWAJIT.RNJ@GMAIL.COM | 15.25 | 0 | 0
184 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dhoabishua PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000436/2024-2025 | 3743/RD/PHE | 18/12/2024 | 135 | DONE ENTERPRISE | 14.77 | 0 | 0
185 | Raiganj Division | Raiganj Sub-Division | Laying distribution of pipe line of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000470/2022-2023 | 819/RD/PHE | 22/03/2023 | 675 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 57.91 | 0 | 60
186 | Raiganj Division | Raiganj Sub-Division | Construction of boundary wall and pump house at head work site of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000486/2022-2023 | 825/RD/PHE | 22/03/2023 | 395 | M/S. ROY & CO. | 24.75 | 0 | 95
187 | Raiganj Division | Raiganj Sub-Division | Construction of OHR (Capacity-250Cum) with pipeline of Dhoabishua Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000509/2022-2023 | 852/RD/PHE | 24/03/2023 | 725 | M/S RATAN SARKAR & SON | 95.77 | 0 | 45
188 | Raiganj Division | Raiganj Sub-Division | Laying Rising Main of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000514/2022-2023 | 857/RD/PHE | 24/03/2023 | 60 | M/S DAS CONSTRUCTION ITAHAR | 4.52 | 0 | 0
189 | Raiganj Division | Raiganj Sub-Division | Laying pipe line of village-Balihar & Shialtore of DHOABISHUA PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000519/2022-2023 | 873/RD/PHE | 27/03/2023 | 705 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 46.8 | 0 | 65
190 | Raiganj Division | Raiganj Sub-Division | Providing functional house hold tap connection at Village-Balihar & Shialtore of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000528/2022-2023 | 878/RD/PHE | 27/03/2023 | 764 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 15.99 | 0 | 0
191 | Raiganj Division | Raiganj Sub-Division | Laying pipe line of village- Deogaon & Ekar of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000536/2022-2023 | 948/RD/PHED | 29/03/2023 | 360 | S. B. CONSTRUCTION | 50.92 | 0 | 55
192 | Raiganj Division | Raiganj Sub-Division | Providing Functional house Hold Tap Connections at village- Balihar and Ekar of DHOABISHUA Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000541/2022-2023 | 953/RD/PHE | 29/03/2023 | 823 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 16.18 | 0 | 0
193 | Raiganj Division | Raiganj Sub-Division | Providing functional house hold tap connection of village-Dhoabishua of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000546/2022-2023 | 958/RD/PHE | 29/03/2023 | 763 | M/S P.S. ENTERPRISE | 15.41 | 0 | 0
194 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000057/2023-2024 | 1680/RD/PHE | 19/06/2023 | 0 | Resource Division | 42.41 | 0 | 0
195 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pakhuria Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 5 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000265/2025-2026 | 1631/RD/PHE | 20/06/2025 | 180 | AJIT PRAMANIK | 12.4 | 0 | 0
196 | Raiganj Division | Raiganj Sub-Division | Implementation of Pakhuria and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000273/2022-2023 | 679/RD/PHE | 06/03/2023 | 90 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 48.68 | 0 | 40
197 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under PAKHURIA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000495/2023-2024 | 615/RD/PHE | 05/03/2024 | 45 | GOPES SAHA | 5.57 | 0 | 100
198 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
199 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000056/2023-2024 | 1678/RD/PHE | 19/06/2023 | 0 | Resource Division | 3.19 | 0 | 0
200 | Raiganj Division | Raiganj Sub-Division | Implementation of HARINARAYANPUR(Zone- II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000014/2023-2024 | 1276/RD/PHE | 08/05/2023 | 900 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 306.66 | 0 | 10
201 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000491/2024-2025 | 24/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.97 | 0 | 0
202 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HARINARAYANPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000509/2023-2024 | 634/RD/PHE | 05/03/2024 | 45 | M/S R.D. CONSTRUCTION | 24.48 | 0 | 0
203 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
204 | Raiganj Division | Raiganj Sub-Division | Trial Run For Harinarayanpur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000687/2024-2025 | 533/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0
205 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000142/2022-2023 | 809/RD/PHE | 21/03/2023 | 0 | Resource Division | 20.28 | 0 | 0
206 | Raiganj Division | Raiganj Sub-Division | Implementation of MAHADIPUR Mini Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | ORD/000054/2023-2024 | 1561/RD/PHE | 29/05/2023 | 90 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 58.48 | 0 | 20
207 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | RTOR000076/2023-2024 | 2254/RD/PHE | 03/08/2023 | 0 | Resource Division | 5.67 | 0 | 0
208 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 08.07.2024 to 12.07.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | BILL/00231/2024-2025 | BP-2024-25-156 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
209 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 01.07.2024 to 05.07.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | BILL/00232/2024-2025 | BP-2024-25-155 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
210 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 29.07.2024 to 02.08.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | BILL/00275/2024-2025 | BP-2024-25-180 | 30/08/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
211 | Raiganj Division | Raiganj Sub-Division | Implementation of BANKUR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | ORD/000050/2023-2024 | 1557/RD/PHE | 29/05/2023 | 90 | UTTAM SAHA | 84.34 | 0 | 55
212 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bankur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | ORD/000348/2025-2026 | 2494/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.82 | 0 | 0
213 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road,Laying Of Pipe Line And Other Allied Works Of Bankur Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | ORD/000401/2024-2025 | 3570/RD/PHE | 05/12/2024 | 30 | UTTAM SAHA | 11.15 | 0 | 0
214 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-06 | RTOR000080/2023-2024 | 2257/RD/PHE | 03/08/2023 | 0 | Resource Division | 6.26 | 0 | 0
215 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
216 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000035/2023-2024 | 1315/RD/PHE | 12/05/2023 | 0 | Resource Division | 6.2 | 0 | 0
217 | Raiganj Division | Raiganj Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 100
218 | Raiganj Division | Raiganj Sub-Division | Construction of Approach Road, Laying of Pipe Line, FHTC And Other Allied Works of Kaliganj(Bangar) Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000390/2024-2025 | 3560/RD/PHE | 05/12/2024 | 91 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 18.03 | 0 | 0
219 | Raiganj Division | Raiganj Sub-Division | Augmentation of Kaliganj (Bangar) and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000524/2022-2023 | 884/RD/PHE | 27/03/2023 | 989 | BHOLA PAUL | 78.26 | 0 | 30
220 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000010/2023-2024 | 1106/RD/PHE | 20/04/2023 | 0 | Resource Division | 6.34 | 0 | 0
221 | Raiganj Division | Islampur Sub-Division | Implementation of TUNIBHITA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000362/2023-2024 | 2477/RD/PHE | 24/08/2023 | 576 | CALCON CONSTRUCTION | 843.51 | 0 | 50
222 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipeline with pathway at TUNIBHITA Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000385/2024-2025 | 3555/RD/PHE | 05/12/2024 | 45 | CALCON CONSTRUCTION | 53.07 | 0 | 0
223 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under TUNIVITA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000513/2023-2024 | 642/RD/PHE | 05/03/2024 | 183 | DULAL DUTTA | 27.71 | 0 | 100
224 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000133/2022-2023 | 637/RD/PHE | 02/03/2023 | 0 | Resource Division | 58.92 | 0 | 0
225 | Raiganj Division | Raiganj Sub-Division | Implementation of SURANGAPUR (ZONE-III) and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000083/2023-2024 | 1995/RD/PHE | 13/07/2023 | 270 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 164.11 | 0 | 40
226 | Raiganj Division | Raiganj Sub-Division | Approach road with land development of headwork site and road restoration of Surangapur zone III PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000472/2024-2025 | 05/RD/PHE | 02/01/2025 | 45 | M/S ROYAL CONSTRUCTION | 5.7 | 0 | 0
227 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under SURANGAPUR ZONE-III PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000517/2023-2024 | 648/RD/PHE | 05/03/2024 | 45 | M/S ARITRA DUTTA | 5.56 | 0 | 0
228 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
229 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000065/2023-2024 | 2239/RD/PHE | 02/08/2023 | 0 | Resource Division | 11.53 | 0 | 0
230 | Raiganj Division | Islampur Sub-Division | Implementation of TOPAMARI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000076/2023-2024 | 2003/RD/PHE | 13/07/2023 | 626 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 833.91 | 0 | 50
231 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Topamari Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000278/2025-2026 | 1797/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.36 | 0 | 0
232 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Topamari piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000382/2024-2025 | 3501/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 40.29 | 0 | 0
233 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Topamari Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000383/2024-2025 | 3502/RD/PHE | 02/12/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 15.72 | 0 | 0
234 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under TOPAMARI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000455/2023-2024 | 563/RD/PHE | 05/03/2024 | 450 | MS SANDHYA CONSTRUCTION | 27.69 | 0 | 95
235 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000113/2022-2023 | 602/RD/PHE | 27/02/2023 | 0 | Resource Division | 57.96 | 0 | 0
236 | Raiganj Division | Raiganj Sub-Division | Implementation of KALUA and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000164/2023-2024 | 2090/RD/PHE | 27/07/2023 | 990 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 798.98 | 0 | 56
237 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kalua Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 150 M3/hr. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000303/2025-2026 | 2472/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 52.02 | 0 | 0
238 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Kalua PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000434/2024-2025 | 3747/RD/PHE | 18/12/2024 | 135 | AJIT PRAMANIK | 84.29 | 0 | 0
239 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work, 2nd, 3rd, 4th & 5th Tube-Well Site under KALUA PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000518/2023-2024 | 651/RD/PHE | 05/03/2024 | 360 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 37.97 | 0 | 80
240 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
241 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
242 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000069/2023-2024 | 2243/RD/PHE | 02/08/2023 | 0 | Resource Division | 99.68 | 0 | 0
243 | Raiganj Division | Islampur Sub-Division | Barbed Fencing work at Kamartor Head Work Site of Kamartor Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000184/2022-2023 | 2254/RD/PHE | 22/12/2022 | 596 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 1.49 | 0 | 100
244 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kamartor and Adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000270/2020-2021 | 1414/RD/PHE | 11/12/2020 | 40 | J.D.J. ENTERPRISE | 88.73 | 0 | 100
245 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 18.06.2024 to 21.06.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00226/2024-2025 | BP-2024-25-153 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
246 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 24.06.2024 to 28.06.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00227/2024-2025 | BP-2024-25-154 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
247 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 22.07.2024 to 26.07.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00273/2024-2025 | BP-2024-25-179 | 30/08/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
248 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
249 | Raiganj Division | Raiganj Sub-Division | DI Pipe Carrying RCC Structure Over Sooin River of Pajol PWSS at Itahar Block under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000121/2024-2025 | 3011/RD/PHE | 03/10/2024 | 30 | BHOLA PAUL | 6.06 | 0 | 0
250 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pajol Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 50 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000266/2025-2026 | 1632/RD/PHE | 20/06/2025 | 180 | AJIT PRAMANIK | 20.74 | 0 | 0
251 | Raiganj Division | Raiganj Sub-Division | Implementation of PAJOL and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000320/2022-2023 | 556/RD/PHE | 23/02/2023 | 1043 | BHOLA PAUL | 315.3 | 0 | 44
252 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Pajol PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000422/2024-2025 | 3734/RD/PHE | 18/12/2024 | 135 | BHOLA PAUL | 48.58 | 0 | 0
253 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under PAJOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000544/2023-2024 | 630/RD/PHE | 05/03/2024 | 118 | R. R. CONSTRUCTION | 12.24 | 0 | 70
254 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under PAJOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000545/2023-2024 | 631/RD/PHE | 05/03/2024 | 90 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 12.24 | 0 | 90
255 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
256 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000139/2022-2023 | 786/RD/PHE | 18/03/2023 | 0 | Resource Division | 137.43 | 0 | 0
257 | Raiganj Division | Raiganj Sub-Division | Construction of Culvert with Hume Pipe Across PWD Borrow Pit for making accessible Road at Chandgaon PWSS Head Work Site at Kaliyaganj Block under Raiganj Division, P.H.E. Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000144/2024-2025 | 3009/RD/PHE | 03/10/2024 | 30 | PINTU SWARNAKAR | 2.17 | 0 | 100
258 | Raiganj Division | Raiganj Sub-Division | Implementation of CHADGAON andit's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000205/2022-2023 | 74/RD/PHE | 16/01/2023 | 1120 | UJJWAL DAS | 408.1 | 0 | 80
259 | Raiganj Division | Raiganj Sub-Division | Balance work i.c.w. Construction of boundary wall of Chandgaon piped water supply scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000402/2025-2026 | 1608/RD/PHE | 17/06/2025 | 120 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 3.36 | 0 | 0
260 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chandgaon PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000423/2024-2025 | 3735/RD/PHE | 18/12/2024 | 135 | UJJWAL DAS | 56.93 | 0 | 0
261 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHADGAON Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000471/2023-2024 | 579/RD/PHE | 05/03/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.57 | 0 | 0
262 | Raiganj Division | Raiganj Sub-Division | Trial Run For Chandgaon PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000674/2024-2025 | 520/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0
263 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000087/2022-2023 | 2198/RD/PHE | 14/12/2022 | 0 | Resource Division | 67.14 | 0 | 0
264 | Raiganj Division | Raiganj Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Puria Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj,Capacity- 80 M3/hr. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000013/2021-2022 | 1218/RD/PHE | 18/06/2021 | 90 | AJIT PARMANIK | 36.22 | 0 | 50
265 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Puria and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000126/2020-2021 | 362/RD/PHE | 04/02/2021 | 40 | UTTAM SAHA | 91.12 | 0 | 1
266 | Raiganj Division | Raiganj Sub-Division | Providing functional household Tap connection under Mahua and adjoining Mouzas Water Supply Scheme at Goalpokher-I Block under Raiganj Division, P.H.E. Dte. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000127/2020-2021 | 344/RD/PHE | 01/02/2021 | 60 | J.D.J. ENTERPRISE | 150.74 | 0 | 1
267 | Raiganj Division | Raiganj Sub-Division | Providing functional household Tap connection under Purba Chutiakhor and adjoining Mouzas Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte.¿ |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000128/2020-2021 | 342/RD/PHE | 01/02/2021 | 60 | SANYAL ENTERPRISE | 110.45 | 0 | 1
268 | Raiganj Division | Raiganj Sub-Division | Providing functional household Tap connection under Bhojpur and adjoining Mouzas Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000129/2020-2021 | 343/RD/PHE | 01/02/2021 | 60 | M/S LOKENATH CONST | 117.62 | 0 | 1
269 | Raiganj Division | Raiganj Sub-Division | Retrofitting of FHTC with additional Pipe Line at Purba Chutiyakhore PWSS in Chopra Block in connection with retrofitting of FHTC under 4nos different schemes Under Raiganj Division, PHE Dte. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000397/2023-2024 | 2658/RD/PHE | 15/09/2023 | 379 | KARTICK BISWAS | 32.47 | 0 | 50
270 | Raiganj Division | Raiganj Sub-Division | Collection of House Hold Details 6 Nos PWSS at Prescribed format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and submission of the same to PHE Dte. in soft copy. |  | Junior Engineer, ISD ,Junior Engineer, RSD | ORD/000474/2020-2021 | 148/RD/PHE | 20/01/2021 | 30 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 2.63 | 0 | 0
271 | Raiganj Division | Raiganj Sub-Division | stationary bill |  | Junior Engineer, ISD ,Junior Engineer, RSD | VCH/000310/2022-2023 | BP-2022-23-17 | 28/04/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.09 | 0 | 0
272 | Raiganj Division | Raiganj Sub-Division | office accessories |  | Junior Engineer, ISD ,Junior Engineer, RSD | VCH/000313/2022-2023 | BP-2022-23-19 | 28/04/2022 | 0 | SAHA CONSTRUCTION | 0.09 | 0 | 0
273 | Raiganj Division | Raiganj Sub-Division | office accessories bill |  | Junior Engineer, ISD ,Junior Engineer, RSD | VCH/000317/2022-2023 | BP-2022-23-32 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
274 | Raiganj Division | Raiganj Sub-Division | office accessories bill |  | Junior Engineer, ISD ,Junior Engineer, RSD | VCH/000318/2022-2023 | BP-2022-23-31 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
275 | Raiganj Division | Raiganj Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Sariabad Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000287/2021-2022 | 1823/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.69 | 0 | 0
276 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Sariabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000384/2021-2022 | 2079/RD/PHE | 02/11/2021 | 30 | M/S GHOSH CONSTRUCTION | 7.63 | 0 | 1
277 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Sariabad Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000735/2021-2022 | 431/RD/PHE | 16/02/2022 | 30 | M/S ARVI CONSTRUCTION | 7.57 | 0 | 0
278 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000002/2021-2022 | 26/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.7 | 0 | 0
279 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000017/2022-2023 | 1805/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.03 | 0 | 0
280 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Matikunda for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-I) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000450/2021-2022 | 2386/RD/PHE | 24/12/2021 | 30 | M/S LUCKY CONSTRUCTION | 7.89 | 0 | 0
281 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dharampur-II Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000279/2021-2022 | 1815/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.94 | 0 | 0
282 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-II Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000390/2021-2022 | 2085/RD/PHE | 02/11/2021 | 30 | M/S CHOUDHURY CONSTRUCTION | 10.38 | 0 | 1
283 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dharampur Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000739/2021-2022 | 435/RD/PHE | 16/02/2022 | 30 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 9.16 | 0 | 0
284 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-Ii Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000746/2021-2022 | 485/RD/PHE | 25/02/2022 | 30 | M/S CHOUDHURY CONSTRUCTION | 10.21 | 0 | 0
285 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000016/2021-2022 | 40/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.51 | 0 | 0
286 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of MAHINAGAR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000409/2021-2022 | 2112/RD/PHE | 03/11/2021 | 30 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 5.69 | 0 | 1
287 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of MASLANDPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000417/2021-2022 | 2120/RD/PHE | 03/11/2021 | 30 | CHAITANYA SAMAL | 19.24 | 0 | 1
288 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Sahavita Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000359/2021-2022 | 2140/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 4.3 | 0 | 1
289 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SAHAVITA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000425/2021-2022 | 2187/RD/PHE | 17/11/2021 | 30 | TAPAN KUMAR DUTTA | 7.31 | 0 | 0
290 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000376/2021-2022 | 2071/RD/PHE | 02/11/2021 | 30 | S.B.CONSTRUCTION | 6.49 | 0 | 100
291 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Lodhon for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000435/2021-2022 | 2197/RD/PHE | 17/11/2021 | 30 | NIMAI DAS | 6.42 | 0 | 0
292 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000729/2021-2022 | 425/RD/PHE | 16/02/2022 | 30 | S.B.CONSTRUCTION | 6.43 | 0 | 100
293 | Raiganj Division | Islampur Sub-Division | Route Survey & Preparation of DPR of MARNAI PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000753/2021-2022 | 151/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.93 | 0 | 0
294 | Raiganj Division | Raiganj Sub-Division | Restoration of pipe line for providing FHTC for Sahavita water Supply Scheme under Itahar Block under Raiganj Division PHE Dte.(Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000030/2022-2023 | 1042/RD/PHED | 12/05/2022 | 30 | BITTU ENTERPRISE | 8.68 | 0 | 1
295 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of KALIGANJ Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000405/2021-2022 | 2108/RD/PHE | 03/11/2021 | 30 | DULAL MAJUMDER | 7.14 | 0 | 1
296 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe line for Retrofitting FHTC of Mahadevpur piped water Supply Scheme under Raiganj Division P.H.E. Dte. (Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000032/2022-2023 | 1044/RD/PHED | 12/05/2022 | 30 | SANKAR DAS | 9.39 | 0 | 1
297 | Raiganj Division | Islampur Sub-Division | hiring of inspection vehicle | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | BILL/01129/2023-2024 | BP-2023-24-279 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0
298 | Raiganj Division | Islampur Sub-Division | Balance work for Pipeline crossing, earth filling & other ancillary works at CHOPRA Piped Water Supply Scheme in connection with Augmentation of Chopra PWSS under Islampur Sub-Division under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000029/2024-2025 | 1689/RD/PHE | 10/06/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 22.38 | 0 | 0
299 | Raiganj Division | Islampur Sub-Division | Soil Investigation for Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir For Augmentation of Chopra W/S Scheme In Chopra Block In Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000048/2022-2023 | 1240/RD/PHE | 20/06/2022 | 20 | G. MITRA & ASSOCIATES | 2.39 | 0 | 0
300 | Raiganj Division | Islampur Sub-Division | Providing Functional household Tap Connection for Chopra Water Supply Scheme (under Augmentation) at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000053/2022-2023 | 1272/RD/PHE | 24/06/2022 | 1191 | UTTAM SAHA | 119.51 | 0 | 65
301 | Raiganj Division | Islampur Sub-Division | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000128/2022-2023 | 1520\RD | 24/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0
302 | Raiganj Division | Islampur Sub-Division | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000130/2022-2023 | 1536\RD | 25/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0
303 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC at different mouzas at Chopra Piped Water Supply Scheme (In Connection with Augmentation of Chopra PWSS) under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000142/2024-2025 | 2838/RD/PHE | 23/09/2024 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.83 | 0 | 0
304 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC for Augmentation of Chopra Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000154/2024-2025 | 2886/RD/PHE | 25/09/2024 | 45 | UTTAM SAHA | 37.35 | 0 | 0
305 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under Augmentation of Chopra PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000158/2024-2025 | 2890/RD/PHE | 25/09/2024 | 450 | MOTI INDUSTRIES | 39.68 | 0 | 50
306 | Raiganj Division | Islampur Sub-Division | Approach Road including earthwork for roads at 2nd & 3rd Tube Well Site of Chopra Piped Water Supply Scheme in connection with Augmentation of Chopra PWSS under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000183/2022-2023 | 2253/RD/PHE | 22/12/2022 | 20 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 3.19 | 0 | 0
307 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Chopra Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000232/2022-2023 | 365/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 5.04 | 0 | 100
308 | Raiganj Division | Islampur Sub-Division | Repairing of Pump House at 2nd Tube well site in connection with Augmentation of Chopra piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000233/2022-2023 | 366/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.1 | 0 | 0
309 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (without Toilet) at 3rd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Chopra Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000234/2022-2023 | 367/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.12 | 0 | 0
310 | Raiganj Division | Islampur Sub-Division | Construction Of Boundary Wall With Gate at 3rd Tube-Well Site in connection with Augmentation of Chopra PWSS at Chopra Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000344/2024-2025 | 3297/RD/PHE | 20/11/2024 | 166 | M C CONSTRUCTION | 5.55 | 0 | 100
311 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chopra Water Supply Scheme (Augmentation) at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 105 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000358/2025-2026 | 2504/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 43.83 | 0 | 0
312 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-600 Cum) of CHOPRA Pipe Water Supply Scheme in connection with Augmentation at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000382/2022-2023 | 736/RD/PHE | 15/03/2023 | 365 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 188.99 | 0 | 80
313 | Raiganj Division | Islampur Sub-Division | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for CHOPRA (augmentation) and its adjoining Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000468/2021-2022 | 395/RD/PHE | 10/02/2022 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 1.57 | 0 | 0
314 | Raiganj Division | Islampur Sub-Division | Sinking 3(Three) nos. of Ground Bored Wells, 300mm diameter x 200mm diameter, 250mtr. Deep Tube Well including proper development and necessary yield for Ground Water Based PWSS for CHOPRA and its adjoining Mouzas Water Supply Scheme under ) of Chopra Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000469/2021-2022 | 396/RD/PHE | 10/02/2022 | 21 | HAQUE CONSTRUCTION | 47.3 | 0 | 1
315 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with augmentation of Chopra Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000501/2024-2025 | 46/RD/PHE | 03/01/2025 | 67 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 23.43 | 0 | 0
316 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
317 | Raiganj Division | Islampur Sub-Division | Laying Distribution System for CHOPRA and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | ORD/000648/2021-2022 | 394/RD/PHE | 10/02/2022 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION | 228.06 | 0 | 1
318 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | RTOR000004/2022-2023 | 1514/RD/PHE | 22/08/2022 | 0 | Resource Division | 19.32 | 0 | 0
319 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | RTOR000020/2021-2022 | 639/RD/PHE | 23/03/2022 | 0 | Resource Division | 126.92 | 0 | 0
320 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | RTOR000052/2022-2023 | 2007/RD/PHE | 16/11/2022 | 0 | Resource Division | 147.27 | 0 | 0
321 | Raiganj Division | Islampur Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | VCH/001764/2022-2023 | BP-2022-23-211 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0
322 | Raiganj Division | Islampur Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD | VCH/001767/2022-2023 | BP-2022-23-209 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0
323 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Chopra & Goalpokhor-II Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000021/2023-2024 | 1283/RD/PHE | 08/05/2023 | 92 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 656.06 | 0 | 30
324 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Biprit Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000149/2022-2023 | 1927/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.13 | 0 | 60
325 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000102/2023-2024 | 2392/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.57 | 0 | 0
326 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Gutin Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000138/2022-2023 | 1916/RD/PHE | 28/10/2022 | 881 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 39.77 | 0 | 75
327 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000114/2023-2024 | 15/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
328 | Raiganj Division | Raiganj Sub-Division | Augmentation work of MARNAI and it's adjoining mouzas Piped Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000099/2022-2023 | 1546/RD/PHE | 26/08/2022 | 1118 | M/S LOKENATH CONSTRUCTION | 354.98 | 0 | 55
329 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Marnai Water Supply Scheme [Augmentation Scheme] in Raiganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000169/2022-2023 | 2029/RD/PHE | 17/11/2022 | 90 | M/S LOKENATH CONSTRUCTION | 79.34 | 0 | 0
330 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Marnai Water Supply Scheme at Itahar Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000267/2022-2023 | 407/RD/PHE | 09/02/2023 | 45 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 3.53 | 0 | 0
331 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Marnai Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000280/2025-2026 | 2207/RD/PHE | 29/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 33.6 | 0 | 0
332 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House (size 4.10 m x 3.50 m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at 3nd Tube-Well Site in connection with Augmentation of Marnai PWSS | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000290/2023-2024 | 2363/RD/PHE | 11/08/2023 | 60 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 5.02 | 0 | 0
333 | Raiganj Division | Raiganj Sub-Division | Construction of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Marnai Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000403/2024-2025 | 3573/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 41.84 | 0 | 0
334 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000090/2022-2023 | 12/RD/PHE | 04/01/2023 | 0 | Resource Division | 58.04 | 0 | 0
335 | Raiganj Division | Raiganj Sub-Division | Augmentation of SARIABAD Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000102/2022-2023 | 1549/RD/PHE | 26/08/2022 | 930 | TAPAN KUMAR DUTTA | 152.36 | 0 | 90
336 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation of Sariabad PWSS at Raiganj Block under Raiganj Division, PHE dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000156/2024-2025 | 2888/RD/PHE | 25/09/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 37.18 | 0 | 0
337 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Sariabad Water Supply Scheme [Augmentation Scheme] in Raiganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000171/2022-2023 | 2031/RD/PHE | 17/11/2022 | 930 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 44.4 | 0 | 67
338 | Raiganj Division | Raiganj Sub-Division | Construction of Pump house for (5.4 x 3.6) at Head work site of Sariabad Augmentation Water Supply Schemes under Raiganj Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000262/2022-2023 | 388/RD/PHE | 07/02/2023 | 45 | SANTOSI ENTERPRISE AMIT.RAIGANJ@GMAIL.COM | 5.79 | 0 | 100
339 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of 2nd Tube Well and 3rd Tube Well Site of Sariabad Augmentation Water Supply Scheme at Raiganj Block under Raiganj Division P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000265/2022-2023 | 401/RD/PHE | 08/02/2023 | 450 | LAXMI CONSTRUCTION NAMEDUTTA@GMAIL.COM | 3.31 | 0 | 80
340 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sariabad Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000272/2025-2026 | 1659/RD/PHE | 23/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.57 | 0 | 0
341 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-300 Cum) of SARIABAD Pipe Water Supply Scheme in connection with Augmentation at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000328/2022-2023 | 657/RD/PHE | 03/03/2023 | 690 | VISCOUS ENGINEERS PVT. LTD. | 84.86 | 0 | 82
342 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sariyabad PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000437/2024-2025 | 3749/RD/PHED | 18/12/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 37.92 | 0 | 75
343 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000036/2022-2023 | 1949/RD/PHE | 04/11/2022 | 0 | Resource Division | 33.5 | 0 | 0
344 | Raiganj Division | Islampur Sub-Division | Restoration of Pipeline for Providing FHTC for LODHON Water Supply Scheme under Raiganj Division, P.H.E Dte (Phase - II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000022/2022-2023 | 1034/RD/PHED | 12/05/2022 | 30 | RAHUL ENTERPRISE | 5.51 | 0 | 1
345 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur. (Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000031/2022-2023 | 1043/RD/PHED | 12/05/2022 | 30 | DAS CONSTRUCTION COMPANY | 7.82 | 0 | 100
346 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Ghirnigaon Khas Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000147/2022-2023 | 1925/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.2 | 0 | 0
347 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000105/2023-2024 | 2398/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0
348 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Katagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000003/2025-2026 | 1174/RD/PHE | 23/04/2025 | 15 | DIPANKAR SARKAR | 6.94 | 0 | 0
349 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
350 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at KATAGAON PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000387/2025-2026 | 2161/RD/PHE | 23/07/2025 | 180 | M/S SACHIN KUMAR | 32.55 | 0 | 0
351 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000001/2023-2024 | 1038/RD/PHE | 04/04/2023 | 0 | Resource Division | 24.58 | 0 | 0
352 | Raiganj Division | Islampur Sub-Division | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of Islampur- Amaljhari- Sonamoti Road under Uttar Dinajpur division, PWD. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00506/2023-2024 | BILL/00506/2023 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 7.97 | 0 | 0
353 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Khabargaon Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000300/2025-2026 | 1949/RD/PHE | 01/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0
354 | Raiganj Division | Islampur Sub-Division | Implementation of KHABARGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000308/2022-2023 | 567/RD/PHE | 23/02/2023 | 1133 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 496.73 | 0 | 50
355 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KHABARGAON PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000492/2023-2024 | 608/RD/PHE | 05/03/2024 | 45 | DUTTA BUILDERS | 22.51 | 0 | 0
356 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000107/2022-2023 | 598/RD/PHE | 27/02/2023 | 0 | Resource Division | 43.88 | 0 | 0
357 | Raiganj Division | Raiganj Sub-Division | Implementation of Laksmania and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000031/2023-2024 | 1306/RD/PHE | 12/05/2023 | 965 | UNIVERSAL ENTERPRISES | 279.7 | 0 | 70
358 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd Tubewell Site and road restoration of Laksmania PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000408/2025-2026 | 1606/RD/PHE | 17/06/2025 | 120 | SARVATAH PROJECTS PRIVATE LIMITED | 39.5 | 0 | 0
359 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAKSMANIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000464/2023-2024 | 572/RD/PHE | 05/03/2024 | 390 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 85
360 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
361 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000104/2022-2023 | 574/RD/PHE | 23/02/2023 | 0 | Resource Division | 31.27 | 0 | 0
362 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Chandol Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000135/2022-2023 | 1913/RD/PHE | 28/10/2022 | 405 | M/S PIONEER ENTERPRISE | 34.31 | 0 | 30
363 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000112/2023-2024 | 08/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
364 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Jharbari Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000001/2025-2026 | 1176/RD/PHE | 23/04/2025 | 30 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 12.6 | 0 | 0
365 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jharbari Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000326/2025-2026 | 2012/RD/PHE | 08/07/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0
366 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000012/2023-2024 | 1124/RD/PHE | 24/04/2023 | 0 | Resource Division | 36.54 | 0 | 0
367 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Barobilla Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000370/2021-2022 | 2151/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 2.17 | 0 | 0
368 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of NOABARI Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000412/2021-2022 | 2115/RD/PHE | 03/11/2021 | 30 | MAA BICHITRA CONSTRUCTION | 13.93 | 0 | 1
369 | Raiganj Division | Islampur Sub-Division | Protection and Restoration work of damaged flank caused by excavation for water supply project of PHE of Matikunda- Moragoti Road under uttar dinajpur division, PWD. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00505/2023-2024 | BP-2023-24-143 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 9.23 | 0 | 0
370 | Raiganj Division | Islampur Sub-Division | Implementation of JAGATGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000271/2022-2023 | 289/RD/PHE | 01/02/2023 | 1307 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 910.72 | 0 | 60
371 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Jagtagaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000350/2024-2025 | 3303/RD/PHE | 20/11/2024 | 135 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 49.57 | 0 | 0
372 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for JAGTAGAON Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000351/2024-2025 | 3304/RD/PHE | 20/11/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 9.63 | 0 | 0
373 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under JAGATAGAON Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000453/2023-2024 | 561/RD/PHE | 05/03/2024 | 360 | M/S RATAN SARKAR & SON | 27.68 | 0 | 85
374 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Jagtagaon Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000510/2024-2025 | 55/RD/PHE | 03/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 5.98 | 0 | 0
375 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
376 | Raiganj Division | Islampur Sub-Division | Trial Run For Jagtagaon PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000718/2024-2025 | 550/RD/PHE | 12/02/2025 | 90 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.87 | 0 | 0
377 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000098/2022-2023 | 581/RD/PHE | 24/02/2023 | 0 | Resource Division | 75.77 | 0 | 0
378 | Raiganj Division | RWS Raiganj Sub-Divisin | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | BILL/00017/2024-2025 | BP-2024-25-11 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.07 | 0 | 0
379 | Raiganj Division | RWS Raiganj Sub-Divisin | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | BILL/00018/2024-2025 | BP-2024-25-12 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
380 | Raiganj Division | RWS Raiganj Sub-Divisin | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | BILL/00019/2024-2025 | BP-2024-25-13 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
381 | Raiganj Division | RWS Raiganj Sub-Divisin | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | BILL/00020/2024-2025 | BP-2024-25-14 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.09 | 0 | 0
382 | Raiganj Division | RWS Raiganj Sub-Divisin | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | BILL/00021/2024-2025 | BP-2024-25-15 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.05 | 0 | 0
383 | Raiganj Division | RWS Raiganj Sub-Divisin | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Raniganj, 2. Alianagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000296/2022-2023 | 542/RD/PHE | 22/02/2023 | 628 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 51.42 | 0 | 80
384 | Raiganj Division | RWS Raiganj Sub-Divisin | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Alianagar Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000331/2025-2026 | 2484/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0
385 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of pipe line at village-Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000406/2022-2023 | 761/RD/PHE | 17/03/2023 | 720 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 49.21 | 0 | 35
386 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of boundary wall and Pump house at 2nd Tube-well site of Aliangar Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000411/2022-2023 | 766/RD/PHE | 17/03/2023 | 702 | M/S UNIQUE 13 | 11.28 | 0 | 100
387 | Raiganj Division | RWS Raiganj Sub-Divisin | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
388 | Raiganj Division | RWS Raiganj Sub-Divisin | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0
389 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village-Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000416/2022-2023 | 771/RD/PHE | 17/03/2023 | 60 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 15.4 | 0 | 0
390 | Raiganj Division | RWS Raiganj Sub-Divisin | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Alianagar PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000453/2024-2025 | 3766/RD/PHED | 18/12/2024 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 33.63 | 0 | 0
391 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying distribution of pipe line of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000466/2022-2023 | 817/RD/PHE | 22/03/2023 | 705 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 49.51 | 0 | 40
392 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of boundary wall and Pump house at head work site of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000484/2022-2023 | 823/RD/PHE | 22/03/2023 | 539 | GULJAN BEGAM | 24.87 | 0 | 100
393 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of Rising Main of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000512/2022-2023 | 855/RD/PHE | 24/03/2023 | 660 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 4.58 | 0 | 10
394 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of pipe line at village-Pargaon of ALIANAGAR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000517/2022-2023 | 871/RD/PHE | 27/03/2023 | 723 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 49.76 | 0 | 35
395 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village-Pargaon of ALIANAGAR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000526/2022-2023 | 876/RD/PHE | 27/03/2023 | 60 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 17.46 | 0 | 0
396 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of pipe line at village-Alianagar of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000534/2022-2023 | 946/RD/PHE | 29/03/2023 | 750 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 45.14 | 0 | 37
397 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000539/2022-2023 | 951/RD/PHE | 29/03/2023 | 600 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 16.85 | 0 | 0
398 | Raiganj Division | RWS Raiganj Sub-Divisin | Providing FHTC at village-Pargaon and Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000544/2022-2023 | 956/RD/PHE | 29/03/2023 | 660 | M/S ARVI CONSTRUCTION | 18.26 | 0 | 0
399 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of OHR(Capacity-300Cum) of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000552/2022-2023 | 1020/RD/PHE | 31/03/2023 | 275 | MS SANDHYA CONSTRUCTION | 96.8 | 0 | 35
400 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | RTOR000042/2023-2024 | 1318/RD/PHE | 12/05/2023 | 0 | Resource Division | 46.84 | 0 | 0
401 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Gunabari Piped Water Supply Scheme of Islampur Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000190/2022-2023 | 58/RD/PHE | 16/01/2023 | 562 | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 17.58 | 0 | 100
402 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 100
403 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000101/2023-2024 | 2394/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
404 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Manora Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000338/2025-2026 | 1798/RD/PHE | 24/06/2025 | 180 | S. DUTTA | 36.38 | 0 | 0
405 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
406 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000177/2022-2023 | 976/RD/PHE | 30/03/2023 | 0 | Resource Division | 97.5 | 0 | 0
407 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
408 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000156/2022-2023 | 889/RD/PHE | 27/03/2023 | 0 | Resource Division | 50.62 | 0 | 0
409 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Mahua Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000191/2022-2023 | 59/RD/PHE | 16/01/2023 | 854 | SUDIP MITRA SUDIP.RNJ@GMAIL.COM | 17.67 | 0 | 100
410 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000278/2022-2023 | 471/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 80
411 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000097/2023-2024 | 2395/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
412 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at BHOTAMARI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000028/2025-2026 | 1206/RD/PHE | 25/04/2025 | 45 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 76.36 | 0 | 0
413 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Botamari Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000297/2025-2026 | 1926/RD/PHE | 30/06/2025 | 180 | RHYNO INFRASTRUCTURE | 36.34 | 0 | 0
414 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
415 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000168/2022-2023 | 970/RD/PHE | 29/03/2023 | 0 | Resource Division | 62.76 | 0 | 0
416 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
417 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapduar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000429/2024-2025 | 3741/RD/PHE | 18/12/2024 | 135 | UTTAM SAHA | 21.16 | 0 | 0
418 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAPDUAR PWSS at Raiganj Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000519/2023-2024 | 652/RD/PHE | 05/03/2024 | 77 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 100
419 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000070/2023-2024 | 2235/RD/PHE | 02/08/2023 | 0 | Resource Division | 32.15 | 0 | 0
420 | Raiganj Division | Raiganj Sub-Division | Implementation of HARINARAYANPUR(Zone- I) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000013/2023-2024 | 1275/RD/PHE | 08/05/2023 | 969 | UJJWAL DAS | 344.33 | 0 | 50
421 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under HARINARAYANPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000051/2024-2025 | 1710/RD/PHE | 10/06/2024 | 45 | ADYA MAA CONSTRUCTION | 24.47 | 0 | 100
422 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Harinarayanpur Zone-I Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Block:- Raiganj,Capacity- 45 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000263/2025-2026 | 1628/RD/PHE | 19/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 19.35 | 0 | 0
423 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000489/2024-2025 | 22/RD/PHE | 02/01/2025 | 45 | UJJWAL DAS | 47.1 | 0 | 0
424 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
425 | Raiganj Division | Raiganj Sub-Division | Trial Run For Harinarayanpur Zone-I PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000688/2024-2025 | 534/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0
426 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000141/2022-2023 | 808/RD/PHE | 21/03/2023 | 0 | Resource Division | 46.32 | 0 | 0
427 | Raiganj Division | Raiganj Sub-Division | Arrangement for erection of display board for different piped water supply schemes (1.Jagadishpur PWSS, 2.Chainagar PWSS, 3.Hemtabad Zone-II PWSS) under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00436/2024-2025 | BP-2024-25-254 | 07/10/2024 | 0 | M/S MANDAL ENTERPRISE | 0.1 | 0 | 0
428 | Raiganj Division | Raiganj Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/01216/2023-2024 | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 11.85 | 0 | 0
429 | Raiganj Division | Raiganj Sub-Division | Implementation of CHAINAGAR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000397/2022-2023 | 749/RD/PHE | 16/03/2023 | 665 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 358.48 | 0 | 58
430 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chainagar PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000432/2024-2025 | 3745/RD/PHE | 18/12/2024 | 135 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 46.37 | 0 | 0
431 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAINAGAR PWSS at HEMTABAD Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000562/2023-2024 | 544/RD/PHE | 05/03/2024 | 45 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 11.28 | 0 | 100
432 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAINAGAR PWSS at HEMTABAD Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000563/2023-2024 | 545/RD/PHE | 05/03/2024 | 45 | MAA MANASHA ENGINEERS | 11.28 | 0 | 100
433 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
434 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000072/2023-2024 | 2242/RD/PHE | 02/08/2023 | 0 | Resource Division | 44.72 | 0 | 0
435 | Raiganj Division | RWS Raiganj Sub-Divisin | Implementation of BILASPUR and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000227/2023-2024 | 2406/RD/PHE | 17/08/2023 | 600 | M/S ALISA CONSTRUCTION | 303.65 | 0 | 30
436 | Raiganj Division | RWS Raiganj Sub-Divisin | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bilaspur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000455/2024-2025 | 3768/RD/PHED | 18/12/2024 | 45 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 19.54 | 0 | 0
437 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | RTOR000126/2022-2023 | 632/RD/PHE | 02/03/2023 | 0 | Resource Division | 38.8 | 0 | 0
438 | Raiganj Division | Raiganj Sub-Division | Implementation of KHALSI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000004/2023-2024 | 1129/RD/PHE | 24/04/2023 | 1111 | SANYAL ENTERPRISE | 386.06 | 0 | 50
439 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Khalsi, 2.Dwipnagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000033/2023-2024 | 1490/RD/PHE | 17/05/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 52.73 | 0 | 90
440 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000046/2023-2024 | 1332/RD/PHE | 15/05/2023 | 0 | Resource Division | 41.2 | 0 | 0
441 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Machhali Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000337/2025-2026 | 2487/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 36.37 | 0 | 0
442 | Raiganj Division | Islampur Sub-Division | Implementation of MACHHALI and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division. (Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000363/2023-2024 | 2479/RD/PHE | 24/08/2023 | 976 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 742.57 | 0 | 55
443 | Raiganj Division | Islampur Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Machhal PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000452/2024-2025 | 3765/RD/PHED | 18/12/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 75.22 | 0 | 0
444 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under MACHHALI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000521/2023-2024 | 656/RD/PHE | 05/03/2024 | 525 | BIKASH KAR | 27.72 | 0 | 100
445 | Raiganj Division | Islampur Sub-Division | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0
446 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000138/2022-2023 | 723/RD/PHE | 15/03/2023 | 0 | Resource Division | 83.09 | 0 | 0
447 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dulehpur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000334/2025-2026 | 2485/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.38 | 0 | 0
448 | Raiganj Division | Islampur Sub-Division | Implementation of DULEPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000361/2023-2024 | 2478/RD/PHE | 24/08/2023 | 1226 | UTTAM SAHA | 660.02 | 0 | 10
449 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0
450 | Raiganj Division | Islampur Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dulepur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000451/2024-2025 | 3763/RD/PHED | 18/12/2024 | 315 | M/S SARKAR ENTERPRISE SILIGURI | 94.92 | 0 | 30
451 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DULEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000558/2023-2024 | 659/RD/PHE | 05/03/2024 | 45 | ANILA CONSTRUCTION | 13.86 | 0 | 0
452 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DULEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000559/2023-2024 | 660/RD/PHE | 05/03/2024 | 45 | BHAGIRATH CONSTRUCTION | 13.86 | 0 | 0
453 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000131/2022-2023 | 636/RD/PHE | 02/03/2023 | 0 | Resource Division | 83.32 | 0 | 0
454 | Raiganj Division | Islampur Sub-Division | Implementation of GUNJARIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000213/2023-2024 | 2296/RD/PHE | 04/08/2023 | 998 | UTTAM SAHA | 631.56 | 0 | 40
455 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Gunjaria Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000285/2025-2026 | 1807/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 33.6 | 0 | 0
456 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
457 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Gunjaria Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000511/2024-2025 | 56/RD/PHE | 03/01/2025 | 45 | M/S. B. PAUL & COMPANY | 13.85 | 0 | 0
458 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under GUNJARIA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000520/2023-2024 | 653/RD/PHE | 05/03/2024 | 45 | M/S LUCKY CONSTRUCTION | 24.49 | 0 | 0
459 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000120/2022-2023 | 618/RD/PHE | 28/02/2023 | 0 | Resource Division | 83.71 | 0 | 0
460 | Raiganj Division | Raiganj Sub-Division | Implementation of DHOARAI ZONE-I and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000080/2023-2024 | 1999/RD/PHE | 13/07/2023 | 903 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 476.5 | 0 | 50
461 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dhoaroi Zone-I Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist:Uttar Dinajpur, Block: Raiganj,Capacity- 60 M3/hr. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000262/2025-2026 | 1627/RD/PHE | 19/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.58 | 0 | 0
462 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dhoarai Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000488/2024-2025 | 21/RD/PHE | 02/01/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 51.46 | 0 | 0
463 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHOARAI (Zone-I)PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000523/2023-2024 | 672/RD/PHE | 05/03/2024 | 270 | D. K. ASSOCIATES | 22.58 | 0 | 100
464 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
465 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
466 | Raiganj Division | Raiganj Sub-Division | Trial Run For Dharai Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000730/2024-2025 | 529/RD/PHE | 12/02/2025 | 90 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 0.82 | 0 | 0
467 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000075/2023-2024 | 2245/RD/PHE | 02/08/2023 | 0 | Resource Division | 30.75 | 0 | 0
468 | Raiganj Division | Raiganj Sub-Division | Preparation of Additional DPR For Itahar Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Itahar PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000175/2022-2023 | 2133/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 1
469 | Raiganj Division | Raiganj Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Itahar Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000292/2021-2022 | 1828/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.5 | 0 | 0
470 | Raiganj Division | Raiganj Sub-Division | Allied works in connection with retrofitting of FHTC in Itahar PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000377/2023-2024 | 2603/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.98 | 0 | 100
471 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Itahar Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000379/2021-2022 | 2074/RD/PHE | 02/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 19.75 | 0 | 1
472 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000736/2021-2022 | 432/RD/PHE | 16/02/2022 | 30 | RAHUL ENTERPRISE | 6.65 | 0 | 0
473 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Itahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000744/2021-2022 | 483/RD/PHE | 25/02/2022 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 19.39 | 0 | 0
474 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000018/2022-2023 | 1806/RD/PHE | 23/09/2022 | 0 | Resource Division | 5.26 | 0 | 0
475 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of NALBITHI MADHABPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000408/2021-2022 | 2111/RD/PHE | 03/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 8.2 | 0 | 1
476 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Nizampur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000336/2025-2026 | 1805/RD/PHE | 24/06/2025 | 180 | S. DUTTA | 29.59 | 0 | 0
477 | Raiganj Division | Islampur Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0
478 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
479 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000146/2022-2023 | 847/RD/PHE | 24/03/2023 | 0 | Resource Division | 36.11 | 0 | 0
480 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Hemtabad, Islampur & Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000022/2023-2024 | 1284/RD/PHE | 08/05/2023 | 969 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 709.96 | 0 | 50
481 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Patnihar village under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000149/2024-2025 | 593/RD/PHE | 19/02/2025 | 60 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 43.7 | 0 | 0
482 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Purba Mohanpur and Khowaspur Mouza under Khowaspur Water Supply Scheme in Karandithi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000250/2020-2021 | 1431/RD/PHE | 11/12/2020 | 30 | M/S PIONEER ENTERPRISE | 24.17 | 0 | 1
483 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Jotilamat and Purba Pipla Mouza under Khowaspur Water Supply Scheme in Karandithi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000251/2020-2021 | 1430/RD/PHE | 11/12/2020 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 22.06 | 0 | 1
484 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002088/2021-2022 | 770/W | 11/03/2022 | 0 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0
485 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Purba Rampur and adjoining Mouzas Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000217/2020-2021 | 1416/RD/PHE | 11/12/2020 | 40 | PRASANTA DUTTA | 84.08 | 0 | 0
486 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000807/2024-2025 | 296/RD/PHE | 15/01/2025 | 181 | DEBASISH GHOSH | 2.4 | 0 | 0
487 | Raiganj Division | Raiganj Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer RSD | Junior Engineer, RSD | VCH/002080/2021-2022 | 774/W | 11/03/2022 | 0 | BEEKAY.COM | 0.09 | 0 | 0
488 | Raiganj Division | Raiganj Sub-Division | FHTC OF MAHAMMADPUR WSS | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000012/2020-2021 | 1239/RD | 16/10/2020 | 40 | TAPAN KUMAR DUTTA | 84.41 | 53.16 | 0
489 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Mahammadpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000181/2020-2021 | 1239/RD/PHE | 16/10/2020 | 40 | TAPAN KUMAR DUTTA | 84.41 | 0 | 0
490 | Raiganj Division | Raiganj Sub-Division | Supply, laying, fitting, fixing & jointing of upvc pipe including PCC & ordinary concrete( 1:2:4) connection with retrofitting of functional household tap connection (FHTC) under MAHAMMADPUR water Supply Scheme Under Raiganj Division, P.H.E.Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000467/2020-2021 | 1501/RD/PHE | 23/12/2020 | 25 | ANILA CONSTRUCTION | 3.11 | 0 | 0
491 | Raiganj Division | Raiganj Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer RSD | Junior Engineer, RSD | VCH/002090/2021-2022 | 773/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0
492 | Raiganj Division | Islampur Sub-Division | FHTC OF CHOPRABARI | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000014/2020-2021 | 1242/RD | 16/10/2020 | 40 | AJIT PARMANIK | 74.59 | 49.06 | 0
493 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Choprabari and adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000125/2020-2021 | 1242/RD/PHE | 16/10/2020 | 40 | AJIT PARMANIK | 74.35 | 0 | 0
494 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FIXING AND JOINTING UPVC PIPE FHTC OF CHOPRABARI PWSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000429/2020-2021 | 1511/RD | 23/12/2020 | 30 | M/S CHOUDHURY CONSTRUCTION | 8.56 | 0 | 0
495 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.01.2025 to 14.07.2025). | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000810/2024-2025 | 299/RD/PHE | 15/01/2025 | 181 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0
496 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002082/2021-2022 | 776/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.09 | 0 | 0
497 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Marnai Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000383/2021-2022 | 2078/RD/PHE | 02/11/2021 | 30 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.05 | 0 | 1
498 | Raiganj Division | Raiganj Sub-Division | Retrofitting Of Functional Household Tap Connections(FHTC) under Marnai Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000734/2021-2022 | 430/RD/PHE | 16/02/2022 | 30 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.98 | 0 | 0
499 | Raiganj Division | Raiganj Sub-Division | Route Survey & Preparation of DPR of MARNAI PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000753/2021-2022 | 151/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.93 | 0 | 0
500 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000003/2021-2022 | 27/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.15 | 0 | 0
501 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000013/2022-2023 | 1804/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.41 | 0 | 0
502 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Pawakhali Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000366/2021-2022 | 2147/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 4.85 | 0 | 1
503 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Pawakhali for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000438/2021-2022 | 2200/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 16.22 | 0 | 0
504 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SRIPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000415/2021-2022 | 2118/RD/PHE | 03/11/2021 | 30 | M/S SARKAR ENTERPRISE | 9.48 | 0 | 1
505 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of PAKHURIYA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000416/2021-2022 | 2119/RD/PHE | 03/11/2021 | 30 | M/S PIONEER ENTERPRISE | 31.98 | 0 | 1
506 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of GOPALPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000407/2021-2022 | 2110/RD/PHE | 03/11/2021 | 30 | DAS CONSTRUCTION COMPANY | 9.22 | 0 | 1
507 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of BINDOL Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000426/2021-2022 | 2188/RD/PHE | 17/11/2021 | 30 | UTTAM SAHA | 12.9 | 0 | 0
508 | Raiganj Division | Raiganj Sub-Division | hiring of inspection vehicle | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | BILL/01130/2023-2024 | BP-2023-24-282 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.2 | 0 | 0
509 | Raiganj Division | Raiganj Sub-Division | Augmentation work of Dhulahar Water Supply Scheme at Ithar Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | ORD/000074/2022-2023 | 1373/RD/PHE | 14/07/2022 | 90 | M/S LOKENATH CONSTRUCTION | 118.85 | 0 | 0
510 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Dhulahar Water Supply Scheme [Augmentation Scheme] in Itahar Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | ORD/000160/2022-2023 | 2020/RD/PHE | 17/11/2022 | 60 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 35.2 | 0 | 100
511 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Dhulahar Water Supply Scheme at Itahar Block Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | ORD/000268/2022-2023 | 432/RD/PHE | 10/02/2023 | 45 | M/S PRIME BUILDERS PRIME.BUILDERS@GMAIL.COM | 3.51 | 0 | 0
512 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-300 Cum) of DHULAHAR Pipe Water Supply Scheme in connection with Augmentation at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | ORD/000327/2022-2023 | 656/RD/PHE | 03/03/2023 | 240 | M/S PIONEER ENTERPRISE | 84.9 | 0 | 0
513 | Raiganj Division | Raiganj Sub-Division | Construction of Approach Road, Laying of Pipe Line,Fhtc And Other Allied Works Of Dhulahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | ORD/000404/2024-2025 | 3574/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.88 | 0 | 0
514 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | RTOR000029/2022-2023 | 1944/RD/PHE | 04/11/2022 | 0 | Resource Division | 7.27 | 0 | 0
515 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02,Junior Engineer-06 | RTOR000037/2022-2023 | 1950/RD/PHE | 04/11/2022 | 0 | Resource Division | 10.93 | 0 | 0
516 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipeline for Providing FHTC for BARUA PIPED Water Supply Scheme for under Raiganj Division, P.H.E Dte. (Phase - II) | Assistant Engineer RSD |  | ORD/000035/2022-2023 | 1047/RD/PHED | 12/05/2022 | 45 | M/S ROYAL CONSTRUCTION | 10.97 | 0 | 1
517 | Raiganj Division | Islampur Sub-Division | Restoration of Damaged Pipe line for providing FHTC at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte.(Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000039/2022-2023 | 1051/RD/PHED | 12/05/2022 | 45 | M/S.BANGARAJ | 15.57 | 0 | 1
518 | Raiganj Division | Raiganj Sub-Division | Implementation of MALADKHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000309/2022-2023 | 555/RD/PHE | 23/02/2023 | 1148 | UTTAM SAHA | 685.62 | 0 | 53
519 | Raiganj Division | Raiganj Sub-Division | Rig bored Tubewell at MALADKHANDA PWSS in connection with Implementation of New Maladkhanda PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000411/2023-2024 | 2751/RD/PHE | 05/10/2023 | 20 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 26.26 | 0 | 100
520 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MALADKHANDA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000462/2023-2024 | 570/RD/PHE | 05/03/2024 | 383 | M/S REGAL BUILDERS | 22.57 | 0 | 100
521 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
522 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000103/2022-2023 | 572/RD/PHE | 23/02/2023 | 0 | Resource Division | 120.41 | 0 | 0
523 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Kaliyaganj & Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000024/2023-2024 | 1286/RD/PHE | 08/05/2023 | 970 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 616.73 | 0 | 15
524 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Kaluhar village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000153/2024-2025 | 2885/RD/PHE | 25/09/2024 | 60 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 40.07 | 0 | 0
525 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Jujharpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000284/2021-2022 | 1820/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.76 | 0 | 0
526 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jujharpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000446/2021-2022 | 2382/RD/PHE | 24/12/2021 | 30 | SAHA CONSTRUCTION | 8.32 | 0 | 0
527 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000010/2021-2022 | 34/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.98 | 0 | 0
528 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000025/2022-2023 | 1817/RD/PHE | 28/09/2022 | 0 | Resource Division | 1.11 | 0 | 0
529 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Bamair Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000133/2022-2023 | 1911/RD/PHE | 28/10/2022 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 35.1 | 0 | 75
530 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000113/2023-2024 | 10/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
531 | Raiganj Division | Islampur Sub-Division | Dismantling of all types of plain cement concrete works and concreting with Ordinary Cement Concrete for laying of Pipe Line to provide FHTC at JUJHARPUR Piped Water Supply Scheme (Augmentation Jujharpur) at Karandighi Block under Islampur Sub-Division under Raiganj Division, PHE Dte. Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000128/2024-2025 | 3019/RD/PHE | 03/10/2024 | 180 | A D ENTERPRISE | 40.14 | 0 | 80
532 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway at Head Work Site Pump House for JUJHARPUR Piped Water Supply Scheme (Augmentation of Jujharpur) under Islampur Sub-Division PHED under Raiganj Division, PHED., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000129/2024-2025 | 3020/RD/PHE | 03/10/2024 | 30 | A D ENTERPRISE | 8.57 | 0 | 0
533 | Raiganj Division | Islampur Sub-Division | Land development at Head Work Site Pump House and other ancillary works for JUJHARPUR Piped Water Supply Scheme(Augmentation Jujharpur PWSS) under Islampur Sub-Division PHED under Raiganj Division, PHED., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000130/2024-2025 | 3021/RD/PHE | 03/10/2024 | 20 | A D ENTERPRISE | 10.89 | 0 | 0
534 | Raiganj Division | Islampur Sub-Division | Augmentation of JUJHARPUR and it's adjoining mouzas Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000223/2022-2023 | 126/RD/PHE | 20/01/2023 | 1075 | A D ENTERPRISE | 281.65 | 0 | 90
535 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jujharpur Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-50 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000360/2025-2026 | 2506/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.74 | 0 | 0
536 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000057/2022-2023 | 2170/RD/PHE | 09/12/2022 | 0 | Resource Division | 37.57 | 0 | 0
537 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line for Providing FHTC for Kotar Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. (Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000046/2022-2023 | 1010/RD/PHE | 11/05/2022 | 20 | SANDIP SARKAR | 4.84 | 0 | 1
538 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC for Bheur Water Supply Scheme Under Kaliyaganj Block under Raiganj Division P.H.E.Dte. in the District Of Uttar Dinajpur. (Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000026/2022-2023 | 1038/RD/PHED | 12/05/2022 | 30 | HERO CONSTRUCTION | 6.61 | 0 | 1
539 | Raiganj Division | Islampur Sub-Division | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of patagora- Moragoti Road under Uttar Dinajpur Division, PWD. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00507/2023-2024 | BP-2023-24-145 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 6.39 | 0 | 0
540 | Raiganj Division | Islampur Sub-Division | Implementation of BARAKHANTI and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000253/2022-2023 | 297/RD/PHE | 01/02/2023 | 1151 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 617.49 | 0 | 30
541 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARAKHANTI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000482/2023-2024 | 591/RD/PHE | 05/03/2024 | 45 | M/S DUTTA ENTERPRISE | 22.57 | 0 | 0
542 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
543 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000068/2022-2023 | 2185/RD/PHE | 12/12/2022 | 0 | Resource Division | 32.36 | 0 | 0
544 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000099/2022-2023 | 583/RD/PHE | 24/02/2023 | 0 | Resource Division | 32.13 | 0 | 0
545 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Bara Mircha Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000006/2025-2026 | 1171/RD/PHE | 23/04/2025 | 15 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.4 | 0 | 0
546 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
547 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at Bara Mircha PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000383/2025-2026 | 2095/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 25.81 | 0 | 0
548 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Mircha Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 25 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000394/2025-2026 | 1977/RD/PHE | 03/07/2025 | 180 | LIMRA CIVIL CONSTRUCTION | 16.3 | 0 | 0
549 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000049/2023-2024 | 1475/RD/PHE | 16/05/2023 | 0 | Resource Division | 16.84 | 0 | 0
550 | Raiganj Division | Raiganj Sub-Division | Implementation of UTTAR MIRZAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000197/2022-2023 | 66/RD/PHE | 16/01/2023 | 1081 | SANYAL ENTERPRISE | 277.69 | 0 | 65
551 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Mirzapur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000475/2024-2025 | 08/RD/PHE | 02/01/2025 | 45 | UTTAM SAHA | 51.89 | 0 | 0
552 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under UTTAR MIRZADPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000529/2023-2024 | 588/RD/PHE | 05/03/2024 | 45 | LAXMI ENTERPRISE (DIPAK MISHRA) | 11.29 | 0 | 0
553 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under UTTAR MIRZADPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000530/2023-2024 | 596/RD/PHE | 05/03/2024 | 405 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 11.29 | 0 | 80
554 | Raiganj Division | Raiganj Sub-Division | Trial Run For Uttar Mirzapur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000677/2024-2025 | 523/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0
555 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000092/2022-2023 | 28/RD/PHE | 06/01/2023 | 0 | Resource Division | 29.02 | 0 | 0
556 | Raiganj Division | Raiganj Sub-Division | Implementation of BHITIHAR andit's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000206/2022-2023 | 75/RD/PHE | 16/01/2023 | 1082 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 503.79 | 0 | 30
557 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHITIHAR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000470/2023-2024 | 578/RD/PHE | 05/03/2024 | 405 | RAKSHIT TRADERS | 22.58 | 0 | 100
558 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhitihar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000482/2024-2025 | 15/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 87.65 | 0 | 0
559 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000075/2022-2023 | 2192/RD/PHE | 12/12/2022 | 0 | Resource Division | 35.44 | 0 | 0
560 | Raiganj Division | Raiganj Sub-Division | Implementation of BALAS and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000199/2022-2023 | 68/RD/PHE | 16/01/2023 | 1081 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 359.92 | 0 | 70
561 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BALAS Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000468/2023-2024 | 576/RD/PHE | 05/03/2024 | 45 | BHOLA PAUL | 22.89 | 0 | 80
562 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Balas PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000495/2024-2025 | 28/RD/PHE | 02/01/2025 | 45 | BHOLA PAUL | 44.41 | 0 | 0
563 | Raiganj Division | Raiganj Sub-Division | Trial Run For Balas PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000681/2024-2025 | 527/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0
564 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000094/2022-2023 | 32/RD/PHE | 06/01/2023 | 0 | Resource Division | 22.64 | 0 | 0
565 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway with land development at Head Work Site Pump House & 2nd TW Site Pump House for BARABILLA Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000018/2025-2026 | 1202/RD/PHE | 25/04/2025 | 45 | GULJAN BEGAM | 9.98 | 0 | 0
566 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Barobilla Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000024/2025-2026 | 1179/RD/PHE | 23/04/2025 | 15 | HAQUE CONSTRUCTION | 6.94 | 0 | 0
567 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
568 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000015/2023-2024 | 1119/RD/PHE | 24/04/2023 | 0 | Resource Division | 27.72 | 0 | 0
569 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Ariagaon Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, ,Capacity- 35 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000323/2025-2026 | 1994/RD/PHE | 07/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.03 | 0 | 0
570 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
571 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000171/2022-2023 | 961/RD/PHE | 29/03/2023 | 0 | Resource Division | 19.09 | 0 | 0
572 | Raiganj Division | Islampur Sub-Division | New Service Connection charge with Security Deposit for Implementation of Manikpur PH-II WSS under Islampur CCC in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00496/2023-2024 | BP-2023-24-134 | 29/09/2023 | 0 | WEST BENGAL STATE ELETRICITY DISTRIBUTION COMPANY LIMITED | 23.16 | 0 | 0
573 | Raiganj Division | Islampur Sub-Division | Implementation of MANIKPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and 2nd Tube Well) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000299/2022-2023 | 548/RD/PHE | 23/02/2023 | 960 | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 457.08 | 0 | 85
574 | Raiganj Division | Islampur Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0
575 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANIKPUR Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000483/2023-2024 | 592/RD/PHE | 05/03/2024 | 180 | CHADNI CONSTRUCTION | 22.58 | 0 | 90
576 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Manikpur Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000512/2024-2025 | 57/RD/PHE | 03/01/2025 | 360 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 15.76 | 0 | 65
577 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
578 | Raiganj Division | Islampur Sub-Division | Trial Run For Manikpur PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000715/2024-2025 | 547/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0
579 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000112/2022-2023 | 597/RD/PHE | 27/02/2023 | 0 | Resource Division | 25.59 | 0 | 0
580 | Raiganj Division | Raiganj Sub-Division | Construction Over Head Resorvoir (OHR) and other allied works of GOURI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000019/2023-2024 | 1281/RD/PHE | 08/05/2023 | 970 | UTTAM SAHA | 240.92 | 0 | 50
581 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
582 | Raiganj Division | Raiganj Sub-Division | Implementation of GOURI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000094/2022-2023 | 1541/RD/PHE | 26/08/2022 | 806 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 376.23 | 0 | 56
583 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GOURI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000460/2023-2024 | 568/RD/PHE | 05/03/2024 | 225 | M/S BARENDRA CONSTRUCTION | 22.58 | 0 | 70
584 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Gouri PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000479/2024-2025 | 12/RD/PHE | 02/01/2025 | 45 | M/S P.S. ENTERPRISE | 88.14 | 0 | 0
585 | Raiganj Division | Raiganj Sub-Division | Trial Run For Gouri PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000691/2024-2025 | 536/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0
586 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000044/2022-2023 | 1957/RD/PHE | 04/11/2022 | 0 | Resource Division | 46.51 | 0 | 0
587 | Raiganj Division | Islampur Sub-Division | Implementation of KAMLAGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000300/2022-2023 | 549/RD/PHE | 23/02/2023 | 1008 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 442.06 | 0 | 45
588 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipeline With landf development and path way for KAMLAGAON Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000416/2024-2025 | 3580/RD/PHE | 05/12/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 80.34 | 0 | 0
589 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000119/2022-2023 | 614/RD/PHE | 28/02/2023 | 0 | Resource Division | 29.14 | 0 | 0
590 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Solpara Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000022/2025-2026 | 1177/RD/PHE | 23/04/2025 | 30 | CHAITANYA SAMAL | 10.15 | 0 | 0
591 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at SHOLPARA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000257/2025-2026 | 2047/RD/PHE | 10/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 52.51 | 0 | 0
592 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sholpara Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000312/2025-2026 | 1979/RD/PHE | 03/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0
593 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000021/2023-2024 | 1117/RD/PHE | 24/04/2023 | 0 | Resource Division | 51.31 | 0 | 0
594 | Raiganj Division | Raiganj Sub-Division | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 0 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0
595 | Raiganj Division | Raiganj Sub-Division | Implementation of Basain and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000152/2022-2023 | 1991/RD/PHE | 14/11/2022 | 1145 | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 456.96 | 0 | 62
596 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House & Boundary Wall at Basain Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000259/2022-2023 | 385/RD/PHE | 08/02/2023 | 60 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 36.15 | 0 | 100
597 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Basain PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000442/2024-2025 | 3754/RD/PHED | 18/12/2024 | 270 | AJIT PRAMANIK | 39.05 | 0 | 80
598 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
599 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000055/2022-2023 | 2124/RD/PHE | 03/12/2022 | 0 | Resource Division | 21.7 | 0 | 0
600 | Raiganj Division | Raiganj Sub-Division | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur -Bhatol Road due to pipe laying under Makdampur Pipe Water Supply Scheme at different stretches of road under Uttar Dinajpur Highway Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00320/2024-2025 | BP-2024-25-197 | 20/09/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 13.36 | 0 | 0
601 | Raiganj Division | Raiganj Sub-Division | Laying Pipe line at MOKDOMPUR Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000037/2023-2024 | 1536/RD/PHE | 24/05/2023 | 678 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 65.55 | 0 | 50
602 | Raiganj Division | Raiganj Sub-Division | Implementation of MAKDAMPUR andit's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000153/2022-2023 | 1992/RD/PHE | 14/11/2022 | 1146 | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 412.01 | 0 | 70
603 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House & Boundary Wall at Makdampur Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubaeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000258/2022-2023 | 384/RD/PHE | 08/02/2023 | 810 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 36.14 | 0 | 60
604 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Makdampur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000441/2024-2025 | 3753/RD/PHED | 18/12/2024 | 225 | SANDIP SARKAR | 34.56 | 0 | 65
605 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000053/2022-2023 | 2122/RD/PHE | 03/12/2022 | 0 | Resource Division | 69.45 | 0 | 0
606 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
607 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000176/2022-2023 | 977/RD/PHE | 30/03/2023 | 0 | Resource Division | 34.86 | 0 | 0
608 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Tarapur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000293/2025-2026 | 1826/RD/PHE | 25/06/2025 | 180 | AJIT PRAMANIK | 29.59 | 0 | 0
609 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
610 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000006/2023-2024 | 1044/RD/PHE | 05/04/2023 | 0 | Resource Division | 29.31 | 0 | 0
611 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Rampur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000318/2025-2026 | 1987/RD/PHE | 04/07/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0
612 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
613 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000148/2022-2023 | 849/RD/PHE | 24/03/2023 | 0 | Resource Division | 28.8 | 0 | 0
614 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Majlishpur Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000192/2022-2023 | 61/RD/PHE | 16/01/2023 | 45 | DONE ENTERPRISE PAPIYABHOWMICK7@GMAIL.COM | 17.7 | 0 | 62
615 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 100
616 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000095/2023-2024 | 2387/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
617 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakhin Ariagaon Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000349/2025-2026 | 2495/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.58 | 0 | 0
618 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
619 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000160/2022-2023 | 899/RD/PHE | 28/03/2023 | 0 | Resource Division | 36.35 | 0 | 0
620 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Pokheria Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000194/2022-2023 | 62/RD/PHE | 16/01/2023 | 941 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17.78 | 0 | 90
621 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000278/2022-2023 | 471/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 80
622 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000099/2023-2024 | 2399/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.38 | 0 | 0
623 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
624 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000145/2022-2023 | 838/RD/PHE | 23/03/2023 | 0 | Resource Division | 41.51 | 0 | 0
625 | Raiganj Division | Islampur Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 13.09.2024 and 18.09.2024. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00385/2024-2025 | BP-2024-25-225 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.05 | 0 | 0
626 | Raiganj Division | Islampur Sub-Division | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bardahi PWSS at Karandighi Block under Raiganj Division, PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000163/2024-2025 | 2897/RD/PHE | 25/09/2024 | 20 | SANDIP SARKAR | 6.83 | 0 | 0
627 | Raiganj Division | Islampur Sub-Division | Implementation of BARDAHI and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000375/2023-2024 | 2628/RD/PHE | 13/09/2023 | 890 | A D ENTERPRISE | 183.7 | 0 | 55
628 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of BARDAHI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000376/2024-2025 | 3495/RD/PHE | 02/12/2024 | 45 | APEX ENTERPRISES | 24.82 | 0 | 0
629 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARDAHI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000554/2023-2024 | 654/RD/PHE | 05/03/2024 | 319 | UJJAL KUMAR SARKAR PARTNER KUMARUJJAL51@GMAIL.COM | 11.27 | 0 | 100
630 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARDAHI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000555/2023-2024 | 655/RD/PHE | 05/03/2024 | 319 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 11.27 | 0 | 100
631 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000029/2023-2024 | 1203/RD/PHE | 28/04/2023 | 0 | Resource Division | 22.84 | 0 | 0
632 | Raiganj Division | Raiganj Sub-Division | Implementation of BAHALA ZONE-II and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000016/2023-2024 | 1278/RD/PHE | 08/05/2023 | 969 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 345.32 | 0 | 52
633 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
634 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahala zone -2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000492/2024-2025 | 25/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 57.51 | 0 | 0
635 | Raiganj Division | Raiganj Sub-Division | Balance distribution System Of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHALA ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000510/2023-2024 | 635/RD/PHE | 05/03/2024 | 225 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 22.7 | 0 | 25
636 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
637 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000074/2023-2024 | 2241/RD/PHE | 02/08/2023 | 0 | Resource Division | 23.33 | 0 | 0
638 | Raiganj Division | Raiganj Sub-Division | Implementation of SAMASPUR and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000018/2023-2024 | 1280/RD/PHE | 08/05/2023 | 900 | UTTAM SAHA | 418.14 | 0 | 35
639 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
640 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
641 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Samaspur PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000493/2024-2025 | 26/RD/PHE | 02/01/2025 | 45 | UTTAM SAHA | 31.62 | 0 | 0
642 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
643 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000067/2023-2024 | 2250/RD/PHE | 03/08/2023 | 0 | Resource Division | 28.77 | 0 | 0
644 | Raiganj Division | Raiganj Sub-Division | Augmentation of ITAHAR Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000078/2023-2024 | 1997/RD/PHE | 13/07/2023 | 928 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 568.17 | 0 | 30
645 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road, Laying of Pipe Line,Retaining And Other Allied Works Of Itahar Zone -I Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000397/2024-2025 | 3566/RD/PHE | 05/12/2024 | 91 | AJIT PRAMANIK | 95.62 | 0 | 0
646 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0
647 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000022/2023-2024 | 1188/RD/PHE | 27/04/2023 | 0 | Resource Division | 288.75 | 0 | 0
648 | Raiganj Division | Raiganj Sub-Division | Implementation of DWIPNAGAR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000006/2023-2024 | 1133/RD/PHE | 24/04/2023 | 983 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 374.36 | 0 | 50
649 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Khalsi, 2.Dwipnagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000033/2023-2024 | 1490/RD/PHE | 17/05/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 52.73 | 0 | 90
650 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000047/2023-2024 | 1330/RD/PHE | 15/05/2023 | 0 | Resource Division | 77.13 | 0 | 0
651 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000135/2022-2023 | 653/RD/PHE | 03/03/2023 | 0 | Resource Division | 77.81 | 0 | 0
652 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Kanki PWSS 2.Deona PWSS 3.Pokheria PWSS 4.Lodhon PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and ongoing PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000321/2024-2025 | 3277/RD/PHE | 20/11/2024 | 45 | HAQUE CONSTRUCTION | 17.33 | 0 | 0
653 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Goagaon PWSS 2.Ghirnigaonkhas PWSS 3.Panjipara PWSS 4.Khowaspur PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000324/2024-2025 | 3278/RD/PHE | 20/11/2024 | 45 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 17.34 | 0 | 0
654 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Dakshin Kundalpukhur PWSS 2.Purba Chutiakhore PWSS 3.Pawakhali PWSS 4.Amalbari PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000325/2024-2025 | 3279/RD/PHE | 20/11/2024 | 45 | M/S LUCKY CONSTRUCTION | 17.32 | 0 | 0
655 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Bhutijhari PWSS 2.Matikunda PWSS 3.Goalpokhur PWSS 4.Chakulia PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000326/2024-2025 | 3280/RD/PHE | 20/11/2024 | 225 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 17.32 | 0 | 0
656 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Chotaparua PWSS 2.Udaypur PWSS 3.Piplan PWSS 4.Barua PWSS 5.Bindol PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000327/2024-2025 | 3281/RD/PHE | 20/11/2024 | 45 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 21.67 | 0 | 0
657 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Kasba NM PWSS 2.Sitgram PWSS 3.Sasan PWSS 4.Gutin PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000328/2024-2025 | 3282/RD/PHE | 20/11/2024 | 45 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 17.34 | 0 | 0
658 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Malgaon PWSS 2.Bheur PWSS 3.Purba Rampur PWSS 4.Faridpur PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte. (TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000329/2024-2025 | 3284/RD/PHE | 20/11/2024 | 45 | UJJAL KUMAR SARKAR PARTNER | 17.33 | 0 | 0
659 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Baruna PWSS 2.Mahinagar PWSS 3.Kunore PWSS 4.Majhiar PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte. (TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000330/2024-2025 | 3285/RD/PHE | 20/11/2024 | 45 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 17.33 | 0 | 0
660 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Sergram PWSS 2.Phulatti PWSS 3.Puria PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000331/2024-2025 | 3286/RD/PHE | 20/11/2024 | 45 | M/S BHOWMIK CONSTRUCTION | 13 | 0 | 0
661 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Surun PWSS 2.Shridharpur PWSS 3.Kaliganj PWSS 4.Chandol PWSS 5.Kotar PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000342/2024-2025 | 3287/RD/PHE | 20/11/2024 | 45 | PANDIT CONSTRUCTION | 21.67 | 0 | 0
662 | Raiganj Division |  | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Bamir PWSS 2.Hemtabad Zone-I PWSS 3.Poaltair PWSS 4.Tungail Bilpara PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. |  |  | ORD/000343/2024-2025 | 3283/RD/PHE | 20/11/2024 | 45 | BISWADEEP MALLICK | 17.34 | 0 | 0
663 | Raiganj Division |  | Construction of Soak well at Head Work Site of Paharajpur Piped Water Supply Scheme in connection with additional source of drinking water by creating stand posts and soak gallery at different locations in each Commissioned and On-Going PWSS under Raiganj Division, P.H.E. Dte. |  |  | ORD/000398/2023-2024 | 2672/RD/PHE | 20/09/2023 | 30 | M/S PRATIMA CHOUDHURY | 5.42 | 0 | 100
664 | Raiganj Division | Islampur Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 23.08.2024 & 28.08.2024. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00387/2024-2025 | BP-2024-25-221 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.08 | 0 | 0
665 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at AGOI PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000020/2025-2026 | 1204/RD/PHE | 25/04/2025 | 45 | M/S PINKI CONSTRUCTION | 63.3 | 0 | 0
666 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Agoi Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000025/2025-2026 | 1182/RD/PHE | 23/04/2025 | 30 | M/S SARKAR ENTERPRISE | 5.06 | 0 | 0
667 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Agoi Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000026/2025-2026 | 1181/RD/PHE | 23/04/2025 | 30 | ANILA CONSTRUCTION | 5.06 | 0 | 0
668 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000024/2023-2024 | 1198/RD/PHE | 28/04/2023 | 0 | Resource Division | 35.74 | 0 | 0
669 | Raiganj Division | Islampur Sub-Division | Source(Rig Bored Tube-Well) Augmentation of Bhagabati Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000126/2022-2023 | 1910/RD | 28/10/2022 | 45 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 32.3 | 0 | 0
670 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000108/2023-2024 | 2401/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0
671 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Kichaktola Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000023/2025-2026 | 1178/RD/PHE | 23/04/2025 | 30 | MAA SHEETALA ENTERPRISE | 12.76 | 0 | 0
672 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTCwith ancillary works at different mouzas at KICHAKTOLA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000264/2025-2026 | 2079/RD/PHE | 14/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 38.99 | 0 | 0
673 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kichaktala Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000292/2025-2026 | 1825/RD/PHE | 25/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.59 | 0 | 0
674 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000027/2023-2024 | 1200/RD/PHE | 28/04/2023 | 0 | Resource Division | 26.38 | 0 | 0
675 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
676 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000169/2022-2023 | 971/RD/PHE | 29/03/2023 | 0 | Resource Division | 31.69 | 0 | 0
677 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Goagaon Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000146/2022-2023 | 1924/RD/PHE | 28/10/2022 | 270 | S. B. CONSTRUCTION | 33.07 | 0 | 25
678 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000103/2023-2024 | 2391/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0
679 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Sherpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000142/2022-2023 | 1920/RD/PHE | 28/10/2022 | 786 | BIKASH KAR | 29.96 | 0 | 100
680 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000118/2023-2024 | 19/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
681 | Raiganj Division | Islampur Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/01223/2023-2024 | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 14.86 | 0 | 0
682 | Raiganj Division | Islampur Sub-Division | Augmentation of KARANDIGHI(Zone-I)Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000118/2022-2023 | 1670/RD/PHE | 05/09/2022 | 90 | DIPESH BHOWMIK | 196.21 | 0 | 100
683 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Karandighi Zone-I Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000170/2022-2023 | 2030/RD/PHE | 17/11/2022 | 1169 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 80.36 | 0 | 70
684 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000231/2022-2023 | 364/RD/PHE | 07/02/2023 | 45 | M/S MANDAL ENTERPRISE TUMPASONU05@YAHOO.COM | 4.12 | 0 | 100
685 | Raiganj Division | Islampur Sub-Division | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site in connection with Augmentation Of Karandighi Zone-I PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000334/2024-2025 | 3290/RD/PHE | 20/11/2024 | 30 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 15.76 | 0 | 0
686 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Karandighi Zone-I Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000355/2025-2026 | 2501/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 19.35 | 0 | 0
687 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-500 Cum) of KARANDIGHI(Zone-I) Pipe Water Supply Scheme at in connection with Augmentation Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000370/2022-2023 | 727/RD/PHE | 15/03/2023 | 839 | M/S ELITE CONSTRUCTION | 165.61 | 0 | 90
688 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC for Augmentation Of Karandighi Zone-I Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000465/2024-2025 | 3783/RD/PHE | 19/12/2024 | 405 | BHOLA PAUL | 46.07 | 0 | 60
689 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with augmentation of Karandighi Zone-I Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000502/2024-2025 | 47/RD/PHE | 03/01/2025 | 45 | M/S P.S. ENTERPRISE | 25.35 | 0 | 0
690 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000567/2022-2023 | 1030/RD/PHE | 31/03/2023 | 45 | M/S SANTI TRADERS | 5.03 | 0 | 100
691 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
692 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
693 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000031/2022-2023 | 1945/RD/PHE | 04/11/2022 | 0 | Resource Division | 112.29 | 0 | 0
694 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Lakhipur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000386/2021-2022 | 2081/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 9.01 | 0 | 100
695 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
696 | Raiganj Division | Islampur Sub-Division | Route Survey & Preparation of DPR of LAKHIPUR PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000754/2021-2022 | 152/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.38 | 0 | 0
697 | Raiganj Division | Islampur Sub-Division | Preparation of Additional DPR For Ramganj Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Ramganj PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000176/2022-2023 | 2134/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 1
698 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Ramganj Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Islampur Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000283/2021-2022 | 1819/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.37 | 0 | 0
699 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Ramganj PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000386/2023-2024 | 2605/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.91 | 0 | 100
700 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) Under Ramganj Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000392/2021-2022 | 2087/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 28.69 | 0 | 1
701 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000011/2021-2022 | 35/RD/PHE | 06/01/2022 | 0 | Resource Division | 6.81 | 0 | 0
702 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of PAHARAJPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000447/2021-2022 | 2383/RD/PHE | 24/12/2021 | 30 | M/S LOKENATH CONSTRUCTION | 8.44 | 0 | 0
703 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Siripur for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000439/2021-2022 | 2201/RD/PHE | 17/11/2021 | 30 | HAQUE CONSTRUCTION | 8.21 | 0 | 0
704 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Goagaon Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000363/2021-2022 | 2144/RD/PHE | 12/11/2021 | 30 | PANDIT CONSTRUCTION | 3.36 | 0 | 1
705 | Raiganj Division | Raiganj Sub-Division | Restoration Of Pipe Line For Providing FHTC for Maslandapur Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000027/2022-2023 | 1039/RD/PHED | 12/05/2022 | 30 | M/S MANDAL ENTERPRISE | 7.33 | 0 | 65
706 | Raiganj Division | Islampur Sub-Division | Restoration of Pipeline for Providing FHTC of Intia Water Supply Scheme for installation of FHTC under Raiganj Division, P.H.E Dte. (Phase - II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000025/2022-2023 | 1037/RD/PHED | 12/05/2022 | 30 | PANDIT CONSTRUCTION | 6.59 | 0 | 1
707 | Raiganj Division | Raiganj Sub-Division | Restoration of pipe line for providing FHTC for Sripur water Supply Scheme under Itahar Block under Raiganj Division PHE Dte.(Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000021/2022-2023 | 1033/RD/PHED | 12/05/2022 | 30 | UJJAL KUMAR SARKAR | 5.15 | 0 | 100
708 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Mahammadpur Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000139/2022-2023 | 1917/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 34.87 | 0 | 0
709 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000122/2023-2024 | 13/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
710 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe Line for providing F.H.T.C. at Bhagabati Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000038/2022-2023 | 1050/RD/PHED | 12/05/2022 | 45 | TAPAN KUMAR MAJUMDER | 14.06 | 0 | 1
711 | Raiganj Division | Islampur Sub-Division | Restoration of damaged Pipe Line work required for FHTC work at Bhagabati Piped Water Supply Scheme under Islampur Sub-Divion, P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000442/2021-2022 | 2319/RD/PHED | 09/12/2021 | 45 | M/S P.S. ENTERPRISE | 10.21 | 0 | 1
712 | Raiganj Division | Raiganj Sub-Division | Additional Pipe Line (UPVC) For Providing FHTC at Kasba(NM) PWSS at Raiganj Block of Uttar Dinajpur District Under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000032/2024-2025 | 1693/RD/PHE | 10/06/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 10.68 | 0 | 100
713 | Raiganj Division | Raiganj Sub-Division | Augmentation work of KASBA(NM) Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000097/2022-2023 | 1544/RD/PHE | 26/08/2022 | 90 | AJIT PARMANIK | 212.07 | 0 | 95
714 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at 2nd and 3rd Tube-Well Site under Augmentation Kasba NM PWSS at Raiganj Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000155/2024-2025 | 2887/RD/PHE | 25/09/2024 | 45 | BHOLA PAUL | 11.13 | 0 | 0
715 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Kasba(NM) Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000269/2022-2023 | 433/RD/PHE | 10/02/2023 | 45 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 3.24 | 0 | 0
716 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kasba(NM) Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000282/2025-2026 | 1801/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 18.73 | 0 | 0
717 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House (size 4.10 m x 3.50 m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at 3nd Tube-Well Site in connection with Augmentation of Kasba-NM PWSS | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000283/2023-2024 | 2362/RD/PHE | 11/08/2023 | 60 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 5.02 | 0 | 92
718 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-450 Cum) of KASBA(NM) Pipe Water Supply Scheme in connection with Augmentation at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000368/2022-2023 | 725/RD/PHE | 15/03/2023 | 716 | CHAKRABORTY CONSTRUCTION | 158.66 | 0 | 40
719 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Kasba(NM) Water Supply Scheme [Augmentation Scheme]in Raiganj Block Of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000402/2022-2023 | 757/RD/PHE | 17/03/2023 | 801 | BHOLA PAUL | 92.67 | 0 | 55
720 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Kasba NM PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000656/2024-2025 | 417/RD/PHE | 29/01/2025 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 11.32 | 0 | 0
721 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000047/2022-2023 | 1974/RD/PHE | 08/11/2022 | 0 | Resource Division | 36.35 | 0 | 0
722 | Raiganj Division | Raiganj Sub-Division | charges for vehicle inspection | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01127/2023-2024 | BP-2023-24-281 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0
723 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC for Noabari(Baruna) Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000559/2022-2023 | 1022/RD/PHE | 31/03/2023 | 45 | ANILA CONSTRUCTION | 11.49 | 0 | 100
724 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe line for providing FHTC for Noabari(Kunore) Pipe Water Supply Scheme of Kaliaganj Block in the District of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000560/2022-2023 | 1024/RD/PHE | 31/03/2023 | 30 | BHOWMICK ENTERPRISE | 0.91 | 0 | 0
725 | Raiganj Division | Islampur Sub-Division | Restoration of road for laying of water pipeline along and across the Kanki-Goagaon Road at different stretches under Chakulia PWSS under Raiganj Division, P.H.E.Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00020/2022-2023 |  | 07/12/2022 | 0 | EXECUTIVE ENGINEER PWD ROADS | 1.7 | 0 | 0
726 | Raiganj Division | Islampur Sub-Division |  | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00072/2022-2023 | BP-2022-23-264 | 30/12/2022 | 0 | EXECUTIVE ENGINEER PWD ROADS | 1.7 | 0 | 0
727 | Raiganj Division | Islampur Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/01219/2023-2024 | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 0.15 | 0 | 0
728 | Raiganj Division | Islampur Sub-Division | Augmentation of CHAKALIA Water Supply Scheme at Goalpokhar-II Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000075/2022-2023 | 1407/RD/PHE | 25/07/2022 | 890 | SANYAL ENTERPRISE | 248.78 | 0 | 85
729 | Raiganj Division | Islampur Sub-Division | Restoration of damaged pipeline due Culvert, Drain & PCC Road Construction with ancillary works at various mouzas in connection with Augmentation of Chakulia PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000134/2024-2025 | 3024/RD/PHE | 03/10/2024 | 60 | SANYAL ENTERPRISE | 20.59 | 0 | 0
730 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Chakulia Water Supply Scheme [Augmentation Scheme] in Goalpukhur-II Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000156/2022-2023 | 2016/RD/PHE | 17/11/2022 | 90 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 80 | 0 | 65
731 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, & 3rd Tube-Well Site under Augmentation of Chakulia PWSS at Goalpukhur-II Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000159/2024-2025 | 2891/RD/PHE | 25/09/2024 | 315 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 44.17 | 0 | 75
732 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-500 Cum) of CHAKULIA Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000371/2022-2023 | 728/RD/PHE | 15/03/2023 | 365 | MD HAKIMUDDIN | 165.54 | 0 | 0
733 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with augmentation of Chakulia Pipe Water Supply Scheme at Goalpokher-II Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000506/2024-2025 | 51/RD/PHE | 03/01/2025 | 45 | AJIT PRAMANIK | 15.76 | 0 | 0
734 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000048/2022-2023 | 1975/RD/PHE | 08/11/2022 | 0 | Resource Division | 70.56 | 0 | 0
735 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pothia Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000317/2025-2026 | 1986/RD/PHE | 04/07/2025 | 180 | AJIT PRAMANIK | 30.94 | 0 | 0
736 | Raiganj Division | Islampur Sub-Division | Implementation of POTHIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000332/2022-2023 | 675/RD/PHE | 06/03/2023 | 1204 | UJJWAL DAS | 511.92 | 0 | 20
737 | Raiganj Division | Islampur Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0
738 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of POTHIA PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000370/2024-2025 | 3489/RD/PHE | 02/12/2024 | 90 | UJJWAL DAS | 36.3 | 0 | 50
739 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under POTHIA Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000485/2023-2024 | 594/RD/PHE | 05/03/2024 | 45 | PRINCE BUILDERS | 22.58 | 0 | 0
740 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000115/2022-2023 | 607/RD/PHE | 27/02/2023 | 0 | Resource Division | 43.16 | 0 | 0
741 | Raiganj Division | Islampur Sub-Division | MDR T01, RAMKRISHHNAPUR TO MDR T10 DIMTI VIA BHARDRAKALI (ROAD CODE T06) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00107/2024-2025 | BP-2024-25-73 | 12/06/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 12.52 | 0 | 0
742 | Raiganj Division | Islampur Sub-Division | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of patagora- Moragoti Road under Uttar Dinajpur Division, PWD. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00507/2023-2024 | BP-2023-24-145 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 6.39 | 0 | 0
743 | Raiganj Division | Islampur Sub-Division | Implementation of AGDIMTI and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under RaiganjDivision. PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000001/2023-2024 | 1035/RD/PHE | 04/04/2023 | 1066 | SOVAN KUMAR ROY | 563.17 | 0 | 71
744 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway ,Land development and other ancillary works for AGDIMTI Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000420/2024-2025 | 3583/RD/PHE | 05/12/2024 | 30 | SOVAN KUMAR ROY | 10.96 | 0 | 0
745 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under AGDIMTI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000480/2023-2024 | 589/RD/PHE | 05/03/2024 | 90 | BABA LOKNATH ENTERPRISE | 22.57 | 0 | 0
746 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
747 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000034/2023-2024 | 1217/RD/PHE | 02/05/2023 | 0 | Resource Division | 30.24 | 0 | 0
748 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000069/2022-2023 | 2186/RD/PHE | 12/12/2022 | 0 | Resource Division | 30.47 | 0 | 0
749 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000065/2022-2023 | 2182/RD/PHE | 12/12/2022 | 0 | Resource Division | 33.1 | 0 | 0
750 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000079/2022-2023 | 580/RD/PHE | 24/02/2023 | 0 | Resource Division | 33.1 | 0 | 0
751 | Raiganj Division | Raiganj Sub-Division | Implementation of PURGRAM and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000201/2022-2023 | 70/RD/PHE | 16/01/2023 | 365 | SANYAL ENTERPRISE | 365.19 | 0 | 70
752 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purgram Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000261/2025-2026 | 1626/RD/PHE | 19/06/2025 | 180 | AJIT PRAMANIK | 18.73 | 0 | 0
753 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Purgram PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000476/2024-2025 | 09/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 38.95 | 0 | 0
754 | Raiganj Division | Raiganj Sub-Division | Trial Run For Purgram PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000680/2024-2025 | 526/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0
755 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000073/2022-2023 | 2190/RD/PHE | 12/12/2022 | 0 | Resource Division | 44.2 | 0 | 0
756 | Raiganj Division | Raiganj Sub-Division | Balance Distribution system of Laying Pipeline with FHTC under Chandipur Piped Water Supply Scheme at Kaliyaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dijanpur. (Phase-II) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000122/2024-2025 | 3012/RD/PHE | 03/10/2024 | 495 | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 66.23 | 0 | 50
757 | Raiganj Division | Raiganj Sub-Division | Implementation of CHANDIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000207/2022-2023 | 76/RD/PHE | 16/01/2023 | 1081 | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 253.54 | 0 | 25
758 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHANDIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000473/2023-2024 | 581/RD/PHE | 05/03/2024 | 45 | TRINAYANI ENTERPRISE | 22.58 | 0 | 0
759 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000071/2022-2023 | 2188/RD/PHE | 12/12/2022 | 0 | Resource Division | 21.78 | 0 | 0
760 | Raiganj Division | Raiganj Sub-Division | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 0 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0
761 | Raiganj Division | Raiganj Sub-Division | Implementation of RAMPUR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000245/2022-2023 | 294/RD/PHE | 01/02/2023 | 1065 | UTTAM SAHA | 588.22 | 0 | 40
762 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Rampur Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000275/2025-2026 | 1796/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.92 | 0 | 0
763 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Rampur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000444/2024-2025 | 3756/RD/PHED | 18/12/2024 | 103 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 95.53 | 0 | 0
764 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAMPUR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000478/2023-2024 | 586/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.82 | 0 | 90
765 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
766 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000066/2022-2023 | 2183/RD/PHE | 12/12/2022 | 0 | Resource Division | 48.49 | 0 | 0
767 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Phulatti Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000143/2022-2023 | 1921/RD/PHE | 28/10/2022 | 815 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 25.83 | 0 | 85
768 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000111/2023-2024 | 09/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
769 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for Kundargaon Piped Water Supply Scheme under Islampur Sub-Division PHED under Raiganj Division, PHED., U/D. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000251/2025-2026 | 2042/RD/PHE | 09/07/2025 | 90 | M/S RATAN SARKAR & SON | 5.4 | 0 | 0
770 | Raiganj Division | Islampur Sub-Division | Implementation of KUNDARGAON and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rd Tube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000303/2022-2023 | 552/RD/PHE | 23/02/2023 | 720 | SANYAL ENTERPRISE | 321.28 | 0 | 60
771 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Kundargaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000365/2024-2025 | 3484/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 41.22 | 0 | 0
772 | Raiganj Division | Islampur Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
773 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KUNDARGAON Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000549/2024-2025 | 293/RD/PHE | 15/01/2025 | 45 | MOON CONSTRUCTION | 22.58 | 0 | 0
774 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
775 | Raiganj Division | Islampur Sub-Division | Trial Run For Kundargaon PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000721/2024-2025 | 553/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0
776 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000118/2022-2023 | 617/RD/PHE | 28/02/2023 | 0 | Resource Division | 24.12 | 0 | 0
777 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at UTTAR GORASAHID PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000030/2025-2026 | 1208/RD/PHE | 25/04/2025 | 45 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 40.28 | 0 | 0
778 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Uttar Gorasahid Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000283/2025-2026 | 1802/RD/PHE | 24/06/2025 | 180 | FIZA CONSTRUCTION | 29.57 | 0 | 0
779 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
780 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000044/2023-2024 | 1328/RD/PHE | 15/05/2023 | 0 | Resource Division | 50.25 | 0 | 0
781 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
782 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ghirnigaon Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 20 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000391/2025-2026 | 1824/RD/PHE | 25/06/2025 | 180 | FARQUE AZAM | 15.37 | 0 | 0
783 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000166/2022-2023 | 969/RD/PHE | 29/03/2023 | 0 | Resource Division | 16.16 | 0 | 0
784 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Goalin Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000276/2025-2026 | 2181/RD/PHE | 29/07/2025 | 90 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 6.17 | 0 | 0
785 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000013/2023-2024 | 1125/RD/PHE | 24/04/2023 | 0 | Resource Division | 43.9 | 0 | 0
786 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC at different mouzas at ANGARBHASA PWSS of Goalpokhar-I Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000258/2025-2026 | 2048/RD/PHE | 10/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 29.06 | 0 | 0
787 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Angurbhasa Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000277/2025-2026 | 2182/RD/PHE | 29/07/2025 | 90 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 5.79 | 0 | 0
788 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Angarbhasa Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000295/2025-2026 | 1923/RD/PHE | 30/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.74 | 0 | 0
789 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
790 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000017/2023-2024 | 1118/RD/PHE | 24/04/2023 | 0 | Resource Division | 29.16 | 0 | 0
791 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
792 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000180/2022-2023 | 981/RD/PHE | 30/03/2023 | 0 | Resource Division | 50.16 | 0 | 0
793 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
794 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000179/2022-2023 | 979/RD/PHE | 30/03/2023 | 0 | Resource Division | 38.57 | 0 | 0
795 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000290/2022-2023 | 539/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 65
796 | Raiganj Division | Raiganj Sub-Division | Implementation of KOKRA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000321/2022-2023 | 557/RD/PHE | 23/02/2023 | 1159 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 264.99 | 0 | 5
797 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kokra PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000446/2024-2025 | 3758/RD/PHED | 18/12/2024 | 90 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 24.91 | 0 | 0
798 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000150/2022-2023 | 863/RD/PHE | 25/03/2023 | 0 | Resource Division | 33.6 | 0 | 0
799 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line for Providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000020/2022-2023 | 1032/RD/PHED | 12/05/2022 | 30 | SARNALI ENTERPRISE | 5.79 | 0 | 1
800 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
801 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000291/2022-2023 | 540/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 80
802 | Raiganj Division | Raiganj Sub-Division | Implementation of BHATTAGIDIGHI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000322/2022-2023 | 559/RD/PHE | 23/02/2023 | 1043 | M/S LOKENATH CONSTRUCTION | 618.78 | 0 | 45
803 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site , Tube well and Pump Houseroad restoration of Bhattadighi PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000469/2024-2025 | 02/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 69.15 | 0 | 0
804 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000105/2022-2023 | 578/RD/PHE | 24/02/2023 | 0 | Resource Division | 47.07 | 0 | 0
805 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall with Gate at Head Work Site & repair, renovation of boundary wall of 2nd Tube-Well Site under Augmentation of Khanta (Rasakhowa) PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000052/2025-2026 | 1542/RD/PHE | 11/06/2025 | 90 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 12.61 | 0 | 0
806 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall with Gate at Head Work Site & repair, renovation of boundary wall of 2nd Tube-Well Site under Augmentation of Khanta (Rasakhowa) PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000088/2025-2026 | 1437/RD/PHE | 30/05/2025 | 90 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 12.61 | 0 | 0
807 | Raiganj Division | Islampur Sub-Division | Repairing for 2nd Pump House & Construction of Toilet at Kahanta (Rasakhowa) in connection with Augmentation of Khanta PWSS under Islampur Sub-Division under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000107/2023-2024 | 2051/RD/PHE | 19/07/2023 | 496 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 3.12 | 0 | 100
808 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (size 5.40m x 4.10m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at Head Work Site of Augmentation Of KHANTA-RASAKHOWA Piped Water Supply Schemes under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000288/2023-2024 | 2361/RD/PHE | 11/08/2023 | 60 | BISWA PROKASH JHA | 5.75 | 0 | 100
809 | Raiganj Division | Islampur Sub-Division | Augmentation of KHANTA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000306/2022-2023 | 570/RD/PHE | 23/02/2023 | 768 | PRASANTA DUTTA | 363.57 | 0 | 65
810 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Khanta-Rasakhowa Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity-70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000351/2025-2026 | 2497/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0
811 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway ,Land development and other ancillary works for Augmentation Of KHANTA RASAKHOWA Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000457/2024-2025 | 3775/RD/PHE | 19/12/2024 | 45 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 26.93 | 0 | 0
812 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000136/2022-2023 | 722/RD/PHE | 15/03/2023 | 0 | Resource Division | 26.68 | 0 | 0
813 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
814 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000157/2022-2023 | 886/RD/PHE | 27/03/2023 | 0 | Resource Division | 47.4 | 0 | 0
815 | Raiganj Division | Islampur Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Raniganj, 2. Alianagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000296/2022-2023 | 542/RD/PHE | 22/02/2023 | 628 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 51.42 | 0 | 80
816 | Raiganj Division | Islampur Sub-Division | Implementation of RANIGANJ and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000359/2023-2024 | 2475/RD/PHE | 24/08/2023 | 862 | UJJWAL DAS | 509.3 | 0 | 80
817 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway ,Land development and other ancillary works for RANIGANJ Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000500/2024-2025 | 45/RD/PHE | 03/01/2025 | 225 | GULJAN BEGAM | 22.31 | 0 | 60
818 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000155/2022-2023 | 887/RD/PHE | 27/03/2023 | 0 | Resource Division | 73.71 | 0 | 0
819 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000291/2022-2023 | 540/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 80
820 | Raiganj Division | Raiganj Sub-Division | Implementation of MAHARAJPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000323/2022-2023 | 560/RD/PHE | 23/02/2023 | 1042 | UTTAM SAHA | 600.95 | 0 | 40
821 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Maharajpur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000445/2024-2025 | 3757/RD/PHED | 18/12/2024 | 45 | UTTAM SAHA | 22.87 | 0 | 0
822 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000151/2022-2023 | 864/RD/PHE | 25/03/2023 | 0 | Resource Division | 46.67 | 0 | 0
823 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
824 | Raiganj Division | Islampur Sub-Division | Trial Run For Samaspur PWSS under Goalpukhur-II Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000722/2024-2025 | 554/RD/PHE | 12/02/2025 | 90 | SANDIP SARKAR | 0.87 | 0 | 0
825 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000164/2022-2023 | 962/RD/PHE | 29/03/2023 | 0 | Resource Division | 31.81 | 0 | 0
826 | Raiganj Division | Islampur Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/01222/2023-2024 | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 9.3 | 0 | 0
827 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway at 2nd TW Site Pump House for BHULKI Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000366/2024-2025 | 3485/RD/PHE | 02/12/2024 | 15 | BHAGYA LAXMI ENTERPRISE | 4.28 | 0 | 0
828 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of BHULKI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000375/2024-2025 | 3494/RD/PHE | 02/12/2024 | 45 | S.B.CONSTRUCTION | 34.78 | 0 | 0
829 | Raiganj Division | Islampur Sub-Division | Construction of Reinforcement Concrete Pathway at Headwork Site for Bhulki PWSS of Islampur Sub-Division under Raiganj Division, PHE Dte.(NEW Scheme) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000393/2023-2024 | 2654/RD/PHE | 15/09/2023 | 30 | R. R. CONSTRUCTION | 9.98 | 0 | 0
830 | Raiganj Division | Islampur Sub-Division | Implementation of BHULKI and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000395/2022-2023 | 747/RD/PHE | 16/03/2023 | 1090 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 463.74 | 0 | 20
831 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC for New Scheme Of Bhulki Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000467/2024-2025 | 3785/RD/PHE | 19/12/2024 | 45 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 34.76 | 0 | 0
832 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHULKI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000516/2023-2024 | 647/RD/PHE | 05/03/2024 | 149 | SANDIP SARKAR | 22.58 | 0 | 0
833 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000129/2022-2023 | 634/RD/PHE | 02/03/2023 | 0 | Resource Division | 58.74 | 0 | 0
834 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of KHESRA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000413/2021-2022 | 2116/RD/PHE | 03/11/2021 | 30 | KARTICK BISWAS | 15.94 | 0 | 1
835 | Raiganj Division | Raiganj Sub-Division | office accessories bill | Assistant Engineer RSD | Junior Engineer, RSD | VCH/000314/2022-2023 | BP-2022-23-35 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.07 | 0 | 0
836 | Raiganj Division | Raiganj Sub-Division | office accessories | Assistant Engineer RSD | Junior Engineer, RSD | VCH/000315/2022-2023 | BP-2022-23-34 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
837 | Raiganj Division | Raiganj Sub-Division | office accessories bill | Assistant Engineer RSD | Junior Engineer, RSD | VCH/000316/2022-2023 | BP-2022-23-33 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
838 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
839 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
840 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000149/2022-2023 | 846/RD/PHE | 24/03/2023 | 0 | Resource Division | 64.22 | 0 | 0
841 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of Boundary Wall with Gate at Head Work Site& 2nd Tube-Well Site under Shripur PWSS at Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000051/2025-2026 | 1541/RD/PHE | 11/06/2025 | 90 | BISWA PROKASH JHA | 24.48 | 0 | 0
842 | Raiganj Division | RWS Raiganj Sub-Divisin | Additional pipeline and other ancillary works at Shiripur piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000356/2024-2025 | 3309/RD/PHE | 20/11/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 12.42 | 0 | 0
843 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of concrete pathway with earth Filling at Head Work Site Pump House & 2nd TW Site Pump House for Shiripur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHE Dte., U/D. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000359/2024-2025 | 3310/RD/PHE | 20/11/2024 | 30 | NIRMAN ENTERPRISE | 10.84 | 0 | 0
844 | Raiganj Division | RWS Raiganj Sub-Divisin | Implementation of SHRIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000384/2023-2024 | 2629/RD/PHE | 13/09/2023 | 1091 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 403.31 | 0 | 45
845 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | RTOR000040/2023-2024 | 1320/RD/PHE | 12/05/2023 | 0 | Resource Division | 35.97 | 0 | 0
846 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakhshin Makhanpukur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000333/2025-2026 | 2016/RD/PHE | 08/07/2025 | 180 | S. DUTTA | 20.74 | 0 | 0
847 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
848 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000161/2022-2023 | 898/RD/PHE | 28/03/2023 | 0 | Resource Division | 21.54 | 0 | 0
849 | Raiganj Division | Raiganj Sub-Division | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 16.02.2023 to 15.03.2023. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00945/2023-2024 |  | 05/12/2023 | 0 | DEBASISH GHOSH | 0.32 | 0 | 0
850 | Raiganj Division | Raiganj Sub-Division |  | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00989/2023-2024 | BP-2023-24-212 | 07/12/2023 | 0 | DEBASISH GHOSH | 0.32 | 0 | 0
851 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Suragapur zone I PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000471/2024-2025 | 04/RD/PHE | 02/01/2025 | 45 | M/S MAA TARA CONSTRUCTION | 51.54 | 0 | 0
852 | Raiganj Division | Raiganj Sub-Division | Implementation of SURANGAPUR (ZONE-I) and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000495/2022-2023 | 806/RD/PHE | 21/03/2023 | 890 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 363.11 | 0 | 60
853 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000548/2023-2024 | 640/RD/PHE | 05/03/2024 | 180 | UTPAL SAHA | 12.24 | 0 | 90
854 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000549/2023-2024 | 641/RD/PHE | 05/03/2024 | 45 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 12.24 | 0 | 80
855 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
856 | Raiganj Division | Raiganj Sub-Division | Trial Run For Surangapur Zone-I PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000684/2024-2025 | 532/RD/PHE | 12/02/2025 | 90 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0
857 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000055/2023-2024 | 1681/RD/PHE | 19/06/2023 | 0 | Resource Division | 29.81 | 0 | 0
858 | Raiganj Division | Raiganj Sub-Division | Implementation of RAYNAGAR and it's adjoining mouzas Pipe Water Supply Scheme at KALIAGANJ Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000053/2023-2024 | 1560/RD/PHE | 29/05/2023 | 701 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 53.01 | 0 | 70
859 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Raynagar Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000346/2025-2026 | 2493/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 13.82 | 0 | 0
860 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000081/2023-2024 | 2258/RD/PHE | 03/08/2023 | 0 | Resource Division | 3.89 | 0 | 0
861 | Raiganj Division | Islampur Sub-Division | Implementation of BIRSINGGACHH Mini Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer-02 | ORD/000230/2023-2024 | 2379/RD/PHE | 14/08/2023 | 896 | MOTI INDUSTRIES | 66.92 | 0 | 80
862 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer-02 | RTOR000092/2023-2024 | 2298/RD/PHE | 04/08/2023 | 0 | Resource Division | 2.18 | 0 | 0
863 | Raiganj Division | Raiganj Sub-Division | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w Balufara to Agapur (Package No. WB15198), under coverage of Balufara Zone I PWSS (SM/17256) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00476/2024-2025 | BP-2024-25-277 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.41 | 0 | 0
864 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Balufara Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000487/2024-2025 | 20/RD/PHE | 02/01/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 10.09 | 0 | 0
865 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahala zone -I PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000490/2024-2025 | 23/RD/PHE | 02/01/2025 | 105 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 44.47 | 0 | 0
866 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under BALUFARA ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000497/2023-2024 | 619/RD/PHE | 05/03/2024 | 45 | M/S PRATIMA CHOUDHURY | 5.57 | 0 | 0
867 | Raiganj Division | Raiganj Sub-Division | Implementation of Balufara Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House Head Work.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000542/2022-2023 | 954/RD/PHE | 29/03/2023 | 703 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 88.07 | 0 | 50
868 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
869 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000071/2023-2024 | 2236/RD/PHE | 02/08/2023 | 0 | Resource Division | 6.43 | 0 | 0
870 | Raiganj Division | Raiganj Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 100
871 | Raiganj Division | Raiganj Sub-Division | Augmentation of Sergram and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000523/2022-2023 | 883/RD/PHE | 27/03/2023 | 720 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 88.22 | 0 | 45
872 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000011/2023-2024 | 1104/RD/PHE | 20/04/2023 | 0 | Resource Division | 4.6 | 0 | 0
873 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line for Providing FHTC for Bamir Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase - II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000045/2022-2023 | 1009/RD/PHED | 11/05/2022 | 20 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 3.51 | 0 | 1
874 | Raiganj Division |  | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Budhra Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. |  |  | ORD/000335/2025-2026 | 2486/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.74 | 0 | 0
875 | Raiganj Division |  | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Budhra PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. |  |  | ORD/000454/2024-2025 | 3767/RD/PHED | 18/12/2024 | 165 | UTTAM SAHA | 33.94 | 0 | 60
876 | Raiganj Division |  | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BUDHRA PWSS at Karandighi Block under Raiganj Division, PHE Dte. |  |  | ORD/000550/2023-2024 | 644/RD/PHE | 05/03/2024 | 45 | JEET CONSTRUCTION UKILPARA | 11.29 | 0 | 0
877 | Raiganj Division |  | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BUDHRA PWSS at Karandighi Block under Raiganj Division, PHE Dte. |  |  | ORD/000551/2023-2024 | 645/RD/PHE | 05/03/2024 | 45 | BITTU ENTERPRISE | 11.29 | 0 | 10
878 | Raiganj Division |  | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). |  |  | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0
879 | Raiganj Division |  | Implementation of BUDHRA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) |  |  | ORD/000633/2023-2024 | 2888/RD/PHE | 30/10/2023 | 488 | M/S ALISA CONSTRUCTION | 352.41 | 0 | 35
880 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 638/RD/PHE | 02/03/2023 | 0 | Resource Division | 43.1 | 0 | 0
881 | Raiganj Division |  | Implementation of SADIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. |  |  | ORD/000421/2023-2024 | 2869/RD/PHE | 17/10/2023 | 990 | UTTAM SAHA | 645.28 | 0 | 57
882 | Raiganj Division |  | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sadipur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. |  |  | ORD/000514/2024-2025 | 3764/RD/PHED | 18/12/2024 | 45 | M/S REGAL BUILDERS | 94.78 | 0 | 0
883 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000125/2022-2023 | 640/RD/PHE | 02/03/2023 | 0 | Resource Division | 46.68 | 0 | 0
884 | Raiganj Division | Islampur Sub-Division | Additional Pipe Line and other ancillary works to provide FHTC at DHARAMPUR ZONE-I PWSS in connection with augmentation of Dharampur PWSS at Goalpokher-I Block under Islampur Sub-Division, P.H.E. Dte. under Raiganj Division ,PHED, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000131/2024-2025 | 3022/RD/PHE | 03/10/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 33.34 | 0 | 0
885 | Raiganj Division | Islampur Sub-Division | Augmentation of DHARAMPUR Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at Goalpukhur-I & II Block of Uttar Dinajpur District under Raiganj Division, PHE Dte.. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000216/2022-2023 | 114/RD/PHE | 20/01/2023 | 1072 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 388.45 | 0 | 74
886 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dharampur Zone-I Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000340/2025-2026 | 2489/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0
887 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
888 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000058/2022-2023 | 2171/RD/PHE | 09/12/2022 | 0 | Resource Division | 34.71 | 0 | 0
889 | Raiganj Division | Raiganj Sub-Division | Hiring of vehicle for inspection and monitoring of Augmentation work of Kasba(Itahar) under JJM under Raiganj sub-division of Raiganj Division, PHE Dte. for the period from 24.11.2022 to 05.12.2022. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00228/2023-2024 | BP-2023-24-76 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.1 | 0 | 0
890 | Raiganj Division | Raiganj Sub-Division | Augmentation work of KASBA(Itahar) and it's adjoining mouzas Piped Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000096/2022-2023 | 1543/RD/PHE | 26/08/2022 | 810 | SANYAL ENTERPRISE | 300.01 | 0 | 100
891 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Kasba (Itahar) Water Supply Scheme [Augmentation Scheme] in Itahar Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000159/2022-2023 | 2019/RD/PHE | 17/11/2022 | 90 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 60.76 | 0 | 0
892 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Kasba (Itahar) Water Supply Scheme Scheme at Itahar Block under Raiganj Division P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000261/2022-2023 | 387/RD/PHE | 07/02/2023 | 45 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 3.48 | 0 | 0
893 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Kasba Itahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000402/2024-2025 | 3571/RD/PHE | 05/12/2024 | 45 | SAHA CONSTRUCTION | 15.15 | 0 | 100
894 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Kasba Itahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000419/2024-2025 | 3572/RD/PHE | 05/12/2024 | 90 | SANTI TRADERS | 15.15 | 0 | 100
895 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000038/2022-2023 | 1951/RD/PHE | 04/11/2022 | 0 | Resource Division | 50.19 | 0 | 0
896 | Raiganj Division | Raiganj Sub-Division | Implementation of PASCHIM GAGRA and it's adjoining mouzas Pipe Water Supply Scheme at KALIAGANJ Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000052/2023-2024 | 1559/RD/PHE | 29/05/2023 | 90 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 59.46 | 0 | 61
897 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Gagra Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000345/2025-2026 | 2492/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 13.83 | 0 | 0
898 | Raiganj Division | Raiganj Sub-Division | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Paschim Gagra PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000464/2024-2025 | 3782/RD/PHE | 19/12/2024 | 45 | DAS CONSTRUCTION COMPANY | 5.78 | 0 | 0
899 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000109/2023-2024 | 3314/RD/PHE | 05/12/2023 | 0 | Resource Division | 3.25 | 0 | 0
900 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Dakshin Kundal Pukur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000449/2021-2022 | 2385/RD/PHE | 24/12/2021 | 30 | M/S LUCKY CONSTRUCTION | 13.19 | 0 | 0
901 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Pawakhali and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000260/2020-2021 | 1415/RD/PHE | 11/12/2020 | 40 | M/S J.S.B ASSOCIATE CONSTRUCTION | 76.67 | 0 | 100
902 | Raiganj Division | Islampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Purba-Rampur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj,Capacity- 80 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000002/2021-2022 | 1207/RD/PHE | 18/06/2021 | 90 | M/S LOKENATH CONSTRUCTION | 36.22 | 0 | 0
903 | Raiganj Division | Islampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Faridpur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj, Capacity- 60 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000006/2021-2022 | 1211/RD/PHE | 18/06/2021 | 90 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0
904 | Raiganj Division | Islampur Sub-Division | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Purba Chutiakhore Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Chopra, Capacity- 100 M3/hr. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000007/2021-2022 | 1212/RD/PHE | 18/06/2021 | 90 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.01 | 0 | 50
905 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-VI) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000018/2021-2022 | 1223/RD/PHE | 18/06/2021 | 30 | DONE ENTERPRISE | 8.83 | 0 | 0
906 | Raiganj Division | Islampur Sub-Division | Work Order for Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000115/2022-2023 | 1511/RD/PHE | 18/08/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 0
907 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Goagaon and adjoining Mouzas Water Supply Scheme in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000136/2020-2021 | 1535/RD/PHE | 23/12/2020 | 45 | ALOK ENTERPRISE | 112.77 | 0 | 0
908 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Malgaon and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000138/2020-2021 | 1536/RD/PHE | 23/12/2020 | 45 | UTTAM SAHA | 110.22 | 0 | 0
909 | Raiganj Division | Islampur Sub-Division | FHTC OF KHESRA WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000157/2020-2021 | 1515/RD | 23/12/2020 | 30 | MAA BICHITRA CONSTRUCTION | 8.64 | 0 | 0
910 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Intia and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000176/2020-2021 | 1541/RD/PHE | 23/12/2020 | 40 | UTTAM SAHA | 90.4 | 0 | 0
911 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Khesra and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000202/2020-2021 | 1525/RD/PHE | 23/12/2020 | 45 | UTTAM SAHA | 126.33 | 0 | 0
912 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Jaingaon and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000204/2020-2021 | 1538/RD/PHE | 23/12/2020 | 45 | M/S SOMNATH KUNDU | 104.31 | 0 | 90
913 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) under Ghirinigaon Khas and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E.Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000208/2020-2021 | 1532/RD/PHE | 23/12/2020 | 45 | SANYAL ENTERPRISE | 122.54 | 0 | 0
914 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER MAJLISHPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN GOALPOKHER-I BLOCK UNDER RAIGANJ DIVISION, P.H.E.DTE. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000215/2020-2021 | 1558/RD/PHE | 24/12/2020 | 60 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 151.59 | 0 | 0
915 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PIROJPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, P.H.E.DTE. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000216/2020-2021 | 1559/RD/PHE | 24/12/2020 | 60 | AJIT PARMANIK | 193.98 | 0 | 0
916 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kamartor and Adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000270/2020-2021 | 1414/RD/PHE | 11/12/2020 | 40 | J.D.J. ENTERPRISE | 88.73 | 0 | 100
917 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER UDAYPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000280/2020-2021 | 1561/RD/PHE | 24/12/2020 | 60 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 138.21 | 0 | 0
918 | Raiganj Division | Islampur Sub-Division | Providing Functional House Hold Connection (FHTC) for the purpose of Udaypur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000280/2022-2023 | 494/RD/PHE | 17/02/2023 | 45 | SANKAR DAS | 8.07 | 0 | 0
919 | Raiganj Division | Islampur Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER PIPLAN AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UNDER RAIGANJ DIVISION. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000281/2020-2021 | 1562/RD/PHE | 24/12/2020 | 60 | UTTAM SAHA | 144.08 | 0 | 0
920 | Raiganj Division | Islampur Sub-Division | Providing Functional House Hold Connection (FHTC) for the purpose of Maslandpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000281/2022-2023 | 495/RD/PHE | 17/02/2023 | 45 | GOPES SAHA | 6.91 | 0 | 0
921 | Raiganj Division | Islampur Sub-Division | Relaying of Pipe Line along embankment of Canal at Churakutti mouza for Functional Household Tap Connection of Majhlishpur Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000345/2021-2022 | 2159/RD/PHE | 12/11/2021 | 30 | SAHA CONSTRUCTION | 4.59 | 0 | 1
922 | Raiganj Division | Islampur Sub-Division | Allied Works for Construction and driving including vertical load test of 500 mm dia. (4 Piles Group) of Pile and 23mtr. deep in connection with construction of O.H.R. of FARIDPUR Water Supply Scheme under Raiganj Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000347/2021-2022 | 2161/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.43 | 0 | 1
923 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING OF FHTC OF MAJLISHPUR WSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000363/2020-2021 | 1576/RD | 23/12/2020 | 30 | DONE ENTERPRISE | 16.14 | 7.45 | 0
924 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Ghirnigaon Khas Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000431/2021-2022 | 2193/RD/PHE | 17/11/2021 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 88.75 | 0 | 0
925 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING OF GOAGAON PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000439/2020-2021 | 1513/RD | 23/12/2020 | 30 | M/S GHOSH CONSTRUCTION | 7.87 | 0 | 0
926 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jujharpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000446/2021-2022 | 2382/RD/PHE | 24/12/2021 | 30 | SAHA CONSTRUCTION | 8.32 | 0 | 0
927 | Raiganj Division | Islampur Sub-Division | SUPPLYING FITTING UPVC PIPE FOR PIROJPUR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000448/2020-2021 | 1521/RD | 03/12/2020 | 30 | M/S HINDUSTHAN CONSTRUCTION | 14.46 | 0 | 1
928 | Raiganj Division | Islampur Sub-Division | Restoration and Laying of Pipe Line for Functional Household Tap Connections of Biprit Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000451/2021-2022 | 2427/RD/PHE | 31/12/2021 | 30 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 4.95 | 0 | 100
929 | Raiganj Division | Islampur Sub-Division | SUPPLYING LAYING FITTING FIXING OF FHTC OF MAJLISHPUR PWSS | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000452/2020-2021 | 1576/ RD | 23/12/2020 | 30 | DONE ENTERPRISE | 16.14 | 0 | 0
930 | Raiganj Division | Islampur Sub-Division | Wok Order for supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete(1:2:4) in connection with Retrofitting of Functional Household Tap Connection(FHTC) under Majlishpur and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000478/2020-2021 | 1516/RD/PHE | 23/12/2020 | 30 | DONE ENTERPRISE | 16.13 | 0 | 0
931 | Raiganj Division | Islampur Sub-Division | office accessories bill | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/000319/2022-2023 | BP-2022-23-30 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0
932 | Raiganj Division | Islampur Sub-Division | office accessories bill | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/000326/2022-2023 | BP-2022-23-27 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.05 | 0 | 0
933 | Raiganj Division | Islampur Sub-Division | RESOURCE BILL | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | VCH/002570/2021-2022 | BP-2021-22-140 | 24/03/2022 | 0 | SUBSIDARY AC OF JJM WB ESCROW AC RESOURCE DIV PHE DIR | 37.16 | 0 | 0
934 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.07.2024 upto 14.01.2025). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000053/2024-2025 | 2159/RD/PHE | 15/07/2024 | 184 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0
935 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Sripur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000123/2020-2021 | 1237/RD/PHE | 16/10/2020 | 40 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 80.5 | 0 | 0
936 | Raiganj Division | Raiganj Sub-Division | LAYING FITTING FHTC OF SRIPUR WSS | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000156/2020-2021 | 1523/RD | 23/12/2020 | 30 | MS SARKAR ENTERPRISE ABDULGHATA | 8.14 | 5.63 | 0
937 | Raiganj Division | Islampur Sub-Division | FHTC FOR DEBIGANJ WSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000016/2020-2021 | 1236/RD | 16/10/2020 | 40 | HAQUE CONSTRUCTION | 56.27 | 53.65 | 0
938 | Raiganj Division | Islampur Sub-Division | FHTC OF DEBIGANJ WSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000111/2020-2021 | 1512/RD | 23/12/2020 | 30 | HAQUE CONSTRUCTION | 18.37 | 18.34 | 0
939 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) under Debiganj and adjoining Mouzas water supply scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000207/2020-2021 | 1236/RD/PHE | 16/10/2020 | 40 | HAQUE CONSTRUCTION | 56.27 | 0 | 0
940 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Chakulia PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000236/2025-2026 | 1040/RD/PHE | 02/04/2025 | 60 | ASHIM CHANDA | 0.98 | 0 | 0
941 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Chakulia Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Islampur Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000282/2021-2022 | 1818/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.84 | 0 | 0
942 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Chakulia Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-Ii Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000388/2021-2022 | 2083/RD/PHE | 02/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 10.6 | 0 | 1
943 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000012/2021-2022 | 36/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.5 | 0 | 0
944 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Goalpukhur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000391/2021-2022 | 2086/RD/PHE | 02/11/2021 | 421 | HAQUE CONSTRUCTION | 9.01 | 0 | 100
945 | Raiganj Division | Islampur Sub-Division | Route Survey & Preparation of DPR of GOALPOKHAR PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000752/2021-2022 | 150/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 4.32 | 0 | 0
946 | Raiganj Division | Islampur Sub-Division | Preparation of Additional DPR For Karandighi Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Karandighi PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000178/2022-2023 | 2150/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 1
947 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Karandighi Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000285/2021-2022 | 1821/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.29 | 0 | 0
948 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Karandighi PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000385/2023-2024 | 2604/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.95 | 0 | 100
949 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Karandighi Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000393/2021-2022 | 2088/RD/PHE | 02/11/2021 | 30 | MAA SHEETALA ENTERPRISE | 16.55 | 0 | 1
950 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Karandighi Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000740/2021-2022 | 436/RD/PHE | 16/02/2022 | 30 | M/S BHOWMIK CONSTRUCTION | 4.6 | 0 | 0
951 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000009/2021-2022 | 33/RD/PHE | 06/01/2022 | 0 | Resource Division | 3.93 | 0 | 0
952 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000023/2022-2023 | 1814/RD/PHE | 26/09/2022 | 0 | Resource Division | 2.83 | 0 | 0
953 | Raiganj Division | Islampur Sub-Division | Preparation of Additional DPR For Panjipara Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Panjipara PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000177/2022-2023 | 2135/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 1
954 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Panjipara Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000280/2021-2022 | 1816/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.3 | 0 | 0
955 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Panjipara PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000388/2023-2024 | 2608/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.84 | 0 | 100
956 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Panjipara Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000395/2021-2022 | 2090/RD/PHE | 02/11/2021 | 30 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.75 | 0 | 100
957 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000014/2021-2022 | 38/RD/PHE | 06/01/2022 | 0 | Resource Division | 3.98 | 0 | 0
958 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Tungail Bilpara Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000374/2021-2022 | 2155/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.55 | 0 | 1
959 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Sherpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000375/2021-2022 | 2156/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 4.51 | 0 | 0
960 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Dakshin Jibhakata Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000371/2021-2022 | 2152/RD/PHE | 12/11/2021 | 30 | M/S BHOWMIK ENTERPRISE | 1.38 | 0 | 1
961 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of GUTIN Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000398/2021-2022 | 2101RD/PHE | 03/11/2021 | 30 | M/S.BANGARAJ | 8.82 | 0 | 1
962 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of BHEUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000403/2021-2022 | 2106/RD/PHE | 03/11/2021 | 30 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 8.82 | 0 | 1
963 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SRIDHARPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000406/2021-2022 | 2109/RD/PHE | 03/11/2021 | 30 | RAHUL ENTERPRISE | 11.38 | 0 | 1
964 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SHERGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (PART-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000420/2021-2022 | 2182/RD/PHE | 17/11/2021 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 5.53 | 0 | 0
965 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SHERGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (PART-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000421/2021-2022 | 2183/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 14.39 | 0 | 0
966 | Raiganj Division | Raiganj Sub-Division | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. | Assistant Engineer RSD |  | BILL/00024/2024-2025 | BP-2024-25-18 | 15/04/2024 | 0 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0
967 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Barua Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD |  | ORD/000360/2021-2022 | 2141/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 1
968 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of BARUA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD |  | ORD/000428/2021-2022 | 2190/RD/PHE | 17/11/2021 | 30 | M/S P.S. ENTERPRISE | 18.32 | 0 | 0
969 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Sitgram Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000361/2021-2022 | 2142/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 1
970 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SITGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000429/2021-2022 | 2191/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 11.69 | 0 | 0
971 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Ghirnigaon Khas Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000431/2021-2022 | 2193/RD/PHE | 17/11/2021 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 88.75 | 0 | 0
972 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Kanki Matiari Water Supply Scheme [Augmentation Scheme] in Goalpukhur-II Block of Uttar Dinajpur District | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000006/2022-2023 | 1018/RD/PHED | 12/05/2022 | 45 | M/S SARKAR ENTERPRISE | 26.8 | 0 | 100
973 | Raiganj Division | Islampur Sub-Division | Additional Pipe line with construction of Boundary Wall(Head Work) and other ancillary works at Kanki-Matiari Piped Water Supply Scheme in connection with Augmentation of Kanki-Matiari PWSS under Islampur Sub-Division P.H.E. Dte Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000031/2024-2025 | 1691/RD/PHE | 10/06/2024 | 480 | HAQUE CONSTRUCTION | 25.31 | 0 | 50
974 | Raiganj Division | Islampur Sub-Division | Soil Investigation for Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Kanki Matiari W/S Scheme in Goalpukhur-II Block in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000051/2022-2023 | 1238/RD/PHE | 20/06/2022 | 20 | MOYTEC | 1.98 | 0 | 0
975 | Raiganj Division | Islampur Sub-Division | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000121/2022-2023 | 1502/RD | 18/08/2022 | 7 | JUMBO XEROX | 0.09 | 0 | 0
976 | Raiganj Division | Islampur Sub-Division | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000122/2022-2023 | 1503/RD | 18/08/2022 | 7 | JUMBO XEROX | 0.02 | 0 | 0
977 | Raiganj Division | Islampur Sub-Division | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000129/2022-2023 | 1537\RD | 25/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0
978 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Kanki-Matiari Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000248/2022-2023 | 378/RD/PHE | 07/02/2023 | 45 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 4.09 | 0 | 100
979 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Kanki Matiari Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000254/2022-2023 | 381/RD/PHE | 07/02/2023 | 45 | UJJAL KUMAR SARKAR KUMARUJJAL51@GMAIL.COM | 5.01 | 0 | 100
980 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-250 Cum) of KANKI MATIARI Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000326/2022-2023 | 655/RD/PHE | 03/03/2023 | 240 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 77.82 | 0 | 75
981 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kanki Matiari Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 25 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000361/2025-2026 | 2507/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 16.3 | 0 | 0
982 | Raiganj Division | Islampur Sub-Division | Laying of Distribution system including construction of Valve Chamber and Other related works for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur. (PART-A) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000467/2021-2022 | 50/RD/PHE | 07/01/2022 | 45 | HAQUE CONSTRUCTION | 59.72 | 0 | 100
983 | Raiganj Division | Islampur Sub-Division | Laying Rising Main pipeline interconnection of Tubewells including construction of Valve Chamber and Other related works for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur.(PART -A) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000472/2021-2022 | 48/RD/PHE | 07/01/2022 | 45 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 0.94 | 0 | 100
984 | Raiganj Division | Islampur Sub-Division | Sinking 2 nos. of Ground Bored wells,(250mm x 150mm X 120mtr) including cost of materials with proper development and necessary yield for ground water based PWSS for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000473/2021-2022 | 49/RD/PHE | 07/01/2022 | 21 | M/S SARKAR ENTERPRISE | 16.99 | 0 | 1
985 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000019/2021-2022 | 638/RD/PHE | 23/03/2022 | 0 | Resource Division | 8.75 | 0 | 0
986 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000051/2022-2023 | 2006/RD/PHE | 16/11/2022 | 0 | Resource Division | 10.51 | 0 | 0
987 | Raiganj Division | Islampur Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | VCH/001765/2022-2023 | BP-2022-23-212 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0
988 | Raiganj Division | Islampur Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | VCH/001770/2022-2023 | BP-2022-23-205 | 04/11/2022 | 0 | JUMBO XEROX | 0.09 | 0 | 0
989 | Raiganj Division | Islampur Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | VCH/001771/2022-2023 | BP-2022-23-206 | 04/11/2022 | 0 | JUMBO XEROX | 0.02 | 0 | 0
990 | Raiganj Division | Raiganj Sub-Division | hiring of inspection vehicle | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01128/2023-2024 | BP-2023-24-283 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0
991 | Raiganj Division | Raiganj Sub-Division | Restoration of pipe line for providing FHTC for Pirojpur Water Supply Scheme at Raiganj Block In the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte.(Phase-II). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000054/2022-2023 | 1273/RD/PHE | 24/06/2022 | 45 | TAPAN KUMAR DUTTA | 80.45 | 0 | 0
992 | Raiganj Division | Raiganj Sub-Division | DI Pipe Carrying RCC Structure Through River of Paschim Goalgaon PWSS(New Scheme) at Raiganj Block under Raiganj Division P.H.E. Dte., Uttar Dinajpur.(Phase-I) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000147/2024-2025 | 3015/RD/PHE | 03/10/2024 | 45 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 29.02 | 0 | 0
993 | Raiganj Division | Raiganj Sub-Division | Implementation of PASCHIM GOALGAON and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000154/2022-2023 | 1993/RD/PHE | 14/11/2022 | 1144 | M/S LOKENATH CONSTRUCTION | 487.48 | 0 | 60
994 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House & Boundary Wall at Paschim Goalgaon Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000257/2022-2023 | 383/RD/PHE | 07/02/2023 | 327 | HERO CONSTRUCTION HEROCONST.RNJ@GMAIL.COM | 35.61 | 0 | 67
995 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Paschim Goalgaon PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000480/2024-2025 | 13/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 43.4 | 0 | 0
996 | Raiganj Division | Raiganj Sub-Division | Trial Run For Paschim Goalgaon PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000690/2024-2025 | 535/RD/PHE | 12/02/2025 | 90 | M/S RATAN SARKAR & SON | 0.87 | 0 | 0
997 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000056/2022-2023 | 2125/RD/PHE | 03/12/2022 | 0 | Resource Division | 26.44 | 0 | 0
998 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Goalpokhor-ll & Goalpokhor-I, Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000035/2023-2024 | 1501/RD/PHE | 19/05/2023 | 92 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 432.57 | 0 | 2
999 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Itahara village under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD,Assistant Engineer RWS SD |  | ORD/000150/2024-2025 | 2882/RD/PHE | 25/09/2024 | 180 | MAA SHEETALA ENTERPRISE | 40.1 | 0 | 0
1000 | Raiganj Division | Raiganj Sub-Division | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 16.01.2023 to 15.02.2023. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00944/2023-2024 | BP-2023-24-213 | 07/12/2023 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0
1001 | Raiganj Division | Raiganj Sub-Division | Implementation of TENAHARI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000155/2022-2023 | 1994/RD/PHE | 14/11/2022 | 365 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 260.7 | 0 | 80
1002 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House & Boundary Wall at Tenahari Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. (Pump House at Head Work, 2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000260/2022-2023 | 386/RD/PHE | 08/02/2023 | 385 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 36.15 | 0 | 100
1003 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Tenahari PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000431/2024-2025 | 3744/RD/PHE | 18/12/2024 | 135 | M/S MAA TARA CONSTRUCTION | 26.62 | 0 | 0
1004 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1005 | Raiganj Division | Raiganj Sub-Division | Trial Run For Tenahari PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000704/2024-2025 | 543/RD/PHE | 12/02/2025 | 90 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0
1006 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000054/2022-2023 | 2123/RD/PHE | 03/12/2022 | 0 | Resource Division | 31.4 | 0 | 0
1007 | Raiganj Division | Raiganj Sub-Division | Implementation of KULIARA ANANTAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000218/2022-2023 | 96/RD/PHE | 19/01/2023 | 1078 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 369 | 0 | 45
1008 | Raiganj Division | Raiganj Sub-Division | Construction of Pump House & Boundary Wall at Kuliara Anantapur Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work, 2nd Tube Well and Boundary Wall at Head work Site and 2nd Tube-Well. ) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000255/2022-2023 | 382/RD/PHE | 08/02/2023 | 781 | M/S. BANGARAJ ASHOKLALRNJ@GMAIL.COM | 36.13 | 0 | 70
1009 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kuliara Anantapur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000438/2024-2025 | 3750/RD/PHED | 18/12/2024 | 135 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 40.59 | 0 | 0
1010 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000076/2022-2023 | 521/RD/PHE | 20/02/2023 | 0 | Resource Division | 33.03 | 0 | 0
1011 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000097/2022-2023 | 521/RD/PHE | 20/02/2023 | 0 | Resource Division | 32.76 | 0 | 0
1012 | Raiganj Division | Islampur Sub-Division | Inter-connecting various CIDF Pipe & with main delivery line and other ancillary works for Dharampur Zone- II Piped Water Supply Scheme (Augmentation Dharampur Zone-II)under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000132/2024-2025 | 3023/RD/PHE | 03/10/2024 | 20 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 8.8 | 0 | 0
1013 | Raiganj Division | Islampur Sub-Division | Augmentation of DHARAMPUR Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000215/2022-2023 | 125/RD/PHE | 20/01/2023 | 802 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 363.42 | 0 | 60
1014 | Raiganj Division | Islampur Sub-Division | Construction of Approach Road in connection with Augmentation of Dharampur Zone-II PWSS at Goalpokhur-I Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000340/2024-2025 | 3296/RD/PHE | 20/11/2024 | 15 | KULICK ENTERPRISE | 3.77 | 0 | 0
1015 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dharampur Zone-II Water Supply Scheme(Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000342/2025-2026 | 2490/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0
1016 | Raiganj Division | Islampur Sub-Division | Laying & Distribution pipeline at Dharampur Zone-II in connection with Augmentation of DHARAMPUR Zone-II at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.( Laying Distribution pipe line.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000427/2023-2024 | 3342/RD/PHE | 06/12/2023 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 71.53 | 0 | 60
1017 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000059/2022-2023 | 2172/RD/PHE | 09/12/2022 | 0 | Resource Division | 40.38 | 0 | 0
1018 | Raiganj Division | Islampur Sub-Division | Augmentation work of LAKHIPUR and it's adjoining mouzas Piped Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000098/2022-2023 | 1545/RD/PHE | 26/08/2022 | 90 | UTTAM SAHA | 194.17 | 0 | 0
1019 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Lakhipur Water Supply Scheme [Augmentation Scheme] in Chopra Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000167/2022-2023 | 2027/RD/PHE | 17/11/2022 | 90 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 79.41 | 0 | 45
1020 | Raiganj Division | Islampur Sub-Division | Repairing of Pump House at 2nd Tubewell Site in connection with Augmentation of Lakhipur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000244/2022-2023 | 375/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.09 | 0 | 0
1021 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Lakhipur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000266/2022-2023 | 406/RD/PHE | 09/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.95 | 0 | 0
1022 | Raiganj Division | Islampur Sub-Division | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation Of Lakhipur PWSS at Chopra Block under Raiganj Division, PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000339/2024-2025 | 3295/RD/PHE | 20/11/2024 | 480 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 8.59 | 0 | 70
1023 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC in connection with Augmentation Of Lakhipur Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000345/2024-2025 | 3298/RD/PHE | 20/11/2024 | 120 | D. K. ASSOCIATES | 9.35 | 0 | 100
1024 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-450 Cum) of LAKHIPUR Pipe Water Supply Scheme in connection with Augmentation at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000384/2022-2023 | 737/RD/PHE | 15/03/2023 | 365 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 158.66 | 0 | 0
1025 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Lakhipur Water Supply Scheme (Aumentation)at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000393/2025-2026 | 1927/RD/PHE | 30/06/2025 | 180 | KOHINOOR ALAM | 32.33 | 0 | 0
1026 | Raiganj Division | Islampur Sub-Division | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 366 | DEBASISH GHOSH | 4.8 | 0 | 0
1027 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000034/2022-2023 | 1946/RD/PHE | 04/11/2022 | 0 | Resource Division | 26.53 | 0 | 0
1028 | Raiganj Division | Raiganj Sub-Division | Augmentation work of HEMTABAD ZONE-I Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000119/2022-2023 | 1754/RD/PHE | 15/09/2022 | 90 | M/S LOKENATH CONSTRUCTION | 501.39 | 0 | 90
1029 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Hemtabad Zone-I Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000168/2022-2023 | 2028/RD/PHE | 17/11/2022 | 852 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 72.5 | 0 | 60
1030 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump house of Head Works and 2nd Tube Well Site in connection with Augmentation of Hemtabad Zone-I Water Supply Scheme at Hemtabad block under Raiganj Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000264/2022-2023 | 400/RD/PHE | 08/02/2023 | 45 | M/S SARKAR ENTERPRISE (UDAYPUR) SARKARTAPATI.UDI@GMAIL.COM | 2.98 | 0 | 100
1031 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-I) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000375/2022-2023 | 730/RD/PHE | 15/03/2023 | 438 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 143.13 | 0 | 40
1032 | Raiganj Division | Raiganj Sub-Division | Construction of boundary wall & toilet block of Augmentation of Hemtabad Zone-I PWSS at 2nd tube well site at Hemtabad block under Raiganj Division PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000413/2023-2024 | 2785/RD/PHE | 10/10/2023 | 75 | M/S SARKAR ENTERPRISE UDAYPUR | 5.05 | 0 | 100
1033 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000039/2022-2023 | 1952/RD/PHE | 04/11/2022 | 0 | Resource Division | 91.08 | 0 | 0
1034 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000051/2023-2024 | 1518/RD/PHE | 23/05/2023 | 0 | Resource Division | 2.02 | 0 | 0
1035 | Raiganj Division | Islampur Sub-Division | Restoration of Pipeline for Providing FHTC of Gunabari Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000034/2022-2023 | 1046/RD/PHED | 12/05/2022 | 45 | M/S.SADHANA ENTERPRISE | 10.26 | 0 | 1
1036 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Dakhshin Besabari Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000004/2025-2026 | 1173/RD/PHE | 23/04/2025 | 15 | R. R. CONSTRUCTION | 6.75 | 0 | 0
1037 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Besabari Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000347/2025-2026 | 1817/RD/PHE | 24/06/2025 | 180 | M K ENTERPRISE | 17.34 | 0 | 0
1038 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1039 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at DAKSHIN BESABRI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000384/2025-2026 | 2096/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 33.76 | 0 | 0
1040 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
1041 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000002/2023-2024 | 1039/RD/PHE | 04/04/2023 | 0 | Resource Division | 17.39 | 0 | 0
1042 | Raiganj Division | Raiganj Sub-Division | Implementation of PALIHAR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000249/2022-2023 | 295/RD/PHE | 01/02/2023 | 1065 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 509.77 | 0 | 67
1043 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Palihar PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000474/2024-2025 | 07/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 58.77 | 0 | 0
1044 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PALIHAR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000477/2023-2024 | 585/RD/PHE | 05/03/2024 | 45 | M/S ARITRA DUTTA | 22.57 | 0 | 0
1045 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1046 | Raiganj Division | Raiganj Sub-Division | Trial Run For Palihar PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000676/2024-2025 | 522/RD/PHE | 12/02/2025 | 90 | AJIT PRAMANIK | 0.88 | 0 | 0
1047 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000064/2022-2023 | 2181/RD/PHE | 12/12/2022 | 0 | Resource Division | 27.75 | 0 | 0
1048 | Raiganj Division | Raiganj Sub-Division | :Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Shibpur Madanpur Pacca Rasta - Kunarhat Tala Pacca Rasta ( WB15296 : Under DLP) caused due to pipe laying by PHED under Madhabpur PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00478/2024-2025 | BP-2024-25-279 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 3.2 | 0 | 0
1049 | Raiganj Division | Raiganj Sub-Division | Implementation of MADHABPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000202/2022-2023 | 71/RD/PHE | 16/01/2023 | 928 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 366.24 | 0 | 60
1050 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Madhabpur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000427/2024-2025 | 3739/RD/PHE | 18/12/2024 | 135 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 23.53 | 0 | 0
1051 | Raiganj Division | Raiganj Sub-Division | Trial Run For Madhabpur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000675/2024-2025 | 521/RD/PHE | 12/02/2025 | 90 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0
1052 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000072/2022-2023 | 2189/RD/PHE | 12/12/2022 | 0 | Resource Division | 33.71 | 0 | 0
1053 | Raiganj Division | Raiganj Sub-Division | Implementation of KHATSA and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000214/2022-2023 | 73/RD/PHE | 16/01/2023 | 725 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 464.26 | 0 | 53
1054 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Khatsa PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000426/2024-2025 | 3738/RD/PHE | 18/12/2024 | 90 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 9.83 | 0 | 0
1055 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KHATSA Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000475/2023-2024 | 583/RD/PHE | 05/03/2024 | 45 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 100
1056 | Raiganj Division | Raiganj Sub-Division | Trial Run For Khatsa PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000672/2024-2025 | 518/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0
1057 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000074/2022-2023 | 2191/RD/PHE | 12/12/2022 | 0 | Resource Division | 28.04 | 0 | 0
1058 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Jaingaon Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000145/2022-2023 | 1923/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.25 | 0 | 70
1059 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000106/2023-2024 | 2390/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0
1060 | Raiganj Division | Islampur Sub-Division | Protection and Restoration work of damaged flank caused by excavation for water supply project of PHE of Matikunda- Moragoti Road under uttar dinajpur division, PWD. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00505/2023-2024 | BP-2023-24-143 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 9.23 | 0 | 0
1061 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Durgapur Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000289/2025-2026 | 1815/RD/PHE | 24/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.35 | 0 | 0
1062 | Raiganj Division | Islampur Sub-Division | Implementation of DURGAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work,2nd & 3rd Tube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000301/2022-2023 | 550/RD/PHE | 23/02/2023 | 960 | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 341.08 | 0 | 38
1063 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Durgapur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000362/2024-2025 | 3481/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22 | 0 | 0
1064 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Durgapur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000363/2024-2025 | 3482/RD/PHE | 02/12/2024 | 30 | SHANKAR SAHA | 9.25 | 0 | 0
1065 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DURGAPUR Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000484/2023-2024 | 593/RD/PHE | 05/03/2024 | 45 | M/S LUCKY CONSTRUCTION | 22.58 | 0 | 0
1066 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Durgapur Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000508/2024-2025 | 53/RD/PHE | 03/01/2025 | 45 | APEX ENTERPRISES | 5.59 | 0 | 0
1067 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000114/2022-2023 | 601/RD/PHE | 27/02/2023 | 0 | Resource Division | 20.57 | 0 | 0
1068 | Raiganj Division | Islampur Sub-Division | Construction Of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Dhantola PWSS at Islampur Block under Raiganj Division, PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000166/2024-2025 | 2894/RD/PHE | 25/09/2024 | 20 | SHANKAR SAHA | 4.31 | 0 | 0
1069 | Raiganj Division | Islampur Sub-Division | Implementation of DHANTALA and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line,Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rdTube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000331/2022-2023 | 674/RD/PHE | 06/03/2023 | 757 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 840.35 | 0 | 6
1070 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of DHANTALA PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2024-2025 | 3491/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 55.01 | 0 | 0
1071 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under DHANTOLA Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000456/2023-2024 | 564/RD/PHE | 05/03/2024 | 180 | M/S CAMELLIA CONSTRUCTION AND CO. | 27.65 | 0 | 100
1072 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Dhantaola Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000507/2024-2025 | 52/RD/PHE | 03/01/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 8.23 | 0 | 0
1073 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000116/2022-2023 | 603/RD/PHE | 27/02/2023 | 0 | Resource Division | 109 | 0 | 0
1074 | Raiganj Division | Islampur Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 16.08.2024 & 20.08.2024. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00384/2024-2025 | BP-2024-25-224 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.06 | 0 | 0
1075 | Raiganj Division | Islampur Sub-Division | Implementation of Pharabari and it's adjoining mouzas Pipe Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000289/2022-2023 | 536/RD/PHE | 22/02/2023 | 591 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 43.62 | 0 | 100
1076 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site Tube-Well Site under PHARABARI PWSS at Goalpokhar-I Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000489/2023-2024 | 605/RD/PHE | 05/03/2024 | 90 | HAQUE CONSTRUCTION | 5.13 | 0 | 100
1077 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000028/2023-2024 | 1204/RD/PHE | 28/04/2023 | 0 | Resource Division | 2.69 | 0 | 0
1078 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at BALRAMPUR PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000029/2025-2026 | 1207/RD/PHE | 25/04/2025 | 45 | M/S PIONEER ENTERPRISE | 40.01 | 0 | 0
1079 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Balrampur Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000322/2025-2026 | 1993/RD/PHE | 07/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.03 | 0 | 0
1080 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1081 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000167/2022-2023 | 968/RD/PHE | 29/03/2023 | 0 | Resource Division | 21.22 | 0 | 0
1082 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chandigram Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 50 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000269/2025-2026 | 1657/RD/PHE | 23/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.73 | 0 | 0
1083 | Raiganj Division | Raiganj Sub-Division | Implementation of CHANDIGRAM and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000317/2022-2023 | 568/RD/PHE | 23/02/2023 | 1276 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 381.9 | 0 | 40
1084 | Raiganj Division | Raiganj Sub-Division | Construction of Approach Road,Laying of Pipe Line,Fhtc And other Allied Works of Chandigram Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000392/2024-2025 | 3562/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 80.89 | 0 | 0
1085 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under CHANDIGRAM PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000499/2023-2024 | 622/RD/PHE | 05/03/2024 | 285 | MITALI CONSTRUCTION | 24.47 | 0 | 60
1086 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1087 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1088 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000061/2023-2024 | 2231/RD/PHE | 01/08/2023 | 0 | Resource Division | 40.65 | 0 | 0
1089 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 20.05.2024 to 22.05.2024 and 24.05.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00132/2024-2025 | BP-2024-25-95 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.07 | 0 | 0
1090 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 27.05.2024 to 31.05.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00133/2024-2025 | BP-2024-25-96 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
1091 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Basratpur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000313/2025-2026 | 2477/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0
1092 | Raiganj Division | Raiganj Sub-Division | Construction of Approach Road, Laying of Pipe Line, FHTC And Other allied Works of Basratpur PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000388/2024-2025 | 3558/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 78.8 | 0 | 0
1093 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BASRATPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000535/2023-2024 | 617/RD/PHE | 05/03/2024 | 451 | M/S UNIQUE 13 | 11.28 | 0 | 40
1094 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BASRATPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000536/2023-2024 | 618/RD/PHE | 05/03/2024 | 406 | M/S PINKI CONSTRUCTION | 11.28 | 0 | 40
1095 | Raiganj Division | Raiganj Sub-Division | Implementation of BASRATPUR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000574/2022-2023 | 566/RD/PHE | 23/02/2023 | 910 | M/S LOKENATH CONSTRUCTION | 352.8 | 0 | 20
1096 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1097 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000087/2023-2024 | 2251/RD/PHE | 03/08/2023 | 0 | Resource Division | 38.67 | 0 | 0
1098 | Raiganj Division | Raiganj Sub-Division | Implementation of DAKHSHIN GOALPARA andit's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000009/2023-2024 | 1271/RD/PHE | 08/05/2023 | 700 | PRASANTA DUTTA | 206.31 | 0 | 50
1099 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000291/2022-2023 | 540/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 80
1100 | Raiganj Division | Raiganj Sub-Division | Providing FHTC with laying distribution of pipe line at village Taherpur of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000404/2022-2023 | 759/RD/PHE | 16/03/2023 | 750 | M/S JHA CONSTRUCTION | 91.73 | 0 | 50
1101 | Raiganj Division | Raiganj Sub-Division | Laying of pipe line at Naopara of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000455/2022-2023 | 815/RD/PHE | 22/03/2023 | 45 | M/S P.S. ENTERPRISE | 50.51 | 0 | 100
1102 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall and Pump House at 2nd Tube-Well with providing Functional House hold Tap Connection of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000475/2022-2023 | 821/RD/PHE | 22/03/2023 | 60 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 39.84 | 0 | 0
1103 | Raiganj Division | Raiganj Sub-Division | pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dakshin Goalpara PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000485/2024-2025 | 18/RD/PHE | 02/01/2025 | 30 | M/S JHA CONSTRUCTION | 18.16 | 0 | 0
1104 | Raiganj Division | Raiganj Sub-Division | Laying distribution of pipe Line and Providing FHTC at Village Dakhin Goal Para of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000582/2022-2023 | 854/RD/PHE | 24/03/2023 | 760 | M/S AMIT KUMAR GUPTA | 85.53 | 0 | 80
1105 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000052/2023-2024 | 1570/RD/PHE | 31/05/2023 | 0 | Resource Division | 43.02 | 0 | 0
1106 | Raiganj Division | Raiganj Sub-Division | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w L026-FATEPUR to PURBA SANKARPUR (Package No. WB15301: Under DLP), under coverage of Atghara PWSS (SM/13796) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00474/2024-2025 | BP-2024-25-275 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.98 | 0 | 0
1107 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
1108 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Atghara Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 100 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000259/2025-2026 | 1620/RD/PHE | 19/06/2025 | 180 | AJIT PRAMANIK | 36.38 | 0 | 0
1109 | Raiganj Division | Raiganj Sub-Division | Implementation of ATGHARA and it's adjoining mouzas Pipe Water Supply Scheme at Kaliyaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000272/2022-2023 | 290/RD/PHE | 01/02/2023 | 1065 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 892 | 0 | 60
1110 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under ATGHARA Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000457/2023-2024 | 565/RD/PHE | 05/03/2024 | 165 | M/S P.S. ENTERPRISE | 27.93 | 0 | 25
1111 | Raiganj Division | Raiganj Sub-Division | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Atghara PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000458/2024-2025 | 3776/RD/PHE | 19/12/2024 | 45 | M/S P.S. ENTERPRISE | 12.46 | 0 | 0
1112 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 366 | DEBASISH GHOSH | 4.8 | 0 | 0
1113 | Raiganj Division | Raiganj Sub-Division | Trial Run For Atghara PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000682/2024-2025 | 528/RD/PHE | 12/02/2025 | 90 | AJIT PRAMANIK | 0.88 | 0 | 0
1114 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000061/2022-2023 | 2178/RD/PHE | 12/12/2022 | 0 | Resource Division | 55.82 | 0 | 0
1115 | Raiganj Division | Islampur Sub-Division | Land development at 3rd Pump House (Source Augmentation) site for Debiganj Piped Water Supply Scheme under Islampur Sub-Division under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000041/2024-2025 | 1701/RD/PHE | 10/06/2024 | 30 | HAQUE CONSTRUCTION | 1.5 | 0 | 100
1116 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Debiganj Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000189/2022-2023 | 57/RD/PHE | 16/01/2023 | 45 | SUBHASIS MAJUMDER SUBHASIS@REDIFFMAIL.COM | 17.69 | 0 | 98
1117 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 100
1118 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000096/2023-2024 | 2397/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
1119 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Basatpur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000287/2025-2026 | 1809/RD/PHE | 24/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0
1120 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1121 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Basatpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000406/2025-2026 | 2363/RD/PHE | 25/08/2025 | 45 | MILAN GHOSH | 67.94 | 0 | 0
1122 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1123 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000178/2022-2023 | 978/RD/PHE | 30/03/2023 | 0 | Resource Division | 48.44 | 0 | 0
1124 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at ATHIALA PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000014/2025-2026 | 1205/RD/PHE | 25/04/2025 | 45 | MD HAKIMUDDIN | 69.94 | 0 | 0
1125 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Athiala Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000316/2025-2026 | 1985/RD/PHE | 04/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 30.95 | 0 | 0
1126 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1127 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000174/2022-2023 | 963/RD/PHE | 29/03/2023 | 0 | Resource Division | 32.29 | 0 | 0
1128 | Raiganj Division | Islampur Sub-Division | Construction Of OHR at Bangaon Pipe Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000332/2024-2025 | 3288/RD/PHE | 20/11/2024 | 45 | VISCOUS ENGINEERS PVT. LTD. | 71.86 | 0 | 0
1129 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000089/2023-2024 | 2270/RD | 03/08/2023 | 0 | Resource Division | 23.83 | 0 | 0
1130 | Raiganj Division | Raiganj Sub-Division | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of L039-PURBADURLAVPUR TO UTTAR MAHESHPUR (Package No. WB15303 : Under DLP) caused due to pipe laying by PHED under Sonapur PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00472/2024-2025 | BP-2024-25-273 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 0.9 | 0 | 0
1131 | Raiganj Division | Raiganj Sub-Division | Implementation of SONAPUR and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000011/2023-2024 | 1273/RD/PHE | 08/05/2023 | 270 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 362.18 | 0 | 50
1132 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
1133 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sonapur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000307/2025-2026 | 2474/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0
1134 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road, Laying of Pipe Line,Fhtc and Other Allied Works Of Sonapur Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000394/2024-2025 | 3565/RD/PHE | 05/12/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 76.02 | 0 | 0
1135 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SONAPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000506/2023-2024 | 629/RD/PHE | 05/03/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 0
1136 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1137 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1138 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 100
1139 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000054/2023-2024 | 1569/RD/PHE | 31/05/2023 | 0 | Resource Division | 22.31 | 0 | 0
1140 | Raiganj Division | Raiganj Sub-Division | Implementation of BAHALA ZONE-I and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000015/2023-2024 | 1277/RD/PHE | 08/05/2023 | 969 | BHOLA PAUL | 310.32 | 0 | 30
1141 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
1142 | Raiganj Division | Raiganj Sub-Division | Balance distribution System Of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHALA ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000511/2023-2024 | 636/RD/PHE | 05/03/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.72 | 0 | 100
1143 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1144 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
1145 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000068/2023-2024 | 2240/RD/PHE | 02/08/2023 | 0 | Resource Division | 22.87 | 0 | 0
1146 | Raiganj Division | Islampur Sub-Division | Implementation of BAGELA andit's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000002/2023-2024 | 1068/RD/PHE | 11/04/2023 | 731 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 647.26 | 0 | 75
1147 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bagela Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 150 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000330/2025-2026 | 2483/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 51.99 | 0 | 0
1148 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipeline, Pathway and Land development with anciliary works for installation of FHTC Work for BAGELA Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000459/2024-2025 | 3777/RD/PHE | 19/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 59.67 | 0 | 0
1149 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under BAGELA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000539/2023-2024 | 601/RD/PHE | 05/03/2024 | 138 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 16.43 | 0 | 0
1150 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under BAGELA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000540/2023-2024 | 602/RD/PHE | 05/03/2024 | 138 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 16.43 | 0 | 0
1151 | Raiganj Division | Islampur Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1152 | Raiganj Division | Islampur Sub-Division | Preparation & Submission of DPR for Proposed Bagela Piped Water Supply Scheme under Karandighi Development Block (sl no-I). | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000807/2021-2022 | 603/RD/PHE | 15/03/2022 | 7 | M/S SOBHA & CO. | 8.6 | 0 | 0
1153 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000031/2023-2024 | 1219/RD/PHE | 02/05/2023 | 0 | Resource Division | 258.85 | 0 | 0
1154 | Raiganj Division | Raiganj Sub-Division | Arrangement for erection of display board for different piped water supply schemes (1.Palaibari PWSS, 2.Bhomra PWSS, 3.Chandgaon PWSS) under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00421/2024-2025 | BP-2024-25-271 | 07/10/2024 | 0 | M/S MANDAL ENTERPRISE | 0.1 | 0 | 0
1155 | Raiganj Division | Raiganj Sub-Division | Implementation of PALAIBARI and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000003/2023-2024 | 1128/RD/PHE | 24/04/2023 | 977 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 555.91 | 0 | 50
1156 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Palaibari, 2.Kashimpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000032/2023-2024 | 1491/RD/PHE | 17/05/2023 | 675 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 57.19 | 0 | 80
1157 | Raiganj Division | Raiganj Sub-Division | Balance work of sinking Rig bored Tube-Well in connection with 2nd and 3rd Tube-Well site due to non-availability of water at the shallow depth of Tube-Well under Palaibari PWSS(New Scheme) at Itahar Block, Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000135/2024-2025 | 3025/RD/PHE | 03/10/2024 | 30 | M/S SARKAR ENTERPRISE SILIGURI | 18.33 | 0 | 0
1158 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000048/2023-2024 | 1331/RD/PHE | 15/05/2023 | 0 | Resource Division | 44.22 | 0 | 0
1159 | Raiganj Division | Malda Mechanical Division | Implementation of DAKSHINAL and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-06 | ORD/000226/2023-2024 | 2385/RD/PHE | 16/08/2023 | 840 | MILAN DEBNATH | 215.59 | 0 | 25
1160 | Raiganj Division | Malda Mechanical Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshinal Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | Assistant Engineer - I | Junior Engineer-06 | ORD/000319/2025-2026 | 2479/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 17.34 | 0 | 0
1161 | Raiganj Division | Malda Mechanical Division | Construction of Approach Road,Laying of Pipe Line,Fhtc and Other Allied Works Of Dakshinal Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I | Junior Engineer-06 | ORD/000395/2024-2025 | 3564/RD/PHE | 05/12/2024 | 252 | M/S. DEBNATH ENTERPRISE | 41.36 | 0 | 0
1162 | Raiganj Division | Malda Mechanical Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHINAL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-06 | ORD/000537/2023-2024 | 624/RD/PHE | 05/03/2024 | 415 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 11.29 | 0 | 100
1163 | Raiganj Division | Malda Mechanical Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHINAL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-06 | ORD/000538/2023-2024 | 625/RD/PHE | 05/03/2024 | 412 | DULAL MAJUMDER | 11.29 | 0 | 100
1164 | Raiganj Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-06 | RTOR000083/2023-2024 | 2266/RD/PHE | 03/08/2023 | 0 | Resource Division | 15.02 | 0 | 0
1165 | Raiganj Division | Islampur Sub-Division | Implementation of DOHASO and its adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000165/2023-2024 | 2091/RD/PHE | 27/07/2023 | 889 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 1441.52 | 0 | 60
1166 | Raiganj Division | Islampur Sub-Division | ADDITIONAL LAYING OF UPVC PIPE LINE with anciliary works at DOHASO PWSS WITHIN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION P.H.E. DTE., RAIGANJ, UTTAR DINAJPUR. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000361/2024-2025 | 3480/RD/PHE | 02/12/2024 | 45 | AJIT PRAMANIK | 81.53 | 0 | 0
1167 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DOHASO PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000541/2023-2024 | 609/RD/PHE | 05/03/2024 | 225 | DIPAK SAHA | 13.85 | 0 | 100
1168 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DOHASO PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000542/2023-2024 | 610/RD/PHE | 05/03/2024 | 225 | M/S ANTARA | 13.85 | 0 | 100
1169 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000108/2022-2023 | 605/RD/PHE | 27/02/2023 | 0 | Resource Division | 93.61 | 0 | 0
1170 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Ikarchala Zone-I & II Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000027/2025-2026 | 1180/RD/PHE | 23/04/2025 | 45 | HAQUE CONSTRUCTION | 38.77 | 0 | 0
1171 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at IKARCHALA ZONE-II PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000256/2025-2026 | 2046/RD/PHE | 10/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 32.95 | 0 | 0
1172 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ikarchala Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000324/2025-2026 | 1995/RD/PHE | 07/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0
1173 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at IKARCHALA ZONE-I PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000390/2025-2026 | 2044/RD/PHE | 09/07/2025 | 180 | GANGARAMPUR UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.29 | 0 | 0
1174 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1175 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000025/2023-2024 | 1202/RD/PHE | 28/04/2023 | 0 | Resource Division | 58.45 | 0 | 0
1176 | Raiganj Division | Raiganj Sub-Division | Implementation of SURANGAPUR (ZONE-II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000017/2023-2024 | 1279/RD/PHE | 08/05/2023 | 969 | SANYAL ENTERPRISE | 281.07 | 0 | 65
1177 | Raiganj Division | Raiganj Sub-Division | Restoration of Damaged CC Road Near 2nd Tubewell Site of Surangapur Zone-II Water Supply Scheme (New Scheme) at Hemtabad Block Under Raiganj Division P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000125/2024-2025 | 3016/RD/PHE | 03/10/2024 | 20 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 3.24 | 0 | 0
1178 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Surangapur Zone II PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000470/2024-2025 | 03/RD/PHE | 02/01/2025 | 45 | SANYAL ENTERPRISE | 42.37 | 0 | 0
1179 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000552/2023-2024 | 649/RD/PHE | 05/03/2024 | 45 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 11.29 | 0 | 100
1180 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000553/2023-2024 | 650/RD/PHE | 05/03/2024 | 45 | CHAITANYA SAMAL | 11.29 | 0 | 100
1181 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
1182 | Raiganj Division | Raiganj Sub-Division | Trial Run For Surangapur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000683/2024-2025 | 531/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0
1183 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000066/2023-2024 | 2238/RD/PHE | 02/08/2023 | 0 | Resource Division | 24.57 | 0 | 0
1184 | Raiganj Division | Raiganj Sub-Division | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-11 under Katihar Division of Northeast Frontier Railway in connection with Jhitkai PWSS in Raiganj Block under Raiganj Division PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00100/2024-2025 | BP-2024-25-69 | 06/06/2024 | 0 | EXECUTIVE ENGINEER | 0.11 | 0 | 0
1185 | Raiganj Division | Raiganj Sub-Division | Way leave/track crossing proposal with application id: NFR-KIR-2024-WL-11 under Kathihar Division of North East Fronter Railway in connection with Jhitkia PWSS in Raiganj Block under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00158/2024-2025 | BP-2024-25-104 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.13 | 0 | 0
1186 | Raiganj Division | Raiganj Sub-Division | Implementation of JHITKAI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000211/2023-2024 | 2294/RD/PHE | 04/08/2023 | 990 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 751.51 | 0 | 50
1187 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Jhitkia, 2.Bhomra in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000225/2023-2024 | 2366/RD/PHE | 11/08/2023 | 540 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 100
1188 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Jhitkai PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000430/2024-2025 | 3742/RD/PHE | 18/12/2024 | 135 | BHOLA PAUL | 29.79 | 0 | 0
1189 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000153/2022-2023 | 1052/RD/PHE | 06/04/2023 | 0 | Resource Division | 74.65 | 0 | 0
1190 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhatol PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. (2nd Call) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000248/2025-2026 | 2035/RD/PHE | 09/07/2025 | 180 | KAMIRUL SK & CO. | 46.67 | 0 | 0
1191 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bhatol Water Supply Scheme(Augmentation) at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000281/2025-2026 | 1800/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0
1192 | Raiganj Division | Raiganj Sub-Division | Augmentation of Bhatol and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000304/2022-2023 | 553/RD/PHE | 23/02/2023 | 1131 | KAMIRUL SK & CO. | 502.82 | 0 | 5
1193 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000137/2022-2023 | 721/RD/PHE | 15/03/2023 | 0 | Resource Division | 53.77 | 0 | 0
1194 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at 3rd Tube Well site (5.40mx3.60m) of Ramganj Zone-I Piped Water Supply Scheme in connection with Augmentation of Ramganj Zone -I PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000042/2023-2024 | 1541/RD/PHE | 24/05/2023 | 547 | M/S ANTARA | 5.32 | 0 | 0
1195 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work site (5.40mx3.60m) of Ramganj Zone-I Piped Water Supply Scheme in connection with Augmentation of Ramganj Zone-I PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000043/2023-2024 | 1542/RD/PHE | 24/05/2023 | 60 | M/S ANTARA | 5.32 | 0 | 100
1196 | Raiganj Division | Islampur Sub-Division | Repairing for 2nd Pump House & Construction of Toilet at Ramganj Zone-I in connection with Augmentation of Ramganj (Zone-I) PWSS under Islampur Sub-Division under Raiganj Division, PHE Dte.. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000108/2023-2024 | 2053/RD/PHE | 19/07/2023 | 45 | MAA SHEETALA ENTERPRISE | 3.12 | 0 | 0
1197 | Raiganj Division | Islampur Sub-Division | Augmentation of RAMGANJ(Zone-I)Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000174/2022-2023 | 2119/RD/PHE | 02/12/2022 | 850 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 324.17 | 0 | 30
1198 | Raiganj Division | Islampur Sub-Division | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site in connection with Augmentation Of Ramganj Zone-I PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000336/2024-2025 | 3292/RD/PHE | 20/11/2024 | 45 | MAA SHEETALA ENTERPRISE | 27.18 | 0 | 0
1199 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ramganj Zone-I Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 135 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000357/2025-2026 | 2503/RD/PHE | 12/09/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 47.78 | 0 | 0
1200 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-700 Cum) of RAMGANJ(Zone-I) Pipe Water Supply Scheme in connection with Augmentation at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000377/2022-2023 | 732/RD/PHE | 15/03/2023 | 365 | SOVAN KUMAR ROY | 231.74 | 0 | 0
1201 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Ramganj Zone-I Water Supply Scheme [Augmentation Scheme] in Islampur Block Of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000403/2022-2023 | 758/RD/PHE | 17/03/2023 | 180 | PRASANTA DUTTA | 123.24 | 0 | 0
1202 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
1203 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1204 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000089/2022-2023 | 2263/RD/PHE | 23/12/2022 | 0 | Resource Division | 116.35 | 0 | 0
1205 | Raiganj Division | Raiganj Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-VI) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000018/2021-2022 | 1223/RD/PHE | 18/06/2021 | 30 | DONE ENTERPRISE | 8.83 | 0 | 0
1206 | Raiganj Division | Raiganj Sub-Division | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-IV) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000021/2021-2022 | 1260/RD/PHE | 25/06/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 6.23 | 5.56 | 10
1207 | Raiganj Division | Raiganj Sub-Division | FHTC OF PHULATTI WSS | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000035/2020-2021 | 1394/RD | 09/12/2020 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 7.56 | 0 | 100
1208 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Phulatti and Sahapur Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000210/2020-2021 | 1393/RD/PHE | 09/12/2020 | 30 | M/S P.S ENTERPRISE | 12.96 | 0 | 60
1209 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Phulatti and Kasidanga Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000211/2020-2021 | 1390/RD/PHE | 09/12/2020 | 30 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 15.15 | 0 | 0
1210 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Phulatti and Banigaon, Phulatti and Lahanda Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000234/2020-2021 | 1392/RD/PHE | 09/12/2020 | 35 | PRASANTA DUTTA | 22.35 | 0 | 1
1211 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000020/2022-2023 | 1813/RD/PHE | 23/09/2022 | 0 | Resource Division | 0.97 | 0 | 0
1212 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000376/2021-2022 | 2071/RD/PHE | 02/11/2021 | 30 | S.B.CONSTRUCTION | 6.49 | 0 | 100
1213 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000729/2021-2022 | 425/RD/PHE | 16/02/2022 | 30 | S.B.CONSTRUCTION | 6.43 | 0 | 100
1214 | Raiganj Division | Raiganj Sub-Division | Route Survey & Preparation of DPR of KASBA NM PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000756/2021-2022 | 154/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0
1215 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000006/2021-2022 | 30/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.54 | 0 | 0
1216 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000014/2022-2023 | 1801/RD/PHE | 23/09/2022 | 0 | Resource Division | 1.66 | 0 | 0
1217 | Raiganj Division | Raiganj Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dhulahar Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000291/2021-2022 | 1827/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.97 | 0 | 0
1218 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000385/2021-2022 | 2080/RD/PHE | 02/11/2021 | 30 | RAHUL ENTERPRISE | 6.95 | 0 | 100
1219 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000736/2021-2022 | 432/RD/PHE | 16/02/2022 | 30 | RAHUL ENTERPRISE | 6.65 | 0 | 0
1220 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000001/2021-2022 | 25/RD/PHE | 06/01/2022 | 0 | Resource Division | 4.69 | 0 | 0
1221 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Mahadevpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000365/2021-2022 | 2146/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 1
1222 | Raiganj Division | Islampur Sub-Division | Additional Pipe Line for Retrofitting of Mahadevpur for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000436/2021-2022 | 2198/RD/PHE | 17/11/2021 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.56 | 0 | 0
1223 | Raiganj Division | Islampur Sub-Division | stationary bill | Assistant Engineer ISD | Junior Engineer, ISD | VCH/000309/2022-2023 | BP-2022-23-18 | 28/04/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0
1224 | Raiganj Division | Islampur Sub-Division | stationary bill | Assistant Engineer ISD | Junior Engineer, ISD | VCH/000311/2022-2023 | BP-2022-23-16 | 28/04/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.09 | 0 | 0
1225 | Raiganj Division | Islampur Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer ISD | Junior Engineer, ISD | BILL/01221/2023-2024 | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 2.84 | 0 | 0
1226 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Khanta (Rasakhowa) PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000387/2023-2024 | 2607/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.88 | 0 | 100
1227 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) Under Khanta[Rasakhowa] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000394/2021-2022 | 2089/RD/PHE | 02/11/2021 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 9.46 | 0 | 1
1228 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Khanta [Rasakhowa] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000738/2021-2022 | 434/RD/PHE | 16/02/2022 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 7.34 | 0 | 0
1229 | Raiganj Division | Islampur Sub-Division | Route Survey & Preparation of DPR of KHANTA PWSS under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000755/2021-2022 | 153/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.02 | 0 | 0
1230 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000027/2022-2023 | 1819/RD/PHE | 28/09/2022 | 0 | Resource Division | 2.25 | 0 | 0
1231 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of PIROJPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000410/2021-2022 | 2113/RD/PHE | 03/11/2021 | 30 | M/S HINDUSTHAN CONSTRUCTION | 11.23 | 0 | 1
1232 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of UDAYPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000411/2021-2022 | 2114/RD/PHE | 03/11/2021 | 30 | M/S SARKAR ENTERPRISE | 15.21 | 0 | 1
1233 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of PIPLAN Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000414/2021-2022 | 2117/RD/PHE | 03/11/2021 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 7.83 | 0 | 1
1234 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of SURUN Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000418/2021-2022 | 2121/RD/PHE | 03/11/2021 | 30 | DIPANKAR SARKAR | 9.99 | 0 | 1
1235 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Pokheria Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000367/2021-2022 | 2148/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 3.81 | 0 | 1
1236 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Biprit Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000368/2021-2022 | 2149/RD/PHE | 12/11/2021 | 30 | HERO CONSTRUCTION | 1.37 | 0 | 1
1237 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Majlishpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000373/2021-2022 | 2154/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 2.17 | 0 | 0
1238 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Intia Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000364/2021-2022 | 2145/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 4.75 | 0 | 1
1239 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Intia Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000433/2021-2022 | 2195/RD/PHE | 17/11/2021 | 30 | M/S P.S. ENTERPRISE | 15.49 | 0 | 0
1240 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC For Chhotoparua Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur. (Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000029/2022-2023 | 1041/RD/PHED | 12/05/2022 | 30 | RAHUL ENTERPRISE | 8.27 | 0 | 1
1241 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Providing Functional Household Tap Connection for Mahammadpur(Surun) Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000285/2022-2023 | 499/RD/PHE | 17/02/2023 | 45 | M/S DUTTA ENTERPRISE (JAYANTAJKD.USE@GMAIL.COM) | 9.08 | 0 | 0
1242 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC for Paharajpur Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur.(Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000024/2022-2023 | 1036/RD/PHED | 12/05/2022 | 30 | RAHUL ENTERPRISE | 6.02 | 0 | 1
1243 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC for Sherpur Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000023/2022-2023 | 1035/RD/PHED | 12/05/2022 | 30 | SARNALI ENTERPRISE | 5.8 | 0 | 1
1244 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Biprit and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000180/2020-2021 | 1244/RD/PHE | 16/10/2020 | 40 | PRASANTO DUTTA | 90.07 | 0 | 0
1245 | Raiganj Division | Islampur Sub-Division | FHTC OF BIPRIT PWSS | Assistant Engineer ISD |  | ORD/000368/2020-2021 | 1497/RD | 23/12/2020 | 25 | HERO CONSTRUCTION | 3.52 | 0 | 0
1246 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD |  | VCH/002099/2021-2022 | 768/W | 11/03/2022 | 0 | DIGITEK SOLUTIONS | 0.1 | 0 | 0
1247 | Raiganj Division | Islampur Sub-Division | Augmentation of PANJIPARA(Zone-II)Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000117/2022-2023 | 1669/RD/PHE | 05/09/2022 | 90 | UTTAM SAHA | 207.19 | 0 | 80
1248 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Panjipara Zone-II Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000165/2022-2023 | 2025/RD/PHE | 17/11/2022 | 90 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 78.25 | 0 | 0
1249 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000229/2022-2023 | 362/RD/PHE | 07/02/2023 | 45 | PULAK TALUKDAR PULAK.RNJ@GMAIL.COM | 5 | 0 | 100
1250 | Raiganj Division | Islampur Sub-Division | Repairing of Pump House at 2nd Tube well site in connection with Augmentation of Panjipara Zone-II piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000230/2022-2023 | 363/RD/PHE | 07/02/2023 | 45 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 2.5 | 0 | 100
1251 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panjipara Zone-II Water Supply Scheme(Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000305/2025-2026 | 1969/RD/PHE | 02/07/2025 | 180 | AJIT PRAMANIK | 32.35 | 0 | 0
1252 | Raiganj Division | Islampur Sub-Division | Construction Of Boundary Wall With Gate at 2nd Tube-Well Site in connection with Augmentation Of Panjipara Zone-II PWSS at Goalpukhur-I Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000341/2024-2025 | 3311/RD/PHE | 20/11/2024 | 315 | MR CONSTRUCTION | 8.86 | 0 | 100
1253 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-400 Cum) of PANJIPARA (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at Goalpokher-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000378/2022-2023 | 733/RD/PHE | 15/03/2023 | 626 | M/S ELITE CONSTRUCTION | 143.09 | 0 | 100
1254 | Raiganj Division | Islampur Sub-Division | Laying distribution of additional pipeline(left out) with construction of Boundary Wall at Panjipara Zone-II in connection with augmentation of Panjipara Zone-II PWSS at Goalpukhor-I Block under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000409/2023-2024 | 2749/RD/PHE | 05/10/2023 | 629 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 25.81 | 0 | 40
1255 | Raiganj Division | Islampur Sub-Division | Construction Of Approach Road in connection with Augmentation Of Panjipara Zone-II PWSS at Goalpokhur- I Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000456/2024-2025 | 3774/RD/PHE | 19/12/2024 | 90 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 7.35 | 0 | 0
1256 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1257 | Raiganj Division | Islampur Sub-Division | Trial Run For Panjipara Zone-II PWSS under Goalpukhur-I Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000723/2024-2025 | 555/RD/PHE | 12/02/2025 | 90 | APEX ENTERPRISES | 0.88 | 0 | 0
1258 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000046/2022-2023 | 1973/RD/PHE | 08/11/2022 | 0 | Resource Division | 67.7 | 0 | 0
1259 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Bindol Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000134/2022-2023 | 1912/RD/PHE | 28/10/2022 | 855 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 29.34 | 0 | 50
1260 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000121/2023-2024 | 14/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1261 | Raiganj Division | Raiganj Sub-Division | Source(Rig Bored Tube-Well) Augmentation of Kotar Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000124/2022-2023 | 1908/RD/PHE | 28/10/2022 | 495 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 32.51 | 0 | 30
1262 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000117/2023-2024 | 11/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1263 | Raiganj Division | Raiganj Sub-Division | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w L042 BHABAK to CHAPOIR (Package No. WB15302: Under DLP), under coverage of Chapoir PWSS (SM/12095) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00477/2024-2025 | BP-2024-25-278 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.68 | 0 | 0
1264 | Raiganj Division | Raiganj Sub-Division | Additional pipe line laying for Chapoir Piped Water Supply Scheme at Kaliyaganj Block of Uttar Diunajpur District Under Raiganj Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000141/2024-2025 | 2837/RD/PHE | 23/09/2024 | 30 | M/S P.S. ENTERPRISE | 20.64 | 0 | 0
1265 | Raiganj Division | Raiganj Sub-Division | Implementation of CHAPOIR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000228/2022-2023 | 291/RD/PHE | 01/02/2023 | 1055 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 570.71 | 0 | 56
1266 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chapoir Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000260/2025-2026 | 1621/RD/PHE | 19/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.58 | 0 | 0
1267 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapor PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000460/2024-2025 | 3778/RD/PHE | 19/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 57.12 | 0 | 0
1268 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAPAIR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000474/2023-2024 | 582/RD/PHE | 05/03/2024 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.87 | 0 | 50
1269 | Raiganj Division | Raiganj Sub-Division | Trial Run For Chapoir PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000701/2024-2025 | 542/RD/PHE | 12/02/2025 | 90 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0
1270 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000062/2022-2023 | 2179/RD/PHE | 12/12/2022 | 0 | Resource Division | 32.43 | 0 | 0
1271 | Raiganj Division | Raiganj Sub-Division | Implementation of LAXMIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000250/2022-2023 | 296/RD/PHE | 01/02/2023 | 1065 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 580.95 | 0 | 65
1272 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000428/2024-2025 | 3740/RD/PHE | 18/12/2024 | 225 | M/S MAA TARA CONSTRUCTION | 35.64 | 0 | 0
1273 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap bconnection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000473/2024-2025 | 06/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 56.25 | 0 | 0
1274 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAXMIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000476/2023-2024 | 584/RD/PHE | 05/03/2024 | 45 | M/S P.S. ENTERPRISE | 22.91 | 0 | 40
1275 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1276 | Raiganj Division | Raiganj Sub-Division | Trial Run For Laxmipur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000679/2024-2025 | 525/RD/PHE | 12/02/2025 | 90 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0
1277 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000067/2022-2023 | 2184/RD/PHE | 12/12/2022 | 0 | Resource Division | 30.98 | 0 | 0
1278 | Raiganj Division | Raiganj Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Itahar & Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000023/2023-2024 | 1285/RD/PHE | 08/05/2023 | 970 | UJJWAL DAS | 503.04 | 0 | 20
1279 | Raiganj Division | Raiganj Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Balahar village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000151/2024-2025 | 2883/RD/PHE | 25/09/2024 | 60 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 43.71 | 0 | 0
1280 | Raiganj Division | Raiganj Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Chakbhabanipur village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000152/2024-2025 | 2884/RD/PHE | 25/09/2024 | 60 | M/S. B. PAUL & COMPANY | 40.94 | 0 | 0
1281 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PASCHIM CHUTIYAKHOR PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000015/2025-2026 | 1209/RD/PHE | 25/04/2025 | 45 | RHYNO INFRASTRUCTURE | 59.96 | 0 | 0
1282 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Paschim Chutikhore Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000273/2025-2026 | 2162/RD/PHE | 23/07/2025 | 90 | M/S MAA BOLLA CONSTRUCTION | 8.62 | 0 | 0
1283 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1284 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Chutiakhore Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000412/2025-2026 | 2511/RD/PHE | 12/09/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 30.95 | 0 | 0
1285 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000173/2022-2023 | 967/RD/PHE | 29/03/2023 | 0 | Resource Division | 38.72 | 0 | 0
1286 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Uttar Jibakata Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000359/2025-2026 | 2505/RD/PHE | 12/09/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.03 | 0 | 0
1287 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1288 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000003/2023-2024 | 1037/RD/PHE | 04/04/2023 | 0 | Resource Division | 48.17 | 0 | 0
1289 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Deona Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000148/2022-2023 | 1926/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 32.87 | 0 | 15
1290 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000107/2023-2024 | 2393/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0
1291 | Raiganj Division | Raiganj Sub-Division | Additional Pipe Line For Providing FHTC CHERAMOTI Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District Under Raiganj Division P.H.E.Dte.(Phase-I) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000030/2024-2025 | 1690/RD/PHE | 10/06/2024 | 270 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 19.23 | 0 | 95
1292 | Raiganj Division | Raiganj Sub-Division | Implementation of CHERAMOTI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000116/2022-2023 | 1668/RD/PHE | 05/09/2022 | 1214 | SANYAL ENTERPRISE | 158.77 | 0 | 99
1293 | Raiganj Division | Raiganj Sub-Division | Additional Pipe Line for Providing FHTC Cheramoti Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District under Raiganj Division, P.H.E. Dte. (Phase-II) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000123/2024-2025 | 3013/RD/PHE | 03/10/2024 | 180 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 19.22 | 0 | 30
1294 | Raiganj Division | Raiganj Sub-Division | Construction of OHR & other allied works of CHERAMOTI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000316/2022-2023 | 588/RD/PHE | 24/02/2023 | 1042 | UTTAM SAHA | 128.61 | 0 | 70
1295 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
1296 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHERAMOTI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000459/2023-2024 | 567/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 95
1297 | Raiganj Division | Raiganj Sub-Division | Trial Run For Cheramoti PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000696/2024-2025 | 537/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0
1298 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000041/2022-2023 | 1954/RD/PHE | 04/11/2022 | 0 | Resource Division | 16.22 | 0 | 0
1299 | Raiganj Division | Raiganj Sub-Division | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w Shibpur - Madanpur Pacca Rasta- Kunarhat tala Pacca Rasta (Package No. WB15296: Under DLP), under coverage of Augmentation of Kunore PWSS (SM/11795) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00475/2024-2025 | BP-2024-25-276 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 3.2 | 0 | 0
1300 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site of Kunore in Connection with Augmentation of Kunore Piped Water Supply Scheme at Kaliyaganj Block under Raiganj Division P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000045/2023-2024 | 1544/RD/PHE | 24/05/2023 | 60 | A.S.B ENTERPRISE | 4.8 | 0 | 100
1301 | Raiganj Division | Raiganj Sub-Division | Augmentation of KUNORE Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000095/2022-2023 | 1542/RD/PHE | 26/08/2022 | 90 | UJJWAL DAS | 259.24 | 0 | 95
1302 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Kunore Water Supply Scheme [Augmentation Scheme] in Kaliaganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000163/2022-2023 | 2023/RD/PHE | 17/11/2022 | 90 | UJJWAL DAS | 73.38 | 0 | 70
1303 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-400 Cum) of KUNORE Pipe Water Supply Scheme in connection with Augmentation at KALIYAGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000369/2022-2023 | 726/RD/PHE | 15/03/2023 | 905 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. DEBASISHGHOSHDG76@GMAIL.COM | 143.15 | 0 | 45
1304 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000035/2022-2023 | 1948/RD/PHE | 04/11/2022 | 0 | Resource Division | 36.52 | 0 | 0
1305 | Raiganj Division | Raiganj Sub-Division | Vehicle hiring for inspection and monitoring of Augmentation work of Sariabad PWSS under Raiganj sub-division under Raiganj division, PHE Dte. for the period 13.12.2022 to 16.12.2022 | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00224/2023-2024 | BP-2023-24-77 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.04 | 0 | 0
1306 | Raiganj Division | Raiganj Sub-Division |  | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00361/2023-2024 | BP-2023-24-78 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.08 | 0 | 0
1307 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of CHANDDOL Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000423/2021-2022 | 2185/RD/PHE | 17/11/2021 | 30 | M/S BHOWMIK CONSTRUCTION | 7.02 | 0 | 0
1308 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sathuar Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000294/2025-2026 | 1877/RD/PHE | 26/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.58 | 0 | 0
1309 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1310 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000158/2022-2023 | 888/RD/PHE | 27/03/2023 | 0 | Resource Division | 23.7 | 0 | 0
1311 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1312 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000154/2022-2023 | 890/RD/PHE | 27/03/2023 | 0 | Resource Division | 16.66 | 0 | 0
1313 | Raiganj Division | Raiganj Sub-Division | Implementation of GORAHAR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000315/2022-2023 | 564/RD/PHE | 23/02/2023 | 1042 | SANYAL ENTERPRISE | 243.13 | 0 | 38
1314 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Gorahar PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000478/2024-2025 | 11/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 29.8 | 0 | 0
1315 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GORAHAR PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000493/2023-2024 | 613/RD/PHE | 05/03/2024 | 45 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 22.58 | 0 | 0
1316 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1317 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000060/2023-2024 | 2230/RD/PHE | 01/08/2023 | 0 | Resource Division | 24.45 | 0 | 0
1318 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at DANGRA DANGRI .PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000031/2025-2026 | 1210/RD/PHE | 25/04/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 61.96 | 0 | 0
1319 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1320 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000090/2023-2024 | 2268/RD | 03/08/2023 | 0 | Resource Division | 49.81 | 0 | 0
1321 | Raiganj Division | RWS Raiganj Sub-Divisin | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
1322 | Raiganj Division | RWS Raiganj Sub-Divisin | Implementation of MALKOT and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000125/2023-2024 | 2066/RD/PHE | 21/07/2023 | 817 | KAMIRUL SK & CO. | 449.37 | 0 | 30
1323 | Raiganj Division | RWS Raiganj Sub-Divisin | Additional pipeline and other ancillary works at Malkot piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000250/2025-2026 | 2040/RD/PHE | 09/07/2025 | 180 | M/S CHOUDHURY CONSTRUCTION | 43.33 | 0 | 0
1324 | Raiganj Division | RWS Raiganj Sub-Divisin | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Malkot Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000299/2025-2026 | 1929/RD/PHE | 30/06/2025 | 180 | AJIT PRAMANIK | 32.36 | 0 | 0
1325 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Malkot Piped Water Supply Scheme under Islampur Sub-Division PHED under Raiganj Division, PHE Dte.,U/D. (2nd Call) | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000381/2025-2026 | 2041/RD/PHE | 09/07/2025 | 180 | PRIYA CONSTRUCTION | 20.46 | 0 | 0
1326 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MALKOT PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000515/2023-2024 | 646/RD/PHE | 05/03/2024 | 335 | MAA DURGA CONSTRUCTION | 22.58 | 0 | 100
1327 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | RTOR000165/2022-2023 | 965/RD/PHE | 29/03/2023 | 0 | Resource Division | 35.14 | 0 | 0
1328 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jamira Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000284/2025-2026 | 1806/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 33.59 | 0 | 0
1329 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1330 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000183/2022-2023 | 983/RD/PHE | 30/03/2023 | 0 | Resource Division | 41.55 | 0 | 0
1331 | Raiganj Division | Islampur Sub-Division | Laying of Rising Main of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000102/2023-2024 | 2048/RD/PHE | 19/07/2023 | 563 | M/S SAHA CONSTRUCTION | 4.31 | 0 | 100
1332 | Raiganj Division | Islampur Sub-Division | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Hemenpur PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000162/2024-2025 | 2896/RD/PHE | 25/09/2024 | 30 | M/S SANJIB BHATTACHARJEE | 6.83 | 0 | 0
1333 | Raiganj Division | Islampur Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000295/2022-2023 | 541/RD/PHE | 22/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 60
1334 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of HEMENPUR PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000378/2024-2025 | 3497/RD/PHE | 02/12/2024 | 90 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 53.33 | 0 | 0
1335 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall & pump House at 2nd Tube-well Site of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000410/2022-2023 | 765/RD/PHE | 17/03/2023 | 60 | M/S BRIGHT CONSTRUCTION | 11.26 | 0 | 100
1336 | Raiganj Division | Islampur Sub-Division | Providing functional house hold tap connection at village-Dubel Babhania & Purba Goalgaon of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000415/2022-2023 | 770/RD/PHE | 17/03/2023 | 60 | UJJAL KUMAR SARKAR KUMARUJJAL51@GMAIL.COM | 11.13 | 0 | 0
1337 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall and pump House at Head work Site of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000483/2022-2023 | 822/RD/PHE | 22/03/2023 | 60 | SAMRAT BOSE | 24.86 | 0 | 95
1338 | Raiganj Division | Islampur Sub-Division | Construction of OHR(Capacity-250 cum) HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000507/2022-2023 | 850/RD/PHE | 24/03/2023 | 275 | BHOWMICK ENTERPRISE | 91.89 | 0 | 0
1339 | Raiganj Division | Islampur Sub-Division | Laying of pipeline main at village-Paschim Goalgaon and Chengatuli of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000516/2022-2023 | 870/RD/PHE | 27/03/2023 | 429 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 35.44 | 0 | 85
1340 | Raiganj Division | Islampur Sub-Division | Providing functional house hold tap connection at village-Paschim Goalgaon & Chengatuli of HEMENPUR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000525/2022-2023 | 875/RD/PHE | 27/03/2023 | 493 | SANDIP SARKAR | 11.81 | 0 | 0
1341 | Raiganj Division | Islampur Sub-Division | Laying of pipeline at village-Bhagabanpur of Hemenpur Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000533/2022-2023 | 945/RD/PHE | 29/03/2023 | 718 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 32.21 | 0 | 100
1342 | Raiganj Division | Islampur Sub-Division | Providing functional house hold tap connection at village- Bhagabanpur of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000538/2022-2023 | 950/RD/PHE | 29/03/2023 | 668 | M/S.SADHANA ENTERPRISE | 11.91 | 0 | 90
1343 | Raiganj Division | Islampur Sub-Division | Providing functional house hold tap connection of Village-Hemenpur of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000543/2022-2023 | 955/RD/PHE | 29/03/2023 | 609 | APEX ENTERPRISES RUPESH.RNJ@GMAIL.COM | 11.81 | 0 | 0
1344 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000032/2023-2024 | 1220/RD/PHE | 02/05/2023 | 0 | Resource Division | 36.73 | 0 | 0
1345 | Raiganj Division | Islampur Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 20.09.2024 and 23.09.2024. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/00386/2024-2025 | BP-2024-25-222 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.06 | 0 | 0
1346 | Raiganj Division | Islampur Sub-Division | Implementation of Chitalghata and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000047/2023-2024 | 1553/RD/PHE | 26/05/2023 | 1080 | UTTAM SAHA | 665.31 | 0 | 65
1347 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
1348 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000007/2023-2024 | 1053/RD/PHE | 06/04/2023 | 0 | Resource Division | 47.89 | 0 | 0
1349 | Raiganj Division | Raiganj Sub-Division | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of L032-GULANDAR TO MUKUNDAPUR Road (Package No. WB15311 : Under DLP) caused due to pipe laying by PHED under Para PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00473/2024-2025 | BP-2024-25-274 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.38 | 0 | 0
1350 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Para Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 50 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000268/2025-2026 | 1656/RD/PHE | 23/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.73 | 0 | 0
1351 | Raiganj Division | Raiganj Sub-Division | Implementation of PARA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000396/2022-2023 | 748/RD/PHE | 16/03/2023 | 1157 | SANYAL ENTERPRISE | 388.91 | 0 | 52
1352 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Para PWSS at Itahar Block under Raiganj Division, PHE Dte.,Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000421/2024-2025 | 3733/RD/PHE | 18/12/2024 | 225 | SANYAL ENTERPRISE | 23.02 | 0 | 0
1353 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PARA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000494/2023-2024 | 614/RD/PHE | 05/03/2024 | 165 | M/S MAA BAIRA KALI CONSTRUCTION | 24.47 | 0 | 100
1354 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1355 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000059/2023-2024 | 1694/RD/PHE | 22/06/2023 | 0 | Resource Division | 29.47 | 0 | 0
1356 | Raiganj Division | Raiganj Sub-Division | Implementation of KASHIMPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02 | ORD/000005/2023-2024 | 1132/RD/PHE | 24/04/2023 | 1080 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 407.34 | 0 | 55
1357 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Palaibari, 2.Kashimpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02 | ORD/000032/2023-2024 | 1491/RD/PHE | 17/05/2023 | 675 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 57.19 | 0 | 80
1358 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kashimpur Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02 | ORD/000306/2025-2026 | 2473/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0
1359 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-02 | RTOR000043/2023-2024 | 1333/RD/PHE | 15/05/2023 | 0 | Resource Division | 36.1 | 0 | 0
1360 | Raiganj Division | Raiganj Sub-Division | Implementation of LOHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000020/2023-2024 | 1282/RD/PHE | 08/05/2023 | 1091 | BHOLA PAUL | 135.29 | 0 | 50
1361 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Lohanda PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000484/2024-2025 | 17/RD/PHE | 02/01/2025 | 30 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 11.25 | 0 | 0
1362 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work & 2nd Tube-Well Site under LOHANDA PWSS at Raiganj Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000505/2023-2024 | 628/RD/PHE | 05/03/2024 | 361 | M/S MANDAL ENTERPRISE | 11.14 | 0 | 48
1363 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000086/2023-2024 | 2262/RD/PHE | 03/08/2023 | 0 | Resource Division | 10.97 | 0 | 0
1364 | Raiganj Division | Raiganj Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 100
1365 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000008/2023-2024 | 1105/RD/PHE | 20/04/2023 | 0 | Resource Division | 4.7 | 0 | 0
1366 | Raiganj Division | Raiganj Sub-Division | Implementation of MOHISHGAON and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000012/2023-2024 | 1274/RD/PHE | 08/05/2023 | 1080 | UTTAM SAHA | 373.39 | 0 | 50
1367 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Mohishgaon Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-45 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000302/2025-2026 | 2471/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 19.34 | 0 | 0
1368 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Mahishgaon PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000435/2024-2025 | 3748/RD/PHE | 18/12/2024 | 135 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 21.97 | 0 | 0
1369 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MOHISHGAON PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000507/2023-2024 | 632/RD/PHE | 05/03/2024 | 45 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 22.58 | 0 | 100
1370 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
1371 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000053/2023-2024 | 2249/RD/PHE | 03/08/2023 | 0 | Resource Division | 125.79 | 0 | 0
1372 | Raiganj Division | Islampur Sub-Division | Implementation of DIGHALGAON and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000077/2023-2024 | 2002/RD/PHE | 13/07/2023 | 786 | DIPESH BHOWMIK | 503.41 | 0 | 40
1373 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under DIGHALGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000546/2023-2024 | 638/RD/PHE | 05/03/2024 | 441 | BASU AND COMPANY | 13.85 | 0 | 60
1374 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Dighalgaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000560/2024-2025 | 327/RD/PHE | 17/01/2025 | 90 | DIPESH BHOWMIK | 52.29 | 0 | 0
1375 | Raiganj Division | Islampur Sub-Division | Laying of pipeline with FHTC of DIGHALGAON and it¿s adjoining mouzas Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000566/2023-2024 | 738/RD/PHE | 12/03/2024 | 430 | M/S SOMNATH KUNDU | 96.35 | 0 | 60
1376 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000132/2022-2023 | 639/RD/PHE | 02/03/2023 | 0 | Resource Division | 53.73 | 0 | 0
1377 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1378 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
1379 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000175/2022-2023 | 980/RD/PHE | 30/03/2023 | 0 | Resource Division | 46.38 | 0 | 0
1380 | Raiganj Division |  | Estimate for the work of PMGSY Road in connection with laying of pipeline along the road shoulder. |  |  | BILL/00189/2024-2025 | BP-2024-25-127 | 22/07/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 9.21 | 0 | 0
1381 | Raiganj Division |  | Construction of Approach Road at Head Work Site, & 3rd Tube-Well Site under New Scheme of Bazargaon PWSS at Karandighi Block under Raiganj Division, PHE dte. |  |  | ORD/000164/2024-2025 | 2898/RD/PHE | 25/09/2024 | 30 | SARNALI ENTERPRISE | 6.78 | 0 | 0
1382 | Raiganj Division |  | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bazargaon Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. |  |  | ORD/000329/2025-2026 | 2014/RD/PHE | 08/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 36.36 | 0 | 0
1383 | Raiganj Division |  | Implementation of BAJARGAON and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rd TubeWell) |  |  | ORD/000364/2023-2024 | 2480/RD/PHE | 24/08/2023 | 591 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 841.02 | 0 | 66
1384 | Raiganj Division |  | Laying of Additional pipeline with other ancillary works at different mouzas of BAZARGAON PWSS under Islampur Sub-Division P.H.E. Dte. |  |  | ORD/000377/2024-2025 | 3496/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 31.92 | 0 | 0
1385 | Raiganj Division |  | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under BAJARGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. |  |  | ORD/000556/2023-2024 | 657/RD/PHE | 05/03/2024 | 315 | M/S CHAKRABORTY ENTERPRISE | 13.85 | 0 | 100
1386 | Raiganj Division |  | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under BAJARGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. |  |  | ORD/000557/2023-2024 | 658/RD/PHE | 05/03/2024 | 315 | DISCOVERY CO. OPERATIVE LABOUR CONT AND CONST SOC. LTD. | 13.85 | 0 | 100
1387 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1317/RD/PHE | 12/05/2023 | 0 | Resource Division | 88.18 | 0 | 0
1388 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purba Gomaidighi Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000288/2025-2026 | 1810/RD/PHE | 24/06/2025 | 180 | PRADIP KUMAR PAUL | 19.12 | 0 | 0
1389 | Raiganj Division | Islampur Sub-Division | Implementation of PURBA GOMAIDIGHI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000344/2023-2024 | 2470/RD/PHE | 24/08/2023 | 861 | PRADIP KUMAR PAUL | 692.96 | 0 | 75
1390 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of PURBA GOMAIDIGHI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000374/2024-2025 | 3493/RD/PHE | 02/12/2024 | 405 | PRADIP KUMAR PAUL | 78.28 | 0 | 40
1391 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PURBA GUMAIDIGHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000525/2023-2024 | 546/RD/PHE | 05/03/2024 | 45 | M/S BABA LOKNATH CONSTRUCTION | 22.57 | 0 | 0
1392 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000122/2022-2023 | 619/RD/PHE | 28/02/2023 | 0 | Resource Division | 41.78 | 0 | 0
1393 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 10.06.2024 to 14.06.2024. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00128/2024-2025 | BP-2024-25-93 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.08 | 0 | 0
1394 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 13.05.2024 to 17.05.2024. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00129/2024-2025 | BP-2024-25-94 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
1395 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 03.09.2024 and 09.09.2024. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00383/2024-2025 | BP-2024-25-223 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.07 | 0 | 0
1396 | Raiganj Division | Raiganj Sub-Division | Beldangi Road from 7.00 km to 9.40 km under Dakshin Dinajpur Highway Division in the District of Dakshin Dinajpur, Urgent restoration of Hard Shoulder in stretches caused due to laying of pipeline by PHED under Chhayghara PWSS under Raiganj Divison, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00494/2024-2025 | BP-2024-25-281 | 05/11/2024 | 0 | EXECUTIVE ENGINEER (DAKSHIN DINAJPUR HIGHWAY DIVISION) | 11.19 | 0 | 0
1397 | Raiganj Division | Raiganj Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 100
1398 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chhayghora Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000315/2025-2026 | 2478/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 19.35 | 0 | 0
1399 | Raiganj Division | Raiganj Sub-Division | Implementation of CHHAYGHARA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000345/2023-2024 | 2471/RD/PHE | 24/08/2023 | 848 | M/S S.D. ENTERPRISE | 775.32 | 0 | 30
1400 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road,Laying Of Pipe Line,Fhtc And Other Allied Works Of Chayaghara Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000399/2024-2025 | 3568/RD/PHE | 05/12/2024 | 91 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 52.27 | 0 | 0
1401 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0
1402 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under CHHAYGHARA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000508/2023-2024 | 633/RD/PHE | 05/03/2024 | 360 | PRIMECON ENTERPRISE | 27.71 | 0 | 60
1403 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 100
1404 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000082/2023-2024 | 2259/RD/PHE | 03/08/2023 | 0 | Resource Division | 141.14 | 0 | 0
1405 | Raiganj Division | Raiganj Sub-Division | Implementation of KAPASIA and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000166/2023-2024 | 2092/RD/PHE | 27/07/2023 | 930 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 1262.96 | 0 | 30
1406 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kapasia Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 150 M3/hr. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000343/2025-2026 | 2491/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 52.01 | 0 | 0
1407 | Raiganj Division | Raiganj Sub-Division | Construction of Approach Road, Laying of Pipe Line, FHTC And Other Allied Works of Kapasia PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000389/2024-2025 | 3559/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 48.29 | 0 | 0
1408 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under KAPASIA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000498/2023-2024 | 621/RD/PHE | 05/03/2024 | 338 | KRISHNA CONSTRUCTION | 35.63 | 0 | 50
1409 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1410 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 100
1411 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000073/2023-2024 | 2244/RD/PHE | 02/08/2023 | 0 | Resource Division | 123.16 | 0 | 0
1412 | Raiganj Division | Islampur Sub-Division | Source(Rig Bored Tube-Well) Augmentation of Dakshin Kundal Pukur Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000125/2022-2023 | 1909/RD/PHE | 28/10/2022 | 45 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 32.3 | 0 | 0
1413 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000104/2023-2024 | 2396/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0
1414 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Surun Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000140/2022-2023 | 1918/RD/PHE | 28/10/2022 | 75 | M/S P.S. ENTERPRISE | 32.83 | 0 | 30
1415 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000124/2023-2024 | 12/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1416 | Raiganj Division | Raiganj Sub-Division | Source(Rig Bored Tube-Well) Augmentation of Baruna Piped Water Supply Scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000120/2022-2023 | 1907/RD/PHE | 28/10/2022 | 45 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 25.99 | 0 | 65
1417 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000116/2023-2024 | 21/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1418 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
1419 | Raiganj Division | Raiganj Sub-Division | Balance UPVC Pipe Line of Bheurjhari PWSS at Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000064/2024-2025 | 2227/RD/PHE | 23/07/2024 | 30 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 8.66 | 0 | 100
1420 | Raiganj Division | Raiganj Sub-Division | Implementation of BEURJHARI and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000198/2022-2023 | 67/RD/HE | 16/01/2023 | 715 | BHOLA PAUL | 223.52 | 0 | 80
1421 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000409/2024-2025 | 3045/RD/PHE | 04/10/2024 | 90 | ARNAB DUTTA | 1.2 | 0 | 0
1422 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Beurjhari PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000424/2024-2025 | 3736/RD/PHE | 18/12/2024 | 135 | BHOLA PAUL | 20.01 | 0 | 0
1423 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BEURJHARI Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000469/2023-2024 | 577/RD/PHE | 05/03/2024 | 75 | BHOLA PAUL | 22.93 | 0 | 90
1424 | Raiganj Division | Raiganj Sub-Division | Trial Run For Beurjhari PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000700/2024-2025 | 541/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.87 | 0 | 0
1425 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000095/2022-2023 | 31/RD/PHE | 06/01/2023 | 0 | Resource Division | 22.57 | 0 | 0
1426 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connection (FHTC) under Chhotaparua and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000206/2020-2021 | 1243/RD/PHE | 16/10/2020 | 40 | PRASANTA DUTTA | 77.11 | 0 | 0
1427 | Raiganj Division | Raiganj Sub-Division | Providing Functional House Hold Connection (FHTC) for the purpose of Chotaparua Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000282/2022-2023 | 496/RD/PHE | 17/02/2023 | 45 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 3.18 | 0 | 0
1428 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000807/2024-2025 | 296/RD/PHE | 15/01/2025 | 181 | DEBASISH GHOSH | 2.4 | 0 | 0
1429 | Raiganj Division | Raiganj Sub-Division | HIRE CHRAGE OF VEHICLE | Assistant Engineer RSD | Junior Engineer, RSD | VCH/001273/2022-2023 | 322/W | 14/09/2022 | 0 | JOYDEB GHOSH | 0.06 | 0 | 0
1430 | Raiganj Division | Raiganj Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer RSD | Junior Engineer, RSD | VCH/002105/2021-2022 | 766/W | 11/03/2022 | 0 | DIGITEK SOLUTIONS | 0.1 | 0 | 0
1431 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1432 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000182/2022-2023 | 982/RD/PHE | 30/03/2023 | 0 | Resource Division | 66.81 | 0 | 0
1433 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under FARIDPUR and ADJOINING Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000468/2020-2021 | 1413/ RD | 11/12/2020 | 40 | M/S MAA TARA CONSTRUCTION BIRNAGAR SUNILPRAMAICK1961@GMAIL.COM | 67.94 | 0 | 1
1434 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Shursa Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000163/2020-2021 | 1433/RD/PHE | 11/12/2020 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 19.38 | 0 | 0
1435 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Sergram Part Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000167/2020-2021 | 1432/RD/PHE | 11/12/2020 | 30 | M/S P.S ENTERPRISE | 17.7 | 0 | 0
1436 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Sergram Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000261/2020-2021 | 1434/RD/PHE | 11/12/2020 | 30 | AJIT PARMANIK | 18.68 | 0 | 0
1437 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000625/2023-2024 | 1722/RD/PHE | 28/06/2023 | 366 | DEBASISH GHOSH | 4.8 | 0 | 0
1438 | Raiganj Division | Raiganj Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer RSD | Junior Engineer, RSD | VCH/002102/2021-2022 | 765/W | 11/03/2022 | 0 | BEEKAY.COM | 0.1 | 0 | 0
1439 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Habipur Mouza under Amalbari and Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000272/2020-2021 | 1420/RD/PHE | 11/12/2020 | 30 | SANJIB BHATTACHARJEE | 10.54 | 0 | 1
1440 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Sahasra Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000273/2020-2021 | 1419/RD/PHE | 11/12/2020 | 30 | LOKENATH CO-OP LBOUR CONTRACT &CONSTRUCTION SOCIETY LTD. | 10.56 | 0 | 1
1441 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Laguar Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000274/2020-2021 | 1418/RD/PHE | 11/12/2020 | 30 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 10.53 | 0 | 1
1442 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Amalbari Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000275/2020-2021 | 1417/RD/PHE | 11/12/2020 | 30 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 10.56 | 0 | 100
1443 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) at Ranipur Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000276/2020-2021 | 467/RD/PHE | 26/02/2021 | 30 | M/S BHOWMIK ENTERPRISE | 10.53 | 0 | 0
1444 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Baldoria Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block Under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD |  | ORD/000292/2020-2021 | 1440/RD/PHE | 11/12/2020 | 30 | DIPANKAR SARKAR | 10.56 | 0 | 1
1445 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD |  | VCH/002089/2021-2022 | 772/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.06 | 0 | 0
1446 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Majhiali Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000130/2020-2021 | 1426/RD/PHE | 11/12/2020 | 30 | S.B.CONSTRUCTION | 16.48 | 0 | 1
1447 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Uttar Besarbari Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000262/2020-2021 | 1429/RD/PHE | 11/12/2020 | 30 | IDEAL CO-OP LABOUR CONTRACT &CONST SOCIETY LTD. | 16.94 | 0 | 1
1448 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Dakshin Kundal Pukur Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000263/2020-2021 | 1428/RD/PHE | 11/12/2020 | 30 | M/S BHOWMIK ENTERPRISE | 16.5 | 0 | 1
1449 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Ariagaon Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000264/2020-2021 | 1427/RD/PHE | 11/12/2020 | 30 | CHAITANYA SAMAL | 17.17 | 4.93 | 1
1450 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002092/2021-2022 | 753/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.1 | 0 | 0
1451 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002106/2021-2022 | 752/W | 11/03/2022 | 0 | JHUNU SAHA | 0.1 | 0 | 0
1452 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Lodhan and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000182/2020-2021 | 1240/RD/PHE | 16/10/2020 | 40 | J.D.J. ENTERPRISE | 65.65 | 0 | 0
1453 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002086/2021-2022 | 775/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.06 | 0 | 0
1454 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Bhatol and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000342/2021-2022 | 2070/RD/PHE | 02/11/2021 | 30 | JEET CONSTRUCTION | 8.09 | 0 | 1
1455 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Bhatol and adjoining mouzas water supply scheme in Raiganj Block Under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000728/2021-2022 | 424/RD/PHE | 16/02/2022 | 30 | JEET CONSTRUCTION | 7.8 | 0 | 0
1456 | Raiganj Division | Raiganj Sub-Division | Route Survey & Preparation of DPR of BHATOL PWSS under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000757/2021-2022 | 155/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.85 | 0 | 0
1457 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000007/2021-2022 | 31/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.89 | 0 | 0
1458 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000015/2022-2023 | 1800/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.12 | 0 | 0
1459 | Raiganj Division | Raiganj Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dilwarpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000289/2021-2022 | 1825/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.73 | 2.72 | 0
1460 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Dilwarpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000381/2021-2022 | 2076/RD/PHE | 02/11/2021 | 30 | M/S GHOSH CONSTRUCTION | 7.18 | 0 | 1
1461 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dilwarpur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000732/2021-2022 | 428/RD/PHE | 16/02/2022 | 30 | MAA SHEETALA ENTERPRISE | 7.07 | 0 | 0
1462 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000008/2022-2023 | 1793/RD/PHE | 22/09/2022 | 0 | Resource Division | 1.9 | 0 | 0
1463 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Kanki-Matiari Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - II Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000281/2021-2022 | 1817/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.6 | 2.49 | 0
1464 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kanki-Matiari Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000396/2021-2022 | 2091/RD/PHE | 02/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 5.8 | 0 | 50
1465 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kanki-Matiari Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000741/2021-2022 | 437/RD/PHE | 16/02/2022 | 30 | TAPAN KUMAR MAJUMDER | 2.99 | 0 | 0
1466 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000013/2021-2022 | 37/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.35 | 0 | 0
1467 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000028/2022-2023 | 1826/RD/PHE | 28/09/2022 | 0 | Resource Division | 1.17 | 0 | 0
1468 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Raghabpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000286/2021-2022 | 1822/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.04 | 0 | 0
1469 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Raghabpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000397/2021-2022 | 2092/RD/PHE | 02/11/2021 | 30 | M/S DOLPHIN CONSTRUCTION | 7.63 | 0 | 1
1470 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Raghabpur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000737/2021-2022 | 433/RD/PHE | 16/02/2022 | 30 | M/S DOLPHIN CONSTRUCTION | 7.34 | 0 | 0
1471 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000008/2021-2022 | 32/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.78 | 0 | 0
1472 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000026/2022-2023 | 1818/RD/PHE | 28/09/2022 | 0 | Resource Division | 2 | 0 | 0
1473 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Purba Durlavpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000357/2021-2022 | 2138/RD/PHE | 12/11/2021 | 30 | UTTAM SAHA | 4.85 | 0 | 1
1474 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of PURBA DURLAVPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000422/2021-2022 | 2184/RD/PHE | 17/11/2021 | 30 | TAPAN KUMAR DUTTA | 5.91 | 0 | 0
1475 | Raiganj Division | Raiganj Sub-Division | Laying of additional Pipeline for providing functional household tap connections for Kaliganj(Poaltair) Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000565/2022-2023 | 1029/RD/PHE | 31/03/2023 | 45 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 7.53 | 0 | 100
1476 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe line for Retrofitting FHTC of Deona piped water Supply Scheme under Raiganj Division P.H.E. Dte. (Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000044/2022-2023 | 1008/RD/PHED | 11/05/2022 | 20 | NIMAI DAS | 2.01 | 0 | 1
1477 | Raiganj Division | Raiganj Sub-Division | Hiring of vehicle for Inspection and monitoring of Augmentation work of Sasan PWSS under JJM for the period 16.11.2022 to 23.11.2022. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00216/2023-2024 |  | 15/06/2023 | 0 | DEBASISH GHOSH | 0.1 | 0 | 0
1478 | Raiganj Division | Raiganj Sub-Division | Hiring of vehicle for Inspection and monitoring of Augmentation work of Sasan PWSS under JJM for the period 16.11.2022 to 23.11.2022. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00362/2023-2024 | BP-2023-24-75 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.1 | 0 | 0
1479 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Sasan Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000004/2022-2023 | 1016/RD/PHED | 12/05/2022 | 45 | M/S HINDUSTHAN CONSTRUCTION | 43.64 | 0 | 20
1480 | Raiganj Division | Raiganj Sub-Division | Construction of 2Nos. Tube-Well (250mm diameter x 150mmx150mtr) for Augmentation of SASAN Water Supply Scheme in HEMTABAD Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000047/2022-2023 | 1201/RD/PHE | 06/06/2022 | 30 | M/S SARKAR ENTERPRISE | 18.2 | 0 | 1
1481 | Raiganj Division | Raiganj Sub-Division | Soil Investigation for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Over Pile Foundation For Augmentation of Sasan Water W/S Scheme in Hemtabad Block in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000052/2022-2023 | 1239/RD/PHE | 20/06/2022 | 20 | K.S. GROUP | 1.99 | 0 | 0
1482 | Raiganj Division | Raiganj Sub-Division | Ancillary Works Regarding Interconnection of Rising Main With Tubewell of Sasan PWSS at Headwork Site & 2nd TW Site In Connection with Sasan Augmentation at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000053/2025-2026 | 1543/RD/PHE | 11/06/2025 | 30 | M/S CHOUDHURY CONSTRUCTION | 1.35 | 0 | 0
1483 | Raiganj Division | Raiganj Sub-Division | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for SASAN PWSS [Augmentation] and its adjoining Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000080/2022-2023 | 1533/RD/PHE | 25/08/2022 | 30 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 0.7 | 0 | 0
1484 | Raiganj Division | Raiganj Sub-Division | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000127/2022-2023 | 1519\RD | 24/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0
1485 | Raiganj Division | Raiganj Sub-Division | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000131/2022-2023 | 1522\RD | 24/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0
1486 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-300 Cum)of SASAN Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000208/2022-2023 | 77/RD/PHE | 17/01/2023 | 690 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 84.28 | 0 | 95
1487 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Sasan Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000270/2022-2023 | 434/RD/PHE | 10/02/2023 | 45 | SHYAM ENTERPRISE SHYAMENTERPRISE.RNJ@GMAIL.COM | 3 | 0 | 100
1488 | Raiganj Division | Raiganj Sub-Division | Ancillary works and inter connection b/w rising main and OHR, I.C.W. Augmentation of Sasan PWSS at Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000401/2025-2026 | 1607/RD/PHE | 17/06/2025 | 120 | SANDIP SARKAR | 3.79 | 0 | 0
1489 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sasan PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000486/2024-2025 | 19/RD/PHE | 02/01/2025 | 120 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 14.82 | 0 | 100
1490 | Raiganj Division | Raiganj Sub-Division | Ancillary works regarding Inter Connection of rising main with Teube-well with construction of boundary wall for additional land for Augmentation of Sasan PWSS at Hemtabad Block under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000654/2024-2025 | 416/RD/PHE | 29/01/2025 | 45 | BHOLA PAUL | 14.33 | 0 | 0
1491 | Raiganj Division | Raiganj Sub-Division | Laying Distribution System for SASAN and its adjoining Mouza Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000748/2021-2022 | 487/RD/PHE | 25/02/2022 | 30 | BHOLA PAUL | 85.26 | 0 | 75
1492 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000023/2021-2022 | 641/RD/PHE | 23/03/2022 | 0 | Resource Division | 4.86 | 0 | 0
1493 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000049/2022-2023 | 1981/RD/PHE | 09/11/2022 | 0 | Resource Division | 9.56 | 0 | 0
1494 | Raiganj Division | Raiganj Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | VCH/001766/2022-2023 | BP-2022-23-208 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0
1495 | Raiganj Division | Raiganj Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | VCH/001768/2022-2023 | BP-2022-23-210 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0
1496 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line for Providing FHTC for Shridharpur WSS (Purba Durlavpur PWSS) under Raiganj Division, PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000416/2023-2024 | 2788/RD/PHE | 11/10/2023 | 30 | GOPES SAHA | 4.67 | 0 | 100
1497 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[Itahar] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000378/2021-2022 | 2073/RD/PHE | 02/11/2021 | 30 | SUBHASIS MAJUMDER | 8.77 | 0 | 1
1498 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba [Itahar] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000731/2021-2022 | 427/RD/PHE | 16/02/2022 | 30 | SUBHASIS MAJUMDER | 8.48 | 0 | 0
1499 | Raiganj Division | Raiganj Sub-Division | Route Survey & Preparation of DPR of KASBA -ITAHAR PWSS under PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000759/2021-2022 | 174/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 0
1500 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000005/2021-2022 | 29/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.06 | 0 | 0
1501 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000012/2022-2023 | 1803/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.31 | 0 | 0
1502 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe line for Ramganj Zone-II Piped water Supply Scheme in connection with Augmentation of Ramganj Zone-II PWSS under Raiganj Division P.H.E. Dte in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000044/2023-2024 | 1543/RD/PHE | 24/05/2023 | 30 | UJJWAL DAS | 7.59 | 0 | 0
1503 | Raiganj Division | Islampur Sub-Division | Augmentation of RAMGANJ(Zone-II)Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000105/2022-2023 | 1552/RD/PHE | 26/08/2022 | 818 | UJJWAL DAS | 177.43 | 0 | 98
1504 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Ramganj Zone-II Water Supply Scheme [Augmentation Scheme] in Islampur Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000158/2022-2023 | 2018/RD/PHE | 17/11/2022 | 90 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 56.88 | 0 | 38
1505 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Ramganj Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000235/2022-2023 | 368/RD/PHE | 07/02/2023 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 5.02 | 0 | 100
1506 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m)in connection with Augmentation of Ramganj Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000251/2022-2023 | 379/RD/PHE | 07/02/2023 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 4.1 | 0 | 100
1507 | Raiganj Division | Islampur Sub-Division | Restoration of damaged pipeline with some ancillary works at different mouzas under Ramganj Z-II PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000346/2024-2025 | 3299/RD/PHE | 20/11/2024 | 135 | UJJWAL DAS | 21.68 | 0 | 0
1508 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ramganj Zone-II Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000356/2025-2026 | 2502/RD/PHE | 12/09/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 32.32 | 0 | 0
1509 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-400 Cum) of RAMGANJ(Zone-II) Pipe Water Supply Scheme in connection with Augmentation at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000376/2022-2023 | 731/RD/PHE | 15/03/2023 | 365 | SOVAN KUMAR ROY | 143.15 | 0 | 0
1510 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with augmentation of Ramganj Zone-II Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000505/2024-2025 | 50/RD/PHE | 03/01/2025 | 45 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 29.19 | 0 | 0
1511 | Raiganj Division | Islampur Sub-Division | Balance Distribution System of Laying Pipeline with Construction of Boundary Wall with Gate at Head Work Site & 2nd Tube-Well Site under RAMGANJ Zone-II PWSS(Augmentation) at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000567/2023-2024 | 739/RD/PHE | 12/03/2024 | 549 | SOVAN KUMAR ROY | 25.87 | 0 | 95
1512 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
1513 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1514 | Raiganj Division | Islampur Sub-Division | Trial Run For Ramganj Zone-II PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000707/2024-2025 | 545/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0
1515 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000033/2022-2023 | 1946/RD/PHE | 04/11/2022 | 0 | Resource Division | 55.2 | 0 | 0
1516 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing FHTC for Udaypur Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase-II) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000037/2022-2023 | 1049/RD/PHED | 12/05/2022 | 45 | M/S P.S. ENTERPRISE | 14.2 | 0 | 1
1517 | Raiganj Division | Raiganj Sub-Division | Restoration of Pipe Line For Providing Functional Household Tap Connection for Mahinagar Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000284/2022-2023 | 498/RD/PHE | 17/02/2023 | 45 | TAPAN KUMAR ROY | 6.11 | 0 | 100
1518 | Raiganj Division | Islampur Sub-Division | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Banikaner Alisa Rahatpur PWSS at Islampur Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000167/2024-2025 | 2895/RD/PHE | 25/09/2024 | 20 | SHANKAR SAHA | 4.31 | 0 | 0
1519 | Raiganj Division | Islampur Sub-Division | Implementation of BANIKANER ALISA RAHATPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000302/2022-2023 | 551/RD/PHE | 23/02/2023 | 1248 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 232.41 | 0 | 80
1520 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of BENIKANER ALIAS RAHATPUR PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000371/2024-2025 | 3490/RD/PHE | 02/12/2024 | 30 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 14.85 | 0 | 0
1521 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BANIKANER ALISA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000486/2023-2024 | 597/RD/PHE | 05/03/2024 | 45 | K.G.N BUILDERS | 22.57 | 0 | 0
1522 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000121/2022-2023 | 616/RD/PHE | 28/02/2023 | 0 | Resource Division | 25.55 | 0 | 0
1523 | Raiganj Division | Raiganj Sub-Division | Implementation of RUNIA and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000220/2022-2023 | 98/RD/PHE | 19/01/2023 | 1078 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451 | 0 | 10
1524 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Runia PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000448/2024-2025 | 3760/RD/PHED | 18/12/2024 | 45 | AJIT PRAMANIK | 74.5 | 0 | 0
1525 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RUNIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000467/2023-2024 | 575/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.94 | 0 | 75
1526 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1527 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000083/2022-2023 | 2199/RD/PHE | 14/12/2022 | 0 | Resource Division | 59.08 | 0 | 0
1528 | Raiganj Division | Raiganj Sub-Division | Implementation of BIRGHAI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000225/2022-2023 | 288/RD/PHE | 01/02/2023 | 1065 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 560.3 | 0 | 15
1529 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BIRGHAI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000466/2023-2024 | 574/RD/PHE | 05/03/2024 | 45 | M/S POYEM ENTERPRISE | 22.57 | 0 | 70
1530 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Birghai PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000481/2024-2025 | 14/RD/PHE | 02/01/2025 | 270 | DULAL MAJUMDER | 78.38 | 0 | 0
1531 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000060/2022-2023 | 2177/RD/PHE | 12/12/2022 | 0 | Resource Division | 27.08 | 0 | 0
1532 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Chhotaparua Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000136/2022-2023 | 1914/RD/PHE | 28/10/2022 | 405 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 30.69 | 0 | 50
1533 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000119/2023-2024 | 18/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1534 | Raiganj Division | Raiganj Sub-Division | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-08 under Katihar Division of Northeast Frontier Railway in connection with Baghan PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00099/2024-2025 | BP-2024-25-67 | 06/06/2024 | 0 | EXECUTIVE ENGINEER | 0.11 | 0 | 0
1535 | Raiganj Division | Raiganj Sub-Division | Wayleave/track crossing proposal with application ID:NFR-KIR-2024-WL-08 under katihar division of northeast frontier railway in connection with Baghan PWSS in kaliyaganj block under Raiganj division PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00156/2024-2025 | BP-2024-25-103 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.13 | 0 | 0
1536 | Raiganj Division | Raiganj Sub-Division | Additional Pipe Line For Providing FHTC at Baghan PWSS at Kaliaganj Block of Uttar Dinajpur District Under Raiganj Division ,PHE Dte.(New PWSS) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000033/2024-2025 | 1694/RD/PHE | 10/06/2024 | 45 | PRASANTA DUTTA | 9.75 | 0 | 0
1537 | Raiganj Division | Raiganj Sub-Division | Implementation of Baghan and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division , PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000079/2022-2023 | 1507/RD/PHE | 18/08/2022 | 1232 | PRASANTA DUTTA | 121.02 | 0 | 70
1538 | Raiganj Division | Raiganj Sub-Division | Jack Pushing of M.S. Pipe of 200 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 37/8 to 37/9 near Kaliyaganj Railway Station (KAJ) for Baghan and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000145/2024-2025 | 2832/RD/PHE | 23/09/2024 | 207 | RAY CONSTRUCTION &CO. | 27.72 | 0 | 100
1539 | Raiganj Division | Raiganj Sub-Division | Construction of OHR & other allied works of BAGHAN and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000318/2022-2023 | 589/RD/PHE | 24/02/2023 | 1042 | PRASANTA DUTTA | 137.78 | 0 | 61
1540 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAGHAN Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000458/2023-2024 | 566/RD/PHE | 05/03/2024 | 405 | M/S P.S. ENTERPRISE | 22.76 | 0 | 80
1541 | Raiganj Division | Raiganj Sub-Division | Trial Run For Baghan PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000705/2024-2025 | 544/RD/PHE | 12/02/2025 | 90 | PRASANTA DUTTA | 0.88 | 0 | 0
1542 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000043/2022-2023 | 1956/RD/PHE | 04/11/2022 | 0 | Resource Division | 28.75 | 0 | 0
1543 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at JIAKHORI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000032/2025-2026 | 1211/RD/PHE | 25/04/2025 | 45 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 69.49 | 0 | 0
1544 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1545 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000050/2023-2024 | 1476/RD/PHE | 16/05/2023 | 0 | Resource Division | 43.66 | 0 | 0
1546 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Fatepur Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000301/2025-2026 | 1950/RD/PHE | 01/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.35 | 0 | 0
1547 | Raiganj Division | Islampur Sub-Division | Implementation of FATEPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000305/2022-2023 | 554/RD/PHE | 23/02/2023 | 825 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.38 | 0 | 60
1548 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Fatepur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000462/2024-2025 | 3780/RD/PHE | 19/12/2024 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.77 | 0 | 0
1549 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under FATEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000491/2023-2024 | 607/RD/PHE | 05/03/2024 | 135 | M/S ARVI CONSTRUCTION | 22.58 | 0 | 60
1550 | Raiganj Division | Islampur Sub-Division | Preparation & submission of DPR for proposed FATEPUR (Kantirpa-Fatepur) PWSS under Karandighi Block. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000802/2021-2022 | 617/RD/PHE | 16/03/2022 | 30 | ECO CARE | 6.64 | 0 | 0
1551 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000033/2023-2024 | 1218/RD/PHE | 02/05/2023 | 0 | Resource Division | 97.41 | 0 | 0
1552 | Raiganj Division | RWS Raiganj Sub-Divisin | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | BILL/01220/2023-2024 | BP-2024-25-26 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 3.85 | 0 | 0
1553 | Raiganj Division | RWS Raiganj Sub-Divisin | Laying of Pipe line at KACHARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000036/2023-2024 | 1535/RD/PHE | 24/05/2023 | 45 | M/S P.S. ENTERPRISE | 14.82 | 0 | 95
1554 | Raiganj Division | RWS Raiganj Sub-Divisin | Implementation of KACHARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000219/2022-2023 | 97/RD/PHE | 19/01/2023 | 1443 | SANYAL ENTERPRISE | 370.28 | 0 | 65
1555 | Raiganj Division | RWS Raiganj Sub-Divisin | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kachra Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000411/2025-2026 | 2510/RD/PHE | 12/09/2025 | 180 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 29.58 | 0 | 0
1556 | Raiganj Division | RWS Raiganj Sub-Divisin | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kochra PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000450/2024-2025 | 3762/RD/PHED | 18/12/2024 | 45 | UTTAM SAHA | 14.05 | 0 | 0
1557 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KACHARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000488/2023-2024 | 604/RD/PHE | 05/03/2024 | 569 | BIMAL KUMAR SINHA | 22.57 | 0 | 65
1558 | Raiganj Division | RWS Raiganj Sub-Divisin | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0
1559 | Raiganj Division | RWS Raiganj Sub-Divisin | Preparation & Submission of DPR for proposed Kochra Piped Water Supply Scheme under Karandighi Development Block. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | ORD/000801/2021-2022 | 618/RD/PHE | 16/03/2022 | 30 | ECO CARE | 5.16 | 0 | 0
1560 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer-02 | RTOR000101/2022-2023 | 582/RD/PHE | 24/02/2023 | 0 | Resource Division | 97.41 | 0 | 0
1561 | Raiganj Division | Islampur Sub-Division | Augmentation of KARANDIGHI(Zone-II)Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal.(2nd Call). | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000151/2022-2023 | 2047/RD/PHE | 21/11/2022 | 951 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 154.85 | 0 | 70
1562 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Karandighi Zone-II Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000157/2022-2023 | 2017/RD/PHE | 17/11/2022 | 629 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.82 | 0 | 60
1563 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-300 Cum) of KARANDIGHI(Zone-II) Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000211/2022-2023 | 80/RD/PHE | 17/01/2023 | 240 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 86.13 | 0 | 1
1564 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000236/2022-2023 | 369/RD/PHE | 07/02/2023 | 45 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 5.03 | 0 | 100
1565 | Raiganj Division | Islampur Sub-Division | Repairing of Pump House at 2nd tube well site in connection with Augmentation of Karandighi Zone -II Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000237/2022-2023 | 370/RD/PHE | 07/02/2023 | 45 | ALI ENTERPRISE ALIENTERPRISE.HEM@GMAIL.COM | 2.1 | 0 | 100
1566 | Raiganj Division | Islampur Sub-Division | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well under Augmentation Of Karandighi Zone-II PWSS at Karandighi Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000333/2024-2025 | 3289/RD/PHE | 20/11/2024 | 45 | KARTICK BISWAS | 36.07 | 0 | 0
1567 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Karandighi Zone-II Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000353/2025-2026 | 2499/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 29.58 | 0 | 0
1568 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with augmentation of Karandighi Zone-II Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000503/2024-2025 | 48/RD/PHE | 03/01/2025 | 45 | AJIT PRAMANIK | 15.76 | 0 | 0
1569 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1570 | Raiganj Division | Islampur Sub-Division | Trial Run For Karandighi Zone-II PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000708/2024-2025 | 546/RD/PHE | 12/02/2025 | 90 | AJIT PRAMANIK | 0.88 | 0 | 0
1571 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000088/2022-2023 | 2264/RD/PHE | 23/12/2022 | 0 | Resource Division | 119.05 | 0 | 0
1572 | Raiganj Division | RWS Raiganj Sub-Divisin | Implementation of BARHANS and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000221/2022-2023 | 99/RD/PHE | 19/01/2023 | 1443 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 271.31 | 0 | 62
1573 | Raiganj Division | RWS Raiganj Sub-Divisin | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Barhans Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000339/2025-2026 | 2488/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 18.74 | 0 | 0
1574 | Raiganj Division | RWS Raiganj Sub-Divisin | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0
1575 | Raiganj Division | RWS Raiganj Sub-Divisin | Additional Laying distribution and Rising Main of Pipe line for Barhans Pipe Water Supply Scheme (Barhans New PWSS) at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000429/2023-2024 | 3393/RD/PHE | 12/12/2023 | 405 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 7.87 | 0 | 100
1576 | Raiganj Division | RWS Raiganj Sub-Divisin | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Barhans PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000449/2024-2025 | 3761/RD/PHED | 18/12/2024 | 30 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 11.73 | 0 | 0
1577 | Raiganj Division | RWS Raiganj Sub-Divisin | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARHANS PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000501/2023-2024 | 603/RD/PHE | 05/03/2024 | 360 | M/S MAA BOLLA CONSTRUCTION | 22.57 | 0 | 100
1578 | Raiganj Division | RWS Raiganj Sub-Divisin | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000626/2023-2024 | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0
1579 | Raiganj Division | RWS Raiganj Sub-Divisin | Preparation & Submission of DPR for proposed Barhans Piped Water Supply Scheme under Karandighi Development Block. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000798/2021-2022 | 616/RD/PHE | 16/03/2022 | 30 | ENVIROTECH SOLUTIONS | 3.11 | 0 | 0
1580 | Raiganj Division | RWS Raiganj Sub-Divisin | Preparation & Submission of DPR for Proposed Barhans Piped Water Supply Scheme under Karandighi block. | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | ORD/000804/2021-2022 | 616/RD/PHED | 16/03/2022 | 30 | ENVIROTECH SOLUTIONS | 3.11 | 0 | 0
1581 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | RTOR000085/2022-2023 | 586/RD/PHE | 24/02/2023 | 0 | Resource Division | 15.91 | 0 | 0
1582 | Raiganj Division | RWS Raiganj Sub-Divisin | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RWS SD | Junior Engineer, RWS,Junior Engineer-02 | RTOR000093/2023-2024 | 2352/RD/PHE | 11/08/2023 | 0 | Resource Division | 16.43 | 0 | 0
1583 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at ATHIALA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000019/2025-2026 | 1203/RD/PHE | 25/04/2025 | 45 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 40.92 | 0 | 0
1584 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Athiala Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000034/2025-2026 | 1200/RD/PHE | 25/04/2025 | 30 | DEEP CONSTRUCTION | 11.93 | 0 | 0
1585 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000632/2023-2024 | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 100
1586 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000018/2023-2024 | 1122/RD/PHE | 24/04/2023 | 0 | Resource Division | 41.33 | 0 | 0
1587 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Dakhshin Sahapur Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000002/2025-2026 | 1175/RD/PHE | 23/04/2025 | 30 | BIKASH KAR | 8.09 | 0 | 0
1588 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Sahapur Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000344/2025-2026 | 1804/RD/PHE | 24/06/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 29.55 | 0 | 0
1589 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at DAKSHIN SAHAPUR PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000382/2025-2026 | 2094/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 39.1 | 0 | 0
1590 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000014/2023-2024 | 1121/RD/PHE | 24/04/2023 | 0 | Resource Division | 27.44 | 0 | 0
1591 | Raiganj Division | Raiganj Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/01218/2023-2024 | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 14.43 | 0 | 0
1592 | Raiganj Division | Raiganj Sub-Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
1593 | Raiganj Division | Raiganj Sub-Division | Construction Culvert with Hume Pipe Across PWD Borrow Pit for Making Accessible Road at Bahin Paharpur PWSS Head Work Site at Hemtabad Block under Raiganj Division, P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000120/2024-2025 | 3010/RD/PHE | 03/10/2024 | 30 | BHOLA PAUL | 4.22 | 0 | 0
1594 | Raiganj Division | Raiganj Sub-Division | Implementation of BAHIN PAHARPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000314/2022-2023 | 563/RD/PHE | 23/02/2023 | 1175 | BHOLA PAUL | 305.86 | 0 | 53
1595 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000409/2024-2025 | 3045/RD/PHE | 04/10/2024 | 90 | ARNAB DUTTA | 1.2 | 0 | 0
1596 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahin Paharpur PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000433/2024-2025 | 3746/RD/PHE | 18/12/2024 | 135 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 32.59 | 0 | 0
1597 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHINPAHARPUR PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000524/2023-2024 | 673/RD/PHE | 05/03/2024 | 45 | BHOLA PAUL | 22.58 | 0 | 100
1598 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
1599 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000063/2023-2024 | 2237/RD/PHE | 02/08/2023 | 0 | Resource Division | 27.73 | 0 | 0
1600 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1601 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000181/2022-2023 | 984/RD/PHE | 30/03/2023 | 0 | Resource Division | 30.7 | 0 | 0
1602 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1603 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000162/2022-2023 | 900/RD/PHE | 28/03/2023 | 0 | Resource Division | 40.24 | 0 | 0
1604 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1605 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000163/2022-2023 | 901/RD/PHE | 28/03/2023 | 0 | Resource Division | 39.85 | 0 | 0
1606 | Raiganj Division | Raiganj Sub-Division | Implementation of KOTGRAM andit's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000010/2023-2024 | 1272/RD/PHE | 08/05/2023 | 969 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 480.8 | 0 | 12
1607 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000064/2023-2024 | 2232/RD/PHE | 02/08/2023 | 0 | Resource Division | 43.48 | 0 | 0
1608 | Raiganj Division | Malda Mechanical Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 15.07.2024 to 16.07.2024 and from 18.07.2024 to 19.07.2024. | Assistant Engineer - I | Junior Engineer-06 | BILL/00274/2024-2025 | BP-2024-25-181 | 30/08/2024 | 0 | M/S DILWAR HOSAIN | 0.08 | 0 | 0
1609 | Raiganj Division | Malda Mechanical Division | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | Assistant Engineer - I | Junior Engineer-06 | ORD/000061/2023-2024 | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 100
1610 | Raiganj Division | Malda Mechanical Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Hasua Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | Assistant Engineer - I | Junior Engineer-06 | ORD/000320/2025-2026 | 2480/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 17.34 | 0 | 0
1611 | Raiganj Division | Malda Mechanical Division | Implementation of HASUA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-06 | ORD/000376/2023-2024 | 2600/RD/PHE | 13/09/2023 | 510 | M/S EVEREST INFRATECH INC | 220.85 | 0 | 45
1612 | Raiganj Division | Malda Mechanical Division | Construction of Approach Road,Laying of Pipe Line,Fhtc and other Allied Works of Hasua Pwss within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I | Junior Engineer-06 | ORD/000393/2024-2025 | 3563/RD/PHE | 05/12/2024 | 45 | M/S SARKAR ENTERPRISE | 47.11 | 0 | 0
1613 | Raiganj Division | Malda Mechanical Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HASUA PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-06 | ORD/000502/2023-2024 | 623/RD/PHE | 05/03/2024 | 45 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 24.48 | 0 | 40
1614 | Raiganj Division | Malda Mechanical Division | Material Requisition To Resource Division | Assistant Engineer - I | Junior Engineer-06 | RTOR000077/2023-2024 | 2263/RD/PHE | 03/08/2023 | 0 | Resource Division | 14.12 | 0 | 0
1615 | Raiganj Division | Islampur Sub-Division | Implementation of BINAPUR and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000229/2023-2024 | 2378/RD/PHE | 14/08/2023 | 90 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 53.95 | 0 | 0
1616 | Raiganj Division | Islampur Sub-Division | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
1617 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000110/2023-2024 | 3315/RD/PHE | 05/12/2023 | 0 | Resource Division | 4.8 | 0 | 0
1618 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000078/2023-2024 | 2255/RD/PHE | 03/08/2023 | 0 | Resource Division | 3.42 | 0 | 0
1619 | Raiganj Division | Raiganj Sub-Division | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000201/2023-2024 | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 100
1620 | Raiganj Division | Raiganj Sub-Division | Construction Of Boundary Wall With Gate at in connection with Augmentation Of KALIGANJ(THARAIS) PWSS at ITAHAR Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000405/2024-2025 | 3575/RD/PHE | 05/12/2024 | 30 | SUBHASIS MAJUMDER | 11.77 | 0 | 0
1621 | Raiganj Division | Raiganj Sub-Division | Augmentation of Kaliganj (Tharais) and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000521/2022-2023 | 881/RD/PHE | 27/03/2023 | 1080 | BHOWMICK ENTERPRISE | 61.85 | 0 | 1
1622 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000009/2023-2024 | 1103/RD/PHE | 20/04/2023 | 0 | Resource Division | 4.82 | 0 | 0
1623 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000374/2023-2024 | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 35
1624 | Raiganj Division | Islampur Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000578/2023-2024 | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0
1625 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000005/2023-2024 | 1045/RD/PHE | 05/04/2023 | 0 | Resource Division | 30.48 | 0 | 0
1626 | Raiganj Division | Raiganj Sub-Division | Augmentation of ITAHAR Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000079/2023-2024 | 1998/RD/PHE | 13/07/2023 | 928 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 639.84 | 0 | 10
1627 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road,Laying Of Pipe Line,Fhtc And Other Allied Works Of Itahar Zone - Ii Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000398/2024-2025 | 3567/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 89.77 | 0 | 0
1628 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000412/2024-2025 | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0
1629 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000023/2023-2024 | 1189/RD/PHE | 27/04/2023 | 0 | Resource Division | 115.81 | 0 | 0
1630 | Raiganj Division | Islampur Sub-Division | MDR T01, RAMKRISHNAPUR TO MDR T10 DIMTI VIA BHARDRAKALI(ROAD CODE T06) | Assistant Engineer ISD | Junior Engineer, ISD | BILL/00106/2024-2025 | BP-2024-25-72 | 12/06/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 15.49 | 0 | 0
1631 | Raiganj Division | Islampur Sub-Division | Implementation of KUCHILA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000081/2023-2024 | 2000/RD/PHE | 13/07/2023 | 896 | UTTAM SAHA | 736.01 | 0 | 40
1632 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kuchila Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000362/2025-2026 | 2508/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.36 | 0 | 0
1633 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Kuchila piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000364/2024-2025 | 3483/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 46.55 | 0 | 0
1634 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KUCHILA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000526/2023-2024 | 547/RD/PHE | 05/03/2024 | 45 | ASHRAFIA BUILDERS | 22.45 | 0 | 0
1635 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000109/2022-2023 | 600/RD/PHE | 27/02/2023 | 0 | Resource Division | 53.38 | 0 | 0
1636 | Raiganj Division | Raiganj Sub-Division | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur- Bhatol Road caused due to pipe laying by PHED under Jagadishpur PWSS at different stretched of road under Uttar Dinajpur Highway Division. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00307/2024-2025 | BP-2024-25-195 | 18/09/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 21.58 | 0 | 0
1637 | Raiganj Division | Raiganj Sub-Division | Implementation of JAGADISHPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000082/2023-2024 | 2001/RD/PHE | 13/07/2023 | 911 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 759.23 | 0 | 50
1638 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000096/2022-2023 | 33/RD/PHE | 06/01/2023 | 0 | Resource Division | 115.16 | 0 | 0
1639 | Raiganj Division |  | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-09 under Katihar Division of Northeast Frontier Railway in connection with Bhomra PWSS in Raiganj Block under Raiganj Division PHE Dte. |  |  | BILL/00098/2024-2025 | BP-2024-25-68 | 06/06/2024 | 0 | EXECUTIVE ENGINEER | 0.1 | 0 | 0
1640 | Raiganj Division |  | Way leave/track crossing proposal with application id: NFR-KIR-2024-WL-11 under Kathihar Division of North East Fronter Railway in connection with Bhomra PWSS in Raiganj Block under Raiganj Division, PHE Dte. |  |  | BILL/00157/2024-2025 | BP-2024-25-105 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.04 | 0 | 0
1641 | Raiganj Division |  | Jack Pushing of M.S. Pipe of 300 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 23/8 to 23/9 near Jhitkia Railway Station (RGJ) for Bhomra and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. In the district of Uttar Dinajpur. |  |  | ORD/000146/2024-2025 | 2833/RD/PHE | 23/09/2024 | 110 | RAY CONSTRUCTION &CO. | 28.76 | 0 | 100
1642 | Raiganj Division |  | Implementation of BHOMRA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under RaiganjDivision, PHE Dte. |  |  | ORD/000210/2023-2024 | 2293/RD/PHE | 04/08/2023 | 881 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 890.66 | 0 | 50
1643 | Raiganj Division |  | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Jhitkia, 2.Bhomra in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. |  |  | ORD/000225/2023-2024 | 2366/RD/PHE | 11/08/2023 | 540 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 100
1644 | Raiganj Division |  | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhomra PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. |  |  | ORD/000468/2024-2025 | 01/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 19.24 | 0 | 0
1645 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 862/RD/PHE | 25/03/2023 | 0 | Resource Division | 79.68 | 0 | 0
1646 | Raiganj Division |  | Implementation of BHABANIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. |  |  | ORD/000355/2023-2024 | 2473/RD/PHE | 24/08/2023 | 660 | M/S PINKI CONSTRUCTION | 974.94 | 0 | 66
1647 | Raiganj Division |  | Construction of concrete pathway at Head Work Site Pump House,2nd TW Site & 3rd TW Site Pump House for BHABANIPUR Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. |  |  | ORD/000369/2024-2025 | 3488/RD/PHE | 02/12/2024 | 30 | SANDIP SARKAR | 9.25 | 0 | 0
1648 | Raiganj Division |  | Laying of Additional pipeline with other ancillary works at different mouzas of BHABANIPUR PWSS under Islampur Sub-Division P.H.E. Dte. |  |  | ORD/000380/2024-2025 | 3499/RD/PHE | 02/12/2024 | 45 | M/S PINKI CONSTRUCTION | 34.81 | 0 | 0
1649 | Raiganj Division |  | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) |  |  | ORD/000411/2024-2025 | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 100
1650 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 633/RD/PHE | 02/03/2023 | 0 | Resource Division | 81.83 | 0 | 0
1651 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purba Joypura Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000298/2025-2026 | 1928/RD/PHE | 30/06/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 32.38 | 0 | 0
1652 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1653 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PURBA JAYPURA PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000386/2025-2026 | 2098/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 56.82 | 0 | 0
1654 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Purba Jaypura Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd call). | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000388/2025-2026 | 2170/RD/PHE | 25/07/2025 | 90 | M/S SHIB ENTERPRISE | 6.63 | 0 | 0
1655 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000170/2022-2023 | 966/RD/PHE | 29/03/2023 | 0 | Resource Division | 28.51 | 0 | 0
1656 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at BARA SINGHNATH PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000267/2025-2026 | 2086/RD/PHE | 14/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 45.73 | 0 | 0
1657 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Singhanath Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000314/2025-2026 | 1984/RD/PHE | 04/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0
1658 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000019/2023-2024 | 1120/RD/PHE | 24/04/2023 | 0 | Resource Division | 37.22 | 0 | 0
1659 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe Line for providing F.H.T.C. at Jaingaon Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000036/2022-2023 | 1048/RD/PHED | 12/05/2022 | 45 | SAHA CONSTRUCTION | 13.7 | 0 | 100
1660 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 03.06.2024 to 07.06.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00130/2024-2025 | BP-2024-25-92 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
1661 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period for 02.05.2024 to 03.05.2024, 06.05.2024 to 07.05.2024 and 09.05.2024 to 10.05.2024. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/00131/2024-2025 | BP-2024-25-91 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0
1662 | Raiganj Division | Raiganj Sub-Division | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | BILL/01217/2023-2024 | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 6.55 | 0 | 0
1663 | Raiganj Division | Raiganj Sub-Division | Implementation of DHAMDOL and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under RaiganjDivision, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000311/2022-2023 | 565/RD/PHE | 23/02/2023 | 1276 | M/S LOKENATH CONSTRUCTION | 300.71 | 0 | 40
1664 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dhamdol Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000311/2025-2026 | 2476/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.01 | 0 | 0
1665 | Raiganj Division | Raiganj Sub-Division | Construction Of Approach Road, Laying of Pipe Line And Other Allied Works Of Dhamdhol PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000391/2024-2025 | 3561/RD/PHE | 05/12/2024 | 271 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 71.06 | 0 | 0
1666 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAMDOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000533/2023-2024 | 611/RD/PHE | 05/03/2024 | 316 | SUBHASIS MAJUMDER | 11.29 | 0 | 100
1667 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAMDOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000534/2023-2024 | 612/RD/PHE | 05/03/2024 | 311 | M/S. ROY & CO. | 11.29 | 0 | 100
1668 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1669 | Raiganj Division | Raiganj Sub-Division | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000576/2022-2023 | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 100
1670 | Raiganj Division | Raiganj Sub-Division | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | ORD/000627/2023-2024 | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 100
1671 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-06 | RTOR000062/2023-2024 | 2232/RD/PHE | 01/08/2023 | 0 | Resource Division | 29.61 | 0 | 0
1672 | Raiganj Division | Islampur Sub-Division | Implementation of ALIGANJ and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000256/2022-2023 | 298/RD/PHE | 01/02/2023 | 1065 | UTTAM SAHA | 707.12 | 0 | 65
1673 | Raiganj Division | Islampur Sub-Division | Laying of Balance Pipeline with ancillary works for ALIGANJ Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000384/2024-2025 | 3554/RD/PHE | 05/12/2024 | 45 | KARTICK BISWAS | 37.13 | 0 | 0
1674 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ALIGANJ Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000481/2023-2024 | 590/RD/PHE | 05/03/2024 | 45 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 22.52 | 0 | 0
1675 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000070/2022-2023 | 2187/RD/PHE | 12/12/2022 | 0 | Resource Division | 48.12 | 0 | 0
1676 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000100/2022-2023 | 579/RD/PHE | 24/02/2023 | 0 | Resource Division | 47.6 | 0 | 0
1677 | Raiganj Division | Raiganj Sub-Division | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00504/2023-2024 | BP-2023-24-129 | 29/09/2023 | 0 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0
1678 | Raiganj Division | Raiganj Sub-Division | Implementation of BAJE BINDOLE and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000093/2022-2023 | 1540/RD/PHE | 26/08/2022 | 630 | M/S MAA TARA CONSTRUCTION | 239.58 | 0 | 100
1679 | Raiganj Division | Raiganj Sub-Division | Construction of OHR & other allied works of BAJE BINDOL and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000312/2022-2023 | 587/RD/PHE | 24/02/2023 | 767 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 157.71 | 0 | 85
1680 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAJE BINDOL Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000461/2023-2024 | 569/RD/PHE | 05/03/2024 | 361 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 22.76 | 0 | 75
1681 | Raiganj Division | Raiganj Sub-Division | Trial Run For Baje Bindol PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000697/2024-2025 | 538/RD/PHE | 12/02/2025 | 90 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0
1682 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000042/2022-2023 | 1955/RD/PHE | 04/11/2022 | 0 | Resource Division | 30.7 | 0 | 0
1683 | Raiganj Division | Raiganj Sub-Division | Implementation of BALIA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer RSD |  | ORD/000212/2023-2024 | 2295/RD/PHE | 04/08/2023 | 990 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 578.22 | 0 | 40
1684 | Raiganj Division | Raiganj Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) BALIA in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer RSD |  | ORD/000224/2023-2024 | 2365/RD/PHE | 11/08/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 17.79 | 0 | 100
1685 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD |  | RTOR000134/2022-2023 | 654/RD/PHE | 03/03/2023 | 0 | Resource Division | 33.83 | 0 | 0
1686 | Raiganj Division | Islampur Sub-Division | Implementation of PRRAUL and its adjoining mouzas Pipe Water Supply Scheme at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, PHEDte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000228/2023-2024 | 2407/RD/PHE | 17/08/2023 | 593 | S.G. CONSTRUCTION | 236.76 | 0 | 95
1687 | Raiganj Division | Islampur Sub-Division | Earth Filling at Parrul PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000352/2024-2025 | 3305/RD/PHE | 20/11/2024 | 30 | S.G. CONSTRUCTION | 11.3 | 0 | 0
1688 | Raiganj Division | Islampur Sub-Division | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000357/2024-2025 | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0
1689 | Raiganj Division | Islampur Sub-Division | Construction Of Approach Road Of Prraul PWSS at Goalpukhur-II Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000358/2024-2025 | 3306/RD/PHE | 20/11/2024 | 30 | M/S TRIBENI CONSTRUCTION | 6.2 | 0 | 0
1690 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000144/2022-2023 | 839/RD/PHE | 23/03/2023 | 0 | Resource Division | 31.09 | 0 | 0
1691 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Butijhari and Adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000271/2020-2021 | 1412/RD/PHE | 11/12/2020 | 40 | SANYAL ENTERPRISE | 86.29 | 0 | 1
1692 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002094/2021-2022 | 754/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.09 | 0 | 0
1693 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Unatiagachh Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000235/2020-2021 | 1424/RD/PHE | 11/12/2020 | 30 | RAHUL ENTERPRISE | 10.45 | 0 | 1
1694 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Bhindabari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000252/2020-2021 | 1425/RD/PHE | 11/12/2020 | 30 | MS SARKAR ENTERPRISE ABDULGHATA | 10.63 | 0 | 100
1695 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Madhya Phulbari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000253/2020-2021 | 1423/RD/PHE | 11/12/2020 | 30 | NIMAI DAS | 10.93 | 0 | 1
1696 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Paschim Phulbari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000254/2020-2021 | 1422/RD/PHE | 11/12/2020 | 30 | KARTICK BISWAS | 11 | 0 | 10
1697 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Dehar Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000255/2020-2021 | 1436/RD/PHE | 11/12/2020 | 30 | MAA BICHITRA CONSTRUCTION | 10.43 | 0 | 1
1698 | Raiganj Division | Islampur Sub-Division | FHTC OF DEHAR PWSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000329/2020-2021 | 1425/RD | 11/12/2020 | 30 | M/S SARKAR ENTERPRISE | 10.63 | 7.39 | 100
1699 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002103/2021-2022 | 764/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.1 | 0 | 0
1700 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Daribhir Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000265/2020-2021 | 1435/RD/PHE | 11/12/2020 | 30 | SAMIRAN PODDAR | 11.06 | 0 | 1
1701 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Amlijhari Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000266/2020-2021 | 1421/RD/PHE | 11/12/2020 | 30 | MAA SHEETALA ENTERPRISE | 11.38 | 0 | 100
1702 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Gangamaila Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000267/2020-2021 | 1439/RD/PHE | 11/12/2020 | 30 | AJIT PARMANIK | 10.77 | 0 | 0
1703 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Bijekhor Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000268/2020-2021 | 1437/RD/PHE | 11/12/2020 | 751 | HAQUE CONSTRUCTION | 11.29 | 0 | 100
1704 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) at Phulhar Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000269/2020-2021 | 1438/RD/PHE | 11/12/2020 | 30 | M/S P.S ENTERPRISE | 10.94 | 0 | 0
1705 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002087/2021-2022 | 769/W | 11/03/2022 | 0 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0
1706 | Raiganj Division | Islampur Sub-Division | OFFICE ACCESSORIES BILL | Assistant Engineer ISD | Junior Engineer, ISD | VCH/002101/2021-2022 | 763/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0
1707 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Siripur and adjoining Mouzas Water Supply Scheme in Galpokher-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000171/2020-2021 | 1234/RD/ PHE | 16/10/2020 | 40 | SAMIRAN PODDAR | 65.04 | 0 | 0
1708 | Raiganj Division | Islampur Sub-Division | LAYING UPVC OF FHTC OF SIRIPUR PWSS | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000442/2020-2021 | 1522/RD | 23/12/2020 | 30 | M/S DOLPHIN CONSTRUCTION | 6.9 | 0 | 0
1709 | Raiganj Division | Islampur Sub-Division | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000164/2020-2021 | 369/RD/PHE | 04/02/2021 | 25 | MAA TARA CONSTRUCTION | 4.12 | 0 | 1
1710 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-III) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000247/2020-2021 | 1389/RD/PHE | 09/12/2020 | 30 | M/S HINDUSTHAN CONSTRUCTION | 15.86 | 0 | 1
1711 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000248/2020-2021 | 1388/RD/PHE | 09/12/2020 | 30 | M/S CHOUDHURY CONSTRUCTION | 15.84 | 0 | 1
1712 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-I) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000249/2020-2021 | 1387/RD/PHE | 09/12/2020 | 30 | M/S LUCKY CONSTRUCTION | 15.93 | 0 | 1
1713 | Raiganj Division | Raiganj Sub-Division | Preliminary Route Survey for finding feasibility of providing FHTC in different PWSS (Which excluded design year) Preparation of DPR of No.1. Goalpukhur PWSS 2. Lakhipur PWSS 3. Khanta PWSS 4. Hemtabad PWSS 5. Dharampur PWSS Zone-II under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000001/2022-2023 | 896/RD/PHED | 20/04/2022 | 7 | M/S DUTTA ENTERPRISE | 4.46 | 0 | 100
1714 | Raiganj Division | Raiganj Sub-Division | Preparation of Additional DPR For Hemtabad Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Hemtabad PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000179/2022-2023 | 2151/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 1
1715 | Raiganj Division | Raiganj Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Hemtabad Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000288/2021-2022 | 1824/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.44 | 0 | 0
1716 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Hemtabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Hemtabad Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000380/2021-2022 | 2075/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 17.93 | 0 | 1
1717 | Raiganj Division | Raiganj Sub-Division | Allied works in connection with retrofitting of FHTC in Hemtabad PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000383/2023-2024 | 2609/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.98 | 0 | 100
1718 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Hemtabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Hemtabad Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000745/2021-2022 | 484/RD/PHE | 25/02/2022 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 17.61 | 0 | 100
1719 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000019/2022-2023 | 1807/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.4 | 0 | 0
1720 | Raiganj Division | Raiganj Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Sasan Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000290/2021-2022 | 1826/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.98 | 0 | 0
1721 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections (FHTC) under Sasan Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000382/2021-2022 | 2077/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 5.8 | 0 | 1
1722 | Raiganj Division | Raiganj Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Sasan Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000733/2021-2022 | 429/RD/PHE | 16/02/2022 | 30 | TAPAN KUMAR MAJUMDER | 5.74 | 0 | 0
1723 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer RSD | Junior Engineer, RSD | RTOR000011/2022-2023 | 1792/RD/PHE | 22/09/2022 | 0 | Resource Division | 1.54 | 0 | 0
1724 | Raiganj Division | Islampur Sub-Division | Pipeline work and other ancillary works at Kulavita village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000023/2021-2022 | 1414/RD/PHE | 07/07/2021 | 30 | M/S MANDAL ENTERPRISE | 4.82 | 0 | 1
1725 | Raiganj Division | Islampur Sub-Division | Pipeline work and other ancillary works at Motilal village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000024/2021-2022 | 1415/RD/PHE | 07/07/2021 | 30 | M/S DUTTA ENTERPRISE | 4.8 | 0 | 1
1726 | Raiganj Division | Islampur Sub-Division | Pipeline work and other ancillary works at Magurjan village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000025/2021-2022 | 1416/RD/PHE | 07/07/2021 | 30 | DONE ENTERPRISE | 4.3 | 0 | 1
1727 | Raiganj Division | Islampur Sub-Division | Laying of D.I. Pipeline and Ancillary works for improving the FHTC of Mahua Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000185/2022-2023 | 2255/RD/PHE | 22/12/2022 | 20 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 1 | 0 | 100
1728 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Mahua for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-IV) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000437/2021-2022 | 2199/RD/PHE | 17/11/2021 | 30 | M/S HINDUSTHAN CONSTRUCTION | 25.63 | 0 | 0
1729 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of MALGAON Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000448/2021-2022 | 2384/RD/PHE | 24/12/2021 | 30 | DONE ENTERPRISE | 13.71 | 0 | 0
1730 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Majhihar Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000353/2021-2022 | 2134/RD/PHE | 12/11/2021 | 30 | PRASANTA DUTTA | 4.74 | 0 | 1
1731 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Majhihar Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000354/2021-2022 | 2135/RD/PHE | 12/11/2021 | 30 | PRASANTA DUTTA | 4.74 | 0 | 1
1732 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of MAHAMMADPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000427/2021-2022 | 2189/RD/PHE | 17/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 18.25 | 0 | 0
1733 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe Line damaged and other allied works at Jaingaon Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000351/2021-2022 | 2165/RD/PHE | 12/11/2021 | 30 | TAPAN KUMAR ROY | 2.62 | 0 | 1
1734 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Butijhari Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000007/2022-2023 | 1019/RD/PHE | 12/05/2022 | 45 | CHAITANYA SAMAL | 10.67 | 0 | 100
1735 | Raiganj Division | Islampur Sub-Division | Laying additional Pipe Line for Providing Functional Household Tap Connection of Faridpur Water Supply Scheme under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000009/2022-2023 | 1021/RD/PHED | 12/05/2022 | 45 | TAPAN KUMAR MAJUMDER | 11.27 | 0 | 100
1736 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Khowaspur Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000010/2022-2023 | 1022/RD/PHED | 12/05/2022 | 45 | DIPANKAR SARKAR | 12.85 | 0 | 1
1737 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Amalbari Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000011/2022-2023 | 1023/RD/PHED | 12/05/2022 | 45 | KARTICK BISWAS | 13.46 | 0 | 1
1738 | Raiganj Division | Islampur Sub-Division | Laying Additional Pipe Line for Providing Functional Household Tap Connection of Puria Water Supply Scheme under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000012/2022-2023 | 1024/RD/PHED | 12/05/2022 | 45 | NIMAI DAS | 18.89 | 0 | 1
1739 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Dehar Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000013/2022-2023 | 1025/RD/PHED | 12/05/2022 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 21.86 | 0 | 1
1740 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Kamartor Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000014/2022-2023 | 1026/RD/PHED | 12/05/2022 | 45 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 23.5 | 0 | 1
1741 | Raiganj Division | Islampur Sub-Division | Laying Additional Pipe Line Beyond the scope of Pipeline to be laid as per DPR Purba Rampur Water Supply Scheme under Raiganj Division P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000015/2022-2023 | 1027/RD/PHED | 12/05/2022 | 45 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 27.28 | 0 | 100
1742 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Bhojpur Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000016/2022-2023 | 1028/RD/PHED | 12/05/2022 | 45 | M/S PIONEER ENTERPRISE | 31.81 | 0 | 1
1743 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Purba Chutiakhore Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000018/2022-2023 | 1030/RD/PHED | 12/05/2022 | 45 | M/S LUCKY CONSTRUCTION | 46.82 | 0 | 1
1744 | Raiganj Division | Islampur Sub-Division | Laying of additional pipe line to be laid the scope of DPR in the command area at Amaljhari Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000019/2022-2023 | 1031/RD/PHED | 12/05/2022 | 30 | APEX ENTERPRISES | 8.95 | 0 | 100
1745 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe Line for providing F.H.T.C. at Bhagabati Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000038/2022-2023 | 1050/RD/PHED | 12/05/2022 | 45 | TAPAN KUMAR MAJUMDER | 14.06 | 0 | 1
1746 | Raiganj Division | Islampur Sub-Division | Restoration of Damaged Pipe line work required for FHTC Work at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte.(PART -B) | Assistant Engineer HQ,Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000180/2022-2023 | 2250/RD/PHE | 22/12/2022 | 20 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 10.28 | 0 | 0
1747 | Raiganj Division | Islampur Sub-Division | Restoration of Pipe Line for providing F.H.T.C. at Pokheria Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000028/2022-2023 | 1040/RD/PHED | 12/05/2022 | 30 | TAPAN KUMAR MAJUMDER | 7.03 | 0 | 1
1748 | Raiganj Division | Raiganj Sub-Division | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 17.12.2022 to 15.01.2023. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | BILL/00946/2023-2024 | BP-2023-24-223 | 15/12/2023 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0
1749 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Dilwarpur Water Supply Scheme [Augmentation Scheme] in Kaliaganj Block of Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000003/2022-2023 | 1015/RD/PHED | 12/05/2022 | 45 | BHOLA PAUL | 45.2 | 0 | 95
1750 | Raiganj Division | Raiganj Sub-Division | Soil Investigation for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Dilwarpur W/S Scheme in Kaliaganj Block in Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000050/2022-2023 | 1237/RD/PHE | 20/06/2022 | 20 | BENGAL CO-OP. ENGINEERS' CONSTRUCTION SOCIETY LTD. | 1.99 | 0 | 0
1751 | Raiganj Division | Raiganj Sub-Division | Repairing of Pump House of Head Works and 2nd Tube Well Site under Augmentation of Dilwarpur Water Supply Scheme at Kaliyaganj Block under Raiganj Division P.H.E Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000081/2022-2023 | 1534/RD/PHE | 25/08/2022 | 30 | M/S CHOUDHURY CONSTRUCTION | 4.23 | 0 | 0
1752 | Raiganj Division | Raiganj Sub-Division | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000123/2022-2023 | 1512/RD | 22/08/2022 | 7 | JUMBO XEROX | 0.09 | 0 | 0
1753 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-300 Cum) of Dilwarpur Pipe Water Supply Scheme in connection with Augmentation at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000209/2022-2023 | 78/RD/PHE | 17/01/2023 | 240 | M/S MASCOT CONSTRUCTION KRISHNADITYA06@GMAIL.COM | 84.11 | 0 | 0
1754 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dilwarpur Water Supply Scheme(Augmentation of Dilwarpur PWSS) under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity-35 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000428/2023-2024 | 3392/RD/PHE | 12/12/2023 | 140 | AJIT PRAMANIK | 17.73 | 0 | 0
1755 | Raiganj Division | Raiganj Sub-Division | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for DILWARPUR (Augmentation) and its adjoining Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000470/2021-2022 | 46/RD/PHE | 07/01/2022 | 45 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 0.77 | 0 | 100
1756 | Raiganj Division | Raiganj Sub-Division | Construction of 2 Nos. Tube-Well ( 250mm diameter x 150mmx140 mtr) for Dilwarpur Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000471/2021-2022 | 47/RD/PHE | 07/01/2022 | 21 | BHOLA PAUL | 17.54 | 0 | 1
1757 | Raiganj Division | Raiganj Sub-Division | Laying Distribution System for DILWARPUR and its adjoining Mouza Water Supply Scheme at KALIAGANJ Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000482/2021-2022 | 177/RD/PHE | 27/01/2022 | 45 | M/S MAA TARA CONSTRUCTION | 119.05 | 0 | 100
1758 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000001/2022-2023 | 1215/RD/PHE | 10/06/2022 | 0 | Resource Division | 8.56 | 0 | 0
1759 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000002/2022-2023 | 125/RSD/PHE | 10/08/2022 | 0 | Resource Division | 0.61 | 0 | 0
1760 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000003/2022-2023 | 126/RSD/PHE | 10/08/2022 | 0 | Resource Division | 0.16 | 0 | 0
1761 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000022/2021-2022 | 637/RD/PHE | 23/03/2022 | 0 | Resource Division | 9.75 | 0 | 0
1762 | Raiganj Division | Raiganj Sub-Division | xerox bill | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | VCH/001769/2022-2023 | BP-2022-23-207 | 04/11/2022 | 0 | JUMBO XEROX | 0.09 | 0 | 0
1763 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Shitlagaon Water Supply Scheme [Augmentation Scheme] in Chopra Block of Uttar Dinajpur District | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000005/2022-2023 | 1017/RD/PHED | 12/05/2022 | 855 | HAQUE CONSTRUCTION | 53.31 | 0 | 50
1764 | Raiganj Division | Islampur Sub-Division | Soil Investigation for Construction of 350 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Shitlagaon W/S Scheme In Chopra Block In Uttar Dinajpur District. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000049/2022-2023 | 1236/RD/PHE | 20/06/2022 | 20 | GEOCON INDIA | 1.98 | 0 | 100
1765 | Raiganj Division | Islampur Sub-Division | Approach Road including earthwork for road at 2nd Tube Well Site of Sitlagaon Piped Water Supply Scheme in connection with Augmentation of Sitalgaon PWSS under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000182/2022-2023 | 2252/RD/PHE | 22/12/2022 | 20 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.65 | 0 | 0
1766 | Raiganj Division | Islampur Sub-Division | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Sitlagaon Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000240/2022-2023 | 373/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.12 | 0 | 100
1767 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Sitlagaon Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000246/2022-2023 | 376/RD/PHE | 07/02/2023 | 45 | BITTU ENTERPRISE BISWAJIT.RNJ@GMAIL.COM | 5.03 | 0 | 100
1768 | Raiganj Division | Islampur Sub-Division | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well in connection with Augmentation Of Sitlagaon PWSS at Chopra Block under Raiganj Division,PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000338/2024-2025 | 3294/RD/PHE | 20/11/2024 | 45 | M/S LUCKY CONSTRUCTION | 29.78 | 0 | 0
1769 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC in connection with Augmentation Of Sitlagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000347/2024-2025 | 3300/RD/PHE | 20/11/2024 | 30 | ZAREEN ENTERPRISE | 6.61 | 0 | 0
1770 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Shitlagaon Water Supply Scheme(Augmentation) at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-45 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000354/2025-2026 | 2500/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.35 | 0 | 0
1771 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-350 Cum) of SITLAGAON Pipe Water Supply Scheme in connection with Augmentation at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000386/2022-2023 | 738/RD/PHE | 15/03/2023 | 635 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 143.55 | 0 | 70
1772 | Raiganj Division | Islampur Sub-Division | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for SITLAGAON (Augmentation) and its adjoining Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000475/2021-2022 | 51/RD/PHE | 07/01/2022 | 45 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 0.52 | 0 | 0
1773 | Raiganj Division | Islampur Sub-Division | Sinking 2 nos. of Ground Bored Wells, 300mm diameter x 200mm diameter, 200mtr. Deep Tube Well including proper development and necessary yield for Ground Water Based PWSS for SITLAGAON nad its adjoining Mouzas Water Supply Scheme under ) of Chopra Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000476/2021-2022 | 52/RD/PHE | 07/01/2022 | 21 | HAQUE CONSTRUCTION | 19.76 | 0 | 1
1774 | Raiganj Division | Islampur Sub-Division | Laying Distribution System for SITLAGAON and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000483/2021-2022 | 178/RD/PHE | 27/01/2022 | 45 | MAA TARA CONSTRUCTION | 111.99 | 0 | 0
1775 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with augmentation of Shitlagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000504/2024-2025 | 49/RD/PHE | 03/01/2025 | 45 | SANDIP SARKAR | 6.17 | 0 | 0
1776 | Raiganj Division | Islampur Sub-Division | Laying Distribution System for SITLAGAON and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000790/2021-2022 | 178/RD /PHE | 27/01/2022 | 180 | M/S MAA TARA CONSTRUCTION | 111.99 | 0 | 0
1777 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000021/2021-2022 | 640/RD/PHE | 23/03/2022 | 0 | Resource Division | 11.38 | 0 | 0
1778 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000050/2022-2023 | 2005/RD/PHE | 16/11/2022 | 0 | Resource Division | 17.06 | 0 | 0
1779 | Raiganj Division | Raiganj Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bamangram Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000271/2025-2026 | 1658/RD/PHE | 23/06/2025 | 180 | AJIT PRAMANIK | 32.35 | 0 | 0
1780 | Raiganj Division | Raiganj Sub-Division | Implementation of BAMANGRAM and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000310/2022-2023 | 561/RD/PHE | 23/02/2023 | 1043 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 525.45 | 0 | 4
1781 | Raiganj Division | Raiganj Sub-Division | Rig bored Tubewell at BAMANGRAM PWSS in connection with Implementation of New Bamangram PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000410/2023-2024 | 2750/RD/PHE | 05/10/2023 | 20 | BHOLA PAUL | 26.11 | 0 | 98
1782 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bamangram PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000440/2024-2025 | 3752/RD/PHED | 18/12/2024 | 135 | BHOLA PAUL | 91.18 | 0 | 0
1783 | Raiganj Division | Raiganj Sub-Division | Balance distribution System of Laying Pipeline with Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAMANGRAM Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000465/2023-2024 | 573/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.87 | 0 | 80
1784 | Raiganj Division | Raiganj Sub-Division | Trial Run For Bamongram PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000699/2024-2025 | 540/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0
1785 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000102/2022-2023 | 573/RD/PHE | 23/02/2023 | 0 | Resource Division | 36.39 | 0 | 0
1786 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Karandighi & Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000025/2023-2024 | 1287/RD/PHE | 08/05/2023 | 1035 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 206.76 | 0 | 5
1787 | Raiganj Division | Islampur Sub-Division | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Jugiamer village under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD,Assistant Engineer RSD |  | ORD/000148/2024-2025 | 2880/RD/PHE | 25/09/2024 | 60 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 43.97 | 0 | 0
1788 | Raiganj Division | Islampur Sub-Division | Repairing for 2nd Pump House & Construction of Toilet at Goalpokher in connection with Goalpokher PWSS under Islampur Sub-Division under Raiganj Division,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000039/2023-2024 | 1538/RD/PHE | 24/05/2023 | 413 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 3.14 | 0 | 100
1789 | Raiganj Division | Islampur Sub-Division | Repairing for Head Work Site Pump House & Construction of Toilet at Goalpokher in connection with Goalpokher PWSS under Islampur Sub-Division under Raiganj Division,PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000040/2023-2024 | 1539/RD/PHE | 24/05/2023 | 45 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 2.35 | 0 | 100
1790 | Raiganj Division | Islampur Sub-Division | Augmentation work of GOALPOKHAR and it's adjoining mouzas Piped Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000100/2022-2023 | 1547/RD/PHE | 26/08/2022 | 90 | AJIT PARMANIK | 319.76 | 0 | 95
1791 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Goalpokhar Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000166/2022-2023 | 2026/RD/PHE | 17/11/2022 | 90 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 66.67 | 0 | 98
1792 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-500 Cum) of GOALPOKHER Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000380/2022-2023 | 735/RD/PHE | 15/03/2023 | 730 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 165.64 | 0 | 85
1793 | Raiganj Division | Islampur Sub-Division | Repair and Maintenance of Boundary Wall and construction of Concrete Pathway at both Head work site and 2nd tube well Pump House site in connection with Augmentation of Goalpokhar Pipe W/S scheme under Islampur Sub-Division PHE Dte.under Raiganj Division, PHE Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000497/2024-2025 | 30/RD/PHE | 02/01/2025 | 45 | HAQUE CONSTRUCTION | 8.16 | 0 | 0
1794 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipeline for Retrofitting in connection with augmentation of Goalpokhar Water Supply Scheme for installation of FHTC under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000499/2024-2025 | 43/RD/PHE | 03/01/2025 | 45 | HAQUE CONSTRUCTION | 40.57 | 0 | 0
1795 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000032/2022-2023 | 1944/RD/PHE | 04/11/2022 | 0 | Resource Division | 33.97 | 0 | 0
1796 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at 3rd tubewell Site (3.60mx3.00m ) Raghabpur Piped Water Supply Scheme in connection with Augmentation of Raghabpur PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000041/2023-2024 | 1540/RD/PHE | 24/05/2023 | 60 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 4.09 | 0 | 100
1797 | Raiganj Division | Islampur Sub-Division | Augmentation of RAGHABPUR Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000103/2022-2023 | 1550/RD/PHE | 26/08/2022 | 90 | DIPESH BHOWMIK | 144.6 | 0 | 100
1798 | Raiganj Division | Islampur Sub-Division | FHTC (Functional Household Tap Connection) for Raghabpur Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000162/2022-2023 | 2022/RD/PHE | 17/11/2022 | 90 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 53.39 | 0 | 70
1799 | Raiganj Division | Islampur Sub-Division | Construction of Over Head Reservoir(Capacity-300 Cum) of RAGHABPUR Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000210/2022-2023 | 79/RD/PHE | 17/01/2023 | 240 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 86.06 | 0 | 0
1800 | Raiganj Division | Islampur Sub-Division | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000238/2022-2023 | 371/RD/PHE | 07/02/2023 | 45 | D. K. ASSOCIATES BISWAJITKAR9434@GMAIL.COM | 4.96 | 0 | 100
1801 | Raiganj Division | Islampur Sub-Division | Repairing of Pump House at 2nd Tubewell site in connection with Augmentation of RAGHABPUR Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000239/2022-2023 | 372/RD/PHE | 07/02/2023 | 45 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.02 | 0 | 100
1802 | Raiganj Division | Islampur Sub-Division | Repairing of Pump House at 3rd Tubewell site in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000252/2022-2023 | 380/RD/PHE | 07/02/2023 | 45 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.06 | 0 | 0
1803 | Raiganj Division | Islampur Sub-Division | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well in connection with Augmentation Of Raghabpur PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000335/2024-2025 | 3291/RD/PHE | 20/11/2024 | 45 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 39.82 | 0 | 0
1804 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Raghabpur Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity-60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000352/2025-2026 | 2498/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.59 | 0 | 0
1805 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line with FHTC for Augmentation Of Raghabpur Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000466/2024-2025 | 3784/RD/PHE | 19/12/2024 | 45 | BIKASH KAR | 26.17 | 0 | 0
1806 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000030/2022-2023 | 1943/RD/PHE | 04/11/2022 | 0 | Resource Division | 20.88 | 0 | 0
1807 | Raiganj Division | Raiganj Sub-Division | Ancillary work I.C.W. retrofitting of Sitgram PWSS, Raiganj Block in connection with Augmentation of Sitgram PWSS under Raiganj Division, PHE Dte. Uttar Dinajpur | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000054/2025-2026 | 1544/RD/PHE | 11/06/2025 | 30 | M/S. BANGARAJ | 2.03 | 0 | 0
1808 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Sitgram Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000141/2022-2023 | 1919/RD/PHE | 28/10/2022 | 45 | BHOLA PAUL | 31.5 | 0 | 30
1809 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000115/2023-2024 | 20/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1810 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Maslandpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000144/2022-2023 | 1922/RD/PHE | 28/10/2022 | 885 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 31.56 | 0 | 71
1811 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000123/2023-2024 | 17/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0
1812 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Rohia Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000304/2025-2026 | 1968/RD/PHE | 02/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.35 | 0 | 0
1813 | Raiganj Division | Islampur Sub-Division | Implementation of ROHIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000330/2022-2023 | 673/RD/PHE | 06/03/2023 | 906 | UTTAM SAHA | 654.73 | 0 | 60
1814 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway With Earth Filling at Head Work Site Pump House & 2nd TW Site Pump House for Rohia Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000381/2024-2025 | 3500/RD/PHE | 02/12/2024 | 15 | SUDIP MITRA | 6.36 | 0 | 0
1815 | Raiganj Division | Islampur Sub-Division | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ROHIA PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000487/2023-2024 | 598/RD/PHE | 05/03/2024 | 45 | PRASANTA DUTTA | 22.75 | 0 | 0
1816 | Raiganj Division | Islampur Sub-Division | Trial Run For Rohia PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000717/2024-2025 | 549/RD/PHE | 12/02/2025 | 90 | UTTAM SAHA | 0.88 | 0 | 0
1817 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000117/2022-2023 | 615/RD/PHE | 28/02/2023 | 0 | Resource Division | 27.28 | 0 | 0
1818 | Raiganj Division | Islampur Sub-Division | Laying Pipe line at MANKAUR Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000038/2023-2024 | 1537/RD/PHE | 24/05/2023 | 45 | M/S P.S. ENTERPRISE | 15.39 | 0 | 0
1819 | Raiganj Division | Islampur Sub-Division | Implementation of MANKAUR andit's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000222/2022-2023 | 113/RD/PHE | 20/01/2023 | 805 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 379.57 | 0 | 60
1820 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Mankaur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000327/2025-2026 | 2482/RD/PHE | 12/09/2025 | 180 | BHOLA PAUL | 29.56 | 0 | 0
1821 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANKAUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000531/2023-2024 | 599/RD/PHE | 05/03/2024 | 360 | M/S CHOUDHURY CONSTRUCTION | 11.29 | 0 | 75
1822 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANKAUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000532/2023-2024 | 600/RD/PHE | 05/03/2024 | 360 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 11.29 | 0 | 80
1823 | Raiganj Division | Islampur Sub-Division | Trial Run For Mankaur PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000719/2024-2025 | 551/RD/PHE | 12/02/2025 | 90 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0
1824 | Raiganj Division | Islampur Sub-Division | Preparation and Submission of DPR for proposed Mankaur Piped Water Supply Scheme under Karandighi Block. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000806/2021-2022 | 611/RD/PHED | 15/03/2022 | 30 | M/S SOBHA & CO. | 4.4 | 0 | 0
1825 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000084/2022-2023 | 585/RD/PHE | 24/02/2023 | 0 | Resource Division | 46.32 | 0 | 0
1826 | Raiganj Division | Islampur Sub-Division | Additional Pipe Line and other ancillary works to provide FHTC at GOPALPUR PWSS (New Scheme) under Islampur Sub-Division ,P.H.E. Dte. under Raiganj Division, PHED, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000127/2024-2025 | 3018/RD/PHE | 03/10/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.54 | 0 | 0
1827 | Raiganj Division | Islampur Sub-Division | Implementation of GOPALPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000224/2022-2023 | 299/RD/PHE | 01/02/2023 | 790 | UTTAM SAHA | 529.88 | 0 | 75
1828 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Gopalpur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000321/2025-2026 | 2481/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0
1829 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway ,Land development and other ancillary works for GOPALPUR Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000406/2024-2025 | 3576/RD/PHE | 05/12/2024 | 45 | UTTAM SAHA | 20.94 | 0 | 0
1830 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GOPALPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000490/2023-2024 | 606/RD/PHE | 05/03/2024 | 45 | M/S PRITHWIRAJ CONSTRUCTION | 22.58 | 0 | 0
1831 | Raiganj Division | Islampur Sub-Division | Trial Run For Gopalpur PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000720/2024-2025 | 552/RD/PHE | 12/02/2025 | 90 | UTTAM SAHA | 0.88 | 0 | 0
1832 | Raiganj Division | Islampur Sub-Division | Preparation & Submission of DPR for proposed Gopalpur Piped Water Supply Scheme under Karandighi Development Block. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000799/2021-2022 | 602/RD/PHE | 15/03/2022 | 30 | ENVIROTECH SOLUTIONS | 5.1 | 0 | 0
1833 | Raiganj Division | Islampur Sub-Division | Preparation and submission of DPR for proposed Gopalpur PWSS under Karandighi block. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000805/2021-2022 | 602/RD/PHED | 15/03/2022 | 30 | ENVIROTECH SOLUTIONS | 5.1 | 0 | 0
1834 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000086/2022-2023 | 584/RD/PHE | 24/02/2023 | 0 | Resource Division | 33.67 | 0 | 0
1835 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at DAKSHIN GORASAHID PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000033/2025-2026 | 1213/RD/PHE | 25/04/2025 | 45 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 40.48 | 0 | 0
1836 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1837 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakhshin Gorasahid Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000392/2025-2026 | 1925/RD/PHE | 30/06/2025 | 180 | KOHINOOR ALAM | 18.72 | 0 | 0
1838 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000045/2023-2024 | 1329/RD/PHE | 15/05/2023 | 0 | Resource Division | 20.34 | 0 | 0
1839 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at UTTAR MOHANGACHH PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000016/2025-2026 | 1212/RD/PHE | 25/04/2025 | 45 | K.G.N BUILDERS | 33.45 | 0 | 0
1840 | Raiganj Division | Islampur Sub-Division | Providing FHTC in connection with Uttar Mahangachh Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000274/2025-2026 | 2173/RD/PHE | 25/07/2025 | 90 | RAKSHIT TRADERS | 8.37 | 0 | 0
1841 | Raiganj Division | Islampur Sub-Division | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000372/2023-2024 | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 30
1842 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000172/2022-2023 | 964/RD/PHE | 29/03/2023 | 0 | Resource Division | 16.24 | 0 | 0
1843 | Raiganj Division | Islampur Sub-Division | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at CHOTA PATNA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000017/2025-2026 | 1201/RD/PHE | 25/04/2025 | 45 | HAQUE CONSTRUCTION | 39.32 | 0 | 0
1844 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chotopatna Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000325/2025-2026 | 1996/RD/PHE | 07/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 30.94 | 0 | 0
1845 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000020/2023-2024 | 1126/RD/PHE | 24/04/2023 | 0 | Resource Division | 36.82 | 0 | 0
1846 | Raiganj Division | Raiganj Sub-Division | Implementation of Dhoarai Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000288/2022-2023 | 535/RD/PHE | 22/02/2023 | 90 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. DEBASISHGHOSHDG76@GMAIL.COM | 41.35 | 0 | 75
1847 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under DHORAI ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000522/2023-2024 | 671/RD/PHE | 05/03/2024 | 45 | SCON | 5.57 | 0 | 0
1848 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
1849 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000036/2023-2024 | 1314/RD/PHE | 12/05/2023 | 0 | Resource Division | 4.13 | 0 | 0
1850 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Siripur Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000195/2022-2023 | 63/RD/PHE | 16/01/2023 | 45 | M/S DOLPHIN CONSTRUCTION DOLPHIN.RGJ@GMAIL.COM | 17.7 | 0 | 60
1851 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000277/2022-2023 | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 100
1852 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000094/2023-2024 | 2400/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
1853 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Pawakhali Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000193/2022-2023 | 60/RD/PHE | 16/01/2023 | 1013 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17.91 | 0 | 50
1854 | Raiganj Division | Islampur Sub-Division | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000278/2022-2023 | 471/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 80
1855 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000100/2023-2024 | 2389/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0
1856 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Rahutara piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000353/2024-2025 | 3307/RD/PHE | 20/11/2024 | 45 | AJIT PRAMANIK | 20.98 | 0 | 0
1857 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Rahutara Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte., U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000354/2024-2025 | 3308/RD/PHE | 20/11/2024 | 45 | AJIT PRAMANIK | 16.57 | 0 | 0
1858 | Raiganj Division | Islampur Sub-Division | Implementation of RAUTARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.( Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000365/2023-2024 | 2481/RD/PHE | 24/08/2023 | 951 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451.99 | 0 | 60
1859 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000560/2023-2024 | 661/RD/PHE | 05/03/2024 | 45 | M/S PRATIMA CHOUDHURY | 11.29 | 0 | 0
1860 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000561/2023-2024 | 662/RD/PHE | 05/03/2024 | 553 | M/S SANTI TRADERS | 11.29 | 0 | 80
1861 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000039/2023-2024 | 1319/RD/PHE | 12/05/2023 | 0 | Resource Division | 45.19 | 0 | 0
1862 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway ,Land development and other ancillary works for KADERGANJ Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHE Dte. under Raiganj Division,PHE Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000463/2024-2025 | 3781/RD/PHE | 19/12/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 12.65 | 0 | 0
1863 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000124/2022-2023 | 641/RD/PHE | 02/03/2023 | 0 | Resource Division | 50.52 | 0 | 0
1864 | Raiganj Division | Islampur Sub-Division | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000295/2022-2023 | 541/RD/PHE | 22/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 60
1865 | Raiganj Division | Islampur Sub-Division | Implementation of BASUDEBPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000324/2022-2023 | 562/RD/PHE | 23/02/2023 | 1035 | M/S LOKENATH CONSTRUCTION | 536.97 | 0 | 45
1866 | Raiganj Division | Islampur Sub-Division | Additional pipeline and other ancillary works at Basudebpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000348/2024-2025 | 3301/RD/PHE | 20/11/2024 | 45 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 36.59 | 0 | 0
1867 | Raiganj Division | Islampur Sub-Division | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for Basudebpur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000349/2024-2025 | 3302/RD/PHE | 20/11/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 10.41 | 0 | 0
1868 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000030/2023-2024 | 1199/RD/PHE | 28/04/2023 | 0 | Resource Division | 54.77 | 0 | 0
1869 | Raiganj Division | Islampur Sub-Division | Implementation of DHAUTA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000360/2023-2024 | 2476/RD/PHE | 24/08/2023 | 823 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 448.76 | 0 | 62
1870 | Raiganj Division | Islampur Sub-Division | Laying Upvc Pipe Line And Others Anciliary Warks Of Dhauta Pwss Within Karandighi Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000496/2024-2025 | 29/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 94.84 | 0 | 0
1871 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAUTA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000514/2023-2024 | 643/RD/PHE | 05/03/2024 | 501 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 22.58 | 0 | 80
1872 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000130/2022-2023 | 635/RD/PHE | 02/03/2023 | 0 | Resource Division | 49.14 | 0 | 0
1873 | Raiganj Division | Islampur Sub-Division | Implementation of NARAYANPUR and its adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000034/2023-2024 | 1500/RD/PHE | 19/05/2023 | 1110 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 270.42 | 0 | 60
1874 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipeline with land development for NARAYANPUR Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000387/2024-2025 | 3557/RD/PHE | 05/12/2024 | 45 | SANDIP SARKAR | 27.06 | 0 | 0
1875 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000140/2022-2023 | 807/RD/PHE | 21/03/2023 | 0 | Resource Division | 27.45 | 0 | 0
1876 | Raiganj Division | Raiganj Sub-Division | Providing Balance Functional House Hold Connection (FHTC) For Balufara Zone-II Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000062/2024-2025 | 2225/RD/PHE | 23/07/2024 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 6.52 | 0 | 0
1877 | Raiganj Division | Raiganj Sub-Division | Implementation of Balufara Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000333/2022-2023 | 680/RD/PHE | 06/03/2023 | 630 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 51.19 | 0 | 100
1878 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under BALUFARA ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000500/2023-2024 | 620/RD/PHE | 05/03/2024 | 225 | M/S MAA BOLLA CONSTRUCTION | 5.56 | 0 | 100
1879 | Raiganj Division | Raiganj Sub-Division | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000575/2022-2023 | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 100
1880 | Raiganj Division | Raiganj Sub-Division | Trial Run For Balufara Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000731/2024-2025 | 530/RD/PHE | 12/02/2025 | 90 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 0.82 | 0 | 0
1881 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000038/2023-2024 | 1313/RD/PHE | 12/05/2023 | 0 | Resource Division | 3.19 | 0 | 0
1882 | Raiganj Division | Islampur Sub-Division | Hiring of vehicle for transportation of water sample collection from different BPHC to district lab uttar dinajpur | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | BILL/01085/2023-2024 | BP-2023-24-274 | 09/02/2024 | 0 | FARHAD ALI | 0.05 | 0 | 0
1883 | Raiganj Division | Islampur Sub-Division | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bhelagachhi PWSS at Islampur Block under Raiganj Division, PHE dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000161/2024-2025 | 2893/RD/PHE | 25/09/2024 | 20 | GOPES SAHA | 6.18 | 0 | 0
1884 | Raiganj Division | Islampur Sub-Division | Implementation of BHELAGACHHI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000329/2022-2023 | 670/RD/PHE | 06/03/2023 | 970 | M/S LOKENATH CONSTRUCTION | 581.2 | 0 | 65
1885 | Raiganj Division | Islampur Sub-Division | Laying of Additional pipeline with other ancillary works at different mouzas of BHELAGACHHI PWSS under Islampur Sub-Division P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000373/2024-2025 | 3492/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 79.83 | 0 | 0
1886 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHELAGACHHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000564/2023-2024 | 542/RD/PHE | 05/03/2024 | 333 | M/S UNIQUE 13 | 11.28 | 0 | 100
1887 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHELAGACHHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000565/2023-2024 | 543/RD/PHE | 05/03/2024 | 360 | KULICK ENTERPRISE | 11.28 | 0 | 100
1888 | Raiganj Division | Islampur Sub-Division | Trial Run For Bhelagachi PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000716/2024-2025 | 548/RD/PHE | 12/02/2025 | 90 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0
1889 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000110/2022-2023 | 606/RD/PHE | 27/02/2023 | 0 | Resource Division | 42.2 | 0 | 0
1890 | Raiganj Division | Islampur Sub-Division | Implementation of DAKSHIN DAMODARGACHH and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division. (Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections & Pump House.) | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000048/2023-2024 | 1555/RD/PHE | 29/05/2023 | 909 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 81.37 | 0 | 50
1891 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHIN DAOMODARGACHH PWSS at Chopra Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000050/2024-2025 | 1709/RD/PHE | 10/06/2024 | 270 | FIZA CONSTRUCTION | 10.19 | 0 | 100
1892 | Raiganj Division | Islampur Sub-Division | Additional pipeline, Pathway, Land Development and other ancillary works at Dakshin Damodargachh Piped Water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | ORD/000397/2025-2026 | 1596/RD/PHE | 16/06/2025 | 120 | SANDIP SARKAR | 12.06 | 0 | 0
1893 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000091/2023-2024 | 2271/RD | 03/08/2023 | 0 | Resource Division | 6.79 | 0 | 0
1894 | Raiganj Division | Raiganj Sub-Division | Demand for placing necessary fund for the work of Permanent restoration of damaged hard shoulder/flank caused due pipe laying by PHE Department under Krishnapur PWSS at a stretches of Thakurbari-Bindol road under Uttar Dinajpur Highway Division, PWD (Roads) Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | BILL/00119/2024-2025 | BP-2024-25-83 | 18/06/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 10.34 | 0 | 0
1895 | Raiganj Division | Raiganj Sub-Division | Implementation of KRISHNAPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000084/2023-2024 | 1996/RD/PHE | 13/07/2023 | 629 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 135.44 | 0 | 55
1896 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Krishnapur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000447/2024-2025 | 3759/RD/PHED | 18/12/2024 | 135 | ANILA CONSTRUCTION | 11.51 | 0 | 0
1897 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KRISNAPUR PWSS at Raiganj Block under Raiganj Division,PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000503/2023-2024 | 626/RD/PHE | 05/03/2024 | 45 | M/S UNIQUE 13 | 10.26 | 0 | 0
1898 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000085/2023-2024 | 2265/RD/PHE | 03/08/2023 | 0 | Resource Division | 11.63 | 0 | 0
1899 | Raiganj Division | Raiganj Sub-Division | Implementation of DALIMGAON and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000026/2023-2024 | 1305/RD/PHE | 12/05/2023 | 810 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 130.31 | 0 | 50
1900 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
1901 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dalimgaon PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000461/2024-2025 | 3779/RD/PHE | 19/12/2024 | 45 | JEET CONSTRUCTION (UKILPARA) | 15.07 | 0 | 0
1902 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DALIMGAON PWSS at Kaliaganj Block under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000504/2023-2024 | 627/RD/PHE | 05/03/2024 | 45 | BIKRAM KUNDU | 10.26 | 0 | 100
1903 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1904 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-07 | RTOR000084/2023-2024 | 2264/RD/PHE | 03/08/2023 | 0 | Resource Division | 11.05 | 0 | 0
1905 | Raiganj Division | Raiganj Sub-Division | Implementation of BHARATPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-02 | ORD/000049/2023-2024 | 1556/RD/PHE | 29/05/2023 | 900 | BHOLA PAUL | 92.43 | 0 | 50
1906 | Raiganj Division | Raiganj Sub-Division | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-02 | ORD/000410/2024-2025 | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0
1907 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer-02 | RTOR000079/2023-2024 | 2256/RD/PHE | 03/08/2023 | 0 | Resource Division | 5.9 | 0 | 0
1908 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer ISD | Junior Engineer, ISD ,Junior Engineer-02 | RTOR000088/2023-2024 | 2269/RD | 03/08/2023 | 0 | Resource Division | 30.86 | 0 | 0
1909 | Raiganj Division |  | GROUND BORED BIG DIA TUBE WELL FOR KUNOR WSS |  |  | ORD/000304/2019-2020 | 157/RD | 04/02/2020 | 2192 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.64 | 0 | 100
1910 | Raiganj Division |  | GROUND BORED BIG DIA TUBE WELL FOR KALIAGANJ MUNICIPAL ZONE-I WSS |  |  | ORD/000307/2019-2020 | 156/RD | 04/02/2020 | 2192 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.01 | 0 | 100
1911 | Raiganj Division |  | Replacement of 250 x150mm dia. Tube-Well 250mtr. deep Rig bored Tube-Well for Pokheria PWSS at Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. |  |  | ORD/000443/2023-2024 | 199/RD/PHE | 25/01/2024 | 20 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 12.89 | 0 | 100
1912 | Raiganj Division |  | SINKING GROUND BORED REPLACEMENT OF ISLAMPUR ZONE-II PWSS |  |  | ORD/000471/2019-2020 | 155/RD | 04/02/2020 | 90 | SAMIRAN PODDAR | 13.96 | 0 | 100
1913 | Raiganj Division |  | Sinking of Ground Bored Replacement Tube-Well 250mm x 150mm dia. of 180 mtr. Direct Rotary Rig Method at Ghirnigaon Khas TW Site under Raiganj Division, P.H.E Dte.(SM/18227) |  |  | ORD/000519/2024-2025 | 71/RD/PHE | 06/01/2025 | 30 | M/S SARKAR ENTERPRISE SILIGURI | 10.69 | 0 | 0
1914 | Raiganj Division |  | Replacement for Replacement Tube-Well & Inter Connection in connection With Head Work Site of Phulatti PWSS under Raiganj Division, P.H.E Dte. |  |  | ORD/000520/2024-2025 | 72/RD/PHE | 06/01/2025 | 30 | M/S SARKAR ENTERPRISE SILIGURI | 11.35 | 0 | 0
1915 | Raiganj Division |  | Implementation of BHIKHANPUR and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. |  |  | ORD/000358/2023-2024 | 2474/RD/PHE | 24/08/2023 | 860 | M/S PINKI CONSTRUCTION | 647.91 | 0 | 65
1916 | Raiganj Division |  | Additional pipeline and other ancillary works at Bhikhanpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. |  |  | ORD/000368/2024-2025 | 3487/RD/PHE | 02/12/2024 | 45 | RAKSHIT TRADERS | 29.04 | 0 | 0
1917 | Raiganj Division |  | Restoration of damage pipeline during road widening at Bikhanpur piped water Supply Scheme at Karandighi Block Under Islampur SubDivision under Raiganj Division,P.H.E Dte. |  |  | ORD/000405/2025-2026 | 1609/RD/PHE | 17/06/2025 | 120 | M/S PINKI CONSTRUCTION | 13.22 | 0 | 0
1918 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000127/2022-2023 | 642/RD/PHE | 02/03/2023 | 0 | Resource Division | 78.14 | 0 | 0
1919 | Raiganj Division |  | Material Requisition To Resource Division |  |  | RTOR000143/2022-2023 | 829/RD/PHE | 22/03/2023 | 0 | Resource Division | 79.15 | 0 | 0
1920 | Raiganj Division | Islampur Sub-Division | Implementation of ILUABARI (Zone-I & Zone-II) and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000214/2023-2024 | 2301/RD/PHE | 04/08/2023 | 881 | M/S. B. PAUL & COMPANY | 1194.94 | 0 | 60
1921 | Raiganj Division | Islampur Sub-Division | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Iluabari Zone-I & Zone-II Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 120 M3/hr. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000328/2025-2026 | 2013/RD/PHE | 08/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 59.18 | 0 | 0
1922 | Raiganj Division | Islampur Sub-Division | Laying additional pipe line,Road Restoration and Approach Road in connection with New Scheme Of Iluabari Zone-I and Zone-II Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000415/2024-2025 | 3579/RD/PHE | 05/12/2024 | 405 | M/S. B. PAUL & COMPANY | 97.01 | 0 | 20
1923 | Raiganj Division | Islampur Sub-Division | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under ILUABARI PWSS (ZONE-I) & ILUABARI PWSS (ZONE-II) at Islampur Block under Raiganj Division, PHE Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000512/2023-2024 | 637/RD/PHE | 05/03/2024 | 434 | M/S. B. PAUL & COMPANY | 47.94 | 0 | 85
1924 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000111/2022-2023 | 604/RD/PHE | 27/02/2023 | 0 | Resource Division | 35.46 | 0 | 0
1925 | Raiganj Division |  | Restoration of Pipe Line For Providing FHTC for Bindol Water Supply Scheme Under Raiganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase-II) |  |  | ORD/000422/2023-2024 | 2873/RD/PHE | 17/10/2023 | 45 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 8.45 | 0 | 100
1926 | Raiganj Division | Raiganj Sub-Division | Implementation of SINTAIR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000212/2022-2023 | 72/RD/PHE | 16/01/2023 | 1081 | SANYAL ENTERPRISE ABHIJITSANYAL2010@GMAIL.COM | 405.17 | 0 | 55
1927 | Raiganj Division | Raiganj Sub-Division | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sintair PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000477/2024-2025 | 10/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 58.34 | 0 | 0
1928 | Raiganj Division | Raiganj Sub-Division | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SINTAIR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000479/2023-2024 | 587/RD/PHE | 05/03/2024 | 45 | M/S KALYAN | 22.57 | 0 | 0
1929 | Raiganj Division | Raiganj Sub-Division | Trial Run For Sintair PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000678/2024-2025 | 524/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0
1930 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000091/2022-2023 | 27/RD/PHE | 06/01/2023 | 0 | Resource Division | 31.09 | 0 | 0
1931 | Raiganj Division | Raiganj Sub-Division | Augmentation work of HEMTABAD ZONE-II Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000101/2022-2023 | 1548/RD/PHE | 26/08/2022 | 90 | UTTAM SAHA | 425.89 | 0 | 52
1932 | Raiganj Division | Raiganj Sub-Division | FHTC (Functional Household Tap Connection) for Hemtabad Zone-II Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000161/2022-2023 | 2021/RD/PHE | 17/11/2022 | 90 | BHOLA PAUL | 64.54 | 0 | 0
1933 | Raiganj Division | Raiganj Sub-Division | Construction of Pump house for (5.4 x 3.6) at Head work site and(3.6x3.0) at 2nd Tubewell Site of Hemtabad Zone-II Water Supply Schemes Augmentation under Hemtabad Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000263/2022-2023 | 389/RD/PHE | 07/02/2023 | 45 | M/S SANJIB BHATTACHARJEE SANJIB.RNJ@GMAIL.COM | 11.8 | 0 | 100
1934 | Raiganj Division | Raiganj Sub-Division | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000372/2022-2023 | 729/RD/PHE | 15/03/2023 | 365 | SOVAN KUMAR ROY | 143.15 | 0 | 0
1935 | Raiganj Division | Raiganj Sub-Division | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | ORD/000543/2023-2024 | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 100
1936 | Raiganj Division | Raiganj Sub-Division | Material Requisition To Resource Division | Assistant Engineer - I,Assistant Engineer RSD | Junior Engineer, RSD ,Junior Engineer-07 | RTOR000040/2022-2023 | 1953/RD/PHE | 04/11/2022 | 0 | Resource Division | 143.46 | 0 | 0
1937 | Raiganj Division | Islampur Sub-Division | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. | Assistant Engineer ISD | Junior Engineer, ISD | BILL/00024/2024-2025 | BP-2024-25-18 | 15/04/2024 | 0 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0
1938 | Raiganj Division | Islampur Sub-Division | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dharampur -I Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000278/2021-2022 | 1814/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.9 | 0 | 0
1939 | Raiganj Division | Islampur Sub-Division | Allied works in connection with retrofitting of FHTC in Dharampur Zone-I PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000380/2023-2024 | 2606/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.98 | 0 | 100
1940 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000385/2021-2022 | 2080/RD/PHE | 02/11/2021 | 30 | RAHUL ENTERPRISE | 6.95 | 0 | 100
1941 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000389/2021-2022 | 2084/RD/PHE | 02/11/2021 | 30 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 10.59 | 0 | 1
1942 | Raiganj Division | Islampur Sub-Division | Retrofitting of Functional Household Tap Connections(FHTC) under Dharampur Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000739/2021-2022 | 435/RD/PHE | 16/02/2022 | 30 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 9.16 | 0 | 0
1943 | Raiganj Division | Islampur Sub-Division | Material Requisition To Resource Division | Assistant Engineer ISD | Junior Engineer, ISD | RTOR000015/2021-2022 | 39/RD/PHE | 06/01/2022 | 0 | Resource Division | 0.76 | 0 | 0
1944 | Raiganj Division | Islampur Sub-Division | Laying of Additional Pipe Line for Retrofitting of Bhagabati Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | Assistant Engineer ISD | Junior Engineer, ISD | ORD/000372/2021-2022 | 2153/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 2.76 | 0 | 1
1945 | Raiganj Division | Raiganj Sub-Division | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/00024/2024-2025 | BP-2024-25-18 | 15/04/2024 | 0 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0
1946 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.09.2023 to 14.09.2023 | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01163/2023-2024 | BP-2023-24-316 | 04/03/2024 | 0 | ARNAB DUTTA | 0.07 | 0 | 0
1947 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.09.2023 to 07.09.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01164/2023-2024 | BP-2023-24-315 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0
1948 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 18.09.2023 to 27.09.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01165/2023-2024 | BP-2023-24-317 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0
1949 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 29.09.2023 to 01.10.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01166/2023-2024 | BP-2023-24-318 | 04/03/2024 | 0 | ARNAB DUTTA | 0.04 | 0 | 0
1950 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 02.05.2023 to 08.05.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01167/2023-2024 | BP-2023-24-302 | 04/03/2024 | 0 | ARNAB DUTTA | 0.09 | 0 | 0
1951 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.05.2023 to 18.05.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01168/2023-2024 | BP-2023-24-303 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0
1952 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.06.2033 to 09.06.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01169/2023-2024 | BP-2023-24-305 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0
1953 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 12.06.2023 to 19.06.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01170/2023-2024 | BP-2023-24-306 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0
1954 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 21.06.2023 to 28.06.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01171/2023-2024 | BP-2023-24-307 | 04/03/2024 | 0 | ARNAB DUTTA | 0.12 | 0 | 0
1955 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.08.2023 to 07.08.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01172/2023-2024 | BP-2023-24-311 | 04/03/2024 | 0 | ARNAB DUTTA | 0.11 | 0 | 0
1956 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 16.08.2023 to 23.08.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01173/2023-2024 | BP-2023-24-313 | 04/03/2024 | 0 | ARNAB DUTTA | 0.12 | 0 | 0
1957 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 09.08.2023 to 14.08.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01174/2023-2024 | BP-2023-24-312 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0
1958 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 22.05.2023 to 30.05.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01175/2023-2024 | BP-2023-24-304 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0
1959 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 25.08.2023 to 29.08.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01176/2023-2024 | BP-2023-24-314 | 04/03/2024 | 0 | ARNAB DUTTA | 0.07 | 0 | 0
1960 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 19.07.2023 to 26.07.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01177/2023-2024 | BP-2023-24-310 | 04/03/2024 | 0 | ARNAB DUTTA | 0.13 | 0 | 0
1961 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.07.2023 to 16.07.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01178/2023-2024 | BP-2023-24-309 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0
1962 | Raiganj Division | Raiganj Sub-Division | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 03.07.2023 to 07.07.2023. | Assistant Engineer RSD | Junior Engineer, RSD | BILL/01179/2023-2024 | BP-2023-24-308 | 04/03/2024 | 0 | ARNAB DUTTA | 0.09 | 0 | 0
1963 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 29.04.2024,30.04.2024, 02.05.2024 and 03.05.2024. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000017/2024-2025 | 1353/RD/PHE | 25/04/2024 | 4 | M/S DILWAR HOSAIN | 0.07 | 0 | 100
1964 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 22.04.2024 to 26.04.2024 | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000018/2024-2025 | 1274/RD/PHE | 19/04/2024 | 5 | M/S DILWAR HOSAIN | 0.08 | 0 | 100
1965 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 15.04.2024 to 19.04.2024. | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000019/2024-2025 | 1238/RD/PHE | 12/04/2024 | 5 | M/S DILWAR HOSAIN | 0.07 | 0 | 100
1966 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 08.04.2024,09.04.2024, and 12.04.2024 | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000020/2024-2025 | 1203/RD/PHE | 06/04/2024 | 3 | M/S DILWAR HOSAIN | 0.07 | 0 | 100
1967 | Raiganj Division | Raiganj Sub-Division | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 01.04.2024 to 05.04.2024 . | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000021/2024-2025 | 1160/RD/PHE | 03/04/2024 | 5 | M/S DILWAR HOSAIN | 0.08 | 0 | 100
1968 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of Joyhat Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000358/2021-2022 | 2139/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 4.85 | 0 | 0
1969 | Raiganj Division | Raiganj Sub-Division | Laying of Additional Pipe Line for Retrofitting of JOYHAT Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part A) | Assistant Engineer RSD | Junior Engineer, RSD | ORD/000424/2021-2022 | 2186/RD/PHE | 17/11/2021 | 30 | M/S.BANGARAJ | 7.76 | 0 | 0
Total | [10 empty] | 576513.81 | 240.51